## Executive Summary
Executive Summary
Metric | Value
Projects total | 28
Projects included | 8
Projects partial | 8
Projects no tightening/link | 12
Erected towers | 5102
Tightened towers | 2235
Erected not tightened towers | 2870
Usable stringing spans | 933
Ready to string spans | 66
Ready to string km | 63.589

## Project Summary
Project Summary
project_code | project_display | project_scope_keys | erection_rows | unique_towers | erected_towers | tightened_towers | erected_not_tightened_towers | usable_stringing_spans | all_erected_spans | all_tightened_spans | already_strung_spans | ready_to_string_spans | ready_to_string_km | data_bucket | coverage_reason
TA 325 | TA 325 | ta325 | 487 | 487 | 487 | 0 | 487 | 231 | 229 | 0 | 224 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TA 413 | TA 413 | ta413 | 336 | 336 | 334 | 334 | 0 | 31 | 17 | 17 | 27 | 2 | 0.65977 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 414 | TA 414 | ta414 | 352 | 352 | 229 | 229 | 0 | 172 | 61 | 61 | 12 | 49 | 40.8603 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 416 | TA 416 | ta416 | 302 | 302 | 302 | 302 | 0 | 72 | 68 | 68 | 68 | 3 | 1.1821 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 418 | TA 418 | ta418 | 127 | 127 | 127 | 121 | 6 | 40 | 12 | 8 | 20 | 5 | 3.823 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 419 | TA 419 | ta419 | 330 | 330 | 206 | 60 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | PARTIAL | Erection tower tightening is available, but no usable stringing spans were found.
TA 421 | TA 421 | ta421 | 309 | 309 | 309 | 300 | 9 | 61 | 59 | 52 | 50 | 3 | 2.591 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 504 | TA 504 | ta504 | 121 | 121 | 121 | 82 | 39 | 53 | 17 | 11 | 10 | 2 | 6.3094 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 505 | TA 505 | ta505 | 358 | 358 | 354 | 177 | 177 | 13 | 12 | 12 | 10 | 2 | 8.164 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 506 | TA 506 | ta506 | 402 | 402 | 402 | 192 | 210 | 36 | 35 | 35 | 35 | 0 | 0 | INCLUDED | Erection tower tightening and usable stringing spans are available.
TA 509 | TA 509 | ta509 | 206 | 206 | 199 | 0 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 512 | TA 512 | ta512 | 223 | 223 | 219 | 0 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 513 | TA 513 - Ere S-P | ta513eresp | 24 | 24 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 513 | TA 513 - Ere S-F | ta513eresf | 7 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 515 | TA 515 | ta515 | 12 | 12 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 601 | TA 601 | ta601 | 70 | 70 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 602 | TA 602 | ta602 | 44 | 44 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 401 | TB 401 | tb401 | 516 | 516 | 514 | 0 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 401 | TB 401 - PKG-G |  | 0 | 0 | 0 | 0 | 0 | 74 | 73 | 0 | 66 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 408 | TB 408 | tb408 | 485 | 485 | 485 | 438 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | PARTIAL | Erection tower tightening is available, but no usable stringing spans were found.
TB 501 | TB 501 - 132kV | tb501132kv | 41 | 41 | 31 | 0 | 31 | 47 | 30 | 0 | 31 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 501 | TB 501 - 220kV | tb501220kv | 203 | 203 | 200 | 0 | 200 | 81 | 78 | 0 | 75 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 507 | TB 507 | tb507 | 3 | 3 | 3 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 507 | TB 507 - MAIN | tb507main | 222 | 222 | 213 | 0 | 213 | 21 | 18 | 0 | 19 | 0 | 0 | PARTIAL | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 605 | TB 605 - SK | tb605sk | 4 | 4 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 605 | TB 605 - Jammu | tb605jammu | 83 | 83 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 605 | TB 605 - Punjab | tb605punjab | 118 | 118 | 113 | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 608 | TB 608 - WIP-ERC | tb608wiperc | 28 | 28 | 22 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | NO_TIGHTENING_OR_LINK | No erection-sheet tower tightening values and no usable stringing span link were found.

## Span Buckets
Span Buckets
Project | Total Spans | Already Strung spans | Stringing Ready | Tightening not started | Tightening partial | Erection Gap
TA 325 | 231 | 224 | 0 | 229 | 0 | 2
TA 413 | 31 | 27 | 2 | 0 | 0 | 14
TA 414 | 172 | 12 | 49 | 0 | 0 | 111
TA 416 | 72 | 68 | 3 | 0 | 0 | 4
TA 418 | 40 | 20 | 5 | 0 | 4 | 28
TA 421 | 61 | 50 | 3 | 2 | 5 | 2
TA 504 | 53 | 10 | 2 | 3 | 3 | 36
TA 505 | 13 | 10 | 2 | 0 | 0 | 1
TA 506 | 36 | 35 | 0 | 0 | 0 | 1
TB 401 - PKG-G | 74 | 66 | 0 | 73 | 0 | 1
TB 501 - 132kV | 47 | 31 | 0 | 30 | 0 | 17
TB 501 - 220kV | 81 | 75 | 0 | 78 | 0 | 3
TB 507 | 1 | 0 | 0 | 0 | 0 | 1
TB 507 - MAIN | 21 | 19 | 0 | 18 | 0 | 3

## Span Readiness
Span Readiness
project_code | project_display | project_scope_key | line_name | source_file | source_sheet | source_row_number | from_ap | to_ap | stretch_identifier | length_km | required_location_count | erected_location_count | tightened_location_count | missing_erection_count | missing_tightening_count | required_locations | erected_locations | tightened_locations | missing_erection_locations | missing_tightening_locations | location_parse_status | location_parse_issue | already_strung | all_erected | all_tightened | ready_to_string | readiness_reason
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 1 | 112/0 | 113/0 | JMB | 0.37584 | 2 | 2 | 0 | 0 | 2 | 112/0, 113/0 | 112/0, 113/0 |  |  | 112/0, 113/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 2 | 111/0 | 112/0 | JMB | 0.3419 | 2 | 2 | 0 | 0 | 2 | 111/0, 112/0 | 111/0, 112/0 |  |  | 111/0, 112/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 3 | 110/0 | 111/0 | JMB | 0.31214 | 2 | 2 | 0 | 0 | 2 | 110/0, 111/0 | 110/0, 111/0 |  |  | 110/0, 111/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 4 | 113/0 | 114/0 | JMB | 0.29705 | 2 | 2 | 0 | 0 | 2 | 113/0, 114/0 | 113/0, 114/0 |  |  | 113/0, 114/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 5 | 109/0 | 110/0 | JMB | 0.34242 | 2 | 2 | 0 | 0 | 2 | 109/0, 110/0 | 109/0, 110/0 |  |  | 109/0, 110/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 6 | 116/0 | 116A/0 | JMB | 0.24341 | 2 | 2 | 0 | 0 | 2 | 116/0, 116A/0 | 116/0, 116A/0 |  |  | 116/0, 116A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 7 | 108/0 | 109/0 | JMB | 0.2772 | 2 | 2 | 0 | 0 | 2 | 108/0, 109/0 | 108/0, 109/0 |  |  | 108/0, 109/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 8 | 107/0 | 108/0 | JMB | 0.55888 | 2 | 2 | 0 | 0 | 2 | 107/0, 108/0 | 107/0, 108/0 |  |  | 107/0, 108/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 9 | 133/0 | 133A/0 | JMB | 2.2677 | 2 | 2 | 0 | 0 | 2 | 133/0, 133A/0 | 133/0, 133A/0 |  |  | 133/0, 133A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 10 | 121/0 | 122/0 | JMB | 0.52549 | 2 | 2 | 0 | 0 | 2 | 121/0, 122/0 | 121/0, 122/0 |  |  | 121/0, 122/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 11 | 129A/0 | 130/0 | JMB | 1.1821 | 2 | 2 | 0 | 0 | 2 | 129A/0, 130/0 | 129A/0, 130/0 |  |  | 129A/0, 130/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 12 | 106B/0 | 107/0 | JMB | 1.1482 | 2 | 2 | 0 | 0 | 2 | 106B/0, 107/0 | 106B/0, 107/0 |  |  | 106B/0, 107/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 13 | 122/0 | 123/0 | JMB | 0.32832 | 2 | 2 | 0 | 0 | 2 | 122/0, 123/0 | 122/0, 123/0 |  |  | 122/0, 123/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 14 | 118/0 | 119/0 | JMB | 0.29443 | 2 | 2 | 0 | 0 | 2 | 118/0, 119/0 | 118/0, 119/0 |  |  | 118/0, 119/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 15 | 117/0 | 118/0 | JMB | 0.28524 | 2 | 2 | 0 | 0 | 2 | 117/0, 118/0 | 117/0, 118/0 |  |  | 117/0, 118/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 16 | 119/0 | 120/0 | JMB | 1.3729 | 2 | 2 | 0 | 0 | 2 | 119/0, 120/0 | 119/0, 120/0 |  |  | 119/0, 120/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 17 | 116B/0 | 117/0 | JMB | 0.437 | 2 | 2 | 0 | 0 | 2 | 116B/0, 117/0 | 116B/0, 117/0 |  |  | 116B/0, 117/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 18 | 144/0 | 144A/0 | JMB | 2.3911 | 2 | 2 | 0 | 0 | 2 | 144/0, 144A/0 | 144/0, 144A/0 |  |  | 144/0, 144A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 19 | 120/0 | 121/0 | JMB | 0.26471 | 2 | 2 | 0 | 0 | 2 | 120/0, 121/0 | 120/0, 121/0 |  |  | 120/0, 121/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 20 | 114/0 | 115/0 | JMB | 0.374 | 2 | 2 | 0 | 0 | 2 | 114/0, 115/0 | 114/0, 115/0 |  |  | 114/0, 115/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 21 | 115/0 | 116/0 | JMB | 0.226 | 2 | 2 | 0 | 0 | 2 | 115/0, 116/0 | 115/0, 116/0 |  |  | 115/0, 116/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 22 | 133A/0 | 134/0 | JMB | 2.0375 | 2 | 2 | 0 | 0 | 2 | 133A/0, 134/0 | 133A/0, 134/0 |  |  | 133A/0, 134/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 23 | 123/0 | 124/0 | JMB | 0.843 | 2 | 2 | 0 | 0 | 2 | 123/0, 124/0 | 123/0, 124/0 |  |  | 123/0, 124/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 24 | 116A/0 | 116B/0 | JMB | 0.675 | 2 | 2 | 0 | 0 | 2 | 116A/0, 116B/0 | 116A/0, 116B/0 |  |  | 116A/0, 116B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 25 | 144A/0 | 145/0 | JMB | 0.39758 | 2 | 2 | 0 | 0 | 2 | 144A/0, 145/0 | 144A/0, 145/0 |  |  | 144A/0, 145/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 26 | 147/1 | 147/2 | JMB | 0.33 | 2 | 2 | 0 | 0 | 2 | 147/1, 147/2 | 147/1, 147/2 |  |  | 147/1, 147/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 27 | 127/0 | 128/0 | JMB | 2.3994 | 2 | 2 | 0 | 0 | 2 | 127/0, 128/0 | 127/0, 128/0 |  |  | 127/0, 128/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 28 | 126/0 | 127/0 | JMB | 0.80843 | 2 | 2 | 0 | 0 | 2 | 126/0, 127/0 | 126/0, 127/0 |  |  | 126/0, 127/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 29 | 132/0 | 133/0 | JMB | 1.2801 | 2 | 2 | 0 | 0 | 2 | 132/0, 133/0 | 132/0, 133/0 |  |  | 132/0, 133/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 30 | 259/0 | 260/0 | BAR | 0.256 | 2 | 2 | 0 | 0 | 2 | 259/0, 260/0 | 259/0, 260/0 |  |  | 259/0, 260/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 31 | 260/0 | 261/0 | BAR | 0.338 | 2 | 2 | 0 | 0 | 2 | 260/0, 261/0 | 260/0, 261/0 |  |  | 260/0, 261/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 32 | 125A/0 | 126/0 | JMB | 0.38008 | 2 | 2 | 0 | 0 | 2 | 125A/0, 126/0 | 125A/0, 126/0 |  |  | 125A/0, 126/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 33 | 106A/0 | 106B/0 | JMB | 2.0164 | 2 | 2 | 0 | 0 | 2 | 106A/0, 106B/0 | 106A/0, 106B/0 |  |  | 106A/0, 106B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 34 | 125/0 | 125A/0 | JMB | 0.40132 | 2 | 2 | 0 | 0 | 2 | 125/0, 125A/0 | 125/0, 125A/0 |  |  | 125/0, 125A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 35 | 128/0 | 129/0 | JMB | 0.25325 | 2 | 2 | 0 | 0 | 2 | 128/0, 129/0 | 128/0, 129/0 |  |  | 128/0, 129/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 36 | 129/0 | 129A/0 | JMB | 0.30553 | 2 | 2 | 0 | 0 | 2 | 129/0, 129A/0 | 129/0, 129A/0 |  |  | 129/0, 129A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 37 | 135A/0 | 135A/1 | JMB | 0.33983 | 2 | 2 | 0 | 0 | 2 | 135A/0, 135A/1 | 135A/0, 135A/1 |  |  | 135A/0, 135A/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 38 | 135A/2 | 135B/0 | JMB | 2.2344 | 2 | 2 | 0 | 0 | 2 | 135A/2, 135B/0 | 135A/2, 135B/0 |  |  | 135A/2, 135B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 39 | 135B/0 | 136/0 | JMB | 2.986 | 2 | 2 | 0 | 0 | 2 | 135B/0, 136/0 | 135B/0, 136/0 |  |  | 135B/0, 136/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 40 | 106/0 | 106A/0 | JMB | 0.41125 | 2 | 2 | 0 | 0 | 2 | 106/0, 106A/0 | 106/0, 106A/0 |  |  | 106/0, 106A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 41 | 164/0 | 165/0 | BAR | 2.9808 | 2 | 2 | 0 | 0 | 2 | 164/0, 165/0 | 164/0, 165/0 |  |  | 164/0, 165/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 42 | 135A/1 | 135A/2 | JMB | 0.45185 | 2 | 2 | 0 | 0 | 2 | 135A/1, 135A/2 | 135A/1, 135A/2 |  |  | 135A/1, 135A/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 43 | 124/0 | 124A/0 | JMB | 0.39528 | 2 | 2 | 0 | 0 | 2 | 124/0, 124A/0 | 124/0, 124A/0 |  |  | 124/0, 124A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 44 | 124A/0 | 124A/1 | JMB | 0.253 | 2 | 2 | 0 | 0 | 2 | 124A/0, 124A/1 | 124A/0, 124A/1 |  |  | 124A/0, 124A/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 45 | 124A/1 | 125/0 | JMB | 0.20313 | 2 | 2 | 0 | 0 | 2 | 124A/1, 125/0 | 124A/1, 125/0 |  |  | 124A/1, 125/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 46 | 257/0 | 259/0 | BAR | 1.809 | 2 | 2 | 0 | 0 | 2 | 257/0, 259/0 | 257/0, 259/0 |  |  | 257/0, 259/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 47 | 137A/0 | 138/0 | JMB | 2.7299 | 2 | 2 | 0 | 0 | 2 | 137A/0, 138/0 | 137A/0, 138/0 |  |  | 137A/0, 138/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 48 | 138/0 | 139/0 | JMB | 1.239 | 2 | 2 | 0 | 0 | 2 | 138/0, 139/0 | 138/0, 139/0 |  |  | 138/0, 139/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 49 | 261/0 | 262/0 | BAR | 0.242 | 2 | 2 | 0 | 0 | 2 | 261/0, 262/0 | 261/0, 262/0 |  |  | 261/0, 262/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 50 | 139/0 | 139A/0 | JMB | 1.211 | 2 | 2 | 0 | 0 | 2 | 139/0, 139A/0 | 139/0, 139A/0 |  |  | 139/0, 139A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 51 | 130/0 | 131/0 | JMB | 2.0411 | 2 | 2 | 0 | 0 | 2 | 130/0, 131/0 | 130/0, 131/0 |  |  | 130/0, 131/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 52 | 131/0 | 132/0 | JMB | 0.23646 | 2 | 2 | 0 | 0 | 2 | 131/0, 132/0 | 131/0, 132/0 |  |  | 131/0, 132/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 53 | 139A/0 | 140/0 | JMB | 0.42714 | 2 | 2 | 0 | 0 | 2 | 139A/0, 140/0 | 139A/0, 140/0 |  |  | 139A/0, 140/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 54 | 262/0 | 263/0 | BAR | 0.686 | 2 | 2 | 0 | 0 | 2 | 262/0, 263/0 | 262/0, 263/0 |  |  | 262/0, 263/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 55 | 263/0 | 264/0 | BAR | 0.243 | 2 | 2 | 0 | 0 | 2 | 263/0, 264/0 | 263/0, 264/0 |  |  | 263/0, 264/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 56 | 142/0 | 143/0 | JMB | 0.22338 | 2 | 2 | 0 | 0 | 2 | 142/0, 143/0 | 142/0, 143/0 |  |  | 142/0, 143/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 57 | 143/0 | 143A/0 | JMB | 0.39322 | 2 | 2 | 0 | 0 | 2 | 143/0, 143A/0 | 143/0, 143A/0 |  |  | 143/0, 143A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 58 | 255/0 | 257/0 | BAR | 1.839 | 2 | 2 | 0 | 0 | 2 | 255/0, 257/0 | 255/0, 257/0 |  |  | 255/0, 257/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 59 | 265/0 | 266/0 | BAR | 0.223 | 2 | 2 | 0 | 0 | 2 | 265/0, 266/0 | 265/0, 266/0 |  |  | 265/0, 266/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 60 | 134/0 | 135/0 | JMB | 0.23587 | 2 | 2 | 0 | 0 | 2 | 134/0, 135/0 | 134/0, 135/0 |  |  | 134/0, 135/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 61 | 163/0 | 163/5 | BAR | 1.894 | 2 | 2 | 0 | 0 | 2 | 163/0, 163/5 | 163/0, 163/5 |  |  | 163/0, 163/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 62 | 163/5 | 163/6 | BAR | 0.339 | 2 | 2 | 0 | 0 | 2 | 163/5, 163/6 | 163/5, 163/6 |  |  | 163/5, 163/6 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 63 | 163/6 | 164/0 | BAR | 0.343 | 2 | 2 | 0 | 0 | 2 | 163/6, 164/0 | 163/6, 164/0 |  |  | 163/6, 164/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 64 | 264/0 | 265/0 | BAR | 0.441 | 2 | 2 | 0 | 0 | 2 | 264/0, 265/0 | 264/0, 265/0 |  |  | 264/0, 265/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 65 | 143A/0 | 143A/2 | JMB | 0.8412 | 2 | 2 | 0 | 0 | 2 | 143A/0, 143A/2 | 143A/0, 143A/2 |  |  | 143A/0, 143A/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 66 | 143A/2 | 143A/3 | JMB | 0.41309 | 2 | 2 | 0 | 0 | 2 | 143A/2, 143A/3 | 143A/2, 143A/3 |  |  | 143A/2, 143A/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 67 | 143A/3 | 144/0 | JMB | 1.2461 | 2 | 2 | 0 | 0 | 2 | 143A/3, 144/0 | 143A/3, 144/0 |  |  | 143A/3, 144/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 68 | 266/0 | 266/1 | BAR | 0.34 | 2 | 2 | 0 | 0 | 2 | 266/0, 266/1 | 266/0, 266/1 |  |  | 266/0, 266/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 69 | 266/1 | 267/0 | BAR | 0.835 | 2 | 2 | 0 | 0 | 2 | 266/1, 267/0 | 266/1, 267/0 |  |  | 266/1, 267/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 70 | 136/0 | 137/0 | JMB | 0.42558 | 2 | 2 | 0 | 0 | 2 | 136/0, 137/0 | 136/0, 137/0 |  |  | 136/0, 137/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 71 | 137/0 | 137A/0 | JMB | 2.8271 | 2 | 2 | 0 | 0 | 2 | 137/0, 137A/0 | 137/0, 137A/0 |  |  | 137/0, 137A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 72 | 145A/0 | 146/0 | JMB | 1.6209 | 2 | 2 | 0 | 0 | 2 | 145A/0, 146/0 | 145A/0, 146/0 |  |  | 145A/0, 146/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 73 | 253/0 | 254/0 | BAR | 0.246 | 2 | 2 | 0 | 0 | 2 | 253/0, 254/0 | 253/0, 254/0 |  |  | 253/0, 254/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 74 | 254/0 | 255/0 | BAR | 0.3 | 2 | 2 | 0 | 0 | 2 | 254/0, 255/0 | 254/0, 255/0 |  |  | 254/0, 255/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 75 | 267/0 | 267A/0 | BAR | 0.511 | 2 | 2 | 0 | 0 | 2 | 267/0, 267A/0 | 267/0, 267A/0 |  |  | 267/0, 267A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 76 | 267A/0 | 268/0 | BAR | 1.44 | 2 | 2 | 0 | 0 | 2 | 267A/0, 268/0 | 267A/0, 268/0 |  |  | 267A/0, 268/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 77 | 141/0 | 141/1 | JMB | 0.39 | 2 | 2 | 0 | 0 | 2 | 141/0, 141/1 | 141/0, 141/1 |  |  | 141/0, 141/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 78 | 141/1 | 141/2 | JMB | 0.37 | 2 | 2 | 0 | 0 | 2 | 141/1, 141/2 | 141/1, 141/2 |  |  | 141/1, 141/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 79 | 141/2 | 142/0 | JMB | 0.80506 | 2 | 2 | 0 | 0 | 2 | 141/2, 142/0 | 141/2, 142/0 |  |  | 141/2, 142/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 80 | 146/0 | 147/0 | JMB | 0.47502 | 2 | 2 | 0 | 0 | 2 | 146/0, 147/0 | 146/0, 147/0 |  |  | 146/0, 147/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 81 | 147/0 | 147/1 | JMB | 0.42552 | 2 | 2 | 0 | 0 | 2 | 147/0, 147/1 | 147/0, 147/1 |  |  | 147/0, 147/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 82 | 147B/0 | 148/0 | JMB | 0.82756 | 2 | 2 | 0 | 0 | 2 | 147B/0, 148/0 | 147B/0, 148/0 |  |  | 147B/0, 148/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 83 | 152/0 | 152A/0 | JMB | 1.7799 | 2 | 2 | 0 | 0 | 2 | 152/0, 152A/0 | 152/0, 152A/0 |  |  | 152/0, 152A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 84 | 270/0 | 270A/0 | BAR | 2.821 | 2 | 2 | 0 | 0 | 2 | 270/0, 270A/0 | 270/0, 270A/0 |  |  | 270/0, 270A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 85 | 145/0 | 145A/0 | JMB | 0.398 | 2 | 2 | 0 | 0 | 2 | 145/0, 145A/0 | 145/0, 145A/0 |  |  | 145/0, 145A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 86 | 268/0 | 269/0 | BAR | 0.292 | 2 | 2 | 0 | 0 | 2 | 268/0, 269/0 | 268/0, 269/0 |  |  | 268/0, 269/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 87 | 269/0 | 270/0 | BAR | 1.237 | 2 | 2 | 0 | 0 | 2 | 269/0, 270/0 | 269/0, 270/0 |  |  | 269/0, 270/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 88 | 270A/0 | 271/0 | BAR | 0.268 | 2 | 2 | 0 | 0 | 2 | 270A/0, 271/0 | 270A/0, 271/0 |  |  | 270A/0, 271/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 89 | 271/0 | 272/0 | BAR | 2.108 | 2 | 2 | 0 | 0 | 2 | 271/0, 272/0 | 271/0, 272/0 |  |  | 271/0, 272/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 90 | 148/0 | 149/0 | JMB | 2.9937 | 2 | 2 | 0 | 0 | 2 | 148/0, 149/0 | 148/0, 149/0 |  |  | 148/0, 149/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 91 | 149/0 | 150/0 | JMB | 0.80876 | 2 | 2 | 0 | 0 | 2 | 149/0, 150/0 | 149/0, 150/0 |  |  | 149/0, 150/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 92 | 162/0 | 163/0 | BAR | 0.40168 | 2 | 2 | 0 | 0 | 2 | 162/0, 163/0 | 162/0, 163/0 |  |  | 162/0, 163/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 93 | 147A/0 | 147B/0 | JMB | 0.263 | 2 | 2 | 0 | 0 | 2 | 147A/0, 147B/0 | 147A/0, 147B/0 |  |  | 147A/0, 147B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 94 | 135/0 | 135A/0 | JMB | 2.9976 | 2 | 2 | 0 | 0 | 2 | 135/0, 135A/0 | 135/0, 135A/0 |  |  | 135/0, 135A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 95 | 251/0 | 252/0 | BAR | 0.222 | 2 | 2 | 0 | 0 | 2 | 251/0, 252/0 | 251/0, 252/0 |  |  | 251/0, 252/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 96 | 161/0 | 162/0 | JMB | 0.27905 | 2 | 2 | 0 | 0 | 2 | 161/0, 162/0 | 161/0, 162/0 |  |  | 161/0, 162/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 97 | 252/0 | 253/0 | BAR | 0.317 | 2 | 2 | 0 | 0 | 2 | 252/0, 253/0 | 252/0, 253/0 |  |  | 252/0, 253/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 98 | 250/0 | 251/0 | BAR | 0.737 | 2 | 2 | 0 | 0 | 2 | 250/0, 251/0 | 250/0, 251/0 |  |  | 250/0, 251/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 99 | 249/0 | 250/0 | BAR | 1.368 | 2 | 2 | 0 | 0 | 2 | 249/0, 250/0 | 249/0, 250/0 |  |  | 249/0, 250/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 100 | 150A/0 | 151/0 | JMB | 1.2524 | 2 | 2 | 0 | 0 | 2 | 150A/0, 151/0 | 150A/0, 151/0 |  |  | 150A/0, 151/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 101 | 151/0 | 152/0 | JMB | 0.40335 | 2 | 2 | 0 | 0 | 2 | 151/0, 152/0 | 151/0, 152/0 |  |  | 151/0, 152/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 102 | 147/2 | 147A/0 | JMB | 2.0209 | 2 | 2 | 0 | 0 | 2 | 147/2, 147A/0 | 147/2, 147A/0 |  |  | 147/2, 147A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 103 | 140/0 | 141/0 | JMB | 0.249 | 2 | 2 | 0 | 0 | 2 | 140/0, 141/0 | 140/0, 141/0 |  |  | 140/0, 141/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 104 | 150/0 | 150/1 | JMB | 0.367 | 2 | 2 | 0 | 0 | 2 | 150/0, 150/1 | 150/0, 150/1 |  |  | 150/0, 150/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 105 | 150/1 | 150A/0 | JMB | 1.266 | 2 | 2 | 0 | 0 | 2 | 150/1, 150A/0 | 150/1, 150A/0 |  |  | 150/1, 150A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 106 | 156/0 | 157/0 | BAR | 0.24053 | 2 | 2 | 0 | 0 | 2 | 156/0, 157/0 | 156/0, 157/0 |  |  | 156/0, 157/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 107 | 272/0 | 272/5 | BAR | 2.053 | 2 | 2 | 0 | 0 | 2 | 272/0, 272/5 | 272/0, 272/5 |  |  | 272/0, 272/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 108 | 155/0 | 156/0 | BAR | 2.7331 | 2 | 2 | 0 | 0 | 2 | 155/0, 156/0 | 155/0, 156/0 |  |  | 155/0, 156/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 109 | 152A/0 | 153/0 | JMB | 0.37034 | 2 | 2 | 0 | 0 | 2 | 152A/0, 153/0 | 152A/0, 153/0 |  |  | 152A/0, 153/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 110 | 158B/0 | 159/0 | BAR | 1.2538 | 2 | 2 | 0 | 0 | 2 | 158B/0, 159/0 | 158B/0, 159/0 |  |  | 158B/0, 159/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 111 | 158A/0 | 158B/0 | BAR | 0.48157 | 2 | 2 | 0 | 0 | 2 | 158A/0, 158B/0 | 158A/0, 158B/0 |  |  | 158A/0, 158B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 112 | 276/0 | Gty | BAR | 0.16 | 2 | 1 | 0 | 1 | 2 | 276/0, GTY | 276/0 |  | GTY | 276/0, GTY | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 113 | 158/0 | 158A/0 | BAR | 1.1306 | 2 | 2 | 0 | 0 | 2 | 158/0, 158A/0 | 158/0, 158A/0 |  |  | 158/0, 158A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 114 | 192/0 | 193/0 | BAR | 0.376 | 2 | 2 | 0 | 0 | 2 | 192/0, 193/0 | 192/0, 193/0 |  |  | 192/0, 193/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 115 | 193/0 | 194/0 | BAR | 0.241 | 2 | 2 | 0 | 0 | 2 | 193/0, 194/0 | 193/0, 194/0 |  |  | 193/0, 194/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 116 | 194/0 | 195/0 | BAR | 0.182 | 2 | 2 | 0 | 0 | 2 | 194/0, 195/0 | 194/0, 195/0 |  |  | 194/0, 195/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 117 | 191/0 | 191/2 | BAR | 0.82 | 2 | 2 | 0 | 0 | 2 | 191/0, 191/2 | 191/0, 191/2 |  |  | 191/0, 191/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 118 | 191/2 | 191/3 | 191/2 - 191/3 | 0.303 | 2 | 2 | 0 | 0 | 2 | 191/2, 191/3 | 191/2, 191/3 |  |  | 191/2, 191/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 119 | 191/3 | 191A/0 | 191/3 - 191A/0 | 0.35356 | 2 | 2 | 0 | 0 | 2 | 191/3, 191A/0 | 191/3, 191A/0 |  |  | 191/3, 191A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 120 | 191A/0 | 192/0 | BAR | 0.612 | 2 | 2 | 0 | 0 | 2 | 191A/0, 192/0 | 191A/0, 192/0 |  |  | 191A/0, 192/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 121 | 204/0 | 205/0 | BAR | 0.198 | 2 | 2 | 0 | 0 | 2 | 204/0, 205/0 | 204/0, 205/0 |  |  | 204/0, 205/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 122 | 195/0 | 195A/0 | BAR | 2.481 | 2 | 2 | 0 | 0 | 2 | 195/0, 195A/0 | 195/0, 195A/0 |  |  | 195/0, 195A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 123 | 196/0 | 197/0 | BAR | 0.246 | 2 | 2 | 0 | 0 | 2 | 196/0, 197/0 | 196/0, 197/0 |  |  | 196/0, 197/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 124 | 275/0 | 276/0 | 275/0 - 276/0 | 0.177 | 2 | 2 | 0 | 0 | 2 | 275/0, 276/0 | 275/0, 276/0 |  |  | 275/0, 276/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 125 | 195A/0 | 196/0 | BAR | 1.542 | 2 | 2 | 0 | 0 | 2 | 195A/0, 196/0 | 195A/0, 196/0 |  |  | 195A/0, 196/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 126 | 157/0 | 158/0 | BAR | 1.5758 | 2 | 2 | 0 | 0 | 2 | 157/0, 158/0 | 157/0, 158/0 |  |  | 157/0, 158/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 127 | 190/0 | 191/0 | BAR | 0.329 | 2 | 2 | 0 | 0 | 2 | 190/0, 191/0 | 190/0, 191/0 |  |  | 190/0, 191/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 128 | 176/0 | 177/0 | BAR | 0.232 | 2 | 2 | 0 | 0 | 2 | 176/0, 177/0 | 176/0, 177/0 |  |  | 176/0, 177/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 129 | 177/0 | 178/0 | BAR | 0.405 | 2 | 2 | 0 | 0 | 2 | 177/0, 178/0 | 177/0, 178/0 |  |  | 177/0, 178/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 130 | 178/0 | 179/0 | BAR | 0.278 | 2 | 2 | 0 | 0 | 2 | 178/0, 179/0 | 178/0, 179/0 |  |  | 178/0, 179/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 131 | 189/0 | 190/0 | BAR | 0.829 | 2 | 2 | 0 | 0 | 2 | 189/0, 190/0 | 189/0, 190/0 |  |  | 189/0, 190/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 132 | 248/0 | 249/0 | BAR | 2.525 | 2 | 2 | 0 | 0 | 2 | 248/0, 249/0 | 248/0, 249/0 |  |  | 248/0, 249/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 133 | 197/0 | 198/0 | BAR | 1.74 | 2 | 2 | 0 | 0 | 2 | 197/0, 198/0 | 197/0, 198/0 |  |  | 197/0, 198/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 134 | 224/0 | 225/0 | BAR | 0.235 | 2 | 2 | 0 | 0 | 2 | 224/0, 225/0 | 224/0, 225/0 |  |  | 224/0, 225/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 135 | 241/0 | 242/0 | BAR | 0.246 | 2 | 2 | 0 | 0 | 2 | 241/0, 242/0 | 241/0, 242/0 |  |  | 241/0, 242/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 136 | 243/0 | 244/0 | BAR | 0.25 | 2 | 2 | 0 | 0 | 2 | 243/0, 244/0 | 243/0, 244/0 |  |  | 243/0, 244/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 137 | 168/0 | 169/0 | BAR | 1.044 | 2 | 2 | 0 | 0 | 2 | 168/0, 169/0 | 168/0, 169/0 |  |  | 168/0, 169/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 138 | 169/0 | 171/0 | 169/0 - 171/0 | 0.433 | 2 | 2 | 0 | 0 | 2 | 169/0, 171/0 | 169/0, 171/0 |  |  | 169/0, 171/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 139 | 181/0 | 182/0 | BAR | 1.778 | 2 | 2 | 0 | 0 | 2 | 181/0, 182/0 | 181/0, 182/0 |  |  | 181/0, 182/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 140 | 242/0 | 243/0 | BAR | 1.335 | 2 | 2 | 0 | 0 | 2 | 242/0, 243/0 | 242/0, 243/0 |  |  | 242/0, 243/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 141 | 179/0 | 180/0 | BAR | 0.264 | 2 | 2 | 0 | 0 | 2 | 179/0, 180/0 | 179/0, 180/0 |  |  | 179/0, 180/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 142 | 188/0 | 189/0 | BAR | 0.218 | 2 | 2 | 0 | 0 | 2 | 188/0, 189/0 | 188/0, 189/0 |  |  | 188/0, 189/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 143 | 198/0 | 199/0 | BAR | 1.149 | 2 | 2 | 0 | 0 | 2 | 198/0, 199/0 | 198/0, 199/0 |  |  | 198/0, 199/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 144 | 244/0 | 244/1 | BAR | 0.494 | 2 | 2 | 0 | 0 | 2 | 244/0, 244/1 | 244/0, 244/1 |  |  | 244/0, 244/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 145 | 246/0 | 247/0 | BAR | 0.24 | 2 | 2 | 0 | 0 | 2 | 246/0, 247/0 | 246/0, 247/0 |  |  | 246/0, 247/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 146 | 205/0 | 206/0 | BAR | 1.063 | 2 | 2 | 0 | 0 | 2 | 205/0, 206/0 | 205/0, 206/0 |  |  | 205/0, 206/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 147 | 230/0 | 231/0 | BAR | 0.227 | 2 | 2 | 0 | 0 | 2 | 230/0, 231/0 | 230/0, 231/0 |  |  | 230/0, 231/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 148 | 247/0 | 248/0 | BAR | 1.957 | 2 | 2 | 0 | 0 | 2 | 247/0, 248/0 | 247/0, 248/0 |  |  | 247/0, 248/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 149 | 244/1 | 245/0 | BAR | 0.427 | 2 | 2 | 0 | 0 | 2 | 244/1, 245/0 | 244/1, 245/0 |  |  | 244/1, 245/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 150 | 231/0 | 232/0 | BAR | 0.419 | 2 | 2 | 0 | 0 | 2 | 231/0, 232/0 | 231/0, 232/0 |  |  | 231/0, 232/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 151 | 233/0 | 234/0 | BAR | 0.305 | 2 | 2 | 0 | 0 | 2 | 233/0, 234/0 | 233/0, 234/0 |  |  | 233/0, 234/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 152 | 245/0 | 246/0 | BAR | 0.569 | 2 | 2 | 0 | 0 | 2 | 245/0, 246/0 | 245/0, 246/0 |  |  | 245/0, 246/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 153 | 232/0 | 233/0 | BAR | 0.195 | 2 | 2 | 0 | 0 | 2 | 232/0, 233/0 | 232/0, 233/0 |  |  | 232/0, 233/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 154 | 234/0 | 235/0 | BAR | 0.328 | 2 | 2 | 0 | 0 | 2 | 234/0, 235/0 | 234/0, 235/0 |  |  | 234/0, 235/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 155 | 180/0 | 181/0 | BAR | 0.263 | 2 | 2 | 0 | 0 | 2 | 180/0, 181/0 | 180/0, 181/0 |  |  | 180/0, 181/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 156 | 210/0 | 211/0 | BAR | 0.223 | 2 | 2 | 0 | 0 | 2 | 210/0, 211/0 | 210/0, 211/0 |  |  | 210/0, 211/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 157 | 222/1 | 223/0 | BAR | 0.183 | 2 | 2 | 0 | 0 | 2 | 222/1, 223/0 | 222/1, 223/0 |  |  | 222/1, 223/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 158 | 209/0 | 210/0 | BAR | 0.699 | 2 | 2 | 0 | 0 | 2 | 209/0, 210/0 | 209/0, 210/0 |  |  | 209/0, 210/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 159 | 235/0 | 236/0 | BAR | 0.305 | 2 | 2 | 0 | 0 | 2 | 235/0, 236/0 | 235/0, 236/0 |  |  | 235/0, 236/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 160 | 171/0 | 172/0 | BAR | 0.274 | 2 | 2 | 0 | 0 | 2 | 171/0, 172/0 | 171/0, 172/0 |  |  | 171/0, 172/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 161 | 226/0 | 227/0 | BAR | 0.417 | 2 | 2 | 0 | 0 | 2 | 226/0, 227/0 | 226/0, 227/0 |  |  | 226/0, 227/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 162 | 229/1 | 230/0 | BAR | 1.884 | 2 | 2 | 0 | 0 | 2 | 229/1, 230/0 | 229/1, 230/0 |  |  | 229/1, 230/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 163 | 184/0 | 184/1 | BAR | 0.468 | 2 | 2 | 0 | 0 | 2 | 184/0, 184/1 | 184/0, 184/1 |  |  | 184/0, 184/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 164 | 184/1 | 185/0 | BAR | 0.412 | 2 | 2 | 0 | 0 | 2 | 184/1, 185/0 | 184/1, 185/0 |  |  | 184/1, 185/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 165 | 225/0 | 226/0 | BAR | 0.678 | 2 | 2 | 0 | 0 | 2 | 225/0, 226/0 | 225/0, 226/0 |  |  | 225/0, 226/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 166 | 236/0 | 237/0 | BAR | 0.28 | 2 | 2 | 0 | 0 | 2 | 236/0, 237/0 | 236/0, 237/0 |  |  | 236/0, 237/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 167 | 237/0 | 239/0 | BAR | 2.519 | 2 | 2 | 0 | 0 | 2 | 237/0, 239/0 | 237/0, 239/0 |  |  | 237/0, 239/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 168 | 240/0 | 241/0 | BAR | 0.207 | 2 | 2 | 0 | 0 | 2 | 240/0, 241/0 | 240/0, 241/0 |  |  | 240/0, 241/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 169 | 239/0 | 240/0 | BAR | 0.248 | 2 | 2 | 0 | 0 | 2 | 239/0, 240/0 | 239/0, 240/0 |  |  | 239/0, 240/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 170 | 165/0 | 165/4 | BAR | 1.613 | 2 | 2 | 0 | 0 | 2 | 165/0, 165/4 | 165/0, 165/4 |  |  | 165/0, 165/4 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 171 | 187/0 | 188/0 | BAR | 1.51 | 2 | 2 | 0 | 0 | 2 | 187/0, 188/0 | 187/0, 188/0 |  |  | 187/0, 188/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 172 | 274/0 | 275/0 | BAR | 0.402 | 2 | 2 | 0 | 0 | 2 | 274/0, 275/0 | 274/0, 275/0 |  |  | 274/0, 275/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 173 | 182/0 | 182A/0 | BAR | 0.246 | 2 | 2 | 0 | 0 | 2 | 182/0, 182A/0 | 182/0, 182A/0 |  |  | 182/0, 182A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 174 | 219/0 | 220/0 | BAR | 0.242 | 2 | 2 | 0 | 0 | 2 | 219/0, 220/0 | 219/0, 220/0 |  |  | 219/0, 220/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 175 | 211/0 | 211A/0 | BAR | 1.158 | 2 | 2 | 0 | 0 | 2 | 211/0, 211A/0 | 211/0, 211A/0 |  |  | 211/0, 211A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 176 | 212/0 | 213/0 | BAR | 0.248 | 2 | 2 | 0 | 0 | 2 | 212/0, 213/0 | 212/0, 213/0 |  |  | 212/0, 213/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 177 | 229/0 | 229/1 | BAR | 0.549 | 2 | 2 | 0 | 0 | 2 | 229/0, 229/1 | 229/0, 229/1 |  |  | 229/0, 229/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 178 | 160/0 | 161/0 | BAR | 0.22982 | 2 | 2 | 0 | 0 | 2 | 160/0, 161/0 | 160/0, 161/0 |  |  | 160/0, 161/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 179 | 167/1 | 168/0 | BAR | 1.338 | 2 | 2 | 0 | 0 | 2 | 167/1, 168/0 | 167/1, 168/0 |  |  | 167/1, 168/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 180 | 223/0 | 224/0 | BAR | 1.398 | 2 | 2 | 0 | 0 | 2 | 223/0, 224/0 | 223/0, 224/0 |  |  | 223/0, 224/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 181 | 218/0 | 219/0 | BAR | 0.822 | 2 | 2 | 0 | 0 | 2 | 218/0, 219/0 | 218/0, 219/0 |  |  | 218/0, 219/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 182 | 182A/0 | 183/0 | BAR | 0.43 | 2 | 2 | 0 | 0 | 2 | 182A/0, 183/0 | 182A/0, 183/0 |  |  | 182A/0, 183/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 183 | 183/0 | 184/0 | BAR | 0.234 | 2 | 2 | 0 | 0 | 2 | 183/0, 184/0 | 183/0, 184/0 |  |  | 183/0, 184/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 184 | 213/0 | 214/0 | BAR | 0.771 | 2 | 2 | 0 | 0 | 2 | 213/0, 214/0 | 213/0, 214/0 |  |  | 213/0, 214/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 185 | 203/1 | 204/0 | BAR | 0.425 | 2 | 2 | 0 | 0 | 2 | 203/1, 204/0 | 203/1, 204/0 |  |  | 203/1, 204/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 186 | 220/0 | 221/0 | BAR | 0.735 | 2 | 2 | 0 | 0 | 2 | 220/0, 221/0 | 220/0, 221/0 |  |  | 220/0, 221/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 187 | 272/5 | 272A/0 | BAR | 1.202 | 2 | 2 | 0 | 0 | 2 | 272/5, 272A/0 | 272/5, 272A/0 |  |  | 272/5, 272A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 188 | 199/0 | 200/0 | BAR | 0.221 | 2 | 2 | 0 | 0 | 2 | 199/0, 200/0 | 199/0, 200/0 |  |  | 199/0, 200/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 189 | 200/0 | 201/0 | BAR | 0.204 | 2 | 2 | 0 | 0 | 2 | 200/0, 201/0 | 200/0, 201/0 |  |  | 200/0, 201/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 190 | 227/0 | 228/0 | BAR | 0.239 | 2 | 2 | 0 | 0 | 2 | 227/0, 228/0 | 227/0, 228/0 |  |  | 227/0, 228/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 191 | 228/0 | 229/0 | BAR | 0.196 | 2 | 2 | 0 | 0 | 2 | 228/0, 229/0 | 228/0, 229/0 |  |  | 228/0, 229/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 192 | 217A/0 | 218/0 | BAR | 1.174 | 2 | 2 | 0 | 0 | 2 | 217A/0, 218/0 | 217A/0, 218/0 |  |  | 217A/0, 218/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 193 | 105/0 | 106/0 | JMB | 0.25645 | 2 | 2 | 0 | 0 | 2 | 105/0, 106/0 | 105/0, 106/0 |  |  | 105/0, 106/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 194 | 165/4 | 165/5 | BAR | 0.538 | 2 | 2 | 0 | 0 | 2 | 165/4, 165/5 | 165/4, 165/5 |  |  | 165/4, 165/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 195 | 165/5 | 166/0 | BAR | 0.423 | 2 | 2 | 0 | 0 | 2 | 165/5, 166/0 | 165/5, 166/0 |  |  | 165/5, 166/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 196 | 201/0 | 201/1 | BAR | 0.532 | 2 | 2 | 0 | 0 | 2 | 201/0, 201/1 | 201/0, 201/1 |  |  | 201/0, 201/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 197 | 272A/0 | 273/0 | BAR | 2.944 | 2 | 2 | 0 | 0 | 2 | 272A/0, 273/0 | 272A/0, 273/0 |  |  | 272A/0, 273/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 198 | 273/0 | 274/0 | BAR | 1.153 | 2 | 2 | 0 | 0 | 2 | 273/0, 274/0 | 273/0, 274/0 |  |  | 273/0, 274/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 199 | 211A/0 | 212/0 | BAR | 1.024 | 2 | 2 | 0 | 0 | 2 | 211A/0, 212/0 | 211A/0, 212/0 |  |  | 211A/0, 212/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 200 | 175/0 | 175/1 | 175/0 - 175/1 | 0.33 | 2 | 2 | 0 | 0 | 2 | 175/0, 175/1 | 175/0, 175/1 |  |  | 175/0, 175/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 201 | 175/1 | 176/0 | BAR | 0.649 | 2 | 2 | 0 | 0 | 2 | 175/1, 176/0 | 175/1, 176/0 |  |  | 175/1, 176/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 202 | 167/0 | 167/1 | BAR | 0.342 | 2 | 2 | 0 | 0 | 2 | 167/0, 167/1 | 167/0, 167/1 |  |  | 167/0, 167/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 203 | 208/0 | 209/0 | BAR | 0.41 | 2 | 2 | 0 | 0 | 2 | 208/0, 209/0 | 208/0, 209/0 |  |  | 208/0, 209/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 204 | 214/0 | 215/0 | BAR | 0.713 | 2 | 2 | 0 | 0 | 2 | 214/0, 215/0 | 214/0, 215/0 |  |  | 214/0, 215/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 205 | 217/0 | 217A/0 | BAR | 0.347 | 2 | 2 | 0 | 0 | 2 | 217/0, 217A/0 | 217/0, 217A/0 |  |  | 217/0, 217A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 206 | 221/0 | 222/0 | BAR | 0.222 | 2 | 2 | 0 | 0 | 2 | 221/0, 222/0 | 221/0, 222/0 |  |  | 221/0, 222/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 207 | 222/0 | 222/1 | BAR | 0.388 | 2 | 2 | 0 | 0 | 2 | 222/0, 222/1 | 222/0, 222/1 |  |  | 222/0, 222/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 208 | 172/0 | 173/0 | BAR | 1.123 | 2 | 2 | 0 | 0 | 2 | 172/0, 173/0 | 172/0, 173/0 |  |  | 172/0, 173/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 209 | 201/1 | 202/0 | BAR | 0.367 | 2 | 2 | 0 | 0 | 2 | 201/1, 202/0 | 201/1, 202/0 |  |  | 201/1, 202/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 210 | 202/0 | 203/0 | BAR | 0.788 | 2 | 2 | 0 | 0 | 2 | 202/0, 203/0 | 202/0, 203/0 |  |  | 202/0, 203/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 211 | 203/0 | 203/1 | BAR | 0.46 | 2 | 2 | 0 | 0 | 2 | 203/0, 203/1 | 203/0, 203/1 |  |  | 203/0, 203/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 212 | 154/1 | 155/0 | BAR | 0.415 | 2 | 2 | 0 | 0 | 2 | 154/1, 155/0 | 154/1, 155/0 |  |  | 154/1, 155/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 213 | 159/0 | 159/2 | BAR | 0.72 | 2 | 2 | 0 | 0 | 2 | 159/0, 159/2 | 159/0, 159/2 |  |  | 159/0, 159/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 214 | 173/0 | 174/0 | BAR | 0.232 | 2 | 2 | 0 | 0 | 2 | 173/0, 174/0 | 173/0, 174/0 |  |  | 173/0, 174/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 215 | 174/0 | 174/1 | BAR | 0.381 | 2 | 2 | 0 | 0 | 2 | 174/0, 174/1 | 174/0, 174/1 |  |  | 174/0, 174/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 216 | 174/1 | 175/0 | BAR | 0.289 | 2 | 2 | 0 | 0 | 2 | 174/1, 175/0 | 174/1, 175/0 |  |  | 174/1, 175/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 217 | 159/2 | 160/0 | BAR | 1.1522 | 2 | 2 | 0 | 0 | 2 | 159/2, 160/0 | 159/2, 160/0 |  |  | 159/2, 160/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 218 | 206/0 | 208/0 | BAR | 0.412 | 2 | 2 | 0 | 0 | 2 | 206/0, 208/0 | 206/0, 208/0 |  |  | 206/0, 208/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 219 | 216/0 | 217/0 | BAR | 0.456 | 2 | 2 | 0 | 0 | 2 | 216/0, 217/0 | 216/0, 217/0 |  |  | 216/0, 217/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 220 | 185/0 | 186/0 | BAR | 0.82 | 2 | 2 | 0 | 0 | 2 | 185/0, 186/0 | 185/0, 186/0 |  |  | 185/0, 186/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 221 | 186/0 | 187/0 | BAR | 0.399 | 2 | 2 | 0 | 0 | 2 | 186/0, 187/0 | 186/0, 187/0 |  |  | 186/0, 187/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 222 | 215/0 | 215/1 | BAR | 0.221 | 2 | 2 | 0 | 0 | 2 | 215/0, 215/1 | 215/0, 215/1 |  |  | 215/0, 215/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 223 | 215/1 | 216/0 | BAR | 0.41077 | 2 | 2 | 0 | 0 | 2 | 215/1, 216/0 | 215/1, 216/0 |  |  | 215/1, 216/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 224 | 166/0 | 167/0 | BAR | 0.27 | 2 | 2 | 0 | 0 | 2 | 166/0, 167/0 | 166/0, 167/0 |  |  | 166/0, 167/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 225 | 101/0 | 102/0 | JMB | 0.665 | 2 | 2 | 0 | 0 | 2 | 101/0, 102/0 | 101/0, 102/0 |  |  | 101/0, 102/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 226 | 102/0 | 103/0 | JMB | 0.685 | 2 | 2 | 0 | 0 | 2 | 102/0, 103/0 | 102/0, 103/0 |  |  | 102/0, 103/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 227 | 103/0 | 104/0 | JMB | 0.68012 | 2 | 2 | 0 | 0 | 2 | 103/0, 104/0 | 103/0, 104/0 |  |  | 103/0, 104/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 228 | 104/0 | 105/0 | JMB | 0.38659 | 2 | 2 | 0 | 0 | 2 | 104/0, 105/0 | 104/0, 105/0 |  |  | 104/0, 105/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 229 | 153/0 | 154/0 | BAR | 0.62 | 2 | 2 | 0 | 0 | 2 | 153/0, 154/0 | 153/0, 154/0 |  |  | 153/0, 154/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 230 | 154/0 | 154/1 | BAR | 0.62 | 2 | 2 | 0 | 0 | 2 | 154/0, 154/1 | 154/0, 154/1 |  |  | 154/0, 154/1 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 325 | TA 325 | ta325 |  | TA 325 - DPR - 2026-01-19.xlsx | Stringing Compiled | 232 |  | Total | Total | 0.17734 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 235 | Section |  | Section |  | 1 | 0 | 0 | 1 | 1 | SECTION |  |  | SECTION | SECTION | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 236 | From | To | From - To |  | 2 | 0 | 0 | 2 | 2 | FROM, TO |  |  | FROM, TO | FROM, TO | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 237 | AP-34 | AP-35 | AP-34 - AP-35 | 4.8986 | 2 | 0 | 0 | 2 | 2 | 34, 35 |  |  | 34, 35 | 34, 35 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 238 | 37A/0 | AP-38/0 | 37A/0 - AP-38/0 | 2.5836 | 2 | 2 | 2 | 0 | 0 | 37A/0, 38/0 | 37A/0, 38/0 | 37A/0, 38/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 239 | AP-38 | AP-39 | AP-38 - AP-39 | 4.1637 | 2 | 0 | 0 | 2 | 2 | 38, 39 |  |  | 38, 39 | 38, 39 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 240 | AP-39 | AP-40 | AP-39 - AP-40 | 4.716 | 2 | 0 | 0 | 2 | 2 | 39, 40 |  |  | 39, 40 | 39, 40 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 241 | AP-7 | AP-7A | AP-7 - AP-7A | 2.6993 | 2 | 1 | 1 | 1 | 1 | 7, 7A | 7 | 7 | 7A | 7A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 242 | AP-7A | AP-8 | AP-7A - AP-8 | 2.4348 | 2 | 1 | 1 | 1 | 1 | 7A, 8 | 8 | 8 | 7A | 7A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 243 | AP-8 | AP-8A | AP-8 - AP-8A | 4.455 | 2 | 1 | 1 | 1 | 1 | 8, 8A | 8 | 8 | 8A | 8A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 244 | AP-8A | AP-9/0 | AP-8A - AP-9/0 | 0.46663 | 2 | 1 | 1 | 1 | 1 | 8A, 9/0 | 9/0 | 9/0 | 8A | 8A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 245 | AP-6 | AP-7 | AP-6 - AP-7 | 4.9012 | 2 | 2 | 2 | 0 | 0 | 6, 7 | 6, 7 | 6, 7 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 246 | AP-5A | AP-6 | AP-5A - AP-6 | 0.41948 | 2 | 1 | 1 | 1 | 1 | 5A, 6 | 6 | 6 | 5A | 5A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 247 | AP-5 | AP-5A | AP-5 - AP-5A | 4.4184 | 2 | 1 | 1 | 1 | 1 | 5, 5A | 5 | 5 | 5A | 5A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 248 | AP-4A | AP-5/0 | AP-4A - AP-5/0 | 2.6816 | 2 | 1 | 1 | 1 | 1 | 4A, 5/0 | 5/0 | 5/0 | 4A | 4A | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 249 | AP-4 | AP4A/0 | AP-4 - AP4A/0 | 0.70916 | 2 | 2 | 2 | 0 | 0 | 4, 4A/0 | 4, 4A/0 | 4, 4A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 250 | AP-33 | AP-34 | AP-33 - AP-34 | 4.0498 | 2 | 0 | 0 | 2 | 2 | 33, 34 |  |  | 33, 34 | 33, 34 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 251 | AP3B/0 | AP4/0 | AP3B/0 - AP4/0 | 1.627 | 2 | 2 | 2 | 0 | 0 | 3B/0, 4/0 | 3B/0, 4/0 | 3B/0, 4/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 252 | AP-32A | AP-33 | AP-32A - AP-33 | 0.84 | 2 | 0 | 0 | 2 | 2 | 32A, 33 |  |  | 32A, 33 | 32A, 33 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 253 | AP32/0 | AP32A/0 | AP32/0 - AP32A/0 | 3.284 | 2 | 2 | 2 | 0 | 0 | 32/0, 32A/0 | 32/0, 32A/0 | 32/0, 32A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 254 | 2A/0 | 3A/0 | 2A/0 - 3A/0 | 2.837 | 2 | 2 | 2 | 0 | 0 | 2A/0, 3A/0 | 2A/0, 3A/0 | 2A/0, 3A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 255 | 3A/0 | 3B/0 | 3A/0 - 3B/0 | 2.6915 | 2 | 2 | 2 | 0 | 0 | 3A/0, 3B/0 | 3A/0, 3B/0 | 3A/0, 3B/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 256 | 1/0 | 2A/0 | 1/0 - 2A/0 | 0.29 | 2 | 2 | 2 | 0 | 0 | 1/0, 2A/0 | 1/0, 2A/0 | 1/0, 2A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 257 | 31/0 | 32/0 | 31/0 - 32/0 | 4.333 | 2 | 2 | 2 | 0 | 0 | 31/0, 32/0 | 31/0, 32/0 | 31/0, 32/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 258 | 30/0 | 31/0 | 30/0 - 31/0 | 4.124 | 2 | 2 | 2 | 0 | 0 | 30/0, 31/0 | 30/0, 31/0 | 30/0, 31/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 259 | 9/0 | 10/0 | 9/0 - 10/0 | 4.9649 | 2 | 2 | 2 | 0 | 0 | 9/0, 10/0 | 9/0, 10/0 | 9/0, 10/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 260 | 29A/0 | 30/0 | 29A/0 - 30/0 | 2.669 | 2 | 2 | 2 | 0 | 0 | 29A/0, 30/0 | 29A/0, 30/0 | 29A/0, 30/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 261 | 10/0 | 11/0 | 10/0 - 11/0 | 1.0042 | 2 | 2 | 2 | 0 | 0 | 10/0, 11/0 | 10/0, 11/0 | 10/0, 11/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 262 | 29/0 | 29A/0 | 29/0 - 29A/0 | 2.3792 | 2 | 2 | 2 | 0 | 0 | 29/0, 29A/0 | 29/0, 29A/0 | 29/0, 29A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 263 | 27/0 | 28/0 | 27/0 - 28/0 | 2.5483 | 2 | 2 | 2 | 0 | 0 | 27/0, 28/0 | 27/0, 28/0 | 27/0, 28/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 264 | 13/0 | 13A/0 | 13/0 - 13A/0 | 0.41688 | 2 | 2 | 2 | 0 | 0 | 13/0, 13A/0 | 13/0, 13A/0 | 13/0, 13A/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 413 | TA 413 | ta413 |  | TA 413 - DPR - 2026-05-25.xlsx | Stringing | 265 | 11/0 | 12/0 | 11/0 - 12/0 | 0.24289 | 2 | 2 | 2 | 0 | 0 | 11/0, 12/0 | 11/0, 12/0 | 11/0, 12/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 271 | 117/0 | 118/0 | 117/0 - 118/0 | 1.1428 | 4 | 3 | 3 | 1 | 1 | 117/0, 118/0, 117/1, 117/2 | 118/0, 117/1, 117/2 | 118/0, 117/1, 117/2 | 117/0 | 117/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 272 | 118/0 | 119/0 | 118/0 - 119/0 | 0.24382 | 2 | 2 | 2 | 0 | 0 | 118/0, 119/0 | 118/0, 119/0 | 118/0, 119/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 273 | 119/0 | 120/0 | 119/0 - 120/0 | 1.4216 | 5 | 5 | 5 | 0 | 0 | 119/0, 120/0, 119/1, 119/2, 119/3 | 119/0, 120/0, 119/1, 119/2, 119/3 | 119/0, 120/0, 119/1, 119/2, 119/3 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 274 | 120/0 | 121/0 | 120/0 - 121/0 | 2.8617 | 9 | 9 | 9 | 0 | 0 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 275 | 121/0 | 121/1 | 121/0 - 121/1 | 0.27614 | 2 | 2 | 2 | 0 | 0 | 121/0, 121/1 | 121/0, 121/1 | 121/0, 121/1 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 276 | 121/1 | 121/7 | 121/1 - 121/7 | 2.284 | 7 | 7 | 7 | 0 | 0 | 121/1, 121/7, 121/2, 121/3, 121/4, 121/5, 121/6 | 121/1, 121/7, 121/2, 121/3, 121/4, 121/5, 121/6 | 121/1, 121/7, 121/2, 121/3, 121/4, 121/5, 121/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 277 | 121/7 | 124/0 | 121/7 - 124/0 | 1.9374 | 6 | 5 | 5 | 1 | 1 | 121/7, 124/0, 121/8, 121/9, 121/10, 121/11 | 121/7, 124/0, 121/9, 121/10, 121/11 | 121/7, 124/0, 121/9, 121/10, 121/11 | 121/8 | 121/8 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 278 | 124/0 | 125/0 | 124/0 - 125/0 | 1.4726 | 5 | 4 | 4 | 1 | 1 | 124/0, 125/0, 124/1, 124/2, 124/3 | 124/0, 125/0, 124/1, 124/3 | 124/0, 125/0, 124/1, 124/3 | 124/2 | 124/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 279 | 125/0 | 126/0 | 125/0 - 126/0 | 1.2889 | 4 | 4 | 4 | 0 | 0 | 125/0, 126/0, 125/1, 125/2 | 125/0, 126/0, 125/1, 125/2 | 125/0, 126/0, 125/1, 125/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 280 | 126/0 | 127/0 | 126/0 - 127/0 | 1.5842 | 5 | 5 | 5 | 0 | 0 | 126/0, 127/0, 126/1, 126/2, 126/3 | 126/0, 127/0, 126/1, 126/2, 126/3 | 126/0, 127/0, 126/1, 126/2, 126/3 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 281 | 127/0 | 127/2 | 127/0 - 127/2 | 0.70998 | 3 | 2 | 2 | 1 | 1 | 127/0, 127/2, 127/1 | 127/0, 127/1 | 127/0, 127/1 | 127/2 | 127/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 282 | 127/2 | 128/0 | 127/2 - 128/0 | 0.33913 | 2 | 1 | 1 | 1 | 1 | 127/2, 128/0 | 128/0 | 128/0 | 127/2 | 127/2 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 283 | 128/0 | 129/0 | 128/0 - 129/0 | 0.62 | 2 | 1 | 1 | 1 | 1 | 128/0, 129/0 | 128/0 | 128/0 | 129/0 | 129/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 284 | 129/0 | 130/0 | 129/0 - 130/0 | 0.62006 | 2 | 0 | 0 | 2 | 2 | 129/0, 130/0 |  |  | 129/0, 130/0 | 129/0, 130/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 285 | 130/0 | 131/0 | 130/0 - 131/0 | 0.53507 | 2 | 0 | 0 | 2 | 2 | 130/0, 131/0 |  |  | 130/0, 131/0 | 130/0, 131/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 286 | 131/0 | 132/0 | 131/0 - 132/0 | 2.2016 | 7 | 2 | 2 | 5 | 5 | 131/0, 132/0, 131/1, 131/2, 131/3, 131/4, 131/5 | 132/0, 131/2 | 132/0, 131/2 | 131/0, 131/1, 131/3, 131/4, 131/5 | 131/0, 131/1, 131/3, 131/4, 131/5 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 287 | 132/0 | 133/0 | 132/0 - 133/0 | 1.2175 | 5 | 4 | 4 | 1 | 1 | 132/0, 133/0, 132/1, 132/2, 132/3 | 132/0, 133/0, 132/1, 132/3 | 132/0, 133/0, 132/1, 132/3 | 132/2 | 132/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 288 | 133/0 | 133/2 | 133/0 - 133/2 | 0.767 | 3 | 2 | 2 | 1 | 1 | 133/0, 133/2, 133/1 | 133/0, 133/2 | 133/0, 133/2 | 133/1 | 133/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 289 | 133/2 | 133/3 | 133/2 - 133/3 | 0.25 | 2 | 2 | 2 | 0 | 0 | 133/2, 133/3 | 133/2, 133/3 | 133/2, 133/3 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 290 | 133/3 | 134/0 | 133/3 - 134/0 | 0.83385 | 3 | 3 | 3 | 0 | 0 | 133/3, 134/0, 133/4 | 133/3, 134/0, 133/4 | 133/3, 134/0, 133/4 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 291 | 134/0 | 135/0 | 134/0 - 135/0 | 0.36067 | 2 | 1 | 1 | 1 | 1 | 134/0, 135/0 | 134/0 | 134/0 | 135/0 | 135/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 292 | 135/0 | 136/0 | 135/0 - 136/0 | 0.24787 | 2 | 1 | 1 | 1 | 1 | 135/0, 136/0 | 136/0 | 136/0 | 135/0 | 135/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 293 | 136/0 | 136/1 | 136/0 - 136/1 | 0.46 | 2 | 2 | 2 | 0 | 0 | 136/0, 136/1 | 136/0, 136/1 | 136/0, 136/1 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 294 | 136/1 | 137/0 | 136/1 - 137/0 | 0.45596 | 2 | 2 | 2 | 0 | 0 | 136/1, 137/0 | 136/1, 137/0 | 136/1, 137/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 295 | 137/0 | 138/0 | 137/0 - 138/0 | 1.1161 | 4 | 4 | 4 | 0 | 0 | 137/0, 138/0, 137/1, 137/2 | 137/0, 138/0, 137/1, 137/2 | 137/0, 138/0, 137/1, 137/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 296 | 138/0 | 139/0 | 138/0 - 139/0 | 0.46054 | 2 | 2 | 2 | 0 | 0 | 138/0, 139/0 | 138/0, 139/0 | 138/0, 139/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 297 | 139/0 | 139/2 | 139/0 - 139/2 | 0.71609 | 3 | 3 | 3 | 0 | 0 | 139/0, 139/2, 139/1 | 139/0, 139/2, 139/1 | 139/0, 139/2, 139/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 298 | 139/2 | 139/3 | 139/2 - 139/3 | 0.34 | 2 | 1 | 1 | 1 | 1 | 139/2, 139/3 | 139/2 | 139/2 | 139/3 | 139/3 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 299 | 139/3 | 140/0 | 139/3 - 140/0 | 0.3601 | 2 | 1 | 1 | 1 | 1 | 139/3, 140/0 | 140/0 | 140/0 | 139/3 | 139/3 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 300 | 140/0 | 141/0 | 140/0 - 141/0 | 0.204 | 2 | 2 | 2 | 0 | 0 | 140/0, 141/0 | 140/0, 141/0 | 140/0, 141/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 301 | 141/0 | 142/0 | 141/0 - 142/0 | 2.6596 | 8 | 8 | 8 | 0 | 0 | 141/0, 142/0, 141/1, 141/2, 141/3, 141/4, 141/5, 141/6 | 141/0, 142/0, 141/1, 141/2, 141/3, 141/4, 141/5, 141/6 | 141/0, 142/0, 141/1, 141/2, 141/3, 141/4, 141/5, 141/6 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 302 | 142/0 | 143/0 | 142/0 - 143/0 | 0.1643 | 2 | 2 | 2 | 0 | 0 | 142/0, 143/0 | 142/0, 143/0 | 142/0, 143/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 303 | 143/0 | 144/0 | 143/0 - 144/0 | 0.27727 | 2 | 2 | 2 | 0 | 0 | 143/0, 144/0 | 143/0, 144/0 | 143/0, 144/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 304 | 144/0 | 145/0 | 144/0 - 145/0 | 0.45168 | 2 | 2 | 2 | 0 | 0 | 144/0, 145/0 | 144/0, 145/0 | 144/0, 145/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 305 | 145/0 | 145/7 | 145/0 - 145/7 | 2.776 | 8 | 7 | 7 | 1 | 1 | 145/0, 145/7, 145/1, 145/2, 145/3, 145/4, 145/5, 145/6 | 145/0, 145/7, 145/2, 145/3, 145/4, 145/5, 145/6 | 145/0, 145/7, 145/2, 145/3, 145/4, 145/5, 145/6 | 145/1 | 145/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 306 | 145/7 | 147/0 | 145/7 - 147/0 | 0.34427 | 2 | 2 | 2 | 0 | 0 | 145/7, 147/0 | 145/7, 147/0 | 145/7, 147/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 307 | 147/0 | 148/0 | 147/0 - 148/0 | 0.25165 | 2 | 2 | 2 | 0 | 0 | 147/0, 148/0 | 147/0, 148/0 | 147/0, 148/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 308 | 148/0 | 148/5 | 148/0 - 148/5 | 2.078 | 6 | 6 | 6 | 0 | 0 | 148/0, 148/5, 148/1, 148/2, 148/3, 148/4 | 148/0, 148/5, 148/1, 148/2, 148/3, 148/4 | 148/0, 148/5, 148/1, 148/2, 148/3, 148/4 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 309 | 148/5 | 149/0 | 148/5 - 149/0 | 0.50809 | 2 | 2 | 2 | 0 | 0 | 148/5, 149/0 | 148/5, 149/0 | 148/5, 149/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 310 | 149/0 | 150/0 | 149/0 - 150/0 | 0.258 | 2 | 1 | 1 | 1 | 1 | 149/0, 150/0 | 149/0 | 149/0 | 150/0 | 150/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 311 | 150/0 | 150/1 | 150/0 - 150/1 | 0.281 | 2 | 0 | 0 | 2 | 2 | 150/0, 150/1 |  |  | 150/0, 150/1 | 150/0, 150/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 312 | 150/1 | 151/0 | 150/1 - 151/0 | 0.36761 | 2 | 0 | 0 | 2 | 2 | 150/1, 151/0 |  |  | 150/1, 151/0 | 150/1, 151/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 313 | 151/0 | 151A/0 | 151/0 - 151A/0 | 0.26699 | 2 | 0 | 0 | 2 | 2 | 151/0, 151A/0 |  |  | 151/0, 151A/0 | 151/0, 151A/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 314 | 151A/0 | 152/0 | 151A/0 - 152/0 | 0.50005 | 2 | 0 | 0 | 2 | 2 | 151A/0, 152/0 |  |  | 151A/0, 152/0 | 151A/0, 152/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 315 | 152/0 | 153/0 | 152/0 - 153/0 | 0.295 | 2 | 0 | 0 | 2 | 2 | 152/0, 153/0 |  |  | 152/0, 153/0 | 152/0, 153/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 316 | 153/0 | 153A/0 | 153/0 - 153A/0 | 1.184 | 4 | 0 | 0 | 4 | 4 | 153/0, 153A/0, 153/1, 153/2 |  |  | 153/0, 153A/0, 153/1, 153/2 | 153/0, 153A/0, 153/1, 153/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 317 | 153A/0 | 154/0 | 153A/0 - 154/0 | 0.49015 | 2 | 0 | 0 | 2 | 2 | 153A/0, 154/0 |  |  | 153A/0, 154/0 | 153A/0, 154/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 318 | 154/0 | 155/0 | 154/0 - 155/0 | 0.29536 | 2 | 0 | 0 | 2 | 2 | 154/0, 155/0 |  |  | 154/0, 155/0 | 154/0, 155/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 319 | 155/0 | 156/0 | 155/0 - 156/0 | 0.25734 | 2 | 0 | 0 | 2 | 2 | 155/0, 156/0 |  |  | 155/0, 156/0 | 155/0, 156/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 320 | 156/0 | 156/1 | 156/0 - 156/1 | 0.34299 | 2 | 0 | 0 | 2 | 2 | 156/0, 156/1 |  |  | 156/0, 156/1 | 156/0, 156/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 321 | 156/1 | 157/0 | 156/1 - 157/0 | 0.33533 | 2 | 0 | 0 | 2 | 2 | 156/1, 157/0 |  |  | 156/1, 157/0 | 156/1, 157/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 322 | 157/0 | 158/0 | 157/0 - 158/0 | 0.23 | 2 | 0 | 0 | 2 | 2 | 157/0, 158/0 |  |  | 157/0, 158/0 | 157/0, 158/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 323 | 158/0 | 159/0 | 158/0 - 159/0 | 0.25362 | 2 | 0 | 0 | 2 | 2 | 158/0, 159/0 |  |  | 158/0, 159/0 | 158/0, 159/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 324 | 159/0 | 160/0 | 159/0 - 160/0 | 0.33334 | 2 | 1 | 1 | 1 | 1 | 159/0, 160/0 | 160/0 | 160/0 | 159/0 | 159/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 325 | 160/0 | 161/0 | 160/0 - 161/0 | 0.39223 | 2 | 2 | 2 | 0 | 0 | 160/0, 161/0 | 160/0, 161/0 | 160/0, 161/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 326 | 161/0 | 162/0 | 161/0 - 162/0 | 0.248 | 2 | 1 | 1 | 1 | 1 | 161/0, 162/0 | 161/0 | 161/0 | 162/0 | 162/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 327 | 162/0 | 163/0 | 162/0 - 163/0 | 0.3285 | 2 | 0 | 0 | 2 | 2 | 162/0, 163/0 |  |  | 162/0, 163/0 | 162/0, 163/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 328 | 163/0 | 163/1 | 163/0 - 163/1 | 0.38299 | 2 | 0 | 0 | 2 | 2 | 163/0, 163/1 |  |  | 163/0, 163/1 | 163/0, 163/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 329 | 163/1 | 164/0 | 163/1 - 164/0 | 0.40159 | 2 | 0 | 0 | 2 | 2 | 163/1, 164/0 |  |  | 163/1, 164/0 | 163/1, 164/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 330 | 164/0 | 165/0 | 164/0 - 165/0 | 0.28506 | 2 | 0 | 0 | 2 | 2 | 164/0, 165/0 |  |  | 164/0, 165/0 | 164/0, 165/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 331 | 165/0 | 165/6 | 165/0 - 165/6 | 2.298 | 7 | 1 | 1 | 6 | 6 | 165/0, 165/6, 165/1, 165/2, 165/3, 165/4, 165/5 | 165/5 | 165/5 | 165/0, 165/6, 165/1, 165/2, 165/3, 165/4 | 165/0, 165/6, 165/1, 165/2, 165/3, 165/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 332 | 165/6 | 166/0 | 165/6 - 166/0 | 0.7301 | 3 | 2 | 2 | 1 | 1 | 165/6, 166/0, 165/7 | 166/0, 165/7 | 166/0, 165/7 | 165/6 | 165/6 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 333 | 166/0 | 167/0 | 166/0 - 167/0 | 0.28 | 2 | 2 | 2 | 0 | 0 | 166/0, 167/0 | 166/0, 167/0 | 166/0, 167/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 334 | 167/0 | 168/0 | 167/0 - 168/0 | 0.57615 | 2 | 1 | 1 | 1 | 1 | 167/0, 168/0 | 167/0 | 167/0 | 168/0 | 168/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 335 | 168/0 | 169/0 | 168/0 - 169/0 | 0.2556 | 2 | 0 | 0 | 2 | 2 | 168/0, 169/0 |  |  | 168/0, 169/0 | 168/0, 169/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 336 | 169/0 | 170/0 | 169/0 - 170/0 | 0.52131 | 2 | 0 | 0 | 2 | 2 | 169/0, 170/0 |  |  | 169/0, 170/0 | 169/0, 170/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 337 | 170/0 | 171/0 | 170/0 - 171/0 | 0.26145 | 2 | 1 | 1 | 1 | 1 | 170/0, 171/0 | 171/0 | 171/0 | 170/0 | 170/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 338 | 171/0 | 172/0 | 171/0 - 172/0 | 0.18677 | 2 | 1 | 1 | 1 | 1 | 171/0, 172/0 | 171/0 | 171/0 | 172/0 | 172/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 339 | 172/0 | 173/0 | 172/0 - 173/0 | 0.68963 | 3 | 1 | 1 | 2 | 2 | 172/0, 173/0, 172/1 | 172/1 | 172/1 | 172/0, 173/0 | 172/0, 173/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 340 | 173/0 | 174/0 | 173/0 - 174/0 | 0.21523 | 2 | 1 | 1 | 1 | 1 | 173/0, 174/0 | 174/0 | 174/0 | 173/0 | 173/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 341 | 174/0 | 175/0 | 174/0 - 175/0 | 2.6334 | 8 | 8 | 8 | 0 | 0 | 174/0, 175/0, 174/1, 174/2, 174/3, 174/4, 174/5, 174/6 | 174/0, 175/0, 174/1, 174/2, 174/3, 174/4, 174/5, 174/6 | 174/0, 175/0, 174/1, 174/2, 174/3, 174/4, 174/5, 174/6 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 342 | 175/0 | 175/1 | 175/0 - 175/1 | 0.468 | 2 | 2 | 2 | 0 | 0 | 175/0, 175/1 | 175/0, 175/1 | 175/0, 175/1 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 343 | 175/1 | 176/0 | 175/1 - 176/0 | 0.44553 | 2 | 2 | 2 | 0 | 0 | 175/1, 176/0 | 175/1, 176/0 | 175/1, 176/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 344 | 176/0 | 177/0 | 176/0 - 177/0 | 1.0433 | 4 | 4 | 4 | 0 | 0 | 176/0, 177/0, 176/1, 176/2 | 176/0, 177/0, 176/1, 176/2 | 176/0, 177/0, 176/1, 176/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 345 | 177/0 | 178/0 | 177/0 - 178/0 | 0.22809 | 2 | 2 | 2 | 0 | 0 | 177/0, 178/0 | 177/0, 178/0 | 177/0, 178/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 346 | 178/0 | 179/0 | 178/0 - 179/0 | 1.3265 | 5 | 5 | 5 | 0 | 0 | 178/0, 179/0, 178/1, 178/2, 178/3 | 178/0, 179/0, 178/1, 178/2, 178/3 | 178/0, 179/0, 178/1, 178/2, 178/3 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 347 | 179/0 | 180/0 | 179/0 - 180/0 | 1.5825 | 5 | 4 | 4 | 1 | 1 | 179/0, 180/0, 179/1, 179/2, 179/3 | 179/0, 179/1, 179/2, 179/3 | 179/0, 179/1, 179/2, 179/3 | 180/0 | 180/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 348 | 180/0 | 180/2 | 180/0 - 180/2 | 0.822 | 3 | 2 | 2 | 1 | 1 | 180/0, 180/2, 180/1 | 180/2, 180/1 | 180/2, 180/1 | 180/0 | 180/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 349 | 180/2 | 182/0 | 180/2 - 182/0 | 2.4126 | 7 | 7 | 7 | 0 | 0 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 350 | 182/0 | 183/0 | 182/0 - 183/0 | 0.20891 | 2 | 2 | 2 | 0 | 0 | 182/0, 183/0 | 182/0, 183/0 | 182/0, 183/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 351 | 183/0 | 184/0 | 183/0 - 184/0 | 1.4794 | 5 | 5 | 5 | 0 | 0 | 183/0, 184/0, 183/1, 183/2, 183/3 | 183/0, 184/0, 183/1, 183/2, 183/3 | 183/0, 184/0, 183/1, 183/2, 183/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 352 | 184/0 | 185/0 | 184/0 - 185/0 | 0.21017 | 2 | 2 | 2 | 0 | 0 | 184/0, 185/0 | 184/0, 185/0 | 184/0, 185/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 353 | 185/0 | 186/0 | 185/0 - 186/0 | 0.271 | 2 | 2 | 2 | 0 | 0 | 185/0, 186/0 | 185/0, 186/0 | 185/0, 186/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 354 | 186/0 | 187/0 | 186/0 - 187/0 | 0.39065 | 2 | 2 | 2 | 0 | 0 | 186/0, 187/0 | 186/0, 187/0 | 186/0, 187/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 355 | 187/0 | 188/0 | 187/0 - 188/0 | 0.42821 | 2 | 1 | 1 | 1 | 1 | 187/0, 188/0 | 187/0 | 187/0 | 188/0 | 188/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 356 | 188/0 | 189/0 | 188/0 - 189/0 | 0.67259 | 2 | 0 | 0 | 2 | 2 | 188/0, 189/0 |  |  | 188/0, 189/0 | 188/0, 189/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 357 | 189/0 | 190/0 | 189/0 - 190/0 | 0.80798 | 3 | 2 | 2 | 1 | 1 | 189/0, 190/0, 189/1 | 190/0, 189/1 | 190/0, 189/1 | 189/0 | 189/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 358 | 190/0 | 191/0 | 190/0 - 191/0 | 0.22648 | 2 | 2 | 2 | 0 | 0 | 190/0, 191/0 | 190/0, 191/0 | 190/0, 191/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 359 | 191/0 | 191/1 | 191/0 - 191/1 | 0.46547 | 2 | 2 | 2 | 0 | 0 | 191/0, 191/1 | 191/0, 191/1 | 191/0, 191/1 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 360 | 191/1 | 192/0 | 191/1 - 192/0 | 0.38951 | 2 | 2 | 2 | 0 | 0 | 191/1, 192/0 | 191/1, 192/0 | 191/1, 192/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 361 | 192/0 | 193/0 | 192/0 - 193/0 | 0.22283 | 2 | 1 | 1 | 1 | 1 | 192/0, 193/0 | 192/0 | 192/0 | 193/0 | 193/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 362 | 193/0 | 194/0 | 193/0 - 194/0 | 0.27742 | 2 | 0 | 0 | 2 | 2 | 193/0, 194/0 |  |  | 193/0, 194/0 | 193/0, 194/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 363 | 194/0 | 194/1 | 194/0 - 194/1 | 0.47 | 2 | 1 | 1 | 1 | 1 | 194/0, 194/1 | 194/1 | 194/1 | 194/0 | 194/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 364 | 194/1 | 195/0 | 194/1 - 195/0 | 0.4797 | 2 | 1 | 1 | 1 | 1 | 194/1, 195/0 | 194/1 | 194/1 | 195/0 | 195/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 365 | 195/0 | 196/0 | 195/0 - 196/0 | 0.23969 | 2 | 1 | 1 | 1 | 1 | 195/0, 196/0 | 196/0 | 196/0 | 195/0 | 195/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 366 | 196/0 | 197/0 | 196/0 - 197/0 | 1.1484 | 4 | 4 | 4 | 0 | 0 | 196/0, 197/0, 196/1, 196/2 | 196/0, 197/0, 196/1, 196/2 | 196/0, 197/0, 196/1, 196/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 367 | 197/0 | 198/0 | 197/0 - 198/0 | 0.98372 | 4 | 4 | 4 | 0 | 0 | 197/0, 198/0, 197/1, 197/2 | 197/0, 198/0, 197/1, 197/2 | 197/0, 198/0, 197/1, 197/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 368 | 198/0 | 199/0 | 198/0 - 199/0 | 0.24674 | 2 | 2 | 2 | 0 | 0 | 198/0, 199/0 | 198/0, 199/0 | 198/0, 199/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 369 | 199/0 | 200/0 | 199/0 - 200/0 | 1.2663 | 4 | 3 | 3 | 1 | 1 | 199/0, 200/0, 199/1, 199/2 | 199/0, 199/1, 199/2 | 199/0, 199/1, 199/2 | 200/0 | 200/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 370 | 200/0 | 201/0 | 200/0 - 201/0 | 0.70998 | 3 | 0 | 0 | 3 | 3 | 200/0, 201/0, 200/1 |  |  | 200/0, 201/0, 200/1 | 200/0, 201/0, 200/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 371 | 201/0 | 202/0 | 201/0 - 202/0 | 0.51396 | 2 | 0 | 0 | 2 | 2 | 201/0, 202/0 |  |  | 201/0, 202/0 | 201/0, 202/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 372 | 202/0 | 203/0 | 202/0 - 203/0 | 0.23314 | 2 | 0 | 0 | 2 | 2 | 202/0, 203/0 |  |  | 202/0, 203/0 | 202/0, 203/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 373 | 203/0 | 203A/0 | 203/0 - 203A/0 | 0.12802 | 2 | 0 | 0 | 2 | 2 | 203/0, 203A/0 |  |  | 203/0, 203A/0 | 203/0, 203A/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 374 | 203A/0 | 203B/0 | 203A/0 - 203B/0 | 0.28282 | 2 | 0 | 0 | 2 | 2 | 203A/0, 203B/0 |  |  | 203A/0, 203B/0 | 203A/0, 203B/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 375 | 203B/0 | 204/0 | 203B/0 - 204/0 | 0.33995 | 2 | 0 | 0 | 2 | 2 | 203B/0, 204/0 |  |  | 203B/0, 204/0 | 203B/0, 204/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 376 | 204/0 | 205/0 | 204/0 - 205/0 | 0.17264 | 2 | 0 | 0 | 2 | 2 | 204/0, 205/0 |  |  | 204/0, 205/0 | 204/0, 205/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 377 | 205/0 | 205/1 | 205/0 - 205/1 | 0.55517 | 2 | 0 | 0 | 2 | 2 | 205/0, 205/1 |  |  | 205/0, 205/1 | 205/0, 205/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 378 | 205/1 | 206/0 | 205/1 - 206/0 | 0.81152 | 3 | 0 | 0 | 3 | 3 | 205/1, 206/0, 205/2 |  |  | 205/1, 206/0, 205/2 | 205/1, 206/0, 205/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 379 | 206/0 | 206/1 | 206/0 - 206/1 | 0.18481 | 2 | 0 | 0 | 2 | 2 | 206/0, 206/1 |  |  | 206/0, 206/1 | 206/0, 206/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 380 | 206/1 | 207/0 | 206/1 - 207/0 | 0.21427 | 2 | 1 | 1 | 1 | 1 | 206/1, 207/0 | 207/0 | 207/0 | 206/1 | 206/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 381 | 207/0 | 208/0 | 207/0 - 208/0 | 0.2723 | 2 | 1 | 1 | 1 | 1 | 207/0, 208/0 | 207/0 | 207/0 | 208/0 | 208/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 382 | 208/0 | 209/0 | 208/0 - 209/0 | 0.28464 | 2 | 1 | 1 | 1 | 1 | 208/0, 209/0 | 209/0 | 209/0 | 208/0 | 208/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 383 | 209/0 | 210/0 | 209/0 - 210/0 | 1.0363 | 4 | 3 | 3 | 1 | 1 | 209/0, 210/0, 209/1, 209/2 | 209/0, 209/1, 209/2 | 209/0, 209/1, 209/2 | 210/0 | 210/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 384 | 210/0 | 211/0 | 210/0 - 211/0 | 0.39766 | 2 | 0 | 0 | 2 | 2 | 210/0, 211/0 |  |  | 210/0, 211/0 | 210/0, 211/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 385 | 211/0 | 211/5 | 211/0 - 211/5 | 1.872 | 6 | 4 | 4 | 2 | 2 | 211/0, 211/5, 211/1, 211/2, 211/3, 211/4 | 211/5, 211/1, 211/2, 211/3 | 211/5, 211/1, 211/2, 211/3 | 211/0, 211/4 | 211/0, 211/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 386 | 211/5 | 212/0 | 211/5 - 212/0 | 0.26696 | 2 | 1 | 1 | 1 | 1 | 211/5, 212/0 | 211/5 | 211/5 | 212/0 | 212/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 387 | 212/0 | 213/0 | 212/0 - 213/0 | 0.37822 | 2 | 0 | 0 | 2 | 2 | 212/0, 213/0 |  |  | 212/0, 213/0 | 212/0, 213/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 388 | 213/0 | 214/0 | 213/0 - 214/0 | 0.32523 | 2 | 1 | 1 | 1 | 1 | 213/0, 214/0 | 214/0 | 214/0 | 213/0 | 213/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 389 | 214/0 | 215/0 | 214/0 - 215/0 | 2.9872 | 9 | 9 | 9 | 0 | 0 | 214/0, 215/0, 214/1, 214/2, 214/3, 214/4, 214/5, 214/6, 214/7 | 214/0, 215/0, 214/1, 214/2, 214/3, 214/4, 214/5, 214/6, 214/7 | 214/0, 215/0, 214/1, 214/2, 214/3, 214/4, 214/5, 214/6, 214/7 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 390 | 215/0 | 216/0 | 215/0 - 216/0 | 0.23141 | 2 | 2 | 2 | 0 | 0 | 215/0, 216/0 | 215/0, 216/0 | 215/0, 216/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 391 | 216/0 | 216/2 | 216/0 - 216/2 | 0.803 | 3 | 1 | 1 | 2 | 2 | 216/0, 216/2, 216/1 | 216/0 | 216/0 | 216/2, 216/1 | 216/2, 216/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 392 | 216/2 | 217/0 | 216/2 - 217/0 | 0.74912 | 3 | 0 | 0 | 3 | 3 | 216/2, 217/0, 216/3 |  |  | 216/2, 217/0, 216/3 | 216/2, 217/0, 216/3 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 393 | 217/0 | 218/0 | 217/0 - 218/0 | 2.2458 | 7 | 4 | 4 | 3 | 3 | 217/0, 218/0, 217/1, 217/2, 217/3, 217/4, 217/5 | 218/0, 217/2, 217/3, 217/4 | 218/0, 217/2, 217/3, 217/4 | 217/0, 217/1, 217/5 | 217/0, 217/1, 217/5 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 394 | 218/0 | 219/0 | 218/0 - 219/0 | 0.23947 | 2 | 1 | 1 | 1 | 1 | 218/0, 219/0 | 218/0 | 218/0 | 219/0 | 219/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 395 | 219/0 | 220/0 | 219/0 - 220/0 | 0.79841 | 3 | 1 | 1 | 2 | 2 | 219/0, 220/0, 219/1 | 220/0 | 220/0 | 219/0, 219/1 | 219/0, 219/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 396 | 220/0 | 221/0 | 220/0 - 221/0 | 0.81927 | 3 | 3 | 3 | 0 | 0 | 220/0, 221/0, 220/1 | 220/0, 221/0, 220/1 | 220/0, 221/0, 220/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 397 | 221/0 | 222/0 | 221/0 - 222/0 | 0.19181 | 2 | 2 | 2 | 0 | 0 | 221/0, 222/0 | 221/0, 222/0 | 221/0, 222/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 398 | 222/0 | 223/0 | 222/0 - 223/0 | 0.2486 | 2 | 2 | 2 | 0 | 0 | 222/0, 223/0 | 222/0, 223/0 | 222/0, 223/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 399 | 223/0 | 224/0 | 223/0 - 224/0 | 1.3862 | 5 | 3 | 3 | 2 | 2 | 223/0, 224/0, 223/1, 223/2, 223/3 | 223/0, 223/1, 223/3 | 223/0, 223/1, 223/3 | 224/0, 223/2 | 224/0, 223/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 400 | 224/0 | 224/2 | 224/0 - 224/2 | 0.714 | 3 | 2 | 2 | 1 | 1 | 224/0, 224/2, 224/1 | 224/2, 224/1 | 224/2, 224/1 | 224/0 | 224/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 401 | 224/2 | 225/0 | 224/2 - 225/0 | 0.4312 | 2 | 2 | 2 | 0 | 0 | 224/2, 225/0 | 224/2, 225/0 | 224/2, 225/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 402 | 225/0 | 226/0 | 225/0 - 226/0 | 2.9654 | 9 | 2 | 2 | 7 | 7 | 225/0, 226/0, 225/1, 225/2, 225/3, 225/4, 225/5, 225/6, 225/7 | 225/0, 226/0 | 225/0, 226/0 | 225/1, 225/2, 225/3, 225/4, 225/5, 225/6, 225/7 | 225/1, 225/2, 225/3, 225/4, 225/5, 225/6, 225/7 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 403 | 226/0 | 227/0 | 226/0 - 227/0 | 1.5747 | 5 | 5 | 5 | 0 | 0 | 226/0, 227/0, 226/1, 226/2, 226/3 | 226/0, 227/0, 226/1, 226/2, 226/3 | 226/0, 227/0, 226/1, 226/2, 226/3 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 404 | 227/0 | 228/0 | 227/0 - 228/0 | 1.2387 | 4 | 4 | 4 | 0 | 0 | 227/0, 228/0, 227/1, 227/2 | 227/0, 228/0, 227/1, 227/2 | 227/0, 228/0, 227/1, 227/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 405 | 228/0 | 229/0 | 228/0 - 229/0 | 0.76707 | 3 | 2 | 2 | 1 | 1 | 228/0, 229/0, 228/1 | 228/0, 228/1 | 228/0, 228/1 | 229/0 | 229/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 406 | 229/0 | 229A/0 | 229/0 - 229A/0 | 0.7915 | 3 | 0 | 0 | 3 | 3 | 229/0, 229A/0, 229/1 |  |  | 229/0, 229A/0, 229/1 | 229/0, 229A/0, 229/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 407 | 229A/0 | 229B/0 | 229A/0 - 229B/0 | 0.17998 | 2 | 0 | 0 | 2 | 2 | 229A/0, 229B/0 |  |  | 229A/0, 229B/0 | 229A/0, 229B/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 408 | 229B/0 | 230/0 | 229B/0 - 230/0 | 0.39065 | 2 | 1 | 1 | 1 | 1 | 229B/0, 230/0 | 230/0 | 230/0 | 229B/0 | 229B/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 409 | 230/0 | 230A/0 | 230/0 - 230A/0 | 0.78667 | 3 | 1 | 1 | 2 | 2 | 230/0, 230A/0, 230/1 | 230/0 | 230/0 | 230A/0, 230/1 | 230A/0, 230/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 410 | 230A/0 | 231/0 | 230A/0 - 231/0 | 0.23951 | 2 | 0 | 0 | 2 | 2 | 230A/0, 231/0 |  |  | 230A/0, 231/0 | 230A/0, 231/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 411 | 231/0 | 232/0 | 231/0 - 232/0 | 0.24698 | 2 | 0 | 0 | 2 | 2 | 231/0, 232/0 |  |  | 231/0, 232/0 | 231/0, 232/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 412 | 232/0 | 233/0 | 232/0 - 233/0 | 1.7282 | 6 | 0 | 0 | 6 | 6 | 232/0, 233/0, 232/1, 232/2, 232/3, 232/4 |  |  | 232/0, 233/0, 232/1, 232/2, 232/3, 232/4 | 232/0, 233/0, 232/1, 232/2, 232/3, 232/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 413 | 233/0 | 234/0 | 233/0 - 234/0 | 0.41114 | 2 | 0 | 0 | 2 | 2 | 233/0, 234/0 |  |  | 233/0, 234/0 | 233/0, 234/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 414 | 234/0 | 235/0 | 234/0 - 235/0 | 0.295 | 2 | 0 | 0 | 2 | 2 | 234/0, 235/0 |  |  | 234/0, 235/0 | 234/0, 235/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 415 | 235/0 | 236/0 | 235/0 - 236/0 | 1.7635 | 6 | 2 | 2 | 4 | 4 | 235/0, 236/0, 235/1, 235/2, 235/3, 235/4 | 235/2, 235/3 | 235/2, 235/3 | 235/0, 236/0, 235/1, 235/4 | 235/0, 236/0, 235/1, 235/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 416 | 236/0 | 237/0 | 236/0 - 237/0 | 0.20082 | 2 | 0 | 0 | 2 | 2 | 236/0, 237/0 |  |  | 236/0, 237/0 | 236/0, 237/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 417 | 237/0 | 238/0 | 237/0 - 238/0 | 0.20228 | 2 | 0 | 0 | 2 | 2 | 237/0, 238/0 |  |  | 237/0, 238/0 | 237/0, 238/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 418 | 238/0 | 239/0 | 238/0 - 239/0 | 0.36332 | 2 | 1 | 1 | 1 | 1 | 238/0, 239/0 | 239/0 | 239/0 | 238/0 | 238/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 419 | 239/0 | 240/0 | 239/0 - 240/0 | 0.7374 | 3 | 3 | 3 | 0 | 0 | 239/0, 240/0, 239/1 | 239/0, 240/0, 239/1 | 239/0, 240/0, 239/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 420 | 240/0 | 241/0 | 240/0 - 241/0 | 0.73405 | 3 | 3 | 3 | 0 | 0 | 240/0, 241/0, 240/1 | 240/0, 241/0, 240/1 | 240/0, 241/0, 240/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 421 | 241/0 | 242/0 | 241/0 - 242/0 | 1.8357 | 6 | 6 | 6 | 0 | 0 | 241/0, 242/0, 241/1, 241/2, 241/3, 241/4 | 241/0, 242/0, 241/1, 241/2, 241/3, 241/4 | 241/0, 242/0, 241/1, 241/2, 241/3, 241/4 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 422 | 242/0 | 243/0 | 242/0 - 243/0 | 0.28002 | 2 | 2 | 2 | 0 | 0 | 242/0, 243/0 | 242/0, 243/0 | 242/0, 243/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 423 | 243/0 | 244/0 | 243/0 - 244/0 | 1.3726 | 5 | 3 | 3 | 2 | 2 | 243/0, 244/0, 243/1, 243/2, 243/3 | 243/0, 243/1, 243/2 | 243/0, 243/1, 243/2 | 244/0, 243/3 | 244/0, 243/3 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 424 | 244/0 | 245/0 | 244/0 - 245/0 | 2.7781 | 8 | 6 | 6 | 2 | 2 | 244/0, 245/0, 244/1, 244/2, 244/3, 244/4, 244/5, 244/6 | 245/0, 244/1, 244/2, 244/4, 244/5, 244/6 | 245/0, 244/1, 244/2, 244/4, 244/5, 244/6 | 244/0, 244/3 | 244/0, 244/3 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 425 | 245/0 | 246/0 | 245/0 - 246/0 | 0.79163 | 3 | 3 | 3 | 0 | 0 | 245/0, 246/0, 245/1 | 245/0, 246/0, 245/1 | 245/0, 246/0, 245/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 426 | 246/0 | 247/0 | 246/0 - 247/0 | 0.4631 | 2 | 1 | 1 | 1 | 1 | 246/0, 247/0 | 246/0 | 246/0 | 247/0 | 247/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 427 | 247/0 | 248/0 | 247/0 - 248/0 | 0.25645 | 2 | 0 | 0 | 2 | 2 | 247/0, 248/0 |  |  | 247/0, 248/0 | 247/0, 248/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 428 | 248/0 | 248/1 | 248/0 - 248/1 | 0.42557 | 2 | 1 | 1 | 1 | 1 | 248/0, 248/1 | 248/1 | 248/1 | 248/0 | 248/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 429 | 248/1 | 249/0 | 248/1 - 249/0 | 0.5669 | 3 | 2 | 2 | 1 | 1 | 248/1, 249/0, 248/2 | 248/1, 248/2 | 248/1, 248/2 | 249/0 | 249/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 430 | 249/0 | 250/0 | 249/0 - 250/0 | 1.6206 | 5 | 1 | 1 | 4 | 4 | 249/0, 250/0, 249/1, 249/2, 249/3 | 249/3 | 249/3 | 249/0, 250/0, 249/1, 249/2 | 249/0, 250/0, 249/1, 249/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 431 | 250/0 | 250A/0 | 250/0 - 250A/0 | 1.631 | 5 | 3 | 3 | 2 | 2 | 250/0, 250A/0, 250/1, 250/2, 250/3 | 250A/0, 250/2, 250/3 | 250A/0, 250/2, 250/3 | 250/0, 250/1 | 250/0, 250/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 432 | 250A/0 | 251/0 | 250A/0 - 251/0 | 1.134 | 4 | 4 | 4 | 0 | 0 | 250A/0, 251/0, 250A/1, 250A/2 | 250A/0, 251/0, 250A/1, 250A/2 | 250A/0, 251/0, 250A/1, 250A/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 433 | 251/0 | 252/0 | 251/0 - 252/0 | 0.84087 | 3 | 3 | 3 | 0 | 0 | 251/0, 252/0, 251/1 | 251/0, 252/0, 251/1 | 251/0, 252/0, 251/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 434 | 252/0 | 252/5 | 252/0 - 252/5 | 2.022 | 6 | 6 | 6 | 0 | 0 | 252/0, 252/5, 252/1, 252/2, 252/3, 252/4 | 252/0, 252/5, 252/1, 252/2, 252/3, 252/4 | 252/0, 252/5, 252/1, 252/2, 252/3, 252/4 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 435 | 252/5 | 253/0 | 252/5 - 253/0 | 0.48745 | 2 | 1 | 1 | 1 | 1 | 252/5, 253/0 | 252/5 | 252/5 | 253/0 | 253/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 436 | 253/0 | 254/0 | 253/0 - 254/0 | 0.30446 | 2 | 0 | 0 | 2 | 2 | 253/0, 254/0 |  |  | 253/0, 254/0 | 253/0, 254/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 437 | 254/0 | 254/1 | 254/0 - 254/1 | 0.35319 | 2 | 1 | 1 | 1 | 1 | 254/0, 254/1 | 254/1 | 254/1 | 254/0 | 254/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 438 | 254/1 | 255/0 | 254/1 - 255/0 | 0.26306 | 2 | 2 | 2 | 0 | 0 | 254/1, 255/0 | 254/1, 255/0 | 254/1, 255/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 439 | 255/0 | 256/0 | 255/0 - 256/0 | 0.73676 | 3 | 3 | 3 | 0 | 0 | 255/0, 256/0, 255/1 | 255/0, 256/0, 255/1 | 255/0, 256/0, 255/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 440 | 256/0 | 257/0 | 256/0 - 257/0 | 0.58335 | 3 | 1 | 1 | 2 | 2 | 256/0, 257/0, 256/1 | 256/0 | 256/0 | 257/0, 256/1 | 257/0, 256/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 441 | 257/0 | 258/0 | 257/0 - 258/0 | 0.09477 | 2 | 0 | 0 | 2 | 2 | 257/0, 258/0 |  |  | 257/0, 258/0 | 257/0, 258/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 414 | TA 414 | ta414 |  | TA 414 - DPR - 2026-05-26.xlsx | Stringing Compiled | 442 | 258/0 | Gantry | 258/0 - Gantry | 0.079 | 2 | 0 | 0 | 2 | 2 | 258/0, GANTRY |  |  | 258/0, GANTRY | 258/0, GANTRY | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 443 | AP7/0 | AP8/0 | UP | 4.8187 | 13 | 13 | 13 | 0 | 0 | 7/0, 8/0, 7/1, 7/2, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 7/10, 7/11 | 7/0, 8/0, 7/1, 7/2, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 7/10, 7/11 | 7/0, 8/0, 7/1, 7/2, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 7/10, 7/11 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 444 | AP6/0 | AP7/0 | UP | 1.2343 | 4 | 4 | 4 | 0 | 0 | 6/0, 7/0, 6/1, 6/2 | 6/0, 7/0, 6/1, 6/2 | 6/0, 7/0, 6/1, 6/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 445 | AP35/0 | AP36/0 | UP | 3.9571 | 11 | 11 | 11 | 0 | 0 | 35/0, 36/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9 | 35/0, 36/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9 | 35/0, 36/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 446 | AP8/0 | AP8A/0 | UP | 2.0167 | 6 | 6 | 6 | 0 | 0 | 8/0, 8A/0, 8/1, 8/2, 8/3, 8/4 | 8/0, 8A/0, 8/1, 8/2, 8/3, 8/4 | 8/0, 8A/0, 8/1, 8/2, 8/3, 8/4 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 447 | AP31/0 | AP32/0 | UP | 4.2837 | 12 | 12 | 12 | 0 | 0 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5, 31/6, 31/7, 31/8, 31/9, 31/10 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5, 31/6, 31/7, 31/8, 31/9, 31/10 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5, 31/6, 31/7, 31/8, 31/9, 31/10 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 448 | AP8A/0 | AP8B/0 | UP | 0.22361 | 2 | 2 | 2 | 0 | 0 | 8A/0, 8B/0 | 8A/0, 8B/0 | 8A/0, 8B/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 449 | AP32/0 | AP33/0 | UP | 0.40717 | 2 | 2 | 2 | 0 | 0 | 32/0, 33/0 | 32/0, 33/0 | 32/0, 33/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 450 | AP8B/0 | AP9/0 | UP | 2.2262 | 7 | 7 | 7 | 0 | 0 | 8B/0, 9/0, 8B/1, 8B/2, 8B/3, 8B/4, 8B/5 | 8B/0, 9/0, 8B/1, 8B/2, 8B/3, 8B/4, 8B/5 | 8B/0, 9/0, 8B/1, 8B/2, 8B/3, 8B/4, 8B/5 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 451 | AP33/0 | AP34/0 | UP | 4.7815 | 13 | 13 | 13 | 0 | 0 | 33/0, 34/0, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/7, 33/8, 33/9, 33/10, 33/11 | 33/0, 34/0, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/7, 33/8, 33/9, 33/10, 33/11 | 33/0, 34/0, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/7, 33/8, 33/9, 33/10, 33/11 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 452 | AP5/0 | AP6/0 | UP | 0.72357 | 3 | 3 | 3 | 0 | 0 | 5/0, 6/0, 5/1 | 5/0, 6/0, 5/1 | 5/0, 6/0, 5/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 453 | AP9/0 | AP10/0 | UP | 0.28343 | 2 | 2 | 2 | 0 | 0 | 9/0, 10/0 | 9/0, 10/0 | 9/0, 10/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 454 | AP34/0 | AP35/0 | UP | 3.1932 | 9 | 9 | 9 | 0 | 0 | 34/0, 35/0, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 34/7 | 34/0, 35/0, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 34/7 | 34/0, 35/0, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 34/7 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 455 | AP4/0 | AP5/0 | UP | 4.4157 | 12 | 12 | 12 | 0 | 0 | 4/0, 5/0, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10 | 4/0, 5/0, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10 | 4/0, 5/0, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 456 | AP14/0 | AP15/0 | UP | 3.611 | 10 | 10 | 10 | 0 | 0 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 14/8 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 14/8 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 14/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 457 | AP36/0 | AP37/0 | UP | 4.9473 | 14 | 14 | 14 | 0 | 0 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7, 36/8, 36/9, 36/10, 36/11, 36/12 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7, 36/8, 36/9, 36/10, 36/11, 36/12 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7, 36/8, 36/9, 36/10, 36/11, 36/12 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 458 | AP3/0 | AP4/0 | UP | 0.28 | 2 | 2 | 2 | 0 | 0 | 3/0, 4/0 | 3/0, 4/0 | 3/0, 4/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 459 | AP30/0 | AP31/0 | UP | 2.7505 | 8 | 8 | 8 | 0 | 0 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 460 | AP20/0 | AP21/0 | UP | 4.958 | 14 | 14 | 14 | 0 | 0 | 20/0, 21/0, 20/1, 20/2, 20/3, 20/4, 20/5, 20/6, 20/7, 20/8, 20/9, 20/10, 20/11, 20/12 | 20/0, 21/0, 20/1, 20/2, 20/3, 20/4, 20/5, 20/6, 20/7, 20/8, 20/9, 20/10, 20/11, 20/12 | 20/0, 21/0, 20/1, 20/2, 20/3, 20/4, 20/5, 20/6, 20/7, 20/8, 20/9, 20/10, 20/11, 20/12 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 461 | AP12/0 | AP13/0 | UP | 3.92 | 11 | 11 | 11 | 0 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 462 | AP39/0 | AP40/0 | UP | 4.4605 | 12 | 12 | 12 | 0 | 0 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 463 | AP21/0 | AP22/0 | UP | 1.606 | 5 | 5 | 5 | 0 | 0 | 21/0, 22/0, 21/1, 21/2, 21/3 | 21/0, 22/0, 21/1, 21/2, 21/3 | 21/0, 22/0, 21/1, 21/2, 21/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 464 | AP13/0 | AP14/0 | UP | 0.31913 | 2 | 2 | 2 | 0 | 0 | 13/0, 14/0 | 13/0, 14/0 | 13/0, 14/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 465 | AP38/0 | AP39/0 | UP | 4.8228 | 13 | 13 | 13 | 0 | 0 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 466 | AP19/0 | AP20/0 | UP | 4.9905 | 14 | 14 | 14 | 0 | 0 | 19/0, 20/0, 19/1, 19/2, 19/3, 19/4, 19/5, 19/6, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12 | 19/0, 20/0, 19/1, 19/2, 19/3, 19/4, 19/5, 19/6, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12 | 19/0, 20/0, 19/1, 19/2, 19/3, 19/4, 19/5, 19/6, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 467 | AP17/0 | AP18/0 | UP | 3.4566 | 10 | 10 | 10 | 0 | 0 | 17/0, 18/0, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8 | 17/0, 18/0, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8 | 17/0, 18/0, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 468 | AP18/0 | AP19/0 | UP | 0.323 | 2 | 2 | 2 | 0 | 0 | 18/0, 19/0 | 18/0, 19/0 | 18/0, 19/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 469 | AP15/0 | AP16/0 | UP | 0.465 | 2 | 2 | 2 | 0 | 0 | 15/0, 16/0 | 15/0, 16/0 | 15/0, 16/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 470 | AP10/0 | AP11/0 | UP | 0.822 | 3 | 3 | 3 | 0 | 0 | 10/0, 11/0, 10/1 | 10/0, 11/0, 10/1 | 10/0, 11/0, 10/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 471 | AP37/0 | AP38/0 | UP | 0.476 | 2 | 2 | 2 | 0 | 0 | 37/0, 38/0 | 37/0, 38/0 | 37/0, 38/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 472 | AP11/0 | AP12/0 | UP | 0.313 | 2 | 2 | 2 | 0 | 0 | 11/0, 12/0 | 11/0, 12/0 | 11/0, 12/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 473 | AP1/0 | AP2/0 | UP | 0.246 | 2 | 2 | 2 | 0 | 0 | 1/0, 2/0 | 1/0, 2/0 | 1/0, 2/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 474 | AP0/0 | AP1/0 | UP | 1.922 | 7 | 7 | 7 | 0 | 0 | 0/0, 1/0, 0/1, 0/2, 0/3, 0/4, 2/0 | 0/0, 1/0, 0/1, 0/2, 0/3, 0/4, 2/0 | 0/0, 1/0, 0/1, 0/2, 0/3, 0/4, 2/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 475 | AP24/0 | AP25/0 | UP | 0.23153 | 2 | 2 | 2 | 0 | 0 | 24/0, 25/0 | 24/0, 25/0 | 24/0, 25/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 476 | AP23/0 | AP24/0 | UP | 2.2273 | 7 | 7 | 7 | 0 | 0 | 23/0, 24/0, 23/1, 23/2, 23/3, 23/4, 23/5 | 23/0, 24/0, 23/1, 23/2, 23/3, 23/4, 23/5 | 23/0, 24/0, 23/1, 23/2, 23/3, 23/4, 23/5 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 477 | AP40/0 | AP41/0 | UP | 0.2393 | 2 | 2 | 2 | 0 | 0 | 40/0, 41/0 | 40/0, 41/0 | 40/0, 41/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 478 | AP16/0 | AP17/0 | UP | 0.26498 | 2 | 2 | 2 | 0 | 0 | 16/0, 17/0 | 16/0, 17/0 | 16/0, 17/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 479 | AP2/0 | AP3/0 | UP | 3.6837 | 10 | 10 | 10 | 0 | 0 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 480 | AP26/0 | AP27/0 | UP | 0.44084 | 2 | 2 | 2 | 0 | 0 | 26/0, 27/0 | 26/0, 27/0 | 26/0, 27/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 481 | AP25/0 | AP26/0 | UP | 1.6664 | 5 | 5 | 5 | 0 | 0 | 25/0, 26/0, 25/1, 25/2, 25/3 | 25/0, 26/0, 25/1, 25/2, 25/3 | 25/0, 26/0, 25/1, 25/2, 25/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 482 | AP42/0 | AP43/0 | UP | 0.30923 | 2 | 2 | 2 | 0 | 0 | 42/0, 43/0 | 42/0, 43/0 | 42/0, 43/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 483 | AP29/0 | AP30/0 | UP | 0.27008 | 2 | 2 | 2 | 0 | 0 | 29/0, 30/0 | 29/0, 30/0 | 29/0, 30/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 484 | AP41/0 | AP42/0 | UP | 1.1416 | 4 | 4 | 4 | 0 | 0 | 41/0, 42/0, 41/1, 41/2 | 41/0, 42/0, 41/1, 41/2 | 41/0, 42/0, 41/1, 41/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 485 | AP28/0 | AP29/0 | UP | 0.68767 | 3 | 3 | 3 | 0 | 0 | 28/0, 29/0, 28/1 | 28/0, 29/0, 28/1 | 28/0, 29/0, 28/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 486 | AP22/0 | AP22A/0 | UP | 0.19095 | 2 | 2 | 2 | 0 | 0 | 22/0, 22A/0 | 22/0, 22A/0 | 22/0, 22A/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 487 | AP27/0 | AP28/0 | UP | 0.29947 | 2 | 2 | 2 | 0 | 0 | 27/0, 28/0 | 27/0, 28/0 | 27/0, 28/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 488 | AP52/1 | AP53/0 | UP | 3.8144 | 11 | 11 | 11 | 0 | 0 | 52/1, 53/0, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7, 52/8, 52/9, 52/10 | 52/1, 53/0, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7, 52/8, 52/9, 52/10 | 52/1, 53/0, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7, 52/8, 52/9, 52/10 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 489 | AP46/0 | AP47/0 | UP | 1.1556 | 4 | 4 | 4 | 0 | 0 | 46/0, 47/0, 46/1, 46/2 | 46/0, 47/0, 46/1, 46/2 | 46/0, 47/0, 46/1, 46/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 490 | AP22A/0 | AP23/0 | UP | 0.26742 | 2 | 2 | 2 | 0 | 0 | 22A/0, 23/0 | 22A/0, 23/0 | 22A/0, 23/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 491 | AP53/0 | AP53A/0 | UP | 0.83178 | 3 | 3 | 3 | 0 | 0 | 53/0, 53A/0, 53/1 | 53/0, 53A/0, 53/1 | 53/0, 53A/0, 53/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 492 | AP45/0 | AP46/0 | UP | 1.4579 | 5 | 5 | 5 | 0 | 0 | 45/0, 46/0, 45/1, 45/2, 45/3 | 45/0, 46/0, 45/1, 45/2, 45/3 | 45/0, 46/0, 45/1, 45/2, 45/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 493 | AP53A/0 | AP54/0 | UP | 3.166 | 9 | 9 | 9 | 0 | 0 | 53A/0, 54/0, 53A/1, 53A/2, 53A/3, 53A/4, 53A/5, 53A/6, 53A/7 | 53A/0, 54/0, 53A/1, 53A/2, 53A/3, 53A/4, 53A/5, 53A/6, 53A/7 | 53A/0, 54/0, 53A/1, 53A/2, 53A/3, 53A/4, 53A/5, 53A/6, 53A/7 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 494 | AP52/0 | AP52/1 | UP | 0.461 | 2 | 2 | 2 | 0 | 0 | 52/0, 52/1 | 52/0, 52/1 | 52/0, 52/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 495 | AP44/0 | AP45/0 | UP | 0.3 | 2 | 2 | 2 | 0 | 0 | 44/0, 45/0 | 44/0, 45/0 | 44/0, 45/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 496 | AP69A/0 | AP70/0 | UP | 0.20246 | 2 | 2 | 2 | 0 | 0 | 69A/0, 70/0 | 69A/0, 70/0 | 69A/0, 70/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 497 | AP70/0 | Gantry | UP | 0.127 | 2 | 1 | 1 | 1 | 1 | 70/0, GANTRY | 70/0 | 70/0 | GANTRY | GANTRY | PARTIAL_PARSE | Unparsed tokens: GANTRY/0 | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 498 | AP43/0 | AP44/0 | UP | 0.45967 | 2 | 2 | 2 | 0 | 0 | 43/0, 44/0 | 43/0, 44/0 | 43/0, 44/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 499 | AP66/0 | AP67/0 | UP | 0.81236 | 3 | 3 | 3 | 0 | 0 | 66/0, 67/0, 66/1 | 66/0, 67/0, 66/1 | 66/0, 67/0, 66/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 500 | AP69/0 | AP69A | UP | 0.2326 | 3 | 2 | 2 | 1 | 1 | 69/0, 69A, 69A/0 | 69/0, 69A/0 | 69/0, 69A/0 | 69A | 69A | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 501 | AP65/0 | AP66 | UP | 0.29804 | 3 | 2 | 2 | 1 | 1 | 65/0, 66, 66/0 | 65/0, 66/0 | 65/0, 66/0 | 66 | 66 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 502 | AP68/0 | AP69/0 | UP | 0.30377 | 2 | 2 | 2 | 0 | 0 | 68/0, 69/0 | 68/0, 69/0 | 68/0, 69/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 503 | AP67/0 | AP68/0 | UP | 0.31841 | 2 | 2 | 2 | 0 | 0 | 67/0, 68/0 | 67/0, 68/0 | 67/0, 68/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 504 | AP62/0 | AP63/0 | UP | 0.34919 | 2 | 2 | 2 | 0 | 0 | 62/0, 63/0 | 62/0, 63/0 | 62/0, 63/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 505 | AP54/0 | AP55/0 | UP | 1.1862 | 4 | 4 | 4 | 0 | 0 | 54/0, 55/0, 54/1, 54/2 | 54/0, 55/0, 54/1, 54/2 | 54/0, 55/0, 54/1, 54/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 506 | AP61/0 | AP62/0 | UP | 0.47807 | 2 | 2 | 2 | 0 | 0 | 61/0, 62/0 | 61/0, 62/0 | 61/0, 62/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 507 | AP64/0 | AP65/0 | UP | 1.5512 | 2 | 2 | 2 | 0 | 0 | 64/0, 65/0 | 64/0, 65/0 | 64/0, 65/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 508 | AP55/0 | AP56/0 | UP | 0.60721 | 3 | 3 | 3 | 0 | 0 | 55/0, 56/0, 55/1 | 55/0, 56/0, 55/1 | 55/0, 56/0, 55/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 509 | AP47/0 | AP48/0 | UP | 0.35863 | 2 | 2 | 2 | 0 | 0 | 47/0, 48/0 | 47/0, 48/0 | 47/0, 48/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 510 | AP56/0 | AP57/0 | UP | 3.374 | 10 | 10 | 10 | 0 | 0 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 511 | AP57/0 | AP58/0 | UP | 0.67728 | 3 | 3 | 3 | 0 | 0 | 57/0, 58/0, 57/1 | 57/0, 58/0, 57/1 | 57/0, 58/0, 57/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 512 | AP59/0 | AP60/0 | UP | 0.418 | 2 | 2 | 2 | 0 | 0 | 59/0, 60/0 | 59/0, 60/0 | 59/0, 60/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 513 | AP63/0 | AP64/0 | UP | 0.286 | 2 | 2 | 2 | 0 | 0 | 63/0, 64/0 | 63/0, 64/0 | 63/0, 64/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 416 | TA 416 | ta416 |  | TA 416 - DPR - 2026-05-26.xlsx | Stringing compiled | 521 |  | Total | Total | 0.1124 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 522 | AP32 | AP33 | KA | 0.24963 | 4 | 2 | 2 | 2 | 2 | 32, 33, 32/0, 33/0 | 32/0, 33/0 | 32/0, 33/0 | 32, 33 | 32, 33 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 523 | AP33 | 33/5 | KA | 2.015 | 7 | 6 | 6 | 1 | 1 | 33, 33/5, 33/0, 33/1, 33/2, 33/3, 33/4 | 33/5, 33/0, 33/1, 33/2, 33/3, 33/4 | 33/5, 33/0, 33/1, 33/2, 33/3, 33/4 | 33 | 33 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 524 | 33/5 | 33/6 | KA | 0.38 | 2 | 2 | 2 | 0 | 0 | 33/5, 33/6 | 33/5, 33/6 | 33/5, 33/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 525 | 33/6 | 34/0 | KA | 2.5374 | 8 | 8 | 8 | 0 | 0 | 33/6, 34/0, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12 | 33/6, 34/0, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12 | 33/6, 34/0, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 526 | 34/0 | AP35 | KA | 1.9835 | 7 | 6 | 6 | 1 | 1 | 34/0, 35, 34/1, 34/2, 34/3, 34/4, 35/0 | 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 | 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 | 35 | 35 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 527 | AP35 | AP36 | KA | 4.48 | 15 | 12 | 12 | 3 | 3 | 35, 36, 35/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9, 35/10, 35/11, 36/0 | 35/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/7, 35/8, 35/9, 35/10, 35/11, 36/0 | 35/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/7, 35/8, 35/9, 35/10, 35/11, 36/0 | 35, 36, 35/6 | 35, 36, 35/6 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 528 | AP36 | 36/1 | KA | 0.48 | 3 | 2 | 2 | 1 | 1 | 36, 36/1, 36/0 | 36/1, 36/0 | 36/1, 36/0 | 36 | 36 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 529 | 36/1 | 37/0 | KA | 0.29732 | 2 | 2 | 2 | 0 | 0 | 36/1, 37/0 | 36/1, 37/0 | 36/1, 37/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 530 | 37/0 | AP38 | KA | 1.2588 | 5 | 4 | 4 | 1 | 1 | 37/0, 38, 37/1, 37/2, 38/0 | 37/0, 37/1, 37/2, 38/0 | 37/0, 37/1, 37/2, 38/0 | 38 | 38 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 531 | AP38 | AP39 | KA | 1.3008 | 6 | 4 | 4 | 2 | 2 | 38, 39, 38/0, 38/1, 38/2, 39/0 | 38/0, 38/1, 38/2, 39/0 | 38/0, 38/1, 38/2, 39/0 | 38, 39 | 38, 39 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 532 | AP39 | AP40 | KA | 0.23087 | 4 | 2 | 2 | 2 | 2 | 39, 40, 39/0, 40/0 | 39/0, 40/0 | 39/0, 40/0 | 39, 40 | 39, 40 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 533 | AP40 | AP41 | KA | 2.4264 | 9 | 7 | 7 | 2 | 2 | 40, 41, 40/0, 40/1, 40/2, 40/3, 40/4, 40/5, 41/0 | 40/0, 40/1, 40/2, 40/3, 40/4, 40/5, 41/0 | 40/0, 40/1, 40/2, 40/3, 40/4, 40/5, 41/0 | 40, 41 | 40, 41 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 534 | AP41 | AP42 | KA | 2.4732 | 9 | 7 | 7 | 2 | 2 | 41, 42, 41/0, 41/1, 41/2, 41/3, 41/4, 41/5, 42/0 | 41/0, 41/1, 41/2, 41/3, 41/4, 41/5, 42/0 | 41/0, 41/1, 41/2, 41/3, 41/4, 41/5, 42/0 | 41, 42 | 41, 42 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 535 | AP42 | AP43 | KA | 1.1058 | 6 | 4 | 4 | 2 | 2 | 42, 43, 42/0, 42/1, 42/2, 43/0 | 42/0, 42/1, 42/2, 43/0 | 42/0, 42/1, 42/2, 43/0 | 42, 43 | 42, 43 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 536 | AP43 | AP44 | KA | 1.4448 | 7 | 5 | 5 | 2 | 2 | 43, 44, 43/0, 43/1, 43/2, 43/3, 44/0 | 43/0, 43/1, 43/2, 43/3, 44/0 | 43/0, 43/1, 43/2, 43/3, 44/0 | 43, 44 | 43, 44 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 537 | AP44 | AP45 | KA | 0.69756 | 5 | 3 | 3 | 2 | 2 | 44, 45, 44/0, 44/1, 45/0 | 44/0, 44/1, 45/0 | 44/0, 44/1, 45/0 | 44, 45 | 44, 45 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 538 | AP45 | 45/1 | KA | 0.242 | 3 | 2 | 2 | 1 | 1 | 45, 45/1, 45/0 | 45/1, 45/0 | 45/1, 45/0 | 45 | 45 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 539 | 45/1 | AP46 | KA | 1.2725 | 5 | 4 | 4 | 1 | 1 | 45/1, 46, 45/0, 45/2, 46/0 | 45/1, 45/0, 45/2, 46/0 | 45/1, 45/0, 45/2, 46/0 | 46 | 46 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 540 | AP46 | 46/7 | KA | 2.745 | 9 | 8 | 8 | 1 | 1 | 46, 46/7, 46/0, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6 | 46/7, 46/0, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6 | 46/7, 46/0, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6 | 46 | 46 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 541 | 46/7 | AP47/0 | KA | 3.5473 | 10 | 10 | 9 | 0 | 1 | 46/7, 47/0, 46/8, 46/9, 46/10, 46/11, 46/12, 46/13, 46/14, 46/15 | 46/7, 47/0, 46/8, 46/9, 46/10, 46/11, 46/12, 46/13, 46/14, 46/15 | 46/7, 47/0, 46/8, 46/10, 46/11, 46/12, 46/13, 46/14, 46/15 |  | 46/9 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 542 | AP47/0 | AP48 | KA | 0.81345 | 4 | 3 | 2 | 1 | 2 | 47/0, 48, 47/1, 48/0 | 47/0, 47/1, 48/0 | 47/0, 47/1 | 48 | 48, 48/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 543 | AP48 | 48A/0 | KA | 1.2571 | 5 | 4 | 3 | 1 | 2 | 48, 48A/0, 48/0, 48/1, 48/2 | 48A/0, 48/0, 48/1, 48/2 | 48A/0, 48/1, 48/2 | 48 | 48, 48/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 544 | 48A/0 | 49/0 | KA | 1.1011 | 4 | 4 | 4 | 0 | 0 | 48A/0, 49/0, 48A/1, 48A/2 | 48A/0, 49/0, 48A/1, 48A/2 | 48A/0, 49/0, 48A/1, 48A/2 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 545 | 49/0 | AP50 | KA | 0.41722 | 3 | 2 | 2 | 1 | 1 | 49/0, 50, 50/0 | 49/0, 50/0 | 49/0, 50/0 | 50 | 50 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 546 | AP50 | AP51 | KA | 0.2496 | 4 | 2 | 2 | 2 | 2 | 50, 51, 50/0, 51/0 | 50/0, 51/0 | 50/0, 51/0 | 50, 51 | 50, 51 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 547 | AP51 | AP52 | KA | 0.3336 | 4 | 2 | 2 | 2 | 2 | 51, 52, 51/0, 52/0 | 51/0, 52/0 | 51/0, 52/0 | 51, 52 | 51, 52 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 548 | AP52 | AP53 | KA | 1.0341 | 6 | 4 | 4 | 2 | 2 | 52, 53, 52/0, 52/1, 52/2, 53/0 | 52/0, 52/1, 52/2, 53/0 | 52/0, 52/1, 52/2, 53/0 | 52, 53 | 52, 53 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 549 | AP53 | AP54 | KA | 0.25862 | 4 | 2 | 1 | 2 | 3 | 53, 54, 53/0, 54/0 | 53/0, 54/0 | 53/0 | 53, 54 | 53, 54, 54/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 550 | AP54 | AP55 | KA | 1.8367 | 8 | 6 | 4 | 2 | 4 | 54, 55, 54/0, 54/1, 54/2, 54/3, 54/4, 55/0 | 54/0, 54/1, 54/2, 54/3, 54/4, 55/0 | 54/1, 54/3, 54/4, 55/0 | 54, 55 | 54, 55, 54/0, 54/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 551 | AP55 | AP56 | KA | 2.7045 | 10 | 8 | 8 | 2 | 2 | 55, 56, 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55, 56 | 55, 56 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 552 | AP56 | 56/3 | KA | 1.23 | 5 | 4 | 4 | 1 | 1 | 56, 56/3, 56/0, 56/1, 56/2 | 56/3, 56/0, 56/1, 56/2 | 56/3, 56/0, 56/1, 56/2 | 56 | 56 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 553 | 56/3 | 57/0 | KA | 0.27649 | 2 | 2 | 1 | 0 | 1 | 56/3, 57/0 | 56/3, 57/0 | 56/3 |  | 57/0 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 554 | 57/0 | 58/0 | KA | 1.5358 | 5 | 5 | 4 | 0 | 1 | 57/0, 58/0, 57/1, 57/2, 57/3 | 57/0, 58/0, 57/1, 57/2, 57/3 | 58/0, 57/1, 57/2, 57/3 |  | 57/0 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 555 | 58/0 | 59/0 | KA | 0.2039 | 2 | 2 | 2 | 0 | 0 | 58/0, 59/0 | 58/0, 59/0 | 58/0, 59/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 556 | 59/0 | 60/0 | KA | 0.7028 | 3 | 3 | 2 | 0 | 1 | 59/0, 60/0, 59/1 | 59/0, 60/0, 59/1 | 59/0, 60/0 |  | 59/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 557 | 60/0 | 61/0 | KA | 1.942 | 6 | 6 | 6 | 0 | 0 | 60/0, 61/0, 60/1, 60/2, 60/3, 60/4 | 60/0, 61/0, 60/1, 60/2, 60/3, 60/4 | 60/0, 61/0, 60/1, 60/2, 60/3, 60/4 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 558 | 61/0 | 62/0 | KA | 0.3581 | 2 | 2 | 2 | 0 | 0 | 61/0, 62/0 | 61/0, 62/0 | 61/0, 62/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 559 | 62/0 | 63/0 | KA | 0.2787 | 2 | 2 | 2 | 0 | 0 | 62/0, 63/0 | 62/0, 63/0 | 62/0, 63/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 560 | 63/0 | GNTY | KA | 0.135 | 3 | 1 | 1 | 2 | 2 | 63/0, GNTY, 63/GNTY | 63/0 | 63/0 | GNTY, 63/GNTY | GNTY, 63/GNTY | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 418 | TA 418 | ta418 |  | TA 418 - DPR - 2026-05-21.xlsx | Stringing Compiled | 564 |  | Total | Total | 0.047837 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 565 | 23/0 | 24/0 | Telangana | 1.826 | 4 | 4 | 4 | 0 | 0 | 23/0, 24/0, 23/1, 23/2 | 23/0, 24/0, 23/1, 23/2 | 23/0, 24/0, 23/1, 23/2 |  |  | PARTIAL_PARSE | Unparsed tokens: 3&24/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 566 | 24/0 | 25/0 | Telangana | 3.406 | 9 | 9 | 9 | 0 | 0 | 24/0, 25/0, 24/1, 24/2, 24/3, 24/4, 24/5, 24/6, 24/7 | 24/0, 25/0, 24/1, 24/2, 24/3, 24/4, 24/5, 24/6, 24/7 | 24/0, 25/0, 24/1, 24/2, 24/3, 24/4, 24/5, 24/6, 24/7 |  |  | PARTIAL_PARSE | Unparsed tokens: 8&25/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 567 | 25/0 | 26/0 | Telangana | 2.279 | 6 | 6 | 6 | 0 | 0 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 |  |  | PARTIAL_PARSE | Unparsed tokens: 5&26/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 568 | 26/0 | 27/0 | Telangana | 1.914 | 5 | 5 | 5 | 0 | 0 | 26/0, 27/0, 26/1, 26/2, 26/3 | 26/0, 27/0, 26/1, 26/2, 26/3 | 26/0, 27/0, 26/1, 26/2, 26/3 |  |  | PARTIAL_PARSE | Unparsed tokens: 4&27/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 569 | 22/0 | 23/0 | Telangana | 2.338 | 6 | 6 | 6 | 0 | 0 | 22/0, 23/0, 22/1, 22/2, 22/3, 22/4 | 22/0, 23/0, 22/1, 22/2, 22/3, 22/4 | 22/0, 23/0, 22/1, 22/2, 22/3, 22/4 |  |  | PARTIAL_PARSE | Unparsed tokens: 5&23/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 570 | 29/0 | 29/9 | Telangana | 3.555 | 10 | 10 | 10 | 0 | 0 | 29/0, 29/9, 29/1, 29/2, 29/3, 29/4, 29/5, 29/6, 29/7, 29/8 | 29/0, 29/9, 29/1, 29/2, 29/3, 29/4, 29/5, 29/6, 29/7, 29/8 | 29/0, 29/9, 29/1, 29/2, 29/3, 29/4, 29/5, 29/6, 29/7, 29/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 571 | 32/0 | 33/0 | Telangana | 1.658 | 4 | 4 | 4 | 0 | 0 | 32/0, 33/0, 32/1, 32/2 | 32/0, 33/0, 32/1, 32/2 | 32/0, 33/0, 32/1, 32/2 |  |  | PARTIAL_PARSE | Unparsed tokens: 3&33/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 572 | 31/0 | 32/0 | Telangana | 2.689 | 7 | 7 | 7 | 0 | 0 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5 |  |  | PARTIAL_PARSE | Unparsed tokens: 6&32/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 573 | 30/0 | 31/0 | Telangana | 2.383 | 7 | 7 | 7 | 0 | 0 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 |  |  | PARTIAL_PARSE | Unparsed tokens: 6&31/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 574 | 29/9 | 30/0 | Telangana | 0.508 | 2 | 2 | 2 | 0 | 0 | 29/9, 30/0 | 29/9, 30/0 | 29/9, 30/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 575 | 21/0 | 22/0 | Telangana | 3.867 | 10 | 10 | 10 | 0 | 0 | 21/0, 22/0, 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8 | 21/0, 22/0, 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8 | 21/0, 22/0, 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8 |  |  | PARTIAL_PARSE | Unparsed tokens: 9&22/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 576 | 20A/0 | 21/0 | Telangana | 0.172 | 2 | 2 | 2 | 0 | 0 | 20A/0, 21/0 | 20A/0, 21/0 | 20A/0, 21/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 577 | 20/0 | 20A/0 | Telangana | 0.241 | 2 | 2 | 2 | 0 | 0 | 20/0, 20A/0 | 20/0, 20A/0 | 20/0, 20A/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 578 | 12/0 | 13/0 | Telangana | 4.9795 | 12 | 12 | 12 | 0 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10 |  |  | PARTIAL_PARSE | Unparsed tokens: 11&13/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 579 | 10/0 | 11/0 | Telangana | 4.1245 | 10 | 10 | 10 | 0 | 0 | 10/0, 11/0, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8 | 10/0, 11/0, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8 | 10/0, 11/0, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8 |  |  | PARTIAL_PARSE | Unparsed tokens: 9&11/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 580 | 19/0 | 20/0 | Telangana | 1.6396 | 4 | 4 | 4 | 0 | 0 | 19/0, 20/0, 19/1, 19/2 | 19/0, 20/0, 19/1, 19/2 | 19/0, 20/0, 19/1, 19/2 |  |  | PARTIAL_PARSE | Unparsed tokens: 3&20/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 581 | 18/0 | 19/0 | Telangana | 1.564 | 4 | 4 | 4 | 0 | 0 | 18/0, 19/0, 18/1, 18/2 | 18/0, 19/0, 18/1, 18/2 | 18/0, 19/0, 18/1, 18/2 |  |  | PARTIAL_PARSE | Unparsed tokens: 3&19/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 582 | 9/0 | 10/0 | Karnataka | 4.598 | 11 | 11 | 11 | 0 | 0 | 9/0, 10/0, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 9/9 | 9/0, 10/0, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 9/9 | 9/0, 10/0, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 9/9 |  |  | PARTIAL_PARSE | Unparsed tokens: 10&10/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 583 | 13/0 | 14/0 | Telangana | 4.9 | 12 | 12 | 12 | 0 | 0 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 13/7, 13/8, 13/9, 13/10 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 13/7, 13/8, 13/9, 13/10 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 13/7, 13/8, 13/9, 13/10 |  |  | PARTIAL_PARSE | Unparsed tokens: 11&14/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 584 | 11/0 | 12/0 | Karnataka | 4.751 | 12 | 12 | 12 | 0 | 0 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10 |  |  | PARTIAL_PARSE | Unparsed tokens: 11&12/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 585 | 17/0 | 18/0 | Telangana | 1.539 | 4 | 4 | 4 | 0 | 0 | 17/0, 18/0, 17/1, 17/2 | 17/0, 18/0, 17/1, 17/2 | 17/0, 18/0, 17/1, 17/2 |  |  | PARTIAL_PARSE | Unparsed tokens: 3&18/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 586 | 14/0 | 15/0 | Telangana | 0.498 | 2 | 2 | 2 | 0 | 0 | 14/0, 15/0 | 14/0, 15/0 | 14/0, 15/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 587 | 16/0 | 17/0 | Telangana | 4.762 | 12 | 12 | 12 | 0 | 0 | 16/0, 17/0, 16/1, 16/2, 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 16/10 | 16/0, 17/0, 16/1, 16/2, 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 16/10 | 16/0, 17/0, 16/1, 16/2, 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 16/10 |  |  | PARTIAL_PARSE | Unparsed tokens: 11&17/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 588 | 15/0 | 16/0 | Telangana | 1.91 | 5 | 5 | 5 | 0 | 0 | 15/0, 16/0, 15/1, 15/2, 15/3 | 15/0, 16/0, 15/1, 15/2, 15/3 | 15/0, 16/0, 15/1, 15/2, 15/3 |  |  | PARTIAL_PARSE | Unparsed tokens: 4&16/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 589 | 8/4 | 9/0 | Karnataka | 4.933 | 12 | 12 | 12 | 0 | 0 | 8/4, 9/0, 8/5, 8/6, 8/7, 8/8, 8/9, 8/10, 8/11, 8/12, 8/13, 8/14 | 8/4, 9/0, 8/5, 8/6, 8/7, 8/8, 8/9, 8/10, 8/11, 8/12, 8/13, 8/14 | 8/4, 9/0, 8/5, 8/6, 8/7, 8/8, 8/9, 8/10, 8/11, 8/12, 8/13, 8/14 |  |  | PARTIAL_PARSE | Unparsed tokens: 15&19/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 590 | 6/0 | 7/0 | Karnataka | 3.294 | 8 | 8 | 8 | 0 | 0 | 6/0, 7/0, 6/1, 6/2, 6/3, 6/4, 6/5, 6/6 | 6/0, 7/0, 6/1, 6/2, 6/3, 6/4, 6/5, 6/6 | 6/0, 7/0, 6/1, 6/2, 6/3, 6/4, 6/5, 6/6 |  |  | PARTIAL_PARSE | Unparsed tokens: 7&7/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 591 | 8/3 | 8/4 | Karnataka | 0.337 | 2 | 2 | 2 | 0 | 0 | 8/3, 8/4 | 8/3, 8/4 | 8/3, 8/4 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 592 | 27/0 | 27/3 | Telangana | 1.179 | 4 | 4 | 4 | 0 | 0 | 27/0, 27/3, 27/1, 27/2 | 27/0, 27/3, 27/1, 27/2 | 27/0, 27/3, 27/1, 27/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 593 | 27/3 | 28/0 | Telangana | 2.68 | 7 | 7 | 7 | 0 | 0 | 27/3, 28/0, 27/4, 27/5, 27/6, 27/7, 27/8 | 27/3, 28/0, 27/4, 27/5, 27/6, 27/7, 27/8 | 27/3, 28/0, 27/4, 27/5, 27/6, 27/7, 27/8 |  |  | PARTIAL_PARSE | Unparsed tokens: 9&28/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 594 | 7/0 | 8/0 | Karnataka | 0.226 | 2 | 2 | 2 | 0 | 0 | 7/0, 8/0 | 7/0, 8/0 | 7/0, 8/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 595 | Gantry | 1/0 | Karnataka | 0.09997 | 2 | 1 | 1 | 1 | 1 | GANTRY, 1/0 | 1/0 | 1/0 | GANTRY | GANTRY | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 596 | 8/2 | 8/3 | Karnataka | 0.406 | 2 | 2 | 2 | 0 | 0 | 8/2, 8/3 | 8/2, 8/3 | 8/2, 8/3 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 597 | 28/0 | 29/0 | Telangana | 0.786 | 2 | 2 | 2 | 0 | 0 | 28/0, 29/0 | 28/0, 29/0 | 28/0, 29/0 |  |  | PARTIAL_PARSE | Unparsed tokens: 1&29/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 598 | 1/0 | 1A/0 | Karnataka | 0.235 | 2 | 2 | 2 | 0 | 0 | 1/0, 1A/0 | 1/0, 1A/0 | 1/0, 1A/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 599 | 1A/0 | 1B/0 | Karnataka | 0.3972 | 2 | 2 | 2 | 0 | 0 | 1A/0, 1B/0 | 1A/0, 1B/0 | 1A/0, 1B/0 |  |  | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 600 | 4/12 | 5/0 | Karnataka | 4.964 | 13 | 13 | 13 | 0 | 0 | 4/12, 5/0, 4/13, 4/14, 4/15, 4/16, 4/17, 4/18, 4/19, 4/20, 4/21, 4/22, 4/23 | 4/12, 5/0, 4/13, 4/14, 4/15, 4/16, 4/17, 4/18, 4/19, 4/20, 4/21, 4/22, 4/23 | 4/12, 5/0, 4/13, 4/14, 4/15, 4/16, 4/17, 4/18, 4/19, 4/20, 4/21, 4/22, 4/23 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 601 | 8/0 | 8/1 | Karnataka | 0.414 | 2 | 2 | 2 | 0 | 0 | 8/0, 8/1 | 8/0, 8/1 | 8/0, 8/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 602 | 8/1 | 8/2 | Karnataka | 0.272 | 2 | 2 | 2 | 0 | 0 | 8/1, 8/2 | 8/1, 8/2 | 8/1, 8/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 603 | 38/0 | 39/0 | Telangana | 3.036 | 8 | 8 | 8 | 0 | 0 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/7 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/7 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/7 |  |  | PARTIAL_PARSE | Unparsed tokens: .6, &38/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 604 | 1C/0 | 2/0 | Karnataka | 0.31 | 2 | 2 | 2 | 0 | 0 | 1C/0, 2/0 | 1C/0, 2/0 | 1C/0, 2/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 605 | 5/0 | 6/0 | Karnataka | 0.182 | 2 | 2 | 2 | 0 | 0 | 5/0, 6/0 | 5/0, 6/0 | 5/0, 6/0 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 606 | 4/0 | 4/12 | Karnataka | 4.968 | 13 | 13 | 13 | 0 | 0 | 4/0, 4/12, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10, 4/11 | 4/0, 4/12, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10, 4/11 | 4/0, 4/12, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10, 4/11 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 607 | 3/0 | 4/0 | Karnataka | 1.681 | 5 | 5 | 5 | 0 | 0 | 3/0, 4/0, 3/1, 3/2, 3/3 | 3/0, 4/0, 3/1, 3/2, 3/3 | 3/0, 4/0, 3/1, 3/2, 3/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 608 | 37/0 | 38/0 | Telangana | 2.779 | 8 | 8 | 8 | 0 | 0 | 37/0, 38/0, 37/1, 37/2, 37/3, 37/4, 37/5, 37/6 | 37/0, 38/0, 37/1, 37/2, 37/3, 37/4, 37/5, 37/6 | 37/0, 38/0, 37/1, 37/2, 37/3, 37/4, 37/5, 37/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 609 | 2/0 | 3/0 | Karnataka | 2.365 | 6 | 6 | 6 | 0 | 0 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4 |  |  | PARTIAL_PARSE | Unparsed tokens: 5&3/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 610 | 1B/0 | 1C/0 | Karnataka | 1.686 | 5 | 5 | 5 | 0 | 0 | 1B/0, 1C/0, 1B/1, 1B/2, 1B/3 | 1B/0, 1C/0, 1B/1, 1B/2, 1B/3 | 1B/0, 1C/0, 1B/1, 1B/2, 1B/3 |  |  | PARTIAL_PARSE | Unparsed tokens: &1C/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 611 | 39/0 | 40/0 | Telangana | 4.21 | 11 | 11 | 11 | 0 | 0 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 612 | 36/0 | 37/0 | Telangana | 3.608 | 9 | 9 | 9 | 0 | 0 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7 |  |  | PARTIAL_PARSE | Unparsed tokens: 8&37/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 613 | 42/0 | 43/0 | Telangana | 3.949 | 10 | 10 | 10 | 0 | 0 | 42/0, 43/0, 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 42/7, 42/8 | 42/0, 43/0, 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 42/7, 42/8 | 42/0, 43/0, 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 42/7, 42/8 |  |  | PARTIAL_PARSE | Unparsed tokens: 9&43/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 614 | 43/0 | 43A/0 | Telangana | 2.262 | 6 | 6 | 6 | 0 | 0 | 43/0, 43A/0, 43/1, 43/2, 43/3, 43/4 | 43/0, 43A/0, 43/1, 43/2, 43/3, 43/4 | 43/0, 43A/0, 43/1, 43/2, 43/3, 43/4 |  |  | PARTIAL_PARSE | Unparsed tokens: 5&43/0 | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 615 | 34/2 | 35/0 | Telangana | 0.248 | 2 | 2 | 2 | 0 | 0 | 34/2, 35/0 | 34/2, 35/0 | 34/2, 35/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 616 | 35/0 | 36/0 | Telangana | 1.858 | 5 | 5 | 5 | 0 | 0 | 35/0, 36/0, 35/1, 35/2, 35/3 | 35/0, 36/0, 35/1, 35/2, 35/3 | 35/0, 36/0, 35/1, 35/2, 35/3 |  |  | PARTIAL_PARSE | Unparsed tokens: 4&36/0 | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 617 | 34/1 | 34/2 | Telangana | 0.43 | 2 | 2 | 1 | 0 | 1 | 34/1, 34/2 | 34/1, 34/2 | 34/2 |  | 34/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 618 | 33/0 | 34/0 | Telangana | 0.966 | 3 | 3 | 2 | 0 | 1 | 33/0, 34/0, 33/1 | 33/0, 34/0, 33/1 | 33/0, 33/1 |  | 34/0 | PARTIAL_PARSE | Unparsed tokens: 2&33/0 | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 619 | 43A/0 | 43A/1 | Telangana | 0.485 | 2 | 2 | 2 | 0 | 0 | 43A/0, 43A/1 | 43A/0, 43A/1 | 43A/0, 43A/1 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 620 | 43A/1 | 43B/0 | Telangana | 1.814 | 5 | 5 | 2 | 0 | 3 | 43A/1, 43B/0, 43A/2, 43A/3, 43A/4 | 43A/1, 43B/0, 43A/2, 43A/3, 43A/4 | 43A/1, 43A/2 |  | 43B/0, 43A/3, 43A/4 | PARTIAL_PARSE | Unparsed tokens: 5&43B/0 | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 621 | 34/0 | 34/1 | Telangana | 0.248 | 2 | 2 | 0 | 0 | 2 | 34/0, 34/1 | 34/0, 34/1 |  |  | 34/0, 34/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 622 | 40/0 | 41/0 | Telangana | 0.713 | 3 | 3 | 1 | 0 | 2 | 40/0, 41/0, 40/1 | 40/0, 41/0, 40/1 | 40/0 |  | 41/0, 40/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 623 | 41/0 | 42/0 | Telangana | 0.762 | 2 | 2 | 1 | 0 | 1 | 41/0, 42/0 | 41/0, 42/0 | 42/0 |  | 41/0 | PARTIAL_PARSE | Unparsed tokens: 1&42/0 | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 624 | 43B/0 | 44/0 | Telangana | 0.45969 | 2 | 2 | 0 | 0 | 2 | 43B/0, 44/0 | 43B/0, 44/0 |  |  | 43B/0, 44/0 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 421 | TA 421 | ta421 |  | TA 421 - DPR - 2026-05-26.xlsx | Stringing Compiled | 640 |  | Total | Total | 43.743 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 641 | 1/0 | 2/0 | 1/0 - 2/0 | 0.10819 | 2 | 0 | 0 | 2 | 2 | 1/0, 2/0 |  |  | 1/0, 2/0 | 1/0, 2/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 642 | 2/0 | 3/0 | 2/0 - 3/0 | 0.21627 | 2 | 0 | 0 | 2 | 2 | 2/0, 3/0 |  |  | 2/0, 3/0 | 2/0, 3/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 643 | 3/0 | 4/0 | 3/0 - 4/0 | 1.4383 | 5 | 0 | 0 | 5 | 5 | 3/0, 4/0, 3/1, 3/2, 3/3 |  |  | 3/0, 4/0, 3/1, 3/2, 3/3 | 3/0, 4/0, 3/1, 3/2, 3/3 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 644 | 4/0 | 5/0 | 4/0 - 5/0 | 0.56194 | 3 | 0 | 0 | 3 | 3 | 4/0, 5/0, 4/1 |  |  | 4/0, 5/0, 4/1 | 4/0, 5/0, 4/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 645 | 5/0 | 5A/0 | 5/0 - 5A/0 | 0.7557 | 3 | 0 | 0 | 3 | 3 | 5/0, 5A/0, 5/1 |  |  | 5/0, 5A/0, 5/1 | 5/0, 5A/0, 5/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 646 | 5A/0 | 5B/0 | 5A/0 - 5B/0 | 0.23364 | 2 | 0 | 0 | 2 | 2 | 5A/0, 5B/0 |  |  | 5A/0, 5B/0 | 5A/0, 5B/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 647 | 5B/0 | 5B/1 | 5B/0 - 5B/1 | 0.24266 | 2 | 0 | 0 | 2 | 2 | 5B/0, 5B/1 |  |  | 5B/0, 5B/1 | 5B/0, 5B/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 648 | 5B/1 | 5C/0 | 5B/1 - 5C/0 | 0.33967 | 2 | 0 | 0 | 2 | 2 | 5B/1, 5C/0 |  |  | 5B/1, 5C/0 | 5B/1, 5C/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 649 | 5C/0 | 5D/0 | 5C/0 - 5D/0 | 0.19617 | 2 | 0 | 0 | 2 | 2 | 5C/0, 5D/0 |  |  | 5C/0, 5D/0 | 5C/0, 5D/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 650 | 5D/0 | 5E/0 | 5D/0 - 5E/0 | 0.20193 | 2 | 0 | 0 | 2 | 2 | 5D/0, 5E/0 |  |  | 5D/0, 5E/0 | 5D/0, 5E/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 651 | 5E/0 | 5F/0 | 5E/0 - 5F/0 | 0.47821 | 2 | 0 | 0 | 2 | 2 | 5E/0, 5F/0 |  |  | 5E/0, 5F/0 | 5E/0, 5F/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 652 | 5F/0 | 5G/0 | 5F/0 - 5G/0 | 0.21564 | 2 | 0 | 0 | 2 | 2 | 5F/0, 5G/0 |  |  | 5F/0, 5G/0 | 5F/0, 5G/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 653 | 5G/0 | 5H/0 | 5G/0 - 5H/0 | 2.4337 | 6 | 0 | 0 | 6 | 6 | 5G/0, 5H/0, 5G/1, 5G/2, 5G/3, 5G/4 |  |  | 5G/0, 5H/0, 5G/1, 5G/2, 5G/3, 5G/4 | 5G/0, 5H/0, 5G/1, 5G/2, 5G/3, 5G/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 654 | 5H/0 | 5I/0 | 5H/0 - 5I/0 | 0.75732 | 3 | 0 | 0 | 3 | 3 | 5H/0, 5I/0, 5H/1 |  |  | 5H/0, 5I/0, 5H/1 | 5H/0, 5I/0, 5H/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 655 | 5I/0 | 6/0 | 5I/0 - 6/0 | 0.38857 | 2 | 0 | 0 | 2 | 2 | 5I/0, 6/0 |  |  | 5I/0, 6/0 | 5I/0, 6/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 656 | 6/0 | 7/0 | 6/0 - 7/0 | 0.23381 | 2 | 0 | 0 | 2 | 2 | 6/0, 7/0 |  |  | 6/0, 7/0 | 6/0, 7/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 657 | 7/0 | 8/0 | 7/0 - 8/0 | 1.1565 | 4 | 1 | 0 | 3 | 4 | 7/0, 8/0, 7/1, 7/2 | 8/0 |  | 7/0, 7/1, 7/2 | 7/0, 8/0, 7/1, 7/2 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 658 | 8/0 | 8/3 | 8/0 - 8/3 | 1.0966 | 4 | 4 | 0 | 0 | 4 | 8/0, 8/3, 8/1, 8/2 | 8/0, 8/3, 8/1, 8/2 |  |  | 8/0, 8/3, 8/1, 8/2 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 659 | 8/3 | 9/0 | 8/3 - 9/0 | 0.34654 | 2 | 1 | 0 | 1 | 2 | 8/3, 9/0 | 8/3 |  | 9/0 | 8/3, 9/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 660 | 9/0 | 10/0 | 9/0 - 10/0 | 0.19543 | 2 | 0 | 0 | 2 | 2 | 9/0, 10/0 |  |  | 9/0, 10/0 | 9/0, 10/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 661 | 10/0 | 10/1 | 10/0 - 10/1 | 0.32743 | 2 | 1 | 0 | 1 | 2 | 10/0, 10/1 | 10/1 |  | 10/0 | 10/0, 10/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 662 | 10/1 | 11/0 | 10/1 - 11/0 | 1.6387 | 5 | 3 | 1 | 2 | 4 | 10/1, 11/0, 10/2, 10/3, 10/4 | 10/1, 11/0, 10/2 | 11/0 | 10/3, 10/4 | 10/1, 10/2, 10/3, 10/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 663 | 11/0 | 12/0 | Bhinder | 2.7329 | 8 | 8 | 8 | 0 | 0 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 664 | 12/0 | 13/0 | Bhinder | 2.3724 | 7 | 7 | 7 | 0 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 665 | 13/0 | 14/0 | Bhinder | 2.7191 | 8 | 7 | 3 | 1 | 5 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6 | 13/0, 14/0, 13/1, 13/3, 13/4, 13/5, 13/6 | 13/0, 14/0, 13/1 | 13/2 | 13/2, 13/3, 13/4, 13/5, 13/6 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 666 | 14/0 | 15/0 | Bhinder | 3.2194 | 9 | 9 | 9 | 0 | 0 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 667 | 15/0 | 16/0 | Bhinder | 3.2297 | 9 | 9 | 9 | 0 | 0 | 15/0, 16/0, 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7 | 15/0, 16/0, 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7 | 15/0, 16/0, 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 668 | 16/0 | 16/3 | Bhinder | 1.246 | 4 | 4 | 4 | 0 | 0 | 16/0, 16/3, 16/1, 16/2 | 16/0, 16/3, 16/1, 16/2 | 16/0, 16/3, 16/1, 16/2 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 669 | 16/3 | 17/0 | Bhinder | 1.4666 | 5 | 5 | 5 | 0 | 0 | 16/3, 17/0, 16/4, 16/5, 16/6 | 16/3, 17/0, 16/4, 16/5, 16/6 | 16/3, 17/0, 16/4, 16/5, 16/6 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 670 | 17/0 | 17/4 | Bhinder | 1.647 | 5 | 5 | 5 | 0 | 0 | 17/0, 17/4, 17/1, 17/2, 17/3 | 17/0, 17/4, 17/1, 17/2, 17/3 | 17/0, 17/4, 17/1, 17/2, 17/3 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 671 | 17/4 | 18/0 | Bhinder | 2.3042 | 7 | 7 | 7 | 0 | 0 | 17/4, 18/0, 17/5, 17/6, 17/7, 17/8, 17/9 | 17/4, 18/0, 17/5, 17/6, 17/7, 17/8, 17/9 | 17/4, 18/0, 17/5, 17/6, 17/7, 17/8, 17/9 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 672 | 18/0 | 18/1 | Bhinder | 0.503 | 2 | 2 | 2 | 0 | 0 | 18/0, 18/1 | 18/0, 18/1 | 18/0, 18/1 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 673 | 18/1 | 19/0 | Bhinder | 3.0252 | 9 | 9 | 9 | 0 | 0 | 18/1, 19/0, 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8 | 18/1, 19/0, 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8 | 18/1, 19/0, 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8 |  |  | OK |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 674 | 19/0 | 20/0 | Bhinder | 1.5736 | 5 | 5 | 2 | 0 | 3 | 19/0, 20/0, 8/1, 8/2, 8/3 | 19/0, 20/0, 8/1, 8/2, 8/3 | 19/0, 20/0 |  | 8/1, 8/2, 8/3 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 675 | 20/0 | 21/0 | Bhinder | 0.46068 | 3 | 2 | 2 | 1 | 1 | 20/0, 21/0, 9/0 | 20/0, 21/0 | 20/0, 21/0 | 9/0 | 9/0 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 676 | 21/0 | 21/3 | Bhinder | 1.199 | 3 | 2 | 2 | 1 | 1 | 21/0, 21/3, 10/0 | 21/0, 21/3 | 21/0, 21/3 | 10/0 | 10/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 677 | 21/3 | 22/0 | Bhinder | 1.1954 | 3 | 3 | 2 | 0 | 1 | 21/3, 22/0, 10/1 | 21/3, 22/0, 10/1 | 21/3, 22/0 |  | 10/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 678 | 22/0 | 23/0 | Bhinder | 1.9725 | 6 | 4 | 3 | 2 | 3 | 22/0, 23/0, 10/2, 10/3, 10/4, 11/0 | 22/0, 23/0, 10/2, 11/0 | 22/0, 23/0, 11/0 | 10/3, 10/4 | 10/2, 10/3, 10/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 679 | 23/0 | 24/0 | Bhinder | 3.09 | 9 | 9 | 9 | 0 | 0 | 23/0, 24/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 | 23/0, 24/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 | 23/0, 24/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 |  |  | OK |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 680 | 24/0 | 24/1 | 24/0 - 24/1 | 0.432 | 8 | 8 | 7 | 0 | 1 | 24/0, 24/1, 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 | 24/0, 24/1, 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 | 24/0, 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 |  | 24/1 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 681 | 24/1 | 24/2. | 24/1 - 24/2. | 0.567 | 9 | 7 | 2 | 2 | 7 | 24/1, 24/2., 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 14/0 | 24/1, 13/1, 13/3, 13/4, 13/5, 13/6, 14/0 | 13/1, 14/0 | 24/2., 13/2 | 24/1, 24/2., 13/2, 13/3, 13/4, 13/5, 13/6 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 682 | 24/2. | 25/0 | 24/2. - 25/0 | 0.54355 | 10 | 8 | 8 | 2 | 2 | 24/2., 25/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 15/0 | 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 15/0 | 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 15/0 | 24/2., 25/0 | 24/2., 25/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 683 | 25/0 | 26/0 | 25/0 - 26/0 | 1.9069 | 6 | 4 | 0 | 2 | 6 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 | 26/0, 25/1, 25/2, 25/4 |  | 25/0, 25/3 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 684 | 26/0 | 27/0 | 26/0 - 27/0 | 4.3402 | 12 | 10 | 0 | 2 | 12 | 26/0, 27/0, 26/1, 26/2, 26/3, 26/4, 26/5, 26/6, 26/7, 26/8, 26/9, 26/10 | 26/0, 26/1, 26/2, 26/3, 26/4, 26/5, 26/6, 26/7, 26/8, 26/10 |  | 27/0, 26/9 | 26/0, 27/0, 26/1, 26/2, 26/3, 26/4, 26/5, 26/6, 26/7, 26/8, 26/9, 26/10 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 685 | 27/0 | 28/0 | 27/0 - 28/0 | 0.79605 | 3 | 2 | 0 | 1 | 3 | 27/0, 28/0, 27/1 | 28/0, 27/1 |  | 27/0 | 27/0, 28/0, 27/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 686 | 28/0 | 28/1 | 28/0 - 28/1 | 0.404 | 2 | 1 | 0 | 1 | 2 | 28/0, 28/1 | 28/0 |  | 28/1 | 28/0, 28/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 687 | 28/1 | 29/0 | 28/1 - 29/0 | 0.26181 | 2 | 1 | 0 | 1 | 2 | 28/1, 29/0 | 29/0 |  | 28/1 | 28/1, 29/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 688 | 29/0 | 30/0 | 29/0 - 30/0 | 1.1448 | 4 | 4 | 0 | 0 | 4 | 29/0, 30/0, 29/1, 29/2 | 29/0, 30/0, 29/1, 29/2 |  |  | 29/0, 30/0, 29/1, 29/2 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 689 | 30/0 | 31/0 | 30/0 - 31/0 | 2.2538 | 7 | 7 | 0 | 0 | 7 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 |  |  | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 | OK |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 690 | 31/0 | 31/2 | 31/0 - 31/2 | 0.8 | 3 | 1 | 0 | 2 | 3 | 31/0, 31/2, 31/1 | 31/0 |  | 31/2, 31/1 | 31/0, 31/2, 31/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 691 | 31/2 | 32/0 | 31/2 - 32/0 | 0.34762 | 2 | 0 | 0 | 2 | 2 | 31/2, 32/0 |  |  | 31/2, 32/0 | 31/2, 32/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 692 | 32/0 | 32/2 | 32/0 - 32/2 | 0.839 | 3 | 1 | 0 | 2 | 3 | 32/0, 32/2, 32/1 | 32/1 |  | 32/0, 32/2 | 32/0, 32/2, 32/1 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 504 | TA 504 | ta504 |  | TA 504 - DPR - 2026-05-27.xlsx | Stringing Compiled | 693 | 32/2 | 33/0 | 32/2 - 33/0 | 0.34361 | 2 | 1 | 0 | 1 | 2 | 32/2, 33/0 | 33/0 |  | 32/2 | 32/2, 33/0 | OK |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 694 | 100/0 | 101/0 | 100/0 To 101/0 | 0.419 | 2 | 2 | 2 | 0 | 0 | 100/0, 101/0 | 100/0, 101/0 | 100/0, 101/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 695 | 101/0 | 102/0 | 101/0 To 102/0 | 3.47 | 2 | 2 | 2 | 0 | 0 | 101/0, 102/0 | 101/0, 102/0 | 101/0, 102/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 696 | 102/0 | 103/0 | 102/0 To 103/0 | 0.461 | 2 | 2 | 2 | 0 | 0 | 102/0, 103/0 | 102/0, 103/0 | 102/0, 103/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 697 | 103/0 | 103/5A | 103/0 To 103/5A | 2.2 | 2 | 2 | 2 | 0 | 0 | 103/0, 103/5A | 103/0, 103/5A | 103/0, 103/5A |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 698 | 103/5A | 103/6A | 103/5A To 103/6A | 0.567 | 2 | 2 | 2 | 0 | 0 | 103/5A, 103/6A | 103/5A, 103/6A | 103/5A, 103/6A |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 699 | 103/6A | 104/0 | 103/6A To 104/0 | 1.403 | 2 | 2 | 2 | 0 | 0 | 103/6A, 104/0 | 103/6A, 104/0 | 103/6A, 104/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 700 | 104/0 | 105/0 | 104/0 To 105/0 | 0.967 | 2 | 2 | 2 | 0 | 0 | 104/0, 105/0 | 104/0, 105/0 | 104/0, 105/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 701 | 111/0 | 112/0 | 111/0 To 112/0 | 1.954 | 2 | 2 | 2 | 0 | 0 | 111/0, 112/0 | 111/0, 112/0 | 111/0, 112/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 702 | 113/0 | 114/0 | 113/0 To 114/0 | 2.565 | 2 | 2 | 2 | 0 | 0 | 113/0, 114/0 | 113/0, 114/0 | 113/0, 114/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 703 | 114/0 | 115/0 | 114/0 To 115/0 | 4.304 | 2 | 2 | 2 | 0 | 0 | 114/0, 115/0 | 114/0, 115/0 | 114/0, 115/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 704 | 110A/0 | 111/0 | 110A/0 To 111/0 | 1.23 | 2 | 2 | 2 | 0 | 0 | 110A/0, 111/0 | 110A/0, 111/0 | 110A/0, 111/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 705 | 110/0 | 110A/0 | 110/0 To 110A/0 | 3.86 | 2 | 2 | 2 | 0 | 0 | 110/0, 110A/0 | 110/0, 110A/0 | 110/0, 110A/0 |  |  | EMPTY |  | FALSE | TRUE | TRUE | TRUE | READY_TO_STRING
TA 505 | TA 505 | ta505 |  | TA 505 - DPR - 2026-05-19.xlsx | Stringing Compiled | 925 |  | Total | Total | 0.0234 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 926 | 1/0 | 2/0 | Sirohi | 4.4241 | 2 | 2 | 2 | 0 | 0 | 1/0, 2/0 | 1/0, 2/0 | 1/0, 2/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 927 | 5/0 | 6/0 | Sirohi | 4.9493 | 2 | 2 | 2 | 0 | 0 | 5/0, 6/0 | 5/0, 6/0 | 5/0, 6/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 928 | 48/0 | 50/0 | Sirohi | 0.68847 | 2 | 2 | 2 | 0 | 0 | 48/0, 50/0 | 48/0, 50/0 | 48/0, 50/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 929 | 50/0 | 51/0 | Sirohi | 1.1601 | 2 | 2 | 2 | 0 | 0 | 50/0, 51/0 | 50/0, 51/0 | 50/0, 51/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 930 | 2/0 | 2A/0 | Sirohi | 3.3186 | 2 | 2 | 2 | 0 | 0 | 2/0, 2A/0 | 2/0, 2A/0 | 2/0, 2A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 931 | 51/0 | 51A/0 | Sirohi | 1.2449 | 2 | 2 | 2 | 0 | 0 | 51/0, 51A/0 | 51/0, 51A/0 | 51/0, 51A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 932 | 51A/0 | 51C/0 | Sirohi | 1.2348 | 2 | 2 | 2 | 0 | 0 | 51A/0, 51C/0 | 51A/0, 51C/0 | 51A/0, 51C/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 933 | 51C/0 | 52/0 | Sirohi | 1.9682 | 2 | 2 | 2 | 0 | 0 | 51C/0, 52/0 | 51C/0, 52/0 | 51C/0, 52/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 934 | 52/0 | 53/0 | Sirohi | 0.99208 | 2 | 2 | 2 | 0 | 0 | 52/0, 53/0 | 52/0, 53/0 | 52/0, 53/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 935 | 4/0 | 5/0 | Sirohi | 2.809 | 2 | 2 | 2 | 0 | 0 | 4/0, 5/0 | 4/0, 5/0 | 4/0, 5/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 936 | 18/0 | 19/0 | Sirohi | 3.934 | 2 | 2 | 2 | 0 | 0 | 18/0, 19/0 | 18/0, 19/0 | 18/0, 19/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 937 | 68/0 | 68/1 | Sirohi | 0.504 | 2 | 2 | 2 | 0 | 0 | 68/0, 68/1 | 68/0, 68/1 | 68/0, 68/1 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 938 | 67/0 | 68/0 | Sirohi | 0.17673 | 2 | 2 | 2 | 0 | 0 | 67/0, 68/0 | 67/0, 68/0 | 67/0, 68/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 939 | 6/0 | 9/0 | Sirohi | 1.2107 | 2 | 2 | 2 | 0 | 0 | 6/0, 9/0 | 6/0, 9/0 | 6/0, 9/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 940 | 66/0 | 67/0 | Sirohi | 0.74377 | 2 | 2 | 2 | 0 | 0 | 66/0, 67/0 | 66/0, 67/0 | 66/0, 67/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 941 | 10/0 | 11/0 | Sirohi | 1.2563 | 2 | 2 | 2 | 0 | 0 | 10/0, 11/0 | 10/0, 11/0 | 10/0, 11/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 942 | 11/0 | 11/3 | Sirohi | 1.114 | 2 | 2 | 2 | 0 | 0 | 11/0, 11/3 | 11/0, 11/3 | 11/0, 11/3 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 943 | 11/3 | 12/0 | Sirohi | 0.53015 | 2 | 2 | 2 | 0 | 0 | 11/3, 12/0 | 11/3, 12/0 | 11/3, 12/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 944 | 65A/3 | 66/0 | Sirohi | 0.24426 | 2 | 2 | 2 | 0 | 0 | 65A/3, 66/0 | 65A/3, 66/0 | 65A/3, 66/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 945 | 213/0 | 214/0 | Udaipur | 2.3513 | 2 | 2 | 2 | 0 | 0 | 213/0, 214/0 | 213/0, 214/0 | 213/0, 214/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 946 | 17/0 | 18/0 | Sirohi | 2.733 | 2 | 2 | 2 | 0 | 0 | 17/0, 18/0 | 17/0, 18/0 | 17/0, 18/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 947 | 9/0 | 10/0 | Sirohi | 0.27218 | 2 | 2 | 2 | 0 | 0 | 9/0, 10/0 | 9/0, 10/0 | 9/0, 10/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 948 | 139/0 | 139A/0 | Gogunda | 0.65583 | 2 | 2 | 2 | 0 | 0 | 139/0, 139A/0 | 139/0, 139A/0 | 139/0, 139A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 949 | 139A/0 | 140/0 | Gogunda | 0.24266 | 2 | 2 | 2 | 0 | 0 | 139A/0, 140/0 | 139A/0, 140/0 | 139A/0, 140/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 950 | 212/0 | 213/0 | Udaipur | 2.3931 | 2 | 2 | 2 | 0 | 0 | 212/0, 213/0 | 212/0, 213/0 | 212/0, 213/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 951 | 12/0 | 13/0 | Sirohi | 3.3153 | 2 | 2 | 2 | 0 | 0 | 12/0, 13/0 | 12/0, 13/0 | 12/0, 13/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 952 | 65/0 | 65A/0 | Sirohi | 0.19507 | 2 | 2 | 2 | 0 | 0 | 65/0, 65A/0 | 65/0, 65A/0 | 65/0, 65A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 953 | 65A/0 | 65A/3 | Sirohi | 0.919 | 2 | 2 | 2 | 0 | 0 | 65A/0, 65A/3 | 65A/0, 65A/3 | 65A/0, 65A/3 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 954 | 15/0 | 16/0 | Sirohi | 1.6749 | 2 | 2 | 2 | 0 | 0 | 15/0, 16/0 | 15/0, 16/0 | 15/0, 16/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 955 | 64/0 | 64A/0 | Sirohi | 0.47196 | 2 | 2 | 2 | 0 | 0 | 64/0, 64A/0 | 64/0, 64A/0 | 64/0, 64A/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 956 | 211/0 | 212/0 | Udaipur | 3.2545 | 2 | 2 | 2 | 0 | 0 | 211/0, 212/0 | 211/0, 212/0 | 211/0, 212/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 957 | 63/0 | 64/0 | Sirohi | 0.77897 | 2 | 2 | 2 | 0 | 0 | 63/0, 64/0 | 63/0, 64/0 | 63/0, 64/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 958 | 13/0 | 14/0 | Sirohi | 2.4545 | 2 | 2 | 2 | 0 | 0 | 13/0, 14/0 | 13/0, 14/0 | 13/0, 14/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 959 | 64A/0 | 65/0 | Sirohi | 1.6591 | 2 | 2 | 2 | 0 | 0 | 64A/0, 65/0 | 64A/0, 65/0 | 64A/0, 65/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 960 | 38/0 | 39/0 | Sirohi | 0.76252 | 2 | 2 | 2 | 0 | 0 | 38/0, 39/0 | 38/0, 39/0 | 38/0, 39/0 |  |  | EMPTY |  | TRUE | TRUE | TRUE | FALSE | ALREADY_STRUNG
TA 506 | TA 506 | ta506 |  | TA 506 - DPR - 2026-05-27.xlsx | Stringing | 1155 |  | Total | Total | 0.056637 | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1156 | 57/6 | 58/0 | 57/6 - 58/0 | 3.141 | 2 | 2 | 0 | 0 | 2 | 57/6, 58/0 | 57/6, 58/0 |  |  | 57/6, 58/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1157 | 57/0 | 57/6 | 57/0 - 57/6 | 2.344 | 2 | 2 | 0 | 0 | 2 | 57/0, 57/6 | 57/0, 57/6 |  |  | 57/0, 57/6 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1158 | 56/0 | 57/0 | 56/0 - 57/0 | 4.127 | 2 | 2 | 0 | 0 | 2 | 56/0, 57/0 | 56/0, 57/0 |  |  | 56/0, 57/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1159 | 55/0 | 56/0 | 55/0 - 56/0 | 4.9 | 2 | 2 | 0 | 0 | 2 | 55/0, 56/0 | 55/0, 56/0 |  |  | 55/0, 56/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1160 | 53/0 | 55/0 | 53/0 - 55/0 | 2.013 | 2 | 2 | 0 | 0 | 2 | 53/0, 55/0 | 53/0, 55/0 |  |  | 53/0, 55/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1161 | 52/0 | 53/0 | 52/0 - 53/0 | 2.364 | 2 | 2 | 0 | 0 | 2 | 52/0, 53/0 | 52/0, 53/0 |  |  | 52/0, 53/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1162 | 51/0 | 52/0 | 51/0 - 52/0 | 4.403 | 2 | 2 | 0 | 0 | 2 | 51/0, 52/0 | 51/0, 52/0 |  |  | 51/0, 52/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1163 | 50/0 | 51/0 | 50/0 - 51/0 | 1.971 | 2 | 2 | 0 | 0 | 2 | 50/0, 51/0 | 50/0, 51/0 |  |  | 50/0, 51/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1164 | 72/7 | 73/0 | 72/7 - 73/0 | 0.49623 | 2 | 2 | 0 | 0 | 2 | 72/7, 73/0 | 72/7, 73/0 |  |  | 72/7, 73/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1165 | 58/0 | 58/7 | 58/0 - 58/7 | 2.797 | 2 | 2 | 0 | 0 | 2 | 58/0, 58/7 | 58/0, 58/7 |  |  | 58/0, 58/7 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1166 | 72/0 | 72/7 | 72/0 - 72/7 | 2.589 | 2 | 2 | 0 | 0 | 2 | 72/0, 72/7 | 72/0, 72/7 |  |  | 72/0, 72/7 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1167 | 67/1 | 68/0 | 67/1 - 68/0 | 0.42647 | 2 | 2 | 0 | 0 | 2 | 67/1, 68/0 | 67/1, 68/0 |  |  | 67/1, 68/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1168 | 68/0 | 69/0 | 68/0 - 69/0 | 2.855 | 2 | 2 | 0 | 0 | 2 | 68/0, 69/0 | 68/0, 69/0 |  |  | 68/0, 69/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1169 | 58/7 | 59/0 | 58/7 - 59/0 | 3.885 | 2 | 2 | 0 | 0 | 2 | 58/7, 59/0 | 58/7, 59/0 |  |  | 58/7, 59/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1170 | 71/0 | 72/0 | 71/0 - 72/0 | 2.092 | 2 | 2 | 0 | 0 | 2 | 71/0, 72/0 | 71/0, 72/0 |  |  | 71/0, 72/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1171 | 67/0 | 67/1 | 67/0 - 67/1 | 0.43755 | 2 | 2 | 0 | 0 | 2 | 67/0, 67/1 | 67/0, 67/1 |  |  | 67/0, 67/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1172 | 69/0 | 70/0 | 69/0 - 70/0 | 3.881 | 2 | 2 | 0 | 0 | 2 | 69/0, 70/0 | 69/0, 70/0 |  |  | 69/0, 70/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1173 | 41/0 | 42/0 | 41/0 - 42/0 | 4.981 | 2 | 2 | 0 | 0 | 2 | 41/0, 42/0 | 41/0, 42/0 |  |  | 41/0, 42/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1174 | 59/0 | 60/0 | 59/0 - 60/0 | 2.581 | 2 | 2 | 0 | 0 | 2 | 59/0, 60/0 | 59/0, 60/0 |  |  | 59/0, 60/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1175 | 42/0 | 43/0 | 42/0 - 43/0 | 0.489 | 2 | 2 | 0 | 0 | 2 | 42/0, 43/0 | 42/0, 43/0 |  |  | 42/0, 43/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1176 | 49/0 | 50/0 | 49/0 - 50/0 | 0.241 | 2 | 2 | 0 | 0 | 2 | 49/0, 50/0 | 49/0, 50/0 |  |  | 49/0, 50/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1177 | 48/0 | 49/0 | 48/0 - 49/0 | 1.162 | 2 | 2 | 0 | 0 | 2 | 48/0, 49/0 | 48/0, 49/0 |  |  | 48/0, 49/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1178 | 47/0 | 48/0 | 47/0 - 48/0 | 1.274 | 2 | 2 | 0 | 0 | 2 | 47/0, 48/0 | 47/0, 48/0 |  |  | 47/0, 48/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1179 | 37/2 | 38/0 | 37/2 - 38/0 | 2.71 | 2 | 2 | 0 | 0 | 2 | 37/2, 38/0 | 37/2, 38/0 |  |  | 37/2, 38/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1180 | 43/0 | 44/0 | 43/0 - 44/0 | 2.856 | 2 | 2 | 0 | 0 | 2 | 43/0, 44/0 | 43/0, 44/0 |  |  | 43/0, 44/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1181 | 61/0 | 62/0 | 61/0 - 62/0 | 1.028 | 2 | 2 | 0 | 0 | 2 | 61/0, 62/0 | 61/0, 62/0 |  |  | 61/0, 62/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1182 | 62/0 | 63/0 | 62/0 - 63/0 | 0.221 | 2 | 2 | 0 | 0 | 2 | 62/0, 63/0 | 62/0, 63/0 |  |  | 62/0, 63/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1183 | 38/0 | 38/9 | 38/0 - 38/9 | 3.215 | 2 | 2 | 0 | 0 | 2 | 38/0, 38/9 | 38/0, 38/9 |  |  | 38/0, 38/9 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1184 | 40/10 | 41/0 | 40/10 - 41/0 | 1.073 | 2 | 2 | 0 | 0 | 2 | 40/10, 41/0 | 40/10, 41/0 |  |  | 40/10, 41/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1185 | 63/0 | 64/0 | 63/0 - 64/0 | 2.879 | 2 | 2 | 0 | 0 | 2 | 63/0, 64/0 | 63/0, 64/0 |  |  | 63/0, 64/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1186 | 39/0 | 40/0 | 39/0 - 40/0 | 2.744 | 2 | 2 | 0 | 0 | 2 | 39/0, 40/0 | 39/0, 40/0 |  |  | 39/0, 40/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1187 | 40/5 | 40/10 | 40/5 - 40/10 | 1.897 | 2 | 2 | 0 | 0 | 2 | 40/5, 40/10 | 40/5, 40/10 |  |  | 40/5, 40/10 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1188 | 38/9 | 39/0 | 38/9 - 39/0 | 0.544 | 2 | 2 | 0 | 0 | 2 | 38/9, 39/0 | 38/9, 39/0 |  |  | 38/9, 39/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1189 | 40/0 | 40/2 | 40/0 - 40/2 | 0.652 | 2 | 2 | 0 | 0 | 2 | 40/0, 40/2 | 40/0, 40/2 |  |  | 40/0, 40/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1190 | 40/2 | 40/5 | 40/2 - 40/5 | 1.219 | 2 | 2 | 0 | 0 | 2 | 40/2, 40/5 | 40/2, 40/5 |  |  | 40/2, 40/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1191 | 66/0 | 67/0 | 66/0 - 67/0 | 2.028 | 2 | 2 | 0 | 0 | 2 | 66/0, 67/0 | 66/0, 67/0 |  |  | 66/0, 67/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1192 | 35/0 | 36/0 | 35/0 - 36/0 | 3.604 | 2 | 2 | 0 | 0 | 2 | 35/0, 36/0 | 35/0, 36/0 |  |  | 35/0, 36/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1193 | 46/0 | 47/0 | 46/0 - 47/0 | 1.728 | 2 | 2 | 0 | 0 | 2 | 46/0, 47/0 | 46/0, 47/0 |  |  | 46/0, 47/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1194 | 31/0 | 32/0 | 31/0 - 32/0 | 1.678 | 2 | 2 | 0 | 0 | 2 | 31/0, 32/0 | 31/0, 32/0 |  |  | 31/0, 32/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1195 | 44/0 | 45/0 | 44/0 - 45/0 | 2.459 | 2 | 2 | 0 | 0 | 2 | 44/0, 45/0 | 44/0, 45/0 |  |  | 44/0, 45/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1196 | Gantry | 1/0 | Gantry - 1/0 | 0.12293 | 2 | 1 | 0 | 1 | 2 | GANTRY, 1/0 | 1/0 |  | GANTRY | GANTRY, 1/0 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1197 | 65/0 | 66/0 | 65/0 - 66/0 | 2.966 | 2 | 2 | 0 | 0 | 2 | 65/0, 66/0 | 65/0, 66/0 |  |  | 65/0, 66/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1198 | 1/0 | 1A/0 | 1/0 - 1A/0 | 0.1 | 2 | 2 | 0 | 0 | 2 | 1/0, 1A/0 | 1/0, 1A/0 |  |  | 1/0, 1A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1199 | 1A/0 | 2/0 | 1A/0 - 2/0 | 3.187 | 2 | 2 | 0 | 0 | 2 | 1A/0, 2/0 | 1A/0, 2/0 |  |  | 1A/0, 2/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1200 | 64/0 | 65/0 | 64/0 - 65/0 | 4.079 | 2 | 2 | 0 | 0 | 2 | 64/0, 65/0 | 64/0, 65/0 |  |  | 64/0, 65/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1201 | 32/0 | 33/0 | 32/0 - 33/0 | 3.747 | 2 | 2 | 0 | 0 | 2 | 32/0, 33/0 | 32/0, 33/0 |  |  | 32/0, 33/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1202 | 33/0 | 34/0 | 33/0 - 34/0 | 3.338 | 2 | 2 | 0 | 0 | 2 | 33/0, 34/0 | 33/0, 34/0 |  |  | 33/0, 34/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1203 | 36/0 | 37/0 | 36/0 - 37/0 | 0.214 | 2 | 2 | 0 | 0 | 2 | 36/0, 37/0 | 36/0, 37/0 |  |  | 36/0, 37/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1204 | 60/0 | 61/0 | 60/0 - 61/0 | 0.206 | 2 | 2 | 0 | 0 | 2 | 60/0, 61/0 | 60/0, 61/0 |  |  | 60/0, 61/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1205 | 34/0 | 34/5 | 34/0 - 34/5 | 2.056 | 2 | 2 | 0 | 0 | 2 | 34/0, 34/5 | 34/0, 34/5 |  |  | 34/0, 34/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1206 | 34/5 | 35/0 | 34/5 - 35/0 | 0.705 | 2 | 2 | 0 | 0 | 2 | 34/5, 35/0 | 34/5, 35/0 |  |  | 34/5, 35/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1207 | 45/0 | 46/0 | 45/0 - 46/0 | 0.233 | 2 | 2 | 0 | 0 | 2 | 45/0, 46/0 | 45/0, 46/0 |  |  | 45/0, 46/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1208 | 37/0 | 37/1 | 37/0 - 37/1 | 0.371 | 2 | 2 | 0 | 0 | 2 | 37/0, 37/1 | 37/0, 37/1 |  |  | 37/0, 37/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1209 | 37/1 | 37/2 | 37/1 - 37/2 | 0.468 | 2 | 2 | 0 | 0 | 2 | 37/1, 37/2 | 37/1, 37/2 |  |  | 37/1, 37/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1210 | 25/0 | 26/0 | 25/0 - 26/0 | 4.965 | 2 | 2 | 0 | 0 | 2 | 25/0, 26/0 | 25/0, 26/0 |  |  | 25/0, 26/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1211 | 2/0 | 3/0 | 2/0 - 3/0 | 3.818 | 2 | 2 | 0 | 0 | 2 | 2/0, 3/0 | 2/0, 3/0 |  |  | 2/0, 3/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1212 | 30/0 | 31/0 | 30/0 - 31/0 | 1.325 | 2 | 2 | 0 | 0 | 2 | 30/0, 31/0 | 30/0, 31/0 |  |  | 30/0, 31/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1213 | 5/0 | 6/0 | 5/0 - 6/0 | 0.237 | 2 | 2 | 0 | 0 | 2 | 5/0, 6/0 | 5/0, 6/0 |  |  | 5/0, 6/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1214 | 4/0 | 5/0 | 4/0 - 5/0 | 1.867 | 2 | 2 | 0 | 0 | 2 | 4/0, 5/0 | 4/0, 5/0 |  |  | 4/0, 5/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1215 | 15/0 | 16/0 | 15/0 - 16/0 | 4.141 | 2 | 2 | 0 | 0 | 2 | 15/0, 16/0 | 15/0, 16/0 |  |  | 15/0, 16/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1216 | 29/0 | 30/0 | 29/0 - 30/0 | 4.45 | 2 | 2 | 0 | 0 | 2 | 29/0, 30/0 | 29/0, 30/0 |  |  | 29/0, 30/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1217 | 16/0 | 17/0 | 16/0 - 17/0 | 2.818 | 2 | 2 | 0 | 0 | 2 | 16/0, 17/0 | 16/0, 17/0 |  |  | 16/0, 17/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1218 | 24/0 | 25/0 | 24/0 - 25/0 | 2.69 | 2 | 2 | 0 | 0 | 2 | 24/0, 25/0 | 24/0, 25/0 |  |  | 24/0, 25/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1219 | 6/0 | 7/0 | 6/0 - 7/0 | 1.175 | 2 | 2 | 0 | 0 | 2 | 6/0, 7/0 | 6/0, 7/0 |  |  | 6/0, 7/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1220 | 28/0 | 29/0 | 28/0 - 29/0 | 3.914 | 2 | 2 | 0 | 0 | 2 | 28/0, 29/0 | 28/0, 29/0 |  |  | 28/0, 29/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1221 | 23/0 | 24/0 | 23/0 - 24/0 | 4.809 | 2 | 2 | 0 | 0 | 2 | 23/0, 24/0 | 23/0, 24/0 |  |  | 23/0, 24/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1222 | 27/1 | 28/0 | 27/1 - 28/0 | 1.752 | 2 | 2 | 0 | 0 | 2 | 27/1, 28/0 | 27/1, 28/0 |  |  | 27/1, 28/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1223 | 9/0 | 10/0 | 9/0 - 10/0 | 0.234 | 2 | 2 | 0 | 0 | 2 | 9/0, 10/0 | 9/0, 10/0 |  |  | 9/0, 10/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1224 | 17/0 | 18/0 | 17/0 - 18/0 | 2.508 | 2 | 2 | 0 | 0 | 2 | 17/0, 18/0 | 17/0, 18/0 |  |  | 17/0, 18/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1225 | 10/12 | 10/20 | 10/12 - 10/20 | 3.208 | 2 | 2 | 0 | 0 | 2 | 10/12, 10/20 | 10/12, 10/20 |  |  | 10/12, 10/20 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1226 | 70/0 | 71/0 | 70/0 - 71/0 | 0.258 | 2 | 2 | 0 | 0 | 2 | 70/0, 71/0 | 70/0, 71/0 |  |  | 70/0, 71/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1227 | 14/0 | 15/0 | 14/0 - 15/0 | 2.624 | 2 | 2 | 0 | 0 | 2 | 14/0, 15/0 | 14/0, 15/0 |  |  | 14/0, 15/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1228 | 3/0 | 4/0 | 3/0 - 4/0 | 0.227 | 2 | 2 | 0 | 0 | 2 | 3/0, 4/0 | 3/0, 4/0 |  |  | 3/0, 4/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 401 | TB 401 - PKG-G | tb401pkgg | PKG-G | TB 401 - DPR - 2025-12-25.xlsx | Stringing - PKG-G | 1229 | 22/0 | 23/0 | 22/0 - 23/0 | 4.035 | 2 | 2 | 0 | 0 | 2 | 22/0, 23/0 | 22/0, 23/0 |  |  | 22/0, 23/0 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1233 | Hydro GTY | Existing Tower-1 | Hydro GTY - Existing Tower-1 | 0.05879 | 2 | 0 | 0 | 2 | 2 | HYDROGTY, EXISTINGTOWER-1 |  |  | HYDROGTY, EXISTINGTOWER-1 | HYDROGTY, EXISTINGTOWER-1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1234 | Existing Tower-1 | Exting Tower-2 | Existing Tower-1 - Exting Tower-2 | 0.14912 | 2 | 0 | 0 | 2 | 2 | EXISTINGTOWER-1, EXTINGTOWER-2 |  |  | EXISTINGTOWER-1, EXTINGTOWER-2 | EXISTINGTOWER-1, EXTINGTOWER-2 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1235 | Exting Tower-2 | Exting Tower-3 | Exting Tower-2 - Exting Tower-3 | 0.1281 | 2 | 0 | 0 | 2 | 2 | EXTINGTOWER-2, EXTINGTOWER-3 |  |  | EXTINGTOWER-2, EXTINGTOWER-3 | EXTINGTOWER-2, EXTINGTOWER-3 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1236 | Exting Tower-3 | Exting Tower-4 | Exting Tower-3 - Exting Tower-4 | 0.25272 | 2 | 0 | 0 | 2 | 2 | EXTINGTOWER-3, EXTINGTOWER-4 |  |  | EXTINGTOWER-3, EXTINGTOWER-4 | EXTINGTOWER-3, EXTINGTOWER-4 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1237 | Exting Tower-4 | Exting Tower-5 | Exting Tower-4 - Exting Tower-5 | 0.14674 | 2 | 0 | 0 | 2 | 2 | EXTINGTOWER-4, EXTINGTOWER-5 |  |  | EXTINGTOWER-4, EXTINGTOWER-5 | EXTINGTOWER-4, EXTINGTOWER-5 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1238 | Exting Tower-5 | Exting Tapping Tower-6 | Exting Tower-5 - Exting Tapping Tower-6 | 0.19005 | 2 | 0 | 0 | 2 | 2 | EXTINGTOWER-5, EXTINGTAPPINGTOWER-6 |  |  | EXTINGTOWER-5, EXTINGTAPPINGTOWER-6 | EXTINGTOWER-5, EXTINGTAPPINGTOWER-6 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1239 | Exting Tapping Tower-6 | Exting Tower-7 | Exting Tapping Tower-6 - Exting Tower-7 | 0.08339 | 2 | 0 | 0 | 2 | 2 | EXTINGTAPPINGTOWER-6, EXTINGTOWER-7 |  |  | EXTINGTAPPINGTOWER-6, EXTINGTOWER-7 | EXTINGTAPPINGTOWER-6, EXTINGTOWER-7 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1240 | Exiting Tower-7 | SC-5 | Exiting Tower-7 - SC-5 | 0.12053 | 2 | 0 | 0 | 2 | 2 | EXITINGTOWER-7, SC-5 |  |  | EXITINGTOWER-7, SC-5 | EXITINGTOWER-7, SC-5 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1241 | SC-5 | SC-4 | SC-5 - SC-4 | 0.25951 | 2 | 0 | 0 | 2 | 2 | SC-5, SC-4 |  |  | SC-5, SC-4 | SC-5, SC-4 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1242 | SC-4 | Sc-3 | SC-4 - Sc-3 | 0.25661 | 2 | 0 | 0 | 2 | 2 | SC-4, SC-3 |  |  | SC-4, SC-3 | SC-4, SC-3 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1243 | Sc-3 | SC-2 | Sc-3 - SC-2 | 0.27795 | 2 | 0 | 0 | 2 | 2 | SC-3, SC-2 |  |  | SC-3, SC-2 | SC-3, SC-2 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1244 | SC-2 | SC-1 | SC-2 - SC-1 | 0.20225 | 2 | 0 | 0 | 2 | 2 | SC-2, SC-1 |  |  | SC-2, SC-1 | SC-2, SC-1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1245 | SC-1 | 1/0 | SC-1 - 1/0 | 0.06276 | 2 | 0 | 0 | 2 | 2 | SC-1, 1/0 |  |  | SC-1, 1/0 | SC-1, 1/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1246 | 1/0 | 2/0 | 1/0 - 2/0 | 0.27815 | 2 | 0 | 0 | 2 | 2 | 1/0, 2/0 |  |  | 1/0, 2/0 | 1/0, 2/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1247 | 2/0 | 2/1 | 2/0 - 2/1 | 0.23456 | 2 | 0 | 0 | 2 | 2 | 2/0, 2/1 |  |  | 2/0, 2/1 | 2/0, 2/1 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1248 | 2/1 | 3/0 | 2/1 - 3/0 | 0.24904 | 2 | 1 | 0 | 1 | 2 | 2/1, 3/0 | 3/0 |  | 2/1 | 2/1, 3/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1249 | 3/0 | 3/1 | 3/0 - 3/1 | 0.256 | 2 | 2 | 0 | 0 | 2 | 3/0, 3/1 | 3/0, 3/1 |  |  | 3/0, 3/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1250 | 3/1 | 4/0 | 3/1 - 4/0 | 0.22652 | 2 | 2 | 0 | 0 | 2 | 3/1, 4/0 | 3/1, 4/0 |  |  | 3/1, 4/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1251 | 4/0 | 4/1 | 4/0 - 4/1 | 0.04362 | 2 | 2 | 0 | 0 | 2 | 4/0, 4/1 | 4/0, 4/1 |  |  | 4/0, 4/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1252 | 4/1 | 4/2 | 4/1 - 4/2 | 0.052 | 2 | 2 | 0 | 0 | 2 | 4/1, 4/2 | 4/1, 4/2 |  |  | 4/1, 4/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1253 | 4/2 | 5/0 | 4/2 - 5/0 | 0.04706 | 2 | 2 | 0 | 0 | 2 | 4/2, 5/0 | 4/2, 5/0 |  |  | 4/2, 5/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1254 | 5/0 | 6/0 | 5/0 - 6/0 | 0.28644 | 2 | 2 | 0 | 0 | 2 | 5/0, 6/0 | 5/0, 6/0 |  |  | 5/0, 6/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1255 | 6/0 | 6/1 | 6/0 - 6/1 | 0.317 | 2 | 2 | 0 | 0 | 2 | 6/0, 6/1 | 6/0, 6/1 |  |  | 6/0, 6/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1256 | 6/1 | 6/2 | 6/1 - 6/2 | 0.328 | 2 | 2 | 0 | 0 | 2 | 6/1, 6/2 | 6/1, 6/2 |  |  | 6/1, 6/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1257 | 6/2 | 6/3 | 6/2 - 6/3 | 0.297 | 2 | 2 | 0 | 0 | 2 | 6/2, 6/3 | 6/2, 6/3 |  |  | 6/2, 6/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1258 | 6/3 | 6/4 | 6/3 - 6/4 | 0.251 | 2 | 2 | 0 | 0 | 2 | 6/3, 6/4 | 6/3, 6/4 |  |  | 6/3, 6/4 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1259 | 6/4 | 7/0 | 6/4 - 7/0 | 0.30823 | 2 | 2 | 0 | 0 | 2 | 6/4, 7/0 | 6/4, 7/0 |  |  | 6/4, 7/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1260 | 7/0 | 8/0 | 7/0 - 8/0 | 0.27812 | 2 | 2 | 0 | 0 | 2 | 7/0, 8/0 | 7/0, 8/0 |  |  | 7/0, 8/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1261 | 8/0 | 9/0 | 8/0 - 9/0 | 0.38596 | 2 | 2 | 0 | 0 | 2 | 8/0, 9/0 | 8/0, 9/0 |  |  | 8/0, 9/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1262 | 9/0 | 10/0 | 9/0 - 10/0 | 0.25992 | 2 | 2 | 0 | 0 | 2 | 9/0, 10/0 | 9/0, 10/0 |  |  | 9/0, 10/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1263 | 10/0 | 11/0 | 10/0 - 11/0 | 0.21513 | 2 | 2 | 0 | 0 | 2 | 10/0, 11/0 | 10/0, 11/0 |  |  | 10/0, 11/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1264 | 11/0 | 12/0 | 11/0 - 12/0 | 0.31615 | 2 | 2 | 0 | 0 | 2 | 11/0, 12/0 | 11/0, 12/0 |  |  | 11/0, 12/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1265 | 12/0 | 12/1 | 12/0 - 12/1 | 0.274 | 2 | 2 | 0 | 0 | 2 | 12/0, 12/1 | 12/0, 12/1 |  |  | 12/0, 12/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1266 | 12/1 | 13/0 | 12/1 - 13/0 | 0.29328 | 2 | 2 | 0 | 0 | 2 | 12/1, 13/0 | 12/1, 13/0 |  |  | 12/1, 13/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1267 | 13/0 | 13/1 | 13/0 - 13/1 | 0.04842 | 2 | 2 | 0 | 0 | 2 | 13/0, 13/1 | 13/0, 13/1 |  |  | 13/0, 13/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1268 | 13/1 | 13/2 | 13/1 - 13/2 | 0.05824 | 2 | 2 | 0 | 0 | 2 | 13/1, 13/2 | 13/1, 13/2 |  |  | 13/1, 13/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1269 | 13/2 | 14/0 | 13/2 - 14/0 | 0.07013 | 2 | 2 | 0 | 0 | 2 | 13/2, 14/0 | 13/2, 14/0 |  |  | 13/2, 14/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1270 | 14/0 | 15/0 | 14/0 - 15/0 | 0.2207 | 2 | 2 | 0 | 0 | 2 | 14/0, 15/0 | 14/0, 15/0 |  |  | 14/0, 15/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1271 | 15/0 | 15/1 | 15/0 - 15/1 | 0.26295 | 2 | 2 | 0 | 0 | 2 | 15/0, 15/1 | 15/0, 15/1 |  |  | 15/0, 15/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1272 | 15/1 | 15/2 | 15/1 - 15/2 | 0.25157 | 2 | 2 | 0 | 0 | 2 | 15/1, 15/2 | 15/1, 15/2 |  |  | 15/1, 15/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1273 | 15/2 | 15/3 | 15/2 - 15/3 | 0.27176 | 2 | 2 | 0 | 0 | 2 | 15/2, 15/3 | 15/2, 15/3 |  |  | 15/2, 15/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1274 | 15/3 | 16/0 | 15/3 - 16/0 | 0.26104 | 2 | 2 | 0 | 0 | 2 | 15/3, 16/0 | 15/3, 16/0 |  |  | 15/3, 16/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1275 | 16/0 | 16/1 | 16/0 - 16/1 | 0.03742 | 2 | 2 | 0 | 0 | 2 | 16/0, 16/1 | 16/0, 16/1 |  |  | 16/0, 16/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1276 | 16/1 | 16/2 | 16/1 - 16/2 | 0.071 | 2 | 2 | 0 | 0 | 2 | 16/1, 16/2 | 16/1, 16/2 |  |  | 16/1, 16/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1277 | 16/2 | 17/0 | 16/2 - 17/0 | 0.03752 | 2 | 2 | 0 | 0 | 2 | 16/2, 17/0 | 16/2, 17/0 |  |  | 16/2, 17/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1278 | 17/0 | 18/0 | 17/0 - 18/0 | 0.16515 | 2 | 2 | 0 | 0 | 2 | 17/0, 18/0 | 17/0, 18/0 |  |  | 17/0, 18/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-132KV | 1279 | 18/0 | Gantry | 18/0 - Gantry | 0.039999 | 2 | 1 | 0 | 1 | 2 | 18/0, GANTRY | 18/0 |  | GANTRY | 18/0, GANTRY | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1280 | Gnty | 0/0 | Gnty - 0/0 | 4.7e-05 | 2 | 1 | 0 | 1 | 2 | GNTY, 0/0 | 0/0 |  | GNTY | GNTY, 0/0 | EMPTY |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1281 | 0/0 | 1/0 | 0/0 - 1/0 | 0.43947 | 2 | 2 | 0 | 0 | 2 | 0/0, 1/0 | 0/0, 1/0 |  |  | 0/0, 1/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1282 | 1/0 | 1A/0 | 1/0 - 1A/0 | 1.0373 | 2 | 2 | 0 | 0 | 2 | 1/0, 1A/0 | 1/0, 1A/0 |  |  | 1/0, 1A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1283 | 1A/0 | 1A/2 | 1A/0 - 1A/2 | 0.609 | 2 | 2 | 0 | 0 | 2 | 1A/0, 1A/2 | 1A/0, 1A/2 |  |  | 1A/0, 1A/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1284 | 1A/2 | 1B/0 | 1A/2 - 1B/0 | 0.2321 | 2 | 2 | 0 | 0 | 2 | 1A/2, 1B/0 | 1A/2, 1B/0 |  |  | 1A/2, 1B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1285 | 1B/0 | 1C/0 | 1B/0 - 1C/0 | 0.23778 | 2 | 2 | 0 | 0 | 2 | 1B/0, 1C/0 | 1B/0, 1C/0 |  |  | 1B/0, 1C/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1286 | 1C/0 | 1D/0 | 1C/0 - 1D/0 | 0.67521 | 2 | 2 | 0 | 0 | 2 | 1C/0, 1D/0 | 1C/0, 1D/0 |  |  | 1C/0, 1D/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1287 | 1D/0 | 1E/0 | 1D/0 - 1E/0 | 0.69992 | 2 | 2 | 0 | 0 | 2 | 1D/0, 1E/0 | 1D/0, 1E/0 |  |  | 1D/0, 1E/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1288 | 1E/0 | 2/0 | 1E/0 - 2/0 | 0.35666 | 2 | 2 | 0 | 0 | 2 | 1E/0, 2/0 | 1E/0, 2/0 |  |  | 1E/0, 2/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1289 | 2/0 | 3/0 | 2/0 - 3/0 | 0.1742 | 2 | 2 | 0 | 0 | 2 | 2/0, 3/0 | 2/0, 3/0 |  |  | 2/0, 3/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1290 | 3/0 | 4/0 | 3/0 - 4/0 | 0.22973 | 2 | 2 | 0 | 0 | 2 | 3/0, 4/0 | 3/0, 4/0 |  |  | 3/0, 4/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1291 | 4/0 | 4/5 | 4/0 - 4/5 | 1.733 | 2 | 2 | 0 | 0 | 2 | 4/0, 4/5 | 4/0, 4/5 |  |  | 4/0, 4/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1292 | 4/5 | 4/6 | 4/5 - 4/6 | 0.349 | 2 | 2 | 0 | 0 | 2 | 4/5, 4/6 | 4/5, 4/6 |  |  | 4/5, 4/6 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1293 | 4/6 | 4/7 | 4/6 - 4/7 | 0.36 | 2 | 2 | 0 | 0 | 2 | 4/6, 4/7 | 4/6, 4/7 |  |  | 4/6, 4/7 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1294 | 4/7 | 4/8 | 4/7 - 4/8 | 0.46 | 2 | 2 | 0 | 0 | 2 | 4/7, 4/8 | 4/7, 4/8 |  |  | 4/7, 4/8 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1295 | 4/8 | 4/9 | 4/8 - 4/9 | 0.23 | 2 | 2 | 0 | 0 | 2 | 4/8, 4/9 | 4/8, 4/9 |  |  | 4/8, 4/9 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1296 | 4/9 | 4/10 | 4/9 - 4/10 | 0.37151 | 2 | 2 | 0 | 0 | 2 | 4/9, 4/10 | 4/9, 4/10 |  |  | 4/9, 4/10 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1297 | 4/10 | 4/11 | 4/10 - 4/11 | 0.33247 | 2 | 2 | 0 | 0 | 2 | 4/10, 4/11 | 4/10, 4/11 |  |  | 4/10, 4/11 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1298 | 4/11 | 4/15 | 4/11 - 4/15 | 1.3351 | 2 | 2 | 0 | 0 | 2 | 4/11, 4/15 | 4/11, 4/15 |  |  | 4/11, 4/15 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1299 | 4/15 | 4/16 | 4/15 - 4/16 | 0.415 | 2 | 2 | 0 | 0 | 2 | 4/15, 4/16 | 4/15, 4/16 |  |  | 4/15, 4/16 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1300 | 4/16 | 4/17 | 4/16 - 4/17 | 0.237 | 2 | 2 | 0 | 0 | 2 | 4/16, 4/17 | 4/16, 4/17 |  |  | 4/16, 4/17 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1301 | 4/17 | 5/0 | 4/17 - 5/0 | 0.18845 | 2 | 2 | 0 | 0 | 2 | 4/17, 5/0 | 4/17, 5/0 |  |  | 4/17, 5/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1302 | 5/0 | 5/1 | 5/0 - 5/1 | 0.383 | 2 | 2 | 0 | 0 | 2 | 5/0, 5/1 | 5/0, 5/1 |  |  | 5/0, 5/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1303 | 5/1 | 5A/0 | 5/1 - 5A/0 | 0.952 | 2 | 2 | 0 | 0 | 2 | 5/1, 5A/0 | 5/1, 5A/0 |  |  | 5/1, 5A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1304 | 5A/0 | 5A/1 | 5A/0 - 5A/1 | 0.322 | 2 | 2 | 0 | 0 | 2 | 5A/0, 5A/1 | 5A/0, 5A/1 |  |  | 5A/0, 5A/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1305 | 5A/1 | 5A/2 | 5A/1 - 5A/2 | 0.284 | 2 | 2 | 0 | 0 | 2 | 5A/1, 5A/2 | 5A/1, 5A/2 |  |  | 5A/1, 5A/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1306 | 5A/2 | 5B/0 | 5A/2 - 5B/0 | 0.28274 | 2 | 2 | 0 | 0 | 2 | 5A/2, 5B/0 | 5A/2, 5B/0 |  |  | 5A/2, 5B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1307 | 5B/0 | 6/0 | 5B/0 - 6/0 | 0.46206 | 2 | 2 | 0 | 0 | 2 | 5B/0, 6/0 | 5B/0, 6/0 |  |  | 5B/0, 6/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1308 | 6/0 | 7/0 | 6/0 - 7/0 | 0.31804 | 2 | 2 | 0 | 0 | 2 | 6/0, 7/0 | 6/0, 7/0 |  |  | 6/0, 7/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1309 | 7/0 | 8/0 | 7/0 - 8/0 | 1.147 | 2 | 2 | 0 | 0 | 2 | 7/0, 8/0 | 7/0, 8/0 |  |  | 7/0, 8/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1310 | 8/0 | 8A/0 | 8/0 - 8A/0 | 0.17357 | 2 | 2 | 0 | 0 | 2 | 8/0, 8A/0 | 8/0, 8A/0 |  |  | 8/0, 8A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1311 | 8A/0 | 8B/0 | 8A/0 - 8B/0 | 0.3365 | 2 | 2 | 0 | 0 | 2 | 8A/0, 8B/0 | 8A/0, 8B/0 |  |  | 8A/0, 8B/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1312 | 8B/0 | 8C/0 | 8B/0 - 8C/0 | 0.90014 | 2 | 2 | 0 | 0 | 2 | 8B/0, 8C/0 | 8B/0, 8C/0 |  |  | 8B/0, 8C/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1313 | 8C/0 | 8D/0 | 8C/0 - 8D/0 | 0.31876 | 2 | 2 | 0 | 0 | 2 | 8C/0, 8D/0 | 8C/0, 8D/0 |  |  | 8C/0, 8D/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1314 | 8D/0 | 8D/1 | 8D/0 - 8D/1 | 0.4361 | 2 | 2 | 0 | 0 | 2 | 8D/0, 8D/1 | 8D/0, 8D/1 |  |  | 8D/0, 8D/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1315 | 8D/1 | 8D/3 | 8D/1 - 8D/3 | 0.65708 | 2 | 2 | 0 | 0 | 2 | 8D/1, 8D/3 | 8D/1, 8D/3 |  |  | 8D/1, 8D/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1316 | 8D/3 | 8D/4 | 8D/3 - 8D/4 | 0.459 | 2 | 2 | 0 | 0 | 2 | 8D/3, 8D/4 | 8D/3, 8D/4 |  |  | 8D/3, 8D/4 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1317 | 8D/4 | 8D/5 | 8D/4 - 8D/5 | 0.195 | 2 | 2 | 0 | 0 | 2 | 8D/4, 8D/5 | 8D/4, 8D/5 |  |  | 8D/4, 8D/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1318 | 8D/5 | 8D/6 | 8D/5 - 8D/6 | 0.295 | 2 | 2 | 0 | 0 | 2 | 8D/5, 8D/6 | 8D/5, 8D/6 |  |  | 8D/5, 8D/6 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1319 | 8D/6 | 8E/0 | 8D/6 - 8E/0 | 0.38025 | 2 | 2 | 0 | 0 | 2 | 8D/6, 8E/0 | 8D/6, 8E/0 |  |  | 8D/6, 8E/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1320 | 8E/0 | 8E/1 | 8E/0 - 8E/1 | 0.428 | 2 | 2 | 0 | 0 | 2 | 8E/0, 8E/1 | 8E/0, 8E/1 |  |  | 8E/0, 8E/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1321 | 8E/1 | 8E/2 | 8E/1 - 8E/2 | 0.419 | 2 | 2 | 0 | 0 | 2 | 8E/1, 8E/2 | 8E/1, 8E/2 |  |  | 8E/1, 8E/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1322 | 8E/2 | 8E/5 | 8E/2 - 8E/5 | 0.9 | 2 | 2 | 0 | 0 | 2 | 8E/2, 8E/5 | 8E/2, 8E/5 |  |  | 8E/2, 8E/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1323 | 8E/5 | 8E/6 | 8E/5 - 8E/6 | 0.34387 | 2 | 2 | 0 | 0 | 2 | 8E/5, 8E/6 | 8E/5, 8E/6 |  |  | 8E/5, 8E/6 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1324 | 8E/6 | 8E/7 | 8E/6 - 8E/7 | 0.49913 | 2 | 2 | 0 | 0 | 2 | 8E/6, 8E/7 | 8E/6, 8E/7 |  |  | 8E/6, 8E/7 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1325 | 8E/7 | 8E/8 | 8E/7 - 8E/8 | 0.434 | 2 | 2 | 0 | 0 | 2 | 8E/7, 8E/8 | 8E/7, 8E/8 |  |  | 8E/7, 8E/8 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1326 | 8E/8 | 8E/11 | 8E/8 - 8E/11 | 0.919 | 2 | 2 | 0 | 0 | 2 | 8E/8, 8E/11 | 8E/8, 8E/11 |  |  | 8E/8, 8E/11 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1327 | 8E/11 | 8E/12 | 8E/11 - 8E/12 | 0.489 | 2 | 2 | 0 | 0 | 2 | 8E/11, 8E/12 | 8E/11, 8E/12 |  |  | 8E/11, 8E/12 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1328 | 8E/12 | AP-9 | 8E/12 - AP-9 | 0.38248 | 2 | 2 | 0 | 0 | 2 | 8E/12, 9 | 8E/12, 9 |  |  | 8E/12, 9 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1329 | AP-9 | 9/4 | AP-9 - 9/4 | 1.2503 | 2 | 2 | 0 | 0 | 2 | 9, 9/4 | 9, 9/4 |  |  | 9, 9/4 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1330 | 9/4 | 9/5 | 9/4 - 9/5 | 0.24676 | 2 | 2 | 0 | 0 | 2 | 9/4, 9/5 | 9/4, 9/5 |  |  | 9/4, 9/5 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1331 | 9/5 | AP-10 | 9/5 - AP-10 | 1.6972 | 2 | 2 | 0 | 0 | 2 | 9/5, 10 | 9/5, 10 |  |  | 9/5, 10 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1332 | AP-10 | AP-11 | AP-10 - AP-11 | 1.6001 | 2 | 2 | 0 | 0 | 2 | 10, 11 | 10, 11 |  |  | 10, 11 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1333 | AP-11 | AP-12 | AP-11 - AP-12 | 0.52589 | 2 | 2 | 0 | 0 | 2 | 11, 12 | 11, 12 |  |  | 11, 12 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1334 | AP-12 | AP-13 | AP-12 - AP-13 | 0.35628 | 2 | 2 | 0 | 0 | 2 | 12, 13 | 12, 13 |  |  | 12, 13 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1335 | AP-13 | AP-14 | AP-13 - AP-14 | 0.66759 | 2 | 2 | 0 | 0 | 2 | 13, 14 | 13, 14 |  |  | 13, 14 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1336 | AP-14 | 14/1 | AP-14 - 14/1 | 0.362 | 2 | 2 | 0 | 0 | 2 | 14, 14/1 | 14, 14/1 |  |  | 14, 14/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1337 | 14/1 | 14/3 | 14/1 - 14/3 | 0.752 | 2 | 2 | 0 | 0 | 2 | 14/1, 14/3 | 14/1, 14/3 |  |  | 14/1, 14/3 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1338 | 14/3 | AP-15 | 14/3 - AP-15 | 2.5362 | 2 | 2 | 0 | 0 | 2 | 14/3, 15 | 14/3, 15 |  |  | 14/3, 15 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1339 | AP-15 | AP-16 | AP-15 - AP-16 | 3.4224 | 2 | 2 | 0 | 0 | 2 | 15, 16 | 15, 16 |  |  | 15, 16 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1340 | AP-16 | AP-17 | AP-16 - AP-17 | 1.3076 | 2 | 2 | 0 | 0 | 2 | 16, 17 | 16, 17 |  |  | 16, 17 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1341 | AP-17 | AP-18 | AP-17 - AP-18 | 1.436 | 2 | 2 | 0 | 0 | 2 | 17, 18 | 17, 18 |  |  | 17, 18 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1342 | AP-18 | AP-19 | AP-18 - AP-19 | 4.2101 | 2 | 2 | 0 | 0 | 2 | 18, 19 | 18, 19 |  |  | 18, 19 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1343 | AP-19 | AP-20 | AP-19 - AP-20 | 1.9466 | 2 | 2 | 0 | 0 | 2 | 19, 20 | 19, 20 |  |  | 19, 20 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1344 | AP-20 | AP-21 | AP-20 - AP-21 | 2.9948 | 2 | 2 | 0 | 0 | 2 | 20, 21 | 20, 21 |  |  | 20, 21 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1345 | AP-21 | AP-22 | AP-21 - AP-22 | 4.9748 | 2 | 2 | 0 | 0 | 2 | 21, 22 | 21, 22 |  |  | 21, 22 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1346 | AP-22 | AP-23 | AP-22 - AP-23 | 0.94723 | 2 | 2 | 0 | 0 | 2 | 22, 23 | 22, 23 |  |  | 22, 23 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1347 | AP-23 | AP-24 | AP-23 - AP-24 | 1.9267 | 2 | 2 | 0 | 0 | 2 | 23, 24 | 23, 24 |  |  | 23, 24 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1348 | AP-24 | AP-25 | AP-24 - AP-25 | 0.19052 | 2 | 2 | 0 | 0 | 2 | 24, 25 | 24, 25 |  |  | 24, 25 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1349 | AP-25 | AP-26 | AP-25 - AP-26 | 0.17354 | 2 | 2 | 0 | 0 | 2 | 25, 26 | 25, 26 |  |  | 25, 26 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1350 | AP-26 | AP-27 | AP-26 - AP-27 | 0.14238 | 2 | 2 | 0 | 0 | 2 | 26, 27 | 26, 27 |  |  | 26, 27 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1351 | AP-27 | AP-28 | AP-27 - AP-28 | 0.077015 | 2 | 2 | 0 | 0 | 2 | 27, 28 | 27, 28 |  |  | 27, 28 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1352 | AP-28 | 28/1 | AP-28 - 28/1 | 0.042266 | 2 | 2 | 0 | 0 | 2 | 28, 28/1 | 28, 28/1 |  |  | 28, 28/1 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1353 | 28/1 | 28/2 | 28/1 - 28/2 | 0.054573 | 2 | 2 | 0 | 0 | 2 | 28/1, 28/2 | 28/1, 28/2 |  |  | 28/1, 28/2 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1354 | 28/2 | AP-29 | 28/2 - AP-29 | 0.041886 | 2 | 2 | 0 | 0 | 2 | 28/2, 29 | 28/2, 29 |  |  | 28/2, 29 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1355 | AP-29 | 29A/0 | AP-29 - 29A/0 | 0.35328 | 2 | 2 | 0 | 0 | 2 | 29, 29A/0 | 29, 29A/0 |  |  | 29, 29A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1356 | 29A/0 | AP-30 | 29A/0 - AP-30 | 1.8605 | 2 | 2 | 0 | 0 | 2 | 29A/0, 30 | 29A/0, 30 |  |  | 29A/0, 30 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1357 | AP-30 | AP-31 | AP-30 - AP-31 | 2.3329 | 2 | 2 | 0 | 0 | 2 | 30, 31 | 30, 31 |  |  | 30, 31 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1358 | AP-31 | AP-32 | AP-31 - AP-32 | 0.74335 | 2 | 2 | 0 | 0 | 2 | 31, 32 | 31, 32 |  |  | 31, 32 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1359 | AP-32 | 33/0 | AP-32 - 33/0 | 0.90922 | 2 | 1 | 0 | 1 | 2 | 32, 33/0 | 32 |  | 33/0 | 32, 33/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | TB 501 - DPR - 2026-05-25.xlsx | Stringing-220kV | 1360 | 33/0 | 34/0 | 33/0 - 34/0 | 0.209 | 2 | 0 | 0 | 2 | 2 | 33/0, 34/0 |  |  | 33/0, 34/0 | 33/0, 34/0 | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 507 | TB 507 | tb507 |  | TB 507 - DPR - 2026-05-25.xlsx | Stringing Compiled | 1507 |  | Total | Total |  | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1508 | 146/0 | 145/0 | Bhinmal | 1.97 | 7 | 6 | 0 | 1 | 7 | 146/0, 145/0, 145/1, 145/2, 145/3, 145/4, 145/5 | 146/0, 145/0, 145/1, 145/2, 145/3, 145/4 |  | 145/5 | 146/0, 145/0, 145/1, 145/2, 145/3, 145/4, 145/5 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1509 | 149A/0 | 149/0 | Bhinmal | 0.188 | 2 | 2 | 0 | 0 | 2 | 149A/0, 149/0 | 149A/0, 149/0 |  |  | 149A/0, 149/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1510 | 149/0 | 148/0 | Bhinmal | 3.031 | 9 | 9 | 0 | 0 | 9 | 149/0, 148/0, 148/1, 148/2, 148/3, 148/4, 148/5, 148/6, 148/7 | 149/0, 148/0, 148/1, 148/2, 148/3, 148/4, 148/5, 148/6, 148/7 |  |  | 149/0, 148/0, 148/1, 148/2, 148/3, 148/4, 148/5, 148/6, 148/7 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1511 | 150/0 | 149B/3 | Bhinmal | 0.489 | 2 | 2 | 0 | 0 | 2 | 150/0, 149B/3 | 150/0, 149B/3 |  |  | 150/0, 149B/3 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1512 | 149B/0 | 149A/0 | Bhinmal | 0.396 | 2 | 2 | 0 | 0 | 2 | 149B/0, 149A/0 | 149B/0, 149A/0 |  |  | 149B/0, 149A/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1513 | 149B/3 | 149B/0 | Bhinmal | 1.265 | 4 | 4 | 0 | 0 | 4 | 149B/3, 149B/0, 149B/1, 149B/2 | 149B/3, 149B/0, 149B/1, 149B/2 |  |  | 149B/3, 149B/0, 149B/1, 149B/2 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1514 | 144/0 | 143/0 | Bhinmal | 3.275 | 8 | 7 | 0 | 1 | 8 | 144/0, 143/0, 143/1, 143/2, 143/3, 143/45, 143/6, 143/7 | 144/0, 143/0, 143/1, 143/2, 143/3, 143/6, 143/7 |  | 143/45 | 144/0, 143/0, 143/1, 143/2, 143/3, 143/45, 143/6, 143/7 | OK |  | TRUE | FALSE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1515 | 145/0 | 144/0 | Bhinmal | 0.232 | 2 | 2 | 0 | 0 | 2 | 145/0, 144/0 | 145/0, 144/0 |  |  | 145/0, 144/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1516 | 113/0 | 112/0 | Sindhari | 0.158 | 2 | 2 | 0 | 0 | 2 | 113/0, 112/0 | 113/0, 112/0 |  |  | 113/0, 112/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1517 | 153/0 | 152/0 | Bhinmal | 0.243 | 2 | 2 | 0 | 0 | 2 | 153/0, 152/0 | 153/0, 152/0 |  |  | 153/0, 152/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1518 | 113A/0 | 113/0 | Sindhari | 0.201 | 2 | 2 | 0 | 0 | 2 | 113A/0, 113/0 | 113A/0, 113/0 |  |  | 113A/0, 113/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1519 | 147/0 | 146/0 | Bhinmal | 1.223 | 4 | 4 | 0 | 0 | 4 | 147/0, 146/0, 146/1, 146/2 | 147/0, 146/0, 146/1, 146/2 |  |  | 147/0, 146/0, 146/1, 146/2 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1520 | 148/0 | 147/0 | Bhinmal | 3.666 | 11 | 11 | 0 | 0 | 11 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 |  |  | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1521 | 151/0 | 150/0 | Bhinmal | 0.29 | 2 | 2 | 0 | 0 | 2 | 151/0, 150/0 | 151/0, 150/0 |  |  | 151/0, 150/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1522 | 152/0 | 151/0 | Bhinmal | 0.419 | 2 | 2 | 0 | 0 | 2 | 152/0, 151/0 | 152/0, 151/0 |  |  | 152/0, 151/0 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1523 | 134/0 | 133/0 | Bhinmal | 3.486 | 10 | 10 | 0 | 0 | 10 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 |  |  | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 | OK |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1524 | 143/0 | 142/0 | Bhinmal | 0.437 | 2 | 2 | 0 | 0 | 2 | 143/0, 142/0 | 143/0, 142/0 |  |  | 143/0, 142/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1525 | 134/0 | 134A/0 | Bhinmal | 0.226 | 2 | 2 | 0 | 0 | 2 | 134/0, 134A/0 | 134/0, 134A/0 |  |  | 134/0, 134A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1526 | 114/0 | 113A/0 | Sindhari | 0.165 | 2 | 2 | 0 | 0 | 2 | 114/0, 113A/0 | 114/0, 113A/0 |  |  | 114/0, 113A/0 | EMPTY |  | TRUE | TRUE | FALSE | FALSE | ALREADY_STRUNG
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1527 | 115/0 | 115/1 | Sindhari | 0.425 | 2 | 2 | 0 | 0 | 2 | 115/0, 115/1 | 115/0, 115/1 |  |  | 115/0, 115/1 | EMPTY |  | FALSE | TRUE | FALSE | FALSE | TIGHTENING_PENDING
TB 507 | TB 507 - MAIN | tb507main | MAIN | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Stringing Compiled | 1529 |  | Total | Total |  | 1 | 0 | 0 | 1 | 1 | TOTAL |  |  | TOTAL | TOTAL | EMPTY |  | FALSE | FALSE | FALSE | FALSE | ERECTION_NOT_COMPLETE

## Tower Gap
Tower Gap
project_code | project_display | project_scope_key | line_name | location_no | complete_date | status | tower_tightening_raw | tower_tightening | source_file | source_sheet
TA 325 | TA 325 | ta325 |  | 101/0 | 2025-09-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 102/0 | 2025-12-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 103/0 | 2026-01-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 104/0 | 2025-08-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 105/0 | 2025-09-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106/0 | 2024-12-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106A/0 | 2025-01-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106A/1 | 2024-12-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106A/2 | 2024-12-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106A/3 | 2024-07-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106A/4 | 2024-06-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106B/0 | 2024-08-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106B/1 | 2024-08-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 106B/2 | 2024-07-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 107/0 | 2024-07-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 107/1 | 2024-09-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 108/0 | 2024-10-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 109/0 | 2024-08-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 110/0 | 2024-08-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 111/0 | 2024-09-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 112/0 | 2024-06-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 113/0 | 2024-07-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 114/0 | 2024-09-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 115/0 | 2024-12-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 116/0 | 2024-09-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 116A/0 | 2024-08-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 116A/1 | 2024-12-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 116B/0 | 2024-10-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 117/0 | 2024-12-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 118/0 | 2024-08-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 119/0 | 2024-09-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 119/1 | 2024-09-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 119/2 | 2024-07-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 119/3 | 2024-07-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 120/0 | 2024-10-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 121/0 | 2024-10-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 122/0 | 2024-10-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 123/0 | 2024-10-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 123/1 | 2024-10-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 124/0 | 2024-11-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 124A/0 | 2025-01-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 124A/1 | 2024-09-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 125/0 | 2025-01-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 125A/0 | 2024-11-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 126/0 | 2024-07-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 126/1 | 2024-12-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/0 | 2024-06-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/1 | 2023-10-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/2 | 2023-10-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/3 | 2024-05-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/4 | 2024-05-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 127/5 | 2024-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 128/0 | 2024-11-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 129/0 | 2025-01-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 129A/0 | 2024-04-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 129A/1 | 2024-05-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 129A/2 | 2024-05-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 130/0 | 2024-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 130/1 | 2025-02-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 130/2 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 130/3 | 2025-01-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 130/4 | 2025-01-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 131/0 | 2025-02-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 132/0 | 2024-12-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 132/1 | 2024-12-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 132/2 | 2024-02-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 132/3 | 2024-06-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/0 | 2024-02-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/1 | 2023-12-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/2 | 2024-03-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/3 | 2024-02-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/4 | 2024-04-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133/5 | 2024-03-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133A/0 | 2024-03-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133A/1 | 2024-03-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133A/2 | 2024-04-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133A/3 | 2024-02-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 133A/4 | 2024-10-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 134/0 | 2024-12-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/0 | 2025-01-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/1 | 2025-01-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/2 | 2023-11-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/3 | 2024-03-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/4 | 2024-06-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/5 | 2024-05-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/6 | 2024-05-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135/7 | 2025-04-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/0 | 2025-01-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/1 | 2024-11-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/2 | 2024-11-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/3 | 2024-01-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/4 | 2023-11-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/5 | 2025-01-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/6 | 2024-12-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135A/7 | 2023-12-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/0 | 2024-02-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/1 | 2024-02-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/2 | 2024-01-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/3 | 2024-01-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/4 | 2024-01-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/5 | 2024-02-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/6 | 2024-02-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 135B/7 | 2024-04-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 136/0 | 2025-01-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/0 | 2025-02-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/1 | 2024-05-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/2 | 2025-02-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/3 | 2024-05-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/4 | 2024-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/5 | 2025-02-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137/6 | 2025-02-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/0 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/1 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/2 | 2025-02-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/3 | 2024-11-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/4 | 2024-12-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/5 | 2024-11-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 137A/6 | 2025-01-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 138/0 | 2025-02-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 138/1 | 2025-02-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 138/2 | 2025-02-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 139/0 | 2025-02-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 139/1 | 2025-02-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 139/2 | 2025-02-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 139A/0 | 2025-02-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 140/0 | 2025-02-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 141/0 | 2025-02-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 141/1 | 2025-02-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 141/2 | 2025-02-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 141/3 | 2025-02-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 142/0 | 2025-03-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143/0 | 2025-03-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/0 | 2025-03-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/1 | 2025-03-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/2 | 2025-03-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/3 | 2025-03-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/4 | 2025-03-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 143A/5 | 2025-03-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/0 | 2024-11-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/1 | 2024-07-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/2 | 2024-06-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/3 | 2024-06-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/4 | 2024-06-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144/5 | 2024-06-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 144A/0 | 2024-11-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 145/0 | 2024-12-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 145A/0 | 2025-03-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 145A/1 | 2025-03-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 145A/2 | 2025-03-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 145A/3 | 2025-03-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 146/0 | 2025-03-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/0 | 2025-04-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/1 | 2024-12-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/2 | 2024-12-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/3 | 2024-12-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/4 | 2024-12-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/5 | 2024-12-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147/6 | 2025-02-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147A/0 | 2025-01-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147B/0 | 2025-03-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 147B/1 | 2025-02-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/0 | 2025-01-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/1 | 2025-02-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/2 | 2025-01-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/3 | 2025-01-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/4 | 2025-01-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/5 | 2025-02-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/6 | 2025-03-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 148/7 | 2025-03-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 149/0 | 2025-04-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 149/1 | 2025-03-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150/0 | 2025-03-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150/1 | 2025-04-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150/2 | 2025-03-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150/3 | 2025-04-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150A/0 | 2025-04-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150A/1 | 2024-11-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 150A/2 | 2024-12-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 151/0 | 2025-03-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152/0 | 2024-10-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152/1 | 2024-10-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152/2 | 2024-11-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152/3 | 2024-10-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152/4 | 2024-11-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 152A/0 | 2025-03-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 153/0 | 2025-08-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 154/0 | 2026-01-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 154/1 | 2025-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/0 | 2025-04-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/1 | 2025-04-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/2 | 2024-11-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/3 | 2024-11-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/4 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/5 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 155/6 | 2025-03-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 156/0 | 2025-03-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 157/0 | 2025-03-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 157/1 | 2025-02-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 157/2 | 2025-03-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 157/3 | 2025-10-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158/0 | 2025-04-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158/1 | 2025-04-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158/2 | 2025-03-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158A/0 | 2024-11-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158B/0 | 2024-12-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158B/1 | 2024-12-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 158B/2 | 2025-01-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 159/0 | 2024-09-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 159/1 | 2025-02-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 159/2 | 2025-12-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 159/3 | 2024-07-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 159/4 | 2025-02-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 160/0 | 2025-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 161/0 | 2025-02-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 162/0 | 2025-03-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/0 | 2025-01-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/1 | 2025-01-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/2 | 2024-12-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/3 | 2024-12-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/4 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/5 | 2025-02-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 163/6 | 2025-01-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/0 | 2025-01-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/1 | 2025-01-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/2 | 2024-08-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/3 | 2025-01-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/4 | 2024-11-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/5 | 2024-12-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/6 | 2024-12-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 164/7 | 2024-10-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/0 | 2024-10-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/1 | 2025-05-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/2 | 2024-09-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/3 | 2024-11-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/4 | 2025-12-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 165/5 | 2025-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 166/0 | 2025-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 167/0 | 2025-12-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 167/1 | 2025-12-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 167/2 | 2025-04-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 167/3 | 2025-04-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 167/4 | 2025-04-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 168/0 | 2025-04-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 168/1 | 2025-05-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 168/2 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 169/0 | 2025-06-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 171/0 | 2025-03-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 172/0 | 2025-04-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 172/1 | 2025-12-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 172/2 | 2025-06-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 173/0 | 2025-12-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 174/0 | 2025-12-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 174/1 | 2025-06-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 175/0 | 2025-06-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 175/1 | 2025-11-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 175/2 | 2025-07-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 176/0 | 2025-07-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 177/0 | 2025-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 178/0 | 2025-04-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 179/0 | 2025-04-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 180/0 | 2025-05-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 181/0 | 2025-04-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 181/1 | 2025-04-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 181/2 | 2025-04-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 181/3 | 2025-05-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 181/4 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 182/0 | 2025-05-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 182A/0 | 2025-12-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 183/0 | 2025-12-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 184/0 | 2025-11-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 184/1 | 2025-11-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 185/0 | 2025-11-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 185/1 | 2025-10-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 186/0 | 2025-12-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 187/0 | 2025-11-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 187/1 | 2025-04-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 187/2 | 2025-01-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 187/3 | 2024-11-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 188/0 | 2024-12-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 189/0 | 2024-12-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 189/1 | 2025-04-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 190/0 | 2025-05-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191/0 | 2025-08-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191/1 | 2024-12-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191/2 | 2025-04-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191/3 | 2025-05-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191A/0 | 2025-04-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 191A/1 | 2024-11-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 192/0 | 2025-04-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 193/0 | 2024-12-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 194/0 | 2025-05-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/0 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/1 | 2025-04-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/2 | 2025-04-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/3 | 2025-04-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/4 | 2025-04-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195/5 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195A/0 | 2025-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195A/1 | 2025-05-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195A/2 | 2025-04-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 195A/3 | 2025-04-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 196/0 | 2025-01-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 197/0 | 2025-01-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 197/1 | 2025-04-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 197/2 | 2025-02-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 197/3 | 2025-01-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 197/4 | 2024-12-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 198/0 | 2025-04-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 198/1 | 2025-01-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 198/2 | 2025-04-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 199/0 | 2025-05-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 200/0 | 2025-12-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 201/0 | 2025-11-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 201/1 | 2025-12-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 202/0 | 2025-11-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 203/0 | 2025-12-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 203/1 | 2025-11-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 204/0 | 2025-05-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 205/0 | 2025-04-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 205/1 | 2025-04-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 205/2 | 2025-05-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 206/0 | 2025-10-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 208/0 | 2025-12-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 209/0 | 2025-05-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 209/1 | 2025-11-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 210/0 | 2025-10-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211/0 | 2025-11-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211/1 | 2025-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211/2 | 2025-11-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211A/0 | 2025-11-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211A/1 | 2025-11-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 211A/2 | 2025-11-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 212/0 | 2025-12-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 213/0 | 2025-11-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 213/1 | 2025-11-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 214/0 | 2025-11-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 214/1 | 2025-11-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 215/0 | 2025-10-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 215/1 | 2025-11-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 216/0 | 2025-12-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 217/0 | 2025-12-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 217A/0 | 2025-11-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 217A/1 | 2025-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 217A/2 | 2025-10-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 218/0 | 2025-11-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 218/1 | 2025-11-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 219/0 | 2025-11-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 220/0 | 2025-11-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 220/1 | 2025-11-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 221/0 | 2025-11-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 222/0 | 2025-12-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 222/1 | 2025-10-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 223/0 | 2025-11-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 223/1 | 2025-10-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 223/2 | 2025-12-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 223/3 | 2025-11-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 224/0 | 2025-10-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 225/0 | 2025-10-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 225/1 | 2025-10-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 226/0 | 2025-11-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 227/0 | 2025-11-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 228/0 | 2025-12-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/0 | 2025-11-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/1 | 2025-11-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/2 | 2025-11-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/3 | 2025-10-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/4 | 2025-10-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 229/5 | 2025-10-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 230/0 | 2025-11-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 231/0 | 2025-10-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 232/0 | 2025-11-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 233/0 | 2025-10-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 234/0 | 2025-10-08 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 235/0 | 2025-10-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 236/0 | 2025-10-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/0 | 2025-11-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/1 | 2025-10-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/2 | 2025-10-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/3 | 2025-10-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/4 | 2025-10-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/5 | 2025-10-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 237/6 | 2025-10-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 239/0 | 2025-11-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 240/0 | 2025-11-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 241/0 | 2025-10-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 242/0 | 2025-10-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 242/1 | 2025-10-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 242/2 | 2025-10-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 242/3 | 2025-10-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 243/0 | 2025-10-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 244/0 | 2025-10-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 244/1 | 2025-10-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 245/0 | 2025-11-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 245/1 | 2025-10-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 246/0 | 2025-10-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 247/0 | 2025-10-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 247/1 | 2025-05-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 247/2 | 2025-10-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 247/3 | 2025-10-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 247/4 | 2025-09-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/0 | 2025-04-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/1 | 2025-05-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/2 | 2025-04-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/3 | 2025-05-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/4 | 2025-05-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/5 | 2025-04-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 248/6 | 2025-05-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 249/0 | 2025-02-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 249/1 | 2025-04-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 249/2 | 2025-03-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 249/3 | 2025-03-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 250/0 | 2025-04-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 250/1 | 2025-02-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 251/0 | 2024-12-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 252/0 | 2025-04-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 253/0 | 2025-02-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 254/0 | 2024-11-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 255/0 | 2024-12-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 255/1 | 2025-01-27 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 255/2 | 2025-01-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 255/3 | 2025-01-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 255/4 | 2024-08-22 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 257/0 | 2024-09-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 257/1 | 2025-01-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 257/2 | 2024-10-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 257/3 | 2024-10-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 257/4 | 2024-11-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 259/0 | 2024-12-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 260/0 | 2024-10-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 261/0 | 2024-12-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 262/0 | 2025-02-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 262/1 | 2024-11-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 263/0 | 2025-01-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 264/0 | 2024-12-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 265/0 | 2024-10-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 266/0 | 2025-01-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 266/1 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 266/2 | 2025-02-12 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 267/0 | 2025-01-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 267A/0 | 2025-03-18 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 267A/1 | 2025-03-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 267A/2 | 2025-03-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 267A/3 | 2024-09-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 268/0 | 2024-12-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 269/0 | 2025-04-01 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 269/1 | 2025-01-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 269/2 | 2025-01-19 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/0 | 2025-03-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/1 | 2024-12-24 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/2 | 2024-10-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/3 | 2025-03-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/4 | 2025-03-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/5 | 2025-02-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/6 | 2025-02-17 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270/7 | 2025-02-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 270A/0 | 2025-02-15 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/0 | 2025-02-13 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/1 | 2025-03-25 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/2 | 2025-02-21 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/3 | 2025-03-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/4 | 2025-03-03 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 271/5 | 2025-01-11 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/0 | 2024-12-31 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/1 | 2024-12-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/2 | 2025-02-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/3 | 2025-02-06 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/4 | 2025-02-02 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/5 | 2025-01-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/6 | 2025-03-30 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272/7 | 2025-03-07 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/0 | 2025-04-26 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/1 | 2025-01-29 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/2 | 2025-02-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/3 | 2025-02-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/4 | 2025-03-20 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/5 | 2025-03-16 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/6 | 2025-03-05 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 272A/7 | 2025-03-10 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 273/0 | 2025-10-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 273/1 | 2025-04-09 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 273/2 | 2025-02-28 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 274/0 | 2025-02-23 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 275/0 | 2025-09-14 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | 276/0 | 2025-10-04 | Completed |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | DA+9 | 1970-01-01 | 14 |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | DD60+0 | 1970-01-01 | 5 |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 325 | TA 325 | ta325 |  | Old | 1970-01-01 | 7 |  |  | TA 325 - DPR - 2026-01-19.xlsx | Erection-Compiled
TA 418 | TA 418 | ta418 |  | 46/9 | 2025-03-11 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 418 | TA 418 | ta418 |  | 48/0 | 2025-11-18 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 418 | TA 418 | ta418 |  | 54/0 | 2025-10-17 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 418 | TA 418 | ta418 |  | 54/2 | 2026-01-28 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 418 | TA 418 | ta418 |  | 57/0 | 2026-01-30 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 418 | TA 418 | ta418 |  | 59/1 | 2026-02-05 | COMPLETED |  |  | TA 418 - DPR - 2026-05-21.xlsx | Erection Compiled
TA 419 | TA 419 | ta419 |  | 10/0 | 2025-08-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 11/0 | 2025-12-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 20/0 | 2025-02-20 | completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 20/1 | 2024-11-27 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 20/2 | 2024-12-03 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 20/3 | 2025-07-26 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 21/0 | 2025-10-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 22/0 | 2025-05-19 | completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 22/1 | 2025-02-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 22/2 | 2024-12-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 22/3 | 2024-12-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 23/0 | 2024-12-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 23/1 | 2024-12-17 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 23/2 | 2024-12-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 23/3 | 2025-03-12 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 24/0 | 2025-03-24 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 24/1 | 2025-01-09 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 24/2 | 2025-04-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 24/3 | 2025-04-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 25/0 | 2026-04-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/0 | 2025-10-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/1 | 2025-03-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/2 | 2025-08-03 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/3 | 2025-04-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/4 | 2025-04-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/5 | 2025-04-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 26/6 | 2025-04-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 27/0 | 2025-06-03 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 27/1 | 2025-06-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 27/2 | 2025-06-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 27/3 | 2025-06-26 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 28/0 | 2025-07-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 28/1 | 2025-04-21 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 29/0 | 2025-07-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 3/0 | 2026-03-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 3/2 | 2025-09-07 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 3/3 | 2025-10-12 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 30/0 | 2025-11-12 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 30/1 | 2025-04-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 31/0 | 2025-05-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 31/1 | 2025-04-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 31/2 | 2025-10-27 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 33/0 | 2026-05-09 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 33/1 | 2026-01-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 34/0 | 2025-07-17 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 34/1 | 2025-07-24 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 35/0 | 2025-11-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/0 | 2025-11-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/1 | 2025-08-01 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/10 | 2025-12-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/2 | 2025-08-07 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/5 | 2026-01-21 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/6 | 2025-10-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/7 | 2025-10-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 36/8 | 2025-11-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/0 | 2025-12-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/10 | 2025-12-19 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/11 | 2025-12-16 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/5 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/6 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/7 | 2025-11-25 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/8 | 2026-01-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 38/9 | 2025-12-21 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/0 | 2026-01-17 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/1 | 2026-05-14 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/2 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/3 | 2025-12-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/4 | 2025-11-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/5 | 2025-11-16 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/6 | 2025-11-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/7 | 2025-12-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/8 | 2026-05-19 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 40/9 | 2025-12-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/1 | 2025-12-16 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/3 | 2025-11-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/4 | 2025-11-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/5 | 2025-11-14 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/6 | 2025-12-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/7 | 2025-12-04 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 41/8 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 43/0 | 2025-12-26 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 43/4 | 2025-12-17 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 43/5 | 2025-12-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 43/6 | 2025-12-11 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 45/0 | 2025-12-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 46/1 | 2025-11-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 46/2 | 2025-11-25 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 46/3 | 2025-12-02 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 46/4 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/1 | 2026-04-12 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/2 | 2026-04-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/3 | 2025-12-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/4 | 2026-01-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/5 | 2026-04-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/6 | 2026-01-02 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 54/7 | 2026-04-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/0 | 2026-04-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/1 | 2026-01-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/2 | 2026-04-25 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/3 | 2026-04-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/4 | 2026-01-25 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/5 | 2026-01-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 55/6 | 2026-02-06 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 57/1 | 2026-02-11 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 59/1 | 2026-01-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/10 | 2024-12-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/11 | 2024-12-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/12 | 2024-12-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/3 | 2024-12-11 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/4 | 2025-01-27 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/5 | 2025-01-21 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/6 | 2025-02-24 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/7 | 2025-02-01 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/8 | 2024-11-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 6/9 | 2025-01-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 61/0 | 2026-05-26 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 62/1 | 2025-12-03 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 62/2 | 2025-12-17 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 62/3 | 2026-01-14 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 62/4 | 2025-12-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 62/5 | 2025-12-24 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63/0 | 2026-01-24 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63/1 | 2026-01-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63/2 | 2026-01-09 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63/4 | 2025-12-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63A/0 | 2026-01-13 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63B/0 | 2026-05-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 63B/1 | 2026-05-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 64/1 | 2026-05-06 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 64/2 | 2026-05-23 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 64/5 | 2026-05-10 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 64A/0 | 2026-05-24 | WIP |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 7/0 | 2026-01-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 7/1 | 2025-03-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 76/3 | 2026-01-05 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 78/0 | 2026-01-28 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 78/1 | 2026-04-22 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 78/2 | 2026-04-29 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 78/4 | 2026-01-07 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 83/0 | 2025-12-30 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 83/1 | 2025-12-08 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 83/5 | 2026-01-07 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 83/7 | 2025-12-20 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 84/1 | 2026-01-14 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 84/3 | 2026-01-04 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 84/4 | 2025-12-26 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 84/5 | 2026-01-18 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 84A/0 | 2026-01-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 419 | TA 419 | ta419 |  | 9/0 | 2025-12-31 | Completed |  |  | TA 419 - DPR - 2026-05-26.xlsx | ERECTION COMPILED
TA 421 | TA 421 | ta421 |  | 34/0 | 2025-06-25 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 34/1 | 2025-08-12 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 40/1 | 2025-09-05 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 41/0 | 2025-09-13 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 43A/3 | 2025-11-29 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 43A/4 | 2025-11-23 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 43A/5 | 2025-11-17 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 43B/0 | 2025-11-11 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 421 | TA 421 | ta421 |  | 44/0 | 2025-12-20 | Completed |  |  | TA 421 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 504 | TA 504 | ta504 |  | 10/1 | 2026-02-18 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 10/2 | 2025-11-24 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 13/3 | 2025-12-20 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 13/4 | 2025-12-14 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 13/5 | 2025-02-01 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 13/6 | 2025-02-05 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 24/1 | 2025-09-26 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 25/1 | 2026-02-10 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 25/2 | 2026-01-14 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 25/3. | 2024-12-27 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 25/4 | 2024-12-31 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/0 | 2026-01-07 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/1 | 2025-01-06 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/10 | 2025-11-11 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/2 | 2026-01-11 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/3 | 2025-01-17 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/4 | 2025-10-24 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/5 | 2025-01-13 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/6 | 2025-01-09 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/7 | 2025-12-30 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 26/8 | 2025-01-21 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 27/1 | 2025-10-16 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 28/0 | 2025-12-24 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 29/0 | 2025-12-14 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 29/1 | 2026-01-20 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 29/2 | 2025-09-26 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/0 | 2025-12-03 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/1 | 2025-11-02 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/2 | 2025-09-17 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/3 | 2026-01-16 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/4 | 2025-10-09 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 30/5 | 2025-10-18 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 31/0 | 2026-01-29 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 32/1 | 2026-02-08 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 33/0 | 2026-01-09 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 8/0 | 2026-04-07 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 8/1 | 2025-12-14 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 8/2 | 2026-01-08 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 504 | TA 504 | ta504 |  | 8/3 | 2025-12-29 | COMPLETED |  |  | TA 504 - DPR - 2026-05-27.xlsx | Tightening
TA 505 | TA 505 | ta505 |  | 123/0 | 2026-01-04 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 124/0 | 2026-02-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 129A/0 | 2026-01-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 129A/2 | 2025-11-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 129A/3 | 2025-06-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 130/0 | 2025-09-09 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 130/1 | 2025-09-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 130/2 | 2025-11-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 131/0 | 2025-09-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 135/3 | 2026-03-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 136/0 | 2025-09-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 136/3 | 2026-05-15 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 137A/0 | 2026-05-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 138/1 | 2026-02-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 138/2 | 2026-04-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 138/3 | 2026-03-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 139/0 | 2026-02-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 139/1 | 2026-02-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 141/0 | 2026-01-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 142/0 | 2026-01-23 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 142/1 | 2026-03-14 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 145/0 | 2025-12-09 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 146/0 | 2026-03-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 146/1 | 2026-02-13 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 147/0 | 2026-03-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 147/1 | 2025-07-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 147A/0 | 2025-10-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 148/0 | 2025-12-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 148A/0 | 2025-11-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 148B/1 | 2026-02-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 148B/2 | 2026-03-14 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 149B/1 | 2026-02-26 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 149B/2 | 2025-11-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 149B/3 | 2025-11-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 149B/4 | 2025-12-05 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 150/0 | 2025-07-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 151/0 | 2026-01-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152/0 | 2025-12-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152/1 | 2025-12-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152/2 | 2026-01-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152/3 | 2026-04-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/1 | 2025-05-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/10 | 2026-04-13 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/11 | 2026-04-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/12 | 2026-03-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/4 | 2025-05-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/5 | 2025-10-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/6 | 2025-12-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/7 | 2025-12-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/8 | 2025-06-05 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 152A/9 | 2025-06-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 154/1 | 2025-07-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 154/2 | 2025-06-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 154/3 | 2025-07-14 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 154/4 | 2025-12-16 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 154/5 | 2025-05-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/0 | 2026-04-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/1 | 2026-04-29 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/2 | 2026-05-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/3 | 2025-05-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/4 | 2025-06-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 155/5 | 2025-05-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/0 | 2025-10-04 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/1 | 2025-06-15 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/2 | 2026-05-13 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/3 | 2026-02-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/4 | 2025-06-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/5 | 2026-03-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 156/6 | 2026-02-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 158/1 | 2026-01-19 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 158/2 | 2025-10-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 158/3 | 2025-09-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 159/0 | 2025-11-02 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 159/1 | 2025-05-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 159/2 | 2025-09-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 159/3 | 2026-03-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 160/4 | 2025-06-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 160/5 | 2025-05-23 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/0 | 2025-11-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/1 | 2026-04-04 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/2 | 2025-09-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/3 | 2025-06-23 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/4 | 2025-05-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 161/5 | 2026-01-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 162/0 | 2026-05-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 163/0 | 2026-02-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/0 | 2026-03-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/2 | 2026-01-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/3 | 2025-12-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/4 | 2025-12-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/5 | 2025-12-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/6 | 2025-12-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/7 | 2025-12-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 164/8 | 2025-12-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/0 | 2025-11-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/1 | 2026-03-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/2 | 2026-03-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/3 | 2026-04-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/4 | 2026-01-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/5 | 2026-01-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 165/6 | 2025-11-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/0 | 2025-11-15 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/1 | 2025-09-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/2 | 2026-02-20 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/3 | 2026-04-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/4 | 2025-12-09 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/5 | 2025-12-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/6 | 2025-11-29 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 166/7 | 2025-11-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 168/0 | 2025-12-19 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/1 | 2025-11-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/2 | 2025-10-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/3 | 2025-09-29 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/4 | 2025-10-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/5 | 2025-10-16 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/6 | 2025-09-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/7 | 2025-10-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 169/8 | 2026-04-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/0 | 2025-12-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/1 | 2025-11-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/2 | 2026-05-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/4 | 2026-01-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/5 | 2026-04-13 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 170/9 | 2026-04-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/0 | 2026-04-09 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/1 | 2026-04-17 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/2 | 2026-03-16 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/3 | 2026-03-29 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/4 | 2026-03-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/6 | 2026-04-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/7 | 2026-04-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/8 | 2026-04-19 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 171/9 | 2026-01-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/0 | 2026-02-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/1 | 2025-12-12 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/2 | 2025-12-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/3 | 2025-11-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/4 | 2025-12-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 172/5 | 2026-03-04 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 173/2 | 2025-12-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 173/3 | 2026-01-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 173/4 | 2026-01-14 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/0 | 2025-11-23 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/1 | 2025-12-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/2 | 2025-11-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/3 | 2025-12-08 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/4 | 2026-04-30 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 174A/5 | 2026-02-15 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 175/1 | 2026-02-16 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 176/0 | 2026-03-21 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 176/2 | 2026-04-25 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 176/3 | 2026-04-26 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/0 | 2025-12-19 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/1 | 2025-12-27 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/2 | 2026-01-24 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/3 | 2026-01-02 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/4 | 2026-01-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 177/5 | 2026-01-18 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/0 | 2026-02-03 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/1 | 2026-02-10 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/2 | 2026-02-22 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/3 | 2025-12-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/4 | 2025-12-19 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 178/5 | 2025-12-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/1 | 2026-01-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/2 | 2026-01-06 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/4 | 2025-12-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/5 | 2025-12-28 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/6 | 2026-01-20 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/7 | 2026-04-07 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 179/9 | 2026-02-09 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 180/0 | 2026-05-13 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 181/0 | 2026-01-31 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 181/1 | 2025-12-26 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 181/4 | 2026-01-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 181/5 | 2026-01-11 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 505 | TA 505 | ta505 |  | 181/6 | 2025-12-20 | Completed |  |  | TA 505 - DPR - 2026-05-19.xlsx | Erection Compiled
TA 506 | TA 506 | ta506 |  | 100/1 | 2026-03-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 100/2 | 2025-09-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 101/0 | 2025-10-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 101/1 | 2025-10-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 107/1 | 2025-11-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 108/0 | 2026-03-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 109B/0 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 109B/1 | 2026-02-06 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 110/0 | 2025-11-06 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 111/0 | 2025-11-17 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 113/0 | 2025-12-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 113A/0 | 2026-01-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 114/0 | 2026-01-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 114/1 | 2025-11-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 117/1 | 2026-02-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 119/0 | 2025-12-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 120/0 | 2025-12-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 120/1 | 2026-02-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 122/0 | 2026-01-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 125/0 | 2026-02-16 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 125G/1 | 2026-03-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 125P/0 | 2026-03-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 128/0 | 2025-12-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 131/0 | 2026-02-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 131/1 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 133/1 | 2026-02-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 134/0 | 2026-02-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 134/1 | 2026-02-21 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 135/0 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 135/1 | 2025-12-07 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 135/2 | 2025-11-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 137/1 | 2026-01-21 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 137/2 | 2025-09-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 138/1 | 2026-01-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 141/0 | 2025-09-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 141/1 | 2025-09-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 142/0 | 2025-10-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 142/1 | 2025-09-29 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 145/1 | 2026-03-17 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 147/1 | 2026-01-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 147/2 | 2026-01-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 147/3 | 2026-01-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 156/0 | 2026-01-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 156/1 | 2026-01-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 156/2 | 2026-01-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 158/0 | 2026-02-16 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 158/1 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 159/1 | 2026-02-06 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 163/2 | 2025-09-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 164/0 | 2025-10-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 164/2 | 2025-08-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 166/0 | 2025-09-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 166/1 | 2026-01-16 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 166/2 | 2025-12-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 166/3 | 2026-01-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167/0 | 2025-07-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167/1 | 2025-10-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167/2 | 2025-12-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167A/0 | 2025-11-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167A/1 | 2026-02-08 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 167A/2 | 2025-07-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 172/1 | 2025-12-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 172/2 | 2026-01-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 172/3 | 2026-01-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 172/4 | 2026-01-13 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 175/1 | 2026-01-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 178/0 | 2026-01-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 181/2 | 2025-08-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 181/3 | 2026-03-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/0 | 2026-01-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/1 | 2025-08-29 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/2 | 2025-02-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/3 | 2025-04-13 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/4 | 2025-04-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/5 | 2025-03-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 182/6 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 183/1 | 2025-03-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 183/2 | 2025-04-08 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 183/3 | 2025-03-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 183/4 | 2025-09-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 183/5 | 2025-04-16 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 184/0 | 2025-09-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 184/2 | 2025-04-21 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 184/3 | 2025-06-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 185/0 | 2025-06-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 185/1 | 2025-02-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 185/2 | 2025-05-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 186/0 | 2025-09-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 186/1 | 2025-03-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 186/2 | 2025-04-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 187/0 | 2025-10-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 187/1 | 2025-04-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 187/2 | 2025-09-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 187A/0 | 2025-05-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 187A/1 | 2025-09-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 19/1 | 2025-09-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 19/2 | 2025-10-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 19/3 | 2025-10-08 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 19/4 | 2025-10-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 19/5 | 2025-10-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 190/0 | 2025-05-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 190/2 | 2025-05-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 190/3 | 2025-05-16 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 190/4 | 2025-05-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 191/0 | 2025-09-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 193/0 | 2026-01-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 193/1 | 2025-10-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 193/2 | 2025-10-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 194/0 | 2025-09-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 194/1 | 2025-10-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 194/2 | 2025-10-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 195/0 | 2026-01-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 195/1 | 2025-02-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 195/2 | 2025-07-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 195/3 | 2026-01-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 197/2 | 2025-11-02 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 197/3 | 2025-07-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/1 | 2026-01-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/2 | 2025-06-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/3 | 2026-03-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/4 | 2025-08-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/5 | 2025-06-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 199/6 | 2025-06-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 200/0 | 2025-06-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 200/1 | 2025-08-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 200/2 | 2025-02-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 200/3 | 2025-03-02 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 201/0 | 2025-07-08 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 202/0 | 2025-07-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 202/1 | 2025-08-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 202/2 | 2025-10-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 203/0 | 2026-04-13 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 204/0 | 2026-03-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 204/1 | 2025-08-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 205/0 | 2025-10-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 205/1 | 2025-10-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 205/2 | 2025-10-24 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 206/0 | 2025-10-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 206/1 | 2025-10-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 207/4 | 2026-05-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 210/8 | 2026-05-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 215/0 | 2025-12-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 218/0 | 2025-09-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 22/0 | 2025-09-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 220/3 | 2025-08-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 223/1 | 2025-08-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 224/0 | 2025-10-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 224/1 | 2025-12-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 227/0 | 2026-01-27 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 227/2 | 2025-12-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 25/0 | 2025-09-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 25/1 | 2025-08-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 25/2 | 2025-11-29 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 26/0 | 2025-11-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 26/1 | 2025-09-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 27/0 | 2025-09-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 28/0 | 2025-11-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 28/2 | 2025-08-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 30/0 | 2025-12-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 31/0 | 2025-12-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 31/1 | 2025-07-02 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 32/0 | 2025-07-23 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 32/1 | 2025-07-02 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 33/0 | 2025-09-05 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 34/2 | 2025-11-11 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 34/3 | 2025-07-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 35/0 | 2025-08-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 35A/0 | 2026-01-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 35A/1 | 2025-09-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 36/1 | 2025-11-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 36/2 | 2025-11-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 42/2 | 2025-11-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 42/4 | 2025-08-10 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 44A/0 | 2025-11-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 44A/1 | 2025-11-30 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 44A/2 | 2025-11-18 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 45/0 | 2025-12-01 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 46/0 | 2025-12-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 47/1 | 2025-12-06 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 54/2 | 2025-05-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 54/3 | 2025-05-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 55/0 | 2025-11-13 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 56/0 | 2025-11-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 60/0 | 2025-10-29 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 60/1 | 2025-11-28 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 60/2 | 2025-09-22 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 60/3 | 2025-09-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 72/2 | 2025-09-17 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 74/0 | 2025-12-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 75/0 | 2026-01-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 76A/0 | 2025-12-03 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 76A/1 | 2025-09-17 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 76F/0 | 2025-11-09 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 76G/0 | 2025-11-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 76G/1 | 2025-11-20 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 77/0 | 2025-11-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 78/0 | 2025-11-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 79/0 | 2025-09-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 92/0 | 2026-02-14 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 92A/0 | 2026-02-21 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 94/0 | 2025-11-25 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 94/1 | 2025-11-08 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 94/2 | 2025-11-15 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 94/3 | 2025-11-19 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 95/0 | 2025-11-06 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 95/1 | 2025-11-13 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 95A/0 | 2025-11-12 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 95A/1 | 2026-02-04 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 96/0 | 2026-02-26 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 506 | TA 506 | ta506 |  | 97/1 | 2025-10-31 | COMPLETED |  |  | TA 506 - DPR - 2026-05-27.xlsx | Tightening
TA 509 | TA 509 | ta509 |  | 10/0 | 2026-01-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 10/1 | 2025-10-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 10/2 | 2025-11-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 10/3 | 2026-01-10 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 11/0 | 2026-03-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/1 | 2025-09-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/2 | 2025-10-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/3 | 2025-11-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/4 | 2026-01-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/5 | 2026-01-19 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/6 | 2025-09-18 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 12/7 | 2026-03-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 13/0 | 2025-11-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 13/1 | 2025-10-13 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 13/2 | 2025-09-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 13/3 | 2026-04-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 13/4 | 2025-09-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/0 | 2026-01-19 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/1 | 2025-09-24 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/2 | 2025-09-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/3 | 2025-10-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/4 | 2026-04-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 14/5 | 2026-04-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/0 | 2026-02-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/1 | 2025-12-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/2 | 2025-09-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/3 | 2025-12-05 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/4 | 2025-11-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/5 | 2025-09-19 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/7 | 2025-12-19 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/8 | 2025-12-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 15/9 | 2025-12-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/0 | 2025-12-31 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/1 | 2025-09-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/10 | 2026-01-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/11 | 2025-10-01 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/2 | 2025-11-24 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/3 | 2026-02-03 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/4 | 2025-09-03 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/5 | 2026-01-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/6 | 2026-01-20 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/7 | 2025-10-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/8 | 2025-09-19 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 16/9 | 2025-09-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 17/0 | 2026-03-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 18/0 | 2026-02-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 18/1 | 2026-01-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 20/1 | 2025-09-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 20/2 | 2025-09-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 21/1 | 2026-05-07 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 21/2 | 2026-05-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 21/4 | 2025-12-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 22/1 | 2025-09-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/10 | 2026-02-08 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/11 | 2026-02-13 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/3 | 2026-05-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/6 | 2025-10-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/7 | 2025-10-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/8 | 2026-01-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 24/9 | 2026-02-01 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 25/0 | 2026-04-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 26/1 | 2026-02-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 26/2 | 2026-02-13 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 26/3 | 2026-04-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 26/4 | 2026-04-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/0 | 2026-02-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/1 | 2026-03-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/2 | 2026-04-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/3 | 2026-03-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/4 | 2026-04-01 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 27/5 | 2026-04-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 29/0 | 2026-05-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 29/1 | 2026-04-13 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 29/2 | 2026-04-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 30/0 | 2026-04-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 30/1 | 2026-04-05 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 30/2 | 2026-03-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 31/0 | 2026-05-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/0 | 2026-05-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/1 | 2026-02-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/2 | 2026-04-10 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/3 | 2025-12-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/4 | 2025-12-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/5 | 2026-01-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/6 | 2026-01-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 32/7 | 2026-02-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 33/0 | 2026-02-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 34/0 | 2026-04-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 34/1 | 2026-04-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 34/2 | 2026-05-18 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 34/3 | 2026-04-18 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/0 | 2026-02-26 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/1 | 2026-04-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/2 | 2026-04-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/3 | 2026-02-05 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/4 | 2026-04-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/5 | 2026-04-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/6 | 2026-04-13 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/7 | 2026-04-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 36/8 | 2026-05-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 37/0 | 2026-03-31 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/0 | 2026-02-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/1 | 2026-01-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/2 | 2026-01-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/3 | 2026-04-05 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/4 | 2026-05-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/6 | 2026-05-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/7 | 2026-05-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 38/8 | 2026-04-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/0 | 2026-03-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/1 | 2026-03-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/2 | 2026-03-20 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/3 | 2026-03-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/4 | 2026-03-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 39/5 | 2026-05-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 40/0 | 2026-02-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 40/1 | 2026-04-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 40/2 | 2026-04-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 40/3 | 2026-03-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 41/0 | 1970-01-01 | Peak u/p |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 45/0 | 2026-02-17 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 45/1 | 2026-04-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 45/3 | 2026-04-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 45/4 | 2026-04-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 45A/0 | 2026-03-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 46/0 | 2026-02-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 46/2 | 2026-04-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 46A/0 | 2026-05-08 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 46A/1 | 2026-04-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 46A/3 | 2026-05-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 47/1 | 2026-04-26 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 47/11 | 2026-01-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 47/8 | 2026-02-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 48/2 | 2026-02-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 48/4 | 2026-01-24 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 48/5 | 2026-04-07 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 48/8 | 2026-03-31 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 49/0 | 2026-02-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 49/1 | 2026-02-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 49/4 | 2026-05-17 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 49/6 | 2026-03-10 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/0 | 2026-04-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/1 | 2025-11-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/2 | 2026-04-26 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/3 | 2025-11-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/4 | 2026-02-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/5 | 2025-12-05 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/6 | 2026-02-17 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 5/7 | 2025-12-11 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 51/1 | 2026-03-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 51/2 | 2026-03-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 52/0 | 2026-03-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 52/1 | 2026-04-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 53/0 | 2026-03-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 53B/1 | 2026-04-07 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 55/1 | 2026-02-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 55/2 | 2026-04-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 6/0 | 2026-04-18 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 6/1 | 2026-02-27 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 6/2 | 2026-04-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 6/3 | 2026-01-03 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 63/1 | 2026-03-17 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 63/3 | 2026-04-30 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 64/0 | 2026-02-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/11 | 2026-02-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/2 | 2026-01-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/5 | 2026-04-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/7 | 2025-12-17 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/8 | 2026-03-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 65/9 | 2026-02-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/0 | 2025-12-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/2 | 2026-05-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/4 | 2026-04-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/5 | 2026-03-23 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/6 | 2026-03-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 66/8 | 2026-04-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 67/0 | 2026-04-15 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 67/2 | 2026-05-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 68/0 | 2026-01-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 7/0 | 2026-02-06 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 7/1 | 2026-02-12 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 7/2 | 2025-12-21 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 7/3 | 2025-12-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 7/4 | 2026-01-09 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/0 | 2025-12-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/1 | 2025-12-03 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/10 | 2025-10-16 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/2 | 2025-12-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/3 | 2025-12-28 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/4 | 2025-11-07 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/5 | 2025-09-08 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/6 | 2025-09-14 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/7 | 2025-09-20 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/8 | 2025-10-25 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 8/9 | 2025-10-22 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 9/0 | 2025-12-29 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 9/1 | 2025-09-26 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 9/2 | 2025-11-02 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 509 | TA 509 | ta509 |  | 9/3 | 2026-01-04 | COMPLETED |  |  | TA 509 - DPR - 2026-05-18.xlsx | ERECTION
TA 512 | TA 512 | ta512 |  | 11/1 | 2025-12-24 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/2 | 2025-12-30 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/3 | 2025-12-19 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/4 | 2025-12-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/5 | 2025-12-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/6 | 2026-01-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 11/8 | 2026-02-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 12/1 | 2025-10-18 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 12/2 | 2026-03-11 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 12/3 | 2025-11-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 12/4 | 2025-11-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 12/5 | 2025-11-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 13/0 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 18/1 | 2026-02-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 18/2 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 18/3 | 2025-11-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 18/4 | 2025-11-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 18/5 | 2025-08-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/0 | 2025-10-30 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/1 | 2025-09-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/2 | 2025-11-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/3 | 2025-11-15 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/4 | 2025-09-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/5 | 2025-09-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/6 | 2025-09-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 19/7 | 2025-09-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 1A/1 | 2026-02-28 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 1A/2 | 2026-03-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2/2 | 2026-02-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2/3 | 2026-03-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2/4 | 2026-02-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2/5 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2/6 | 2026-03-18 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/0 | 2026-01-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/1 | 2025-10-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/2 | 2025-10-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/3 | 2025-12-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/4 | 2025-12-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/5 | 2025-12-18 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/6 | 2026-01-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 20/7 | 2026-01-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 23/1 | 2026-02-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 23/2 | 2026-02-11 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 23/3 | 2026-02-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/0 | 2026-02-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/1 | 2025-10-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/2 | 2025-10-18 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/3 | 2026-02-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/4 | 2025-11-05 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/5 | 2025-10-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/6 | 2025-11-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 28/7 | 2025-10-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/0 | 2025-10-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/1 | 2025-12-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/10 | 2025-12-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/11 | 2026-01-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/12 | 2025-12-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/13 | 2026-01-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/14 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/15 | 2025-12-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/17 | 2026-01-17 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/2 | 2025-10-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/20 | 2026-01-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/21 | 2026-01-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/22 | 2026-02-01 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/3 | 2025-11-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/4 | 2025-11-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/5 | 2025-11-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/6 | 2025-11-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/7 | 2025-11-17 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/8 | 2025-12-28 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 29/9 | 2025-12-24 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 2A/4 | 2026-04-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3/3 | 2026-02-24 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3/4 | 2026-03-05 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3/5 | 2026-02-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3/6 | 2026-02-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3/7 | 2026-01-30 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/10 | 2025-12-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/11 | 2026-02-19 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/12 | 2025-12-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/13 | 2026-02-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/14 | 2025-12-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/17 | 2026-03-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/18 | 2025-09-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/2 | 2025-10-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/3 | 2026-02-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/4 | 2026-01-28 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/5 | 2026-01-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/6 | 2026-01-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/7 | 2025-10-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/8 | 2025-12-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 30/9 | 2026-03-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/1 | 2025-09-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/12 | 2026-02-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/13 | 2026-02-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/14 | 2026-02-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/15 | 2026-01-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/16 | 2026-01-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/17 | 2025-12-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/18 | 2026-01-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/19 | 2026-03-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/2 | 2025-09-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/20 | 2025-12-17 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/23 | 2026-03-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/25 | 2026-03-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/26 | 2025-12-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/27 | 2026-01-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/3 | 2026-01-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/4 | 2026-02-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/5 | 2026-01-18 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/6 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/7 | 2026-01-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/8 | 2026-02-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 31/9 | 2026-03-01 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 32/2 | 2026-04-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 33/2 | 2026-03-05 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 33/3 | 2026-04-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 33/4 | 2026-04-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/10 | 2026-03-10 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/3 | 2026-03-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/4 | 2026-05-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/5 | 2026-05-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/6 | 2026-03-10 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/7 | 2026-05-05 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/8 | 2026-05-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 34/9 | 2026-04-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/0 | 2026-02-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/1 | 2026-03-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/2 | 2026-04-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/3 | 2026-03-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/4 | 2026-03-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/5 | 2026-03-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/6 | 2026-03-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/7 | 2026-03-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/8 | 2026-03-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 35/9 | 2026-02-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 36/3 | 2026-03-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 36/6 | 2026-02-11 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 36/7 | 2026-02-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 36/8 | 2026-02-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/0 | 2026-03-29 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/10 | 2026-01-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/2 | 2026-04-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/3 | 2026-04-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/4 | 2026-04-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/5 | 2026-02-01 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/7 | 2026-01-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/8 | 2026-01-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 37/9 | 2026-01-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 38/0 | 2026-04-17 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3A/0 | 2026-04-04 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3A/1 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3A/2 | 2026-01-19 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 3A/3 | 2026-01-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/0 | 2026-01-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/10 | 2026-02-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/11 | 2026-04-12 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/12 | 2026-03-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/13 | 2026-03-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/14 | 2026-03-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/4 | 2026-02-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/6 | 2025-12-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/7 | 2026-01-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/8 | 2026-02-15 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 4/9 | 2026-02-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/1 | 2026-04-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/2 | 2026-03-30 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/3 | 2026-05-15 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/4 | 2026-05-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/5 | 2026-04-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 41/6 | 2026-04-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/0 | 2026-02-10 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/1 | 2026-02-28 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/10 | 2025-12-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/11 | 2025-12-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/2 | 2026-01-31 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/3 | 2026-02-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/4 | 2026-01-24 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/5 | 2025-12-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/6 | 2026-03-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/7 | 2026-03-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 5/9 | 2025-12-14 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/0 | 2026-01-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/1 | 2025-09-01 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/10 | 2026-02-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/2 | 2026-01-17 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/3 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/4 | 2026-02-02 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/5 | 2026-02-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/6 | 2026-02-08 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/7 | 2026-02-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/8 | 2026-01-13 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 6/9 | 2026-03-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/0 | 2026-02-25 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/1 | 2025-09-11 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/10 | 2026-01-19 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/11 | 2026-01-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/3 | 2025-09-23 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/4 | 2025-09-16 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/5 | 2026-02-05 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/6 | 2025-09-01 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/7 | 2026-01-28 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/8 | 2025-08-26 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 7/9 | 2025-08-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/0 | 2025-12-22 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/1 | 2025-12-06 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/2 | 2026-03-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/3 | 2025-08-10 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/4 | 2026-02-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/5 | 2025-09-10 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/6 | 2025-09-03 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/7 | 2025-08-27 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 8/8 | 2025-08-20 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 9/0 | 2025-10-09 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 9/1 | 2025-12-07 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 9/2 | 2025-09-19 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 9/3 | 2025-09-24 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 512 | TA 512 | ta512 |  | 9/4 | 2026-01-21 |  |  |  | TA 512 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 24/4 | 2025-10-03 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 25/0 | 2025-10-14 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 25/1 | 2025-09-29 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 25/2 | 2025-09-22 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 26/0 | 2025-10-19 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 26/2 | 2025-10-09 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-F | ta513eresf | Ere S-F | 27/0 | 2025-10-25 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-F
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 28/2 | 2025-11-03 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 28/3 | 2025-10-31 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 28/4 | 2025-11-10 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/0 | 2025-11-26 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/1 | 2025-12-07 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/2 | 2025-12-01 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/3 | 2025-11-18 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/4 | 2025-11-06 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 29/5 | 2025-11-14 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 30/0 | 2025-12-14 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 51/2 | 2026-05-18 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 51/4 | 2026-05-23 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 52/4 | 2026-04-07 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 54/3 | 2026-03-07 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 54/5 | 2026-03-16 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 54/6 | 2026-02-03 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 54/7 | 2026-03-20 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 54/8 | 2026-03-31 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 55/1 | 2026-03-24 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 55/5 | 2025-12-24 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 55/6 | 2026-01-22 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 56/1 | 2026-03-11 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 513 | TA 513 - Ere S-P | ta513eresp | Ere S-P | 56/2 | 2026-01-29 |  |  |  | TA 513 - DPR - 2026-05-26.xlsx | Ere S-P
TA 515 | TA 515 | ta515 |  | 194/9 | 2026-03-18 | Completed |  |  | TA 515 - DPR - 2026-05-11.xlsx | Erection Compiled
TA 515 | TA 515 | ta515 |  | 232/3 | 2026-03-08 | Completed |  |  | TA 515 - DPR - 2026-05-11.xlsx | Erection Compiled
TA 515 | TA 515 | ta515 |  | A+9 | 1970-01-01 | 0 |  |  | TA 515 - DPR - 2026-05-11.xlsx | Erection Compiled
TA 515 | TA 515 | ta515 |  | D60+0 | 1970-01-01 | 0 |  |  | TA 515 - DPR - 2026-05-11.xlsx | Erection Compiled
TA 515 | TA 515 | ta515 |  | Old | 1970-01-01 | 0 |  |  | TA 515 - DPR - 2026-05-11.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/0 | 2026-04-12 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/1 | 2026-02-05 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/2 | 2026-01-31 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/4 | 2026-03-29 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/5 | 2026-02-24 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/6 | 2026-03-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/7 | 2025-03-23 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 100/8 | 2026-03-04 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/0 | 2026-03-03 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/1 | 2026-02-20 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/2 | 2026-02-12 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/3 | 2026-02-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/5 | 2026-03-02 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/6 | 2026-03-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 101/7 | 2026-03-20 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 102/1 | 2026-02-27 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 102/2 | 2026-02-22 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 102/3 | 2026-02-24 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 102/4 | 2026-02-17 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 102/5 | 2026-02-19 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 51/9 | 2026-03-05 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 52/0 | 2026-02-21 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 53/1 | 2026-02-25 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 53/2 | 2026-02-28 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 53/4 | 2026-04-01 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 53/5 | 2026-04-07 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 55/1 | 2026-02-17 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 55/3 | 2026-03-18 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/2 | 2026-02-26 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/3 | 2026-03-08 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/4 | 2026-03-25 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/6 | 2026-02-11 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/7 | 2026-02-20 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/8 | 2026-02-09 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 56/9 | 2026-02-13 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 58/1 | 2026-01-10 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 58/2 | 2026-01-10 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 58/3 | 2026-01-14 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 59/2 | 2025-12-27 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 59/4 | 2026-01-21 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 59/5 | 2026-01-27 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 60/0 | 2026-05-18 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 60/2 | 2026-02-02 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/1 | 2026-01-13 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/10 | 2026-01-30 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/2 | 2026-01-08 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/3 | 2025-12-31 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/4 | 2026-01-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/7 | 2026-01-21 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 77/9 | 2026-02-28 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 79/2 | 2026-01-31 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 79/3 | 2026-02-04 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 80/1 | 2026-01-25 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 80/5 | 2026-01-20 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 81/1 | 2026-02-13 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 82/1 | 2026-01-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 83/1 | 2026-03-09 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 84/0 | 2026-02-10 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 84/1 | 2026-01-28 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 84/3 | 2026-01-21 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 84/4 | 2026-01-24 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 84/5 | 2026-02-05 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 85/1 | 2026-03-11 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 85/2 | 2026-02-03 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/10 | 2026-01-27 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/11 | 2026-01-21 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/6 | 2026-02-09 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/7 | 2026-01-29 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/8 | 2026-02-03 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 601 | TA 601 | ta601 |  | 99/9 | 2026-02-16 | Erection Completed. |  |  | TA 601 - DPR - 2026-05-26.xlsx | Erection Compiled
TA 602 | TA 602 | ta602 |  | 102/7 | 2026-05-04 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 109/1 | 2026-05-10 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 109/2 | 2026-05-16 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 109/5 | 2025-05-21 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 111/1 | 2026-05-14 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 111/2 | 2026-05-18 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 116/1 | 2026-05-09 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 116/2 | 2026-05-04 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/1 | 2026-05-08 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/2 | 2026-05-04 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/4 | 2026-05-12 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/5 | 2026-05-20 |  |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/6 | 2026-05-18 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 121/7 | 2026-05-16 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 122/2 | 2026-02-28 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 124/4 | 2026-04-02 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 125/2 | 2026-02-22 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 125/3 | 2026-03-28 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 126/10 | 2026-03-07 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 126/3 | 2026-03-23 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 126/4 | 2026-03-19 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 126/5 | 2026-03-15 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 126/9 | 2026-03-11 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 129A/3 | 2026-03-10 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 129A/4 | 2026-03-14 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 130/1 | 2026-02-28 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 130/2 | 2026-03-19 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 130/3 | 2026-03-22 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/2 | 2026-03-27 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/3 | 2026-03-30 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/4 | 2026-04-03 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/5 | 2026-04-19 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/7 | 2026-04-15 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/8 | 2026-04-07 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 134/9 | 2026-04-11 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/1 | 2026-04-28 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/2 | 2026-04-23 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/3 | 2026-05-02 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/4 | 2026-05-04 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/5 | 2026-05-08 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 136/8 | 2026-05-18 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 139/1 | 2025-05-21 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 139/2 | 2026-05-12 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TA 602 | TA 602 | ta602 |  | 139/5 | 2026-05-15 | Completed |  |  | TA 602 - DPR - 2026-05-21.xlsx | Erection
TB 401 | TB 401 | tb401 |  | 1/0 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/0 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/1 | 2025-10-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/10 | 2024-11-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/11 | 2024-11-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/12 | 2024-11-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/13 | 2024-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/14 | 2024-09-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/15 | 2025-10-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/16 | 2025-09-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/17 | 2025-09-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/18 | 2024-10-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/19 | 2024-09-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/20 | 2024-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/21 | 2024-10-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/22 | 2025-12-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/23 | 2025-11-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/3 | 2024-09-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/4 | 2024-09-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/5 | 2024-09-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/6 | 2024-09-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/7 | 2024-10-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/8 | 2024-11-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 10/9 | 2024-10-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/0 | 2025-11-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/1 | 2025-12-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/10 | 2025-12-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/11 | 2024-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/12 | 2024-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/13 | 2024-12-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/14 | 2024-11-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/15 | 2024-11-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/2 | 2025-11-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/3 | 2025-10-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/4 | 2025-07-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/5 | 2024-10-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/6 | 2024-11-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/7 | 2024-10-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/8 | 2024-10-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 11/9 | 2024-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 12/0 | 2025-07-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 13/0 | 2024-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 13/1 | 2024-11-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 13/2 | 2025-12-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 13/3 | 2025-12-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 13/4 | 2025-12-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/0 | 2025-07-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/1 | 2025-07-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/2 | 2024-11-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/3 | 2025-09-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/4 | 2024-09-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/5 | 2024-09-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 14/6 | 2025-11-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/0 | 2024-10-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/1 | 2024-11-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/2 | 2024-09-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/3 | 2024-09-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/4 | 2024-09-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/5 | 2025-07-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/6 | 2024-11-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/7 | 2025-07-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/8 | 2025-07-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 15/9 | 2024-11-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/0 | 2024-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/1 | 2025-08-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/2 | 2024-09-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/3 | 2024-09-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/4 | 2024-09-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/5 | 2024-10-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 16/6 | 2025-08-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/0 | 2024-10-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/1 | 2025-11-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/2 | 2025-11-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/3 | 2025-10-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/4 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 17/5 | 2025-08-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/0 | 2025-08-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/1 | 2025-07-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/10 | 2025-11-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/2 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/4 | 2025-10-10 | Complete ROW resolve after 26 days letter (ROW since 10.09.25) |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/6 | 2025-11-21 | Completed (ROW since 21.10.25 to 21.11.25 ) |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/7 | 2025-10-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/8 | 2025-08-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 18/9 | 2025-08-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/0 | 2025-08-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/1 | 2025-12-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/10 | 2025-10-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/11 | 2025-11-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/13 | 2025-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/14 | 2024-10-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/2 | 2025-10-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/3 | 2025-11-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/4 | 2025-12-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/5 | 2025-11-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/6 | 2025-12-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/7 | 2024-11-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/8 | 2025-11-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 19/9 | 2025-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/0 | 2025-07-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/1 | 2025-03-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/2 | 2025-03-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/3 | 2025-06-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/4 | 2025-06-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/5 | 2025-06-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/6 | 2025-06-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 1A/7 | 2025-07-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/0 | 2025-08-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/1 | 2025-08-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/2 | 2025-09-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/3 | 2025-08-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/4 | 2025-08-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/5 | 2025-07-31 | Cross arm |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/6 | 2025-08-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/7 | 2025-08-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/8 | 2025-07-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 2/9 |  | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 20/0 | 2025-08-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/0 | 2025-08-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/1 | 2025-12-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/11 | 2025-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/12 | 2025-08-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/13 | 2025-09-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/14 | 2025-08-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/2 | 2025-07-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/3 | 2025-07-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/4 | 2025-07-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/5 | 2025-07-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/6 | 2025-07-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/7 | 2025-07-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/8 | 2025-07-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 21/9 | 2025-11-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/0 | 2025-08-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/1 | 2025-08-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/2 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/3 | 2025-07-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/4 | 2025-07-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/5 | 2025-07-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/6 | 2025-07-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/7 | 2025-07-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/8 | 2025-12-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 22/9 | 2025-07-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/0 | 2025-08-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/1 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/10 | 2025-07-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/11 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/2 | 2025-08-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/3 | 2025-07-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/4 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/5 | 2025-08-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/6 | 2025-07-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/7 | 2025-07-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/8 | 2025-07-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 23/9 | 2025-08-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/0 | 2025-07-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/1 | 2025-08-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/2 | 2025-07-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/3 | 2025-07-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/4 | 2025-07-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/5 | 2025-06-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 24/6 | 2025-06-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/0 | 2025-11-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/1 | 2025-07-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/10 | 2025-07-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/11 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/2 | 2025-08-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/3 | 2025-07-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/4 | 2025-08-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/5 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/6 | 2025-07-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/7 | 2025-07-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/8 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 25/9 | 2025-07-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/0 | 2025-07-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/1 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/2 | 2025-07-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/3 | 2025-08-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/4 | 2025-09-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/5 | 2025-09-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/6 | 2025-09-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 26/7 | 2025-08-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/0 | 2025-10-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/1 | 2025-08-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/2 | 2025-08-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/3 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/4 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 27/5 | 2025-07-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/0 | 2025-07-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/1 | 2025-07-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/2 | 2025-07-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/3 | 2025-08-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/4 | 2025-08-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/5 | 2025-09-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/6 | 2025-10-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/7 | 2025-09-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/8 | 2025-07-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 28/9 | 2025-07-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/0 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/1 | 2025-07-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/10 | 2024-07-06 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/2 | 2025-07-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/3 | 2025-07-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/4 | 2025-07-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/5 | 2024-02-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/6 | 2024-06-08 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/7 | 2024-02-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/8 | 2024-02-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 29/9 | 2024-06-24 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 3/0 | 2025-11-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 30/0 | 2025-08-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 30/1 | 2025-07-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 30/2 | 2025-07-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 30/3 | 2025-11-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 31/0 | 2024-12-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 31/1 | 2025-08-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 31/2 | 2024-07-22 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 31/3 | 2024-07-12 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 31/4 | 2024-08-04 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/0 | 2024-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/1 | 2024-11-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/2 | 2024-08-20 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/3 | 2024-11-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/4 | 2024-10-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/5 | 2024-08-01 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/6 | 2024-08-09 |  |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/7 | 2025-08-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 32/8 | 2025-08-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/0 | 2025-07-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/1 | 2025-08-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/2 | 2025-08-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/3 | 2025-07-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/4 | 2025-07-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/5 | 2025-05-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/6 | 2025-07-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/7 | 2025-07-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 33/8 | 2025-07-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/0 | 2025-07-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/1 | 2025-07-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/2 | 2025-07-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/3 | 2025-07-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/4 | 2025-05-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/5 | 2025-07-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 34/6 | 2025-06-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/0 | 2025-05-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/1 | 2025-06-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/2 | 2025-06-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/3 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/4 | 2025-07-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/5 | 2025-04-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/6 | 2025-04-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/7 | 2025-04-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/8 | 2025-04-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 35/9 | 2025-04-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 36/0 | 2025-06-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/0 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/1 | 2025-05-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/2 | 2025-01-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/3 | 2024-12-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/4 | 2025-01-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/5 | 2025-01-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/6 | 2025-01-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/7 | 2025-01-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 37/8 | 2025-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/0 | 2025-02-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/1 | 2024-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/2 | 2024-12-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/3 | 2024-12-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/4 | 2025-03-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/5 | 2025-03-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/6 | 2025-03-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/7 | 2025-03-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/8 | 2025-03-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 38/9 | 2025-03-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/0 | 2025-02-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/1 | 2025-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/2 | 2025-05-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/3 | 2025-05-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/4 | 2025-05-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/5 | 2025-06-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/6 | 2025-06-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 39/7 | 2025-07-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 4/0 | 2025-08-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 4/1 | 2025-08-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 4/2 | 2025-10-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 4/3 | 2025-08-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 4/4 | 2025-08-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/0 | 2025-03-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/1 | 2025-03-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/10 | 2024-11-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/11 | 2024-10-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/12 | 2025-02-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/2 | 2025-01-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/3 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/4 | 2025-03-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/5 | 2025-03-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/6 | 2025-02-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/7 | 2025-02-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/8 | 2025-06-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 40/9 | 2025-06-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/0 | 2025-01-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/1 | 2025-01-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/10 | 2024-01-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/11 | 2024-01-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/12 | 2024-12-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/2 | 2024-12-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/3 | 2025-01-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/4 | 2024-02-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/5 | 2024-01-31 | Bottom complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/6 | 2024-02-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/7 | 2024-01-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/8 | 2024-02-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 41/9 | 2024-02-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 42/0 | 2024-12-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/0 | 2025-02-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/1 | 2024-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/2 | 2024-10-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/3 | 2024-10-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/4 | 2024-01-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/5 | 2024-01-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 43/6 | 2024-09-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/0 | 2025-02-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/1 | 2024-02-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/2 | 2024-01-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/3 | 2024-01-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/4 | 2024-01-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 44/5 | 2025-05-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 45/0 | 2025-05-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 46/0 | 2025-06-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 46/1 | 2025-06-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 46/2 | 2024-02-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 46/3 | 2024-01-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 46/4 | 2024-08-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 47/0 | 2024-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 47/1 | 2024-09-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 47/2 | 2024-01-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 47/3 | 2023-12-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 48/0 | 2024-01-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 48/1 | 2023-12-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 48/2 | 2023-12-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 49/0 | 2025-02-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 5/0 | 2025-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 50/0 | 2024-09-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 50/1 | 2024-09-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 50/2 | 2024-09-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 50/3 | 2023-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 50/4 | 2023-12-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/0 | 2024-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/1 | 2024-02-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/10 | 2023-11-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/2 | 2023-10-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/3 | 2023-11-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/4 | 2023-10-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/5 | 2023-10-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/6 | 2024-01-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/7 | 2023-11-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/8 | 2024-01-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 51/9 | 2023-12-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/0 | 2024-01-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/1 | 2023-10-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/2 | 2023-11-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/3 | 2024-05-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/4 | 2023-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 52/5 | 2023-11-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 53/0 | 2024-04-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 53/1 | 2024-02-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 53/2 | 2024-01-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 53/3 | 2023-11-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 53/4 | 2023-12-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/0 | 2024-04-04 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/1 | 2023-12-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/10 | 2023-12-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/11 | 2023-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/2 | 2023-12-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/3 | 2023-12-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/4 | 2023-12-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/5 | 2023-11-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/6 | 2023-12-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/7 | 2023-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/8 | 2023-12-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 55/9 | 2023-12-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/0 | 2024-01-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/1 | 2024-04-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/2 | 2023-12-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/3 | 2023-11-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/4 | 2023-12-02 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/5 | 2023-12-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/6 | 2023-12-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/7 | 2023-11-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/8 | 2023-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 56/9 | 2023-11-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/0 | 2023-12-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/1 | 2023-11-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/10 | 2023-10-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/11 | 2023-09-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/12 | 2023-10-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/13 | 2023-10-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/2 | 2023-10-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/3 | 2023-10-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/4 | 2023-10-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/5 | 2023-10-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/6 | 2023-12-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/7 | 2023-11-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/8 | 2023-11-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 57/9 | 2023-09-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/0 | 2024-04-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/1 | 2023-10-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/10 | 2023-10-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/11 | 2023-10-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/12 | 2023-09-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/13 | 2024-12-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/14 | 2023-10-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/15 | 2023-12-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/16 | 2023-10-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/2 | 2024-05-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/3 | 2023-10-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/4 | 2023-11-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/5 | 2023-10-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/6 | 2023-11-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/7 | 2024-01-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/8 | 2023-10-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 58/9 | 2023-10-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/0 | 2023-12-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/1 | 2023-11-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/2 | 2023-11-24 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/3 | 2023-11-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/4 | 2025-01-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/5 | 2023-11-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 59/6 | 2023-11-07 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 6/0 | 2025-09-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 6/1 | 2025-09-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 6/2 | 2025-09-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 60/0 | 2025-02-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 61/0 | 2025-03-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 61/1 | 2023-12-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 61/2 | 2023-12-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 62/0 | 2025-05-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/0 | 2025-05-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/1 | 2025-04-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/2 | 2025-04-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/3 | 2025-04-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/4 | 2025-04-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/5 | 2025-04-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 63/6 | 2025-04-20 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/0 | 2025-06-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/1 | 2025-06-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/2 | 2025-06-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/3 | 2025-06-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/4 | 2025-07-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/5 | 2025-06-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/6 | 2025-05-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/7 | 2025-06-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/8 | 2025-05-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 64/9 | 2025-05-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/0 | 2025-06-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/1 | 2025-07-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/2 | 2025-06-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/3 | 2024-05-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/4 | 2024-05-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/5 | 2024-05-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/6 | 2024-12-18 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 65/7 | 2024-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 66/0 | 2024-12-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 66/1 | 2024-12-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 66/2 | 2024-10-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 66/3 | 2025-06-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 66/4 | 2024-11-14 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 67/0 | 2024-12-08 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 67/1 | 2024-10-19 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/0 | 2024-11-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/1 | 2024-10-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/2 | 2024-10-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/3 | 2024-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/4 | 2024-11-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/5 | 2024-11-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 68/6 | 2024-11-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/0 | 2024-11-30 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/1 | 2024-11-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/2 | 2024-11-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/3 | 2024-11-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/4 | 2024-11-09 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/5 | 2024-11-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/6 | 2024-10-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/7 | 2024-10-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/8 | 2024-12-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 69/9 | 2024-12-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 7/0 | 2025-10-21 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 70/0 | 2024-12-31 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/0 | 2024-12-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/1 | 2024-10-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/2 | 2024-09-26 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/3 | 2024-10-23 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/4 | 2024-09-22 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 71/5 | 2024-09-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/0 | 2024-09-16 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/1 | 2024-10-03 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/2 | 2024-09-29 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/3 | 2024-09-01 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/4 | 2024-09-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/5 | 2024-09-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/6 | 2024-09-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 72/7 | 2024-09-25 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 73/0 | 2024-10-17 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/0 | 2025-10-13 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/1 | 2025-10-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/10 | 2025-07-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/11 | 2025-07-15 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/12 | 2025-08-05 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/2 | 2025-09-10 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/3 | 2025-11-12 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/4 | 2025-08-28 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/5 | 2025-09-11 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/6 | 2025-01-06 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 8/9 | 2025-06-27 | Complete |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 401 | TB 401 | tb401 |  | 9/0 | 2025-10-25 | Complete (ROW) work start with police proctution on date 27.-09.25 |  |  | TB 401 - DPR - 2025-12-25.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 13/0 | 2026-03-05 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 14A/2 | 2026-01-14 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 18/4 | 2024-09-27 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 19/0 | 2024-10-26 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 19/1 | 2026-01-07 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 19/3 | 2025-12-30 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 20/0 | 2025-09-29 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 20/1 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 20/3 | 2025-09-03 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/0 | 2025-09-05 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/1 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/10 | 2026-04-20 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/2 | 2026-03-31 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/4 | 2025-09-12 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/5 | 2025-09-22 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/6 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/7 | 2026-04-27 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/8 | 2026-03-31 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 21/9 | 2026-03-26 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/0 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/1 | 2026-04-20 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/12 | 2026-05-04 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/2 | 2025-12-31 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/3 | 2026-01-09 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/4 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/5 | 2025-12-31 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/6 | 2025-12-26 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/8 | 2026-02-28 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 22/9 | 2026-03-27 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 23/0 |  | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 25/0 | 2026-01-30 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 25/3 | 2025-08-09 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 26/1 | 2025-09-16 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 26/2 | 2025-07-24 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 26/3 | 2025-07-28 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 26/5 | 2025-11-27 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 26/6 | 2026-01-11 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 27/0 | 2025-09-03 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 27/9 | 2025-12-19 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 28/3 | 2025-12-24 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 28/4 | 2025-12-27 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 29/1 | 2025-08-04 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 29/3 | 2025-09-23 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 30/0 | 2025-11-26 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 37/1 | 2025-10-17 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 37/2 | 2025-10-24 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 408 | TB 408 | tb408 |  | 37/3 | 2025-10-30 | COMPLETED | No |  | TB 408 - DPR - 2026-05-11.xlsx | Erection Compiled
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 10/0 | 2025-12-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 11/0 | 2026-01-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 12/0 | 2026-01-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 12/1 | 2026-01-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 13/0 | 2026-01-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 13/1 | 2026-01-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 13/2 | 2026-01-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 14/0 | 2026-01-10 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 15/0 | 2026-02-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 15/1 | 2026-01-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 15/2 | 2025-12-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 15/3 | 2025-12-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 16/0 | 2025-12-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 16/1 | 2025-11-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 16/2 | 2025-11-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 17/0 | 2025-08-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 18/0 | 2025-12-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 3/0 | 2026-04-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 3/1 | 2026-04-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 4/0 | 2026-03-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 4/1 | 2026-03-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 4/2 | 2026-03-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 5/0 | 2026-03-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 6/0 | 2026-02-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 6/1 | 2026-02-11 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 6/2 | 2026-03-18 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 6/3 | 2026-02-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 6/4 | 2026-03-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 7/0 | 2026-02-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 8/0 | 2026-02-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 132kV | tb501132kv | 132kV | 9/0 | 2026-02-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-132kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 0/0 | 2025-04-09 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 0/1 | 2025-04-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1/0 | 2025-04-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1/1 | 2025-04-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1/2 | 2025-03-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-10 | 2025-03-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 10/1 | 2025-05-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 10/2 | 2025-03-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 10/3 | 2025-03-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 10/4 | 2025-04-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-11 | 2025-05-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 11/1 | 2025-03-14 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-12 | 2025-03-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-13 | 2025-05-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 13/1 | 2025-11-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-14 | 2025-05-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/1 | 2025-10-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/2 | 2025-10-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/3 | 2025-10-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/4 | 2025-11-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/5 | 2025-10-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/6 | 2025-11-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/7 | 2025-01-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/8 | 2025-02-01 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 14/9 | 2025-02-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-15 | 2025-02-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/1 | 2024-12-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/2 | 2024-12-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/3 | 2024-12-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/4 | 2025-02-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/5 | 2025-02-09 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/6 | 2025-02-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/7 | 2025-02-11 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/8 | 2025-02-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 15/9 | 2025-02-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-16 | 2025-02-15 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 16/1 | 2025-02-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 16/2 | 2025-02-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 16/3 | 2025-02-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-17 | 2025-02-09 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 17/1 | 2025-02-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 17/2 | 2025-02-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 17/3 | 2025-01-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-18 | 2025-02-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/1 | 2024-12-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/10 | 2025-01-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/11 | 2025-01-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/2 | 2024-12-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/3 | 2025-01-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/4 | 2025-01-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/5 | 2025-01-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/6 | 2025-01-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/7 | 2025-01-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/8 | 2025-01-10 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 18/9 | 2025-01-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-19 | 2025-01-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 19/1 | 2025-01-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 19/2 | 2025-01-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 19/3 | 2025-01-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 19/4 | 2025-01-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 19/5 | 2025-05-10 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1A/0 | 2025-04-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1A/1 | 2025-04-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1A/2 | 2025-04-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1B/0 | 2025-04-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1C/0 | 2026-03-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1C/1 | 2025-05-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1D/0 | 2025-03-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1D/1 | 2025-03-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 1E/0 | 2025-05-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 2/0 | 2025-04-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-20 | 2025-02-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/1 | 2025-02-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/2 | 2025-02-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/3 | 2025-03-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/4 | 2025-03-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/5 | 2025-02-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/6 | 2025-03-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/7 | 2025-02-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 20/8 | 2025-11-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-21 | 2025-03-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/1 | 2025-05-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/10 | 2025-02-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/11 | 2025-05-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/12 | 2025-03-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/13 | 2025-05-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/2 | 2025-05-15 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/3 | 2025-02-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/4 | 2025-02-09 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/5 | 2025-02-11 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/6 | 2025-02-14 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/7 | 2025-02-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/8 | 2025-02-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 21/9 | 2025-02-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-22 | 2025-02-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 22/1 | 2025-03-01 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 22/2 | 2025-02-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-23 | 2025-08-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 23/1 | 2025-03-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 23/2 | 2025-03-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 23/3 | 2025-05-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 23/4 | 2025-03-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 23/5 | 2025-05-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-24 | 2025-06-11 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-25 | 2025-07-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-26 | 2025-06-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-27 | 2025-07-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-28 | 2025-06-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 28/1 | 2025-10-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 28/2 | 2025-08-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-29 | 2025-06-15 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 29A/0 | 2025-08-14 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 29A/1 | 2025-02-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 29A/2 | 2025-02-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 29A/3 | 2025-02-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 29A/4 | 2025-02-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 3/0 | 2025-05-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-30 | 2025-02-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/1 | 2025-02-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/2 | 2025-03-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/3 | 2025-02-01 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/4 | 2025-03-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/5 | 2025-03-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 30/6 | 2025-03-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-31 | 2025-03-02 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 31/1 | 2025-07-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-32 | 2025-07-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 32/1 | 2025-05-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 32/2 | 2025-05-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 33/0 (New) | 2026-05-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 33/1 (New) | 2026-05-15 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 34/0 (New) | 2026-05-21 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/0 | 2025-05-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/1 | 2025-03-26 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/10 | 2025-03-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/11 | 2025-03-12 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/12 | 2025-06-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/13 | 2025-03-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/14 | 2025-03-18 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/15 | 2025-03-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/16 | 2025-03-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/17 | 2025-03-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/2 | 2025-03-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/3 | 2025-03-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/4 | 2025-03-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/5 | 2025-03-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/6 | 2025-03-10 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/7 | 2026-01-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/8 | 2025-12-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 4/9 | 2025-03-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5/0 | 2025-07-16 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5/1 | 2025-04-13 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5/2 | 2025-03-28 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5/3 | 2025-03-31 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5A/0 | 2025-03-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5A/1 | 2025-11-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5A/2 | 2025-11-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 5B/0 | 2025-11-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 6/0 | 2025-12-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 7/0 | 2025-04-10 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 7/1 | 2025-04-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 7/2 | 2025-04-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 7/3 | 2025-04-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8/0 | 2025-06-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8A/0 | 2025-04-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8B/0 | 2025-04-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8B/1 | 2025-04-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8B/2 | 2025-04-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8C/0 | 2025-06-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/0 | 2025-04-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/0A | 2025-12-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/1 | 2025-11-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/2 | 2025-12-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/3 | 2025-11-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/4 | 2025-11-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/5 | 2025-11-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8D/6 | 2025-11-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/0 | 2025-11-09 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/1 | 2025-06-25 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/10 | 2025-06-14 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/11 | 2025-06-17 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/12 | 2025-07-08 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/2 | 2025-06-11 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/3 | 2025-06-24 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/4 | 2025-06-23 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/5 | 2025-06-27 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/6 | 2025-06-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/7 | 2025-12-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/8 | 2025-06-22 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 8E/9 | 2025-06-19 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | AP-9 | 2025-07-04 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/1 | 2025-07-06 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/2 | 2025-07-03 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/3 | 2025-07-05 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/4 | 2025-07-07 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/5 | 2025-07-30 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/6 | 2025-06-29 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/7 | 2025-07-01 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/8 | 2025-03-15 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 501 | TB 501 - 220kV | tb501220kv | 220kV | 9/9 | 2025-05-20 | C |  |  | TB 501 - DPR - 2026-05-25.xlsx | Progress-220kV
TB 507 | TB 507 | tb507 |  | 1/1 | 2026-04-06 | COMPLETE |  |  | TB 507 - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 | tb507 |  | 1/2 | 2026-04-15 | COMPLETE |  |  | TB 507 - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 | tb507 |  | 2/1 | 2026-04-26 | COMPLETE |  |  | TB 507 - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/14 | 2026-05-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/2 | 2026-05-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/5 | 2026-04-17 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/6 | 2026-04-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/7 | 2026-04-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 10/8 | 2026-04-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 102/1 | 2026-05-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 102/2 | 2026-01-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 104B/2 | 2025-12-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 105/1 | 2025-05-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 109A/0 | 2025-11-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 110/0 | 2025-10-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 111/0 | 2025-11-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 112/0 | 2025-10-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 113/0 | 2026-01-17 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 113A/0 | 2025-09-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 114/0 | 2026-01-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 114/1 | 2025-09-26 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 115/0 | 2025-10-13 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 115/1 | 2025-11-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 116/0 | 2025-10-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 116/1 | 2025-09-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 117/1 | 2026-05-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 118/0 | 2026-01-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 119/1 | 2025-12-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 119/2 | 2025-12-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 120/1 | 2025-12-25 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 123/0 | 2025-12-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 125/3 | 2026-01-04 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 126/0 | 2026-01-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 126/1 | 2025-12-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 126/2 | 2025-12-12 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 127/1 | 2026-01-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 128/0 | 2025-11-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 128/1 | 2026-02-08 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 129/0 | 2025-11-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 129/1 | 2025-11-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 129/2 | 2026-01-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 130/0 | 2025-12-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 130/1 | 2026-02-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 131/0 | 2026-02-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 131/1 | 2025-11-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 131/2 | 2025-11-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 132/0 | 2026-02-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 132/1 | 2025-11-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 132/2 | 2026-02-13 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 132/3 | 2025-11-04 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 132/4 | 2025-11-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/0 | 2025-10-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/1 | 2025-10-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/2 | 2025-09-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/3 | 2025-09-22 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/4 | 2025-10-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/5 | 2025-11-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/6 | 2025-09-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/7 | 2025-10-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 133/8 | 2025-10-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134/0 | 2025-10-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134A/0 | 2025-10-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134A/1 | 2025-11-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134A/2 | 2025-10-26 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134A/3 | 2025-11-25 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 134A/4 | 2025-11-06 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 135/0 | 2025-11-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 135/1 | 2025-10-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 135/2 | 2025-11-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 135/3 | 2025-11-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 136/0 | 2025-11-08 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 137/0 | 2025-11-12 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 138/0 | 2025-10-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 138/1 | 2025-10-13 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 138/2 | 2025-10-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 138/3 | 2025-10-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 139/0 | 2025-10-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 139/1 | 2025-12-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 140/0 | 2025-12-13 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 140/1 | 2025-12-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 140/2 | 2025-10-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 140/3 | 2025-10-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 141/0 | 2025-10-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 141/1 | 2025-09-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 141/2 | 2025-09-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 142/0 | 2025-10-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/0 | 2025-09-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/1 | 2025-09-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/2 | 2025-09-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/3 | 2025-09-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/4 | 2025-09-17 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/5 | 2025-09-17 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/6 | 2025-09-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 143/7 | 2025-09-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 144/0 | 2025-10-08 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 145/0 | 2025-11-17 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 145/1 | 2025-09-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 145/2 | 2025-09-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 145/3 | 2025-09-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 145/4 | 2025-09-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 146/0 | 2025-10-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 146/1 | 2025-10-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 146/2 | 2025-10-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/0 | 2025-10-12 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/1 | 2025-10-22 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/2 | 2025-10-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/3 | 2025-10-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/4 | 2025-10-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/5 | 2025-10-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/6 | 2025-10-26 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/7 | 2025-10-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/8 | 2025-10-22 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 147/9 | 2025-10-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/0 | 2025-11-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/1 | 2025-10-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/2 | 2025-09-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/3 | 2025-09-04 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/4 | 2025-08-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/5 | 2025-09-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/6 | 2025-09-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 148/7 | 2025-09-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149/0 | 2025-10-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149A/0 | 2025-10-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149B/0 | 2025-11-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149B/1 | 2025-09-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149B/2 | 2025-09-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 149B/3 | 2025-11-22 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 150/0 | 2025-12-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 151/0 | 2025-12-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 152/0 | 2025-11-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 153/0 | 2026-01-04 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 153A/0 | 2025-11-01 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 154/0 | 2025-12-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 64/7 | 2026-03-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 65/0 | 2026-03-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 65/1 | 2026-03-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 66/0 | 2026-03-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 66/1 | 2026-03-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 7/1 | 2026-05-03 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 7/6 | 2026-05-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 7/7 | 2026-04-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 7/8 | 2026-05-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 7/9 | 2026-04-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 71/2 | 2026-01-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 71/3 | 2026-01-13 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 72/0 | 2026-05-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 72/2 | 2025-12-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 73/0 | 2025-12-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 73/1 | 2026-05-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 73/2 | 2025-08-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 73/3 | 2025-08-08 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 74/1 | 2025-07-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/0 | 2025-08-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/1 | 2025-08-04 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/2 | 2025-07-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/3 | 2025-07-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/4 | 2025-07-25 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/5 | 2025-07-22 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/6 | 2025-07-18 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 75/7 | 2025-07-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 76/0 | 2025-10-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 76/1 | 2025-09-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/0 | 2025-11-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/1 | 2025-07-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/2 | 2025-06-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/3 | 2025-07-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/4 | 2025-07-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 77/5 | 2025-07-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 78/0 | 2025-08-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 78/1 | 2025-11-25 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 79/0 | 2025-08-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 79/1 | 2025-11-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 79/2 | 2025-09-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 8/1 | 2026-05-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 8/2 | 2026-05-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 80/0 | 2025-11-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 80/1 | 2025-08-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/0 | 2025-12-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/1 | 2025-12-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/2 | 2025-09-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/3 | 2025-08-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/4 | 2025-09-09 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 81/5 | 2025-12-26 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 82/0 | 2025-11-20 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 82/1 | 2025-09-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 82/2 | 2025-10-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 83/0 | 2026-01-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 83/1 | 2025-09-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 84/0 | 2025-12-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 85/0 | 2025-12-16 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 85/1 | 2025-08-23 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 86/0 | 2025-12-31 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 86/1 | 2025-08-28 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 89/1 | 2026-01-05 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 9/2 | 2026-05-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 9/3 | 2026-05-06 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 9/4 | 2026-05-08 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 9/5 | 2026-05-12 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 90/0 | 2026-02-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 90/1 | 2025-12-26 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 91/1 | 2026-02-27 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 91/3 | 2026-05-14 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 92/0 | 2026-05-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 93/0 | 2026-05-19 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 95/0 | 2025-12-07 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 95/1 | 2025-12-30 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 95A/0 | 2026-01-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 95A/1 | 2025-09-02 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 96/1 | 2025-09-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 97/0 | 2025-09-11 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 97/1 | 2025-09-21 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 98/0 | 2025-11-10 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 98/1 | 2025-09-24 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 98A/0 | 2025-10-15 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 98A/1 | 2025-10-01 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 507 | TB 507 - MAIN | tb507main | MAIN | 98B/0 | 2025-11-29 | COMPLETE |  |  | TB 507 [MAIN] - DPR - 2026-05-25.xlsx | Erection Compiled
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 15/1 | 2026-01-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 15/2 | 2026-01-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 15/3 | 2026-04-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP16 | 2026-04-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP17 | 2026-04-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP18 | 2026-01-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 18/1 | 2026-03-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 18/2 | 2026-03-04 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP19 | 2026-02-24 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 19/1 | 2026-02-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 19/2 | 2026-02-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP20 | 2026-04-15 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP23 | 2026-02-15 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 23/1 | 2026-02-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 23/4 | 2026-02-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 23/5 | 2026-02-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP24 | 2026-04-06 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP25 | 2026-03-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 25/1 | 2026-03-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 25/2 | 2026-03-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP26 | 2026-03-03 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 27/0 | 2025-11-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 27/1 | 2026-05-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP28 | 2026-05-26 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP29 | 2026-05-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/1 | 2026-03-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/2 | 2026-04-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/3 | 2026-05-09 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/4 | 2025-12-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/5 | 2025-12-03 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 29/6 | 2025-12-29 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP30 | 2026-04-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 30/2 | 2026-05-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 30/3 | 2026-01-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 30/4 | 2026-01-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 30/5 | 2026-01-18 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP31 | 2026-04-04 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 31/1 | 2026-02-01 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 31/2 | 2026-02-06 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 31/3 | 2026-02-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 31/4 | 2026-02-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 31/5 | 2026-03-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP32 | 2026-02-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 32/1 | 2026-02-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP33 | 2026-03-24 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 33/1 | 2026-05-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 33/2 | 2026-03-29 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP34 | 2026-05-14 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 37/1 | 2026-05-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP38 | 2026-05-26 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 38/1 | 2026-05-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 39/2 | 2026-02-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP40 | 2026-03-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 40/1 | 2026-02-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 40/2 | 2026-05-02 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 42/2 | 2026-05-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 42/3 | 2026-05-03 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP43 | 2026-04-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 43/1 | 2026-04-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 43/2 | 2026-04-06 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 43/3 | 2026-04-02 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 43/4 | 2026-04-14 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP44 | 2026-03-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 44/1 | 2026-03-24 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 44/2 | 2026-03-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 44/3 | 2026-03-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP45 | 2026-05-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 45/1 | 2026-03-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 45/2 | 2026-02-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP46 | 2026-05-15 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 46/1 | 2026-03-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 46/2 | 2026-04-18 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 46/3 | 2026-04-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 46/4 | 2026-04-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 46/5 | 2026-04-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | AP47 | 2026-05-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 47/1 | 2026-04-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 50A/3 | 2026-04-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 50A/7 | 2026-04-26 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Jammu | tb605jammu | Jammu | 50A/8 | 2026-04-29 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -Jammu
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP100 | 2026-03-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP102 | 2026-03-14 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP103 | 2026-03-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 103/1 | 2026-03-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP104 | 2026-03-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 104/1 | 2026-03-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP106 | 2026-03-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP111 | 2026-03-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP114 | 2026-04-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP115 | 2026-02-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 115/1 | 2026-03-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 116/1 | 2026-03-09 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP117 | 2026-02-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 117/1 | 2026-02-11 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 117/2 | 2026-02-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 117/3 | 2026-02-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP118 | 2026-05-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 118/1 | 2026-02-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP129 | 2026-05-15 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 130/1 | 2026-05-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 130/2 | 2026-03-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/1 | 2026-03-02 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/2 | 2026-05-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/3 | 2026-02-27 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/4 | 2026-02-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/5 | 2026-02-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 131/6 | 2026-03-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 132/1 | 2026-03-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP135 | 2026-04-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 135/1 | 2026-04-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 136/1 | 2026-03-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 136/2 | 2026-04-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 136/3 | 2026-04-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 137/1 | 2026-05-14 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 144/4 | 2026-05-04 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP145 | 2026-05-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 145/1 | 2026-04-04 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 145/2 | 2026-04-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP146 | 2026-04-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP147 | 2026-04-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 150/1 | 2026-04-26 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 150/2 | 2026-04-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 151/1 | 2026-04-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 151/2 | 2026-05-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 152/1 | 2026-04-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 152/3 | 2026-05-19 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 152/4 | 2026-05-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 153/1 | 2026-05-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 153/2 | 2026-05-23 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 155/1 | 2026-04-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 155/2 | 2026-04-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 155/3 | 2026-04-27 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP156 | 2026-03-29 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 156/1 | 2026-05-04 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 156/2 | 2026-04-09 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 156/3 | 2026-04-14 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 156/4 | 2026-03-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP157 | 2026-03-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 157/1 | 2026-04-03 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 67/1 | 2026-04-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 67/3 | 2026-05-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP68 | 2026-03-29 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP69 | 2026-04-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 69/1 | 2026-03-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 69/2 | 2026-03-24 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 69/3 | 2026-03-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP70 | 2026-04-07 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 70/2 | 2026-04-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 71/2 | 2026-03-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 71/3 | 2026-05-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP72 | 2026-05-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 72/1 | 2026-04-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 72/2 | 2026-04-30 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP74 | 2026-05-03 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP75 | 2026-04-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 76/1 | 2026-02-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 76/2 | 2026-02-27 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 76/3 | 2026-03-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP77 | 2026-03-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 77/1 | 2026-03-22 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 77/2 | 2026-03-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP79 | 2026-04-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP80 | 2026-04-05 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 82/1 | 2026-04-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 82/2 | 2026-05-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP85 | 2026-04-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 86/1 | 2026-05-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 87/2 | 2026-02-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 89/1 | 2026-02-06 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP90 | 2026-05-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 90/1 | 2026-05-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 90/2 | 2026-03-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 92/1 | 2026-02-28 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 92/2 | 2026-02-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 92/3 | 2026-02-16 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP93 | 2026-02-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 93/1 | 2026-05-10 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 93/2 | 2026-02-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP94 | 2026-02-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP95 | 2026-02-25 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 95/1 | 2026-03-15 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 95/2 | 2026-02-11 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 95/3 | 2026-02-08 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 95/4 | 2026-02-13 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP96 | 2026-02-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP97 | 2026-03-09 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 97/1 | 2026-02-12 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 97/2 | 2026-02-09 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 97/3 | 2026-02-17 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP98 | 2026-02-26 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 98/1 | 2026-02-20 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | AP99 | 2026-03-02 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - Punjab | tb605punjab | Punjab | 99/1 | 2026-04-27 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection-Punjab
TB 605 | TB 605 - SK | tb605sk | SK | AP27A | 2026-03-31 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -SK
TB 605 | TB 605 - SK | tb605sk | SK | 30/1 | 2026-03-24 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -SK
TB 605 | TB 605 - SK | tb605sk | SK | AP31 | 2026-05-21 | Completed |  |  | TB 605 - DPR - 2026-05-26.xlsx | Erection -SK
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 131/2 | 2026-04-23 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 29/2 | 2026-03-11 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 29/3 | 2026-03-04 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 29/4 | 2026-02-25 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 40/0 | 2026-04-12 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 40/1 | 2026-04-18 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 41/0 | 2026-04-30 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 58/1 | 2026-01-10 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 69/1 | 2026-04-21 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 69/2 | 2026-04-30 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 70/2 | 2026-02-17 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 70/3 | 2026-02-09 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 71/1 | 2026-01-23 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 71/2 | 2026-04-23 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 72/0 | 2026-05-04 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 72/6 | 2026-01-31 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 75/3 | 2026-02-28 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 76/3 | 2026-03-06 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 77/0 | 2026-03-15 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 81/0 | 2026-04-09 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 88/0 | 2026-04-11 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC
TB 608 | TB 608 - WIP-ERC | tb608wiperc | WIP-ERC | 91/8 | 2026-03-25 |  |  |  | TB 608 - DPR - 2026-04-05.xlsm | WIP-ERC

## Coverage
Coverage
project_code | project_display | data_bucket | has_erection_rows | has_tightening_values | has_usable_stringing_spans | erected_towers | tightened_towers | usable_stringing_spans | ready_to_string_spans | reason
TA 325 | TA 325 | PARTIAL | TRUE | FALSE | TRUE | 487 | 0 | 231 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TA 413 | TA 413 | INCLUDED | TRUE | TRUE | TRUE | 334 | 334 | 31 | 2 | Erection tower tightening and usable stringing spans are available.
TA 414 | TA 414 | INCLUDED | TRUE | TRUE | TRUE | 229 | 229 | 172 | 49 | Erection tower tightening and usable stringing spans are available.
TA 416 | TA 416 | INCLUDED | TRUE | TRUE | TRUE | 302 | 302 | 72 | 3 | Erection tower tightening and usable stringing spans are available.
TA 418 | TA 418 | INCLUDED | TRUE | TRUE | TRUE | 127 | 121 | 40 | 5 | Erection tower tightening and usable stringing spans are available.
TA 419 | TA 419 | PARTIAL | TRUE | TRUE | FALSE | 206 | 60 | 0 | 0 | Erection tower tightening is available, but no usable stringing spans were found.
TA 421 | TA 421 | INCLUDED | TRUE | TRUE | TRUE | 309 | 300 | 61 | 3 | Erection tower tightening and usable stringing spans are available.
TA 504 | TA 504 | INCLUDED | TRUE | TRUE | TRUE | 121 | 82 | 53 | 2 | Erection tower tightening and usable stringing spans are available.
TA 505 | TA 505 | INCLUDED | TRUE | TRUE | TRUE | 354 | 177 | 13 | 2 | Erection tower tightening and usable stringing spans are available.
TA 506 | TA 506 | INCLUDED | TRUE | TRUE | TRUE | 402 | 192 | 36 | 0 | Erection tower tightening and usable stringing spans are available.
TA 509 | TA 509 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 199 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 512 | TA 512 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 219 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 513 | TA 513 - Ere S-P | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 23 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 513 | TA 513 - Ere S-F | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 7 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 515 | TA 515 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 5 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 601 | TA 601 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 70 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TA 602 | TA 602 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 44 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 401 | TB 401 | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 514 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 401 | TB 401 - PKG-G | PARTIAL | FALSE | FALSE | TRUE | 0 | 0 | 74 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 408 | TB 408 | PARTIAL | TRUE | TRUE | FALSE | 485 | 438 | 0 | 0 | Erection tower tightening is available, but no usable stringing spans were found.
TB 501 | TB 501 - 132kV | PARTIAL | TRUE | FALSE | TRUE | 31 | 0 | 47 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 501 | TB 501 - 220kV | PARTIAL | TRUE | FALSE | TRUE | 200 | 0 | 81 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 507 | TB 507 | PARTIAL | TRUE | FALSE | TRUE | 3 | 0 | 1 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 507 | TB 507 - MAIN | PARTIAL | TRUE | FALSE | TRUE | 213 | 0 | 21 | 0 | Usable stringing spans are available, but no erection-sheet tower tightening values were found.
TB 605 | TB 605 - SK | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 3 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 605 | TB 605 - Jammu | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 80 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 605 | TB 605 - Punjab | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 113 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.
TB 608 | TB 608 - WIP-ERC | NO_TIGHTENING_OR_LINK | TRUE | FALSE | FALSE | 22 | 0 | 0 | 0 | No erection-sheet tower tightening values and no usable stringing span link were found.

## Assumptions
Assumptions
Topic | Assumption
Source policy | Only Tower Tightening Raw / Tower Tightening fields from erection compiled raw data are used.
Tightening complete tokens | dates; yes; y; true; ok; done; completed; complete; c
Tightening blocker tokens | no; n; false; pending; wip; balance; row; hold; blocked
Ready-to-string rule | All required locations erected and tightened, and no paying-out/final-sag/status completion recorded.
Span Buckets Stringing Ready | Uses ready_to_string, so already-strung spans are excluded from the leadership-ready count.
Assumed tightening complete | TA 413 and TA 416 are treated as tightened wherever tower erection is complete.
Location matching | Stringing endpoints plus Location Nos are matched to normalized erection location numbers by project scope, then project fallback.