## RawData
project_code | project_display | project_scope_key | line_name | line_name_source | section_label | report_date | source_file | source_sheet | configured_sheet | template_sheet | stringing_resolution_policy | header_row_number | source_row_number | activity_raw | activity_norm | quantity_loa | quantity_estimated_or_total | quantity_primary | cumulative_last_month | plan_for_month | progress_for_month | today_progress | cumulative_progress | balance_progress | gangs_working | remarks
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 4 | 0 | 316 | 3 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 7 | 2 | 244 | 75 | 11/307
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 0 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-10 | TA 512 - DPR - 2026-07-10.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-28 | TA 418 - DPR - 2026-06-28.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-28 | TA 418 - DPR - 2026-06-28.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-28 | TA 418 - DPR - 2026-06-28.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-28 | TA 418 - DPR - 2026-06-28.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 7.283 | 0 | 36.865 | 10.975 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 98.032 | 0 |  |  | 98.032 | 16.484
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 8 |  | 93 | 200 | 4 | ROW & Fronts are not cleared for further work
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-21 | TA 510 - DPR - 2026-06-21.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 6 | 0 | 314 | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 24 | 6 | 293 | 26
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 10 |  | 231 | 88 | 07/212
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 23 | 2 | 102 | 217
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-21 | TA 512 - DPR - 2026-06-21.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 8 |  | 72 | 327 | 3 | Loc-62/0-3Pit Casting compl(ROW) Loc-51/0-Casting WIP Loc-54/2-2 pit Block setting done Loc-58/2-Casting WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 3 |  | 27 | 372 | 2 | Loc-52/2-Tower Erection WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-21 | TA 513 - DPR - 2026-06-21.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 10 | 1 | 164 | 316 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 1 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 21 | 2 | 73 | 407 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-21 | TA 602 - DPR - 2026-06-21.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 29 | 0 | 399 | 124 | 27.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 35 | 0 | 343 | 180 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 31 | 2 | 234 | 289 | 13.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 2.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-21 | TB 605 - DPR - 2026-06-21.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 0 |  | 0 | 175.719
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 1 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 5 |  | 212 | 118 | 12 | 36/4, 37/0, 38/3, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/1 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-12 | TA 419 - DPR - 2026-06-12.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 1 | 310 | 9 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 3 | 1 | 224 | 95 | 06/206
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 14 | 1 | 93 | 226
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-12 | TA 512 - DPR - 2026-06-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 4 |  | 68 | 331 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting WIP Loc-74/7-Casting WIP Loc-54/2-Pit Collapse.
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-13 | TA 513 - DPR - 2026-06-13.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 0 | 20 | 2 | 390 | 133 | 25
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 0 | 16 | 1 | 219 | 304 | 11
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-12 | TB 605 - DPR - 2026-06-12.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 1 | 0 | 132 | 134 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 2 | 0 | 33 | 235 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 1 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-12 | TB 608 - DPR - 2026-06-12.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 11 | Route Alignment | route_alignment |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 12 | Detailed Survey | detailed_survey |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 13 | Check Survey | check_survey |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 14 | Foundation | foundation |  | 37 | 37 | 0 | 0 |  | 5 | 3 | 25 | 3.0 | 12
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 15 | Earthing-Pipe | earthing |  | 7 | 7 | 0 | 0 | 0 |  |  | 2 |  | 5
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 16 | Earthing-CP/SE/CE | earthing |  | 30 | 30 | 0 | 0 | 0 | 5 |  | 8 |  | 22
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 17 | Tower Erection | tower_erection |  | 37 | 37 | 0 | 0 |  | 6 |  | 0 |  | 37
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 18 | Tack welding | tack_welding |  | 134 | 134 | 134 | 0 | 0 | 0 | 1 | 52 | 1.0 | 82
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 19 | Stringing | stringing |  | 8.572 | 8.572 | 0 | 0 |  | 0 |  | 0 |  | 8.572
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 20 | Paying Out | paying_out |  | 52.39 | 52.39 | 52.39 |  |  |  |  | 15.1581 |  | 50.853
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 21 | Final Sag | final_sag |  | 52.39 | 52.39 | 52.39 |  |  |  |  | 15.1581 |  | 50.853
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 22 | OPGW | opgw_stringing |  | 8.572 | 8.572 | 0 |  |  |  |  | 0 |  | 8.572
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 23 | Foundation | foundation
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 14 | Soil Investigation | soil_investigation |  | 29 | 29 | 29 | 0 |  |  | 29 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 15 | Foundation | foundation |  | 484 | 484 | 484 | 0 |  |  | 484 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 16 | Earthing | earthing |  | 484 | 484 | 484 | 0 |  |  | 484 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 17 | Tower Erection | tower_erection |  | 484 | 484 | 482 | 2 | 2 |  | 484 | 0 | 3.0 | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 18 | Tack welding | tack_welding |  | 484 | 484 | 441 | 43 | 26 | 1 | 467 | 17 | 4.0 | 4 No Location WIP.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 19 | Stringing(Km) | stringing |  | 177.35 | 177.35 | 164.769 | 12.581 | 8.924 | 0 | 173.693 | 3.657 | 17.0 | 2.42 Km P/O and 2.42 Km F/S WIP
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-10 | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-10 | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-10 | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-10 | TA 418 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 0 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 |  |  | 283 | 26 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.492 |  | 118.925 | 2.417 | 2.0 | 43A/0 - 43A/1 - Insulator hosting done & 43B/0 -44/0 - WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 0.678 |  | 116.145 | 5.197 | 1.0 | WIP - 33/0- 34/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-10 | TA 421 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 1 |  | 145 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 |  |  | 121 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-10 | TA 504 - DPR - 2026-06-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 0 |  | 375 | 4 |  | 1 Locations are under severe RoW.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 3 |  | 360 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 0 |  | 15.462 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-09 | TA 505 - DPR - 2026-06-09.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 4.304 |  | 20.733 | 123.171 |  | 115/0-116/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 1 |  | 493 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 2 |  | 407 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-10 | TA 506 - DPR - 2026-06-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 3 | 1 | 88 | 205 | 5.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 |  |  | 80 | 213
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 4 |  | 44 | 249 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-10 | TA 510 - DPR - 2026-06-10.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 2 | 0 | 310 | 9
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 2 | 0 | 308 | 11 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 2 |  | 223 | 96 | 06/185
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 9 | 2 | 88 | 231
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-09 | TA 512 - DPR - 2026-06-09.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 4 | 1 | 68 | 331 | 4 | Loc-51/1-2 Pit PCC Done Loc-54/2-Steel Binding WIP(Pit Collapse) Loc-62/0-3Pit Casting compl(ROW) Loc-62/1-Casting compl Loc-74/7-4 pit PCC Compl
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 1 |  | 25 | 374 | 1 | Loc-56/4-Tower erection WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 | 1 | 26 | 194 | 1 | Loc-55/1-Casting compl
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-09 | TA 513 - DPR - 2026-06-09.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 5 | 0 | 129 | 163 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 2 | 0 | 104 | 188
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-10 | TA 601 - DPR - 2026-06-10.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | ¦ ROUTE ALIGNMENT | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 8 | 9 | ¦ ROUTE ALIGNMENT | route_alignment |  | 184.986 | 184.986 | 185.149 |  | 0 |  | 185.149 | 0
TA 602 | TA 602 | ta602 |  | filename | ¦ SOIL INVESTIGATION | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 11 | 12 | ¦ SOIL INVESTIGATION | soil_investigation |  | 31 | 31 | 17 |  | 1 |  | 18 | 13
TA 602 | TA 602 | ta602 |  | filename | ¦ DETAILED SURVEY | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 14 | 15 | ¦ DETAILED SURVEY | detailed_survey |  | 184.986 | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455
TA 602 | TA 602 | ta602 |  | filename | ¦ CHECK SURVEY | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 17 | 18 | ¦ CHECK SURVEY | check_survey |  | 184.986 | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847
TA 602 | TA 602 | ta602 |  | filename | ¦ FOUNDATION | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 20 | 21 | ¦ FOUNDATION | foundation |  | 480 | 480 | 154 |  | 7 |  | 161 | 319
TA 602 | TA 602 | ta602 |  | filename | ¦ EARTHING | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 23 | 24 | ¦ EARTHING | earthing |  | 480 | 480 | 96 |  | 8 |  | 104 | 376
TA 602 | TA 602 | ta602 |  | filename | ¦ TOWER ERECTION | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 26 | 27 | ¦ TOWER ERECTION | tower_erection |  | 480 | 480 | 52 |  | 9 |  | 61 | 419
TA 602 | TA 602 | ta602 |  | filename | ¦ STRINGING | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 29 | 30 | ¦ STRINGING | stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TA 602 | TA 602 | ta602 |  | filename | ¦ OPGW STRINGING | 2026-06-09 | TA 602 - DPR - 2026-06-09.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 32 | 33 | ¦ OPGW STRINGING | opgw_stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 5 | FOUNDATION | foundation |  | 521 | 521 | 519 | 2 | 1 |  | 520 | 1 | 0.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 6 | EARTHING | earthing |  | 521 | 521 | 494 | 27 | 1 |  | 495 | 26
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 7 | ERECTION | tower_erection |  | 521 | 521 | 502 | 19 | 12 |  | 514 | 7 | 2.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 8 | TACK WELDING | tack_welding |  | 521 | 521 | 356 | 35 | 31 |  | 387 | 134 | 3.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 10 | Strg (Final Sag) | final_sag |  | 202 | 202 | 119.886 | 51 | 16.203 |  | 136.089 | 65.911 | 4.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 11 | Stringing OPGW | opgw_stringing |  | 202 | 202 | 51.706 | 30 | 19.57 |  | 71.276 | 130.724 | 1.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 0 | 16 | 6 | 386 | 137 | 27
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 0 | 11 | 0 | 214 | 309 | 13
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-09 | TB 605 - DPR - 2026-06-09.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 0 | 0 | 131 | 135 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 2 | 1 | 33 | 235 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-09 | TB 608 - DPR - 2026-06-09.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 0 | 0 | 307 | 2
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 |  | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 2 | 0 | 257 | 49 | 1.0 | G_1:- M.S Enterprises (WIP 35/3 )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 15/0 to AP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0.243 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-06 | TA 413 - DPR - 2026-06-06.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 6 | 2 | 325 | 27
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 6 | 2 | 325 | 27 | 7.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 20 | 2 | 316 | 36
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 10 | 1 | 245 | 107 | 14.0 | 1 gang arrived on 08.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 22 | 4 | 142 | 210 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 0.226 |  | 21.844 | 105.955
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-09 | TA 414 - DPR - 2026-06-09.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-08 | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-08 | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-08 | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-08 | TA 416 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 0.807 | 0.282 | 111.94 | 3.194 | 5
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-08 | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-08 | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-08 | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-08 | TA 418 - DPR - 2026-06-08.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.3677 | 0.27649 | 30.9497 | 16.8903 | 3 | *Work Front Required for Hotline Gang
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 7 |  | 262 | 68 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 52/2, 59/0, 63B/3, 66/0, 74/0, 76/1, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 4 |  | 211 | 119 | 11 | 36/4, 38/3, 41/2, 42/0 ,52/1, 53/0, 62/0, 65/0 64/4, 71/0, 81/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-08 | TA 419 - DPR - 2026-06-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 |  |  | 283 | 26 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 1.814 |  | 118.247 | 3.095 | 3.0 | 34/0- 34/1 - Payingout under progress + 34/1 - 34/2 - Payingout under progress + 43A/0 - 43A/1 - Insulator hosting done
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 |  |  | 115.467 | 5.875 |  | 43A/1-43B/0 - Rough sag done & 33/0- 34/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-07 | TA 421 - DPR - 2026-06-07.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 1 |  | 145 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 |  |  | 121 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-09 | TA 504 - DPR - 2026-06-09.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 0 |  | 375 | 4 |  | 1 Locations are under severe RoW.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 3 |  | 360 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 0 |  | 15.462 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-08 | TA 505 - DPR - 2026-06-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 4.304 |  | 20.733 | 123.171 |  | 115/0-116/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 1 |  | 493 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 2 |  | 407 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-09 | TA 506 - DPR - 2026-06-09.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 88 | 205
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 2 |  | 87 | 206 | 5.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 |  |  | 80 | 213
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 3 | 1 | 43 | 250 | 3.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-08 | TA 510 - DPR - 2026-06-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 2 | 0 | 310 | 9
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 2 | 0 | 308 | 11 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 2 |  | 223 | 96 | 05/144
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 7 | 2 | 86 | 233
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-08 | TA 512 - DPR - 2026-06-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 3 | 2 | 67 | 332 | 5 | Loc-54/1-Casting compl Loc-54/2-Steel Binding WIP Loc-62/0-3Pit Casting compl Loc-62/1-2 Pit steel binding Compl Loc-74/8-Casting compl
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 1 |  | 25 | 374 | 1 | Loc-56/4-Tower erection WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 |  |  | 25 | 195 | 1 | Loc-55/1-Casting WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-07 | TA 513 - DPR - 2026-06-07.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 4 | 0 | 128 | 164 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 2 | 1 | 104 | 188
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-08 | TA 601 - DPR - 2026-06-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 32/0-33/0 Stringing WIP, Final checking Stringing WIP
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 0.95161 | 0 | 62.1516 | 1.8484 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 0.95161 | 0 | 62.1516 | 1.8484
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 10.389 | 0 | 64.1108 | -0.11079 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 0 | 0 | 36 | 3 | 1.0 | SC-2 and SC-4 Foundation WIP
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 0 | 0 | 31 | 8 | 1.0 | 2/1 and 1/0 Erection WIP
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-08 | TB 501 - DPR - 2026-06-08.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 4 |  | 312 | 201 | 5.0 | 45.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 3 |  | 221 | 292 | 4.0 | 79.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 |  |  | 104 | 409 | 1.0 | 3.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 40.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-08 | TB 507 [MAIN] - DPR - 2026-06-08.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 1 |  | 35 | 5 | 2.0 | 20.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-08 | TB 507 - DPR - 2026-06-08.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 88 | 10 | 0 | 380 | 143 | 27
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 82 | 0 | 0 | 308 | 215 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 80 | 9 | 1 | 212 | 311 | 13
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 80 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-07 | TB 605 - DPR - 2026-06-07.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 14.92 | 0 | 0 | 0 | 175.719 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 0 | 0 | 131 | 135 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 1 | 0 | 32 | 236 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-07 | TB 608 - DPR - 2026-06-07.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 1 | 308 | 1
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 5 | 1 | 260 | 46 | 1.0 | G_1:- M.S Enterprises (WIP 22/0 )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 15/0 to AP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-10 | TA 413 - DPR - 2026-06-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | LOC no 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 7 | 1 | 262 | 44 | 1.0 | G_1:- M.S Enterprises
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.243 | 0 | 77.432 | 40.4189 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-11 | TA 413 - DPR - 2026-06-11.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 6 |  | 325 | 27
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 6 |  | 325 | 27 | 7.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 21 | 1 | 317 | 35
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 10 | 1 | 245 | 107 | 14.0 | 1 gang arrived on 08.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 26 | 3 | 146 | 206 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 0.226 |  | 21.844 | 105.955
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 4.4432 |  | 20.3872 | 107.4118
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-10 | TA 414 - DPR - 2026-06-10.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-11 | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-11 | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-11 | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-11 | TA 418 - DPR - 2026-06-11.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 1.8367 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 5 |  | 212 | 118 | 11 | 36/4, 37/0, 38/3, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-11 | TA 419 - DPR - 2026-06-11.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 1 |  | 145 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 |  |  | 121 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-11 | TA 504 - DPR - 2026-06-11.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 0 |  | 375 | 4
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 4.304 |  | 19.766 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-11 | TA 505 - DPR - 2026-06-11.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 8.164 |  | 23.626 | 123.171 |  | 115/0-116/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 1 |  | 493 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 4 |  | 409 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 2.32 |  | 57.952 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-11 | TA 506 - DPR - 2026-06-11.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 4 | 1 | 89 | 204 | 5.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 |  |  | 80 | 213
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 4 |  | 44 | 249 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-11 | TA 510 - DPR - 2026-06-11.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 1 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 3 | 0 | 309 | 10 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 2 |  | 223 | 96 | 06/206
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 13 | 2 | 92 | 227
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-11 | TA 512 - DPR - 2026-06-11.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 4 |  | 68 | 331 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting WIP Loc-74/7-Casting WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 1 |  | 25 | 374 | 2 | Loc-56/4-Tower erection U/P Loc-56/3-Material Shifting U/P
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-11 | TA 513 - DPR - 2026-06-11.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 5 | 0 | 129 | 163 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 2 | 0 | 104 | 188
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 1 | 0 | 72 | 220 | 5
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-11 | TA 601 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | ROUTE ALIGNMENT | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 8 | 9 | ROUTE ALIGNMENT | route_alignment |  | 184.986 | 184.986 | 185.149 |  | 0 |  | 185.149 | 0
TA 602 | TA 602 | ta602 |  | filename | SOIL INVESTIGATION | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 11 | 12 | SOIL INVESTIGATION | soil_investigation |  | 31 | 31 | 17 |  | 1 |  | 18 | 13
TA 602 | TA 602 | ta602 |  | filename | DETAILED SURVEY | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 14 | 15 | DETAILED SURVEY | detailed_survey |  | 184.986 | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455
TA 602 | TA 602 | ta602 |  | filename | CHECK SURVEY | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 17 | 18 | CHECK SURVEY | check_survey |  | 184.986 | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847
TA 602 | TA 602 | ta602 |  | filename | FOUNDATION | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 20 | 21 | FOUNDATION | foundation |  | 480 | 480 | 154 |  | 7 |  | 161 | 319
TA 602 | TA 602 | ta602 |  | filename | EARTHING | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 23 | 24 | EARTHING | earthing |  | 480 | 480 | 96 |  | 9 |  | 105 | 375
TA 602 | TA 602 | ta602 |  | filename | TOWER ERECTION | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 26 | 27 | TOWER ERECTION | tower_erection |  | 480 | 480 | 52 |  | 11 |  | 63 | 417
TA 602 | TA 602 | ta602 |  | filename | STRINGING | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 29 | 30 | STRINGING | stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TA 602 | TA 602 | ta602 |  | filename | OPGW STRINGING | 2026-06-11 | TA 602 - DPR - 2026-06-11.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 32 | 33 | OPGW STRINGING | opgw_stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 32/0-33/0-33/1 all Phase Final sag complet , Final checking Stringing WIP
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.5681 | 0 | 62.7681 | 1.2319 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.5681 | 0 | 62.7681 | 1.2319
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 0 | 0 | 36 | 3 | 1.0 | SC-4 Pit-A,C,D Steel Binding Done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 0 | 0 | 31 | 8 | 1.0 | 2/1 Erection second section WIP
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-09 | TB 501 - DPR - 2026-06-09.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 6 |  | 314 | 199 | 5.0 | 45.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 5 |  | 223 | 290 | 4.0 | 79.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 8 |  | 112 | 401 | 1.0 | 3.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 40.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-11 | TB 507 [MAIN] - DPR - 2026-06-11.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 1 |  | 35 | 8 | 2.0 | 20.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-11 | TB 507 - DPR - 2026-06-11.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 0 | 18 | 0 | 388 | 135 | 26
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 0 | 0 | 0 | 308 | 215 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 0 | 15 | 1 | 218 | 305 | 11
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-11 | TB 605 - DPR - 2026-06-11.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 1 | 1 | 132 | 134 | 6.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 2 | 0 | 33 | 235 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-10 | TB 608 - DPR - 2026-06-10.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | LOC no 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 7 | 0 | 262 | 44 | 1.0 | G_1:- M.S Enterprises
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13A/0 to 14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0.224 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 14/0 to AP 15/0 Spacering work)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-12 | TA 413 - DPR - 2026-06-12.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-10 | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-10 | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-10 | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-10 | TA 416 - DPR - 2026-06-10.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 0.807 | 0 | 111.94 | 3.194 | 5
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 0 |  | 375 | 4
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-13 | TA 505 - DPR - 2026-06-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 9.165 |  | 24.627 | 123.171 |  | 115/0-116/0= Hot line work Completed
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-13 | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-13 | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-13 | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-13 | TA 418 - DPR - 2026-06-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 8 |  | 327 | 25
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 8 |  | 327 | 25 | 7.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 29 |  | 325 | 27
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 14 | 2 | 249 | 103 | 15.0 | 1 gang arrived on 14.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 35 | 3 | 155 | 197 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-15 | TA 414 - DPR - 2026-06-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-14 | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-14 | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-14 | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-14 | TA 418 - DPR - 2026-06-14.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 9 |  | 264 | 66 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 6 |  | 213 | 117 | 12 | 36/4, 37/0, 38/2, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-14 | TA 419 - DPR - 2026-06-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 1 |  | 145 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 1 |  | 122 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 1.574 |  | 14.996 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-13 | TA 504 - DPR - 2026-06-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 0 |  | 375 | 4
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 132/354, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-14 | TA 505 - DPR - 2026-06-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 9.165 |  | 24.627 | 123.171 |  | 117/0-118/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 2 |  | 494 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 5 |  | 410 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 3.288 |  | 58.92 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-13 | TA 506 - DPR - 2026-06-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 6 | 2 | 91 | 202 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 |  |  | 82 | 211
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-14 | TA 510 - DPR - 2026-06-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 4 | 1 | 225 | 94 | 06/206
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 14 | 0 | 93 | 226
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-14 | TA 512 - DPR - 2026-06-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 6 | 2 | 70 | 329 | 3 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/0-Casting Compl Loc-61/1-Excavation WIP Loc-74/7-Casting Compl Loc-74/6-Excavation (Farmer Stop the Work) Loc-54/2-Boring & Dewatering WIP.
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-14 | TA 513 - DPR - 2026-06-14.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 7 | 0 | 131 | 161 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 2 | 0 | 104 | 188
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 3 | 0 | 74 | 218 | 5
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-14 | TA 601 - DPR - 2026-06-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | ROUTE ALIGNMENT | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 8 | 9 | ROUTE ALIGNMENT | route_alignment |  | 184.986 | 184.986 | 185.149 |  | 0 |  | 185.149 | 0
TA 602 | TA 602 | ta602 |  | filename | SOIL INVESTIGATION | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 11 | 12 | SOIL INVESTIGATION | soil_investigation |  | 31 | 31 | 17 |  | 1 |  | 18 | 13
TA 602 | TA 602 | ta602 |  | filename | DETAILED SURVEY | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 14 | 15 | DETAILED SURVEY | detailed_survey |  | 184.986 | 184.986 | 166.531 |  | 0 |  | 166.531 | 18.455
TA 602 | TA 602 | ta602 |  | filename | CHECK SURVEY | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 17 | 18 | CHECK SURVEY | check_survey |  | 184.986 | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847
TA 602 | TA 602 | ta602 |  | filename | FOUNDATION | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 20 | 21 | FOUNDATION | foundation |  | 480 | 480 | 154 |  | 7 |  | 161 | 319
TA 602 | TA 602 | ta602 |  | filename | EARTHING | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 23 | 24 | EARTHING | earthing |  | 480 | 480 | 96 |  | 9 |  | 105 | 375
TA 602 | TA 602 | ta602 |  | filename | TOWER ERECTION | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 26 | 27 | TOWER ERECTION | tower_erection |  | 480 | 480 | 52 |  | 12 |  | 64 | 416
TA 602 | TA 602 | ta602 |  | filename | STRINGING | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 29 | 30 | STRINGING | stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TA 602 | TA 602 | ta602 |  | filename | OPGW STRINGING | 2026-06-12 | TA 602 - DPR - 2026-06-12.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 32 | 33 | OPGW STRINGING | opgw_stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 8C/0 to 8D/3 Stringing final checking done, 33/1 Jumper done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation PCC completed,
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/1 Erection Completed
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-13 | TB 501 - DPR - 2026-06-13.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 6 |  | 314 | 199 | 6.0 | 45.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 5 |  | 223 | 290 | 4.0 | 79.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 12 | 1 | 116 | 397 | 1.0 | 3.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-12 | TB 507 [MAIN] - DPR - 2026-06-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 1 |  | 35 | 8 | 2.0 | 20.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-12 | TB 507 - DPR - 2026-06-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 0 | 21 | 1 | 391 | 132 | 26
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 0 | 17 | 0 | 325 | 198 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 0 | 21 | 0 | 224 | 299 | 12
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-14 | TB 605 - DPR - 2026-06-14.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 2
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 8 |  | 327 | 25
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 9 | 1 | 328 | 24 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 28 | 1 | 324 | 28
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 17 | 3 | 252 | 100 | 15.0 | 1 gang arrived on 14.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 40 | 3 | 160 | 192 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-16 | TA 414 - DPR - 2026-06-16.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-15 | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-15 | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-15 | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-15 | TA 418 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 |  |  | 283 | 26 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.492 |  | 118.925 | 2.417 | 1.0 | 43A/0 - 43A/1 - Conductor paying out under progress & 43B/0 -44/0 - WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 0.678 |  | 116.145 | 5.197 | 1.0 | WIP - 33/0- 34/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-11 | TA 421 - DPR - 2026-06-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 4.504 |  | 19.966 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-15 | TA 505 - DPR - 2026-06-15.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 9.165 |  | 24.627 | 123.171 |  | 117/0-118/0= Hot line work U/P
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 7 | 1 | 92 | 201 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 |  |  | 82 | 211
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-15 | TA 510 - DPR - 2026-06-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 4 | 1 | 225 | 94 | 06/206
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 15 | 1 | 94 | 225
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-15 | TA 512 - DPR - 2026-06-15.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 8 | 1 | 132 | 160 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 3 | 0 | 74 | 218 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-15 | TA 601 - DPR - 2026-06-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | ROUTE ALIGNMENT | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 8 | 9 | ROUTE ALIGNMENT | route_alignment |  | 184.986 | 184.986 | 185.149 |  | 0 |  | 185.149 | 0
TA 602 | TA 602 | ta602 |  | filename | SOIL INVESTIGATION | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 11 | 12 | SOIL INVESTIGATION | soil_investigation |  | 31 | 31 | 17 |  | 0 |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | DETAILED SURVEY | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 14 | 15 | DETAILED SURVEY | detailed_survey |  | 184.986 | 184.986 | 178.3635 |  | 11.83 |  | 178.3635 | 6.6225
TA 602 | TA 602 | ta602 |  | filename | CHECK SURVEY | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 17 | 18 | CHECK SURVEY | check_survey |  | 184.986 | 184.986 | 136.139 |  | 0 |  | 136.139 | 48.847
TA 602 | TA 602 | ta602 |  | filename | FOUNDATION | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 20 | 21 | FOUNDATION | foundation |  | 480 | 480 | 154 |  | 8 |  | 162 | 318
TA 602 | TA 602 | ta602 |  | filename | EARTHING | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 23 | 24 | EARTHING | earthing |  | 480 | 480 | 96 |  | 10 |  | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | TOWER ERECTION | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 26 | 27 | TOWER ERECTION | tower_erection |  | 480 | 480 | 52 |  | 17 |  | 69 | 411
TA 602 | TA 602 | ta602 |  | filename | STRINGING | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 29 | 30 | STRINGING | stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TA 602 | TA 602 | ta602 |  | filename | OPGW STRINGING | 2026-06-15 | TA 602 - DPR - 2026-06-15.xlsx | DPR Sheet | DPR-KEC | TA 602 Status | prefer_final_else_stringing | 32 | 33 | OPGW STRINGING | opgw_stringing |  | 184.986 | 184.986 | 0 |  | 0 |  | 0 | 184.986
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 0 | 23 | 2 | 393 | 130 | 26
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 0 | 23 | 0 | 331 | 192 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 0 | 23 | 2 | 226 | 297 | 12
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 0 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-15 | TB 605 - DPR - 2026-06-15.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 0 | 0 | 0 | 0 | 175.719 | 2
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 10 | 3 | 265 | 41 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13/0 to 14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-14 | TA 413 - DPR - 2026-06-14.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 6 |  | 213 | 117 | 12 | 36/4, 37/0, 38/2, 41/2, 42/0 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-15 | TA 419 - DPR - 2026-06-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-05-31 | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 258 | 25 | 10 |  | 268 | 41 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-05-31 | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 228 | 25 | 19 |  | 247 | 62
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-05-31 | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | erection_loc | 309 | 309 | 309 | 180 | 45 | 28 |  | 208 | 101 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-05-31 | TA 509 - DPR - 2026-05-31.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 118.397 | 118.397 |  |  |  |  | 0 | 118.397 | 0.0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 1 |  | 122 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-16 | TA 504 - DPR - 2026-06-16.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 3 |  | 495 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 6 |  | 411 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-16 | TA 506 - DPR - 2026-06-16.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 9 |  | 328 | 24
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 9 |  | 328 | 24 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 28 |  | 324 | 28
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 18 | 1 | 253 | 99 | 15.0 | 1 gang arrived on 14.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 41 | 1 | 161 | 191 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-17 | TA 414 - DPR - 2026-06-17.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-15 | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-15 | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-15 | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-15 | TA 416 - DPR - 2026-06-15.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 0.807 | 0 | 111.94 | 3.194 | 5
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-16 | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-16 | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-16 | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-16 | TA 418 - DPR - 2026-06-16.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 2.0953 | 31.2262 | 16.6138 | 4 | *Work Front Required for Hotline Gang
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 7 |  | 214 | 116 | 12 | 36/4, 37/0, 38/2, 41/2 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-16 | TA 419 - DPR - 2026-06-16.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 13 |  | 296 | 13 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.492 |  | 118.925 | 2.417 | 1.0 | 43B/0 -44/0 - WIP & 27/0-27/3-28/0 - Rectification work under Progress
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 1.644 |  | 117.111 | 4.231 | 1.0 | 43A/0 - 43A/1 - WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-16 | TA 421 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 93.542 | 0 |  |  | 93.542 | 20.974
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 7 |  | 92 | 201 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 | 1 | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-16 | TA 510 - DPR - 2026-06-16.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 5 | 0 | 226 | 93 | 06/195
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 17 | 2 | 96 | 223
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-16 | TA 512 - DPR - 2026-06-16.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 6 |  | 70 | 329 | 4 | Loc-51/1-Casting WIP Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting WIP Loc-74/6-Excavation (ROW) Loc-54/2-Boring & Dewatering WIP.
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 2 |  | 26 | 373 | 2 | Loc-56/3-Material Shifting U/P
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-15 | TA 513 - DPR - 2026-06-15.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 8 | 0 | 132 | 160 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 4 | 1 | 75 | 217 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-16 | TA 601 - DPR - 2026-06-16.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 8D/4 to 8E/1 Stringing final checking done,
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation pit-B,C &D steel binding wip
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/1 Erection Tighting wip and one side insulator hosting done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-15 | TB 501 - DPR - 2026-06-15.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 2 | 0 | 133 | 133 | 6.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 4 | 2 | 35 | 233 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-14 | TB 608 - DPR - 2026-06-14.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-16 | TA 505 - DPR - 2026-06-16.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 9.165 |  | 24.627 | 123.171 |  | 117/0-118/0= Hot line work U/P
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-16 | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-16 | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 1 |  | 248 | 61
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-16 | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 7 |  | 215 | 94 | 5.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-16 | TA 509 - DPR - 2026-06-16.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 |  |  |  |  | 0 | 119.178 | 1.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 17 | 2 | 69 | 411 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-16 | TA 602 - DPR - 2026-06-16.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 8 | 2 | 316 | 197 | 4.0 | 45.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 7 | 1 | 225 | 288 | 5.0 | 79.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 12 | 1 | 116 | 397 | 1.0 | 3.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 |  |  | 21.797 | 166.881 | 2.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-15 | TB 507 [MAIN] - DPR - 2026-06-15.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 2 | 1 | 36 | 7 | 2.0 | 20.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-15 | TB 507 - DPR - 2026-06-15.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 23 | 0 | 393 | 130 | 26
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 34 | 0 | 342 | 181 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 24 | 1 | 227 | 296 | 12
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-16 | TB 605 - DPR - 2026-06-16.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 0 | 0 | 0 | 175.719 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 1 |  | 122 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-17 | TA 504 - DPR - 2026-06-17.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 3 |  | 495 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 6 |  | 411 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-17 | TA 506 - DPR - 2026-06-17.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 13 |  | 296 | 13 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.492 |  | 118.925 | 2.417 | 1.0 | 43B/0 -44/0 - WIP & 27/0-27/3-28/0 - Rectification work under Progress
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 1.644 |  | 117.111 | 4.231 | 1.0 | 43A/0 - 43A/1 - WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-17 | TA 421 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 98.032 | 0 |  |  | 98.032 | 16.484
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 7 |  | 92 | 201 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-17 | TA 510 - DPR - 2026-06-17.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 5 | 0 | 226 | 93 | 07/220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 19 | 2 | 98 | 221
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-17 | TA 512 - DPR - 2026-06-17.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 7 | 1 | 71 | 328 | 4 | Loc-51/1-Casting compl Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting WIP Loc-74/6-Excavation (ROW) Loc-54/2-Boring & Dewatering WIP.
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 3 | 1 | 27 | 372 | 2 | Loc-56/3-Tower Erection completed
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-17 | TA 513 - DPR - 2026-06-17.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 9 | 1 | 133 | 159 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 4 | 0 | 75 | 217 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-17 | TA 601 - DPR - 2026-06-17.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 18 | 2 | 70 | 410 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-17 | TA 602 - DPR - 2026-06-17.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 4/9 to 4/10 Bottom Final sag done, 9/0 to 9/4 Stringing final checking done,
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation pit-A,B,C &D steel binding done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/0 Erection wip
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-17 | TB 501 - DPR - 2026-06-17.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 1 | 121.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 10 |  | 265 | 65 | 16 | 38/4, 39/0,44/0. 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 7 |  | 214 | 116 | 12 | 36/4, 37/0, 38/2, 41/2 ,52/1, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 35 | 295 | 1
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-17 | TA 419 - DPR - 2026-06-17.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 162/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-17 | TA 505 - DPR - 2026-06-17.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 9.165 |  | 24.627 | 123.171 |  | 117/0-118/0= Hot line work U/P
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-17 | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-17 | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 1 |  | 248 | 61
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-17 | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 7 |  | 215 | 94 | 5.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-17 | TA 509 - DPR - 2026-06-17.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 |  |  |  |  | 0 | 119.178 | 1.0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 1 |  | 122 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-18 | TA 504 - DPR - 2026-06-18.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 3 |  | 495 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 7 |  | 412 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-18 | TA 506 - DPR - 2026-06-18.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 0 | 0 | 302 | 4 | 1.0 | G_1:- Amit Kumar Singh (WIP 16/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 12 | 0 | 267 | 39 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (13/0 to 14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ROW )
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-16 | TA 413 - DPR - 2026-06-16.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 10 |  | 329 | 23
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 10 | 1 | 329 | 23 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 28 |  | 324 | 28
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 20 | 2 | 255 | 97 | 16.0 | 1 gang arrived on 14.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 43 | 2 | 163 | 189 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 1.893 |  | 23.511 | 104.288
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 5.1112 |  | 21.0552 | 106.7438
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-18 | TA 414 - DPR - 2026-06-18.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-17 | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-17 | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-17 | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-17 | TA 416 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 2.061 | 1.254 | 113.2 | 1.934 | 5
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 11 |  | 266 | 64 | 15 | 38/4, 39/0, 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 7 |  | 214 | 116 | 13 | 36/4, 37/0, 38/2, 41/2 ,52/1, 52/2, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 73/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-18 | TA 419 - DPR - 2026-06-18.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 13 |  | 296 | 13 | 1
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.977 | 0.485 | 119.41 | 1.932 | 2` | 43B/0 -44/0 - WIP & 40/0-41/0-42/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 2.129 | 0.485 | 117.596 | 3.746
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-18 | TA 421 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 1 |  | 122 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 4.407 |  | 17.829 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-19 | TA 504 - DPR - 2026-06-19.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 1 |  | 376 | 4 |  | Earthing-261/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 164/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 8.364 |  | 23.826 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-18 | TA 505 - DPR - 2026-06-18.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 11.114 |  | 26.576 | 123.171 |  | 117/0-118/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 3 |  | 495 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 8 |  | 413 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 3.53 |  | 59.162 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-19 | TA 506 - DPR - 2026-06-19.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-18 | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 4 |  | 272 | 37 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-18 | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-18 | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 8 |  | 216 | 93 | 5.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-18 | TA 509 - DPR - 2026-06-18.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 |  |  |  |  | 0 | 119.178 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.492 | 0 |  |  | 107.492 | 7.024
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 98.032 | 0 |  |  | 98.032 | 16.484
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 7 |  | 92 | 201 | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-18 | TA 510 - DPR - 2026-06-18.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 4 | 0 | 312 | 7
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/18
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  |  |  | 269 | 50
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 6 | 1 | 227 | 92 | 07/220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 20 | 1 | 99 | 220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-18 | TA 512 - DPR - 2026-06-18.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 8 | 1 | 72 | 327 | 3 | Loc-62/0-3Pit Casting compl(ROW) Loc-61/1-Casting compl Loc-54/2-Boring & Dewatering WIP. Loc-58/2-Trial Pit
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 3 |  | 27 | 372 | 2 | Loc-55/2-Tower Erection WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-18 | TA 513 - DPR - 2026-06-18.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 9 | 0 | 133 | 159 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 5 | 1 | 76 | 216 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-18 | TA 601 - DPR - 2026-06-18.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 8 | 0 | 162 | 318 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 18 | 2 | 70 | 410 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-18 | TA 602 - DPR - 2026-06-18.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 13 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 15 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 16 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 17 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 18 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 20 |  | 294 | 211 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 19 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 13 |  | 277 | 214 | 14.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 20 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 87 | 17 |  | 202 | 303 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 21 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 18 |  | 105 | 391 | 9.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 22 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 9 | 55 | 0 |  | 9 | 496 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 23 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 0 |  | 0 | 147.643 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-14 | TB 412 - DPR - 2026-06-14.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 24 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 195 | 4 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 8E/8, 8E/9, 8E/10,9/5, 9/6, 9/7 Stringing final checking done,
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 5 | 1 | 0 | 37 | 2 | 1.0 | SC-2 Foundation wip
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 2 | 0 | 36 | 3 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 1 | 0 | 32 | 7 | 1.0 | 2/0 Erection wip
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-18 | TB 501 - DPR - 2026-06-18.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 9 | 1 | 317 | 196 | 5.0 | 30.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 9 |  | 227 | 286 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 12 |  | 116 | 397 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 0.425 |  | 22.222 | 166.456 | 2.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-17 | TB 507 [MAIN] - DPR - 2026-06-17.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 2 |  | 36 | 7 | 2.0 | 20.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-17 | TB 507 - DPR - 2026-06-17.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 25 | 2 | 395 | 128 | 26
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 35 | 0 | 343 | 180 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 26 | 2 | 229 | 294 | 13
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-17 | TB 605 - DPR - 2026-06-17.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 0 | 0 | 0 | 175.719 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 2 | 0 | 133 | 133 | 6.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 7 | 2 | 38 | 230 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 142 | 142
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 31 | 31
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-17 | TB 608 - DPR - 2026-06-17.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 11 |  | 266 | 64 | 15 | 38/4, 39/0, 47/0, 48/0, 48/1, 50/0, 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 9 |  | 216 | 114 | 13 | 36/4, 37/0, 38/2, 41/0,52/1, 52/2, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 73/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-21 | TA 419 - DPR - 2026-06-21.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 2 |  | 123 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-22 | TA 504 - DPR - 2026-06-22.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 4 |  | 496 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 11 |  | 416 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 4.683 |  | 60.315 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-22 | TA 506 - DPR - 2026-06-22.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 13 | 0 | 268 | 38 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 3.497 | 0 | 80.686 | 37.1649 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-21 | TA 413 - DPR - 2026-06-21.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 15 | 1 | 334 | 18
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 15 | 1 | 334 | 18 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 34 | 1 | 330 | 22
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 24 | 2 | 259 | 93 | 17.0 | 1 gang arrived on 22.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 51 | 2 | 171 | 181 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 6.5842 |  | 22.5282 | 105.2708 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 3.971 |  | 25.589 | 102.21
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 6.5842 |  | 22.5282 | 105.2708
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-22 | TA 414 - DPR - 2026-06-22.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-21 | TA 509 - DPR - 2026-06-21.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 5 |  | 273 | 36 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-21 | TA 509 - DPR - 2026-06-21.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-21 | TA 509 - DPR - 2026-06-21.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 9 |  | 217 | 92 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-21 | TA 509 - DPR - 2026-06-21.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 |  |  |  |  | 0 | 119.178 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 8 |  | 93 | 200 | 4 | ROW & Fronts are not cleared for further work
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-22 | TA 510 - DPR - 2026-06-22.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 6 | 0 | 314 | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 4 | 0 | 310 | 9 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 6 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 10 |  | 231 | 88 | 07/211
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 26 | 3 | 105 | 214
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-22 | TA 512 - DPR - 2026-06-22.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 14 | 2 | 138 | 154 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 8 | 0 | 79 | 213 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-22 | TA 601 - DPR - 2026-06-22.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 10 | 0 | 164 | 316 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 21 | 2 | 73 | 407 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-22 | TA 602 - DPR - 2026-06-22.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 10 |  | 318 | 195 | 5.0 | 65.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 9 |  | 227 | 286 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 18 | 2 | 122 | 391 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 0.425 |  | 22.222 | 166.456 | 2.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-20 | TB 507 [MAIN] - DPR - 2026-06-20.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 2 |  | 36 | 7 | 3.0 | 45.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 |  | 0 | 3 | 40 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-20 | TB 507 - DPR - 2026-06-20.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 32 | 3 | 402 | 121 | 27.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 35 | 0 | 343 | 180 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 34 | 3 | 237 | 286 | 12.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-22 | TB 605 - DPR - 2026-06-22.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 0.442 |  | 0.442 | 175.277
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 13 | 0 | 268 | 38 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 3.497 | 0 | 80.686 | 37.1649 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 0.467 | 0 | 77.656 | 40.1949 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-22 | TA 413 - DPR - 2026-06-22.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-22 | TA 509 - DPR - 2026-06-22.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 5 |  | 273 | 36 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-22 | TA 509 - DPR - 2026-06-22.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-22 | TA 509 - DPR - 2026-06-22.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 10 |  | 218 | 91 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-22 | TA 509 - DPR - 2026-06-22.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 |  |  |  |  | 0 | 119.178 | 1.0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 11 |  | 266 | 64 | 14 | 38/4, 39/0, 47/0, 48/0, 48/1, 50/0, 50/1 , 59/0, 61/1, 63B/3, 66/0, 74/0, 79/0, 82/0, 86/1, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 10 |  | 217 | 113 | 13 | 36/4, 37/0, 38/2, 41/0,52/1, 52/0, 54/0, 62/0, 65/0, 65/2, 64/4, 71/0, 73/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-22 | TA 419 - DPR - 2026-06-22.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 13 |  | 296 | 13 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 | 2.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.977 |  | 119.41 | 1.932
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 2.129 |  | 117.596 | 3.746 | 2.0 | 43B/0 -44/0 - WIP & 40/0-41/0-42/0 - 1.475 Km
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 |  |  | 97.672 | 23.67 | 1.0 | WIP - 35/0 - 36/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-21 | TA 421 - DPR - 2026-06-21.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 2 |  | 123 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-23 | TA 504 - DPR - 2026-06-23.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 2 |  | 377 | 4 |  | Earthing-263/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 171/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-21 | TA 505 - DPR - 2026-06-21.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 117/0-118/0= Hot line work Completed
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 5 |  | 497 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 13 |  | 418 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 5.478 |  | 61.11 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-23 | TA 506 - DPR - 2026-06-23.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 13 | 0 | 268 | 38 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 1.364 | 0 | 78.553 | 39.2979 | 2.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 4.394 | 0 | 81.583 | 36.2679 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 1.364 | 0 | 78.553 | 39.2979 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-23 | TA 413 - DPR - 2026-06-23.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 | 1.0 | G_1 B.K Construction.
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-19 | TA 416 - DPR - 2026-06-19.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-19 | TA 416 - DPR - 2026-06-19.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-19 | TA 416 - DPR - 2026-06-19.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-19 | TA 416 - DPR - 2026-06-19.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 2.947 | 0.886 | 114.086 | 1.048 | 5
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-265/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 5 |  | 362 | 22 |  | Tack Welding Completed- 171/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-23 | TA 505 - DPR - 2026-06-23.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 117/0-118/0= Hot line work Completed
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 8 |  | 93 | 200 | 4.0 | ROW & Fronts are not cleared for further work
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-23 | TA 510 - DPR - 2026-06-23.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 6 | 0 | 314 | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 5 | 1 | 311 | 8 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 10 |  | 231 | 88 | 07/211
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 28 | 2 | 107 | 212
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-23 | TA 512 - DPR - 2026-06-23.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 16 | 2 | 140 | 152 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 10 | 2 | 81 | 211 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-23 | TA 601 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 10 | 0 | 164 | 316 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 21 | 2 | 73 | 407 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-23 | TA 602 - DPR - 2026-06-23.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 13 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 15 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 16 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 17 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 18 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 30 |  | 304 | 201 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 19 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 27 |  | 291 | 201 | 13.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 20 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 80 | 25 |  | 210 | 295 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 21 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 32 |  | 119 | 378 | 8.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 22 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 55 | 0 |  | 21 | 484 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 23 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 1.717 |  | 1.717 | 147.633 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-22 | TB 412 - DPR - 2026-06-22.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 24 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 34 | 2 | 404 | 119 | 25.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 39 | 0 | 347 | 176 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 34 | 0 | 237 | 286 | 12.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-23 | TB 605 - DPR - 2026-06-23.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 0.442 |  | 0.442 | 175.277
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 14 |  | 269 | 61 | 14 | 38/4, 39/0, 47/0, 48/0, 48/1, 50/0, 50/1 , 61/1, 66/0,79/0, 82/0, 86/0, 86/1, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 10 |  | 217 | 113 | 13 | 36/4, 37/0, 38/2, 41/0,52/1, 52/0, 54/0, 65/0, 65/2, 64/4, 71/0, 73/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0C/1-0C/0, 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-23 | TA 419 - DPR - 2026-06-23.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 2 |  | 123 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-24 | TA 504 - DPR - 2026-06-24.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 6 |  | 498 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 13 |  | 418 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 6.198 |  | 61.83 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-24 | TA 506 - DPR - 2026-06-24.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 15 |  | 334 | 18
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 15 |  | 334 | 18 | 5.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 34 |  | 330 | 22
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 25 | 1 | 260 | 92 | 16.0 | 1 gang arrived on 22.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 53 | 2 | 173 | 179 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 6.5842 |  | 22.5282 | 105.2708 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 5.512 |  | 27.13 | 100.669
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 6.5842 |  | 22.5282 | 105.2708
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-24 | TA 414 - DPR - 2026-06-24.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-24 | TA 416 - DPR - 2026-06-24.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-24 | TA 416 - DPR - 2026-06-24.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-24 | TA 416 - DPR - 2026-06-24.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-24 | TA 416 - DPR - 2026-06-24.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 2.947 |  | 114.086 | 1.048 | 5
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 24 |  | 307 | 2 | 1.0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 2.977 |  | 119.41 | 1.932
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 2.129 |  | 117.596 | 3.746 | 2.0 | 43B/0 -44/0 - WIP & 40/0-41/0-42/0 - 1.475 Km [ 41/0 - Row ] & 43A/1 - 43B/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 | 1.858 | 1.858 | 99.53 | 21.812 | 1.0 | WIP - 36/0 - 37/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-23 | TA 421 - DPR - 2026-06-23.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-265/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 171/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-24 | TA 505 - DPR - 2026-06-24.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 117/0-118/0= Hot line work Completed
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 8 |  | 93 | 200 | 4.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-24 | TA 510 - DPR - 2026-06-24.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 7 | 1 | 315 | 4
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 5 | 0 | 311 | 8 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 10 |  | 231 | 88 | 08/248
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 28 | 0 | 107 | 212
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-24 | TA 512 - DPR - 2026-06-24.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 17 | 1 | 141 | 151 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 10 | 0 | 81 | 211 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-24 | TA 601 - DPR - 2026-06-24.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 194 | 5 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 4/6-4/9 Stringing Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-2 Earthing completed, SC-5 Pit marking done,
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 3 | 0 | 37 | 2 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 2 | 0 | 33 | 6 | 1.0 | 1/0 Erection Wip
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-22 | TB 501 - DPR - 2026-06-22.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 15 |  | 270 | 60 | 14 | 38/4, 39/0, 47/0, 48/1, 50/0, 50/1 , 61/1, 63B/4 66/0,79/0, 82/0, 86/0, 86/1, 87/1, 96/0, 96/2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 11 |  | 218 | 112 | 13 | 36/4, 37/0, 41/0, 44/0,52/1, 52/0, 54/0, 65/0, 65/2, 64/4, 71/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 |  |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 |  |  | 0.447 |  |  | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | 3 | 0C/1-0C/0, 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0 |  | 0.447 |  | 0.447 | 121.624 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-24 | TA 419 - DPR - 2026-06-24.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 10 |  | 318 | 195 | 5.0 | 51.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 10 |  | 228 | 285 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 23 | 2 | 127 | 386 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 0.425 |  | 22.222 | 166.456 | 2.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-23 | TB 507 [MAIN] - DPR - 2026-06-23.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 3 |  | 37 | 6 | 3.0 | 45.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 1 |  | 4 | 39 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-23 | TB 507 - DPR - 2026-06-23.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 2 |  | 123 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-25 | TA 504 - DPR - 2026-06-25.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 6 |  | 498 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 14 |  | 419 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 6.198 |  | 61.83 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-25 | TA 506 - DPR - 2026-06-25.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-23 | TA 509 - DPR - 2026-06-23.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 6 |  | 274 | 35 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-23 | TA 509 - DPR - 2026-06-23.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-23 | TA 509 - DPR - 2026-06-23.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 10 |  | 218 | 91 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-23 | TA 509 - DPR - 2026-06-23.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 1.555 |  | 1.555 | 117.623 | 1.0
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 13 | 0 | 268 | 38 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 9.554 | 0 | 86.743 | 31.1079 | 3.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 4.394 | 0 | 81.583 | 36.2679 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 1.364 | 0 | 78.553 | 39.2979 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-25 | TA 413 - DPR - 2026-06-25.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 0 | 0 | 59.762 | 58.0889 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 15 |  | 334 | 18
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 15 |  | 334 | 18 | 5.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 34 |  | 330 | 22
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 25 |  | 260 | 92 | 17.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 58 | 2 | 178 | 174 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 7.0242 | 0.44 | 22.9682 | 104.8308 | 6.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 5.952 | 0.44 | 27.57 | 100.229
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 7.0242 | 0.44 | 22.9682 | 104.8308
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-26 | TA 414 - DPR - 2026-06-26.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 330 | 330 | 167 |  |  |  | 167 | 163
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 330 | 330 | 255 | 49 | 15 |  | 270 | 60 | 14 | 38/4, 39/0, 47/0, 48/1, 50/0, 50/1 , 61/1, 63B/4 66/0, 79/0, 82/0, 86/0, 86/1, 87/1, 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 330 | 330 | 207 | 50 | 11 |  | 218 | 112 | 13 | 36/4, 37/0, 41/0, 44/0,52/1, 52/0, 54/0, 65/0, 65/2, 64/4, 71/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 330 | 330 | 35 | 50 | 25 |  | 60 | 270 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | 3 | 0C/1-0C/0, 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-25 | TA 419 - DPR - 2026-06-25.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 3 |  | 124 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-26 | TA 504 - DPR - 2026-06-26.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-265/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 174/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-25 | TA 505 - DPR - 2026-06-25.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 119/0-120/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 6 |  | 498 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 14 |  | 419 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 6.198 |  | 61.83 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-26 | TA 506 - DPR - 2026-06-26.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 10 | 2 | 95 | 198 | 4.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-25 | TA 510 - DPR - 2026-06-25.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 8 | 1 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 1 | 312 | 7 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 11 | 1 | 232 | 87 | 08/248
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 28 | 0 | 107 | 212
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-25 | TA 512 - DPR - 2026-06-25.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 |  | 0 | 124.568
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 9 | Detailed Survey Completed | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 10 | Submission of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  | 0 | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 11 | Approval of Detailed Survey | detailed_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 12 | Check Survey | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 13 | Check Survey Submision | check_survey | 144.2 | 147.584 | 147.584 | 147.575 | 0 |  |  | 147.575 | 0.009
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 14 | Check Survey Approved | check_survey | 144.2 | 147.584 | 147.584 | 140.738 | 0 |  |  | 140.738 | 6.846 |  | Gantry to AP3 Approval Pending (Submitted on date : 06.02.2026)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 15 | Foundation (No) | foundation | 387 | 399 | 399 | 64 | 25 | 8 |  | 72 | 327 | 3 | Loc-62/0-3Pit Casting compl(ROW) Loc-51/0-Casting WIP Loc-54/2-Casting WIP Loc-58/2-Casting WIP
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 16 | Earthing | earthing | 387 | 399 | 399 | 7 |  |  |  | 7 | 392
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 17 | Tower Erection (Nos) | tower_erection | 387 | 399 | 399 | 24 | 11 | 4 | 1 | 28 | 371 | 2 | Loc-52/2-Tower Erection Compl
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 18 | Tack Welding | tack_welding | 387 | 399 | 399 | 0 |  |  |  | 0 | 399
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 19 | Stringing (Km) | stringing | 144.2 | 147.584 | 147.584 | 0 |  |  |  |  | 147.584
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 20 | Paying Out | paying_out | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 21 | Final Sag | final_sag | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 22 | OPGW (Km) | opgw_stringing | 144.2 | 147.69 | 147.69 | 0 |  | 0 |  |  | 147.69
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 27 | Detailed Survey Completed | detailed_survey | 78.73 | 82.803 | 82.803 | 82.803 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 28 | Submission of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.796 |  |  |  | 82.796 | 0.007
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 29 | Approval of Detailed Survey | detailed_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.803 | 0
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 30 | Check Survey | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 31 | Check Survey Submision | check_survey | 78.73 | 82.803 | 82.803 | 82.795 |  |  |  | 82.795 | 0.008
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 32 | Check Survey Approved | check_survey | 78.73 | 82.803 | 82.803 | 76.267 |  |  |  | 76.267 | 6.536 |  | Gantry to AP3 Approval Pending (Submitted on date : 24.12.2025)
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 33 | Foundation (No) | foundation | 210 | 220 | 220 | 25 | 10 | 1 |  | 26 | 194 | 1
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 34 | Earthing | earthing | 210 | 220 | 220 | 10 |  |  | 0 | 10 | 210
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 35 | Tower Erection (Nos) | tower_erection | 210 | 220 | 220 | 7 | 5 |  |  | 7 | 213
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 36 | Tack Welding | tack_welding | 210 | 220 | 220 |  |  |  |  | 0 | 220
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 37 | Stringing (Km) | stringing | 78.73 | 82.803 | 82.803 | [5 empty] | 82.803
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 38 | Paying Out | paying_out | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 39 | Final Sag | final_sag | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 513 | TA 513 | ta513 |  | filename | 400 KV Siwani To Patran TL | 2026-06-22 | TA 513 - DPR - 2026-06-22.xlsx | Summary | Summary | TA 513 Status |  | 7 | 40 | OPGW (Km) | opgw_stringing | 78.73 | 82.97 | 82.97 | [5 empty] | 82.97
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 18 | 1 | 142 | 150 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 3 | 0 | 105 | 187
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 12 | 2 | 83 | 209 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-25 | TA 601 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 10 | 0 | 164 | 316 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 21 | 2 | 73 | 407 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-24 | TA 602 - DPR - 2026-06-24.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 195 | 4 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 4/6-4/9 Stringing payingout done, Coping work done 0/0-4/17
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 1.7751 | 0 | 62.9751 | 1.0249
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 Foundation WIP
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 3 | 0 | 37 | 2 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0 | 2/0 Tighting work complet
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-25 | TB 501 - DPR - 2026-06-25.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 37 | 3 | 407 | 116 | 25.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 39 | 0 | 347 | 176 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 36 | 2 | 239 | 284 | 12.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-24 | TB 605 - DPR - 2026-06-24.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 1.47 | 1.03 | 1.47 | 174.249
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 13 | 0 | 268 | 38 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 2.105 | 0.244 | 79.294 | 38.5569 | 3.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 5.657 | 87.24 | 30.6109 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 2.105 | 0.244 | 79.294 | 38.5569 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-26 | TA 413 - DPR - 2026-06-26.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 4.498 | 0 | 64.26 | 53.5909 | 1.0 | G_1 B.K Construction.
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 7 | 0 | 315 | 4
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 0 | 312 | 7 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 12 | 1 | 233 | 86 | 08/252
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 28 | 0 | 107 | 212
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-26 | TA 512 - DPR - 2026-06-26.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-265/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 174/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-26 | TA 505 - DPR - 2026-06-26.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 119/0-120/0= Hot line work U/P
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-25 | TA 509 - DPR - 2026-06-25.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 6 |  | 274 | 35 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-25 | TA 509 - DPR - 2026-06-25.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-25 | TA 509 - DPR - 2026-06-25.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 10 |  | 218 | 91 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-25 | TA 509 - DPR - 2026-06-25.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 3.461 |  | 3.461 | 115.717 | 1.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 11 |  | 319 | 194 | 6.0 | 57.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 11 |  | 229 | 284 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 24 |  | 128 | 385 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 3.345 |  | 25.142 | 163.536 | 1.0 | 54.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-25 | TB 507 [MAIN] - DPR - 2026-06-25.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 4 | 2 | 38 | 5 | 1.0 | 15.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 2 | 1 | 5 | 38 | 1.0 | 22.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-25 | TB 507 - DPR - 2026-06-25.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 4 | 1 | 135 | 131 | 5.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 8 | 0 | 39 | 229 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 142 | 142
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 31 | 31
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-21 | TB 608 - DPR - 2026-06-21.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 26 |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 3.4367 |  | 119.8697 | 1.4723
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 4.403 |  | 119.87 | 1.472 | 2.0 | 40/0-41/0-42/0 - 1.475 Km -WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 | 1.858 |  | 99.53 | 21.812 | 1.0 | WIP - 36/0 - 37/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-25 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 102.67 | 0 |  |  | 102.67 | 11.846
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 10 |  | 95 | 198 | 4.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-28 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 21 | 1 | 145 | 147 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 5 | 0 | 107 | 185
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 13 | 0 | 84 | 208 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-27 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip, Coping done- 7/2 to 8D/2
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0 | 34/0 Tack welding and painting done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 4/6-4/7 Stringing Top final sag done,
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64 | 64 | 61.2 | 2.8 | 2.4651 | 0 | 63.6651 | 0.3349 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64 | 64 | 61.2 | 2.8 | 2.4651 | 0 | 63.6651 | 0.3349
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64 | 64 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7609 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 Foundation WIP
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 3 | 0 | 37 | 2 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087 | 1.0 | 2/1-2/0 Stringing Wip,
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.000326 | 0 | 6.2313 | 3.0087
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-27 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 43 | 0 | 413 | 110 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 39 | 0 | 347 | 176 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 42 | 1 | 245 | 278 | 9.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 1.47 | 0 | 1.47 | 174.249
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-266/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 174/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 119/0-120/0= Hot line work U/P
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 8 | 1 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 0 | 312 | 7 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 14 | 2 | 235 | 84 | 08/244
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 30 | 1 | 109 | 210
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 14 | 1 | 322 | 191 | 6.0 | 57.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 13 |  | 231 | 282 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 24 |  | 128 | 385 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 3.345 |  | 25.142 | 163.536 | 3.0 | 62.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 4 |  | 38 | 5 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 2 |  | 5 | 38 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 255 | 49 | 15 |  | 270 | 61 | 14 | 38/4, 39/0, 47/0, 48/1, 50/0, 50/1 , 61/1, 63B/4 66/0, 79/0, 82/0, 86/0, 86/1, 87/1, 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 207 | 50 | 11 |  | 218 | 113 | 13 | 36/4, 37/0, 41/0, 44/0,52/1, 52/0, 54/0, 65/0, 65/2, 64/4, 71/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 35 | 50 | 25 |  | 60 | 271 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | 3 | 0C/0-0D/0, 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 3 |  | 124 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 7 |  | 499 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 15 |  | 420 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 7.478 |  | 63.11 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 6 |  | 274 | 35 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 11 |  | 219 | 90 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 3.461 |  | 3.461 | 115.717 | 1.0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 3.319 | 0.372 | 114.458 | 0.676 | 4
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 26 |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 4.9087 | 1.475 | 121.3417 |  |  | RS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 4.4027 |  | 119.8697 | 1.4723 | 2.0 | 40/0-41/0-42/0 - 1.475 Km -WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 | 5.466 |  | 103.138 | 18.204 | 1.0 | WIP - 39/0 - 41/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 8 | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 0 | 312 | 7 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 15 | 1 | 236 | 83 | 08/227
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 30 | 0 | 109 | 210
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-29 | TA 512 - DPR - 2026-06-29.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 21 | 0 | 145 | 147 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 6 | 0 | 108 | 184
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 16 | 0 | 87 | 205 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 14/0 to 14/2 Stringing final checking done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 All pits Foundation excavation done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251 | 1.0 | 1/0-2/0 Stringing Wip,
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 44 | 1 | 414 | 109 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 39 | 0 | 347 | 176 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 44 | 2 | 247 | 276 | 9.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-29 | TB 605 - DPR - 2026-06-29.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 1.47 | 0 | 1.47 | 174.249
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-266/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 174/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 11.7 |  | 27.162 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-29 | TA 505 - DPR - 2026-06-29.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 16.525 |  | 31.987 | 123.171 |  | 119/0-120/0= Hot line work U/P
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 11 | 0 | 165 | 315 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 25 | 2 | 77 | 403 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 13 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 15 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 16 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 17 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 18 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 30 |  | 304 | 201 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 19 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 32 |  | 296 | 196 | 13.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 20 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 80 | 29 |  | 214 | 291 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 21 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 38 |  | 125 | 372 | 8.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 22 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 55 | 0 |  | 21 | 484 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 23 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 3.199 |  | 3.199 | 147.285 | 2.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 24 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 4 |  | 125 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-30 | TA 504 - DPR - 2026-06-30.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 9 |  | 501 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 16 |  | 421 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 7.478 |  | 63.11 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-30 | TA 506 - DPR - 2026-06-30.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 14 |  | 322 | 191 | 6 | 57.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 13 |  | 231 | 282 | 3 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 24 |  | 128 | 385 | 2 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 3.345 |  | 25.142 | 163.536 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 62.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 | 2.92 | 2.92 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-29 | TB 507 [MAIN] - DPR - 2026-06-29.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 4 |  | 38 | 5 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 2 |  | 5 | 38 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-29 | TB 507 - DPR - 2026-06-29.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 17 |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 17 |  | 336 | 16 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 36 | 1 | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 30 | 2 | 265 | 87 | 16.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 61 |  | 181 | 171 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 9.1022 |  | 25.0462 | 102.7528 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 5.952 |  | 27.57 | 100.229
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 9.1022 |  | 25.0462 | 102.7528
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 3.6311 | 31.2262 | 16.6138 | 5
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 306 | 3 | 1 |  | 307 | 2 | 1.0 | AP 7/0 & 8/0 - Court case
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 287 | 22 | 2 |  | 289 | 20
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 238 | 30 | 18 | 1 | 256 | 53 | 6.0 | WIP - 4/13, 11/7, 36/8, 39/8, 39/9,43/1
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 107 |  | 12 |  | 124 | 185
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 120 |  | 10 |  | 129 | 180 | 2.0 | WIP - 16/5, 13/11, 14/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 31.816 | 23.239 | 11.927 |  | 43.743 | 77.599 | 2.0 | 17/0-18/0 ( 1.539 km ) - Pilot Paying out u/p ; AP 13/0 to 14/0(4.900 km) -Insulator Hosting t under Progress
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 31.816 | 23.239 | 11.927 |  | 43.743 | 77.599
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 20.897 | 23.239 | 13.385 |  | 34.282 | 87.06
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-30 | TA 421 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 8 | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 0 | 312 | 7 | 02/21
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 16 | 1 | 237 | 82 | 08/220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 32 | 2 | 111 | 208
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-30 | TA 512 - DPR - 2026-06-30.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 24 | 3 | 148 | 144 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 6 | 0 | 108 | 184
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 17 | 1 | 88 | 204 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-30 | TA 601 - DPR - 2026-06-30.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 14/3 to 14/6 Stringing final checking done, 4/7-4/8- Jumper fixing done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 All pits Block Level done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251 | 1.0 | 1/0-2/0-Top Conductor final sag done, 2/0-2/1-Top Conductor final sag done, 2/1-3/0- 4 Phase final sag done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-30 | TB 501 - DPR - 2026-06-30.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 4 | 0 | 135 | 131 | 6.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 9 | 1 | 40 | 228 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 142 | 142
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 31 | 31
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 15 | 0 | 270 | 36 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 | 3.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 9.298 | 4.8 | 69.06 | 48.7909 | 1.0 | G_1 B.K Construction.
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 255 | 49 | 17 |  | 272 | 59 | 14 | 38/4, 47/0, 50/0, 50/1, 63B/4 66/0, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 207 | 50 | 13 |  | 220 | 111 | 13 | 36/4, 37/0, 41/0, 44/0,52/1, 52/0, 54/0, 64/4, 66/1, 67/0, 71/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 35 | 50 | 25 |  | 60 | 271 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.549 |  | 2.996 | 119.075 | 3 | 0C/0-0D/0, 0D/5-0E/0, 0G/0-0H/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.549 |  | 2.996 | 119.075 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-29 | TA 419 - DPR - 2026-06-29.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-30 | TA 416 - DPR - 2026-06-30.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-30 | TA 416 - DPR - 2026-06-30.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-30 | TA 416 - DPR - 2026-06-30.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-30 | TA 416 - DPR - 2026-06-30.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 3.319 | 0 | 114.458 | 0.676 | 4
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tower Tightening Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 |  |  | RS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 | 0 | 2.0 | FS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 108.06 | 13.282 |  |  | 108.06 | 13.282 | 1.0 | WIP - 43/0 - 44/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-01 | TA 421 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-266/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 185/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 11.545 |  | 27.007 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-30 | TA 505 - DPR - 2026-06-30.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 16.639 |  | 32.101 | 123.171 |  | 119/0-120/0= Hot line work Completed
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 10 |  | 95 | 198 | 4.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 1 | 1 | 313 | 6 | 02/21
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 0 |  | 237 | 82 | 08/220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 0 |  | 111 | 208
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-01 | TA 512 - DPR - 2026-07-01.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 0 | 0 | 148 | 144 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 1 | 1 | 109 | 183
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 0 | 0 | 88 | 204 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-01 | TA 601 - DPR - 2026-07-01.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 48 | 4 | 418 | 105 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 55 | 0 | 363 | 160 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 45 | 1 | 248 | 275 | 10.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-30 | TB 605 - DPR - 2026-06-30.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 1.47 | 0 | 1.47 | 174.249
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 2 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0 | 0 | 87.24 | 30.6109 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0 | 0 | 87.24 | 30.6109 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0 | 0 | 87.24 | 30.6109 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-01 | TA 413 - DPR - 2026-07-01.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 0 | 0 | 69.06 | 48.7909 | 1.0 | G_1 B.K Construction.
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 0 |  | 272 | 59 | 13 | 38/4, 47/0, 50/0, 50/1, 63B/4 66/0, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 2 |  | 224 | 107 | 13 | 36/4, 37/0, 41/0, 44/0, 48/1, 54/0, 64/4, 66/1, 67/0, 71/0, 70/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 18 | 0 |  | 3 | 119.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 18 | 0 |  | 3 | 119.071 | 3 | 0C/0-0D/0, 0G/0-0H/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 18 | 0 |  | 3 | 119.071 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-01 | TA 419 - DPR - 2026-07-01.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-01 | TA 418 - DPR - 2026-07-01.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-01 | TA 418 - DPR - 2026-07-01.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-01 | TA 418 - DPR - 2026-07-01.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-01 | TA 418 - DPR - 2026-07-01.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 36.865 | 10.975 | 0 | 0 | 36.865 | 10.975 | 4
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 1 |  | 273 | 58 | 13 | 38/4, 47/0, 50/0, 63B/4 66/0, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 3 |  | 225 | 106 | 13 | 36/4, 37/0, 41/0, 43/2, 44/0, 48/1, 54/0, 64/4, 66/1, 67/0, 70/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071 | 3 | 0C/0-0D/0, 0G/0-0H/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-03 | TA 419 - DPR - 2026-07-03.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 |  |  | 45 | 248 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-02 | TA 510 - DPR - 2026-07-02.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 2 | 2 | 150 | 142 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 3 | 0 | 111 | 181
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 0 | 0 | 88 | 204 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-02 | TA 601 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 0 | 0 | 418 | 105 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 0 | 0 | 363 | 160 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 1 | 1 | 249 | 274 | 10.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0 | 0 | 1.47 | 174.249 | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-02 | TB 605 - DPR - 2026-07-02.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0 | 0 | 1.47 | 174.249
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 2 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.211 | 0.211 | 87.451 | 30.3999 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.211 | 0.211 | 87.451 | 30.3999 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.211 | 0.211 | 87.451 | 30.3999 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-02 | TA 413 - DPR - 2026-07-02.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 0 | 0 | 69.06 | 48.7909 | 1.0 | G_1 B.K Construction.
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-02 | TA 416 - DPR - 2026-07-02.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-02 | TA 416 - DPR - 2026-07-02.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-02 | TA 416 - DPR - 2026-07-02.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-02 | TA 416 - DPR - 2026-07-02.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 3.319 | 0 | 114.458 | 0.676 | 4
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 1 |  | 273 | 58 | 13 | 38/4, 47/0, 50/0, 63B/4 66/0, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 4 |  | 226 | 105 | 13 | 36/4, 37/0, 41/0, 43/2, 44/0, 48/1, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071 | 3 | 0C/0-0D/0, 0G/0-0H/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0 |  | 3 | 119.071 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-04 | TA 419 - DPR - 2026-07-04.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 4 |  | 125 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-01 | TA 504 - DPR - 2026-07-01.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 |  |  |  | 379 | 4 |  | Earthing-266/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 |  |  |  | 363 | 22 |  | Tack Welding Completed- 185/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 11.966 |  | 27.428 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-02 | TA 505 - DPR - 2026-07-02.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 16.639 |  | 32.101 | 123.171 |  | 119/0-120/0= Hot line work Completed
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 12 |  | 504 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 18 |  | 423 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 7.478 |  | 63.11 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-01 | TA 506 - DPR - 2026-07-01.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 | 1 | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-03 | TA 510 - DPR - 2026-07-03.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 1 | 0 | 313 | 6 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 0 |  | 237 | 82 | 08/220
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 1 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-02 | TA 512 - DPR - 2026-07-02.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 2 | 0 | 150 | 142 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 3 | 0 | 111 | 181
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 1 | 1 | 89 | 203 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-03 | TA 601 - DPR - 2026-07-03.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 10 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 11 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 12 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 14 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 15 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 16 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 17 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 30 |  | 304 | 201 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 18 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 48 |  | 312 | 180 | 11.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 19 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 80 | 38 |  | 223 | 282 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 20 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 51 |  | 138 | 359 | 6.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 21 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 55 | 0 |  | 21 | 484 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 22 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 3.199 |  | 3.199 | 147.285 | 1.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-30 | TB 412 - DPR - 2026-06-30.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 23 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 14/7 to 15/1 Stringing final checking done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 All pits pcc done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.76208 | 0 | 6.9931 | 2.2469 | 1.0 | 1/0-2/0-Final sag done, 2/0-2/1-Final sag done, 2/1-3/0- Final sag done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.76208 | 0 | 6.9931 | 2.2469
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-01 | TB 501 - DPR - 2026-07-01.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 16 |  | 324 | 189 | 6 | 57.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 13 |  | 231 | 282 | 3 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 27 | 3 | 131 | 382 | 2 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 3.345 |  | 25.142 | 163.536 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 62.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 | 2.92 | 2.92 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-30 | TB 507 [MAIN] - DPR - 2026-06-30.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 5 |  | 39 | 4 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 3 |  | 6 | 37 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-30 | TB 507 - DPR - 2026-06-30.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 1 | 1 | 419 | 104 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 1 | 0 | 364 | 159 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 1 | 0 | 249 | 274 | 11.0 | Additional 1 gang Anannya Traders will reach today
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0 | 0 | 1.47 | 174.249 | 4.0 | Saliundin gang will be bifurcated into 2 gangs
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-03 | TB 605 - DPR - 2026-07-03.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0 | 0 | 1.47 | 174.249
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 6 | 2 | 137 | 129 | 5.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 10 | 1 | 41 | 227 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 2 | 1 | 2 | 21 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 142 | 142
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 31 | 31
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-30 | TB 608 - DPR - 2026-06-30.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 |  |  | 266 | 86 | 16.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 1.937 | 1.937 | 26.983 | 100.816 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.57 | 15 |  |  | 27.57 | 100.229
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 1.937 | 1.937 | 26.983 | 100.816
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-02 | TA 414 - DPR - 2026-07-02.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-03 | TA 418 - DPR - 2026-07-03.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-03 | TA 418 - DPR - 2026-07-03.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-03 | TA 418 - DPR - 2026-07-03.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-03 | TA 418 - DPR - 2026-07-03.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 36.865 | 10.975 | 0 | 0 | 36.865 | 10.975 | 4
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 3 | 0 | 315 | 4 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 2 | 1 | 239 | 80 | 09/261
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 0 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-05 | TA 512 - DPR - 2026-07-05.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 4 | 1 | 152 | 140 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 5 | 2 | 113 | 179
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 4 | 2 | 92 | 200 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-05 | TA 601 - DPR - 2026-07-05.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 15/0 Jumpering done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 1 | 1 | 39 | 0 | 1.0 | SC-5 Foundation Completed
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 5 | 2 | 34 | 5 | 0.0 | Tack Welding done- 3/0, 3/1
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.6976 | 0 | 6.9286 | 2.3114 | 1.0 | 10/0 to 13/0 Stringing final checking done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.6976 | 0 | 6.9286 | 2.3114
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-04 | TB 501 - DPR - 2026-07-04.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.1821 | 0 | 6.1821 | 3.0579 | 0.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-05 | TA 510 - DPR - 2026-07-05.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 1 |  | 325 | 188 | 6 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 1 | 1 | 232 | 281 | 3 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 139 | 34 | 3 | 138 | 375 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0 | 0 | 24.705 | 163.973 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-05 | TB 507 [MAIN] - DPR - 2026-07-05.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 1 | 1 | 7 | 36 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-05 | TB 507 - DPR - 2026-07-05.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 13 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 4 |  | 226 | 105 | 12 | 36/4, 37/0, 41/0, 43/2, 44/0, 48/1, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0,78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | 3 | 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-06 | TA 419 - DPR - 2026-07-06.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 2 |  | 268 | 84 | 14.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-06 | TA 414 - DPR - 2026-07-06.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 13 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 4 |  | 226 | 105 | 12 | 36/4, 37/0, 41/0, 43/2, 44/0, 48/1, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0,78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | 3 | 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-07 | TA 419 - DPR - 2026-07-07.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 |  |  | 146 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 |  |  | 125 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-03 | TA 504 - DPR - 2026-07-03.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 379 |  |  |  | 379 | 0 |  | Earthing-267/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 363 | 6 |  |  | 363 | 16 |  | Tack Welding Completed- 185/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 27.428 | 21.328 | 0 |  | 27.428 | 112.172
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-05 | TA 505 - DPR - 2026-07-05.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 30.433 | 22 | 1.668 |  | 32.101 | 109.167 |  | 119/0-120/0= Hot line work Completed
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 2 |  | 506 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 1 |  | 424 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 4.783 |  | 67.893 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-03 | TA 506 - DPR - 2026-07-03.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-29 | TA 509 - DPR - 2026-06-29.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 6 |  | 274 | 35 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-29 | TA 509 - DPR - 2026-06-29.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 10 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-29 | TA 509 - DPR - 2026-06-29.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 11 |  | 219 | 90 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-29 | TA 509 - DPR - 2026-06-29.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 3.461 |  | 3.461 | 115.717 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-06 | TA 510 - DPR - 2026-07-06.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 3 | 0 | 315 | 4 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 3 | 1 | 240 | 79 | 09/261
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 0 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-06 | TA 512 - DPR - 2026-07-06.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 5 | 1 | 153 | 139 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 5 | 0 | 113 | 179
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 6 | 2 | 94 | 198 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-06 | TA 601 - DPR - 2026-07-06.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 10 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 11 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.147 | 1.686 | 0 |  | 149.147 | 1.686 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 12 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.499 | 3.334 | 0 |  | 147.499 | 3.334 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 14 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 137.191 | 13.642 | 0 |  | 137.191 | 13.642 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 15 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 119.607 | 31.226 | 0 |  | 119.607 | 31.226 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 16 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 17 | Excavation (Nos) | excavation | 564 | 505 | 505 | 324 | 35 | 0 |  | 324 | 181 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 18 | Foundation (Nos) | foundation | 564 | 505 | 505 | 312 | 35 | 3 |  | 315 | 179 | 11.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 19 | Earthing (Nos) | earthing | 564 | 505 | 505 | 226 | 38 | 4 |  | 230 | 275
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 20 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 138 | 45 | 6 |  | 144 | 355 | 6.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 21 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 45 | 0 |  | 21 | 484
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 22 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 3.199 | 6.2 | 0 |  | 3.199 | 147.235 | 2.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-05 | TB 412 - DPR - 2026-07-05.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 23 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 1 | 0 | 419 | 104 | 23.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 1 | 0 | 364 | 159 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 2 | 1 | 250 | 273 | 14.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0.852 | 0 | 2.322 | 173.397 | 4.0 | Saliundin gang will be bifurcated into 2 gangs and gang is working on final checking of towers in 43-44 section JS _J
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-05 | TB 605 - DPR - 2026-07-05.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0 | 0 | 1.47 | 174.249
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1 |  | Loc no 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 2 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0.44 | 87.8917 | 29.9592 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0.44 | 87.8917 | 29.9592 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0.44 | 87.8917 | 29.9592 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-04 | TA 413 - DPR - 2026-07-04.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 0 | 0 | 69.06 | 48.7909 | 1.0 | G_1 B.K Construction.
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 1 |  | 147 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 |  |  | 125 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-06 | TA 504 - DPR - 2026-07-06.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 2 |  | 506 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 2 |  | 425 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 4.783 |  | 67.893 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-06 | TA 506 - DPR - 2026-07-06.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 2 | 1 | 326 | 187 | 6 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 1 |  | 232 | 281 | 3 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 139 | 34 | 3 | 138 | 375 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0 | 0 | 24.705 | 163.973 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-06 | TB 507 [MAIN] - DPR - 2026-07-06.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 1 | 1 | 7 | 36 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-06 | TB 507 - DPR - 2026-07-06.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 0 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-07 | TA 413 - DPR - 2026-07-07.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 4.775 | 4.775 | 73.835 | 44.0159 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 2 |  | 268 | 84 | 14.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-07 | TA 414 - DPR - 2026-07-07.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-07 | TA 510 - DPR - 2026-07-07.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 3 | 0 | 315 | 4 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 3 | 0 | 240 | 79 | 09/278
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 0 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-07 | TA 512 - DPR - 2026-07-07.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 6 | 1 | 154 | 138 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 5 | 0 | 113 | 179
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 6 | 0 | 94 | 198 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-07 | TA 601 - DPR - 2026-07-07.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 25 | 0 | 0 | 167 | 313 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 107 | 25 | 0 | 0 | 107 | 373
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 78 | 30 | 0 | 2 | 78 | 402 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 30 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-30 | TA 602 - DPR - 2026-06-30.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 1 |  | 147 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 |  |  | 125 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-07 | TA 504 - DPR - 2026-07-07.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 3 |  | 507 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 2 |  | 425 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 4.783 |  | 67.893 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-07 | TA 506 - DPR - 2026-07-07.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 0 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-08 | TA 413 - DPR - 2026-07-08.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 4.775 | 4.775 | 73.835 | 44.0159 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 2 |  | 268 | 84 | 14.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-08 | TA 414 - DPR - 2026-07-08.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-05 | TA 416 - DPR - 2026-07-05.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-05 | TA 416 - DPR - 2026-07-05.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-05 | TA 416 - DPR - 2026-07-05.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-05 | TA 416 - DPR - 2026-07-05.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 3.319 | 0 | 114.458 | 0.676 | 4
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-06 | TA 418 - DPR - 2026-07-06.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-06 | TA 418 - DPR - 2026-07-06.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-06 | TA 418 - DPR - 2026-07-06.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-06 | TA 418 - DPR - 2026-07-06.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 36.865 | 10.975 | 3.199 | 0 | 40.064 | 7.776 | 5
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 12 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 5 |  | 227 | 104 | 12 | 36/4, 37/0, 41/0, 43/2, 48/1, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0,78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | 3 | 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-08 | TA 419 - DPR - 2026-07-08.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tower Tightening Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 |  |  | RS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 | 0 | 2.0 | FS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 108.06 | 13.282 | 5.02 | 5.02 | 113.08 | 8.262 | 1.0 | WIP - 41/0 - 43/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-02 | TA 421 - DPR - 2026-07-02.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 1 |  | 147 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 |  |  | 125 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-08 | TA 504 - DPR - 2026-07-08.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 379 |  |  |  | 379 | 0 |  | Earthing-267/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 363 | 6 |  |  | 363 | 16 |  | Tack Welding Completed- 191/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 27.428 | 21.328 | 3.261 |  | 30.689 | 112.172
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-08 | TA 505 - DPR - 2026-07-08.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 30.433 | 22 | 9.538 |  | 36.966 | 109.167 |  | 119/0-120/0= Hot line work Completed
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 3 |  | 507 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 4 |  | 427 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 4.783 |  | 67.893 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-08 | TA 506 - DPR - 2026-07-08.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-06 | TA 509 - DPR - 2026-07-06.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 274 | 8 | 2 |  | 276 | 33 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-06 | TA 509 - DPR - 2026-07-06.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 260 | 10 | 10 |  | 270 | 39
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-06 | TA 509 - DPR - 2026-07-06.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 220 | 15 | 2 |  | 222 | 87 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-06 | TA 509 - DPR - 2026-07-06.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 3.461 |  | 3.461 | 115.717 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-08 | TA 510 - DPR - 2026-07-08.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 3 | 0 | 315 | 4 | 02/32
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 3 | 0 | 240 | 79 | 10/284
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 1 | 0 | 112 | 207
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-08 | TA 512 - DPR - 2026-07-08.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 8 | 2 | 156 | 136 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 7 | 2 | 115 | 177
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 7 | 1 | 95 | 197 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-08 | TA 601 - DPR - 2026-07-08.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 10 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 11 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.147 | 1.686 | 0 |  | 149.147 | 1.686 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 12 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.499 | 3.334 | 0 |  | 147.499 | 3.334 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 14 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 137.191 | 13.642 | 0 |  | 137.191 | 13.642 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 15 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 119.607 | 31.226 | 0 |  | 119.607 | 31.226 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 16 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 17 | Excavation (Nos) | excavation | 564 | 505 | 505 | 324 | 35 | 0 |  | 324 | 181 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 18 | Foundation (Nos) | foundation | 564 | 505 | 505 | 312 | 35 | 5 |  | 317 | 177 | 11.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 19 | Earthing (Nos) | earthing | 564 | 505 | 505 | 226 | 38 | 5 |  | 231 | 274
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 20 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 138 | 45 | 6 |  | 144 | 355 | 6.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 21 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 45 | 0 |  | 21 | 484
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 22 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 3.199 | 6.2 | 0 |  | 3.199 | 146.886 | 2.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-07 | TB 412 - DPR - 2026-07-07.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 23 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 2 | 1 | 326 | 187 | 6 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 3 |  | 234 | 279 | 4 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 141 | 43 | 3 | 147 | 366 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0 | 0 | 24.705 | 163.973 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-07 | TB 507 [MAIN] - DPR - 2026-07-07.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 3 |  | 9 | 34 | 3.0 | 89.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-07 | TB 507 - DPR - 2026-07-07.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 2 | 0 | 420 | 103 | 22.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 2 | 0 | 365 | 158 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 5 | 3 | 253 | 270 | 14.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0.852 | 0 | 2.322 | 173.397 | 4.0 | Muslindin gang will be bifurcated into 2 gangs and gang is working on final checking of towers in 43-44 section JS _J
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-07 | TB 605 - DPR - 2026-07-07.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0.366 | 0 | 1.836 | 173.883
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 9 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 6 |  | 228 | 103 | 12 | 36/4, 37/0, 41/0, 43/2, 43/3, 48/0, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0,78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | 4 | 0B/0-0C/0, 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 0.775 |  | 3.775 | 118.296 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-10 | TA 419 - DPR - 2026-07-10.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 379 |  |  |  | 379 | 0 |  | Earthing-268/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 363 | 6 |  |  | 363 | 16 |  | Tack Welding Completed- 192/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 27.428 | 21.328 | 4.825 |  | 32.253 | 112.172
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-10 | TA 505 - DPR - 2026-07-10.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 30.433 | 22 | 9.538 |  | 39.899 | 109.167
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 2 |  | 148 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 | 1 |  | 126 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-10 | TA 504 - DPR - 2026-07-10.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 3 |  | 507 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 5 |  | 428 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 5.84 |  | 68.95 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-10 | TA 506 - DPR - 2026-07-10.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 2 |  | 326 | 187 | 6 | 72.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 4 | 1 | 235 | 278 | 4 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 142 | 45 | 1 | 149 | 364 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0.361 | 0 | 25.066 | 163.612 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-09 | TB 507 [MAIN] - DPR - 2026-07-09.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3 | 1.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 3 |  | 9 | 34 | 3.0 | 89.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-09 | TB 507 - DPR - 2026-07-09.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 0 | 274 | 32 | 1.0 | G_1:- M.S Enterprises
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 0.65167 | 0 | 87.8917 | 29.9592 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-10 | TA 413 - DPR - 2026-07-10.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 4.775 | 0 | 73.835 | 44.0159 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 4 | 2 | 270 | 82 | 11.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-12 | TA 414 - DPR - 2026-07-12.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-09 | TA 418 - DPR - 2026-07-09.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-09 | TA 418 - DPR - 2026-07-09.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-09 | TA 418 - DPR - 2026-07-09.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-09 | TA 418 - DPR - 2026-07-09.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 36.865 | 10.975 | 3.199 | 0 | 40.064 | 7.776 | 5
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 4 | 0 | 316 | 3 | 01/15
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 9 | 1 | 246 | 73 | 13/370
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 4 | 2 | 115 | 204
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-12 | TA 512 - DPR - 2026-07-12.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 13 | 1 | 161 | 131 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 13 | 2 | 121 | 171
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 12 | 2 | 100 | 192 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-12 | TA 601 - DPR - 2026-07-12.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 2 |  | 148 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 | 2 |  | 127 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-12 | TA 504 - DPR - 2026-07-12.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 4 |  | 508 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 7 |  | 430 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 7.01 |  | 70.12 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-12 | TA 506 - DPR - 2026-07-12.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 5 | 2 | 329 | 184 | 6 | 59.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 4 |  | 235 | 278 | 10 | 90.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 142 | 47 | 2 | 151 | 362 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0.361 | 0 | 25.066 | 163.612 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-12 | TB 507 [MAIN] - DPR - 2026-07-12.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 3 |  | 9 | 34 | 3.0 | 89.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-12 | TB 507 - DPR - 2026-07-12.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 9 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 6 |  | 228 | 103 | 12 | 36/4, 37/0, 41/0, 43/2, 43/3, 48/0, 54/0, 66/1, 67/0, 70/0, 74/0, 75/0, 76/0,78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306 | 4 | 0B/0-0C/0, 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-13 | TA 419 - DPR - 2026-07-13.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 137 | 8 | 0 | 0 | 137 | 129 | 5.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 41 | 20 | 3 | 2 | 44 | 224 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 2 | 0 | 0 | 0 | 2 | 21
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 148 | 148
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 43 | 43
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-05 | TB 608 - DPR - 2026-07-05.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 335 | 17
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 5 | 1 | 271 | 81 | 10.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-13 | TA 414 - DPR - 2026-07-13.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 379 |  |  |  | 379 | 0 |  | Earthing-268/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 363 | 6 |  |  | 363 | 16 |  | Tack Welding Completed- 195/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 27.428 | 21.328 | 5.037 |  | 32.465 | 112.172
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-13 | TA 505 - DPR - 2026-07-13.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 30.433 | 22 | 9.538 |  | 39.899 | 109.167
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-12 | TA 510 - DPR - 2026-07-12.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  |  | 0 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 4 | 0 | 316 | 3 | 01/15
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 9 | 0 | 246 | 73 | 13/370
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 6 | 2 | 117 | 202
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-13 | TA 512 - DPR - 2026-07-13.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 14 | 1 | 162 | 130 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 14 | 1 | 122 | 170
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 13 | 1 | 101 | 191 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-13 | TA 601 - DPR - 2026-07-13.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 3 | 0 | 421 | 102 | 21.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 3 | 0 | 366 | 157 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 9 | 3 | 257 | 266 | 13.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 2.398 | 1.546 | 3.868 | 171.851 | 4.0 | Muslindin gang will be bifurcated into 2 gangs and gang is working on final checking of towers in 46-47 section JS _J
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-12 | TB 605 - DPR - 2026-07-12.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0.366 | 0 | 1.836 | 173.883
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 3 |  | 275 | 56 | 9 | 38/4, 47/0, 50/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0 96/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 7 |  | 229 | 102 | 13 | 37/0, 41/0, 43/2, 43/3, 48/0, 54/0, 65/1, 66/1, 67/0, 68/0, 70/0, 74/0, 75/0, 76/0, 76/1, 78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306 | 4 | 0B/0-0C/0, 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 2.765 |  | 5.765 | 116.306 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-14 | TA 419 - DPR - 2026-07-14.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 2 |  | 148 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 | 2 |  | 127 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-13 | TA 504 - DPR - 2026-07-13.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 5 |  | 509 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 7 |  | 430 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 7.01 |  | 70.12 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-13 | TA 506 - DPR - 2026-07-13.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-10 | TA 509 - DPR - 2026-07-10.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 274 | 8 | 2 |  | 276 | 33 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-10 | TA 509 - DPR - 2026-07-10.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 260 | 10 | 10 |  | 270 | 39
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-10 | TA 509 - DPR - 2026-07-10.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 220 | 15 | 2 |  | 222 | 87 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-10 | TA 509 - DPR - 2026-07-10.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 3.461 | 12 | 4.304 |  | 7.765 | 111.413 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-14 | TA 510 - DPR - 2026-07-14.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 14 | 0 | 162 | 130 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 16 | 2 | 124 | 168
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 14 | 1 | 102 | 190 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-14 | TA 601 - DPR - 2026-07-14.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 308 | 1 | 0 | 0 | 308 | 1
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 303 | 3 | 0 | 0 | 303 | 3 | 1.0 | G_1:- R.S construction
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 272 | 33 | 2 | 0 | 274 | 32 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 1.1057 | 0 | 88.3457 | 29.5052 | 3.0 | G_1:- Rahim Khan
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 1.1057 | 0 | 88.3457 | 29.5052 |  | G_2:- SK infra
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 87.24 | 20 | 1.1057 | 0 | 88.3457 | 29.5052 |  | G_3 Amir Sekh
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-07-13 | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 69.06 | 38.08 | 4.775 | 0 | 73.835 | 44.0159 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 336 | 16 |  |  | 336 | 16 | 1.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 332 | 20 |  |  | 335 | 17
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 266 | 30 | 6 | 1 | 272 | 80 | 9.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 186 | 55 |  |  | 186 | 166 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832 | 2.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 27.967 | 15 |  |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 25.046 | 15 | 2.921 |  | 27.967 | 99.832
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-07-15 | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 |  |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-11 | TA 416 - DPR - 2026-07-11.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-11 | TA 416 - DPR - 2026-07-11.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-11 | TA 416 - DPR - 2026-07-11.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-07-11 | TA 416 - DPR - 2026-07-11.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 0.678 | 0.678 | 115.136 | -0.002 | 4
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-13 | TA 418 - DPR - 2026-07-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-13 | TA 418 - DPR - 2026-07-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-13 | TA 418 - DPR - 2026-07-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-07-13 | TA 418 - DPR - 2026-07-13.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 36.865 | 10.975 | 4.262 | 0 | 41.127 | 6.713 | 4
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 272 | 30 | 5 |  | 277 | 54 | 9 | 38/4, 47/0, 57/0, 63B/4, 79/0, 82/0, 86/1, 87/1, 93C/0, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 265 | 35 | 0 |  | 265 | 65
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 222 | 40 | 9 |  | 231 | 100 | 14 | 37/0, 41/0, 43/3, 48/0, 50/1 ,54/0, 65/1, 66/1, 67/0, 68/0, 70/0, 74/0, 75/0, 76/1, 78A/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 110 | 50 | 0 |  | 110 | 221 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 3.525 |  | 6.525 | 115.546
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 3.525 |  | 6.525 | 115.546 | 4 | 0B/0-0C/0, 0C/0-0D/0, 0G/0-0H/0, 5/0-6/0, 6/0-7/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 3 | 19.5 | 3.525 |  | 6.525 | 115.546 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-07-15 | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0 |  | Tower Tightening Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 |  |  | RS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 121.342 |  |  |  | 121.342 | 0 | 2.0 | FS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 108.06 | 13.282 | 9.731 |  | 117.791 | 3.551 | 1.0 | 32/0 - 35/0 - 3.55 Km is on hold due to proposed repeater station
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-07-11 | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 146 | 7 | 2 |  | 148 | 40
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 125 | 6 | 2 |  | 127 | 61
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 20.561 |  |  |  | 20.561 | 48.439
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-07-14 | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 379 |  |  |  | 379 | 0 |  | Earthing-269/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 363 | 6 |  |  | 363 | 16 |  | Tack Welding Completed- 195/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 27.428 | 21.328 | 5.792 |  | 33.22 | 112.172
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-07-14 | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 30.433 | 22 | 12.462 |  | 39.899 | 109.167
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 504 | 37 | 5 |  | 509 | 98
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 423 | 20 | 7 |  | 430 | 179
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 63.11 | 27 | 7.01 |  | 70.12 | 159.89
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-07-14 | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-14 | TA 509 - DPR - 2026-07-14.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 274 | 8 | 3 |  | 277 | 32 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-14 | TA 509 - DPR - 2026-07-14.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 260 | 10 | 10 |  | 270 | 39
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-14 | TA 509 - DPR - 2026-07-14.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 220 | 15 | 3 |  | 223 | 86 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-07-14 | TA 509 - DPR - 2026-07-14.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 3.461 | 12 | 4.304 |  | 7.765 | 111.413 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 96 | 0 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 95 | 293 |  |  | 95 | 198 | 1.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 89 | 293 |  |  | 89 | 204
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 45 | 285 | 1 |  | 46 | 247 | 2.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 285 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 95 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-07-15 | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 75.27 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 316 |  | 1 | 1 | 317 | 2
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 312 |  | 4 | 0 | 316 | 3 | 01/15
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 299 |  |  | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 237 | 20 | 9 | 0 | 246 | 73 | 13/370
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 111 |  | 7 | 1 | 118 | 201
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-07-14 | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 148 | 35 | 16 | 2 | 164 | 128 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 108 | 35 | 16 | 0 | 124 | 168
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 88 | 25 | 14 | 0 | 102 | 190 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-07-15 | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 22 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 12 | 2 | 0 | 169 | 311 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 107 | 12 | 4 | 0 | 111 | 369
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 78 | 20 | 4 | 0 | 82 | 398 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 20 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-07-08 | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 6 | Foundation (Nos.) | foundation |  | 485 | 485 | 485 | 0 |  |  | 485 | 0 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 7 | Earthing (Nos.) | earthing |  | 485 | 485 | 485 | 0 |  |  | 485 | 0 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 8 | Tower Erection (Nos) | tower_erection |  | 485 | 485 | 484 | 1 |  |  | 484 | 1 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 9 | Tack Welding (Nos) | tack_welding |  | 485 | 485 | 433 | 52 |  |  | 433 | 52 | 1
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 10 | Paying Out (Kms) | paying_out |  | 191.392 | 191.392 | 125.953 | 25 |  |  | 125.953 | 31.673 | 2 | AP12-13:- WIP.
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 11 | Final Sag (Kms) | final_sag |  | 191.392 | 191.392 | 125.9367 | 25 |  |  | 125.9367 | 31.6893 |  | AP11A-12:- Completed AP12-13:- WIP.
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 12 | OPGW (Kms) | opgw_stringing |  | 191.392 | 191.392 | 88.466 | 30 |  |  | 88.466 | 69.16
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 10 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 11 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.147 | 1.686 | 0 |  | 149.147 | 1.686 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 12 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.499 | 3.334 | 0 |  | 147.499 | 3.334 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 14 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 137.191 | 13.642 | 0 |  | 137.191 | 13.642 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 15 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 119.607 | 31.226 | 0 |  | 119.607 | 31.226 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 16 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 17 | Excavation (Nos) | excavation | 564 | 505 | 505 | 324 | 35 | 0 |  | 324 | 181 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 18 | Foundation (Nos) | foundation | 564 | 505 | 505 | 312 | 35 | 7 |  | 319 | 175 | 11.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 19 | Earthing (Nos) | earthing | 564 | 505 | 505 | 226 | 38 | 5 |  | 231 | 274
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 20 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 138 | 45 | 8 |  | 146 | 353 | 6.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 21 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 45 | 0 |  | 21 | 484
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 22 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 3.199 | 6.2 | 0 |  | 3.199 | 146.886 | 2.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-07-09 | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 7 | 23 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 1 | 1 | 39 | 0 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 5 | 2 | 34 | 5 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.6976 | 0 | 6.9286 | 2.3114 | 1.0 | 3/1 to 4/0, 17/0 to 18/0, 18/0 to gantry Stringing final checking done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.6976 | 0 | 6.9286 | 2.3114
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-07-06 | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.1821 | 0 | 6.1821 | 3.0579 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 324 | 35 | 6 | 1 | 330 | 183 | 6 | 59.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  | 8 |  | 274 | 239
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 231 | 39 | 5 | 1 | 236 | 277 | 10 | 185.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 143 | 48 | 2 | 152 | 361 | 2 | 6.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 24.705 | 21.084 | 0.361 | 0 | 25.066 | 163.612 | 4(SK Tajirul; Tarikul Islam; KP Group; Mahadev Const) | 77.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 24.28 | 21.084 | 0 | 0 | 24.28 | 164.398
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-07-13 | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status | prefer_final_else_stringing | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 39 | 4 | 1 |  | 40 | 3
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 6 | 16 | 4 |  | 10 | 33 | 3.0 | 89.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 | 5 | 17 |  |  | 5 | 38
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-07-13 | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status | prefer_final_else_stringing | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 8 | Foundation | foundation |  | 523 | 523 | 418 | 46 | 5 | 1 | 423 | 100 | 21.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 9 | Earthing | earthing |  | 523 | 523 | 363 | 46 | 3 | 0 | 366 | 157 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 248 | 41 | 9 | 0 | 257 | 266 | 14.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 41 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 3.137 | 0.739 | 4.607 | 171.112 | 4.0 | Muslindin gang will be bifurcated into 2 gangs and gang is working on final checking of towers in 46-47 section JS _J
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-07-14 | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | TB 605 Status | prefer_final_else_stringing | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 | 1.47 | 9.6 | 0.366 | 0 | 1.836 | 173.883
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 137 | 8 | 1 | 0 | 138 | 128 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 41 | 20 | 5 | 0 | 46 | 222 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 2 | 0 | 0 | 0 | 2 | 21
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 148 | 148
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 43 | 43
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-07-13 | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | FilenameDate | InternalDate | DateQuality | Status | Reason
TA 413 - DPR - 2026-07-13.xlsx | TA 413 | TA413_PBNTL | TA413_PBNTL |  | filename | TA 413 Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:As per latest Estimate->quantity_estimated_or_total; C5:Cumm. Progress up to last Month->cumulative_last_month; C7:Plan for this Month->plan_for_month; C8:Current Month Achieved (As on dated )->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working | XML scrub fallback used for sheet 'TA413_PBNTL' | 1 | 1 | 12 | 2026-07-13 | 2024-03-12 | MISMATCH | OK
TA 414 - DPR - 2026-07-15.xlsx | TA 414 | VNTL - KEC | VNTL - KEC |  | filename | TA 414 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month (June'26)->cumulative_last_month; C6:L3 Plan for the month (July'26 )->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks | XML scrub fallback used for sheet 'VNTL - KEC' | 1 | 1 | 13 | 2026-07-15 |  | MISSING_INTERNAL | OK
TA 416 - DPR - 2026-07-11.xlsx | TA 416 | MASTER SHEET | MASTER SHEET |  | filename | TA 416 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-07-11 | 2026-03-31 | MISMATCH | OK
TA 418 - DPR - 2026-07-13.xlsx | TA 418 | MASTER SHEET | MASTER SHEET |  | filename | TA 418 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-07-13 | 2026-07-13 | MATCH | OK
TA 419 - DPR - 2026-07-15.xlsx | TA 419 | DPR_TA419 | DPR_TA419 |  | filename | TA 419 Status | TRUE | C3:Activity->activity_raw; C4:Quantity->quantity_loa; C5:unnamed_col_5->quantity_estimated_or_total; C7:unnamed_col_7->cumulative_last_month; C9:unnamed_col_9->plan_for_month; C10:Progress for the Month->progress_for_month; C11:unnamed_col_11->today_progress; C12:Cumulative Progress->cumulative_progress; C13:Balance Progress->balance_progress; C14:Gangs working Jul-26->gangs_working; C15:2026-07-14 00:00:00 Remarks->remarks | XML scrub fallback used for sheet 'DPR_TA419' | 1 | 1 | 14 | 2026-07-15 |  | MISSING_INTERNAL | OK
TA 421 - DPR - 2026-07-11.xlsx | TA 421 | Master Sheet | Master Sheet |  | filename | TA 421 Status | TRUE | C3:Activity->activity_raw; C4:Final Estimated Quantity->quantity_estimated_or_total; C6:Cumulative Progress till Last Month->cumulative_last_month; C8:Plan for the Month->plan_for_month; C9:Today's Progress->today_progress; C10:Progress till Date for the Month->progress_for_month; C12:Completed till Date->cumulative_progress; C13:Balance Work->balance_progress; C15:Gangs at Present->gangs_working |  | 1 | 1 | 10 | 2026-07-11 | 2026-07-12 | MISMATCH | OK
TA 504 - DPR - 2026-07-14.xlsx | TA 504 | DPR_TA-504 | DPR_TA-504 |  | filename | TA 504 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-06-01 00:00:00->cumulative_last_month; C6:Balance as on 1 July'26->balance_progress; C7:2026-07-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-504' | 1 | 1 | 6 | 2026-07-14 |  | MISSING_INTERNAL | OK
TA 505 - DPR - 2026-07-14.xlsx | TA 505 | DPR-Summary | DPR-Summary |  | filename | TA 505 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-06-30 00:00:00->cumulative_last_month; C6:Balance as on 1st July-26->balance_progress; C7:July'26 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress |  | 1 | 1 | 6 | 2026-07-14 |  | MISSING_INTERNAL | OK
TA 506 - DPR - 2026-07-14.xlsx | TA 506 | DPR_TA-506 | DPR_TA-506 |  | filename | TA 506 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-06-01 00:00:00->cumulative_last_month; C6:Balance as on 1 July'26->balance_progress; C7:2026-06-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-506' | 1 | 1 | 6 | 2026-07-14 |  | MISSING_INTERNAL | OK
TA 509 - DPR - 2026-07-14.xlsx | TA 509 | SUMMARY | SUMMARY |  | filename | TA 509 Status | TRUE | C1:Activity->activity_raw; C4:LOA Quantity->quantity_loa; C5:Final Estimated Quantity->quantity_estimated_or_total; C7:Cum Progress till Last Month->cumulative_last_month; C9:Plan for the Month->plan_for_month; C10:Progress for Today->today_progress; C11:Progress for the Month->progress_for_month; C13:Cum. Progress till date->cumulative_progress; C14:Balance Work->balance_progress; C16:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-07-14 | 2026-07-14 | MATCH | OK
TA 510 - DPR - 2026-07-15.xlsx | TA 510 | AOTL - KEC | AOTL - KEC |  | filename | TA 510 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month June'26)->cumulative_last_month; C5:Target as per L2 Schedule Cummulative (upto June'26)->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-07-15 |  | MISSING_INTERNAL | OK
TA 512 - DPR - 2026-07-14.xlsx | TA 512 | Summary E | Summary E |  | filename | TA 512 Status | TRUE | C2:Activity->activity_raw; C3:LOA Qty->quantity_loa; C4:Estimated Quantity->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (Jun'26)->cumulative_last_month; C7:Month's Plan as per L2 Schedule->plan_for_month; C8:Progress of Month->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress Till Date->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs/MP->gangs_working |  | 1 | 1 | 13 | 2026-07-14 |  | MISSING_INTERNAL | OK
TA 513 - DPR - 2026-07-15.xlsx | TA 513 | Summary | Summary |  | filename | TA 513 Status | TRUE |  |  | 0 | 0 | 0 | 2026-07-15 |  | MISSING_INTERNAL | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 601 - DPR - 2026-07-15.xlsx | TA 601 | Master Sheet | Master Sheet |  | filename | TA 601 Status | TRUE | C2:Activity->activity_raw; C3:Scope Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress for Current Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 11 | 2026-07-15 | 2026-07-15 | MATCH | OK
TA 602 - DPR - 2026-07-08.xlsx | TA 602 | 800kV HVDC TA-602 | 800kV HVDC TA-602 |  | filename | TA 602 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(June'26)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working | XML scrub fallback used for sheet '800kV HVDC TA-602' | 1 | 1 | 6 | 2026-07-08 | 2026-07-09 | MISMATCH | OK
TB 408 - DPR - 2026-06-01.xlsx | TB 408 | Progress Summary | Progress Summary |  | filename | TB 408 Status | TRUE | C2:Activity->activity_raw; C3:As per latest Estimate->quantity_estimated_or_total; C4:Cumm. Progress up to last Month->cumulative_last_month; C6:Plan for this Month->plan_for_month; C7:Today Progress->today_progress; C8:MTD->progress_for_month; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:Gangs at present->gangs_working |  | 1 | 1 | 7 | 2026-06-01 | 2026-06-01 | MATCH | OK
TB 412 - DPR - 2026-07-09.xlsx | TB 412 | TB-412 SUMMARY | TB-412 SUMMARY |  | filename | TB 412 Status | TRUE | C2:Activity->activity_raw; C3:Total Quantity->quantity_loa; C4:unnamed_col_4->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (June'26)->cumulative_last_month; C7:Target of Month for (July'2026)->plan_for_month; C8:Comp This Month (July'2026)->progress_for_month; C9:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-07-09 | 2026-07-09 | MATCH | OK
TB 501 - DPR - 2026-07-06.xlsx | TB 501 | Summary | Summary |  | filename | TB 501 Status | TRUE | C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (July'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks; C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (July'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks |  | 2 | 2 | 20 | 2026-07-06 | 2026-07-06 | MATCH | OK
TB 507 [MAIN] - DPR - 2026-07-13.xlsx | TB 507 | 400kV Summery | 400kV Summery | MAIN | config | TB 507 400kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For JULY'26->plan_for_month; C7:Progress in JULY'26->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jul-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 14 | 2026-07-13 |  | MISSING_INTERNAL | OK
TB 507 - DPR - 2026-07-13.xlsx | TB 507 | 765kV Summery | 765kV Summery | 765kV | config | TB 507 765kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For July'26->plan_for_month; C7:Progress in July'26->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jul-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 12 | 2026-07-13 |  | MISSING_INTERNAL | OK
TB 605 - DPR - 2026-07-14.xlsx | TB 605 | TB-605 | TB-605 |  | filename | TB 605 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Qty->quantity_estimated_or_total; C4:Cumulative Progress till Last Month->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working |  | 1 | 1 | 7 | 2026-07-14 | 2026-07-14 | MATCH | OK
TB 608 - DPR - 2026-07-13.xlsm | TB 608 | DPR Sum. | DPR Sum. |  | filename | TB 608 Status | TRUE | C2:Description->activity_raw; C4:LOA Qty->quantity_loa; C5:Revised Qty->quantity_estimated_or_total; C9:As Per Actual->cumulative_last_month; C10:unnamed_col_10->progress_for_month; C11:unnamed_col_11->cumulative_progress; C12:Balance->balance_progress; C13:Target for the month->plan_for_month; C22:Today's progress->today_progress; C23:Gang->gangs_working |  | 1 | 1 | 41 | 2026-07-13 |  | MISSING_INTERNAL | OK

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason
TA 513 - DPR - 2026-07-15.xlsx | TA 513 | Summary | Summary |  | filename | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 515 - DPR - 2026-06-18.xlsx | TA 515 | DPR | DPR |  | filename | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found.

## Coverage
project_code | project_display | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | filename_date | internal_date | date_quality | available_sheets
TA 413 | TA 413 | OK | OK |  | TA 413 - DPR - 2026-07-13.xlsx | TA413_PBNTL | TA413_PBNTL | 12 | 2026-07-13 | 2024-03-12 | MISMATCH | TA413_PBNTL; WIP; Visual Chart; Stringing; Stretch readiness ; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Aviation Paint; Accessories; OPGW; Foundation; JUMPER Details; Crossing status; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area
TA 414 | TA 414 | OK | OK |  | TA 414 - DPR - 2026-07-15.xlsx | VNTL - KEC | VNTL - KEC | 13 | 2026-07-15 |  | MISSING_INTERNAL | Project Details; 765KV TA 414 VNTL; VNTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Sheet6; Sheet4; Sheet7; Stringing Compiled; Visual chart; Pile Fdn; Crossing; Sheet2; Survey; Soil Inv.; Survey Anx
TA 416 | TA 416 | OK | OK |  | TA 416 - DPR - 2026-07-11.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-07-11 | 2026-03-31 | MISMATCH | Project Details; MASTER SHEET; Erection Compiled ; Stringing compiled; Progress.; Visual chart.; PENDING FDN DETAILS; PENDING ERE DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; TS; TS (2)
TA 418 | TA 418 | OK | OK |  | TA 418 - DPR - 2026-07-13.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-07-13 | 2026-07-13 | MATCH | MASTER SHEET; Progress; Erection Completed; Stringing Completed; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2)
TA 419 | TA 419 | OK | OK |  | TA 419 - DPR - 2026-07-15.xlsx | DPR_TA419 | DPR_TA419 | 14 | 2026-07-15 |  | MISSING_INTERNAL | DPR_TA419; Soil Inv; RATE; FDN; Updated Tower Schedule; Visual Chart; ERT; ERECTION COMPILED; Stringing Compiled; Stringing Stretch Readiness; Project details; Detailed Survey; Supply; dont change; TOWER ABSTRACT; Corridor LS; Foundation Daily Progresss; Erection Daily Progress; Statutory
TA 421 | TA 421 | OK | OK |  | TA 421 - DPR - 2026-07-11.xlsx | Master Sheet | Master Sheet | 10 | 2026-07-11 | 2026-07-12 | MISMATCH | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; AL Bond ; Birdguard ; Tower Tightening ; Hardwares & Tower Accessories ; SwE
TA 504 | TA 504 | OK | OK |  | TA 504 - DPR - 2026-07-14.xlsx | DPR_TA-504 | DPR_TA-504 | 6 | 2026-07-14 |  | MISSING_INTERNAL | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_MAIN; VC_Lilo; Project Details; Location Summary
TA 505 | TA 505 | OK | OK |  | TA 505 - DPR - 2026-07-14.xlsx | DPR-Summary | DPR-Summary | 6 | 2026-07-14 |  | MISSING_INTERNAL | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2
TA 506 | TA 506 | OK | OK |  | TA 506 - DPR - 2026-07-14.xlsx | DPR_TA-506 | DPR_TA-506 | 6 | 2026-07-14 |  | MISSING_INTERNAL | DPR_TA-506; VC; Erection compiled; Tightening; Stringing; Project Details; Location Summary
TA 509 | TA 509 | OK | OK |  | TA 509 - DPR - 2026-07-14.xlsx | SUMMARY | SUMMARY | 4 | 2026-07-14 | 2026-07-14 | MATCH | VC-765kV MKTL; FDN pivot; Erc pivot; Visual Chart.; Sheet3; DPR; SUMMARY; Sheet2; XING; FOUNDATION; ERECTION; EARTHING; SUPPLY; Visual Chart; OLD Gantry To AP 68 Old TS; Final Tower Schedule TS; Sheet1; SURVEY SUMMARY; SURVEY STATUS ; Erection productivity
TA 510 | TA 510 | OK | OK |  | TA 510 - DPR - 2026-07-15.xlsx | AOTL - KEC | AOTL - KEC | 13 | 2026-07-15 |  | MISSING_INTERNAL | 765KV TA 414 VNTL; 765KV ASOTL; Project Details; AOTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; Soil Inv.; Survey Anx; Survey; FDN; Erection ; Visual chart 1 ; Pile Foundation; Sheet6; Sheet4; Sheet7; Stringing Compiled; String; Crossing; Tree Enumeration; Sheet2
TA 512 | TA 512 | OK | OK |  | TA 512 - DPR - 2026-07-14.xlsx | Summary E | Summary E | 13 | 2026-07-14 |  | MISSING_INTERNAL | Summary S; Supply Status; Summary E; DPR Sheet ; DS; CS; Hindrance Record; Earthing; Foundation; Erection Compiled; Tack Welding; Visual Chart; WIP; Statuary clearance; Stringing; OPGW; Accessories; Shield Wire Earthing; TS Gantry - AP47; Project Details; L3 Plan; Supply DPR ; Power line Crossings ; Hardware
TA 513 | TA 513 | HEADER_NOT_FOUND | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters. | TA 513 - DPR - 2026-07-15.xlsx | Summary | Summary | 0 | 2026-07-15 |  | MISSING_INTERNAL | Summary; SF Village Wise; Earthing S-P; T.Marking; ERT; SP Village Wise; LS Physical; VC SF ; VC SP; LS; Survey ; FDN S-P; FDN S-F; Ere S-F ; Total Supply; Ere S-P ; T.Abstract; Crossing status ; Earthing S-F; Proposal .; ROW S-F; ROW S-P; TS SP ; TS SF; Sheet1; Forest
TA 515 | TA 515 | TEMPLATE_CONFIG_ERROR | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found. | TA 515 - DPR - 2026-06-18.xlsx | DPR | DPR | 0 | 2026-06-18 |  | UNREADABLE | DPR; Foundation Compiled; Earthing; Erection Compiled; Store Stock; Visual chart
TA 601 | TA 601 | OK | OK |  | TA 601 - DPR - 2026-07-15.xlsx | Master Sheet | Master Sheet | 11 | 2026-07-15 | 2026-07-15 | MATCH | Visual Chart ; Master Sheet; Progress Sheet ; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled
TA 602 | TA 602 | OK | OK |  | TA 602 - DPR - 2026-07-08.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6 | 2026-07-08 | 2026-07-09 | MISMATCH | Completion Plan; Project Details; PGCIL - KEC; PPT-Erection Part; CMD-1; CMD-2; PPT _Statutory; PPT Supply; Supply Status; 800kV HVDC TA-602; DPR Sheet; Survey details 11-06-2026; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; TA-602Visual Chart ; Visual chart; Pile Fdn; Crossing; Survey; Soil Inv.; Survey Anx
TB 408 | TB 408 | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | 7 | 2026-06-01 | 2026-06-01 | MATCH | Progress Summary; Project Details; X-ing Status; L2 Schedule vs Actual; Hindrance Register (Row); Page Chart; Survey; Foundation; Earthing; Erection Productivity; Crane Erection Productivity; Erection Compiled; Tackwelding; Stringing; Stringing associated works; Stringing Productivity; OPGW; Accessories details; Visual chart; Visual chart Edit; Benching F
TB 412 | TB 412 | OK | OK |  | TB 412 - DPR - 2026-07-09.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | 13 | 2026-07-09 | 2026-07-09 | MATCH | TB-412 SUMMARY; Summary-; Survey Status; Sheet3; DPR Sheet ; WIP; GANG Mapping MAY-26 ; Soil Investigation; Sheet1; Progress 400kV QM; VC 400 KV QM; Progress 220KV TM; VC 220 TM; VC 220 SZ; ROW; 220 SZ Status; CS-220kV TM ; DS-220 KV TM; DS 400kV LI; DS 400 kV LO; Survey Report; Foundation; Earthing Pending; Erection; Earthing; Stringing; Earthing Balance; Statutary ; Power line Crossings
TB 501 | TB 501 | OK | OK |  | TB 501 - DPR - 2026-07-06.xlsx | Summary | Summary | 20 | 2026-07-06 | 2026-07-06 | MATCH | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body
TB 507 | TB 507 - MAIN | OK | OK |  | TB 507 [MAIN] - DPR - 2026-07-13.xlsx | 400kV Summery | 400kV Summery | 14 | 2026-07-13 |  | MISSING_INTERNAL | 400kV Summery; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Project Details; Foundation; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Royalty; Sheet14; Sheet7; Erection ; Completion date; Sheet12; Erection Compiled ; Earthing; Final Check In And Tack Welding; Sheet10; Sheet11; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart 1; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 507 | TB 507 - 765kV | OK | OK |  | TB 507 - DPR - 2026-07-13.xlsx | 765kV Summery | 765kV Summery | 12 | 2026-07-13 |  | MISSING_INTERNAL | 765kV Summery; Check Survey Status; Check Survey; Sheet8; Sheet2; Sheet1; VC 51-96; VC; ROW; June; Check survey Loop out; Check survey Loop In; Royalty; Sheet14; Sheet7; Project Details; Foundation; Erection ; Completion date; Erection Compiled ; Earthing; Final Checking and Tack Welding; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 605 | TB 605 | OK | OK |  | TB 605 - DPR - 2026-07-14.xlsx | TB-605 | TB-605 | 7 | 2026-07-14 | 2026-07-14 | MATCH | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); Sheet2; Sheet3; Sheet4; Sheet5; ROW; Sheet13 (2); TB-605; Sheet19; Sheet16; Sheet14; Sheet12; Sheet13; Sheet15; TB401 DPR; Survey-Summary; Sheet6; Approved Survey; Approved CS J-S Line; Approved CS K-S Line; Foundation JS-Line -Jammu; Sheet10; Erection -Jammu; Vertical Chart -JS Line Jammu ; Sheet17; Stringing JS-Jammu; Erection -SK; Sheet7; Sheet8; LILO; Erection-Punjab; Vertical Chart -JS Line Punjab; Sheet9; ROW Front vs Progress; Foundation -JS Line- Punjab; Pile FDN; Hindrance; Foundation -KS Line; Manpower; Final Checking; Stubs JS; Stubs SK; Towers JS; Towers SK; Sum; Sheet18; JS-Supply Stubs; JS Supply Towers; SK Supply Stubs; SK Supply Towers; Sheet11; Planned Vs Actual -FDN; Supply Status; Material Status-Jammu-Punjab; Material Status-Punjab; Earthing (PKG-F); Earthing (PKG-G); Revetment Pkg-G; Benching Status-F; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-G; Tack Welding - PKG-F; Painting - PKG-G; Painting - PKG-F; Eretion - PKG-G; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Clear locs shared by client
TB 608 | TB 608 | OK | OK |  | TB 608 - DPR - 2026-07-13.xlsm | DPR Sum. | DPR Sum. | 41 | 2026-07-13 |  | MISSING_INTERNAL | Master Sheet; DPR Sum.; Master Sheet ; Gang Movement; Support Required; WIP-FDN; WIP-ERC; Line Details; Visual_Chart; Foundation Activity; Supply; Sheet2