## Main
KEC INTERNATIONAL LTD. | [12 empty] | PGCIL
|  | Project Code | TA-416 | [5 empty] | Date | 2025-09-14 | Chief Executive, India(T&D | Rajinder Gupta
|  | Project Name | TWR PKG TL03 FOR NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE WZ-5 (Part-III) | [5 empty] | NOA/LOA Start date | 2024-02-07 | PCH | Arun Felbin
|  | Client Name | POWERGRID Neemrana II Bareilly Transmission Ltd | [5 empty] | LOA End Date | 2025-11-06 | PM | Sanjay Gupta
|  | NOA | CC/T/W-TW/DOM/A10/23/10706/NOA-2/24-101862/02 | [5 empty] | Planning | Sanjib Samantaray
Line Name:NEEMRANA-II-BAREILLY (PG) 765KV D/C LINE,WZ-5 (Part-III) | [8 empty] | Current Status |  | Revenue for the month |  | Remark
Activity | LOA Quantity | Estimated Quantity | Cumm. L2 till Last Month | Cumm. Progress till Last Month | L2 for current month | Plan for Sep 2025 | Progress for Sep 2025 | Today Progress | Cumulative progress Till date | Balance | Revenue for the Day in Cr. | Cumulative Revenue for the Month in Cr. |  | Gangs at Present
Detail Survey | 143.486 | 144 | 143.49 | 144 | -- | -- | -- | -- | 144 | -- |  |  | --
Detail Survey | 115.512 | 114.985 | 115.51 | 114.985 | -- | -- |  |  | 114.985 | 0 | -- | --
Check Survey | 115.512 | 114.985 | 116 | 115 |  |  |  |  | 115 | -0.015 | 0 | 0 | Survey Completed
Soil Investigation | 12 | 19 |  | 19 |  |  |  |  | 19 | 0 | 0 | 0.013843
Foundation | 303 | 302 | 303 | 302 | 0 | 0 |  |  | 302 | 0 |  |  | All Foundation completed
Earthing | 303 | 302 | 303 | 302 | 0 | 0 |  |  | 302 | 0 |  |  | All Earthing Completed
Erection | 303 | 302 | 302 | 243 | 0 | 30 | 5 | 2 | 248 | 54 | 0.18356 | 0.42298 | 'Loc - 11/0,16/0 erection Completed .Loc - 23/0,29/0,25/0,19/0,2/0,17/6,26/0,17/0 ,52/0,64/0,47/0,56/8,48/1,53A/1 are WIP | 14
Tac Welding | 303 | 302 | 302 | 150 | 0 | 50 | 1 |  | 151 | 151 |  |  |  | 2
Stringing (PO) | 115.51 | 114.985 | 110 | 32.55 | 6 | 24 | 8.5 |  | 41.05 | 73.935 |  |  | 3/0-4/0:-Conductor bit cutting u/p 30/0-31/0:-Insulator hoisting u/p 20/0-21/0:-Insulator Hoisting Completed | 3
Stringing (FS) | 115.51 | 115 | 110 | 28.14 | 6 | 24 | 4.4 |  | 32.54 | 82.46 |  | 0.39856
Stringing OPGW | 115.51 | 114.985 |  |  | -- |  |  |  | 0 | 114.985 | -- | 0.82153
Accessories | 115.51 | 302 |  |  | -- |  |  |  | 0 | 302 |  | 0
0.82153
Crossing Summary
Type of Hold | Locations Affected | Kms Affected | No. of crossing proposed | Date of Submission Actual/Expected | Approved | Concerning Authority | Total Locs Affected | Total Kms Affected | Remarks
Row
Power Line |  |  | 21 |  | 21 |  |  |  | All Powerline crossing approval Coompleted
NH/SH/Express way. |  |  | 7 |  | 7 |  |  |  | ALL NH Xing approval Completed
Railway |  |  | 3 |  | 3 |  |  |  | All RLY Xing approval Completed
River Crossing |  |  | 1 |  | 1 |  |  |  | River Crossing Approved
Others
Foundation
SL No. | Location No. | Tower Type. | Soil Classification. | Starting Date | Completion Date | Excavation Volume | PCC-M10 | RCC-M20 | Work Status as on Date |  | Name of Gang | Gang Strength | Remark
1 | 2/8 | DA+0 | Wet Paddy | 2024-04-24 | 2024-05-06 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
2 | 2/7 | DA+3 | Wet Paddy | 2024-05-01 | 2024-05-10 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
3 | 2/6 | DA+0 | Wet Paddy | 2024-05-09 | 2024-05-14 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
4 | 2/5 | DA+3 | Wet Paddy | 2024-05-13 | 2024-05-18 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
5 | 2/4 | DA+0 | Wet Paddy | 2024-05-16 | 2024-05-21 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
6 | 2/3 | DA+3 | Wet Paddy | 2024-05-22 | 2024-05-28 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
7 | 39/10 | DA+0 | Wet Paddy | 2024-05-28 | 2024-06-04 | 248.14 | 3.06 | 34.58 | Completed |  | Dharamdas Contractor
8 | 17/4 | DA+3 | Wet Paddy | 2024-05-31 | 2024-06-03 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
9 | 17/5 | DA+3 | Wet Paddy | 2024-05-31 | 2024-06-06 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
10 | 17/3 | DA+0 | Wet Paddy | 2024-06-04 | 2024-06-09 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
11 | 39/8 | DA+0 | Wet Paddy | 2024-06-04 | 2024-06-08 | 248.14 | 3.06 | 34.58 | Completed |  | Dharamdas Contractor
12 | 6/2 | DA+3 | Sandy | 2024-06-06 | 2024-06-12 | 340.27 | 4.29 | 44.74 | Completed |  | Khalil Const.
13 | 17/6 | DA-3 | Wet Paddy | 2024-06-07 | 2024-06-11 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
14 | 39/9 | DA+3 | Wet Paddy | 2024-06-08 | 2024-06-13 | 278.48 | 3.46 | 37.91 | Completed |  | Dharamdas Contractor
15 | 17/7 | DA+3 | Wet Paddy | 2024-06-10 | 2024-06-14 | 278.48 | 3.46 | 37.91 | Completed |  | Sumit Constrcution
16 | 39/7 | DA+3 | Wet Paddy | 2024-06-12 | 2024-06-19 | 278.48 | 3.46 | 37.91 | Completed |  | Dharamdas Contractor
17 | 39/1 | DA+3 | Wet Paddy | 2024-06-13 | 2024-06-23 | 278.48 | 3.46 | 37.91 | Completed |  | Anshika con.
18 | 20/6 | DA+0 | Wet Paddy | 2024-06-13 | 2024-06-22 | 248.14 | 3.06 | 34.58 | Completed |  | Khalil Const.
19 | 17/8 | DA-3 | Wet Paddy | 2024-06-13 | 2024-06-17 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
20 | 17/1 | DA-3 | Wet Paddy | 2024-06-13 | 2024-06-20 | 248.14 | 3.06 | 34.58 | Completed |  | Sumit Constrcution
21 | 39/6 | DA+3 | Wet Paddy | 2024-06-20 | 2024-06-25 | 278.48 | 3.46 | 37.91 | Completed |  | Dharamdas Contractor
22 | 20/7 | DA-3 | Wet Paddy | 2024-06-21 | 2024-06-27 | 248.14 | 3.06 | 34.58 | Completed |  | Khalil Const.
23 | 38/11 | DA+3 | Sandy | 2024-06-22 | 2024-06-30 | 340.27 | 4.29 | 44.74 | Completed |  | Anshika con.
24 | 38/1 | DA+3 | Sandy | 2024-07-01 | 2024-07-11 | 340.27 | 4.29 | 44.74 | Completed |  | Anshika con.
25 | 20/12 | DA-3 | Wet Paddy | 2024-07-08 | 2024-07-15 | 248.14 | 3.06 | 34.58 | Completed |  | Jay Sri Ram
26 | 38/2 | DA+3 | Sandy | 2024-07-11 | 2024-07-18 | 340.27 | 4.29 | 44.74 | Completed |  | Anshika con.
27 | 19/11 | DA-3 | Wet Paddy | 2024-07-12 | 2024-07-23 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
28 | 14/5 | DA+3 | Wet Paddy | 2024-07-13 | 2024-07-20 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
29 | 38/3 | DA+3 | Sandy | 2024-07-15 | 2024-07-25 | 340.27 | 4.29 | 44.74 | Completed |  | Anshika con.
30 | 38/4 | DA+3 | WET | 2024-07-20 | 2024-07-31 | 435.91 | 5.58 | 55.48 | Completed |  | Anshika con.
31 | 19/8 | DA-3 | Wet Paddy | 2024-07-20 | 2024-07-30 | 248.14 | 3.06 | 34.58 | Completed |  | Jay Sri Ram
32 | 20/8 | DA+0 | Wet Paddy | 2024-07-20 | 2024-07-29 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
33 | 14/6 | DA+3 | Wet Paddy | 2024-07-22 | 2024-07-28 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
34 | 19/9 | DA+3 | Wet Paddy | 2024-07-28 | 2024-08-04 | 278.48 | 3.46 | 37.91 | Completed |  | K R Associates
35 | 14/4 | DA+3 | Wet Paddy | 2024-07-28 | 2024-08-09 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
36 | 20/9 | DA+3 | Wet Paddy | 2024-07-30 | 2024-08-03 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
37 | 36/12 | DA+0 | Sandy | 2025-08-01 | 2024-08-08 | 317.21 | 3.98 | 42.18 | Completed |  | Anshika con.
38 | 20/5 | DA+3 | Wet Paddy | 2024-08-05 | 2024-08-10 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
39 | 36/11 | DA-3 | Wet Paddy | 2024-08-08 | 2024-08-14 | 248.14 | 3.06 | 34.58 | Completed |  | Anshika con.
40 | 14/3 | DA+0 | Wet Paddy | 2024-08-10 | 2024-08-21 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
41 | 23/3 | DA-3 | Wet Paddy | 2024-08-12 | 2024-08-18 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
42 | 19/12 | DA-3 | Wet Paddy | 2024-08-12 | 2024-08-24 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
43 | 12/9 | DA+3 | Wet Paddy | 2024-08-16 | 2024-08-31 | 278.48 | 3.46 | 37.91 | Completed |  | VED ENTTERPRISE
44 | 23/4 | DA-3 | Wet Paddy | 2024-08-23 | 2024-08-31 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
45 | 36/3 | DA+3 | Wet Paddy | 2024-08-23 | 2024-08-31 | 278.48 | 3.46 | 37.91 | Completed |  | J M Enterprise
46 | 14/7 | DA+0 | Wet Paddy | 2024-08-24 | 2024-08-30 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
47 | 36/7 | DA+3 | Wet Paddy | 2024-08-24 | 2024-09-09 | 278.48 | 3.46 | 37.91 | Completed |  | SAIFI CON.
48 | 38/8 | DA+3 | WET | 2024-08-24 | 2024-09-08 | 435.91 | 5.58 | 55.48 | Completed |  | A V I ENTERPRISE
49 | 19/1 | DA+0 | Wet Paddy | 2024-08-24 | 2024-09-30 | 248.14 | 3.06 | 34.58 | Completed |  | MALLIK CON
50 | 19/3 | DA+3 | Wet Paddy | 2024-08-24 | 2024-09-05 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
51 | 19/2 | DA+0 | Wet Paddy | 2024-08-24 | 2024-09-22 | 248.14 | 3.06 | 34.58 | Completed |  | Shree Krishna
52 | 36/6 | DA+3 | Wet Paddy | 2024-08-24 | 2024-09-20 | 278.48 | 3.46 | 37.91 | Completed |  | SAIFI CON.
53 | 45/3 | DA-3 | WET | 2024-08-24 | 2024-09-08 | 415.84 | 5.3 | 53.21 | Completed |  | Vinayak Enterprise
54 | 50/1 | DA+0 | Wet Paddy | 2024-08-24 | 2024-09-11 | 248.14 | 3.06 | 34.58 | Completed |  | Vishal construction
55 | 39/4 | DA+3 | WET | 2024-08-29 | 2024-09-08 | 435.91 | 5.58 | 55.48 | Completed |  | Dharamdas Contractor
56 | 20/1 | DA+6 | Wet Paddy | 2024-08-30 | 2024-09-22 | 278.48 | 3.46 | 37.91 | Completed |  | K R Associates
57 | 12/8 | DA-3 | Wet Paddy | 2024-09-01 | 2024-09-09 | 248.14 | 3.06 | 34.58 | Completed |  | VED ENTTERPRISE
58 | 12/4 | DA+3 | Wet Paddy | 2024-09-01 | 2024-09-08 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
59 | 12/2 | DA+3 | Wet Paddy | 2024-09-08 | 2024-09-24 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
60 | 23/5 | DA-3 | Wet Paddy | 2024-09-08 | 2024-09-11 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
61 | 30/3 | DA+0 | Wet Paddy | 2024-09-08 | 2024-09-22 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
62 | 41/1 | DA+0 | Wet Paddy | 2024-09-09 | 2024-09-20 | 248.14 | 3.06 | 34.58 | Completed |  | Dharamdas Contractor
63 | 36/10 | DA-3 | Wet Paddy | 2024-09-09 | 2024-09-30 | 248.14 | 3.06 | 34.58 | Completed |  | J M Enterprise
64 | 45/2 | DA+3 | Wet Paddy | 2024-09-09 | 2024-09-29 | 278.48 | 3.46 | 37.91 | Completed |  | Vinayak Enterprise
65 | 23/2 | DA+0 | Wet Paddy | 2024-09-11 | 2024-09-20 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
66 | 30/6 | DA-3 | Wet Paddy | 2024-09-19 | 2024-09-24 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
67 | 35/2 | DA-3 | Wet Paddy | 2024-09-19 | 2024-09-26 | 248.14 | 3.06 | 34.58 | Completed |  | A V I ENTERPRISE
68 | 41/2 | DA+3 | Wet Paddy | 2024-09-19 | 2024-09-26 | 278.48 | 3.46 | 37.91 | Completed |  | Dharamdas Contractor
69 | 36/9 | DA-3 | Wet Paddy | 2024-09-19 | 2024-09-24 | 248.14 | 3.06 | 34.58 | Completed |  | SAIFI CON.
70 | 36/5 | DA+0 | Wet Paddy | 2024-09-20 | 2024-09-26 | 248.14 | 3.06 | 34.58 | Completed |  | J M Enterprise
71 | 25/1 | DA+9 | Wet Paddy | 2024-09-22 | 2024-09-26 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
72 | 30/4 | DA+3 | Wet Paddy | 2024-09-22 | 2024-09-30 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
73 | 12/6 | DA-3 | Wet Paddy | 2024-09-23 | 2024-09-30 | 248.14 | 3.06 | 34.58 | Completed |  | VED ENTTERPRISE
74 | 12/1 | DA-3 | Wet Paddy | 2024-09-25 | 2024-09-30 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
75 | 23/1 | DA+9 | Wet Paddy | 2024-09-26 | 2024-09-30 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
76 | 12/7 | DA-3 | Wet Paddy | 2024-09-27 | 2024-10-06 | 248.14 | 3.06 | 34.58 | Completed |  | VED ENTTERPRISE
77 | 46/1 | DA+0 | Wet Paddy | 2024-09-09 | 2024-10-10 | 248.14 | 3.06 | 34.58 | Completed |  | Vinayak Enterprise
78 | 35/1 | DA+3 | Wet Paddy | 2024-09-20 | 2024-10-01 | 278.48 | 3.46 | 37.91 | Completed |  | Maa Durga
79 | 46/2 | DA+3 | Wet Paddy | 2024-09-25 | 2024-10-03 | 278.48 | 3.46 | 37.91 | Completed |  | Vishal construction
80 | 36/8 | DA-3 | Wet Paddy | 2024-09-26 | 2024-10-06 | 248.14 | 3.06 | 34.58 | Completed |  | SAIFI CON.
81 | 34/7 | DA+3 | Wet Paddy | 2024-09-26 | 2024-10-03 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
82 | 35/3 | DA+0 | Wet Paddy | 2024-09-27 | 2024-10-01 | 248.14 | 3.06 | 34.58 | Completed |  | A V I ENTERPRISE
83 | 25/2 | DA+0 | Wet Paddy | 2024-10-01 | 2024-10-04 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
84 | 12/3 | DA+3 | Wet Paddy | 2024-10-01 | 2024-10-07 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
85 | 30/2 | DA-3 | Wet Paddy | 2024-10-01 | 2024-10-07 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
86 | 31/2 | DA+0 | Wet Paddy | 2024-10-03 | 2024-10-07 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
87 | 25/3 | DA+3 | Wet Paddy | 2024-10-04 | 2024-10-08 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
88 | 35/9 | DA+3 | Wet Paddy | 2024-10-04 | 2024-10-10 | 278.48 | 3.46 | 37.91 | Completed |  | A V I ENTERPRISE
89 | 39/5 | DA-3 | Wet Paddy | 2024-10-04 | 2024-10-08 | 248.14 | 3.06 | 34.58 | Completed |  | Dharamdas Contractor
90 | 34/6 | DA+0 | Wet Paddy | 2024-10-04 | 2024-10-08 | 248.14 | 3.06 | 34.58 | Completed |  | Aneshwar Traders
91 | 34/3 | DA+3 | Wet Paddy | 2024-10-04 | 2024-10-10 | 278.48 | 3.46 | 37.91 | Completed |  | Maa Durga
92 | 34/4 | DA-3 | Wet Paddy | 2024-10-04 | 2024-10-10 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
93 | 31/1 | DA+0 | Wet Paddy | 2024-10-08 | 2024-10-10 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
94 | 34/2 | DA+3 | Wet Paddy | 2024-10-08 | 2024-10-13 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
95 | 12/5 | DA+3 | Wet Paddy | 2024-10-10 | 2024-10-13 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
96 | 4/2 | DA-3 | Wet Paddy | 2024-10-10 | 2024-10-14 | 248.14 | 3.06 | 34.58 | Completed |  | VED ENTTERPRISE
97 | 31/8 | DA-3 | Wet Paddy | 2024-10-10 | 2024-10-14 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
98 | 30/1 | DA-3 | Wet Paddy | 2024-10-10 | 2024-10-14 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
99 | 30/5 | DA+0 | Wet Paddy | 2024-10-10 | 2024-10-16 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
100 | 20/2 | DA+0 | Wet Paddy | 2024-10-12 | 2024-10-21 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
101 | 36/2 | DA+0 | Wet Paddy | 2024-10-12 | 2024-10-16 | 248.14 | 3.06 | 34.58 | Completed |  | SAIFI CON.
102 | 35/8 | DA-3 | Wet Paddy | 2024-10-12 | 2024-10-21 | 248.14 | 3.06 | 34.58 | Completed |  | A V I ENTERPRISE
103 | 52/9 | DA-3 | WET | 2024-10-13 | 2024-10-22 | 415.84 | 5.3 | 53.21 | Completed |  | Dharamdas Contractor
104 | 14/2 | DA+0 | Wet Paddy | 2024-10-13 | 2024-10-20 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
105 | 33/11 | DA+3 | Wet Paddy | 2024-10-13 | 2024-10-18 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
106 | 33/1 | DA-3 | Wet Paddy | 2024-10-13 | 2024-10-16 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
107 | 34/1 | DA+3 | Wet Paddy | 2024-10-13 | 2024-10-21 | 278.48 | 3.46 | 37.91 | Completed |  | Maa Durga
108 | 31/10 | DA-3 | Wet Paddy | 2024-10-13 | 2024-10-18 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
109 | 31/3 | DA+3 | Wet Paddy | 2024-10-16 | 2024-10-20 | 278.48 | 3.46 | 37.91 | Completed |  | Laxmi Const.
110 | 33/2 | DA-3 | Wet Paddy | 2024-10-16 | 2024-10-20 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
111 | 4/3 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-23 | 278.48 | 3.46 | 37.91 | Completed |  | VED ENTTERPRISE
112 | 8B/3 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-26 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
113 | 28/1 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-24 | 278.48 | 3.46 | 37.91 | Completed |  | J M Enterprise
114 | 31/9 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-24 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
115 | 33/5 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-24 | 278.48 | 3.46 | 37.91 | Completed |  | Vinayak Enterprise
116 | 33/10 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-23 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
117 | 36/1 | DA+3 | Wet Paddy | 2024-10-17 | 2024-10-24 | 278.48 | 3.46 | 37.91 | Completed |  | SAIFI CON.
118 | 7/10 | DA+3 | Wet Paddy | 2024-10-19 | 2024-10-25 | 278.48 | 3.46 | 37.91 | Completed |  | Vivan Enterprise
119 | 14/1 | DA+0 | Wet Paddy | 2024-10-21 | 2024-10-24 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
120 | 31/5 | DA-3 | Wet Paddy | 2024-10-22 | 2024-10-25 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
121 | 33/3 | DA+3 | Wet Paddy | 2024-10-22 | 2024-10-26 | 278.48 | 3.46 | 37.91 | Completed |  | M A Construction
122 | 33/9 | DA+0 | Wet Paddy | 2024-10-24 | 2024-10-26 | 248.14 | 3.06 | 34.58 | Completed |  | Aneshwar Traders
123 | 35/7 | DA+3 | Wet Paddy | 2024-10-24 | 2024-10-26 | 278.48 | 3.46 | 37.91 | Completed |  | A V I ENTERPRISE
124 | 4/4 | DA+0 | Wet Paddy | 2024-10-24 | 2024-10-27 | 248.14 | 3.06 | 34.58 | Completed |  | VED ENTTERPRISE
125 | 7/11 | DA+0 | Wet Paddy | 2024-10-24 | 2024-10-27 | 248.14 | 3.06 | 34.58 | Completed |  | Vivan Enterprise
126 | 14/8 | DA+3 | Wet Paddy | 2024-10-24 | 2024-11-01 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering
127 | 31/6 | DA+3 | Wet Paddy | 2024-10-24 | 2024-11-01 | 278.48 | 3.46 | 37.91 | Completed |  | Laxmi Const.
128 | 31/7 | DA+0 | Wet Paddy | 2024-10-24 | 2024-11-01 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
129 | 52/10 | DA+3 | WET | 2024-10-24 | 2024-11-01 | 435.91 | 5.58 | 55.48 | Completed |  | Dharamdas Contractor
130 | 20/4 | DA-3 | Wet Paddy | 2024-10-24 | 2024-11-01 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
131 | 35/4 | DA+0 | Wet Paddy | 2024-10-25 | 2024-11-10 | 248.14 | 3.06 | 34.58 | Completed |  | Maa Durga
132 | 33/4 | DA-3 | Wet Paddy | 2024-10-25 | 2024-11-02 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
133 | 35/5 | DA+3 | Wet Paddy | 2024-10-25 | 2024-11-02 | 278.48 | 3.46 | 37.91 | Completed |  | A V I ENTERPRISE
134 | 8B/1 | DA-3 | Wet Paddy | 2024-11-03 | 2024-11-05 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
135 | 20/0 | DB1+0 | Wet Paddy | 2024-11-03 | 2024-11-13 | 362.71 | 4.59 | 53.66 | Completed |  | J M Enterprise
136 | 7/9 | DA+0 | Wet Paddy | 2024-11-03 | 2024-11-11 | 248.14 | 3.06 | 34.58 | Completed |  | Vivan Enterprise
137 | 20/3 | DA+0 | Wet Paddy | 2024-11-03 | 2024-11-13 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
138 | 31/4 | DA-3 | Wet Paddy | 2024-11-03 | 2024-11-09 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
139 | 8B/2 | DA-3 | Wet Paddy | 2024-11-03 | 2024-11-13 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
140 | 33/8 | DA+3 | Wet Paddy | 2024-11-03 | 2024-11-11 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
141 | 33/6 | DA+3 | Wet Paddy | 2024-11-03 | 2024-11-08 | 278.48 | 3.46 | 37.91 | Completed |  | Vinayak Enterprise
142 | 34/0 | DB1+0 | Wet Paddy | 2024-11-03 | 2024-11-09 | 362.71 | 4.59 | 53.66 | Completed |  | M A Construction
143 | 19/7 | DA+3 | Wet Paddy | 2024-11-06 | 2024-11-13 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
144 | 17/2 | DA+0 | Wet Paddy | 2024-11-06 | 2024-11-10 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
145 | 19/4 | DA+0 | Wet Paddy | 2024-11-06 | 2024-11-11 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
146 | 7/8 | DA+3 | Wet Paddy | 2024-11-06 | 2024-11-15 | 278.48 | 3.46 | 37.91 | Completed |  | Vivan Enterprise
147 | 33/7 | DA+3 | Wet Paddy | 2024-11-06 | 2024-11-15 | 278.48 | 3.46 | 37.91 | Completed |  | Aneshwar Traders
148 | 32/0 | DC1+6 | Wet Paddy | 2024-11-08 | 2024-11-16 | 404.6 | 5.16 | 65.88 | Completed |  | Laxmi Const.
149 | 10/1 | DA-3 | Wet Paddy | 2024-11-09 | 2024-11-18 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering
150 | 19/5 | DA-3 | Wet Paddy | 2024-11-10 | 2024-11-18 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
151 | 39/3 | DA+3 | PS | 2024-11-12 | 2024-11-20 | 517.53 | 6.68 | 64.75 | Completed |  | M A Construction
152 | 8B/4 | DA+6 | Wet Paddy | 2024-11-14 | 2024-11-21 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
153 | 4/8 | DA+0 | Wet Paddy | 2024-11-14 | 2024-11-21 | 248.14 | 3.06 | 34.58 | Completed |  | R K Constrcution
154 | 33/0 | DC2+6 | Wet Paddy | 2024-11-14 | 2024-11-21 | 456.35 | 5.87 | 71.94 | Completed |  | Aneshwar Traders
155 | 19/6 | DA+0 | Wet Paddy | 2024-11-18 | 2024-11-21 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
156 | 36/4 | DA+0 | Wet Paddy | 2024-11-18 | 2024-11-21 | 248.14 | 3.06 | 34.58 | Completed |  | Maa Durga
157 | 54/1 | DA+9 | PS | 2024-11-16 | 2024-11-23 | 517.53 | 6.68 | 64.75 | Completed |  | Dharamdas Contractor
158 | 21/0 | DB1+0 | Wet Paddy | 2024-11-18 | 2024-11-22 | 362.71 | 4.59 | 53.66 | Completed |  | J M Enterprise
159 | 8/3 | DA-3 | Wet Paddy | 2024-11-18 | 2024-11-22 | 248.14 | 3.06 | 34.58 | Completed |  | A V I ENTERPRISE
160 | 20/11 | DA-3 | Wet Paddy | 2024-11-18 | 2024-11-24 | 248.14 | 3.06 | 34.58 | Completed |  | K R Associates
161 | 38/6 | DA+3 | PS | 2024-11-20 | 2024-11-29 | 517.53 | 6.68 | 64.75 | Completed |  | Vinayak Enterprise
162 | 39/2 | DA-3 | Wet Paddy | 2024-11-22 | 2024-11-26 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
163 | 35/0 | DC1+0 | Wet Paddy | 2024-11-22 | 2024-11-29 | 398.56 | 5.08 | 65.17 | Completed |  | Aneshwar Traders
164 | 36/0 | DB2+0 | Wet Paddy | 2024-11-22 | 2024-11-27 | 372.59 | 4.724 | 60.99 | Completed |  | SAIFI CON.
165 | 8/4 | DA+9 | Wet Paddy | 2024-11-22 | 2024-11-27 | 278.48 | 3.46 | 37.91 | Completed |  | A V I ENTERPRISE
166 | 4/7 | DA+3 | Wet Paddy | 2024-11-22 | 2024-11-29 | 278.48 | 3.46 | 37.91 | Completed |  | R K Constrcution
167 | 8B/5 | DA+6 | Wet Paddy | 2024-11-22 | 2024-11-29 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
168 | 7/3 | DA-3 | Wet Paddy | 2024-11-22 | 2024-11-26 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
169 | 7/2 | DA+3 | Wet Paddy | 2024-11-22 | 2024-11-29 | 278.48 | 3.46 | 37.91 | Completed |  | Laxmi Const.
170 | 10/0 | DB1+9 | Wet Paddy | 2024-11-22 | 2024-11-30 | 362.71 | 4.59 | 53.66 | Completed |  | SSR engineering
171 | 31/0 | DB2+0 | Wet Paddy | 2024-11-22 | 2024-11-29 | 372.59 | 4.724 | 60.99 | Completed |  | VH Rajpoot cont.
172 | 54/2 | DA-3 | PS | 2024-11-20 | 2024-12-01 | 497.3 | 6.41 | 62.44 | Completed |  | Dharamdas Contractor
173 | 39/0 | DB2+0 | Wet Paddy | 2024-11-22 | 2024-12-02 | 372.59 | 4.724 | 60.99 | Completed |  | M A Construction
174 | 8/2 | DA+0 | Wet Paddy | 2024-11-25 | 2024-12-03 | 248.14 | 3.06 | 34.58 | Completed |  | A V I ENTERPRISE
175 | 26/0 | DB2+9 | Wet Paddy | 2024-11-29 | 2024-12-04 | 374.03 | 4.742 | 61.17 | Completed |  | VH Rajpoot cont.
176 | 7/1 | DA+0 | Wet Paddy | 2024-11-30 | 2024-12-04 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
177 | 4/5 | DA+3 | Wet Paddy | 2024-11-30 | 2024-12-06 | 278.48 | 3.46 | 37.91 | Completed |  | R K Constrcution
178 | 5/1 | DA+3 | Wet Paddy | 2024-12-03 | 2024-12-09 | 278.48 | 3.46 | 37.91 | Completed |  | J M Enterprise
179 | 7/4 | DA+0 | Wet Paddy | 2024-12-03 | 2024-12-09 | 248.14 | 3.06 | 34.58 | Completed |  | Laxmi Const.
180 | 7/7 | DA+0 | Wet Paddy | 2024-12-03 | 2024-12-09 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
181 | 8/1 | DA+3 | Wet Paddy | 2024-12-03 | 2024-12-09 | 278.48 | 3.46 | 37.91 | Completed |  | A V I ENTERPRISE
182 | 17/0 | DB2+6 | Wet Paddy | 2024-12-03 | 2024-12-09 | 374.03 | 4.742 | 61.17 | Completed |  | SSR engineering
183 | 3/0 | DC2+0 | Wet Paddy | 2024-12-04 | 2024-12-10 | 450.69 | 5.79 | 71.28 | Completed |  | VH Rajpoot cont.
184 | 56/5 | DA-3 | WET | 2024-12-04 | 2024-12-10 | 415.84 | 5.3 | 53.21 | Completed |  | Aneshwar Traders
185 | 38/10 | DA-3 | WET | 2024-12-01 | 2024-12-11 | 415.84 | 5.3 | 53.21 | Completed |  | Maa Durga
186 | 55/1 | DA-3 | WET | 2024-12-02 | 2024-12-11 | 415.84 | 5.3 | 53.21 | Completed |  | Dharamdas Contractor
187 | 7/5 | DA+3 | Wet Paddy | 2024-12-09 | 2024-12-13 | 278.48 | 3.46 | 37.91 | Completed |  | Laxmi Const.
188 | 49/0 | DC2+9 | WET | 2024-12-09 | 2024-12-15 | 727.51 | 9.56 | 103.7 | Completed |  | M A Construction
189 | 4/9 | DA-3 | Wet Paddy | 2024-12-09 | 2024-12-16 | 248.14 | 3.06 | 34.58 | Completed |  | R K Constrcution
190 | 7/6 | DA+0 | Wet Paddy | 2024-12-09 | 2024-12-16 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction
191 | 6/1 | DA+3 | Wet Paddy | 2024-12-09 | 2024-12-16 | 278.48 | 3.46 | 37.91 | Completed |  | J M Enterprise
192 | 4/0 | DD45+0 | Wet Paddy | 2024-12-09 | 2024-12-17 | 524.99 | 6.8 | 87.75 | Completed |  | VH Rajpoot cont.
193 | 56/8 | DA-3 | PS | 2024-12-09 | 2024-12-17 | 497.3 | 6.41 | 62.44 | Completed |  | Aneshwar Traders
194 | 38/7 | DA-3 | PS | 2024-12-09 | 2024-12-17 | 497.3 | 6.41 | 62.44 | Completed |  | Vinayak Enterprise
195 | 52/7 | DA+6 | PS | 2024-12-09 | 2024-12-18 | 517.53 | 6.68 | 64.75 | Completed |  | SAIFI CON.
196 | 7/0 | DB2+0 | Wet Paddy | 2024-12-10 | 2024-12-20 | 372.59 | 4.724 | 60.99 | Completed |  | Laxmi Const.
197 | 8/0 | DB2+0 | Wet Paddy | 2024-12-10 | 2024-12-20 | 372.59 | 4.724 | 60.99 | Completed |  | A V I ENTERPRISE
198 | 48/1 | DA-3 | Wet Paddy | 2024-12-15 | 2024-12-20 | 248.14 | 3.06 | 34.58 | Completed |  | M A Construction
199 | 47/0 | DC2+9 | Wet Paddy | 2024-12-10 | 2024-12-21 | 456.35 | 5.87 | 71.94 | Completed |  | Maa Durga
200 | 56/1 | DA+0 | WET | 2024-12-10 | 2024-12-22 | 415.84 | 5.3 | 53.21 | Completed |  | Dharamdas Contractor
201 | 9/0 | DB2+6 | Wet Paddy | 2024-12-10 | 2024-12-24 | 374.03 | 4.742 | 61.17 | Completed |  | VH Rajpoot cont.
202 | 4/10 | DA+3 | Wet Paddy | 2024-12-17 | 2024-12-24 | 278.48 | 3.46 | 37.91 | Completed |  | R K Constrcution
203 | 52/8 | DA-3 | Wet Paddy | 2024-12-19 | 2024-12-27 | 248.14 | 3.06 | 34.58 | Completed |  | SAIFI CON.
204 | 6/0 | DB1+0 | Wet Paddy | 2024-12-20 | 2024-12-27 | 362.71 | 4.59 | 53.66 | Completed |  | J M Enterprise
205 | 56/7 | DA+6 | PS | 2024-11-20 | 2024-12-27 | 517.53 | 6.68 | 64.75 | Completed |  | Aneshwar Traders
206 | 46/0 | DB2+0 | Wet Paddy | 2024-12-18 | 2024-12-28 | 372.59 | 4.724 | 60.99 | Completed |  | Vinayak Enterprise
207 | 4/6 | DA+0 | Wet Paddy | 2024-12-23 | 2024-12-31 | 248.14 | 3.06 | 34.58 | Completed |  | R K Constrcution
208 | 54/0 | DB1+3 | WET | 2024-12-23 | 2024-12-31 | 587.87 | 7.64 | 74.87 | Completed |  | Dharamdas Contractor
209 | 53A/5 | DA-3 | WET | 2024-11-24 | 2025-01-02 | 415.84 | 5.3 | 53.21 | Completed |  | A K Rajpoot
210 | 64/1 | DA+0 | WET | 2024-11-24 | 2025-01-02 | 415.84 | 5.3 | 53.21 | Completed |  | M A Construction
211 | 15/0 | DC2+3 | Wet Paddy | 2024-12-17 | 2025-01-03 | 456.35 | 5.87 | 71.94 | Completed |  | SSR engineering
212 | 38/9 | DA-3 | WET | 2024-11-24 | 2025-01-03 | 415.84 | 5.3 | 53.21 | Completed |  | Maa Durga
213 | 8A/0 | DD60+0 | Wet Paddy | 2024-11-20 | 2025-01-09 | 882.61 | 11.67 | 158.04 | Completed |  | Garg Construction
214 | 5/0 | DB1+0 | Wet Paddy | 2024-12-29 | 2025-01-09 | 362.71 | 4.59 | 53.66 | Completed |  | J M Enterprise | 14
215 | 53A/0 | DB2+0 | WET | 2025-01-03 | 2025-01-10 | 602.2 | 7.84 | 86.63 | Completed |  | Laxmi Const. | 15
216 | 53A/4 | DA+3 | WET | 2025-01-03 | 2025-01-11 | 435.91 | 5.58 | 55.48 | Completed |  | A K Rajpoot | 15
217 | 56/0 | DD45+0 | WET | 2025-01-03 | 2025-01-11 | 825.01 | 10.9 | 128.13 | Completed |  | Aneshwar Traders | 15
218 | 64/2 | DA+3 | PS | 2025-01-03 | 2025-01-11 | 517.53 | 6.68 | 64.75 | Completed |  | M A Construction | 12
219 | 52/0 | DC2+9 | Wet Paddy | 2025-01-03 | 2025-01-11 | 456.35 | 5.87 | 71.94 | Completed |  | Vinayak Enterprise | 15
220 | 48/0 | DD45+9 | Wet Paddy | 2025-01-04 | 2025-01-12 | 524.99 | 6.8 | 87.75 | Completed |  | Maa Durga | 12
221 | 28/0 | DD60+0 | FS | 2024-12-28 | 2025-01-12 | 1743.64 | 23.59 | 303.03 | Completed |  | VH Rajpoot cont. | 15
222 | 8B/0 | DD60+0 | Wet Paddy | 2024-12-26 | 2025-01-14 | 882.61 | 11.67 | 158.04 | Completed |  | A V I ENTERPRISE | 15
223 | 19/10 | DA+3 | Wet Paddy | 2025-01-10 | 2025-01-14 | 278.48 | 3.46 | 37.91 | Completed |  | SSR engineering | 15
224 | 53/0 | DC1+0 | WET | 2025-01-03 | 2025-01-15 | 616.36 | 8.03 | 90.53 | Completed |  | SAIFI CON. | 15
225 | 53A/2 | DA+3 | WET | 2025-01-10 | 2025-01-18 | 435.91 | 5.58 | 55.48 | Completed |  | Laxmi Const. | 12
226 | 52/3 | DA-3 | Wet Paddy | 2025-01-12 | 2025-01-20 | 248.14 | 3.06 | 34.58 | Completed |  | Vinayak Enterprise | 18
227 | 20/10 | DA+3 | Wet Paddy | 2025-01-10 | 2025-01-20 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction | 15
228 | 55/0 | DC1+0 | PS | 2025-01-04 | 2025-01-22 | 711.8 | 9.34 | 101.83 | Completed |  | Dharamdas Contractor | 15
229 | 53A/6 | DA+3 | WET | 2025-01-12 | 2025-01-23 | 435.91 | 5.58 | 55.48 | Completed |  | A K Rajpoot | 12
230 | 51/0 | DD60+0 | Wet paddy | 2025-01-12 | 2025-01-24 | 882.61 | 11.67 | 158.04 | Completed |  | M A Construction | 12
231 | 53A/3 | DA-3 | WET | 2025-01-18 | 2025-01-25 | 415.84 | 5.3 | 53.21 | Completed |  | Laxmi Const. | 10
232 | 27/0 | DD60+3 | FS | 2025-01-14 | 2025-01-29 | 1771.88 | 23.98 | 307.84 | Completed |  | VH Rajpoot cont. | 15
233 | 45/1 | DA+3 | Wet Paddy | 2025-01-21 | 2025-01-30 | 278.48 | 3.46 | 37.91 | Completed |  | Maa Durga | 12
234 | 21/3 | DA+3 | Wet Paddy | 2025-01-25 | 2025-01-31 | 278.48 | 3.46 | 37.91 | Completed |  | A K Rajpoot | 12
235 | 52/6 | DA+3 | WET | 2025-01-21 | 2025-01-31 | 435.91 | 5.58 | 55.48 | Completed |  | SAIFI CON. | 13
236 | 57/0 | DB2+0 | PS | 2025-01-15 | 2025-01-31 | 785.905 | 10.345 | 109.29 | Completed |  | Aneshwar Traders | 18
237 | 0/2 | DA-3 | Wet Paddy | 2025-01-23 | 2025-01-31 | 248.14 | 3.06 | 34.58 | Completed |  | SSR engineering | 12
238 | 0/3 | DA-3 | Wet Paddy | 2025-01-24 | 2025-01-31 | 248.14 | 3.06 | 34.58 | Completed |  | Garg Construction | 15
239 | 53/1 | DA+6 | WET | 2025-01-26 | 2025-02-03 | 435.91 | 5.58 | 55.48 | Completed |  | Laxmi Const. | 15
240 | 24/0 | DD60+25 | Wet Paddy | 2025-01-18 | 2025-02-04 | 858.32 | 11.34 | 154.02 | Completed |  | A V I ENTERPRISE | 10
241 | 42/0 | DD60+18 | Wet Paddy | 2025-01-23 | 2025-02-05 | 858.32 | 11.34 | 154.02 | Completed |  | Dharamdas Contractor | 14
242 | 35/6 | DA+0 | Wet Paddy | 2025-02-01 | 2025-02-06 | 248.14 | 3.06 | 34.58 | Completed |  | Maa Durga | 12
243 | 22/0 | DB2+3 | Wet Paddy | 2025-02-01 | 2025-02-07 | 374.03 | 4.742 | 61.17 | Completed |  | A K Rajpoot | 12
244 | 56/2 | DA+3 | WET | 2025-02-01 | 2025-02-07 | 435.91 | 5.58 | 55.48 | Completed |  | R K Constrcution | 18
245 | 0/4 | DA+9 | Wet Paddy | 2025-02-01 | 2025-02-09 | 278.48 | 3.46 | 37.91 | Completed |  | Garg Construction
246 | 29/0 | DD60+25 | Wet Paddy | 2025-01-30 | 2025-02-09 | 858.32 | 11.34 | 154.02 | Completed |  | VH Rajpoot cont.
247 | 52/4 | DA-3 | WET | 2025-02-01 | 2025-02-10 | 415.84 | 5.3 | 53.21 | Completed |  | Vinayak Enterprise
248 | 52/5 | DA-3 | WET | 2025-02-02 | 2025-02-15 | 415.84 | 5.3 | 53.21 | Completed |  | SAIFI CON.
249 | 40/0 | DD60+25 2mtr RC | Wet Paddy | 2025-02-02 | 2025-02-15 | 858.32 | 11.34 | 162.452 | Completed |  | Aneshwar Traders
250 | 59/0 | DD60+6 | WET | 2025-02-02 | 2025-02-15 | 1344.56 | 18.05 | 235.32 | Completed |  | M A Construction
251 | 0/1 | DA-3 | WET | 2025-02-02 | 2025-02-15 | 415.84 | 5.3 | 53.21 | Completed |  | SSR engineering
252 | 22A/0 | DB1+25 | Wet Paddy | 2025-02-09 | 2025-02-17 | 338.89 | 4.27 | 55.28 | Completed |  | A K Rajpoot
253 | 25/0 | DD60+25 | Wet Paddy | 2025-02-06 | 2025-02-18 | 858.32 | 11.34 | 154.02 | Completed |  | A V I ENTERPRISE
254 | 64/0 | DC1+0 | WET | 2025-02-06 | 2025-02-18 | 616.36 | 8.03 | 90.53 | Completed |  | Laxmi Const.
255 | 53A/7 | DA+0 | Wet Paddy | 2025-02-10 | 2025-02-20 | 248.14 | 3.06 | 34.58 | Completed |  | Maa Durga
256 | 30/0 | DD60+18 | Wet Paddy | 2025-02-10 | 2025-02-21 | 858.32 | 11.34 | 154.02 | Completed |  | VH Rajpoot cont.
257 | 52/2 | DA+3 | WET | 2025-02-11 | 2025-02-21 | 435.91 | 5.58 | 55.48 | Completed |  | Vinayak Enterprise
258 | 43/0 | DD60+9,2mtr RC | Wet Paddy | 2025-02-06 | 2025-02-21 | 898.24 | 11.892 | 165.36 | Completed |  | Dharamdas Contractor
259 | 4/1 | DA+3 Normal leg A,B | Wet Paddy | 2025-02-10 | 2025-02-22 | 139.24 | 1.73 | 18.955 | Completed |  | Garg Construction
| 4/1 | DA+3, 2mtr RC(C,D) | Wet Paddy | 2025-02-10 | 2025-02-22 | 155.95 | 1.955 | 25.21 | Completed |  | Garg Construction
260 | 56/3 | DA-3 | WET | 2025-02-10 | 2025-02-23 | 415.84 | 5.3 | 53.21 | Completed |  | R K Constrcution
261 | 41/0 | DD60+18,2mtr RC | Wet Paddy | 2025-02-16 | 2025-02-25 | 858.32 | 11.34 | 162.452 | Completed |  | Aneshwar Traders
262 | 63/0 | DC1+3 | WET | 2025-02-19 | 2025-02-27 | 630.02 | 8.22 | 92.15 | Completed |  | Laxmi Const.
263 | 11/0 | DB1+18 | Wet Paddy | 2025-02-19 | 2025-02-28 | 338.89 | 4.27 | 55.28 | Completed |  | SSR engineering
264 | 58/0 | DD60+18 | WET | 2025-02-19 | 2025-02-28 | 1290.24 | 17.3 | 226.16 | Completed |  | M A Construction
265 | 53A/1 | DA+6 | WET | 2025-02-20 | 2025-02-28 | 435.91 | 5.58 | 55.48 | Completed |  | SAIFI CON.
266 | 21/2 | DA+3 | Wet Paddy | 2025-02-26 | 2025-02-28 | 278.48 | 3.46 | 37.91 | Completed |  | VH Rajpoot cont.
267 | 13/0 | DD60+30 | Wet Paddy | 2025-02-26 | 2025-03-03 | 858.32 | 11.34 | 154.02 | Completed |  | A K Rajpoot
268 | 50/0 | DC1+18 | Wet Paddy | 2025-02-26 | 2025-03-04 | 517.53 | 6.68 | 83.76 | Completed |  | Maa Durga
269 | 23/0 | DC2+18 | Wet Paddy | 2025-03-01 | 2025-03-08 | 586.05 | 7.61 | 92.58 | Completed |  | VH Rajpoot cont.
270 | 60/0 | DD45+6 | WET | 2025-02-27 | 2025-03-08 | 813.35 | 11.15 | 130.6 | Completed |  | Laxmi Const.
271 | 14/0 | DD60+30 | Wet Paddy | 2025-03-04 | 2025-03-09 | 858.32 | 11.34 | 154.02 | Completed |  | A K Rajpoot
272 | 34/5 | DA+0 | Wet Paddy | 2025-03-04 | 2025-03-09 | 248.14 | 3.06 | 34.58 | Completed |  | Maa Durga
273 | 12/0 | DB2+18 | Wet Paddy | 2025-03-01 | 2025-03-10 | 409.75 | 5.22 | 62.89 | Completed |  | Garg Construction
274 | 56/4 | DA-3 | WET | 2025-03-01 | 2025-03-11 | 415.84 | 5.3 | 53.21 | Completed |  | R K Constrcution
275 | 61/0 | DD60+30 | WET | 2025-03-01 | 2025-03-20 | 1290.24 | 17.3 | 225.16 | Completed |  | M A Construction
276 | 67/0 | DD60+30 | WET | 2025-03-01 | 2025-03-20 | 1290.24 | 17.3 | 225.16 | Completed |  | Aneshwar Traders
277 | 52/1 | DB1+6 | WET | 2025-03-01 | 2025-03-22 | 587.87 | 7.64 | 74.87 | Completed |  | Vinayak Enterprise
278 | 18/0 | DB1+6 | Wet Paddy | 2025-03-20 | 2025-03-25 | 362.71 | 4.59 | 53.66 | Completed |  | A K Rajpoot
279 | 64/3 | DA-3 | WET | 2025-03-20 | 2025-03-26 | 415.84 | 5.3 | 53.21 | Completed |  | Laxmi Const.
280 | 66/1 | DA+0 | WET | 2025-03-20 | 2025-03-26 | 415.84 | 5.3 | 53.21 | Completed |  | SAIFI CON.
281 | 62/0 | DC1+25 | WET | 2025-03-20 | 2025-03-27 | 808.64 | 10.66 | 121.57 | Completed |  | M A Construction
282 | 19/0 | DC2+6 | Wet Paddy | 2025-03-25 | 2025-03-30 | 456.35 | 5.87 | 71.94 | Completed |  | A K Rajpoot
283 | 57/1 | DA-3 | WET | 2025-03-25 | 2025-04-02 | 415.84 | 5.3 | 53.21 | Completed |  | Maa Durga
284 | 56/6 | DA+0 | WET | 2025-03-25 | 2025-04-02 | 415.84 | 5.3 | 53.21 | Completed |  | R K Constrcution
285 | 21/1 | DA-3 | Wet Paddy | 2025-03-31 | 2025-04-03 | 248.14 | 3.06 | 34.58 | Completed |  | A K Rajpoot
286 | 66/0 A,B | DD60+0 | FS | 2025-03-25 | 2025-04-10 | 871.82 | 11.795 | 151.515 | Completed |  | Dharamdas Contractor
| 66/0 C,D | DD60+0, 1mtr RC | FS | 2025-03-25 | 2025-04-10 | 871.82 | 11.795 | 152.7 | Completed |  | Dharamdas Contractor
287 | 16/0 | DB2+25 | Wet Paddy | 2025-04-04 | 2025-04-10 | 409.75 | 5.22 | 62.89 | Completed |  | A K Rajpoot
288 | 68/0 | DD60+30 | WET | 2025-04-04 | 2025-04-17 | 1290.24 | 17.3 | 225.16 | Completed |  | Aneshwar Traders
289 | 2/1 | DA+3 | WET | 2025-04-17 | 2025-04-21 | 435.91 | 5.58 | 55.48 | Completed |  | VH Rajpoot cont.
290 | 44/0 | DD60+3 | FS | 2025-04-04 | 2025-04-21 | 1771.88 | 23.98 | 307.84 | Completed |  | Laxmi Const.
291 | 1/0 | DC1+3 | Wet Paddy | 2025-04-22 | 2025-04-27 | 404.6 | 5.16 | 65.88 | Completed |  | VH Rajpoot cont.
292 | 65/0 | DD60+0 | FS | 2025-04-11 | 2025-04-28 | 1743.64 | 23.59 | 303.03 | Completed |  | Dharamdas Contractor
293 | 2/0 | DD45+3 | Wet Paddy | 2025-04-22 | 2025-04-29 | 524.99 | 6.8 | 87.75 | Completed |  | A V I ENTERPRISE
294 | 70/0 | DD60+0 | WET | 2025-04-17 | 2025-04-30 | 1322.7 | 17.75 | 231.63 | Completed |  | SAIFI CON.
295 | 2/2 | DA+0 | Wet Paddy | 2025-04-27 | 2025-04-30 | 248.14 | 3.06 | 34.58 | Completed |  | VH Rajpoot cont.
296 | 45/0 | DD60+0 | FS | 2025-04-25 | 2025-05-11 | 1743.64 | 23.59 | 303.03 | Completed |  | Laxmi Const.
297 | 38/5 | DA+3 | WET | 2025-05-05 | 2025-05-11 | 435.91 | 5.58 | 55.48 | Completed |  | VH Rajpoot cont.
298 | 0/0 | DCT+0 | WET | 2025-05-10 | 2025-05-17 | 884.84 | 11.7 | 106.84 | Completed |  | A V I ENTERPRISE | 10
299 | 69/0 | DC2+0 | WET | 2025-05-11 | 2025-05-18 | 703.07 | 9.23 | 100.8 | Completed |  | SAIFI CON. | 12
300 | 37/0 | DC2+18 | FS | 414684 | 2025-05-22 | 2024.072 | 19.052 | 242.144 | Completed |  | VH Rajpoot cont. | 20
301 | 38/0 | DC2+18 | FS | 2025-05-24 |  |  |  |  | Completed |  | A V I ENTERPRISE | 10
302 | 69A/0 | DD60+0 | WET | 2025-05-20 | 2025-06-03 | 1322.7 | 17.75 | 231.63 | Completed |  | Aneshwar Traders | 13
285
TOWER ERECTION
SL No. | Location No. | Tower Type | Tower Weight | Starting Date | Completion Date | Work status | Gang Name | Gang strength | Gang type(Subcontractor/Company) |  | Tac welding | Remark
1 | 2/8 | DA+0 | 43.7758 | 2024-09-01 | 2024-09-16 | Completed | Dewi Construction
2 | 2/4 | DA+0 | 43.7758 | 2024-09-16 | 2024-09-29 | Completed | Dewi Construction(Girendra)
3 | 39/10 | DA+0 | 43.7758 | 2024-09-16 | 2024-10-01 | Completed | Horil Mahto
4 | 20/8 | DA+0 | 43.7758 | 2024-10-01 | 2024-10-07 | Completed | Dewi Construction(Girendra)
5 | 39/8 | DA+0 | 43.7758 | 2024-10-03 | 2024-10-15 | Completed | Horil Mahto
6 | 20/6 | DA+0 | 43.7758 | 2024-10-08 | 2024-10-13 | Completed | Dewi Construction(Girendra)
7 | 20/9 | DA+3 | 46.0492 | 2024-10-14 | 2024-10-19 | Completed | Dewi Construction(Girendra)
8 | 39/7 | DA+3 | 46.0492 | 2024-10-15 | 2024-10-24 | Completed | Horil Mahto
9 | 20/5 | DA+3 | 46.0492 | 2024-10-20 | 2024-10-24 | Completed | Dewi Construction(Girendra)
10 | 20/7 | DA-3 | 42.3742 | 2024-10-24 | 2024-10-29 | Completed | Dewi Construction(Girendra)
11 | 39/9 | DA+3 | 46.0492 | 2024-10-24 | 2024-10-31 | Completed | Horil Mahto
12 | 20/12 | DA-3 | 42.3742 | 2024-11-01 | 2024-11-04 | Completed | Dewi Construction(Girendra)
13 | 14/6 | DA+3 | 46.0492 | 2024-11-05 | 2024-11-10 | Completed | Dewi Construction(Girendra)
14 | 39/6 | DA+3 | 46.0492 | 2024-11-01 | 14.11.2024 | Completed | Horil Mahto
15 | 14/5 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-17 | Completed | Dewi Construction(Girendra)
16 | 14/4 | DA+3 | 46.0492 | 2024-11-17 | 2024-11-22 | Completed | Dewi Construction(Girendra)
17 | 2/5 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-24 | Completed | Pankaj
18 | 19/3 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-26 | Completed | Reeta Bharti
19 | 6/2 | DA+3 | 46.0492 | 2024-11-14 | 2026-11-25 | Completed | Pinky Dewi
20 | 38/3 | DA+3 | 46.0492 | 2024-11-10 | 2026-11-25 | Completed | Horil Mahto
21 | 14/8 | DA+3 | 46.0492 | 2024-11-22 | 2024-11-28 | Completed | Dewi Construction(Girendra)
22 | 41/1 | DA+0 | 43.7758 | 2024-11-10 | 2024-11-29 | Completed | Amar Singh
23 | 2/7 | DA+3 | 46.0492 | 2024-11-26 | 2024-12-03 | Completed | Pankaj
24 | 19/2 | DA+0 | 43.7758 | 2024-11-28 | 2024-12-05 | Completed | Reeta Bharti
25 | 14/7 | DA+0 | 43.7758 | 2024-11-29 | 2024-12-05 | Completed | Dewi Construction(Girendra)
26 | 4/3 | DA+3 | 46.0492 | 2024-11-28 | 2024-12-05 | Completed | Pinky Dewi
27 | 36/12 | DA+0 | 43.7758 | 2024-11-29 | 2024-12-06 | Completed | Horil Mahto
28 | 2/6 | DA+0 | 43.7758 | 2024-12-01 | 2024-12-09 | Completed | Pankaj
29 | 41/2 | DA+3 | 46.0492 | 2024-11-30 | 2024-12-10 | Completed | Amar Singh
30 | 14/3 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-12 | Completed | Dewi Construction(Girendra)
31 | 4/4 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-12 | Completed | Pinky Dewi
32 | 19/4 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-13 | Completed | Reeta Bharti
33 | 2/3 | DA+3 | 46.0492 | 2024-12-10 | 2024-12-16 | Completed | Pankaj
34 | 4/2 | DA-3 | 42.3742 | 2024-12-12 | 2024-12-16 | Completed | Pinky Dewi
35 | 14/2 | DA+0 | 43.7758 | 2024-12-12 | 2024-12-17 | Completed | Dewi Construction(Girendra)
36 | 38/2 | DA+3 | 46.0492 | 2024-12-06 | 2024-12-19 | Completed | Horil Mahto
37 | 45/3 | DA-3 | 42.3742 | 2024-12-10 | 2024-12-20 | Completed | Amar Singh
38 | 19/1 | DA+0 | 43.7758 | 2024-12-13 | 2024-12-21 | Completed | Reeta Bharti
39 | 4/8 | DA+0 | 43.7758 | 2024-12-17 | 2024-12-22 | Completed | Pinky Dewi
40 | 14/1 | DA+0 | 43.7758 | 2024-12-18 | 2024-12-23 | Completed | Dewi Construction(Girendra)
41 | 7/10 | DA+3 | 46.0492 | 2024-12-18 | 2024-12-23 | Completed | Pankaj
42 | 45/2 | DA+3 | 46.0492 | 2024-12-21 | 2024-12-27 | Completed | Amar Singh
43 | 19/5 | DA-3 | 42.3742 | 2024-12-22 | 2024-12-27 | Completed | Reeta Bharti
44 | 4/7 | DA+3 | 46.0492 | 2024-12-24 | 2024-12-27 | Completed | Pinky Dewi
45 | 7/9 | DA+0 | 43.7758 | 2024-12-24 | 2024-12-30 | Completed | Pankaj
46 | 38/4 | DA+3 | 46.0492 | 2024-12-20 | 2024-12-31 | Completed | Horil Mahto
47 | 17/1 | DA-3 | 42.3742 | 2024-12-24 | 2024-12-31 | Completed | Dewi Construction(Girendra)
48 | 31/3 | DA+3 | 46.0492 | 2024-12-24 | 2025-01-03 | Completed | ASC heights
49 | 4/5 | DA+3 | 46.0492 | 2024-12-28 | 2025-01-03 | Completed | Pinky Dewi
50 | 46/1 | DA+0 | 43.7758 | 2024-12-28 | 2025-01-04 | Completed | Amar Singh
51 | 7/2 | DA+3 | 46.0492 | 2024-12-31 | 2025-01-07 | Completed | Pankaj
52 | 19/6 | DA+0 | 43.7758 | 2024-12-28 | 2025-01-08 | Completed | Reeta Bharti
53 | 17/4 | DA+3 | 46.0492 | 2025-01-01 | 2025-01-10 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
54 | 31/4 | DA-3 | 42.3742 | 2025-01-04 | 2025-01-11 | Completed | ASC heights | 38 | Sub Contractor
55 | 12/2 | DA+3 | 46.0492 | 2025-01-03 | 2025-01-11 | Completed | Pinky Dewi | 42 | Sub Contractor
56 | 7/8 | DA+3 | 46.0492 | 2025-01-08 | 2025-01-15 | Completed | Pankaj | 23 | Sub Contractor
57 | 36/3 | DA+3 | 46.0492 | 2025-01-07 | 2025-01-15 | Completed | Amar Singh | 22 | Sub Contractor
58 | 38/1 | DA+3 | 46.0492 | 2025-01-07 | 2025-01-17 | Completed | Horil Mahto | 24 | Sub Contractor
59 | 19/7 | DA+3 | 46.0492 | 2025-01-09 | 2025-01-17 | Completed | Reeta Bharti | 25 | Sub Contractor
60 | 17/3 | DA+0 | 43.7758 | 2025-01-10 | 2025-01-17 | Completed | Dewi Construction | 40 | Sub Contractor
61 | 31/2 | DA+0 | 43.7758 | 2025-01-11 | 2025-01-19 | Completed | ASC heights | 38 | Sub Contractor
62 | 12/3 | DA+3 | 46.0492 | 2025-01-12 | 2025-01-21 | Completed | Pinky Dewi | 35 | Sub Contractor
63 | 7/7 | DA+0 | 43.7758 | 2025-01-16 | 2025-01-22 | Completed | Pankaj | 23 | Sub Contractor
64 | 17/2 | DA+0 | 43.7758 | 2025-01-18 | 2025-01-23 | Completed | Dewi Construction | 40 | Sub Contractor
65 | 36/5 | DA+0 | 43.7758 | 2025-01-16 | 2025-01-24 | Completed | Amar Singh | 24 | Sub Contractor
66 | 33/10 | DA+3 | 46.0492 | 2025-01-10 | 2025-01-31 | Completed | Rudra Construction | 22 | Sub Contractor
67 | 19/9 | DA+3 | 46.0492 | 2025-01-18 | 2025-01-27 | Completed | Reeta Bharti | 25 | Sub Contractor
68 | 35/1 | DA+3 | 46.0492 | 2025-01-18 | 2025-01-28 | Completed | Horil Mahto | 26 | Sub Contractor
69 | 31/6 | DA+3 | 46.0492 | 2025-10-20 | 2025-01-25 | Completed | ASC heights | 38 | Sub Contractor
70 | 12/4 | DA+3 | 46.0492 | 2025-01-22 | 2025-01-25 | Completed | Pinky Dewi | 35 | Sub Contractor
71 | 7/6 | DA+0 | 43.7758 | 2025-01-23 | 2025-01-30 | Completed | Pankaj | 23 | Sub Contractor
72 | 17/5 | DA+3 | 46.0492 | 2025-01-24 | 2025-01-29 | Completed | Dewi Construction | 40 | Sub Contractor
73 | 36/1 | DA+3 | 46.0492 | 2025-01-25 | 2025-01-30 | Completed | Amar Singh | 24 | Sub Contractor
74 | 31/1 | DA+0 | 43.7758 | 2025-01-26 | 2025-02-02 | Completed | ASC heights |  | Sub Contractor
75 | 12/5 | DA+3 | 46.0492 | 2025-01-26 | 2025-02-01 | Completed | Pinky Dewi |  | Sub Contractor
76 | 17/7 | DA+3 | 46.0492 | 2025-01-30 | 2025-02-05 | Completed | Dewi Construction |  | Sub Contractor
77 | 36/2 | DA+0 | 43.7758 | 2025-02-02 | 2025-02-07 | Completed | Amar Singh |  | Sub Contractor
78 | 20/0 | DB1+0 | 64.482 | 2025-01-28 | 2025-02-06 | Completed | Reeta Bharti |  | Sub Contractor
79 | 12/9 | DA+3 | 46.0492 | 2025-02-02 | 2025-02-08 | Completed | Pinky Dewi |  | Sub Contractor
80 | 31/7 | DA+0 | 43.7758 | 2025-02-03 | 2025-02-10 | Completed | ASC heights |  | Sub Contractor
81 | 35/0 | DC1+0 | 73.426 | 2025-01-29 | 2025-02-10 | Completed | Horil Mahto |  | Sub Contractor
82 | 7/5 | DA+3 | 46.0492 | 2025-01-31 | 2025-02-10 | Completed | Pankaj |  | Sub Contractor
83 | 33/11 | DA+3 | 46.0492 | 2025-02-02 |  | Completed | Rudra Construction |  | Sub Contractor
84 | 21/0 | DB+0 | 64.482 | 2025-02-06 |  | Completed | Dewi Construction |  | Sub Contractor
85 | 20/2 | DA+0 | 43.7758 | 2025-02-07 |  | Completed | Reeta Bharti |  | Sub Contractor
86 | 35/9 | DA+3 | 46.0492 | 2025-02-08 |  | Completed | Amar Singh |  | Sub Contractor
87 | 8/1 | DA+3 | 46.049 | 2025-02-09 | 2025-02-15 | Completed | Pinky Dewi |  | Sub Contractor
88 | 7/4 | DA+0 | 43.7758 | 2025-02-11 | 2025-02-18 | Completed | Pankaj |  | Sub Contractor
89 | 34/7 | DA+3 | 46.049 | 2025-02-11 | 20-20-2025 | Completed | Horil Mahto |  | Sub Contractor
90 | 31/9 | DA+3 | 46.049 | 2025-02-11 | 20-20-2025 | Completed | ASC heights |  | Sub Contractor
91 | 35/7 | DA+3 | 46.049 | 2025-02-16 | 2025-02-21 | Completed | Amar Singh |  | Sub Contractor
92 | 20/3 | DA+0 | 43.7758 | 2025-02-12 | 2025-02-19 | Completed | Reeta Bharti |  | Sub Contractor
93 | 8/2 | DA+0 | 43.7758 | 2025-02-16 | 2025-02-21 | Completed | Pinky Dewi |  | Sub Contractor
94 | 33/6 | DA+3 | 46.049 | 2025-02-14 | 2025-02-20 | Completed | Dewi Construction |  | Sub Contractor
95 | 33/9 | DA+0 | 43.7758 | 2025-02-14 | 2025-02-23 | Completed | Rudra Construction |  | Sub Contractor
96 | 20/4 | DA-3 | 42.375 | 2025-02-20 | 2025-02-25 | Completed | Reeta Bharti |  | Sub Contractor
97 | 7/1 | DA+0 | 43.7758 | 2025-02-19 | 2025-02-25 | Completed | Pankaj |  | Sub Contractor
98 | 33/7 | DA+3 | 46.049 | 2025-02-21 | 2025-02-25 | Completed | Dewi Construction |  | Sub Contractor
99 | 4/10 |  |  |  |  | Completed | Reeta Bharti |  | Sub Contractor
100 | 33/3 |  |  |  |  | Completed | Dewi Construction |  | Sub Contractor
101 | 7/0 |  |  |  |  | Completed | Pankaj |  | Sub Contractor
102 | 8/0 |  |  |  |  | Completed | Pinky Dewi |  | Sub Contractor
103 | 33/3 | DA+3 | 46.0492 | 2025-02-26 | 2025-03-02 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
104 | 35/5 | DA+3 | 46.0492 | 2025-02-27 | 2025-03-03 | Completed | Amar Singh |  | Sub Contractor
105 | 4/10 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-05 | Completed | Reeta Bharti |  | Sub Contractor
106 | 33/8 | DA+3 | 46.0492 | 2025-03-03 | 2025-03-07 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
107 | 7/0 | DB+0 | 64.4817 | 2025-02-27 | 2025-03-08 | Completed | Pankaj |  | Sub Contractor
108 | 7/11 | DA+0 | 43.7758 | 2025-03-01 | 2025-03-08 | Completed | Pinky Dewi |  | Sub Contractor
109 | 35/3 | DA+0 | 43.7758 | 2025-02-28 | 2025-03-08 | Completed | Horil Mahto |  | Sub Contractor
110 | 30/4 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-09 | Completed | ASC heights |  | Sub Contractor
111 | 34/1 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-11 | Completed | Rudra Construction |  | Sub Contractor
112 | 33/4 | DA-3 | 42.3742 | 2025-03-08 | 2025-03-11 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
113 | 8/3 | DA-3 | 42.3742 | 2025-03-08 | 2025-03-12 | Completed | Pinky Dewi |  | Sub Contractor
114 | 5/0 | DB+0 | 64.4817 | 2025-02-27 | 2025-03-13 | Completed | Reeta Bharti |  | Sub Contractor
115 | 30/5 | DA+0 | 43.7758 | 2025-03-10 | 2025-03-16 | Completed | ASC heights |  | Sub Contractor
116 | 35/6 | DA+0 | 43.7758 | 2025-03-10 | 2025-03-18 | Completed | Horil Mahto |  | Sub Contractor
117 | 33/1 | DA-3 | 42.3742 | 2025-03-12 | 2025-03-18 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
118 | 6/1 | DA+3 | 46.0492 | 2025-03-09 | 2025-03-19 | Completed | Pankaj |  | Sub Contractor
119 | 8/4 | DA+9 | 55.3387 | 2025-03-13 | 2025-03-21 | Completed | Pinky Dewi |  | Sub Contractor
120 | 5/1 | DA+3 | 46.0492 | 2025-03-16 | 2025-03-21 | Completed | Reeta Bharti |  | Sub Contractor
121 | 31/8 | DA-3 | 42.3742 | 2025-03-16 | 2025-03-23 | Completed | ASC heights |  | Sub Contractor
122 | 33/2 | DA-3 | 42.3742 | 2025-03-19 | 2025-03-23 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
123 | 8B/1 | DA-3 | 42.375 | 2025-03-23 | 2025-03-26 | Completed | Pinky Dewi |  | Sub Contractor
124 | 6/0 | DB1+0 | 64.482 | 2025-03-22 | 29-3-225 | Completed | Reeta Bharti |  | Sub Contractor
125 | 7/3 | DA-3 | 42.375 | 2025-03-20 | 2025-03-27 | Completed | Pankaj |  | Sub Contractor
126 | 35/2 | DA-3 | 42.375 | 2025-03-20 | 2025-03-30 | Completed | Horil Mahto |  | Sub Contractor
127 | 31/10 | DA-3 | 42.375 | 2025-03-24 | 2025-03-30 | Completed | ASC heights |  | Sub Contractor
128 | 35/8 | DA-3 | 42.375 | 2025-03-23 | 2025-03-31 | Completed | Amar Singh |  | Sub Contractor
129 | 38/8 | DA+3 | 46.0492 | 2025-03-22 | 31-3-20255 | Completed | MK Infra |  | Sub Contractor
130 | 39/3 | DA+3 | 46.0492 | 2025-03-24 | 2025-03-31 | Completed | Ananya Traders |  | Sub Contractor
131 | 8B/5 | DA+6 | 53.324 | 2025-03-23 | 2025-03-31 | Completed | Pinky Dewi |  | Sub Contractor
132 | 34/0 | DB+0 | 64.482 | 2025-03-24 | 2025-03-31 | Completed | Dewi Construction |  | Sub Contractor
133 | 9/0 | DB+6 | 75.8584 | 2025-04-01 | 2025-04-11 | Completed | Gagan 2 |  | Sub Contractor
134 | 4/1 | DA+3 | 46.0492 | 2025-03-31 | 2025-04-11 | Completed | Anand Const. |  | Sub Contractor
135 | 4/6 | DA+0 | 43.7758 | 2025-03-28 | 2025-04-05 | Completed | Reeta Bharti |  | Sub Contractor
136 | 20/11 | DA-3 | 42.375 | 2025-03-31 | 2025-04-08 | Completed | Gagan |  | Sub Contractor
137 | 32/0 | DC1+6 |  | 2025-04-01 | 2025-04-11 | Completed | ASC heights |  | Sub Contractor
138 | 8B/3 | DA+3 | 46.0492 | 2025-03-28 | 2025-04-07 | Completed | Pinky Dewi |  | Sub Contractor
139 | 38/6 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-11 | Completed | MK Infra |  | Sub Contractor
140 | 34/4 | DA-3 | 42.375 | 2025-04-03 | 2025-04-10 | Completed | Dewi Construction |  | Sub Contractor
141 | 8B/2 | DA-3 | 42.3742 | 2025-04-08 | 2025-04-12 | Completed | Pinky Dewi 1 |  | Sub Contractor
142 | 53A/4 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-12 | Completed | Horil Mahto |  | Sub Contractor
143 | 39/1 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-11 | Completed | Ananya Traders-1 |  | Sub Contractor
144 | 20/10 | DA+3 | 46.0492 | 2025-04-09 | 2025-04-14 | Completed | Gagan enterprise.1 |  | Sub Contractor
145 | 36/0 | DB+0 | 64.4817 | 2025-04-01 | 2025-04-14 | Completed | Amar Singh |  | Sub Contractor
146 | 52/6 | DA+3 | 46.0492 | 2025-04-03 | 2025-04-17 | Completed | Ananya Traders-2 |  | Sub Contractor
147 | 10/1 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-17 | Completed | Gagan 2 |  | Sub Contractor
148 | 4/0 | DD45+0 | 86.2562 | 2025-04-06 | 2025-04-17 | Completed | Reeta Bharti |  | Sub Contractor
149 | 39/0 | DB+0 | 64.4817 | 2025-04-12 | 2025-04-19 | Completed | Ananya Traders-1 |  | Sub Contractor
150 | 8B/4 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-21 | Completed | Pinky Dewi |  | Sub Contractor
151 | 31/5 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-21 | Completed | ASC heights |  | Sub Contractor
152 | 33/0 | DC+6 | 87.0116 | 2025-04-12 | 2025-04-22 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
153 | 38/7 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-22 | Completed | M K infra |  | Sub Contractor
154 | 36/6 | DA+0 | 43.7758 | 1900-02-11 18:37 | 2025-04-22 | Completed | Amar Singh |  | Sub Contractor
155 | 20/1 | DA+6 | 53.3239 | 2025-04-12 | 2025-04-22 | Completed | Gagan enterprise.1 |  | Sub Contractor
156 | 25/2 | DA+0 | 43.7758 | 2025-04-12 | 2025-04-23 | Completed | Rudra Construction |  | Sub Contractor
157 | 52/5 | DA-3 | 42.3742 | 2025-04-17 | 2025-04-25 | Completed | Ananya Traders-2 |  | Sub Contractor
158 | 0/4 | DA+9 | 55.3387 | 2025-04-12 | 2025-04-26 | Completed | Anand Construction |  | Sub Contractor
159 | 19/12 | DA-3 | 42.3742 | 2025-04-23 | 2025-04-26 | Completed | Gagan enterprise.1 |  | Sub Contractor
160 | 39/2 | DA-3 | 42.3742 | 2025-04-20 | 2025-04-26 | Completed | Ananya Traders-1 |  | Sub Contractor
161 | 36/7 | DA+3 | 46.0492 | 2025-04-23 | 2025-04-28 | Completed | Amar Singh |  | Sub Contractor
162 | 34/2 | DA+3 | 46.0492 | 2025-04-23 | 2025-04-28 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
163 | 10/0 | DB+9 | 78.6775 | 2025-04-17 | 2025-04-28 | Completed | Gagan enterprise.2 |  | Sub Contractor
164 | 30/6 | DA-3 | 42.3742 | 2025-04-22 | 2025-04-28 | Completed | ASC heights |  | Sub Contractor
165 | 52/4 | DA-3 | 42.3742 | 2025-04-26 | 2025-04-29 | Completed | Ananya Traders-2 |  | Sub Contractor
166 | 38/9 | DA-3 | 42.3742 | 2025-04-23 | 2025-04-29 | Completed | M K infra |  | Sub Contractor
167 | 8A/0 | DD60+0 | 97.2286 | 2025-04-22 | 2025-04-30 | Completed | Pinky Dewi |  | Sub Contractor
168 | 19/11 | DA-3 | 42.3742 | 2025-04-27 | 2025-04-30 | Completed | Gagan enterprise.1 |  | Sub Contractor
169 | 34/3 | DA+3 | 46.0492 | 2025-04-29 | 2025-05-03 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
170 | 39/4 | DA+3 | 46.0492 | 2025-04-27 | 2025-05-04 | Completed | Ananya Traders-1 |  | Sub Contractor
171 | 36/8 | DA-3 | 42.3742 | 2025-04-29 | 2025-05-05 | Completed | Amar Singh |  | Sub Contractor
172 | 52/3 | DA-3 | 42.3742 | 2025-05-02 | 2025-05-06 | Completed | Ananya Traders-2 |  | Sub Contractor
173 | 30/3 | DA+0 | 43.7758 | 2025-05-01 | 2025-05-06 | Completed | ASC heights |  | Sub Contractor
174 | 19/10 | DA+3 | 46.0492 | 2025-05-02 | 2025-05-06 | Completed | Gagan enterprise.1 |  | Sub Contractor
175 | 25/3 | DA+3 | 46.0492 | 2025-04-27 | 2025-05-07 | Completed | Rudra Construction |  | Sub Contractor
176 | 19/8 | DA-3 | 42.3742 | 2025-05-06 | 2025-05-09 | Completed | Gagan enterprise.1 |  | Sub Contractor
177 | 12/1 | DA-3 | 42.3742 | 2025-05-04 | 2025-05-10 | Completed | Gagan enterprise.2 |  | Sub Contractor
178 | 4/9 | DA-3 | 42.3742 | 2025-05-04 | 2025-05-11 | Completed | Reeta Bharti |  | Sub Contractor
179 | 39/5 | DA-3 | 42.3742 | 2025-05-05 | 2025-05-11 | Completed | Ananya Traders-1 |  | Sub Contractor
180 | 52/2 | DA+3 | 46.0492 | 2025-05-07 | 2025-05-12 | Completed | Ananya Traders-2 |  | Sub Contractor
181 | 30/1 | DA-3 | 42.3742 | 2025-05-07 | 2025-05-13 | Completed | ASC heights |  | Sub Contractor
182 | 36/4 | DA+0 | 43.7758 | 2025-05-07 | 2025-05-13 | Completed | Amar Singh |  | Sub Contractor
183 | 56/2 | DA+3 | 46.0492 | 2025-05-07 | 2025-05-14 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
184 | 8B/0 | DD60+0 | 97.2286 | 2025-05-05 | 2025-05-14 | Completed | Pinky Dewi |  | Sub Contractor
185 | 52/9 | DA-3 | 42.3742 | 2025-05-13 | 2025-05-15 | Completed | Ananya Traders-2 |  | Sub Contractor
186 | 17/8 | DA-3 | 42.3742 | 2025-05-11 | 2025-05-15 | Completed | Gagan enterprise.1 |  | Sub Contractor
187 | 38/11 | DA+3 | 46.0492 | 2025-05-12 | 2025-05-19 | Completed | Ananya Traders-1 |  | Sub Contractor
188 | 36/11 | DA-3 | 42.3742 | 2025-05-14 | 2025-05-19 | Completed | Amar Singh |  | Sub Contractor
189 | 56/1 | DA+0 | 43.7758 | 2025-05-14 | 2025-05-19 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
190 | 30/2 | DA-3 | 42.3742 | 2025-05-14 | 2025-05-20 | Completed | ASC heights |  | Sub Contractor
191 | 52/10 | DA+3 | 46.0492 | 2025-05-16 | 2025-05-21 | Completed | Ananya Traders-2 |  | Sub Contractor
192 | 2/1 | DA+3 | 46.0492 | 2025-05-12 | 2025-05-21 | Completed | Reeta Bharti |  | Sub Contractor
193 | 12/6 | DA-3 | 42.3742 | 2025-05-11 | 2025-05-22 | Completed | Gagan enterprise.2 |  | Sub Contractor
194 | 53/1 | DA+6 | 53.3239 | 2025-05-12 | 2025-05-22 | Completed | Amit Const |  | Sub Contractor
195 | 23/3 | DA-3 | 42.3742 | 2025-05-15 | 2025-05-22 | Completed | Pinky Dewi |  | Sub Contractor
196 | 38/10 | DA-3 | 42.3742 | 2025-05-13 | 2025-05-24 | Completed | Ananya Traders-1 |  | Sub Contractor
197 | 56/3 | DA-3 | 42.3742 | 2025-05-20 | 2025-05-24 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
198 | 36/9 | DA-3 | 42.3742 | 2025-05-20 | 2025-05-24 | Completed | Amar Singh |  | Sub Contractor
199 | 15/0 | DC+3 | 78.073 | 2025-05-16 | 2025-05-25 | Completed | Gagan enterprise.1 |  | Sub Contractor
200 | 23/5 | DA-3 | 42.3742 | 2025-05-10 | 2025-05-25 | Completed | Rudra Construction |  | Sub Contractor
201 | 0/2 | DA-3 | 42.3742 | 2025-05-22 | 2025-05-30 | Completed | Reeta Bharti |  | Sub Contractor
202 | 23/4 | DA-3 | 42.3742 | 2025-05-23 | 2025-05-28 | Completed | Pinky Dewi |  | Sub Contractor
203 | 56/4 | DA-3 | 42.3742 | 2025-05-24 | 2025-05-28 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
204 | 36/10 | DA-3 | 42.3742 | 2025-05-24 | 2025-05-31 | Completed | Amar Singh |  | Sub Contractor
205 | 12/8 | DA-3 | 42.3742 | 2025-05-25 | 2025-05-31 | Completed | Gagan enterprise.1 |  | Sub Contractor
206 | 52/8 | DA-3 | 42.3742 | 2025-05-22 | 2025-05-27 | Completed | Ananya Traders-2 |  | Sub Contractor
207 | 38/5 | DA+3 | 46.049 | 2025-05-28 | 2025-06-02 | Completed | Ananya Traders-1 | 30 | Sub Contractor
208 | 23/1 | DA+9 | 55.339 | 2025-05-28 | 2025-06-03 | Completed | Pinky Dewi | 31 | Sub Contractor
209 | 0/3 | DA-3 | 42.374 | 2025-05-25 | 2025-06-04 | Completed | Reeta Bharti | 25 | Sub Contractor
210 | 56/5 | DA-3 | 42.374 | 2025-05-30 | 2025-06-04 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
211 | 51/0 | DD60+0 | 97.229 | 2025-05-27 | 2025-06-07 | Completed | Ananya Traders-2 | 42 | Sub Contractor
212 | 33/5 | DA+3 | 46.049 | 2025-06-03 | 2025-06-08 | Completed | Amar Singh | 34 | Sub Contractor
213 | 23/2 | DA+0 | 43.776 | 2025-06-04 | 2025-06-08 | Completed | Pinki Dewi | 30 | Sub Contractor
214 | 0/1 | DA-3 | 42.374 | 2025-06-05 | 2025-06-10 | Completed | Reeta Bharti | 24 | Sub Contractor
215 | 50/1 | DA+0 | 43.776 | 2025-06-08 | 2025-06-12 | Completed | Ananya Traders-2 | 42 | Sub Contractor
216 | 53A/5 | DA-3 | 42.374 | 2025-06-02 | 2025-06-12 | Completed | Devine | 20 | Sub Contractor
217 | 34/5 | DA+0 | 43.776 | 2025-06-09 | 2025-06-17 | Completed | Amar Singh | 24 | Sub Contractor
218 | 53A/2 | DA+3 | 46.049 | 2025-05-30 | 2025-06-17 | Completed | Amit Const | 21 | Sub Contractor
219 | 22/0 | DB+3 | 67.112 | 2025-06-09 | 2025-06-19 | Completed | Pinki Dewi | 25 | Sub Contractor
220 | 30/0 | DD60+18 | 143.462 | 2025-05-21 | 2025-06-21 | Completed | ASC heights | 25 | Sub Contractor
221 | 3/0 | DC+0 | 73.426 | 2025-06-05 | 2025-06-23 | Completed | Reeta Bharti | 21 | Sub Contractor
222 | 21/2 | DA+3 | 46.049 | 2025-06-20 | 2025-06-26 | Completed | Pinki Dewi | 25
223 | 45/1 | DA+3 | 46.049 | 2025-06-06 | 2025-06-26 | Completed | MK Infra | 18 | Sub Contractor
224 | 48/0 | DD45+9 | 104.867 | 2025-06-14 | 1935-06-28 | Completed | Ananya Traders-2 | 33 | Sub Contractor
225 | 53A/3 | DA-3 | 42.374 | 2025-06-20 | 1935-06-28 | Completed | Amit Const | 22 | Sub Contractor
226 | 21/1 | DA-3 | 42.374 | 1935-06-27 | 2025-06-29 | Completed | Pinki Dewi | 28 | Sub Contractor
227 | 40/0 | DD60+25 | 161.355 | 2025-06-03 | 2025-06-29 | Completed | Ananya Traders-1 | 32 | Sub Contractor
228 | 12/7 | DA-3 | 42.374 | 2025-06-24 | 2025-06-29 | Completed | Reeta Bharti | 22 | Sub Contractor
229 | 14/0 | DD60+30 | 188.378 | 2025-05-28 | 2025-06-30 | Completed | Gagan | 41 | Sub Contractor
230 | 28/1 | DA+3 | 46.049 | 2025-06-22 | 2025-07-05 | Completed | ASC heights | 25 | Sub Contractor
231 | 21/3 | DA+3 | 46.049 | 2025-07-02 | 2025-07-07 | Completed | Pinki Dewi | 28 | Sub Contractor
232 | 25/1 | DA+9 | 55.339 | 2025-07-02 | 2025-07-12 | Completed | Reeta Bharti | 23 | Sub Contractor
233 | 44/0 | DD60+3 | 101.692 | 2025-07-05 | 2025-07-18 | Completed | Ananya Traders-1 | 28 | Sub Contractor
234 | 56/0 | DD45+0 | 86.256 | 2025-06-20 | 2025-07-22 | Completed | Amar Singh | 22 | Sub Contractor
235 | 28/0 | DD60+0 | 97.23 | 2025-07-13 | 2025-07-31 | Completed | Reeta Bharti | 28 | Sub Contractor
236 | 41/0 | DD60+18 | 143.462 | 2025-07-19 | 2025-08-08 | Completed | Ananya Traders-1 | 32 | Sub Contractor
237 | 13/0 | DD60+30 | 188.378 | 2025-07-02 | 2025-08-11 | Completed | Gagan | 27 | Sub Contractor
238 | 53A/6 | DA+3 | 46.049 | 2025-07-28 | 2025-08-17 | Completed | Punam kumari | 30 | Sub Contractor
239 | 46/2 | DA+3 | 46.049 | 2025-08-14 | 2025-08-26 | Completed | kajal Const. | 27 | Sub Contractor
240 | 24/0 | DD60+25 | 161.355 | 2025-07-26 | 2025-08-27 | Completed | Kangresh -1 | 32 | Sub Contractor
241 | 1/0 | DC+3 | 78.073 | 2025-08-09 | 2025-08-30 | Completed | Radha Const. | 30 | Sub Contractor
242 | 18/0 | DB+6 | 75.85 | 2025-08-04 | 2025-08-30 | Completed | Sainik Ent. | 25 | Sub Contractor
243 | 65/0 | DD60+0 | 97.229 | 2025-08-02 | 2025-08-30 | Completed | Kangresh -2 | 30 | Sub Contractor
244 | 12/0 | DB+18 | 97.65 | 2025-08-12 | 2025-09-02 | Completed | Gagan | 30 | Sub Contractor
245 | 43/0 | DD60+18 | 118.43 | 2025-08-10 | 2025-09-07 | Completed | Ananya | 34 | Sub Contractor
246 | 54/1 | DA+9 | 55.339 | 2025-08-18 | 2025-09-04 | Completed | Punam kumari | 27 | Sub Contractor
247 | 47/0 | DC+9 | 90.125 | 2025-09-08 |  | 3rd section wip | Ananya | 34 | Sub Contractor
248 | 48/1 | DA-3 | 42.374 | 2025-08-18 |  | 1st section wip | MK Infra | 22 | Sub Contractor
249 | 53A/1 | DA+6 | 53.324 | 2025-08-18 |  | 2nd section wip | Spotify pvt ltd-2 | 20 | Sub Contractor
250 | 56/8 | DA-3 | 42.374 | 2025-08-18 |  | 3rd section wip | Spotify pvt ltd-3 | 24 | Sub Contractor
251 | 19/0 | DC+6 | 87.01 | 2025-08-31 |  | 3rd section Completed | Sainik Ent. | 25 | Sub Contractor
252 | 64/0 | DC+0 | 73.426 | 2025-08-31 |  | Bottom section wip | Kangresh -2 | 30 | Sub Contractor
253 | 2/0 | DD45+3 | 89.7 | 2025-08-31 |  | Cage 1 wip | Radha Const. | 33 | Sub Contractor
254 | 11/0 | DB+18 | 97.65 | 2025-08-24 | 2025-09-14 | Completed | Gouri shankar | 45 | Sub Contractor
255 | 23/0 | DC+18 |  | 2025-09-04 |  | 1st section Completed | Gagan | 34 | Sub Contractor
256 | 16/0 | DB+25 | 110.6 | 2025-08-16 | 2025-09-14 | Completed | Amit Const | 40 | Sub Contractor
257 | 25/0 | DD60+25 | 161.355 | 2025-08-28 |  | 3rd section wip | Kangresh -1 | 32 | Sub Contractor
258 | 29/0 | DD60+25 | 161.355 | 2025-08-06 |  | Cage 2 Completed | Reeta Bharti | 32 | Sub Contractor
259 | 52/0 | DC2+9 |  | 2025-09-08 |  | 3rd section wip | Punam kumari | 33 | Sub Contractor
260 | 17/0 | DB+6 |  | 2025-09-11 |  | leg joint Done | Maa Const. | 25 | Sub Contractor
STRINGING
S.No | Section | Length (km) | TSE/Manual | Gang | Payingout/Rough Sag |  | Final Sag |  | STATUS |  | Remark
[5 empty] | Start | End | Start | End
1 | AP7 to AP8 | 4.818 | TSE | Anarul | 2025-05-03 | 2025-05-10 | 2025-05-15 | 2025-05-18 | Final sag Completed |  | Clipping & Spacer installation completed
2 | AP6 to AP7 | 1.234 | TSE | Anarul | 2025-05-11 | 2025-05-11 | 2025-05-17 | 2025-05-21 | Final sag Completed |  | Clipping & Spacer installation completed
3 | AP35 to AP36 | 3.957 | TSE | SK Const. | 2025-05-16 | 2025-05-25 | 2025-06-26 | 2025-06-30 | Final sag Completed |  | Clipping Done
4 | AP8 to AP8A/0 | 2.016 | TSE | Anarul | 2025-05-22 | 2025-05-29 | 2025-06-21 | 2025-06-24 | Final sag Completed |  | Clipping & Spacer installation completed
5 | AP31 to AP32 | 4.283 | TSE | SK Const. | 2025-06-02 | 2025-06-08 | 2025-06-21 | 2025-06-26 | Final sag Completed |  | Clipping Done
6 | AP8A/0 to AP8B/0 | 0.223 | Manual | Anarul | 2025-06-10 | 2025-06-17 | 2025-07-22 | 2025-07-23 | Final sag Completed
7 | AP32 to AP33 | 0.407 | Manual | SK Const. | 2025-06-12 | 2025-06-19 | 2025-07-22 | 2023-07-29 | Final sag Completed
8 | AP8B/0 to AP9/0 | 2.226 | TSE | Anarul | 2025-07-18 | 2025-07-21 | 2025-07-24 | 2025-07-28 | Final sag Completed |  | Clipping Done and spacer installation u/p
9 | AP33/0 to AP34/0 | 4.78 | TSE | SK Const. | 2025-07-01 | 2025-07-21 | 2025-07-22 | 2023-07-29 | Final sag Completed |  | Clipping and spacer installation u/p
10 | AP5/0 to AP6/0 | 0.723 | TSE | Anarul | 2025-07-29 | 2025-08-08 | 2025-08-26 | 2025-08-27 | Final sag Completed
11 | AP34/0 to AP35/0 | 3.193 | TSE | SK Const. | 2025-08-11 | 2025-08-22 | 2025-08-22 | 2025-08-24 | Final sag Completed
12 | AP9/0 to AP10/0 | 0.2834 | Manual | Anarul | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-11 | Final sag Completed
13 | AP4/0 to AP5/0 | 4.416 | TSE | Anarul | 2025-08-12 | 2025-08-25 | 2025-08-29 | 2025-09-02 | Final sag Completed
14 | AP20/0 to AP21/0 | 4.958 | TSE | GPJ const |  |  |  |  | Insulator hoisting Done
15 | AP36/0 to AP37/0 | 4.947 | TSE | SK Const. | 2025-08-30 | 2025-09-12 |  |  | All phase Rough sag Done
16 | AP14/0 to AP15/0 | 3.611 | TSE | Anarul | 2025-09-03 | 2025-09-10 |  |  | All phase Rough sag Done
17 | 3/0 to 4/0 | 0.28 | Manual | Anarul |  |  |  |  | Conductor Bit cutting u/p
18 | 30/0 to 31/0 | 2.75 | TSE | SK Const. |  |  |  |  | Insulator hoisting u/p
19
20
21
22
Formulas:
Date of Submission Actual/Expected = [1]!'!Erection!R216C6:R219C7'

## Erection Compiled
SL No. | Location No. | Tower Type | Tower Weight | Starting Date | Completion Date | Work status | Gang Name | Gang strength | Gang type(Subcontractor/Company) | Tac welding | Remark
1 | 2/8 | DA+0 | 43.7758 | 2024-09-01 | 2024-09-16 | Completed | Dewi Construction
2 | 2/4 | DA+0 | 43.7758 | 2024-09-16 | 2024-09-29 | Completed | Dewi Construction(Girendra)
3 | 39/10 | DA+0 | 43.7758 | 2024-09-16 | 2024-10-01 | Completed | Horil Mahto
4 | 20/8 | DA+0 | 43.7758 | 2024-10-01 | 2024-10-07 | Completed | Dewi Construction(Girendra)
5 | 39/8 | DA+0 | 43.7758 | 2024-10-03 | 2024-10-15 | Completed | Horil Mahto
6 | 20/6 | DA+0 | 43.7758 | 2024-10-08 | 2024-10-13 | Completed | Dewi Construction(Girendra)
7 | 20/9 | DA+3 | 46.0492 | 2024-10-14 | 2024-10-19 | Completed | Dewi Construction(Girendra)
8 | 39/7 | DA+3 | 46.0492 | 2024-10-15 | 2024-10-24 | Completed | Horil Mahto
9 | 20/5 | DA+3 | 46.0492 | 2024-10-20 | 2024-10-24 | Completed | Dewi Construction(Girendra)
10 | 20/7 | DA-3 | 42.3742 | 2024-10-24 | 2024-10-29 | Completed | Dewi Construction(Girendra)
11 | 39/9 | DA+3 | 46.0492 | 2024-10-24 | 2024-10-31 | Completed | Horil Mahto
12 | 20/12 | DA-3 | 42.3742 | 2024-11-01 | 2024-11-04 | Completed | Dewi Construction(Girendra)
13 | 14/6 | DA+3 | 46.0492 | 2024-11-05 | 2024-11-10 | Completed | Dewi Construction(Girendra)
14 | 39/6 | DA+3 | 46.0492 | 2024-11-01 | 14.11.2024 | Completed | Horil Mahto
15 | 14/5 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-17 | Completed | Dewi Construction(Girendra)
16 | 14/4 | DA+3 | 46.0492 | 2024-11-17 | 2024-11-22 | Completed | Dewi Construction(Girendra)
17 | 2/5 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-24 | Completed | Pankaj
18 | 19/3 | DA+3 | 46.0492 | 2024-11-10 | 2024-11-26 | Completed | Reeta Bharti
19 | 6/2 | DA+3 | 46.0492 | 2024-11-14 | 2026-11-25 | Completed | Pinky Dewi
20 | 38/3 | DA+3 | 46.0492 | 2024-11-10 | 2026-11-25 | Completed | Horil Mahto
21 | 14/8 | DA+3 | 46.0492 | 2024-11-22 | 2024-11-28 | Completed | Dewi Construction(Girendra)
22 | 41/1 | DA+0 | 43.7758 | 2024-11-10 | 2024-11-29 | Completed | Amar Singh
23 | 2/7 | DA+3 | 46.0492 | 2024-11-26 | 2024-12-03 | Completed | Pankaj
24 | 19/2 | DA+0 | 43.7758 | 2024-11-28 | 2024-12-05 | Completed | Reeta Bharti
25 | 14/7 | DA+0 | 43.7758 | 2024-11-29 | 2024-12-05 | Completed | Dewi Construction(Girendra)
26 | 4/3 | DA+3 | 46.0492 | 2024-11-28 | 2024-12-05 | Completed | Pinky Dewi
27 | 36/12 | DA+0 | 43.7758 | 2024-11-29 | 2024-12-06 | Completed | Horil Mahto
28 | 2/6 | DA+0 | 43.7758 | 2024-12-01 | 2024-12-09 | Completed | Pankaj
29 | 41/2 | DA+3 | 46.0492 | 2024-11-30 | 2024-12-10 | Completed | Amar Singh
30 | 14/3 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-12 | Completed | Dewi Construction(Girendra)
31 | 4/4 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-12 | Completed | Pinky Dewi
32 | 19/4 | DA+0 | 43.7758 | 2024-12-06 | 2024-12-13 | Completed | Reeta Bharti
33 | 2/3 | DA+3 | 46.0492 | 2024-12-10 | 2024-12-16 | Completed | Pankaj
34 | 4/2 | DA-3 | 42.3742 | 2024-12-12 | 2024-12-16 | Completed | Pinky Dewi
35 | 14/2 | DA+0 | 43.7758 | 2024-12-12 | 2024-12-17 | Completed | Dewi Construction(Girendra)
36 | 38/2 | DA+3 | 46.0492 | 2024-12-06 | 2024-12-19 | Completed | Horil Mahto
37 | 45/3 | DA-3 | 42.3742 | 2024-12-10 | 2024-12-20 | Completed | Amar Singh
38 | 19/1 | DA+0 | 43.7758 | 2024-12-13 | 2024-12-21 | Completed | Reeta Bharti
39 | 4/8 | DA+0 | 43.7758 | 2024-12-17 | 2024-12-22 | Completed | Pinky Dewi
40 | 14/1 | DA+0 | 43.7758 | 2024-12-18 | 2024-12-23 | Completed | Dewi Construction(Girendra)
41 | 7/10 | DA+3 | 46.0492 | 2024-12-18 | 2024-12-23 | Completed | Pankaj
42 | 45/2 | DA+3 | 46.0492 | 2024-12-21 | 2024-12-27 | Completed | Amar Singh
43 | 19/5 | DA-3 | 42.3742 | 2024-12-22 | 2024-12-27 | Completed | Reeta Bharti
44 | 4/7 | DA+3 | 46.0492 | 2024-12-24 | 2024-12-27 | Completed | Pinky Dewi
45 | 7/9 | DA+0 | 43.7758 | 2024-12-24 | 2024-12-30 | Completed | Pankaj
46 | 38/4 | DA+3 | 46.0492 | 2024-12-20 | 2024-12-31 | Completed | Horil Mahto
47 | 17/1 | DA-3 | 42.3742 | 2024-12-24 | 2024-12-31 | Completed | Dewi Construction(Girendra)
48 | 31/3 | DA+3 | 46.0492 | 2024-12-24 | 2025-01-03 | Completed | ASC heights
49 | 4/5 | DA+3 | 46.0492 | 2024-12-28 | 2025-01-03 | Completed | Pinky Dewi
50 | 46/1 | DA+0 | 43.7758 | 2024-12-28 | 2025-01-04 | Completed | Amar Singh
51 | 7/2 | DA+3 | 46.0492 | 2024-12-31 | 2025-01-07 | Completed | Pankaj
52 | 19/6 | DA+0 | 43.7758 | 2024-12-28 | 2025-01-08 | Completed | Reeta Bharti
53 | 17/4 | DA+3 | 46.0492 | 2025-01-01 | 2025-01-10 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
54 | 31/4 | DA-3 | 42.3742 | 2025-01-04 | 2025-01-11 | Completed | ASC heights | 38 | Sub Contractor
55 | 12/2 | DA+3 | 46.0492 | 2025-01-03 | 2025-01-11 | Completed | Pinky Dewi | 42 | Sub Contractor
56 | 7/8 | DA+3 | 46.0492 | 2025-01-08 | 2025-01-15 | Completed | Pankaj | 23 | Sub Contractor
57 | 36/3 | DA+3 | 46.0492 | 2025-01-07 | 2025-01-15 | Completed | Amar Singh | 22 | Sub Contractor
58 | 38/1 | DA+3 | 46.0492 | 2025-01-07 | 2025-01-17 | Completed | Horil Mahto | 24 | Sub Contractor
59 | 19/7 | DA+3 | 46.0492 | 2025-01-09 | 2025-01-17 | Completed | Reeta Bharti | 25 | Sub Contractor
60 | 17/3 | DA+0 | 43.7758 | 2025-01-10 | 2025-01-17 | Completed | Dewi Construction | 40 | Sub Contractor
61 | 31/2 | DA+0 | 43.7758 | 2025-01-11 | 2025-01-19 | Completed | ASC heights | 38 | Sub Contractor
62 | 12/3 | DA+3 | 46.0492 | 2025-01-12 | 2025-01-21 | Completed | Pinky Dewi | 35 | Sub Contractor
63 | 7/7 | DA+0 | 43.7758 | 2025-01-16 | 2025-01-22 | Completed | Pankaj | 23 | Sub Contractor
64 | 17/2 | DA+0 | 43.7758 | 2025-01-18 | 2025-01-23 | Completed | Dewi Construction | 40 | Sub Contractor
65 | 36/5 | DA+0 | 43.7758 | 2025-01-16 | 2025-01-24 | Completed | Amar Singh | 24 | Sub Contractor
66 | 33/10 | DA+3 | 46.0492 | 2025-01-10 | 2025-01-31 | Completed | Rudra Construction | 22 | Sub Contractor
67 | 19/9 | DA+3 | 46.0492 | 2025-01-18 | 2025-01-27 | Completed | Reeta Bharti | 25 | Sub Contractor
68 | 35/1 | DA+3 | 46.0492 | 2025-01-18 | 2025-01-28 | Completed | Horil Mahto | 26 | Sub Contractor
69 | 31/6 | DA+3 | 46.0492 | 2025-10-20 | 2025-01-25 | Completed | ASC heights | 38 | Sub Contractor
70 | 12/4 | DA+3 | 46.0492 | 2025-01-22 | 2025-01-25 | Completed | Pinky Dewi | 35 | Sub Contractor
71 | 7/6 | DA+0 | 43.7758 | 2025-01-23 | 2025-01-30 | Completed | Pankaj | 23 | Sub Contractor
72 | 17/5 | DA+3 | 46.0492 | 2025-01-24 | 2025-01-29 | Completed | Dewi Construction | 40 | Sub Contractor
73 | 36/1 | DA+3 | 46.0492 | 2025-01-25 | 2025-01-30 | Completed | Amar Singh | 24 | Sub Contractor
74 | 31/1 | DA+0 | 43.7758 | 2025-01-26 | 2025-02-02 | Completed | ASC heights |  | Sub Contractor
75 | 12/5 | DA+3 | 46.0492 | 2025-01-26 | 2025-02-01 | Completed | Pinky Dewi |  | Sub Contractor
76 | 17/7 | DA+3 | 46.0492 | 2025-01-30 | 2025-02-05 | Completed | Dewi Construction |  | Sub Contractor
77 | 36/2 | DA+0 | 43.7758 | 2025-02-02 | 2025-02-07 | Completed | Amar Singh |  | Sub Contractor
78 | 20/0 | DB1+0 | 64.482 | 2025-01-28 | 2025-02-06 | Completed | Reeta Bharti |  | Sub Contractor
79 | 12/9 | DA+3 | 46.0492 | 2025-02-02 | 2025-02-08 | Completed | Pinky Dewi |  | Sub Contractor
80 | 31/7 | DA+0 | 43.7758 | 2025-02-03 | 2025-02-10 | Completed | ASC heights |  | Sub Contractor
81 | 35/0 | DC1+0 | 73.426 | 2025-01-29 | 2025-02-10 | Completed | Horil Mahto |  | Sub Contractor
82 | 7/5 | DA+3 | 46.0492 | 2025-01-31 | 2025-02-10 | Completed | Pankaj |  | Sub Contractor
83 | 33/11 | DA+3 | 46.0492 | 2025-02-02 |  | Completed | Rudra Construction |  | Sub Contractor
84 | 21/0 | DB+0 | 64.482 | 2025-02-06 |  | Completed | Dewi Construction |  | Sub Contractor
85 | 20/2 | DA+0 | 43.7758 | 2025-02-07 |  | Completed | Reeta Bharti |  | Sub Contractor
86 | 35/9 | DA+3 | 46.0492 | 2025-02-08 |  | Completed | Amar Singh |  | Sub Contractor
87 | 8/1 | DA+3 | 46.049 | 2025-02-09 | 2025-02-15 | Completed | Pinky Dewi |  | Sub Contractor
88 | 7/4 | DA+0 | 43.7758 | 2025-02-11 | 2025-02-18 | Completed | Pankaj |  | Sub Contractor
89 | 34/7 | DA+3 | 46.049 | 2025-02-11 | 20-20-2025 | Completed | Horil Mahto |  | Sub Contractor
90 | 31/9 | DA+3 | 46.049 | 2025-02-11 | 20-20-2025 | Completed | ASC heights |  | Sub Contractor
91 | 35/7 | DA+3 | 46.049 | 2025-02-16 | 2025-02-21 | Completed | Amar Singh |  | Sub Contractor
92 | 20/3 | DA+0 | 43.7758 | 2025-02-12 | 2025-02-19 | Completed | Reeta Bharti |  | Sub Contractor
93 | 8/2 | DA+0 | 43.7758 | 2025-02-16 | 2025-02-21 | Completed | Pinky Dewi |  | Sub Contractor
94 | 33/6 | DA+3 | 46.049 | 2025-02-14 | 2025-02-20 | Completed | Dewi Construction |  | Sub Contractor
95 | 33/9 | DA+0 | 43.7758 | 2025-02-14 | 2025-02-23 | Completed | Rudra Construction |  | Sub Contractor
96 | 20/4 | DA-3 | 42.375 | 2025-02-20 | 2025-02-25 | Completed | Reeta Bharti |  | Sub Contractor
97 | 7/1 | DA+0 | 43.7758 | 2025-02-19 | 2025-02-25 | Completed | Pankaj |  | Sub Contractor
98 | 33/7 | DA+3 | 46.049 | 2025-02-21 | 2025-02-25 | Completed | Dewi Construction |  | Sub Contractor
99 | 4/10 |  |  |  |  | Completed | Reeta Bharti |  | Sub Contractor
100 | 33/3 |  |  |  |  | Completed | Dewi Construction |  | Sub Contractor
101 | 7/0 |  |  |  |  | Completed | Pankaj |  | Sub Contractor
102 | 8/0 |  |  |  |  | Completed | Pinky Dewi |  | Sub Contractor
103 | 33/3 | DA+3 | 46.0492 | 2025-02-26 | 2025-03-02 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
104 | 35/5 | DA+3 | 46.0492 | 2025-02-27 | 2025-03-03 | Completed | Amar Singh |  | Sub Contractor
105 | 4/10 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-05 | Completed | Reeta Bharti |  | Sub Contractor
106 | 33/8 | DA+3 | 46.0492 | 2025-03-03 | 2025-03-07 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
107 | 7/0 | DB+0 | 64.4817 | 2025-02-27 | 2025-03-08 | Completed | Pankaj |  | Sub Contractor
108 | 7/11 | DA+0 | 43.7758 | 2025-03-01 | 2025-03-08 | Completed | Pinky Dewi |  | Sub Contractor
109 | 35/3 | DA+0 | 43.7758 | 2025-02-28 | 2025-03-08 | Completed | Horil Mahto |  | Sub Contractor
110 | 30/4 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-09 | Completed | ASC heights |  | Sub Contractor
111 | 34/1 | DA+3 | 46.0492 | 2025-03-01 | 2025-03-11 | Completed | Rudra Construction |  | Sub Contractor
112 | 33/4 | DA-3 | 42.3742 | 2025-03-08 | 2025-03-11 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
113 | 8/3 | DA-3 | 42.3742 | 2025-03-08 | 2025-03-12 | Completed | Pinky Dewi |  | Sub Contractor
114 | 5/0 | DB+0 | 64.4817 | 2025-02-27 | 2025-03-13 | Completed | Reeta Bharti |  | Sub Contractor
115 | 30/5 | DA+0 | 43.7758 | 2025-03-10 | 2025-03-16 | Completed | ASC heights |  | Sub Contractor
116 | 35/6 | DA+0 | 43.7758 | 2025-03-10 | 2025-03-18 | Completed | Horil Mahto |  | Sub Contractor
117 | 33/1 | DA-3 | 42.3742 | 2025-03-12 | 2025-03-18 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
118 | 6/1 | DA+3 | 46.0492 | 2025-03-09 | 2025-03-19 | Completed | Pankaj |  | Sub Contractor
119 | 8/4 | DA+9 | 55.3387 | 2025-03-13 | 2025-03-21 | Completed | Pinky Dewi |  | Sub Contractor
120 | 5/1 | DA+3 | 46.0492 | 2025-03-16 | 2025-03-21 | Completed | Reeta Bharti |  | Sub Contractor
121 | 31/8 | DA-3 | 42.3742 | 2025-03-16 | 2025-03-23 | Completed | ASC heights |  | Sub Contractor
122 | 33/2 | DA-3 | 42.3742 | 2025-03-19 | 2025-03-23 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
123 | 8B/1 | DA-3 | 42.375 | 2025-03-23 | 2025-03-26 | Completed | Pinky Dewi |  | Sub Contractor
124 | 6/0 | DB1+0 | 64.482 | 2025-03-22 | 29-3-225 | Completed | Reeta Bharti |  | Sub Contractor
125 | 7/3 | DA-3 | 42.375 | 2025-03-20 | 2025-03-27 | Completed | Pankaj |  | Sub Contractor
126 | 35/2 | DA-3 | 42.375 | 2025-03-20 | 2025-03-30 | Completed | Horil Mahto |  | Sub Contractor
127 | 31/10 | DA-3 | 42.375 | 2025-03-24 | 2025-03-30 | Completed | ASC heights |  | Sub Contractor
128 | 35/8 | DA-3 | 42.375 | 2025-03-23 | 2025-03-31 | Completed | Amar Singh |  | Sub Contractor
129 | 38/8 | DA+3 | 46.0492 | 2025-03-22 | 31-3-20255 | Completed | MK Infra |  | Sub Contractor
130 | 39/3 | DA+3 | 46.0492 | 2025-03-24 | 2025-03-31 | Completed | Ananya Traders |  | Sub Contractor
131 | 8B/5 | DA+6 | 53.324 | 2025-03-23 | 2025-03-31 | Completed | Pinky Dewi |  | Sub Contractor
132 | 34/0 | DB+0 | 64.482 | 2025-03-24 | 2025-03-31 | Completed | Dewi Construction |  | Sub Contractor
133 | 9/0 | DB+6 | 75.8584 | 2025-04-01 | 2025-04-11 | Completed | Gagan 2 |  | Sub Contractor
134 | 4/1 | DA+3 | 46.0492 | 2025-03-31 | 2025-04-11 | Completed | Anand Const. |  | Sub Contractor
135 | 4/6 | DA+0 | 43.7758 | 2025-03-28 | 2025-04-05 | Completed | Reeta Bharti |  | Sub Contractor
136 | 20/11 | DA-3 | 42.375 | 2025-03-31 | 2025-04-08 | Completed | Gagan |  | Sub Contractor
137 | 32/0 | DC1+6 |  | 2025-04-01 | 2025-04-11 | Completed | ASC heights |  | Sub Contractor
138 | 8B/3 | DA+3 | 46.0492 | 2025-03-28 | 2025-04-07 | Completed | Pinky Dewi |  | Sub Contractor
139 | 38/6 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-11 | Completed | MK Infra |  | Sub Contractor
140 | 34/4 | DA-3 | 42.375 | 2025-04-03 | 2025-04-10 | Completed | Dewi Construction |  | Sub Contractor
141 | 8B/2 | DA-3 | 42.3742 | 2025-04-08 | 2025-04-12 | Completed | Pinky Dewi 1 |  | Sub Contractor
142 | 53A/4 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-12 | Completed | Horil Mahto |  | Sub Contractor
143 | 39/1 | DA+3 | 46.0492 | 2025-04-01 | 2025-04-11 | Completed | Ananya Traders-1 |  | Sub Contractor
144 | 20/10 | DA+3 | 46.0492 | 2025-04-09 | 2025-04-14 | Completed | Gagan enterprise.1 |  | Sub Contractor
145 | 36/0 | DB+0 | 64.4817 | 2025-04-01 | 2025-04-14 | Completed | Amar Singh |  | Sub Contractor
146 | 52/6 | DA+3 | 46.0492 | 2025-04-03 | 2025-04-17 | Completed | Ananya Traders-2 |  | Sub Contractor
147 | 10/1 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-17 | Completed | Gagan 2 |  | Sub Contractor
148 | 4/0 | DD45+0 | 86.2562 | 2025-04-06 | 2025-04-17 | Completed | Reeta Bharti |  | Sub Contractor
149 | 39/0 | DB+0 | 64.4817 | 2025-04-12 | 2025-04-19 | Completed | Ananya Traders-1 |  | Sub Contractor
150 | 8B/4 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-21 | Completed | Pinky Dewi |  | Sub Contractor
151 | 31/5 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-21 | Completed | ASC heights |  | Sub Contractor
152 | 33/0 | DC+6 | 87.0116 | 2025-04-12 | 2025-04-22 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
153 | 38/7 | DA-3 | 42.3742 | 2025-04-12 | 2025-04-22 | Completed | M K infra |  | Sub Contractor
154 | 36/6 | DA+0 | 43.7758 | 2025-02-12 18:37 | 2025-04-22 | Completed | Amar Singh |  | Sub Contractor
155 | 20/1 | DA+6 | 53.3239 | 2025-04-12 | 2025-04-22 | Completed | Gagan enterprise.1 |  | Sub Contractor
156 | 25/2 | DA+0 | 43.7758 | 2025-04-12 | 2025-04-23 | Completed | Rudra Construction |  | Sub Contractor
157 | 52/5 | DA-3 | 42.3742 | 2025-04-17 | 2025-04-25 | Completed | Ananya Traders-2 |  | Sub Contractor
158 | 0/4 | DA+9 | 55.3387 | 2025-04-12 | 2025-04-26 | Completed | Anand Construction |  | Sub Contractor
159 | 19/12 | DA-3 | 42.3742 | 2025-04-23 | 2025-04-26 | Completed | Gagan enterprise.1 |  | Sub Contractor
160 | 39/2 | DA-3 | 42.3742 | 2025-04-20 | 2025-04-26 | Completed | Ananya Traders-1 |  | Sub Contractor
161 | 36/7 | DA+3 | 46.0492 | 2025-04-23 | 2025-04-28 | Completed | Amar Singh |  | Sub Contractor
162 | 34/2 | DA+3 | 46.0492 | 2025-04-23 | 2025-04-28 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
163 | 10/0 | DB+9 | 78.6775 | 2025-04-17 | 2025-04-28 | Completed | Gagan enterprise.2 |  | Sub Contractor
164 | 30/6 | DA-3 | 42.3742 | 2025-04-22 | 2025-04-28 | Completed | ASC heights |  | Sub Contractor
165 | 52/4 | DA-3 | 42.3742 | 2025-04-26 | 2025-04-29 | Completed | Ananya Traders-2 |  | Sub Contractor
166 | 38/9 | DA-3 | 42.3742 | 2025-04-23 | 2025-04-29 | Completed | M K infra |  | Sub Contractor
167 | 8A/0 | DD60+0 | 97.2286 | 2025-04-22 | 2025-04-30 | Completed | Pinky Dewi |  | Sub Contractor
168 | 19/11 | DA-3 | 42.3742 | 2025-04-27 | 2025-04-30 | Completed | Gagan enterprise.1 |  | Sub Contractor
169 | 34/3 | DA+3 | 46.0492 | 2025-04-29 | 2025-05-03 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
170 | 39/4 | DA+3 | 46.0492 | 2025-04-27 | 2025-05-04 | Completed | Ananya Traders-1 |  | Sub Contractor
171 | 36/8 | DA-3 | 42.3742 | 2025-04-29 | 2025-05-05 | Completed | Amar Singh |  | Sub Contractor
172 | 52/3 | DA-3 | 42.3742 | 2025-05-02 | 2025-05-06 | Completed | Ananya Traders-2 |  | Sub Contractor
173 | 30/3 | DA+0 | 43.7758 | 2025-05-01 | 2025-05-06 | Completed | ASC heights |  | Sub Contractor
174 | 19/10 | DA+3 | 46.0492 | 2025-05-02 | 2025-05-06 | Completed | Gagan enterprise.1 |  | Sub Contractor
175 | 25/3 | DA+3 | 46.0492 | 2025-04-27 | 2025-05-07 | Completed | Rudra Construction |  | Sub Contractor
176 | 19/8 | DA-3 | 42.3742 | 2025-05-06 | 2025-05-09 | Completed | Gagan enterprise.1 |  | Sub Contractor
177 | 12/1 | DA-3 | 42.3742 | 2025-05-04 | 2025-05-10 | Completed | Gagan enterprise.2 |  | Sub Contractor
178 | 4/9 | DA-3 | 42.3742 | 2025-05-04 | 2025-05-11 | Completed | Reeta Bharti |  | Sub Contractor
179 | 39/5 | DA-3 | 42.3742 | 2025-05-05 | 2025-05-11 | Completed | Ananya Traders-1 |  | Sub Contractor
180 | 52/2 | DA+3 | 46.0492 | 2025-05-07 | 2025-05-12 | Completed | Ananya Traders-2 |  | Sub Contractor
181 | 30/1 | DA-3 | 42.3742 | 2025-05-07 | 2025-05-13 | Completed | ASC heights |  | Sub Contractor
182 | 36/4 | DA+0 | 43.7758 | 2025-05-07 | 2025-05-13 | Completed | Amar Singh |  | Sub Contractor
183 | 56/2 | DA+3 | 46.0492 | 2025-05-07 | 2025-05-14 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
184 | 8B/0 | DD60+0 | 97.2286 | 2025-05-05 | 2025-05-14 | Completed | Pinky Dewi |  | Sub Contractor
185 | 52/9 | DA-3 | 42.3742 | 2025-05-13 | 2025-05-15 | Completed | Ananya Traders-2 |  | Sub Contractor
186 | 17/8 | DA-3 | 42.3742 | 2025-05-11 | 2025-05-15 | Completed | Gagan enterprise.1 |  | Sub Contractor
187 | 38/11 | DA+3 | 46.0492 | 2025-05-12 | 2025-05-19 | Completed | Ananya Traders-1 |  | Sub Contractor
188 | 36/11 | DA-3 | 42.3742 | 2025-05-14 | 2025-05-19 | Completed | Amar Singh |  | Sub Contractor
189 | 56/1 | DA+0 | 43.7758 | 2025-05-14 | 2025-05-19 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
190 | 30/2 | DA-3 | 42.3742 | 2025-05-14 | 2025-05-20 | Completed | ASC heights |  | Sub Contractor
191 | 52/10 | DA+3 | 46.0492 | 2025-05-16 | 2025-05-21 | Completed | Ananya Traders-2 |  | Sub Contractor
192 | 2/1 | DA+3 | 46.0492 | 2025-05-12 | 2025-05-21 | Completed | Reeta Bharti |  | Sub Contractor
193 | 12/6 | DA-3 | 42.3742 | 2025-05-11 | 2025-05-22 | Completed | Gagan enterprise.2 |  | Sub Contractor
194 | 53/1 | DA+6 | 53.3239 | 2025-05-12 | 2025-05-22 | Completed | Amit Const |  | Sub Contractor
195 | 23/3 | DA-3 | 42.3742 | 2025-05-15 | 2025-05-22 | Completed | Pinky Dewi |  | Sub Contractor
196 | 38/10 | DA-3 | 42.3742 | 2025-05-13 | 2025-05-24 | Completed | Ananya Traders-1 |  | Sub Contractor
197 | 56/3 | DA-3 | 42.3742 | 2025-05-20 | 2025-05-24 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
198 | 36/9 | DA-3 | 42.3742 | 2025-05-20 | 2025-05-24 | Completed | Amar Singh |  | Sub Contractor
199 | 15/0 | DC+3 | 78.073 | 2025-05-16 | 2025-05-25 | Completed | Gagan enterprise.1 |  | Sub Contractor
200 | 23/5 | DA-3 | 42.3742 | 2025-05-10 | 2025-05-25 | Completed | Rudra Construction |  | Sub Contractor
201 | 0/2 | DA-3 | 42.3742 | 2025-05-22 | 2025-05-30 | Completed | Reeta Bharti |  | Sub Contractor
202 | 23/4 | DA-3 | 42.3742 | 2025-05-23 | 2025-05-28 | Completed | Pinky Dewi |  | Sub Contractor
203 | 56/4 | DA-3 | 42.3742 | 2025-05-24 | 2025-05-28 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
204 | 36/10 | DA-3 | 42.3742 | 2025-05-24 | 2025-05-31 | Completed | Amar Singh |  | Sub Contractor
205 | 12/8 | DA-3 | 42.3742 | 2025-05-25 | 2025-05-31 | Completed | Gagan enterprise.1 |  | Sub Contractor
206 | 52/8 | DA-3 | 42.3742 | 2025-05-22 | 2025-05-27 | Completed | Ananya Traders-2 |  | Sub Contractor
207 | 38/5 | DA+3 | 46.049 | 2025-05-28 | 2025-06-02 | Completed | Ananya Traders-1 | 30 | Sub Contractor
208 | 23/1 | DA+9 | 55.339 | 2025-05-28 | 2025-06-03 | Completed | Pinky Dewi | 31 | Sub Contractor
209 | 0/3 | DA-3 | 42.374 | 2025-05-25 | 2025-06-04 | Completed | Reeta Bharti | 25 | Sub Contractor
210 | 56/5 | DA-3 | 42.374 | 2025-05-30 | 2025-06-04 | Completed | Dewi Construction(Girendra) |  | Sub Contractor
211 | 51/0 | DD60+0 | 97.229 | 2025-05-27 | 2025-06-07 | Completed | Ananya Traders-2 | 42 | Sub Contractor
212 | 33/5 | DA+3 | 46.049 | 2025-06-03 | 2025-06-08 | Completed | Amar Singh | 34 | Sub Contractor
213 | 23/2 | DA+0 | 43.776 | 2025-06-04 | 2025-06-08 | Completed | Pinki Dewi | 30 | Sub Contractor
214 | 0/1 | DA-3 | 42.374 | 2025-06-05 | 2025-06-10 | Completed | Reeta Bharti | 24 | Sub Contractor
215 | 50/1 | DA+0 | 43.776 | 2025-06-08 | 2025-06-12 | Completed | Ananya Traders-2 | 42 | Sub Contractor
216 | 53A/5 | DA-3 | 42.374 | 2025-06-02 | 2025-06-12 | Completed | Devine | 20 | Sub Contractor
217 | 34/5 | DA+0 | 43.776 | 2025-06-09 | 2025-06-17 | Completed | Amar Singh | 24 | Sub Contractor
218 | 53A/2 | DA+3 | 46.049 | 2025-05-30 | 2025-06-17 | Completed | Amit Const | 21 | Sub Contractor
219 | 22/0 | DB+3 | 67.112 | 2025-06-09 | 2025-06-19 | Completed | Pinki Dewi | 25 | Sub Contractor
220 | 30/0 | DD60+18 | 143.462 | 2025-05-21 | 2025-06-21 | Completed | ASC heights | 25 | Sub Contractor
221 | 3/0 | DC+0 | 73.426 | 2025-06-05 | 2025-06-23 | Completed | Reeta Bharti | 21 | Sub Contractor
222 | 21/2 | DA+3 | 46.049 | 2025-06-20 | 2025-06-26 | Completed | Pinki Dewi | 25
223 | 45/1 | DA+3 | 46.049 | 2025-06-06 | 2025-06-26 | Completed | MK Infra | 18 | Sub Contractor
224 | 48/0 | DD45+9 | 104.867 | 2025-06-14 | 1935-06-28 | Completed | Ananya Traders-2 | 33 | Sub Contractor
225 | 53A/3 | DA-3 | 42.374 | 2025-06-20 | 1935-06-28 | Completed | Amit Const | 22 | Sub Contractor
226 | 21/1 | DA-3 | 42.374 | 1935-06-27 | 2025-06-29 | Completed | Pinki Dewi | 28 | Sub Contractor
227 | 40/0 | DD60+25 | 161.355 | 2025-06-03 | 2025-06-29 | Completed | Ananya Traders-1 | 32 | Sub Contractor
228 | 12/7 | DA-3 | 42.374 | 2025-06-24 | 2025-06-29 | Completed | Reeta Bharti | 22 | Sub Contractor
229 | 14/0 | DD60+30 | 188.378 | 2025-05-28 | 2025-06-30 | Completed | Gagan | 41 | Sub Contractor
230 | 28/1 | DA+3 | 46.049 | 2025-06-22 | 2025-07-05 | Completed | ASC heights | 25 | Sub Contractor
231 | 21/3 | DA+3 | 46.049 | 2025-07-02 | 2025-07-07 | Completed | Pinki Dewi | 28 | Sub Contractor
232 | 25/1 | DA+9 | 55.339 | 2025-07-02 | 2025-07-12 | Completed | Reeta Bharti | 23 | Sub Contractor
233 | 44/0 | DD60+3 | 101.692 | 2025-07-05 | 2025-07-18 | Completed | Ananya Traders-1 | 28 | Sub Contractor
234 | 56/0 | DD45+0 | 86.256 | 2025-06-20 | 2025-07-22 | Completed | Amar Singh | 22 | Sub Contractor
235 | 28/0 | DD60+0 | 97.23 | 2025-07-13 | 2025-07-31 | Completed | Reeta Bharti | 28 | Sub Contractor
236 | 41/0 | DD60+18 | 143.462 | 2025-07-19 | 2025-08-08 | Completed | Ananya Traders-1 | 32 | Sub Contractor
237 | 13/0 | DD60+30 | 188.378 | 2025-07-02 | 2025-08-11 | Completed | Gagan | 27 | Sub Contractor
238 | 53A/6 | DA+3 | 46.049 | 2025-07-28 | 2025-08-17 | Completed | Punam kumari | 30 | Sub Contractor
239 | 46/2 | DA+3 | 46.049 | 2025-08-14 | 2025-08-26 | Completed | kajal Const. | 27 | Sub Contractor
240 | 24/0 | DD60+25 | 161.355 | 2025-07-26 | 2025-08-27 | Completed | Kangresh -1 | 32 | Sub Contractor
241 | 1/0 | DC+3 | 78.073 | 2025-08-09 | 2025-08-30 | Completed | Radha Const. | 30 | Sub Contractor
242 | 18/0 | DB+6 | 75.85 | 2025-08-04 | 2025-08-30 | Completed | Sainik Ent. | 25 | Sub Contractor
243 | 65/0 | DD60+0 | 97.229 | 2025-08-02 | 2025-08-30 | Completed | Kangresh -2 | 30 | Sub Contractor
244 | 12/0 | DB+18 | 97.65 | 2025-08-12 | 2025-09-02 | Completed | Gagan | 30 | Sub Contractor
245 | 43/0 | DD60+18 | 118.43 | 2025-08-10 | 2025-09-07 | Completed | Ananya | 34 | Sub Contractor
246 | 54/1 | DA+9 | 55.339 | 2025-08-18 | 2025-09-04 | Completed | Punam kumari | 27 | Sub Contractor
247 | 47/0 | DC+9 | 90.125 | 2025-09-08 |  | 3rd section wip | Ananya | 34 | Sub Contractor
248 | 48/1 | DA-3 | 42.374 | 2025-08-18 |  | 1st section wip | MK Infra | 22 | Sub Contractor
249 | 53A/1 | DA+6 | 53.324 | 2025-08-18 |  | 2nd section wip | Spotify pvt ltd-2 | 20 | Sub Contractor
250 | 56/8 | DA-3 | 42.374 | 2025-08-18 |  | 3rd section wip | Spotify pvt ltd-3 | 24 | Sub Contractor
251 | 19/0 | DC+6 | 87.01 | 2025-08-31 |  | 3rd section Completed | Sainik Ent. | 25 | Sub Contractor
252 | 64/0 | DC+0 | 73.426 | 2025-08-31 |  | Bottom section wip | Kangresh -2 | 30 | Sub Contractor
253 | 2/0 | DD45+3 | 89.7 | 2025-08-31 |  | Cage 1 wip | Radha Const. | 33 | Sub Contractor
254 | 11/0 | DB+18 | 97.65 | 2025-08-24 | 2025-09-14 | Completed | Gouri shankar | 45 | Sub Contractor
255 | 23/0 | DC+18 |  | 2025-09-04 |  | 1st section Completed | Gagan | 34 | Sub Contractor
256 | 16/0 | DB+25 | 110.6 | 2025-08-16 | 2025-09-14 | Completed | Amit Const | 40 | Sub Contractor
257 | 25/0 | DD60+25 | 161.355 | 2025-08-28 |  | 3rd section wip | Kangresh -1 | 32 | Sub Contractor
258 | 29/0 | DD60+25 | 161.355 | 2025-08-06 |  | Cage 2 Completed | Reeta Bharti | 32 | Sub Contractor
259 | 52/0 | DC2+9 |  | 2025-09-08 |  | 3rd section wip | Punam kumari | 33 | Sub Contractor
260 | 17/0 | DB+6 |  | 2025-09-11 |  | leg joint Done | Maa Const. | 25 | Sub Contractor
Formulas:
Starting Date = [1]!'!Erection!R216C6:R219C7'

## VC
Visual Chart :- 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03
[8 empty] | Project Code : TA416 | [25 empty] | Dated: |  | 2025-09-26
[11 empty] | LEGEND: |  |  |  |  | OPGW Stringing | [7 empty] | Description of Item |  |  |  |  | Total Line Qty |  |  | Total Completed |  | WIP locations |  |  | Total Balance
|  |  |  | Stringing Comp | [12 empty] | Location No.
|  | Erection Comp | [16 empty] | Stringing WIP |  |  |  |  | Foundation |  |  |  |  | 302 |  |  | 302 |  | 0 |  |  | 0
[13 empty] | TW |  |  |  | Erection Comp | [6 empty] | Earthing |  |  |  |  | 302 |  |  | 302 |  |  |  |  | 0
|  | Foundation Comp | [7 empty] | C | B | SPAN |  | C | B | [8 empty] | Erection |  |  |  |  | 302 |  |  | 248 |  | 14 |  |  | 54
[10 empty] | D | A |  |  | D | A |  | Foundation Comp | [6 empty] | Tack Welding |  |  |  |  | 302 |  |  | 151 |  |  |  |  | 151
|  | Earthing Comp | [18 empty] | Holdup location |  |  | Stringing (Rough Sag) |  |  |  |  | 114.985 |  |  | 41.1222 |  | 3 |  |  | 73.8628
[24 empty] | Stringing (Final Sag) |  |  |  |  | 114.985 |  |  | 32.5639 |  |  |  |  | 82.4211
[5 empty] | Type of Tower |  |  |  |  | TREE CUTTING CLEARANCE
|  | NH/SH Xing |  |  |  | RAILWAY Xing | [6 empty] | 132/220/400/765 Kv CROSSING |  |  | RIVER X-ING |  |  |  | Gas pipeline
|  | OPGW DRUM-1 | [21 empty] | OPGW DRUM-2
[40 empty] | 115133.98 | 301
| 0/0 |  |  |  | 0/1 |  |  |  | 0/2 |  |  |  | 0/3 |  |  | 0/4 |  |  |  | 1/0 |  |  | 2/0 |  |  | 2/1 |  |  |  | 2/2 |  |  | 2/3 |  |  |  | 2/4
| C | B | 369 |  | C | B | 367 |  | C | B | 354 |  | C | B | 381 | C | B | 450.563 |  | C | B | 245.982 | C | B | 420 | C | B | 412 |  | C | B | 413 | C | B | 415 |  | C | B | 414 | 4241.545 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| TPT+0 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DC1+3 |  |  | DD45+3 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
[22 empty] | NH 509, Agra-Moradabad | [7 empty] | Hold
| OPGW DRUM-2 | [19 empty] | OPGW DRUM-3
| 2/5 |  |  |  | 2/6 |  |  |  | 2/7 |  |  |  | 2/8 |  |  | 3/0 |  |  |  | 4/0 |  |  | 4/1 |  |  | 4/2 |  |  |  | 4/3 |  |  | 4/4 |  |  |  | 4/5
| C | B | 410 |  | C | B | 378 |  | C | B | 420 |  | C | B | 401.695 | C | B | 279.997 |  | C | B | 383.064 | C | B | 400.004 | C | B | 397.002 |  | C | B | 414 | C | B | 415 |  | C | B | 411 | 4309.762 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DC2+0 |  |  |  | DD45+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
[17 empty] | 220 KV SC Moradabad - Narora TL | [5 empty] | 2M RC in C&D Leg
132 KV DC LINE DISMANTLED
OPGW DRUM-3 | [20 empty] | OPGW DRUM-4
| 4/6 |  |  |  | 4/7 |  |  |  | 4/8 |  |  |  | 4/9 |  |  | 4/10 |  |  |  | 5/0 |  |  | 5/1 |  |  | 6/0 |  |  |  | 6/1 |  |  | 6/2 |  |  |  | 7/0
| C | B | 416 |  | C | B | 409.231 |  | C | B | 378.001 |  | C | B | 391 | C | B | 401.443 |  | C | B | 321 | C | B | 402.569 | C | B | 408 |  | C | B | 419 | C | B | 407.275 |  | C | B | 414 | 4367.519 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DB1+0 |  |  | DA+3 |  |  | DB1+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DB2+0
| OPGW DRUM-4 | [19 empty] | OPGW DRUM-5
| 7/1 |  |  |  | 7/2 |  |  |  | 7/3 |  |  |  | 7/4 |  |  | 7/5 |  |  |  | 7/6 |  |  | 7/7 |  |  | 7/8 |  |  |  | 7/9 |  |  | 7/10 |  |  |  | 7/11
| C | B | 419 |  | C | B | 361.097 |  | C | B | 361 |  | C | B | 404 | C | B | 424 |  | C | B | 406 | C | B | 410 | C | B | 423 |  | C | B | 409 | C | B | 425 |  | C | B | 362.65 | 4404.747 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
| OPGW DRUM-5 | [22 empty] | OPGW DRUM-6
| 8/0 |  |  |  | 8/1 |  |  |  | 8/2 |  |  |  | 8/3 |  |  | 8/4 |  |  |  | 8A/0 |  |  | 8B/0 |  |  | 8B/1 |  |  |  | 8B/2 |  |  | 8B/3 |  |  |  | 8B/4
| C | B | 416 |  | C | B | 400 |  | C | B | 367 |  | C | B | 420 | C | B | 413.716 |  | C | B | 223.61 | C | B | 341 | C | B | 332 |  | C | B | 292.526 | C | B | 426.186 |  | C | B | 373 | 4005.038 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DB2+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DD60+0 |  |  | DD60+0 |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+6
GAIL GAS PIPE LINE
OPGW DRUM-6 | [20 empty] | OPGW DRUM-7
| 8B/5 |  |  |  | 9/0 |  |  |  | 10/0 |  |  |  | 10/1 |  |  | 11/0 |  |  |  | 12/0 |  |  | 12/1 |  |  | 12/2 |  |  |  | 12/3 |  |  | 12/4 |  |  |  | 12/5
| C | B | 461.51 |  | C | B | 283.431 |  | C | B | 426 |  | C | B | 396.092 | C | B | 312.879 |  | C | B | 418.999 | C | B | 370.199 | C | B | 424.996 |  | C | B | 404 | C | B | 428 |  | C | B | 395 | 4321.106 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+6 |  |  |  | DB2+6 |  |  |  | DB1+9 |  |  |  | DA-3 |  |  | DB1+18 |  |  |  | DB2+18 |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[6 empty] | 132 Kv S/C Sambhal-Babrala | [10 empty] | 132 KV D/C CKT-I Sambhal-Babrala
& CKT-II Sambhsal-Bisauli Line
OPGW DRUM-7 | [20 empty] | OPGW DRUM-8
| 12/6 |  |  |  | 12/7 |  |  |  | 12/8 |  |  |  | 12/9 |  |  | 13/0 |  |  |  | 14/0 |  |  | 14/1 |  |  | 14/2 |  |  |  | 14/3 |  |  | 14/4 |  |  |  | 14/5
| C | B | 318 |  | C | B | 357 |  | C | B | 385 |  | C | B | 418.776 | C | B | 319.133 |  | C | B | 436 | C | B | 395 | C | B | 306 |  | C | B | 412 | C | B | 414 |  | C | B | 420 | 4180.909 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  | DD60+30 |  |  |  | DD60+30 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
400 KV D/C Sambhal - Budaun Line
OPGW DRUM-8 | [20 empty] | OPGW DRUM-9
| 14/6 |  |  |  | 14/7 |  |  |  | 14/8 |  |  |  | 15/0 |  |  | 16/0 |  |  |  | 17/0 |  |  | 17/1 |  |  | 17/2 |  |  |  | 17/3 |  |  | 17/4 |  |  |  | 17/5
| C | B | 410 |  | C | B | 410 |  | C | B | 407.995 |  | C | B | 464.742 | C | B | 264.687 |  | C | B | 400 | C | B | 310 | C | B | 361.497 |  | C | B | 366.002 | C | B | 436.999 |  | C | B | 389.999 | 4221.921 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC2+3 |  |  | DB2+25 |  |  |  | DB2+6 |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | SH-51, Islamnagr- Bhajoi Road |  | 132 KV D/C Sahaswan-Chandausi
CGD INFRA GA LINE
OPGW DRUM-9 | [16 empty] | OPGW DRUM-10
| 17/6 |  |  |  | 17/7 |  |  |  | 17/8 |  |  |  | 18/0 |  |  | 19/0 |  |  |  | 19/1 |  |  | 19/2 |  |  | 19/3 |  |  |  | 19/4 |  |  | 19/5 |  |  |  | 19/6
| C | B | 400.999 |  | C | B | 391.999 |  | C | B | 374.07 |  | C | B | 323.03 | C | B | 343.13 |  | C | B | 392 | C | B | 407 | C | B | 412 |  | C | B | 371 | C | B | 376 |  | C | B | 421 | 4212.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DB1+6 |  |  | DC2+6 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA-3 |  |  |  | DA+0
Ganga Express-way
OPGW DRUM-10 | [23 empty] | OPGW DRUM-11
| 19/7 |  |  |  | 19/8 |  |  |  | 19/9 |  |  |  | 19/10 |  |  | 19/11 |  |  |  | 19/12 |  |  | 20/0 |  |  | 20/1 |  |  |  | 20/2 |  |  | 20/3 |  |  |  | 20/4
| C | B | 387 |  | C | B | 364 |  | C | B | 423 |  | C | B | 335 | C | B | 343 |  | C | B | 362.453 | C | B | 433 | C | B | 393 |  | C | B | 400 | C | B | 375.659 |  | C | B | 366.466 | 4182.578 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DB1+0 |  |  | DA+6 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA-3
OPGW DRUM-11 | [30 empty] | OPGW DRUM-12
| 20/5 |  |  |  | 20/6 |  |  |  | 20/7 |  |  |  | 20/8 |  |  | 20/9 |  |  |  | 20/10 |  |  | 20/11 |  |  | 20/12 |  |  |  | 21/0 |  |  | 21/1 |  |  |  | 21/2
| C | B | 408 |  | C | B | 372 |  | C | B | 370 |  | C | B | 400 | C | B | 426 |  | C | B | 399 | C | B | 358 | C | B | 256.857 |  | C | B | 388 | C | B | 391 |  | C | B | 394 | 4162.857 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  | DA-3 |  |  |  | DB1+0 |  |  | DA-3 |  |  |  | DA+3
GAIL GAS PIPE LINE
OPGW DRUM-12 | [37 empty] | OPGW DRUM-13
| 21/3 |  |  |  | 22/0 |  |  |  | 22A/0 |  |  |  | 23/0 |  |  | 23/1 |  |  |  | 23/2 |  |  | 23/3 |  |  | 23/4 |  |  |  | 23/5 |  |  | 24/0 |  |  |  | 25/0
| C | B | 432.898 |  | C | B | 190.948 |  | C | B | 267.423 |  | C | B | 371 | C | B | 438.912 |  | C | B | 340.132 | C | B | 283.996 | C | B | 323 |  | C | B | 470.227 | C | B | 231.533 |  | C | B | 386 | 3736.069 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DB2+3 |  |  |  | DB1+25 |  |  |  | DC2+18 |  |  | DA+9 |  |  |  | DA+0 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DD60+25 |  |  |  | DD60+25
|  | SH-43, |  |  |  |  | 132 Kv S/C Budaun-Chandausi Dead line | [26 empty] | 765 KV S/C Ghatampur-Hapur
Chandausi - Badaun Road | [6 empty] | 132 Kv S/C Bisauli To Chandausi
OPGW DRUM-13 | [30 empty] | OPGW DRUM-14
| 25/1 |  |  |  | 25/2 |  |  |  | 25/3 |  |  |  | 26/0 |  |  | 27/0 |  |  |  | 28/0 |  |  | 28/1 |  |  | 29/0 |  |  |  | 30/0 |  |  | 30/1 |  |  |  | 30/2
| C | B | 446 |  | C | B | 368 |  | C | B | 466.431 |  | C | B | 440.836 | C | B | 299.473 |  | C | B | 233 | C | B | 454.669 | C | B | 270.08 |  | C | B | 435 | C | B | 347 |  | C | B | 396 | 4156.489 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+9 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DB2+9 |  |  | DD60+3 |  |  |  | DD60+0 |  |  | DA+3 |  |  | DD60+25 |  |  |  | DD60+18 |  |  | DA-3 |  |  |  | DA-3
[19 empty] | Rly Crossing Single track, Chandausi-Bareilly | [8 empty] | 765 Kv S/c Ghatampur-Rampur
OPGW DRUM-14 | [16 empty] | OPGW DRUM-15
| 30/3 |  |  |  | 30/4 |  |  |  | 30/5 |  |  |  | 30/6 |  |  | 31/0 |  |  |  | 31/1 |  |  | 31/2 |  |  | 31/3 |  |  |  | 31/4 |  |  | 31/5 |  |  |  | 31/6
| C | B | 410 |  | C | B | 424 |  | C | B | 373 |  | C | B | 365.461 | C | B | 376 |  | C | B | 403 | C | B | 399 | C | B | 404 |  | C | B | 358 | C | B | 363 |  | C | B | 407 | 4282.461 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-15 | [20 empty] | OPGW DRUM-16
| 31/7 |  |  |  | 31/8 |  |  |  | 31/9 |  |  |  | 31/10 |  |  | 32/0 |  |  |  | 33/0 |  |  | 33/1 |  |  | 33/2 |  |  |  | 33/3 |  |  | 33/4 |  |  |  | 33/5
| C | B | 384 |  | C | B | 386 |  | C | B | 394 |  | C | B | 409.666 | C | B | 407.17 |  | C | B | 365 | C | B | 365 | C | B | 406 |  | C | B | 389 | C | B | 395 |  | C | B | 430 | 4330.836 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DC1+6 |  |  |  | DC2+6 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-16 | [23 empty] | OPGW DRUM-17
| 33/6 |  |  |  | 33/7 |  |  |  | 33/8 |  |  |  | 33/9 |  |  | 33/10 |  |  |  | 33/11 |  |  | 34/0 |  |  | 34/1 |  |  |  | 34/2 |  |  | 34/3 |  |  |  | 34/4
| C | B | 394 |  | C | B | 439.95 |  | C | B | 355.05 |  | C | B | 410 | C | B | 410 |  | C | B | 421.496 | C | B | 418 | C | B | 378 |  | C | B | 417 | C | B | 395 |  | C | B | 364 | 4402.496 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DB1+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-17 | [13 empty] | OPGW DRUM-18
| 34/5 |  |  |  | 34/6 |  |  |  | 34/7 |  |  |  | 35/0 |  |  | 35/1 |  |  |  | 35/2 |  |  | 35/3 |  |  | 35/4 |  |  |  | 35/5 |  |  | 35/6 |  |  |  | 35/7
| C | B | 397 |  | C | B | 419 |  | C | B | 405.228 |  | C | B | 383 | C | B | 397 |  | C | B | 345 | C | B | 389 | C | B | 416 |  | C | B | 414 | C | B | 415 |  | C | B | 404 | 4384.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
SH-125
Shahabad-Aonla Road
OPGW DRUM-18 | [9 empty] | OPGW DRUM-19
| 35/8 |  |  |  | 35/9 |  |  |  | 36/0 |  |  |  | 36/1 |  |  | 36/2 |  |  |  | 36/3 |  |  | 36/4 |  |  | 36/5 |  |  |  | 36/6 |  |  | 36/7 |  |  |  | 36/8
| C | B | 373 |  | C | B | 421.049 |  | C | B | 401 |  | C | B | 412 | C | B | 415 |  | C | B | 411 | C | B | 395 | C | B | 402 |  | C | B | 432 | C | B | 392.011 |  | C | B | 352.989 | 4407.049 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DB2+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-19 | [16 empty] | OPGW DRUM-20
| 36/9 |  |  |  | 36/10 |  |  |  | 36/11 |  |  |  | 36/12 |  |  | 37/0 |  |  |  | 38/0 |  |  | 38/1 |  |  | 38/2 |  |  |  | 38/3 |  |  | 38/4 |  |  |  | 38/5
| C | B | 361 |  | C | B | 302 |  | C | B | 310 |  | C | B | 361.31 | C | B | 475.951 |  | C | B | 399 | C | B | 426 | C | B | 408 |  | C | B | 419 | C | B | 415 |  | C | B | 415.118 | 4292.379 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DC2+18 |  |  |  | DC2+18 |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | 5 Mtr Depth |  |  |  |  | 5 Mtr Depth
Ramganga River Crossing
OPGW DRUM-20 | [20 empty] | OPGW DRUM-21
| 38/6 |  |  |  | 38/7 |  |  |  | 38/8 |  |  |  | 38/9 |  |  | 38/10 |  |  |  | 38/11 |  |  | 39/0 |  |  | 39/1 |  |  |  | 39/2 |  |  | 39/3 |  |  |  | 39/4
| C | B | 400 |  | C | B | 408.002 |  | C | B | 393 |  | C | B | 353 | C | B | 383 |  | C | B | 403.723 | C | B | 398 | C | B | 402 |  | C | B | 393.003 | C | B | 436.597 |  | C | B | 376.011 | 4346.336 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DB2+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3
OPGW DRUM-21 | [23 empty] | OPGW DRUM-22
| 39/5 |  |  |  | 39/6 |  |  |  | 39/7 |  |  |  | 39/8 |  |  | 39/9 |  |  |  | 39/10 |  |  | 40/0 |  |  | 41/0 |  |  |  | 41/1 |  |  | 41/2 |  |  |  | 42/0
| C | B | 374.389 |  | C | B | 420.398 |  | C | B | 414.002 |  | C | B | 416.001 | C | B | 408.002 |  | C | B | 422.124 | C | B | 239.302 | C | B | 425 |  | C | B | 370 | C | B | 346.556 |  | C | B | 309.23 | 4145.004 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DD60+25 |  |  | DD60+18 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DD60+18
[23 empty] | 2 M RC |  |  | 2 M RC | [10 empty] | 220 KV S/C Rampur-CB Ganj
[23 empty] | 400 Kv D/C Bareilly-Meerut | [13 empty] | 400 KV S/C Bareilly-Moradabad
OPGW DRUM-22 | [33 empty] | OPGW DRUM-23
| 43/0 |  |  |  | 44/0 |  |  |  | 45/0 |  |  |  | 45/1 |  |  | 45/2 |  |  |  | 45/3 |  |  | 46/0 |  |  | 46/1 |  |  |  | 46/2 |  |  | 47/0 |  |  |  | 48/0
| C | B | 459.669 |  | C | B | 300.001 |  | C | B | 331 |  | C | B | 422 | C | B | 395 |  | C | B | 309.881 | C | B | 331 | C | B | 421 |  | C | B | 403.606 | C | B | 358.626 |  | C | B | 388 | 4119.783 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD60+9 |  |  |  | DD60+3 |  |  |  | DD60+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3 |  |  | DB2+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DC2+9 |  |  |  | DD45+9
| 2 M RC |  |  |  |  | NH-530, RAILWAY TRACK, | [27 empty] | 132 KV S/c CB Ganj-Meerganj
OPGW DRUM-23 | [23 empty] | OPGW DRUM-24
| 48/1 |  |  |  | 49/0 |  |  |  | 50/0 |  |  |  | 50/1 |  |  | 51/0 |  |  |  | 52/0 |  |  | 52/1 |  |  | 52/2 |  |  |  | 52/3 |  |  | 52/4 |  |  |  | 52/5
| C | B | 387.943 |  | C | B | 372.026 |  | C | B | 435 |  | C | B | 242.996 | C | B | 238.926 |  | C | B | 461 | C | B | 421 | C | B | 375 |  | C | B | 346 | C | B | 348 |  | C | B | 357 | 3984.891 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DC2+9 |  |  |  | DC1+18 |  |  |  | DA+0 |  |  | DD60+0 |  |  |  | DC2+9 |  |  | DB1+6 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3
[5 empty] | 132 KV D/C CB Ganj-Meerganj | [10 empty] | 132 KV D/C CB-GANJ - MEERGANJ T/L
OPGW DRUM-24 | [20 empty] | OPGW DRUM-25
| 52/6 |  |  |  | 52/7 |  |  |  | 52/8 |  |  |  | 52/9 |  |  | 52/10 |  |  |  | 53/0 |  |  | 53/1 |  |  | 53A/0 |  |  |  | 53A/1 |  |  | 53A/2 |  |  |  | 53A/3
| C | B | 439 |  | C | B | 378 |  | C | B | 349 |  | C | B | 392 | C | B | 409.43 |  | C | B | 428 | C | B | 403.778 | C | B | 370 |  | C | B | 441 | C | B | 375 |  | C | B | 399 | 4384.208 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+6 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+6 |  |  | DB2+0 |  |  |  | DA+6 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-25 | [16 empty] | OPGW DRUM-26
| 53A/4 |  |  |  | 53A/5 |  |  |  | 53A/6 |  |  |  | 53A/7 |  |  | 54/0 |  |  |  | 54/1 |  |  | 54/2 |  |  | 55/0 |  |  |  | 55/1 |  |  | 56/0 |  |  |  | 56/1
| C | B | 391 |  | C | B | 392 |  | C | B | 412 |  | C | B | 385.995 | C | B | 460 |  | C | B | 360 | C | B | 366.157 | C | B | 300 |  | C | B | 307.205 | C | B | 336 |  | C | B | 409 | 4119.357 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DB1+3 |  |  |  | DA+9 |  |  | DA-3 |  |  | DC1+0 |  |  |  | DA-3 |  |  | DD45+0 |  |  |  | DA+0
OPGW DRUM-26 | [16 empty] | OPGW DRUM-27
| 56/2 |  |  |  | 56/3 |  |  |  | 56/4 |  |  |  | 56/5 |  |  | 56/6 |  |  |  | 56/7 |  |  | 56/8 |  |  | 57/0 |  |  |  | 57/1 |  |  | 58/0 |  |  |  | 59/0
| C | B | 374 |  | C | B | 351 |  | C | B | 345 |  | C | B | 380.058 | C | B | 422 |  | C | B | 387.54 | C | B | 369 | C | B | 291 |  | C | B | 386.28 | C | B | 281.561 |  | C | B | 418.001 | 4005.44 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+6 |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA-3 |  |  | DD60+18 |  |  |  | DD60+6
400 KV S/C BAREILLY - RAMPUR T/L
OPGW DRUM-27 | [16 empty] | OPGW DRUM-28
| 60/0 |  |  |  | 61/0 |  |  |  | 62/0 |  |  |  | 63/0 |  |  | 64/0 |  |  |  | 64/1 |  |  | 64/2 |  |  | 64/3 |  |  |  | 65/0 |  |  | 66/0 |  |  |  | 66/1
| C | B | 467.857 |  | C | B | 478.067 |  | C | B | 349.189 |  | C | B | 285.978 | C | B | 395 |  | C | B | 384 | C | B | 409 | C | B | 363.017 |  | C | B | 298.042 | C | B | 387 |  | C | B | 425.359 | 4242.509 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD45+6 |  |  |  | DD60+30 |  |  |  | DC1+25 |  |  |  | DC1+3 |  |  | DC1+0 |  |  |  | DA+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | DA+0
[9 empty] | 220 KV S/C BAIKUNTHAPUR - PANTNAGAR T/L |  | 132 KV S/C DOHNA - RICHHA T/L | [21 empty] | 1M RC in C&D Leg
OPGW DRUM-28 | [30 empty] | SH-37, ELECTRIFIED, SINGLE RAILWAY TRACK
Bareilly
| 67/0 |  |  |  | 68/0 |  |  |  | 69/0 |  |  |  | 69A/0 |  |  | 70/0 |  |  |  | Gantry
| C | B | 318.405 |  | C | B | 303.77 |  | C | B | 232.6 |  | C | B | 202.46 | C | B | 127 | [21 empty] | 1184.235 | 4
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A
| DD60+30 |  |  |  | DD60+30 |  |  |  | DC2+0 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | Gantry
400 KV D/c Bareilly-Kasipur
TW