## ANTL - KEC
KEC INTERNATIONAL LIMITED | [18 empty] | 2025-08-18
Name of Client: Power Grid Corporation of India Limited
Name of Line: 765 kV D/C Ahmedabad - Navsari Transmission Lines (Pkg 02)
NOA Ref. No.: CC/T/W/-TW/DOM/A00/23/01149/NOA-2/23-100346/02, Dt.23.03.23
Sr No. | Activity | Estimated Quantity |  |  | Cumm. Progress up to till last Month (Jul'25) |  |  | Target as per L2 Schedule Cummulative (upto Aug'25) | Plan for the month (Aug'25) |  |  | Today's Progress | Progress in this month |  | Cumm. Progress till date | Cumm. Balance ANTL (Part-1 & 2) | WIP | No of Gangs | Remark
|  | ANTL Part 01 Vadodara | ANTL Part 02 Navsari | Total Quantity | ANTL Part 01 Vadodara | ANTL Part 02 Navsari | Total Quantity |  | ANTL Part 01 Vadodara | ANTL Part 02 Navsari | Total |  | Approved ANTL Part 01 Vadodara | Approved ANTL Part 02 Navsari
1 | Route Alignment (Km) | 70.495 | 106.855 | 177.35 | 70.495 | 106.855 | 177.35 | 177.35 | 0 | 0 | 0 |  |  |  | 177.35 | 0 | 0 | 0 | Completed
2 | Detailed Survey (Km) | 70.495 | 106.855 | 177.35 | 70.495 | 106.855 | 177.35 | 177.35 | 0 | 0 | 0 |  |  |  | 177.35 | 0 | 0 | 0 | Completed
3 | Profiling (Km) | 70.495 | 106.855 | 177.35 | 70.495 | 106.855 | 177.35 | 177.35 | 0 | 0 | 0 |  |  |  | 177.35 | 0 | 0 | 0 | Completed
4 | Check Survey (Km) | 70.495 | 106.855 | 177.35 | 70.495 | 106.855 | 177.35 | 177.35 | 0 | 0 | 0 |  |  |  | 177.35 | 0 | 0 | 0 | Completed
5 | Soil Investigation (Nos.) | 11 | 18 | 29 | 11 | 18 | 29 | 29 | 0 | 0 | 0 |  |  |  | 29 | 0 | 0 | 0 | Completed
6 | Excavation | [13 empty] | 0
7 | Foundation (Nos.) | 186 | 298 | 484 | 185 | 292 | 477 | 484 | 0 | 1 | 1 |  |  |  | 477 | 7 | 3 | 1 | WIP-166/0
8 | Earthing (Nos.) | 186 | 298 | 484 | 185 | 292 | 477 | 484 | 0 | 1 | 1 |  |  |  | 477 | 7
9 | Tower Erection (Nos) | 186 | 298 | 484 | 180 | 191 | 371 | 484 | 4 | 4 | 8 |  | 2 |  | 373 | 111 | 5 | 5 | 1.05 loc. In WIP.
10 | Tack Welding | 186 | 298 | 484 | 180 | 130 | 310 | 484 | 4 | 30 | 34 |  |  |  | 310 | 174 |  | 1
11 | Stringing (Km) | 70.495 | 106.855 | 177.35 | 67.443 | 30.38 | 97.823 | 177.35 | 2.866 | 0 | 2.866 |  |  |  | 97.823 | 79.527 | 0 | 1 | 147/2-147A/0 spacering work u/p.
a) | Paying Out | 70.495 | 106.855 | 177.35 | 67.442 | 30.381 | 97.823 | 177.35 | 2.866 | 0 | 2.866 |  |  |  | 97.823 | 79.527 | 0
b) | Final Sag | 70.495 | 106.855 | 177.35 | 67.443 | 30.38 | 97.823 | 177.35 | 2.866 | 0 | 2.866 |  |  |  | 97.823 | 79.527 | 0
12 | OPGW (Km) | 70.495 | 106.855 | 177.35 | 61.106 | 4.836 | 65.942 | 177.35 | 4.702 | 0 | 4.702 |  |  |  | 65.942 | 111.408 | 0 | 1

## DPR Sheet
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : SUBMISSION STATUS AS ON |  |  |  |  | 2025-08-18
Name of the Project: |  | 765 kV D/C Ahmedabad - Navsari Transmission Line (Pkg-02)
Contract No. & Date : |  | CC/T/W/-TW/DOM/A00/23/01149/NOA-2/23-100346/02, Dt.23.03.23
ROUTE ALIGNMENT PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
177.35 | 177.35 | 0 | 177.35 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
29 | 29 | 0 | 29 | 0
DETAILED SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
177.35 | 177.35 | 0 | 177.35 | 0
CHECK SURVEY PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
177.35 | 177.35 | 0 | 177.35 | 0
FOUNDATION PROGRESS SUMMARY
TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
484 | 477 | 0 | 477 | 7
EARTHING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
484 | 477 | 0 | 477 | 7
TOWER ERECTION PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
484 | 371 | 2 | 373 | 111
STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY(KM)
177.35 | 97.823 | 0 | 97.823 | 79.527
OPGW STRINGING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
177.35 | 65.942 | 0 | 65.942 | 111.408
TACK WELDING PROGRESS SUMMARY
TOTAL QTY | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
484 | 310 | 0 | 310 | 174

## Soil Inv.
ANTL PROJECT - SOIL INVESTIGATION LOCATIONS
Sl. No. | Loc. No. | Work Portion | Status | Classification | Approval Letter Status | Drawing Status
1 | AP101 | Vadodara | Completed
2 | AP102 | Vadodara | Completed
3 | AP103 | Vadodara | Completed
4 | AP104 | Vadodara | Completed
5 | AP105 | Vadodara | Completed
6 | AP120 | Vadodara | Completed
7 | AP129 | Vadodara | Completed
8 | AP134 | Vadodara | Completed
9 | AP136 | Vadodara | Completed
10 | AP141 | Vadodara | Completed
11 | AP146 | Vadodara | Completed
12 | 154/1 | Navsari | Completed | Sandy Wet | Received
13 | AP154 | Navsari | Completed | Sandy Wet
14 | AP157 | Navsari | Completed | BC | Received | Avail.
15 | AP162 | Navsari | Completed | BC | Received | Avail.
16 | AP167 | Navsari | Completed | BC | Received | Avail.
17 | AP179 | Navsari | Completed | BC | Received | Avail.
18 | AP185 | Navsari | Completed | BC | Received | Avail.
19 | AP196 | Navsari | Completed | BC | Received | Avail.
20 | AP203 | Navsari | Completed | BC | Received
21 | AP213 | Navsari | Completed | BC | Received
22 | AP229 | Navsari | Completed | WBC | Received | Avail.
23 | AP241 | Navsari | Completed | BC | Received
24 | AP244 | Navsari | Completed | BC | Received
25 | AP249 | Navsari | Completed
26 | AP252 | Navsari | Completed
27 | AP260 | Navsari | Completed | BC | Received | Avail.
28 | AP270 | Navsari | Completed
29 | AP274 | Navsari | Completed

## FDN-Compile
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Start Date | Todays Status | End Date | Remarks | Sub-Contractor Name
1 | 101/0 | DD60+35(6M RC) | FS |  | 440.345 | 2025-01-01 | Completed. | 2025-02-02 |  | Rawat Construction
1
2 | 102/0 | DD45+35(11.84M RC) | Pile |  |  | 2025-03-06 | Completed. | 2025-06-28 |  | AK Construction
2
3 | 103/0 |  | Pile |  |  |  | U/P.
3
4 | 104/0 | DD60+35 | Pile |  | 861.11 | 2024-11-17 | Completed. | 2025-02-28 |  | Jai Mata Di
4
5 | 105/0 | DD60+35 | Pile Foundation |  | 861.114 | 2024-11-25 | Completed. | 2025-01-17 |  | Jai Mata Di
5
6 | 106/0 | DD60+9 | Wet Paddy |  | 180.61 | 2024-05-21 | Completed | 2024-07-15 |  | JMD
6
7 | 106A/0 | DC2+0 | PS |  | 168.913 | 2024-11-18 | Completed. | 2024-12-18 |  | Rawat Construction
7
8 | 106A/1 | DA+6 | PS | 1215596 | 83.812 | 2024-11-23 | Completed. | 2024-12-10 |  | Rawat Construction
8
9 | 106A/2 | DA-3 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | 2024-12-05 |  | Verma
9
10 | 106A/3 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-19 | Completed | 2024-06-10
10
11 | 106A/4 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-05-06 | Completed | 2024-05-16
11
12 | 106B/0 | DB2+9 | WET PADDY | 2143792.36 | 65.135 | 2024-04-24 | Completed | 2024-06-06
12
13 | 106B/1 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-04-18 | Completed | 2024-04-26
13
14 | 106B/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-05-15 | Completed | 2024-05-24
14
15 | 107/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-03-31 | Completed | 2024-04-17
15
16 | 107/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed | 2024-04-01
16
17 | 108/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-08-14 | Completed. | 2024-09-20 |  | Prince
17
18 | 109/0 | DB2+0 | Wet Paddy | 1196479 | 62.882 | 2024-07-02 | Completed | 2024-07-14 |  | Integar
18
19 | 110/0 | DB2+0 | WET PADDY | 1196479 | 62.882 | 2024-07-16 | Completed | 2024-07-31 |  | Jyoti Construction (Departmental Gang)
19
20 | 111/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-08-03 | Completed. | 2024-08-21 |  | Jyoti Construction (Departmental Gang)
20
21 | 112/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-01-18 | Completed | 2024-02-10
21
22 | 113/0 | DD60+0 | WET PADDY |  | 178.19 | 2024-02-08 | Completed | 2024-05-09
22
23 | 114/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-31 | Completed. | 2024-08-13 |  | Prince
23
24 | 115/0 | DC2+25 | Wet Paddy |  | 103.703 | 2024-07-08 | Completed | 2024-07-31 |  | Prince
24
25 | 116/0 | DD45+18 | WET PADDY |  | 151.172 | 2024-07-17 | Completed. | 2024-08-17 |  | B K Traders
25
26 | 116A/0 | DC1+0 | Wet Paddy |  | 79.994 | 2024-07-08 | Completed | 2024-07-17 |  | B K Traders
26
27 | 116A/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | 2024-11-23
27
28 | 116B/0 | DD45+6 | WET PADDY |  | 131.047 | 2024-08-18 | Completed. | 2024-09-20 | No work due to approach road damaged badly. | B K Traders
28
29 | 117/0 | DD60+3 | WET PADDY |  | 180.61 | 2024-07-16 | Completed | 2024-07-31 |  | Alamin Construction
29
30 | 118/0 | DD45+0 | Wet Paddy |  | 128.427 | 2024-07-09 | Completed | 2024-07-17 |  | Alamin Construction
30
31 | 119/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-10 | Completed. | 2024-08-14 |  | Jeet Infra (Departmental Gang)
31
32 | 119/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-06-04 | Completed | 2024-06-08
32
33 | 119/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-08 | Completed | 2024-06-15
33
34 | 119/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-29 | Completed | 2024-06-03
34
35 | 120/0 | DD60+9 | WET PADDY |  | 180.61 | 2024-08-17 | Completed | 2024-09-15 | Work hampered due to rain | Jeet Infra (Departmental Gang)
35
36 | 121/0 | DD60+18 | WET PADDY |  | 201.075 | 2024-06-15 | Completed | 2024-07-18 |  | H K Construction
36
37 | 122/0 | DC1+6 | WET PADDY |  | 82.223 | 2024-08-22 | Completed. | 2024-09-22 |  | Haaji Saheb
37
38 | 123/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-03 | Completed. | 2024-08-11 |  | Alamin Construction
38
39 | 123/1 | DA+3 | WPS | 623377 | 40.36 | 2024-09-20 | Completed. | 2024-10-05 |  | Prince
39
40 | 124/0 | DC1+3 | WPS |  | 82.223 | 2024-09-20 | Completed | 2024-10-06 |  | B K Traders
40
41 | 124A/0 | DD60+0 | WPS |  | 178.19 | 2024-11-07 | Completed. | 2024-11-14 |  | Alamin
41
42 | 124A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-08-16 | Completed. | 2024-08-18 |  | Alamin Construction
42
43 | 125/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-21 | Completed. | 2024-11-07 |  | Alamin Construction
43
44 | 125A/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-09-12 | Completed | 2024-10-19 |  | Jyoti Construction (Departmental Gang)
44
45 | 126/0 | DC2+0 | WET PADDY |  | 92.292 | 2023-12-23 | Completed | 2024-01-15
45
46 | 126/1 | DA+6 | WPS | 623377 | 40.63 | 2024-09-24 | Completed | 2024-10-11 |  | Hajji Saheb
46
47 | 127/0 | DD45+0 | WET PADDY |  | 128.427 | 2023-11-11 | Completed | 2023-12-13
47
48 | 127/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-18 | Completed | 2023-08-29
48
49 | 127/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed | 2023-09-14
49
50 | 127/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed | 2023-11-02
50
51 | 127/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-10-16 | Completed | 2023-10-29
51
52 | 127/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-12-19 | Completed | 2024-01-04
52
53 | 128/0 | DD60+6 | WPS |  | 180.61 | 2024-09-24 | Completed | 2024-10-22 |  | Alamin Construction
53
54 | 129/0 | DD60+6 | WPS |  | 180.61 | 2024-10-07 | Completed. | 2024-11-12 | No work due to approach road issues. | Prince Construction
54
55 | 129A/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-01-31 | Completed | 2024-02-15
55
56 | 129A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-07 | Completed | 2024-02-02
56
57 | 129A/2 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-13 | Completed | 2024-02-24
57
58 | 130/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2024-01-12 | Completed | 2024-01-30
58
59 | 130/1 | DA+0 | WPS | 545016 | 39.126 | 2024-10-28 | Completed. | 2024-11-20 |  | Haji Saheb
59
60 | 130/2 | DA+3 | WPS | 623377 | 40.634 | 2024-11-30 | Completed. | 2024-12-07 |  | haji saheb
60
61 | 130/3 | DA+0 | WPS | 545016 | 39.126 | 2024-11-22 | Completed. | 2024-12-02 |  | Hajji Saheb
61
62 | 130/4 | DA+3 | WPS | 623377 | 40.634 | 2024-11-24 | Completed. | 2024-11-30
62
63 | 131/0 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | 2024-12-06 |  | Arvind singh
63
64 | 132/0 | DC2+3 | WPS |  | 94.746 | 2024-10-15 | Completed. | 2024-11-13 | No work due to waterlogged. | Hajji Saheb
64
65 | 132/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-18 | Completed. | 2024-11-27
65
66 | 132/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-05 | Completed | 2023-08-14
66
67 | 132/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-06-12 | Completed | 2023-06-21
67
68 | 133/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed | 2024-01-10
68
69 | 133/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed | 2023-09-04
69
70 | 133/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed | 2023-10-29
70
71 | 133/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-28 | Completed | 2023-11-09
71
72 | 133/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-17 | Completed | 2023-12-26
72
73 | 133/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-19 | Completed | 2023-12-09
73
74 | 133A/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed | 2024-01-05
74
75 | 133A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-07 | Completed | 2023-11-23
75
76 | 133A/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-11-22 | Completed | 2023-12-01
76
77 | 133A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-31 | Completed | 2024-01-10
77
78 | 133A/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-08-11 | Completed | 2023-08-29
78
79 | 134/0 | DC2+25 | WPS |  | 103.7 | 2024-09-21 | Completed | 2024-10-26 |  | Jeet Infra (Departmental Gang)
79
80 | 135/0 | DC2+25 | WPS |  | 103.703 | 2024-12-02 | Completed. | 2024-12-20 |  | Haaji Saheb
80
81 | 135/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-02 | Completed. | 2024-12-24 |  | haji saheb
81
82 | 135/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-09-03 | Completed | 2023-09-24
82
83 | 135/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed | 2023-10-20
83
84 | 135/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-11 | Completed | 2024-03-20
84
85 | 135/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-27 | Completed | 2024-03-10
85
86 | 135/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-18 | Completed | 2024-02-26
86
87 | 135/7 | DA+0 | WPS | 545016 | 39.126 | 2025-03-26 | Completed. | 2025-04-03
87
88 | 135A/0 | DC1+0 | PS |  | 138.086 | 2024-11-11 | Completed. | 2024-12-08 |  | Niraj Tiwari
88
89 | 135A/1 | DD45+3 | WET PADDY |  | 131.047 | 2024-05-07 | Completed | 2024-05-26
89
90 | 135A/2 | DB2+9 | Wet Paddy | 2143792.36 | 65.135 | 2024-05-21 | Completed | 2024-06-17
90
91 | 135A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-26 | Completed | 2023-09-07
91
92 | 135A/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-10 | Completed | 2023-08-23
92
93 | 135A/5 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | 2024-12-31 |  | Lal Hussain
93
94 | 135A/6 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | 2024-12-17 |  | Neeraj Tiwari
94
95 | 135A/7 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed | 2023-10-29
95
96 | 135B/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-12 | Completed | 2023-12-30
96
97 | 135B/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-27 | Completed | 2024-02-06
97
98 | 135B/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed | 2023-12-20
98
99 | 135B/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed | 2023-12-17
99
100 | 135B/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-10-07 | Completed | 2023-10-19
100
101 | 135B/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed | 2023-12-31
101
102 | 135B/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed | 2024-01-05
102
103 | 135B/7 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-08 | Completed | 2024-02-17
103
104 | 136/0 | DD45+18(3M RC) | WPS |  | 161.632 | 2024-11-19 | Completed. | 2024-12-28 |  | Lala rams
104
105 | 137/0 | DC2+9 (3M RC) | WPS |  | 112.877 | 2024-10-15 | Completed. | 2024-12-23 |  | Himashi
105
106 | 137/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-29 | Completed | 2024-03-08
106
107 | 137/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-06 | Completed | 2024-03-14
107
108 | 137/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-09 | Completed | 2024-03-16
108
109 | 137/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-29 | Completed | 2024-03-10
109
110 | 137/5 | DA+3 | WPS | 623377 | 40.634 | 2024-11-22 | Completed | 2024-12-31 |  | Himanshi-01
110
111 | 137/6 | DA+0 | WPS | 545016 | 39.126 | 2024-11-24 | Completed. | 2024-12-14 |  | Shree Krishna Const.
111
112 | 137A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-15 | Completed. | 2024-12-29 |  | Shree Krishna Const.
112
113 | 137A/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-01 | Completed. | 2024-12-20 |  | Rabari Vankabhai
113
114 | 137A/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-21 | Completed. | 2024-12-30 |  | Rabari Vankabhai
114
115 | 137A/3 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-03-14 | Completed | 2024-03-23
115
116 | 137A/4 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-13 | Completed | 2024-04-20
116
117 | 137A/5 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-19 | Completed | 2024-04-28
117
118 | 137A/6 | DA+9 | WPS | 623377 | 40.634 | 2024-10-28 | Completed. | 2024-12-05 |  | Suresh Choudhary
118
119 | 138/0 | DB2+0 | WPS | 1196479 | 62.882 |  | Completed. | 2024-12-17 |  | Nav Durga
119
120 | 138/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-03 | Completed. | 2024-12-20 |  | Suresh Choudhary
120
121 | 138/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-27 | Completed. | 2025-01-03 |  | SA Enterprises
121
122 | 139/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-12-28 | Completed. | 2025-01-04 |  | Nav Durga
122
123 | 139/1 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | 2024-12-28 |  | Rawat Construction
123
124 | 139/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-18 | Completed. | 2024-12-24 |  | PR Construction
124
125 | 139A/0 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-12-19 | Completed. | 2024-12-31 |  | Lala Ram
125
126 | 140/0 | DD60+0 | WPS |  | 178.19 | 2024-12-13 | Completed. | 2024-12-23 |  | Nav Durga
126
127 | 141/0 | DD60+3 | WPS |  | 180.61 | 2024-12-16 | Completed. | 2024-12-29 |  | Nav Durga
127
128 | 141/1 | DA+0 | WPS | 545016 | 39.126 | 2024-12-15 | Completed. | 2024-12-27 |  | SA Enterprises
128
129 | 141/2 | DA-3 | WPS | 545016 | 39.126 | 2024-12-11 | Completed. | 2024-12-27 |  | Pratibha
129
130 | 141/3 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | 2024-12-31 |  | Pratibha
130
131 | 142/0 | DD60+0 | WPS |  | 178.19 | 2025-01-07 | Completed. | 2025-01-16 |  | Nav Durga
131
132 | 143/0 | DD60+3 | WPS |  | 180.61 | 2025-01-18 | Completed. | 2025-01-28 |  | Nav Durga
132
133 | 143A/0 | DD45+0 | WPS |  | 128.427 | 2025-01-15 | Completed | 2025-01-20 |  | Nav Durga
133
134 | 143A/1 | DA+6 | WPS | 623377 | 40.634 | 2025-01-28 | Completed. | 2025-01-31 |  | Nav Durga
134
135 | 143A/2 | DD45+0 | WPS |  | 128.427 | 2025-01-30 | Completed. | 2025-02-10 |  | Nav Durga
135
136 | 143A/3 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | 2024-12-11 |  | Madhav Constr.
136
137 | 143A/4 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | 2024-12-23 |  | Lalhusain
137
138 | 143A/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-06-19 | Completed | 2024-07-13 |  | Himanshi Agency
138
139 | 144/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-06-16 | Completed | 2024-06-26
139
140 | 144/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-11 | Completed | 2024-06-18
140
141 | 144/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-29 | Completed | 2024-04-06
141
142 | 144/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed | 2024-03-31
142
143 | 144/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-04-07 | Completed | 2024-04-15
143
144 | 144/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-15 | Completed | 2024-03-26
144
145 | 144A/0 | DB1+9 | WET PADDY | 1108538 | 54.992 | 2024-04-03 | Completed | 2024-04-14
145
146 | 145/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-03-23 | Completed | 2024-04-04
146
147 | 145A/0 | DB1+6 | WPS | 1108538 | 54.992 | 2024-12-13 | Completed. | 2024-12-21 |  | Himanshi
147
148 | 145A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-03-09 | Completed | 2024-03-22
148
149 | 145A/2 | DA+3 | WPS | 623377 | 40.634 | 2025-01-19 | Completed. | 2025-01-23 |  | Himanshi
149
150 | 145A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-19 | Completed | 2024-03-27
150
151 | 146/0 | DC1+9 | WBC |  | 192.814 | 2024-12-12 | Completed. | 2024-12-25 |  | Himanshi
151
152 | 147/0 | DC2+9 | WPS |  | 94.746 | 2024-12-07 | Completed. | 2024-12-18 |  | Himanshi
152
153 | 147/1 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-20 | Completed | 2024-06-08
153
154 | 147/2 | DC1+0 | Wet Paddy |  | 79.994 | 2024-05-20 | Completed | 2024-06-03
154
155 | 147/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-16 | Completed | 2024-05-29
155
156 | 147/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-04 | Completed | 2024-05-17
156
157 | 147/5 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-04-20 | Completed | 2024-05-03
157
158 | 147/6 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-15 | Completed | 2024-05-25
158
159 | 147A/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-06-05 | Completed | 2024-06-14
159
160 | 147B/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-04-30 | Completed | 2024-05-10
160
161 | 147B/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-25 | Completed. | 2024-12-05 |  | Himanshi-01
161
162 | 148/0 | DC2+0 | Wet |  | 134.785 | 2024-11-05 | Completed. | 2024-11-20 |  | Himanshi Construction
162
163 | 148/1 | DA+3 | WET | 986514 | 65.631 | 2024-11-18 | Completed. | 2024-11-27
163
164 | 148/2 | DA+0 | WPS | 545016 | 39.126 | 2024-11-19 | Completed. | 2024-11-26
164
165 | 148/3 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | 2024-12-05 |  | BK Traders
165
166 | 148/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-13 | Completed | 2024-06-20
166
167 | 148/5 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | 2024-12-10 |  | Himanshi
167
168 | 148/6 | DA+0 | Wet | 881091 | 63.346 | 2025-01-03 | Completed | 2025-01-06 |  | Himanshi
168
169 | 148/7 | DA+0 | Wet | 881091 | 63.346 | 2025-01-04 | Completed. | 2025-01-08 |  | Himanshi
169
170 | 149/0 | DB2+0 | Wet | 1880164 | 89.905 | 2024-12-23 | Completed | 2024-12-31 |  | Himanshi
170
171 | 149/1 | DA+0 | Wet | 881091 | 63.346 | 2024-12-24 | Completed | 2024-12-29 |  | Himanshi
171
172 | 150/0 | DD60+9 | Wet |  | 255.731 | 2025-01-11 | Completed. | 2025-01-28 |  | Himanshi
172
173 | 150/1 | DA+9 | Wet | 986514 | 65.631 | 2025-01-07 | Completed. | 2025-01-12 |  | Himanshi
173
174 | 150/2 | DA+3 | Wet | 986514 | 65.631 | 2025-01-12 | Completed. | 2025-01-16 |  | Himanshi
174
175 | 150/3 | DA+6 | WPS | 623377 | 40.634 | 2025-01-15 | Completed. | 2025-01-18 |  | Himanshi
175
176 | 150A/0 | DC1+0 | WET |  | 117.033 | 2024-05-29 | Completed | 2024-06-11
176
177 | 150A/1 | DA+3 | WET | 986514 | 65.631 | 2024-05-08 | Completed | 2024-05-22
177
178 | 150A/2 | DA+0 | WET | 881091 | 63.346 | 2024-04-12 | Completed | 2024-04-26
178
179 | 151/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2025-01-20 | Completed. | 2025-01-27 |  | Himanshi
179
180 | 152/0 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-19 | Completed | 2024-05-30
180
181 | 152/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-25 | Completed | 2024-05-31
181
182 | 152/2 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-25 | Completed | 2024-05-03
182
183 | 152/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-01 | Completed | 2024-05-09
183
184 | 152/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-05 | Completed | 2024-05-14
184
185 | 152A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-16 | Completed. | 2024-12-24 |  | BK Traders
185
186 | 153/0 | DD60+25(1M RC) | Wet |  | 602.294 | 2024-12-18 | Completed. | 2024-12-30 |  | BK Traders
186
187 | 154/0 |  | Pile |  |  |  | U/P.
187
188 | 154/1 | DD45+25(11.96 M RC) | PILE |  |  | 2025-01-24 | Completed. | 2025-05-11 |  | Harshi
188
189 | 155/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2024-04-16 | Completed. | 2024-05-11
189
190 | 155/1 | DA+0 | PS | 1086615 | 80.771 | 2024-10-03 | Completed. | 2024-10-24 |  | Jyoti Const.
190
191 | 155/2 | DA+3 | PS | 1215596 | 83.812 | 2024-10-03 | Completed. | 2024-10-11 |  | Jyoti Const.
191
192 | 155/3 | DA+3 | WET | 986514 | 65.631 | 2024-04-08 | Completed. | 2024-04-25
192
193 | 155/4 | DA+0 | Wet | 881091 | 63.346 |  | Completed. | 2025-04-12 |  | Nav Durga
193
194 | 155/5 | DA+0 | WET | 881091 | 63.346 | 2025-04-13 | Completed. | 2025-04-16 |  | Nav Durga
194
195 | 155/6 | DA-3 | PS | 1086615 | 80.771 | 2024-10-15 | Completed. | 2024-10-29 |  | M/s Rudra Associate
195
196 | 156/0 | DD60+3 | PS | 5188063.13 | 309.952 | 2024-10-30 | Completed. | 2024-11-24 |  | Rudra Associate
196
197 | 157/0 | DD60+6 | PS |  | 309.952 | 2025-01-12 | Completed. | 2025-01-29 |  | Anya Constr.
197
198 | 157/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | 2024-12-20 |  | Anya Construction
198
199 | 157/2 | DA+0 | FS | 1287409 | 91.088 | 2024-12-27 | Completed. | 2025-01-07 |  | Anya Construction.
199
200 | 157/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed. | 2024-12-24 |  | Maa Bhawani
200
201 | 158/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-01-23 | Completed. | 2025-01-30 |  | NR road Contr.
201
202 | 158/1 | DA-3 | PS | 1086615 | 80.771 | 2025-01-23 | Completed. | 2025-01-31 |  | NR road Contr.
202
203 | 158/2 | DA-3 | FS | 1287409 | 91.088 | 2025-01-10 | Completed. | 2025-01-23 |  | Haaji Saheb
203
204 | 158A/0 | DD45+6 | WET | 3953330 | 192.374 | 2024-07-01 | Completed. | 2024-07-30 |  | Kudiyaar
204
205 | 158B/0 | DD45+18 | PS | 5320583 | 257.278 | 2024-10-24 | Completed. | 2024-10-31 |  | Maa Bhawani
205
206 | 158B/1 | DA+3 | PS | 1215596 | 83.812 | 2024-11-06 | Completed. | 2024-11-09 |  | Maa Bhawani
206
207 | 158B/2 | DA+3 | PS | 1215596 | 83.812 | 2024-10-20 | Completed. | 2024-10-26 |  | Maa Bhawani
207
208 | 159/0 | DB1+0 | WET | 1598139 | 79.944 | 2024-03-26 | Completed. | 2024-04-04
208
209 | 159/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-27 | Completed. | 2024-12-14 |  | Rudra Associate
209
210 | 159/2 | DCT+0 | FS |  | 158.016 | 2025-01-02 | Completed. | 2025-01-13 | DC2+0 | NR road Contr.
210
211 | 159/3 | DA+0 | WET | 881091 | 63.346 | 2024-02-09 | Completed. | 2024-02-16
211
212 | 159/4 | DA+0 | FS | 1287409 | 91.088 | 2024-11-26 | Completed. | 2024-12-03 |  | Alamin
212
213 | 160/0 | DD60+18 | FS |  | 39.682 | 2024-12-28 | Completed. | 2025-01-13 |  | Haji Saheb
213
214 | 161/0 | DD60+25 | PS |  | 341.95 | 2024-12-01 | Completed | 2024-12-30 |  | Tes Transco
214
215 | 162/0 | DD60+25 | PS |  | 341.95 | 2025-01-03 | Completed. | 2025-01-24 |  | BK Traders
215
216 | 163/0 | DC2+0 | FS |  | 193.49 | 2024-12-14 | Completed. | 2024-12-29 |  | Lala Ram
216
217 | 163/1 | DA+0 | WET | 881091 | 63.346 | 2024-01-29 | Completed. | 2024-02-05
217
218 | 163/2 | DA+0 | WET | 881091 | 63.346 | 2024-01-24 | Completed. | 2023-01-29
218
219 | 163/3 | DA+0 | WET | 881091 | 63.346 | 2024-01-17 | Completed. | 2024-01-23
219
220 | 163/4 | DA+0 | WET | 881091 | 63.346 | 2024-02-08 | Completed. | 2024-02-13
220
221 | 163/5 | DA+0 | FS | 1287409 | 91.088 | 2024-02-14 | Completed. | 2024-02-23
221
222 | 163/6 | DA+0 | FS | 1287409 | 91.088 | 2024-02-22 | Completed. | 2024-02-29
222
223 | 164/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2024-10-21 | Completed. | 2024-11-07 |  | Tes Transco
223
224 | 164/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-11 | Completed. | 2024-11-28 |  | Tes Transco
224
225 | 164/2 | DA+0 | WET | 881091 | 63.346 | 2023-12-28 | Completed. | 2024-01-17
225
226 | 164/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-04 | Completed. | 2024-12-14 |  | Lala Ram
226
227 | 164/4 | DA+0 | WFR | 947845 | 60.634 | 2024-03-11 | Completed. | 2024-03-22
227
228 | 164/5 | DA+0 | WFR | 947845 | 60.634 | 2024-02-12 | Completed. | 2024-02-23
228
229 | 164/6 | DA+0 | PS | 1086615 | 80.771 | 2024-03-11 | Completed. | 2024-03-22
229
230 | 164/7 | DA+0 | WET | 881091 | 63.346 | 2024-01-18 | Completed. | 2024-01-29
230
231 | 165/0 | DB2+0 | PS | 2481749.46 | 115.247 | 2024-01-09 | Completed. | 2024-01-21
231
232 | 165/1 | DA+0 | PS | 1086615 | 80.771 | 2024-01-30 | Completed. | 2024-02-09
232
233 | 165/2 | DA+0 | WET | 881091 | 63.346 | 2024-02-13 | Completed. | 2024-02-28
233
234 | 165/3 | DA+6 | WET | 986514 | 65.631 | 2024-02-28 | Completed. | 2024-03-10
234
235 | 165/4 | DA+0 | WET | 881091 | 63.346 | 2023-10-20 | Completed. | 2023-11-03
235
236 | 166/0 | DD60+6 | PS | 5188063.13 | 309.952 | 2024-11-28 | Completed. | 2024-12-10 |  | Jyoti Constr.
236
237 | 167/0 | DD60+0 | WBC |  | 396.566 | 2025-01-06 | Completed. | 2025-01-18 |  | Sukhriddin
237
238 | 167/1 | DA+9 | FS | 1442822 | 94.623 | 2024-12-21 | Completed. | 2024-12-28 |  | Sukhriddin
238
239 | 167/2 | DA+6 | WET | 986514 | 65.631 | 2023-11-13 | Completed. | 2023-11-30
239
240 | 167/3 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-11-23 | Completed. | 2023-11-30
240
241 | 167/4 | DA+0 | WET | 881091 | 63.346 | 2023-12-09 | Completed. | 2023-12-15
241
242 | 168/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2025-03-13 | Completed. | 2025-03-27 |  | Ammu Engg.
242
243 | 168/1 | DA-3 | Wet | 881091 | 63.346 | 2024-11-09 | Completed. | 2024-11-18 |  | M/s Rajesh Singh
243
244 | 168/2 | DA+0 | FS | 1287409 | 91.088 | 2024-10-07 | Completed. | 2024-10-24 |  | M/s Rajesh Singh
244
245 | 169/0 | DD45+18 | PS | 5320583 | 257.278 | 2024-10-22 | Completed. | 2024-11-06 |  | M/s Rajesh Singh
245
246 | 171/0 | DD60+25 (3M RC) | PS |  | 353.162 | 2024-10-26 | Completed. | 2024-11-19 |  | Jyoti Const.
246
247 | 172/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2024-12-16 | Completed. | 2025-01-04 |  | Khodiyar Krupa
247
248 | 172/1 | DA+3 | PS | 1215596 | 83.812 | 2024-12-24 | Completed. | 2024-12-28 |  | Value Constr.
248
249 | 172/2 | DA+6 | PS | 1215596 | 83.812 | 2024-12-29 | Completed. | 2025-01-04 |  | Value Constr.
249
250 | 173/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2024-12-10 | Completed. | 2024-12-24 |  | Value Constr.
250
251 | 174/0 | DD60+18 | FS | 6685851 | 390.682 | 2025-02-11 | Completed. | 2025-02-22 |  | Jyoti
251
252 | 174/1 | DB1+0 | PS | 2122856.48 | 98.821 | 2025-03-26 | Completed. | 2025-03-30 |  | Jyoti
252
253 | 175/0 | DD45+0 | Wet | 3743190.59 | 189.081 | 2025-03-22 | Completed. | 2025-03-28 |  | Arvind
253
254 | 175/1 | DA+0 | Wet | 881091 | 63.346 | 2025-03-16 | Completed. | 2025-03-19 |  | Arvind
254
255 | 175/2 | DA+0 | Wet | 881091 | 63.346 | 2025-05-18 | Completed. | 2025-05-22 |  | Himanshi Construction
255
256 | 176/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-05-15 | Completed. | 2025-05-23 |  | Jyoti
256
257 | 177/0 | DD60+0 | PS | 4780790.5 | 306.052 | 2025-03-12 | Completed. | 2025-03-22 |  | Jyoti
257
258 | 178/0 | DD60+6 | PS | 5188063.13 | 309.952 | 2024-12-23 | Completed. | 2024-12-31 |  | Jyoti
258
259 | 179/0 | DD60+0 | WBC |  | 396.566 | 2024-12-31 | Completed. | 2025-01-18 |  | Jyoti
259
260 | 180/0 | DD45+9 (3M RC) | Wet |  | 213.318 | 2025-01-25 | Completed. | 2025-01-31 |  | Jyoti
260
261 | 181/0 | DD45+18 | Wet | 4465782 | 224.07 | 2025-02-02 | Completed. | 2025-02-08 |  | Jyoti
261
262 | 181/1 | DA+0 | Wet | 881091 | 63.346 | 2025-03-13 | Completed. | 2025-03-20 |  | Himanshi
262
263 | 181/2 | DA+0 | Wet | 881091 | 63.346 | 2025-03-03 | Completed. | 2025-03-06 |  | Jyoti
263
264 | 181/3 | DA+0 | Wet | 881091 | 63.346 | 2025-01-20 | Completed. | 2025-01-23 |  | Jyoti
264
265 | 181/4 | DA+0 | Wet | 881091 | 63.346 | 2025-02-25 | Completed. | 2025-02-28 |  | Jyoti
265
266 | 182/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-02-27 | Completed. | 2025-03-13 |  | Arvind
266
267 | 182A/0 | DD45+6(2M RC) | PS |  | 239.926 | 2024-12-02 | Completed. | 2024-12-22 |  | Jyoti
267
268 | 183/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2025-04-07 | Completed. | 2025-04-20 |  | Tes Transco
268
269 | 184/0 | DD60+25 | Wet | 4801423 | 298.554 | 2024-12-28 | Completed. | 2025-01-08 |  | Maa Bhawani
269
270 | 184/1 | DB1+6 | Wet | 1741972 | 80.469 | 2025-02-20 | Completed. | 2025-02-26 |  | Arvind
270
271 | 185/0 | DC2+0 | Wet | 2530056 | 134.785 | 2025-02-27 | Completed. | 2025-03-13 |  | Himanshi
271
272 | 185/1 | DA+9 | Wet | 986514 | 65.631 | 2024-11-28 | Completed. | 2024-11-30 |  | Jyoti
272
273 | 186/0 | DD60+35 | Wet | 7665610 | 315.149 | 2024-12-28 | Completed. | 2025-04-04 | Again start date is 30-03-2025 | Sukhriddin
273
274 | 187/0 | DD60+25 | Wet | 4801423 | 298.554 | 2025-02-17 | Completed. | 2025-03-03 |  | Jyoti-2
274
275 | 187/1 | DA+3 | Wet | 986514 | 65.631 | 2025-03-04 | Completed. | 2025-03-10 |  | Jyoti
275
276 | 187/2 | DA-3 | FS | 1287409 | 91.088 |  | Completed. | 2024-04-13
276
277 | 187/3 | DA+0 | PS | 1086615 | 80.771 | 2024-03-09 | Completed. | 2024-03-20
277
278 | 188/0 | DB1+6 | WET | 1741972 | 80.469 | 2024-04-01 | Completed. | 2024-04-07
278
279 | 189/0 | DB2+6 | WET | 2143792.36 | 94.918 | 2024-03-22 | Completed. | 2024-03-31
279
280 | 189/1 | DA+0 | Wet | 881091 | 63.346 | 2025-01-06 | Completed | 2025-01-09 |  | Value Constr.
280
281 | 190/0 | DD45+25 | Wet | 4465782 | 224.07 | 2024-11-30 | Completed. | 2024-12-31 |  | Tes transco
281
282 | 191/0 | DD45+25 | WET | 4465782 | 224.07 | 2024-03-06 | Completed. | 2024-03-17
282
283 | 191/1 | DA+0 | WET | 881091 | 63.346 | 2024-03-16 | Completed. | 2024-03-21
283
284 | 191/2 | DA-3 | Wet | 881091 | 63.346 | 2024-12-14 | Completed. | 2024-12-21 |  | Khodiyar Krupa
284
285 | 191/3 | DA-3 | PS | 1086615 | 80.771 | 2024-12-17 | Completed. | 2024-12-24 |  | Khodiyar Krupa
285
286 | 191A/0 | DB2+0 | WET | 1880164 | 89.905 | 2024-04-25 | Completed. | 2024-05-13
286
287 | 191A/1 | DA-3 | FS | 1287409 | 91.088 | 2024-04-14 | Completed. | 2024-04-21
287
288 | 192/0 | DC1+0 | PS | 3074652.99 | 138.086 | 2024-11-29 | Completed. | 2024-12-14 |  | M/s Rajesh Singh
288
289 | 193/0 | DD60+6 | WET | 4251845 | 255.731 | 2024-04-21 | Completed. | 2024-04-30
289
290 | 194/0 | DD60+6 | Wet | 4251845 | 255.731 | 2025-03-19 | Completed. | 2025-03-31 |  | Himanshi
290
291 | 195/0 | DC2+0 | PS | 3206945.94 | 168.913 | 2024-05-14 | Completed. | 2024-05-24 | Again completed on 16-04-2025
291
292 | 195/1 | DA+6 | PS | 1215596 | 83.812 | 2024-12-30 | Completed | 2025-01-07 |  | Hari Krishna
292
293 | 195/2 | DA+0 | Wet | 881091 | 63.346 | 2025-02-21 | Completed. | 2025-02-26 |  | Himanshi
293
294 | 195/3 | DA+6 | PS | 1215596 | 83.812 | 2023-12-07 | Completed. | 2023-12-26
294
295 | 195/4 | DA+0 | WET | 881091 | 63.346 | 2023-12-26 | Completed. | 2024-01-12
295
296 | 195/5 | DA+6 | WBC | 1821043 | 113.924 | 2025-01-08 | Completed. | 2025-01-16 |  | Hari Krishna
296
297 | 195A/0 | DB1+0 | PS | 2122856.48 | 98.821 | 2024-11-30 | Completed. | 2024-12-28 |  | Hari Krishna
297
298 | 195A/1 | DA+6 | FS | 1442822 | 94.623 | 2025-03-25 | Completed. | 2025-03-29 |  | kastabhanja
298
299 | 195A/2 | DA+6 | FS | 1442822 | 94.623 | 2024-12-07 | Completed. | 2024-12-12 |  | Maa Bhawanis
299
300 | 195A/3 | DA+0 | PS | 1086615 | 80.771 | 2023-08-22 | Completed. | 2023-10-01
300
301 | 196/0 | DD60+9 | WBC |  | 401.731 | 2024-11-16 | Completed. | 2024-11-30 |  | Maa Bhawani
301
302 | 197/0 | DD60+9 | Wet | 4251845 | 255.731 | 2024-11-12 | Completed. | 2024-11-18 |  | Maa Bhawani
302
303 | 197/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-18 | Completed. | 2024-11-22 |  | Maa Bhawani
303
304 | 197/2 | DA+0 | Wet | 881091 | 63.346 | 2024-11-25 | Completed. | 2024-11-30 |  | Maa Bhawani
304
305 | 197/3 | DA+0 | PS | 1086615 | 80.771 | 2023-08-18 | Completed. | 2023-08-31
305
306 | 197/4 | DA+0 | WET | 881091 | 63.346 | 2024-11-08 | Completed. | 2024-11-10 |  | Maa Bhawani
306
307 | 198/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2024-11-13 | Completed. | 2024-11-30 |  | M/s Rajesh Singh
307
308 | 198/1 | DA+0 | Wet | 881091 | 63.346 | 2024-11-17 | Completed. | 2024-12-12 |  | Kumar
308
309 | 198/2 | DA+0 | Wet | 881091 | 63.346 | 2025-02-16 | Completed. | 2025-02-23 |  | Hari Krishna
309
310 | 199/0 | DD45+18 | Wet | 4465782 | 224.07 | 02-02-025 | Completed. | 2025-02-13 |  | Hari Krishna
310
311 | 200/0 | DB2+18 | Wet | 2472338 | 111.669 | 2025-01-19 | Completed. | 2025-01-31 |  | Hari Krishna
311
312 | 201/0 | DC2+18 | Wet | 3336290 | 149.965 | 2025-02-26 | Completed. | 2025-03-06 |  | Hari Krishna
312
313 | 201/1 | DD60+9 (2M RC) | Wet | 5379537 | 282.692 | 2025-03-30 | Completed. | 2025-04-09 |  | Kastabbhanja
313
314 | 202/0 | DD60+55(4.5M RC) | WBC |  | 768.133 | 2025-04-05 | Completed. | 2025-05-06 |  | Sukhriddin
314
315 | 203/0 | DD60+55(4.5M RC) | WBC |  | 768.133 | 2025-03-09 | Completed. | 2025-03-31 |  | Sukhriddin
315
316 | 203/1 | DD60+6 | Wet | 4251845 | 255.731 | 2025-02-21 | Completed. | 2025-02-28 |  | Sukhriddin
316
317 | 204/0 | DD60+9 | Wet | 4251845 | 255.731 | 2025-03-02 | Completed. | 2025-03-08 |  | Sukhriddin
317
318 | 205/0 | DD60+3 (2M RC) | Wet |  | 282.692 | 2025-02-13 | Completed. | 2025-02-20 |  | Sukhridin
318
319 | 205/1 | DA-3 | Wet | 881091 | 63.346 | 2025-01-29 | Completed. | 2025-01-31 |  | Sukhridin
319
320 | 205/2 | DA+3 | Wet | 986514 | 65.631 | 2025-02-26 | Completed. | 2025-02-28 |  | Kastbahana
320
321 | 206/0 | DD60+25 | Wet | 4801423 | 298.554 | 2025-01-21 | Completed. | 2025-01-28 |  | Sukhridin
321
322 | 208/0 | DD60+25 | Wet | 4801423 | 298.554 | 2025-01-20 | Completed. | 2025-01-29 |  | Velly
322
323 | 209/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2025-01-09 | Completed. | 2025-01-17 |  | Velly Constr.
323
324 | 209/1 | DA+3 | Wet | 986514 | 65.631 | 2025-01-13 | Completed. | 2025-01-20 |  | Velly Constr.
324
325 | 210/0 | DB2+18 | Wet | 2472338 | 111.669 | 2025-03-02 | Completed. | 2025-03-20 |  | Tes Trasnsco
325
326 | 211/0 | DB1+9 | Wet | 1741972 | 80.469 | 2025-03-02 | Completed. | 2025-03-16 |  | Tower foundation
326
327 | 211/1 | DA+0 | Wet | 881091 | 63.346 | 2025-01-13 | Completed. | 2025-01-19 |  | Tower Foundation
327
328 | 211/2 | DA+0 | Wet | 881091 | 63.346 | 2025-01-21 | Completed | 2025-01-25 |  | Tower Foundation
328
329 | 211A/0 | DB2+0 | Wet | 1880164 | 89.905 | 2025-02-02 | Completed. | 2025-02-08 |  | Tower foundation
329
330 | 211A/1 | DA-3 | Wet | 881091 | 63.346 | 2025-01-21 | Completed. | 2025-01-25 |  | Khodiyar
330
331 | 211A/2 | DA+0 | Wet | 881091 | 63.346 | 28-01-202 | Completed. | 2025-01-31 |  | Tower Foundation
331
332 | 212/0 | DD45+3 | Wet | 3953330 | 192.374 | 2025-02-10 | Completed. | 2025-02-21 |  | Tower Foundation
332
333 | 213/0 | DD60+3 | WBC |  | 401.731 | 2025-01-16 | Completed. | 2025-02-04 |  | Tes Transco
333
334 | 213/1 | DA+0 | Wet | 881091 | 63.346 | 2025-01-23 | Completed. | 2025-01-31 |  | Tes Transco
334
335 | 214/0 | DD45+0 | PS | 4512711.95 | 233.46 | 2025-01-31 | Completed. | 2025-02-17 |  | Tes Transco
335
336 | 214/1 | DA+6 | Wet | 986514 | 65.631 | 2025-02-03 | Completed. | 2025-02-12 |  | Tes Transco
336
337 | 215/0 | DB1+6 | Wet | 1741972 | 80.469 | 2025-01-12 | Completed. | 2025-01-18 |  | BLG Infratech
337
338 | 215/1 | DA+9 | Wet | 986514 | 65.631 | 2025-01-17 | Completed. | 2025-01-22 |  | BLG
338
339 | 216/0 | DB2+25(2M RC) | Wet |  | 120.61 | 2025-02-27 | Completed. | 2025-03-12 |  | Tes Transco
339
340 | 217/0 | DD45+25(2M RC) | Wet |  | 231.258 | 2025-03-18 | Completed. | 2025-03-31 |  | Tes Transco
340
341 | 217A/0 | DB1+3 | Wet | 1741972 | 80.469 | 2025-03-19 | Completed. | 2025-03-23 |  | Kastabhanja
341
342 | 217A/1 | DA+3 | PS | 1215596 | 83.812 | 2025-02-17 | Completed. | 2025-02-25 |  | Tes Transco
342
343 | 217A/2 | DA+0 | PS | 1086615 | 80.771 | 2025-02-25 | Completed. | 2025-02-28 |  | Tes Transco
343
344 | 218/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-03-10 | Completed. | 2025-03-31 |  | Tes Transcvo
344
345 | 218/1 | DA+3 | Wet | 986514 | 65.631 | 2025-01-12 | Completed. | 2025-01-19 |  | Tes Transco
345
346 | 219/0 | DC2+18 | Wet | 3336290 | 149.965 | 2025-01-12 | Completed. | 2025-01-25 |  | Tes Transco
346
347 | 220/0 | DD45+9 | Wet | 3953330 | 192.374 | 2025-02-02 | Completed. | 2025-02-11 |  | Tes Transco
347
348 | 220/1 | DA+3 | Wet | 986514 | 65.631 | 2025-02-07 | Completed. | 2025-02-16 |  | Tes Transco
348
349 | 221/0 | DD60+18 | FS | 6685851 | 390.682 | 2025-02-11 | Completed. | 2025-02-25 |  | Tes Transco
349
350 | 222/0 | DD60+25 | FS | 6685851 | 390.682 | 2025-02-13 | Completed. | 2025-02-23 |  | Kastbhanja
350
351 | 222/1 | DB1+3 | Wet | 1741972 | 80.469 | 2025-03-14 | Completed. | 2025-03-17 |  | Kastabhanja
351
352 | 223/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2025-01-26 | Completed. | 2025-01-31 |  | BLG
352
353 | 223/1 | DA+0 | Wet | 881091 | 63.346 | 2025-02-18 | Completed. | 2025-02-21 |  | Murgan
353
354 | 223/2 | DA+0 | Wet | 881091 | 63.346 | 2025-02-14 | Completed. | 2025-02-18 |  | Murgan
354
355 | 223/3 | DA+0 | Wet | 881091 | 63.346 | 2025-01-30 | Completed. | 2025-02-02 |  | Khodiyar
355
356 | 224/0 | DC2+6 | Wet | 2772635 | 138.207 | 2025-01-23 | Completed. | 2025-01-30 |  | Khodiyar
356
357 | 225/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-02-04 | Completed. | 2025-02-12 |  | Khodiyar
357
358 | 225/1 | DA+6 | Wet | 986514 | 65.631 | 2025-02-03 | Completed. | 2025-02-07 |  | BLG
358
359 | 226/0 | DC2+0 | Wet | 2530056 | 134.785 | 2025-02-03 | Completed. | 2025-02-10 |  | Kastabhanja
359
360 | 227/0 | DB1+6 | PS | 2075500 | 99.33 | 2025-01-26 | Completed. | 2025-02-04 |  | Ammu Eng.
360
361 | 228/0 | DD60+25 | PS | 5611385.97 | 341.95 | 2025-03-01 | Completed. | 2025-05-28 | Again start date is 14-05-2025 | Kastabhanja
361
362 | 229/0 | DD60+18 | WBC |  | 448.208 | 2025-02-02 | Completed. | 2025-02-11 |  | Sukhridin
362
363 | 229/1 | DB1+6 | Wet | 1741972 | 80.469 | 2025-03-25 | Completed. | 2025-04-07 |  | Tes Transco
363
364 | 229/2 | DA+6 | Wet | 986514 | 65.631 | 2025-02-10 | Completed. | 2025-02-13 |  | Murgan
364
365 | 229/3 | DA+0 | Wet | 881091 | 63.346 | 2025-02-01 | Completed. | 2025-02-05 |  | Velly Constr.
365
366 | 229/4 | DA+0 | Wet | 881091 | 63.346 | 2025-03-14 | Completed. | 2025-03-17 |  | Tes Transco
366
367 | 229/5 | DA+0 | Wet | 881091 | 63.346 | 2025-02-05 | Completed. | 2025-02-08 |  | Velly Constr.
367
368 | 230/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-02-10 | Completed. | 2025-02-17 |  | Velly Constr.
368
369 | 231/0 | DD60+6 | Wet | 4251845 | 255.731 | 2025-02-09 | Completed. | 2025-02-18 |  | BLG
369
370 | 232/0 | DD60+3 | Wet | 4251845 | 255.731 | 2025-02-19 | Completed. | 2025-02-28 |  | Velly Constr
370
371 | 233/0 | DD45+0 | Wet | 3743190.59 | 189.081 | 2025-02-07 | Completed. | 2025-02-15 |  | Ammu Engg.-1
371
372 | 234/0 | DD45+0 | Wet | 3743190.59 | 189.081 | 2025-02-13 | Completed. | 2025-02-21 |  | Ammu Engg.
372
373 | 235/0 | DC2+3 | PS |  | 162.896 | 2025-02-17 | Completed. | 2025-02-28 |  | Ammu Engg.
373
374 | 236/0 | DB2+0 | Wet | 1880164 | 89.905 | 2025-03-02 | Completed. | 2025-03-19 |  | Ammu Engg.
374
375 | 237/0 | DD45+9 (3M RC) | Wet |  | 213.318 | 2025-02-14 | Completed. | 2025-02-23 |  | Khodiyar
375
376 | 237/1 | DA+0 | Wet | 881091 | 63.346 | 2025-02-24 | Completed. | 2025-02-27 |  | Khodiyar
376
377 | 237/2 | DA-3 | Wet | 881091 | 63.346 | 2025-02-26 | Completed. | 2025-02-28 |  | Khodiyar
377
378 | 237/3 | DA-3 | Wet | 881091 | 63.346 | 2025-03-03 | Completed. | 2025-03-07 |  | Ammu
378
379 | 237/4 | DA+0 | PS | 1086615 | 80.771 | 2025-02-22 | Completed. | 2025-02-27 |  | Tower Foundation
379
380 | 237/5 | DA-3 | Wet | 881091 | 63.346 | 2025-02-23 | Completed. | 2025-02-28 |  | Ammu Engg-1
380
381 | 237/6 | DA+3 | Wet | 986514 | 65.631 | 2025-02-12 | Completed. | 2025-02-16 |  | Jayesh Electrical
381
382 | 239/0 | DD60+25 | Wet | 4801423 | 298.554 | 2025-04-01 | Completed. | 2025-04-11 |  | Khodiyar Krupa
382
383 | 240/0 | DD60+25 | FS | 6685851 | 390.682 | 2025-02-18 | Completed. | 2025-02-28 |  | Jayesh Electrical
383
384 | 241/0 | DB2+9 | WBC | 3850981 | 173.061 | 2025-03-23 | Completed. | 2025-04-06 |  | Jayesh Electrical
384
385 | 242/0 | DB1+0 | FS |  | 113.343 | 2025-02-19 | Completed. | 2025-02-27 |  | Tes Trasnsco
385
386 | 242/1 | DA-3 | Wet | 881091 | 63.346 | 2025-03-02 | Completed. | 2025-03-06 |  | Tes Transco
386
387 | 242/2 | DA-3 | Wet | 881091 | 63.346 | 2025-02-18 | Completed. | 2025-02-21 |  | BLG
387
388 | 242/3 | DA-3 | Wet | 881091 | 63.346 | 2025-03-10 | Completed. | 2025-03-13 |  | Khodiyar
388
389 | 243/0 | DB1+9 | FS |  | 113.896 | 2025-03-23 | Completed. | 2025-03-29 |  | Khodiyar
389
390 | 244/0 | DC1+9 | WBC |  | 197.882 | 2025-03-01 | Completed. | 2025-03-13 |  | BLG
390
391 | 244/1 | DB1+9 | WBC |  | 138.164 | 2025-03-27 | Completed. | 2025-03-31 |  | BLG
391
392 | 245/0 | DD45+0 | FS | 5295995.92 | 266.818 | 2025-03-16 | Completed. | 2025-03-26 |  | BLG
392
393 | 245/1 | DA+0 | FS | 1287409 | 91.088 | 2025-02-16 | Completed. | 2025-02-22 |  | Neelkanth
393
394 | 246/0 | DD60+0 | PS | 4780790.5 | 306.052 | 2025-03-02 | Completed. | 2025-03-21 |  | Khodiyar
394
395 | 247/0 | DD60+0 | FS | 5576159.92 | 346.952 | 2025-02-27 | Completed. | 2025-03-12 |  | Murgan
395
396 | 247/1 | DA+0 | FS | 1287409 | 91.088 | 2025-02-23 | Completed. | 2025-02-26 |  | Murgan
396
397 | 247/2 | DA+3 | Wet | 986514 | 65.631 | 2025-02-24 | Completed. | 2025-02-28 |  | Neel Kanth
397
398 | 247/3 | DA-3 | Wet | 881091 | 63.346 | 2025-03-03 | Completed. | 2025-03-07 |  | Khodiyar
398
399 | 247/4 | DA+0 | Wet | 881091 | 63.346 | 2025-02-24 | Completed. | 2025-02-27 |  | BLG
399
400 | 248/0 | DC2+9 | Wet | 2772635 | 138.207 | 2025-03-09 | Completed. | 2025-03-26 |  | Ketan
400
401 | 248/1 | DA+9 | Wet | 986514 | 65.631 | 2025-02-25 | Completed. | 2025-02-28 |  | Ketan
401
402 | 248/2 | DA+9 | Wet | 986514 | 65.631 | 2025-02-18 | Completed. | 2025-02-24 |  | Ketan
402
403 | 248/3 | DA+6 | Wet | 986514 | 65.631 | 2025-03-03 | Completed. | 2025-03-07 |  | Ketan
403
404 | 248/4 | DA+3 | Wet | 986514 | 65.631 | 2025-01-25 | Completed. | 2025-01-29 |  | Kastabhanja
404
405 | 248/5 | DA+0 | Wet | 881091 | 63.346 | 2025-01-29 | Completed. | 2025-01-31 |  | Kastabhanja
405
406 | 248/6 | DA+0 | Wet | 881091 | 63.346 | 2025-01-08 | Completed. | 2025-01-11 |  | Kastabhanja
406
407 | 249/0 | DB2+0 | Wet | 1880164 | 89.905 | 2025-01-14 | Completed. | 2025-01-19 |  | Khodiyar Krupa
407
408 | 249/1 | DA+0 | Wet | 881091 | 63.346 | 2025-01-07 | Completed. | 2025-01-10 |  | Khodiyar Krupa
408
409 | 249/2 | DA+0 | Wet | 881091 | 63.346 | 2025-01-11 | Completed. | 2025-01-13 |  | Khodiyar Krupa
409
410 | 249/3 | DA+0 | Wet | 881091 | 63.346 | 2025-01-10 | Completed. | 2025-01-13 |  | Jayesh Electrical
410
411 | 250/0 | DD60+0 | Wet | 3915704.88 | 252.474 | 2025-01-14 | Completed. | 2025-01-23 |  | Jayesh Electrical
411
412 | 250/1 | DA-3 | Wet | 881091 | 63.346 | 2025-01-12 | Completed. | 2025-01-16 |  | Kastabhanja
412
413 | 251/0 | DB1+9 | FS |  | 113.896 | 2024-09-04 | Completed. | 2024-09-19 |  | Kudiyaar
413
414 | 252/0 | DC1+18 | Wet | 3216269 | 131.849 | 2025-01-17 | Completed. | 2025-01-24 |  | Kastabhanja
414
415 | 253/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2025-01-08 | Completed | 2025-01-19 |  | Tes Transco
415
416 | 254/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2024-08-04 | Completed. | 2024-08-22
416
417 | 255/0 | DD60+3 | FS | 5918512 | 351.748 | 2024-09-13 | Completed. | 2024-10-10 |  | Tes Transco
417
418 | 255/1 | DA+6 | Wet | 986514 | 65.631 | 2025-01-02 | Completed. | 2025-01-07 |  | Kastabhanja
418
419 | 255/2 | DA+0 | Wet | 881091 | 63.346 | 2024-12-10 | Completed. | 2024-12-15 |  | Jayesh Electrical
419
420 | 255/3 | DA+3 | Wet | 986514 | 65.631 | 2024-11-13 | Completed. | 2024-11-21 |  | Paresh mahto
420
421 | 255/4 | DA+0 | WPS | 545016 | 39.126 | 2024-06-14 | Completed. | 2024-06-21
421
422 | 257/0 | DC2+0 | WET | 2530056 | 134.785 | 2024-05-29 | Completed. | 2024-06-01
422
423 | 257/1 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed. | 2024-12-31 |  | Jayesh Electrical
423
424 | 257/2 | DA-3 | WET | 881091 | 63.346 | 2024-04-21 | Completed. | 2024-04-30
424
425 | 257/3 | DA+0 | WET | 881091 | 63.346 | 2024-03-18 | Completed. | 2024-03-30
425
426 | 257/4 | DA+0 | WET | 881091 | 63.346 | 2024-05-03 | Completed. | 2024-05-10
426
427 | 259/0 | DD60+18 | PS | 5611385.97 | 341.95 | 2024-06-14 | Completed. | 2024-07-11
427
428 | 260/0 | DD60+18 | WBC |  | 448.208 |  | Completed. | 2024-05-31
428
429 | 261/0 | DC2+18 | WET | 3336290 | 149.965 | 2024-05-03 | Completed. | 2024-05-10
429
430 | 262/0 | DD45+9 | WET | 3953330 | 192.374 | 2024-05-13 | Completed. | 2024-06-01
430
431 | 262/1 | DA+0 | WET | 881091 | 63.346 | 2024-04-13 | Completed. | 2024-04-27
431
432 | 263/0 | DC2+0 | PS | 3206945.94 | 168.913 | 2024-10-09 | Completed. | 2024-10-29 |  | Tes Transco
432
433 | 264/0 | DC1+6 | WET | 2633913 | 120.461 | 2024-05-01 | Completed. | 2024-05-11
433
434 | 265/0 | DB2+3 | WET | 2143792.36 | 94.918 | 2024-04-27 | Completed. | 2024-05-12
434
435 | 266/0 | DB1+0 | Wet | 1598139 | 79.944 | 2024-12-01 | Completed. | 2024-12-08 |  | Kastabhaja
435
436 | 266/1 | DB1+6 | Wet | 1741972 | 80.469 | 2024-11-15 | Completed. | 2024-11-22 |  | Tes Transco
436
437 | 266/2 | DA+0 | Wet | 881091 | 63.346 | 2025-01-25 | Completed. | 2025-01-29 |  | Jayesh Electrical
437
438 | 267/0 | DC1+9 (2M RC) | WET |  | 139.849 | 2024-05-10 | Completed. | 2024-05-21 | RC done o 16-12-2024. | Jayesh Electrical
438
439 | 267A/0 | DC2+9 (2M RC) | WET |  | 151.836 | 2024-04-13 | Completed. | 2024-04-28 | RC done on 17-12-2024 | Jayesh Electrical
439
440 | 267A/1 | DA+0 | FS | 1287409 | 91.088 | 2024-08-14 | Completed. | 2024-09-23 |  | Rudra Associate
440
441 | 267A/2 | DA-3 | WET | 881091 | 63.346 | 2024-04-27 | Completed. | 2024-05-15
441
442 | 267A/3 | DA+0 | WET | 881091 | 63.346 | 2024-04-30 | Completed. | 2024-05-08
442
443 | 268/0 | DD60+6 | WET | 4251845 | 255.731 | 2024-05-12 | Completed. | 2024-05-22
443
444 | 269/0 | DD60+0 | WET | 3915704.88 | 252.474 | 2024-06-03 | Completed. | 2024-06-14
444
445 | 269/1 | DA+0 | WeT | 881091 | 63.346 | 2024-11-23 | Completed. | 2024-11-29 |  | Paresh
445
446 | 269/2 | DA+6 | PS | 1215596 | 83.812 | 2025-01-02 | Completed. | 2025-01-08 |  | Jayesh Electrical
446
447 | 270/0 | DD45+0 | FS | 5295995.92 | 266.818 | 2025-01-30 | Completed. | 2025-02-10 |  | Jayesh Electrical
447
448 | 270/1 | DA+0 | PS | 1086615 | 80.771 | 2024-05-27 | Completed. | 2024-06-01
448
449 | 270/2 | DA+3 | WET | 986514 | 65.631 | 2024-05-20 | Completed. | 2024-05-26
449
450 | 270/3 | DA-3 | WBC | 1686873 | 109.919 | 2025-01-07 | Completed. | 2025-01-17 |  | Tes Transco
450
451 | 270/4 | DA+0 | Wet | 881091 | 63.346 | 2024-11-28 | Completed. | 2024-12-20 |  | Maa Bhawani(Jitu)
451
452 | 270/5 | DA+0 | Wet | 881091 | 63.346 | 2025-01-20 | Completed. | 2025-01-28 |  | Tes Transco
452
453 | 270/6 | DA-3 | Wet | 881091 | 63.346 | 2025-01-18 | Completed. | 2025-01-24 |  | Tes Transco
453
454 | 270/7 | DA-3 | Wet | 881091 | 63.346 | 2024-12-01 | Completed. | 2024-12-06 |  | Tes Trasnsco
454
455 | 270A/0 | DC2+0 | Wet | 2530056 | 134.785 | 2024-12-18 | Completed. | 2024-12-31 |  | Tes transco
455
456 | 271/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2024-11-23 | Completed. | 2024-11-30 |  | Tes Transco
456
457 | 271/1 | DA-3 | FS | 1287409 | 91.088 | 2025-03-03 | Completed. | 2025-03-13 |  | Neekl Kanta
457
458 | 271/2 | DA+0 | Wet | 881091 | 63.346 | 2025-01-14 | Completed | 2025-01-21 |  | Tes Transco
458
459 | 271/3 | DA-3 | WBC | 1686873 | 109.919 | 2024-12-01 | Completed. | 2024-12-08 |  | Jayesh Electrical
459
460 | 271/4 | DA-3 | Wet | 881091 | 63.346 | 2025-01-23 | Completed. | 2025-01-29 |  | Tes Transco
460
461 | 271/5 | DA-3 | WET | 881091 | 63.346 | 2024-05-26 | Completed. | 2024-06-01
461
462 | 272/0 | DC1+6 | WET | 2633913 | 120.461 | 2024-06-04 | Completed. | 2024-06-13
462
463 | 272/1 | DA+9 | WET | 986514 | 65.631 | 2024-06-05 | Completed. | 2024-06-12
463
464 | 272/2 | DA-3 | Wet | 881091 | 63.346 | 2024-11-18 | Completed. | 2024-11-26 |  | Tes Transco
464
465 | 272/3 | DA+3 | Wet | 986514 | 65.631 | 2024-12-14 | Completed. | 2024-12-21 |  | Tes transco
465
466 | 272/4 | DA+3 | Wet | 986514 | 65.631 | 2024-12-08 | Completed. | 2024-12-12 |  | Tes Transco
466
467 | 272/5 | DB1+0 | Wet | 1598139 | 79.944 | 2024-11-23 | Completed. | 2024-11-30 |  | Tes Transco
467
468 | 272/6 | DA+3 | FS | 1442822 | 94.623 | 2025-02-26 | Completed. | 2025-03-04 |  | New Gang
468
469 | 272/7 | DA+9 (2M RC) | Wet |  | 71.29 | 2024-11-20 | Completed. | 2024-12-10 |  | Tes Transco
469
470 | 272A/0 | DB1+18 (2M RC) | PS |  | 117.99 | 2024-11-05 | Completed. | 2024-11-13 |  | Tes Transco
470
471 | 272A/1 | DA+6 | WET | 986514 | 65.631 | 2024-11-07 | Completed. | 2024-11-17 |  | Tes Transco
471
472 | 272A/2 | DA+0 | WET | 881091 | 63.346 | 2024-11-06 | Completed. | 2024-11-13 |  | Tes Transco
472
473 | 272A/3 | DA+0 | Wet | 881091 | 63.346 | 2024-12-28 | Completed. | 2025-01-03 |  | Tes Transco
473
474 | 272A/4 | DA+0 | Wet | 881091 | 63.346 | 2025-01-02 | Completed. | 2025-01-08 |  | Tes Transco
474
475 | 272A/5 | DA+3 | Wet | 986514 | 65.631 | 2025-01-04 | Completed. | 2025-01-11 |  | Tes Transco
475
476 | 272A/6 | DA-3 | Wet | 881091 | 63.346 | 2024-12-22 | Completed. | 2024-12-29 |  | Tes Transco
476
477 | 272A/7 | DA-3 | Wet | 881091 | 63.346 | 2025-01-05 | Completed. | 2025-01-12 |  | Tes Transco
477
478 | 273/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-05-01 | Completed. | 2025-06-13 | Again start date is 06-06-2025 | Tes Transco
478
479 | 273/1 | DA+6 | WBC | 1821043 | 113.924 | 2025-02-22 | Completed. | 2025-02-27 |  | Neelkanth
479
480 | 273/2 | DA+6 | Wet | 986514 | 65.631 | 2024-12-09 | Completed. | 2024-12-15 |  | Kastabhanja
480
481 | 274/0 | DC1+0 | Wet | 2328166.27 | 117.033 | 2025-01-02 | Completed. | 2025-01-11 |  | Tes Transco
481
482 | 275/0 | DD45+0(2M RC) | Wet |  | 206.583 | 2024-12-09 | Completed. | 2024-12-23 |  | Tes Transco
482
483 | 276/0 | DD60+0(2M RC) | Wet |  | 265.697 | 2024-12-18 | Completed. | 2024-12-31 |  | Kastabhanja
483

## FDN-VDRA
Foundation Part-I (VADODARA SECTION)
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Start Date | Todays Status | Cumulative Status | End Date | Remarks | Sub-Contractor name | Earthing Status | Earthing Completion Date
1 | 132/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-06-12 | Completed |  | 2023-06-21
2 | 132/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-05 | Completed |  | 2023-08-14
3 | 135A/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-10 | Completed |  | 2023-08-23
4 | 133A/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-08-11 | Completed |  | 2023-08-29
5 | 127/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-18 | Completed |  | 2023-08-29
6 | 127/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed |  | 2023-09-14
7 | 135A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-26 | Completed |  | 2023-09-07
8 | 133/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-08-28 | Completed |  | 2023-09-04
9 | 135/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-09-03 | Completed |  | 2023-09-24
10 | 135/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed |  | 2023-10-20
11 | 127/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-03 | Completed |  | 2023-11-02
12 | 133/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed |  | 2023-10-29
13 | 135A/7 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-07 | Completed |  | 2023-10-29
14 | 135B/4 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-10-07 | Completed |  | 2023-10-19
15 | 127/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-10-16 | Completed |  | 2023-10-29
16 | 133/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-10-28 | Completed |  | 2023-11-09
17 | 133A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-07 | Completed |  | 2023-11-23
18 | 127/0 | DD45+0 | WET PADDY |  | 128.427 | 2023-11-11 | Completed |  | 2023-12-13
19 | 133/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-11-19 | Completed |  | 2023-12-09
20 | 133A/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2023-11-22 | Completed |  | 2023-12-01
21 | 135B/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed |  | 2023-12-20
22 | 135B/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-07 | Completed |  | 2023-12-17
23 | 133A/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed |  | 2024-01-05
24 | 135B/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-12 | Completed |  | 2023-12-30
25 | 133/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2023-12-11 | Completed |  | 2024-01-10
26 | 133/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-17 | Completed |  | 2023-12-26
27 | 127/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2023-12-19 | Completed |  | 2024-01-04
28 | 135B/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed |  | 2023-12-31
29 | 135B/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-24 | Completed |  | 2024-01-05
30 | 126/0 | DC2+0 | WET PADDY |  | 92.292 | 2023-12-23 | Completed |  | 2024-01-15
31 | 133A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2023-12-31 | Completed |  | 2024-01-10
32 | 129A/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-07 | Completed |  | 2024-02-02
33 | 130/0 | DB1+0 | WET PADDY | 1017007 | 54.675 | 2024-01-12 | Completed |  | 2024-01-30
34 | 112/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-01-18 | Completed |  | 2024-02-10
35 | 135B/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-01-27 | Completed |  | 2024-02-06
36 | 129A/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-01-31 | Completed |  | 2024-02-15
37 | 135B/7 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-08 | Completed |  | 2024-02-17
38 | 113/0 | DD60+0 | WET PADDY |  | 178.19 | 2024-02-08 | Completed |  | 2024-05-09
39 | 129A/2 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-13 | Completed |  | 2024-02-24
40 | 135/6 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-18 | Completed |  | 2024-02-26
41 | 137/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-29 | Completed |  | 2024-03-10
42 | 135/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-02-27 | Completed |  | 2024-03-10
43 | 137/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-02-29 | Completed |  | 2024-03-08
44 | 144/5 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-15 | Completed |  | 2024-03-26
45 | 145A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-03-09 | Completed |  | 2024-03-22
46 | 137/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-06 | Completed |  | 2024-03-14
47 | 137/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-09 | Completed |  | 2024-03-16
48 | 135/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-11 | Completed |  | 2024-03-20
49 | 137A/3 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-03-14 | Completed |  | 2024-03-23
50 | 145A/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-19 | Completed |  | 2024-03-27
51 | 107/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-03-31 | Completed |  | 2024-04-17
52 | 107/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed |  | 2024-04-01
53 | 144/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-22 | Completed |  | 2024-03-31
54 | 145/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-03-23 | Completed |  | 2024-04-04
55 | 144/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-03-29 | Completed |  | 2024-04-06
56 | 144/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-04-07 | Completed |  | 2024-04-15
57 | 144A/0 | DB1+9 | WET PADDY | 1108538 | 54.992 | 2024-04-03 | Completed |  | 2024-04-14
58 | 137A/4 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-13 | Completed |  | 2024-04-20
59 | 150A/2 | DA+0 | WET | 881091 | 63.346 | 2024-04-12 | Completed |  | 2024-04-26
60 | 104/0 | DD60+35 | Pile |  | 861.11 | 2024-11-17 | Completed. | Completed. | 2025-02-28 |  | Jai Mata Di
61 | 152/2 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-25 | Completed |  | 2024-05-03
62 | 147/5 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-04-20 | Completed |  | 2024-05-03
63 | 137A/5 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-04-19 | Completed |  | 2024-04-28
64 | 106B/1 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-04-18 | Completed |  | 2024-04-26
65 | 152/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-01 | Completed |  | 2024-05-09
66 | 147B/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-04-30 | Completed |  | 2024-05-10
67 | 152/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-05 | Completed |  | 2024-05-14
68 | 147/4 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-04 | Completed |  | 2024-05-17
69 | 106A/4 | DA+9 | WET PADDY | 623377 | 40.634 | 2024-05-06 | Completed |  | 2024-05-16
70 | 135A/1 | DD45+3 | WET PADDY |  | 131.047 | 2024-05-07 | Completed |  | 2024-05-26
71 | 150A/1 | DA+3 | WET | 986514 | 65.631 | 2024-05-08 | Completed |  | 2024-05-22
72 | 147/3 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-16 | Completed |  | 2024-05-29
73 | 147/6 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-05-15 | Completed |  | 2024-05-25
74 | 106B/2 | DA+6 | WET PADDY | 623377 | 40.634 | 2024-05-15 | Completed |  | 2024-05-24
75 | 106B/0 | DB2+9 | WET PADDY | 2143792.36 | 65.135 | 2024-04-24 | Completed |  | 2024-06-06
76 | 106A/3 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-05-19 | Completed |  | 2024-06-10
77 | 147/1 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-20 | Completed |  | 2024-06-08
78 | 147/2 | DC1+0 | Wet Paddy |  | 79.994 | 2024-05-20 | Completed |  | 2024-06-03
79 | 152/0 | DC2+0 | Wet Paddy |  | 92.292 | 2024-05-19 | Completed |  | 2024-05-30
80 | 135A/2 | DB2+9 | Wet Paddy | 2143792.36 | 65.135 | 2024-05-21 | Completed |  | 2024-06-17
81 | 152/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-25 | Completed |  | 2024-05-31
82 | 119/2 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-08 | Completed |  | 2024-06-15
83 | 119/1 | DA-3 | WET PADDY | 545016 | 39.126 | 2024-06-04 | Completed |  | 2024-06-08
84 | 105/0 | DD60+35 | Pile Foundation |  | 861.114 | 2024-11-25 | Completed. | Completed. | 2025-01-17 |  | Jai Mata Di
85 | 119/3 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-05-29 | Completed |  | 2024-06-03
86 | 147A/0 | DB1+18 | WET PADDY | 1330245 | 61.574 | 2024-06-05 | Completed |  | 2024-06-14
87 | 144/1 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-11 | Completed |  | 2024-06-18
88 | 150A/0 | DC1+0 | WET |  | 117.033 | 2024-05-29 | Completed |  | 2024-06-11
89 | 144/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-06-16 | Completed |  | 2024-06-26
90 | 148/4 | DA+0 | WET PADDY | 545016 | 39.126 | 2024-06-13 | Completed |  | 2024-06-20
91 | 106/0 | DD60+9 | Wet Paddy |  | 180.61 | 2024-05-21 | Completed |  | 2024-07-15 |  | JMD
92 | 109/0 | DB2+0 | Wet Paddy | 1196479 | 62.882 | 2024-07-02 | Completed |  | 2024-07-14 |  | Integar
93 | 116A/0 | DC1+0 | Wet Paddy |  | 79.994 | 2024-07-08 | Completed |  | 2024-07-17 |  | B K Traders
94 | 115/0 | DC2+25 | Wet Paddy |  | 103.703 | 2024-07-08 | Completed |  | 2024-07-31 |  | Prince
95 | 118/0 | DD45+0 | Wet Paddy |  | 128.427 | 2024-07-09 | Completed |  | 2024-07-17 |  | Alamin Construction
96 | 121/0 | DD60+18 | WET PADDY |  | 201.075 | 2024-06-15 | Completed |  | 2024-07-18 |  | H K Construction
| 143A/5 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-06-19 | Completed |  | 2024-07-13 |  | Himanshi Agency
| 119/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-10 | Completed. |  | 2024-08-14 |  | Jeet Infra (Departmental Gang)
| 117/0 | DD60+3 | WET PADDY |  | 180.61 | 2024-07-16 | Completed |  | 2024-07-31 |  | Alamin Construction
| 116/0 | DD45+18 | WET PADDY |  | 151.172 | 2024-07-17 | Completed. |  | 2024-08-17 |  | B K Traders
| 110/0 | DB2+0 | WET PADDY | 1196479 | 62.882 | 2024-07-16 | Completed |  | 2024-07-31 |  | Jyoti Construction (Departmental Gang)
| 114/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-07-31 | Completed. |  | 2024-08-13 |  | Prince
| 111/0 | DC1+0 | WET PADDY |  | 79.994 | 2024-08-03 | Completed. |  | 2024-08-21 |  | Jyoti Construction (Departmental Gang)
| 123/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-03 | Completed. |  | 2024-08-11 |  | Alamin Construction
| 124A/1 | DA+3 | WET PADDY | 623377 | 40.634 | 2024-08-16 | Completed. |  | 2024-08-18 |  | Alamin Construction
| 108/0 | DD45+0 | WET PADDY |  | 128.427 | 2024-08-14 | Completed. |  | 2024-09-20 |  | Prince
| 120/0 | DD60+9 | WET PADDY |  | 180.61 | 2024-08-17 | Completed |  | 2024-09-15 | Work hampered due to rain | Jeet Infra (Departmental Gang) | Completed | 2024-09-16
| 116B/0 | DD45+6 | WET PADDY |  | 131.047 | 2024-08-18 | Completed. |  | 2024-09-20 | No work due to approach road damaged badly. | B K Traders
| 125/0 | DD60+6 | WET PADDY |  | 180.61 | 2024-08-21 | Completed. | Complete. | 2024-11-07 |  | Alamin Construction
| 122/0 | DC1+6 | WET PADDY |  | 82.223 | 2024-08-22 | Completed. |  | 2024-09-22 |  | Haaji Saheb | Completed | 2024-09-24
| 125A/0 | DB2+3 | WET PADDY | 2143792.36 | 65.135 | 2024-09-12 | Completed |  | 2024-10-19 |  | Jyoti Construction (Departmental Gang)
| 134/0 | DC2+25 | WPS |  | 103.7 | 2024-09-21 | Completed | Complete. | 2024-10-26 |  | Jeet Infra (Departmental Gang)
| 123/1 | DA+3 | WPS | 623377 | 40.36 | 2024-09-20 | Completed. |  | 2024-10-05 |  | Prince
| 124/0 | DC1+3 | WPS |  | 82.223 | 2024-09-20 | Completed |  | 2024-10-06 |  | B K Traders
| 126/1 | DA+6 | WPS | 623377 | 40.63 | 2024-09-24 | Completed |  | 2024-10-11 |  | Hajji Saheb | Completed | 2024-10-14
| 128/0 | DD60+6 | WPS |  | 180.61 | 2024-09-24 | Completed |  | 2024-10-22 |  | Alamin Construction
118 | 106A/2 | DA-3 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | Completed. | 2024-12-05 |  | Verma
120 | 129/0 | DD60+6 | WPS |  | 180.61 | 2024-10-07 | Completed. | Completed. | 2024-11-12 | No work due to approach road issues. | Prince Construction
121 | 132/0 | DC2+3 | WPS |  | 94.746 | 2024-10-15 | Completed. | Completed. | 2024-11-13 | No work due to waterlogged. | Hajji Saheb
122 | 137/0 | DC2+9 (3M RC) | WPS |  | 112.877 | 2024-10-15 | Completed. | Completed. | 2024-12-23 |  | Himashi
123 | 130/1 | DA+0 | WPS | 545016 | 39.126 | 2024-10-28 | Completed. |  | 2024-11-20 |  | Haji Saheb
124 | 137A/6 | DA+9 | WPS | 623377 | 40.634 | 2024-10-28 | Completed. | Completed. | 2024-12-05 |  | Suresh Choudhary
126 | 148/0 | DC2+0 | Wet |  | 134.785 | 2024-11-05 | Completed. |  | 2024-11-20 |  | Himanshi Construction
128 | 124A/0 | DD60+0 | WPS |  | 178.19 | 2024-11-07 | Completed. | Completed. | 2024-11-14 |  | Alamin
129 | 135A/0 | DC1+0 | PS |  | 138.086 | 2024-11-11 | Completed. | Completed. | 2024-12-08 |  | Niraj Tiwari
130 | 146/0 | DC1+9 | WBC |  | 192.814 | 2024-12-12 | Completed. | Completed. | 2024-12-25 |  | Himanshi
131 | 143A/3 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | Completed. | 2024-12-11 |  | Madhav Constr.
132 | 132/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-18 | Completed. |  | 2024-11-27
133 | 148/1 | DA+3 | WET | 986514 | 65.631 | 2024-11-18 | Completed. |  | 2024-11-27
134 | 148/2 | DA+0 | WPS | 545016 | 39.126 | 2024-11-19 | Completed. |  | 2024-11-26
| 106A/0 | DC2+0 | PS |  | 168.913 | 2024-11-18 | Completed. | Completed. | 2024-12-18 |  | Rawat Construction
| 106A/1 | DA+6 | PS | 1215596 | 83.812 | 2024-11-23 | Completed. | Completed. | 2024-12-10 |  | Rawat Construction
| 116A/1 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | Completed. | 2024-11-23
| 130/3 | DA+0 | WPS | 545016 | 39.126 | 2024-11-22 | Completed. | Completed. | 2024-12-02 |  | Hajji Saheb
| 136/0 | DD45+18(3M RC) | WPS |  | 161.632 | 2024-11-19 | Completed. | Completed. | 2024-12-28 |  | Lala rams
| 143A/4 | DA+0 | WPS | 545016 | 39.126 | 2024-11-21 | Completed. | Completed. | 2024-12-23 |  | Lalhusain
| 130/4 | DA+3 | WPS | 623377 | 40.634 | 2024-11-24 | Completed. | Completed. | 2024-11-30
| 137/5 | DA+3 | WPS | 623377 | 40.634 | 2024-11-22 | Completed | Completed. | 2024-12-31 |  | Himanshi-01
| 147B/1 | DA+0 | WET | 881091 | 63.346 | 2024-11-25 | Completed. | Completed. | 2024-12-05 |  | Himanshi-01
| 148/3 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | Completed. | 2024-12-05 |  | BK Traders
| 157/1 | DA+0 | PS | 1086615 | 80.771 | 2024-11-23 | Completed. | Completed. | 2024-12-20 |  | Anya Construction
| 159/4 | DA+0 | FS | 1287409 | 91.088 | 2024-11-26 | Completed. | Completed. | 2024-12-03 |  | Alamin
| 131/0 | DD45+3 | WPS |  | 131.047 | 2024-11-18 | Completed. | Completed. | 2024-12-06 |  | Arvind singh
| 137/6 | DA+0 | WPS | 545016 | 39.126 | 2024-11-24 | Completed. | Completed. | 2024-12-14 |  | Shree Krishna Const.
| 164/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-11 | Completed. | Completed. | 2024-11-28 |  | Tes Transco
| 159/1 | DA+0 | FS | 1287409 | 91.088 | 2024-11-27 | Completed. | Completed. | 2024-12-14 |  | Rudra Associate
| 148/5 | DA+0 | WET | 881091 | 63.346 | 2024-11-24 | Completed. | Completed. | 2024-12-10 |  | Himanshi
| 161/0 | DD60+25 | PS |  | 341.95 | 2024-12-01 | Completed | Completed. | 2024-12-30 |  | Tes Transco
| 130/2 | DA+3 | WPS | 623377 | 40.634 | 2024-11-30 | Completed. | Completed. | 2024-12-07 |  | haji saheb
| 137A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-15 | Completed. | Completed. | 2024-12-29 |  | Shree Krishna Const.
| 137A/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-01 | Completed. | Completed. | 2024-12-20 |  | Rabari Vankabhai
| 135/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-02 | Completed. | Completed. | 2024-12-24 |  | haji saheb
| 135A/5 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | Completed. | 2024-12-31 |  | Lal Hussain
| 135A/6 | DA+0 | WPS | 545016 | 39.126 | 2024-12-02 | Completed. | Completed. | 2024-12-17 |  | Neeraj Tiwari | Completed. | 2024-12-18
| 163/0 | DC2+0 | FS |  | 193.49 | 2024-12-14 | Completed. | Completed. | 2024-12-29 |  | Lala Ram
| 135/0 | DC2+25 | WPS |  | 103.703 | 2024-12-02 | Completed. | Completed. | 2024-12-20 |  | Haaji Saheb
| 138/1 | DA+6 | WPS | 623377 | 40.634 | 2024-12-03 | Completed. | Completed. | 2024-12-20 |  | Suresh Choudhary
| 152A/0 | DB1+0 | WPS | 1017007 | 54.675 | 2024-12-16 | Completed. | Completed. | 2024-12-24 |  | BK Traders
| 164/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-04 | Completed. | Completed. | 2024-12-14 |  | Lala Ram
| 138/0 | DB2+0 | WPS | 1196479 | 62.882 |  | Completed. | Completed. | 2024-12-17 |  | Nav Durga
| 141/1 | DA+0 | WPS | 545016 | 39.126 | 2024-12-15 | Completed. | Completed. | 2024-12-27 |  | SA Enterprises
| 147/0 | DC2+9 | WPS |  | 94.746 | 2024-12-07 | Completed. | Completed. | 2024-12-18 |  | Himanshi
| 140/0 | DD60+0 | WPS |  | 178.19 | 2024-12-13 | Completed. | Completed. | 2024-12-23 |  | Nav Durga
| 141/0 | DD60+3 | WPS |  | 180.61 | 2024-12-16 | Completed. | Completed. | 2024-12-29 |  | Nav Durga
| 141/2 | DA-3 | WPS | 545016 | 39.126 | 2024-12-11 | Completed. | Completed. | 2024-12-27 |  | Pratibha
| 141/3 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | Completed. | 2024-12-31 |  | Pratibha
| 145A/0 | DB1+6 | WPS | 1108538 | 54.992 | 2024-12-13 | Completed. | Completed. | 2024-12-21 |  | Himanshi
| 153/0 | DD60+25(1M RC) | Wet |  | 602.294 | 2024-12-18 | Completed. | Completed. | 2024-12-30 |  | BK Traders
| 157/3 | DA+0 | FS | 1287409 | 91.088 | 2024-12-18 | Completed. | Completed. | 2024-12-24 |  | Maa Bhawani
| 159/2 | DCT+0 | FS |  | 158.016 | 2025-01-02 | Completed. | Completed. | 2025-01-13 | DC2+0 | NR road Contr.
| 139/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-18 | Completed. | Completed. | 2024-12-24 |  | PR Construction
| 139A/0 | DB2+9 | WPS | 2143792.36 | 65.135 | 2024-12-19 | Completed. | Completed. | 2024-12-31 |  | Lala Ram
| 149/1 | DA+0 | Wet | 881091 | 63.346 | 2024-12-24 | Completed | Completed. | 2024-12-29 |  | Himanshi
| 137A/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-21 | Completed. | Completed. | 2024-12-30 |  | Rabari Vankabhai
| 139/1 | DA+3 | WPS | 623377 | 40.634 | 2024-12-22 | Completed. | Completed. | 2024-12-28 |  | Rawat Construction
| 148/6 | DA+0 | Wet | 881091 | 63.346 | 2025-01-03 | Completed | Completed. | 2025-01-06 |  | Himanshi
| 148/7 | DA+0 | Wet | 881091 | 63.346 | 2025-01-04 | Completed. | Completed. | 2025-01-08 |  | Himanshi
| 149/0 | DB2+0 | Wet | 1880164 | 89.905 | 2024-12-23 | Completed | Completed. | 2024-12-31 |  | Himanshi
| 157/0 | DD60+6 | PS |  | 309.952 | 2025-01-12 | Completed. | Completed. | 2025-01-29 |  | Anya Constr.
| 157/2 | DA+0 | FS | 1287409 | 91.088 | 2024-12-27 | Completed. | Completed. | 2025-01-07 |  | Anya Construction.
| 138/2 | DA+0 | WPS | 545016 | 39.126 | 2024-12-27 | Completed. | Completed. | 2025-01-03 |  | SA Enterprises
| 139/0 | DB2+0 | WPS | 1196479 | 62.882 | 2024-12-28 | Completed. | Completed. | 2025-01-04 |  | Nav Durga
| 160/0 | DD60+18 | FS |  | 39.682 | 2024-12-28 | Completed. | Completed. | 2025-01-13 |  | Haji Saheb
| 101/0 | DD60+35(6M RC) | FS |  | 440.345 | 2025-01-01 | Completed. | Completed. | 2025-02-02 |  | Rawat Construction
| 162/0 | DD60+25 | PS |  | 341.95 | 2025-01-03 | Completed. | Completed. | 2025-01-24 |  | BK Traders
| 142/0 | DD60+0 | WPS |  | 178.19 | 2025-01-07 | Completed. | Completed. | 2025-01-16 |  | Nav Durga
| 150/1 | DA+9 | Wet | 986514 | 65.631 | 2025-01-07 | Completed. | Completed. | 2025-01-12 |  | Himanshi
| 150/2 | DA+3 | Wet | 986514 | 65.631 | 2025-01-12 | Completed. | Completed. | 2025-01-16 |  | Himanshi
| 150/3 | DA+6 | WPS | 623377 | 40.634 | 2025-01-15 | Completed. | Completed. | 2025-01-18 |  | Himanshi
| 150/0 | DD60+9 | Wet |  | 255.731 | 2025-01-11 | Completed. | Completed. | 2025-01-28 |  | Himanshi
| 158/2 | DA-3 | FS | 1287409 | 91.088 | 2025-01-10 | Completed. | Completed. | 2025-01-23 |  | Haaji Saheb
| 143A/0 | DD45+0 | WPS |  | 128.427 | 2025-01-15 | Completed | Completed. | 2025-01-20 |  | Nav Durga
| 151/0 | DB2+3 | WPS | 2143792.36 | 65.135 | 2025-01-20 | Completed. | Completed. | 2025-01-27 |  | Himanshi
| 154/1 | DD45+25(11.96 M RC) | PILE |  |  | 2025-01-24 | Completed. | Completed. | 2025-05-11 |  | Harshi
| 158/0 | DB2+0 | FS | 2986642.46 | 132.205 | 2025-01-23 | Completed. | Completed. | 2025-01-30 |  | NR road Contr.
| 158/1 | DA-3 | PS | 1086615 | 80.771 | 2025-01-23 | Completed. | Completed. | 2025-01-31 |  | NR road Contr.
| 143/0 | DD60+3 | WPS |  | 180.61 | 2025-01-18 | Completed. | Compeleted. | 2025-01-28 |  | Nav Durga
| 145A/2 | DA+3 | WPS | 623377 | 40.634 | 2025-01-19 | Completed. | Completed. | 2025-01-23 |  | Himanshi
| 143A/2 | DD45+0 | WPS |  | 128.427 | 2025-01-30 | Completed. | Completed. | 2025-02-10 |  | Nav Durga
| 143A/1 | DA+6 | WPS | 623377 | 40.634 | 2025-01-28 | Completed. | Completed. | 2025-01-31 |  | Nav Durga
| 155/4 | DA+0 | Wet | 881091 | 63.346 |  | Completed. | Completed. | 2025-04-12 |  | Nav Durga
| 102/0 | DD45+35(11.84M RC) | Pile |  |  | 2025-03-06 | Completed. | Completed. | 2025-06-28 |  | AK Construction
| 135/7 | DA+0 | WPS | 545016 | 39.126 | 2025-03-26 | Completed. | Completed. | 2025-04-03
| 154/0 | DD45+25(10.96 M RC) | Pile |  |  | 2025-04-04 | No work. | All pile completed. Pit D pile cap casting done. |  |  | KND
| 155/5 | DA+0 | WET | 881091 | 63.346 | 2025-04-13 | Completed. | Completed. | 2025-04-16 |  | Nav Durga
| 103/0 | DD45+25 | Pile |  |  | 2025-05-23 | No work. | All pile(16) completed. Pit A pile cap shuttering worku/p. Pit D pile cap shuttering work u/p. |  |  | Choudhry Construction
17956.57

## FDN-NVSR
Foundation Part-II (NAVSARI SECTION)
Sl. No. | Location No. | Tower Type | Classification | Revenue | Concreting Volume in M3 | Trial pit start date | Start Date | Todays Status | Cumulative Status | End Date | Remarks | Sub-Contractor Name | Manpower | Earthing Status | Earthing Completed Date | Hindrance total days | Hindance details
1 | 197/3 | DA+0 | PS | 1086615 | 80.771 |  | 2023-08-18 | Completed. | Completed. | 2023-08-31 |  |  |  | Completed
2 | 195A/3 | DA+0 | PS | 1086615 | 80.771 |  | 2023-08-22 | Completed. | Completed. | 2023-10-01 |  |  |  | Completed
3 | 165/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-10-20 | Completed. | Completed. | 2023-11-03 |  |  |  | Completed
4 | 167/2 | DA+6 | WET | 986514 | 65.631 |  | 2023-11-13 | Completed. | Completed. | 2023-11-30 |  |  |  | Completed
5 | 167/3 | DA+6 | WET PADDY | 623377 | 40.634 |  | 2023-11-23 | Completed. | Completed. | 2023-11-30 |  |  |  | Completed
6 | 167/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-09 | Completed. | Completed. | 2023-12-15 |  |  |  | Completed
7 | 195/3 | DA+6 | PS | 1215596 | 83.812 |  | 2023-12-07 | Completed. | Completed. | 2023-12-26 |  |  |  | Completed
8 | 195/4 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-26 | Completed. | Completed. | 2024-01-12 |  |  |  | Completed
9 | 164/2 | DA+0 | WET | 881091 | 63.346 |  | 2023-12-28 | Completed. | Completed. | 2024-01-17 |  |  |  | Completed
10 | 163/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-17 | Completed. | Completed. | 2024-01-23 |  |  |  | Completed
11 | 165/0 | DB2+0 | PS | 2481749.46 | 115.247 |  | 2024-01-09 | Completed. | Completed. | 2024-01-21 |  |  |  | Completed
12 | 163/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-24 | Completed. | Completed. | 2023-01-29 |  |  |  | Completed
13 | 164/7 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-18 | Completed. | Completed. | 2024-01-29 |  |  |  | Completed
14 | 163/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-01-29 | Completed. | Completed. | 2024-02-05 |  |  |  | Completed
15 | 165/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-01-30 | Completed. | Completed. | 2024-02-09 |  |  |  | Completed
16 | 163/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-08 | Completed. | Completed. | 2024-02-13 |  |  |  | Completed
17 | 159/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-09 | Completed. | Completed. | 2024-02-16
18 | 163/5 | DA+0 | FS | 1287409 | 91.088 |  | 2024-02-14 | Completed. | Completed. | 2024-02-23 |  |  |  | Completed
19 | 164/5 | DA+0 | WFR | 947845 | 60.634 |  | 2024-02-12 | Completed. | Completed. | 2024-02-23
20 | 165/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-02-13 | Completed. | Completed. | 2024-02-28 |  |  |  | Completed
21 | 163/6 | DA+0 | FS | 1287409 | 91.088 |  | 2024-02-22 | Completed. | Completed. | 2024-02-29 |  |  |  | Completed
22 | 164/6 | DA+0 | PS | 1086615 | 80.771 |  | 2024-03-11 | Completed. | Completed. | 2024-03-22 |  |  |  | Completed
23 | 165/3 | DA+6 | WET | 986514 | 65.631 |  | 2024-02-28 | Completed. | Completed. | 2024-03-10 |  |  |  | Completed
24 | 191/0 | DD45+25 | WET | 4465782 | 224.07 |  | 2024-03-06 | Completed. | Completed. | 2024-03-17 |  |  |  | Completed
25 | 187/3 | DA+0 | PS | 1086615 | 80.771 |  | 2024-03-09 | Completed. | Completed. | 2024-03-20 |  |  |  | Completed
26 | 191/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-03-16 | Completed. | Completed. | 2024-03-21 |  |  |  | Completed
27 | 164/4 | DA+0 | WFR | 947845 | 60.634 |  | 2024-03-11 | Completed. | Completed. | 2024-03-22
28 | 257/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-03-18 | Completed. | Completed. | 2024-03-30 |  |  |  | Completed
29 | 189/0 | DB2+6 | WET | 2143792.36 | 94.918 |  | 2024-03-22 | Completed. | Completed. | 2024-03-31 |  |  |  | Completed
30 | 159/0 | DB1+0 | WET | 1598139 | 79.944 |  | 2024-03-26 | Completed. | Completed. | 2024-04-04 |  |  |  | Completed
31 | 188/0 | DB1+6 | WET | 1741972 | 80.469 |  | 2024-04-01 | Completed. | Completed. | 2024-04-07 |  |  |  | Completed
32 | 187/2 | DA-3 | FS | 1287409 | 91.088 |  |  | Completed. | Completed. | 2024-04-13 |  |  |  | Completed
33 | 191A/1 | DA-3 | FS | 1287409 | 91.088 |  | 2024-04-14 | Completed. | Completed. | 2024-04-21 |  |  |  | Completed
34 | 267A/0 | DC2+9 (2M RC) | WET |  | 151.836 |  | 2024-04-13 | Completed. | Completed. | 2024-04-28 | RC done on 17-12-2024 | Jayesh Electrical |  | Completed
35 | 155/3 | DA+3 | WET | 986514 | 65.631 |  | 2024-04-08 | Completed. | Completed. | 2024-04-25 |  |  |  | Completed
36 | 262/1 | DA+0 | WET | 881091 | 63.346 |  | 2024-04-13 | Completed. | Completed. | 2024-04-27 |  |  |  | Completed
37 | 257/2 | DA-3 | WET | 881091 | 63.346 |  | 2024-04-21 | Completed. | Completed. | 2024-04-30 |  |  |  | Completed
38 | 193/0 | DD60+6 | WET | 4251845 | 255.731 |  | 2024-04-21 | Completed. | Completed. | 2024-04-30 |  |  |  | Completed
39 | 267A/3 | DA+0 | WET | 881091 | 63.346 |  | 2024-04-30 | Completed. | Completed. | 2024-05-08 |  |  |  | Completed
40 | 264/0 | DC1+6 | WET | 2633913 | 120.461 |  | 2024-05-01 | Completed. | Completed. | 2024-05-11
41 | 257/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-05-03 | Completed. | Completed. | 2024-05-10 |  |  |  | Completed
42 | 155/0 | DD60+0 | WET | 3915704.88 | 252.474 |  | 2024-04-16 | Completed. | Completed. | 2024-05-11 |  |  |  | Completed
43 | 261/0 | DC2+18 | WET | 3336290 | 149.965 |  | 2024-05-03 | Completed. | Completed. | 2024-05-10 |  |  |  | Completed
44 | 191A/0 | DB2+0 | WET | 1880164 | 89.905 |  | 2024-04-25 | Completed. | Completed. | 2024-05-13 |  |  |  | Completed
45 | 265/0 | DB2+3 | WET | 2143792.36 | 94.918 |  | 2024-04-27 | Completed. | Completed. | 2024-05-12 |  |  |  | Completed
46 | 267A/2 | DA-3 | WET | 881091 | 63.346 |  | 2024-04-27 | Completed. | Completed. | 2024-05-15 |  |  |  | Completed
47 | 268/0 | DD60+6 | WET | 4251845 | 255.731 |  | 2024-05-12 | Completed. | Completed. | 2024-05-22 |  |  |  | Completed
48 | 267/0 | DC1+9 (2M RC) | WET |  | 139.849 |  | 2024-05-10 | Completed. | Completed. | 2024-05-21 | RC done o 16-12-2024. | Jayesh Electrical
49 | 195/0 | DC2+0 | PS | 3206945.94 | 168.913 |  | 2024-05-14 | Completed. | Completed. | 2024-05-24 | Again completed on 16-04-2025 |  |  | Completed
50 | 270/2 | DA+3 | WET | 986514 | 65.631 |  | 2024-05-20 | Completed. | Completed. | 2024-05-26 |  |  |  | Completed
51 | 270/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-05-27 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
52 | 271/5 | DA-3 | WET | 881091 | 63.346 |  | 2024-05-26 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
53 | 262/0 | DD45+9 | WET | 3953330 | 192.374 |  | 2024-05-13 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
54 | 257/0 | DC2+0 | WET | 2530056 | 134.785 |  | 2024-05-29 | Completed. | Completed. | 2024-06-01 |  |  |  | Completed
55 | 260/0 | DD60+18 | WBC |  | 448.208 |  |  | Completed. | Completed. | 2024-05-31 |  |  |  | Completed
56 | 272/1 | DA+9 | WET | 986514 | 65.631 |  | 2024-06-05 | Completed. | Completed. | 2024-06-12 |  |  |  | Completed
57 | 272/0 | DC1+6 | WET | 2633913 | 120.461 |  | 2024-06-04 | Completed. | Completed. | 2024-06-13 |  |  |  | Completed
58 | 269/0 | DD60+0 | WET | 3915704.88 | 252.474 |  | 2024-06-03 | Completed. | Completed. | 2024-06-14 |  |  |  | Completed
59 | 255/4 | DA+0 | WPS | 545016 | 39.126 |  | 2024-06-14 | Completed. | Completed. | 2024-06-21 |  |  |  | Completed
60 | 259/0 | DD60+18 | PS | 5611385.97 | 341.95 |  | 2024-06-14 | Completed. | Completed. | 2024-07-11
61 | 158A/0 | DD45+6 | WET | 3953330 | 192.374 |  | 2024-07-01 | Completed. | Completed. | 2024-07-30 |  | Kudiyaar |  | Completed
62 | 263/0 | DC2+0 | PS | 3206945.94 | 168.913 |  | 2024-10-09 | Completed. | Completed. | 2024-10-29 |  | Tes Transco | 23 | Completed | 2024-11-03
64 | 254/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2024-08-04 | Completed. | Completed. | 2024-08-22 |  |  |  | Completed
65 | 267A/1 | DA+0 | FS | 1287409 | 91.088 |  | 2024-08-14 | Completed. | Completed. | 2024-09-23 |  | Rudra Associate |  | Completed
66 | 251/0 | DB1+9 | FS |  | 113.896 |  | 2024-09-04 | Completed. | Completed. | 2024-09-19 |  | Kudiyaar |  | Completed
67 | 255/0 | DD60+3 | FS | 5918512 | 351.748 |  | 2024-09-13 | Completed. | Completed. | 2024-10-10 |  | Tes Transco |  | Completed
68 | 169/0 | DD45+18 | PS | 5320583 | 257.278 |  | 2024-10-22 | Completed. | Completed. | 2024-11-06 |  | M/s Rajesh Singh | 18
69 | 168/2 | DA+0 | FS | 1287409 | 91.088 |  | 2024-10-07 | Completed. | Completed. | 2024-10-24 |  | M/s Rajesh Singh
71 | 155/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-10-03 | Completed. | Completed | 2024-10-24 |  | Jyoti Const. |  | Completed | 2024-10-23
72 | 155/2 | DA+3 | PS | 1215596 | 83.812 |  | 2024-10-03 | Completed. | Completed | 2024-10-11 |  | Jyoti Const. |  | Completed | 2024-10-13
74 | 155/6 | DA-3 | PS | 1086615 | 80.771 |  | 2024-10-15 | Completed. | Completed. | 2024-10-29 |  | M/s Rudra Associate | 14 | Completed | 2024-10-30
76 | 158B/2 | DA+3 | PS | 1215596 | 83.812 |  | 2024-10-20 | Completed. | Completed. | 2024-10-26 |  | Maa Bhawani |  | Completed
77 | 164/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2024-10-21 | Completed. | Completed. | 2024-11-07 |  | Tes Transco | 28
78 | 158B/0 | DD45+18 | PS | 5320583 | 257.278 |  | 2024-10-24 | Completed. | Completed. | 2024-10-31 |  | Maa Bhawani | 20 | Completed
79 | 171/0 | DD60+25 (3M RC) | PS |  | 353.162 |  | 2024-10-26 | Completed. | Completed | 2024-11-19 |  | Jyoti Const. | 14
80 | 156/0 | DD60+3 | PS | 5188063.13 | 309.952 |  | 2024-10-30 | Completed. | Completed | 2024-11-24 |  | Rudra Associate | 14
83 | 158B/1 | DA+3 | PS | 1215596 | 83.812 |  | 2024-11-06 | Completed. | Completed. | 2024-11-09 |  | Maa Bhawani |  | Completed
84 | 272A/0 | DB1+18 (2M RC) | PS |  | 117.99 |  | 2024-11-05 | Completed. | Completed | 2024-11-13 |  | Tes Transco |  | Completed | 2024-11-15
85 | 272A/2 | DA+0 | WET | 881091 | 63.346 |  | 2024-11-06 | Completed. | Completed | 2024-11-13 |  | Tes Transco |  | Completed | 2024-11-14
86 | 272A/1 | DA+6 | WET | 986514 | 65.631 |  | 2024-11-07 | Completed. | Completed | 2024-11-17 |  | Tes Transco |  | Completed | 2024-11-19
87 | 168/1 | DA-3 | Wet | 881091 | 63.346 |  | 2024-11-09 | Completed. | Completed. | 2024-11-18 |  | M/s Rajesh Singh
88 | 197/4 | DA+0 | WET | 881091 | 63.346 |  | 2024-11-08 | Completed. | Completed. | 2024-11-10 |  | Maa Bhawani
90 | 197/0 | DD60+9 | Wet | 4251845 | 255.731 |  | 2024-11-12 | Completed. | Completed. | 2024-11-18 |  | Maa Bhawani
91 | 255/3 | DA+3 | Wet | 986514 | 65.631 |  | 2024-11-13 | Completed. | Completed. | 2024-11-21 |  | Paresh mahto | 15 | Completed
92 | 198/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2024-11-13 | Completed. | Completed. | 2024-11-30 |  | M/s Rajesh Singh
93 | 266/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2024-11-15 | Completed. | Completed. | 2024-11-22 |  | Tes Transco |  | Completed | 2024-11-22
94 | 196/0 | DD60+9 | WBC |  | 401.731 |  | 2024-11-16 | Completed. | Completed. | 2024-11-30 |  | Maa Bhawani
95 | 198/1 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-17 | Completed. | Completed. | 2024-12-12 |  | Kumar
96 | 272/7 | DA+9 (2M RC) | Wet |  | 71.29 |  | 2024-11-20 | Completed. | Completed. | 2024-12-10 |  | Tes Transco |  | Completed
97 | 272/2 | DA-3 | Wet | 881091 | 63.346 |  | 2024-11-18 | Completed. | Completed. | 2024-11-26 |  | Tes Transco |  | Completed | 2024-11-28
98 | 197/1 | DA+0 | PS | 1086615 | 80.771 |  | 2024-11-18 | Completed. | Completed. | 2024-11-22 |  | Maa Bhawani
99 | 272/5 | DB1+0 | Wet | 1598139 | 79.944 |  | 2024-11-23 | Completed. | Completed. | 2024-11-30 |  | Tes Transco |  | Completed.
100 | 269/1 | DA+0 | WeT | 881091 | 63.346 |  | 2024-11-23 | Completed. | Completed. | 2024-11-29 |  | Paresh |  | Completed.
101 | 197/2 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-25 | Completed. | Completed | 2024-11-30 |  | Maa Bhawani
102 | 271/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2024-11-23 | Completed. | Completed. | 2024-11-30 |  | Tes Transco |  | Completed.
103 | 271/3 | DA-3 | WBC | 1686873 | 109.919 |  | 2024-12-01 | Completed. | Completed. | 2024-12-08 |  | Jayesh Electrical |  | Completed.
| 185/1 | DA+9 | Wet | 986514 | 65.631 |  | 2024-11-28 | Completed. | Completed. | 2024-11-30 |  | Jyoti
105 | 270/4 | DA+0 | Wet | 881091 | 63.346 |  | 2024-11-28 | Completed. | Completed. | 2024-12-20 |  | Maa Bhawani(Jitu)
106 | 166/0 | DD60+6 | PS | 5188063.13 | 309.952 |  | 2024-11-28 | Completed. | Completed. | 2024-12-10 |  | Jyoti Constr.
107 | 192/0 | DC1+0 | PS | 3074652.99 | 138.086 |  | 2024-11-29 | Completed. | Completed. | 2024-12-14 |  | M/s Rajesh Singh
108 | 266/0 | DB1+0 | Wet | 1598139 | 79.944 |  | 2024-12-01 | Completed. | Completed. | 2024-12-08 |  | Kastabhaja |  | Completed.
109 | 195A/0 | DB1+0 | PS | 2122856.48 | 98.821 |  | 2024-11-30 | Completed. | Completed. | 2024-12-28 |  | Hari Krishna
110 | 190/0 | DD45+25 | Wet | 4465782 | 224.07 |  | 2024-11-30 | Completed. | Completed. | 2024-12-31 |  | Tes transco
111 | 182A/0 | DD45+6(2M RC) | PS |  | 239.926 |  | 2024-12-02 | Completed. | Completed. | 2024-12-22 |  | Jyoti
112 | 270/7 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-01 | Completed. | Completed. | 2024-12-06 |  | Tes Trasnsco |  | Completed.
113 | 178/0 | DD60+6 | PS | 5188063.13 | 309.952 |  | 2024-12-23 | Completed. | Completed. | 2024-12-31 |  | Jyoti
114 | 195A/2 | DA+6 | FS | 1442822 | 94.623 |  | 2024-12-07 | Completed. | Completed. | 2024-12-12 |  | Maa Bhawanis
115 | 275/0 | DD45+0(2M RC) | Wet |  | 206.583 |  | 2024-12-09 | Completed. | Completed. | 2024-12-23 |  | Tes Transco |  | Completed. | 2024-12-23
116 | 272/4 | DA+3 | Wet | 986514 | 65.631 |  | 2024-12-08 | Completed. | Completed. | 2024-12-12 |  | Tes Transco |  | Completed.
117 | 273/2 | DA+6 | Wet | 986514 | 65.631 |  | 2024-12-09 | Completed. | Completed. | 2024-12-15 |  | Kastabhanja |  | Completed. | 2024-12-15
118 | 255/2 | DA+0 | Wet | 881091 | 63.346 |  | 2024-12-10 | Completed. | Completed. | 2024-12-15 |  | Jayesh Electrical |  | Completed.
119 | 173/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2024-12-10 | Completed. | Completed. | 2024-12-24 |  | Value Constr.
120 | 167/1 | DA+9 | FS | 1442822 | 94.623 |  | 2024-12-21 | Completed. | Completed. | 2024-12-28 |  | Sukhriddin
121 | 272/3 | DA+3 | Wet | 986514 | 65.631 |  | 2024-12-14 | Completed. | Completed. | 2024-12-21 |  | Tes transco |  | Completed
122 | 191/2 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-14 | Completed. | Completed. | 2024-12-21 |  | Khodiyar Krupa
123 | 172/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2024-12-16 | Completed. | Completed. | 2025-01-04 |  | Khodiyar Krupa
124 | 172/1 | DA+3 | PS | 1215596 | 83.812 |  | 2024-12-24 | Completed. | Completed. | 2024-12-28 |  | Value Constr.
125 | 195/1 | DA+6 | PS | 1215596 | 83.812 |  | 2024-12-30 | Completed | Completed | 2025-01-07 |  | Hari Krishna
126 | 191/3 | DA-3 | PS | 1086615 | 80.771 |  | 2024-12-17 | Completed. | Completed. | 2024-12-24 |  | Khodiyar Krupa
127 | 276/0 | DD60+0(2M RC) | Wet |  | 265.697 |  | 2024-12-18 | Completed. | Completed. | 2024-12-31 |  | Kastabhanja
128 | 270A/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2024-12-18 | Completed. | Completed. | 2024-12-31 |  | Tes transco |  | Completed | 2024-12-31
129 | 257/1 | DA+0 | FS | 1287409 | 91.088 |  | 2024-12-18 | Completed. | Completed | 2024-12-31 |  | Jayesh Electrical |  | Completed | 2024-12-31
130 | 272A/6 | DA-3 | Wet | 881091 | 63.346 |  | 2024-12-22 | Completed. | Completed. | 2024-12-29 |  | Tes Transco |  | Completed | 2024-12-31
131 | 186/0 | DD60+35 | Wet | 7665610 | 315.149 |  | 2024-12-28 | Completed. | Completed. | 2025-04-04 | Again start date is 30-03-2025 | Sukhriddin
132 | 272A/3 | DA+0 | Wet | 881091 | 63.346 |  | 2024-12-28 | Completed. | Completed. | 2025-01-03 |  | Tes Transco |  | Completed. | 2025-01-04
133 | 184/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2024-12-28 | Completed. | Completed | 2025-01-08 |  | Maa Bhawani
134 | 172/2 | DA+6 | PS | 1215596 | 83.812 |  | 2024-12-29 | Completed. | Completed. | 2025-01-04 |  | Value Constr.
135 | 274/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-02 | Completed. | Completed. | 2025-01-11 |  | Tes Transco |  | Completed | 2025-01-13
136 | 269/2 | DA+6 | PS | 1215596 | 83.812 |  | 2025-01-02 | Completed. | Completed | 2025-01-08 |  | Jayesh Electrical |  | Completed | 2025-01-08
137 | 179/0 | DD60+0 | WBC |  | 396.566 |  | 2024-12-31 | Completed. | Completed. | 2025-01-18 |  | Jyoti
138 | 255/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-01-02 | Completed. | Completed. | 2025-01-07 |  | Kastabhanja
139 | 272A/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-02 | Completed. | Completed | 2025-01-08 |  | Tes Transco |  | Completed | 2025-01-08
140 | 272A/5 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-04 | Completed. | Completed. | 2025-01-11 |  | Tes Transco |  | Completed | 2025-01-13
141 | 272A/7 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-05 | Completed. | Completed. | 2025-01-12 |  | Tes Transco
142 | 270/3 | DA-3 | WBC | 1686873 | 109.919 |  | 2025-01-07 | Completed. | Completed. | 2025-01-17 |  | Tes Transco
143 | 189/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-06 | Completed | Completed | 2025-01-09 |  | Value Constr.
144 | 167/0 | DD60+0 | WBC |  | 396.566 |  | 2025-01-06 | Completed. | Completed. | 2025-01-18 |  | Sukhriddin
146 | 248/6 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-08 | Completed. | Completed | 2025-01-11 |  | Kastabhanja
147 | 249/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-01-14 | Completed. | Completed. | 2025-01-19 |  | Khodiyar Krupa
148 | 249/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-07 | Completed. | Completed. | 2025-01-10 |  | Khodiyar Krupa |  | Completed | 2025-01-18
149 | 249/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-11 | Completed. | completed. | 2025-01-13 |  | Khodiyar Krupa |  | Completed | 2025-01-18
150 | 195/5 | DA+6 | WBC | 1821043 | 113.924 |  | 2025-01-08 | Completed. | Completed. | 2025-01-16 |  | Hari Krishna
153 | 250/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-01-14 | Completed. | Completed. | 2025-01-23 |  | Jayesh Electrical |  | Completed. | 2025-01-23
154 | 249/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-10 | Completed. | Completed. | 2025-01-13 |  | Jayesh Electrical
155 | 253/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-08 | Completed | Completed. | 2025-01-19 |  | Tes Transco
156 | 250/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-12 | Completed. | Completed. | 2025-01-16 |  | Kastabhanja
157 | 252/0 | DC1+18 | Wet | 3216269 | 131.849 |  | 2025-01-17 | Completed. | Completed. | 2025-01-24 |  | Kastabhanja
158 | 209/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-09 | Completed. | Completed. | 2025-01-17 |  | Velly Constr.
159 | 209/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-13 | Completed. | Completed. | 2025-01-20 |  | Velly Constr.
160 | 211/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-13 | Completed. | Completed. | 2025-01-19 |  | Tower Foundation
161 | 211/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-21 | Completed | Compleed. | 2025-01-25 |  | Tower Foundation
162 | 218/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-12 | Completed. | Completed. | 2025-01-19 |  | Tes Transco
164 | 219/0 | DC2+18 | Wet | 3336290 | 149.965 |  | 2025-01-12 | Completed. | Completed. | 2025-01-25 |  | Tes Transco
167 | 208/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-01-20 | Completed. | Completed. | 2025-01-29 |  | Velly
168 | 215/0 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-01-12 | Completed. | Completed. | 2025-01-18 |  | BLG Infratech
169 | 213/0 | DD60+3 | WBC |  | 401.731 |  | 2025-01-16 | Completed. | Completed. | 2025-02-04 |  | Tes Transco
171 | 200/0 | DB2+18 | Wet | 2472338 | 111.669 | 2025-01-11 | 2025-01-19 | Completed. | Completed. | 2025-01-31 |  | Hari Krishna
173 | 271/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-14 | Completed | Completed. | 2025-01-21 |  | Tes Transco
174 | 270/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-20 | Completed. | Completed. | 2025-01-28 |  | Tes Transco
175 | 270/6 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-18 | Completed. | Completed. | 2025-01-24 |  | Tes Transco
176 | 215/1 | DA+9 | Wet | 986514 | 65.631 |  | 2025-01-17 | Completed. | Completed. | 2025-01-22 |  | BLG
181 | 213/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-23 | Completed. | Completed. | 2025-01-31 |  | Tes Transco
182 | 180/0 | DD45+9 (3M RC) | Wet |  | 213.318 |  | 2025-01-25 | Completed. | Completed. | 2025-01-31 |  | Jyoti
183 | 181/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-20 | Completed. | Completed. | 2025-01-23 |  | Jyoti
184 | 206/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-01-21 | Completed. | Completed. | 2025-01-28 |  | Sukhridin
185 | 211A/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-21 | Completed. | Completed. | 2025-01-25 |  | Khodiyar
186 | 271/4 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-23 | Completed. | Completed. | 2025-01-29 |  | Tes Transco
187 | 224/0 | DC2+6 | Wet | 2772635 | 138.207 |  | 2025-01-23 | Completed. | Completed. | 2025-01-30 |  | Khodiyar
188 | 211A/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-02-02 | Completed. | Completed. | 2025-02-08 |  | Tower foundation
189 | 227/0 | DB1+6 | PS | 2075500 | 99.33 |  | 2025-01-26 | Completed. | Completed. | 2025-02-04 |  | Ammu Eng.
190 | 248/4 | DA+3 | Wet | 986514 | 65.631 |  | 2025-01-25 | Completed. | Completed. | 2025-01-29 |  | Kastabhanja
191 | 266/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-25 | Completed. | Completed. | 2025-01-29 |  | Jayesh Electrical
192 | 223/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-01-26 | Completed. | Completed. | 2025-01-31 |  | BLG
193 | 205/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-01-29 | Completed. | Completed. | 2025-01-31 |  | Sukhridin
196 | 248/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-29 | Completed. | Completed. | 2025-01-31 |  | Kastabhanja
197 | 211A/2 | DA+0 | Wet | 881091 | 63.346 |  | 28-01-202 | Completed. | Completed. | 2025-01-31 |  | Tower Foundation
198 | 270/0 | DD45+0 | FS | 5295995.92 | 266.818 |  | 2025-01-30 | Completed. | Completed. | 2025-02-10 |  | Jayesh Electrical
200 | 223/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-01-30 | Completed. | Completed. | 2025-02-02 |  | Khodiyar
202 | 214/0 | DD45+0 | PS | 4512711.95 | 233.46 |  | 2025-01-31 | Completed. | Completed. | 2025-02-17 |  | Tes Transco
203 | 229/3 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-01 | Completed. | Completed. | 2025-02-05 |  | Velly Constr.
204 | 199/0 | DD45+18 | Wet | 4465782 | 224.07 |  | 02-02-025 | Completed. | Completed. | 2025-02-13 |  | Hari Krishna
205 | 181/0 | DD45+18 | Wet | 4465782 | 224.07 |  | 2025-02-02 | Completed. | Completed. | 2025-02-08 |  | Jyoti
206 | 225/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-03 | Completed. | Completed. | 2025-02-07 |  | BLG
207 | 225/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-04 | Completed. | Completed. | 2025-02-12 |  | Khodiyar
208 | 229/0 | DD60+18 | WBC |  | 448.208 |  | 2025-02-02 | Completed. | Completed. | 2025-02-11 |  | Sukhridin
209 | 226/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2025-02-03 | Completed. | Completed. | 2025-02-10 |  | Kastabhanja
210 | 214/1 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-03 | Completed. | Completed. | 2025-02-12 |  | Tes Transco
211 | 220/0 | DD45+9 | Wet | 3953330 | 192.374 |  | 2025-02-02 | Completed. | Completed. | 2025-02-11 |  | Tes Transco
212 | 229/5 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-05 | Completed. | Completed. | 2025-02-08 |  | Velly Constr.
213 | 233/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-02-07 | Completed. | Competed. | 2025-02-15 |  | Ammu Engg.-1
214 | 220/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-07 | Completed. | Completed. | 2025-02-16 |  | Tes Transco
215 | 231/0 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-02-09 | Completed. | Completed. | 2025-02-18 |  | BLG
217 | 212/0 | DD45+3 | Wet | 3953330 | 192.374 |  | 2025-02-10 | Completed. | Completed. | 2025-02-21 |  | Tower Foundation
218 | 230/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-10 | Completed. | Completed. | 2025-02-17 |  | Velly Constr.
219 | 174/0 | DD60+18 | FS | 6685851 | 390.682 |  | 2025-02-11 | Completed. | Completed. | 2025-02-22 |  | Jyoti
220 | 229/2 | DA+6 | Wet | 986514 | 65.631 |  | 2025-02-10 | Completed. | Completed. | 2025-02-13 |  | Murgan
221 | 221/0 | DD60+18 | FS | 6685851 | 390.682 |  | 2025-02-11 | Completed. | Completed. | 2025-02-25 |  | Tes Transco
222 | 222/0 | DD60+25 | FS | 6685851 | 390.682 |  | 2025-02-13 | Completed. | Completed. | 2025-02-23 |  | Kastbhanja
223 | 205/0 | DD60+3 (2M RC) | Wet |  | 282.692 |  | 2025-02-13 | Completed. | Completed. | 2025-02-20 |  | Sukhridin
224 | 237/6 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-12 | Completed. | Completed. | 2025-02-16 |  | Jayesh Electrical
225 | 237/0 | DD45+9 (3M RC) | Wet |  | 213.318 |  | 2025-02-14 | Completed. | Completed. | 2025-02-23 |  | Khodiyar
226 | 234/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-02-13 | Completed. | Completed. | 2025-02-21 |  | Ammu Engg.
227 | 223/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-14 | Completed. | Completed. | 2025-02-18 |  | Murgan
228 | 198/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-16 | Completed. | Completed. | 2025-02-23 |  | Hari Krishna
229 | 187/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-02-17 | Completed. | Completed. | 2025-03-03 |  | Jyoti-2
230 | 235/0 | DC2+3 | PS |  | 162.896 |  | 2025-02-17 | Completed. | Completed. | 2025-02-28 |  | Ammu Engg.
231 | 245/1 | DA+0 | FS | 1287409 | 91.088 |  | 2025-02-16 | Completed. | Completed. | 2025-02-22 |  | Neelkanth | 25
232 | 217A/1 | DA+3 | PS | 1215596 | 83.812 |  | 2025-02-17 | Completed. | Completed. | 2025-02-25 |  | Tes Transco
233 | 240/0 | DD60+25 | FS | 6685851 | 390.682 |  | 2025-02-18 | Completed. | Completed. | 2025-02-28 |  | Jayesh Electrical
235 | 248/2 | DA+9 | Wet | 986514 | 65.631 |  | 2025-02-18 | Completed. | Completed. | 2025-02-24 |  | Ketan
236 | 223/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-18 | Completed. | Completed. | 2025-02-21 |  | Murgan
237 | 232/0 | DD60+3 | Wet | 4251845 | 255.731 |  | 2025-02-19 | Completed. | Completed. | 2025-02-28 |  | Velly Constr
238 | 242/0 | DB1+0 | FS |  | 113.343 |  | 2025-02-19 | Completed. | Completed. | 2025-02-27 |  | Tes Trasnsco
239 | 242/2 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-18 | Completed. | Completed. | 2025-02-21 |  | BLG
241 | 184/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-02-20 | Completed. | Completed. | 2025-02-26 |  | Arvind
242 | 195/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-21 | Completed. | Completed. | 2025-02-26 |  | Himanshi
243 | 203/1 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-02-21 | Completed. | Completed. | 2025-02-28 |  | Sukhriddin
244 | 237/4 | DA+0 | PS | 1086615 | 80.771 |  | 2025-02-22 | Completed. | Completed. | 2025-02-27 |  | Tower Foundation
245 | 247/1 | DA+0 | FS | 1287409 | 91.088 |  | 2025-02-23 | Completed. | Completed. | 2025-02-26 |  | Murgan
246 | 237/5 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-23 | Completed. | Completed. | 2025-02-28 |  | Ammu Engg-1
247 | 273/1 | DA+6 | WBC | 1821043 | 113.924 |  | 2025-02-22 | Completed. | Completed. | 2025-02-27 |  | Neelkanth
248 | 247/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-24 | Completed. | Completed. | 2025-02-27 |  | BLG
249 | 181/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Jyoti
250 | 247/2 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-24 | Completed. | Completed. | 2025-02-28 |  | Neel Kanth
251 | 272/6 | DA+3 | FS | 1442822 | 94.623 |  | 2025-02-26 | Completed. | Completed. | 2025-03-04 |  | New Gang
252 | 248/1 | DA+9 | Wet | 986514 | 65.631 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Ketan
253 | 217A/2 | DA+0 | PS | 1086615 | 80.771 |  | 2025-02-25 | Completed. | Completed. | 2025-02-28 |  | Tes Transco
254 | 216/0 | DB2+25(2M RC) | Wet |  | 120.61 |  | 2025-02-27 | Completed. | Completed. | 2025-03-12 |  | Tes Transco
255 | 205/2 | DA+3 | Wet | 986514 | 65.631 |  | 2025-02-26 | Completed. | Completed. | 2025-02-28 |  | Kastbahana
256 | 201/0 | DC2+18 | Wet | 3336290 | 149.965 |  | 2025-02-26 | Completed. | Completed. | 2025-03-06 |  | Hari Krishna
257 | 237/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-02-24 | Completed. | Completed. | 2025-02-27 |  | Khodiyar
258 | 237/2 | DA-3 | Wet | 881091 | 63.346 |  | 2025-02-26 | Completed. | Completed. | 2025-02-28 |  | Khodiyar
259 | 182/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-02-27 | Completed. | Completed. | 2025-03-13 |  | Arvind
260 | 185/0 | DC2+0 | Wet | 2530056 | 134.785 |  | 2025-02-27 | Completed. | Completed. | 2025-03-13 |  | Himanshi
261 | 247/0 | DD60+0 | FS | 5576159.92 | 346.952 |  | 2025-02-27 | Completed. | Completed. | 2025-03-12 |  | Murgan
263 | 211/0 | DB1+9 | Wet | 1741972 | 80.469 |  | 2025-03-02 | Completed. | Completed. | 2025-03-16 |  | Tower foundation
264 | 244/0 | DC1+9 | WBC |  | 197.882 |  | 2025-03-01 | Completed. | Completed. | 2025-03-13 |  | BLG
265 | 228/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2025-03-01 | Completed. | Completed. | 2025-05-28 | Again start date is 14-05-2025 | Kastabhanja
266 | 204/0 | DD60+9 | Wet | 4251845 | 255.731 |  | 2025-03-02 | Completed. | Completed. | 2025-03-08 |  | Sukhriddin
267 | 210/0 | DB2+18 | Wet | 2472338 | 111.669 |  | 2025-03-02 | Completed. | Completed. | 2025-03-20 |  | Tes Trasnsco
268 | 241/0 | DB2+9 | WBC | 3850981 | 173.061 |  | 2025-03-23 | Completed. | Completed. | 2025-04-06 |  | Jayesh Electrical
269 | 246/0 | DD60+0 | PS | 4780790.5 | 306.052 |  | 2025-03-02 | Completed. | Completed. | 2025-03-21 |  | Khodiyar
270 | 271/1 | DA-3 | FS | 1287409 | 91.088 |  | 2025-03-03 | Completed. | Completed. | 2025-03-13 |  | Neekl Kanta
273 | 236/0 | DB2+0 | Wet | 1880164 | 89.905 |  | 2025-03-02 | Completed. | Completed. | 2025-03-19 |  | Ammu Engg.
274 | 237/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Ammu
275 | 242/1 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-02 | Completed. | Completed. | 2025-03-06 |  | Tes Transco
277 | 181/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-06 |  | Jyoti
279 | 187/1 | DA+3 | Wet | 986514 | 65.631 |  | 2025-03-04 | Completed. | Completed. | 2025-03-10 |  | Jyoti
280 | 247/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Khodiyar
281 | 248/3 | DA+6 | Wet | 986514 | 65.631 |  | 2025-03-03 | Completed. | Completed. | 2025-03-07 |  | Ketan
282 | 248/0 | DC2+9 | Wet | 2772635 | 138.207 |  | 2025-03-09 | Completed. | Completed. | 2025-03-26 |  | Ketan
283 | 242/3 | DA-3 | Wet | 881091 | 63.346 |  | 2025-03-10 | Completed. | Completed. | 2025-03-13 |  | Khodiyar
284 | 181/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-13 | Completed. | Completed. | 2025-03-20 |  | Himanshi
285 | 218/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-03-10 | Completed. | Completed. | 2025-03-31 |  | Tes Transcvo
286 | 168/0 | DC1+0 | Wet | 2328166.27 | 117.033 |  | 2025-03-13 | Completed. | Completed. | 2025-03-27 |  | Ammu Engg.
287 | 203/0 | DD60+55(4.5M RC) | WBC |  | 768.133 |  | 2025-03-09 | Completed. | Completed. | 2025-03-31 |  | Sukhriddin
288 | 177/0 | DD60+0 | PS | 4780790.5 | 306.052 |  | 2025-03-12 | Completed. | Completed. | 2025-03-22 |  | Jyoti
289 | 175/1 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-16 | Completed. | Completed. | 2025-03-19 |  | Arvind
290 | 245/0 | DD45+0 | FS | 5295995.92 | 266.818 |  | 2025-03-16 | Completed. | Completed. | 2025-03-26 |  | BLG
293 | 229/4 | DA+0 | Wet | 881091 | 63.346 |  | 2025-03-14 | Completed. | Completed. | 2025-03-17 |  | Tes Transco
294 | 222/1 | DB1+3 | Wet | 1741972 | 80.469 |  | 2025-03-14 | Completed. | Completed. | 2025-03-17 |  | Kastabhanja
295 | 217A/0 | DB1+3 | Wet | 1741972 | 80.469 |  | 2025-03-19 | Completed. | Completed. | 2025-03-23 |  | Kastabhanja
296 | 217/0 | DD45+25(2M RC) | Wet |  | 231.258 |  | 2025-03-18 | Completed. | Completed. | 2025-03-31 |  | Tes Transco
297 | 194/0 | DD60+6 | Wet | 4251845 | 255.731 |  | 2025-03-19 | Completed. | Completed. | 2025-03-31 |  | Himanshi |  |  |  | 04 days idle due to 02 pit in row
298 | 175/0 | DD45+0 | Wet | 3743190.59 | 189.081 |  | 2025-03-22 | Completed. | Completed. | 2025-03-28 |  | Arvind
299 | 243/0 | DB1+9 | FS |  | 113.896 |  | 2025-03-23 | Completed. | Completed. | 2025-03-29 |  | Khodiyar
300 | 174/1 | DB1+0 | PS | 2122856.48 | 98.821 |  | 2025-03-26 | Completed. | Completed. | 2025-03-30 |  | Jyoti
301 | 195A/1 | DA+6 | FS | 1442822 | 94.623 |  | 2025-03-25 | Completed. | Completed. | 2025-03-29 |  | kastabhanja
302 | 229/1 | DB1+6 | Wet | 1741972 | 80.469 |  | 2025-03-25 | Completed. | Completed. | 2025-04-07 |  | Tes Transco
303 | 244/1 | DB1+9 | WBC |  | 138.164 |  | 2025-03-27 | Completed. | Completed. | 2025-03-31 |  | BLG
304 | 201/1 | DD60+9 (2M RC) | Wet | 5379537 | 282.692 |  | 2025-03-30 | Completed. | Completed. | 2025-04-09 |  | Kastabbhanja
305 | 239/0 | DD60+25 | Wet | 4801423 | 298.554 |  | 2025-04-01 | Completed. | Completed. | 2025-04-11 |  | Khodiyar Krupa
306 | 202/0 | DD60+55(4.5M RC) | WBC |  | 768.133 |  | 2025-04-05 | Completed. | Completed. | 2025-05-06 |  | Sukhriddin | 18 |  | 2025-05-09
307 | 183/0 | DD60+25 | PS | 5611385.97 | 341.95 |  | 2025-04-07 | Completed. | Completed. | 2025-04-20 |  | Tes Transco | 26
308 | 273/0 | DB2+0 | FS | 2986642.46 | 132.205 |  | 2025-05-01 | Completed. | Completed. | 2025-06-13 | Again start date is 06-06-2025 | Kastabhanja |  |  |  |  | Hindrance from 02-05-2025 to continue
309 | 176/0 | DD60+0 | Wet | 3915704.88 | 252.474 |  | 2025-05-15 | Completed. | Completed. | 2025-05-23 |  | Jyoti
310 | 175/2 | DA+0 | Wet | 881091 | 63.346 |  | 2025-05-18 | Completed. | Completed. | 2025-05-22 |  | Himanshi Construction
311 | 166/0 | DD60+6 | FS |  |  |  | 2025-08-17 | Pit C excavation is u/p. | Pit D excavation u/p. |  |  | Kastabhanja
38482.842

## Erection Compiled
Sl. No. | Location No. | Type | Type of Tower | Starting Date | Revenue | Tower Weight | Todays Status | Completion Date | Gang Name
1 | 104/0 | DD60 | DD60+35 |  |  | 172.151 | Completed | 2025-08-13
2 | 106/0 | DD60 | DD60+9 | 2024-10-03 | 753337 | 98.836 | Completed. | 2024-12-08 | DK Verma
3 | 106A/0 | DC | DC2+0 | 2024-12-29 | 470077 | 64.254 | Completed. | 2025-01-03 | DK Verma
4 | 106A/1 | DA | DA+6 | 2024-12-22 | 342192 | 44.728 | Completed | 2024-12-28 | DK Verma
5 | 106A/2 | DA | DA-3 | 2024-12-19 | 273608.93 | 36.045 | Completed. | 2024-12-28 | Barkat Ali
6 | 106A/3 | DA | DA+3 | 2024-06-25 | 297143 | 39.459 | Completed | 2024-07-02 | Gourishankar
7 | 106A/4 | DA | DA+9 | 2024-06-14 | 357181 | 46.623 | Completed | 2024-06-24 | Gourishankar
8 | 106B/0 | DB | DB2+9 | 2024-08-08 | 503365 | 65.757 | Completed. | 2024-08-24 | Rahul Kumar
9 | 106B/1 | DA | DA+9 | 2024-07-28 | 357181 | 46.263 | Completed. | 2024-08-08 | Ajay Kumar
10 | 106B/2 | DA | DA+6 | 2024-07-02 | 342192 | 44.728 | Completed | 2024-07-12 | Gourishankar
11 | 107/0 | DD45 | DD45+0 | 2024-07-13 | 546238 | 72.238 | Completed | 2024-07-29 | Gourishankar
12 | 107/1 | DA | DA-3 | 2024-09-16 | 273608.93 | 36.045 | Completed. | 2024-09-26 | Barkat Ali
13 | 108/0 | DD45 | DD45+0 | 2024-09-28 | 546238 | 72.238 | Completed. | 2024-10-13 | DK Verma
14 | 109/0 | DB | DB2+0 | 2024-08-11 | 403998 | 54.418 | Completed | 2024-08-23 | Gourishankar
15 | 110/0 | DB | DB2+0 | 2024-08-18 | 403998 | 54.418 | Completed | 2024-08-31 | Rahul Kumar
16 | 111/0 | DC | DC1+0 | 2024-09-09 | 470077 | 64.254 | Completed. | 2024-09-21 | Rahul Kumar
17 | 112/0 | DD45 | DD45+0 | 2024-06-05 | 546238 | 72.238 | Completed | 2024-06-13 | Gourishankar
18 | 113/0 | DD60 | DD60+0 | 2024-07-08 | 604881 | 80.408 | Completed | 2024-07-25 | Ajay Kumar
19 | 114/0 | DD45 | DD45+0 | 2024-09-02 | 546238 | 72.238 | Completed | 2024-09-13 | Gourishankar
20 | 115/0 | DC | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Gourishankar
21 | 116/0 | DD45 | DD45+18 | 2024-09-10 | 906755 | 112.424 | Completed. | 2024-09-27 | Dhaneswar Mahto
22 | 116A/0 | DC | DC1+0 | 2024-07-30 | 470077 | 64.254 | Completed. | 2024-08-11 | Gourishankar
23 | 116A/1 | DA | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-21 | DK Verma
24 | 116B/0 | DD45 | DD45+6 | 2024-10-13 | 650023 | 85.234 | Completed. | 2024-10-31 | Ajay Kumar
25 | 117/0 | DD60 | DD60+3 | 2024-11-20 | 635073 | 84.299 | Completed. | 2024-12-03 | Gourishankar
26 | 118/0 | DD45 | DD45+0 | 2024-08-01 | 546238 | 72.238 | Completed. | 2024-08-20 | Rahul Kumar
27 | 119/0 | DD45 | DD45+0 | 2024-09-12 | 546238 | 72.238 | Completed. | 2024-09-24 | Ajay Kumar
28 | 119/1 | DA | DA-3 | 2024-09-14 | 273608.93 | 36.045 | Completed. | 2024-09-23 | Gourishankar
29 | 119/2 | DA | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-12 | Rahul Kumar
30 | 119/3 | DA | DA+0 | 2024-07-13 | 286911 | 37.73 | Completed | 2024-07-18 | Rahul Kumar
31 | 120/0 | DD60 | DD60+9 | 2024-10-01 | 753337 | 98.836 | Completed | 2024-10-24 | Gourishankar
32 | 121/0 | DD60 | DD60+18 | 2024-09-23 | 1003256 | 129.341 | Completed. | 2024-10-10 | Rahul Kumar
33 | 122/0 | DC | DC1+6 | 2024-10-04 | 559332 | 74.632 | Completed. | 2024-10-15 | Gourishankar
34 | 123/0 | DD60 | DD60+6 | 2024-09-26 | 719574 | 94.408 | Completed. | 2024-10-10 | Ajay Kumar
35 | 123/1 | DA | DA+3 | 2024-10-17 | 297143 | 39.459 | Completed | 2024-10-31 | Gourishankar
36 | 124/0 | DC | DC1+3 | 2024-10-28 | 493565 | 66.268 | Completed. | 2024-11-11 | Ajay Kumar
37 | 124A/0 | DD60 | DD60+0 | 2024-12-21 | 604881 | 80.408 | Completed. | 2025-01-05 | Gourishankar
38 | 124A/1 | DA | DA+3 | 2024-09-16 | 297143 | 39.459 | Completed. | 2024-09-30 | Senahul
39 | 125/0 | DD60 | DD60+0 | 2024-12-22 | 604881 | 80.408 | Completed. | 2025-01-05 | MJR
40 | 125A/0 | DB | DB2+3 | 2024-11-02 | 424198 | 56.863 | Completed. | 2024-11-13 | Gourishankar
41 | 126/0 | DC | DC2+0 | 2024-07-20 | 470077 | 64.254 | Completed | 2024-07-31 | Rahul Kumar
42 | 126/1 | DA | DA+6 | 2024-12-21 | 342192 | 44.728 | Completed. | 2024-12-27 | Gourishankar
43 | 127/0 | DD45 | DD45+0 | 2024-05-31 | 546238 | 72.238 | Completed | 2024-06-10 | Lalan Mahto
44 | 127/1 | DA | DA+0 | 2023-09-30 | 286911 | 37.73 | Completed | 2023-10-15 | Ghanshyam Mahto
45 | 127/2 | DA | DA+0 | 2023-10-16 | 286911 | 37.73 | Completed | 2023-10-29 | Ghanshyam Mahto
46 | 127/3 | DA | DA+0 | 2024-05-25 | 286911 | 37.73 | Completed | 2024-05-31 | Lalan Mahto
47 | 127/4 | DA | DA+3 | 2024-05-19 | 297143 | 39.459 | Completed | 2024-05-24 | Lalan Mahto
48 | 127/5 | DA | DA+3 | 2024-11-27 | 297143 | 39.459 | Completed. | 2024-12-07 | Ajay Kumar
49 | 128/0 | DD60 | DD60+6 | 2024-11-13 | 719574 | 94.408 | Completed. | 2024-11-26 | Ajay Kumar
50 | 129/0 | DD60 | DD60+6 | 2024-12-30 | 719574 | 94.408 | Completed. | 2025-01-18 | Barkat Ali
51 | 129A/0 | DC | DC1+0 | 2024-04-25 | 470077 | 64.254 | Completed | 2024-04-30 | Lalan Mahto
52 | 129A/1 | DA | DA+0 | 2024-05-02 | 286911 | 37.73 | Completed | 2024-05-07 | Lalan Mahto
53 | 129A/2 | DA | DA+3 | 2024-05-07 | 297143 | 39.459 | Completed | 2024-05-12 | Lalan Mahto
54 | 130/0 | DB | DB1+0 | 2024-05-07 | 403998 | 54.418 | Completed | 2024-05-18 | Lalan Mahto
55 | 130/1 | DA | DA+0 | 2025-01-25 | 286911 | 37.73 | Completed. | 2025-02-09 | SK Samuil
56 | 130/2 | DA | DA+3 | 2025-01-20 | 297143 | 39.459 | Completed. | 2025-01-29 | MJR
57 | 130/3 | DA | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-18 | MJR
58 | 130/4 | DA | DA+3 | 2024-12-22 | 297143 | 39.459 | Completed. | 2025-01-21 | SK Samuil
59 | 131/0 | DD45 | DD45+3 | 2025-01-21 | 573550 | 75.452 | Completed. | 2025-02-05 | Barkat Ali
60 | 132/0 | DC | DC2+3 | 2024-12-08 |  | 66.268 | Completed. | 2024-12-21 | SK Samuil
61 | 132/1 | DA | DA+0 | 2024-12-22 | 286911 | 37.73 | Completed. | 2024-12-30 | SK Samuil
62 | 132/2 | DA | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-13 | Lalan Mahto
63 | 132/3 | DA | DA+0 | 2024-06-12 | 286911 | 37.73 | Completed | 2024-06-18 | Lalan Mahto
64 | 133/0 | DB | DB1+0 | 2024-02-13 | 403998 | 54.418 | Completed | 2024-02-21 | Lalan Mahto
65 | 133/1 | DA | DA+0 | 2023-12-02 | 286911 | 37.73 | Completed | 2023-12-15 | Ghanshyam Mahto
66 | 133/2 | DA | DA+0 | 2024-02-27 | 286911 | 37.73 | Completed | 2024-03-03 | Lalan Mahto
67 | 133/3 | DA | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-28 | Lalan Mahto
68 | 133/4 | DA | DA+0 | 2024-04-20 | 286911 | 37.73 | Completed | 2024-04-24 | Lalan Mahto
69 | 133/5 | DA | DA+0 | 2024-03-03 | 286911 | 37.73 | Completed | 2024-03-08 | Lalan Mahto
70 | 133A/0 | DB | DB1+0 | 2024-03-08 | 403998 | 54.418 | Completed | 2024-03-13 | Lalan Mahto
71 | 133A/1 | DA | DA+0 | 2024-03-13 | 286911 | 37.73 | Completed | 2024-03-13 | Lalan Mahto
72 | 133A/2 | DA | DA+6 | 2024-04-13 | 342192 | 44.728 | Completed | 2024-04-19 | Lalan Mahto
73 | 133A/3 | DA | DA+0 | 2024-02-15 | 286911 | 37.73 | Completed | 2024-02-20 | Poonam Kumari
74 | 133A/4 | DA | DA+6 | 2024-09-27 | 342192 | 44.728 | Completed. | 2024-10-12 | Mithun Kumar
75 | 134/0 | DC | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Dhaneswar Mahto
76 | 135/0 | DC | DC2+25 | 2025-01-09 |  | 109.628 | Completed. | 2025-01-22 | DK Verma
77 | 135/1 | DA | DA+6 | 2025-01-06 | 342192 | 44.728 | Completed. | 2025-01-11 | Surender Mahto
78 | 135/2 | DA | DA+0 | 2023-11-11 | 286911 | 37.73 | Completed | 2023-11-17 | Ghanshyam Mahto
79 | 135/3 | DA | DA+0 | 2024-02-26 | 286911 | 37.73 | Completed | 2024-03-02 | Poonam Kumari
80 | 135/4 | DA | DA+0 | 2024-05-31 | 286911 | 37.73 | Completed | 2024-06-10 | Intizer Infratech
81 | 135/5 | DA | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-31 | Intizer Infratech
82 | 135/6 | DA | DA+0 | 2024-05-01 | 286911 | 37.73 | Completed | 2024-05-19 | Intizer Infratech
83 | 135/7 | DA | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-22 | SK Samuil
84 | 135A/0 | DC | DC1+0 | 2024-12-27 | 470077 | 64.254 | Completed. | 2025-01-04 | Dhaneswar Mahto
85 | 135A/1 | DD45 | DD45+3 | 2024-10-08 | 573550 | 75.452 | Completed. | 2024-11-03 | Dhaneswar Mahto
86 | 135A/2 | DB | DB2+9 | 2024-11-05 | 503365 | 65.757 | Completed. | 2024-11-13 | Dhaneswar Mahto
87 | 135A/3 | DA | DA+0 | 2024-01-23 | 286911 | 37.73 | Completed | 2024-01-28 | Poonam Kumari
88 | 135A/4 | DA | DA+0 | 2023-11-01 | 286911 | 37.73 | Completed | 2023-11-09 | Ghanshyam Mahto
89 | 135A/5 | DA | DA+0 | 2025-01-13 | 286911 | 37.73 | Completed. | 2025-01-18 | Dhaneswar Mahto
90 | 135A/6 | DA | DA+0 | 2024-12-21 | 286911 | 37.73 | Completed. | 2024-12-26 | Dhaneswar Mahto
91 | 135A/7 | DA | DA+0 | 2023-11-19 | 286911 | 37.73 | Completed | 2023-12-01 | Ghanshyam Mahto
92 | 135B/0 | DB | DB1+0 | 2024-02-02 | 403998 | 54.418 | Completed | 2024-02-09 | Poonam Kumari
93 | 135B/1 | DA | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-26 | Poonam Kumari
94 | 135B/2 | DA | DA+0 | 2024-01-18 | 286911 | 37.73 | Completed | 2024-01-23 | Poonam Kumari
95 | 135B/3 | DA | DA+0 | 2024-01-12 | 286911 | 37.73 | Completed | 2024-01-18 | Poonam Kumari
96 | 135B/4 | DA | DA+6 | 2024-01-04 | 342192 | 44.728 | Completed | 2024-01-12 | Poonam Kumari
97 | 135B/5 | DA | DA+0 | 2024-01-28 | 286911 | 37.73 | Completed | 2024-02-02 | Poonam Kumari
98 | 135B/6 | DA | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-15 | Poonam Kumari
99 | 135B/7 | DA | DA+3 | 2024-03-02 | 297143 | 39.459 | Completed | 2024-04-11 | Poonam Kumari
100 | 136/0 | DD45 | DD45+18 | 2025-01-09 | 906755 | 112.424 | Completed. | 2025-01-25 | Gourishankar
101 | 137/0 | DC | DC2+9 | 2025-02-01 | 585620 | 77.718 | Completed. | 2025-02-15 | MJR
102 | 137/1 | DA | DA+3 | 2024-05-25 | 297143 | 39.459 | Completed | 2024-05-31 | Rahul Kumar
103 | 137/2 | DA | DA+0 | 2025-02-18 | 286911 | 37.73 | Completed. | 2025-02-27 | MJR
104 | 137/3 | DA | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-24 | Rahul Kumar
105 | 137/4 | DA | DA+0 | 2024-05-07 | 286911 | 37.73 | Completed | 2024-05-18 | Rahul Kumar
106 | 137/5 | DA | DA+3 | 2025-02-03 | 297143 | 39.459 | Completed. | 2025-02-07 | Dhaneswar Mahto
107 | 137/6 | DA | DA+0 | 2025-01-27 | 286911 | 37.73 | Completed. | 2025-02-07 | SK Samuil
108 | 137A/0 | DB | DB1+0 | 2025-01-23 | 403998 | 54.418 | Completed. | 2025-01-29 | DK Verma
109 | 137A/1 | DA | DA+6 | 2025-01-27 | 342192 | 44.728 | Completed. | 2025-01-29 | Dhaneswar Mahto
110 | 137A/2 | DA | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-02 | Dhaneswar Mahto
111 | 137A/3 | DA | DA+6 | 2024-11-20 | 342192 | 44.728 | Completed. | 2024-11-28 | Dhaneswar Mahto
112 | 137A/4 | DA | DA-3 | 2024-11-29 | 273608.93 | 36.045 | Completed. | 2024-12-03 | Dhaneswar Mahto
113 | 137A/5 | DA | DA-3 | 2024-11-14 | 273608.93 | 36.045 | Completed. | 2024-11-20 | Dhaneswar Mahto
114 | 137A/6 | DA | DA+9 | 2025-01-20 | 357181 | 46.623 | Completed. | 2025-01-24 | Dhaneswar Mahto
115 | 138/0 | DB | DB2+0 | 2025-01-27 | 403998 | 54.418 | Completed. | 2025-02-01 | Gourishankar
116 | 138/1 | DA | DA+6 | 2025-02-03 | 342192 | 44.728 | Completed. | 2025-02-09 | Gourishankar
117 | 138/2 | DA | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-11 | DK Verma
118 | 139/0 | DB | DB2+0 | 2025-01-30 | 403998 | 54.418 | Completed. | 2025-02-04 | DK Verma
119 | 139/1 | DA | DA+3 | 2025-02-12 | 297143 | 39.459 | Completed. | 2025-02-17 | DK Verma
120 | 139/2 | DA | DA+0 | 2025-02-10 | 286911 | 37.73 | Completed. | 2025-02-14 | Gourishankar
121 | 139A/0 | DB | DB2+9 | 2025-02-09 | 503365 | 65.757 | Completed. | 2025-02-14 | Dhaneswar Mahto
122 | 140/0 | DD60 | DD60+0 | 2025-02-16 | 604881 | 80.408 | Completed. | 2025-02-22 | Dhaneswar Mahto
123 | 141/0 | DD60 | DD60+3 | 2025-02-16 | 635073 | 84.299 | Completed. | 2025-02-23 | Gourishankar
124 | 141/1 | DA | DA+0 | 2025-02-11 | 286911 | 37.73 | Completed. | 2025-02-17 | SK Samuil
125 | 141/2 | DA | DA-3 | 2025-02-13 | 273608.93 | 36.045 | Completed. | 2025-02-19 | SK Samuil
126 | 141/3 | DA | DA+3 | 2025-02-19 | 297143 | 39.459 | Completed. | 2025-02-25 | SK Samuil
127 | 142/0 | DD60 | DD60+0 | 2025-02-18 | 604881 | 80.408 | Completed. | 2025-03-03 | DK Verma
128 | 143/0 | DD60 | DD60+3 | 2025-02-25 | 635073 | 84.299 | Completed. | 2025-03-04 | Gourishankar
129 | 143A/0 | DD45 | DD45+0 | 2025-02-24 | 546238 | 72.238 | Completed. | 2025-03-02 | Dhaneswar Mahto
130 | 143A/1 | DA | DA+6 | 2025-03-01 | 342192 | 44.728 | Completed. | 2025-03-09 | SK Samuil
131 | 143A/2 | DD45 | DD45+0 | 2025-03-04 | 546238 | 72.238 | Completed. | 2025-03-17 | Dhaneswar Mahto
132 | 143A/3 | DD45 | DD45+3 | 2025-03-05 | 573550 | 75.452 | Completed. | 2025-03-11 | Gourishankar
133 | 143A/4 | DA | DA+0 | 2025-03-02 | 286911 | 37.73 | Completed. | 2025-03-10 | MJR
134 | 143A/5 | DA | DA+3 | 2025-03-05 | 297143 | 39.459 | Completed. | 2025-03-10 | DK Verma
135 | 144/0 | DB | DB2+3 | 2024-10-15 | 424198 | 56.863 | Completed. | 2024-11-16 | Mukesh
136 | 144/1 | DA | DA+0 | 2024-06-30 | 286911 | 37.73 | Completed | 2024-07-05 | Rahul Kumar
137 | 144/2 | DA | DA+0 | 2024-06-11 | 286911 | 37.73 | Completed | 2024-06-15 | Rahul Kumar
138 | 144/3 | DA | DA+0 | 2024-06-13 | 286911 | 37.73 | Completed | 2024-06-15 | Rahul Kumar
139 | 144/4 | DA | DA+0 | 2024-06-16 | 286911 | 37.73 | Completed | 2024-06-20 | Rahul Kumar
140 | 144/5 | DA | DA+0 | 2024-06-21 | 286911 | 37.73 | Completed | 2024-06-26 | Rahul Kumar
141 | 144A/0 | DB | DB1+9 | 2024-11-18 | 503365 | 65.757 | Completed. | 2024-11-24 | Mukesh
142 | 145/0 | DB | DB1+18 | 2024-11-18 | 670636 | 82.239 | Completed. | 2024-12-08 | Mukesh
143 | 145A/0 | DB | DB1+6 | 2025-03-15 | 480757 | 63.509 | Completed. | 2025-03-28 | MJR
144 | 145A/1 | DA | DA+3 | 2025-02-22 | 297143 | 39.459 | Completed. | 2025-03-07 | Sulen sarkar
145 | 145A/2 | DA | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-27 | Sulen sarkar
146 | 145A/3 | DA | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-16 | Sulen sarkar
147 | 146/0 | DC | DC1+9 | 2025-03-12 | 585620 | 77.718 | Completed. | 2025-03-22 | DK Verma
148 | 147/0 | DC | DC2+9 | 2025-03-24 | 585620 | 77.718 | Completed. | 2025-04-01 | DK Verma
149 | 147/1 | DC | DC2+0 | 2024-12-09 | 470077 | 64.254 | Completed. | 2024-12-16 | Mukesh
150 | 147/2 | DC | DC1+0 | 2024-12-17 | 470077 | 64.254 | Completed. | 2024-12-23 | Mukesh
151 | 147/3 | DA | DA-3 | 2024-11-13 | 273608.93 | 36.045 | Completed. | 2024-12-02 | Modina India
152 | 147/4 | DA | DA+3 | 2024-12-10 | 297143 | 39.459 | Completed. | 2024-12-25 | Modina India
153 | 147/5 | DA | DA+6 | 2024-12-03 | 342192 | 44.728 | Completed. | 2024-12-22 | Modina India
154 | 147/6 | DA | DA-3 | 2025-01-27 | 273608.93 | 36.045 | Completed. | 2025-02-18 | Ajay Kumar
155 | 147A/0 | DB | DB1+18 | 2024-12-24 | 670636 | 82.239 | Completed. | 2025-01-03 | Mukesh
156 | 147B/0 | DB | DB1+18 | 2025-02-26 | 670636 | 82.239 | Completed. | 2025-03-22 | Modina India
157 | 147B/1 | DA | DA+0 | 2025-02-13 | 286911 | 37.73 | Completed. | 2025-02-21 | Modina India
158 | 148/0 | DC | DC2+0 | 2025-01-04 | 470077 | 64.254 | Completed. | 2025-01-10 | Mukesh
159 | 148/1 | DA | DA+3 | 2025-02-01 | 297143 | 39.459 | Completed. | 2025-02-09 | Modina India
160 | 148/2 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-01-30 | Modina India
161 | 148/3 | DA | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-19 | Modina India
162 | 148/4 | DA | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2025-01-06 | Modina India
163 | 148/5 | DA | DA+0 | 2025-02-25 | 286911 | 37.73 | Completed. | 2025-02-28 | SK Samuil
164 | 148/6 | DA | DA+0 | 2025-03-03 | 286911 | 37.73 | Completed. | 2025-03-09 | SK Samuil
165 | 148/7 | DA | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-20 | Rahim Khan
166 | 149/0 | DB | DB2+0 | 2025-03-10 | 403998 | 54.418 | Completed. | 2025-04-06 | SK Samuil
167 | 149/1 | DA | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-27 | SK Samuil
168 | 150/0 | DD60 | DD60+9 | 2025-03-22 | 753337 | 98.836 | Completed. | 2025-03-31 | Dhaneswar Mahto
169 | 150/1 | DA | DA+9 | 2025-03-20 | 357181 | 46.623 | Completed. | 2025-04-06 | MJR
170 | 150/2 | DA | DA+3 | 2025-03-18 | 297143 | 39.459 | Completed. | 2025-03-22 | SK Samuil
171 | 150/3 | DA | DA+6 | 2025-03-19 | 342192 | 44.728 | Completed. | 2025-04-01 | Rupesh
172 | 150A/0 | DC | DC1+0 | 2025-03-25 | 470077 | 64.254 | Completed. | 2025-04-11 | Rahim Khan
173 | 150A/1 | DA | DA+3 | 2024-11-10 | 297143 | 39.459 | Completed. | 2024-11-22 | SK Samuil
174 | 150A/2 | DA | DA+0 | 2024-11-23 | 286911 | 37.73 | Completed. | 2024-12-02 | SK Samuil
175 | 151/0 | DB | DB2+3 | 2025-03-21 | 424198 | 56.863 | Completed. | 2025-03-27 | Gourishankar
176 | 152/0 | DC | DC2+0 | 2024-10-15 | 470077 | 64.254 | Completed | 2024-10-24 | Mukesh
177 | 152/1 | DA | DA+0 | 2024-09-16 | 286911 | 37.73 | Completed. | 2024-10-12 | Rejaul
178 | 152/2 | DA | DA-3 | 2024-09-24 | 273608.93 | 36.045 | Completed. | 2024-11-07 | SK Samuil
179 | 152/3 | DA | DA-3 | 2024-10-25 | 273608.93 | 36.045 | Completed | 2024-10-31 | Mukesh
180 | 152/4 | DA | DA+0 | 2024-11-02 | 286911 | 37.73 | Completed. | 2024-11-07 | Mukesh
181 | 152A/0 | DB | DB1+0 | 2025-03-16 | 403998 | 54.418 | Completed. | 2025-03-20 | Gourishankar
182 | 153/0 | DD60 | DD60+25 |  |  | 141.874 | Completed. | 2025-08-08
183 | 155/0 | DD60 | DD60+0 | 2025-04-02 | 604881 | 80.408 | Completed. | 2025-04-11 | Rahul Kumar
184 | 155/1 | DA | DA+0 | 2025-03-26 | 286911 | 37.73 | Completed. | 2025-04-03 | Barkat Ali
185 | 155/2 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-30 | Rahul Kumar
186 | 155/3 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-22 | Rahul Kumar
187 | 155/4 | DA | DA+0 | 2025-04-28 | 286911 | 37.73 | Completed. | 2025-05-11 | SK Samuil
188 | 155/5 | DA | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-11 | Barkat Ali
189 | 155/6 | DA | DA-3 | 2025-03-15 | 273608.93 | 36.045 | Completed. | 2025-03-23 | Barkat Ali
190 | 156/0 | DD60 | DD60+3 | 2025-03-22 | 635073 | 84.299 | Completed. | 2025-03-28 | Rahul Kumar
191 | 157/0 | DD60 | DD60+6 | 2025-03-12 | 719574 | 94.408 | Completed. | 2025-03-27 | Rahim Khan
192 | 157/1 | DA | DA+0 | 2025-02-09 | 286911 | 37.73 | Completed. | 2025-02-18 | Sukhriddin
193 | 157/2 | DA | DA+0 | 2025-02-23 | 286911 | 37.73 | Completed. | 2025-03-11 | Barkat Ali
194 | 158/0 | DB | DB2+0 | 2025-04-02 | 403998 | 54.418 | Completed. | 2025-04-10 | Rahim Khan
195 | 158/1 | DA | DA-3 | 2025-04-07 | 273608.93 | 36.045 | Completed. | 2025-04-25 | Barkat Ali
196 | 158/2 | DA | DA-3 | 2025-03-13 | 273608.93 | 36.045 | Completed. | 2025-03-18 | Rahul Kumar
197 | 158A/0 | DD45 | DD45+6 | 2024-10-23 | 650023 | 85.234 | Completed. | 2024-11-12 | Rahul Kumar
198 | 158B/0 | DD45 | DD45+18 | 2024-11-13 | 906755 | 112.424 | Completed. | 2024-12-30 | Rahul Kumar
199 | 158B/1 | DA | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-12-12 | Rahul Kumar
200 | 158B/2 | DA | DA+3 | 2024-12-31 | 297143 | 39.459 | Completed. | 2025-01-10 | Rahul Kumar
201 | 159/0 | DB | DB+0 | 2024-08-14 | 403998 | 54.418 | Completed. | 2024-09-08 | Sukhriddin
202 | 159/1 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-12 | Rahim Khan
203 | 159/3 | DA | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-23 | Sukhriddin
204 | 159/4 | DA | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-03 | Modina India
205 | 161/0 | DD60 | DD60+25 | 2025-01-28 | 1099828 | 141.874 | Completed. | 2025-02-16 | Rahul Kumar
206 | 162/0 | DD60 | DD60+25 | 2025-02-20 | 1099828 | 141.874 | Completed. | 2025-03-09 | Rahul Kumar
207 | 163/0 | DC | DC2+0 | 2025-01-16 | 470077 | 64.254 | Completed. | 2025-01-23 | Rahul Kumar
208 | 163/1 | DA | DA+0 | 2024-12-30 | 286911 | 37.73 | Completed. | 2025-01-08 | Rahim Khan
209 | 163/2 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-29 | Rahim Khan
210 | 163/3 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-18 | Rahim Khan
211 | 163/4 | DA | DA+0 | 2025-01-16 | 286911 | 37.73 | Completed. | 2025-01-29 | Sukhriddin
212 | 163/5 | DA | DA+0 | 2025-01-12 | 286911 | 37.73 | Completed. | 2025-02-20 | Barkat Ali
213 | 163/6 | DA | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-25 | Barkat Ali
214 | 164/0 | DB | DB2+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Sukhriddin
215 | 164/1 | DA | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-16 | Modina India
216 | 164/2 | DA | DA+0 | 2024-07-27 | 286911 | 37.73 | Completed | 2024-08-13 | Sukhriddin
217 | 164/3 | DA | DA+0 | 2025-01-11 | 286911 | 37.73 | Completed. | 2025-01-20 | Rahim Khan
218 | 164/4 | DA | DA+0 | 2024-11-16 | 286911 | 37.73 | Completed. | 2024-11-27 | Sukhriddin
219 | 164/5 | DA | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-14 | Sukhriddin
220 | 164/6 | DA | DA+0 | 2024-12-14 | 286911 | 37.73 | Completed. | 2024-12-25 | Sukhriddin
221 | 164/7 | DA | DA+0 | 2024-09-22 | 286911 | 37.73 | Completed | 2024-10-09 | Sukhriddin
222 | 165/0 | DB | DB2+0 | 2024-10-09 | 403998 | 54.418 | Completed. | 2024-10-28 | Sukhriddin
223 | 165/1 | DA | DA+0 | 2025-05-16 | 286911 | 37.73 | Completed. | 2025-05-25 | Barkat Ali
224 | 165/2 | DA | DA+0 | 2024-09-09 | 286911 | 37.73 | Completed | 2024-09-20 | Sukhriddin
225 | 165/3 | DA | DA+6 | 2024-10-30 | 342192 | 44.728 | Completed. | 2024-11-15 | Sukhriddin
226 | 167/0 | DD60 | DD60+0 | 2025-04-18 | 604881 | 80.408 | Completed. | 2025-05-05 | Rupesh
227 | 167/1 | DA | DA+9 | 2025-05-04 | 357181 | 46.623 | Completed. | 2025-05-19 | Barkat Ali
228 | 167/2 | DA | DA+6 | 2025-04-08 | 342192 | 44.728 | Completed. | 2025-04-18 | Barkat Ali
229 | 167/3 | DA | DA+6 | 2025-03-28 | 342192 | 44.728 | Completed. | 2025-04-06 | Barkat Ali
230 | 167/4 | DA | DA+0 | 2025-04-20 | 286911 | 37.73 | Completed. | 2025-04-29 | Barkat Ali
231 | 168/0 | DC | DC1+0 | 2025-04-06 | 470077 | 64.254 | Completed. | 2025-04-16 | Rupesh
232 | 168/1 | DA | DA-3 | 2025-05-13 | 273608.93 | 36.045 | Completed. | 2025-05-20 | Rahim Khan
233 | 168/2 | DA | DA+0 | 2025-05-02 | 286911 | 37.73 | Completed. | 2025-05-11 | Sukhriddin
234 | 169/0 | DD45 | DD45+18 | 2025-05-24 | 906755 | 112.424 | Completed. | 2025-06-08 | DK Verma
235 | 171/0 | DD60 | DD60+25(3M RC) | 2025-02-26 | 1099828 | 141.874 | Completed. | 2025-03-29 | Sukhriddin
236 | 172/0 | DD60 | DD60+25 | 2025-04-02 | 1099828 | 141.874 | Completed. | 2025-04-28 | Sukhriddin
237 | 172/2 | DA | DA+6 | 2025-05-29 | 342192 | 44.728 | Completed. | 2025-06-06 | Thanu Mahto
238 | 174/1 | DB | DB1+0 | 2025-06-06 | 403998 | 54.418 | Completed. | 2025-06-13 | Gourishankar
239 | 175/0 | DD45 | DD45+0 | 2025-05-28 | 546238 | 72.238 | Completed. | 2025-06-05 | Gourishankar
240 | 175/2 | DA | DA+0 |  |  | 37.73 | Completed. | 2025-07-20
241 | 176/0 | DD60 | DD60+0 | 2025-06-11 | 604881 | 80.408 | Completed. | 2025-07-04 | DK Verma
242 | 177/0 | DD60 | DD60+0 | 2025-05-06 | 604881 | 80.408 | Completed. | 2025-05-18 | Gourishankar
243 | 178/0 | DD60 | DD60+6 | 2025-04-06 | 719574 | 94.408 | Completed. | 2025-04-13 | Gourishankar
244 | 179/0 | DD60 | DD60+0 | 2025-04-16 | 604881 | 80.408 | Completed. | 2025-04-22 | Gourishankar
245 | 180/0 | DD45 | DD45+9 | 2025-04-24 | 680590 | 89.146 | Completed. | 2025-05-03 | Gourishankar
246 | 181/0 | DD45 | DD45+18 | 2025-04-06 | 906755 | 112.424 | Completed. | 2025-04-27 | DK Verma
247 | 181/1 | DA | DA+0 | 2025-04-24 | 286911 | 37.73 | Completed. | 2025-04-30 | Rahim Khan
248 | 181/2 | DA | DA+0 | 2025-04-16 | 286911 | 37.73 | Completed. | 2025-04-22 | Rahim Khan
249 | 181/3 | DA | DA+0 | 2025-05-19 | 286911 | 37.73 | Completed. | 2025-05-24 | Gourishankar
250 | 181/4 | DA | DA+0 | 2025-05-03 | 286911 | 37.73 | Completed. | 2025-05-11 | Rahim Khan
251 | 182/0 | DD60 | DD60+0 | 2025-04-28 | 604881 | 80.408 | Completed. | 2025-05-06 | DK Verma
252 | 187/1 | DA | DA+3 | 2025-04-03 | 297143 | 39.459 | Completed. | 2025-04-12 | Thanu mahto
253 | 187/2 | DA | DA-3 | 2024-12-26 | 273608.93 | 36.045 | Completed. | 2025-01-04 | Mithun Kumar
254 | 187/3 | DA | DA+0 | 2024-11-22 | 286911 | 37.73 | Completed. | 2024-11-26 | Jwala
255 | 188/0 | DB | DB1+6 | 2024-11-27 | 480757 | 63.509 | Completed. | 2024-12-10 | Jwala
256 | 189/0 | DB | DB2+6 | 2024-11-22 | 480757 | 63.509 | Completed. | 2024-12-14 | Barkat Ali
257 | 189/1 | DA | DA+0 | 2025-04-05 | 286911 | 37.73 | Completed. | 2025-04-11 | Dhaneswar Mahto
258 | 190/0 | DD45 | DD45+25 | 2025-04-18 | 994153 | 122.808 | Completed. | 2025-05-06 | Dhaneswar Mahto
259 | 191/1 | DA | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-23 | Mithun Kumar
260 | 191/2 | DA | DA-3 | 2025-04-23 | 273608.93 | 36.045 | Completed. | 2025-04-27 | Rahul Kumar
261 | 191/3 | DA | DA-3 | 2025-04-29 | 273608.93 | 36.045 | Completed. | 2025-05-04 | Rahul Kumar
262 | 191A/0 | DB | DB2+0 | 2025-04-15 | 403998 | 54.418 | Completed. | 2025-04-22 | Rahul Kumar
263 | 191A/1 | DA | DA-3 | 2024-11-22 | 273608.93 | 36.045 | Completed. | 2024-11-30 | Mithun Kumar
264 | 192/0 | DC | DC1+0 | 2025-04-13 | 470077 | 64.254 | Completed. | 2025-04-28 | MJR
265 | 193/0 | DD60 | DD60+6 | 2024-12-11 | 719574 | 94.408 | Completed. | 2024-12-21 | Jwala
266 | 194/0 | DD60 | DD60+6 | 2025-04-22 | 719574 | 94.408 | Completed. | 2025-05-15 | MJR
267 | 195/0 | DC | DC2+0 | 2025-04-28 | 470077 | 64.254 | Completed. | 2025-05-11 | Mithun Kumar
268 | 195/1 | DA | DA+6 | 2025-04-16 | 342192 | 44.728 | Completed. | 2025-04-25 | Mithun Kumar
269 | 195/2 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-08 | SK Samuil
270 | 195/3 | DA | DA+6 | 2025-04-18 | 342192 | 44.728 | Completed. | 2025-04-28 | SK Samuil
271 | 195/4 | DA | DA+0 | 2025-04-09 | 286911 | 37.73 | Completed. | 2025-04-15 | SK Samuil
272 | 195/5 | DA | DA+6 | 2025-05-02 | 342192 | 44.728 | Completed. | 2025-05-11 | SK Samuil
273 | 195A/0 | DB | DB1+0 | 2025-04-22 | 403998 | 54.418 | Completed. | 2025-05-18 | Daulat Mahto
274 | 195A/1 | DA | DA+6 | 2025-04-24 | 342192 | 44.728 | Completed. | 2025-05-09 | Modina India
275 | 195A/2 | DA | DA+6 | 2025-04-11 | 342192 | 44.728 | Completed. | 2025-04-22 | Modina India
276 | 195A/3 | DA | DA+0 | 2025-03-30 | 286911 | 37.73 | Completed. | 2025-04-08 | Modina India
277 | 196/0 | DD60 | DD60+9 | 2024-12-31 | 753337 | 98.839 | Completed. | 2025-01-10 | Jwala
278 | 197/0 | DD60 | DD60+9 | 2025-01-12 | 753337 | 98.836 | Completed. | 2025-01-22 | Jwala
279 | 197/1 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | Mithun Kumar
280 | 197/2 | DA | DA+0 | 2025-01-29 | 286911 | 37.73 | Completed. | 2025-02-07 | Mithun Kumar
281 | 197/3 | DA | DA+0 | 2025-01-07 | 286911 | 37.73 | Completed. | 2025-01-16 | Mithun Kumar
282 | 197/4 | DA | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2024-12-29 | Jwala
283 | 198/0 | DC | DC1+0 | 2025-04-01 | 470077 | 64.254 | Completed. | 2025-04-15 | Mithun Kumar
284 | 198/1 | DA | DA+0 | 2025-01-17 | 286911 | 37.73 | Completed. | 2025-01-27 | Mithun Kumar
285 | 198/2 | DA | DA+0 | 2025-04-04 | 286911 | 37.73 | Completed. | 2025-04-12 | Daulat Mahto
286 | 199/0 | DD45 | DD45+18 | 2025-04-18 | 906755 | 112.424 | Completed. | 2025-05-22 | Mithun Kumar
287 | 204/0 | DD60 | DD60+9 | 2025-05-02 | 753337 | 98.836 | Completed. | 2025-05-11 | Jwala
288 | 205/0 | DD60 | DD60+3 (2M RC) | 2025-04-18 | 635073 | 84.299 | Completed. | 2025-04-29 | Jwala
289 | 205/1 | DA | DA-3 | 2025-04-11 | 273608.93 | 36.045 | Completed | 2025-04-16 | Jwala
290 | 205/2 | DA | DA+3 | 2025-05-15 | 297143 | 39.459 | Completed. | 2025-05-21 | Jwala
291 | 209/0 | DC | DC1+0 | 2025-05-08 | 470077 | 64.254 | Completed. | 2025-05-16 | Rahul Kumar
292 | 211/1 | DA | DA+0 | 2025-05-13 | 286911 | 37.73 | Completed. | 2025-05-18 | Dhaneswar Mahto
293 | 217A/1 | DA | DA+3 | 2025-05-04 | 297143 | 39.459 | Completed. | 2025-05-18 | Rahim Khan
294 | 247/1 | DA | DA+0 | 2025-05-11 | 286911 | 37.73 | Completed. | 2025-05-19 | Sulen sarkar
295 | 248/0 | DC | DC2+9 | 2025-04-14 | 585620 | 77.718 | Completed. | 2025-04-30 | Anarul Haque
296 | 248/1 | DA | DA+9 | 2025-05-06 | 357181 | 46.623 | Completed. | 2025-05-18 | DK Verma
297 | 248/2 | DA | DA+9 | 2025-04-17 | 357181 | 46.623 | Completed. | 2025-04-30 | Sulen sarkar
298 | 248/3 | DA | DA+6 | 2025-05-09 | 342192 | 44.728 | Completed. | 2025-05-20 | MJR
299 | 248/4 | DA | DA+3 | 2025-04-17 | 297143 | 39.459 | Completed. | 2025-05-05 | MJR
300 | 248/5 | DA | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | Sulen sarkar
301 | 248/6 | DA | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-09 | Senahul
302 | 249/0 | DB | DB2+0 | 2025-02-14 | 403998 | 54.418 | Completed. | 2025-02-26 | Maa Construction
303 | 249/1 | DA | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-21 | Sulen sarkar
304 | 249/2 | DA | DA+0 | 2025-03-01 | 286911 | 37.73 | Completed. | 2025-03-09 | Maa Construction
305 | 249/3 | DA | DA+0 | 2025-03-10 | 286911 | 37.73 | Completed. | 2025-03-18 | Maa Construction
306 | 250/0 | DD60 | DD60+0 | 2025-03-21 | 604881 | 80.408 | Completed. | 2025-04-12 | Maa Construction
307 | 250/1 | DA | DA-3 | 2025-02-14 | 273608.93 | 36.045 | Completed. | 2025-02-24 | Ghanshyam Mahto
308 | 251/0 | DB | DB1+9 | 2024-12-03 | 503365 | 65.757 | Completed. | 2024-12-28 | Senahul
309 | 252/0 | DC | DC1+18 | 2025-03-18 | 780122 | 97.934 | Completed. | 2025-04-11 | Anarul Haque
310 | 253/0 | DC | DC1+0 | 2025-02-01 | 470077 | 64.254 | Completed. | 2025-02-17 | Senahul
311 | 254/0 | DB | DB2+0 | 2024-11-04 | 403998 | 54.418 | Completed. | 2024-11-21 | Senahul
312 | 255/0 | DD60 | DD60+3 | 2024-11-27 | 635073 | 84.299 | Completed. | 2024-12-21 | Senahul
313 | 255/1 | DA | DA+6 | 2025-01-19 | 342192 | 44.728 | Completed. | 2025-01-27 | Daulat Mahto
314 | 255/2 | DA | DA+0 | 2025-01-03 | 286911 | 37.73 | Completed. | 2025-01-10 | Maa Construction
315 | 255/3 | DA | DA+3 | 2024-12-26 | 297143 | 39.459 | Completed. | 2025-01-02 | Maa Construction
316 | 255/4 | DA | DA+0 | 2024-07-10 | 286911 | 37.73 | Completed | 2024-08-22 | Ghanshyam Mahto
317 | 257/0 | DC | DC+0 | 2024-08-30 | 470077 | 64.254 | Completed | 2024-09-23 | Ghanshyam Mahto
318 | 257/1 | DA | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-17 | Daulat Mahto
319 | 257/2 | DA | DA-3 | 2024-09-23 | 273608.93 | 36.044 | Completed | 2024-10-24 | Ghanshyam Mahto
320 | 257/3 | DA | DA+0 | 2024-08-29 | 286911 | 37.73 | Completed | 2024-10-06 | Chahanur Bibi
321 | 257/4 | DA | DA+0 | 2024-10-29 | 286911 | 37.73 | Completed. | 2024-11-16 | Thanu mahto
322 | 259/0 | DD60 | DD60+18 | 2024-11-10 | 1003256 | 129.341 | Completed. | 2024-12-23 | Maa Construction
323 | 260/0 | DD60 | DD60+18 | 2024-09-11 | 1003256 | 129.341 | Completed. | 2024-10-31 | Ramjivan
324 | 261/0 | DC | DC2+18 | 2024-11-23 | 780122 | 97.934 | Completed. | 2024-12-28 | Ghanshyam Mahto
325 | 262/0 | DD45 | DD45+9 | 2025-01-18 | 680590 | 89.146 | Completed. | 2025-02-11 | Ghanshyam Mahto
326 | 262/1 | DA | DA+0 | 2024-10-25 | 286911 | 37.73 | Completed. | 2024-11-07 | Ghanshyam Mahto
327 | 263/0 | DC | DC2+0 | 2024-12-31 | 470077 | 64.254 | Completed. | 2025-01-13 | Ghanshyam Mahto
328 | 264/0 | DC | DC1+6 | 2024-11-17 | 559332 | 74.632 | Completed. | 2024-12-10 | Thanu Mahto
329 | 265/0 | DB | DB2+3 | 2024-09-30 | 424198 | 56.863 | Completed. | 2024-10-31 | Thanu mahto
330 | 266/0 | DB | DB1+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Senahul
331 | 266/1 | DB | DB1+6 | 2025-01-13 | 480757 | 63.509 | Completed. | 2025-01-29 | Senahul
332 | 266/2 | DA | DA+0 | 2025-02-04 | 286911 | 37.73 | Completed. | 2025-02-12 | Maa Construction
333 | 267/0 | DC | DC1+9(2M RC) | 2025-01-21 | 585620 | 77.718 | Completed. | 2025-01-31 | Maa Construction
334 | 267A/0 | DC | DC2+9(2M RC) | 2025-02-21 |  | 77.718 | Completed. | 2025-03-18 | Senahul
335 | 267A/1 | DA | DA+0 | 2025-02-27 | 286911 | 37.73 | Completed. | 2025-03-05 | Daulat Mahto
336 | 267A/2 | DA | DA-3 | 2025-03-07 | 273608.93 | 36.045 | Completed. | 2025-03-15 | Daulat Mahto
337 | 267A/3 | DA | DA+0 | 2024-08-21 | 286911 | 37.73 | Completed. | 2024-09-13 | Ramjivan
338 | 268/0 | DD60 | DD60+6 | 2024-11-10 | 719574 | 94.408 | Completed. | 2024-12-07 | Daulat Mahto
339 | 269/0 | DD60 | DD60+0 | 2025-03-26 | 604881 | 80.408 | Completed. | 2025-04-01 | Jwala
340 | 269/1 | DA | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-07 | Daulat Mahto
341 | 269/2 | DA | DA+6 | 2025-01-11 | 342192 | 44.728 | Completed. | 2025-01-19 | Maa Construction
342 | 270/0 | DD45 | DD45+0 | 2025-02-22 | 546238 | 72.238 | Completed. | 2025-03-16 | Anarul Haque
343 | 270/1 | DA | DA+0 | 2024-12-11 | 286911 | 37.73 | Completed. | 2024-12-24 | Daulat Mahto
344 | 270/2 | DA | DA+3 | 2024-09-14 | 297143 | 39.459 | Completed. | 2024-10-28 | Senahul
345 | 270/3 | DA | DA-3 | 2025-03-19 | 273608.93 | 36.045 | Completed. | 2025-03-28 | Thanu mahto
346 | 270/4 | DA | DA+0 | 2025-03-09 | 286911 | 37.73 | Completed. | 2025-03-28 | Mithun Kumar
347 | 270/5 | DA | DA+0 | 2025-02-20 | 286911 | 37.73 | Completed. | 2025-02-28 | Mithun Kumar
348 | 270/6 | DA | DA-3 | 2025-02-11 | 273608.93 | 36.045 | Completed. | 2025-02-17 | Mithun Kumar
349 | 270/7 | DA | DA-3 | 2025-02-17 | 273608.93 | 36.045 | Completed. | 2025-02-23 | Daulat Mahto
350 | 270A/0 | DC | DC2+0 | 2025-02-05 | 470077 | 64.254 | Completed. | 2025-02-15 | Daulat Mahto
351 | 271/0 | DC | DC1+0 | 2025-02-04 | 470077 | 64.254 | Completed. | 2025-02-13 | Thanu mahto
352 | 271/1 | DA | DA-3 | 2025-03-21 | 273608.93 | 36.045 | Completed. | 2025-03-25 | Jwala
353 | 271/2 | DA | DA+0 | 2025-02-14 | 286911 | 37.73 | Completed. | 2025-02-21 | Thanu Mahto
354 | 271/3 | DA | DA-3 | 2035-03-04 | 273608.93 | 36.045 | Completed. | 2025-03-11 | Thanu Mahto
355 | 271/4 | DA | DA-3 | 2025-02-22 | 273608.93 | 36.045 | Completed. | 2025-03-03 | Thanu Mahto
356 | 271/5 | DA | DA-3 | 2025-01-01 | 273608.93 | 36.045 | Completed. | 2025-01-11 | Thanu mahto
357 | 272/0 | DC | DC1+6 | 2024-12-11 | 559332 | 74.632 | Completed. | 2024-12-31 | Thanu mahto
358 | 272/1 | DA | DA+9 | 2024-12-02 | 357181 | 46.623 | Completed. | 2024-12-16 | MJR
359 | 272/2 | DA | DA-3 | 2025-01-30 | 273608.93 | 36.045 | Completed. | 2025-02-04 | Daulat Mahto
360 | 272/3 | DA | DA+3 | 2025-01-17 | 297143 | 39.459 | Completed. | 2025-02-06 | Tajirul
361 | 272/4 | DA | DA+3 | 2025-01-25 | 297143 | 39.459 | Completed. | 2025-02-02 | Thanu mahto
362 | 272/5 | DB | DB1+0 | 2025-01-13 | 403998 | 54.418 | Completed. | 2025-01-23 | Thanu mahto
363 | 272/6 | DA | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-30 | Daulat Mahto
364 | 272/7 | DA | DA+9 | 2025-02-10 | 357181 | 46.623 | Completed. | 2025-03-07 | Tajirul
365 | 272A/0 | DB | DB1+18(2M RC) | 2025-04-03 | 670636 | 82.239 | Completed. | 2025-04-26 | Senahul
366 | 272A/1 | DA | DA+6 | 2025-01-24 | 342192 | 44.728 | Completed. | 2025-01-29 | Jwala
367 | 272A/2 | DA | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-04 | Jwala
368 | 272A/3 | DA | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-09 | Jwala
369 | 272A/4 | DA | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-20 | Jwala
370 | 272A/5 | DA | DA+3 | 2025-03-11 | 297143 | 39.459 | Completed. | 2025-03-16 | Jwala
371 | 272A/6 | DA | DA-3 | 2025-03-02 | 273608.93 | 36.045 | Completed. | 2025-03-05 | Jwala
372 | 272A/7 | DA | DA-3 | 2025-03-06 | 273608.93 | 36.045 | Completed. | 2025-03-10 | Jwala
373 | 273/1 | DA | DA+6 | 2025-04-04 | 342192 | 44.728 | Completed. | 2025-04-09 | Jwala
374 | 273/2 | DA | DA+6 | 2025-02-24 | 342192 | 44.728 | Completed. | 2025-02-28 | Jwala
375 | 274/0 | DC | DC1+0 | 2025-02-17 | 470077 | 64.254 | Completed. | 2025-02-23 | Jwala
20361.708
Summary
|  | DA | 230 |  | Tower Type | Supply | Completed Erection
|  | DB | 39 |  | DA-3 | 40 | 32
|  | DC | 39 |  | DA+0 | 146 | 127
|  | DD45 | 25 |  | DA+3 | 40 | 33
|  | DD60 | 41 |  | DA+6 | 30 | 28
|  | Total | 374 |  | DA+9 | 11 | 9
[5 empty] | DA Type | 267 | 229
[5 empty] | DB+0 | 25
[5 empty] | DB+3 | 6
[5 empty] | DB+6 | 8
[5 empty] | DB+9 | 9
[5 empty] | DB+18 | 6
[5 empty] | DB+25 | 1
[5 empty] | DB Type | 55
[5 empty] | DC+0 | 26
[5 empty] | DC+3 | 3
[5 empty] | DC+6 | 4
[5 empty] | DC+9 | 7
[5 empty] | DC+18 | 4
[5 empty] | DC+25 | 3
[5 empty] | DC Type | 47
[5 empty] | DD45+0 | 16
[5 empty] | DD45+3 | 4
[5 empty] | DD45+6 | 3
[5 empty] | DD45+9 | 4
[5 empty] | DD45+18 | 6
[5 empty] | DD45+25 | 5
[5 empty] | DD45+35 | 2
[5 empty] | DD45 Type | 40
[5 empty] | DD60+0 | 19
[5 empty] | DD60+3 | 8
[5 empty] | DD60+6 | 11
[5 empty] | DD60+9 | 7
[5 empty] | DD60+18 | 7
[5 empty] | DD60+25 | 15
[5 empty] | DD60+35 | 4
[5 empty] | DD60+55 | 2
[5 empty] | DD60+55 Type | 73
[5 empty] | DCT+0 | 1
[5 empty] | DCT Type | 1
[5 empty] | Total | 483

## EREC-VDRA
2025-08-18
Tower Erection Part-I (Vadodara Section)
Sl. No. | Loc. No. | Type of Tower | Start Date | Revenue | Tower Wgt. (MT) | Todays Status | End Date | Sub Contractor | Remarks | Tackwelding Status | Tackwelding Start date | Tackwelding Completion date | Sub Contractor
1 | 127/1 | DA+0 | 2023-09-30 | 286911 | 37.73 | Completed | 2023-10-15 | Team 01 |  | Completed | 2024-02-18 | 2024-02-19 | Bharath Const.
2 | 127/2 | DA+0 | 2023-10-16 | 286911 | 37.73 | Completed | 2023-10-29 | Team 01 |  | Completed | 2024-02-17 | 2024-02-18 | Bharath Const.
3 | 135A/4 | DA+0 | 2023-11-01 | 286911 | 37.73 | Completed | 2023-11-09 | Team 01 |  | Completed | 2024-02-08 | 2024-02-09 | Bharath Const.
4 | 135/2 | DA+0 | 2023-11-11 | 286911 | 37.73 | Completed | 2023-11-17 | Team 01 |  | Completed | 2024-02-09 | 2024-02-10 | Bharath Const.
5 | 135A/7 | DA+0 | 2023-11-19 | 286911 | 37.73 | Completed | 2023-12-01 | Team 01 |  | Completed | 2024-02-14 | 2024-02-15 | Bharath Const.
6 | 133/1 | DA+0 | 2023-12-02 | 286911 | 37.73 | Completed | 2023-12-15 | Team 01 |  | Completed | 2024-02-15 | 2024-02-17 | Bharath Const.
7 | 135B/4 | DA+6 | 2024-01-04 | 342192 | 44.728 | Completed | 2024-01-12 | Team 02 |  | Completed | 2024-02-11 | 2024-02-12 | Bharath Const.
8 | 135B/3 | DA+0 | 2024-01-12 | 286911 | 37.73 | Completed | 2024-01-18 | Team 02 |  | Completed | 2024-02-12 | 2024-02-13 | Bharath Const.
9 | 135B/2 | DA+0 | 2024-01-18 | 286911 | 37.73 | Completed | 2024-01-23 | Team 02 |  | Completed | 2024-02-21 | 2024-02-21 | Bharath Const.
10 | 135A/3 | DA+0 | 2024-01-23 | 286911 | 37.73 | Completed | 2024-01-28 | Team 02 |  | Completed | 2024-02-13 | 2024-02-14 | Bharath Const.
11 | 135B/5 | DA+0 | 2024-01-28 | 286911 | 37.73 | Completed | 2024-02-02 | Team 02 |  | Completed | 2024-02-10 | 2024-02-11 | Bharath Const.
12 | 135B/0 | DB1+0 | 2024-02-02 | 403998 | 54.418 | Completed | 2024-02-09 | Team 02 |  | Completed | 2024-05-07 | 2024-05-07 | Bharath Const.
13 | 132/2 | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-13 | Team 03 |  | Completed | 2024-02-25 | 2024-02-25 | Bharath Const.
14 | 135B/6 | DA+0 | 2024-02-04 | 286911 | 37.73 | Completed | 2024-02-15 | Team 02 |  | Completed | 2024-02-24 | 2024-02-24 | Bharath Const.
15 | 133/0 | DB1+0 | 2024-02-13 | 403998 | 54.418 | Completed | 2024-02-21 | Team 03
16 | 133A/3 | DA+0 | 2024-02-15 | 286911 | 37.73 | Completed | 2024-02-20 | Team 02 |  | Completed | 2024-03-02 | 2024-03-02 | Bharath Const.
17 | 135B/1 | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-26 | Team 02 |  | Completed | 2024-05-06 | 2024-05-06 | Bharath Const.
18 | 133/3 | DA+0 | 2024-02-20 | 286911 | 37.73 | Completed | 2024-02-28 | Team 03
19 | 135/3 | DA+0 | 2024-02-26 | 286911 | 37.73 | Completed | 2024-03-02 | Team 02 |  | Completed | 2024-03-03 | 2024-03-04 | Bharath Const.
20 | 133/2 | DA+0 | 2024-02-27 | 286911 | 37.73 | Completed | 2024-03-03 | Team 03
21 | 135B/7 | DA+3 | 2024-03-02 | 297143 | 39.459 | Completed | 2024-04-11 | Team 02 |  | Completed | 2024-05-08 | 2024-05-08 | Bharath Const.
22 | 133/5 | DA+0 | 2024-03-03 | 286911 | 37.73 | Completed | 2024-03-08 | Team 03
23 | 133A/0 | DB1+0 | 2024-03-08 | 403998 | 54.418 | Completed | 2024-03-13 | Team 03
24 | 133A/1 | DA+0 | 2024-03-13 | 286911 | 37.73 | Completed | 2024-03-13 | Team 03
25 | 133A/2 | DA+6 | 2024-04-13 | 342192 | 44.728 | Completed | 2024-04-19 | Team 03
26 | 133/4 | DA+0 | 2024-04-20 | 286911 | 37.73 | Completed | 2024-04-24 | Team 03
27 | 129A/0 | DC1+0 | 2024-04-25 | 470077 | 64.254 | Completed | 2024-04-30 | Team 03
28 | 129A/1 | DA+0 | 2024-05-02 | 286911 | 37.73 | Completed | 2024-05-07 | Team 03
29 | 135/6 | DA+0 | 2024-05-01 | 286911 | 37.73 | Completed | 2024-05-19 | Team 04
30 | 129A/2 | DA+3 | 2024-05-07 | 297143 | 39.459 | Completed | 2024-05-12 | Team 03
31 | 137/4 | DA+0 | 2024-05-07 | 286911 | 37.73 | Completed | 2024-05-18 | Team 04
32 | 130/0 | DB1+0 | 2024-05-07 | 403998 | 54.418 | Completed | 2024-05-18 | Team 03
33 | 137/3 | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-24 | Team 03
34 | 135/5 | DA+0 | 2024-05-19 | 286911 | 37.73 | Completed | 2024-05-31 | Team 04
35 | 127/4 | DA+3 | 2024-05-19 | 297143 | 39.459 | Completed | 2024-05-24 | Team 01
36 | 127/3 | DA+0 | 2024-05-25 | 286911 | 37.73 | Completed | 2024-05-31 | Team 02
37 | 137/1 | DA+3 | 2024-05-25 | 297143 | 39.459 | Completed | 2024-05-31 | Team 03
38 | 127/0 | DD45+0 | 2024-05-31 | 546238 | 72.238 | Completed | 2024-06-10 | Team 01
39 | 135/4 | DA+0 | 2024-05-31 | 286911 | 37.73 | Completed | 2024-06-10 | Team 03
40 | 144/2 | DA+0 | 2024-06-11 | 286911 | 37.73 | Completed | 2024-06-15 | Team 04 |  | Completed |  |  | Bharath Const.
41 | 112/0 | DD45+0 | 2024-06-05 | 546238 | 72.238 | Completed | 2024-06-13 | Team-05
42 | 132/3 | DA+0 | 2024-06-12 | 286911 | 37.73 | Completed | 2024-06-18 | Team 02
43 | 144/3 | DA+0 | 2024-06-13 | 286911 | 37.73 | Completed | 2024-06-15 | Team 04 |  | Completed | 2024-06-23 | 2024-06-23 | Bharath Const.
44 | 106A/4 | DA+9 | 2024-06-14 | 357181 | 46.623 | Completed | 2024-06-24 | Team-05
45 | 144/4 | DA+0 | 2024-06-16 | 286911 | 37.73 | Completed | 2024-06-20 | Team 04
46 | 144/5 | DA+0 | 2024-06-21 | 286911 | 37.73 | Completed | 2024-06-26 | Team 04
47 | 144/1 | DA+0 | 2024-06-30 | 286911 | 37.73 | Completed | 2024-07-05 | Team 04
48 | 106A/3 | DA+3 | 2024-06-25 | 297143 | 39.459 | Completed | 2024-07-02 | Team-05
49 | 106B/2 | DA+6 | 2024-07-02 | 342192 | 44.728 | Completed | 2024-07-12 | Gouri Shankar
50 | 119/2 | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-12 | Rahul Kumar
51 | 113/0 | DD60+0 | 2024-07-08 | 604881 | 80.408 | Completed | 2024-07-25 | Ajay Kumar
52 | 119/3 | DA+0 | 2024-07-13 | 286911 | 37.73 | Completed | 2024-07-18 | Rahul Kumar
53 | 107/0 | DD45+0 | 2024-07-13 | 546238 | 72.238 | Completed | 2024-07-29 | Gouri Shankar
54 | 126/0 | DC2+0 | 2024-07-20 | 470077 | 64.254 | Completed | 2024-07-31 | Rahul Kumar
55 | 106B/1 | DA+9 | 2024-07-28 | 357181 | 46.263 | Completed. | 2024-08-08 | Ajay Kumar
56 | 116A/0 | DC1+0 | 2024-07-30 | 470077 | 64.254 | Completed. | 2024-08-11 | Gouri Shankar
57 | 118/0 | DD45+0 | 2024-08-01 | 546238 | 72.238 | Completed. | 2024-08-20 | Rahul Kumar
58 | 106B/0 | DB2+9 | 2024-08-08 | 503365 | 65.757 | Completed. | 2024-08-24 | Rahul Kumar
59 | 109/0 | DB2+0 | 2024-08-11 | 403998 | 54.418 | Completed | 2024-08-23 | Gouri Shankar
60 | 110/0 | DB2+0 | 2024-08-18 | 403998 | 54.418 | Completed | 2024-08-31 | Rahul Kumar
61 | 117/0 | DD60+3 | 2024-11-20 | 635073 | 84.299 | Completed. | 2024-12-03 | Gouri Shankar
62 | 123/0 | DD60+6 | 2024-09-26 | 719574 | 94.408 | Completed. | 2024-10-10 | Ajay Kumar
63 | 114/0 | DD45+0 | 2024-09-02 | 546238 | 72.238 | Completed | 2024-09-13 | Gouri Shankar
64 | 111/0 | DC1+0 | 2024-09-09 | 470077 | 64.254 | Completed. | 2024-09-21 | Rahul Kumar
65 | 119/0 | DD45+0 | 2024-09-12 | 546238 | 72.238 | Completed. | 2024-09-24 | Ajay Kumar
66 | 116/0 | DD45+18 | 2024-09-10 | 906755 | 112.424 | Completed. | 2024-09-27 | Dhaneswar Mahto
67 | 107/1 | DA-3 | 2024-09-16 | 273608.93 | 36.045 | Completed. | 2024-09-26 | Barkad Alli
71 | 152/1 | DA+0 | 2024-09-16 | 286911 | 37.73 | Completed. | 2024-10-12 | Rejaul | No work due to holiday.
69 | 119/1 | DA-3 | 2024-09-14 | 273608.93 | 36.045 | Completed. | 2024-09-23 | Gouri Shankar
70 | 124A/1 | DA+3 | 2024-09-16 | 297143 | 39.459 | Completed. | 2024-09-30 | Senaul Haque
71 | 121/0 | DD60+18 | 2024-09-23 | 1003256 | 129.341 | Completed. | 2024-10-10 | Rahul Kumar
73 | 133A/4 | DA+6 | 2024-09-27 | 342192 | 44.728 | Completed. | 2024-10-12 | Mithun Kumar
74 | 108/0 | DD45+0 | 2024-09-28 | 546238 | 72.238 | Completed. | 2024-10-13 | Dherendra Kumar
75 | 120/0 | DD60+9 | 2024-10-01 | 753337 | 98.836 | Completed | 2024-10-24 | Gouri Shankar-01
76 | 122/0 | DC1+6 | 2024-10-04 | 559332 | 74.632 | Completed. | 2024-10-15 | Gouri Shankar-02
77 | 106/0 | DD60+9 | 2024-10-03 | 753337 | 98.836 | Completed. | 2024-12-08 | DK Verma
78 | 135A/1 | DD45+3 | 2024-10-08 | 573550 | 75.452 | Completed. | 2024-11-03 | Dhaneshwar
79 | 116B/0 | DD45+6 | 2024-10-13 | 650023 | 85.234 | Completed. | 2024-10-31 | Ajay Kumar
80 | 152/0 | DC2+0 | 2024-10-15 | 470077 | 64.254 | Completed | 2024-10-24 | Mukesh
81 | 144/0 | DB2+3 | 2024-10-15 | 424198 | 56.863 | Completed. | 2024-11-16 | Mukesh
84 | 152/2 | DA-3 | 2024-09-24 | 273608.93 | 36.045 | Completed. | 2024-11-07 | SK Samuil
85 | 123/1 | DA+3 | 2024-10-17 | 297143 | 39.459 | Completed | 2024-10-31 | Gourishankar-02
86 | 152/3 | DA-3 | 2024-10-25 | 273608.93 | 36.045 | Completed | 2024-10-31 | Mukesh
87 | 126/1 | DA+6 | 2024-12-21 | 342192 | 44.728 | Completed. | 2024-12-27 | Gouri Shankar-01
88 | 124/0 | DC1+3 | 2024-10-28 | 493565 | 66.268 | Completed. | 2024-11-11 | Ajay Kumar
89 | 125A/0 | DB2+3 | 2024-11-02 | 424198 | 56.863 | Completed. | 2024-11-13 | Gouri Shankar-02
90 | 152/4 | DA+0 | 2024-11-02 | 286911 | 37.73 | Completed. | 2024-11-07 | Mukesh
91 | 135A/2 | DB2+9 | 2024-11-05 | 503365 | 65.757 | Completed. | 2024-11-13 | Dhaneshwar
92 | 150A/1 | DA+3 | 2024-11-10 | 297143 | 39.459 | Completed. | 2024-11-22 | SK Samuil
93 | 128/0 | DD60+6 | 2024-11-13 | 719574 | 94.408 | Completed. | 2024-11-26 | Ajay
94 | 147/3 | DA-3 | 2024-11-13 | 273608.93 | 36.045 | Completed. | 2024-12-02 | Modina India
95 | 137A/5 | DA-3 | 2024-11-14 | 273608.93 | 36.045 | Completed. | 2024-11-20 | Dahneshwar
96 | 144A/0 | DB1+9 | 2024-11-18 | 503365 | 65.757 | Completed. | 2024-11-24 | Mukesh
97 | 137A/3 | DA+6 | 2024-11-20 | 342192 | 44.728 | Completed. | 2024-11-28 | Dhaneshwar Mahto
| 127/5 | DA+3 | 2024-11-27 | 297143 | 39.459 | Completed. | 2024-12-07 | Ajay Kumar
99 | 150A/2 | DA+0 | 2024-11-23 | 286911 | 37.73 | Completed. | 2024-12-02 | SK Samuil
100 | 155/2 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-30 | Rahul Kumar
101 | 164/4 | DA+0 | 2024-11-16 | 286911 | 37.73 | Completed. | 2024-11-27 | Sukhriddin
102 | 145/0 | DB1+18 | 2024-11-18 | 670636 | 82.239 | Completed. | 2024-12-08 | Mukesh Kumar
103 | 163/3 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-18 | Rahim
104 | 164/5 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-14 | Sukhriddin
105 | 137A/4 | DA-3 | 2024-11-29 | 273608.93 | 36.045 | Completed. | 2024-12-03 | Dhaeshwar Mahto
106 | 158B/1 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-12-12 | Rahul Kumar
107 | 115/0 | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Gouri Shankar
108 | 134/0 | DC2+25 | 2024-12-04 |  | 109.608 | Completed. | 2024-12-20 | Dhaneshawar Mahto
109 | 147/5 | DA+6 | 2024-12-03 | 342192 | 44.728 | Completed. | 2024-12-22 | Modina India
110 | 148/4 | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2025-01-06 | Modina India-1
111 | 147/1 | DC2+0 | 2024-12-09 | 470077 | 64.254 | Completed. | 2024-12-16 | Mukesh Kumar
113 | 116A/1 | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-21 | DK Verma
115 | 132/0 | DC2+3 | 2024-12-08 |  | 66.268 | Completed. | 2024-12-21 | SK Samuil
116 | 147/4 | DA+3 | 2024-12-10 | 297143 | 39.459 | Completed. | 2024-12-25 | Modina India
117 | 158B/0 | DD45+18 | 2024-11-13 | 906755 | 112.424 | Completed. | 2024-12-30 | Rahul Kumar
118 | 164/6 | DA+0 | 2024-12-14 | 286911 | 37.73 | Completed. | 2024-12-25 | Sukhriddin
119 | 147/2 | DC1+0 | 2024-12-17 | 470077 | 64.254 | Completed. | 2024-12-23 | Mukesh Kumar
120 | 106A/2 | DA-3 | 2024-12-19 | 273608.93 | 36.045 | Completed. | 2024-12-28 | Barkat Ali
121 | 163/2 | DA+0 | 2024-11-28 | 286911 | 37.73 | Completed. | 2024-12-29 | Rahim
122 | 106A/1 | DA+6 | 2024-12-22 | 342192 | 44.728 | Completed | 2024-12-28 | DK Verma
123 | 125/0 | DD60+0 | 2024-12-22 | 604881 | 80.408 | Completed. | 2025-01-05 | MJR
124 | 132/1 | DA+0 | 2024-12-22 | 286911 | 37.73 | Completed. | 2024-12-30 | SK Samuil
125 | 135A/6 | DA+0 | 2024-12-21 | 286911 | 37.73 | Completed. | 2024-12-26 | Dhaneshwar mahto
126 | 147A/0 | DB1+18 | 2024-12-24 | 670636 | 82.239 | Completed. | 2025-01-03 | Mukesh Kumar
127 | 135A/0 | DC1+0 | 2024-12-27 | 470077 | 64.254 | Completed. | 2025-01-04 | Dhaneshwar Mahto
128 | 106A/0 | DC2+0 | 2024-12-29 | 470077 | 64.254 | Completed. | 2025-01-03 | DK Verma
129 | 124A/0 | DD60+0 | 2024-12-21 | 604881 | 80.408 | Completed. | 2025-01-05 | Gouri Shankar
130 | 129/0 | DD60+6 | 2024-12-30 | 719574 | 94.408 | Completed. | 2025-01-18 | Barkat Ali
131 | 164/0 | DB2+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Sukhriddin
132 | 164/1 | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-16 | Modina India-2
133 | 130/4 | DA+3 | 2024-12-22 | 297143 | 39.459 | Completed. | 2025-01-21 | SK Samuil
134 | 158B/2 | DA+3 | 2024-12-31 | 297143 | 39.459 | Completed. | 2025-01-10 | Rahul Kumar
135 | 163/1 | DA+0 | 2024-12-30 | 286911 | 37.73 | Completed. | 2025-01-08 | Rahim
136 | 135/0 | DC2+25 | 2025-01-09 |  | 109.628 | Completed. | 2025-01-22 | DK Verma
137 | 148/0 | DC2+0 | 2025-01-04 | 470077 | 64.254 | Completed. | 2025-01-10 | Mukesh Kumar
138 | 135/1 | DA+6 | 2025-01-06 | 342192 | 44.728 | Completed. | 2025-01-11 | Surender Mahto
139 | 130/3 | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-18 | MJR
140 | 136/0 | DD45+18 | 2025-01-09 | 906755 | 112.424 | Completed. | 2025-01-25 | Gouri Shankar
141 | 148/3 | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-19 | Modina Inda-1
142 | 163/6 | DA+0 | 2025-01-10 | 286911 | 37.73 | Completed. | 2025-01-25 | Barkat Ali
143 | 164/3 | DA+0 | 2025-01-11 | 286911 | 37.73 | Completed. | 2025-01-20 | Rahim Khan
144 | 135A/5 | DA+0 | 2025-01-13 | 286911 | 37.73 | Completed. | 2025-01-18 | Dhaneshwar Mahto
145 | 163/4 | DA+0 | 2025-01-16 | 286911 | 37.73 | Completed. | 2025-01-29 | Sukhriddin
146 | 163/5 | DA+0 | 2025-01-12 | 286911 | 37.73 | Completed. | 2025-02-20 | Barkat Ali
147 | 130/2 | DA+3 | 2025-01-20 | 297143 | 39.459 | Completed. | 2025-01-29 | MJR
148 | 163/0 | DC2+0 | 2025-01-16 | 470077 | 64.254 | Completed. | 2025-01-23 | Rahul Kumar
149 | 159/4 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-03 | Modina India-2
150 | 137A/6 | DA+9 | 2025-01-20 | 357181 | 46.623 | Completed. | 2025-01-24 | Dhaneshwar Mahto
151 | 131/0 | DD45+3 | 2025-01-21 | 573550 | 75.452 | Completed. | 2025-02-05 | Barkat Ali
152 | 148/2 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-01-30 | Modina India-1
153 | 159/1 | DA+0 | 2025-01-21 | 286911 | 37.73 | Completed. | 2025-02-12 | Rahim Khan
154 | 130/1 | DA+0 | 2025-01-25 | 286911 | 37.73 | Completed. | 2025-02-09 | SK Samuil
155 | 137A/0 | DB1+0 | 2025-01-23 | 403998 | 54.418 | Completed. | 2025-01-29 | DK Verma
156 | 147/6 | DA-3 | 2025-01-27 | 273608.93 | 36.045 | Completed. | 2025-02-18 | Ajay Kumar
157 | 161/0 | DD60+25 | 2025-01-28 | 1099828 | 141.874 | Completed. | 2025-02-16 | Rahul Kumar
158 | 137/6 | DA+0 | 2025-01-27 | 286911 | 37.73 | Completed. | 2025-02-07 | SK Samuil
159 | 137A/1 | DA+6 | 2025-01-27 | 342192 | 44.728 | Completed. | 2025-01-29 | Dhaneshwar Mahto
160 | 138/0 | DB2+0 | 2025-01-27 | 403998 | 54.418 | Completed. | 2025-02-01 | Gouri Shankar
161 | 137A/2 | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-02 | Dhaneshwar Mahto
162 | 139/0 | DB2+0 | 2025-01-30 | 403998 | 54.418 | Completed. | 2025-02-04 | DK Verma
163 | 148/1 | DA+3 | 2025-02-01 | 297143 | 39.459 | Completed. | 2025-02-09 | Modina India
165 | 137/0 | DC2+9 | 2025-02-01 | 585620 | 77.718 | Completed. | 2025-02-15 | MJR
166 | 137/5 | DA+3 | 2025-02-03 | 297143 | 39.459 | Completed. | 2025-02-07 | Dhaneshwar Mahto
167 | 138/1 | DA+6 | 2025-02-03 | 342192 | 44.728 | Completed. | 2025-02-09 | Gouri Shankar
168 | 157/1 | DA+0 | 2025-02-09 | 286911 | 37.73 | Completed. | 2025-02-18 | Sukhriddin
169 | 157/2 | DA+0 | 2025-02-23 | 286911 | 37.73 | Completed. | 2025-03-11 | Barkat Ali
170 | 138/2 | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-11 | DK Verma
171 | 139A/0 | DB2+9 | 2025-02-09 | 503365 | 65.757 | Completed. | 2025-02-14 | Dhaneshwar Mahto
172 | 141/1 | DA+0 | 2025-02-11 | 286911 | 37.73 | Completed. | 2025-02-17 | SK Samuil
173 | 139/2 | DA+0 | 2025-02-10 | 286911 | 37.73 | Completed. | 2025-02-14 | Gouri Shankar
174 | 141/2 | DA-3 | 2025-02-13 | 273608.93 | 36.045 | Completed. | 2025-02-19 | SK Samui
175 | 147B/1 | DA+0 | 2025-02-13 | 286911 | 37.73 | Completed. | 2025-02-21 | Modina India
176 | 139/1 | DA+3 | 2025-02-12 | 297143 | 39.459 | Completed. | 2025-02-17 | DK Verma
177 | 141/3 | DA+3 | 2025-02-19 | 297143 | 39.459 | Completed. | 2025-02-25 | SK Samui-3
178 | 137/2 | DA+0 | 2025-02-18 | 286911 | 37.73 | Completed. | 2025-02-27 | MJR
179 | 140/0 | DD60+0 | 2025-02-16 | 604881 | 80.408 | Completed. | 2025-02-22 | Dhaneshwar Mahto
180 | 141/0 | DD60+3 | 2025-02-16 | 635073 | 84.299 | Completed. | 2025-02-23 | Gouri Shankar
181 | 162/0 | DD60+25 | 2025-02-20 | 1099828 | 141.874 | Completed. | 2025-03-09 | Rahul Kumar
182 | 142/0 | DD60+0 | 2025-02-18 | 604881 | 80.408 | Completed. | 2025-03-03 | DK Verma
183 | 148/5 | DA+0 | 2025-02-25 | 286911 | 37.73 | Completed. | 2025-02-28 | SK Samui | Crane erection
185 | 145A/1 | DA+3 | 2025-02-22 | 297143 | 39.459 | Completed. | 2025-03-07 | Sulen sarkar
186.3333 | 147B/0 | DB1+18 | 2025-02-26 | 670636 | 82.239 | Completed. | 2025-03-22 | Modina India
187.8333 | 143/0 | DD60+3 | 2025-02-25 | 635073 | 84.299 | Completed. | 2025-03-04 | Gouri Shankar
189.3333 | 143A/0 | DD45+0 | 2025-02-24 | 546238 | 72.238 | Completed. | 2025-03-02 | Dhaneshwar Mahto
190.8333 | 145A/3 | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-16 | Sulen Sarkar
192.3333 | 149/1 | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-27 | SK Samui | Crane erection
193.8333 | 143A/1 | DA+6 | 2025-03-01 | 342192 | 44.728 | Completed. | 2025-03-09 | SK Samui
195.3333 | 143A/4 | DA+0 | 2025-03-02 | 286911 | 37.73 | Completed. | 2025-03-10 | MJR
196.8333 | 148/6 | DA+0 | 2025-03-03 | 286911 | 37.73 | Completed. | 2025-03-09 | SK Samui
198.3333 | 143A/2 | DD45+0 | 2025-03-04 | 546238 | 72.238 | Completed. | 2025-03-17 | Dhaneshwar Mahto
199.8333 | 143A/3 | DD45+3 | 2025-03-05 | 573550 | 75.452 | Completed. | 2025-03-11 | Gouri Shankar
201.3333 | 143A/5 | DA+3 | 2025-03-05 | 297143 | 39.459 | Completed. | 2025-03-10 | DK Verma
202.8333 | 148/7 | DA+0 | 2025-03-08 | 286911 | 37.73 | Completed. | 2025-03-20 | Rahim Khan | Crane erection
204.3333 | 149/0 | DB2+0 | 2025-03-10 | 403998 | 54.418 | Completed. | 2025-04-06 | SK Samui
205.8333 | 157/0 | DD60+6 | 2025-03-12 | 719574 | 94.408 | Completed. | 2025-03-27 | Rahim Khan
207.3333 | 145A/0 | DB1+6 | 2025-03-15 | 480757 | 63.509 | Completed. | 2025-03-28 | MJR
208.8333 | 146/0 | DC1+9 | 2025-03-12 | 585620 | 77.718 | Completed. | 2025-03-22 | DK Verma
210.3333 | 158/2 | DA-3 | 2025-03-13 | 273608.93 | 36.045 | Completed. | 2025-03-18 | Rahul Kumar
211.8333 | 150/1 | DA+9 | 2025-03-20 | 357181 | 46.623 | Completed. | 2025-04-06 | MJR
213.3333 | 150/2 | DA+3 | 2025-03-18 | 297143 | 39.459 | Completed. | 2025-03-22 | SK Samui
214.8333 | 150/3 | DA+6 | 2025-03-19 | 342192 | 44.728 | Completed. | 2025-04-01 | Rupesh
216.3333 | 152A/0 | DB1+0 | 2025-03-16 | 403998 | 54.418 | Completed. | 2025-03-20 | Gouri Shankar
217.8333 | 155/6 | DA-3 | 2025-03-15 | 273608.93 | 36.045 | Completed. | 2025-03-23 | Barkat Ali
219.3333 | 145A/2 | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-27 | Sulen sarkar
220.8333 | 156/0 | DD60+3 | 2025-03-22 | 635073 | 84.299 | Completed. | 2025-03-28 | Rahul Kumar
222.3333 | 147/0 | DC2+9 | 2025-03-24 | 585620 | 77.718 | Completed. | 2025-04-01 | DK Verma
223.8333 | 151/0 | DB2+3 | 2025-03-21 | 424198 | 56.863 | Completed. | 2025-03-27 | Gouri Shankar
225.3333 | 150A/0 | DC1+0 | 2025-03-25 | 470077 | 64.254 | Completed. | 2025-04-11 | Rahim Khan
226.8333 | 155/1 | DA+0 | 2025-03-26 | 286911 | 37.73 | Completed. | 2025-04-03 | Barkat Ali
228.3333 | 158/0 | DB2+0 | 2025-04-02 | 403998 | 54.418 | Completed. | 2025-04-10 | Rahim Khan
229.8333 | 155/0 | DD60+0 | 2025-04-02 | 604881 | 80.408 | Completed. | 2025-04-11 | Rahul Kumar
231.3333 | 158/1 | DA-3 | 2025-04-07 | 273608.93 | 36.045 | Completed. | 2025-04-25 | Barkat Ali
232 | 135/7 | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-22 | SK samui
233 | 155/4 | DA+0 | 2025-04-28 | 286911 | 37.73 | Completed. | 2025-05-11 | SK Samui | 02 days idle |  |  |  | 04 days ROW.
234 | 155/5 | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-11 | Barkat Ali | 02 days idle
235 | 150/0 | DD60+9 | 2025-03-22 | 753337 | 98.836 | Completed. | 2025-03-31 | Dhaneshwar mahto
236 | 105/0 | DD60+35 | 2025-05-24 | 1294023 | 172.017 | Middle section is u/p. |  | Rupesh
237 | 165/1 | DA+0 | 2025-05-16 | 286911 | 37.73 | Completed. | 2025-05-25 | Barkat Ali
238 | 104/0 | DD60+35 | 2025-06-01 | 1294023 | 172.017 | Completed.Tightening u/p. | 2025-08-13 | Dhaneshwar
240 | 153/0 | DD60+25 | 2025-06-15 | 1099828 | 141.874 | Completed. | 2025-08-08 | Barkat Ali & Mithun Gang | Mithun gang shifted to this loc. on 12-06-2026
241 | 160/0 | DD60+18 |  | 1003256 | 129.341 | Materials shifting is u/p.Gang shifted.
242 | 101/0 | DD60+35 | 2025-06-15 | 1294023 | 171.017 | 2nd section completed. |  | Sanjay Kumar & Dhaneshwar | Sanjya kumar demobilsed on 20-07-2025. Dhaneshwar mahto gang joined on 19-08-2025.
243 | 157/3 | DA+0 | 2025-06-15 | 286911 | 37.73 | 2nd section is u/p.Gang shifting done.No work due to ROW. Again ROW from 23-07-2025. |  | Barkat Ali & Sukhriddin | Sukhriddin gang moved to this loc. On 22-07-2025.ROW from 24-06-2025 to 21-07-2025.Sukhriddin gang demobilized on 25-07-2025.
12183.502

## EREC-NAV
Tower Erection Part-II (Navsari Section)
Sl. No. | Loc. No. | Type of Tower | Start Date | Revenue | Tower Weight (MT) | Status | End Date | Sub Contractor | Manpower | Hindarnce Days | Remarks | Tackweldng Status | Tackwelding start date | Tackwelding Completion date | Sub Contractor name
1 | 159/3 | DA+0 | 2024-07-08 | 286911 | 37.73 | Completed | 2024-07-23 | Sukhridwin
2 | 255/4 | DA+0 | 2024-07-10 | 286911 | 37.73 | Completed | 2024-08-22 | Ghanshyam
3 | 164/2 | DA+0 | 2024-07-27 | 286911 | 37.73 | Completed | 2024-08-13 | Sukhridwin
4 | 159/0 | DB+0 | 2024-08-14 | 403998 | 54.418 | Completed. | 2024-09-08 | Sukhridwin
5 | 267A/3 | DA+0 | 2024-08-21 | 286911 | 37.73 | Completed. | 2024-09-13 | Ramjivan-01
6 | 257/3 | DA+0 | 2024-08-29 | 286911 | 37.73 | Completed | 2024-10-06 | Chahanur Bibi
7 | 257/0 | DC+0 | 2024-08-30 | 470077 | 64.254 | Completed | 2024-09-23 | Ghanshyam Mahto
8 | 165/2 | DA+0 | 2024-09-09 | 286911 | 37.73 | Completed | 2024-09-20 | Sukhridwin
9 | 260/0 | DD60+18 | 2024-09-11 | 1003256 | 129.341 | Completed. | 2024-10-31 | Ramjivan-02 | 34
11 | 270/2 | DA+3 | 2024-09-14 | 297143 | 39.459 | Completed. | 2024-10-28 | Senahul
12 | 164/7 | DA+0 | 2024-09-22 | 286911 | 37.73 | Completed | 2024-10-09 | Sukuriddne
13 | 257/2 | DA-3 | 2024-09-23 | 273608.93 | 36.044 | Completed | 2024-10-24 | Ghanshyam Mahto | 42
14 | 265/0 | DB2+3 | 2024-09-30 | 424198 | 56.863 | Completed. | 2024-10-31 | Thanu mahto
16 | 165/0 | DB2+0 | 2024-10-09 | 403998 | 54.418 | Completed. | 2024-10-28 | Sukuriddne
17 | 158A/0 | DD45+6 | 2024-10-23 | 650023 | 85.234 | Completed. | 2024-11-12 | Rahul Kumar | 23
18 | 262/1 | DA+0 | 2024-10-25 | 286911 | 37.73 | Completed. | 2024-11-07 | Ghanshyam Mahto
19 | 257/4 | DA+0 | 2024-10-29 | 286911 | 37.73 | Completed. | 2024-11-16 | Thanu mahto
20 | 165/3 | DA+6 | 2024-10-30 | 342192 | 44.728 | Completed. | 2024-11-15 | Sukhruddin | 35
21 | 254/0 | DB2+0 | 2024-11-04 | 403998 | 54.418 | Completed. | 2024-11-21 | Senahul
23 | 259/0 | DD60+18 | 2024-11-10 | 1003256 | 129.341 | Completed. | 2024-12-23 | Maa Construction | 29
24 | 268/0 | DD60+6 | 2024-11-10 | 719574 | 94.408 | Completed. | 2024-12-07 | Daulat Mahto | 29
25 | 155/3 | DA+3 | 2024-11-16 | 297143 | 39.459 | Completed. | 2024-11-22 | Rahul Kumar
27 | 189/0 | DB2+6 | 2024-11-22 | 480757 | 63.509 | Completed. | 2024-12-14 | Barkat Ali
28 | 191A/1 | DA-3 | 2024-11-22 | 273608.93 | 36.045 | Completed. | 2024-11-30 | Midhun
29 | 187/3 | DA+0 | 2024-11-22 | 286911 | 37.73 | Completed. | 2024-11-26 | Jwala
30 | 261/0 | DC2+18 | 2024-11-23 | 780122 | 97.934 | Completed. | 2024-12-28 | Ghanshyam mahto
31 | 264/0 | DC1+6 | 2024-11-17 | 559332 | 74.632 | Completed. | 2024-12-10 | Thanu Mahto
33 | 255/0 | DD60+3 | 2024-11-27 | 635073 | 84.299 | Completed. | 2024-12-21 | Senahul-01
34 | 188/0 | DB1+6 | 2024-11-27 | 480757 | 63.509 | Completed. | 2024-12-10 | Jwala
35 | 251/0 | DB1+9 | 2024-12-03 | 503365 | 65.757 | Completed. | 2024-12-28 | Senahul-02
36 | 272/1 | DA+9 | 2024-12-02 | 357181 | 46.623 | Completed. | 2024-12-16 | MJR
37 | 191/1 | DA+0 | 2024-12-09 | 286911 | 37.73 | Completed. | 2024-12-23 | Midhun
38 | 193/0 | DD60+6 | 2024-12-11 | 719574 | 94.408 | Completed. | 2024-12-21 | Jwala
39 | 270/1 | DA+0 | 2024-12-11 | 286911 | 37.73 | Completed. | 2024-12-24 | Daulat Mahto
40 | 272/0 | DC1+6 | 2024-12-11 | 559332 | 74.632 | Completed. | 2024-12-31 | Thanu mahto
41 | 197/4 | DA+0 | 2024-12-23 | 286911 | 37.73 | Completed. | 2024-12-29 | Jwala
42 | 266/0 | DB1+0 | 2024-12-28 | 403998 | 54.418 | Completed. | 2025-01-12 | Senahul-01
43 | 187/2 | DA-3 | 2024-12-26 | 273608.93 | 36.045 | Completed. | 2025-01-04 | Midhun
44 | 255/3 | DA+3 | 2024-12-26 | 297143 | 39.459 | Completed. | 2025-01-02 | Maa Construction
45 | 269/1 | DA+0 | 2024-12-28 | 286911 | 37.73 | Completed. | 2025-01-07 | Daulat Mahto
46 | 263/0 | DC2+0 | 2024-12-31 | 470077 | 64.254 | Completed. | 2025-01-13 | Ghanshyam Mahto
47 | 196/0 | DD60+9 | 2024-12-31 | 753337 | 98.839 | Completed. | 2025-01-10 | Jwala
| 266/1 | DB1+6 | 2025-01-13 | 480757 | 63.509 | Completed. | 2025-01-29 | Senahul
49 | 271/5 | DA-3 | 2025-01-01 | 273608.93 | 36.045 | Completed. | 2025-01-11 | Thanu mahto
50 | 255/2 | DA+0 | 2025-01-03 | 286911 | 37.73 | Completed. | 2025-01-10 | Maa Construction
51 | 197/3 | DA+0 | 2025-01-07 | 286911 | 37.73 | Completed. | 2025-01-16 | Midhun
52 | 197/0 | DD60+9 | 2025-01-12 | 753337 | 98.836 | Completed. | 2025-01-22 | Jwala
53 | 257/1 | DA+0 | 2025-01-09 | 286911 | 37.73 | Completed. | 2025-01-17 | Daulat Mahto
54 | 269/2 | DA+6 | 2025-01-11 | 342192 | 44.728 | Completed. | 2025-01-19 | Maa Construction
55 | 272/5 | DB1+0 | 2025-01-13 | 403998 | 54.418 | Completed. | 2025-01-23 | Thanu mahto
56 | 262/0 | DD45+9 | 2025-01-18 | 680590 | 89.146 | Completed. | 2025-02-11 | Ghanshyam Mahto
57 | 272/3 | DA+3 | 2025-01-17 | 297143 | 39.459 | Completed. | 2025-02-06 | Tajirul
58 | 198/1 | DA+0 | 2025-01-17 | 286911 | 37.73 | Completed. | 2025-01-27 | Midhun
59 | 255/1 | DA+6 | 2025-01-19 | 342192 | 44.728 | Completed. | 2025-01-27 | Daulat Mahto
60 | 267/0 | DC1+9(2M RC) | 2025-01-21 | 585620 | 77.718 | Completed. | 2025-01-31 | Maa Construction
61 | 272/4 | DA+3 | 2025-01-25 | 297143 | 39.459 | Completed. | 2025-02-02 | Thanu mahto
62 | 272A/1 | DA+6 | 2025-01-24 | 342192 | 44.728 | Completed. | 2025-01-29 | Jwala
63 | 197/2 | DA+0 | 2025-01-29 | 286911 | 37.73 | Completed. | 2025-02-07 | Midhun
64 | 272/2 | DA-3 | 2025-01-30 | 273608.93 | 36.045 | Completed. | 2025-02-04 | Daulat Mahto
65 | 253/0 | DC1+0 | 2025-02-01 | 470077 | 64.254 | Completed. | 2025-02-17 | Senahul
66 | 272A/2 | DA+0 | 2025-01-30 | 286911 | 37.73 | Completed. | 2025-02-04 | Jwala
67 | 271/0 | DC1+0 | 2025-02-04 | 470077 | 64.254 | Completed. | 2025-02-13 | Thanu mahto
68 | 266/2 | DA+0 | 2025-02-04 | 286911 | 37.73 | Completed. | 2025-02-12 | Maa Construction
69 | 270A/0 | DC2+0 | 2025-02-05 | 470077 | 64.254 | Completed. | 2025-02-15 | Daulat Mahto
70 | 272A/3 | DA+0 | 2025-02-05 | 286911 | 37.73 | Completed. | 2025-02-09 | Jwala
71 | 272/7 | DA+9 | 2025-02-10 | 357181 | 46.623 | Completed. | 2025-03-07 | Tajirul |  |  | Mithun Gang join at 02-03-2025
72 | 270/6 | DA-3 | 2025-02-11 | 273608.93 | 36.045 | Completed. | 2025-02-17 | Mithun
73 | 250/1 | DA-3 | 2025-02-14 | 273608.93 | 36.045 | Completed. | 2025-02-24 | Ghanshyam Mahto
74 | 249/0 | DB2+0 | 2025-02-14 | 403998 | 54.418 | Completed. | 2025-02-26 | Maa Construction
75 | 271/2 | DA+0 | 2025-02-14 | 286911 | 37.73 | Completed. | 2025-02-21 | Thanu Mahto
76 | 270/7 | DA-3 | 2025-02-17 | 273608.93 | 36.045 | Completed. | 2025-02-23 | Daulat Mahto
77 | 274/0 | DC1+0 | 2025-02-17 | 470077 | 64.254 | Completed. | 2025-02-23 | Jwala
78 | 267A/0 | DC2+9(2M RC) | 2025-02-21 |  | 77.718 | Completed. | 2025-03-18 | Senahul
79 | 270/5 | DA+0 | 2025-02-20 | 286911 | 37.73 | Completed. | 2025-02-28 | Mithun
80 | 270/0 | DD45+0 | 2025-02-22 | 546238 | 72.238 | Completed. | 2025-03-16 | Anarul Haque
81 | 271/4 | DA-3 | 2025-02-22 | 273608.93 | 36.045 | Completed. | 2025-03-03 | Thanu Mahto
82 | 273/2 | DA+6 | 2025-02-24 | 342192 | 44.728 | Completed. | 2025-02-28 | Jwala
83 | 267A/1 | DA+0 | 2025-02-27 | 286911 | 37.73 | Completed. | 2025-03-05 | Daulat Mahto
84 | 171/0 | DD60+25(3M RC) | 2025-02-26 | 1099828 | 141.874 | Completed. | 2025-03-29 | Sukhriddin |  |  | Crane erection
85 | 249/2 | DA+0 | 2025-03-01 | 286911 | 37.73 | Completed. | 2025-03-09 | Maa Construction
86 | 270/4 | DA+0 | 2025-03-09 | 286911 | 37.73 | Completed. | 2025-03-28 | Mithun | 15
87 | 272A/6 | DA-3 | 2025-03-02 | 273608.93 | 36.045 | Completed. | 2025-03-05 | Jwala
88 | 272A/7 | DA-3 | 2025-03-06 | 273608.93 | 36.045 | Completed. | 2025-03-10 | Jwala
89 | 271/3 | DA-3 | 2035-03-04 | 273608.93 | 36.045 | Completed. | 2025-03-11 | Thanu Mahto
90 | 267A/2 | DA-3 | 2025-03-07 | 273608.93 | 36.045 | Completed. | 2025-03-15 | Daulat Mahto
91 | 249/3 | DA+0 | 2025-03-10 | 286911 | 37.73 | Completed. | 2025-03-18 | Maa Construction |  |  | After complete 02 days gang not interested to work.
92 | 272A/5 | DA+3 | 2025-03-11 | 297143 | 39.459 | Completed. | 2025-03-16 | Jwala
93 | 270/3 | DA-3 | 2025-03-19 | 273608.93 | 36.045 | Completed. | 2025-03-28 | Thanu mahto
95 | 252/0 | DC1+18 | 2025-03-18 | 780122 | 97.934 | Completed. | 2025-04-11 | Anarul Haque | 20 |  | 24
96 | 272A/4 | DA+0 | 2025-03-17 | 286911 | 37.73 | Completed. | 2025-03-20 | Jwala
97 | 272/6 | DA+3 | 2025-03-19 | 297143 | 39.459 | Completed. | 2025-03-30 | Daulat Mahto
98 | 272A/0 | DB1+18(2M RC) | 2025-04-03 | 670636 | 82.239 | Completed. | 2025-04-26 | Senahul | 34
99 | 271/1 | DA-3 | 2025-03-21 | 273608.93 | 36.045 | Completed. | 2025-03-25 | Jwala
100 | 250/0 | DD60+0 | 2025-03-21 | 604881 | 80.408 | Completed. | 2025-04-12 | Maa Construction | 16 |  | 22
101 | 269/0 | DD60+0 | 2025-03-26 | 604881 | 80.408 | Completed. | 2025-04-01 | Jwala
102 | 167/3 | DA+6 | 2025-03-28 | 342192 | 44.728 | Completed. | 2025-04-06 | Barkat Ali | 34 |  | 9
103 | 195/2 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-08 | Samirul | 24
104 | 195A/3 | DA+0 | 2025-03-30 | 286911 | 37.73 | Completed. | 2025-04-08 | Modina India | 22
105 | 198/0 | DC1+0 | 2025-04-01 | 470077 | 64.254 | Completed. | 2025-04-15 | Mithun-2 | 21
106 | 197/1 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | Mithun-1 | 22
107 | 187/1 | DA+3 | 2025-04-03 | 297143 | 39.459 | Completed. | 2025-04-12 | Thanu mahto | 24
108 | 172/0 | DD60+25 | 2025-04-02 | 1099828 | 141.874 | Completed. | 2025-04-28 | Sukhriddin | 36 |  | Crane erection
109 | 198/2 | DA+0 | 2025-04-04 | 286911 | 37.73 | Completed. | 2025-04-12 | Daulat Mahto | 27 |  | 8
110 | 248/5 | DA+0 | 2025-04-01 | 286911 | 37.73 | Completed. | 2025-04-12 | SulenSarkar | 26
111 | 181/0 | DD45+18 | 2025-04-06 | 906755 | 112.424 | Completed. | 2025-04-27 | DK Verma | 26
112 | 178/0 | DD60+6 | 2025-04-06 | 719574 | 94.408 | Completed. | 2025-04-13 | Gouri Shankar | 27 |  | 7
113 | 273/1 | DA+6 | 2025-04-04 | 342192 | 44.728 | Completed. | 2025-04-09 | Jwala | 28
114 | 168/0 | DC1+0 | 2025-04-06 | 470077 | 64.254 | Completed. | 2025-04-16 | Rupesh | 22
115 | 189/1 | DA+0 | 2025-04-05 | 286911 | 37.73 | Completed. | 2025-04-11 | Dhaneshwar | 26 |  | 6
116 | 167/2 | DA+6 | 2025-04-08 | 342192 | 44.728 | Completed. | 2025-04-18 | Barkat Ali
117 | 195A/2 | DA+6 | 2025-04-11 | 342192 | 44.728 | Completed. | 2025-04-22 | Modina india
118 | 195/4 | DA+0 | 2025-04-09 | 286911 | 37.73 | Completed. | 2025-04-15 | Samirul
120 | 179/0 | DD60+0 | 2025-04-16 | 604881 | 80.408 | Completed. | 2025-04-22 | Gouri Shankar
121 | 190/0 | DD45+25 | 2025-04-18 | 994153 | 122.808 | Completed. | 2025-05-06 | Dhaneshwar |  |  | Crane erection
122 | 187/0 | DD60+25 | 2025-04-22 | 1099828 | 141.874 | Cage section is u/p. ROW |  | Thanu Mahto |  | ROW from 22-05-2025 | Crane erection
123 | 205/1 | DA-3 | 2025-04-11 | 273608.93 | 36.045 | Completed | 2025-04-16 | Jwala
124 | 182/0 | DD60+0 | 2025-04-28 | 604881 | 80.408 | Completed. | 2025-05-06 | DK Verma
125 | 192/0 | DC1+0 | 2025-04-13 | 470077 | 64.254 | Completed. | 2025-04-28 | MJR | 34
126 | 194/0 | DD60+6 | 2025-04-22 | 719574 | 94.408 | Completed. | 2025-05-15 | MJR-2
127 | 248/0 | DC2+9 | 2025-04-14 | 585620 | 77.718 | Completed. | 2025-04-30 | Anarul Haque
128 | 249/1 | DA+0 | 2025-04-13 | 286911 | 37.73 | Completed. | 2025-04-21 | SulenSarkar
129 | 167/0 | DD60+0 | 2025-04-18 | 604881 | 80.408 | Completed. | 2025-05-05 | Rupesh
130 | 195/1 | DA+6 | 2025-04-16 | 342192 | 44.728 | Completed. | 2025-04-25 | Mithun-1
131 | 248/4 | DA+3 | 2025-04-17 | 297143 | 39.459 | Completed. | 2025-05-05 | Rahim Khan-2 & MJR-1
132 | 205/0 | DD60+3 (2M RC) | 2025-04-18 | 635073 | 84.299 | Completed. | 2025-04-29 | Jwala
133 | 199/0 | DD45+18 | 2025-04-18 | 906755 | 112.424 | Completed. | 2025-05-22 | Mithun-2
134 | 191A/0 | DB2+0 | 2025-04-15 | 403998 | 54.418 | Completed. | 2025-04-22 | Rahul Kumar
135 | 181/2 | DA+0 | 2025-04-16 | 286911 | 37.73 | Completed. | 2025-04-22 | Rahim Khan-1
136 | 195/3 | DA+6 | 2025-04-18 | 342192 | 44.728 | Completed. | 2025-04-28 | Samirul
137 | 248/2 | DA+9 | 2025-04-17 | 357181 | 46.623 | Completed. | 2025-04-30 | Rahim Khan-3 & Sulen sarkar |  |  | Sulen sarkar
138 | 195A/0 | DB1+0 | 2025-04-22 | 403998 | 54.418 | Completed. | 2025-05-18 | Daulat Mahto |  | 1 | After lunch gang strike.
139 | 167/4 | DA+0 | 2025-04-20 | 286911 | 37.73 | Completed. | 2025-04-29 | Barkat Ali
140 | 248/6 | DA+0 | 2025-04-29 | 286911 | 37.73 | Completed. | 2025-05-09 | Senahul
141 | 195A/1 | DA+6 | 2025-04-24 | 342192 | 44.728 | Completed. | 2025-05-09 | Modina India
142 | 191/2 | DA-3 | 2025-04-23 | 273608.93 | 36.045 | Completed. | 2025-04-27 | Rahul Kumar
143 | 180/0 | DD45+9 | 2025-04-24 | 680590 | 89.146 | Completed. | 2025-05-03 | Gouri Shankar |  |  | Crane erection
144 | 181/1 | DA+0 | 2025-04-24 | 286911 | 37.73 | Completed. | 2025-04-30 | Rahim Khan-1
145 | 195/0 | DC2+0 | 2025-04-28 | 470077 | 64.254 | Completed. | 2025-05-11 | Mithun-1 |  |  | Crane erection
146 | 204/0 | DD60+9 | 2025-05-02 | 753337 | 98.836 | Completed. | 2025-05-11 | Jwala
147 | 191/3 | DA-3 | 2025-04-29 | 273608.93 | 36.045 | Completed. | 2025-05-04 | Rahul Kumar
148 | 195/5 | DA+6 | 2025-05-02 | 342192 | 44.728 | Completed. | 2025-05-11 | Samirul
149 | 168/2 | DA+0 | 2025-05-02 | 286911 | 37.73 | Completed. | 2025-05-11 | Sukhriddin
151 | 167/1 | DA+9 | 2025-05-04 | 357181 | 46.623 | Completed. | 2025-05-19 | Barkat Ali
152 | 217A/1 | DA+3 | 2025-05-04 | 297143 | 39.459 | Completed. | 2025-05-18 | Rahim Khan-3
153 | 181/4 | DA+0 | 2025-05-03 | 286911 | 37.73 | Completed. | 2025-05-11 | Rahim Khan-1
155 | 248/1 | DA+9 | 2025-05-06 | 357181 | 46.623 | Completed. | 2025-05-18 | Sulen Sarkar & DK Verma |  |  | 02days no work due to strike.
157 | 177/0 | DD60+0 | 2025-05-06 | 604881 | 80.408 | Completed. | 2025-05-18 | Gouri Shankar
158 | 209/0 | DC1+0 | 2025-05-08 | 470077 | 64.254 | Completed. | 2025-05-16 | Rahul Kumar
159 | 248/3 | DA+6 | 2025-05-09 | 342192 | 44.728 | Completed. | 2025-05-20 | MJR-1
160 | 172/1 | DA+3 | 2025-05-16 | 297143 | 39.459 | Ist section done.Collapse on 24-05-2025 |  | Rupesh |  | 1 | 1-S/D not avail.
161 | 247/1 | DA+0 | 2025-05-11 | 286911 | 37.73 | Completed. | 2025-05-19 | Sulen sarkar
162 | 211/1 | DA+0 | 2025-05-13 | 286911 | 37.73 | Completed. | 2025-05-18 | Dhaneshwar |  |  | Crane
163 | 247/3 | DA-3 | 2025-03-14 | 273608.93 | 36.045 | Cage section is u/p. ROW. |  | Modina india |  | 4 | ROW from 19-05-2025
164 | 247/4 | DA+0 | 2025-05-13 | 286911 | 37.73 | Body completed.ROW |  | Senahul |  | 4 | ROW from 19-05-2025-04-06-2025
165 | 168/1 | DA-3 | 2025-05-13 | 273608.93 | 36.045 | Completed. | 2025-05-20 | Rahim Khan-1
166 | 205/2 | DA+3 | 2025-05-15 | 297143 | 39.459 | Completed. | 2025-05-21 | Jwala
167 | 247/2 | DA+3 |  | 297143 | 39.459 | Materiala shifting has been done.ROW |  | MJR-2 | Gang demobilized on 26-05-2025. | 4 | From 16-05-2025 idle due to ROW.
168 | 210/0 | DB2+18 | 2025-05-17 | 670636 | 82.239 | 3rd section is u/p.ROW |  | Rahul Kumar |  |  | ROW from 23-05-2025
169 | 191/0 | DD45+25 | 2025-06-02 | 994153 | 122.808 | Body with peak completed. |  | Daulat Mahto |  | 1 | 1-Approach road issues
170 | 181/3 | DA+0 | 2025-05-19 | 286911 | 37.73 | Completed. | 2025-05-24 | Gouri Shankar
171 | 218/0 | DD60+0 |  | 604881 | 80.408 | Ground assemble is u/p.ROW |  | Dhaneshwar |  | 3 | 02 days idle at 214/0 due to ROW
172 | 217A/2 | DA+0 | 2025-05-19 | 286911 | 37.73 | Ist section done.ROW |  | Rahim Khan-3 |  |  | ROW from 22-05-2025
173 | 247/0 | DD60+0 |  | 604881 |  |  |  | DK Verma |  | 3 | ROW from 19-05-2025 to 23-05-2025.Gang moved to 169/0.
174 | 242/2 |  |  |  |  | ROW |  | Sulen Sarkar | Gang demobilized on 26-05-2025. | 3 | ROW from 20-05-2025
175 | 243/0 |  |  |  |  | ROW |  | MJR-1 | Gang demobilized on 26-05-2025. | 3 | ROW from 21-05-2025
176 | 206/0 | DD60+25 | 2025-05-23 | 1099828 | 141.874 | 3rd section is u/p.ROW |  | Jwala |  |  | ROW since 31-05-2025
177 | 169/0 | DD45+18 | 2025-05-24 | 906755 | 112.424 | Completed. | 2025-06-08 | DK Verma
178 | 175/0 | DD45+0 | 2025-05-28 | 546238 | 72.238 | Completed. | 2025-06-05 | Gouri Shankar
179 | 172/2 | DA+6 | 2025-05-29 | 342192 | 44.728 | Completed. | 2025-06-06 | Thanu Mahto
180 | 174/0 | DD60+18 | 2025-06-01 | 1003256 | 129.341 | Ist section is u/p.ROW |  | Mithun |  | 5 | ROW since 04-06-2025-06-06-2025 & 09-06-2025-12-06-2025. Then gang shifted to 153/0.
181 | 175/2 | DA+0 | 2025-06-08 | 286911 | 37.73 | Completed. | 2025-07-20 | Senahul,Sulen Sarkar & MJR |  |  | Sulen Sarkar join on 02-07-2025.Sulen Sarkar demobilized on 05-07-2025.And MJR join on 08-07-2025.
182 | 174/1 | DB1+0 | 2025-06-06 | 403998 | 54.418 | Completed. | 2025-06-13 | Gouri Shankar
183 | 176/0 | DD60+0 | 2025-06-11 | 604881 | 80.408 | Completed | 2025-07-04 | DK Verma
184 | 275/0 | DD45+0 | 2025-08-06 | 546238 | 72.238 | 2nd section is u/p. |  | Modina India
185 | 273/0 | DB2+0 | 2025-06-28 | 403998 | 54.418 | Ist section is u/p. No work due to heacy waterlogged at loc. |  | MJR |  |  | Due to waterlogged, MJR gang moved to 175/2 on 08-07-2025.
186 | 276/0 | DD60+0 |  |  |  | Materials shifting & headloading is u/p. |  | Kamruddin
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
214

## Striging-VDRA
Stringing Part-I (Vadodara Section)
Sr. No. | Section | Length (M) | PO Length | FS Length | Manual/TSE | Start Date | Status | Cumulative Status | Completion Date | Sub-Contractor name | Manpower | Remarks
1 | 112/0-113/0 | 0.376 | 0.376 | 0.376 | Manual | 2024-08-12 | Completed | Completed. | 2024-08-19 | Muslaahudin
2 | 106/0-106A/0 | 0.411 | 0.411 | 0.411 | Manual | 2025-02-02 | Completed. | Completed. | 2025-02-15 | Muslaahudin
3 | 106A/0-106B/0 | 2.016 | 2.016 | 2.016 | TSE | 2025-01-28 | Completed. | Compeleted. | 2025-02-06 | Muslaahudin
4 | 106B/0- 107/0 | 1.148 | 1.148 | 1.148 | TSE | 2024-11-15 | Completed. | Completed. | 2024-11-24 | Muslaahudin
5 | 107/0-108/0 | 0.559 | 0.559 | 0.559 | Manual | 2024-10-20 | Completed | Completed. | 2024-11-07 | Muslaahudin
6 | 108/0-109/0 | 0.277 | 0.277 | 0.277 | Manual | 2024-10-10 | Completed | Final sag done. | 2024-10-28 | Muslaahudin
7 | 109/0-110/0 | 0.342 | 0.342 | 0.342 | Manual | 2024-08-20 | Completed | Completed. | 2024-10-13 | Muslaahudin
8 | 110/0-111/0 | 0.312 | 0.312 | 0.312 | Manual | 2024-09-11 | Completed | Completed. | 2024-10-06 | Muslaahudin
9 | 111/0-112/0 | 0.342 | 0.342 | 0.342 | Manual | 2024-09-23 | Completed | Completed. | 2024-10-06 | Muslaahudin
10 | 113/0-114/0 | 0.297 | 0.297 | 0.297 | Manual | 2024-09-24 | Completed | Completed. | 2024-10-07 | Gokul Sarkar
11 | 114/0-115/0 | 0.374 | 0.374 | 0.374 | Manual | 2024-12-25 | Completed. | Completed. | 2025-01-02 | Muslaahudin
12 | 115/0-116/0 | 0.226 | 0.226 | 0.226 | Manual | 2024-12-25 | Completed. | Completed. | 2025-01-02 | Muslaahudin
13 | 116/0- 116A/0 | 0.243 | 0.243 | 0.243 | Manual | 2024-09-24 | Completed | Completed. | 2024-10-27 | Gokul Sarkar
14 | 116A/0-116B/0 | 0.675 | 0.675 | 0.675 | Manual | 2024-11-03 | Completed. | Completed. | 2025-01-13 | Muslaahudin
15 | 116B/0-117/0 | 0.436 | 0.436 | 0.436 | Manual | 2024-11-14 | Completed. | Completed. | 2024-12-24 | Zahirul+Yakub
16 | 117/0-118/0 | 0.285 | 0.285 | 0.285 | Manual | 2024-11-09 | Completed. | Completed. | 2024-12-20 | Zahirul
17 | 118/0- 119/0 | 0.294 | 0.294 | 0.294 | Manual | 2024-11-09 | Completed. | Completed. | 2024-12-03 | Zahirul
18 | 119/0-120/0 | 1.373 | 1.373 | 1.373 | TSE | 2024-11-09 | Completed. | Completed. | 2024-12-22 | Gokul Sarkar
19 | 120/0-121/0 | 0.265 | 0.265 | 0.265 | Hotline | 2024-11-02 | Completed. | Completed. | 2025-01-01 | Dharvendra+Yakub
20 | 121/0-122/0 | 0.525 | 0.525 | 0.525 | Manual | 2024-11-01 | Completed | Completed. | 2024-11-19 | Gokul Sarkar
21 | 122/0-123/0 | 0.328 | 0.328 | 0.328 | Manual | 2024-11-19 | Completed. | Completed. | 2024-11-30 | Dharvendra
22 | 123/0-124/0 | 0.843 | 0.843 | 0.843 | Manual | 2024-11-09 | Completed. | Completed. | 2025-01-06 | Zahirul
23 | 124/0-124A/0 | 0.395 | 0.395 | 0.395 | Manual | 2024-12-10 | Completed. | Completed. | 2025-02-19 | Enamul Haque
| 124A/0-124A/1 | 0.253 | 0.253 | 0.253 | Hotline | 2025-02-15 | Completed. | Completed. | 2025-02-19 | Dharvendra
| 124A/1-125/0 | 0.203 | 0.203 | 0.203 | Manual | 2025-02-15 | Completed. | Completed. | 2025-02-19 | Dharvendra
25 | 125/0-125A/0 | 0.401 | 0.401 | 0.401 | Manual |  | Completed. | Completed. | 2025-02-07 | Enamul Haque
26 | 125A/0-126/0 | 0.38 | 0.38 | 0.38 | Manual | 2025-01-16 | Completed. | Completed. | 2025-02-05 | Enamul Haque
27 | 126/0-127/0 | 0.808 | 0.808 | 0.808 | Manual | 2025-01-04 | Completed. | Completed. | 2025-01-24 | Zahirul
28 | 127/0-128/0 | 2.399 | 2.399 | 2.399 | TSE | 2024-11-08 | Completed. | Completed. | 2025-01-19 | Muslaahudin
29 | 128/0-129/0 | 0.253 | 0.253 | 0.253 | Manual | 2025-02-10 | Completed. | Completed. | 2025-02-12 | Alamin Construction
30 | 129/0-129A/0 | 0.305 | 0.305 | 0.305 | Manual | 2025-02-10 | Completed. | Completed. | 2025-02-12 | Alamin Construction
31 | 129A/0-130/0 | 1.182 | 1.182 | 1.182 | TSE | 2024-11-16 | Completed. | Completed. | 2024-11-18 | Rejaul
32 | 130/0-131/0 | 2.041 | 2.041 | 2.041 | TSE | 2025-03-03 | Completed. | Completed. | 2025-03-10 | Muslaahudin
33 | 131/0-132/0 | 0.236 | 0.236 | 0.236 | Hotline | 2025-03-06 | Completed. | Completed. | 2025-03-10 | Dharvendra
34 | 132/0-133/0 | 1.28 | 1.28 | 1.28 | TSE | 2025-01-12 | Completed. | Completed. | 2025-01-24 | Rejaul
35 | 133/0-133A/0 | 2.267 | 2.267 | 2.267 | TSE | 2024-10-17 | Completed. | Completed. | 2024-11-07 | Rejaul | 18
36 | 133A/0-134/0 | 2.037 | 2.037 | 2.037 | TSE | 2024-12-03 | Completed. | Completed. | 2025-01-04 | Rejaul
37 | 134/0-135/0 | 0.235 | 0.235 | 0.235 | Hotline |  | Completed. | Completed. | 2025-03-22
38 | 135/0-135A/0 | 2.998 | 2.998 | 2.998 | TSE | 2025-03-21 | Completed. | Completed. | 2025-05-01 | Rafikul Alam Construction
39 | 135A/0-135A/1 | 0.34 | 0.34 | 0.34 | Manual | 2025-01-20 | Completed. | Completed. | 2025-02-14 | Matirul | 26
40 | 135A/1-135A/2 | 0.452 | 0.452 | 0.452 | Manual | 2025-01-29 | Completed. | Completed. | 2025-02-16 | Matirul+Rejaul
41 | 135A/2-135B/0 | 2.234 | 2.234 | 2.234 | TSE | 2025-02-04 | Completed. | Completed. | 2025-02-14 | Matirul
42 | 135B/0-136/0 | 2.989 | 2.989 | 2.989 | TSE | 2025-01-04 | Completed. | Completed. | 2025-02-14 | Matirul
43 | 136/0-137/0 | 0.426 | 0.426 | 0.426 | Hotline | 2025-03-26 | Completed. | Completed. | 2025-04-01 | Dharvendra | 26
44 | 137/0-137A/0 | 2.827 | 2.827 | 2.827 | TSE | 2025-03-05 | Completed. | Completed. | 2025-04-01 | Rafikul Alam Construction | 18
45 | 137A/0-138/0 | 2.729 | 2.729 | 2.729 | TSE |  | Completed. | Completed. | 2025-03-04 | Alamin Construction | 15
47 | 138/0-139/0 | 1.238 | 1.238 | 1.238 | TSE |  | Completed. | Completed. | 2025-03-04 | Enamul Haque
48 | 139/0-139A/0 | 1.211 | 1.211 | 1.211 | Machine | 2025-03-02 | Completed. | Completed. | 2025-03-09 | SK Zenarul
49 | 139A/0-140/0 | 0.427 | 0.427 | 0.427 | Manual | 2025-03-02 | Completed. | Completed. | 2025-03-13 | SK Zenarul
50 | 140/0-141/0 | 0.249 | 0.249 | 0.249 | Manual | 2025-05-22 | Completed. | Completed. | 2025-05-23 | Rafikul alam & Enamul
51 | 141/0-142/0 | 1.565 | 1.565 | 1.565 | TSE | 2025-04-05 | Completed. | Completed. | 2025-04-13 | Alam Construction
52 | 142/0-143/0 | 0.223 | 0.223 | 0.223 | Manual | 2025-03-18 | Completed. | Completed. | 2025-03-18 | Enamal Haque
53 | 143/0-143A/0 | 0.393 | 0.393 | 0.393 | Manual | 2025-03-08 | Completed. | Completed. | 2025-03-21 | Alamin Construction |  | TSE-1
54 | 143A/0-143A/2 | 0.841 | 0.841 | 0.841 | Manual | 2025-03-19 | Completed. | Completed. | 2025-03-26 | Alam Construction
55 | 143A/2-143A/3 | 0.413 | 0.413 | 0.413 | Manual | 2025-03-23 | Completed. | Completed. | 2025-03-26 | Enamul Haque
56 | 158B/0-159/0 |  |  |  | TSE |  | ROW. |  |  | Gokul Sarkar
57 | 143A/3-144/0 | 1.246 | 1.246 | 1.246 | TSE | 2025-03-18 | Completed. | Completed. | 2025-03-26 | Enamul Haque
58 | 144/0-144A/0 | 2.391 | 2.391 | 2.391 | TSE | 2024-12-05 | Completed. | Completed. | 2024-12-24 | Gokul Sarkar
59 | 144A/0-145/0 | 0.398 | 0.398 | 0.398 | Hotline | 2024-12-25 | Completed. | Completed. | 2025-01-13 | Gokul Sarkar
60 | 145/0-145A/0 | 0.398 | 0.398 | 0.398 | Hotline | 2025-04-19 | Completed. | Completed. | 2025-04-23 | Dharvendra
61 | 145A/0-146/0 | 1.621 | 1.621 | 1.621 | TSE | 2025-04-02 | Completed. | Completed. |  | Enamal Haque |  | TSE-2
62 | 146/0-147/0 | 0.475 | 0.475 | 0.475 | Hotline | 2025-04-12 | Completed. | Completed. | 2025-04-15 | Enamal Haque
63 | 147/0-147/1 | 0.426 | 0.426 | 0.426 | Hotline | 2025-04-11 | Completed. | Completed. | 2025-04-15 | Dharvendra
64 | 147/1-147/2 | 0.33 | 0.33 | 0.33 | Manual | 2025-01-04 | Completed. | Completed. | 2025-01-16 | Gokul Sarkar
65 | 147/2-147A/0 | 2.02 | 2.02 | 2.02 | TSE | 2025-05-16 | Completed. | Completed. | 2025-05-18 | Rafikul Alam Construction |  | Spacering work u/p.
66 | 147A/0-147B/0 | 0.263 | 0.263 | 0.263 | Manual | 2025-04-30 | Completed. | Completed. | 2025-05-01 | Enamal Haque
67 | 147B/0-148/0 | 0.828 | 0.828 | 0.828 | TSE | 2025-04-04 | Completed. | Completed. | 2025-04-15 | Muslaahudin
68 | 148/0-149/0 | 2.994 | 2.994 | 2.994 | TSE | 2025-04-17 | Completed. | Completed. | 2025-04-26 | Muslaahudin
69 | 149/0-150/0 | 0.809 | 0.809 | 0.809 | TSE | 2025-04-22 | Completed. | Completed. | 2025-04-26 | Rafikul Alam Construction
70 | 150/0-150A/0 | 1.633 | 1.633 | 1.633 | TSE | 2025-05-06 | Completed. | Completed. | 2025-05-26 | Alaam Construction
71 | 150A/0-151/0 | 1.252 | 1.252 | 1.252 | TSE | 2025-04-26 | Completed. | Completed. | 2025-05-15 | Alam Construction
72 | 151/0-152/0 | 0.403 | 0.403 | 0.403 | Manual | 2025-04-11 | Completed. | Completed. | 2025-05-15 | Dharvendra
73 | 152/0-152A/0 | 1.78 | 1.78 | 1.78 | TSE | 2025-04-03 | Completed. | Completed. | 2025-04-15 | Alangir
74 | 155/0-156/0 | 2.733 | 2.733 | 2.733 | TSE | 2025-06-06 | Completed. | Completed. | 2025-06-20 | Gokul & Enamul
75 | 156/0-157/0 | 0.24 | 0.24 | 0.24 | Manual | 2025-06-03 | Completed | Completed. | 2025-06-04 | Gokul Sarkar
76 | 167/0-168/0 | 1.95 |  |  | TSE |  | No work. | Insulator hoisting & final chceking u/p.Materials shifting. |  | Enamal Haque
77 | 161/0-162/0 | 0.279 | 0.279 | 0.279 | Hotline | 2025-04-28 | Completed. | Completed. | 2025-05-04 | Gokul Sarkar Dharvendra
78 | 162/0-163/0 | 0.402 | 0.402 | 0.402 | Manual | 2025-04-07 | Completed. | Completed. | 2025-04-26 | Gokul Sarkar
79 | 163/0-164/0 | 2.576 | 2.576 | 2.576 | TSE | 2025-02-24 | Completed. | Completed. | 2025-03-22 | Gokul Sarkar
80 | 164/0-165/0 | 2.981 | 2.981 | 2.981 | TSE | 2025-02-07 | Completed. | Completed. | 2025-02-15 | Gokul Sarkar
81 | 158/0-158A/0 | 1.131 |  |  | TSE |  | No work.

## String-Nav
Stringing Part-II (Navsari Section)
Sr. No. | Section | length | Manual/TSE | Engaged Date | Paying Out |  | Final Sag |  | P/O Completed | F/S Completed | Stringing Status As on Today | Cumulative Status | Sub Contractor name | Manpower | Hindarnce Days | Remarks
[5 empty] | Start Date | End Date | Start Date | End Date
1 | 259/0-260/0 | 0.256 | Hotline | 2025-01-18 | 2025-01-23 | 2025-01-24 | 2025-01-26 | 2025-01-28 | 0.256 | 0.256 | Completed. | Final sag done. | Dharmendra Electrical |  |  | Clipping & jumpering done.
2 | 260/0-261/0 | 0.338 | Manual | 2025-01-17 | 2025-01-23 | 2025-01-25 | 2025-01-26 | 2025-01-28 | 0.338 | 0.338 | Completed. | Final sag done. | Monera | 34 |  | Jumpering & spacering done.
3 | 263/0-264/0 | 0.243 | Hotline | 2025-03-09 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-15 | 0.243 | 0.243 | Completed. | Completed. | Dharmendra Electrical |  |  | Spacer work done.
4 | 264/0-265/0 | 0.44 | Manual |  | 2025-03-16 | 2025-03-18 | 2025-03-19 | 2025-03-22 | 0.44 | 0.44 | Completed. | Completed. | Monera |  |  | Spaer work done.
5 | 257/0-259/0 | 1.809 | TSE | 2025-02-10 | 2025-02-11 | 2025-02-13 | 2025-02-21 | 2025-02-24 | 1.809 | 1.809 | Completed. | Completed. | Monera | 45 |  | Clipping & jumpering done.
6 | 255/0-257/0 | 1.839 | TSE | 2025-02-13 | 2025-02-12 | 2025-02-25 | 2025-03-20 | 2025-03-21 | 1.839 | 1.839 | Completed. | Completed. | Kamruddin | 54 | 4
7 | 262/0-263/0 | 0.685 | Manual | 2025-02-16 | 2025-02-17 | 2025-02-19 | 2025-03-12 | 2025-03-15 | 0.685 | 0.685 | Completed. | Completed. | Monera |  |  | Clipping & spacer work done.
8 | 265/0-266/0 | 0.222 | Hotline |  | 2025-03-16 | 2025-03-18 | 2025-03-19 | 2025-03-21 | 0.222 | 0.222 | Completed. | Completed. | Dharmendra Electrical |  |  | Spcaer work done.
9 | 261/0-262/0 | 0.242 | Hotline | 2025-02-28 | 2025-03-02 | 2025-03-04 | 2025-03-06 | 2025-03-08 | 0.242 | 0.242 | Completed. | Completed. | Dharmendra Electrical | 10 |  | jumpering done.
10 | 254/0-255/0 | 0.3 | Manual |  | 2025-02-26 | 2025-02-28 | 2025-04-07 | 2025-04-08 | 0.3 | 0.3 | Completed. | Completed. | Monera
11 | 272/0-272/5 | 2.053 | TSE | 2025-03-01 | 2025-03-12 | 2025-03-15 | 2025-06-13 | 2025-06-15 | 2.053 | 2.053 | Completed. | Completed. | Kamruddin & Deepak Sarkar |  |  | Deepak sarkar enganged on 12-06-2025 to doing final sag
12 | 266/1-267/0 | 0.835 | Manual |  | 2025-03-22 | 2025-03-24 | 2025-03-25 | 2025-03-28 | 0.835 | 0.835 | Completed. | Completed. | Monera |  |  | Clipping work u/p.
13 | 266/0-266/1 | 0.34 | Hotline |  | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-28 | 0.34 | 0.34 | Completed. | Completed. | Dharmendra Electrical
14 | 267A/0-268/0 | 1.44 | TSE | 2025-03-25 | 2025-03-27 | 2025-03-29 | 2025-04-07 | 2025-04-10 | 1.44 | 1.44 | Completed. | Completed. | Kamruddin
15 | 253/0-254/0 | 0.246 | Hotline |  | 2025-04-04 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 0.246 | 0.246 | Completed. | Completed. | Dharmendra Electrical
16 | 267/0-267A/0 | 0.511 | Manual |  | 2025-04-01 | 2025-04-03 | 2025-04-07 | 2025-04-10 | 0.511 | 0.511 | Completed. | Completed. | Kamruddin Deepak Sarkar
17 | 269/0-270/0 | 1.237 | TSE |  | 2025-04-05 | 2025-04-08 | 2025-04-18 | 2025-04-23 | 1.237 | 1.237 | Completed. | Completed. | Kamruddin & Maidul rahman
18 | 270/0-270A/0 | 2.821 | TSE |  | 2025-04-12 | 2025-04-14 | 2025-04-14 | 2025-04-15 | 2.821 | 2.821 | Completed. | Completed. | Kamruddin & Deepak |  |  | Clipping work u/p.
19 | 268/0-269/0 | 0.292 | Hotline |  | 2025-04-17 | 2025-04-19 | 2025-04-21 | 2025-04-23 | 0.292 | 0.292 | Completed. | Completed. | Dharmendra Electrical
20 | 270A/0-271/0 | 0.268 | Manual |  | 2025-04-12 | 2025-04-15 | 2025-04-21 | 2025-04-25 | 0.268 | 0.268 | Completed. | Completed. | Alamgir
21 | 271/0-272/0 | 2.108 | TSE |  | 2025-04-18 | 2025-04-20 | 2025-04-21 | 2025-04-25 | 2.108 | 2.108 | Completed. | Completed. | Kamruddin & Deepak |  |  | Clipping work u/p.
22 | 252/0-253/0 | 0.317 | Manual |  | 2025-04-17 | 2025-04-19 | 2025-05-04 | 2025-05-06 | 0.317 | 0.317 | Completed. | Completed. | Deepak Sarkar
23 | 251/-252/0 | 0.222 | Hotline |  | 2025-04-29 | 2025-05-01 | 2025-05-02 | 2025-05-04 | 0.222 | 0.222 | Completed. | Completed. | Dharmendra Electrical
24 | 250/0-251/0 | 0.737 | Manual |  | 2025-05-04 | 2025-05-05 | 2025-05-08 | 2025-05-10 | 0.737 | 0.737 | Completed. | Completed. | Deepak Sarkar
25 | 249/0-250/0 | 1.368 | TSE |  | 2025-04-29 | 2025-05-03 | 2025-05-09 | 2025-05-12 | 1.368 | 1.368 | Completed. | Completed. | Kamruddin
26 | 197/0-198/0 | 1.74 | TSE | [7 empty] | No work due to ROW. | 197/1/2/3/4 insulator hoisting done. Final checking u/p. |  |  | 3
27 | 248/0-249/0 | 2.525 | TSE | [7 empty] | No work due to ROW. | 04 towers final checking with insulator hoisting done.Cable bypass work u/p. | Kamruddin & Deepak Sarkar | 69 | 1 | ROW from 20-05-2025
28 | 272/5-272A/0 | 1.202 | TSE | [7 empty] | No work. | Insulator hoisting completed.

## Visual chart Vadodara
Visual Chart | [31 empty] | 2025-08-18
Name of the Line : |  |  |  | 765 kV D/C Ahmedabad - Navsari Transmission Line | [17 empty] | Completed
Name of Project: |  |  |  | Power Grid Khavda-II C Transmission Limited | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | TOWER ERECTION |  |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. | EAR | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 70.4955 |  | 70.4955 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 23 |  | 22 |  | 1
2 | Check Survey |  |  | Kms | 70.4955 |  | 70.4955 |  | 0 |  | TRUE | 66 kV |  |  |  | 13 |  | 12 |  | 1
3 | Soil Investigation |  |  | Nos. | 11 |  | 11 |  | 0 |  | TRUE | 132 kV |  |  |  | 0 |  | 0 |  | 0
4 | Foundation |  |  | Nos. | 186 |  | 185 |  | 1 |  | TRUE | 220 kV |  |  |  | 7 |  | 7 |  | 0
5 | Earthing |  |  | Nos. | 186 |  | 185 |  | 1 |  | TRUE | 400 kV |  |  |  | 3 |  | 3 |  | 0
6 | Erection |  |  | Nos. | 186 |  | 182 |  | 4 |  | 2 | RLY X-ING |  |  |  | 3 |  | 1 |  | 2
7 | Tack Welding |  |  | Nos. | 186 |  | 180 |  | 6 |  | 3 | NH X-ING |  |  |  | 1 |  | 0 |  | 1
8 | Stringing (P/O) |  |  | Kms | 70.4955 |  | 67.443 |  | 3.0525 |  | 4 | Bullet Train |  |  |  | 0 |  | 0 |  | 0
9 | Stringing (F/S) |  |  | Kms | 70.4955 |  | 67.442 |  | 3.0535 |  | 5 | Express-way |  |  |  | 0 |  | 0 |  | 0
10 | OPGW Stringing |  |  | Kms | 70.4955 |  | 61.106 |  | 9.3895 |  | 6 | GAS PIPELINE |  |  |  | 17 |  | 0 |  | 17
[22 empty] | 4.7514 | 4.7514 | 5 | 10 | 9 | 1 | 9 | 10 | 6 | 4 | 5 |  | 2.078 | 2.078 | 0.442
VADODARA DISTRICT FROM 101/0 - 133A/2 = 74 Locations (Length 27.031 Kms)
| 1 | MAHI | 2 | MAHI | 3 | MAHI | 4 | MAHI | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
| 101/0 | RIVER | 102/0 | RIVER | 103/0 | RIVER | 104/0 | RIVER | 105/0 |  | 106/0 |  | 106A/0 |  | 106A/1 |  | 106A/2 |  | 106A/3
|  | 665.001 |  | 685 |  | 680.117 |  | 386.59 |  | 256.448 |  | 411.252 |  | 414 |  | 414 |  | 397 |  | 442 | 4751.408
|  |  | PILE |  | PILE |  | PILE |  | PILE |  | WPS | [7 empty] | WPS
| DD60+35 |  | DD45+35 |  | DD45+35 |  | DD60+35 |  | DD60+35 |  | DD60+9 |  | DC2+0 |  | DA+6 |  | DA-3 |  | DA+3
| 6M RC |  | 11.84M RC |  | 12.51M RC |  | 9.97M RC |  | 6M RC
[8 empty] | 400 kV GETCO |  | 220 kV GETCO | [11 empty] | 3.3301 | 3.3301 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.33 | 3.33 | 3.33
GAS PIPELINE-GAIL
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
| 106A/4 |  | 106B/0 |  | 106B/1 |  | 106B/2 |  | 107/0 |  | 107/1 |  | 108/0 |  | 109/0 |  | 110/0 |  | 111/0
|  | 349.362 |  | 324 |  | 431 |  | 393.243 |  | 279 |  | 279.876 |  | 277.199 |  | 342.42 |  | 312.143 |  | 341.895 | 3330.138
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+9 |  | DB2+9 |  | DA+9 |  | DA+6 |  | DD45+0 |  | DA-3 |  | DD45+0 |  | DB2+0 |  | DB2+0 |  | DC1+0
GAS PIPELINE-GAIL
[16 empty] | GAS PIPELINE-RELIANCE | [5 empty] | 3.2075 | 3.2075 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.207 | 3.207 | 3.207
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
| 112/0 |  | 113/0 |  | 114/0 |  | 115/0 |  | 116/0 |  | 116A/0 |  | 116A/1 |  | 116B/0 |  | 117/0 |  | 118/0
|  | 375.843 |  | 297.046 |  | 373.958 |  | 225.6 |  | 243.413 |  | 360 |  | 315.161 |  | 436.813 |  | 285.244 |  | 294.43 | 3207.508
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  |  |  | WPS |  | WPS |  | WPS
| DD45+0 |  | DD60+0 |  | DD45+0 |  | DC2+25 |  | DD45+18 |  | DC1+0 |  | DA+0 |  | DD45+6 |  | DD60+3 |  | DD45+0
66 kV GETCO (H-FRAME)
[8 empty] | 220 kV GETCO | [9 empty] | GAS PIPELINE-GAIL |  |  |  | 3.7298 | 3.7298 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.729 | 3.729 | 3.729
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
| 119/0 |  | 119/1 |  | 119/2 |  | 119/3 |  | 120/0 |  | 121/0 |  | 122/0 |  | 123/0 |  | 123/1 |  | 124/0
|  | 347 |  | 333 |  | 328 |  | 364.873 |  | 264.71 |  | 525.488 |  | 328.315 |  | 444.001 |  | 399.102 |  | 395.28 | 3729.769
| DD45+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DD60+9 |  | DD60+18 |  | DC1+6 |  | DD60+6 |  | DA+3 |  | DC1+3
[6 empty] | 66 kV GETCO (H-FRAME) |  | 66 kV GETCO |  | 400 kV GETCO |  |  |  | 66 kV GETCO |  | GAS PIPELINE-ONGC
[22 empty] | 3.604 | 3.604 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.603 | 3.603 | 3.603
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
| 124A/0 |  | 124A/1 |  | 125/0 |  | 125A/0 |  | 126/0 |  | 126/1 |  | 127/0 |  | 127/1 |  | 127/2 |  | 127/3
|  | 253 |  | 203.134 |  | 401.324 |  | 380.082 |  | 425 |  | 383.43 |  | 376.001 |  | 389 |  | 379 |  | 414 | 3603.971
| DD60+0 |  | DA+3 |  | DD60+0 |  | DB2+3 |  | DC2+0 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+0 |  | DA+0
|  | 66 kV GETCO |  | GAS PIPELINE-ONGC | [15 empty] | 66 kV GETCO
[22 empty] | 3.7823 | 3.7823 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.782 | 3.782 | 3.782
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
| 127/4 |  | 127/5 |  | 128/0 |  | 129/0 |  | 129A/0 |  | 129A/1 |  | 129A/2 |  | 130/0 |  | 130/1 |  | 130/2
|  | 428 |  | 413.379 |  | 253.252 |  | 305.53 |  | 373 |  | 400 |  | 409.118 |  | 385 |  | 404 |  | 411 | 3782.279
| DA+3 |  | DA+3 |  | DD60+6 |  | DD60+6 |  | DC1+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+3
3-GAS PIPELINE
[6 empty] | RLY X-ING (NOT IN USE) | [15 empty] | 3.4877 | 3.4877 |  | 10 | 10 | 1 | 10 | 10 | 10 | 0 | 10 |  | 3.487 | 3.487 | 3.487
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
| 130/3 |  | 130/4 |  | 131/0 |  | 132/0 |  | 132/1 |  | 132/2 |  | 132/3 |  | 133/0 |  | 133/1 |  | 133/2
|  | 409 |  | 432.128 |  | 236.46 |  | 338 |  | 308 |  | 293 |  | 341.12 |  | 375 |  | 385 |  | 370 | 3487.708
| DA+0 |  | DA+3 |  | DD45+3 |  | DC2+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0
66 kV GETCO
[11 empty] | VADODARA SECTION <<<<<<<<< | BHARUCH DISTRICT FROM 133A/3-153/0 =112 Locations (Length 43.464 Kms) | [9 empty] | 3.8361 | 3.8361 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.836 | 3.836 | 3.836
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
| 133/3 |  | 133/4 |  | 133/5 |  | 133A/0 |  | 133A/1 |  | 133A/2 |  | 133A/3 |  | 133A/4 |  | 134/0 |  | 135/0
|  | 373 |  | 386 |  | 378.721 |  | 377 |  | 389 |  | 430 |  | 350 |  | 491.5 |  | 235.866 |  | 425 | 3836.087
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DC2+25 |  | DC2+25
220 kV GETCO
[22 empty] | 3.7683 | 3.7683 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.768 | 3.768 | 3.768
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
| 135/1 |  | 135/2 |  | 135/3 |  | 135/4 |  | 135/5 |  | 135/6 |  | 135/7 |  | 135A/0 |  | 135A/1 |  | 135A/2
|  | 410 |  | 385 |  | 365 |  | 360 |  | 393 |  | 358 |  | 301.642 |  | 339.827 |  | 451.848 |  | 404 | 3768.317
|  |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS | [5 empty] | WPS |  | WPS
| DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC1+0 |  | DD45+3 |  | DB2+9
[16 empty] | GAS PIPELINE-IOCL |  |  |  | 66 kV GETCO (H-FRAME)
[22 empty] | 3.7404 | 3.7404 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.74 | 3.74 | 3.74
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
| 135A/3 |  | 135A/4 |  | 135A/5 |  | 135A/6 |  | 135A/7 |  | 135B/0 |  | 135B/1 |  | 135B/2 |  | 135B/3 |  | 135B/4
|  | 331 |  | 369 |  | 365 |  | 401 |  | 364.387 |  | 362 |  | 356 |  | 352 |  | 430 |  | 410 | 3740.387
| WPS |  | WPS | [5 empty] | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6
[22 empty] | 3.9486 | 3.9486 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.948 | 3.948 | 3.948
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
| 135B/5 |  | 135B/6 |  | 135B/7 |  | 136/0 |  | 137/0 |  | 137/1 |  | 137/2 |  | 137/3 |  | 137/4 |  | 137/5
|  | 352 |  | 319 |  | 404.986 |  | 425.582 |  | 447 |  | 396 |  | 369 |  | 400 |  | 420 |  | 415 | 3948.568
| WPS |  | WPS |  | WPS | [5 empty] | WPS |  | WPS |  | WPS |  | WPS
| DA+0 |  | DA+0 |  | DA+3 |  | DD45+18 |  | DC2+9 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3
[7 empty] | 3M RC | 220 kV GETCO | 3M RC
[8 empty] | GAS PIPELINE-IHB | [13 empty] | 3.953 | 3.953 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.953 | 3.952 | 3.953
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
| 137/6 |  | 137A/0 |  | 137A/1 |  | 137A/2 |  | 137A/3 |  | 137A/4 |  | 137A/5 |  | 137A/6 |  | 138/0 |  | 138/1
|  | 380.097 |  | 414 |  | 428 |  | 406 |  | 417 |  | 251.002 |  | 374 |  | 439.899 |  | 420.001 |  | 423 | 3952.999
[9 empty] | WPS |  | WPS |  | WPS
| DA+0 |  | DB1+0 |  | DA+6 |  | DA+0 |  | DA+6 |  | DA-3 |  | DA-3 |  | DA+9 |  | DB2+0 |  | DA+6
[22 empty] | 3.8482 | 3.8482 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.848 | 3.848 | 3.848
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
| 138/2 |  | 139/0 |  | 139/1 |  | 139/2 |  | 139A/0 |  | 140/0 |  | 141/0 |  | 141/1 |  | 141/2 |  | 141/3
|  | 395.993 |  | 386.999 |  | 397 |  | 427.031 |  | 427.136 |  | 249 |  | 390 |  | 370 |  | 391 |  | 414.063 | 3848.222
| DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DB2+9 |  | DD60+0 |  | DD60+3 |  | DA+0 |  | DA-3 |  | DA+3
[10 empty] | 66 kV GETCO |  | RLY X-ING |  |  |  | 66 kV GETCO |  |  |  | GAS PIPELINE-GAIL
[12 empty] | NH X-ING | [9 empty] | 3.907 | 3.907 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.906 | 3.906 | 3.906
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
| 142/0 |  | 143/0 |  | 143A/0 |  | 143A/1 |  | 143A/2 |  | 143A/3 |  | 143A/4 |  | 143A/5 |  | 144/0 |  | 144/1
|  | 223.383 |  | 393.222 |  | 432 |  | 409.199 |  | 413.091 |  | 413 |  | 419 |  | 414.062 |  | 402 |  | 388 | 3906.957
[15 empty] | WPS |  | WPS |  | WPS
| DD60+0 |  | DD60+3 |  | DD45+0 |  | DA+6 |  | DD45+0 |  | DD45+3 |  | DA+0 |  | DA+3 |  | DB2+3 |  | DA+0
|  | RLY X-ING |  | GAS PIPELINE-GAIL | [5 empty] | GAS PIPELINE-GSPL
|  | GAS PIPELINE-GAIL | [19 empty] | 4.0175 | 4.0175 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 4.017 | 4.017 | 4.017
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
| 144/2 |  | 144/3 |  | 144/4 |  | 144/5 |  | 144A/0 |  | 145/0 |  | 145A/0 |  | 145A/1 |  | 145A/2 |  | 145A/3
|  | 394 |  | 373 |  | 389 |  | 445 |  | 397.583 |  | 398 |  | 442.999 |  | 383 |  | 417 |  | 377.887 | 4017.469
| WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  |  |  | WPS |  |  |  | WPS
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB1+18 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DA+0
[10 empty] | 220 kV GETCO |  | 220 kV GETCO | [9 empty] | 3.9866 | 3.9866 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.986 | 3.986 | 3.986
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
| 146/0 |  | 147/0 |  | 147/1 |  | 147/2 |  | 147/3 |  | 147/4 |  | 147/5 |  | 147/6 |  | 147A/0 |  | 147B/0
|  | 475.024 |  | 425.519 |  | 330.117 |  | 354.995 |  | 381 |  | 443 |  | 400 |  | 441.898 |  | 263 |  | 472 | 3986.553
[5 empty] | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS |  | WPS
| DC1+9 |  | DC2+9 |  | DC2+0 |  | DC1+0 |  | DA-3 |  | DA+3 |  | DA+6 |  | DA-3 |  | DB1+18 |  | DB1+18
|  | 66 kV GETCO (H-Frame) |  | 66 kV GETCO
[6 empty] | GAS PIPELINE-GAIL | [11 empty] | 220 kV GETCO |  |  |  | 3.7193 | 3.7193 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.719 | 3.719 | 3.719
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
| 147B/1 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 148/4 |  | 148/5 |  | 148/6 |  | 148/7 |  | 149/0
|  | 355.562 |  | 393 |  | 411 |  | 386 |  | 386 |  | 388 |  | 350 |  | 353 |  | 326.719 |  | 370 | 3719.281
WPS
| DA+0 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0
[22 empty] | 4.0916 | 4.0916 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 4.091 | 4.091 | 0.805
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
| 149/1 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150A/0 |  | 150A/1 |  | 150A/2 |  | 151/0 |  | 152/0
|  | 438.762 |  | 367 |  | 475 |  | 362 |  | 429.025 |  | 412 |  | 421 |  | 419.42 |  | 403.348 |  | 364 | 4091.555
[11 empty] | WET |  | WET |  | WET |  |  |  | WET
| DA+0 |  | DD60+9 |  | DA+9 |  | DA+3 |  | DA+6 |  | DC1+0 |  | DA+3 |  | DA+0 |  | DB2+3 |  | DC2+0
|  |  |  | 66 kV GETCO | [7 empty] | GAS PIPELINE-GSPL
[11 empty] | BHARUCH SECTION <<<<<<<<< | [10 empty] | 1.7863 | 1.7863 |  | 6 | 6 | 0 | 6 | 6 | 6 | 0 | 5 |  | 1.415 | 1.415
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186
| 152/1 |  | 152/2 |  | 152/3 |  | 152/4 |  | 152A/0 |  | 153/0
|  | 343 |  | 331 |  | 344 |  | 397.942 |  | 370.343 | [10 empty] | 1786.285
| WET |  | WET |  | WET |  | WET
| DA+0 |  | DA-3 |  | DA-3 |  | DA+0 |  | DB1+0 |  | DD60+25 | [9 empty] | 70.4955
[11 empty] | 1M RC | [8 empty] | TOTAL - >>>>> |  | 70.4955 | 70.4955 | 11 | 186 | 185 | 2 | 185 | 186 | 182 | 4 | 180 | 0 | 67.443 | 67.442 | 61.106
GAS PIPELINE

## Visual chart NAVSARI Revised
Visual Chart
Visual Chart | [30 empty] | 2025-08-18
Name of the Line : |  |  |  | 765 kV D/C Ahmedabad - Navsari Transmission Line (Navsari Portion) | [17 empty] | Completed
Name of Project: |  |  |  | Power Grid Khavda-II C Transmission Limited | [17 empty] | DS (Aprd) | CS (Aprd) | SOIL INVSTGN | FOUNDATION |  |  | EARTH | TOWER ERECTION |  |  | TW | TIG & PUN | STR P/O | STR F/S | OPGW STR
Name of Contractor: |  |  |  | KEC International Limited
[25 empty] | TOTAL | COMP. | BAL. |  | TOTAL | COMP. | BAL.
PROGRESS AT A GLANCE : | [10 empty] | CROSSING PROPOSAL STATUS :
Sl. No. | Activity |  |  | UoM | Total Qty |  | Completed Till Date |  | Balance |  | Sl. No. | Type of Crossing |  |  |  | No. of X-ing |  | Approved |  | Balance
1 | Detailed Survey |  |  | Kms | 106.8547 |  | 106.8547 |  | 0 |  | 1 | Powerline X-ing |  |  |  | 44 |  | 42 |  | 2
2 | Check Survey |  |  | Kms | 106.8547 |  | 106.8547 |  | 0 |  | TRUE | 66 kV |  |  |  | 18 |  | 16 |  | 2
3 | Soil Investigation |  |  | Nos. | 19 |  | 19 |  | 0 |  | TRUE | 132 kV |  |  |  | 2 |  | 2 |  | 0
4 | Foundation |  |  | Nos. | 298 |  | 292 |  | 6 |  | TRUE | 220 kV |  |  |  | 13 |  | 13 |  | 0
5 | Earthing |  |  | Nos. | 298 |  | 292 |  | 6 |  | TRUE | 400 kV |  |  |  | 11 |  | 11 |  | 0
6 | Erection |  |  | Nos. | 298 |  | 191 |  | 107 |  | 2 | RLY X-ING |  |  |  | 3 |  | 3 |  | 0
7 | Tack Welding |  |  | Nos. | 298 |  | 127 |  | 171 |  | 3 | NH X-ING |  |  |  | 3 |  | 0 |  | 3
8 | Stringing (P/O) |  |  | Kms | 106.8547 |  | 30.379 |  | 76.4757 |  | 4 | Bullet Train |  |  |  | 2 |  | 0 |  | 2
9 | Stringing (F/S) |  |  | Kms | 106.8547 |  | 30.379 |  | 76.4757 |  | 5 | Express-way |  |  |  | 5 |  | 0 |  | 5
10 | OPGW Stringing |  |  | Kms | 106.8547 |  | 4.836 |  | 102.0187 |  | 6 | GAS PIPELINE |  |  |  | 6 |  | 0 |  | 6
[22 empty] | 4.3881 | 4.3881 | 2 | 9 | 8 | 1 | 8 | 9 | 7 | 2 | 7 |  | 2.733 | 2.733
BHARUCH DISTRICT FROM 154/0 - 165/3 = 48 Locations (Length 18.616 Kms)
| 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10
| 153/0 |  | 154/0 |  | 154/1 |  | 155/0 |  | 155/1 |  | 155/2 |  | 155/3 |  | 155/4 |  | 155/5 |  | 155/6
|  | 620 |  | 620 |  | 414.995 |  | 400 |  | 408 |  | 428 |  | 408 |  | 384 |  | 337 |  | 368.134 | 4388.129
|  |  | PILE |  | PILE |  | WET |  | PS |  | PS |  | WET | [5 empty] | PS
| DD60+25 |  | DD45+25 |  | DD45+25 |  | DD60+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA-3
| 1M RC |  | 10.96M RC |  | 11.96M RC
[22 empty] | 3.8435 | 3.8435 | 1 | 10 | 10 | 0 | 10 | 10 | 9 | 1 | 9 |  | 0.24 | 0.24
| 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20
| 156/0 |  | 157/0 |  | 157/1 |  | 157/2 |  | 157/3 |  | 158/0 |  | 158/1 |  | 158/2 |  | 158A/0 |  | 158B/0
|  | 240.527 |  | 418 |  | 393 |  | 389 |  | 375.803 |  | 367 |  | 343 |  | 420.567 |  | 481.567 |  | 415 | 3843.464
| WPS | [7 empty] | FS | [7 empty] | WET |  | PS
| DD60+3 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA-3 |  | DD45+6 |  | DD45+18
|  | XPRESSWAY | [13 empty] | GAS PIPELINE |  | 66 kV GETCO
[22 empty] | 3.6216 | 3.6216 | 1 | 10 | 10 | 0 | 10 | 10 | 8 | 2 | 8 |  | 0.68 | 0.68
| 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30
| 158B/1 |  | 158B/2 |  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 159/4 |  | 160/0 |  | 161/0 |  | 162/0
|  | 421 |  | 417.829 |  | 340 |  | 380 |  | 371 |  | 354 |  | 427.196 |  | 229.824 |  | 279.052 |  | 401.678 | 3621.579
| PS |  | PS |  | WET | [5 empty] | WET
| DA+3 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DCT+0 |  | DA+0 |  | DA+0 |  | DD60+18 |  | DD60+25 |  | DD60+25
[8 empty] | GAS PIPELINE | [7 empty] | 400KV EASER POWER |  | BULLET
[22 empty] | 3.703 | 3.703 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.703 | 3.703 | 3.702
| 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40
| 163/0 |  | 163/1 |  | 163/2 |  | 163/3 |  | 163/4 |  | 163/5 |  | 163/6 |  | 164/0 |  | 164/1 |  | 164/2
|  | 385 |  | 383 |  | 384 |  | 367 |  | 375 |  | 339 |  | 342.998 |  | 370 |  | 382 |  | 375 | 3702.998
|  |  | WET |  | WET |  | WET |  | WET |  | FS |  | FS |  | FS |  |  |  | WET
| DC2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0
66KV GETCO
[18 empty] | SURAT DISTRICT From 165/3-248/3 |  |  |  | 4.0054 | 4.0054 |  | 10 | 9 | 1 | 9 | 10 | 9 | 1 | 9 |  | 1.853 | 1.853 | 1.134
[16 empty] | BHARUCH SECTION <<<<<<<<< |  | 169 Locations (Length 59.223 Kms)
| 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50
| 164/3 |  | 164/4 |  | 164/5 |  | 164/6 |  | 164/7 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4
|  | 376 |  | 372 |  | 386 |  | 379 |  | 340.776 |  | 382 |  | 390 |  | 434 |  | 407 |  | 538.65 | 4005.426
|  |  | WFR |  | WFR |  | PS |  | WET |  | PS |  | PS |  | WET |  | WET
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD45+9
4.5M RC
[22 empty] | 3.4188 | 3.4188 | 1 | 10 | 6 | 4 | 6 | 10 | 6 | 4 | 6
| 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60
| 165/5 |  | 166/0 |  | 167/0 |  | 167/1 |  | 167/2 |  | 167/3 |  | 167/4 |  | 168/0 |  | 168/1 |  | 168/2
|  | 423.12 |  | 270.31 |  | 342.5 |  | 229.11 |  | 444 |  | 339 |  | 326.332 |  | 310 |  | 328 |  | 406.389 | 3418.761
[9 empty] | WET |  | WPS |  | WET | [5 empty] | FS
| DD45+9 |  | DD60+6 |  | DD60+6 |  | DD60+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DC1+0 |  | DA-3 |  | DA+0
| 4.5M RC |  |  | RLY X-ING
[22 empty] | 3.3882 | 3.3882 |  | 10 | 10 | 0 | 10 | 10 | 6 | 4
| 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
| 169/0 |  | 171/0 |  | 172/0 |  | 172/1 |  | 172/2 |  | 173/0 |  | 174/0 |  | 174/1 |  | 175/0 |  | 175/1
|  | 433.217 |  | 274.117 |  | 446 |  | 272 |  | 405.018 |  | 231.552 |  | 381 |  | 289.251 |  | 329.999 |  | 326 | 3388.154
| PS |  | PS
| DD45+18 |  | DD60+25 |  | DD60+25 |  | DA+3 |  | DA+6 |  | DD60+25 |  | DD60+18 |  | DB1+0 |  | DD45+0 |  | DA+0
|  | GAS PIPELINE | 3M RC | 400KV GETCO | [7 empty] | 400KV TORRENT | [5 empty] | GAS PIPELINE
|  | 220KV PGCIL | [15 empty] | 66KV GETCO |  |  |  | 3.2591 | 3.2591 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80
| 175/2 |  | 176/0 |  | 177/0 |  | 178/0 |  | 179/0 |  | 180/0 |  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3
|  | 323.209 |  | 231.636 |  | 404.857 |  | 277.839 |  | 264.355 |  | 263.234 |  | 414.999 |  | 326 |  | 377 |  | 376 | 3259.129
| DA+0 |  | DD60+0 |  | DD60+0 |  | DD60+6 |  | DD60+0 |  | DD45+9 |  | DD45+18 |  | DA+0 |  | DA+0 |  | DA+0
|  |  |  | NH X-ING |  |  |  | RLY X-ING NOT IN USE |  | 66KV GETCO | 3M RC | 220KV GETCO
[22 empty] | 3.7405 | 3.7405 | 1 | 10 | 10 | 0 | 10 | 10 | 2 | 8
| 81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90
| 181/4 |  | 182/0 |  | 182A/0 |  | 183/0 |  | 184/0 |  | 184/1 |  | 185/0 |  | 185/1 |  | 186/0 |  | 187/0
|  | 284.072 |  | 246.217 |  | 430.404 |  | 234.635 |  | 468 |  | 412.076 |  | 360 |  | 460.116 |  | 398.978 |  | 446 | 3740.498
| DA+0 |  | DD60+0 |  | DD45+6 |  | DD60+25 |  | DD60+25 |  | DB1+6 |  | DC2+0 |  | DA+9 |  | DD60+35 |  | DD60+25
|  |  |  | 66KV GETCO | 2M RC |  |  | 400KV TORRENT |  |  |  | KIM RIVER | [5 empty] | 400KV TORRENT
[18 empty] | 66KV GETCO |  |  |  | 3.5631 | 3.5631 |  | 10 | 10 | 0 | 10 | 10 | 9 | 1
| 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100
| 187/1 |  | 187/2 |  | 187/3 |  | 188/0 |  | 189/0 |  | 189/1 |  | 190/0 |  | 191/0 |  | 191/1 |  | 191/2
|  | 317 |  | 335 |  | 411.498 |  | 218.419 |  | 370 |  | 458.939 |  | 329.237 |  | 465 |  | 355 |  | 303 | 3563.093
|  |  | FS |  | PS |  | WET |  | WET | [5 empty] | WET |  | WET
| DA+3 |  | DA-3 |  | DA+0 |  | DB1+6 |  | DB2+6 |  | DA+0 |  | DD45+25 |  | DD45+25 |  | DA+0 |  | DA-3
[8 empty] | 220KV GETCO | [5 empty] | 220KV GETCO | [5 empty] | 66KV GETCO
[22 empty] | 3.4393 | 3.4393 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110
| 191/3 |  | 191A/0 |  | 191A/1 |  | 192/0 |  | 193/0 |  | 194/0 |  | 195/0 |  | 195/1 |  | 195/2 |  | 195/3
|  | 353.561 |  | 290 |  | 321.994 |  | 376.036 |  | 241.118 |  | 181.604 |  | 408 |  | 433 |  | 407 |  | 427 | 3439.313
|  |  | WET |  | FS |  |  |  | WET |  |  |  | PS | [5 empty] | PS
| DA-3 |  | DB2+0 |  | DA-3 |  | DC1+0 |  | DD60+6 |  | DD60+6 |  | DC2+0 |  | DA+6 |  | DA+0 |  | DA+6
400KV TORRENT
[22 empty] | 3.6648 | 3.6648 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0
| 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120
| 195/4 |  | 195/5 |  | 195A/0 |  | 195A/1 |  | 195A/2 |  | 195A/3 |  | 196/0 |  | 197/0 |  | 197/1 |  | 197/2
|  | 411 |  | 395 |  | 339 |  | 443 |  | 386 |  | 374.31 |  | 246.469 |  | 385.999 |  | 353 |  | 331 | 3664.778
| WET | [9 empty] | PS |  | WBC
| DA+0 |  | DA+6 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DD60+9 |  | DD60+9 |  | DA+0 |  | DA+0
XPRESSWAY
[22 empty] | 3.9332 | 3.9332 |  | 10 | 10 | 0 | 10 | 10 | 6 | 4
| 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130
| 197/3 |  | 197/4 |  | 198/0 |  | 198/1 |  | 198/2 |  | 199/0 |  | 200/0 |  | 201/0 |  | 201/1 |  | 202/0
|  | 368 |  | 302.151 |  | 374 |  | 366 |  | 409.422 |  | 221.436 |  | 204.39 |  | 532.469 |  | 366.962 |  | 788.368 | 3933.198
| PS |  | WET |  | WET |  | WET
| DA+0 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DD45+18 |  | DB2+18 |  | DC2+18 |  | DD60+9 |  | DD60+55
[12 empty] | 220KV TORRENT |  | 220KV TORRENT |  |  | 2M RC |  | 4.5M RC | TAPI RIVER
[12 empty] | 66KV TORRENT | [9 empty] | 3.6672 | 3.6672 | 1 | 10 | 10 | 0 | 10 | 10 | 5 | 5
| 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
| 203/0 |  | 203/1 |  | 204/0 |  | 205/0 |  | 205/1 |  | 205/2 |  | 206/0 |  | 208/0 |  | 209/0 |  | 209/1
|  | 459.999 |  | 424.69 |  | 198.036 |  | 328 |  | 292 |  | 443.161 |  | 412.08 |  | 409.847 |  | 299.999 |  | 399.426 | 3667.238
| DD60+55 |  | DD60+6 |  | DD60+9 |  | DD60+3 |  | DA-3 |  | DA+3 |  | DD60+25 |  | DD60+25 |  | DC1+0 |  | DA+3
| 4.5M RC |  |  |  |  | 400KV TORRENT | 2M RC | [6 empty] | 220KV TORRENT
[14 empty] | 400KV GETCO | [7 empty] | 3.4246 | 3.4246 | 1 | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150
| 210/0 |  | 211/0 |  | 211/1 |  | 211/2 |  | 211A/0 |  | 211A/1 |  | 211A/2 |  | 212/0 |  | 213/0 |  | 213/1
|  | 223.42 |  | 386.999 |  | 378 |  | 393.196 |  | 359 |  | 354 |  | 311.323 |  | 248.056 |  | 385 |  | 385.596 | 3424.59
| DB2+18 |  | DB1+9 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA+0 |  | DD45+3 |  | DD60+3 |  | DA+0
|  | 220KV TORRENT | [13 empty] | XPRESSWAY
[22 empty] | 3.7323 | 3.7323 |  | 10 | 10 | 0 | 10 | 10 | 1 | 9
| 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160
| 214/0 |  | 214/1 |  | 215/0 |  | 215/1 |  | 216/0 |  | 217/0 |  | 217A/0 |  | 217A/1 |  | 217A/2 |  | 218/0
|  | 250 |  | 463.098 |  | 221 |  | 410.769 |  | 456.491 |  | 347 |  | 426 |  | 400 |  | 347.899 |  | 410 | 3732.257
| DD45+0 |  | DA+6 |  | DB1+6 |  | DA+9 |  | DB2+25 |  | DD45+25 |  | DB1+3 |  | DA+3 |  | DA+0 |  | DD60+0
[6 empty] | 66KV GETCO |  |  | 2M RC | 220KV PGCIL | 2M RC | 220KV GETCO
[22 empty] | 3.2464 | 3.2464 |  | 10 | 10 | 0 | 10 | 10 |  | 10
| 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170
| 218/1 |  | 219/0 |  | 220/0 |  | 220/1 |  | 221/0 |  | 222/0 |  | 222/1 |  | 223/0 |  | 223/1 |  | 223/2
|  | 412.193 |  | 242.397 |  | 324.003 |  | 411.037 |  | 222.183 |  | 388.109 |  | 182.523 |  | 342 |  | 338 |  | 384 | 3246.445
| DA+3 |  | DC2+18 |  | DD45+9 |  | DA+3 |  | DD60+18 |  | DD60+25 |  | DB1+3 |  | DC1+0 |  | DA+0 |  | DA+0
|  |  |  | 220KV GETCO | [5 empty] | 400KV PGCIL |  |  |  | 66KV GETCO
[22 empty] | 3.4818 | 3.4818 | 1 | 10 | 10 | 0 | 10 | 10 |  | 10
| 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180
| 223/3 |  | 224/0 |  | 225/0 |  | 225/1 |  | 226/0 |  | 227/0 |  | 228/0 |  | 229/0 |  | 229/1 |  | 229/2
|  | 333.514 |  | 234.721 |  | 409 |  | 268.584 |  | 417.449 |  | 238.569 |  | 196.002 |  | 549 |  | 463 |  | 372 | 3481.839
| DA+0 |  | DC2+6 |  | DD60+0 |  | DA+6 |  | DC2+0 |  | DB1+6 |  | DD60+25 |  | DD60+18 |  | DB1+6 |  | DA+6
|  |  |  | 66KV GETCO | [9 empty] | 400KV PGCIL
[22 empty] | 3.1085 | 3.1085 |  | 10 | 10 | 0 | 10 | 10 |  | 10
| 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190
| 229/3 |  | 229/4 |  | 229/5 |  | 230/0 |  | 231/0 |  | 232/0 |  | 233/0 |  | 234/0 |  | 235/0 |  | 236/0
|  | 365 |  | 351 |  | 333.363 |  | 226.874 |  | 419.216 |  | 194.761 |  | 305.03 |  | 328.278 |  | 305.141 |  | 279.863 | 3108.526
| DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DD60+6 |  | DD60+3 |  | DD45+0 |  | DD45+0 |  | DC2+3 |  | DB2+0
[8 empty] | RLY X-ING |  |  |  | 66KV GETCO |  |  |  | 66KV GETCO |  |  |  | 66KV GETCO
[22 empty] | 3.2209 | 3.2209 | 1 | 10 | 10 | 0 | 10 | 10 |  | 10
| 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200
| 237/0 |  | 237/1 |  | 237/2 |  | 237/3 |  | 237/4 |  | 237/5 |  | 237/6 |  | 239/0 |  | 240/0 |  | 241/0
|  | 446 |  | 312 |  | 308 |  | 353 |  | 347 |  | 290 |  | 463.512 |  | 247.697 |  | 207.386 |  | 246.351 | 3220.946
| DD45+9 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA+3 |  | DD60+25 |  | DD60+25 |  | DB2+9
| 3M RC | [14 empty] | 400KV PGCIL |  |  |  | XPRESSWAY
[22 empty] | 3.3145 | 3.3145 | 1 | 10 | 10 | 0 | 10 | 10 |  | 10
| 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
| 242/0 |  | 242/1 |  | 242/2 |  | 242/3 |  | 243/0 |  | 244/0 |  | 244/1 |  | 245/0 |  | 245/1 |  | 246/0
|  | 320 |  | 308 |  | 312 |  | 394.895 |  | 249.614 |  | 494 |  | 426.974 |  | 233 |  | 335.543 |  | 240.465 | 3314.491
| DB1+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DB1+9 |  | DC1+9 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DD60+0
[10 empty] | XPRESSWAY | [9 empty] | NH X-ING
[16 empty] | NAVSARI DISTRICT FROM 248/3 - GANTRY | [5 empty] | 3.7896 | 3.7896 |  | 10 | 10 | 0 | 10 | 10 | 6 | 4 | 5
[14 empty] | SURAT SECTION <<<<<<<<< |  | 80 Locations (Length 28.711 Kms)
| 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220
| 247/0 |  | 247/1 |  | 247/2 |  | 247/3 |  | 247/4 |  | 248/0 |  | 248/1 |  | 248/2 |  | 248/3 |  | 248/4
|  | 382.999 |  | 415 |  | 391 |  | 300 |  | 467.57 |  | 486 |  | 265 |  | 271 |  | 380 |  | 431 | 3789.569
| DD60+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA+0 |  | DC2+9 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3
[22 empty] | 3.3357 | 3.3357 | 2 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 2.643 | 2.643
| 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230
| 248/5 |  | 248/6 |  | 249/0 |  | 249/1 |  | 249/2 |  | 249/3 |  | 250/0 |  | 250/1 |  | 251/0 |  | 252/0
|  | 380 |  | 311.881 |  | 303 |  | 357 |  | 367 |  | 340.703 |  | 337 |  | 400.076 |  | 222.09 |  | 316.922 | 3335.672
FS
| DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD60+0 |  | DA-3 |  | DB1+9 |  | DC1+18
220KV GETCO
[22 empty] | 3.3663 | 3.3663 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.366 | 3.366
| 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240
| 253/0 |  | 254/0 |  | 255/0 |  | 255/1 |  | 255/2 |  | 255/3 |  | 255/4 |  | 257/0 |  | 257/1 |  | 257/2
|  | 245.523 |  | 300.466 |  | 315 |  | 428 |  | 408 |  | 412.002 |  | 276.298 |  | 374 |  | 296 |  | 311 | 3366.289
|  |  | FS |  | FS | [7 empty] | WPS |  | WET |  |  |  | WET
| DC1+0 |  | DB2+0 |  | DD60+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA-3
|  | NH X-ING |  |  |  | 66KV GETCO
[22 empty] | 3.256 | 3.256 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.256 | 3.256
| 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250
| 257/3 |  | 257/4 |  | 259/0 |  | 260/0 |  | 261/0 |  | 262/0 |  | 262/1 |  | 263/0 |  | 264/0 |  | 265/0
|  | 358 |  | 470.323 |  | 255.672 |  | 337.664 |  | 242.024 |  | 367 |  | 318.597 |  | 243.259 |  | 440.728 |  | 222.758 | 3256.025
| wet |  | WET |  | PS |  | WBC |  | WET |  | WET |  | WET |  | PS |  | WET |  | WET
| DA+0 |  | DA+0 |  | DD60+18 |  | DD60+18 |  | DC2+18 |  | DD45+9 |  | DA+0 |  | DC2+0 |  | DC1+6 |  | DB2+3
|  |  |  | GAS PIPELINE |  | BULLET |  |  |  | 220KV PGCIL | [5 empty] | 132KV GETCO |  |  |  | 66KV GETCO
[22 empty] | 3.8115 | 3.8115 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.812 | 3.812
| 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260
| 266/0 |  | 266/1 |  | 266/2 |  | 267/0 |  | 267A/0 |  | 267A/1 |  | 267A/2 |  | 267A/3 |  | 268/0 |  | 269/0
|  | 340 |  | 440 |  | 395.057 |  | 511.129 |  | 380 |  | 338 |  | 302 |  | 420.092 |  | 292.226 |  | 393 | 3811.504
[7 empty] | WET |  | WET |  | FS |  | WET |  | WET |  | WET |  | WET
| DB1+0 |  | DB1+6 |  | DA+0 |  | DC1+9 |  | DC2+9 |  | DA+0 |  | DA-3 |  | DA+0 |  | DD60+6 |  | DD60+0
|  | 132KV GETCO |  |  |  |  | 2M RC | GAS PIPELINE | 2M RC | [8 empty] | RLY X-ING
[22 empty] | 3.6642 | 3.6642 | 1 | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.664 | 3.664
| 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270
| 269/1 |  | 269/2 |  | 270/0 |  | 270/1 |  | 270/2 |  | 270/3 |  | 270/4 |  | 270/5 |  | 270/6 |  | 270/7
|  | 421 |  | 422.589 |  | 330 |  | 399 |  | 379 |  | 353 |  | 378 |  | 344 |  | 307 |  | 330.606 | 3664.195
[7 empty] | PS |  | WET
| DA+0 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3
GAS PIPELINE
[22 empty] | 3.5903 | 3.5903 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 3.59 | 3.59
| 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280
| 270A/0 |  | 271/0 |  | 271/1 |  | 271/2 |  | 271/3 |  | 271/4 |  | 271/5 |  | 272/0 |  | 272/1 |  | 272/2
|  | 268.315 |  | 354 |  | 360 |  | 362 |  | 341 |  | 331 |  | 360.025 |  | 478 |  | 359 |  | 377 | 3590.34
|  |  | WET | [9 empty] | WET |  | WET |  | WET |  | WET
| DC2+0 |  | DC1+0 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DC1+6 |  | DA+9 |  | DA-3
[22 empty] | 3.9316 | 3.9316 |  | 10 | 10 | 0 | 10 | 10 | 10 | 0 | 10 |  | 0.839 | 0.839
| 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290
| 272/3 |  | 272/4 |  | 272/5 |  | 272/6 |  | 272/7 |  | 272A/0 |  | 272A/1 |  | 272A/2 |  | 272A/3 |  | 272A/4
|  | 434 |  | 405.02 |  | 390.995 |  | 312 |  | 498.56 |  | 382 |  | 346 |  | 381 |  | 366 |  | 416 | 3931.575
[5 empty] | WET |  |  |  | WET |  | PS |  | WET |  | WET
| DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+9 |  | DB1+18 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+0
[9 empty] | 2M RC | 66KV GETCO | 2M RC
[22 empty] | 2.9447 | 2.9447 | 1 | 9 | 9 | 0 | 9 | 9 | 6 | 3 | 3
| 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | NAVSARI
| 272A/5 |  | 272A/6 |  | 272A/7 |  | 273/0 |  | 273/1 |  | 273/2 |  | 274/0 |  | 275/0 |  | 276/0 |  | GANTRY
|  | 370 |  | 328 |  | 354.532 |  | 390 |  | 395 |  | 368.331 |  | 401.674 |  | 177.173 |  | 159.989 | GANTRY |  | 2944.699
| DA+3 |  | DA-3 |  | DA-3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DC1+0 |  | DD45+0 |  | DD60+0 |  |  |  | 106.8547
[15 empty] | 2M RC | 66KV GETCO | 2M RC |  |  | TOTAL - >>>>> |  | 106.8547 | 106.8547 | 19 | 298 | 292 | 6 | 292 | 298 | 191 | 107 | 127 | 0 | 30.379 | 30.379 | 4.836
R
R
R
R
R
R
R
R
R
NARMADA RIVER
NARMADA RIVER
NARMADA RIVER
GAS PIPELINE

## Crossing Vadodara
765KV D/C HEXA AHEMDABAD - NAVSARI TL (PKG 02)- CROSSING DETAILS
Sl No | AP NO | AP No | Type of Crossings | OWNER | Nos. | Work Portion | Submitted to Client for Review | Revised Submisison due to Route Div. | Confirmation received from Client | Hard Copy Submission Date | Joint Inspection Date | Proposal Currently With
1 | 104 | 105 | 400KV | GETCO | 2 | Vadodara | 2014-02-27 |  |  |  | 2024-05-03 | Approved 30.07.24
2 | 104 | 105 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-14 |  |  |  |  | Online proposal submitted
3 | 105 | 106 | 220KV | GETCO | 1 | Vadodara | 2024-03-22 | 2024-04-10 |  | 2024-04-23 |  | Approved
4 | 108 | 109 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-22 |  |  |  |  | Online proposal submitted
5 | 109 | 110 | Gas Pipe Line | RELIANCE | 1 | Vadodara | 2024-02-22 |  |  |  | 2024-04-05 | Awaiting DD
6 | 115 | 116 | 220KV | GETCO | 1 | Vadodara | 2023-09-28 | 2024-04-10 | 2023-10-16 | 2024-04-23 | 2023-11-22 | Approved
7 | 117 | 118 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-02-22 |  |  |  |  | Online proposal submitted
8 | 118 | 119 | 66KV H-Frame Mobha – Karkhadi TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
9 | 119/2 | 119/3 | 66KV H-Frame Mobha – Karkhadi TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
10 | 119/3 | 120 | 66KV D/C Gavasad to Sterling/Sarod TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
11 | 120 | 121 | 400KV S/C Kasor – Jeepek TL | GETCO | 1 | Vadodara | 2023-09-11 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-29 | Approved
12 | 122 | 123 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
13 | 123 | 123/1 | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Online proposal submitted
14 | 124A/0 | 124A/1 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
15 | 124A/1 | 125 | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Online proposal submitted
16 | 127/3 | 127/4 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
17 | 128 | 129 | RLY Crossing (Not in Use) | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-05-13 | Submitted to Railway - Vadodara
18 | 129 | 129A | Gas Pipe Line | ONGC | 1 | Vadodara | 2024-02-26 |  |  |  |  | Proposal submitted.
| 129 | 129A | Gas Pipe Line | GSPL | 1 | Vadodara | [5 empty] | Proposal submitted,Demand received.
| 129 | 129A | Gas Pipe Line | GAIL | 1 | Vadodara | [5 empty] | Online Proposal Submitted.
19 | 131 | 132 | 66KV Line | GETCO | 1 | Vadodara | 2023-09-09 | 2023-09-28 | 2023-10-16 | 2023-10-23 | 2023-11-22 | Approved
20 | 134 | 135 | 220KV M/C Gavasad - Amod TL | GETCO | 1 | Vadodara | 2023-07-06 |  | 2023-07-12 | 2023-07-16 | 2023-09-12 | Approved
21 | 135A/0 | 135A/1 | Gas Pipe Line | IOCL | 1 | Vadodara | 2024-02-14 | 2024-02-20 |  |  | 2024-04-13 | Demand & aggrement awaiting
22 | 135A/2 | 135A/3 | 66KV H FRAME SARBHAN-AMOD | GETCO | 1 | Vadodara | 2024-03-31 |  |  |  | 2024-05-04 | Approved 01-08-2024
23 | 136 | 137 | 220KVD/C MBH - SUV TL | GETCO | 1 | Vadodara | 2023-07-06 |  | 2023-10-16 | 2023-10-23 | 19.04.2024 | Approved
24 | 136 | 137 | Gas Pipe Line | IHB | 1 | Vadodara | 2024-01-23 | 2024-03-27 |  |  | 2024-04-03 | Demand received, E office note 844813 initiate.
25 | 139A/0 | 140 | 66KV U/C TOWER LINE | GETCO | 1 | Vadodara | 2023-09-09 | 2024-04-10 | 2023-10-16 | 2023-10-23 | 2024-05-08 | Approved
26 | 140 | 141 | NH 228 | NH | 1 | Vadodara | 2023-09-09 |  | 2023-09-12 | 2023-12-10 |  | Submitted in Bharuch
27 | 140 | 141 | RLY Line | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-05-08 | Awaited for DD
28 | 141/1 | 141/2 | 66KV H Frame Kurchan-Wagra | GETCO | 1 | Vadodara | 2024-04-05 | 2024-04-10 |  |  | 2024-05-02 | Pole no. 40 of existing line has to be shift away from corridor of 67 mtr.
| 141/3 | 142/0 | Gas Pipe Line | GAIL | 1 | Vadodara | [5 empty] | Online proposal submitted.
29 | 142 | 143 | RLY Line | RLY | 1 | Vadodara | 2023-09-01 |  |  | 2023-12-10 | 2024-01-24 | Approved
30 | 142 | 143 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 |  |  |  | Online proposal submitted
31 | 143 | 143A | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 |  |  |  | Online proposal submitted
32 | 143A/2 | 143A/3 | Gas Pipe Line | GSPL | 1 | Vadodara | [5 empty] | Reapplied in PM gatishakti portal
33 | 144A | 145 | 220KV D/C Haldarva - Wagra TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 | 2023-11-02 | Approved
34 | 145 | 145A | 220KV Haldarva- IPCL (Dahej) TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 | 2023-11-02 | Approved
35 | 146 | 147 | 66KV H FRAME NANDEWAR - WAGRA TL | GETCO | 1 | Vadodara | 2023-09-09 | 2024-01-03 | 2023-10-16 | 2024-01-03 |  | Approved
36 | 147 | 147/1 | 66KV TOWER TAPPING FROM NANDEWAR - WAGRA TO VILAYAT S/S | GETCO | 1 | Vadodara | 2023-09-09 | 2024-01-03 | 2023-09-12 | 2024-01-03 |  | Approved
37 | 147/1 | 147/2 | Gas Pipe Line | GAIL | 1 | Vadodara | 2024-01-23 | 2024-01-23 | 2024-03-18 |  |  | Online proposal submitted.
38 | 147A | 147B | 220KV D/C Wagra - TSS (Tham) TL | GETCO | 1 | Vadodara | 2023-08-17 |  | 2023-08-20 | 2023-09-08 |  | Approved 02-08-2024
39 | 150 | 150/1 | 66KV | GETCO | 1 | Vadodara | 2023-09-28 |  | 2023-10-16 | 2023-10-23 | 12.04.2024 | Approved 03-08-2024
40 | 150A/0 | 151A/1 | Gas Pipe Line | GSPL | 1 | Vadodara | 2024-02-14 | 2024-02-20 |  |  |  | Reapplied in PM gatishakti portal
44

## Crossing Navsari
765KV D/C HEXA AHEMDABAD - NAVSARI TL PKG 02 (NAVSARI PORTION) - CROSSING STATUS
Sl No | AP NO | Towe Type | AP No | Tower Type | Type of Crossings | LINE OWNER | Nos. | Work Portion | Status | Submitted to Client for Review | Submission to Line Owner Date | Joint Inspection Date | Proposal Currently With | Remarks
1 | 156/0 | DD60+3 | 157/0 | DD60+6 | DEL - MUM Xpressway (SAKKARPUR - ANKLESHWAR) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | 2024-02-23 | NHAI Kamrej
2 | 158/2 | DA-3 | 158A/0 | DD45+6 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
3 | 158A/0 | DD45+6 | 158B/0 | DD45+18 | 66KV Hansot - Urban TL | GETCO | 1 | Navsari | Submitted |  | 2024-06-04 |  |  | Approved on 01-08-2024
4 | 159/1 | DA+0 | 159/2 | DA+0 | Gas Pipeline (Avanton) |  |  | Navsari | Proposal Not Required |  |  | Done
5 | 160/0 | DD60+18 | 161/0 | DD60+25 | 400KV HZR - GDR | EASER POWER | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-15 | 2023-09-30 | Eassar | Approved on 09-09-2024
6 | 161/0 | DD60+25 | 162/0 | DD60+25 | Bullet Train |  | 1 | Navsari | Submitted | 2024-02-19 | 2024-02-22 | 2024-04-30 |  | Approved
7 | 163/5 | DA+0 | 163/6 | DA+0 | 66KV Panoli - Hansot TL | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-14 | Vadodara GETCO | Approved on 01-03-2024
8 | 166/0 | DD60+6 | 167/0 | DD60+0 | RLY Line Haturan - Panoli | Western Railway Vadodara | 1 | Navsari | Submitted | 2023-09-08 | 2023-10-05 | 2024-01-19 | Vadodara GETCO (DRM office) | Approved
9 | 169/0 | DD45+9 | 171/0 | DD60+25 | Gas Pipeline |  | 1 | Navsari | Submitted |  | 2024-03-08 | Done
10 | 169/0 | DD45+9 | 171/0 | DD60+25 | 220KV D/C KWS - HAL | PGCIL | 1 | Navsari | Submitted | 2023-09-02 | 2023-09-04 |  | PGCIL DASTAN | Approved on 20.06.2024
11 | 171/0 | DD60+25 | 172/0 | DD60+25 | 400KV Kosamba - Chorania | GETCO | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-09 | 2023-10-03 | Vadodara GETCO | Approved on 01-03-2024
12 | 173/0 | DD60+18 | 174/0 | DD60+18 | 400KV DGEN - Navsari | TORRENT POWER | 1 | Navsari | Submitted | 2023-09-07 | 2023-09-09 | 2023-10-09 | TORRENT Surat | Approved
13 | 175/0 | DD45+0 | 175/1 | DA+0 | 66KV Dinoda - Kharch | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-10-03 | Vadodara GETCO | Resubmit to GETCO
14 | 175/0 | DD45+0 | 175/1 | DA+0 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
15 | 176/0 | DD60+0 | 177/0 | DD60+0 | NH48 (Delhi - Mumbai) - Kosamba | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-11-28 | NHAI Kamrej | Approved
16 | 178/0 | DD60+6 | 179/0 | DD60+0 | RLY Crossing (Not in Use) | Western Railway Vadodara | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-17 |  | Available with PGCIL | No need approval
17 | 179/0 | DD60+0 | 180/0 | DD45+9 | 66KV D/C Palod - Kosamba TL | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-10-13 | Vadodara GETCO | Approved on 22-04-2024
18 | 180/0 | DD45+9 | 181/0 | DD45+18 | 220KV Jiseg - Kosamba | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2023-10-13 | Vadodara GETCO | Approved on 22-04-2024
19 | 182/0 | DD60+0 | 182A/0 | DD45+6 | 66KV D/C Kim - FTP TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved
20 | 183/0 | DD60+25 | 184/0 | DD60+25 | 400KV D/C DGEN - Navsari | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | TORRENT Surat | Approved
21 | 184/1 | DB1+6 | 185/0 | DC2+0 | KIM RIVER |  | 1 | Navsari | Proposal Not Required |  | 2023-12-11
22 | 186/0 | DD60+25 | 187/0 | DD60+18 | 400KV SUG - PIR | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 |  | TORRENT Surat | Approved
23 | 186/0 | DD60+25 | 187/0 | DD60+18 | 66KV Lilo - Simodra | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2023-12-11 | 2024-02-10 | GETCO BHARUCH | Approved on 01-08-2024
24 | 188/0 | DB1+6 | 189/0 | DB2+6 | 220KV D/C Kim - Kosamba TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved on 01.-08-2024
25 | 190/0 | DD45+25 | 191/0 | DD45+25 | 220KV D/C Kosamba - Vav TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Approved on 01-08-2024
26 | 191/2 | DA-3 | 191/3 | DA-3 | 66KV Kim - Masoli TL | GETCO | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | GETCO BHARUCH | Awaiting NOC
27 | 193/0 | DD60+6 | 194/0 | DD60+6 | 400KV S/C GHT - TPL | TORRENT POWER | 1 | Navsari | Submitted | 2023-11-03 | 2023-12-11 | 2024-01-17 | TORRENT Surat | Approved
28 | 196/0 | DD60+9 | 197/0 | DD60+9 | DEL - MUM Xpressway - Roswad | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-11-18 | NHAI Kamrej
29 | 199/0 | DD45+18 | 200/0 | DB2+18 | 66KV Karanj - Areth | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-31 | 2024-02-10 | GETCO BHARUCH | Approved
30 | 199/0 | DD45+18 | 200/0 | DB2+18 | 220KV Sugen - Bhatar | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT Surat | Approved on 14-05-2024
31 | 200/0 | DB2+18 | 201/0 | DC1+18 | 220KV Sugen - Puna | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT Surat | Approved on 14-05-2024
32 | 202/0 |  | 203/0 |  | TAPI RIVER |  | 1 | Navsari | Proposal Not Required
33 | 204/0 | DD60+6 | 205/0 | DD60+3 | 400KV TPL - VAP | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved
34 | 206/0 | DD60+25 | 208/0 | DD60+25 | 220KV Sugen - Puna | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved on 14-05-2024
35 | 206/0 | DD60+25 | 208/0 | DD60+25 | 400KV Kosamba - Vav | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-06 | GETCO NAVSARI | Approved
36 | 210/0 | DB1+18 | 211/0 | DB2+6 | 220KV Sugen - Bhatar | TORRENT POWER | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-01 |  | TORRENT surat | Approved on 14-05-2024
37 | 212/0 | DD60+0 | 213/0 | DD60+0 | DEL - MUM Xpressway (Jat Barthana Kamrej) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
38 | 215/0 | DB1+6 | 215/1 | DA+9 | 66KV Vav - Shmpura Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2024-02-03 | 2023-10-11 | Vadodara GETCO | Approved on 12-02-2024
39 | 216/0 | DB2+25 | 217/0 | DD45+25 | 220KV D/C Kap - Vav | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2024-02-03 |  | PGCIL DASTAN | Approved
40 | 217/0 | DD45+25 | 217A/0 | DB1+3 | 220KV Vav - Mota | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-10-04 | Vadodara GETCO | Approved
41 | 219/0 | DC2+18 | 220/0 | DD45+9 | 220KV D/C Mota - Koshamba | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 01-04-2024
42 | 221/0 | DD60+25 | 222/0 | DD60+25 | 400KV GND - NAV | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 |  | PGCIL DASTAN | Approved on 20.06.2024
43 | 222/1 | DB1+3 | 223/0 | DC1+0 | 66KV Parab - Shampura | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 09-02-2024
44 | 224/0 | DC2+6 | 225/0 | DD60+0 | 66KV D/C Mota - Kejriwal TL | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-29 | Vadodara GETCO | Approved on 01-04-2024
45 | 228/0 | DD60+25 | 229/0 | DD60+18 | 400KV D/C KPP - Nav | PGCIL | 1 | Navsari | Submitted | 2023-09-08 | 2023-09-18 |  | PGCIL DASTAN | Approved on 20.06.2024
46 | 230/0 | DD60+0 | 231/0 | DD60+6 | RLY LINE | Western Railway Mumbai | 1 | Navsari | Submitted | 2023-10-13 | 2023-10-13 |  | Mumbai | Approved 05.08.2024
47 | 232/0 | DD60+3 | 233/0 | DD45+0 | 66KV Mota - Bardoli Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-16 | Bharuch GETCO | Approved on 01-04-2024
48 | 234/0 | DC2+3 | 235/0 | DD45+0 | 66KV VAV -Jolwa-Palsana | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-07 | GETCO NAVSARI | Approved
49 | 236/0 | DB2+0 | 237/0 | DD45+9 | 66KV Mota - Sharvon | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-06 | GETCO NAVSARI | Approved on 01-08-2024
50 | 239/0 | DD60+25 | 240/0 | DD60+25 | 400KV Navsari - Magarwada | PGCIL | 1 | Navsari | Submitted | 2024-01-29 | 2024-02-02 |  | PGCIL DASTAN | Approved on 20.06.2024
51 | 241/0 | DD60+9 | 242/0 | DD60+0 | DEL - MUM Xpressway (Ena - Palsana) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
52 | 243/0 | DD60+9 | 244/0 | DD60+9 | DEL - MUM Xpressway (Ghaluda) | NHAI | 1 | Navsari | Submitted | 2024-01-30 | 2024-02-03 | Done | NHAI Kamrej
53 | 246/0 | DD60+0 | 247/0 | DD60+0 | NH Crossing | NHAI | 1 | Navsari | Route Divertion |  |  | 2024-09-05 |  | Succeding span Not Available
54 | 251/0 | DB1+9 | 252/0 | DC1+18 | 220KV Nav - Popda | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 01-04-2024
55 | 253/0 | DD60+0 | 254/0 | DD60+0 | NH48 (Delhi - Mumbai) - Vesma | NHAI | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-05 | 2024-09-03 | NHAI Kamrej
56 | 255/0 | DD60+3 | 255/1 | DA+6 | 66KV Tavdi - Vesma | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 12-02-2024
57 | 257/4 | DA+0 | 259/0 | DD60+18 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done
58 | 259/0 | DD60+18 | 260/0 | DD60+18 | Bullet Train |  | 1 | Navsari | Submitted | 2024-02-19 | 2024-02-22 | 2024-04-29 |  | Approved
59 | 261/0 | DC2+9 | 262/0 | DD45+9 | 220KV D/C Nav - Nav | PGCIL | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 |  | PGCIL DASTAN | Approved on 20.06.2024
60 | 263/0 | DC2+0 | 264/0 | DC1+6 | 132KV S/C NAV - Popda TL | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved on 12-02-2024
61 | 265/0 | DB2+3 | 266/0 | DB1+0 | 66KV Nav - Eklera | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved on 12-02-2024
62 | 266/0 | DB1+0 | 266/1 | DB1+6 | 132KV Nav - Bhestan | GETCO | 1 | Navsari | Submitted | 2023-09-18 | 2023-09-19 | 2023-09-27 | Vadodara GETCO | Approved
63 | 267/0 | DB2+0 | 267A/0 | DC2+9 | Gas Pipeline |  | 1 | Navsari | Submitted |  |  | Done |  | Route Divertion not confirmed from PGCIL
64 | 268/0 | DD60+6 | 269/0 | DD60+0 | RLY LINE | Western Railway Mumbai | 1 | Navsari | Submitted | 2023-10-13 | 2023-10-13 |  | Mumbai | Approved 05.08.2024
65 | 270/0 | DD45+0 | 270/1 | DA+0 | Gas Pipeline |  | 1 | Navsari | Submitted |  | 2024-03-08 | Done
66 | 272/7 | DB1+0 | 272A/0 | DA+3 | 66KV Talangpur - Mangrol Line | GETCO | 1 | Navsari | Submitted | 2023-10-03 | 2023-10-06 | 2023-10-11 | Vadodara GETCO | Approved on 29-01-2024
67 | 275/0 | DD60+0 | 276/0 | DD60+3 | 66KV Mangrol. - Umbrath | GETCO | 1 | Navsari | Submitted | 2024-01-29 | 2024-01-30 | 2024-02-05 | GETCO NAVSARI | Approved on 01-08-2024
66

## Subcontractor
Navsari Portion Sub Contractor Details
Sr. No. | Activity | Sub-Contractor Name | Manpower | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Manpower | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Gang Mobilization Date
1 | Foundation | M/s Rudra Associate | 14 |  |  | 1 | Erection | M/s Sukhridwin | 35 |  |  | 1 | Stringing
2 | Foundation | M/s Khodiyar Krupra |  |  |  | 2 | Erection | M/s Ghanshyam | 42 |  |  | 2
3 | Foundation | M/s Tes Transco-01 | 26 | 2024-09-10 |  | 3 | Erection | M/s Ram Jivan-01 |  |  |  | 3
4 | Foundation | M/s Tes Transco-02 | 15 | 2024-09-15 |  | 4 | Erection | M/s Ram Jivan-02 |  |  |  | 4
5 | Foundation | M/s Tes Transco-03 | 15 | 2024-10-03 |  | 5 | Erection | M/s Hari Narayan |  |  |  | 5
6 | Foundation | M/s Maa Bhawani | 25 | 2024-09-30 |  | 6 | Erection | M/s Chahnur Bibi |  |  |  | 6
7 | Foundation | M/s Rajesh Singh | 16 | 2024-09-30 |  | 7 | Erection | M/s Thanu Mahto | 32 | 2024-09-28 |  | 7
8 | Foundation | M/s Jyoti Constr. | 15 | 2024-10-01 |  | 8 | Erection | M/s Senaul-01 | 22 | 2024-10-02 |  | 8
9 | Foundation | M/s Kastabhanja | 15 | 2024-11-22 |  | 9 | Erection | M/s Rahul Kumar | 23 | 2024-10-23 |  | 9
10 | Foundation | M/s Jitu Bhai | 18 |  |  | 10 | Erection | M/s Modina India | 29 | 2024-11-08 |  | 10
11 | [5 empty] | 11 | Erection | M/s Modina India | 29 | 2024-11-08 |  | 11
12 | [5 empty] | 12 | Erection | M/s Mithun | 23 | 2024-11-17 |  | 12
13 | [5 empty] | 13 | Erection | M/s Barkat Ali | 29 | 2024-11-15 |  | 13
14 | [5 empty] | 14 | Erection | M/s Jwala | 23 | 2024-11-18 |  | 14
[6 empty] | 15 | Erection | M/s Rahim | 12 | 2024-11-26
[6 empty] | 16 | Erection | M/s MJR | 30 | 2024-11-27
[6 empty] | 17 | Erection | M/s Senahul-02 | 12 | 2024-11-28
[6 empty] | 18 | [5 empty] | 15
Vadodara Portion Sub Contractor Details
Sr. No. | Activity | Sub-Contractor Name |  | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name |  | Gang Mobilization Date | Gang Demobilization date | Sr. No. | Activity | Sub-Contractor Name | Gang Mobilization Date
1 | Foundation | M/s Alamin Constr.-01 |  |  |  | 1 | Erection | M/s Ajay Kumar | 22 |  |  | 1 | Stringing | M/s Musladudin
2 | Foundation | M/s Alamin Constr.-02 |  |  |  | 2 | Erection | M/s Gouri Shankar | 30 |  |  | 2 | Stringing | M/s Gokul Sarkar
3 | Foundation | M/s hajji saheb |  |  |  | 3 | Erection | M/s Rahul Kumar |  |  |  | 3
4 | Foundation | M/s Jyoti Construction |  |  |  | 4 | Erection | M/s Dhaneshwar mahto | 28 |  |  | 4
5 | Foundation | M/s Jeet Infra |  |  |  | 5 | Erection | M/s Barkad Alli |  |  |  | 5
6 | Foundation | M/s Prince construction |  |  |  | 6 | Erection | M/s Rejaul |  |  |  | 6
7 | Foundation | M/s BK Traders | 14 | 146/0 |  | 7 | Erection | M/s Senaul Haque | 18 |  |  | 7
8 |  | Hmanshi Constr.-01 | 13 | 148/0 |  | 8 | Erection | M/s SK Samiul |  |  |  | 8
9 |  | Himanshi-02 | 12 | 148/1 |  | 9 |  | M/s Vijay Sah | 22 | 147/3 |  | 9
10 | [5 empty] | 10 |  | Mukesh Kumar | 28 |  |  | 10
11 | [5 empty] | 11 | [5 empty] | 11
12 | [5 empty] | 12 | [5 empty] | 12
13 | [5 empty] | 13 | [5 empty] | 13
14 | [5 empty] | 14 | [5 empty] | 14
15 | [5 empty] | 15 | [5 empty] | 15

## Balance Erection
Erection Balance Location Status of ANTL Project
Sr. No. | Loc. No. | TOT | Village | Tehsil | District | Tower Weight | Start Date | Status | Comp Date | Sub-Contractor | Remarks
1 | 101/0 | DD60+35 | GAJANA | BORSAD | ANAND | 172.151 |  | WIP |  | Dhaneshwar | 2nd section completed.
2 | 102/0 | DD45+35 | DABKA | PADRA | VADODARA | 156.901 |  | Clear |  |  | Waterlogged
3 | 103/0 | DD45+35 | DABKA | PADRA | VADODARA | 156.901 |  | Pending |  |  | Foundation u/p.
4 | 105/0 | DD60+35 | DABKA | PADRA | VADODARA | 172.151 | 2025-06-24 | WIP |  | Rupesh Kumar | 4rth section is u/p.
5 | 154/0 | DD45+25 | Kukurwada | Bharuch | Bharuch | 122.8082 |  | Pending |  |  | Foundation u/p.
6 | 154/1 | DD45+25 | Kukurwada | Bharuch | Bharuch | 122.8082 |  | Clear |  |  | Waterlogged
7 | 157/3 | DA+0 | Pungam | Ankleshwar | Bharuch | 37.73 |  | ROW |  |  | 2nd section is u/p.
8 | 159/2 | DCT+0 | Boidra | Ankleshwar | Bharuch | 64.2538 |  | Clear |  |  | Approach road issues.
9 | 160/0 | DD60+18 | Umarwada | Ankleshwar | Bharuch | 129.341 |  | Clear |  |  | Waterlogged
10 | 165/4 | DD45+9 | Haturan | Mangrol | Surat | 89.1461 |  | Pending |  |  | Foundation Pending
11 | 165/5 | DD45+9 | Haturan | Mangrol | Surat | 89.1461 |  | Pending |  |  | Foundation Pending
12 | 166/0 | DD60+6 | Haturan | Mangrol | Surat | 94.4077 |  | Pending |  |  | Foundation Pending
13 | 167/0 | DD60+6 | Haturan | Mangrol | Surat | 94.4077 |  | Pending |  |  | Foundation Pending
14 | 167/1 | DD60+0 | Haturan | Mangrol | Surat | 80.408 |  | Pending |  |  | Foundation Pending
15 | 172/1 | DA+3 | Mahuvej | Mangrol | Surat | 39.4589 |  | Pending |  | MJR | Dismantling work u/p.
16 | 173/0 | DD60+25 | Mahuvej | Mangrol | Surat | 141.874 |  | ROW
17 | 174/0 | DD60+18 | Mahuvej | Mangrol | Surat | 129.341 |  | ROW |  |  | Ist section is u/p.
18 | 175/1 | DA+0 | Kosamba | Mangrol | Surat | 37.73 |  | ROW
19 | 182A/0 | DD45+6 | Valecha | Mangrol | Surat | 85.2338 |  | ROW
20 | 183/0 | DD60+25 | Valecha | Mangrol | Surat | 141.874 |  | ROW
21 | 184/0 | DD60+25 | Valecha | Mangrol | Surat | 141.874 |  | ROW
22 | 184/1 | DB1+6 | Valecha | Mangrol | Surat | 63.509 |  | ROW
23 | 185/0 | DC2+0 | Valecha | Mangrol | Surat | 64.2538 |  | ROW
24 | 185/1 | DA+9 | Valecha | Mangrol | Surat | 46.6235 |  | ROW
25 | 186/0 | DD60+35 | Valecha | Mangrol | Surat | 172.151 |  | ROW
26 | 187/0 | DD60+25 | Panetha | Mangrol | Surat | 141.874 |  | ROW
27 | 191/0 | DD45+25 | Varethi | Mandvi | Surat | 122.8082 | 2025-06-02 | WIP |  | Modina India | Top section is u/p.
28 | 200/0 | DB2+18 | Ghala | Kamrej | Surat | 82.2388 |  | ROW
29 | 201/0 | DC2+18 | Ghala | Kamrej | Surat | 97.9336 |  | ROW
30 | 201/1 | DD60+9 | Ghala | Kamrej | Surat | 98.8356 |  | ROW
31 | 202/0 | DD60+55 | Ghala | Kamrej | Surat | 226.737 |  | ROW
32 | 203/0 | DD60+55 | Jior | Kamrej | Surat | 226.737 |  | ROW
33 | 203/1 | DD60+6 | Jior | Kamrej | Surat | 94.4077 |  | ROW
34 | 206/0 | DD60+25 | Dhatav | Kamrej | Surat | 141.874 |  | ROW |  |  | 3rd section.
35 | 208/0 | DD60+25 | Netrang | Kamrej | Surat | 141.874 |  | ROW
36 | 209/1 | DA+3 | Netrang | Kamrej | Surat | 39.459 |  | ROW
37 | 210/0 | DB2+18 | Netrang | Kamrej | Surat | 82.239 |  | ROW |  |  | 3rd section .
38 | 211/0 | DB1+9 | Netrang | Kamrej | Surat | 65.757 |  | ROW
39 | 211/2 | DA+0 | Netrang | Kamrej | Surat | 37.73 |  | ROW
40 | 211A/0 | DB2+0 | Dharutha | Kamrej | Surat | 54.418 |  | ROW
41 | 211A/1 | DA-3 | Dharutha | Kamrej | Surat | 36.045 |  | ROW
42 | 211A/2 | DA+0 | Jat Barthana | Kamrej | Surat | 37.73 |  | ROW
43 | 212/0 | DD45+3 | Asta | Kamrej | Surat | 75.452 |  | ROW
44 | 213/0 | DD60+3 | Asta | Kamrej | Surat | 84.2993 |  | ROW
45 | 213/1 | DA+0 | Asta | Kamrej | Surat | 37.73 |  | ROW
46 | 214/0 | DD45+0 | Asta | Kamrej | Surat | 72.238 |  | ROW
47 | 214/1 | DA+6 | Asta | Kamrej | Surat | 44.728 |  | ROW
48 | 215/0 | DB1+6 | Asta | Kamrej | Surat | 63.509 |  | ROW
49 | 215/1 | DA+9 | Asta | Kamrej | Surat | 46.623 |  | ROW
50 | 216/0 | DB2+25 | Segva | Kamrej | Surat | 91.083 |  | ROW
51 | 217/0 | DD45+25 | Segva | Kamrej | Surat | 122.808 |  | ROW
52 | 217A/0 | DB1+3 | Segva | Kamrej | Surat | 56.863 |  | ROW
53 | 217A/2 | DA+0 | Segva | Kamrej | Surat | 37.73 |  | ROW |  |  | Ist section done.
54 | 218/0 | DD60+0 | Segva | Kamrej | Surat | 80.408 |  | ROW
55 | 218/1 | DA+3 | Segva | Kamrej | Surat | 39.459 |  | ROW
56 | 219/0 | DC2+18 | Pali | Kamrej | Surat | 97.934 |  | ROW
57 | 220/0 | DD45+9 | Pali | Kamrej | Surat | 89.1461 |  | ROW
58 | 220/1 | DA+3 | Pali | Kamrej | Surat | 39.459 |  | ROW
59 | 221/0 | DD60+18 | Pali | Kamrej | Surat | 129.341 |  | ROW
60 | 222/0 | DD60+25 | Mota | Bardoli | Surat | 141.874 |  | ROW
61 | 222/1 | DB1+3 | Mota | Bardoli | Surat | 56.863 |  | ROW
62 | 223/0 | DC1+0 | Mota | Bardoli | Surat | 64.254 |  | ROW
63 | 223/1 | DA+0 | Mota | Bardoli | Surat | 37.73 |  | ROW
64 | 223/2 | DA+0 | Mota | Bardoli | Surat | 37.73 |  | ROW
65 | 223/3 | DA+0 | Mota | Bardoli | Surat | 37.73 |  | ROW
66 | 224/0 | DC2+6 | Mota | Bardoli | Surat | 74.632 |  | ROW
67 | 225/0 | DD60+0 | Mota | Bardoli | Surat | 80.408 |  | ROW
68 | 225/1 | DA+6 | Mota | Bardoli | Surat | 44.728 |  | ROW
69 | 226/0 | DC2+0 | Mota | Bardoli | Surat | 64.254 |  | ROW
70 | 227/0 | DB1+6 | Mota | Bardoli | Surat | 63.509 |  | ROW
71 | 228/0 | DD60+25 | Mota | Bardoli | Surat | 141.874 |  | ROW
72 | 229/0 | DD60+18 | Mota | Bardoli | Surat | 129.341 |  | ROW
73 | 229/1 | DB1+6 | Umrakh | Bardoli | Surat | 63.509 |  | ROW
74 | 229/2 | DA+6 | Umrakh | Bardoli | Surat | 44.728 |  | ROW
75 | 229/3 | DA+0 | Umrakh | Bardoli | Surat | 37.73 |  | ROW
76 | 229/4 | DA+0 | Umrakh | Bardoli | Surat | 37.73 |  | ROW
77 | 229/5 | DA+0 | Gangpore | Palsana | Surat | 37.73 |  | ROW
78 | 230/0 | DD60+0 | Gangpore | Palsana | Surat | 80.408 |  | ROW
79 | 231/0 | DD60+6 | Gangpore | Palsana | Surat | 94.4077 |  | ROW
80 | 232/0 | DD60+3 | Gangpore | Palsana | Surat | 84.2993 |  | ROW
81 | 233/0 | DD45+0 | Jetpor | Palsana | Surat | 72.238 |  | ROW
82 | 234/0 | DD45+0 | Barasadi | Palsana | Surat | 72.238 |  | ROW
83 | 235/0 | DC2+3 | Barasadi | Palsana | Surat | 66.268 |  | ROW
84 | 236/0 | DB2+0 | Barasadi | Palsana | Surat | 54.418 |  | ROW
85 | 237/0 | DD45+9 | Barasadi | Palsana | Surat | 89.1461 |  | ROW
86 | 237/1 | DA+0 | Barasadi | Palsana | Surat | 37.73 |  | ROW
87 | 237/2 | DA-3 | Barasadi | Palsana | Surat | 36.045 |  | ROW
88 | 237/3 | DA-3 | Barasadi | Palsana | Surat | 36.045 |  | ROW
89 | 237/4 | DA+0 | Barasadi | Palsana | Surat | 37.73 |  | ROW
90 | 237/5 | DA-3 | Dhamdod | Palsana | Surat | 36.045 |  | ROW
91 | 237/6 | DA+3 | Dhamdod | Palsana | Surat | 39.459 |  | ROW
92 | 239/0 | DD60+25 | Dhamdod | Palsana | Surat | 141.874 |  | ROW
93 | 240/0 | DD60+25 | Ena | Palsana | Surat | 141.874 |  | ROW
94 | 241/0 | DB2+9 | Ena | Palsana | Surat | 65.757 |  | ROW
95 | 242/0 | DB1+0 | Ena | Palsana | Surat | 54.418 |  | ROW
96 | 242/1 | DA-3 | Ena | Palsana | Surat | 36.045 |  | ROW
97 | 242/2 | DA-3 | Ena | Palsana | Surat | 36.045 |  | ROW
98 | 242/3 | DA-3 | Ena | Palsana | Surat | 36.045 |  | ROW
99 | 243/0 | DB1+9 | Ena | Palsana | Surat | 65.757 |  | ROW
100 | 244/0 | DC1+9 | Ena | Palsana | Surat | 77.718 |  | ROW
101 | 244/1 | DB1+9 | Ghaluda | Palsana | Surat | 65.757 |  | ROW
102 | 245/0 | DD45+0 | Bhutpor | Palsana | Surat | 72.238 |  | ROW
103 | 245/1 | DA+0 | Bhutpor | Palsana | Surat | 37.73 |  | ROW
104 | 246/0 | DD60+0 | Kanav | Palsana | Surat | 80.408 |  | ROW
105 | 247/0 | DD60+0 | Kanav | Palsana | Surat | 80.408 |  | ROW
106 | 247/2 | DA+3 | Kanav | Palsana | Surat | 39.459 |  | ROW
107 | 247/3 | DA-3 | Kanav | Palsana | Surat | 36.045 |  | ROW |  |  | Cage section .
108 | 247/4 | DA+0 | Kanav | Palsana | Surat | 37.73 |  | ROW |  |  | Body completed.
109 | 273/0 | DB2+0 | Nimlai | Jalalpore | Navsari | 54.418 |  | Clear |  |  | Ist section, Waterlogged.
110 | 275/0 | DD45+0 | Umbhrat | Jalalpore | Navsari | 72.238 | 2025-08-08 | WIP |  | Modina India | Ist section is u/p.
111 | 276/0 | DD60+0 | Umbhrat | Jalalpore | Navsari | 80.408 |  | WIP |  | Kamruddin | Materials shifting is u/p.
[5 empty] | Total | 8929.1956
Summary
|  |  | ROW | 93
|  |  | Clear | 5
|  |  | WIP | 5
|  |  | Pending | 8
|  |  | Total | 111

## Balance ready stringing
Balance Stringing Ready Status of ANTL project
Sr. No. | Section | Length(Km.) | Total Length | Method | Crossing | Readyness | Status
1 | 152A/0-153/0 | 0.37 | 2.758(8) | Manual | NA | Ready | Clear
2 | 174/1-175/0 | 0.289 |  | Manual | NA | Ready | ROW
3 | 177/0-178/0 | 0.405 |  | Manual | NA | Ready | ROW
4 | 178/0-179/0 | 0.278 |  | Manual | NA | Ready | ROW
5 | 191A/0-192/0 | 0.612 |  | Manual | NA | Ready | ROW
6 | 192/0-193/0 | 0.376 |  | Manual | NA | Ready | ROW
7 | 194/0-195/0 | 0.182 |  | Manual | NA | Ready | ROW
8 | 196/0-197/0 | 0.246 |  | Manual | Xpressway | Ready | ROW
9 | 158A/0-158B/0 | 0.482 | 2.605(9) | Hotline | 66kV | Ready | ROW
10 | 169/0-171/0 | 0.433 |  | Hotline | 220kV | Ready | ROW
11 | 171/0-172/0 | 0.274 |  | Hotline | 400kV | Ready | ROW
12 | 176/0-177/0 | 0.232 |  | Hotline | NH | Ready | ROW
13 | 179/0-180/0 | 0.264 |  | Hotline | 66kV | Ready | ROW
14 | 180/0-181/0 | 0.263 |  | Hotline | 220kV | Ready | ROW
15 | 188/0-189/0 | 0.218 |  | Hotline | 220kV | Ready | ROW
16 | 193/0-194/0 | 0.241 |  | Hotline | 400kV | Ready | ROW
17 | 204/0-205/0 | 0.198 |  | Hotline | 400kV | Ready | ROW
18 | 158/0-158A/0 | 1.131 | 18.625(12) | Machine | NA | Ready | ROW
19 | 158B/0-159/0 | 1.254 |  | Machine | NA | Ready | ROW
20 | 167/0-168/0 | 1.95 |  | Machine | NA | Ready | ROW
21 | 168/0-169/0 | 1.044 |  | Machine | NA | Ready | ROW
22 | 181/0-182/0 | 1.778 |  | Machine | NA | Ready | ROW
23 | 189/0-190/0 | 0.829 |  | Machine | NA | Ready | ROW
24 | 195/0-195A/0 | 2.481 |  | Machine | NA | Ready | ROW
25 | 195A/0-196/0 | 1.542 |  | Machine | NA | Ready | ROW
26 | 197/0-198/0 | 1.74 |  | Machine | NA | Ready | ROW |  | ROW
27 | 198/0-199/0 | 1.149 |  | Machine | NA | Ready | ROW |  | Clear
28 | 248/0-249/0 | 2.525 |  | Machine | NA | Ready | ROW
29 | 272/5-272A/0 | 1.202 |  | Machine | 66kV | Ready | Clear | Waterlogged
Total | 28 | 23.988
Summary
|  | ROW | 27 | 22.416
|  | Clear | 2 | 1.572
|  | Total | 29 | 23.988

## OPGW
OPGW stringing Status for TA-325 Project
Sr. No. | Drum No. | [5 empty] | Section Length | OPGW length | Completed Length | Status
1 | AHMD-NVSA-1 | 101/0 | DD60+35 | - | 106A/3 | DA+3 | 4309.408 | 4581
2 | AHMD-NVSA-2 | 106A/3 | DA+3 | - | 112/0 | DD45+0 | 3772.138 | 3995 | 3772.138 | Completed.
3 | AHMD-NVSA-3 | 112/0 | DD45+0 | - | 119/3 | DA+0 | 4215.508 | 4442 | 4215.508 | Completed.
4 | AHMD-NVSA-4 | 119/3 | DA+0 | - | 124A/1 | DA+3 | 2974.769 | 3187 | 2974.769 | Completed.
5 | AHMD-NVSA-5 | 124A/1 | DA+3 | - | 129/0 | DD60+6 | 4445.602 | 4684 | 4445.602 | Completed.
6 | AHMD-NVSA-6 | 129/0 | DD60+6 | - | 132/3 | DA+0 | 4704.236 | 4944 | 4704.236 | Completed.
7 | AHMD-NVSA-7 | 132/3 | DA+0 | - | 133A/0 | DB1+0 | 2608.841 | 2811 | 2608.841 | Completed.
8 | AHMD-NVSA-8 | 133A/0 | DB1+0 | - | 135/5 | DA+0 | 4218.366 | 4445 | 4218.366 | Completed.
9 | AHMD-NVSA-9 | 135/5 | DA+0 | - | 135B/2 | DA+0 | 4796.704 | 5033 | 4796.704 | Completed.
10 | AHMD-NVSA-10 | 135B/2 | DA+0 | - | 137/5 | DA+3 | 4725.568 | 4964 | 4725.568 | Completed.
11 | AHMD-NVSA-11 | 137/5 | DA+3 | - | 138/2 | DA+0 | 4367.999 | 4601 | 4367.999 | Completed.
12 | AHMD-NVSA-12 | 138/2 | DA+0 | - | 141/3 | DA+3 | 3434.159 | 3653 | 3434.159 | Completed.
13 | AHMD-NVSA-13 | 141/3 | DA+3 | - | 144/3 | DA+0 | 4715.02 | 4953 | 4715.02 | Completed.
14 | AHMD-NVSA-14 | 144/3 | DA+0 | - | 145A/2 | DA+3 | 2828.582 | 3038 | 2828.582 | Completed.
15 | AHMD-NVSA-15 | 145A/2 | DA+3 | - | 147A/0 | DB1+18 | 4046.44 | 4291 | 4046.44 | Completed.
16 | AHMD-NVSA-16 | 147A/0 | DB1+18 | - | 150/1 | DA+9 | 5260.043 | 5529 | 5260.043 | Completed.
17 | AHMD-NVSA-17 | 150/1 | DA+9 | - | 152A/0 | DB1+0 | 4701.735 | 4944
18 | AHMD-NVSA-18 | 152A/0 | DB1+0 | - | 155/3 | DA+3 | 3261.338 | 3476
19 | AHMD-NVSA-19 | 155/3 | DA+3 | - | 158A/0 | DD45+6 | 4444.031 | 4683
20 | AHMD-NVSA-20 | 158A/0 | DD45+6 | - | 163/0 | DC2+0 | 4518.146 | 4753
21 | AHMD-NVSA-21 | 163/0 | DC2+0 | - | 164/6 | DA+0 | 4836.998 | 5072 | 4836.998 | Completed.
22 | AHMD-NVSA-22 | 164/6 | DA+0 | - | 167/4 | DA+0 | 4614.529 | 4848
23 | AHMD-NVSA-23 | 167/4 | DA+0 | - | 175/2 | DA+0 | 4758.875 | 4995
24 | AHMD-NVSA-24 | 175/2 | DA+0 | - | 182/0 | DD60+0 | 3543.201 | 3759
25 | AHMD-NVSA-25 | 182/0 | DD60+0 | - | 187/1 | DA+3 | 3456.426 | 3674
26 | AHMD-NVSA-26 | 187/1 | DA+3 | - | 192/0 | DC1+0 | 4528.648 | 4762
27 | AHMD-NVSA-27 | 192/0 | DC1+0 | - | 195A/3 | DA+0 | 4447.758 | 4677
28 | AHMD-NVSA-28 | 195A/3 | DA+0 | - | 199/0 | DD45+18 | 3510.351 | 3744
29 | AHMD-NVSA-29 | 199/0 | DD45+18 | - | 206/0 | DD60+25 | 4259.511 | 4549
30 | AHMD-NVSA-30 | 206/0 | DD60+25 | - | 213/1 | DA+0 | 4560.346 | 4817
31 | AHMD-NVSA-31 | 213/1 | DA+0 | - | 220/0 | DD45+9 | 4772.443 | 5016
32 | AHMD-NVSA-32 | 220/0 | DD45+9 | - | 227/0 | DB1+6 | 4255.123 | 4496
33 | AHMD-NVSA-33 | 227/0 | DB1+6 | - | 237/0 | DD45+9 | 4927.097 | 5178
34 | AHMD-NVSA-34 | 237/0 | DD45+9 | - | 243/0 | DB1+9 | 4555.841 | 4804
35 | AHMD-NVSA-35 | 243/0 | DB1+9 | - | 245/0 | DD45+0 | 1170.588 | 1359
36 | AHMD-NVSA-36 | 245/0 | DD45+0 | - | 248/5 | DA+0 | 4598.577 | 4830
37 | AHMD-NVSA-37 | 248/5 | DA+0 | - | 255/2 | DA+0 | 4624.661 | 4858
38 | AHMD-NVSA-38 | 152A/0 | DB1+0 | - | 264/0 | DC1+6 | 4669.839 | 4909
39 | AHMD-NVSA-39 | 264/0 | DC1+6 | - | 269/2 | DA+6 | 4895.99 | 5144
40 | AHMD-NVSA-40 | 269/2 | DA+6 | - | 270/3 | DA-3 | 1530.589 | 1721
41 | AHMD-NVSA-41 | 270/3 | DA-3 | - | 272/1 | DA+9 | 4566.946 | 4806
42 | AHMD-NVSA-42 | 272/1 | DA+9 | - | 272A/5 | DA+3 | 4667.575 | 4914
43 | AHMD-NVSA-43 | 272A/5 | DA+3 | - | GANTRY | S/S GANTRY | 2944.699 | 3130
Total Drum Length in Meter | [6 empty] | 177045.244 | 187069 | 65950.973
Total Drum Length in Km | [6 empty] | 177.0452 | 187.069 | 65.951

## 18-8-25
KEC International Limited - 765 KV ANTL | [11 empty] | Date:- | 2025-08-18
Locations-wise Status for 756 KV D/C ANTL | [17 empty] | Issue
Sl.No | Location No | Type of Tower | Type of Classification | Trial Pit date. | Start Date | Date of Completion | WIP | Comp. | Status as on Date-03.07.2025 | Plan for Tomorrow | Gang | Man Power | Name of the Gang | Remarks | KEC person | Safety Person | Fitter
1 | 103/0 | DD45+35 | PILE |  | 2025-05-23 |  | 1 |  | No work due to high tide and critical approach road | No work due to high tide and critical approach road | Gang 2 | 11 | Chaudhary Construction |  | Sandeep Kumar |  | 4
[7 empty] | 1 | 0 |  | Total Manpower in Foundation |  | 11
Foundation |  | Type of Tower | Volume |  | Start Date | Date of Completion | WIP | Comp. | Foundation STATUS | Plan for Tomorrow | Gang | Man power | Remark | Remarks
1 | 166/0 | DD60+6 |  |  | 2025-08-17 |  | 1 |  | Pit C excavation is u/p. |  | Kastabhanja | 14
[7 empty] | 1 | 0 |  | Total Manpower in Foundation |  | 14
Erection |  | Type of Tower | Tower Weight, MT |  | Start Date | Date of Completion | WIP | Comp. | ERECTION STATUS | Plan for Tomorrow | Gang | Man power | Remark | Remarks | KEC person | Safety Person | Fitter
1 | 104/0 | DD60+35 | 172.1513 |  | 2025-06-01 |  |  | 1 | Completed. Tower tightening u/p. | Gang shift to 101/0. | Gang 1 | 39 | Dhaneswar Mahto |  | Sushanta | Vivek Kumar | 10
2 | 105/0 | DD60+35 | 172.1513 |  | 2025-06-24 |  | 1 |  | Middle section is u/p. |  | Gang 2 | 26 | Rupesh Kumar |  | Kalicharan | Deepak | 6
3 | 191/0 | DD45+25 | 122.8048 |  | 2025-06-12 |  | 1 |  | Cross arm assemble is u/p. |  | Gang 3 | 30 | Modina India |  | Mohan Kumar |  | 6
4 | 275/0 | DD45+0 | 72.238 |  | 2025-08-08 |  | 1 |  | 2nd section is u/p. |  | Gang 4 | 23 | Modina India
5 | 276/0 | DD60+0 |  |  |  |  | 1 |  | Materials shifting & headloading is u/p. |  | Gang-5 | 32 | Kamruddin |  | Khemlal | Pintu Banjara | 6
|  |  | 539.3454 |  |  |  | 4 | 1 |  | Total Manpower in Erection |  | 150
Comp. in August |  | FDN |  | ERC |  | STR in Kms
Balance FND |  | 7 | Bal. ERE |  | 111 | Bal. STR | 79.527
FND COMP- |  | 477 | ERE Comp | 373 | 223 | STR Comp | 97.823 |  |  | Total Manpower. |  | 193
Final Checking (Punch Point) |  | Type of Tower | Tower Weight, MT |  | Start Date | Date of Completion | WIP | Comp. | Final Checking Status | Plan for Tomorrow | Gang | Man power | Remark | Remarks | KEC person | Safety Person | Fitter
1 | 123/0 | DD60+6 | 94.2545 |  | 2025-08-04 |  | 1 |  | Stringing final checking and rectification completed |  | Gang 1 | 14 | Nand kishor |  | Tapan
2 | 124/0 | DC1+3 | 66.503 |  | 2025-08-04 |  | 1 |  | Stringing final checking and rectification completed | [7 empty] | 11
3 | 124A/0 | DD60+0 | 80.2549 |  | 2025-08-04 |  | 1 |  | Stringing final checking and rectification U/P | Stringing rectification
4 | 125/0 | DD60+0 | 80.2549 | [6 empty] | Stringing rectification
5 | 125A/0 | DB2+3 | 56.8632 | [6 empty] | Stringing rectification
6 | 121/0 | DD60+18 | 129.1879 |  | 2025-08-04 |  | 1 |  | Stringing final checking and rectification completed
7 | 129/0 | DD60+6 | 94.2545 |  | 2025-08-04 |  | 1 |  | Tower tightening and shortage fixing U/P | Tower tightening and shortage fixing | Gang 2 | 7 | Balgobind |  | Atul Kumar |  | 5
8 | 128/0 | DD60+6 | 94.2545 |  | 2025-07-29 |  | 1 |  | Tower tightening, Punching and shortage fixing U/P | Tower tightening and shortage fixing | Gang 2 | 7 | Balgobind |  | Atul Kumar |  | 5
9 | 127/5 | DA+3 | 39.453 |  | 2025-07-30 |  | 1 |  | Tower tightening, Punching and shortage fixing U/P | Tower tightening and shortage fixing | Gang 2 | 6 | Balgobind |  | Atul Kumar |  | 4
10 | 161/0 | DD60+25 | 141.7209 |  | 2025-07-30 |  | 1 |  | Tower tightening and shortage fixing U/P | Tower tightening and shortage fixing | Gang 3 | 9 | Taluram |  | Sanjit |  | 6
11 | 163/1 | DA+0 | 37.73 |  | 2025-08-02 |  | 1 |  | Punching completed and gang shifted to 172/1 |  | Gang 4 | 10 | Abhishek Kumar |  | Sanjit |  | 6
[7 empty] | 9 |  |  | Total manpower in Final checking |  | 43 |  |  |  |  | 37
OPGW |  | length Kms | Paying out |  | Final Sag |  | P/O U/P | F/S U/P | OPGW STATUS. | Plan for Tomorrow | Gang | Man power | Name of the Gang | Remarks
|  |  | Start Date | End Date | Start Date | End Date | [8 empty] | KEC person | Safety Person | Fitter
Sl.No | Section | [5 empty] | P/0 Comp. | F/S Comp.
[6 empty] | Completed | 64.542 | 64.542
[6 empty] | Balance | 25.389 | 25.389 |  | Total Manpower in OPGW |  | 0
OPGW Splicing
Sl.No | Location | Type of Tower | Completion Date |  |  |  | Completed |  | Splicing status | Plan for Tomorrow | Gang | Man Power | Name of the Gang | Remarks | KEC person | Safety Person | Fitter
[6 empty] | Completed | 9
[6 empty] | Balance | 13 |  |  | Total Manpower in OPGW |  | 0
* Above given programmes are tentative and subject to readiness of location and duly verification by the KEC site engineer.