## ES Delay Summary
ES Delay Summary
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Lag Days | Median Lag Days | % Lag >60 Days | Negative Lag Excluded | Fallback Rows | Fallback %
OVERALL | All Projects | All | 631 | 321 | 50.9 | 88 | 77 | 64.3 | 10 | 527 | 83.5
OVERALL | All Projects | TSE | 186 | 76 | 40.9 | 93.4 | 77 | 70.7 | 1 | 181 | 97.3
OVERALL | All Projects | Others | 220 | 37 | 16.8 | 60.1 | 58 | 48.6 | 2 | 218 | 99.1
PROJECT | TA 325 | All | 228 | 0 | 0 |  |  |  | 0 | 228 | 100
PROJECT | TA 413 | All | 27 | 27 | 100 | 91.1 | 76 | 78.3 | 4 | 27 | 100
PROJECT | TA 414 | All | 11 | 11 | 100 | 53.4 | 52 | 45.5 | 0 | 6 | 54.5
PROJECT | TA 416 | All | 67 | 67 | 100 | 83 | 84 | 66.2 | 2 | 4 | 6
PROJECT | TA 418 | All | 21 | 21 | 100 | 118.9 | 91 | 76.2 | 0 | 18 | 85.7
PROJECT | TA 421 | All | 52 | 52 | 100 | 80.7 | 51 | 49 | 1 | 42 | 80.8
PROJECT | TA 504 | All | 10 | 10 | 100 | 74 | 61.5 | 50 | 0 | 1 | 10
PROJECT | TA 505 | All | 10 | 9 | 90 | 132.3 | 149 | 88.9 | 0 | 10 | 100
PROJECT | TB 401 - PKG-G | All | 68 | 0 | 0 |  |  |  | 0 | 68 | 100
PROJECT | TB 501 - 132kV | All | 30 | 30 | 100 | 42.6 | 41 | 33.3 | 0 | 30 | 100
PROJECT | TB 501 - 220kV | All | 88 | 75 | 85.2 | 99.2 | 86 | 70.8 | 3 | 88 | 100
PROJECT | TB 507 - MAIN | All | 19 | 19 | 100 | 121.9 | 129 | 100 | 0 | 5 | 26.3
SERIES | 4xx | All | 335 | 254 | 75.8 | 83.8 | 71.5 | 60.7 | 10 | 251 | 74.9
SERIES | 5xx | All | 68 | 67 | 98.5 | 103.1 | 97 | 77.6 | 0 | 48 | 70.6
SERIES | Other | All | 228 | 0 | 0 |  |  |  | 0 | 228 | 100
CLIENT_TYPE | TA | All | 566 | 272 | 48.1 | 85.2 | 71.5 | 61.1 | 10 | 473 | 83.6
CLIENT_TYPE | TB | All | 65 | 49 | 75.4 | 102.8 | 97 | 81.6 | 0 | 54 | 83.1

## ES Delay Coverage
ES Delay Coverage
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Fallback Rows | Fallback % | LOCATION_NOS Rows | HYBRID_PARTIAL_FALLBACK Rows | ALPHABETIC_FALLBACK Rows | Parse EMPTY Rows | Parse OK Rows | Parse PARTIAL_PARSE Rows | Parse SHORTHAND_NO_ANCHOR Rows | Negative Lag Excluded | Average Lag Days | Median Lag Days
OVERALL | All Projects | All | 631 | 321 | 50.9 | 527 | 83.5 | 104 | 67 | 460 | 460 | 130 | 31 | 10 | 10 | 88 | 77
OVERALL | All Projects | TSE | 186 | 76 | 40.9 | 181 | 97.3 | 5 | 4 | 177 | 177 | 9 | 0 | 0 | 1 | 93.4 | 77
OVERALL | All Projects | Others | 220 | 37 | 16.8 | 218 | 99.1 | 2 | 6 | 212 | 212 | 7 | 1 | 0 | 2 | 60.1 | 58
PROJECT | TA 325 | All | 228 | 0 | 0 | 228 | 100 | 0 | 0 | 228 | 228 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 325 | TSE | 69 | 0 | 0 | 69 | 100 | 0 | 0 | 69 | 69 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 325 | Others | 159 | 0 | 0 | 159 | 100 | 0 | 0 | 159 | 159 | 0 | 0 | 0 | 0
PROJECT | TA 413 | All | 27 | 27 | 100 | 27 | 100 | 0 | 0 | 27 | 27 | 0 | 0 | 0 | 4 | 91.1 | 76
PROJECT_METHOD | TA 413 | TSE | 17 | 17 | 100 | 17 | 100 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 0 | 96.4 | 105
PROJECT_METHOD | TA 413 | Others | 2 | 2 | 100 | 2 | 100 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 71 | 71
PROJECT | TA 414 | All | 11 | 11 | 100 | 6 | 54.5 | 5 | 0 | 6 | 6 | 5 | 0 | 0 | 0 | 53.4 | 52
PROJECT_METHOD | TA 414 | TSE | 7 | 7 | 100 | 5 | 71.4 | 2 | 0 | 5 | 5 | 2 | 0 | 0 | 0 | 69.1 | 65
PROJECT_METHOD | TA 414 | Others | 1 | 1 | 100 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 14 | 14
PROJECT | TA 416 | All | 67 | 67 | 100 | 4 | 6 | 63 | 4 | 0 | 0 | 65 | 1 | 1 | 2 | 83 | 84
PROJECT_METHOD | TA 416 | TSE | 1 | 1 | 100 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 62 | 62
PROJECT_METHOD | TA 416 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 418 | All | 21 | 21 | 100 | 18 | 85.7 | 3 | 18 | 0 | 0 | 21 | 0 | 0 | 0 | 118.9 | 91
PROJECT_METHOD | TA 418 | TSE | 3 | 3 | 100 | 3 | 100 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 195.3 | 152
PROJECT_METHOD | TA 418 | Others | 5 | 5 | 100 | 5 | 100 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 83.6 | 70
PROJECT | TA 421 | All | 52 | 52 | 100 | 42 | 80.8 | 10 | 42 | 0 | 0 | 13 | 30 | 9 | 1 | 80.7 | 51
PROJECT_METHOD | TA 421 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 421 | Others | 1 | 1 | 100 | 1 | 100 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 3
PROJECT | TA 504 | All | 10 | 10 | 100 | 1 | 10 | 9 | 1 | 0 | 0 | 10 | 0 | 0 | 0 | 74 | 61.5
PROJECT_METHOD | TA 504 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 504 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TA 505 | All | 10 | 9 | 90 | 10 | 100 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 132.3 | 149
PROJECT_METHOD | TA 505 | TSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT_METHOD | TA 505 | Others | 1 | 1 | 100 | 1 | 100 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 65 | 65
PROJECT | TB 401 - PKG-G | All | 68 | 0 | 0 | 68 | 100 | 0 | 0 | 68 | 68 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 401 - PKG-G | TSE | 32 | 0 | 0 | 32 | 100 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0
PROJECT_METHOD | TB 401 - PKG-G | Others | 20 | 0 | 0 | 20 | 100 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 132kV | All | 30 | 30 | 100 | 30 | 100 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 42.6 | 41
PROJECT_METHOD | TB 501 - 132kV | TSE | 7 | 7 | 100 | 7 | 100 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 35.4 | 39
PROJECT_METHOD | TB 501 - 132kV | Others | 11 | 11 | 100 | 11 | 100 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 23.9 | 8
PROJECT | TB 501 - 220kV | All | 88 | 75 | 85.2 | 88 | 100 | 0 | 0 | 88 | 88 | 0 | 0 | 0 | 3 | 99.2 | 86
PROJECT_METHOD | TB 501 - 220kV | TSE | 47 | 38 | 80.9 | 47 | 100 | 0 | 0 | 47 | 47 | 0 | 0 | 0 | 1 | 99.5 | 79
PROJECT_METHOD | TB 501 - 220kV | Others | 19 | 15 | 78.9 | 19 | 100 | 0 | 0 | 19 | 19 | 0 | 0 | 0 | 2 | 86.8 | 80
PROJECT | TB 507 - MAIN | All | 19 | 19 | 100 | 5 | 26.3 | 14 | 2 | 3 | 3 | 16 | 0 | 0 | 0 | 121.9 | 129
PROJECT_METHOD | TB 507 - MAIN | TSE | 3 | 3 | 100 | 1 | 33.3 | 2 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 102.3 | 89
PROJECT_METHOD | TB 507 - MAIN | Others | 1 | 1 | 100 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 72 | 72
SERIES | 4xx | All | 335 | 254 | 75.8 | 251 | 74.9 | 84 | 65 | 186 | 186 | 108 | 31 | 10 | 10 | 83.8 | 71.5
SERIES | 5xx | All | 68 | 67 | 98.5 | 48 | 70.6 | 20 | 2 | 46 | 46 | 22 | 0 | 0 | 0 | 103.1 | 97
SERIES | Other | All | 228 | 0 | 0 | 228 | 100 | 0 | 0 | 228 | 228 | 0 | 0 | 0 | 0
CLIENT_TYPE | TA | All | 566 | 272 | 48.1 | 473 | 83.6 | 93 | 66 | 407 | 407 | 118 | 31 | 10 | 10 | 85.2 | 71.5
CLIENT_TYPE | TB | All | 65 | 49 | 75.4 | 54 | 83.1 | 11 | 1 | 53 | 53 | 12 | 0 | 0 | 0 | 102.8 | 97

## ES Delay Anomalies
ES Delay Anomalies
Project | Project Scope Key | Series | Client Type | Method Split | Span Key | From AP | To AP | PO Start Date | Last Erection Completion Date | Gap Days | Issue | Lag Inference Mode | Location Parse Status | Required Location Count | Matched Location Count | Unmatched Location Count | Fallback Used
TA 325 | ta325 | Other | TA | Others | ta325¦112/0¦113/0 | 112/0 | 113/0 | 2024-08-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦111/0¦112/0 | 111/0 | 112/0 | 2024-09-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦110/0¦111/0 | 110/0 | 111/0 | 2024-09-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦113/0¦114/0 | 113/0 | 114/0 | 2024-09-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦109/0¦110/0 | 109/0 | 110/0 | 2024-09-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦116/0¦116A/0 | 116/0 | 116A/0 | 2024-10-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦108/0¦109/0 | 108/0 | 109/0 | 2024-10-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦107/0¦108/0 | 107/0 | 108/0 | 2024-10-30 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦133/0¦133A/0 | 133/0 | 133A/0 | 2024-10-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦121/0¦122/0 | 121/0 | 122/0 | 2024-11-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦129A/0¦130/0 | 129A/0 | 130/0 | 2024-11-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦106B/0¦107/0 | 106B/0 | 107/0 | 2024-11-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦122/0¦123/0 | 122/0 | 123/0 | 2024-11-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦118/0¦119/0 | 118/0 | 119/0 | 2024-11-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦117/0¦118/0 | 117/0 | 118/0 | 2024-12-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦119/0¦120/0 | 119/0 | 120/0 | 2024-12-19 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦116B/0¦117/0 | 116B/0 | 117/0 | 2024-11-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦144/0¦144A/0 | 144/0 | 144A/0 | 2024-12-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦120/0¦121/0 | 120/0 | 121/0 | 2024-12-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦114/0¦115/0 | 114/0 | 115/0 | 2024-12-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦115/0¦116/0 | 115/0 | 116/0 | 2024-12-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦133A/0¦134/0 | 133A/0 | 134/0 | 2024-12-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦123/0¦124/0 | 123/0 | 124/0 | 2024-12-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦116A/0¦116B/0 | 116A/0 | 116B/0 | 2025-01-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦144A/0¦145/0 | 144A/0 | 145/0 | 2024-01-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦147/1¦147/2 | 147/1 | 147/2 | 2025-01-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦127/0¦128/0 | 127/0 | 128/0 | 2024-12-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦126/0¦127/0 | 126/0 | 127/0 | 2025-01-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦132/0¦133/0 | 132/0 | 133/0 | 2025-01-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦259/0¦260/0 | 259/0 | 260/0 | 2025-01-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦260/0¦261/0 | 260/0 | 261/0 | 2025-01-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦125A/0¦126/0 | 125A/0 | 126/0 | 2025-01-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦106A/0¦106B/0 | 106A/0 | 106B/0 | 2025-01-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦125/0¦125A/0 | 125/0 | 125A/0 | 2025-01-31 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦128/0¦129/0 | 128/0 | 129/0 | 2025-02-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦129/0¦129A/0 | 129/0 | 129A/0 | 2025-02-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦135A/0¦135A/1 | 135A/0 | 135A/1 | 2025-01-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦135A/2¦135B/0 | 135A/2 | 135B/0 | 2025-02-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦135B/0¦136/0 | 135B/0 | 136/0 | 2025-01-25 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦106/0¦106A/0 | 106/0 | 106A/0 | 2025-02-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦164/0¦165/0 | 164/0 | 165/0 | 2025-02-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦135A/1¦135A/2 | 135A/1 | 135A/2 | 2025-01-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦124/0¦124A/0 | 124/0 | 124A/0 | 2025-02-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦124A/0¦124A/1 | 124A/0 | 124A/1 | 2025-02-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦124A/1¦125/0 | 124A/1 | 125/0 | 2025-02-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦257/0¦259/0 | 257/0 | 259/0 | 2025-02-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦137A/0¦138/0 | 137A/0 | 138/0 | 2025-02-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦138/0¦139/0 | 138/0 | 139/0 | 2025-02-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦261/0¦262/0 | 261/0 | 262/0 | 2025-03-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦139/0¦139A/0 | 139/0 | 139A/0 | 2025-03-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦130/0¦131/0 | 130/0 | 131/0 | 2025-03-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦131/0¦132/0 | 131/0 | 132/0 | 2025-03-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦139A/0¦140/0 | 139A/0 | 140/0 | 2025-02-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦262/0¦263/0 | 262/0 | 263/0 | 2025-02-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦263/0¦264/0 | 263/0 | 264/0 | 2025-03-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦142/0¦143/0 | 142/0 | 143/0 | 2025-03-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦143/0¦143A/0 | 143/0 | 143A/0 | 2025-03-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦255/0¦257/0 | 255/0 | 257/0 | 2025-02-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦265/0¦266/0 | 265/0 | 266/0 | 2025-03-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦134/0¦135/0 | 134/0 | 135/0 | 2025-03-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦163/0¦163/5 | 163/0 | 163/5 | 2025-02-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦163/5¦163/6 | 163/5 | 163/6 | 2025-03-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦163/6¦164/0 | 163/6 | 164/0 | 2025-03-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦264/0¦265/0 | 264/0 | 265/0 | 2025-03-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦143A/0¦143A/2 | 143A/0 | 143A/2 | 2025-03-19 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦143A/2¦143A/3 | 143A/2 | 143A/3 | 2025-03-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦143A/3¦144/0 | 143A/3 | 144/0 | 2025-03-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦266/0¦266/1 | 266/0 | 266/1 | 2025-03-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦266/1¦267/0 | 266/1 | 267/0 | 2025-03-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦136/0¦137/0 | 136/0 | 137/0 | 2025-03-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦137/0¦137A/0 | 137/0 | 137A/0 | 2025-03-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦145A/0¦146/0 | 145A/0 | 146/0 | 2025-04-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦253/0¦254/0 | 253/0 | 254/0 | 2025-04-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦254/0¦255/0 | 254/0 | 255/0 | 2025-02-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦267/0¦267A/0 | 267/0 | 267A/0 | 2025-04-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦267A/0¦268/0 | 267A/0 | 268/0 | 2025-03-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦141/0¦141/1 | 141/0 | 141/1 | 2025-04-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦141/1¦141/2 | 141/1 | 141/2 | 2025-04-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦141/2¦142/0 | 141/2 | 142/0 | 2025-04-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦146/0¦147/0 | 146/0 | 147/0 | 2025-04-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦147/0¦147/1 | 147/0 | 147/1 | 2025-04-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦147B/0¦148/0 | 147B/0 | 148/0 | 2025-04-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦152/0¦152A/0 | 152/0 | 152A/0 | 2025-04-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦270/0¦270A/0 | 270/0 | 270A/0 | 2025-04-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦145/0¦145A/0 | 145/0 | 145A/0 | 2025-04-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦268/0¦269/0 | 268/0 | 269/0 | 2025-04-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦269/0¦270/0 | 269/0 | 270/0 | 2025-04-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦270A/0¦271/0 | 270A/0 | 271/0 | 2025-04-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦271/0¦272/0 | 271/0 | 272/0 | 2025-04-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦148/0¦149/0 | 148/0 | 149/0 | 2025-04-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦149/0¦150/0 | 149/0 | 150/0 | 2025-04-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦162/0¦163/0 | 162/0 | 163/0 | 2025-04-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦147A/0¦147B/0 | 147A/0 | 147B/0 | 2025-04-30 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦135/0¦135A/0 | 135/0 | 135A/0 | 2025-03-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦251/0¦252/0 | 251/0 | 252/0 | 2025-04-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦161/0¦162/0 | 161/0 | 162/0 | 2025-04-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦252/0¦253/0 | 252/0 | 253/0 | 2025-04-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦250/0¦251/0 | 250/0 | 251/0 | 2025-05-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦249/0¦250/0 | 249/0 | 250/0 | 2025-04-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦150A/0¦151/0 | 150A/0 | 151/0 | 2025-04-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦151/0¦152/0 | 151/0 | 152/0 | 2025-05-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦147/2¦147A/0 | 147/2 | 147A/0 | 2025-05-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦140/0¦141/0 | 140/0 | 141/0 | 2025-05-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦150/0¦150/1 | 150/0 | 150/1 | 2025-05-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦150/1¦150A/0 | 150/1 | 150A/0 | 2025-05-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦156/0¦157/0 | 156/0 | 157/0 | 2025-06-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦272/0¦272/5 | 272/0 | 272/5 | 2025-03-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦155/0¦156/0 | 155/0 | 156/0 | 2025-06-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦152A/0¦153/0 | 152A/0 | 153/0 | 2025-09-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦158B/0¦159/0 | 158B/0 | 159/0 | 2025-09-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦158A/0¦158B/0 | 158A/0 | 158B/0 | 2025-10-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦276/0¦Gty | 276/0 | Gty | 2025-10-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦158/0¦158A/0 | 158/0 | 158A/0 | 2025-10-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦192/0¦193/0 | 192/0 | 193/0 | 2025-10-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦193/0¦194/0 | 193/0 | 194/0 | 2025-10-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦194/0¦195/0 | 194/0 | 195/0 | 2025-10-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦191/0¦191/2 | 191/0 | 191/2 | 2025-10-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦191/2¦191/3 | 191/2 | 191/3 | 2025-10-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦191/3¦191A/0 | 191/3 | 191A/0 | 2025-10-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦191A/0¦192/0 | 191A/0 | 192/0 | 2025-10-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦204/0¦205/0 | 204/0 | 205/0 | 2025-10-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦195/0¦195A/0 | 195/0 | 195A/0 | 2025-10-19 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦196/0¦197/0 | 196/0 | 197/0 | 2025-10-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦275/0¦276/0 | 275/0 | 276/0 | 2025-10-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦195A/0¦196/0 | 195A/0 | 196/0 | 2025-10-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦157/0¦158/0 | 157/0 | 158/0 | 2025-11-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦190/0¦191/0 | 190/0 | 191/0 | 2025-11-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦176/0¦177/0 | 176/0 | 177/0 | 2025-11-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦177/0¦178/0 | 177/0 | 178/0 | 2025-11-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦178/0¦179/0 | 178/0 | 179/0 | 2025-11-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦189/0¦190/0 | 189/0 | 190/0 | 2025-11-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦248/0¦249/0 | 248/0 | 249/0 | 2025-11-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦197/0¦198/0 | 197/0 | 198/0 | 2025-11-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦224/0¦225/0 | 224/0 | 225/0 | 2025-11-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦241/0¦242/0 | 241/0 | 242/0 | 2025-11-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦243/0¦244/0 | 243/0 | 244/0 | 2025-11-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦168/0¦169/0 | 168/0 | 169/0 | 2025-11-05 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦169/0¦171/0 | 169/0 | 171/0 | 2025-11-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦181/0¦182/0 | 181/0 | 182/0 | 2025-11-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦242/0¦243/0 | 242/0 | 243/0 | 2025-11-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦179/0¦180/0 | 179/0 | 180/0 | 2025-11-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦188/0¦189/0 | 188/0 | 189/0 | 2025-11-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦198/0¦199/0 | 198/0 | 199/0 | 2025-11-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦244/0¦244/1 | 244/0 | 244/1 | 2025-11-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦246/0¦247/0 | 246/0 | 247/0 | 2025-11-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦205/0¦206/0 | 205/0 | 206/0 | 2025-11-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦230/0¦231/0 | 230/0 | 231/0 | 2025-11-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦247/0¦248/0 | 247/0 | 248/0 | 2025-11-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦244/1¦245/0 | 244/1 | 245/0 | 2025-11-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦231/0¦232/0 | 231/0 | 232/0 | 2025-11-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦233/0¦234/0 | 233/0 | 234/0 | 2025-11-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦245/0¦246/0 | 245/0 | 246/0 | 2025-11-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦232/0¦233/0 | 232/0 | 233/0 | 2025-11-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦234/0¦235/0 | 234/0 | 235/0 | 2025-11-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦180/0¦181/0 | 180/0 | 181/0 | 2025-11-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦210/0¦211/0 | 210/0 | 211/0 | 2025-11-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦222/1¦223/0 | 222/1 | 223/0 | 2025-12-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦209/0¦210/0 | 209/0 | 210/0 | 2025-12-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦235/0¦236/0 | 235/0 | 236/0 | 2025-12-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦171/0¦172/0 | 171/0 | 172/0 | 2025-11-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦226/0¦227/0 | 226/0 | 227/0 | 2025-12-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦229/1¦230/0 | 229/1 | 230/0 | 2025-11-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦184/0¦184/1 | 184/0 | 184/1 | 2025-12-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦184/1¦185/0 | 184/1 | 185/0 | 2025-12-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦225/0¦226/0 | 225/0 | 226/0 | 2025-11-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦236/0¦237/0 | 236/0 | 237/0 | 2025-12-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦237/0¦239/0 | 237/0 | 239/0 | 2025-11-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦240/0¦241/0 | 240/0 | 241/0 | 2025-12-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦239/0¦240/0 | 239/0 | 240/0 | 2025-12-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦165/0¦165/4 | 165/0 | 165/4 | 2025-11-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦187/0¦188/0 | 187/0 | 188/0 | 2025-12-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦274/0¦275/0 | 274/0 | 275/0 | 2025-10-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦182/0¦182A/0 | 182/0 | 182A/0 | 2025-12-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦219/0¦220/0 | 219/0 | 220/0 | 2025-12-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦211/0¦211A/0 | 211/0 | 211A/0 | 2025-12-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦212/0¦213/0 | 212/0 | 213/0 | 2025-12-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦229/0¦229/1 | 229/0 | 229/1 | 2025-12-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦160/0¦161/0 | 160/0 | 161/0 | 2025-12-13 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦167/1¦168/0 | 167/1 | 168/0 | 2025-11-19 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦223/0¦224/0 | 223/0 | 224/0 | 2025-12-09 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦218/0¦219/0 | 218/0 | 219/0 | 2025-12-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦182A/0¦183/0 | 182A/0 | 183/0 | 2025-12-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦183/0¦184/0 | 183/0 | 184/0 | 2025-12-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦213/0¦214/0 | 213/0 | 214/0 | 2025-12-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦203/1¦204/0 | 203/1 | 204/0 | 2025-12-13 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦220/0¦221/0 | 220/0 | 221/0 | 2025-12-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦272/5¦272A/0 | 272/5 | 272A/0 | 2025-12-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦199/0¦200/0 | 199/0 | 200/0 | 2025-12-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦200/0¦201/0 | 200/0 | 201/0 | 2025-12-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦227/0¦228/0 | 227/0 | 228/0 | 2025-12-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦228/0¦229/0 | 228/0 | 229/0 | 2025-12-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦217A/0¦218/0 | 217A/0 | 218/0 | 2025-12-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦105/0¦106/0 | 105/0 | 106/0 | 2025-12-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦165/4¦165/5 | 165/4 | 165/5 | 2025-12-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦165/5¦166/0 | 165/5 | 166/0 | 2025-12-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦201/0¦201/1 | 201/0 | 201/1 | 2025-12-23 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦272A/0¦273/0 | 272A/0 | 273/0 | 2025-12-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦273/0¦274/0 | 273/0 | 274/0 | 2025-12-08 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦211A/0¦212/0 | 211A/0 | 212/0 | 2025-12-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦175/0¦175/1 | 175/0 | 175/1 | 2025-12-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦175/1¦176/0 | 175/1 | 176/0 | 2025-12-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦167/0¦167/1 | 167/0 | 167/1 | 2025-12-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦208/0¦209/0 | 208/0 | 209/0 | 2025-12-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦214/0¦215/0 | 214/0 | 215/0 | 2025-12-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦217/0¦217A/0 | 217/0 | 217A/0 | 2025-12-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦221/0¦222/0 | 221/0 | 222/0 | 2025-12-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦222/0¦222/1 | 222/0 | 222/1 | 2025-12-25 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦172/0¦173/0 | 172/0 | 173/0 | 2025-12-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦201/1¦202/0 | 201/1 | 202/0 | 2025-12-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦202/0¦203/0 | 202/0 | 203/0 | 2025-12-29 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦203/0¦203/1 | 203/0 | 203/1 | 2025-12-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦154/1¦155/0 | 154/1 | 155/0 | 2025-12-28 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦159/0¦159/2 | 159/0 | 159/2 | 2025-12-31 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦173/0¦174/0 | 173/0 | 174/0 | 2025-12-31 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦174/0¦174/1 | 174/0 | 174/1 | 2025-12-31 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦174/1¦175/0 | 174/1 | 175/0 | 2026-01-02 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦159/2¦160/0 | 159/2 | 160/0 | 2025-12-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦206/0¦208/0 | 206/0 | 208/0 | 2025-12-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦216/0¦217/0 | 216/0 | 217/0 | 2026-01-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦185/0¦186/0 | 185/0 | 186/0 | 2026-01-07 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦186/0¦187/0 | 186/0 | 187/0 | 2026-01-10 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦215/0¦215/1 | 215/0 | 215/1 | 2025-01-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦215/1¦216/0 | 215/1 | 216/0 | 2025-01-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦166/0¦167/0 | 166/0 | 167/0 | 2026-01-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦101/0¦102/0 | 101/0 | 102/0 | 2026-01-14 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦102/0¦103/0 | 102/0 | 103/0 | 2026-01-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦103/0¦104/0 | 103/0 | 104/0 | 2026-01-15 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦104/0¦105/0 | 104/0 | 105/0 | 2026-01-17 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 413 |  | 4xx | TA |  | ta413¦34¦35 | AP-34 | AP-35 | 2025-02-21 | 2025-02-23 | -2 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 413 |  | 4xx | TA |  | ta413¦37A/0¦38/0 | 37A/0 | AP-38/0 | 2025-03-17 | 2025-04-11 | -25 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 2 | 0 | TRUE
TA 413 |  | 4xx | TA |  | ta413¦38¦39 | AP-38 | AP-39 | 2025-03-29 | 2025-04-11 | -13 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 413 |  | 4xx | TA |  | ta413¦39¦40 | AP-39 | AP-40 | 2025-04-25 | 2025-04-30 | -5 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TA 416 |  | 4xx | TA |  | ta416¦36/0¦37/0 | AP36/0 | AP37/0 | 2025-09-05 | 2025-10-31 | -56 | NEGATIVE_LAG_EXCLUDED | LOCATION_NOS | OK | 14 | 14 | 0 | FALSE
TA 416 |  | 4xx | TA |  | ta416¦66/0¦67/0 | AP66/0 | AP67/0 | 2026-03-19 | 2026-03-23 | -4 | NEGATIVE_LAG_EXCLUDED | LOCATION_NOS | OK | 3 | 3 | 0 | FALSE
TA 421 |  | 4xx | TA |  | ta421¦29/0¦29/9 | 29/0 | 29/9 | 2025-05-05 | 2025-06-18 | -44 | NEGATIVE_LAG_EXCLUDED | LOCATION_NOS | OK | 10 | 10 | 0 | FALSE
TA 505 |  | 5xx | TA |  | ta505¦103/5A¦103/6A | 103/5A | 103/6A | 2026-02-24 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦57/6¦58/0 | 57/6 | 58/0 | 2024-05-06 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦57/0¦57/6 | 57/0 | 57/6 | 2024-05-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦56/0¦57/0 | 56/0 | 57/0 | 2024-06-04 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦55/0¦56/0 | 55/0 | 56/0 | 2024-06-25 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦53/0¦55/0 | 53/0 | 55/0 | 2024-07-16 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦52/0¦53/0 | 52/0 | 53/0 | 2024-08-19 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦51/0¦52/0 | 51/0 | 52/0 | 2024-09-01 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦50/0¦51/0 | 50/0 | 51/0 | 2024-09-26 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦72/7¦73/0 | 72/7 | 73/0 | 2024-11-12 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦58/0¦58/7 | 58/0 | 58/7 | 2024-11-20 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦72/0¦72/7 | 72/0 | 72/7 | 2024-11-18 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦67/1¦68/0 | 67/1 | 68/0 | 2024-12-22 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦68/0¦69/0 | 68/0 | 69/0 | 2024-12-11 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦58/7¦59/0 | 58/7 | 59/0 | 2024-12-27 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦71/0¦72/0 | 71/0 | 72/0 | 2024-12-03 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G |  | 4xx | TB |  | tb401pkgg¦67/0¦67/1 | 67/0 | 67/1 | 2024-12-21 |  |  | PROJECT_SCOPE_KEY_NO_ERECTION_MATCH | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦69/0¦70/0 | 69/0 | 70/0 | 2024-12-30 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦41/0¦42/0 | 41/0 | 42/0 | 2025-02-13 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦59/0¦60/0 | 59/0 | 60/0 | 2025-01-20 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦42/0¦43/0 | 42/0 | 43/0 | 2025-05-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦49/0¦50/0 | 49/0 | 50/0 | 2025-05-15 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦48/0¦49/0 | 48/0 | 49/0 | 2025-05-14 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦47/0¦48/0 | 47/0 | 48/0 | 2025-05-19 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦37/2¦38/0 | 37/2 | 38/0 | 2025-05-24 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦43/0¦44/0 | 43/0 | 44/0 | 2025-05-05 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦61/0¦62/0 | 61/0 | 62/0 | 2025-06-27 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦62/0¦63/0 | 62/0 | 63/0 | 2025-07-07 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦38/0¦38/9 | 38/0 | 38/9 | 2025-06-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦40/10¦41/0 | 40/10 | 41/0 | 2025-07-02 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦63/0¦64/0 | 63/0 | 64/0 | 2025-07-24 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦39/0¦40/0 | 39/0 | 40/0 | 2025-07-30 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦40/5¦40/10 | 40/5 | 40/10 | 2025-07-11 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦38/9¦39/0 | 38/9 | 39/0 | 2025-07-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦40/0¦40/2 | 40/0 | 40/2 | 2025-07-28 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦40/2¦40/5 | 40/2 | 40/5 | 2025-08-08 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦66/0¦67/0 | 66/0 | 67/0 | 2025-09-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦35/0¦36/0 | 35/0 | 36/0 | 2025-09-07 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦46/0¦47/0 | 46/0 | 47/0 | 2025-06-22 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦31/0¦32/0 | 31/0 | 32/0 | 2025-09-18 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦44/0¦45/0 | 44/0 | 45/0 | 2025-06-13 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦Gantry¦1/0 | Gantry | 1/0 | 2025-10-08 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦65/0¦66/0 | 65/0 | 66/0 | 2025-10-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦1/0¦1A/0 | 1/0 | 1A/0 | 2025-10-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦1A/0¦2/0 | 1A/0 | 2/0 | 2025-10-10 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦64/0¦65/0 | 64/0 | 65/0 | 2025-10-10 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦32/0¦33/0 | 32/0 | 33/0 | 2025-10-04 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦33/0¦34/0 | 33/0 | 34/0 | 2025-10-21 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦36/0¦37/0 | 36/0 | 37/0 | 2025-10-30 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦60/0¦61/0 | 60/0 | 61/0 | 2025-11-10 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦34/0¦34/5 | 34/0 | 34/5 | 2025-01-01 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦34/5¦35/0 | 34/5 | 35/0 | 2025-11-10 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦45/0¦46/0 | 45/0 | 46/0 | 2025-11-14 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦37/0¦37/1 | 37/0 | 37/1 | 2025-11-29 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦37/1¦37/2 | 37/1 | 37/2 | 2025-11-29 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦25/0¦26/0 | 25/0 | 26/0 | 2025-11-13 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦2/0¦3/0 | 2/0 | 3/0 | 2025-10-30 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦30/0¦31/0 | 30/0 | 31/0 | 2025-11-19 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦5/0¦6/0 | 5/0 | 6/0 | 2025-12-05 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦4/0¦5/0 | 4/0 | 5/0 | 2025-12-05 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦15/0¦16/0 | 15/0 | 16/0 | 2025-12-03 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦29/0¦30/0 | 29/0 | 30/0 | 2025-12-01 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦16/0¦17/0 | 16/0 | 17/0 | 2025-12-14 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦24/0¦25/0 | 24/0 | 25/0 | 2025-12-01 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦6/0¦7/0 | 6/0 | 7/0 | 2025-12-17 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦28/0¦29/0 | 28/0 | 29/0 | 2025-12-15 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦23/0¦24/0 | 23/0 | 24/0 | 2025-12-12 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | TSE | tb401pkgg¦27/1¦28/0 | 27/1 | 28/0 | 2025-12-24 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 401 - PKG-G | ta416 | 4xx | TA | Others | tb401pkgg¦3/0¦4/0 | 3/0 | 4/0 | 2025-12-23 |  |  | UNMATCHED_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 2 | 0 | 2 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others | tb501220kv¦20¦21 | AP-20 | AP-21 | 2025-07-22 | 2025-11-12 | -113 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 2 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE | tb501220kv¦22¦23 | AP-22 | AP-23 | 2025-08-08 | 2025-08-19 | -11 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 2 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others | tb501220kv¦29A/0¦30 | 29A/0 | AP-30 | 2025-07-16 | 2025-08-14 | -29 | NEGATIVE_LAG_EXCLUDED | ALPHABETIC_FALLBACK | EMPTY | 2 | 2 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 1900-01-02 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others |  |  |  | 1900-01-14 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others |  |  |  | 1900-01-05 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | Others |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE
TB 501 - 220kV | ta421 | 4xx | TA | TSE |  |  |  | 0 |  |  | INSUFFICIENT_REQUIRED_LOCATIONS | ALPHABETIC_FALLBACK | EMPTY | 0 | 0 | 0 | TRUE

## ES Delay Detail
ES Delay Detail
Project | Project Code | Project Display | Project Scope Key | Join Project Key | Base Project Code | Series | Client Type | Method Split | Section | Span | Span Key | Gang Name | From AP | To AP | PO Start Date | Last Erection Completion Date | Gap Days | Gap Days Non-Negative | Lag Inference Mode | Fallback Used | Location Parse Status | Location Parse Issue | Required Location Count | Matched Location Count | Unmatched Location Count | Required Locations | Matched Locations | Unmatched Locations | Location Nos Raw | Project Key In Erection Map
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 112/0-113/0 | ta325¦112/0¦113/0 | Muslehuddin | 112/0 | 113/0 | 2024-08-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 112/0, 113/0 |  | 112/0, 113/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 111/0-112/0 | ta325¦111/0¦112/0 | Gokul Sarkar | 111/0 | 112/0 | 2024-09-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 111/0, 112/0 |  | 111/0, 112/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 110/0-111/0 | ta325¦110/0¦111/0 | Gokul Sarkar | 110/0 | 111/0 | 2024-09-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 110/0, 111/0 |  | 110/0, 111/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 113/0-114/0 | ta325¦113/0¦114/0 | Muslehuddin | 113/0 | 114/0 | 2024-09-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 113/0, 114/0 |  | 113/0, 114/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 109/0-110/0 | ta325¦109/0¦110/0 | Gokul Sarkar | 109/0 | 110/0 | 2024-09-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 109/0, 110/0 |  | 109/0, 110/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116/0-116A/0 | ta325¦116/0¦116A/0 | Gokul Sarkar | 116/0 | 116A/0 | 2024-10-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 116/0, 116A/0 |  | 116/0, 116A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 108/0-109/0 | ta325¦108/0¦109/0 | Muslehuddin | 108/0 | 109/0 | 2024-10-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 108/0, 109/0 |  | 108/0, 109/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 107/0-108/0 | ta325¦107/0¦108/0 | Muslehuddin | 107/0 | 108/0 | 2024-10-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 107/0, 108/0 |  | 107/0, 108/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 133/0-133A/0 | ta325¦133/0¦133A/0 | Rejaul | 133/0 | 133A/0 | 2024-10-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 133/0, 133A/0 |  | 133/0, 133A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 121/0-122/0 | ta325¦121/0¦122/0 | Gokul Sarkar | 121/0 | 122/0 | 2024-11-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 121/0, 122/0 |  | 121/0, 122/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 129A/0-130/0 | ta325¦129A/0¦130/0 | Rejaul | 129A/0 | 130/0 | 2024-11-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 129A/0, 130/0 |  | 129A/0, 130/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 106B/0-107/0 | ta325¦106B/0¦107/0 | Muslehuddin | 106B/0 | 107/0 | 2024-11-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 106B/0, 107/0 |  | 106B/0, 107/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 122/0-123/0 | ta325¦122/0¦123/0 | Dhervendra Electricals | 122/0 | 123/0 | 2024-11-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 122/0, 123/0 |  | 122/0, 123/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 118/0-119/0 | ta325¦118/0¦119/0 | Enamul Haque | 118/0 | 119/0 | 2024-11-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 118/0, 119/0 |  | 118/0, 119/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 117/0-118/0 | ta325¦117/0¦118/0 | Enamul Haque | 117/0 | 118/0 | 2024-12-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 117/0, 118/0 |  | 117/0, 118/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 119/0-120/0 | ta325¦119/0¦120/0 | Muslehuddin | 119/0 | 120/0 | 2024-12-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 119/0, 120/0 |  | 119/0, 120/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116B/0-117/0 | ta325¦116B/0¦117/0 | Yakub Ali + Enamul | 116B/0 | 117/0 | 2024-11-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 116B/0, 117/0 |  | 116B/0, 117/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 144/0-144A/0 | ta325¦144/0¦144A/0 | Gokul Sarkar | 144/0 | 144A/0 | 2024-12-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 144/0, 144A/0 |  | 144/0, 144A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 120/0-121/0 | ta325¦120/0¦121/0 | Dhervendra Electricals | 120/0 | 121/0 | 2024-12-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 120/0, 121/0 |  | 120/0, 121/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 114/0-115/0 | ta325¦114/0¦115/0 | Muslehuddin | 114/0 | 115/0 | 2024-12-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 114/0, 115/0 |  | 114/0, 115/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 115/0-116/0 | ta325¦115/0¦116/0 | Muslehuddin | 115/0 | 116/0 | 2024-12-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 115/0, 116/0 |  | 115/0, 116/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 133A/0-134/0 | ta325¦133A/0¦134/0 | Rejaul + Rafikul | 133A/0 | 134/0 | 2024-12-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 133A/0, 134/0 |  | 133A/0, 134/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 123/0-124/0 | ta325¦123/0¦124/0 | Enamul Haque | 123/0 | 124/0 | 2024-12-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 123/0, 124/0 |  | 123/0, 124/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116A/0-116B/0 | ta325¦116A/0¦116B/0 | Muslehuddin | 116A/0 | 116B/0 | 2025-01-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 116A/0, 116B/0 |  | 116A/0, 116B/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 144A/0-145/0 | ta325¦144A/0¦145/0 | Dhervendra Electricals | 144A/0 | 145/0 | 2024-01-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 144A/0, 145/0 |  | 144A/0, 145/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147/1-147/2 | ta325¦147/1¦147/2 | Gokul Sarkar | 147/1 | 147/2 | 2025-01-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 147/1, 147/2 |  | 147/1, 147/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 127/0-128/0 | ta325¦127/0¦128/0 | Muslehuddin + Enamul | 127/0 | 128/0 | 2024-12-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 127/0, 128/0 |  | 127/0, 128/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 126/0-127/0 | ta325¦126/0¦127/0 | Enamul Haque | 126/0 | 127/0 | 2025-01-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 126/0, 127/0 |  | 126/0, 127/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 132/0-133/0 | ta325¦132/0¦133/0 | Rejaul + enamul | 132/0 | 133/0 | 2025-01-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 132/0, 133/0 |  | 132/0, 133/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 259/0-260/0 | ta325¦259/0¦260/0 | Dharmendra Electrical | 259/0 | 260/0 | 2025-01-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 259/0, 260/0 |  | 259/0, 260/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 260/0-261/0 | ta325¦260/0¦261/0 | Monera | 260/0 | 261/0 | 2025-01-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 260/0, 261/0 |  | 260/0, 261/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 125A/0-126/0 | ta325¦125A/0¦126/0 | Enamul Haque | 125A/0 | 126/0 | 2025-01-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 125A/0, 126/0 |  | 125A/0, 126/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 106A/0-106B/0 | ta325¦106A/0¦106B/0 | Muslehuddin | 106A/0 | 106B/0 | 2025-01-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 106A/0, 106B/0 |  | 106A/0, 106B/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 125/0-125A/0 | ta325¦125/0¦125A/0 | Enamul Haque | 125/0 | 125A/0 | 2025-01-31 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 125/0, 125A/0 |  | 125/0, 125A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 128/0-129/0 | ta325¦128/0¦129/0 | Alam Construction | 128/0 | 129/0 | 2025-02-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 128/0, 129/0 |  | 128/0, 129/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 129/0-129A/0 | ta325¦129/0¦129A/0 | Alam Construction | 129/0 | 129A/0 | 2025-02-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 129/0, 129A/0 |  | 129/0, 129A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 135A/0-135A/1 | ta325¦135A/0¦135A/1 | SK Zenarul | 135A/0 | 135A/1 | 2025-01-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 135A/0, 135A/1 |  | 135A/0, 135A/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135A/2-135B/0 | ta325¦135A/2¦135B/0 | Rafikul Alam construction + Enamul | 135A/2 | 135B/0 | 2025-02-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 135A/2, 135B/0 |  | 135A/2, 135B/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135B/0-136/0 | ta325¦135B/0¦136/0 | Rafikul Alam construction + Enamul | 135B/0 | 136/0 | 2025-01-25 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 135B/0, 136/0 |  | 135B/0, 136/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 106/0-106A/0 | ta325¦106/0¦106A/0 | Muslehuddin | 106/0 | 106A/0 | 2025-02-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 106/0, 106A/0 |  | 106/0, 106A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 164/0-165/0 | ta325¦164/0¦165/0 | Manik Sarkar | 164/0 | 165/0 | 2025-02-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 164/0, 165/0 |  | 164/0, 165/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 135A/1-135A/2 | ta325¦135A/1¦135A/2 | SK Zenarul | 135A/1 | 135A/2 | 2025-01-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 135A/1, 135A/2 |  | 135A/1, 135A/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124/0-124A/0 | ta325¦124/0¦124A/0 | Enamul Haque | 124/0 | 124A/0 | 2025-02-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 124/0, 124A/0 |  | 124/0, 124A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124A/0-124A/1 | ta325¦124A/0¦124A/1 | Enamul Haque | 124A/0 | 124A/1 | 2025-02-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 124A/0, 124A/1 |  | 124A/0, 124A/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124A/1-125/0 | ta325¦124A/1¦125/0 | Dhervendra Electricals | 124A/1 | 125/0 | 2025-02-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 124A/1, 125/0 |  | 124A/1, 125/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 257/0-259/0 | ta325¦257/0¦259/0 | Monera | 257/0 | 259/0 | 2025-02-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 257/0, 259/0 |  | 257/0, 259/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 137A/0-138/0 | ta325¦137A/0¦138/0 | Alam Construction | 137A/0 | 138/0 | 2025-02-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 137A/0, 138/0 |  | 137A/0, 138/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 138/0-139/0 | ta325¦138/0¦139/0 | Enamul Haque | 138/0 | 139/0 | 2025-02-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 138/0, 139/0 |  | 138/0, 139/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 261/0-262/0 | ta325¦261/0¦262/0 | Dharmendra Electrical | 261/0 | 262/0 | 2025-03-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 261/0, 262/0 |  | 261/0, 262/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 139/0-139A/0 | ta325¦139/0¦139A/0 | SK Zenarul | 139/0 | 139A/0 | 2025-03-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 139/0, 139A/0 |  | 139/0, 139A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 130/0-131/0 | ta325¦130/0¦131/0 | Muslehuddin | 130/0 | 131/0 | 2025-03-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 130/0, 131/0 |  | 130/0, 131/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 131/0-132/0 | ta325¦131/0¦132/0 | Dhervendra Electricals | 131/0 | 132/0 | 2025-03-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 131/0, 132/0 |  | 131/0, 132/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 139A/0-140/0 | ta325¦139A/0¦140/0 | SK Zenarul | 139A/0 | 140/0 | 2025-02-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 139A/0, 140/0 |  | 139A/0, 140/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 262/0-263/0 | ta325¦262/0¦263/0 | Monera | 262/0 | 263/0 | 2025-02-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 262/0, 263/0 |  | 262/0, 263/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 263/0-264/0 | ta325¦263/0¦264/0 | Dharmendra Electrical | 263/0 | 264/0 | 2025-03-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 263/0, 264/0 |  | 263/0, 264/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 142/0-143/0 | ta325¦142/0¦143/0 | Enamul + Alam Constrution | 142/0 | 143/0 | 2025-03-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 142/0, 143/0 |  | 142/0, 143/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143/0-143A/0 | ta325¦143/0¦143A/0 | Alam Construction | 143/0 | 143A/0 | 2025-03-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 143/0, 143A/0 |  | 143/0, 143A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 255/0-257/0 | ta325¦255/0¦257/0 | Kamruddin | 255/0 | 257/0 | 2025-02-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 255/0, 257/0 |  | 255/0, 257/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 265/0-266/0 | ta325¦265/0¦266/0 | Dharmendra Electrical | 265/0 | 266/0 | 2025-03-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 265/0, 266/0 |  | 265/0, 266/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 134/0-135/0 | ta325¦134/0¦135/0 | Dhervendra Electricals | 134/0 | 135/0 | 2025-03-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 134/0, 135/0 |  | 134/0, 135/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 163/0-163/5 | ta325¦163/0¦163/5 | Manik Sarkar | 163/0 | 163/5 | 2025-02-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 163/0, 163/5 |  | 163/0, 163/5 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 163/5-163/6 | ta325¦163/5¦163/6 | Dhervendra Electricals | 163/5 | 163/6 | 2025-03-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 163/5, 163/6 |  | 163/5, 163/6 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 163/6-164/0 | ta325¦163/6¦164/0 | Manik Sarkar | 163/6 | 164/0 | 2025-03-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 163/6, 164/0 |  | 163/6, 164/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 264/0-265/0 | ta325¦264/0¦265/0 | Monera | 264/0 | 265/0 | 2025-03-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 264/0, 265/0 |  | 264/0, 265/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143A/0-143A/2 | ta325¦143A/0¦143A/2 | Alam Construction | 143A/0 | 143A/2 | 2025-03-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 143A/0, 143A/2 |  | 143A/0, 143A/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143A/2-143A/3 | ta325¦143A/2¦143A/3 | Enamul Haque | 143A/2 | 143A/3 | 2025-03-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 143A/2, 143A/3 |  | 143A/2, 143A/3 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 143A/3-144/0 | ta325¦143A/3¦144/0 | Enamul Haque | 143A/3 | 144/0 | 2025-03-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 143A/3, 144/0 |  | 143A/3, 144/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 266/0-266/1 | ta325¦266/0¦266/1 | Dharmendra Electrical | 266/0 | 266/1 | 2025-03-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 266/0, 266/1 |  | 266/0, 266/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 266/1-267/0 | ta325¦266/1¦267/0 | Monera | 266/1 | 267/0 | 2025-03-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 266/1, 267/0 |  | 266/1, 267/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 136/0-137/0 | ta325¦136/0¦137/0 | Dhervendra Electricals | 136/0 | 137/0 | 2025-03-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 136/0, 137/0 |  | 136/0, 137/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 137/0-137A/0 | ta325¦137/0¦137A/0 | Rafikul Alam construction | 137/0 | 137A/0 | 2025-03-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 137/0, 137A/0 |  | 137/0, 137A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 145A/0-146/0 | ta325¦145A/0¦146/0 | Enamul Haque | 145A/0 | 146/0 | 2025-04-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 145A/0, 146/0 |  | 145A/0, 146/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 253/0-254/0 | ta325¦253/0¦254/0 | Dharmendra Electrical | 253/0 | 254/0 | 2025-04-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 253/0, 254/0 |  | 253/0, 254/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 254/0-255/0 | ta325¦254/0¦255/0 | Monera | 254/0 | 255/0 | 2025-02-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 254/0, 255/0 |  | 254/0, 255/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 267/0-267A/0 | ta325¦267/0¦267A/0 | Kamruddin Deepak Sarkar | 267/0 | 267A/0 | 2025-04-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 267/0, 267A/0 |  | 267/0, 267A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 267A/0-268/0 | ta325¦267A/0¦268/0 | Kamruddin | 267A/0 | 268/0 | 2025-03-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 267A/0, 268/0 |  | 267A/0, 268/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 141/0-141/1 | ta325¦141/0¦141/1 | Alam Construction | 141/0 | 141/1 | 2025-04-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 141/0, 141/1 |  | 141/0, 141/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 141/1-141/2 | ta325¦141/1¦141/2 | Dhervendra Electricals | 141/1 | 141/2 | 2025-04-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 141/1, 141/2 |  | 141/1, 141/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 141/2-142/0 | ta325¦141/2¦142/0 | Alam Construction | 141/2 | 142/0 | 2025-04-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 141/2, 142/0 |  | 141/2, 142/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 146/0-147/0 | ta325¦146/0¦147/0 | Enamul Haque | 146/0 | 147/0 | 2025-04-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 146/0, 147/0 |  | 146/0, 147/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147/0-147/1 | ta325¦147/0¦147/1 | Dhervendra Electricals | 147/0 | 147/1 | 2025-04-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 147/0, 147/1 |  | 147/0, 147/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 147B/0-148/0 | ta325¦147B/0¦148/0 | Muslehuddinn + GPJ | 147B/0 | 148/0 | 2025-04-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 147B/0, 148/0 |  | 147B/0, 148/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 152/0-152A/0 | ta325¦152/0¦152A/0 | Alongir | 152/0 | 152A/0 | 2025-04-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 152/0, 152A/0 |  | 152/0, 152A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 270/0-270A/0 | ta325¦270/0¦270A/0 | Kamruddin & Deepak | 270/0 | 270A/0 | 2025-04-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 270/0, 270A/0 |  | 270/0, 270A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 145/0-145A/0 | ta325¦145/0¦145A/0 | Dhervendra Electricals | 145/0 | 145A/0 | 2025-04-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 145/0, 145A/0 |  | 145/0, 145A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 268/0-269/0 | ta325¦268/0¦269/0 | Dharmendra Electrical | 268/0 | 269/0 | 2025-04-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 268/0, 269/0 |  | 268/0, 269/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 269/0-270/0 | ta325¦269/0¦270/0 | Kamruddin & Maidul rahman | 269/0 | 270/0 | 2025-04-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 269/0, 270/0 |  | 269/0, 270/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 270A/0-271/0 | ta325¦270A/0¦271/0 | Alamgir | 270A/0 | 271/0 | 2025-04-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 270A/0, 271/0 |  | 270A/0, 271/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 271/0-272/0 | ta325¦271/0¦272/0 | Kamruddin & Deepak | 271/0 | 272/0 | 2025-04-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 271/0, 272/0 |  | 271/0, 272/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 148/0-149/0 | ta325¦148/0¦149/0 | Muslehuddin | 148/0 | 149/0 | 2025-04-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 148/0, 149/0 |  | 148/0, 149/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 149/0-150/0 | ta325¦149/0¦150/0 | Enamul Haque | 149/0 | 150/0 | 2025-04-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 149/0, 150/0 |  | 149/0, 150/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 162/0-163/0 | ta325¦162/0¦163/0 | Manik Sarkar | 162/0 | 163/0 | 2025-04-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 162/0, 163/0 |  | 162/0, 163/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147A/0-147B/0 | ta325¦147A/0¦147B/0 | Enamul Haque | 147A/0 | 147B/0 | 2025-04-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 147A/0, 147B/0 |  | 147A/0, 147B/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135/0-135A/0 | ta325¦135/0¦135A/0 | RafikulAlam Construction | 135/0 | 135A/0 | 2025-03-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 135/0, 135A/0 |  | 135/0, 135A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 251/0-252/0 | ta325¦251/0¦252/0 | Dharmendra Electrical | 251/0 | 252/0 | 2025-04-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 251/0, 252/0 |  | 251/0, 252/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 161/0-162/0 | ta325¦161/0¦162/0 | Dhervendra Electricals | 161/0 | 162/0 | 2025-04-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 161/0, 162/0 |  | 161/0, 162/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 252/0-253/0 | ta325¦252/0¦253/0 | Deepak Sarkar | 252/0 | 253/0 | 2025-04-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 252/0, 253/0 |  | 252/0, 253/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 250/0-251/0 | ta325¦250/0¦251/0 | Deepak Sarkar | 250/0 | 251/0 | 2025-05-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 250/0, 251/0 |  | 250/0, 251/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 249/0-250/0 | ta325¦249/0¦250/0 | Kamruddin | 249/0 | 250/0 | 2025-04-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 249/0, 250/0 |  | 249/0, 250/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 150A/0-151/0 | ta325¦150A/0¦151/0 | Alam Construction | 150A/0 | 151/0 | 2025-04-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 150A/0, 151/0 |  | 150A/0, 151/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 151/0-152/0 | ta325¦151/0¦152/0 | Dhervendra Electricals | 151/0 | 152/0 | 2025-05-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 151/0, 152/0 |  | 151/0, 152/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 147/2-147A/0 | ta325¦147/2¦147A/0 | Rafikul Alam + Alam Const. + Enamul | 147/2 | 147A/0 | 2025-05-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 147/2, 147A/0 |  | 147/2, 147A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 140/0-141/0 | ta325¦140/0¦141/0 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 140/0 | 141/0 | 2025-05-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 140/0, 141/0 |  | 140/0, 141/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 150/0-150/1 | ta325¦150/0¦150/1 | Dhervendra Electricals | 150/0 | 150/1 | 2025-05-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 150/0, 150/1 |  | 150/0, 150/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 150/1-150A/0 | ta325¦150/1¦150A/0 | Alam Construction | 150/1 | 150A/0 | 2025-05-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 150/1, 150A/0 |  | 150/1, 150A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 156/0-157/0 | ta325¦156/0¦157/0 | Deepak Sarkar + Manik Sarkar | 156/0 | 157/0 | 2025-06-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 156/0, 157/0 |  | 156/0, 157/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272/0-272/5 | ta325¦272/0¦272/5 | Kamruddin & Deepak Sarkar | 272/0 | 272/5 | 2025-03-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 272/0, 272/5 |  | 272/0, 272/5 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 155/0-156/0 | ta325¦155/0¦156/0 | Deepak Sarkar + Manik Sarkar | 155/0 | 156/0 | 2025-06-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 155/0, 156/0 |  | 155/0, 156/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 152A/0-153/0 | ta325¦152A/0¦153/0 | Alam Construction | 152A/0 | 153/0 | 2025-09-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 152A/0, 153/0 |  | 152A/0, 153/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 158B/0-159/0 | ta325¦158B/0¦159/0 | Deepak Sarkar | 158B/0 | 159/0 | 2025-09-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 158B/0, 159/0 |  | 158B/0, 159/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 158A/0-158B/0 | ta325¦158A/0¦158B/0 | Dharmendra 1 | 158A/0 | 158B/0 | 2025-10-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 158A/0, 158B/0 |  | 158A/0, 158B/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 276/0-Gty | ta325¦276/0¦Gty | Bhola | 276/0 | Gty | 2025-10-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 276/0, GTY |  | 276/0, GTY |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 158/0-158A/0 | ta325¦158/0¦158A/0 | Deepak Sarkar | 158/0 | 158A/0 | 2025-10-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 158/0, 158A/0 |  | 158/0, 158A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 192/0-193/0 | ta325¦192/0¦193/0 | Teklal Saw | 192/0 | 193/0 | 2025-10-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 192/0, 193/0 |  | 192/0, 193/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 193/0-194/0 | ta325¦193/0¦194/0 | Ramsingh Yadav | 193/0 | 194/0 | 2025-10-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 193/0, 194/0 |  | 193/0, 194/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 194/0-195/0 | ta325¦194/0¦195/0 | Enamul Haque | 194/0 | 195/0 | 2025-10-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 194/0, 195/0 |  | 194/0, 195/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 191/0-191/2 | ta325¦191/0¦191/2 | Alam Construction | 191/0 | 191/2 | 2025-10-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 191/0, 191/2 |  | 191/0, 191/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 191/2-191/3 | ta325¦191/2¦191/3 | Alam Construction | 191/2 | 191/3 | 2025-10-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 191/2, 191/3 |  | 191/2, 191/3 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 191/3-191A/0 | ta325¦191/3¦191A/0 | Alam Construction | 191/3 | 191A/0 | 2025-10-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 191/3, 191A/0 |  | 191/3, 191A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 191A/0-192/0 | ta325¦191A/0¦192/0 | Md Anwar | 191A/0 | 192/0 | 2025-10-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 191A/0, 192/0 |  | 191A/0, 192/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 204/0-205/0 | ta325¦204/0¦205/0 | Dharmendra 2 | 204/0 | 205/0 | 2025-10-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 204/0, 205/0 |  | 204/0, 205/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 195/0-195A/0 | ta325¦195/0¦195A/0 | Enamul Haque | 195/0 | 195A/0 | 2025-10-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 195/0, 195A/0 |  | 195/0, 195A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 196/0-197/0 | ta325¦196/0¦197/0 | Ramsingh Yadav | 196/0 | 197/0 | 2025-10-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 196/0, 197/0 |  | 196/0, 197/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 275/0-276/0 | ta325¦275/0¦276/0 | Dharmendra 1 | 275/0 | 276/0 | 2025-10-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 275/0, 276/0 |  | 275/0, 276/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 195A/0-196/0 | ta325¦195A/0¦196/0 | Muslehuddin | 195A/0 | 196/0 | 2025-10-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 195A/0, 196/0 |  | 195A/0, 196/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 157/0-158/0 | ta325¦157/0¦158/0 | Deepak Sarkar | 157/0 | 158/0 | 2025-11-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 157/0, 158/0 |  | 157/0, 158/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 190/0-191/0 | ta325¦190/0¦191/0 | Ramsingh Yadav | 190/0 | 191/0 | 2025-11-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 190/0, 191/0 |  | 190/0, 191/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 176/0-177/0 | ta325¦176/0¦177/0 | Sanjay Singh | 176/0 | 177/0 | 2025-11-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 176/0, 177/0 |  | 176/0, 177/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 177/0-178/0 | ta325¦177/0¦178/0 | Ruhul Amin / Alam Constr. | 177/0 | 178/0 | 2025-11-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 177/0, 178/0 |  | 177/0, 178/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 178/0-179/0 | ta325¦178/0¦179/0 | Giyash | 178/0 | 179/0 | 2025-11-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 178/0, 179/0 |  | 178/0, 179/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 189/0-190/0 | ta325¦189/0¦190/0 | Md Anwar | 189/0 | 190/0 | 2025-11-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 189/0, 190/0 |  | 189/0, 190/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 248/0-249/0 | ta325¦248/0¦249/0 | Kamaruddin | 248/0 | 249/0 | 2025-11-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 248/0, 249/0 |  | 248/0, 249/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 197/0-198/0 | ta325¦197/0¦198/0 | Muslehuddin | 197/0 | 198/0 | 2025-11-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 197/0, 198/0 |  | 197/0, 198/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 224/0-225/0 | ta325¦224/0¦225/0 | Dharmendra 2 | 224/0 | 225/0 | 2025-11-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 224/0, 225/0 |  | 224/0, 225/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 241/0-242/0 | ta325¦241/0¦242/0 | Singhvahini | 241/0 | 242/0 | 2025-11-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 241/0, 242/0 |  | 241/0, 242/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 243/0-244/0 | ta325¦243/0¦244/0 | Dharmendra 1 | 243/0 | 244/0 | 2025-11-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 243/0, 244/0 |  | 243/0, 244/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 168/0-169/0 | ta325¦168/0¦169/0 | Rafikul Alam constr. | 168/0 | 169/0 | 2025-11-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 168/0, 169/0 |  | 168/0, 169/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 169/0-171/0 | ta325¦169/0¦171/0 | Ramavat Electricals | 169/0 | 171/0 | 2025-11-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 169/0, 171/0 |  | 169/0, 171/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 181/0-182/0 | ta325¦181/0¦182/0 | Alam Construction | 181/0 | 182/0 | 2025-11-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 181/0, 182/0 |  | 181/0, 182/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 242/0-243/0 | ta325¦242/0¦243/0 | Enamul Haque | 242/0 | 243/0 | 2025-11-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 242/0, 243/0 |  | 242/0, 243/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 179/0-180/0 | ta325¦179/0¦180/0 | Sanjay Singh | 179/0 | 180/0 | 2025-11-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 179/0, 180/0 |  | 179/0, 180/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 188/0-189/0 | ta325¦188/0¦189/0 | Ramsingh Yadav | 188/0 | 189/0 | 2025-11-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 188/0, 189/0 |  | 188/0, 189/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 198/0-199/0 | ta325¦198/0¦199/0 | Muslehuddin | 198/0 | 199/0 | 2025-11-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 198/0, 199/0 |  | 198/0, 199/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 244/0-244/1 | ta325¦244/0¦244/1 | Bhola Prasad | 244/0 | 244/1 | 2025-11-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 244/0, 244/1 |  | 244/0, 244/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 246/0-247/0 | ta325¦246/0¦247/0 | Dharmendra 1 | 246/0 | 247/0 | 2025-11-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 246/0, 247/0 |  | 246/0, 247/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 205/0-206/0 | ta325¦205/0¦206/0 | Deepak Sarkar | 205/0 | 206/0 | 2025-11-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 205/0, 206/0 |  | 205/0, 206/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 230/0-231/0 | ta325¦230/0¦231/0 | Alam Construction / Enamul / Giyash / Alongir | 230/0 | 231/0 | 2025-11-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 230/0, 231/0 |  | 230/0, 231/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 247/0-248/0 | ta325¦247/0¦248/0 | Kamruddinn | 247/0 | 248/0 | 2025-11-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 247/0, 248/0 |  | 247/0, 248/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 244/1-245/0 | ta325¦244/1¦245/0 | Bhola Prasad | 244/1 | 245/0 | 2025-11-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 244/1, 245/0 |  | 244/1, 245/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 231/0-232/0 | ta325¦231/0¦232/0 | Giyash / Alongir | 231/0 | 232/0 | 2025-11-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 231/0, 232/0 |  | 231/0, 232/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 233/0-234/0 | ta325¦233/0¦234/0 | Singhvahini | 233/0 | 234/0 | 2025-11-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 233/0, 234/0 |  | 233/0, 234/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 245/0-246/0 | ta325¦245/0¦246/0 | Kamruddinn / Bhola prasad | 245/0 | 246/0 | 2025-11-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 245/0, 246/0 |  | 245/0, 246/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 232/0-233/0 | ta325¦232/0¦233/0 | Sanjay Singh | 232/0 | 233/0 | 2025-11-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 232/0, 233/0 |  | 232/0, 233/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 234/0-235/0 | ta325¦234/0¦235/0 | Dharmendra 2 | 234/0 | 235/0 | 2025-11-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 234/0, 235/0 |  | 234/0, 235/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 180/0-181/0 | ta325¦180/0¦181/0 | Ramavat Electricals -2 | 180/0 | 181/0 | 2025-11-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 180/0, 181/0 |  | 180/0, 181/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 210/0-211/0 | ta325¦210/0¦211/0 | Ramsingh Yadav | 210/0 | 211/0 | 2025-11-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 210/0, 211/0 |  | 210/0, 211/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 222/1-223/0 | ta325¦222/1¦223/0 | Ramsingh Yadav 2 | 222/1 | 223/0 | 2025-12-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 222/1, 223/0 |  | 222/1, 223/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 209/0-210/0 | ta325¦209/0¦210/0 | Deepak Sarkar | 209/0 | 210/0 | 2025-12-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 209/0, 210/0 |  | 209/0, 210/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 235/0-236/0 | ta325¦235/0¦236/0 | Singhvahini | 235/0 | 236/0 | 2025-12-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 235/0, 236/0 |  | 235/0, 236/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 171/0-172/0 | ta325¦171/0¦172/0 | Ramavat Electricals 1& 2 | 171/0 | 172/0 | 2025-11-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 171/0, 172/0 |  | 171/0, 172/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 226/0-227/0 | ta325¦226/0¦227/0 | Muslehuddin | 226/0 | 227/0 | 2025-12-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 226/0, 227/0 |  | 226/0, 227/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 229/1-230/0 | ta325¦229/1¦230/0 | Teklal Saw | 229/1 | 230/0 | 2025-11-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 229/1, 230/0 |  | 229/1, 230/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 184/0-184/1 | ta325¦184/0¦184/1 | Alam Construction | 184/0 | 184/1 | 2025-12-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 184/0, 184/1 |  | 184/0, 184/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 184/1-185/0 | ta325¦184/1¦185/0 | Alam Construction | 184/1 | 185/0 | 2025-12-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 184/1, 185/0 |  | 184/1, 185/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 225/0-226/0 | ta325¦225/0¦226/0 | Muslehuddin | 225/0 | 226/0 | 2025-11-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 225/0, 226/0 |  | 225/0, 226/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 236/0-237/0 | ta325¦236/0¦237/0 | Dharmendra 1 | 236/0 | 237/0 | 2025-12-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 236/0, 237/0 |  | 236/0, 237/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 237/0-239/0 | ta325¦237/0¦239/0 | Enamul Haque | 237/0 | 239/0 | 2025-11-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 237/0, 239/0 |  | 237/0, 239/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 240/0-241/0 | ta325¦240/0¦241/0 | Enamul Haque | 240/0 | 241/0 | 2025-12-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 240/0, 241/0 |  | 240/0, 241/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 239/0-240/0 | ta325¦239/0¦240/0 | Ramsingh Yadav | 239/0 | 240/0 | 2025-12-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 239/0, 240/0 |  | 239/0, 240/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 165/0-165/4 | ta325¦165/0¦165/4 | Rafikul Alam | 165/0 | 165/4 | 2025-11-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 165/0, 165/4 |  | 165/0, 165/4 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 187/0-188/0 | ta325¦187/0¦188/0 | Alam Construction | 187/0 | 188/0 | 2025-12-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 187/0, 188/0 |  | 187/0, 188/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 274/0-275/0 | ta325¦274/0¦275/0 | Bhola Prasad | 274/0 | 275/0 | 2025-10-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 274/0, 275/0 |  | 274/0, 275/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 182/0-182A/0 | ta325¦182/0¦182A/0 | Ramavat Electricals 2 | 182/0 | 182A/0 | 2025-12-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 182/0, 182A/0 |  | 182/0, 182A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 219/0-220/0 | ta325¦219/0¦220/0 | Sanjay Singh | 219/0 | 220/0 | 2025-12-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 219/0, 220/0 |  | 219/0, 220/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 211/0-211A/0 | ta325¦211/0¦211A/0 | Deepak Sarkar | 211/0 | 211A/0 | 2025-12-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 211/0, 211A/0 |  | 211/0, 211A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 212/0-213/0 | ta325¦212/0¦213/0 | Ramsingh Yadav 2 | 212/0 | 213/0 | 2025-12-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 212/0, 213/0 |  | 212/0, 213/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 229/0-229/1 | ta325¦229/0¦229/1 | Alongir | 229/0 | 229/1 | 2025-12-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 229/0, 229/1 |  | 229/0, 229/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 160/0-161/0 | ta325¦160/0¦161/0 | Dharmendra 2 | 160/0 | 161/0 | 2025-12-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 160/0, 161/0 |  | 160/0, 161/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 167/1-168/0 | ta325¦167/1¦168/0 | Rafikul Alam Construction | 167/1 | 168/0 | 2025-11-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 167/1, 168/0 |  | 167/1, 168/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 223/0-224/0 | ta325¦223/0¦224/0 | Muslehuddin and Giyash | 223/0 | 224/0 | 2025-12-09 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 223/0, 224/0 |  | 223/0, 224/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 218/0-219/0 | ta325¦218/0¦219/0 | Singhvahini | 218/0 | 219/0 | 2025-12-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 218/0, 219/0 |  | 218/0, 219/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 182A/0-183/0 | ta325¦182A/0¦183/0 | Alam Construction | 182A/0 | 183/0 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 182A/0, 183/0 |  | 182A/0, 183/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 183/0-184/0 | ta325¦183/0¦184/0 | Ramavat Electricals 1 | 183/0 | 184/0 | 2025-12-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 183/0, 184/0 |  | 183/0, 184/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 213/0-214/0 | ta325¦213/0¦214/0 | Kudus Ali | 213/0 | 214/0 | 2025-12-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 213/0, 214/0 |  | 213/0, 214/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 203/1-204/0 | ta325¦203/1¦204/0 | Modia India | 203/1 | 204/0 | 2025-12-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 203/1, 204/0 |  | 203/1, 204/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 220/0-221/0 | ta325¦220/0¦221/0 | Abdul Adut | 220/0 | 221/0 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 220/0, 221/0 |  | 220/0, 221/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272/5-272A/0 | ta325¦272/5¦272A/0 | Bhola Prasad & Kamruddin | 272/5 | 272A/0 | 2025-12-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 272/5, 272A/0 |  | 272/5, 272A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 199/0-200/0 | ta325¦199/0¦200/0 | Ramsingh Yadav | 199/0 | 200/0 | 2025-12-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 199/0, 200/0 |  | 199/0, 200/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 200/0-201/0 | ta325¦200/0¦201/0 | Ramsingh Yadav 2 | 200/0 | 201/0 | 2025-12-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 200/0, 201/0 |  | 200/0, 201/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 227/0-228/0 | ta325¦227/0¦228/0 | Munni Bibi 2 | 227/0 | 228/0 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 227/0, 228/0 |  | 227/0, 228/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 228/0-229/0 | ta325¦228/0¦229/0 | Sanjay Singh | 228/0 | 229/0 | 2025-12-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 228/0, 229/0 |  | 228/0, 229/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 217A/0-218/0 | ta325¦217A/0¦218/0 | Teklal Saw | 217A/0 | 218/0 | 2025-12-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 217A/0, 218/0 |  | 217A/0, 218/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 105/0-106/0 | ta325¦105/0¦106/0 | Kudus Ali 2 | 105/0 | 106/0 | 2025-12-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 105/0, 106/0 |  | 105/0, 106/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 165/4-165/5 | ta325¦165/4¦165/5 | Munni Bibi 1 | 165/4 | 165/5 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 165/4, 165/5 |  | 165/4, 165/5 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 165/5-166/0 | ta325¦165/5¦166/0 | Munni Bibi 1 | 165/5 | 166/0 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 165/5, 166/0 |  | 165/5, 166/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 201/0-201/1 | ta325¦201/0¦201/1 | Modina India 2 | 201/0 | 201/1 | 2025-12-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 201/0, 201/1 |  | 201/0, 201/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272A/0-273/0 | ta325¦272A/0¦273/0 | Kamaruddin | 272A/0 | 273/0 | 2025-12-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 272A/0, 273/0 |  | 272A/0, 273/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 273/0-274/0 | ta325¦273/0¦274/0 | Kamaruddin | 273/0 | 274/0 | 2025-12-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 273/0, 274/0 |  | 273/0, 274/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 211A/0-212/0 | ta325¦211A/0¦212/0 | Deepak Sarkar | 211A/0 | 212/0 | 2025-12-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 211A/0, 212/0 |  | 211A/0, 212/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 175/0-175/1 | ta325¦175/0¦175/1 | Dharmendra 2 | 175/0 | 175/1 | 2025-12-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 175/0, 175/1 |  | 175/0, 175/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 175/1-176/0 | ta325¦175/1¦176/0 | Alam Construction | 175/1 | 176/0 | 2025-12-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 175/1, 176/0 |  | 175/1, 176/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 167/0-167/1 | ta325¦167/0¦167/1 | Rafikul Alam | 167/0 | 167/1 | 2025-12-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 167/0, 167/1 |  | 167/0, 167/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 208/0-209/0 | ta325¦208/0¦209/0 | Deepak Sarkar | 208/0 | 209/0 | 2025-12-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 208/0, 209/0 |  | 208/0, 209/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 214/0-215/0 | ta325¦214/0¦215/0 | Kudus Ali | 214/0 | 215/0 | 2025-12-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 214/0, 215/0 |  | 214/0, 215/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 217/0-217A/0 | ta325¦217/0¦217A/0 | Ramsingh Yadav 1&2 | 217/0 | 217A/0 | 2025-12-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 217/0, 217A/0 |  | 217/0, 217A/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 221/0-222/0 | ta325¦221/0¦222/0 | Sanjay Singh | 221/0 | 222/0 | 2025-12-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 221/0, 222/0 |  | 221/0, 222/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 222/0-222/1 | ta325¦222/0¦222/1 | Muslehuddin and Giyash | 222/0 | 222/1 | 2025-12-25 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 222/0, 222/1 |  | 222/0, 222/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 172/0-173/0 | ta325¦172/0¦173/0 | Alam Construction | 172/0 | 173/0 | 2025-12-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 172/0, 173/0 |  | 172/0, 173/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 201/1-202/0 | ta325¦201/1¦202/0 | Modina India 2 | 201/1 | 202/0 | 2025-12-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 201/1, 202/0 |  | 201/1, 202/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 202/0-203/0 | ta325¦202/0¦203/0 | Teklal Saw / Muslehuddin | 202/0 | 203/0 | 2025-12-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 202/0, 203/0 |  | 202/0, 203/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 203/0-203/1 | ta325¦203/0¦203/1 | Modia India | 203/0 | 203/1 | 2025-12-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 203/0, 203/1 |  | 203/0, 203/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 154/1-155/0 | ta325¦154/1¦155/0 | Munni Bibi 2 | 154/1 | 155/0 | 2025-12-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 154/1, 155/0 |  | 154/1, 155/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 159/0-159/2 | ta325¦159/0¦159/2 | Enamul Haque | 159/0 | 159/2 | 2025-12-31 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 159/0, 159/2 |  | 159/0, 159/2 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 173/0-174/0 | ta325¦173/0¦174/0 | Dharmendra 2 | 173/0 | 174/0 | 2025-12-31 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 173/0, 174/0 |  | 173/0, 174/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 174/0-174/1 | ta325¦174/0¦174/1 | Alam Construction | 174/0 | 174/1 | 2025-12-31 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 174/0, 174/1 |  | 174/0, 174/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 174/1-175/0 | ta325¦174/1¦175/0 | Alam Construction | 174/1 | 175/0 | 2026-01-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 174/1, 175/0 |  | 174/1, 175/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 159/2-160/0 | ta325¦159/2¦160/0 | Enamul Haque | 159/2 | 160/0 | 2025-12-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 159/2, 160/0 |  | 159/2, 160/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 206/0-208/0 | ta325¦206/0¦208/0 | Ramavat Electricals 2 | 206/0 | 208/0 | 2025-12-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 206/0, 208/0 |  | 206/0, 208/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 216/0-217/0 | ta325¦216/0¦217/0 | Ramavat Electricals 1 | 216/0 | 217/0 | 2026-01-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 216/0, 217/0 |  | 216/0, 217/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 185/0-186/0 | ta325¦185/0¦186/0 | Alam Construction | 185/0 | 186/0 | 2026-01-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 185/0, 186/0 |  | 185/0, 186/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 186/0-187/0 | ta325¦186/0¦187/0 | Dharmendra 2 | 186/0 | 187/0 | 2026-01-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 186/0, 187/0 |  | 186/0, 187/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 215/0-215/1 | ta325¦215/0¦215/1 | Ramavat Electricals 1&2 | 215/0 | 215/1 | 2025-01-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 215/0, 215/1 |  | 215/0, 215/1 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 215/1-216/0 | ta325¦215/1¦216/0 | Kudus Ali | 215/1 | 216/0 | 2025-01-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 215/1, 216/0 |  | 215/1, 216/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 166/0-167/0 | ta325¦166/0¦167/0 | Muni bibi / Enamul / Alam / Rafikul | 166/0 | 167/0 | 2026-01-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 166/0, 167/0 |  | 166/0, 167/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 101/0-102/0 | ta325¦101/0¦102/0 | Kudus Ali 2 | 101/0 | 102/0 | 2026-01-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 101/0, 102/0 |  | 101/0, 102/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 102/0-103/0 | ta325¦102/0¦103/0 | Modina India 1 | 102/0 | 103/0 | 2026-01-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 102/0, 103/0 |  | 102/0, 103/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 103/0-104/0 | ta325¦103/0¦104/0 | Muslehuddin | 103/0 | 104/0 | 2026-01-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 103/0, 104/0 |  | 103/0, 104/0 |  | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 104/0-105/0 | ta325¦104/0¦105/0 | Dharmendra 2 | 104/0 | 105/0 | 2026-01-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 104/0, 105/0 |  | 104/0, 105/0 |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 34-35 | ta413¦34¦35 |  | AP-34 | AP-35 | 2025-02-21 | 2025-02-23 | -2 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 34, 35 |  | 34, 35 |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 37A/0-38/0 | ta413¦37A/0¦38/0 |  | 37A/0 | AP-38/0 | 2025-03-17 | 2025-04-11 | -25 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 37A/0, 38/0 | 37A/0, 38/0 |  |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 38-39 | ta413¦38¦39 |  | AP-38 | AP-39 | 2025-03-29 | 2025-04-11 | -13 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 38, 39 |  | 38, 39 |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 39-40 | ta413¦39¦40 |  | AP-39 | AP-40 | 2025-04-25 | 2025-04-30 | -5 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 39, 40 |  | 39, 40 |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 7-7A | ta413¦7¦7A |  | AP-7 | AP-7A | 2025-08-27 | 2025-07-31 | 27 | 27 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 7, 7A |  | 7, 7A |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 7A-8 | ta413¦7A¦8 |  | AP-7A | AP-8 | 2025-09-12 | 2025-02-14 | 210 | 210 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 7A, 8 |  | 7A, 8 |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 8-8A | ta413¦8¦8A |  | AP-8 | AP-8A | 2025-10-05 | 2025-08-14 | 52 | 52 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 8, 8A |  | 8, 8A |  | FALSE
TA 413 |  |  |  |  | TA 413 | 4xx | TA |  | Unassigned | 8A-9/0 | ta413¦8A¦9/0 |  | AP-8A | AP-9/0 | 2025-10-03 | 2025-09-06 | 27 | 27 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 8A, 9/0 | 9/0 | 8A |  | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 6-7 | ta413¦6¦7 |  | AP-6 | AP-7 | 2025-11-19 | 2025-09-06 | 74 | 74 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 6, 7 |  | 6, 7 |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 5A-6 | ta413¦5A¦6 |  | AP-5A | AP-6 | 2025-11-05 | 2025-09-01 | 65 | 65 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 5A, 6 |  | 5A, 6 |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 5-5A | ta413¦5¦5A |  | AP-5 | AP-5A | 2025-12-07 | 2025-09-30 | 68 | 68 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 5, 5A |  | 5, 5A |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 4A-5/0 | ta413¦4A¦5/0 |  | AP-4A | AP-5/0 | 2025-12-15 | 2025-09-30 | 76 | 76 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 4A, 5/0 | 5/0 | 4A |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 4-4A/0 | ta413¦4¦4A/0 |  | AP-4 | AP4A/0 | 2025-12-27 | 2025-10-12 | 76 | 76 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 4, 4A/0 | 4A/0 | 4 |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 33-34 | ta413¦33¦34 |  | AP-33 | AP-34 | 2026-01-07 | 2025-09-20 | 109 | 109 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 33, 34 |  | 33, 34 |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 3B/0-4/0 | ta413¦3B/0¦4/0 |  | AP3B/0 | AP4/0 | 2026-01-14 | 2025-11-08 | 67 | 67 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3B/0, 4/0 | 3B/0, 4/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 32A-33 | ta413¦32A¦33 |  | AP-32A | AP-33 | 2026-01-16 | 2025-09-20 | 118 | 118 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 32A, 33 |  | 32A, 33 |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 32/0-32A/0 | ta413¦32/0¦32A/0 |  | AP32/0 | AP32A/0 | 2026-01-25 | 2025-09-14 | 133 | 133 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 32/0, 32A/0 | 32/0, 32A/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 2A/0-3A/0 | ta413¦2A/0¦3A/0 |  | 2A/0 | 3A/0 | 2026-02-18 | 2026-01-25 | 24 | 24 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 2A/0, 3A/0 | 2A/0, 3A/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 3A/0-3B/0 | ta413¦3A/0¦3B/0 |  | 3A/0 | 3B/0 | 2026-02-08 | 2025-10-26 | 105 | 105 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3A/0, 3B/0 | 3A/0, 3B/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 1/0-2A/0 | ta413¦1/0¦2A/0 |  | 1/0 | 2A/0 | 2026-02-14 | 2026-01-25 | 20 | 20 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1/0, 2A/0 | 1/0, 2A/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 31/0-32/0 | ta413¦31/0¦32/0 |  | 31/0 | 32/0 | 2026-02-10 | 2025-09-21 | 142 | 142 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 31/0, 32/0 | 31/0, 32/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 30/0-31/0 | ta413¦30/0¦31/0 |  | 30/0 | 31/0 | 2026-02-27 | 2025-12-26 | 63 | 63 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 30/0, 31/0 | 30/0, 31/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 9/0-10/0 | ta413¦9/0¦10/0 |  | 9/0 | 10/0 | 2026-03-28 | 2025-12-12 | 106 | 106 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/0, 10/0 | 9/0, 10/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29A/0-30/0 | ta413¦29A/0¦30/0 |  | 29A/0 | 30/0 | 2026-04-22 | 2026-01-06 | 106 | 106 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29A/0, 30/0 | 29A/0, 30/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 10/0-11/0 | ta413¦10/0¦11/0 |  | 10/0 | 11/0 | 2026-04-07 | 2025-11-26 | 132 | 132 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 10/0, 11/0 | 10/0, 11/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29/0-29A/0 | ta413¦29/0¦29A/0 |  | 29/0 | 29A/0 | 2026-05-08 | 2025-12-20 | 139 | 139 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29/0, 29A/0 | 29/0, 29A/0 |  |  | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 27/0-28/0 | ta413¦27/0¦28/0 |  | 27/0 | 28/0 | 2026-05-20 | 2025-12-14 | 157 | 157 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 27/0, 28/0 | 27/0, 28/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Complete | 120/0-121/0 | ta414¦120/0¦121/0 | Enamul Haque | 120/0 | 121/0 | 2026-05-03 | 2026-04-19 | 14 | 14 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 | 120/0, 121/0, 120/1, 120/2, 120/3, 120/4, 120/5, 120/6, 120/7 |  | 120/1,120/2,120/3,120/4,120/5,120/6,120/7 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 175/0-175/1 | ta414¦175/0¦175/1 | Alam Construction | 175/0 | 175/1 | 2026-05-02 | 2026-01-15 | 107 | 107 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 175/0, 175/1 | 175/0, 175/1 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 175/1-176/0 | ta414¦175/1¦176/0 | Maa Singhvahini | 175/1 | 176/0 | 2026-04-06 | 2026-01-06 | 90 | 90 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 175/1, 176/0 | 175/1, 176/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 176/0-177/0 | ta414¦176/0¦177/0 | Alam Construction | 176/0 | 177/0 | 2026-04-24 | 2026-02-20 | 63 | 63 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 176/0, 177/0, 176/1, 176/2 | 176/0, 177/0, 176/1, 176/2 |  | 176/1,176/2 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 177/0-178/0 | ta414¦177/0¦178/0 | Sanjay singh 2 | 177/0 | 178/0 | 2026-05-15 | 2026-04-04 | 41 | 41 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 177/0, 178/0 | 177/0, 178/0 |  |  | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 180/2-182/0 | ta414¦180/2¦182/0 | Alam Construction | 180/2 | 182/0 | 2026-04-06 | 2026-02-13 | 52 | 52 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 | 180/2, 182/0, 180/3, 180/4, 180/5, 180/6, 180/7 |  | 180/3,180/4,180/5,180/6,180/7 | TRUE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 182/0-183/0 | ta414¦182/0¦183/0 | Sanjay Singh | 182/0 | 183/0 | 2026-04-05 | 2026-01-29 | 66 | 66 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 182/0, 183/0 | 182/0, 183/0 |  |  | TRUE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Complete | 183/0-184/0 | ta414¦183/0¦184/0 | Alam Construction | 183/0 | 184/0 | 2026-04-18 | 2026-03-21 | 28 | 28 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 183/0, 184/0, 183/1, 183/2, 183/3 | 183/0, 184/0, 183/1, 183/2, 183/3 |  | 183/1,183/2,183/3 | FALSE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Complete | 184/0-185/0 | ta414¦184/0¦185/0 |  | 184/0 | 185/0 | 2026-05-06 | 2026-04-20 | 16 | 16 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 184/0, 185/0 | 184/0, 185/0 |  |  | FALSE
TA 414 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Complete | 198/0-199/0 | ta414¦198/0¦199/0 |  | 198/0 | 199/0 | 2026-04-17 | 2026-02-11 | 65 | 65 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 198/0, 199/0 | 198/0, 199/0 |  |  | TRUE
TA 414 |  |  |  |  | TA 414 | 4xx | TA |  | Complete | 245/0-246/0 | ta414¦245/0¦246/0 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 2026-04-11 | 2026-02-25 | 45 | 45 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 245/0, 246/0, 245/1 | 245/0, 246/0, 245/1 |  | 245/1 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 7/0-8/0 | ta416¦7/0¦8/0 | ANARUL ISLAM | AP7/0 | AP8/0 | 2025-05-03 | 2025-03-27 | 37 | 37 | LOCATION_NOS | FALSE | OK |  | 13 | 13 | 0 | 7/0, 8/0, 7/1, 7/2, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 7/10, 7/11 | 7/0, 8/0, 7/1, 7/2, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 7/10, 7/11 |  | 7/0,1,2,3,4,5,6,7,8,9,10,11,8/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 6/0-7/0 | ta416¦6/0¦7/0 | ANARUL ISLAM | AP6/0 | AP7/0 | 2025-05-14 | 2025-03-29 | 46 | 46 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 6/0, 7/0, 6/1, 6/2 | 6/0, 7/0, 6/1, 6/2 |  | 6/0,1,2,7/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 35/0-36/0 | ta416¦35/0¦36/0 | S K INFRA | AP35/0 | AP36/0 | 2025-05-18 | 2025-04-14 | 34 | 34 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 35/0, 36/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9 | 35/0, 36/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9 |  | 35/0,1,2,3,4,5,6,7,8,9,36/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 8/0-8A/0 | ta416¦8/0¦8A/0 | ANARUL ISLAM | AP8/0 | AP8A/0 | 2025-05-24 | 2025-04-30 | 24 | 24 | LOCATION_NOS | FALSE | OK |  | 6 | 6 | 0 | 8/0, 8A/0, 8/1, 8/2, 8/3, 8/4 | 8/0, 8A/0, 8/1, 8/2, 8/3, 8/4 |  | 8/0,1,2,3,4,8A/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 31/0-32/0 | ta416¦31/0¦32/0 | S K INFRA | AP31/0 | AP32/0 | 2025-06-02 | 2025-04-21 | 42 | 42 | LOCATION_NOS | FALSE | OK |  | 12 | 12 | 0 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5, 31/6, 31/7, 31/8, 31/9, 31/10 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5, 31/6, 31/7, 31/8, 31/9, 31/10 |  | 31/0,1,2,3,4,5,6,7,8,9,10,32/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 8A/0-8B/0 | ta416¦8A/0¦8B/0 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 2025-06-17 | 2025-05-14 | 34 | 34 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 8A/0, 8B/0 | 8A/0, 8B/0 |  | 8A,8B | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 32/0-33/0 | ta416¦32/0¦33/0 | S K INFRA | AP32/0 | AP33/0 | 2025-06-18 | 2025-04-22 | 57 | 57 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 32/0, 33/0 | 32/0, 33/0 |  | 32/0,33/0 | FALSE
TA 416 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 8B/0-9/0 | ta416¦8B/0¦9/0 | ANARUL ISLAM | AP8B/0 | AP9/0 | 2025-07-15 | 2025-05-14 | 62 | 62 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 8B/0, 9/0, 8B/1, 8B/2, 8B/3, 8B/4, 8B/5 | 8B/0, 9/0, 8B/1, 8B/2, 8B/3, 8B/4, 8B/5 |  | 8B/0,1,2,3,4,5,9/0 | TRUE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 33/0-34/0 | ta416¦33/0¦34/0 | S K INFRA | AP33/0 | AP34/0 | 2025-07-17 | 2025-06-10 | 37 | 37 | LOCATION_NOS | FALSE | OK |  | 13 | 13 | 0 | 33/0, 34/0, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/7, 33/8, 33/9, 33/10, 33/11 | 33/0, 34/0, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/7, 33/8, 33/9, 33/10, 33/11 |  | 33/0,1,2,3,4,5,6,7,8,9,10,11,34/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 5/0-6/0 | ta416¦5/0¦6/0 | ANARUL ISLAM | AP5/0 | AP6/0 | 2025-08-05 | 2025-03-29 | 129 | 129 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 5/0, 6/0, 5/1 | 5/0, 6/0, 5/1 |  | 5/0,1,6/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 9/0-10/0 | ta416¦9/0¦10/0 | ANARUL ISLAM | AP9/0 | AP10/0 | 2025-08-11 | 2025-04-28 | 105 | 105 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 9/0, 10/0 | 9/0, 10/0 |  | 9/0,10/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 34/0-35/0 | ta416¦34/0¦35/0 | S K INFRA | AP34/0 | AP35/0 | 2025-08-11 | 2025-06-18 | 54 | 54 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 34/0, 35/0, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 34/7 | 34/0, 35/0, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 34/7 |  | 34/0,1,2,3,4,5,6,7,35/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 4/0-5/0 | ta416¦4/0¦5/0 | ANARUL ISLAM | AP4/0 | AP5/0 | 2025-08-22 | 2025-05-11 | 103 | 103 | LOCATION_NOS | FALSE | OK |  | 12 | 12 | 0 | 4/0, 5/0, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10 | 4/0, 5/0, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10 |  | 4/0,1,2,3,4,5,6,7,8,9,10,5/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 14/0-15/0 | ta416¦14/0¦15/0 | ANARUL ISLAM | AP14/0 | AP15/0 | 2025-09-05 | 2025-06-30 | 67 | 67 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 14/8 | 14/0, 15/0, 14/1, 14/2, 14/3, 14/4, 14/5, 14/6, 14/7, 14/8 |  | 14/0,1,2,3,4,5,6,7,8,15/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 36/0-37/0 | ta416¦36/0¦37/0 | S K INFRA | AP36/0 | AP37/0 | 2025-09-05 | 2025-10-31 | -56 |  | LOCATION_NOS | FALSE | OK |  | 14 | 14 | 0 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7, 36/8, 36/9, 36/10, 36/11, 36/12 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7, 36/8, 36/9, 36/10, 36/11, 36/12 |  | 36/0,1,2,3,4,5,6,7,8,9,10,11,12,37/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 3/0-4/0 | ta416¦3/0¦4/0 | ANARUL ISLAM | AP3/0 | AP4/0 | 2025-09-15 | 2025-06-23 | 84 | 84 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 3/0, 4/0 | 3/0, 4/0 |  | 3/0,4/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 30/0-31/0 | ta416¦30/0¦31/0 | S K INFRA | AP30/0 | AP31/0 | 2025-09-21 | 2025-06-21 | 92 | 92 | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5, 30/6 |  | 30/0,1,2,3,4,5,6,31/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 20/0-21/0 | ta416¦20/0¦21/0 | J PG CON | AP20/0 | AP21/0 | 2025-09-21 | 2025-04-22 | 152 | 152 | LOCATION_NOS | FALSE | OK |  | 14 | 14 | 0 | 20/0, 21/0, 20/1, 20/2, 20/3, 20/4, 20/5, 20/6, 20/7, 20/8, 20/9, 20/10, 20/11, 20/12 | 20/0, 21/0, 20/1, 20/2, 20/3, 20/4, 20/5, 20/6, 20/7, 20/8, 20/9, 20/10, 20/11, 20/12 |  | 20/0,1,2,3,4,5,6,7,8,9,10,11,12,21/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 12/0-13/0 | ta416¦12/0¦13/0 | ANARUL ISLAM | AP12/0 | AP13/0 | 2025-10-12 | 2025-09-02 | 40 | 40 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9 |  | 12/0,1,2,3,4,5,6,7,8,9,13/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 39/0-40/0 | ta416¦39/0¦40/0 | S K INFRA | AP39/0 | AP40/0 | 2025-10-14 | 2025-06-30 | 106 | 106 | LOCATION_NOS | FALSE | OK |  | 12 | 12 | 0 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10 |  | 39/0,1,2,3,4,5,6,7,8,9,10,40/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 21/0-22/0 | ta416¦21/0¦22/0 | J PG CON | AP21/0 | AP22/0 | 2025-10-24 | 2025-07-07 | 109 | 109 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 21/0, 22/0, 21/1, 21/2, 21/3 | 21/0, 22/0, 21/1, 21/2, 21/3 |  | 21/0,1,2,3,22/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 13/0-14/0 | ta416¦13/0¦14/0 | ANARUL ISLAM | AP13/0 | AP14/0 | 2025-11-03 | 2025-08-11 | 84 | 84 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 13/0, 14/0 | 13/0, 14/0 |  | 13/0,14/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 38/0-39/0 | ta416¦38/0¦39/0 | S K INFRA | AP38/0 | AP39/0 | 2025-11-02 | 2025-10-26 | 7 | 7 | LOCATION_NOS | FALSE | OK |  | 13 | 13 | 0 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11 |  | 38/0,1,2,3,4,5,6,7,8,9,10,11,39/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 19/0-20/0 | ta416¦19/0¦20/0 | J PG CON | AP19/0 | AP20/0 | 2025-11-06 | 2025-09-24 | 43 | 43 | LOCATION_NOS | FALSE | OK |  | 14 | 14 | 0 | 19/0, 20/0, 19/1, 19/2, 19/3, 19/4, 19/5, 19/6, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12 | 19/0, 20/0, 19/1, 19/2, 19/3, 19/4, 19/5, 19/6, 19/7, 19/8, 19/9, 19/10, 19/11, 19/12 |  | 19/0,1,2,3,4,5,6,7,8,9,10,11,12,20/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 17/0-18/0 | ta416¦17/0¦18/0 | ANARUL ISLAM | AP17/0 | AP18/0 | 2025-11-17 | 2025-09-28 | 50 | 50 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 17/0, 18/0, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8 | 17/0, 18/0, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8 |  | 17/0,1,2,3,4,5,6,7,8,18/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 18/0-19/0 | ta416¦18/0¦19/0 | J PG CON | AP18/0 | AP19/0 | 2025-11-21 | 2025-09-24 | 58 | 58 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 18/0, 19/0 | 18/0, 19/0 |  | 18/0,19/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 15/0-16/0 | ta416¦15/0¦16/0 | ANARUL ISLAM | AP15/0 | AP16/0 | 2025-11-22 | 2025-09-14 | 69 | 69 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 15/0, 16/0 | 15/0, 16/0 |  | 15/0,16/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 10/0-11/0 | ta416¦10/0¦11/0 | ANARUL ISLAM | AP10/0 | AP11/0 | 2025-12-02 | 2025-09-14 | 79 | 79 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 10/0, 11/0, 10/1 | 10/0, 11/0, 10/1 |  | 10/0,1,11/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 37/0-38/0 | ta416¦37/0¦38/0 | S K INFRA | AP37/0 | AP38/0 | 2025-12-05 | 2025-10-31 | 35 | 35 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 37/0, 38/0 | 37/0, 38/0 |  | 37/0,38/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 11/0-12/0 | ta416¦11/0¦12/0 | ANARUL ISLAM | AP11/0 | AP12/0 | 2025-12-08 | 2025-09-14 | 85 | 85 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 11/0, 12/0 | 11/0, 12/0 |  | 11/0,12/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 1/0-2/0 | ta416¦1/0¦2/0 | AE Solution | AP1/0 | AP2/0 | 2025-12-17 | 2025-09-21 | 87 | 87 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 1/0, 2/0 | 1/0, 2/0 |  | 1/0,2/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 0/0-1/0 | ta416¦0/0¦1/0 | ANARUL ISLAM | AP0/0 | AP1/0 | 2025-12-21 | 2025-10-28 | 54 | 54 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 0/0, 1/0, 0/1, 0/2, 0/3, 0/4, 2/0 | 0/0, 1/0, 0/1, 0/2, 0/3, 0/4, 2/0 |  | 0/0,1,2,3,4,2/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 24/0-25/0 | ta416¦24/0¦25/0 | AE Solution | AP24/0 | AP25/0 | 2025-12-24 | 2025-09-29 | 86 | 86 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 24/0, 25/0 | 24/0, 25/0 |  | 24/0,25/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 23/0-24/0 | ta416¦23/0¦24/0 | Jahangir(Company) | AP23/0 | AP24/0 | 2025-12-26 | 2025-12-14 | 12 | 12 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 23/0, 24/0, 23/1, 23/2, 23/3, 23/4, 23/5 | 23/0, 24/0, 23/1, 23/2, 23/3, 23/4, 23/5 |  | 23/0,1,2,3,4,5,24/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 40/0-41/0 | ta416¦40/0¦41/0 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 2025-12-24 | 2025-08-08 | 138 | 138 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 40/0, 41/0 | 40/0, 41/0 |  | 40/0,41/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 16/0-17/0 | ta416¦16/0¦17/0 | Ramawat-Hot line | AP16/0 | AP17/0 | 2025-12-31 | 2025-09-28 | 94 | 94 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 16/0, 17/0 | 16/0, 17/0 |  | 16/0,17/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 2/0-3/0 | ta416¦2/0¦3/0 | ANARUL ISLAM | AP2/0 | AP3/0 | 2026-01-13 | 2025-11-13 | 61 | 61 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4, 2/5, 2/6, 2/7, 2/8 |  | 2/0,1,2,3,4,5,6,7,8,2/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 26/0-27/0 | ta416¦26/0¦27/0 | AE Solution(Company) | AP26/0 | AP27/0 | 2026-01-09 | 2025-10-12 | 89 | 89 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 26/0, 27/0 | 26/0, 27/0 |  | 26/0,27/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 25/0-26/0 | ta416¦25/0¦26/0 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 2026-01-23 | 2025-09-29 | 116 | 116 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 25/0, 26/0, 25/1, 25/2, 25/3 | 25/0, 26/0, 25/1, 25/2, 25/3 |  | 25/0,1,2,3,26/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 42/0-43/0 | ta416¦42/0¦43/0 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 2026-01-25 | 2025-10-14 | 103 | 103 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 42/0, 43/0 | 42/0, 43/0 |  | 42/0,43/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 29/0-30/0 | ta416¦29/0¦30/0 | ANARUL ISLAM | AP29/0 | AP30/0 | 2026-03-16 | 2025-09-22 | 175 | 175 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 29/0, 30/0 | 29/0, 30/0 |  | 29/0,30/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 41/0-42/0 | ta416¦41/0¦42/0 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 2026-02-03 | 2025-10-14 | 112 | 112 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 41/0, 42/0, 41/1, 41/2 | 41/0, 42/0, 41/1, 41/2 |  | 41/0,1,2,42/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 28/0-29/0 | ta416¦28/0¦29/0 | Jahangir(Company) | AP28/0 | AP29/0 | 2026-02-05 | 2025-09-22 | 136 | 136 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 28/0, 29/0, 28/1 | 28/0, 29/0, 28/1 |  | 28/0,1,29/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 22/0-22A/0 | ta416¦22/0¦22A/0 | ANARUL ISLAM | AP22/0 | AP22A/0 | 2026-02-17 | 2026-01-17 | 31 | 31 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 22/0, 22A/0 | 22/0, 22A/0 |  | 22/0,22/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 27/0-28/0 | ta416¦27/0¦28/0 | Bhola+Sing bahini(Company) | AP27/0 | AP28/0 | 2026-02-11 | 2025-10-12 | 122 | 122 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 27/0, 28/0 | 27/0, 28/0 |  | 27/0,28/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 52/1-53/0 | ta416¦52/1¦53/0 | Astharul (company) | AP52/1 | AP53/0 | 2026-03-24 | 2025-12-24 | 90 | 90 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 52/1, 53/0, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7, 52/8, 52/9, 52/10 | 52/1, 53/0, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7, 52/8, 52/9, 52/10 |  | 52/1,2,3,4,5,6,7,8,9,10,53/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 46/0-47/0 | ta416¦46/0¦47/0 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 2026-02-14 | 2025-10-08 | 129 | 129 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 46/0, 47/0, 46/1, 46/2 | 46/0, 47/0, 46/1, 46/2 |  | 46/0,1,2,47/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 22A/0-23/0 | ta416¦22A/0¦23/0 | ANARUL ISLAM | AP22A/0 | AP23/0 | 2026-02-21 | 2026-01-17 | 35 | 35 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 22A/0, 23/0 | 22A/0, 23/0 |  | 22A/0,23/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 53/0-53A/0 | ta416¦53/0¦53A/0 | SADIK Con(company) | AP53/0 | AP53A/0 | 2026-02-25 | 2025-11-30 | 87 | 87 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 53/0, 53A/0, 53/1 | 53/0, 53A/0, 53/1 |  | 53/0,1,53A/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 45/0-46/0 | ta416¦45/0¦46/0 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 2026-02-22 | 2025-11-07 | 107 | 107 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 45/0, 46/0, 45/1, 45/2, 45/3 | 45/0, 46/0, 45/1, 45/2, 45/3 |  | 45/0,1,2,3,46/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 53A/0-54/0 | ta416¦53A/0¦54/0 | Jahangir(Company) | AP53A/0 | AP54/0 | 2026-03-10 | 2026-01-07 | 62 | 62 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 53A/0, 54/0, 53A/1, 53A/2, 53A/3, 53A/4, 53A/5, 53A/6, 53A/7 | 53A/0, 54/0, 53A/1, 53A/2, 53A/3, 53A/4, 53A/5, 53A/6, 53A/7 |  | 53A/0,1,2,3,4,5,6,7,54/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 52/0-52/1 | ta416¦52/0¦52/1 | Astharul (company) | AP52/0 | AP52/1 | 2026-03-10 | 2025-11-10 | 120 | 120 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 52/0, 52/1 | 52/0, 52/1 |  | 52/0,52/1 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 44/0-45/0 | ta416¦44/0¦45/0 | Dharmendra Hot line | AP44/0 | AP45/0 | 2026-03-12 | 2025-11-07 | 125 | 125 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 44/0, 45/0 | 44/0, 45/0 |  | 44/0,45/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 69A/0-70/0 | ta416¦69A/0¦70/0 | SADIK Con(company) | AP69A/0 | AP70/0 | 2026-03-12 | 2026-01-10 | 61 | 61 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 69A/0, 70/0 | 69A/0, 70/0 |  | 69A/0,70/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 70/0-Gantry | ta416¦70/0¦Gantry | SADIK Con(company) | AP70/0 | Gantry | 2026-03-12 | 2026-01-10 | 61 | 61 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: GANTRY/0 | 2 | 1 | 1 | 70/0, GANTRY | 70/0 | GANTRY | 70/0,Gantry/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 43/0-44/0 | ta416¦43/0¦44/0 | Anarul-2 | AP43/0 | AP44/0 | 2026-03-12 | 2025-09-06 | 187 | 187 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 43/0, 44/0 | 43/0, 44/0 |  | 43/0,44/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 66/0-67/0 | ta416¦66/0¦67/0 | Astharul (company) | AP66/0 | AP67/0 | 2026-03-19 | 2026-03-23 | -4 |  | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 66/0, 67/0, 66/1 | 66/0, 67/0, 66/1 |  | 66/0,1,67/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 69/0-69A | ta416¦69/0¦69A | SADIK Con(company) | AP69/0 | AP69A | 2026-03-19 | 2026-02-08 | 39 | 39 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 2 | 1 | 69/0, 69A, 69A/0 | 69/0, 69A/0 | 69A | 69/0,69A/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 65/0-66 | ta416¦65/0¦66 | Dharmendra Hot line | AP65/0 | AP66 | 2026-03-25 | 2025-12-19 | 96 | 96 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 2 | 1 | 65/0, 66, 66/0 | 65/0, 66/0 | 66 | 65/0,66/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 68/0-69/0 | ta416¦68/0¦69/0 | SADIK Con(company) | AP68/0 | AP69/0 | 2026-03-25 | 2026-02-08 | 45 | 45 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 68/0, 69/0 | 68/0, 69/0 |  | 68/0,69/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 67/0-68/0 | ta416¦67/0¦68/0 | Anarul-2 | AP67/0 | AP68/0 | 2026-03-28 | 2026-03-23 | 5 | 5 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 67/0, 68/0 | 67/0, 68/0 |  | 67/0,68/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 62/0-63/0 | ta416¦62/0¦63/0 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 2026-04-14 | 2025-12-04 | 131 | 131 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 62/0, 63/0 | 62/0, 63/0 |  | 62/0,63/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 54/0-55/0 | ta416¦54/0¦55/0 | Jahangir(Company) | AP54/0 | AP55/0 | 2026-04-02 | 2025-11-07 | 146 | 146 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 54/0, 55/0, 54/1, 54/2 | 54/0, 55/0, 54/1, 54/2 |  | 54/0,1,2,55/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 64/0-65/0 | ta416¦64/0¦65/0 | Astharul (company) | AP64/0 | AP65/0 | 2026-04-10 | 2025-09-22 | 200 | 200 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 64/0, 65/0 | 64/0, 65/0 |  | 64/0,65/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 55/0-56/0 | ta416¦55/0¦56/0 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 2026-04-12 | 2025-11-17 | 146 | 146 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 55/0, 56/0, 55/1 | 55/0, 56/0, 55/1 |  | 55/0,1,56/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 56/0-57/0 | ta416¦56/0¦57/0 | ANARUL ISLAM | AP56/0 | AP57/0 | 2026-05-10 | 2026-03-09 | 62 | 62 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 | 56/0, 57/0, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 56/7, 56/8 |  | 56/0,1,2,3,4,5,6,7,8,57/0 | FALSE
TA 416 |  |  |  |  | TA 416 | 4xx | TA |  | Ready | 57/0-58/0 | ta416¦57/0¦58/0 | ANARUL ISLAM | AP57/0 | AP58/0 | 2026-05-17 | 2026-01-17 | 120 | 120 | LOCATION_NOS | FALSE | OK |  | 3 | 3 | 0 | 57/0, 58/0, 57/1 | 57/0, 58/0, 57/1 |  | 57/0,1,58/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 32-33 | ta418¦32¦33 | Ramawat | AP32 | AP33 | 2026-02-16 | 2025-11-07 | 101 | 101 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 4 | 2 | 2 | 32, 33, 32/0, 33/0 | 32/0, 33/0 | 32, 33 | 32/0, 33/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 33-33/5 | ta418¦33¦33/5 | SUFIYAN / Haque | AP33 | 33/5 | 2026-02-05 | 2025-11-21 | 76 | 76 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 7 | 6 | 1 | 33, 33/5, 33/0, 33/1, 33/2, 33/3, 33/4 | 33/5, 33/0, 33/1, 33/2, 33/3, 33/4 | 33 | 33/0, 33/1, 33/2, 33/3, 33/4, 33/5 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 33/5-33/6 | ta418¦33/5¦33/6 | Ramawat | 33/5 | 33/6 | 2026-01-19 | 2025-06-24 | 209 | 209 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 33/5, 33/6 | 33/5, 33/6 |  | 33/5, 33/6 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 33/6-34/0 | ta418¦33/6¦34/0 | SUFIYAN / Haque | 33/6 | 34/0 | 2026-01-18 | 2025-06-24 | 208 | 208 | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 33/6, 34/0, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12 | 33/6, 34/0, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12 |  | 33/6, 33/7, 33/8, 33/9, 33/10, 33/11, 33/12, 34/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 34/0-35 | ta418¦34/0¦35 | SUFIYAN | 34/0 | AP35 | 2025-11-26 | 2025-05-28 | 182 | 182 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 7 | 6 | 1 | 34/0, 35, 34/1, 34/2, 34/3, 34/4, 35/0 | 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 | 35 | 34/0, 34/1, 34/2, 34/3, 34/4, 35/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 35-36 | ta418¦35¦36 | SUFIYAN | AP35 | AP36 | 2025-11-07 | 2025-08-17 | 82 | 82 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 15 | 12 | 3 | 35, 36, 35/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/6, 35/7, 35/8, 35/9, 35/10, 35/11, 36/0 | 35/0, 35/1, 35/2, 35/3, 35/4, 35/5, 35/7, 35/8, 35/9, 35/10, 35/11, 36/0 | 35, 36, 35/6 | 35/0, 35/1, 35/2,35/3,35/4, 35/5, 35/6,35/7,35/8, 35/9, 35/10,35/11,36/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 36-36/1 | ta418¦36¦36/1 | SUFIYAN | AP36 | 36/1 | 2025-11-01 | 2025-08-19 | 74 | 74 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 2 | 1 | 36, 36/1, 36/0 | 36/1, 36/0 | 36 | 36/0, 36/1 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 37/0-38 | ta418¦37/0¦38 | SUFIYAN | 37/0 | AP38 | 2026-05-10 | 2026-04-01 | 39 | 39 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 5 | 4 | 1 | 37/0, 38, 37/1, 37/2, 38/0 | 37/0, 37/1, 37/2, 38/0 | 38 | 37/0, 37/1, 37/2, 38/0 | FALSE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 38-39 | ta418¦38¦39 | SUFIYAN | AP38 | AP39 | 2026-05-20 | 2026-04-01 | 49 | 49 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 6 | 4 | 2 | 38, 39, 38/0, 38/1, 38/2, 39/0 | 38/0, 38/1, 38/2, 39/0 | 38, 39 | 38/0, 38/1, 38/2, 39/0 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 39-40 | ta418¦39¦40 | Ramawat | AP39 | AP40 | 2026-02-07 | 2025-11-29 | 70 | 70 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 4 | 2 | 2 | 39, 40, 39/0, 40/0 | 39/0, 40/0 | 39, 40 | 39/0,40/0 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 40-41 | ta418¦40¦41 | SUFIYAN / Haque | AP40 | AP41 | 2025-12-20 | 2025-07-21 | 152 | 152 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 9 | 7 | 2 | 40, 41, 40/0, 40/1, 40/2, 40/3, 40/4, 40/5, 41/0 | 40/0, 40/1, 40/2, 40/3, 40/4, 40/5, 41/0 | 40, 41 | 40/0,40/1,40/2,40/3,40/4,40/5,41/0 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 41-42 | ta418¦41¦42 | SUFIYAN / Haque | AP41 | AP42 | 2025-10-03 | 2025-08-06 | 58 | 58 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 9 | 7 | 2 | 41, 42, 41/0, 41/1, 41/2, 41/3, 41/4, 41/5, 42/0 | 41/0, 41/1, 41/2, 41/3, 41/4, 41/5, 42/0 | 41, 42 | 41/0,41/1,41/2,41/3,41/4,41/5,42/0 | TRUE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 42-43 | ta418¦42¦43 | SUFIYAN | AP42 | AP43 | 2025-09-25 | 2025-04-10 | 168 | 168 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 6 | 4 | 2 | 42, 43, 42/0, 42/1, 42/2, 43/0 | 42/0, 42/1, 42/2, 43/0 | 42, 43 | 42/0,42/1,42/2,43/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 43-44 | ta418¦43¦44 | SUFIYAN | AP43 | AP44 | 2026-03-07 | 2026-02-28 | 7 | 7 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 7 | 5 | 2 | 43, 44, 43/0, 43/1, 43/2, 43/3, 44/0 | 43/0, 43/1, 43/2, 43/3, 44/0 | 43, 44 | 43/0,43/1,43/2,43/3,44/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 44-45 | ta418¦44¦45 | Haque | AP44 | AP45 | 2026-03-07 | 2025-12-02 | 95 | 95 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 5 | 3 | 2 | 44, 45, 44/0, 44/1, 45/0 | 44/0, 44/1, 45/0 | 44, 45 | 44/0,44/1,45/0 | FALSE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 45-45/1 | ta418¦45¦45/1 | Ramawat | AP45 | 45/1 | 2026-03-06 | 2025-03-28 | 343 | 343 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 2 | 1 | 45, 45/1, 45/0 | 45/1, 45/0 | 45 | 45/0, 45/1 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 45/1-46 | ta418¦45/1¦46 | Haque | 45/1 | AP46 | 2026-02-28 | 2025-09-30 | 151 | 151 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 5 | 4 | 1 | 45/1, 46, 45/0, 45/2, 46/0 | 45/1, 45/0, 45/2, 46/0 | 46 | 45/0,45/1,45/2,46/0 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 55-56 | ta418¦55¦56 | SUFIYAN | AP55 | AP56 | 2026-04-28 | 2026-01-27 | 91 | 91 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 10 | 8 | 2 | 55, 56, 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55/0, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 56/0 | 55, 56 | 55/0,55/1,55/2,55/3,55/4,55/5,55/6,56/0 | TRUE
TA 418 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 56-56/3 | ta418¦56¦56/3 | SUFIYAN | AP56 | 56/3 | 2026-03-26 | 2025-12-26 | 90 | 90 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 5 | 4 | 1 | 56, 56/3, 56/0, 56/1, 56/2 | 56/3, 56/0, 56/1, 56/2 | 56 | 56/0,56/1,56/2,56/3 | TRUE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 61/0-62/0 | ta418¦61/0¦62/0 | SUFIYAN | 61/0 | 62/0 | 2026-04-08 | 2025-09-25 | 195 | 195 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 61/0, 62/0 | 61/0, 62/0 |  | 61/0,62/0 | FALSE
TA 418 |  |  |  |  | TA 418 | 4xx | TA |  | Ready | 63/0-GNTY | ta418¦63/0¦GNTY | SUFIYAN | 63/0 | GNTY | 2026-04-15 | 2026-02-17 | 57 | 57 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 1 | 2 | 63/0, GNTY, 63/GNTY | 63/0 | GNTY, 63/GNTY | 63/0,GNTY | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 23/0-24/0 | ta421¦23/0¦24/0 | M R Constructions | 23/0 | 24/0 | 2025-02-12 | 2024-11-26 | 78 | 78 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3&24/0 | 4 | 4 | 0 | 23/0, 24/0, 23/1, 23/2 | 23/0, 24/0, 23/1, 23/2 |  | 23/0,1,2,3 & 24/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 24/0-25/0 | ta421¦24/0¦25/0 | M R Constructions | 24/0 | 25/0 | 2025-02-24 | 2024-12-11 | 75 | 75 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 8&25/0 | 9 | 9 | 0 | 24/0, 25/0, 24/1, 24/2, 24/3, 24/4, 24/5, 24/6, 24/7 | 24/0, 25/0, 24/1, 24/2, 24/3, 24/4, 24/5, 24/6, 24/7 |  | 24/0,1,2,3,4,5,6,7,8 & 25/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 25/0-26/0 | ta421¦25/0¦26/0 | M R Constructions | 25/0 | 26/0 | 2025-03-08 | 2025-02-25 | 11 | 11 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 5&26/0 | 6 | 6 | 0 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 | 25/0, 26/0, 25/1, 25/2, 25/3, 25/4 |  | 25/0,1,2,3,4,5 & 26/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 26/0-27/0 | ta421¦26/0¦27/0 | M R Constructions | 26/0 | 27/0 | 2025-03-23 | 2024-11-30 | 113 | 113 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 4&27/0 | 5 | 5 | 0 | 26/0, 27/0, 26/1, 26/2, 26/3 | 26/0, 27/0, 26/1, 26/2, 26/3 |  | 26/0,1,2,3,4 & 27/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 22/0-23/0 | ta421¦22/0¦23/0 | M R Constructions | 22/0 | 23/0 | 2025-04-07 | 2025-03-12 | 26 | 26 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 5&23/0 | 6 | 6 | 0 | 22/0, 23/0, 22/1, 22/2, 22/3, 22/4 | 22/0, 23/0, 22/1, 22/2, 22/3, 22/4 |  | 22/0,1,2,3,4,5 & 23/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 29/0-29/9 | ta421¦29/0¦29/9 | M R Constructions | 29/0 | 29/9 | 2025-05-05 | 2025-06-18 | -44 |  | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 29/0, 29/9, 29/1, 29/2, 29/3, 29/4, 29/5, 29/6, 29/7, 29/8 | 29/0, 29/9, 29/1, 29/2, 29/3, 29/4, 29/5, 29/6, 29/7, 29/8 |  | 29/0,1,2,3,4,5,6,7,8,9 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 32/0-33/0 | ta421¦32/0¦33/0 | M R Constructions | 32/0 | 33/0 | 2025-05-22 | 2025-04-09 | 43 | 43 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3&33/0 | 4 | 4 | 0 | 32/0, 33/0, 32/1, 32/2 | 32/0, 33/0, 32/1, 32/2 |  | 32/0,1,2,3 & 33/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 31/0-32/0 | ta421¦31/0¦32/0 | M R Constructions | 31/0 | 32/0 | 2025-06-12 | 2025-06-06 | 6 | 6 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 6&32/0 | 7 | 7 | 0 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5 | 31/0, 32/0, 31/1, 31/2, 31/3, 31/4, 31/5 |  | 31/0,1,2,3,4,5,6 & 32/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 30/0-31/0 | ta421¦30/0¦31/0 | M R Constructions | 30/0 | 31/0 | 2025-06-22 | 2025-06-11 | 11 | 11 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 6&31/0 | 7 | 7 | 0 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 | 30/0, 31/0, 30/1, 30/2, 30/3, 30/4, 30/5 |  | 30/0,1,2,3,4,5,6 & 31/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 29/9-30/0 | ta421¦29/9¦30/0 | M R Constructions | 29/9 | 30/0 | 2025-07-06 | 2025-06-18 | 18 | 18 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 29/9, 30/0 | 29/9, 30/0 |  | 29/9 & 30/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 21/0-22/0 | ta421¦21/0¦22/0 | M R Constructions | 21/0 | 22/0 | 2025-07-17 | 2025-06-19 | 28 | 28 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 9&22/0 | 10 | 10 | 0 | 21/0, 22/0, 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8 | 21/0, 22/0, 21/1, 21/2, 21/3, 21/4, 21/5, 21/6, 21/7, 21/8 |  | 21/0,1,2,3,4,5,6,7,8,9 & 22/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 20A/0-21/0 | ta421¦20A/0¦21/0 | M R Constructions | 20A/0 | 21/0 | 2025-08-23 | 2025-07-07 | 47 | 47 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 20A/0, 21/0 | 20A/0, 21/0 |  | 20A/0 & 21/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 20/0-20A/0 | ta421¦20/0¦20A/0 | M R Constructions | 20/0 | 20A/0 | 2025-08-22 | 2025-07-07 | 46 | 46 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 20/0, 20A/0 | 20/0, 20A/0 |  | 20/0 & 20A/0 | FALSE
TA 421 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 12/0-13/0 | ta421¦12/0¦13/0 | Nasiruddin | 12/0 | 13/0 | 2025-09-01 | 2025-08-29 | 3 | 3 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 11&13/0 | 12 | 12 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10 |  | 12/1,2,3,4,5,6,7,8,9,10,11 & 13/0 | TRUE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 10/0-11/0 | ta421¦10/0¦11/0 | Nasiruddin | 10/0 | 11/0 | 2025-09-28 | 2025-08-12 | 47 | 47 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 9&11/0 | 10 | 10 | 0 | 10/0, 11/0, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8 | 10/0, 11/0, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/7, 10/8 |  | 10/0,1,2,3,4,5,6,7,8,9 & 11/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 19/0-20/0 | ta421¦19/0¦20/0 | M R Constructions | 19/0 | 20/0 | 2025-09-15 | 2025-05-22 | 116 | 116 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3&20/0 | 4 | 4 | 0 | 19/0, 20/0, 19/1, 19/2 | 19/0, 20/0, 19/1, 19/2 |  | 19/0,1,2,3 & 20/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 18/0-19/0 | ta421¦18/0¦19/0 | M R Constructions | 18/0 | 19/0 | 2025-09-21 | 2025-05-22 | 122 | 122 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3&19/0 | 4 | 4 | 0 | 18/0, 19/0, 18/1, 18/2 | 18/0, 19/0, 18/1, 18/2 |  | 18/0,1,2,3 & 19/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 9/0-10/0 | ta421¦9/0¦10/0 | M R Constructions | 9/0 | 10/0 | 2025-10-16 | 2025-10-12 | 4 | 4 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 10&10/0 | 11 | 11 | 0 | 9/0, 10/0, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 9/9 | 9/0, 10/0, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 9/9 |  | 9/1,2,3,4,5,6,7,8,9,10 & 10/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 13/0-14/0 | ta421¦13/0¦14/0 | Nasiruddin | 13/0 | 14/0 | 2025-11-13 | 2025-07-13 | 123 | 123 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 11&14/0 | 12 | 12 | 0 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 13/7, 13/8, 13/9, 13/10 | 13/0, 14/0, 13/1, 13/2, 13/3, 13/4, 13/5, 13/6, 13/7, 13/8, 13/9, 13/10 |  | 13/0,1,2,3,4,5,6,7,8,9,10,11 & 14/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 11/0-12/0 | ta421¦11/0¦12/0 | Nasiruddin | 11/0 | 12/0 | 2025-12-03 | 2025-11-19 | 14 | 14 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 11&12/0 | 12 | 12 | 0 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10 |  | 11/0,1,2,3,4,5,6,7,8,9,10,11 & 12/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 17/0-18/0 | ta421¦17/0¦18/0 | M R Constructions | 17/0 | 18/0 | 2025-11-10 | 2025-06-04 | 159 | 159 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 3&18/0 | 4 | 4 | 0 | 17/0, 18/0, 17/1, 17/2 | 17/0, 18/0, 17/1, 17/2 |  | 17/0,1,2,3 & 18/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 14/0-15/0 | ta421¦14/0¦15/0 | Nasiruddin | 14/0 | 15/0 | 2025-12-15 | 2025-07-13 | 155 | 155 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 14/0, 15/0 | 14/0, 15/0 |  | 14/0 & 15/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 16/0-17/0 | ta421¦16/0¦17/0 | M R Constructions | 16/0 | 17/0 | 2025-11-27 | 2025-11-23 | 4 | 4 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 11&17/0 | 12 | 12 | 0 | 16/0, 17/0, 16/1, 16/2, 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 16/10 | 16/0, 17/0, 16/1, 16/2, 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 16/10 |  | 16/1,2,3,4,5,6,7,8,9,10,11 & 17/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 15/0-16/0 | ta421¦15/0¦16/0 | M R Constructions | 15/0 | 16/0 | 2025-12-19 | 2025-07-04 | 168 | 168 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 4&16/0 | 5 | 5 | 0 | 15/0, 16/0, 15/1, 15/2, 15/3 | 15/0, 16/0, 15/1, 15/2, 15/3 |  | 15/0,1,2,3,4 & 16/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 8/4-9/0 | ta421¦8/4¦9/0 | Nasiruddin | 8/4 | 9/0 | 2025-12-31 | 2025-12-08 | 23 | 23 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 15&19/0 | 12 | 11 | 1 | 8/4, 9/0, 8/5, 8/6, 8/7, 8/8, 8/9, 8/10, 8/11, 8/12, 8/13, 8/14 | 8/4, 9/0, 8/5, 8/6, 8/7, 8/8, 8/9, 8/10, 8/12, 8/13, 8/14 | 8/11 | 8/4,5,6,7,8,9,10,11,12,13,14,15 & 19/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 6/0-7/0 | ta421¦6/0¦7/0 | Nasiruddin | 6/0 | 7/0 | 2026-01-12 | 2025-12-16 | 27 | 27 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 7&7/0 | 8 | 8 | 0 | 6/0, 7/0, 6/1, 6/2, 6/3, 6/4, 6/5, 6/6 | 6/0, 7/0, 6/1, 6/2, 6/3, 6/4, 6/5, 6/6 |  | 6/0,1,2,3,4,5,6,7 & 7/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 8/3-8/4 | ta421¦8/3¦8/4 | Ramavath Electricals | 8/3 | 8/4 | 2026-01-20 | 2025-11-14 | 67 | 67 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 8/3, 8/4 | 8/3, 8/4 |  | 8/3 & 8/4 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 27/0-27/3 | ta421¦27/0¦27/3 | M R Constructions | 27/0 | 27/3 | 2026-12-09 | 2025-12-10 | 364 | 364 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 27/0, 27/3, 27/1, 27/2 | 27/0, 27/3, 27/1, 27/2 |  | 27/0,1,2,3 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 27/3-28/0 | ta421¦27/3¦28/0 | M R Constructions | 27/3 | 28/0 | 2026-01-12 | 2025-12-10 | 33 | 33 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 9&28/0 | 7 | 7 | 0 | 27/3, 28/0, 27/4, 27/5, 27/6, 27/7, 27/8 | 27/3, 28/0, 27/4, 27/5, 27/6, 27/7, 27/8 |  | 27/3,4,5,6,7,8 ,9 & 28/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 7/0-8/0 | ta421¦7/0¦8/0 | Nasiruddin | 7/0 | 8/0 | 2026-01-30 | 2025-12-13 | 48 | 48 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 1 | 1 | 7/0, 8/0 | 7/0 | 8/0 | 7/0 & 8/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | Gantry-1/0 | ta421¦Gantry¦1/0 | Kamruddin | Gantry | 1/0 | 2026-01-30 | 2025-10-09 | 113 | 113 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 2 | 1 | 1 | GANTRY, 1/0 | 1/0 | GANTRY | 1/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 8/2-8/3 | ta421¦8/2¦8/3 | Nasiruddin | 8/2 | 8/3 | 2026-02-03 | 2025-12-21 | 44 | 44 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 8/2, 8/3 | 8/2, 8/3 |  | 8/2 & 8/3 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 28/0-29/0 | ta421¦28/0¦29/0 | M R Constructions | 28/0 | 29/0 | 2026-02-01 | 2026-01-13 | 19 | 19 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 1&29/0 | 2 | 2 | 0 | 28/0, 29/0 | 28/0, 29/0 |  | 28/0,1 & 29/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 1/0-1A/0 | ta421¦1/0¦1A/0 | Kamruddin | 1/0 | 1A/0 | 2026-02-07 | 2025-10-09 | 121 | 121 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 1/0, 1A/0 | 1/0, 1A/0 |  | 1/0 & 1A/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 1A/0-1B/0 | ta421¦1A/0¦1B/0 | Kamruddin | 1A/0 | 1B/0 | 2026-02-03 | 2025-12-16 | 49 | 49 | HYBRID_PARTIAL_FALLBACK | TRUE | SHORTHAND_NO_ANCHOR | Location Nos has shorthand tokens without an explicit anchor token. | 2 | 2 | 0 | 1A/0, 1B/0 | 1A/0, 1B/0 |  | 1A/0 - 1B/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 4/12-5/0 | ta421¦4/12¦5/0 | Nasiruddin | 4/12 | 5/0 | 2026-02-06 | 2026-01-03 | 34 | 34 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 13 | 12 | 1 | 4/12, 5/0, 4/13, 4/14, 4/15, 4/16, 4/17, 4/18, 4/19, 4/20, 4/21, 4/22, 4/23 | 4/12, 5/0, 4/13, 4/14, 4/15, 4/17, 4/18, 4/19, 4/20, 4/21, 4/22, 4/23 | 4/16 | 4/12,13,14,15,16,17,18,19,20,21,22,23,5/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 8/0-8/1 | ta421¦8/0¦8/1 | Ramavath Electricals 2 | 8/0 | 8/1 | 2026-02-09 | 2025-12-31 | 40 | 40 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 2 | 1 | 1 | 8/0, 8/1 | 8/1 | 8/0 | 8/0 , 8/1 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 8/1-8/2 | ta421¦8/1¦8/2 | Ramavath Electricals 1 | 8/1 | 8/2 | 2026-02-09 | 2025-12-31 | 40 | 40 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 8/1, 8/2 | 8/1, 8/2 |  | 8/1, 8/2 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 38/0-39/0 | ta421¦38/0¦39/0 | M R Constructions | 38/0 | 39/0 | 2026-02-12 | 2025-07-30 | 197 | 197 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: .6, &38/0 | 8 | 8 | 0 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/7 | 38/0, 39/0, 38/1, 38/2, 38/3, 38/4, 38/5, 38/7 |  | 38/0,1,2,3,4,5,.6,7,& 38/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 1C/0-2/0 | ta421¦1C/0¦2/0 | Ramavath Electricals | 1C/0 | 2/0 | 2026-02-24 | 2026-01-04 | 51 | 51 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 1C/0, 2/0 | 1C/0, 2/0 |  | 1C/0 , 2/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 5/0-6/0 | ta421¦5/0¦6/0 | Ramavath Electricals | 5/0 | 6/0 | 2026-03-01 | 2025-12-03 | 88 | 88 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 5/0, 6/0 | 5/0, 6/0 |  | 5/0 , 6/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 4/0-4/12 | ta421¦4/0¦4/12 | Nasiruddin | 4/0 | 4/12 | 2026-02-20 | 2026-01-06 | 45 | 45 | LOCATION_NOS | FALSE | OK |  | 13 | 13 | 0 | 4/0, 4/12, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10, 4/11 | 4/0, 4/12, 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/7, 4/8, 4/9, 4/10, 4/11 |  | 4/0,1,2,3,4,5,6,7,8,9,10,11,12 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 3/0-4/0 | ta421¦3/0¦4/0 | Nasiruddin | 3/0 | 4/0 | 2026-03-01 | 2025-12-21 | 70 | 70 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 3/0, 4/0, 3/1, 3/2, 3/3 | 3/0, 4/0, 3/1, 3/2, 3/3 |  | 3/0,1,2,3, | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 37/0-38/0 | ta421¦37/0¦38/0 | M R Constructions | 37/0 | 38/0 | 2026-02-24 | 2025-12-18 | 68 | 68 | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 37/0, 38/0, 37/1, 37/2, 37/3, 37/4, 37/5, 37/6 | 37/0, 38/0, 37/1, 37/2, 37/3, 37/4, 37/5, 37/6 |  | 37/0,1,2,3,4,5,6,38/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 2/0-3/0 | ta421¦2/0¦3/0 | Nasiruddin | 2/0 | 3/0 | 2026-03-16 | 2026-01-04 | 71 | 71 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 5&3/0 | 6 | 6 | 0 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4 | 2/0, 3/0, 2/1, 2/2, 2/3, 2/4 |  | 2/0,1,2,3,4,5 & 3/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 1B/0-1C/0 | ta421¦1B/0¦1C/0 | Nasiruddin | 1B/0 | 1C/0 | 2026-03-26 | 2025-12-30 | 86 | 86 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: &1C/0 | 5 | 5 | 0 | 1B/0, 1C/0, 1B/1, 1B/2, 1B/3 | 1B/0, 1C/0, 1B/1, 1B/2, 1B/3 |  | 1B/0 ,1,2,3, & 1C/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 39/0-40/0 | ta421¦39/0¦40/0 | Kamruddin | 39/0 | 40/0 | 2026-03-26 | 2025-12-21 | 95 | 95 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9 | 39/0, 40/0, 39/1, 39/2, 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9 |  | 39/1,2,3,4,5,6,7,8,9 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 36/0-37/0 | ta421¦36/0¦37/0 | Kamruddin | 36/0 | 37/0 | 2026-04-13 | 2025-11-26 | 138 | 138 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 8&37/0 | 9 | 9 | 0 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7 | 36/0, 37/0, 36/1, 36/2, 36/3, 36/4, 36/5, 36/6, 36/7 |  | 36/1,2,3,4,5,6,7,8 & 37/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 42/0-43/0 | ta421¦42/0¦43/0 | Nasiruddin | 42/0 | 43/0 | 2026-04-30 | 2025-12-09 | 142 | 142 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 9&43/0 | 10 | 10 | 0 | 42/0, 43/0, 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 42/7, 42/8 | 42/0, 43/0, 42/1, 42/2, 42/3, 42/4, 42/5, 42/6, 42/7, 42/8 |  | 42/0,1,2,3,4,5,6,7,8,9 & 43/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 43/0-43A/0 | ta421¦43/0¦43A/0 | Nasiruddin | 43/0 | 43A/0 | 2026-05-14 | 2025-12-09 | 156 | 156 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 5&43/0 | 6 | 5 | 1 | 43/0, 43A/0, 43/1, 43/2, 43/3, 43/4 | 43/0, 43/1, 43/2, 43/3, 43/4 | 43A/0 | 43/0,1,2,3,4,5 & 43/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 34/2-35/0 | ta421¦34/2¦35/0 | Ramavath | 34/2 | 35/0 | 2026-05-18 | 2025-08-03 | 288 | 288 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 34/2, 35/0 | 34/2, 35/0 |  | 34/2, 35/0 | FALSE
TA 421 |  |  |  |  | TA 421 | 4xx | TA |  | Ready | 35/0-36/0 | ta421¦35/0¦36/0 | Kamruddin | 35/0 | 36/0 | 2026-05-18 | 2025-11-19 | 180 | 180 | HYBRID_PARTIAL_FALLBACK | TRUE | PARTIAL_PARSE | Unparsed tokens: 4&36/0 | 5 | 5 | 0 | 35/0, 36/0, 35/1, 35/2, 35/3 | 35/0, 36/0, 35/1, 35/2, 35/3 |  | 35/1,2,3,4 & 36/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 11/0-12/0 | ta504¦11/0¦12/0 | Tanjira Bibi | 11/0 | 12/0 | 2026-05-09 | 2026-04-15 | 24 | 24 | LOCATION_NOS | FALSE | OK |  | 8 | 8 | 0 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 | 11/0, 12/0, 11/1, 11/2, 11/3, 11/4, 11/5, 11/6 |  | 11/1, 11/2, 11/3, 11/4, 11/5, 11/6, 12/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 12/0-13/0 | ta504¦12/0¦13/0 | Tanjira Bibi | 12/0 | 13/0 | 2026-05-16 | 2025-11-17 | 180 | 180 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 | 12/0, 13/0, 12/1, 12/2, 12/3, 12/4, 12/5 |  | 12/1, 12/2, 12/3, 12/4, 12/5, 13/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 15/0-16/0 | ta504¦15/0¦16/0 | Lamba Construction | 15/0 | 16/0 | 2026-03-25 | 2026-01-24 | 60 | 60 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 15/0, 16/0, 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7 | 15/0, 16/0, 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7 |  | 15/1, 15/2, 15/3, 15/4, 15/5, 15/6, 15/7, 16/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 16/0-16/3 | ta504¦16/0¦16/3 | Lamba Construction | 16/0 | 16/3 | 2026-04-01 | 2026-01-24 | 67 | 67 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 16/0, 16/3, 16/1, 16/2 | 16/0, 16/3, 16/1, 16/2 |  | 16/1, 16/2, 16/3 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 16/3-17/0 | ta504¦16/3¦17/0 | Lamba Construction | 16/3 | 17/0 | 2026-02-04 | 2025-12-11 | 55 | 55 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 16/3, 17/0, 16/4, 16/5, 16/6 | 16/3, 17/0, 16/4, 16/5, 16/6 |  | 16/4, 16/5, 16/6, 17/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 17/0-17/4 | ta504¦17/0¦17/4 | Lamba Construction | 17/0 | 17/4 | 2026-02-11 | 2025-12-30 | 43 | 43 | LOCATION_NOS | FALSE | OK |  | 5 | 5 | 0 | 17/0, 17/4, 17/1, 17/2, 17/3 | 17/0, 17/4, 17/1, 17/2, 17/3 |  | 17/1, 17/2, 17/3, 17/4 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 17/4-18/0 | ta504¦17/4¦18/0 | Lamba Construction | 17/4 | 18/0 | 2026-02-17 | 2025-12-30 | 49 | 49 | LOCATION_NOS | FALSE | OK |  | 7 | 7 | 0 | 17/4, 18/0, 17/5, 17/6, 17/7, 17/8, 17/9 | 17/4, 18/0, 17/5, 17/6, 17/7, 17/8, 17/9 |  | 17/5, 17/6, 17/7, 17/8, 17/9, 18/0 | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 18/0-18/1 | ta504¦18/0¦18/1 | Lamba Construction | 18/0 | 18/1 | 2026-02-19 | 2025-12-18 | 63 | 63 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 18/0, 18/1 | 18/0, 18/1 |  | 18/1, | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 18/1-19/0 | ta504¦18/1¦19/0 | Lamba Construction | 18/1 | 19/0 | 2026-02-19 | 2025-12-18 | 63 | 63 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 18/1, 19/0, 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8 | 18/1, 19/0, 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8 |  | 18/2, 18/3, 18/4, 18/5, 18/6, 18/7, 18/8,19/0, | FALSE
TA 504 |  |  |  |  | TA 504 | 5xx | TA |  | Ready | 20/0-21/0 | ta504¦20/0¦21/0 | Lamba Construction | 20/0 | 21/0 | 2026-05-16 | 2025-12-31 | 136 | 136 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 3 | 2 | 1 | 20/0, 21/0, 9/0 | 20/0, 21/0 | 9/0 | 9/0 | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 100/0-101/0 | ta505¦100/0¦101/0 | Alimuddin | 100/0 | 101/0 | 2026-01-20 | 2025-11-29 | 52 | 52 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 100/0, 101/0 | 100/0, 101/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 101/0-102/0 | ta505¦101/0¦102/0 | Alimuddin | 101/0 | 102/0 | 2026-01-27 | 2025-10-26 | 93 | 93 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 101/0, 102/0 | 101/0, 102/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 102/0-103/0 | ta505¦102/0¦103/0 | Alimuddin | 102/0 | 103/0 | 2026-02-08 | 2025-10-26 | 105 | 105 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 102/0, 103/0 | 102/0, 103/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 103/0-103/5A | ta505¦103/0¦103/5A | Alimuddin | 103/0 | 103/5A | 2026-02-16 | 2025-09-20 | 149 | 149 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 103/0, 103/5A | 103/0 | 103/5A |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 103/5A-103/6A | ta505¦103/5A¦103/6A | Alimuddin | 103/5A | 103/6A | 2026-02-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 103/5A, 103/6A |  | 103/5A, 103/6A |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 103/6A-104/0 | ta505¦103/6A¦104/0 | Alimuddin | 103/6A | 104/0 | 2026-03-12 | 2025-09-05 | 188 | 188 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 103/6A, 104/0 | 104/0 | 103/6A |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 104/0-105/0 | ta505¦104/0¦105/0 | Alimuddin | 104/0 | 105/0 | 2026-03-07 | 2025-09-28 | 160 | 160 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 104/0, 105/0 | 104/0, 105/0 |  |  | FALSE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 111/0-112/0 | ta505¦111/0¦112/0 | Alimuddin | 111/0 | 112/0 | 2026-03-28 | 2025-10-26 | 153 | 153 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 111/0, 112/0 | 111/0, 112/0 |  |  | FALSE
TA 505 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 113/0-114/0 | ta505¦113/0¦114/0 | Jahangir Alam | 113/0 | 114/0 | 2026-03-25 | 2026-01-19 | 65 | 65 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 113/0, 114/0 | 113/0, 114/0 |  |  | TRUE
TA 505 |  |  |  |  | TA 505 | 5xx | TA |  | Ready | 110A/0-111/0 | ta505¦110A/0¦111/0 | Alimuddin | 110A/0 | 111/0 | 2026-05-14 | 2025-09-30 | 226 | 226 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 110A/0, 111/0 | 110A/0, 111/0 |  |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 57/6-58/0 | tb401pkgg¦57/6¦58/0 | GPJ Const. | 57/6 | 58/0 | 2024-05-06 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 57/6, 58/0 |  | 57/6, 58/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 57/0-57/6 | tb401pkgg¦57/0¦57/6 | GPJ Const. | 57/0 | 57/6 | 2024-05-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 57/0, 57/6 |  | 57/0, 57/6 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 56/0-57/0 | tb401pkgg¦56/0¦57/0 | GPJ Const. | 56/0 | 57/0 | 2024-06-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 56/0, 57/0 |  | 56/0, 57/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 55/0-56/0 | tb401pkgg¦55/0¦56/0 | GPJ Const. | 55/0 | 56/0 | 2024-06-25 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 55/0, 56/0 |  | 55/0, 56/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 53/0-55/0 | tb401pkgg¦53/0¦55/0 | GPJ Const. | 53/0 | 55/0 | 2024-07-16 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 53/0, 55/0 |  | 53/0, 55/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 52/0-53/0 | tb401pkgg¦52/0¦53/0 | GPJ Const. | 52/0 | 53/0 | 2024-08-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 52/0, 53/0 |  | 52/0, 53/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 51/0-52/0 | tb401pkgg¦51/0¦52/0 | GPJ Const. | 51/0 | 52/0 | 2024-09-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 51/0, 52/0 |  | 51/0, 52/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 50/0-51/0 | tb401pkgg¦50/0¦51/0 | GPJ Const. | 50/0 | 51/0 | 2024-09-26 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 50/0, 51/0 |  | 50/0, 51/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 72/7-73/0 | tb401pkgg¦72/7¦73/0 | MR Power | 72/7 | 73/0 | 2024-11-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 72/7, 73/0 |  | 72/7, 73/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 58/0-58/7 | tb401pkgg¦58/0¦58/7 | Kddus Ali | 58/0 | 58/7 | 2024-11-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 58/0, 58/7 |  | 58/0, 58/7 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 72/0-72/7 | tb401pkgg¦72/0¦72/7 | MR Power | 72/0 | 72/7 | 2024-11-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 72/0, 72/7 |  | 72/0, 72/7 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 67/1-68/0 | tb401pkgg¦67/1¦68/0 | Nasruddin | 67/1 | 68/0 | 2024-12-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 67/1, 68/0 |  | 67/1, 68/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 68/0-69/0 | tb401pkgg¦68/0¦69/0 | Nasruddin | 68/0 | 69/0 | 2024-12-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 68/0, 69/0 |  | 68/0, 69/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 58/7-59/0 | tb401pkgg¦58/7¦59/0 | MR Power | 58/7 | 59/0 | 2024-12-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 58/7, 59/0 |  | 58/7, 59/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 71/0-72/0 | tb401pkgg¦71/0¦72/0 | MR Power | 71/0 | 72/0 | 2024-12-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 71/0, 72/0 |  | 71/0, 72/0 |  | FALSE
TB 401 - PKG-G |  |  |  |  | TB 401 | 4xx | TB |  | Unassigned | 67/0-67/1 | tb401pkgg¦67/0¦67/1 | Nasruddin | 67/0 | 67/1 | 2024-12-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 67/0, 67/1 |  | 67/0, 67/1 |  | FALSE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 69/0-70/0 | tb401pkgg¦69/0¦70/0 | Nasruddin | 69/0 | 70/0 | 2024-12-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 69/0, 70/0 |  | 69/0, 70/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 41/0-42/0 | tb401pkgg¦41/0¦42/0 | Nasruddin | 41/0 | 42/0 | 2025-02-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 41/0, 42/0 |  | 41/0, 42/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 59/0-60/0 | tb401pkgg¦59/0¦60/0 | MR Power | 59/0 | 60/0 | 2025-01-20 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 59/0, 60/0 |  | 59/0, 60/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 42/0-43/0 | tb401pkgg¦42/0¦43/0 | Indrajeet | 42/0 | 43/0 | 2025-05-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 42/0, 43/0 |  | 42/0, 43/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 49/0-50/0 | tb401pkgg¦49/0¦50/0 | Indrajeet | 49/0 | 50/0 | 2025-05-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 49/0, 50/0 |  | 49/0, 50/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 48/0-49/0 | tb401pkgg¦48/0¦49/0 | Indrajeet | 48/0 | 49/0 | 2025-05-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 48/0, 49/0 |  | 48/0, 49/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 47/0-48/0 | tb401pkgg¦47/0¦48/0 | Indrajeet | 47/0 | 48/0 | 2025-05-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 47/0, 48/0 |  | 47/0, 48/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 37/2-38/0 | tb401pkgg¦37/2¦38/0 | Indrajeet | 37/2 | 38/0 | 2025-05-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 37/2, 38/0 |  | 37/2, 38/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 43/0-44/0 | tb401pkgg¦43/0¦44/0 | Indrajeet | 43/0 | 44/0 | 2025-05-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 43/0, 44/0 |  | 43/0, 44/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 61/0-62/0 | tb401pkgg¦61/0¦62/0 | GPJ Const. | 61/0 | 62/0 | 2025-06-27 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 61/0, 62/0 |  | 61/0, 62/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 62/0-63/0 | tb401pkgg¦62/0¦63/0 | GPJ Const. | 62/0 | 63/0 | 2025-07-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 62/0, 63/0 |  | 62/0, 63/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 38/0-38/9 | tb401pkgg¦38/0¦38/9 | Indrajeet | 38/0 | 38/9 | 2025-06-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 38/0, 38/9 |  | 38/0, 38/9 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 40/10-41/0 | tb401pkgg¦40/10¦41/0 | Indrajeet/Rahim | 40/10 | 41/0 | 2025-07-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 40/10, 41/0 |  | 40/10, 41/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 63/0-64/0 | tb401pkgg¦63/0¦64/0 | GPJ Const. | 63/0 | 64/0 | 2025-07-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 63/0, 64/0 |  | 63/0, 64/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 39/0-40/0 | tb401pkgg¦39/0¦40/0 | Amir Sheikh | 39/0 | 40/0 | 2025-07-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 39/0, 40/0 |  | 39/0, 40/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 40/5-40/10 | tb401pkgg¦40/5¦40/10 | Indrajeet/Rahim | 40/5 | 40/10 | 2025-07-11 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 40/5, 40/10 |  | 40/5, 40/10 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 38/9-39/0 | tb401pkgg¦38/9¦39/0 | Indrajeet/Mohan/Amir Sheikh | 38/9 | 39/0 | 2025-07-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 38/9, 39/0 |  | 38/9, 39/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 40/0-40/2 | tb401pkgg¦40/0¦40/2 | Rahim Khan | 40/0 | 40/2 | 2025-07-28 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 40/0, 40/2 |  | 40/0, 40/2 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 40/2-40/5 | tb401pkgg¦40/2¦40/5 | Rahim Khan | 40/2 | 40/5 | 2025-08-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 40/2, 40/5 |  | 40/2, 40/5 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 66/0-67/0 | tb401pkgg¦66/0¦67/0 | MC Const. | 66/0 | 67/0 | 2025-09-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 66/0, 67/0 |  | 66/0, 67/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 35/0-36/0 | tb401pkgg¦35/0¦36/0 | Amir Sheikh | 35/0 | 36/0 | 2025-09-07 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 35/0, 36/0 |  | 35/0, 36/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 46/0-47/0 | tb401pkgg¦46/0¦47/0 | Indrajeet | 46/0 | 47/0 | 2025-06-22 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 46/0, 47/0 |  | 46/0, 47/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 31/0-32/0 | tb401pkgg¦31/0¦32/0 | Krishna Const. | 31/0 | 32/0 | 2025-09-18 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 31/0, 32/0 |  | 31/0, 32/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 44/0-45/0 | tb401pkgg¦44/0¦45/0 | Indrajeet | 44/0 | 45/0 | 2025-06-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 44/0, 45/0 |  | 44/0, 45/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | Gantry-1/0 | tb401pkgg¦Gantry¦1/0 | Devi Power | Gantry | 1/0 | 2025-10-08 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | GANTRY, 1/0 |  | GANTRY, 1/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 65/0-66/0 | tb401pkgg¦65/0¦66/0 | MC Const. | 65/0 | 66/0 | 2025-10-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 65/0, 66/0 |  | 65/0, 66/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 1/0-1A/0 | tb401pkgg¦1/0¦1A/0 | Devi Power | 1/0 | 1A/0 | 2025-10-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 1/0, 1A/0 |  | 1/0, 1A/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 1A/0-2/0 | tb401pkgg¦1A/0¦2/0 | Devi Power | 1A/0 | 2/0 | 2025-10-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 1A/0, 2/0 |  | 1A/0, 2/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 64/0-65/0 | tb401pkgg¦64/0¦65/0 | MC Const. | 64/0 | 65/0 | 2025-10-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 64/0, 65/0 |  | 64/0, 65/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 32/0-33/0 | tb401pkgg¦32/0¦33/0 | Krishna Const. | 32/0 | 33/0 | 2025-10-04 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 32/0, 33/0 |  | 32/0, 33/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 33/0-34/0 | tb401pkgg¦33/0¦34/0 | Krishna Const. | 33/0 | 34/0 | 2025-10-21 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 33/0, 34/0 |  | 33/0, 34/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 36/0-37/0 | tb401pkgg¦36/0¦37/0 | Telegance Power | 36/0 | 37/0 | 2025-10-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 36/0, 37/0 |  | 36/0, 37/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 60/0-61/0 | tb401pkgg¦60/0¦61/0 | Indrajeet | 60/0 | 61/0 | 2025-11-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 60/0, 61/0 |  | 60/0, 61/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 34/0-34/5 | tb401pkgg¦34/0¦34/5 | Krishna Const. | 34/0 | 34/5 | 2025-01-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 34/0, 34/5 |  | 34/0, 34/5 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 34/5-35/0 | tb401pkgg¦34/5¦35/0 | Krishna Const. | 34/5 | 35/0 | 2025-11-10 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 34/5, 35/0 |  | 34/5, 35/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 45/0-46/0 | tb401pkgg¦45/0¦46/0 | Gopal Ji | 45/0 | 46/0 | 2025-11-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 45/0, 46/0 |  | 45/0, 46/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 37/0-37/1 | tb401pkgg¦37/0¦37/1 | Indrajeet | 37/0 | 37/1 | 2025-11-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 37/0, 37/1 |  | 37/0, 37/1 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 37/1-37/2 | tb401pkgg¦37/1¦37/2 | Indrajeet | 37/1 | 37/2 | 2025-11-29 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 37/1, 37/2 |  | 37/1, 37/2 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 25/0-26/0 | tb401pkgg¦25/0¦26/0 | Krishna Const. -2 | 25/0 | 26/0 | 2025-11-13 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 25/0, 26/0 |  | 25/0, 26/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 2/0-3/0 | tb401pkgg¦2/0¦3/0 | Devi Power | 2/0 | 3/0 | 2025-10-30 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 2/0, 3/0 |  | 2/0, 3/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 30/0-31/0 | tb401pkgg¦30/0¦31/0 | Krishna Const. | 30/0 | 31/0 | 2025-11-19 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 30/0, 31/0 |  | 30/0, 31/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 5/0-6/0 | tb401pkgg¦5/0¦6/0 | Kunal Kumar | 5/0 | 6/0 | 2025-12-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 5/0, 6/0 |  | 5/0, 6/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 4/0-5/0 | tb401pkgg¦4/0¦5/0 | Devi Power | 4/0 | 5/0 | 2025-12-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 4/0, 5/0 |  | 4/0, 5/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 15/0-16/0 | tb401pkgg¦15/0¦16/0 | Nasir | 15/0 | 16/0 | 2025-12-03 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 15/0, 16/0 |  | 15/0, 16/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 29/0-30/0 | tb401pkgg¦29/0¦30/0 | Krishna Const. | 29/0 | 30/0 | 2025-12-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 29/0, 30/0 |  | 29/0, 30/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 16/0-17/0 | tb401pkgg¦16/0¦17/0 | Nasir | 16/0 | 17/0 | 2025-12-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 16/0, 17/0 |  | 16/0, 17/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 24/0-25/0 | tb401pkgg¦24/0¦25/0 | Krishna Const. -2 | 24/0 | 25/0 | 2025-12-01 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 24/0, 25/0 |  | 24/0, 25/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 6/0-7/0 | tb401pkgg¦6/0¦7/0 | Devi Power | 6/0 | 7/0 | 2025-12-17 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 6/0, 7/0 |  | 6/0, 7/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 28/0-29/0 | tb401pkgg¦28/0¦29/0 | Krishna Const. | 28/0 | 29/0 | 2025-12-15 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 28/0, 29/0 |  | 28/0, 29/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 23/0-24/0 | tb401pkgg¦23/0¦24/0 | Krishna Const. -2 | 23/0 | 24/0 | 2025-12-12 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 23/0, 24/0 |  | 23/0, 24/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | 27/1-28/0 | tb401pkgg¦27/1¦28/0 | Krishna Const. | 27/1 | 28/0 | 2025-12-24 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 27/1, 28/0 |  | 27/1, 28/0 |  | TRUE
TB 401 - PKG-G | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Unassigned | 3/0-4/0 | tb401pkgg¦3/0¦4/0 | Gopal Ji | 3/0 | 4/0 | 2025-12-23 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 0 | 2 | 3/0, 4/0 |  | 3/0, 4/0 |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 3/0-3/1 | tb501132kv¦3/0¦3/1 | Sammirul Sekh | 3/0 | 3/1 | 2026-05-07 | 2026-04-30 | 7 | 7 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/0, 3/1 | 3/0, 3/1 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 3/1-4/0 | tb501132kv¦3/1¦4/0 | Sammirul Sekh | 3/1 | 4/0 | 2026-05-07 | 2026-04-22 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/1, 4/0 | 3/1, 4/0 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 4/0-4/1 | tb501132kv¦4/0¦4/1 | Sammirul Sekh | 4/0 | 4/1 | 2026-03-30 | 2026-03-22 | 8 | 8 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/0, 4/1 | 4/0, 4/1 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 4/1-4/2 | tb501132kv¦4/1¦4/2 |  | 4/1 | 4/2 | 2026-03-30 | 2026-03-23 | 7 | 7 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/1, 4/2 | 4/1, 4/2 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 4/2-5/0 | tb501132kv¦4/2¦5/0 | National Construction | 4/2 | 5/0 | 2026-03-30 | 2026-03-23 | 7 | 7 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/2, 5/0 | 4/2, 5/0 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 5/0-6/0 | tb501132kv¦5/0¦6/0 | National Construction | 5/0 | 6/0 | 2026-03-25 | 2026-03-16 | 9 | 9 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5/0, 6/0 | 5/0, 6/0 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 6/0-6/1 | tb501132kv¦6/0¦6/1 | National Construction | 6/0 | 6/1 | 2026-03-26 | 2026-02-19 | 35 | 35 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/0, 6/1 | 6/0, 6/1 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 6/1-6/2 | tb501132kv¦6/1¦6/2 | National Construction | 6/1 | 6/2 | 2026-03-26 | 2026-03-18 | 8 | 8 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/1, 6/2 | 6/1, 6/2 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 6/2-6/3 | tb501132kv¦6/2¦6/3 | National Construction | 6/2 | 6/3 | 2026-03-26 | 2026-03-18 | 8 | 8 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/2, 6/3 | 6/2, 6/3 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | C | 6/3-6/4 | tb501132kv¦6/3¦6/4 | National Construction | 6/3 | 6/4 | 2026-03-26 | 2026-03-20 | 6 | 6 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/3, 6/4 | 6/3, 6/4 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 6/4-7/0 | tb501132kv¦6/4¦7/0 | National Construction | 6/4 | 7/0 | 2026-03-26 | 2026-03-20 | 6 | 6 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/4, 7/0 | 6/4, 7/0 |  |  | TRUE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 7/0-8/0 | tb501132kv¦7/0¦8/0 | National Construction | 7/0 | 8/0 | 2026-03-23 | 2026-02-08 | 43 | 43 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 7/0, 8/0 | 7/0, 8/0 |  |  | FALSE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 8/0-9/0 | tb501132kv¦8/0¦9/0 | Sawariya seth | 8/0 | 9/0 | 2026-03-17 | 2026-02-06 | 39 | 39 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8/0, 9/0 | 8/0, 9/0 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 9/0-10/0 | tb501132kv¦9/0¦10/0 | Sawariya seth | 9/0 | 10/0 | 2026-03-17 | 2026-02-06 | 39 | 39 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/0, 10/0 | 9/0, 10/0 |  |  | TRUE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 11/0-12/0 | tb501132kv¦11/0¦12/0 | Sammirul Sekh | 11/0 | 12/0 | 2026-05-10 | 2026-01-17 | 113 | 113 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11/0, 12/0 | 11/0, 12/0 |  |  | FALSE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 12/0-12/1 | tb501132kv¦12/0¦12/1 | Sawariya seth | 12/0 | 12/1 | 2026-03-13 | 2026-01-31 | 41 | 41 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12/0, 12/1 | 12/0, 12/1 |  |  | TRUE
TB 501 - 132kV | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | C | 12/1-13/0 | tb501132kv¦12/1¦13/0 | Sawariya seth | 12/1 | 13/0 | 2026-03-13 | 2026-01-31 | 41 | 41 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12/1, 13/0 | 12/1, 13/0 |  |  | TRUE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 13/0-13/1 | tb501132kv¦13/0¦13/1 | Sawariya seth | 13/0 | 13/1 | 2026-03-12 | 2026-01-29 | 42 | 42 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13/0, 13/1 | 13/0, 13/1 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 13/1-13/2 | tb501132kv¦13/1¦13/2 | Sawariya seth | 13/1 | 13/2 | 2026-03-12 | 2026-01-29 | 42 | 42 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13/1, 13/2 | 13/1, 13/2 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 13/2-14/0 | tb501132kv¦13/2¦14/0 | Sawariya seth | 13/2 | 14/0 | 2026-03-15 | 2026-01-27 | 47 | 47 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13/2, 14/0 | 13/2, 14/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 14/0-15/0 | tb501132kv¦14/0¦15/0 | Sammirul Sekh | 14/0 | 15/0 | 2026-05-14 | 2026-02-24 | 79 | 79 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/0, 15/0 | 14/0, 15/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 15/0-15/1 | tb501132kv¦15/0¦15/1 | Sawariya seth | 15/0 | 15/1 | 2026-03-07 | 2026-02-24 | 11 | 11 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/0, 15/1 | 15/0, 15/1 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 15/1-15/2 | tb501132kv¦15/1¦15/2 | Sawariya seth | 15/1 | 15/2 | 2026-03-07 | 2026-01-02 | 64 | 64 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/1, 15/2 | 15/1, 15/2 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 15/2-15/3 | tb501132kv¦15/2¦15/3 | Sawariya seth | 15/2 | 15/3 | 2026-03-07 | 2025-12-27 | 70 | 70 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/2, 15/3 | 15/2, 15/3 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 15/3-16/0 | tb501132kv¦15/3¦16/0 | Sawariya seth | 15/3 | 16/0 | 2026-03-07 | 2025-12-26 | 71 | 71 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15/3, 16/0 | 15/3, 16/0 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 16/0-16/1 | tb501132kv¦16/0¦16/1 | SK Basirul | 16/0 | 16/1 | 2026-03-05 | 2025-12-13 | 82 | 82 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16/0, 16/1 | 16/0, 16/1 |  |  | FALSE
TB 501 - 132kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 16/1-16/2 | tb501132kv¦16/1¦16/2 | SK Basirul | 16/1 | 16/2 | 2026-03-03 | 2025-11-20 | 103 | 103 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16/1, 16/2 | 16/1, 16/2 |  |  | FALSE
TB 501 - 132kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 16/2-17/0 | tb501132kv¦16/2¦17/0 | SK Basirul | 16/2 | 17/0 | 2026-02-23 | 2025-11-20 | 95 | 95 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16/2, 17/0 | 16/2, 17/0 |  |  | TRUE
TB 501 - 132kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 17/0-18/0 | tb501132kv¦17/0¦18/0 | SK Basirul | 17/0 | 18/0 | 2026-03-02 | 2025-12-17 | 75 | 75 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 17/0, 18/0 | 17/0, 18/0 |  |  | TRUE
TB 501 - 132kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 18/0-Gantry | tb501132kv¦18/0¦Gantry | SK Basirul | 18/0 | Gantry | 2026-02-20 | 2025-12-17 | 65 | 65 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | 18/0, GANTRY | 18/0 | GANTRY |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | Gnty-0/0 | tb501220kv¦Gnty¦0/0 | Harshvivek | Gnty | 0/0 | 2026-01-31 | 2025-04-09 | 297 | 297 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 1 | 1 | GNTY, 0/0 | 0/0 | GNTY |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 0/0-1/0 | tb501220kv¦0/0¦1/0 | National Construction | 0/0 | 1/0 | 2025-05-19 | 2025-04-13 | 36 | 36 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 0/0, 1/0 | 0/0, 1/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 1/0-1A/0 | tb501220kv¦1/0¦1A/0 | National Construction | 1/0 | 1A/0 | 2025-05-19 | 2025-04-23 | 26 | 26 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1/0, 1A/0 | 1/0, 1A/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 1A/0-1A/2 | tb501220kv¦1A/0¦1A/2 | National Construction | 1A/0 | 1A/2 | 2025-06-29 | 2025-04-23 | 67 | 67 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1A/0, 1A/2 | 1A/0, 1A/2 |  |  | TRUE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 1A/2-1B/0 | tb501220kv¦1A/2¦1B/0 | National Construction | 1A/2 | 1B/0 | 2025-06-29 | 2025-04-27 | 63 | 63 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1A/2, 1B/0 | 1A/2, 1B/0 |  |  | FALSE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 1B/0-1C/0 | tb501220kv¦1B/0¦1C/0 | National Construction | 1B/0 | 1C/0 | 2026-04-09 | 2026-03-25 | 15 | 15 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1B/0, 1C/0 | 1B/0, 1C/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 1C/0-1D/0 | tb501220kv¦1C/0¦1D/0 | National Construction | 1C/0 | 1D/0 | 2026-04-11 | 2026-03-25 | 17 | 17 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1C/0, 1D/0 | 1C/0, 1D/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 1D/0-1E/0 | tb501220kv¦1D/0¦1E/0 | Dilruba Bibi | 1D/0 | 1E/0 | 2025-08-01 | 2025-05-27 | 66 | 66 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1D/0, 1E/0 | 1D/0, 1E/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 1E/0-2/0 | tb501220kv¦1E/0¦2/0 | Dilruba Bibi | 1E/0 | 2/0 | 2025-07-26 | 2025-05-27 | 60 | 60 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 1E/0, 2/0 | 1E/0, 2/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 2/0-3/0 | tb501220kv¦2/0¦3/0 | National Construction | 2/0 | 3/0 | 2026-03-20 | 2025-05-03 | 321 | 321 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 2/0, 3/0 | 2/0, 3/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 3/0-4/0 | tb501220kv¦3/0¦4/0 | National Construction | 3/0 | 4/0 | 2026-04-06 | 2025-05-30 | 311 | 311 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 3/0, 4/0 | 3/0, 4/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 4/0-4/5 | tb501220kv¦4/0¦4/5 | Dilruba Bibi | 4/0 | 4/5 | 2025-07-11 | 2025-05-30 | 42 | 42 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/0, 4/5 | 4/0, 4/5 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 4/5-4/6 | tb501220kv¦4/5¦4/6 | Dilruba Bibi | 4/5 | 4/6 | 2025-07-11 | 2025-03-25 | 108 | 108 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/5, 4/6 | 4/5, 4/6 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 4/9-4/10 | tb501220kv¦4/9¦4/10 | National Construction | 4/9 | 4/10 | 2025-08-22 | 2025-03-17 | 158 | 158 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/9, 4/10 | 4/9, 4/10 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 4/10-4/11 | tb501220kv¦4/10¦4/11 | National Construction | 4/10 | 4/11 | 2025-08-22 | 2025-03-13 | 162 | 162 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/10, 4/11 | 4/10, 4/11 |  |  | TRUE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 4/11-4/15 | tb501220kv¦4/11¦4/15 | National Construction | 4/11 | 4/15 | 2025-08-22 | 2025-06-04 | 79 | 79 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/11, 4/15 | 4/11, 4/15 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 4/15-4/16 | tb501220kv¦4/15¦4/16 | National Construction | 4/15 | 4/16 | 2025-08-22 | 2025-03-25 | 150 | 150 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/15, 4/16 | 4/15, 4/16 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 4/16-4/17 | tb501220kv¦4/16¦4/17 | National Construction | 4/16 | 4/17 | 2025-08-22 | 2025-03-23 | 152 | 152 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/16, 4/17 | 4/16, 4/17 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 4/17-5/0 | tb501220kv¦4/17¦5/0 | National Construction | 4/17 | 5/0 | 2025-08-28 | 2025-07-16 | 43 | 43 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 4/17, 5/0 | 4/17, 5/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5/0-5/1 | tb501220kv¦5/0¦5/1 | National Construction | 5/0 | 5/1 | 2025-08-28 | 2025-07-16 | 43 | 43 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5/0, 5/1 | 5/0, 5/1 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5/1-5A/0 | tb501220kv¦5/1¦5A/0 | National Construction | 5/1 | 5A/0 | 2025-10-16 | 2025-04-13 | 186 | 186 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5/1, 5A/0 | 5/1, 5A/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5A/0-5A/1 | tb501220kv¦5A/0¦5A/1 | National Construction | 5A/0 | 5A/1 | 2026-02-10 | 2025-11-24 | 78 | 78 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5A/0, 5A/1 | 5A/0, 5A/1 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5A/1-5A/2 | tb501220kv¦5A/1¦5A/2 | National Construction | 5A/1 | 5A/2 | 2026-02-09 | 2025-11-24 | 77 | 77 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5A/1, 5A/2 | 5A/1, 5A/2 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5A/2-5B/0 | tb501220kv¦5A/2¦5B/0 | National Construction | 5A/2 | 5B/0 | 2026-02-06 | 2025-11-23 | 75 | 75 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5A/2, 5B/0 | 5A/2, 5B/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 5B/0-6/0 | tb501220kv¦5B/0¦6/0 | National Construction | 5B/0 | 6/0 | 2026-01-28 | 2025-12-20 | 39 | 39 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 5B/0, 6/0 | 5B/0, 6/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 6/0-7/0 | tb501220kv¦6/0¦7/0 | National Construction | 6/0 | 7/0 | 2026-01-28 | 2025-12-20 | 39 | 39 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 6/0, 7/0 | 6/0, 7/0 |  |  | FALSE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 7/0-8/0 | tb501220kv¦7/0¦8/0 | National Construction | 7/0 | 8/0 | 2025-09-22 | 2025-06-08 | 106 | 106 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 7/0, 8/0 | 7/0, 8/0 |  |  | TRUE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | C | 8/0-8A/0 | tb501220kv¦8/0¦8A/0 | National Construction | 8/0 | 8A/0 | 2025-10-01 | 2025-06-08 | 115 | 115 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8/0, 8A/0 | 8/0, 8A/0 |  |  | TRUE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8A/0-8B/0 | tb501220kv¦8A/0¦8B/0 | National Construction | 8A/0 | 8B/0 | 2025-10-03 | 2025-04-30 | 156 | 156 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8A/0, 8B/0 | 8A/0, 8B/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8B/0-8C/0 | tb501220kv¦8B/0¦8C/0 | National Construction | 8B/0 | 8C/0 | 2025-10-04 | 2025-06-06 | 120 | 120 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8B/0, 8C/0 | 8B/0, 8C/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8C/0-8D/0 | tb501220kv¦8C/0¦8D/0 | National Construction | 8C/0 | 8D/0 | 2026-03-13 | 2025-06-06 | 280 | 280 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8C/0, 8D/0 | 8C/0, 8D/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8D/0-8D/1 | tb501220kv¦8D/0¦8D/1 | National Construction | 8D/0 | 8D/1 | 2026-03-05 | 2025-11-29 | 96 | 96 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/0, 8D/1 | 8D/0, 8D/1 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8D/1-8D/3 | tb501220kv¦8D/1¦8D/3 | National Construction | 8D/1 | 8D/3 | 2026-03-02 | 2025-12-08 | 84 | 84 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/1, 8D/3 | 8D/1, 8D/3 |  |  | FALSE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 8D/3-8D/4 | tb501220kv¦8D/3¦8D/4 | National Construction | 8D/3 | 8D/4 | 2026-02-15 | 2025-11-27 | 80 | 80 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/3, 8D/4 | 8D/3, 8D/4 |  |  | TRUE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8D/4-8D/5 | tb501220kv¦8D/4¦8D/5 | National Construction | 8D/4 | 8D/5 | 2026-02-15 | 2025-11-05 | 102 | 102 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/4, 8D/5 | 8D/4, 8D/5 |  |  | FALSE
TB 501 - 220kV | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | C | 8D/5-8D/6 | tb501220kv¦8D/5¦8D/6 | National Construction | 8D/5 | 8D/6 | 2026-02-15 | 2025-11-07 | 100 | 100 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/5, 8D/6 | 8D/5, 8D/6 |  |  | TRUE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8D/6-8E/0 | tb501220kv¦8D/6¦8E/0 | National Construction | 8D/6 | 8E/0 | 2026-02-15 | 2025-11-09 | 98 | 98 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8D/6, 8E/0 | 8D/6, 8E/0 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8E/0-8E/1 | tb501220kv¦8E/0¦8E/1 | National Construction | 8E/0 | 8E/1 | 2026-02-15 | 2025-11-09 | 98 | 98 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/0, 8E/1 | 8E/0, 8E/1 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8E/1-8E/2 | tb501220kv¦8E/1¦8E/2 | National Construction | 8E/1 | 8E/2 | 2025-11-11 | 2025-06-25 | 139 | 139 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/1, 8E/2 | 8E/1, 8E/2 |  |  | FALSE
TB 501 - 220kV |  |  |  |  | TB 501 | 5xx | TB |  | C | 8E/2-8E/5 | tb501220kv¦8E/2¦8E/5 | National Construction | 8E/2 | 8E/5 | 2025-11-11 | 2025-06-27 | 137 | 137 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/2, 8E/5 | 8E/2, 8E/5 |  |  | FALSE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/5-8E/6 | tb501220kv¦8E/5¦8E/6 | National Construction | 8E/5 | 8E/6 | 2025-11-11 | 2025-06-27 | 137 | 137 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/5, 8E/6 | 8E/5, 8E/6 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/6-8E/7 | tb501220kv¦8E/6¦8E/7 | National Construction | 8E/6 | 8E/7 | 2026-02-20 | 2025-12-03 | 79 | 79 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/6, 8E/7 | 8E/6, 8E/7 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/7-8E/8 | tb501220kv¦8E/7¦8E/8 | National Construction | 8E/7 | 8E/8 | 2026-02-20 | 2025-12-03 | 79 | 79 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/7, 8E/8 | 8E/7, 8E/8 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/8-8E/11 | tb501220kv¦8E/8¦8E/11 | National Construction | 8E/8 | 8E/11 | 2025-11-17 | 2025-06-22 | 148 | 148 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/8, 8E/11 | 8E/8, 8E/11 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/11-8E/12 | tb501220kv¦8E/11¦8E/12 | National Construction | 8E/11 | 8E/12 | 2025-11-05 | 2025-07-08 | 120 | 120 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/11, 8E/12 | 8E/11, 8E/12 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 8E/12-9 | tb501220kv¦8E/12¦9 | National Construction | 8E/12 | AP-9 | 2025-11-05 | 2025-07-08 | 120 | 120 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 8E/12, 9 | 8E/12, 9 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 9-9/4 | tb501220kv¦9¦9/4 | National Construction | AP-9 | 9/4 | 2025-11-05 | 2025-07-07 | 121 | 121 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9, 9/4 | 9, 9/4 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 9/4-9/5 | tb501220kv¦9/4¦9/5 | National Construction | 9/4 | 9/5 | 2025-10-26 | 2025-07-30 | 88 | 88 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/4, 9/5 | 9/4, 9/5 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 9/5-10 | tb501220kv¦9/5¦10 | National Construction | 9/5 | AP-10 | 2025-09-26 | 2025-07-30 | 58 | 58 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 9/5, 10 | 9/5, 10 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 10-11 | tb501220kv¦10¦11 | National Construction | AP-10 | AP-11 | 2025-10-10 | 2025-05-22 | 141 | 141 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 10, 11 | 10, 11 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 11-12 | tb501220kv¦11¦12 | National Construction | AP-11 | AP-12 | 2025-10-10 | 2025-05-02 | 161 | 161 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 11, 12 | 11, 12 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 12-13 | tb501220kv¦12¦13 | National Construction | AP-12 | AP-13 | 2025-10-01 | 2025-05-24 | 130 | 130 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 12, 13 | 12, 13 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 13-14 | tb501220kv¦13¦14 | National Construction | AP-13 | AP-14 | 2025-12-18 | 2025-11-12 | 36 | 36 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 13, 14 | 13, 14 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 14-14/1 | tb501220kv¦14¦14/1 | National Construction | AP-14 | 14/1 | 2025-12-18 | 2025-10-26 | 53 | 53 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14, 14/1 | 14, 14/1 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 14/1-14/3 | tb501220kv¦14/1¦14/3 | National Construction | 14/1 | 14/3 | 2025-12-18 | 2025-10-29 | 50 | 50 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/1, 14/3 | 14/1, 14/3 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 14/3-15 | tb501220kv¦14/3¦15 | National Construction | 14/3 | AP-15 | 2025-12-13 | 2025-11-17 | 26 | 26 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 14/3, 15 | 14/3, 15 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 15-16 | tb501220kv¦15¦16 | Nemchand | AP-15 | AP-16 | 2025-06-17 | 2025-02-17 | 120 | 120 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 15, 16 | 15, 16 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 16-17 | tb501220kv¦16¦17 | National Construction | AP-16 | AP-17 | 2025-06-30 | 2025-02-24 | 126 | 126 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 16, 17 | 16, 17 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 17-18 | tb501220kv¦17¦18 | National Construction | AP-17 | AP-18 | 2025-06-30 | 2025-02-23 | 127 | 127 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 17, 18 | 17, 18 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 18-19 | tb501220kv¦18¦19 | National Construction | AP-18 | AP-19 | 2025-07-14 | 2025-02-23 | 141 | 141 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 18, 19 | 18, 19 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 19-20 | tb501220kv¦19¦20 | National Construction | AP-19 | AP-20 | 2025-07-20 | 2025-05-10 | 71 | 71 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 19, 20 | 19, 20 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 20-21 | tb501220kv¦20¦21 | National Construction | AP-20 | AP-21 | 2025-07-22 | 2025-11-12 | -113 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 20, 21 | 20, 21 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 21-22 | tb501220kv¦21¦22 | National Construction | AP-21 | AP-22 | 2025-08-04 | 2025-05-19 | 77 | 77 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 21, 22 | 21, 22 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 22-23 | tb501220kv¦22¦23 | National Construction | AP-22 | AP-23 | 2025-08-08 | 2025-08-19 | -11 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 22, 23 | 22, 23 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 23-24 | tb501220kv¦23¦24 | National Construction | AP-23 | AP-24 | 2025-09-04 | 2025-08-19 | 16 | 16 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 23, 24 | 23, 24 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 24-25 | tb501220kv¦24¦25 | National Construction | AP-24 | AP-25 | 2025-10-04 | 2025-07-26 | 70 | 70 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 24, 25 | 24, 25 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 25-26 | tb501220kv¦25¦26 | National Construction | AP-25 | AP-26 | 2025-09-13 | 2025-07-26 | 49 | 49 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 25, 26 | 25, 26 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 26-27 | tb501220kv¦26¦27 | National Construction | AP-26 | AP-27 | 2025-10-06 | 2025-07-26 | 72 | 72 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 26, 27 | 26, 27 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 27-28 | tb501220kv¦27¦28 | National Construction | AP-27 | AP-28 | 2025-11-02 | 2025-07-26 | 99 | 99 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 27, 28 | 27, 28 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 28-28/1 | tb501220kv¦28¦28/1 | National Construction | AP-28 | 28/1 | 2025-11-02 | 2025-10-22 | 11 | 11 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 28, 28/1 | 28, 28/1 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 28/1-28/2 | tb501220kv¦28/1¦28/2 | National Construction | 28/1 | 28/2 | 2025-11-02 | 2025-10-22 | 11 | 11 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 28/1, 28/2 | 28/1, 28/2 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 28/2-29 | tb501220kv¦28/2¦29 | National Construction | 28/2 | AP-29 | 2025-09-16 | 2025-08-17 | 30 | 30 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 28/2, 29 | 28/2, 29 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | C | 29-29A/0 | tb501220kv¦29¦29A/0 | National Construction | AP-29 | 29A/0 | 2025-09-15 | 2025-08-14 | 32 | 32 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29, 29A/0 | 29, 29A/0 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 29A/0-30 | tb501220kv¦29A/0¦30 | National Construction | 29A/0 | AP-30 | 2025-07-16 | 2025-08-14 | -29 |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 29A/0, 30 | 29A/0, 30 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | C | 30-31 | tb501220kv¦30¦31 | Kohinoor | AP-30 | AP-31 | 2025-07-08 | 2025-03-06 | 124 | 124 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 30, 31 | 30, 31 |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 1900-01-02 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Unassigned | [5 empty] | 1900-01-14 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Unassigned | [5 empty] | 1900-01-05 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 501 - 220kV | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [5 empty] | 0 |  |  |  | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 0 | 0 | 0 |  |  |  |  | TRUE
TB 507 - MAIN | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 146/0-145/0 | tb507main¦146/0¦145/0 | Mahadev Enterprises | 146/0 | 145/0 | 2026-02-14 | 2025-11-17 | 89 | 89 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 7 | 6 | 1 | 146/0, 145/0, 145/1, 145/2, 145/3, 145/4, 145/5 | 146/0, 145/0, 145/1, 145/2, 145/3, 145/4 | 145/5 | 145/1,2,3,4,5 | TRUE
TB 507 - MAIN | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 149A/0-149/0 | tb507main¦149A/0¦149/0 | Mahadev Enterprises | 149A/0 | 149/0 | 2026-03-01 | 2025-10-15 | 137 | 137 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 149A/0, 149/0 | 149A/0, 149/0 |  | 149/0 | TRUE
TB 507 - MAIN | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 149/0-148/0 | tb507main¦149/0¦148/0 | Mahadev Enterprises | 149/0 | 148/0 | 2026-02-01 | 2025-11-21 | 72 | 72 | LOCATION_NOS | FALSE | OK |  | 9 | 9 | 0 | 149/0, 148/0, 148/1, 148/2, 148/3, 148/4, 148/5, 148/6, 148/7 | 149/0, 148/0, 148/1, 148/2, 148/3, 148/4, 148/5, 148/6, 148/7 |  | 148/1,2,3,4,5,6,7 | TRUE
TB 507 - MAIN | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 150/0-149B/3 | tb507main¦150/0¦149B/3 | Mahadev Enterprises | 150/0 | 149B/3 | 2026-02-26 | 2025-12-07 | 81 | 81 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 150/0, 149B/3 | 150/0, 149B/3 |  | 149B/3 | TRUE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 149B/0-149A/0 | tb507main¦149B/0¦149A/0 | Mahadev Enterprises | 149B/0 | 149A/0 | 2026-03-05 | 2025-11-28 | 97 | 97 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 149B/0, 149A/0 | 149B/0, 149A/0 |  | 149A/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 149B/3-149B/0 | tb507main¦149B/3¦149B/0 | Mahadev Enterprises | 149B/3 | 149B/0 | 2026-03-05 | 2025-11-28 | 97 | 97 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 149B/3, 149B/0, 149B/1, 149B/2 | 149B/3, 149B/0, 149B/1, 149B/2 |  | 149B/0,1,2 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 144/0-143/0 | tb507main¦144/0¦143/0 | Mahadev Enterprises | 144/0 | 143/0 | 2026-03-23 | 2025-10-08 | 166 | 166 | HYBRID_PARTIAL_FALLBACK | TRUE | OK |  | 8 | 7 | 1 | 144/0, 143/0, 143/1, 143/2, 143/3, 143/45, 143/6, 143/7 | 144/0, 143/0, 143/1, 143/2, 143/3, 143/6, 143/7 | 143/45 | 143/0,1,2,3,45,6,7 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 145/0-144/0 | tb507main¦145/0¦144/0 | Mahadev Enterprises | 145/0 | 144/0 | 2026-04-09 | 2025-11-17 | 143 | 143 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 145/0, 144/0 | 145/0, 144/0 |  | 144/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 113/0-112/0 | tb507main¦113/0¦112/0 | Mahadev Maan Construction | 113/0 | 112/0 | 2026-04-09 | 2026-01-17 | 82 | 82 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 113/0, 112/0 | 113/0, 112/0 |  | 113/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 153/0-152/0 | tb507main¦153/0¦152/0 | Mahadev Enterprises | 153/0 | 152/0 | 2026-04-16 | 2026-01-04 | 102 | 102 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 153/0, 152/0 | 153/0, 152/0 |  | 152/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 113A/0-113/0 | tb507main¦113A/0¦113/0 | Mahadev Maan Construction | 113A/0 | 113/0 | 2026-04-10 | 2026-01-17 | 83 | 83 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 113A/0, 113/0 | 113A/0, 113/0 |  | 113A/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 147/0-146/0 | tb507main¦147/0¦146/0 | Mahadev Enterprises | 147/0 | 146/0 | 2026-02-18 | 2025-10-12 | 129 | 129 | LOCATION_NOS | FALSE | OK |  | 4 | 4 | 0 | 147/0, 146/0, 146/1, 146/2 | 147/0, 146/0, 146/1, 146/2 |  | 146/0,1,2 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 148/0-147/0 | tb507main¦148/0¦147/0 | Mahadev Enterprises | 148/0 | 147/0 | 2026-04-09 | 2025-11-21 | 139 | 139 | LOCATION_NOS | FALSE | OK |  | 11 | 11 | 0 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 | 148/0, 147/0, 147/1, 147/2, 147/3, 147/4, 147/5, 147/6, 147/7, 147/8, 147/9 |  | 147/0,1,2,3,4,5,6,7,8,9 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 151/0-150/0 | tb507main¦151/0¦150/0 | Mahadev Enterprises | 151/0 | 150/0 | 2026-04-27 | 2025-12-14 | 134 | 134 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 151/0, 150/0 | 151/0, 150/0 |  | 150/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 152/0-151/0 | tb507main¦152/0¦151/0 | Mahadev Enterprises | 152/0 | 151/0 | 2026-04-28 | 2025-12-14 | 135 | 135 | LOCATION_NOS | FALSE | OK |  | 2 | 2 | 0 | 152/0, 151/0 | 152/0, 151/0 |  | 151/0 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 134/0-133/0 | tb507main¦134/0¦133/0 | Mahadev Enterprises | 134/0 | 133/0 | 2026-04-29 | 2025-11-20 | 160 | 160 | LOCATION_NOS | FALSE | OK |  | 10 | 10 | 0 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 | 134/0, 133/0, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 133/8 |  | 133/1,2,3,4,5,6,7,8 | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 143/0-142/0 | tb507main¦143/0¦142/0 | Mahadev Enterprises | 143/0 | 142/0 | 2026-03-23 | 2025-10-07 | 167 | 167 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 143/0, 142/0 | 143/0, 142/0 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 134/0-134A/0 | tb507main¦134/0¦134A/0 |  | 134/0 | 134A/0 | 2026-05-12 | 2025-10-29 | 195 | 195 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 134/0, 134A/0 | 134/0, 134A/0 |  |  | FALSE
TB 507 - MAIN |  |  |  |  | TB 507 | 5xx | TB |  | Ready | 114/0-113A/0 | tb507main¦114/0¦113A/0 | Tanisha Enterprises | 114/0 | 113A/0 | 2026-05-13 | 2026-01-24 | 109 | 109 | ALPHABETIC_FALLBACK | TRUE | EMPTY |  | 2 | 2 | 0 | 114/0, 113A/0 | 114/0, 113A/0 |  |  | FALSE

## POFS Delay Summary
POFS Delay Summary
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Average Lag Days | Median Lag Days | % Lag >15 Days | Negative Lag Excluded
OVERALL | All Projects | All | 1302 | 577 | 44.3 | 8.5 | 3 | 15.6 | 148
OVERALL | All Projects | TSE | 897 | 366 | 40.8 | 9.6 | 4 | 17.5 | 51
OVERALL | All Projects | Others | 405 | 211 | 52.1 | 5.5 | 2 | 10.5 | 97
PROJECT | TA 325 | All | 232 | 224 | 96.6 | 6.8 | 3 | 10.6 | 92
PROJECT | TA 413 | All | 38 | 26 | 68.4 | 11 | 8 | 20 | 1
PROJECT | TA 414 | All | 172 | 11 | 6.4 | 0.8 | 0.5 | 0 | 7
PROJECT | TA 416 | All | 79 | 65 | 82.3 | 6.2 | 1 | 11.5 | 4
PROJECT | TA 418 | All | 43 | 18 | 41.9 | 22.1 | 16.5 | 50 | 10
PROJECT | TA 421 | All | 76 | 41 | 53.9 | 10.2 | 6 | 17.2 | 12
PROJECT | TA 504 | All | 53 | 7 | 13.2 | 4 | 3 | 0 | 0
PROJECT | TA 505 | All | 232 | 9 | 3.9 | 11.8 | 6 | 11.1 | 0
PROJECT | TB 401 - PKG-G | All | 77 | 64 | 83.1 | 16.7 | 9 | 30.2 | 11
PROJECT | TB 501 - 132kV | All | 47 | 30 | 63.8 | 1.8 | 1 | 0 | 7
PROJECT | TB 501 - 220kV | All | 226 | 74 | 32.7 | 6.7 | 2 | 18.1 | 2
PROJECT | TB 507 | All | 2 | 0 | 0 |  |  |  | 0
PROJECT | TB 507 - MAIN | All | 25 | 8 | 32 | 13.5 | 7 | 33.3 | 2
SERIES | 4xx | All | 485 | 225 | 46.4 | 11.2 | 5 | 20.6 | 45
SERIES | 5xx | All | 585 | 128 | 21.9 | 6.3 | 2 | 13.7 | 11
SERIES | Other | All | 232 | 224 | 96.6 | 6.8 | 3 | 10.6 | 92
CLIENT_TYPE | TA | All | 925 | 401 | 43.4 | 7.9 | 3 | 13.1 | 126
CLIENT_TYPE | TB | All | 377 | 176 | 46.7 | 9.7 | 3 | 20.1 | 22

## POFS Delay Coverage
POFS Delay Coverage
Scope Type | Scope Name | Method Split | Spans Considered | Spans With Computable Lag | Lag Coverage % | Negative Lag Excluded | Negative Gap Flag Rows | Missing PO Completion Rows | Missing FS Start Rows | Average Lag Days | Median Lag Days
OVERALL | All Projects | All | 1302 | 577 | 44.3 | 148 | 148 | 709 | 717 | 8.5 | 3
OVERALL | All Projects | TSE | 897 | 366 | 40.8 | 51 | 51 | 521 | 529 | 9.6 | 4
OVERALL | All Projects | Others | 405 | 211 | 52.1 | 97 | 97 | 188 | 188 | 5.5 | 2
PROJECT | TA 325 | All | 232 | 224 | 96.6 | 92 | 92 | 8 | 4 | 6.8 | 3
PROJECT_METHOD | TA 325 | TSE | 71 | 69 | 97.2 | 10 | 10 | 2 | 2 | 8.1 | 4
PROJECT_METHOD | TA 325 | Others | 161 | 155 | 96.3 | 82 | 82 | 6 | 2 | 5.7 | 2
PROJECT | TA 413 | All | 38 | 26 | 68.4 | 1 | 1 | 12 | 12 | 11 | 8
PROJECT_METHOD | TA 413 | TSE | 33 | 23 | 69.7 | 1 | 1 | 10 | 10 | 9.2 | 8
PROJECT_METHOD | TA 413 | Others | 5 | 3 | 60 | 0 | 0 | 2 | 2 | 24 | 21
PROJECT | TA 414 | All | 172 | 11 | 6.4 | 7 | 7 | 161 | 161 | 0.8 | 0.5
PROJECT_METHOD | TA 414 | TSE | 41 | 4 | 9.8 | 2 | 2 | 37 | 37 | 1.5 | 1.5
PROJECT_METHOD | TA 414 | Others | 131 | 7 | 5.3 | 5 | 5 | 124 | 124 | 0 | 0
PROJECT | TA 416 | All | 79 | 65 | 82.3 | 4 | 4 | 13 | 14 | 6.2 | 1
PROJECT_METHOD | TA 416 | TSE | 47 | 36 | 76.6 | 2 | 2 | 10 | 11 | 8.6 | 2
PROJECT_METHOD | TA 416 | Others | 32 | 29 | 90.6 | 2 | 2 | 3 | 3 | 3.3 | 1
PROJECT | TA 418 | All | 43 | 18 | 41.9 | 10 | 10 | 23 | 25 | 22.1 | 16.5
PROJECT_METHOD | TA 418 | TSE | 28 | 12 | 42.9 | 5 | 5 | 15 | 16 | 24.3 | 18
PROJECT_METHOD | TA 418 | Others | 15 | 6 | 40 | 5 | 5 | 8 | 9 | 7 | 7
PROJECT | TA 421 | All | 76 | 41 | 53.9 | 12 | 12 | 35 | 34 | 10.2 | 6
PROJECT_METHOD | TA 421 | TSE | 55 | 36 | 65.5 | 9 | 9 | 19 | 19 | 10.5 | 6
PROJECT_METHOD | TA 421 | Others | 21 | 5 | 23.8 | 3 | 3 | 16 | 15 | 6.5 | 6.5
PROJECT | TA 504 | All | 53 | 7 | 13.2 | 0 | 0 | 43 | 46 | 4 | 3
PROJECT_METHOD | TA 504 | TSE | 27 | 6 | 22.2 | 0 | 0 | 19 | 21 | 4.5 | 3.5
PROJECT_METHOD | TA 504 | Others | 26 | 1 | 3.8 | 0 | 0 | 24 | 25 | 1 | 1
PROJECT | TA 505 | All | 232 | 9 | 3.9 | 0 | 0 | 222 | 223 | 11.8 | 6
PROJECT_METHOD | TA 505 | TSE | 230 | 7 | 3 | 0 | 0 | 222 | 223 | 12.7 | 4
PROJECT_METHOD | TA 505 | Others | 2 | 2 | 100 | 0 | 0 | 0 | 0 | 8.5 | 8.5
PROJECT | TB 401 - PKG-G | All | 77 | 64 | 83.1 | 11 | 11 | 11 | 12 | 16.7 | 9
PROJECT_METHOD | TB 401 - PKG-G | TSE | 77 | 64 | 83.1 | 11 | 11 | 11 | 12 | 16.7 | 9
PROJECT_METHOD | TB 401 - PKG-G | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 132kV | All | 47 | 30 | 63.8 | 7 | 7 | 17 | 16 | 1.8 | 1
PROJECT_METHOD | TB 501 - 132kV | TSE | 47 | 30 | 63.8 | 7 | 7 | 17 | 16 | 1.8 | 1
PROJECT_METHOD | TB 501 - 132kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 501 - 220kV | All | 226 | 74 | 32.7 | 2 | 2 | 151 | 152 | 6.7 | 2
PROJECT_METHOD | TB 501 - 220kV | TSE | 226 | 74 | 32.7 | 2 | 2 | 151 | 152 | 6.7 | 2
PROJECT_METHOD | TB 501 - 220kV | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 507 | All | 2 | 0 | 0 | 0 | 0 | 2 | 2
PROJECT_METHOD | TB 507 | TSE | 2 | 0 | 0 | 0 | 0 | 2 | 2
PROJECT_METHOD | TB 507 | Others | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT | TB 507 - MAIN | All | 25 | 8 | 32 | 2 | 2 | 11 | 16 | 13.5 | 7
PROJECT_METHOD | TB 507 - MAIN | TSE | 13 | 5 | 38.5 | 2 | 2 | 6 | 8 | 22.3 | 25
PROJECT_METHOD | TB 507 - MAIN | Others | 12 | 3 | 25 | 0 | 0 | 5 | 8 | 4.7 | 5
SERIES | 4xx | All | 485 | 225 | 46.4 | 45 | 45 | 255 | 258 | 11.2 | 5
SERIES | 5xx | All | 585 | 128 | 21.9 | 11 | 11 | 446 | 455 | 6.3 | 2
SERIES | Other | All | 232 | 224 | 96.6 | 92 | 92 | 8 | 4 | 6.8 | 3
CLIENT_TYPE | TA | All | 925 | 401 | 43.4 | 126 | 126 | 517 | 519 | 7.9 | 3
CLIENT_TYPE | TB | All | 377 | 176 | 46.7 | 22 | 22 | 192 | 198 | 9.7 | 3

## POFS Delay Anomalies
POFS Delay Anomalies
Project | Project Scope Key | Series | Client Type | Method Split | Span Key | From AP | To AP | PO Completion Date | FS Starting Date | Gap Days | Issue | Negative Gap Flag
TA 325 | ta325 | Other | TA | Others | ta325¦120/0¦121/0 | 120/0 | 121/0 | 2025-01-01 | 2024-12-28 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦144A/0¦145/0 | 144A/0 | 145/0 | 2025-01-13 | 2024-01-08 | -371 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦147/1¦147/2 | 147/1 | 147/2 | 2025-01-16 | 2025-01-15 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦124A/0¦124A/1 | 124A/0 | 124A/1 | 2025-02-19 | 2025-02-15 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦124A/1¦125/0 | 124A/1 | 125/0 | 2025-02-19 | 2025-02-15 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦131/0¦132/0 | 131/0 | 132/0 | 2025-03-10 | 2025-03-06 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦134/0¦135/0 | 134/0 | 135/0 | 2025-03-22 | 2025-03-18 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦163/5¦163/6 | 163/5 | 163/6 | 2025-03-22 | 2025-03-21 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦143A/2¦143A/3 | 143A/2 | 143A/3 | 2025-03-24 | 2025-03-23 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦136/0¦137/0 | 136/0 | 137/0 | 2025-04-01 | 2025-03-26 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦146/0¦147/0 | 146/0 | 147/0 | 2025-04-15 | 2025-04-12 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦147/0¦147/1 | 147/0 | 147/1 | 2025-04-15 | 2025-04-11 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦145/0¦145A/0 | 145/0 | 145A/0 | 2025-04-23 | 2025-04-18 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦161/0¦162/0 | 161/0 | 162/0 | 2025-05-06 | 2025-04-28 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦151/0¦152/0 | 151/0 | 152/0 | 2025-05-15 | 2025-05-11 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦147/2¦147A/0 | 147/2 | 147A/0 | 2025-05-18 | 2025-05-16 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦150/0¦150/1 | 150/0 | 150/1 | 2025-05-25 | 2025-05-23 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦156/0¦157/0 | 156/0 | 157/0 | 2025-06-04 | 2025-06-03 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦152A/0¦153/0 | 152A/0 | 153/0 | 2025-09-10 | 2025-09-06 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦158A/0¦158B/0 | 158A/0 | 158B/0 | 2025-10-21 | 2025-10-07 | -14 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦276/0¦Gty | 276/0 | Gty | 2025-10-21 | 2025-10-18 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦192/0¦193/0 | 192/0 | 193/0 | 2025-10-23 | 2025-10-19 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦193/0¦194/0 | 193/0 | 194/0 | 2025-10-25 | 2025-10-21 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦194/0¦195/0 | 194/0 | 195/0 | 2025-10-29 | 2025-10-24 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦204/0¦205/0 | 204/0 | 205/0 | 2025-11-03 | 2025-10-26 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦196/0¦197/0 | 196/0 | 197/0 | 2025-11-04 | 2025-10-26 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦275/0¦276/0 | 275/0 | 276/0 | 2025-11-04 | 2025-10-26 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦157/0¦158/0 | 157/0 | 158/0 | 2025-11-11 | 2025-11-07 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦190/0¦191/0 | 190/0 | 191/0 | 2025-11-12 | 2025-11-08 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦176/0¦177/0 | 176/0 | 177/0 | 2025-11-12 | 2025-11-06 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦177/0¦178/0 | 177/0 | 178/0 | 2025-11-12 | 2025-11-10 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦248/0¦249/0 | 248/0 | 249/0 | 2025-11-10 | 2025-11-07 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦169/0¦171/0 | 169/0 | 171/0 | 2025-11-18 | 2025-11-08 | -10 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦181/0¦182/0 | 181/0 | 182/0 | 2025-11-17 | 2025-11-14 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦179/0¦180/0 | 179/0 | 180/0 | 2025-11-21 | 2025-11-16 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦188/0¦189/0 | 188/0 | 189/0 | 2025-11-21 | 2025-11-16 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦198/0¦199/0 | 198/0 | 199/0 | 2025-11-19 | 2025-11-18 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦246/0¦247/0 | 246/0 | 247/0 | 2025-11-23 | 2025-11-20 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦205/0¦206/0 | 205/0 | 206/0 | 2025-11-24 | 2025-11-21 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦230/0¦231/0 | 230/0 | 231/0 | 2025-11-25 | 2025-11-24 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦231/0¦232/0 | 231/0 | 232/0 | 2025-11-28 | 2025-11-26 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦233/0¦234/0 | 233/0 | 234/0 | 2025-11-29 | 2025-11-26 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦232/0¦233/0 | 232/0 | 233/0 | 2025-11-30 | 2025-11-26 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦234/0¦235/0 | 234/0 | 235/0 | 2025-11-30 | 2025-11-26 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦180/0¦181/0 | 180/0 | 181/0 | 2025-12-01 | 2025-11-20 | -11 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦210/0¦211/0 | 210/0 | 211/0 | 2025-12-03 | 2025-11-28 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦222/1¦223/0 | 222/1 | 223/0 | 2025-12-04 | 2025-12-02 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦209/0¦210/0 | 209/0 | 210/0 | 2025-12-04 | 2025-12-02 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦235/0¦236/0 | 235/0 | 236/0 | 2025-12-05 | 2025-12-03 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦171/0¦172/0 | 171/0 | 172/0 | 2025-12-06 | 2025-11-27 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦226/0¦227/0 | 226/0 | 227/0 | 2025-12-07 | 2025-12-04 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦184/0¦184/1 | 184/0 | 184/1 | 2025-12-08 | 2025-12-04 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦184/1¦185/0 | 184/1 | 185/0 | 2025-12-08 | 2025-12-04 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦236/0¦237/0 | 236/0 | 237/0 | 2025-12-08 | 2025-12-03 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦240/0¦241/0 | 240/0 | 241/0 | 2025-12-10 | 2025-12-07 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦239/0¦240/0 | 239/0 | 240/0 | 2025-12-11 | 2025-12-07 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦182/0¦182A/0 | 182/0 | 182A/0 | 2025-12-13 | 2025-12-11 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦219/0¦220/0 | 219/0 | 220/0 | 2025-12-13 | 2025-12-08 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦211/0¦211A/0 | 211/0 | 211A/0 | 2025-12-13 | 2025-12-11 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦212/0¦213/0 | 212/0 | 213/0 | 2025-12-14 | 2025-12-10 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦229/0¦229/1 | 229/0 | 229/1 | 2025-12-15 | 2025-12-07 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦160/0¦161/0 | 160/0 | 161/0 | 2025-12-16 | 2025-12-13 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦182A/0¦183/0 | 182A/0 | 183/0 | 2025-12-20 | 2025-12-15 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦183/0¦184/0 | 183/0 | 184/0 | 2025-12-20 | 2025-12-15 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦272/5¦272A/0 | 272/5 | 272A/0 | 2025-12-20 | 2025-12-18 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦199/0¦200/0 | 199/0 | 200/0 | 2025-12-22 | 2025-12-20 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦200/0¦201/0 | 200/0 | 201/0 | 2025-12-22 | 2025-12-20 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦227/0¦228/0 | 227/0 | 228/0 | 2025-12-18 | 2025-12-17 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦228/0¦229/0 | 228/0 | 229/0 | 2025-12-22 | 2025-12-17 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦105/0¦106/0 | 105/0 | 106/0 | 2025-12-25 | 2025-12-24 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦201/0¦201/1 | 201/0 | 201/1 | 2025-12-26 | 2025-12-23 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦272A/0¦273/0 | 272A/0 | 273/0 | 2025-12-25 | 2025-12-22 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | TSE | ta325¦211A/0¦212/0 | 211A/0 | 212/0 | 2025-12-25 | 2025-12-10 | -15 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦175/0¦175/1 | 175/0 | 175/1 | 2025-12-27 | 2025-12-23 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦175/1¦176/0 | 175/1 | 176/0 | 2025-12-27 | 2025-12-24 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦167/0¦167/1 | 167/0 | 167/1 | 2025-12-29 | 2025-12-27 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦208/0¦209/0 | 208/0 | 209/0 | 2025-12-23 | 2025-12-18 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦217/0¦217A/0 | 217/0 | 217A/0 | 2025-12-31 | 2025-12-29 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦221/0¦222/0 | 221/0 | 222/0 | 2025-12-31 | 2025-12-27 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦222/0¦222/1 | 222/0 | 222/1 | 2025-12-31 | 2025-12-25 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦201/1¦202/0 | 201/1 | 202/0 | 2026-01-04 | 2025-12-29 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦202/0¦203/0 | 202/0 | 203/0 | 2026-01-04 | 2025-12-30 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦154/1¦155/0 | 154/1 | 155/0 | 2026-01-05 | 2025-12-30 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦159/0¦159/2 | 159/0 | 159/2 | 2026-01-05 | 2026-01-03 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦173/0¦174/0 | 173/0 | 174/0 | 2026-01-05 | 2025-12-31 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦174/0¦174/1 | 174/0 | 174/1 | 2026-01-06 | 2026-01-03 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦174/1¦175/0 | 174/1 | 175/0 | 2026-01-06 | 2026-01-03 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦206/0¦208/0 | 206/0 | 208/0 | 2026-01-09 | 2025-12-18 | -22 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦216/0¦217/0 | 216/0 | 217/0 | 2026-01-09 | 2026-01-01 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦186/0¦187/0 | 186/0 | 187/0 | 2026-01-11 | 2026-01-10 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦215/0¦215/1 | 215/0 | 215/1 | 2026-01-14 | 2026-01-13 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦215/1¦216/0 | 215/1 | 216/0 | 2026-01-14 | 2026-01-13 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 325 | ta325 | Other | TA | Others | ta325¦101/0¦102/0 | 101/0 | 102/0 |  | 2026-01-16 |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | Others | ta325¦102/0¦103/0 | 102/0 | 103/0 |  | 2026-01-16 |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | Others | ta325¦103/0¦104/0 | 103/0 | 104/0 |  | 2026-01-16 |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | Others | ta325¦104/0¦105/0 | 104/0 | 105/0 |  | 2026-01-17 |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | Others | ta325¦153/0¦154/0 | 153/0 | 154/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | Others | ta325¦154/0¦154/1 | 154/0 | 154/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 325 | ta325 | Other | TA | TSE | ta325¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | ta413¦Section¦ | Section |  |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | ta413¦From¦To | From | To |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | ta413¦9/0¦10/0 | 9/0 | 10/0 | 2026-04-02 | 2026-03-06 | -27 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 413 | ta413 | 4xx | TA | Others | ta413¦13/0¦13A/0 | 13/0 | 13A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | Others | ta413¦11/0¦12/0 | 11/0 | 12/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | ta413¦27/0¦28/0 | 27/0 | 28/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 413 | ta413 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦117/0¦118/0 | 117/0 | 118/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦118/0¦119/0 | 118/0 | 119/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦119/0¦120/0 | 119/0 | 120/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦121/0¦121/1 | 121/0 | 121/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦121/1¦121/7 | 121/1 | 121/7 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦121/7¦124/0 | 121/7 | 124/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦124/0¦125/0 | 124/0 | 125/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦125/0¦126/0 | 125/0 | 126/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦126/0¦127/0 | 126/0 | 127/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦127/0¦127/2 | 127/0 | 127/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦127/2¦128/0 | 127/2 | 128/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦128/0¦129/0 | 128/0 | 129/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦129/0¦130/0 | 129/0 | 130/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦130/0¦131/0 | 130/0 | 131/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦131/0¦132/0 | 131/0 | 132/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦132/0¦133/0 | 132/0 | 133/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦133/0¦133/2 | 133/0 | 133/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦133/2¦133/3 | 133/2 | 133/3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦133/3¦134/0 | 133/3 | 134/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦134/0¦135/0 | 134/0 | 135/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦135/0¦136/0 | 135/0 | 136/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦136/0¦136/1 | 136/0 | 136/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦136/1¦137/0 | 136/1 | 137/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦137/0¦138/0 | 137/0 | 138/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦138/0¦139/0 | 138/0 | 139/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦139/0¦139/2 | 139/0 | 139/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦139/2¦139/3 | 139/2 | 139/3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦139/3¦140/0 | 139/3 | 140/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦140/0¦141/0 | 140/0 | 141/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦141/0¦142/0 | 141/0 | 142/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦142/0¦143/0 | 142/0 | 143/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦143/0¦144/0 | 143/0 | 144/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦144/0¦145/0 | 144/0 | 145/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦145/0¦145/7 | 145/0 | 145/7 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦145/7¦147/0 | 145/7 | 147/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦147/0¦148/0 | 147/0 | 148/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦148/0¦148/5 | 148/0 | 148/5 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦148/5¦149/0 | 148/5 | 149/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦149/0¦150/0 | 149/0 | 150/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦150/0¦150/1 | 150/0 | 150/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦150/1¦151/0 | 150/1 | 151/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦151/0¦151A/0 | 151/0 | 151A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦151A/0¦152/0 | 151A/0 | 152/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦152/0¦153/0 | 152/0 | 153/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦153/0¦153A/0 | 153/0 | 153A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦153A/0¦154/0 | 153A/0 | 154/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦154/0¦155/0 | 154/0 | 155/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦155/0¦156/0 | 155/0 | 156/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦156/0¦156/1 | 156/0 | 156/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦156/1¦157/0 | 156/1 | 157/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦157/0¦158/0 | 157/0 | 158/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦158/0¦159/0 | 158/0 | 159/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦159/0¦160/0 | 159/0 | 160/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦160/0¦161/0 | 160/0 | 161/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦161/0¦162/0 | 161/0 | 162/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦162/0¦163/0 | 162/0 | 163/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦163/0¦163/1 | 163/0 | 163/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦163/1¦164/0 | 163/1 | 164/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦164/0¦165/0 | 164/0 | 165/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦165/0¦165/6 | 165/0 | 165/6 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦165/6¦166/0 | 165/6 | 166/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦166/0¦167/0 | 166/0 | 167/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦167/0¦168/0 | 167/0 | 168/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦168/0¦169/0 | 168/0 | 169/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦169/0¦170/0 | 169/0 | 170/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦170/0¦171/0 | 170/0 | 171/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦171/0¦172/0 | 171/0 | 172/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦172/0¦173/0 | 172/0 | 173/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦173/0¦174/0 | 173/0 | 174/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦174/0¦175/0 | 174/0 | 175/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦175/0¦175/1 | 175/0 | 175/1 | 2026-05-07 | 2026-05-03 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦175/1¦176/0 | 175/1 | 176/0 | 2026-04-12 | 2026-04-07 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦176/0¦177/0 | 176/0 | 177/0 | 2026-04-27 | 2026-04-24 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦178/0¦179/0 | 178/0 | 179/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦179/0¦180/0 | 179/0 | 180/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦180/0¦180/2 | 180/0 | 180/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦182/0¦183/0 | 182/0 | 183/0 | 2026-04-11 | 2026-04-05 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦183/0¦184/0 | 183/0 | 184/0 | 2026-04-21 | 2026-04-20 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦184/0¦185/0 | 184/0 | 185/0 | 2026-05-13 | 2026-05-06 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | Others | ta414¦185/0¦186/0 | 185/0 | 186/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦186/0¦187/0 | 186/0 | 187/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦187/0¦188/0 | 187/0 | 188/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦188/0¦189/0 | 188/0 | 189/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦189/0¦190/0 | 189/0 | 190/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦190/0¦191/0 | 190/0 | 191/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦191/0¦191/1 | 191/0 | 191/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦191/1¦192/0 | 191/1 | 192/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦192/0¦193/0 | 192/0 | 193/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦193/0¦194/0 | 193/0 | 194/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦194/0¦194/1 | 194/0 | 194/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦194/1¦195/0 | 194/1 | 195/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦195/0¦196/0 | 195/0 | 196/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦196/0¦197/0 | 196/0 | 197/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦197/0¦198/0 | 197/0 | 198/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦198/0¦199/0 | 198/0 | 199/0 | 2026-04-23 | 2026-04-17 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦199/0¦200/0 | 199/0 | 200/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦200/0¦201/0 | 200/0 | 201/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦201/0¦202/0 | 201/0 | 202/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦202/0¦203/0 | 202/0 | 203/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦203/0¦203A/0 | 203/0 | 203A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦203A/0¦203B/0 | 203A/0 | 203B/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦203B/0¦204/0 | 203B/0 | 204/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦204/0¦205/0 | 204/0 | 205/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦205/0¦205/1 | 205/0 | 205/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦205/1¦206/0 | 205/1 | 206/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦206/0¦206/1 | 206/0 | 206/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦206/1¦207/0 | 206/1 | 207/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦207/0¦208/0 | 207/0 | 208/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦208/0¦209/0 | 208/0 | 209/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦209/0¦210/0 | 209/0 | 210/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦210/0¦211/0 | 210/0 | 211/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦211/0¦211/5 | 211/0 | 211/5 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦211/5¦212/0 | 211/5 | 212/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦212/0¦213/0 | 212/0 | 213/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦213/0¦214/0 | 213/0 | 214/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦214/0¦215/0 | 214/0 | 215/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦215/0¦216/0 | 215/0 | 216/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦216/0¦216/2 | 216/0 | 216/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦216/2¦217/0 | 216/2 | 217/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦217/0¦218/0 | 217/0 | 218/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦218/0¦219/0 | 218/0 | 219/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦219/0¦220/0 | 219/0 | 220/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦220/0¦221/0 | 220/0 | 221/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦221/0¦222/0 | 221/0 | 222/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦222/0¦223/0 | 222/0 | 223/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦223/0¦224/0 | 223/0 | 224/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦224/0¦224/2 | 224/0 | 224/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦224/2¦225/0 | 224/2 | 225/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦225/0¦226/0 | 225/0 | 226/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦226/0¦227/0 | 226/0 | 227/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦227/0¦228/0 | 227/0 | 228/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦228/0¦229/0 | 228/0 | 229/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦229/0¦229A/0 | 229/0 | 229A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦229A/0¦229B/0 | 229A/0 | 229B/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦229B/0¦230/0 | 229B/0 | 230/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦230/0¦230A/0 | 230/0 | 230A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦230A/0¦231/0 | 230A/0 | 231/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦231/0¦232/0 | 231/0 | 232/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦232/0¦233/0 | 232/0 | 233/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦233/0¦234/0 | 233/0 | 234/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦234/0¦235/0 | 234/0 | 235/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦235/0¦236/0 | 235/0 | 236/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦236/0¦237/0 | 236/0 | 237/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦237/0¦238/0 | 237/0 | 238/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦238/0¦239/0 | 238/0 | 239/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦239/0¦240/0 | 239/0 | 240/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦240/0¦241/0 | 240/0 | 241/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦241/0¦242/0 | 241/0 | 242/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦242/0¦243/0 | 242/0 | 243/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦243/0¦244/0 | 243/0 | 244/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦244/0¦245/0 | 244/0 | 245/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦246/0¦247/0 | 246/0 | 247/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦247/0¦248/0 | 247/0 | 248/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦248/0¦248/1 | 248/0 | 248/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦248/1¦249/0 | 248/1 | 249/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦249/0¦250/0 | 249/0 | 250/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦250/0¦250A/0 | 250/0 | 250A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦250A/0¦251/0 | 250A/0 | 251/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦251/0¦252/0 | 251/0 | 252/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | TSE | ta414¦252/0¦252/5 | 252/0 | 252/5 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦252/5¦253/0 | 252/5 | 253/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦253/0¦254/0 | 253/0 | 254/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦254/0¦254/1 | 254/0 | 254/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦254/1¦255/0 | 254/1 | 255/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦255/0¦256/0 | 255/0 | 256/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦256/0¦257/0 | 256/0 | 257/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦257/0¦258/0 | 257/0 | 258/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 414 | ta414 | 4xx | TA | Others | ta414¦258/0¦Gantry | 258/0 | Gantry |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | Others | ta416¦37/0¦38/0 | AP37/0 | AP38/0 | 2025-12-10 | 2025-12-06 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | Others | ta416¦24/0¦25/0 | AP24/0 | AP25/0 | 2025-12-30 | 2025-12-29 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦25/0¦26/0 | AP25/0 | AP26/0 | 2026-01-31 | 2026-01-27 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦52/1¦53/0 | AP52/1 | AP53/0 | 2026-03-31 | 2026-03-28 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 416 | ta416 | 4xx | TA | Others | ta416¦61/0¦62/0 | AP61/0 | AP62/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦64/0¦65/0 | AP64/0 | AP65/0 | 2026-04-17 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | Others | ta416¦47/0¦48/0 | AP47/0 | AP48/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦57/0¦58/0 | AP57/0 | AP58/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | Others | ta416¦60/0¦61/0 | AP60/0 | AP61/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 416 | ta416 | 4xx | TA | TSE | ta416¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦32¦33 | AP32 | AP33 | 2026-02-22 | 2026-02-16 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦33¦33/5 | AP33 | 33/5 | 2026-02-09 | 2026-02-07 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦33/5¦33/6 | 33/5 | 33/6 | 2026-01-30 | 2026-01-26 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦33/6¦34/0 | 33/6 | 34/0 | 2026-01-27 | 2026-01-26 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦36/1¦37/0 | 36/1 | 37/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦37/0¦38 | 37/0 | AP38 | 2026-05-12 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦38¦39 | AP38 | AP39 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦39¦40 | AP39 | AP40 | 2026-02-10 | 2026-02-09 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦43¦44 | AP43 | AP44 | 2026-03-11 | 2026-03-09 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦44¦45 | AP44 | AP45 | 2026-03-18 | 2026-03-14 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦45¦45/1 | AP45 | 45/1 | 2026-03-12 | 2026-03-06 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦46¦46/7 | AP46 | 46/7 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦46/7¦47/0 | 46/7 | AP47/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦47/0¦48 | AP47/0 | AP48 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦48¦48A/0 | AP48 | 48A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦48A/0¦49/0 | 48A/0 | 49/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦49/0¦50 | 49/0 | AP50 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦50¦51 | AP50 | AP51 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦51¦52 | AP51 | AP52 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦52¦53 | AP52 | AP53 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦53¦54 | AP53 | AP54 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦54¦55 | AP54 | AP55 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦55¦56 | AP55 | AP56 | 2026-05-03 | 2026-05-02 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | Others | ta418¦56/3¦57/0 | 56/3 | 57/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦57/0¦58/0 | 57/0 | 58/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦58/0¦59/0 | 58/0 | 59/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦59/0¦60/0 | 59/0 | 60/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦60/0¦61/0 | 60/0 | 61/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦61/0¦62/0 | 61/0 | 62/0 | 2026-04-15 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦62/0¦63/0 | 62/0 | 63/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | Others | ta418¦63/0¦GNTY | 63/0 | GNTY | 2026-04-18 | 2026-04-16 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 418 | ta418 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 418 | ta418 | 4xx | TA | TSE | ta418¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦31/0¦32/0 | 31/0 | 32/0 | 2025-06-17 | 2025-06-13 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦30/0¦31/0 | 30/0 | 31/0 | 2025-07-02 | 2025-06-23 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | Others | ta421¦29/9¦30/0 | 29/9 | 30/0 | 2025-07-11 | 2025-07-07 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | Others | ta421¦20A/0¦21/0 | 20A/0 | 21/0 | 2025-08-31 | 2025-08-24 | -7 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦20/0¦20A/0 | 20/0 | 20A/0 | 2025-09-01 | 2025-08-24 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦19/0¦20/0 | 19/0 | 20/0 | 2025-10-19 | 2025-09-17 | -32 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦18/0¦19/0 | 18/0 | 19/0 | 2025-10-20 | 2025-09-22 | -28 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | Others | ta421¦14/0¦15/0 | 14/0 | 15/0 | 2025-12-17 | 2025-12-15 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦27/3¦28/0 | 27/3 | 28/0 | 2026-01-28 | 2026-01-22 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | Others | ta421¦7/0¦8/0 | 7/0 | 8/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦Gantry¦1/0 | Gantry | 1/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦8/2¦8/3 | 8/2 | 8/3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦1/0¦1A/0 | 1/0 | 1A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦1A/0¦1B/0 | 1A/0 | 1B/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦8/0¦8/1 | 8/0 | 8/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦8/1¦8/2 | 8/1 | 8/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦1C/0¦2/0 | 1C/0 | 2/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦5/0¦6/0 | 5/0 | 6/0 |  | 2026-03-02 |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦2/0¦3/0 | 2/0 | 3/0 | 2026-03-20 | 2026-03-17 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦39/0¦40/0 | 39/0 | 40/0 | 2026-03-31 | 2026-03-29 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦43/0¦43A/0 | 43/0 | 43A/0 | 2026-05-16 | 2026-05-15 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TA 421 | ta421 | 4xx | TA | Others | ta421¦34/2¦35/0 | 34/2 | 35/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦35/0¦36/0 | 35/0 | 36/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦34/1¦34/2 | 34/1 | 34/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦33/0¦34/0 | 33/0 | 34/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦43A/0¦43A/1 | 43A/0 | 43A/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦43A/1¦43B/0 | 43A/1 | 43B/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦34/0¦34/1 | 34/0 | 34/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦40/0¦41/0 | 40/0 | 41/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦41/0¦42/0 | 41/0 | 42/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | Others | ta421¦43B/0¦44/0 | 43B/0 | 44/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 421 | ta421 | 4xx | TA | TSE | ta421¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦1/0¦2/0 | 1/0 | 2/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦2/0¦3/0 | 2/0 | 3/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦3/0¦4/0 | 3/0 | 4/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦4/0¦5/0 | 4/0 | 5/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦5/0¦5A/0 | 5/0 | 5A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5A/0¦5B/0 | 5A/0 | 5B/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5B/0¦5B/1 | 5B/0 | 5B/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5B/1¦5C/0 | 5B/1 | 5C/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5C/0¦5D/0 | 5C/0 | 5D/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5D/0¦5E/0 | 5D/0 | 5E/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5E/0¦5F/0 | 5E/0 | 5F/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5F/0¦5G/0 | 5F/0 | 5G/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦5G/0¦5H/0 | 5G/0 | 5H/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦5H/0¦5I/0 | 5H/0 | 5I/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦5I/0¦6/0 | 5I/0 | 6/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦6/0¦7/0 | 6/0 | 7/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦7/0¦8/0 | 7/0 | 8/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦8/0¦8/3 | 8/0 | 8/3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦8/3¦9/0 | 8/3 | 9/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦9/0¦10/0 | 9/0 | 10/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦10/0¦10/1 | 10/0 | 10/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦10/1¦11/0 | 10/1 | 11/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦11/0¦12/0 | 11/0 | 12/0 | 2026-05-12 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦12/0¦13/0 | 12/0 | 13/0 | 2026-05-20 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦13/0¦14/0 | 13/0 | 14/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦14/0¦15/0 | 14/0 | 15/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦19/0¦20/0 | 19/0 | 20/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦20/0¦21/0 | 20/0 | 21/0 | 2026-05-17 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦21/0¦21/3 | 21/0 | 21/3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦21/3¦22/0 | 21/3 | 22/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦22/0¦23/0 | 22/0 | 23/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦23/0¦24/0 | 23/0 | 24/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦24/0¦24/1 | 24/0 | 24/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦24/1¦24/2. | 24/1 | 24/2. |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦24/2.¦25/0 | 24/2. | 25/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦25/0¦26/0 | 25/0 | 26/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦26/0¦27/0 | 26/0 | 27/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦27/0¦28/0 | 27/0 | 28/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦28/0¦28/1 | 28/0 | 28/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦28/1¦29/0 | 28/1 | 29/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦29/0¦30/0 | 29/0 | 30/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | TSE | ta504¦30/0¦31/0 | 30/0 | 31/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦31/0¦31/2 | 31/0 | 31/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦31/2¦32/0 | 31/2 | 32/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦32/0¦32/2 | 32/0 | 32/2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 504 | ta504 | 5xx | TA | Others | ta504¦32/2¦33/0 | 32/2 | 33/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | ta505¦114/0¦115/0 | 114/0 | 115/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | ta505¦110A/0¦111/0 | 110A/0 | 111/0 | 2026-05-18 |  |  | FS_STARTING_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | ta505¦110/0¦110A/0 | 110/0 | 110A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TA 505 | ta505 | 5xx | TA | TSE | ta505¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦58/0¦58/7 | 58/0 | 58/7 | 2024-11-23 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦42/0¦43/0 | 42/0 | 43/0 | 2025-05-11 | 2025-05-07 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦49/0¦50/0 | 49/0 | 50/0 | 2025-05-17 | 2025-05-15 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦62/0¦63/0 | 62/0 | 63/0 | 2025-07-10 | 2025-07-07 | -3 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦Gantry¦1/0 | Gantry | 1/0 | 2025-10-17 | 2025-10-09 | -8 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦33/0¦34/0 | 33/0 | 34/0 | 2025-10-27 | 2025-10-23 | -4 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦36/0¦37/0 | 36/0 | 37/0 | 2025-11-08 | 2025-10-30 | -9 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦60/0¦61/0 | 60/0 | 61/0 | 2025-11-11 | 2025-11-10 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦45/0¦46/0 | 45/0 | 46/0 | 2025-11-26 | 2025-11-14 | -12 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦37/0¦37/1 | 37/0 | 37/1 | 2025-11-30 | 2025-11-29 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦37/1¦37/2 | 37/1 | 37/2 | 2025-11-30 | 2025-11-29 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦5/0¦6/0 | 5/0 | 6/0 | 2025-12-11 | 2025-12-05 | -6 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦6/0¦7/0 | 6/0 | 7/0 | 2025-12-18 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦27/1¦28/0 | 27/1 | 28/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦9/0¦10/0 | 9/0 | 10/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦17/0¦18/0 | 17/0 | 18/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦10/12¦10/20 | 10/12 | 10/20 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦70/0¦71/0 | 70/0 | 71/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦14/0¦15/0 | 14/0 | 15/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦3/0¦4/0 | 3/0 | 4/0 |  | 2025-12-23 |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | tb401pkgg¦22/0¦23/0 | 22/0 | 23/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 401 - PKG-G | tb401pkgg | 4xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Hydro GTY¦Existing Tower-1 | Hydro GTY | Existing Tower-1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Existing Tower-1¦Exting Tower-2 | Existing Tower-1 | Exting Tower-2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exting Tower-2¦Exting Tower-3 | Exting Tower-2 | Exting Tower-3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exting Tower-3¦Exting Tower-4 | Exting Tower-3 | Exting Tower-4 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exting Tower-4¦Exting Tower-5 | Exting Tower-4 | Exting Tower-5 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exting Tower-5¦Exting Tapping Tower-6 | Exting Tower-5 | Exting Tapping Tower-6 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exting Tapping Tower-6¦Exting Tower-7 | Exting Tapping Tower-6 | Exting Tower-7 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Exiting Tower-7¦SC-5 | Exiting Tower-7 | SC-5 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦SC-5¦SC-4 | SC-5 | SC-4 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦SC-4¦Sc-3 | SC-4 | Sc-3 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦Sc-3¦SC-2 | Sc-3 | SC-2 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦SC-2¦SC-1 | SC-2 | SC-1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦SC-1¦1/0 | SC-1 | 1/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦1/0¦2/0 | 1/0 | 2/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦2/0¦2/1 | 2/0 | 2/1 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦2/1¦3/0 | 2/1 | 3/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦10/0¦11/0 | 10/0 | 11/0 |  | 2026-05-18 |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦15/0¦15/1 | 15/0 | 15/1 | 2026-03-09 | 2026-03-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦15/1¦15/2 | 15/1 | 15/2 | 2026-03-09 | 2026-03-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦15/2¦15/3 | 15/2 | 15/3 | 2026-03-09 | 2026-03-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦15/3¦16/0 | 15/3 | 16/0 | 2026-03-09 | 2026-03-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦16/0¦16/1 | 16/0 | 16/1 | 2026-03-06 | 2026-03-05 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦17/0¦18/0 | 17/0 | 18/0 | 2026-03-03 | 2026-03-02 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 132kV | tb501132kv | 5xx | TB | TSE | tb501132kv¦18/0¦Gantry | 18/0 | Gantry | 2026-02-21 | 2026-02-20 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦Gnty¦0/0 | Gnty | 0/0 | 2026-02-02 | 2026-01-31 | -2 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦4/6¦4/7 | 4/6 | 4/7 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦4/7¦4/8 | 4/7 | 4/8 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦4/8¦4/9 | 4/8 | 4/9 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦15¦16 | AP-15 | AP-16 | 2025-06-25 | 2025-06-20 | -5 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦20¦21 | AP-20 | AP-21 | 2025-07-24 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦31¦32 | AP-31 | AP-32 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦32¦33/0 | AP-32 | 33/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | tb501220kv¦33/0¦34/0 | 33/0 | 34/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 501 - 220kV | tb501220kv | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 | tb507 | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 | tb507 | 5xx | TB | TSE | tb507¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦149B/3¦149B/0 | 149B/3 | 149B/0 | 2026-03-09 | 2026-03-08 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦144/0¦143/0 | 144/0 | 143/0 | 2026-04-04 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦145/0¦144/0 | 145/0 | 144/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦113/0¦112/0 | 113/0 | 112/0 | 2026-04-10 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦153/0¦152/0 | 153/0 | 152/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦113A/0¦113/0 | 113A/0 | 113/0 | 2026-04-10 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦148/0¦147/0 | 148/0 | 147/0 | 2026-04-20 | 2026-04-19 | -1 | NEGATIVE_LAG_EXCLUDED | TRUE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦151/0¦150/0 | 151/0 | 150/0 |  | 2026-04-25 |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦152/0¦151/0 | 152/0 | 151/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦134/0¦133/0 | 134/0 | 133/0 | 2026-05-13 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦143/0¦142/0 | 143/0 | 142/0 | 2026-03-26 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦134/0¦134A/0 | 134/0 | 134A/0 | 2026-05-13 |  |  | FS_STARTING_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | Others | tb507main¦114/0¦113A/0 | 114/0 | 113A/0 |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | tb507main¦¦Total |  | Total |  |  |  | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE
TB 507 - MAIN | tb507main | 5xx | TB | TSE | [6 empty] | PO_COMPLETION_DATE_MISSING | FALSE

## POFS Delay Detail
POFS Delay Detail
Project | Project Code | Project Display | Project Scope Key | Join Project Key | Base Project Code | Series | Client Type | Method Split | Section | Span | Span Key | Gang Name | From AP | To AP | PO Completion Date | FS Starting Date | Gap Days | Gap Days Non-Negative | Negative Gap Flag | Has PO Completion Date | Has FS Starting Date
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 112/0-113/0 | ta325¦112/0¦113/0 | Muslehuddin | 112/0 | 113/0 | 2024-08-15 | 2024-08-17 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 111/0-112/0 | ta325¦111/0¦112/0 | Gokul Sarkar | 111/0 | 112/0 | 2024-09-24 | 2024-10-02 | 8 | 8 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 110/0-111/0 | ta325¦110/0¦111/0 | Gokul Sarkar | 110/0 | 111/0 | 2024-09-12 | 2024-10-04 | 22 | 22 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 113/0-114/0 | ta325¦113/0¦114/0 | Muslehuddin | 113/0 | 114/0 | 2024-09-29 | 2024-10-01 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 109/0-110/0 | ta325¦109/0¦110/0 | Gokul Sarkar | 109/0 | 110/0 | 2024-09-09 | 2024-10-10 | 31 | 31 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116/0-116A/0 | ta325¦116/0¦116A/0 | Gokul Sarkar | 116/0 | 116A/0 | 2024-10-18 | 2024-10-26 | 8 | 8 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 108/0-109/0 | ta325¦108/0¦109/0 | Muslehuddin | 108/0 | 109/0 | 2024-10-20 | 2024-10-25 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 107/0-108/0 | ta325¦107/0¦108/0 | Muslehuddin | 107/0 | 108/0 | 2024-11-02 | 2024-11-04 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 133/0-133A/0 | ta325¦133/0¦133A/0 | Rejaul | 133/0 | 133A/0 | 2024-11-02 | 2024-11-03 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 121/0-122/0 | ta325¦121/0¦122/0 | Gokul Sarkar | 121/0 | 122/0 | 2024-11-03 | 2024-11-18 | 15 | 15 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 129A/0-130/0 | ta325¦129A/0¦130/0 | Rejaul | 129A/0 | 130/0 | 2024-11-18 | 2024-11-21 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 106B/0-107/0 | ta325¦106B/0¦107/0 | Muslehuddin | 106B/0 | 107/0 | 2024-11-16 | 2024-11-20 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 122/0-123/0 | ta325¦122/0¦123/0 | Dhervendra Electricals | 122/0 | 123/0 | 2024-11-26 | 2024-11-28 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 118/0-119/0 | ta325¦118/0¦119/0 | Enamul Haque | 118/0 | 119/0 | 2024-11-25 | 2024-12-02 | 7 | 7 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 117/0-118/0 | ta325¦117/0¦118/0 | Enamul Haque | 117/0 | 118/0 | 2024-12-13 | 2024-12-18 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 119/0-120/0 | ta325¦119/0¦120/0 | Muslehuddin | 119/0 | 120/0 | 2024-12-20 | 2024-12-21 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116B/0-117/0 | ta325¦116B/0¦117/0 | Yakub Ali + Enamul | 116B/0 | 117/0 | 2024-12-18 | 2024-12-23 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 144/0-144A/0 | ta325¦144/0¦144A/0 | Gokul Sarkar | 144/0 | 144A/0 | 2024-12-19 | 2024-12-22 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 120/0-121/0 | ta325¦120/0¦121/0 | Dhervendra Electricals | 120/0 | 121/0 | 2025-01-01 | 2024-12-28 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 114/0-115/0 | ta325¦114/0¦115/0 | Muslehuddin | 114/0 | 115/0 | 2024-12-28 | 2024-12-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 115/0-116/0 | ta325¦115/0¦116/0 | Muslehuddin | 115/0 | 116/0 | 2024-12-28 | 2024-12-31 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 133A/0-134/0 | ta325¦133A/0¦134/0 | Rejaul + Rafikul | 133A/0 | 134/0 | 2025-01-01 | 2025-01-02 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 123/0-124/0 | ta325¦123/0¦124/0 | Enamul Haque | 123/0 | 124/0 | 2024-12-30 | 2025-01-05 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 116A/0-116B/0 | ta325¦116A/0¦116B/0 | Muslehuddin | 116A/0 | 116B/0 | 2025-01-11 | 2025-01-12 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 144A/0-145/0 | ta325¦144A/0¦145/0 | Dhervendra Electricals | 144A/0 | 145/0 | 2025-01-13 | 2024-01-08 | -371 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147/1-147/2 | ta325¦147/1¦147/2 | Gokul Sarkar | 147/1 | 147/2 | 2025-01-16 | 2025-01-15 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 127/0-128/0 | ta325¦127/0¦128/0 | Muslehuddin + Enamul | 127/0 | 128/0 | 2024-12-13 | 2025-01-17 | 35 | 35 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 126/0-127/0 | ta325¦126/0¦127/0 | Enamul Haque | 126/0 | 127/0 | 2025-01-11 | 2025-01-23 | 12 | 12 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 132/0-133/0 | ta325¦132/0¦133/0 | Rejaul + enamul | 132/0 | 133/0 | 2025-01-14 | 2025-01-21 | 7 | 7 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 259/0-260/0 | ta325¦259/0¦260/0 | Dharmendra Electrical | 259/0 | 260/0 | 2025-01-24 | 2025-01-26 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 260/0-261/0 | ta325¦260/0¦261/0 | Monera | 260/0 | 261/0 | 2025-01-25 | 2025-01-26 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 125A/0-126/0 | ta325¦125A/0¦126/0 | Enamul Haque | 125A/0 | 126/0 | 2025-01-18 | 2025-02-04 | 17 | 17 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 106A/0-106B/0 | ta325¦106A/0¦106B/0 | Muslehuddin | 106A/0 | 106B/0 | 2025-02-01 | 2025-02-04 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 125/0-125A/0 | ta325¦125/0¦125A/0 | Enamul Haque | 125/0 | 125A/0 | 2025-02-02 | 2025-02-06 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 128/0-129/0 | ta325¦128/0¦129/0 | Alam Construction | 128/0 | 129/0 | 2025-02-10 | 2025-02-12 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 129/0-129A/0 | ta325¦129/0¦129A/0 | Alam Construction | 129/0 | 129A/0 | 2025-02-10 | 2025-02-12 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 135A/0-135A/1 | ta325¦135A/0¦135A/1 | SK Zenarul | 135A/0 | 135A/1 | 2025-01-21 | 2025-02-06 | 16 | 16 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135A/2-135B/0 | ta325¦135A/2¦135B/0 | Rafikul Alam construction + Enamul | 135A/2 | 135B/0 | 2025-02-06 | 2025-02-12 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135B/0-136/0 | ta325¦135B/0¦136/0 | Rafikul Alam construction + Enamul | 135B/0 | 136/0 | 2025-01-29 | 2025-02-12 | 14 | 14 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 106/0-106A/0 | ta325¦106/0¦106A/0 | Muslehuddin | 106/0 | 106A/0 | 2025-02-05 | 2025-02-14 | 9 | 9 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 164/0-165/0 | ta325¦164/0¦165/0 | Manik Sarkar | 164/0 | 165/0 | 2025-02-10 | 2025-02-12 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 135A/1-135A/2 | ta325¦135A/1¦135A/2 | SK Zenarul | 135A/1 | 135A/2 | 2025-02-02 | 2025-02-07 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124/0-124A/0 | ta325¦124/0¦124A/0 | Enamul Haque | 124/0 | 124A/0 | 2025-02-13 | 2025-02-16 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124A/0-124A/1 | ta325¦124A/0¦124A/1 | Enamul Haque | 124A/0 | 124A/1 | 2025-02-19 | 2025-02-15 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 124A/1-125/0 | ta325¦124A/1¦125/0 | Dhervendra Electricals | 124A/1 | 125/0 | 2025-02-19 | 2025-02-15 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 257/0-259/0 | ta325¦257/0¦259/0 | Monera | 257/0 | 259/0 | 2025-02-13 | 2025-02-21 | 8 | 8 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 137A/0-138/0 | ta325¦137A/0¦138/0 | Alam Construction | 137A/0 | 138/0 | 2025-02-25 | 2025-02-28 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 138/0-139/0 | ta325¦138/0¦139/0 | Enamul Haque | 138/0 | 139/0 | 2025-03-01 | 2025-03-02 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 261/0-262/0 | ta325¦261/0¦262/0 | Dharmendra Electrical | 261/0 | 262/0 | 2025-03-04 | 2025-03-06 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 139/0-139A/0 | ta325¦139/0¦139A/0 | SK Zenarul | 139/0 | 139A/0 | 2025-03-04 | 2025-03-07 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 130/0-131/0 | ta325¦130/0¦131/0 | Muslehuddin | 130/0 | 131/0 | 2025-03-05 | 2025-03-07 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 131/0-132/0 | ta325¦131/0¦132/0 | Dhervendra Electricals | 131/0 | 132/0 | 2025-03-10 | 2025-03-06 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 139A/0-140/0 | ta325¦139A/0¦140/0 | SK Zenarul | 139A/0 | 140/0 | 2025-03-05 | 2025-03-07 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 262/0-263/0 | ta325¦262/0¦263/0 | Monera | 262/0 | 263/0 | 2025-02-19 | 2025-03-12 | 21 | 21 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 263/0-264/0 | ta325¦263/0¦264/0 | Dharmendra Electrical | 263/0 | 264/0 | 2025-03-12 | 2025-03-13 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 142/0-143/0 | ta325¦142/0¦143/0 | Enamul + Alam Constrution | 142/0 | 143/0 | 2025-03-18 | 2025-03-18 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143/0-143A/0 | ta325¦143/0¦143A/0 | Alam Construction | 143/0 | 143A/0 | 2025-03-09 | 2025-03-20 | 11 | 11 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 255/0-257/0 | ta325¦255/0¦257/0 | Kamruddin | 255/0 | 257/0 | 2025-02-25 | 2025-03-20 | 23 | 23 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 265/0-266/0 | ta325¦265/0¦266/0 | Dharmendra Electrical | 265/0 | 266/0 | 2025-03-18 | 2025-03-19 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 134/0-135/0 | ta325¦134/0¦135/0 | Dhervendra Electricals | 134/0 | 135/0 | 2025-03-22 | 2025-03-18 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 163/0-163/5 | ta325¦163/0¦163/5 | Manik Sarkar | 163/0 | 163/5 | 2025-02-28 | 2025-03-21 | 21 | 21 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 163/5-163/6 | ta325¦163/5¦163/6 | Dhervendra Electricals | 163/5 | 163/6 | 2025-03-22 | 2025-03-21 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 163/6-164/0 | ta325¦163/6¦164/0 | Manik Sarkar | 163/6 | 164/0 | 2025-03-08 | 2025-03-21 | 13 | 13 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 264/0-265/0 | ta325¦264/0¦265/0 | Monera | 264/0 | 265/0 | 2025-03-18 | 2025-03-19 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143A/0-143A/2 | ta325¦143A/0¦143A/2 | Alam Construction | 143A/0 | 143A/2 | 2025-03-21 | 2025-03-23 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 143A/2-143A/3 | ta325¦143A/2¦143A/3 | Enamul Haque | 143A/2 | 143A/3 | 2025-03-24 | 2025-03-23 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 143A/3-144/0 | ta325¦143A/3¦144/0 | Enamul Haque | 143A/3 | 144/0 | 2025-03-20 | 2025-03-23 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 266/0-266/1 | ta325¦266/0¦266/1 | Dharmendra Electrical | 266/0 | 266/1 | 2025-03-24 | 2025-03-25 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 266/1-267/0 | ta325¦266/1¦267/0 | Monera | 266/1 | 267/0 | 2025-03-24 | 2025-03-25 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 136/0-137/0 | ta325¦136/0¦137/0 | Dhervendra Electricals | 136/0 | 137/0 | 2025-04-01 | 2025-03-26 | -6 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 137/0-137A/0 | ta325¦137/0¦137A/0 | Rafikul Alam construction | 137/0 | 137A/0 | 2025-03-09 | 2025-03-26 | 17 | 17 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 145A/0-146/0 | ta325¦145A/0¦146/0 | Enamul Haque | 145A/0 | 146/0 | 2025-04-04 | 2025-04-07 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 253/0-254/0 | ta325¦253/0¦254/0 | Dharmendra Electrical | 253/0 | 254/0 | 2025-04-06 | 2025-04-07 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 254/0-255/0 | ta325¦254/0¦255/0 | Monera | 254/0 | 255/0 | 2025-02-28 | 2025-04-07 | 38 | 38 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 267/0-267A/0 | ta325¦267/0¦267A/0 | Kamruddin Deepak Sarkar | 267/0 | 267A/0 | 2025-04-03 | 2025-04-07 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 267A/0-268/0 | ta325¦267A/0¦268/0 | Kamruddin | 267A/0 | 268/0 | 2025-03-29 | 2025-04-07 | 9 | 9 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 141/0-141/1 | ta325¦141/0¦141/1 | Alam Construction | 141/0 | 141/1 | 2025-04-09 | 2025-04-11 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 141/1-141/2 | ta325¦141/1¦141/2 | Dhervendra Electricals | 141/1 | 141/2 | 2025-04-09 | 2025-04-11 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 141/2-142/0 | ta325¦141/2¦142/0 | Alam Construction | 141/2 | 142/0 | 2025-04-09 | 2025-04-11 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 146/0-147/0 | ta325¦146/0¦147/0 | Enamul Haque | 146/0 | 147/0 | 2025-04-15 | 2025-04-12 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147/0-147/1 | ta325¦147/0¦147/1 | Dhervendra Electricals | 147/0 | 147/1 | 2025-04-15 | 2025-04-11 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 147B/0-148/0 | ta325¦147B/0¦148/0 | Muslehuddinn + GPJ | 147B/0 | 148/0 | 2025-04-05 | 2025-04-13 | 8 | 8 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 152/0-152A/0 | ta325¦152/0¦152A/0 | Alongir | 152/0 | 152A/0 | 2025-04-09 | 2025-04-13 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 270/0-270A/0 | ta325¦270/0¦270A/0 | Kamruddin & Deepak | 270/0 | 270A/0 | 2025-04-14 | 2025-04-14 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 145/0-145A/0 | ta325¦145/0¦145A/0 | Dhervendra Electricals | 145/0 | 145A/0 | 2025-04-23 | 2025-04-18 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 268/0-269/0 | ta325¦268/0¦269/0 | Dharmendra Electrical | 268/0 | 269/0 | 2025-04-19 | 2025-04-21 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 269/0-270/0 | ta325¦269/0¦270/0 | Kamruddin & Maidul rahman | 269/0 | 270/0 | 2025-04-08 | 2025-04-18 | 10 | 10 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 270A/0-271/0 | ta325¦270A/0¦271/0 | Alamgir | 270A/0 | 271/0 | 2025-04-15 | 2025-04-21 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 271/0-272/0 | ta325¦271/0¦272/0 | Kamruddin & Deepak | 271/0 | 272/0 | 2025-04-20 | 2025-04-21 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 148/0-149/0 | ta325¦148/0¦149/0 | Muslehuddin | 148/0 | 149/0 | 2025-04-21 | 2025-04-24 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 149/0-150/0 | ta325¦149/0¦150/0 | Enamul Haque | 149/0 | 150/0 | 2025-04-23 | 2025-04-24 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 162/0-163/0 | ta325¦162/0¦163/0 | Manik Sarkar | 162/0 | 163/0 | 2025-04-13 | 2025-04-23 | 10 | 10 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 147A/0-147B/0 | ta325¦147A/0¦147B/0 | Enamul Haque | 147A/0 | 147B/0 | 2025-04-30 | 2025-04-30 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 135/0-135A/0 | ta325¦135/0¦135A/0 | RafikulAlam Construction | 135/0 | 135A/0 | 2025-03-24 | 2025-04-28 | 35 | 35 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 251/0-252/0 | ta325¦251/0¦252/0 | Dharmendra Electrical | 251/0 | 252/0 | 2025-05-01 | 2025-05-02 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 161/0-162/0 | ta325¦161/0¦162/0 | Dhervendra Electricals | 161/0 | 162/0 | 2025-05-06 | 2025-04-28 | -8 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 252/0-253/0 | ta325¦252/0¦253/0 | Deepak Sarkar | 252/0 | 253/0 | 2025-04-19 | 2025-05-04 | 15 | 15 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 250/0-251/0 | ta325¦250/0¦251/0 | Deepak Sarkar | 250/0 | 251/0 | 2025-05-05 | 2025-05-08 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 249/0-250/0 | ta325¦249/0¦250/0 | Kamruddin | 249/0 | 250/0 | 2025-05-03 | 2025-05-09 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 150A/0-151/0 | ta325¦150A/0¦151/0 | Alam Construction | 150A/0 | 151/0 | 2025-04-29 | 2025-05-12 | 13 | 13 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 151/0-152/0 | ta325¦151/0¦152/0 | Dhervendra Electricals | 151/0 | 152/0 | 2025-05-15 | 2025-05-11 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 147/2-147A/0 | ta325¦147/2¦147A/0 | Rafikul Alam + Alam Const. + Enamul | 147/2 | 147A/0 | 2025-05-18 | 2025-05-16 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 140/0-141/0 | ta325¦140/0¦141/0 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 140/0 | 141/0 | 2025-05-22 | 2025-05-23 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 150/0-150/1 | ta325¦150/0¦150/1 | Dhervendra Electricals | 150/0 | 150/1 | 2025-05-25 | 2025-05-23 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 150/1-150A/0 | ta325¦150/1¦150A/0 | Alam Construction | 150/1 | 150A/0 | 2025-05-11 | 2025-05-23 | 12 | 12 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 156/0-157/0 | ta325¦156/0¦157/0 | Deepak Sarkar + Manik Sarkar | 156/0 | 157/0 | 2025-06-04 | 2025-06-03 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272/0-272/5 | ta325¦272/0¦272/5 | Kamruddin & Deepak Sarkar | 272/0 | 272/5 | 2025-03-15 | 2025-06-13 | 90 | 90 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 155/0-156/0 | ta325¦155/0¦156/0 | Deepak Sarkar + Manik Sarkar | 155/0 | 156/0 | 2025-06-11 | 2025-06-14 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 152A/0-153/0 | ta325¦152A/0¦153/0 | Alam Construction | 152A/0 | 153/0 | 2025-09-10 | 2025-09-06 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 158B/0-159/0 | ta325¦158B/0¦159/0 | Deepak Sarkar | 158B/0 | 159/0 | 2025-09-27 | 2025-10-02 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 158A/0-158B/0 | ta325¦158A/0¦158B/0 | Dharmendra 1 | 158A/0 | 158B/0 | 2025-10-21 | 2025-10-07 | -14 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 276/0-Gty | ta325¦276/0¦Gty | Bhola | 276/0 | Gty | 2025-10-21 | 2025-10-18 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 158/0-158A/0 | ta325¦158/0¦158A/0 | Deepak Sarkar | 158/0 | 158A/0 | 2025-10-13 | 2025-10-17 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 192/0-193/0 | ta325¦192/0¦193/0 | Teklal Saw | 192/0 | 193/0 | 2025-10-23 | 2025-10-19 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 193/0-194/0 | ta325¦193/0¦194/0 | Ramsingh Yadav | 193/0 | 194/0 | 2025-10-25 | 2025-10-21 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 194/0-195/0 | ta325¦194/0¦195/0 | Enamul Haque | 194/0 | 195/0 | 2025-10-29 | 2025-10-24 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 191/0-191/2 | ta325¦191/0¦191/2 | Alam Construction | 191/0 | 191/2 | 2025-10-25 | 2025-10-25 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 191/2-191/3 | ta325¦191/2¦191/3 | Alam Construction | 191/2 | 191/3 | 2025-10-25 | 2025-10-25 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 191/3-191A/0 | ta325¦191/3¦191A/0 | Alam Construction | 191/3 | 191A/0 | 2025-10-25 | 2025-10-25 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 191A/0-192/0 | ta325¦191A/0¦192/0 | Md Anwar | 191A/0 | 192/0 | 2025-10-19 | 2025-10-24 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 204/0-205/0 | ta325¦204/0¦205/0 | Dharmendra 2 | 204/0 | 205/0 | 2025-11-03 | 2025-10-26 | -8 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 195/0-195A/0 | ta325¦195/0¦195A/0 | Enamul Haque | 195/0 | 195A/0 | 2025-10-26 | 2025-10-31 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 196/0-197/0 | ta325¦196/0¦197/0 | Ramsingh Yadav | 196/0 | 197/0 | 2025-11-04 | 2025-10-26 | -9 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 275/0-276/0 | ta325¦275/0¦276/0 | Dharmendra 1 | 275/0 | 276/0 | 2025-11-04 | 2025-10-26 | -9 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 195A/0-196/0 | ta325¦195A/0¦196/0 | Muslehuddin | 195A/0 | 196/0 | 2025-10-18 | 2025-10-29 | 11 | 11 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 157/0-158/0 | ta325¦157/0¦158/0 | Deepak Sarkar | 157/0 | 158/0 | 2025-11-11 | 2025-11-07 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 190/0-191/0 | ta325¦190/0¦191/0 | Ramsingh Yadav | 190/0 | 191/0 | 2025-11-12 | 2025-11-08 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 176/0-177/0 | ta325¦176/0¦177/0 | Sanjay Singh | 176/0 | 177/0 | 2025-11-12 | 2025-11-06 | -6 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 177/0-178/0 | ta325¦177/0¦178/0 | Ruhul Amin / Alam Constr. | 177/0 | 178/0 | 2025-11-12 | 2025-11-10 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 178/0-179/0 | ta325¦178/0¦179/0 | Giyash | 178/0 | 179/0 | 2025-11-09 | 2025-11-10 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 189/0-190/0 | ta325¦189/0¦190/0 | Md Anwar | 189/0 | 190/0 | 2025-11-07 | 2025-11-10 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 248/0-249/0 | ta325¦248/0¦249/0 | Kamaruddin | 248/0 | 249/0 | 2025-11-10 | 2025-11-07 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 197/0-198/0 | ta325¦197/0¦198/0 | Muslehuddin | 197/0 | 198/0 | 2025-11-12 | 2025-11-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 224/0-225/0 | ta325¦224/0¦225/0 | Dharmendra 2 | 224/0 | 225/0 | 2025-11-12 | 2025-11-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 241/0-242/0 | ta325¦241/0¦242/0 | Singhvahini | 241/0 | 242/0 | 2025-11-12 | 2025-11-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 243/0-244/0 | ta325¦243/0¦244/0 | Dharmendra 1 | 243/0 | 244/0 | 2025-11-12 | 2025-11-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 168/0-169/0 | ta325¦168/0¦169/0 | Rafikul Alam constr. | 168/0 | 169/0 | 2025-11-08 | 2025-11-15 | 7 | 7 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 169/0-171/0 | ta325¦169/0¦171/0 | Ramavat Electricals | 169/0 | 171/0 | 2025-11-18 | 2025-11-08 | -10 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 181/0-182/0 | ta325¦181/0¦182/0 | Alam Construction | 181/0 | 182/0 | 2025-11-17 | 2025-11-14 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 242/0-243/0 | ta325¦242/0¦243/0 | Enamul Haque | 242/0 | 243/0 | 2025-11-18 | 2025-11-19 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 179/0-180/0 | ta325¦179/0¦180/0 | Sanjay Singh | 179/0 | 180/0 | 2025-11-21 | 2025-11-16 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 188/0-189/0 | ta325¦188/0¦189/0 | Ramsingh Yadav | 188/0 | 189/0 | 2025-11-21 | 2025-11-16 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 198/0-199/0 | ta325¦198/0¦199/0 | Muslehuddin | 198/0 | 199/0 | 2025-11-19 | 2025-11-18 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 244/0-244/1 | ta325¦244/0¦244/1 | Bhola Prasad | 244/0 | 244/1 | 2025-11-13 | 2025-11-19 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 246/0-247/0 | ta325¦246/0¦247/0 | Dharmendra 1 | 246/0 | 247/0 | 2025-11-23 | 2025-11-20 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 205/0-206/0 | ta325¦205/0¦206/0 | Deepak Sarkar | 205/0 | 206/0 | 2025-11-24 | 2025-11-21 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 230/0-231/0 | ta325¦230/0¦231/0 | Alam Construction / Enamul / Giyash / Alongir | 230/0 | 231/0 | 2025-11-25 | 2025-11-24 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 247/0-248/0 | ta325¦247/0¦248/0 | Kamruddinn | 247/0 | 248/0 | 2025-11-18 | 2025-11-23 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 244/1-245/0 | ta325¦244/1¦245/0 | Bhola Prasad | 244/1 | 245/0 | 2025-11-18 | 2025-11-23 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 231/0-232/0 | ta325¦231/0¦232/0 | Giyash / Alongir | 231/0 | 232/0 | 2025-11-28 | 2025-11-26 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 233/0-234/0 | ta325¦233/0¦234/0 | Singhvahini | 233/0 | 234/0 | 2025-11-29 | 2025-11-26 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 245/0-246/0 | ta325¦245/0¦246/0 | Kamruddinn / Bhola prasad | 245/0 | 246/0 | 2025-11-21 | 2025-11-27 | 6 | 6 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 232/0-233/0 | ta325¦232/0¦233/0 | Sanjay Singh | 232/0 | 233/0 | 2025-11-30 | 2025-11-26 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 234/0-235/0 | ta325¦234/0¦235/0 | Dharmendra 2 | 234/0 | 235/0 | 2025-11-30 | 2025-11-26 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 180/0-181/0 | ta325¦180/0¦181/0 | Ramavat Electricals -2 | 180/0 | 181/0 | 2025-12-01 | 2025-11-20 | -11 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 210/0-211/0 | ta325¦210/0¦211/0 | Ramsingh Yadav | 210/0 | 211/0 | 2025-12-03 | 2025-11-28 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 222/1-223/0 | ta325¦222/1¦223/0 | Ramsingh Yadav 2 | 222/1 | 223/0 | 2025-12-04 | 2025-12-02 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 209/0-210/0 | ta325¦209/0¦210/0 | Deepak Sarkar | 209/0 | 210/0 | 2025-12-04 | 2025-12-02 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 235/0-236/0 | ta325¦235/0¦236/0 | Singhvahini | 235/0 | 236/0 | 2025-12-05 | 2025-12-03 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 171/0-172/0 | ta325¦171/0¦172/0 | Ramavat Electricals 1& 2 | 171/0 | 172/0 | 2025-12-06 | 2025-11-27 | -9 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 226/0-227/0 | ta325¦226/0¦227/0 | Muslehuddin | 226/0 | 227/0 | 2025-12-07 | 2025-12-04 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 229/1-230/0 | ta325¦229/1¦230/0 | Teklal Saw | 229/1 | 230/0 | 2025-12-03 | 2025-12-04 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 184/0-184/1 | ta325¦184/0¦184/1 | Alam Construction | 184/0 | 184/1 | 2025-12-08 | 2025-12-04 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 184/1-185/0 | ta325¦184/1¦185/0 | Alam Construction | 184/1 | 185/0 | 2025-12-08 | 2025-12-04 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 225/0-226/0 | ta325¦225/0¦226/0 | Muslehuddin | 225/0 | 226/0 | 2025-11-29 | 2025-12-04 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 236/0-237/0 | ta325¦236/0¦237/0 | Dharmendra 1 | 236/0 | 237/0 | 2025-12-08 | 2025-12-03 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 237/0-239/0 | ta325¦237/0¦239/0 | Enamul Haque | 237/0 | 239/0 | 2025-12-03 | 2025-12-07 | 4 | 4 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 240/0-241/0 | ta325¦240/0¦241/0 | Enamul Haque | 240/0 | 241/0 | 2025-12-10 | 2025-12-07 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 239/0-240/0 | ta325¦239/0¦240/0 | Ramsingh Yadav | 239/0 | 240/0 | 2025-12-11 | 2025-12-07 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 165/0-165/4 | ta325¦165/0¦165/4 | Rafikul Alam | 165/0 | 165/4 | 2025-12-01 | 2025-12-08 | 7 | 7 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 187/0-188/0 | ta325¦187/0¦188/0 | Alam Construction | 187/0 | 188/0 | 2025-12-05 | 2025-12-10 | 5 | 5 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 274/0-275/0 | ta325¦274/0¦275/0 | Bhola Prasad | 274/0 | 275/0 | 2025-10-27 | 2025-12-09 | 43 | 43 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 182/0-182A/0 | ta325¦182/0¦182A/0 | Ramavat Electricals 2 | 182/0 | 182A/0 | 2025-12-13 | 2025-12-11 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 219/0-220/0 | ta325¦219/0¦220/0 | Sanjay Singh | 219/0 | 220/0 | 2025-12-13 | 2025-12-08 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 211/0-211A/0 | ta325¦211/0¦211A/0 | Deepak Sarkar | 211/0 | 211A/0 | 2025-12-13 | 2025-12-11 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 212/0-213/0 | ta325¦212/0¦213/0 | Ramsingh Yadav 2 | 212/0 | 213/0 | 2025-12-14 | 2025-12-10 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 229/0-229/1 | ta325¦229/0¦229/1 | Alongir | 229/0 | 229/1 | 2025-12-15 | 2025-12-07 | -8 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 160/0-161/0 | ta325¦160/0¦161/0 | Dharmendra 2 | 160/0 | 161/0 | 2025-12-16 | 2025-12-13 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 167/1-168/0 | ta325¦167/1¦168/0 | Rafikul Alam Construction | 167/1 | 168/0 | 2025-11-23 | 2025-12-14 | 21 | 21 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 223/0-224/0 | ta325¦223/0¦224/0 | Muslehuddin and Giyash | 223/0 | 224/0 | 2025-12-13 | 2025-12-14 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 218/0-219/0 | ta325¦218/0¦219/0 | Singhvahini | 218/0 | 219/0 | 2025-12-14 | 2025-12-16 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 182A/0-183/0 | ta325¦182A/0¦183/0 | Alam Construction | 182A/0 | 183/0 | 2025-12-20 | 2025-12-15 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 183/0-184/0 | ta325¦183/0¦184/0 | Ramavat Electricals 1 | 183/0 | 184/0 | 2025-12-20 | 2025-12-15 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 213/0-214/0 | ta325¦213/0¦214/0 | Kudus Ali | 213/0 | 214/0 | 2025-12-17 | 2025-12-18 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 203/1-204/0 | ta325¦203/1¦204/0 | Modia India | 203/1 | 204/0 | 2025-12-18 | 2025-12-19 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 220/0-221/0 | ta325¦220/0¦221/0 | Abdul Adut | 220/0 | 221/0 | 2025-12-16 | 2025-12-19 | 3 | 3 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272/5-272A/0 | ta325¦272/5¦272A/0 | Bhola Prasad & Kamruddin | 272/5 | 272A/0 | 2025-12-20 | 2025-12-18 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 199/0-200/0 | ta325¦199/0¦200/0 | Ramsingh Yadav | 199/0 | 200/0 | 2025-12-22 | 2025-12-20 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 200/0-201/0 | ta325¦200/0¦201/0 | Ramsingh Yadav 2 | 200/0 | 201/0 | 2025-12-22 | 2025-12-20 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 227/0-228/0 | ta325¦227/0¦228/0 | Munni Bibi 2 | 227/0 | 228/0 | 2025-12-18 | 2025-12-17 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 228/0-229/0 | ta325¦228/0¦229/0 | Sanjay Singh | 228/0 | 229/0 | 2025-12-22 | 2025-12-17 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 217A/0-218/0 | ta325¦217A/0¦218/0 | Teklal Saw | 217A/0 | 218/0 | 2025-12-19 | 2025-12-20 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 105/0-106/0 | ta325¦105/0¦106/0 | Kudus Ali 2 | 105/0 | 106/0 | 2025-12-25 | 2025-12-24 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 165/4-165/5 | ta325¦165/4¦165/5 | Munni Bibi 1 | 165/4 | 165/5 | 2025-12-22 | 2025-12-22 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 165/5-166/0 | ta325¦165/5¦166/0 | Munni Bibi 1 | 165/5 | 166/0 | 2025-12-15 | 2025-12-22 | 7 | 7 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 201/0-201/1 | ta325¦201/0¦201/1 | Modina India 2 | 201/0 | 201/1 | 2025-12-26 | 2025-12-23 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 272A/0-273/0 | ta325¦272A/0¦273/0 | Kamaruddin | 272A/0 | 273/0 | 2025-12-25 | 2025-12-22 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 273/0-274/0 | ta325¦273/0¦274/0 | Kamaruddin | 273/0 | 274/0 | 2025-12-11 | 2025-12-22 | 11 | 11 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 211A/0-212/0 | ta325¦211A/0¦212/0 | Deepak Sarkar | 211A/0 | 212/0 | 2025-12-25 | 2025-12-10 | -15 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 175/0-175/1 | ta325¦175/0¦175/1 | Dharmendra 2 | 175/0 | 175/1 | 2025-12-27 | 2025-12-23 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 175/1-176/0 | ta325¦175/1¦176/0 | Alam Construction | 175/1 | 176/0 | 2025-12-27 | 2025-12-24 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 167/0-167/1 | ta325¦167/0¦167/1 | Rafikul Alam | 167/0 | 167/1 | 2025-12-29 | 2025-12-27 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 208/0-209/0 | ta325¦208/0¦209/0 | Deepak Sarkar | 208/0 | 209/0 | 2025-12-23 | 2025-12-18 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 214/0-215/0 | ta325¦214/0¦215/0 | Kudus Ali | 214/0 | 215/0 | 2025-12-28 | 2025-12-29 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 217/0-217A/0 | ta325¦217/0¦217A/0 | Ramsingh Yadav 1&2 | 217/0 | 217A/0 | 2025-12-31 | 2025-12-29 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 221/0-222/0 | ta325¦221/0¦222/0 | Sanjay Singh | 221/0 | 222/0 | 2025-12-31 | 2025-12-27 | -4 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 222/0-222/1 | ta325¦222/0¦222/1 | Muslehuddin and Giyash | 222/0 | 222/1 | 2025-12-31 | 2025-12-25 | -6 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 172/0-173/0 | ta325¦172/0¦173/0 | Alam Construction | 172/0 | 173/0 | 2025-12-30 | 2025-12-31 | 1 | 1 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 201/1-202/0 | ta325¦201/1¦202/0 | Modina India 2 | 201/1 | 202/0 | 2026-01-04 | 2025-12-29 | -6 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 202/0-203/0 | ta325¦202/0¦203/0 | Teklal Saw / Muslehuddin | 202/0 | 203/0 | 2026-01-04 | 2025-12-30 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 203/0-203/1 | ta325¦203/0¦203/1 | Modia India | 203/0 | 203/1 | 2025-12-28 | 2025-12-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 154/1-155/0 | ta325¦154/1¦155/0 | Munni Bibi 2 | 154/1 | 155/0 | 2026-01-05 | 2025-12-30 | -6 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 159/0-159/2 | ta325¦159/0¦159/2 | Enamul Haque | 159/0 | 159/2 | 2026-01-05 | 2026-01-03 | -2 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 173/0-174/0 | ta325¦173/0¦174/0 | Dharmendra 2 | 173/0 | 174/0 | 2026-01-05 | 2025-12-31 | -5 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 174/0-174/1 | ta325¦174/0¦174/1 | Alam Construction | 174/0 | 174/1 | 2026-01-06 | 2026-01-03 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 174/1-175/0 | ta325¦174/1¦175/0 | Alam Construction | 174/1 | 175/0 | 2026-01-06 | 2026-01-03 | -3 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Ready | 159/2-160/0 | ta325¦159/2¦160/0 | Enamul Haque | 159/2 | 160/0 | 2025-12-26 | 2026-01-07 | 12 | 12 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 206/0-208/0 | ta325¦206/0¦208/0 | Ramavat Electricals 2 | 206/0 | 208/0 | 2026-01-09 | 2025-12-18 | -22 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 216/0-217/0 | ta325¦216/0¦217/0 | Ramavat Electricals 1 | 216/0 | 217/0 | 2026-01-09 | 2026-01-01 | -8 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 185/0-186/0 | ta325¦185/0¦186/0 | Alam Construction | 185/0 | 186/0 | 2026-01-09 | 2026-01-09 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 186/0-187/0 | ta325¦186/0¦187/0 | Dharmendra 2 | 186/0 | 187/0 | 2026-01-11 | 2026-01-10 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 215/0-215/1 | ta325¦215/0¦215/1 | Ramavat Electricals 1&2 | 215/0 | 215/1 | 2026-01-14 | 2026-01-13 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 215/1-216/0 | ta325¦215/1¦216/0 | Kudus Ali | 215/1 | 216/0 | 2026-01-14 | 2026-01-13 | -1 |  | TRUE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 166/0-167/0 | ta325¦166/0¦167/0 | Muni bibi / Enamul / Alam / Rafikul | 166/0 | 167/0 | 2026-01-17 | 2026-01-17 | 0 | 0 | FALSE | TRUE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 101/0-102/0 | ta325¦101/0¦102/0 | Kudus Ali 2 | 101/0 | 102/0 |  | 2026-01-16 |  |  | FALSE | FALSE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 102/0-103/0 | ta325¦102/0¦103/0 | Modina India 1 | 102/0 | 103/0 |  | 2026-01-16 |  |  | FALSE | FALSE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 103/0-104/0 | ta325¦103/0¦104/0 | Muslehuddin | 103/0 | 104/0 |  | 2026-01-16 |  |  | FALSE | FALSE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 104/0-105/0 | ta325¦104/0¦105/0 | Dharmendra 2 | 104/0 | 105/0 |  | 2026-01-17 |  |  | FALSE | FALSE | TRUE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 153/0-154/0 | ta325¦153/0¦154/0 | Modina india 2 | 153/0 | 154/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | Others | Ready | 154/0-154/1 | ta325¦154/0¦154/1 | Deepak Sarkar | 154/0 | 154/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 325 | TA 325 | TA 325 | ta325 | ta325 | TA 325 | Other | TA | TSE | Unassigned | Total | ta325¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | Section | ta413¦Section¦ |  | Section | [5 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | From-To | ta413¦From¦To |  | From | To |  |  |  |  | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 34-35 | ta413¦34¦35 |  | AP-34 | AP-35 | 2025-02-26 | 2025-03-03 | 5 | 5 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 37A/0-38/0 | ta413¦37A/0¦38/0 |  | 37A/0 | AP-38/0 | 2025-03-20 | 2025-04-15 | 26 | 26 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 38-39 | ta413¦38¦39 |  | AP-38 | AP-39 | 2025-04-05 | 2025-04-15 | 10 | 10 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 39-40 | ta413¦39¦40 |  | AP-39 | AP-40 | 2025-04-29 | 2025-04-29 | 0 | 0 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 7-7A | ta413¦7¦7A |  | AP-7 | AP-7A | 2025-09-04 | 2025-09-17 | 13 | 13 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 7A-8 | ta413¦7A¦8 |  | AP-7A | AP-8 | 2025-09-16 | 2025-09-24 | 8 | 8 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 8-8A | ta413¦8¦8A |  | AP-8 | AP-8A | 2025-10-15 | 2025-10-21 | 6 | 6 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 8A-9/0 | ta413¦8A¦9/0 |  | AP-8A | AP-9/0 | 2025-10-05 | 2025-10-26 | 21 | 21 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 6-7 | ta413¦6¦7 |  | AP-6 | AP-7 | 2025-11-23 | 2025-11-27 | 4 | 4 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 5A-6 | ta413¦5A¦6 |  | AP-5A | AP-6 | 2025-11-09 | 2025-12-11 | 32 | 32 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 5-5A | ta413¦5¦5A |  | AP-5 | AP-5A | 2025-12-12 | 2025-12-21 | 9 | 9 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 4A-5/0 | ta413¦4A¦5/0 |  | AP-4A | AP-5/0 | 2025-12-22 | 2025-12-30 | 8 | 8 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 4-4A/0 | ta413¦4¦4A/0 |  | AP-4 | AP4A/0 | 2025-12-31 | 2026-01-14 | 14 | 14 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 33-34 | ta413¦33¦34 |  | AP-33 | AP-34 | 2026-01-13 | 2026-01-21 | 8 | 8 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 3B/0-4/0 | ta413¦3B/0¦4/0 |  | AP3B/0 | AP4/0 | 2026-01-17 | 2026-01-24 | 7 | 7 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 32A-33 | ta413¦32A¦33 |  | AP-32A | AP-33 | 2026-01-19 | 2026-01-31 | 12 | 12 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 32/0-32A/0 | ta413¦32/0¦32A/0 |  | AP32/0 | AP32A/0 | 2026-01-30 | 2026-01-31 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 2A/0-3A/0 | ta413¦2A/0¦3A/0 |  | 2A/0 | 3A/0 | 2026-02-26 | 2026-02-27 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 3A/0-3B/0 | ta413¦3A/0¦3B/0 |  | 3A/0 | 3B/0 | 2026-02-13 | 2026-02-27 | 14 | 14 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 1/0-2A/0 | ta413¦1/0¦2A/0 |  | 1/0 | 2A/0 | 2026-02-18 | 2026-03-09 | 19 | 19 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 31/0-32/0 | ta413¦31/0¦32/0 |  | 31/0 | 32/0 | 2026-02-15 | 2026-03-02 | 15 | 15 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 30/0-31/0 | ta413¦30/0¦31/0 |  | 30/0 | 31/0 | 2026-03-06 | 2026-03-12 | 6 | 6 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 9/0-10/0 | ta413¦9/0¦10/0 |  | 9/0 | 10/0 | 2026-04-02 | 2026-03-06 | -27 |  | TRUE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29A/0-30/0 | ta413¦29A/0¦30/0 |  | 29A/0 | 30/0 | 2026-04-28 | 2026-04-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 10/0-11/0 | ta413¦10/0¦11/0 |  | 10/0 | 11/0 | 2026-04-09 | 2026-05-12 | 33 | 33 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 29/0-29A/0 | ta413¦29/0¦29A/0 |  | 29/0 | 29A/0 | 2026-05-12 | 2026-05-13 | 1 | 1 | FALSE | TRUE | TRUE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 13/0-13A/0 | ta413¦13/0¦13A/0 |  | 13/0 | 13A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | Others | Unassigned | 11/0-12/0 | ta413¦11/0¦12/0 |  | 11/0 | 12/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | 27/0-28/0 | ta413¦27/0¦28/0 |  | 27/0 | 28/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 413 | TA 413 | TA 413 | ta413 | ta413 | TA 413 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 117/0-118/0 | ta414¦117/0¦118/0 |  | 117/0 | 118/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | WIP | 118/0-119/0 | ta414¦118/0¦119/0 |  | 118/0 | 119/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | WIP | 119/0-120/0 | ta414¦119/0¦120/0 | Enamul Haque | 119/0 | 120/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Complete | 120/0-121/0 | ta414¦120/0¦121/0 | Enamul Haque | 120/0 | 121/0 | 2026-05-08 | 2026-05-10 | 2 | 2 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 121/0-121/1 | ta414¦121/0¦121/1 | Enamul Haque | 121/0 | 121/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 121/1-121/7 | ta414¦121/1¦121/7 |  | 121/1 | 121/7 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 121/7-124/0 | ta414¦121/7¦124/0 |  | 121/7 | 124/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 124/0-125/0 | ta414¦124/0¦125/0 |  | 124/0 | 125/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 125/0-126/0 | ta414¦125/0¦126/0 |  | 125/0 | 126/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | WIP | 126/0-127/0 | ta414¦126/0¦127/0 |  | 126/0 | 127/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 127/0-127/2 | ta414¦127/0¦127/2 |  | 127/0 | 127/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 127/2-128/0 | ta414¦127/2¦128/0 |  | 127/2 | 128/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 128/0-129/0 | ta414¦128/0¦129/0 |  | 128/0 | 129/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 129/0-130/0 | ta414¦129/0¦130/0 |  | 129/0 | 130/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 130/0-131/0 | ta414¦130/0¦131/0 |  | 130/0 | 131/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 131/0-132/0 | ta414¦131/0¦132/0 |  | 131/0 | 132/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 132/0-133/0 | ta414¦132/0¦133/0 |  | 132/0 | 133/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 133/0-133/2 | ta414¦133/0¦133/2 |  | 133/0 | 133/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 133/2-133/3 | ta414¦133/2¦133/3 |  | 133/2 | 133/3 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 133/3-134/0 | ta414¦133/3¦134/0 |  | 133/3 | 134/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 134/0-135/0 | ta414¦134/0¦135/0 |  | 134/0 | 135/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 135/0-136/0 | ta414¦135/0¦136/0 |  | 135/0 | 136/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 136/0-136/1 | ta414¦136/0¦136/1 |  | 136/0 | 136/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 136/1-137/0 | ta414¦136/1¦137/0 |  | 136/1 | 137/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 137/0-138/0 | ta414¦137/0¦138/0 |  | 137/0 | 138/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 138/0-139/0 | ta414¦138/0¦139/0 |  | 138/0 | 139/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 139/0-139/2 | ta414¦139/0¦139/2 |  | 139/0 | 139/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 139/2-139/3 | ta414¦139/2¦139/3 |  | 139/2 | 139/3 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 139/3-140/0 | ta414¦139/3¦140/0 |  | 139/3 | 140/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 140/0-141/0 | ta414¦140/0¦141/0 |  | 140/0 | 141/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 141/0-142/0 | ta414¦141/0¦142/0 |  | 141/0 | 142/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 142/0-143/0 | ta414¦142/0¦143/0 |  | 142/0 | 143/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 143/0-144/0 | ta414¦143/0¦144/0 |  | 143/0 | 144/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 144/0-145/0 | ta414¦144/0¦145/0 |  | 144/0 | 145/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 145/0-145/7 | ta414¦145/0¦145/7 |  | 145/0 | 145/7 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 145/7-147/0 | ta414¦145/7¦147/0 |  | 145/7 | 147/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 147/0-148/0 | ta414¦147/0¦148/0 |  | 147/0 | 148/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 148/0-148/5 | ta414¦148/0¦148/5 |  | 148/0 | 148/5 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 148/5-149/0 | ta414¦148/5¦149/0 |  | 148/5 | 149/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 149/0-150/0 | ta414¦149/0¦150/0 |  | 149/0 | 150/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 150/0-150/1 | ta414¦150/0¦150/1 |  | 150/0 | 150/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 150/1-151/0 | ta414¦150/1¦151/0 |  | 150/1 | 151/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 151/0-151A/0 | ta414¦151/0¦151A/0 |  | 151/0 | 151A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 151A/0-152/0 | ta414¦151A/0¦152/0 |  | 151A/0 | 152/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 152/0-153/0 | ta414¦152/0¦153/0 |  | 152/0 | 153/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 153/0-153A/0 | ta414¦153/0¦153A/0 |  | 153/0 | 153A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 153A/0-154/0 | ta414¦153A/0¦154/0 |  | 153A/0 | 154/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 154/0-155/0 | ta414¦154/0¦155/0 |  | 154/0 | 155/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 155/0-156/0 | ta414¦155/0¦156/0 |  | 155/0 | 156/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 156/0-156/1 | ta414¦156/0¦156/1 |  | 156/0 | 156/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 156/1-157/0 | ta414¦156/1¦157/0 |  | 156/1 | 157/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 157/0-158/0 | ta414¦157/0¦158/0 |  | 157/0 | 158/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 158/0-159/0 | ta414¦158/0¦159/0 |  | 158/0 | 159/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 159/0-160/0 | ta414¦159/0¦160/0 |  | 159/0 | 160/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 160/0-161/0 | ta414¦160/0¦161/0 |  | 160/0 | 161/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 161/0-162/0 | ta414¦161/0¦162/0 |  | 161/0 | 162/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 162/0-163/0 | ta414¦162/0¦163/0 |  | 162/0 | 163/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 163/0-163/1 | ta414¦163/0¦163/1 |  | 163/0 | 163/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 163/1-164/0 | ta414¦163/1¦164/0 |  | 163/1 | 164/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 164/0-165/0 | ta414¦164/0¦165/0 |  | 164/0 | 165/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 165/0-165/6 | ta414¦165/0¦165/6 |  | 165/0 | 165/6 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 165/6-166/0 | ta414¦165/6¦166/0 |  | 165/6 | 166/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 166/0-167/0 | ta414¦166/0¦167/0 |  | 166/0 | 167/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 167/0-168/0 | ta414¦167/0¦168/0 |  | 167/0 | 168/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 168/0-169/0 | ta414¦168/0¦169/0 |  | 168/0 | 169/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 169/0-170/0 | ta414¦169/0¦170/0 |  | 169/0 | 170/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 170/0-171/0 | ta414¦170/0¦171/0 |  | 170/0 | 171/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 171/0-172/0 | ta414¦171/0¦172/0 |  | 171/0 | 172/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 172/0-173/0 | ta414¦172/0¦173/0 |  | 172/0 | 173/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 173/0-174/0 | ta414¦173/0¦174/0 |  | 173/0 | 174/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | WIP | 174/0-175/0 | ta414¦174/0¦175/0 |  | 174/0 | 175/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 175/0-175/1 | ta414¦175/0¦175/1 | Alam Construction | 175/0 | 175/1 | 2026-05-07 | 2026-05-03 | -4 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 175/1-176/0 | ta414¦175/1¦176/0 | Maa Singhvahini | 175/1 | 176/0 | 2026-04-12 | 2026-04-07 | -5 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Complete | 176/0-177/0 | ta414¦176/0¦177/0 | Alam Construction | 176/0 | 177/0 | 2026-04-27 | 2026-04-24 | -3 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 177/0-178/0 | ta414¦177/0¦178/0 | Sanjay singh 2 | 177/0 | 178/0 | 2026-05-20 | 2026-05-20 | 0 | 0 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | WIP | 178/0-179/0 | ta414¦178/0¦179/0 |  | 178/0 | 179/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 179/0-180/0 | ta414¦179/0¦180/0 |  | 179/0 | 180/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 180/0-180/2 | ta414¦180/0¦180/2 |  | 180/0 | 180/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Complete | 180/2-182/0 | ta414¦180/2¦182/0 | Alam Construction | 180/2 | 182/0 | 2026-04-13 | 2026-04-14 | 1 | 1 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 182/0-183/0 | ta414¦182/0¦183/0 | Sanjay Singh | 182/0 | 183/0 | 2026-04-11 | 2026-04-05 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Complete | 183/0-184/0 | ta414¦183/0¦184/0 | Alam Construction | 183/0 | 184/0 | 2026-04-21 | 2026-04-20 | -1 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 184/0-185/0 | ta414¦184/0¦185/0 |  | 184/0 | 185/0 | 2026-05-13 | 2026-05-06 | -7 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | WIP | 185/0-186/0 | ta414¦185/0¦186/0 |  | 185/0 | 186/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 186/0-187/0 | ta414¦186/0¦187/0 |  | 186/0 | 187/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 187/0-188/0 | ta414¦187/0¦188/0 |  | 187/0 | 188/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 188/0-189/0 | ta414¦188/0¦189/0 |  | 188/0 | 189/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 189/0-190/0 | ta414¦189/0¦190/0 |  | 189/0 | 190/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 190/0-191/0 | ta414¦190/0¦191/0 |  | 190/0 | 191/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | WIP | 191/0-191/1 | ta414¦191/0¦191/1 |  | 191/0 | 191/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | WIP | 191/1-192/0 | ta414¦191/1¦192/0 |  | 191/1 | 192/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 192/0-193/0 | ta414¦192/0¦193/0 |  | 192/0 | 193/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 193/0-194/0 | ta414¦193/0¦194/0 |  | 193/0 | 194/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 194/0-194/1 | ta414¦194/0¦194/1 |  | 194/0 | 194/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 194/1-195/0 | ta414¦194/1¦195/0 |  | 194/1 | 195/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 195/0-196/0 | ta414¦195/0¦196/0 |  | 195/0 | 196/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 196/0-197/0 | ta414¦196/0¦197/0 |  | 196/0 | 197/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | WIP | 197/0-198/0 | ta414¦197/0¦198/0 |  | 197/0 | 198/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 198/0-199/0 | ta414¦198/0¦199/0 |  | 198/0 | 199/0 | 2026-04-23 | 2026-04-17 | -6 |  | TRUE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 199/0-200/0 | ta414¦199/0¦200/0 |  | 199/0 | 200/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 200/0-201/0 | ta414¦200/0¦201/0 |  | 200/0 | 201/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 201/0-202/0 | ta414¦201/0¦202/0 |  | 201/0 | 202/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 202/0-203/0 | ta414¦202/0¦203/0 |  | 202/0 | 203/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 203/0-203A/0 | ta414¦203/0¦203A/0 |  | 203/0 | 203A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 203A/0-203B/0 | ta414¦203A/0¦203B/0 |  | 203A/0 | 203B/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 203B/0-204/0 | ta414¦203B/0¦204/0 |  | 203B/0 | 204/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 204/0-205/0 | ta414¦204/0¦205/0 |  | 204/0 | 205/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 205/0-205/1 | ta414¦205/0¦205/1 |  | 205/0 | 205/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 205/1-206/0 | ta414¦205/1¦206/0 |  | 205/1 | 206/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 206/0-206/1 | ta414¦206/0¦206/1 |  | 206/0 | 206/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 206/1-207/0 | ta414¦206/1¦207/0 |  | 206/1 | 207/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 207/0-208/0 | ta414¦207/0¦208/0 |  | 207/0 | 208/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 208/0-209/0 | ta414¦208/0¦209/0 |  | 208/0 | 209/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 209/0-210/0 | ta414¦209/0¦210/0 |  | 209/0 | 210/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 210/0-211/0 | ta414¦210/0¦211/0 |  | 210/0 | 211/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 211/0-211/5 | ta414¦211/0¦211/5 |  | 211/0 | 211/5 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 211/5-212/0 | ta414¦211/5¦212/0 |  | 211/5 | 212/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 212/0-213/0 | ta414¦212/0¦213/0 |  | 212/0 | 213/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 213/0-214/0 | ta414¦213/0¦214/0 |  | 213/0 | 214/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 214/0-215/0 | ta414¦214/0¦215/0 |  | 214/0 | 215/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 215/0-216/0 | ta414¦215/0¦216/0 |  | 215/0 | 216/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 216/0-216/2 | ta414¦216/0¦216/2 |  | 216/0 | 216/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 216/2-217/0 | ta414¦216/2¦217/0 |  | 216/2 | 217/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 217/0-218/0 | ta414¦217/0¦218/0 |  | 217/0 | 218/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 218/0-219/0 | ta414¦218/0¦219/0 |  | 218/0 | 219/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 219/0-220/0 | ta414¦219/0¦220/0 |  | 219/0 | 220/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 220/0-221/0 | ta414¦220/0¦221/0 |  | 220/0 | 221/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 221/0-222/0 | ta414¦221/0¦222/0 |  | 221/0 | 222/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 222/0-223/0 | ta414¦222/0¦223/0 |  | 222/0 | 223/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 223/0-224/0 | ta414¦223/0¦224/0 |  | 223/0 | 224/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 224/0-224/2 | ta414¦224/0¦224/2 |  | 224/0 | 224/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 224/2-225/0 | ta414¦224/2¦225/0 |  | 224/2 | 225/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 225/0-226/0 | ta414¦225/0¦226/0 |  | 225/0 | 226/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 226/0-227/0 | ta414¦226/0¦227/0 |  | 226/0 | 227/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 227/0-228/0 | ta414¦227/0¦228/0 |  | 227/0 | 228/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 228/0-229/0 | ta414¦228/0¦229/0 |  | 228/0 | 229/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 229/0-229A/0 | ta414¦229/0¦229A/0 |  | 229/0 | 229A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 229A/0-229B/0 | ta414¦229A/0¦229B/0 |  | 229A/0 | 229B/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 229B/0-230/0 | ta414¦229B/0¦230/0 |  | 229B/0 | 230/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 230/0-230A/0 | ta414¦230/0¦230A/0 |  | 230/0 | 230A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 230A/0-231/0 | ta414¦230A/0¦231/0 |  | 230A/0 | 231/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 231/0-232/0 | ta414¦231/0¦232/0 |  | 231/0 | 232/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 232/0-233/0 | ta414¦232/0¦233/0 |  | 232/0 | 233/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 233/0-234/0 | ta414¦233/0¦234/0 |  | 233/0 | 234/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 234/0-235/0 | ta414¦234/0¦235/0 |  | 234/0 | 235/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 235/0-236/0 | ta414¦235/0¦236/0 |  | 235/0 | 236/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 236/0-237/0 | ta414¦236/0¦237/0 |  | 236/0 | 237/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 237/0-238/0 | ta414¦237/0¦238/0 |  | 237/0 | 238/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 238/0-239/0 | ta414¦238/0¦239/0 |  | 238/0 | 239/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 239/0-240/0 | ta414¦239/0¦240/0 |  | 239/0 | 240/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 240/0-241/0 | ta414¦240/0¦241/0 |  | 240/0 | 241/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 241/0-242/0 | ta414¦241/0¦242/0 |  | 241/0 | 242/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 242/0-243/0 | ta414¦242/0¦243/0 |  | 242/0 | 243/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 243/0-244/0 | ta414¦243/0¦244/0 |  | 243/0 | 244/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 244/0-245/0 | ta414¦244/0¦245/0 |  | 244/0 | 245/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Complete | 245/0-246/0 | ta414¦245/0¦246/0 | Bhola prasad+ Deepak Sarkar | 245/0 | 246/0 | 2026-04-14 | 2026-04-14 | 0 | 0 | FALSE | TRUE | TRUE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 246/0-247/0 | ta414¦246/0¦247/0 |  | 246/0 | 247/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 247/0-248/0 | ta414¦247/0¦248/0 |  | 247/0 | 248/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 248/0-248/1 | ta414¦248/0¦248/1 |  | 248/0 | 248/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 248/1-249/0 | ta414¦248/1¦249/0 |  | 248/1 | 249/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 249/0-250/0 | ta414¦249/0¦250/0 |  | 249/0 | 250/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Not Ready | 250/0-250A/0 | ta414¦250/0¦250A/0 |  | 250/0 | 250A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 250A/0-251/0 | ta414¦250A/0¦251/0 |  | 250A/0 | 251/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 251/0-252/0 | ta414¦251/0¦252/0 |  | 251/0 | 252/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | TSE | Ready | 252/0-252/5 | ta414¦252/0¦252/5 |  | 252/0 | 252/5 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 252/5-253/0 | ta414¦252/5¦253/0 |  | 252/5 | 253/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 253/0-254/0 | ta414¦253/0¦254/0 |  | 253/0 | 254/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 254/0-254/1 | ta414¦254/0¦254/1 |  | 254/0 | 254/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Ready | 254/1-255/0 | ta414¦254/1¦255/0 |  | 254/1 | 255/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 255/0-256/0 | ta414¦255/0¦256/0 |  | 255/0 | 256/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 256/0-257/0 | ta414¦256/0¦257/0 |  | 256/0 | 257/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 257/0-258/0 | ta414¦257/0¦258/0 |  | 257/0 | 258/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 414 | TA 414 | TA 414 | ta414 | ta414 | TA 414 | 4xx | TA | Others | Not Ready | 258/0-Gantry | ta414¦258/0¦Gantry |  | 258/0 | Gantry |  |  |  |  | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 7/0-8/0 | ta416¦7/0¦8/0 | ANARUL ISLAM | AP7/0 | AP8/0 | 2025-05-12 | 2025-05-15 | 3 | 3 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 6/0-7/0 | ta416¦6/0¦7/0 | ANARUL ISLAM | AP6/0 | AP7/0 | 2025-05-17 | 2025-05-19 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 35/0-36/0 | ta416¦35/0¦36/0 | S K INFRA | AP35/0 | AP36/0 | 2025-05-25 | 2025-06-27 | 33 | 33 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 8/0-8A/0 | ta416¦8/0¦8A/0 | ANARUL ISLAM | AP8/0 | AP8A/0 | 2025-05-29 | 2025-05-30 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 31/0-32/0 | ta416¦31/0¦32/0 | S K INFRA | AP31/0 | AP32/0 | 2025-06-09 | 2025-06-22 | 13 | 13 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 8A/0-8B/0 | ta416¦8A/0¦8B/0 | ANARUL ISLAM | AP8A/0 | AP8B/0 | 2025-06-19 | 2025-07-22 | 33 | 33 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 32/0-33/0 | ta416¦32/0¦33/0 | S K INFRA | AP32/0 | AP33/0 | 2025-06-19 | 2025-07-25 | 36 | 36 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 8B/0-9/0 | ta416¦8B/0¦9/0 | ANARUL ISLAM | AP8B/0 | AP9/0 | 2025-07-21 | 2025-07-26 | 5 | 5 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 33/0-34/0 | ta416¦33/0¦34/0 | S K INFRA | AP33/0 | AP34/0 | 2025-07-21 | 2025-07-25 | 4 | 4 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 5/0-6/0 | ta416¦5/0¦6/0 | ANARUL ISLAM | AP5/0 | AP6/0 | 2025-08-08 | 2025-08-26 | 18 | 18 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 9/0-10/0 | ta416¦9/0¦10/0 | ANARUL ISLAM | AP9/0 | AP10/0 | 2025-08-11 | 2025-08-11 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 34/0-35/0 | ta416¦34/0¦35/0 | S K INFRA | AP34/0 | AP35/0 | 2025-08-20 | 2025-08-21 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 4/0-5/0 | ta416¦4/0¦5/0 | ANARUL ISLAM | AP4/0 | AP5/0 | 2025-08-25 | 2025-08-27 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 14/0-15/0 | ta416¦14/0¦15/0 | ANARUL ISLAM | AP14/0 | AP15/0 | 2025-09-10 | 2025-09-28 | 18 | 18 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 36/0-37/0 | ta416¦36/0¦37/0 | S K INFRA | AP36/0 | AP37/0 | 2025-09-11 | 2025-12-06 | 86 | 86 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 3/0-4/0 | ta416¦3/0¦4/0 | ANARUL ISLAM | AP3/0 | AP4/0 | 2025-09-15 | 2025-09-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 30/0-31/0 | ta416¦30/0¦31/0 | S K INFRA | AP30/0 | AP31/0 | 2025-09-28 | 2025-09-30 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 20/0-21/0 | ta416¦20/0¦21/0 | J PG CON | AP20/0 | AP21/0 | 2025-09-30 | 2025-10-01 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 12/0-13/0 | ta416¦12/0¦13/0 | ANARUL ISLAM | AP12/0 | AP13/0 | 2025-10-16 | 2025-10-24 | 8 | 8 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 39/0-40/0 | ta416¦39/0¦40/0 | S K INFRA | AP39/0 | AP40/0 | 2025-10-19 | 2025-10-23 | 4 | 4 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 21/0-22/0 | ta416¦21/0¦22/0 | J PG CON | AP21/0 | AP22/0 | 2025-10-26 | 2025-10-27 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 13/0-14/0 | ta416¦13/0¦14/0 | ANARUL ISLAM | AP13/0 | AP14/0 | 2025-11-03 | 2025-11-03 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 38/0-39/0 | ta416¦38/0¦39/0 | S K INFRA | AP38/0 | AP39/0 | 2025-11-10 | 2025-11-25 | 15 | 15 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 19/0-20/0 | ta416¦19/0¦20/0 | J PG CON | AP19/0 | AP20/0 | 2025-11-13 | 2025-11-15 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 17/0-18/0 | ta416¦17/0¦18/0 | ANARUL ISLAM | AP17/0 | AP18/0 | 2026-02-28 | 2026-02-28 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 18/0-19/0 | ta416¦18/0¦19/0 | J PG CON | AP18/0 | AP19/0 | 2025-11-24 | 2025-11-24 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 15/0-16/0 | ta416¦15/0¦16/0 | ANARUL ISLAM | AP15/0 | AP16/0 | 2025-11-25 | 2025-11-26 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 10/0-11/0 | ta416¦10/0¦11/0 | ANARUL ISLAM | AP10/0 | AP11/0 | 2025-12-04 | 2025-12-05 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 37/0-38/0 | ta416¦37/0¦38/0 | S K INFRA | AP37/0 | AP38/0 | 2025-12-10 | 2025-12-06 | -4 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 11/0-12/0 | ta416¦11/0¦12/0 | ANARUL ISLAM | AP11/0 | AP12/0 | 2025-12-10 | 2025-12-11 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 1/0-2/0 | ta416¦1/0¦2/0 | AE Solution | AP1/0 | AP2/0 | 2025-12-19 | 2025-12-21 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 0/0-1/0 | ta416¦0/0¦1/0 | ANARUL ISLAM | AP0/0 | AP1/0 | 2025-12-30 | 2025-12-31 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 24/0-25/0 | ta416¦24/0¦25/0 | AE Solution | AP24/0 | AP25/0 | 2025-12-30 | 2025-12-29 | -1 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 23/0-24/0 | ta416¦23/0¦24/0 | Jahangir(Company) | AP23/0 | AP24/0 | 2026-01-15 | 2026-01-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 40/0-41/0 | ta416¦40/0¦41/0 | Babloo Haque/Anarul-2 | AP40/0 | AP41/0 | 2026-01-16 | 2026-01-16 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 16/0-17/0 | ta416¦16/0¦17/0 | Ramawat-Hot line | AP16/0 | AP17/0 | 2026-01-10 | 2026-01-11 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 2/0-3/0 | ta416¦2/0¦3/0 | ANARUL ISLAM | AP2/0 | AP3/0 | 2026-01-22 | 2026-01-23 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 26/0-27/0 | ta416¦26/0¦27/0 | AE Solution(Company) | AP26/0 | AP27/0 | 2026-01-15 | 2026-01-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 25/0-26/0 | ta416¦25/0¦26/0 | Bhola prasad(Company)+Sing Bahini | AP25/0 | AP26/0 | 2026-01-31 | 2026-01-27 | -4 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 42/0-43/0 | ta416¦42/0¦43/0 | Babloo Haque/Anarul-2 | AP42/0 | AP43/0 | 2026-01-27 | 2026-01-27 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 29/0-30/0 | ta416¦29/0¦30/0 | ANARUL ISLAM | AP29/0 | AP30/0 | 2026-03-16 | 2026-03-16 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 41/0-42/0 | ta416¦41/0¦42/0 | Babloo Haque/Anarul-2 | AP41/0 | AP42/0 | 2026-02-06 | 2026-02-08 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 28/0-29/0 | ta416¦28/0¦29/0 | Jahangir(Company) | AP28/0 | AP29/0 | 2026-02-06 | 2026-02-17 | 11 | 11 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 22/0-22A/0 | ta416¦22/0¦22A/0 | ANARUL ISLAM | AP22/0 | AP22A/0 | 2026-02-18 | 2026-02-18 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 27/0-28/0 | ta416¦27/0¦28/0 | Bhola+Sing bahini(Company) | AP27/0 | AP28/0 | 2026-02-12 | 2026-02-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 52/1-53/0 | ta416¦52/1¦53/0 | Astharul (company) | AP52/1 | AP53/0 | 2026-03-31 | 2026-03-28 | -3 |  | TRUE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 46/0-47/0 | ta416¦46/0¦47/0 | Babloo Haque/Anarul-2 | AP46/0 | AP47/0 | 2026-02-16 | 2026-02-28 | 12 | 12 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 22A/0-23/0 | ta416¦22A/0¦23/0 | ANARUL ISLAM | AP22A/0 | AP23/0 | 2026-02-22 | 2026-02-22 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 53/0-53A/0 | ta416¦53/0¦53A/0 | SADIK Con(company) | AP53/0 | AP53A/0 | 2026-02-28 | 2026-02-28 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 45/0-46/0 | ta416¦45/0¦46/0 | Babloo Haque/Anarul-2 | AP45/0 | AP46/0 | 2026-02-25 | 2026-02-26 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 53A/0-54/0 | ta416¦53A/0¦54/0 | Jahangir(Company) | AP53A/0 | AP54/0 | 2026-03-20 | 2026-03-24 | 4 | 4 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 52/0-52/1 | ta416¦52/0¦52/1 | Astharul (company) | AP52/0 | AP52/1 | 2026-03-13 | 2026-03-14 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 44/0-45/0 | ta416¦44/0¦45/0 | Dharmendra Hot line | AP44/0 | AP45/0 | 2026-03-15 | 2026-03-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 69A/0-70/0 | ta416¦69A/0¦70/0 | SADIK Con(company) | AP69A/0 | AP70/0 | 2026-03-15 | 2026-03-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 70/0-Gantry | ta416¦70/0¦Gantry | SADIK Con(company) | AP70/0 | Gantry | 2026-03-15 | 2026-03-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 43/0-44/0 | ta416¦43/0¦44/0 | Anarul-2 | AP43/0 | AP44/0 | 2026-03-15 | 2026-03-16 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 66/0-67/0 | ta416¦66/0¦67/0 | Astharul (company) | AP66/0 | AP67/0 | 2026-03-28 | 2026-03-29 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 69/0-69A | ta416¦69/0¦69A | SADIK Con(company) | AP69/0 | AP69A | 2026-03-24 | 2026-03-29 | 5 | 5 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 65/0-66 | ta416¦65/0¦66 | Dharmendra Hot line | AP65/0 | AP66 | 2026-03-28 | 2026-03-29 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 68/0-69/0 | ta416¦68/0¦69/0 | SADIK Con(company) | AP68/0 | AP69/0 | 2026-03-26 | 2026-03-26 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 67/0-68/0 | ta416¦67/0¦68/0 | Anarul-2 | AP67/0 | AP68/0 | 2026-03-29 | 2026-03-30 | 1 | 1 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 62/0-63/0 | ta416¦62/0¦63/0 | Khosibur Ali(Company) | AP62/0 | AP63/0 | 2026-04-15 | 2026-04-15 | 0 | 0 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 54/0-55/0 | ta416¦54/0¦55/0 | Jahangir(Company) | AP54/0 | AP55/0 | 2026-04-06 | 2026-04-08 | 2 | 2 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 61/0-62/0 | ta416¦61/0¦62/0 | Anarul-2 | AP61/0 | AP62/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 64/0-65/0 | ta416¦64/0¦65/0 | Astharul (company) | AP64/0 | AP65/0 | 2026-04-17 |  |  |  | FALSE | TRUE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 55/0-56/0 | ta416¦55/0¦56/0 | Jahangir(Company)FS-Anarul | AP55/0 | AP56/0 | 2026-04-14 | 2026-05-16 | 32 | 32 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 47/0-48/0 | ta416¦47/0¦48/0 | Kunal Hot line | AP47/0 | AP48/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 56/0-57/0 | ta416¦56/0¦57/0 | ANARUL ISLAM | AP56/0 | AP57/0 | 2026-05-14 | 2026-05-17 | 3 | 3 | FALSE | TRUE | TRUE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Ready | 57/0-58/0 | ta416¦57/0¦58/0 | ANARUL ISLAM | AP57/0 | AP58/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | Others | Ready | 60/0-61/0 | ta416¦60/0¦61/0 | RK Enterprise | AP60/0 | AP61/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 416 | TA 416 | TA 416 | ta416 | ta416 | TA 416 | 4xx | TA | TSE | Unassigned | Total | ta416¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 32-33 | ta418¦32¦33 | Ramawat | AP32 | AP33 | 2026-02-22 | 2026-02-16 | -6 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 33-33/5 | ta418¦33¦33/5 | SUFIYAN / Haque | AP33 | 33/5 | 2026-02-09 | 2026-02-07 | -2 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 33/5-33/6 | ta418¦33/5¦33/6 | Ramawat | 33/5 | 33/6 | 2026-01-30 | 2026-01-26 | -4 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 33/6-34/0 | ta418¦33/6¦34/0 | SUFIYAN / Haque | 33/6 | 34/0 | 2026-01-27 | 2026-01-26 | -1 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 34/0-35 | ta418¦34/0¦35 | SUFIYAN | 34/0 | AP35 | 2025-11-30 | 2025-12-05 | 5 | 5 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 35-36 | ta418¦35¦36 | SUFIYAN | AP35 | AP36 | 2025-11-17 | 2025-12-05 | 18 | 18 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 36-36/1 | ta418¦36¦36/1 | SUFIYAN | AP36 | 36/1 | 2025-11-03 | 2025-11-10 | 7 | 7 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 36/1-37/0 | ta418¦36/1¦37/0 |  | 36/1 | 37/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 37/0-38 | ta418¦37/0¦38 | SUFIYAN | 37/0 | AP38 | 2026-05-12 |  |  |  | FALSE | TRUE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 38-39 | ta418¦38¦39 | SUFIYAN | AP38 | AP39 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 39-40 | ta418¦39¦40 | Ramawat | AP39 | AP40 | 2026-02-10 | 2026-02-09 | -1 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 40-41 | ta418¦40¦41 | SUFIYAN / Haque | AP40 | AP41 | 2025-12-26 | 2025-12-30 | 4 | 4 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 41-42 | ta418¦41¦42 | SUFIYAN / Haque | AP41 | AP42 | 2025-10-06 | 2025-12-22 | 77 | 77 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 42-43 | ta418¦42¦43 | SUFIYAN | AP42 | AP43 | 2025-09-28 | 2025-10-13 | 15 | 15 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 43-44 | ta418¦43¦44 | SUFIYAN | AP43 | AP44 | 2026-03-11 | 2026-03-09 | -2 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 44-45 | ta418¦44¦45 | Haque | AP44 | AP45 | 2026-03-18 | 2026-03-14 | -4 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 45-45/1 | ta418¦45¦45/1 | Ramawat | AP45 | 45/1 | 2026-03-12 | 2026-03-06 | -6 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 45/1-46 | ta418¦45/1¦46 | Haque | 45/1 | AP46 | 2026-03-03 | 2026-03-22 | 19 | 19 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 46-46/7 | ta418¦46¦46/7 |  | AP46 | 46/7 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 46/7-47/0 | ta418¦46/7¦47/0 |  | 46/7 | AP47/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 47/0-48 | ta418¦47/0¦48 |  | AP47/0 | AP48 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 48-48A/0 | ta418¦48¦48A/0 |  | AP48 | 48A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 48A/0-49/0 | ta418¦48A/0¦49/0 |  | 48A/0 | 49/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 49/0-50 | ta418¦49/0¦50 |  | 49/0 | AP50 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 50-51 | ta418¦50¦51 |  | AP50 | AP51 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 51-52 | ta418¦51¦52 |  | AP51 | AP52 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 52-53 | ta418¦52¦53 |  | AP52 | AP53 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 53-54 | ta418¦53¦54 |  | AP53 | AP54 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 54-55 | ta418¦54¦55 |  | AP54 | AP55 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 55-56 | ta418¦55¦56 | SUFIYAN | AP55 | AP56 | 2026-05-03 | 2026-05-02 | -1 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 56-56/3 | ta418¦56¦56/3 | SUFIYAN | AP56 | 56/3 | 2026-03-31 | 2026-05-02 | 32 | 32 | FALSE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 56/3-57/0 | ta418¦56/3¦57/0 |  | 56/3 | 57/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 57/0-58/0 | ta418¦57/0¦58/0 |  | 57/0 | 58/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 58/0-59/0 | ta418¦58/0¦59/0 |  | 58/0 | 59/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Pending | 59/0-60/0 | ta418¦59/0¦60/0 |  | 59/0 | 60/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Ready | 60/0-61/0 | ta418¦60/0¦61/0 |  | 60/0 | 61/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 61/0-62/0 | ta418¦61/0¦62/0 | SUFIYAN | 61/0 | 62/0 | 2026-04-15 |  |  |  | FALSE | TRUE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 62/0-63/0 | ta418¦62/0¦63/0 |  | 62/0 | 63/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | Others | Ready | 63/0-GNTY | ta418¦63/0¦GNTY | SUFIYAN | 63/0 | GNTY | 2026-04-18 | 2026-04-16 | -2 |  | TRUE | TRUE | TRUE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 418 | TA 418 | TA 418 | ta418 | ta418 | TA 418 | 4xx | TA | TSE | Unassigned | Total | ta418¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 23/0-24/0 | ta421¦23/0¦24/0 | M R Constructions | 23/0 | 24/0 | 2025-02-16 | 2025-02-27 | 11 | 11 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 24/0-25/0 | ta421¦24/0¦25/0 | M R Constructions | 24/0 | 25/0 | 2025-03-04 | 2025-03-09 | 5 | 5 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 25/0-26/0 | ta421¦25/0¦26/0 | M R Constructions | 25/0 | 26/0 | 2025-03-13 | 2025-03-24 | 11 | 11 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 26/0-27/0 | ta421¦26/0¦27/0 | M R Constructions | 26/0 | 27/0 | 2025-03-28 | 2025-04-18 | 21 | 21 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 22/0-23/0 | ta421¦22/0¦23/0 | M R Constructions | 22/0 | 23/0 | 2025-04-11 | 2025-04-22 | 11 | 11 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 29/0-29/9 | ta421¦29/0¦29/9 | M R Constructions | 29/0 | 29/9 | 2025-05-16 | 2025-07-06 | 51 | 51 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 32/0-33/0 | ta421¦32/0¦33/0 | M R Constructions | 32/0 | 33/0 | 2025-05-25 | 2025-05-28 | 3 | 3 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 31/0-32/0 | ta421¦31/0¦32/0 | M R Constructions | 31/0 | 32/0 | 2025-06-17 | 2025-06-13 | -4 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 30/0-31/0 | ta421¦30/0¦31/0 | M R Constructions | 30/0 | 31/0 | 2025-07-02 | 2025-06-23 | -9 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 29/9-30/0 | ta421¦29/9¦30/0 | M R Constructions | 29/9 | 30/0 | 2025-07-11 | 2025-07-07 | -4 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 21/0-22/0 | ta421¦21/0¦22/0 | M R Constructions | 21/0 | 22/0 | 2025-07-24 | 2025-08-06 | 13 | 13 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 20A/0-21/0 | ta421¦20A/0¦21/0 | M R Constructions | 20A/0 | 21/0 | 2025-08-31 | 2025-08-24 | -7 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 20/0-20A/0 | ta421¦20/0¦20A/0 | M R Constructions | 20/0 | 20A/0 | 2025-09-01 | 2025-08-24 | -8 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 12/0-13/0 | ta421¦12/0¦13/0 | Nasiruddin | 12/0 | 13/0 | 2025-09-07 | 2025-09-15 | 8 | 8 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 10/0-11/0 | ta421¦10/0¦11/0 | Nasiruddin | 10/0 | 11/0 | 2025-10-05 | 2025-10-08 | 3 | 3 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 19/0-20/0 | ta421¦19/0¦20/0 | M R Constructions | 19/0 | 20/0 | 2025-10-19 | 2025-09-17 | -32 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 18/0-19/0 | ta421¦18/0¦19/0 | M R Constructions | 18/0 | 19/0 | 2025-10-20 | 2025-09-22 | -28 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 9/0-10/0 | ta421¦9/0¦10/0 | M R Constructions | 9/0 | 10/0 | 2025-10-23 | 2025-10-24 | 1 | 1 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 13/0-14/0 | ta421¦13/0¦14/0 | Nasiruddin | 13/0 | 14/0 | 2025-11-19 | 2025-11-20 | 1 | 1 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 11/0-12/0 | ta421¦11/0¦12/0 | Nasiruddin | 11/0 | 12/0 | 2025-12-07 | 2025-12-07 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 17/0-18/0 | ta421¦17/0¦18/0 | M R Constructions | 17/0 | 18/0 | 2025-11-15 | 2025-12-08 | 23 | 23 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 14/0-15/0 | ta421¦14/0¦15/0 | Nasiruddin | 14/0 | 15/0 | 2025-12-17 | 2025-12-15 | -2 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 16/0-17/0 | ta421¦16/0¦17/0 | M R Constructions | 16/0 | 17/0 | 2025-12-08 | 2025-12-24 | 16 | 16 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 15/0-16/0 | ta421¦15/0¦16/0 | M R Constructions | 15/0 | 16/0 | 2025-10-23 | 2025-12-24 | 62 | 62 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 8/4-9/0 | ta421¦8/4¦9/0 | Nasiruddin | 8/4 | 9/0 | 2026-01-06 | 2026-01-06 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 6/0-7/0 | ta421¦6/0¦7/0 | Nasiruddin | 6/0 | 7/0 | 2026-01-15 | 2026-01-18 | 3 | 3 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 8/3-8/4 | ta421¦8/3¦8/4 | Ramavath Electricals | 8/3 | 8/4 | 2026-01-28 | 2026-01-28 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 27/0-27/3 | ta421¦27/0¦27/3 | M R Constructions | 27/0 | 27/3 | 2026-01-12 | 2026-01-22 | 10 | 10 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 27/3-28/0 | ta421¦27/3¦28/0 | M R Constructions | 27/3 | 28/0 | 2026-01-28 | 2026-01-22 | -6 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 7/0-8/0 | ta421¦7/0¦8/0 | Nasiruddin | 7/0 | 8/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | Gantry-1/0 | ta421¦Gantry¦1/0 | Kamruddin | Gantry | 1/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 8/2-8/3 | ta421¦8/2¦8/3 | Nasiruddin | 8/2 | 8/3 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 28/0-29/0 | ta421¦28/0¦29/0 | M R Constructions | 28/0 | 29/0 | 2026-02-04 | 2026-02-04 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 1/0-1A/0 | ta421¦1/0¦1A/0 | Kamruddin | 1/0 | 1A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 1A/0-1B/0 | ta421¦1A/0¦1B/0 | Kamruddin | 1A/0 | 1B/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 4/12-5/0 | ta421¦4/12¦5/0 | Nasiruddin | 4/12 | 5/0 | 2026-02-12 | 2026-02-12 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 8/0-8/1 | ta421¦8/0¦8/1 | Ramavath Electricals 2 | 8/0 | 8/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 8/1-8/2 | ta421¦8/1¦8/2 | Ramavath Electricals 1 | 8/1 | 8/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 38/0-39/0 | ta421¦38/0¦39/0 | M R Constructions | 38/0 | 39/0 | 2026-02-19 | 2026-03-01 | 10 | 10 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 1C/0-2/0 | ta421¦1C/0¦2/0 | Ramavath Electricals | 1C/0 | 2/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 5/0-6/0 | ta421¦5/0¦6/0 | Ramavath Electricals | 5/0 | 6/0 |  | 2026-03-02 |  |  | FALSE | FALSE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 4/0-4/12 | ta421¦4/0¦4/12 | Nasiruddin | 4/0 | 4/12 | 2026-02-26 | 2026-03-02 | 4 | 4 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 3/0-4/0 | ta421¦3/0¦4/0 | Nasiruddin | 3/0 | 4/0 | 2026-03-05 | 2026-03-14 | 9 | 9 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 37/0-38/0 | ta421¦37/0¦38/0 | M R Constructions | 37/0 | 38/0 | 2026-03-10 | 2026-03-16 | 6 | 6 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 2/0-3/0 | ta421¦2/0¦3/0 | Nasiruddin | 2/0 | 3/0 | 2026-03-20 | 2026-03-17 | -3 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 1B/0-1C/0 | ta421¦1B/0¦1C/0 | Nasiruddin | 1B/0 | 1C/0 | 2026-03-28 | 2026-03-28 | 0 | 0 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 39/0-40/0 | ta421¦39/0¦40/0 | Kamruddin | 39/0 | 40/0 | 2026-03-31 | 2026-03-29 | -2 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 36/0-37/0 | ta421¦36/0¦37/0 | Kamruddin | 36/0 | 37/0 | 2026-04-17 | 2026-04-29 | 12 | 12 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 42/0-43/0 | ta421¦42/0¦43/0 | Nasiruddin | 42/0 | 43/0 | 2026-05-05 | 2026-05-08 | 3 | 3 | FALSE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 43/0-43A/0 | ta421¦43/0¦43A/0 | Nasiruddin | 43/0 | 43A/0 | 2026-05-16 | 2026-05-15 | -1 |  | TRUE | TRUE | TRUE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Ready | 34/2-35/0 | ta421¦34/2¦35/0 | Ramavath | 34/2 | 35/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Ready | 35/0-36/0 | ta421¦35/0¦36/0 | Kamruddin | 35/0 | 36/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 34/1-34/2 | ta421¦34/1¦34/2 |  | 34/1 | 34/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Not Ready (34/0) | 33/0-34/0 | ta421¦33/0¦34/0 | Pankaj | 33/0 | 34/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 43A/0-43A/1 | ta421¦43A/0¦43A/1 |  | 43A/0 | 43A/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Not Ready | 43A/1-43B/0 | ta421¦43A/1¦43B/0 |  | 43A/1 | 43B/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 34/0-34/1 | ta421¦34/0¦34/1 |  | 34/0 | 34/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 40/0-41/0 | ta421¦40/0¦41/0 |  | 40/0 | 41/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 41/0-42/0 | ta421¦41/0¦42/0 |  | 41/0 | 42/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | Others | Not Ready | 43B/0-44/0 | ta421¦43B/0¦44/0 |  | 43B/0 | 44/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 421 | TA 421 | TA 421 | ta421 | ta421 | TA 421 | 4xx | TA | TSE | Unassigned | Total | ta421¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 1/0-2/0 | ta504¦1/0¦2/0 |  | 1/0 | 2/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 2/0-3/0 | ta504¦2/0¦3/0 |  | 2/0 | 3/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 3/0-4/0 | ta504¦3/0¦4/0 |  | 3/0 | 4/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 4/0-5/0 | ta504¦4/0¦5/0 |  | 4/0 | 5/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 5/0-5A/0 | ta504¦5/0¦5A/0 |  | 5/0 | 5A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5A/0-5B/0 | ta504¦5A/0¦5B/0 |  | 5A/0 | 5B/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5B/0-5B/1 | ta504¦5B/0¦5B/1 |  | 5B/0 | 5B/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5B/1-5C/0 | ta504¦5B/1¦5C/0 |  | 5B/1 | 5C/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5C/0-5D/0 | ta504¦5C/0¦5D/0 |  | 5C/0 | 5D/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5D/0-5E/0 | ta504¦5D/0¦5E/0 |  | 5D/0 | 5E/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5E/0-5F/0 | ta504¦5E/0¦5F/0 |  | 5E/0 | 5F/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5F/0-5G/0 | ta504¦5F/0¦5G/0 |  | 5F/0 | 5G/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 5G/0-5H/0 | ta504¦5G/0¦5H/0 |  | 5G/0 | 5H/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 5H/0-5I/0 | ta504¦5H/0¦5I/0 |  | 5H/0 | 5I/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 5I/0-6/0 | ta504¦5I/0¦6/0 |  | 5I/0 | 6/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 6/0-7/0 | ta504¦6/0¦7/0 |  | 6/0 | 7/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 7/0-8/0 | ta504¦7/0¦8/0 |  | 7/0 | 8/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 8/0-8/3 | ta504¦8/0¦8/3 |  | 8/0 | 8/3 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 8/3-9/0 | ta504¦8/3¦9/0 |  | 8/3 | 9/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 9/0-10/0 | ta504¦9/0¦10/0 |  | 9/0 | 10/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 10/0-10/1 | ta504¦10/0¦10/1 |  | 10/0 | 10/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 10/1-11/0 | ta504¦10/1¦11/0 |  | 10/1 | 11/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 11/0-12/0 | ta504¦11/0¦12/0 | Tanjira Bibi | 11/0 | 12/0 | 2026-05-12 |  |  |  | FALSE | TRUE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 12/0-13/0 | ta504¦12/0¦13/0 | Tanjira Bibi | 12/0 | 13/0 | 2026-05-20 |  |  |  | FALSE | TRUE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 13/0-14/0 | ta504¦13/0¦14/0 |  | 13/0 | 14/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 14/0-15/0 | ta504¦14/0¦15/0 |  | 14/0 | 15/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 15/0-16/0 | ta504¦15/0¦16/0 | Lamba Construction | 15/0 | 16/0 | 2026-03-29 | 2026-04-01 | 3 | 3 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 16/0-16/3 | ta504¦16/0¦16/3 | Lamba Construction | 16/0 | 16/3 | 2026-04-04 | 2026-04-06 | 2 | 2 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 16/3-17/0 | ta504¦16/3¦17/0 | Lamba Construction | 16/3 | 17/0 | 2026-02-07 | 2026-02-19 | 12 | 12 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 17/0-17/4 | ta504¦17/0¦17/4 | Lamba Construction | 17/0 | 17/4 | 2026-02-14 | 2026-02-19 | 5 | 5 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 17/4-18/0 | ta504¦17/4¦18/0 | Lamba Construction | 17/4 | 18/0 | 2026-02-21 | 2026-02-25 | 4 | 4 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Ready | 18/0-18/1 | ta504¦18/0¦18/1 | Lamba Construction | 18/0 | 18/1 | 2026-02-24 | 2026-02-25 | 1 | 1 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 18/1-19/0 | ta504¦18/1¦19/0 | Lamba Construction | 18/1 | 19/0 | 2026-02-24 | 2026-02-25 | 1 | 1 | FALSE | TRUE | TRUE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 19/0-20/0 | ta504¦19/0¦20/0 |  | 19/0 | 20/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Ready | 20/0-21/0 | ta504¦20/0¦21/0 | Lamba Construction | 20/0 | 21/0 | 2026-05-17 |  |  |  | FALSE | TRUE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 21/0-21/3 | ta504¦21/0¦21/3 |  | 21/0 | 21/3 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 21/3-22/0 | ta504¦21/3¦22/0 |  | 21/3 | 22/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 22/0-23/0 | ta504¦22/0¦23/0 |  | 22/0 | 23/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Ready | 23/0-24/0 | ta504¦23/0¦24/0 |  | 23/0 | 24/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 24/0-24/1 | ta504¦24/0¦24/1 |  | 24/0 | 24/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 24/1-24/2. | ta504¦24/1¦24/2. |  | 24/1 | 24/2. |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 24/2.-25/0 | ta504¦24/2.¦25/0 |  | 24/2. | 25/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 25/0-26/0 | ta504¦25/0¦26/0 |  | 25/0 | 26/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 26/0-27/0 | ta504¦26/0¦27/0 |  | 26/0 | 27/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 27/0-28/0 | ta504¦27/0¦28/0 |  | 27/0 | 28/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 28/0-28/1 | ta504¦28/0¦28/1 |  | 28/0 | 28/1 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 28/1-29/0 | ta504¦28/1¦29/0 |  | 28/1 | 29/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 29/0-30/0 | ta504¦29/0¦30/0 |  | 29/0 | 30/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | TSE | Unassigned | 30/0-31/0 | ta504¦30/0¦31/0 |  | 30/0 | 31/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 31/0-31/2 | ta504¦31/0¦31/2 |  | 31/0 | 31/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 31/2-32/0 | ta504¦31/2¦32/0 |  | 31/2 | 32/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 32/0-32/2 | ta504¦32/0¦32/2 |  | 32/0 | 32/2 |  |  |  |  | FALSE | FALSE | FALSE
TA 504 | TA 504 | TA 504 | ta504 | ta504 | TA 504 | 5xx | TA | Others | Unassigned | 32/2-33/0 | ta504¦32/2¦33/0 |  | 32/2 | 33/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Ready | 100/0-101/0 | ta505¦100/0¦101/0 | Alimuddin | 100/0 | 101/0 | 2026-01-25 | 2026-02-05 | 11 | 11 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 101/0-102/0 | ta505¦101/0¦102/0 | Alimuddin | 101/0 | 102/0 | 2026-02-02 | 2026-02-10 | 8 | 8 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | Others | Ready | 102/0-103/0 | ta505¦102/0¦103/0 | Alimuddin | 102/0 | 103/0 | 2026-02-12 | 2026-02-18 | 6 | 6 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 103/0-103/5A | ta505¦103/0¦103/5A | Alimuddin | 103/0 | 103/5A | 2026-02-22 | 2026-02-26 | 4 | 4 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 103/5A-103/6A | ta505¦103/5A¦103/6A | Alimuddin | 103/5A | 103/6A | 2026-02-26 | 2026-03-12 | 14 | 14 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 103/6A-104/0 | ta505¦103/6A¦104/0 | Alimuddin | 103/6A | 104/0 | 2026-03-16 | 2026-03-17 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 104/0-105/0 | ta505¦104/0¦105/0 | Alimuddin | 104/0 | 105/0 | 2026-02-10 | 2026-04-12 | 61 | 61 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 111/0-112/0 | ta505¦111/0¦112/0 | Alimuddin | 111/0 | 112/0 | 2026-03-29 | 2026-03-29 | 0 | 0 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 113/0-114/0 | ta505¦113/0¦114/0 | Jahangir Alam | 113/0 | 114/0 | 2026-03-27 | 2026-03-28 | 1 | 1 | FALSE | TRUE | TRUE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 114/0-115/0 | ta505¦114/0¦115/0 | Jahangir Alam | 114/0 | 115/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 110A/0-111/0 | ta505¦110A/0¦111/0 | Alimuddin | 110A/0 | 111/0 | 2026-05-18 |  |  |  | FALSE | TRUE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Ready | 110/0-110A/0 | ta505¦110/0¦110A/0 | Nasiruddin | 110/0 | 110A/0 |  |  |  |  | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TA 505 | TA 505 | TA 505 | ta505 | ta505 | TA 505 | 5xx | TA | TSE | Unassigned | Total | ta505¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 57/6-58/0 | tb401pkgg¦57/6¦58/0 | GPJ Const. | 57/6 | 58/0 | 2024-05-10 | 2024-05-19 | 9 | 9 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 57/0-57/6 | tb401pkgg¦57/0¦57/6 | GPJ Const. | 57/0 | 57/6 | 2024-05-24 | 2024-06-07 | 14 | 14 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 56/0-57/0 | tb401pkgg¦56/0¦57/0 | GPJ Const. | 56/0 | 57/0 | 2024-06-12 | 2024-06-28 | 16 | 16 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 55/0-56/0 | tb401pkgg¦55/0¦56/0 | GPJ Const. | 55/0 | 56/0 | 2024-07-04 | 2024-07-17 | 13 | 13 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 53/0-55/0 | tb401pkgg¦53/0¦55/0 | GPJ Const. | 53/0 | 55/0 | 2024-07-22 | 2024-08-09 | 18 | 18 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 52/0-53/0 | tb401pkgg¦52/0¦53/0 | GPJ Const. | 52/0 | 53/0 | 2024-08-22 | 2024-09-04 | 13 | 13 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 51/0-52/0 | tb401pkgg¦51/0¦52/0 | GPJ Const. | 51/0 | 52/0 | 2024-09-08 | 2024-09-28 | 20 | 20 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 50/0-51/0 | tb401pkgg¦50/0¦51/0 | GPJ Const. | 50/0 | 51/0 | 2024-10-02 | 2024-10-08 | 6 | 6 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 72/7-73/0 | tb401pkgg¦72/7¦73/0 | MR Power | 72/7 | 73/0 | 2024-11-15 | 2024-11-27 | 12 | 12 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 58/0-58/7 | tb401pkgg¦58/0¦58/7 | Kddus Ali | 58/0 | 58/7 | 2024-11-23 |  |  |  | FALSE | TRUE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 72/0-72/7 | tb401pkgg¦72/0¦72/7 | MR Power | 72/0 | 72/7 | 2024-11-23 | 2024-12-06 | 13 | 13 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 67/1-68/0 | tb401pkgg¦67/1¦68/0 | Nasruddin | 67/1 | 68/0 | 2024-12-23 | 2024-12-23 | 0 | 0 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 68/0-69/0 | tb401pkgg¦68/0¦69/0 | Nasruddin | 68/0 | 69/0 | 2024-12-20 | 2025-01-01 | 12 | 12 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 58/7-59/0 | tb401pkgg¦58/7¦59/0 | MR Power | 58/7 | 59/0 | 2025-01-04 | 2025-01-07 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 71/0-72/0 | tb401pkgg¦71/0¦72/0 | MR Power | 71/0 | 72/0 | 2024-12-10 | 2025-01-16 | 37 | 37 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 67/0-67/1 | tb401pkgg¦67/0¦67/1 | Nasruddin | 67/0 | 67/1 | 2024-12-22 | 2025-01-20 | 29 | 29 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 69/0-70/0 | tb401pkgg¦69/0¦70/0 | Nasruddin | 69/0 | 70/0 | 2025-01-05 | 2025-01-27 | 22 | 22 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 41/0-42/0 | tb401pkgg¦41/0¦42/0 | Nasruddin | 41/0 | 42/0 | 2025-02-20 | 2025-02-28 | 8 | 8 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 59/0-60/0 | tb401pkgg¦59/0¦60/0 | MR Power | 59/0 | 60/0 | 2025-01-25 | 2025-05-02 | 97 | 97 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 42/0-43/0 | tb401pkgg¦42/0¦43/0 | Indrajeet | 42/0 | 43/0 | 2025-05-11 | 2025-05-07 | -4 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 49/0-50/0 | tb401pkgg¦49/0¦50/0 | Indrajeet | 49/0 | 50/0 | 2025-05-17 | 2025-05-15 | -2 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 48/0-49/0 | tb401pkgg¦48/0¦49/0 | Indrajeet | 48/0 | 49/0 | 2025-05-17 | 2025-05-19 | 2 | 2 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 47/0-48/0 | tb401pkgg¦47/0¦48/0 | Indrajeet | 47/0 | 48/0 | 2025-05-21 | 2025-05-25 | 4 | 4 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 37/2-38/0 | tb401pkgg¦37/2¦38/0 | Indrajeet | 37/2 | 38/0 | 2025-05-30 | 2025-06-11 | 12 | 12 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 43/0-44/0 | tb401pkgg¦43/0¦44/0 | Indrajeet | 43/0 | 44/0 | 2025-05-10 | 2025-06-20 | 41 | 41 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 61/0-62/0 | tb401pkgg¦61/0¦62/0 | GPJ Const. | 61/0 | 62/0 | 2025-06-29 | 2025-07-07 | 8 | 8 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 62/0-63/0 | tb401pkgg¦62/0¦63/0 | GPJ Const. | 62/0 | 63/0 | 2025-07-10 | 2025-07-07 | -3 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 38/0-38/9 | tb401pkgg¦38/0¦38/9 | Indrajeet | 38/0 | 38/9 | 2025-06-10 | 2025-07-07 | 27 | 27 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 40/10-41/0 | tb401pkgg¦40/10¦41/0 | Indrajeet/Rahim | 40/10 | 41/0 | 2025-07-05 | 2025-07-24 | 19 | 19 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 63/0-64/0 | tb401pkgg¦63/0¦64/0 | GPJ Const. | 63/0 | 64/0 | 2025-07-28 | 2025-07-31 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 39/0-40/0 | tb401pkgg¦39/0¦40/0 | Amir Sheikh | 39/0 | 40/0 | 2025-08-06 | 2025-08-09 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 40/5-40/10 | tb401pkgg¦40/5¦40/10 | Indrajeet/Rahim | 40/5 | 40/10 | 2025-07-20 | 2025-08-10 | 21 | 21 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 38/9-39/0 | tb401pkgg¦38/9¦39/0 | Indrajeet/Mohan/Amir Sheikh | 38/9 | 39/0 | 2025-07-11 | 2025-08-19 | 39 | 39 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 40/0-40/2 | tb401pkgg¦40/0¦40/2 | Rahim Khan | 40/0 | 40/2 | 2025-08-01 | 2025-08-23 | 22 | 22 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 40/2-40/5 | tb401pkgg¦40/2¦40/5 | Rahim Khan | 40/2 | 40/5 | 2025-08-14 | 2025-08-23 | 9 | 9 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 66/0-67/0 | tb401pkgg¦66/0¦67/0 | MC Const. | 66/0 | 67/0 | 2025-09-10 | 2025-09-13 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 35/0-36/0 | tb401pkgg¦35/0¦36/0 | Amir Sheikh | 35/0 | 36/0 | 2025-09-14 | 2025-09-18 | 4 | 4 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 46/0-47/0 | tb401pkgg¦46/0¦47/0 | Indrajeet | 46/0 | 47/0 | 2025-06-27 | 2025-10-04 | 99 | 99 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 31/0-32/0 | tb401pkgg¦31/0¦32/0 | Krishna Const. | 31/0 | 32/0 | 2025-09-24 | 2025-10-07 | 13 | 13 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 44/0-45/0 | tb401pkgg¦44/0¦45/0 | Indrajeet | 44/0 | 45/0 | 2025-06-18 | 2025-10-12 | 116 | 116 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | Gantry-1/0 | tb401pkgg¦Gantry¦1/0 | Devi Power | Gantry | 1/0 | 2025-10-17 | 2025-10-09 | -8 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 65/0-66/0 | tb401pkgg¦65/0¦66/0 | MC Const. | 65/0 | 66/0 | 2025-10-06 | 2025-10-13 | 7 | 7 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 1/0-1A/0 | tb401pkgg¦1/0¦1A/0 | Devi Power | 1/0 | 1A/0 | 2025-10-06 | 2025-10-12 | 6 | 6 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 1A/0-2/0 | tb401pkgg¦1A/0¦2/0 | Devi Power | 1A/0 | 2/0 | 2025-10-17 | 2025-10-23 | 6 | 6 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 64/0-65/0 | tb401pkgg¦64/0¦65/0 | MC Const. | 64/0 | 65/0 | 2025-10-18 | 2025-10-23 | 5 | 5 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 32/0-33/0 | tb401pkgg¦32/0¦33/0 | Krishna Const. | 32/0 | 33/0 | 2025-10-13 | 2025-10-23 | 10 | 10 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 33/0-34/0 | tb401pkgg¦33/0¦34/0 | Krishna Const. | 33/0 | 34/0 | 2025-10-27 | 2025-10-23 | -4 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 36/0-37/0 | tb401pkgg¦36/0¦37/0 | Telegance Power | 36/0 | 37/0 | 2025-11-08 | 2025-10-30 | -9 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 60/0-61/0 | tb401pkgg¦60/0¦61/0 | Indrajeet | 60/0 | 61/0 | 2025-11-11 | 2025-11-10 | -1 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 34/0-34/5 | tb401pkgg¦34/0¦34/5 | Krishna Const. | 34/0 | 34/5 | 2025-11-06 | 2025-11-14 | 8 | 8 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 34/5-35/0 | tb401pkgg¦34/5¦35/0 | Krishna Const. | 34/5 | 35/0 | 2025-11-13 | 2025-11-14 | 1 | 1 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 45/0-46/0 | tb401pkgg¦45/0¦46/0 | Gopal Ji | 45/0 | 46/0 | 2025-11-26 | 2025-11-14 | -12 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 37/0-37/1 | tb401pkgg¦37/0¦37/1 | Indrajeet | 37/0 | 37/1 | 2025-11-30 | 2025-11-29 | -1 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 37/1-37/2 | tb401pkgg¦37/1¦37/2 | Indrajeet | 37/1 | 37/2 | 2025-11-30 | 2025-11-29 | -1 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 25/0-26/0 | tb401pkgg¦25/0¦26/0 | Krishna Const. -2 | 25/0 | 26/0 | 2025-11-24 | 2025-11-29 | 5 | 5 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 2/0-3/0 | tb401pkgg¦2/0¦3/0 | Devi Power | 2/0 | 3/0 | 2025-11-05 | 2025-11-30 | 25 | 25 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 30/0-31/0 | tb401pkgg¦30/0¦31/0 | Krishna Const. | 30/0 | 31/0 | 2025-11-24 | 2025-11-30 | 6 | 6 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 5/0-6/0 | tb401pkgg¦5/0¦6/0 | Kunal Kumar | 5/0 | 6/0 | 2025-12-11 | 2025-12-05 | -6 |  | TRUE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 4/0-5/0 | tb401pkgg¦4/0¦5/0 | Devi Power | 4/0 | 5/0 | 2025-12-08 | 2025-12-09 | 1 | 1 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 15/0-16/0 | tb401pkgg¦15/0¦16/0 | Nasir | 15/0 | 16/0 | 2025-12-10 | 2025-12-11 | 1 | 1 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 29/0-30/0 | tb401pkgg¦29/0¦30/0 | Krishna Const. | 29/0 | 30/0 | 2025-12-08 | 2025-12-11 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 16/0-17/0 | tb401pkgg¦16/0¦17/0 | Nasir | 16/0 | 17/0 | 2025-12-17 | 2025-12-20 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 24/0-25/0 | tb401pkgg¦24/0¦25/0 | Krishna Const. -2 | 24/0 | 25/0 | 2025-12-08 | 2025-12-13 | 5 | 5 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 6/0-7/0 | tb401pkgg¦6/0¦7/0 | Devi Power | 6/0 | 7/0 | 2025-12-18 |  |  |  | FALSE | TRUE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 28/0-29/0 | tb401pkgg¦28/0¦29/0 | Krishna Const. | 28/0 | 29/0 | 2025-12-21 | 2025-12-23 | 2 | 2 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 23/0-24/0 | tb401pkgg¦23/0¦24/0 | Krishna Const. -2 | 23/0 | 24/0 | 2025-12-22 | 2025-12-25 | 3 | 3 | FALSE | TRUE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 27/1-28/0 | tb401pkgg¦27/1¦28/0 | Krishna Const. | 27/1 | 28/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 9/0-10/0 | tb401pkgg¦9/0¦10/0 | Gopal Ji | 9/0 | 10/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 17/0-18/0 | tb401pkgg¦17/0¦18/0 | Nasir | 17/0 | 18/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 10/12-10/20 | tb401pkgg¦10/12¦10/20 | Deepak | 10/12 | 10/20 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 70/0-71/0 | tb401pkgg¦70/0¦71/0 | GPJ Const. | 70/0 | 71/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 14/0-15/0 | tb401pkgg¦14/0¦15/0 | Nasir | 14/0 | 15/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 3/0-4/0 | tb401pkgg¦3/0¦4/0 | Gopal Ji | 3/0 | 4/0 |  | 2025-12-23 |  |  | FALSE | FALSE | TRUE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | 22/0-23/0 | tb401pkgg¦22/0¦23/0 | Krishna Const. -2 | 22/0 | 23/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 401 - PKG-G | TB 401 | TB 401 - PKG-G | tb401pkgg | tb401pkgg | TB 401 | 4xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Hydro GTY-Existing Tower-1 | tb501132kv¦Hydro GTY¦Existing Tower-1 |  | Hydro GTY | Existing Tower-1 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Existing Tower-1-Exting Tower-2 | tb501132kv¦Existing Tower-1¦Exting Tower-2 |  | Existing Tower-1 | Exting Tower-2 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exting Tower-2-Exting Tower-3 | tb501132kv¦Exting Tower-2¦Exting Tower-3 |  | Exting Tower-2 | Exting Tower-3 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exting Tower-3-Exting Tower-4 | tb501132kv¦Exting Tower-3¦Exting Tower-4 |  | Exting Tower-3 | Exting Tower-4 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exting Tower-4-Exting Tower-5 | tb501132kv¦Exting Tower-4¦Exting Tower-5 |  | Exting Tower-4 | Exting Tower-5 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exting Tower-5-Exting Tapping Tower-6 | tb501132kv¦Exting Tower-5¦Exting Tapping Tower-6 |  | Exting Tower-5 | Exting Tapping Tower-6 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exting Tapping Tower-6-Exting Tower-7 | tb501132kv¦Exting Tapping Tower-6¦Exting Tower-7 |  | Exting Tapping Tower-6 | Exting Tower-7 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Exiting Tower-7-SC-5 | tb501132kv¦Exiting Tower-7¦SC-5 |  | Exiting Tower-7 | SC-5 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | SC-5-SC-4 | tb501132kv¦SC-5¦SC-4 |  | SC-5 | SC-4 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | SC-4-Sc-3 | tb501132kv¦SC-4¦Sc-3 |  | SC-4 | Sc-3 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | Sc-3-SC-2 | tb501132kv¦Sc-3¦SC-2 |  | Sc-3 | SC-2 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | SC-2-SC-1 | tb501132kv¦SC-2¦SC-1 |  | SC-2 | SC-1 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | SC-1-1/0 | tb501132kv¦SC-1¦1/0 |  | SC-1 | 1/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 1/0-2/0 | tb501132kv¦1/0¦2/0 |  | 1/0 | 2/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 2/0-2/1 | tb501132kv¦2/0¦2/1 |  | 2/0 | 2/1 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | Unassigned | 2/1-3/0 | tb501132kv¦2/1¦3/0 |  | 2/1 | 3/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 3/0-3/1 | tb501132kv¦3/0¦3/1 | Sammirul Sekh | 3/0 | 3/1 | 2026-05-08 | 2026-05-08 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 3/1-4/0 | tb501132kv¦3/1¦4/0 | Sammirul Sekh | 3/1 | 4/0 | 2026-05-08 | 2026-05-08 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 4/0-4/1 | tb501132kv¦4/0¦4/1 | Sammirul Sekh | 4/0 | 4/1 | 2026-03-31 | 2026-04-01 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 4/1-4/2 | tb501132kv¦4/1¦4/2 |  | 4/1 | 4/2 | 2026-03-31 | 2026-03-31 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 4/2-5/0 | tb501132kv¦4/2¦5/0 | National Construction | 4/2 | 5/0 | 2026-03-31 | 2026-04-01 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 5/0-6/0 | tb501132kv¦5/0¦6/0 | National Construction | 5/0 | 6/0 | 2026-03-25 | 2026-04-01 | 7 | 7 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 6/0-6/1 | tb501132kv¦6/0¦6/1 | National Construction | 6/0 | 6/1 | 2026-03-27 | 2026-03-30 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 6/1-6/2 | tb501132kv¦6/1¦6/2 | National Construction | 6/1 | 6/2 | 2026-03-27 | 2026-03-30 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 6/2-6/3 | tb501132kv¦6/2¦6/3 | National Construction | 6/2 | 6/3 | 2026-03-27 | 2026-03-30 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 6/3-6/4 | tb501132kv¦6/3¦6/4 | National Construction | 6/3 | 6/4 | 2026-03-27 | 2026-03-30 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 6/4-7/0 | tb501132kv¦6/4¦7/0 | National Construction | 6/4 | 7/0 | 2026-03-27 | 2026-03-30 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 7/0-8/0 | tb501132kv¦7/0¦8/0 | National Construction | 7/0 | 8/0 | 2026-03-24 | 2026-03-29 | 5 | 5 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 8/0-9/0 | tb501132kv¦8/0¦9/0 | Sawariya seth | 8/0 | 9/0 | 2026-03-18 | 2026-03-19 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 9/0-10/0 | tb501132kv¦9/0¦10/0 | Sawariya seth | 9/0 | 10/0 | 2026-03-18 | 2026-03-19 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 10/0-11/0 | tb501132kv¦10/0¦11/0 |  | 10/0 | 11/0 |  | 2026-05-18 |  |  | FALSE | FALSE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 11/0-12/0 | tb501132kv¦11/0¦12/0 | Sammirul Sekh | 11/0 | 12/0 | 2026-05-11 | 2026-05-12 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 12/0-12/1 | tb501132kv¦12/0¦12/1 | Sawariya seth | 12/0 | 12/1 | 2026-03-13 | 2026-03-16 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 12/1-13/0 | tb501132kv¦12/1¦13/0 | Sawariya seth | 12/1 | 13/0 | 2026-03-13 | 2026-03-16 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 13/0-13/1 | tb501132kv¦13/0¦13/1 | Sawariya seth | 13/0 | 13/1 | 2026-03-12 | 2026-03-12 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 13/1-13/2 | tb501132kv¦13/1¦13/2 | Sawariya seth | 13/1 | 13/2 | 2026-03-12 | 2026-03-14 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 13/2-14/0 | tb501132kv¦13/2¦14/0 | Sawariya seth | 13/2 | 14/0 | 2026-03-15 | 2026-03-15 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 14/0-15/0 | tb501132kv¦14/0¦15/0 | Sammirul Sekh | 14/0 | 15/0 | 2026-05-14 | 2026-05-15 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 15/0-15/1 | tb501132kv¦15/0¦15/1 | Sawariya seth | 15/0 | 15/1 | 2026-03-09 | 2026-03-08 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 15/1-15/2 | tb501132kv¦15/1¦15/2 | Sawariya seth | 15/1 | 15/2 | 2026-03-09 | 2026-03-08 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 15/2-15/3 | tb501132kv¦15/2¦15/3 | Sawariya seth | 15/2 | 15/3 | 2026-03-09 | 2026-03-08 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 15/3-16/0 | tb501132kv¦15/3¦16/0 | Sawariya seth | 15/3 | 16/0 | 2026-03-09 | 2026-03-08 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 16/0-16/1 | tb501132kv¦16/0¦16/1 | SK Basirul | 16/0 | 16/1 | 2026-03-06 | 2026-03-05 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 16/1-16/2 | tb501132kv¦16/1¦16/2 | SK Basirul | 16/1 | 16/2 | 2026-03-03 | 2026-03-03 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 16/2-17/0 | tb501132kv¦16/2¦17/0 | SK Basirul | 16/2 | 17/0 | 2026-02-23 | 2026-02-23 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 17/0-18/0 | tb501132kv¦17/0¦18/0 | SK Basirul | 17/0 | 18/0 | 2026-03-03 | 2026-03-02 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 132kV | TB 501 | TB 501 - 132kV | tb501132kv | tb501132kv | TB 501 | 5xx | TB | TSE | C | 18/0-Gantry | tb501132kv¦18/0¦Gantry | SK Basirul | 18/0 | Gantry | 2026-02-21 | 2026-02-20 | -1 |  | TRUE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | Gnty-0/0 | tb501220kv¦Gnty¦0/0 | Harshvivek | Gnty | 0/0 | 2026-02-02 | 2026-01-31 | -2 |  | TRUE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 0/0-1/0 | tb501220kv¦0/0¦1/0 | National Construction | 0/0 | 1/0 | 2025-05-24 | 2025-05-26 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1/0-1A/0 | tb501220kv¦1/0¦1A/0 | National Construction | 1/0 | 1A/0 | 2025-05-24 | 2025-05-26 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1A/0-1A/2 | tb501220kv¦1A/0¦1A/2 | National Construction | 1A/0 | 1A/2 | 2025-06-29 | 2025-06-30 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1A/2-1B/0 | tb501220kv¦1A/2¦1B/0 | National Construction | 1A/2 | 1B/0 | 2025-06-29 | 2025-06-29 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1B/0-1C/0 | tb501220kv¦1B/0¦1C/0 | National Construction | 1B/0 | 1C/0 | 2026-04-09 | 2026-04-10 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1C/0-1D/0 | tb501220kv¦1C/0¦1D/0 | National Construction | 1C/0 | 1D/0 | 2026-04-13 | 2026-04-14 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1D/0-1E/0 | tb501220kv¦1D/0¦1E/0 | Dilruba Bibi | 1D/0 | 1E/0 | 2025-08-02 | 2025-08-04 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 1E/0-2/0 | tb501220kv¦1E/0¦2/0 | Dilruba Bibi | 1E/0 | 2/0 | 2025-07-29 | 2025-07-31 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 2/0-3/0 | tb501220kv¦2/0¦3/0 | National Construction | 2/0 | 3/0 | 2026-03-20 | 2026-03-21 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 3/0-4/0 | tb501220kv¦3/0¦4/0 | National Construction | 3/0 | 4/0 | 2026-04-06 | 2026-04-07 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/0-4/5 | tb501220kv¦4/0¦4/5 | Dilruba Bibi | 4/0 | 4/5 | 2025-07-14 | 2025-07-16 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/5-4/6 | tb501220kv¦4/5¦4/6 | Dilruba Bibi | 4/5 | 4/6 | 2025-07-14 | 2025-07-16 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/6-4/7 | tb501220kv¦4/6¦4/7 |  | 4/6 | 4/7 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/7-4/8 | tb501220kv¦4/7¦4/8 |  | 4/7 | 4/8 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 4/8-4/9 | tb501220kv¦4/8¦4/9 |  | 4/8 | 4/9 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/9-4/10 | tb501220kv¦4/9¦4/10 | National Construction | 4/9 | 4/10 | 2025-08-25 | 2025-09-19 | 25 | 25 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/10-4/11 | tb501220kv¦4/10¦4/11 | National Construction | 4/10 | 4/11 | 2025-08-25 | 2025-09-19 | 25 | 25 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/11-4/15 | tb501220kv¦4/11¦4/15 | National Construction | 4/11 | 4/15 | 2025-08-25 | 2025-09-10 | 16 | 16 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/15-4/16 | tb501220kv¦4/15¦4/16 | National Construction | 4/15 | 4/16 | 2025-08-25 | 2025-08-31 | 6 | 6 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/16-4/17 | tb501220kv¦4/16¦4/17 | National Construction | 4/16 | 4/17 | 2025-08-25 | 2025-09-16 | 22 | 22 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 4/17-5/0 | tb501220kv¦4/17¦5/0 | National Construction | 4/17 | 5/0 | 2025-08-31 | 2025-09-07 | 7 | 7 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5/0-5/1 | tb501220kv¦5/0¦5/1 | National Construction | 5/0 | 5/1 | 2025-08-31 | 2025-09-08 | 8 | 8 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5/1-5A/0 | tb501220kv¦5/1¦5A/0 | National Construction | 5/1 | 5A/0 | 2025-10-16 | 2025-10-17 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5A/0-5A/1 | tb501220kv¦5A/0¦5A/1 | National Construction | 5A/0 | 5A/1 | 2026-02-12 | 2026-02-13 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5A/1-5A/2 | tb501220kv¦5A/1¦5A/2 | National Construction | 5A/1 | 5A/2 | 2026-02-10 | 2026-02-14 | 4 | 4 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5A/2-5B/0 | tb501220kv¦5A/2¦5B/0 | National Construction | 5A/2 | 5B/0 | 2026-02-09 | 2026-02-09 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 5B/0-6/0 | tb501220kv¦5B/0¦6/0 | National Construction | 5B/0 | 6/0 | 2026-02-04 | 2026-02-07 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 6/0-7/0 | tb501220kv¦6/0¦7/0 | National Construction | 6/0 | 7/0 | 2026-02-04 | 2026-02-04 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 7/0-8/0 | tb501220kv¦7/0¦8/0 | National Construction | 7/0 | 8/0 | 2025-09-24 | 2025-09-25 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8/0-8A/0 | tb501220kv¦8/0¦8A/0 | National Construction | 8/0 | 8A/0 | 2025-10-01 | 2025-10-04 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8A/0-8B/0 | tb501220kv¦8A/0¦8B/0 | National Construction | 8A/0 | 8B/0 | 2025-10-03 | 2025-10-08 | 5 | 5 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8B/0-8C/0 | tb501220kv¦8B/0¦8C/0 | National Construction | 8B/0 | 8C/0 | 2025-10-04 | 2025-10-08 | 4 | 4 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8C/0-8D/0 | tb501220kv¦8C/0¦8D/0 | National Construction | 8C/0 | 8D/0 | 2026-03-13 | 2026-03-14 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/0-8D/1 | tb501220kv¦8D/0¦8D/1 | National Construction | 8D/0 | 8D/1 | 2026-03-06 | 2026-03-07 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/1-8D/3 | tb501220kv¦8D/1¦8D/3 | National Construction | 8D/1 | 8D/3 | 2026-03-05 | 2026-03-08 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/3-8D/4 | tb501220kv¦8D/3¦8D/4 | National Construction | 8D/3 | 8D/4 | 2026-02-19 | 2026-02-27 | 8 | 8 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/4-8D/5 | tb501220kv¦8D/4¦8D/5 | National Construction | 8D/4 | 8D/5 | 2026-02-19 | 2026-02-28 | 9 | 9 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/5-8D/6 | tb501220kv¦8D/5¦8D/6 | National Construction | 8D/5 | 8D/6 | 2026-02-19 | 2026-03-17 | 26 | 26 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8D/6-8E/0 | tb501220kv¦8D/6¦8E/0 | National Construction | 8D/6 | 8E/0 | 2026-02-19 | 2026-03-16 | 25 | 25 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/0-8E/1 | tb501220kv¦8E/0¦8E/1 | National Construction | 8E/0 | 8E/1 | 2026-02-19 | 2026-03-15 | 24 | 24 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/1-8E/2 | tb501220kv¦8E/1¦8E/2 | National Construction | 8E/1 | 8E/2 | 2025-11-14 | 2025-11-15 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/2-8E/5 | tb501220kv¦8E/2¦8E/5 | National Construction | 8E/2 | 8E/5 | 2025-11-14 | 2025-11-15 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/5-8E/6 | tb501220kv¦8E/5¦8E/6 | National Construction | 8E/5 | 8E/6 | 2025-11-14 | 2025-11-15 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/6-8E/7 | tb501220kv¦8E/6¦8E/7 | National Construction | 8E/6 | 8E/7 | 2026-02-22 | 2026-02-24 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/7-8E/8 | tb501220kv¦8E/7¦8E/8 | National Construction | 8E/7 | 8E/8 | 2026-02-23 | 2026-02-25 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/8-8E/11 | tb501220kv¦8E/8¦8E/11 | National Construction | 8E/8 | 8E/11 | 2025-11-19 | 2025-11-22 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/11-8E/12 | tb501220kv¦8E/11¦8E/12 | National Construction | 8E/11 | 8E/12 | 2025-11-09 | 2025-11-11 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 8E/12-9 | tb501220kv¦8E/12¦9 | National Construction | 8E/12 | AP-9 | 2025-11-09 | 2025-11-09 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 9-9/4 | tb501220kv¦9¦9/4 | National Construction | AP-9 | 9/4 | 2025-11-09 | 2025-11-09 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 9/4-9/5 | tb501220kv¦9/4¦9/5 | National Construction | 9/4 | 9/5 | 2025-10-27 | 2025-10-28 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 9/5-10 | tb501220kv¦9/5¦10 | National Construction | 9/5 | AP-10 | 2025-09-30 | 2025-10-26 | 26 | 26 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 10-11 | tb501220kv¦10¦11 | National Construction | AP-10 | AP-11 | 2025-10-12 | 2025-10-12 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 11-12 | tb501220kv¦11¦12 | National Construction | AP-11 | AP-12 | 2025-10-12 | 2025-10-12 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 12-13 | tb501220kv¦12¦13 | National Construction | AP-12 | AP-13 | 2025-10-01 | 2025-10-08 | 7 | 7 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 13-14 | tb501220kv¦13¦14 | National Construction | AP-13 | AP-14 | 2025-12-20 | 2025-12-24 | 4 | 4 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 14-14/1 | tb501220kv¦14¦14/1 | National Construction | AP-14 | 14/1 | 2025-12-20 | 2025-12-24 | 4 | 4 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 14/1-14/3 | tb501220kv¦14/1¦14/3 | National Construction | 14/1 | 14/3 | 2025-12-20 | 2025-12-21 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 14/3-15 | tb501220kv¦14/3¦15 | National Construction | 14/3 | AP-15 | 2025-12-15 | 2025-12-22 | 7 | 7 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 15-16 | tb501220kv¦15¦16 | Nemchand | AP-15 | AP-16 | 2025-06-25 | 2025-06-20 | -5 |  | TRUE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 16-17 | tb501220kv¦16¦17 | National Construction | AP-16 | AP-17 | 2025-07-06 | 2025-07-08 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 17-18 | tb501220kv¦17¦18 | National Construction | AP-17 | AP-18 | 2025-07-06 | 2025-07-08 | 2 | 2 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 18-19 | tb501220kv¦18¦19 | National Construction | AP-18 | AP-19 | 2025-07-15 | 2025-07-16 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 19-20 | tb501220kv¦19¦20 | National Construction | AP-19 | AP-20 | 2025-07-21 | 2025-07-21 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 20-21 | tb501220kv¦20¦21 | National Construction | AP-20 | AP-21 | 2025-07-24 |  |  |  | FALSE | TRUE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 21-22 | tb501220kv¦21¦22 | National Construction | AP-21 | AP-22 | 2025-08-12 | 2025-08-18 | 6 | 6 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 22-23 | tb501220kv¦22¦23 | National Construction | AP-22 | AP-23 | 2025-08-12 | 2025-09-07 | 26 | 26 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 23-24 | tb501220kv¦23¦24 | National Construction | AP-23 | AP-24 | 2025-09-06 | 2025-09-07 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 24-25 | tb501220kv¦24¦25 | National Construction | AP-24 | AP-25 | 2025-10-04 | 2025-10-04 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 25-26 | tb501220kv¦25¦26 | National Construction | AP-25 | AP-26 | 2025-09-15 | 2025-09-15 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 26-27 | tb501220kv¦26¦27 | National Construction | AP-26 | AP-27 | 2025-10-06 | 2025-10-06 | 0 | 0 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 27-28 | tb501220kv¦27¦28 | National Construction | AP-27 | AP-28 | 2025-11-02 | 2025-12-03 | 31 | 31 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 28-28/1 | tb501220kv¦28¦28/1 | National Construction | AP-28 | 28/1 | 2025-11-02 | 2025-12-03 | 31 | 31 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 28/1-28/2 | tb501220kv¦28/1¦28/2 | National Construction | 28/1 | 28/2 | 2025-11-02 | 2025-12-03 | 31 | 31 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 28/2-29 | tb501220kv¦28/2¦29 | National Construction | 28/2 | AP-29 | 2025-09-16 | 2025-09-17 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 29-29A/0 | tb501220kv¦29¦29A/0 | National Construction | AP-29 | 29A/0 | 2025-09-15 | 2025-09-16 | 1 | 1 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 29A/0-30 | tb501220kv¦29A/0¦30 | National Construction | 29A/0 | AP-30 | 2025-07-20 | 2025-08-28 | 39 | 39 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | C | 30-31 | tb501220kv¦30¦31 | Kohinoor | AP-30 | AP-31 | 2025-07-13 | 2025-07-16 | 3 | 3 | FALSE | TRUE | TRUE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 31-32 | tb501220kv¦31¦32 |  | AP-31 | AP-32 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 32-33/0 | tb501220kv¦32¦33/0 |  | AP-32 | 33/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | 33/0-34/0 | tb501220kv¦33/0¦34/0 |  | 33/0 | 34/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 501 - 220kV | TB 501 | TB 501 - 220kV | tb501220kv | tb501220kv | TB 501 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 | TB 507 | TB 507 | tb507 | tb507 | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 | TB 507 | TB 507 | tb507 | tb507 | TB 507 | 5xx | TB | TSE | Unassigned | Total | tb507¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 146/0-145/0 | tb507main¦146/0¦145/0 | Mahadev Enterprises | 146/0 | 145/0 | 2026-02-16 | 2026-02-20 | 4 | 4 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 149A/0-149/0 | tb507main¦149A/0¦149/0 | Mahadev Enterprises | 149A/0 | 149/0 | 2026-03-03 | 2026-03-03 | 0 | 0 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 149/0-148/0 | tb507main¦149/0¦148/0 | Mahadev Enterprises | 149/0 | 148/0 | 2026-02-06 | 2026-03-16 | 38 | 38 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 150/0-149B/3 | tb507main¦150/0¦149B/3 | Mahadev Enterprises | 150/0 | 149B/3 | 2026-02-27 | 2026-03-08 | 9 | 9 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 149B/0-149A/0 | tb507main¦149B/0¦149A/0 | Mahadev Enterprises | 149B/0 | 149A/0 | 2026-03-05 | 2026-03-10 | 5 | 5 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 149B/3-149B/0 | tb507main¦149B/3¦149B/0 | Mahadev Enterprises | 149B/3 | 149B/0 | 2026-03-09 | 2026-03-08 | -1 |  | TRUE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 144/0-143/0 | tb507main¦144/0¦143/0 | Mahadev Enterprises | 144/0 | 143/0 | 2026-04-04 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 145/0-144/0 | tb507main¦145/0¦144/0 | Mahadev Enterprises | 145/0 | 144/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 113/0-112/0 | tb507main¦113/0¦112/0 | Mahadev Maan Construction | 113/0 | 112/0 | 2026-04-10 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 153/0-152/0 | tb507main¦153/0¦152/0 | Mahadev Enterprises | 153/0 | 152/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 113A/0-113/0 | tb507main¦113A/0¦113/0 | Mahadev Maan Construction | 113A/0 | 113/0 | 2026-04-10 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 147/0-146/0 | tb507main¦147/0¦146/0 | Mahadev Enterprises | 147/0 | 146/0 | 2026-02-23 | 2026-03-20 | 25 | 25 | FALSE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 148/0-147/0 | tb507main¦148/0¦147/0 | Mahadev Enterprises | 148/0 | 147/0 | 2026-04-20 | 2026-04-19 | -1 |  | TRUE | TRUE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 151/0-150/0 | tb507main¦151/0¦150/0 | Mahadev Enterprises | 151/0 | 150/0 |  | 2026-04-25 |  |  | FALSE | FALSE | TRUE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 152/0-151/0 | tb507main¦152/0¦151/0 | Mahadev Enterprises | 152/0 | 151/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Ready | 134/0-133/0 | tb507main¦134/0¦133/0 | Mahadev Enterprises | 134/0 | 133/0 | 2026-05-13 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 143/0-142/0 | tb507main¦143/0¦142/0 | Mahadev Enterprises | 143/0 | 142/0 | 2026-03-26 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 134/0-134A/0 | tb507main¦134/0¦134A/0 |  | 134/0 | 134A/0 | 2026-05-13 |  |  |  | FALSE | TRUE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | Others | Ready | 114/0-113A/0 | tb507main¦114/0¦113A/0 | Tanisha Enterprises | 114/0 | 113A/0 |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | Total | tb507main¦¦Total |  |  | Total |  |  |  |  | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE
TB 507 - MAIN | TB 507 | TB 507 - MAIN | tb507main | tb507main | TB 507 | 5xx | TB | TSE | Unassigned | [9 empty] | FALSE | FALSE | FALSE