## TA413_PBNTL
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02 | [11 empty] | 24.07.2026
Name of Client: PowerGrid Bikaner Neemrana Transmission Limited (Power Grid Corporation of India) | [9 empty] | Project Duration : 21 Month EOT -31/09/2026
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 378 Crore
NOA No: CC/T/W-TW/DOM/A04/23/10569/NOA-1&2/24-103421/01&02 Date.12/03/2024 Amendment -II Comp Value As on: 401 Crore
Office: Hansera, Bikaner, Rajasthan.
Sl. No. | Activity | LOA Quantity | As per latest Estimate | Cumm. Progress up to last Month | Cumm L2 Schedule till Dec'25 | Plan for this Month | Current Month Achieved (As on dated ) | Today | Cumulative Progress | Balance | No of Gangs | Remarks
1 | Detail Survey (Km) | 112.611 | 117.8509 | 117.8509 | 112.611 |  | 0 | 0 | 117.8509 | 0 |  | Completed
2 | Soil Investigation (Nos.) | 29 | 29 | 26 | 0 |  | 0 | 0 | 26 | 0 |  | Completed
3 | Check Survey approved(Km) | 112.611 | 117.8509 | 117.8509 | 112.611 |  | 0 | 0 | 117.8509 | 0 |  | Completed
4 | Excavation | 287 | 316 | 316 | 287 | 0 | 0 | 0 | 316 | 0 |  | Completed
5 | Foundation (Nos.) | 287 | 316 | 316 | 287 | 0 | 0 | 0 | 316 | 0 |  | Completed
6 | Earthing (Nos.) | 287 | 309 | 308 | 287 | 1 | 0 | 0 | 308 | 1
7 | Tower Erection (Nos) | 287 | 306 | 303 | 287 | 3 | 0 | 0 | 303 | 3 | 1 | G_1:- R.S construction
8 | Tack Welding | 287 | 306 | 272 | 287 | 33 | 8 | 1 | 280 | 26 | 1 | G_1:- M.S Enterprises G_2:- M.B Sharma
9 | Bird Guard (Set of Three) | 241 | 244 | 133 | 244 | 4 | 4 | 0 | 137 | 107
10 | Stringing (Km) | 112.611 | 117.8509 | 87.24 | 112 | 20 | 6.362 | 0 | 93.602 | 24.2489 | 3 | G_1:- Rahim Khan
a) | Paying Out | 112.611 | 117.8509 | 87.24 | 112 | 20 | 11.028 |  | 98.268 | 19.5829 |  | G_2:- SK infra
b) | Final Sag | 112.611 | 117.8509 | 87.24 | 112 | 20 | 6.362 |  | 93.602 | 24.2489 |  | G_3 Amir Sekh
11 | OPGW (Km) | 112.611 | 117.8509 | 69.06 | 112 | 38.08 | 4.775 | 0 | 73.835 | 44.0159
.
2MRC Sandy
2MRC Sandy
2MRC Sandy

## WIP
KEC International Limited
DAILY PROGRESS REPORT : STATUS AS ON | [6 empty] | 24.07.2026
Name of the Project: |  | 765 kV D/C Bikaner III to Neemrana II (TL-02)
Contract No. & Date : |  | CC/T/W-TW/DOM/A04/23/10569/NOA-1&2/24-103421/01&02 Date.12/03/2024
ERECTION
S.NO | GANG | LOC. NO. | T.O.T | D.O.S | D.O.C | Manpower | Status
1 | R.S Construction | 37/0-N | DB2+9 | 2026-07-12 |  | 28 | Bottom Section WIP
STRINGING
S.NO | GANG | SECTION | LENGTH (KM) | D.O.S | D.O.C | Manpower | Status
1 | Rahim Khan | AP20/0 to 21/0 | 2.5502 | 2026-07-13 |  | 67 | Insulator hoisting wip
2 | SK infra | AP 40- AP 40A/0 | 4.6659 | 2026-07-15 |  | 65 | 4 PHASE Final sag WIP
3 | SK infra | AP 43A/0 to AP44/0 | 1.5845 |  |  |  | Material shifting Done
4 | Amir Sekh | AP 22/0 to AP 23/0 | 0.25905 | 2026-07-21 |  | 35 | Conductor bit cutting backstay arrangment lefty
Earthing
SR.NO | GANG | LOC. NO. | T.O.T | T.O.E. | D.O.S | D.O.C | REMARKS
1
2
OPGW
SR.NO | GANG | SECTION | LENGTH (KM) | D.O.S | D.O.C | REMARKS
Tackwelding
SR.NO | GANG | LOC. NO. | T.O.T |  | D.O.S | D.O.C | REMARKS
1
2
Accessories
SR.NO | GANG | LOC. NO. | T.O.T | ACD | NO/PH/DANGER/ CKT PLATE |  | REMARKS
1
2
3

## Visual Chart
KEC INTERNATIONAL LIMITED
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 378 Crore | [19 empty] | Visual Chart | [20 empty] | 24.07.2026
| S. No. |  | Description |  |  |  | UOM |  | Total Qty |  | Completed |  |  | Balance |  |  |  | Power Line Crossing | [8 empty] | Stringing U/P | [8 empty] | Stringing completed
| 1 |  | Foundation |  |  |  | Nos |  | 316 |  | 316 |  |  | 0 | [12 empty] | Tack Welding U/P | [8 empty] | Tack Welding completed
| 2 |  | Earthing |  |  |  | Nos |  | 309 |  | 308 |  |  | 1 |  |  |  | NH / SH Crossing | [8 empty] | Erection U/P | [6 empty] | 4 |  | Erection completed
| 3 |  | Tower Erection |  |  |  | Nos |  | 306 |  | 303 |  |  | 3 | [10 empty] | 1 |  | Foundation U/P | [8 empty] | Foundation completed
| 4 |  | Rough Sag |  |  |  | KM |  | 117.8509 |  | 98.268 |  |  | 19.5829 |  |  |  | Railway Crossing | [15 empty] | 3
| 5 |  | Final Sag |  |  |  | KM |  | 117.8509 |  | 93.602 |  |  | 24.2489 | [10 empty] | 1 |  | Excavation U/P | [6 empty] | 2 |  | Excavation completed
[18 empty] | Canal | [17 empty] | Earthing completed
[15 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15
|  | Hold | [10 empty] | Gantry |  | 1/0 |  | 2A/0 |  | 2A/1 |  | 2A/2 |  | 2A/3 |  | 2A/4 |  | 2A/5 |  | 2A/6 |  | 3A/0 |  | 3A/1 |  | 3A/2 |  | 3A/3 |  | 3A/4 |  | 3A/5 |  | 3A/6
Foundation ROW
[9 empty] | Bikaner III Gantry |  |  |  |  | 150 | 3 | 290.21 | 3 | 378 | 3 | 381 | 3 | 419 | 3 | 422 | 3 | 399 | 3 | 423 | 3 | 414.992 | 3 | 409 | 3 | 402 | 3 | 409 | 3 | 337 | 3 | 365 | 3 | 378 | 3 | 391.467
|  | Erection ROW | [12 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
[13 empty] | Gantry |  | DD60+0 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
| 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37
| 3B/0 |  | 3B/1 |  | 3B/2 |  | 3B/3 |  | 4/0 |  | 4/1 |  | 4A/0 |  | 4A/1 |  | 4A/2 |  | 4A/3 |  | 4A/4 |  | 4A/5 |  | 4A/6 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 5/7 |  | 5/8
| 3 | 356 | 3 | 439 | 3 | 377 | 3 | 455.07 | 3 | 344.163 | 3 | 365 | 3 | 340 | 3 | 420 | 3 | 415 | 3 | 365 | 3 | 330 | 3 | 457 | 3 | 354.611 | 3 | 428.389 | 3 | 340 | 3 | 375 | 3 | 365 | 3 | 460 | 3 | 380 | 3 | 410 | 3 | 400 | 3 | 420
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DB1+9 |  | DA+3 |  | DA+9 |  | DA+6 |  | DB2+9 |  | DA+6 |  | DB1+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9 |  | DB1+6 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA-1.5 |  | DA+6 |  | DA+3 |  | DA+9 |  | DA+6
| 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59
| 5/9 |  | 5/10 |  | 5A/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5 |  | 6/6 |  | 6/7 |  | 6/8 |  | 6/9 |  | 6/10 |  | 6/11 |  | 6/12 |  | 7/0 |  | 7/1 |  | 7/2 |  | 7/3 |  | 7/4 |  | 7/5
| 3 | 345 | 3 | 495 | 3 | 419.48 | 3 | 350.52 | 3 | 445 | 3 | 390 | 3 | 350 | 3 | 490 | 3 | 350 | 3 | 347 | 3 | 373 | 3 | 380 | 3 | 335 | 3 | 315 | 3 | 410 | 3 | 365.716 | 3 | 319.284 | 3 | 465 | 3 | 375 | 3 | 355 | 3 | 420 | 3 | 315
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+9 |  | DB1+12 |  | DB1+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+9 |  | DA+9 |  | DA-3 |  | DA+1.5 |  | DA+3 |  | DA+6 |  | DA+1.5 |  | DA-1.5 |  | DA+1.5 |  | DB2+0 |  | DA-3 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+6
| 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81
| 7/6 |  | 7A/0 |  | 7A/1 |  | 7A/2 |  | 7A/3 |  | 7A/4 |  | 7A/5 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8 |  | 8/9 |  | 8/10 |  | 8/11 |  | 8A/0 |  | 9/0 |  | 9/1
| 3 | 450 | 3 | 435 | 3 | 385 | 3 | 390 | 3 | 405 | 3 | 390 | 3 | 429.77 | 3 | 350 | 3 | 330 | 3 | 390 | 3 | 400 | 3 | 338 | 3 | 357 | 3 | 335 | 3 | 415 | 3 | 375 | 3 | 375 | 3 | 375 | 3 | 415 | 3 | 466.63 | 3 | 418.372 | 3 | 410
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-1.5 |  | DB1+6 |  | DA+1.5 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA-3 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+9 |  | DB1+12 |  | DB1+12 |  | DA+3
| 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103
| 9/2 |  | 9/3 |  | 9/4 |  | 9/5 |  | 9/6 |  | 9/7 |  | 9/8 |  | 9/9 |  | 9/10 |  | 9/11 |  | 10/0 |  | 10/1 |  | 10/2 |  | 11/0 |  | 12/0 |  | 13/0 |  | 13A/0 |  | 14/0 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3
[30 empty] | 132kV | [5 empty] | 400kV
| 3 | 395 | 3 | 395 | 3 | 425 | 3 | 415 | 3 | 405 | 3 | 435 | 3 | 405 | 3 | 435 | 3 | 395 | 3 | 431.548 | 3 | 363.452 | 3 | 295 | 3 | 345.731 | 3 | 242.89 | 3 | 329.73 | 3 | 416.88 | 3 | 480.27 | 3 | 223.82 | 3 | 405.915 | 3 | 405 | 3 | 420 | 3 | 415
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DB1+6 |  | DA+3 |  | DA+3 |  | DD45+0 |  | DB1+9 |  | DD60+9 |  | DB1+9 |  | DD60+18 |  | DD60+25 |  | DA+6 |  | DA+3 |  | DA+3
[27 empty] | NH-62 | [6 empty] | RC 4 Leg
| 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125
| 15/4 |  | 15/5 |  | 15/6 |  | 15/7 |  | 15/8 |  | 15/9 |  | 15/10 |  | 15/11 |  | 15/12 |  | 16/0 |  | 17/0 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 18/5 |  | 18/6 |  | 18/7 |  | 19/0 |  | 20/0 |  | 20/1
| 3 | 410 | 3 | 285 | 3 | 355 | 3 | 355 | 3 | 410 | 3 | 430 | 3 | 385 | 3 | 455 | 3 | 288.425 | 3 | 392.69 | 3 | 398.4 | 3 | 307.595 | 3 | 390 | 3 | 380 | 3 | 405 | 3 | 335 | 3 | 425 | 3 | 402 | 3 | 385.434 | 3 | 279.36 | 3 | 388.515 | 3 | 330
[5 empty] | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA+3 |  | DA+9 |  | DA+0 |  | DA+1.5 |  | DA+0 |  | DA-1.5 |  | DA+0 |  | DA+6 |  | DC2+0 |  | DC1+3 |  | DB2+6 |  | DA+3 |  | DA+1.5 |  | DA+6 |  | DA-3 |  | DA+0 |  | DA+9 |  | DA+1.5 |  | DD60+3 |  | DD60+3 |  | DA-3
[9 empty] | Canal | [28 empty] | RLY
| 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147
| 20/2 |  | 20/3 |  | 20/4 |  | 20/5 |  | 20/6 |  | 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 22/0 |  | 23/0 |  | 23A/0 |  | 24/0 |  | 25/0 |  | 26/0 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 27/4
[24 empty] | 220kV | [5 empty] | 400kV |  |  |  | 765kV
| 3 | 340 | 3 | 420 | 3 | 396 | 3 | 355 | 3 | 320.652 | 3 | 326.348 | 3 | 427 | 3 | 410 | 3 | 405 | 3 | 300 | 3 | 415.187 | 3 | 259.05 | 3 | 440.46 | 3 | 496.69 | 3 | 244.03 | 3 | 237.43 | 3 | 203.48 | 3 | 453.688 | 3 | 345 | 3 | 360 | 3 | 410 | 3 | 350
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-3 |  | DA+1.5 |  | DA+3 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DC2+15 |  | DB2+9 |  | DB1+9 |  | DD60+18 |  | DD60+18 |  | DD60+35 |  | DD60+35 |  | DA+9 |  | DA-1.5 |  | DA+1.5 |  | DA+1.5
| 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168 |  | 169
| 27/5 |  | 27/6 |  | 28/0 |  | 29/0 |  | 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 29A/0 |  | 29A/1 |  | 29A/2 |  | 29A/3 |  | 29A/4 |  | 29A/5 |  | 29A/6 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5
| 3 | 355 | 3 | 274.587 | 3 | 211.21 | 3 | 384.204 | 3 | 430 | 3 | 370 | 3 | 390 | 3 | 435 | 3 | 370 | 3 | 455 | 3 | 325 | 3 | 395 | 3 | 345 | 3 | 345 | 3 | 440 | 3 | 364.008 | 3 | 295.993 | 3 | 425 | 3 | 315 | 3 | 380 | 3 | 430 | 3 | 380
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA-1.5 |  | DA-3 |  | DC2-3 |  | DC1+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+9 |  | DB1+0 |  | DA+0 |  | DA+9 |  | DA+3 |  | DA+9 |  | DA+0
Exp. Way
| 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191
| 30/6 |  | 30/7 |  | 30/8 |  | 30/9 |  | 30/10 |  | 31/0 |  | 31/1 |  | 31/2 |  | 31/3 |  | 31/4 |  | 31/5 |  | 31/6 |  | 31/7 |  | 31/8 |  | 31/9 |  | 31/10 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 32/4 |  | 32/5
| 3 | 335 | 3 | 395 | 3 | 390 | 3 | 350 | 3 | 428.239 | 3 | 376.761 | 3 | 410 | 3 | 430 | 3 | 380 | 3 | 445 | 3 | 385 | 3 | 420 | 3 | 415 | 3 | 310 | 3 | 445 | 3 | 316.608 | 3 | 385.51 | 3 | 410 | 3 | 390 | 3 | 450 | 3 | 370 | 3 | 439
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+6 |  | DA-3 |  | DA+3 |  | DA-3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA-1.5 |  | DA+6 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+1.5 |  | DA+4.5 |  | DB2+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+9 |  | DA+9
RC 4 Leg
| 192 |  | 193 |  | 194 |  | 195 |  | 196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213
| 32/6 |  | 32/7 |  | 32A/0 |  | 32A/1 |  | 33/0 |  | 33/1 |  | 33/2 |  | 33/3 |  | 33/4 |  | 33/5 |  | 33/6 |  | 33/7 |  | 33/8 |  | 33/9 |  | 34/0 |  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | 34/5 |  | 34/6 |  | 34/7
| 3 | 360 | 3 | 479 | 3 | 402 | 3 | 438.439 | 3 | 430.56 | 3 | 406 | 3 | 435 | 3 | 405 | 3 | 420 | 3 | 405 | 3 | 415 | 3 | 355 | 3 | 380 | 3 | 398.203 | 3 | 441.798 | 3 | 395 | 3 | 375 | 3 | 445 | 3 | 395 | 3 | 435 | 3 | 330 | 3 | 330
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+3 |  | DB1+9 |  | DA+6 |  | DB1+9 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+1.5 |  | DB1+6 |  | DA+9 |  | DA+9 |  | DA+1.5 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+0
| RC 4 Leg | [7 empty] | RC 4 Leg |  | RC 4 Leg
| 214 | 5 | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235
| 34/8 |  | 34/9 |  | 34/10 |  | 34/11 |  | 34/12 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  | 35/6 |  | 35/7 |  | 35/8 |  | 35/9 |  | 35/10 |  | 35/11 |  | 36/0 |  | 36A/0 |  | 36A/1 |  | 36B/0 N |  | 36C/0 N
| 3 | 400 | 3 | 310 | 3 | 325 | 3 | 365 | 3 | 351.79 | 3 | 393.209 | 3 | 435 | 3 | 405 | 3 | 405 | 3 | 435 | 3 | 345 | 3 | 395 | 3 | 440 | 3 | 400 | 3 | 440 | 3 | 330 | 3 | 493.084 | 3 | 454 | 3 | 451 | 3 | 375.7 | 3 | 420.81 | 3 | 469.33
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+0 |  | DA+1.5 |  | DA-3 |  | DA+1.5 |  | DA+3 |  | DB2+0 |  | DA+6 |  | DA+6 |  | DA-3 |  | DA+9 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+1.5 |  | DA+3 |  | DA+3 |  | DB2+3 |  | DB1+9 |  | DA+3 |  | DB2+9 |  | DC2+15
HMPL OIL PIPE LINE
| 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257
| 37/0 N |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 37A/0 |  | 37A/1 |  | 37A/2 |  | 37A/3 |  | 37A/4 |  | 37A/5 |  | 37A/6 |  | 38/0 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 38/6 |  | 38/7 |  | 38/8 |  | 38/9
| 3 | 411.28 | 3 | 405 | 3 | 430 | 3 | 410 | 3 | 420 | 3 | 280 | 3 | 345 | 3 | 330 | 3 | 455 | 3 | 340 | 3 | 435 | 3 | 398.589 | 3 | 426.411 | 3 | 390 | 3 | 335 | 3 | 440 | 3 | 280 | 3 | 450 | 3 | 285 | 3 | 445 | 3 | 360 | 3 | 430
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DB2+9 |  | DA+3 |  | DA-1.5 |  | DA+9 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+3 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+1.5 |  | DA+0
| 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279
| 38/10 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  | 39/5 |  | 39/6 |  | 39/7 |  | 39/8 |  | 39/9 |  | 39/10 |  | 39/11 |  | 40/0 |  | 40/1 |  | 40/2 |  | 40/3 |  | 40/4 |  | 40/5 |  | 40/6 |  | 40/7 |  | 40/8
| 3 | 322.266 | 3 | 392.73 | 3 | 395 | 3 | 385 | 3 | 340 | 3 | 395 | 3 | 410 | 3 | 415 | 3 | 415 | 3 | 350 | 3 | 425 | 3 | 350 | 3 | 444.081 | 3 | 260.918 | 3 | 385 | 3 | 435 | 3 | 385 | 3 | 455 | 3 | 370 | 3 | 400 | 3 | 350 | 3 | 470
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DB2+0 |  | DA-1.5 |  | DA+3 |  | DA+1.5 |  | DA+3 |  | DA+1.5 |  | DA+1.5 |  | DA+3 |  | DA+1.5 |  | DA+6 |  | DA+3 |  | DA+6 |  | DB1+6 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA-1.5
RC 4 Leg
| 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301
| 40/9 |  | 40/10 |  | 40/11 |  | 40A/0 |  | 41/0 |  | 41/1 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42A/0 |  | 43/0 |  | 43/1 |  | 43/2 |  | 43/3 |  | 43/4 |  | 43A/0 |  | 43/6 |  | 43/7 |  | 43/8 |  | 44/0 |  | 44/1 |  | 44/2
| 3 | 355 | 3 | 485 | 3 | 315 | 3 | 410.61 | 3 | 358 | 3 | 465.782 | 3 | 419.998 | 3 | 375 | 3 | 464 | 3 | 424.891 | 3 | 341.866 | 3 | 375 | 3 | 375 | 3 | 355 | 3 | 405 | 3 | 375 | 3 | 385 | 3 | 415 | 3 | 409.546 | 3 | 400 | 3 | 427 | 3 | 366
| 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+9 |  | DA+3 |  | DA+9 |  | DB1+9 |  | DB1+9 |  | DA+9 |  | DB2+0 |  | DA+3 |  | DA+9 |  | DB1+9 |  | DB1+0 |  | DA-1.5 |  | DA+6 |  | DA-1.5 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+9 |  | DB1+6 |  | DA+3 |  | DA+3
[7 empty] | ROW | [22 empty] | TP TWR
| 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | Common Point
| 44/3 |  | 44/4 |  | 44/5 |  | 45/0 |  | 46/0
132KV
| 3 | 350 | 3 | 383 | 3 | 457.155 | 3 | 208.53 | 3
| 2 |  | 2 |  | 2 |  | 2 |  | 2
| DA+3 |  | DA+0 |  | DA+0 |  | DB1+9 |  | DB1+12
CP
Progress overview (Tower wise breakups)
| TOT |  | Total Qty in No's |  | FDN |  |  | ERE
[5 empty] | Comp. |  | Bal. | Comp. |  | Balance |  |  |  | SUNSURE(SOLAR) ROUTE DIVERTED AREA | [16 empty] | OILPIPE LINE ROUTE DIVERTED AREA
| DA-3 |  | 12 |  | 12 |  | 0 | 12 |  | 0 | [22 empty] | Existing configuration | [6 empty] | Revised configuration
| DA-1.5 |  | 12 |  | 12 |  | 0 | 12 |  | 0 |  |  |  | Existing (Approved ) route | [7 empty] | Modified Diverted route | [10 empty] | Loc |  | ToT |  | Span |  |  | Loc |  | ToT |  | Span
| DA+0 |  | 33 |  | 33 |  | 0 | 33 |  | 0 |  |  |  | DA |  |  |  |  | 15 |  |  | DA | [5 empty] | 15 |  |  |  |  | 36A/1 |  | DA+3 |  |  |  |  | 36A/1 |  | DA+3
| DA+1.5 |  | 24 |  | 24 |  | 0 | 24 |  | 0 |  |  |  | DB1 |  |  |  |  | 1 |  |  | DB1 | [5 empty] | 1 | [8 empty] | 389 | [6 empty] | 375.69
| DA+3 |  | 69 |  | 69 |  | 0 | 69 |  | 0 |  |  |  | DB2 |  |  |  |  | 1 |  |  | DB2 | [5 empty] | 1 |  |  |  |  | 36A/2 |  | DA+9 |  |  |  |  | 36B/0 |  | DB2+9
| DA+4.5 |  | 1 |  | 1 |  | 0 | 1 |  | 0 |  |  |  | DC1 |  |  |  |  | 0 |  |  | DC1 | [5 empty] | 0 | [8 empty] | 451.52 | [6 empty] | 420.81
| DA+6 |  | 47 |  | 47 |  | 0 | 47 |  | 0 |  |  |  | DC2 |  |  |  |  | 0 |  |  | DC2 | [5 empty] | 0 |  |  |  |  | 37/0 |  | DB2+3 |  |  |  |  | 37/0 |  | DC2+15
| DA+9 |  | 46 |  | 46 |  | 0 | 46 |  | 0 |  |  |  | DD45 |  |  |  |  | 1 |  |  | DD45 | [5 empty] | 2 | [8 empty] | 401.39 | [6 empty] | 469.33
| DB1+0 |  | 7 |  | 7 |  | 0 | 7 |  | 0 |  |  |  | DD60 |  |  |  |  | 1 |  |  | DD60 | [5 empty] | 1 |  |  |  |  | 37/1 |  | DA+3 |  |  |  |  | 37A/0 |  | DB2+9
| DB1+3 |  | 2 |  | 2 |  | 0 | 2 |  | 0 |  |  |  | Total |  |  |  |  | 19 |  |  | Total | [5 empty] | 20 | [8 empty] | 430 | [6 empty] | 411.28
| DB1+6 |  | 6 |  | 6 |  | 0 | 6 |  | 0 | [22 empty] | 37/2 |  | DA+3 |  |  |  |  | 37/2 |  | DA+3
| DB1+9 |  | 12 |  | 12 |  | 0 | 12 |  | 0 |  |  |  |  | Foundation Dismentling required
| DB1+12 |  | 4 |  | 4 |  | 0 | 4 |  | 0
| DB2+0 |  | 5 |  | 5 |  | 0 | 5 |  | 0 | [5 empty] | 1 | 3/4 | DA+6 |  | Due to sunsure objection change in Route | [10 empty] | 1. Dismantling of 03 nos of foundations 36A/2, 37/0, 37/1.
| DB2+3 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 2 | 3/6 | DA+3 |  | Due to sunsure objection change in Route
| DB2+6 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 3 | 3/7 | DA+3 |  | Due to sunsure objection change in Route | [10 empty] | 2. Dismantling of already erected tower at 36A/2.
| DB2+9 |  | 4 |  | 4 |  | 0 | 3 |  | 1 | [5 empty] | 4 | 3/8 | DA+0 |  | Due to sunsure objection change in Route
| DC1+0 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 5 | 3/9 | DA+0 |  | Due to sunsure objection change in Route | [10 empty] | 3. 03 Nos of New foundations and Erections as per revised configuration.
| DC1+3 |  | 1 |  | 1 |  | 0 | 1 |  | 0 | [5 empty] | 6 | 3/10 | DA+9 |  | Due to sunsure objection change in Route
| DC2+0 |  | 2 |  | 2 |  | 0 | 2 |  | 0 | [5 empty] | 7 | 3/11 | DA+0 |  | Due to sunsure objection change in Route
| DC2-3 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DC2+15 |  | 2 |  | 2 |  | 0 | 1 |  | 1
| DD45+0 |  | 2 |  | 2 |  | 0 | 2 |  | 0
| DD45+3 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+0 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+3 |  | 2 |  | 2 |  | 0 | 2 |  | 0
| DD60+9 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+18 |  | 3 |  | 3 |  | 0 | 3 |  | 0
| DD60+25 |  | 1 |  | 1 |  | 0 | 1 |  | 0
| DD60+35 |  | 2 |  | 2 |  | 0 | 2 |  | 0
| Total |  | 306 |  | 306 |  | 0 | 304 |  | 2
Global Footprint in 110+ countries*
*Includes EPC and Supply
Location Summary

## Stringing
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Stringing | [19 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Section | [14 empty] | 7.4846
|  | From | To | Length in Km's | Cum. Length in Km's | TSE/Manual | Insulator hoisting Start | Insulator Hoisting Complete | Paying Out Start | Paying Out Completed | Final sag start | Final sag complete | Earthwire Final Sag | Jumpuring | Spacering | Clipping | Revenue | JMC Status | Name of the Contractor | Remarks
1 | 1 | AP-34 | AP-35 | 4.8986 | 4.8986 | TSE | 2025-02-06 | 2025-02-08 | 2025-02-21 | 2025-02-26 | 2025-03-01 | 2025-03-04 | 2025-03-05 | complete | complete | complete | 4696115.5929 | Received | SK Infratech | Completed | Gang Engauged on : 18-01-25
2 | 1 | 37A/0 | AP-38/0 | 2.5836 | 7.4822 | TSE | 2025-03-11 | 2025-03-13 | 2025-03-17 | 2025-03-20 | 2025-04-13 | 2025-04-16 | 2025-04-17 | 2025-04-21 | 2025-05-06 | complete | 2476802.0067 | Received | SK Infratech | Completed
3 | 2 | AP-38 | AP-39 | 4.1637 | 11.6459 | TSE | 2025-03-26 | 2025-03-28 | 2025-03-29 | 2025-04-05 | 2025-04-15 | 2025-04-16 | 2025-04-17 | complete | complete | complete | 3991580.5297 | Received | SK Infratech | Completed | 4921849.1215 |  | 0.49218
4 | 3 | AP-39 | AP-40 | 4.716 | 16.3619 | TSE | 2025-04-04 | 2025-04-06 | 2025-04-25 | 2025-04-29 | 2025-04-29 | 2025-04-30 | 2025-05-27 | complete | 2025-12-23 | 2025-12-23 | 4521074.468 | Received | SK Infratech | Completed
5 | 4 | AP-7 | AP-7A | 2.6993 | 19.0611 | TSE | 2025-08-21 | 2025-08-23 | 2025-08-27 | 2025-09-04 | 2025-09-17 | 2025-09-18 | 2025-09-18 | complete | complete | complete | 2587715.0073 | Received | Rahim Khan | Completed | Gang Engauged on: 16.08.25
6 | 4 | AP-7A | AP-8 | 2.4348 | 21.4959 | TSE | 2025-09-08 | 2025-09-10 | 2025-09-12 | 2025-09-16 | 2025-09-24 | 2025-09-25 | 2025-09-25 | complete | complete | complete | 2334134.1142 | Received | Rahim Khan | Completed
7 | 5 | AP-8 | AP-8A | 4.455 | 25.9509 | TSE | 2025-09-29 | 2025-10-01 | 2025-10-05 | 2025-10-15 | 2025-10-21 | 2025-10-22 | 2025-10-22 | 2025-10-28 | complete | complete | 4270862.3314 | Received | Rahim Khan | Completed
8 | 6 | AP-8A | AP-9/0 | 0.46663 | 26.4175 | Manual | 2025-09-29 | 2025-10-01 | 2025-10-03 | 2025-10-05 | 2025-10-26 | 2025-10-27 | 2025-10-27 | 9/0 Balance | complete | complete | 447341.9122 | Received | Rahim Khan | Completed
9 | 7 | AP-6 | AP-7 | 4.9012 | 31.3188 | TSE | 2025-11-12 | 2025-11-14 | 2025-11-19 | 2025-11-23 | 2025-11-27 | 2025-11-28 | 2025-11-30 | 2025-12-24 | 2025-12-19 | complete | 4698654.1436 | Received | Rahim Khan | Completed | Gang Engauged 03/09/25
10 | 8 | AP-5A | AP-6 | 0.41948 | 31.7383 | Manual | 2025-11-25 | 2025-11-27 | 2025-11-05 | 2025-11-09 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2026-01-11 | 2025-12-19 | complete | 402141.7129 | Received | Rahim Khan | Completed
11 | 9 | AP-5 | AP-5A | 4.4184 | 36.1566 | TSE | 2025-11-24 | 2025-12-05 | 2025-12-07 | 2025-12-12 | 2025-12-21 | 2025-12-22 | 2026-01-05 | 2026-02-16 | 2026-01-09 | complete | 4235764.567 | Received | Rahim Khan | Completed
12 | 10 | AP-4A | AP-5/0 | 2.6816 | 38.8383 | TSE | 2025-12-12 | 2025-12-14 | 2025-12-15 | 2025-12-22 | 2025-12-30 | 2025-12-31 | 2026-01-02 | 2026-02-21 | 2026-01-19 | 2026-01-11 | 2570772.482 | Received | Rahim Khan | Completed
13 | 1 | AP-4 | AP4A/0 | 0.70916 | 39.5474 | TSE | 2025-12-23 | 2025-12-25 | 2025-12-27 | 2025-12-31 | 2026-01-14 | 2026-01-18 | 2026-01-18 | complete | complete | complete | 679851.3005 | Received | Rahim Khan | Completed
14 | 2 | AP-33 | AP-34 | 4.0498 | 43.5972 | TSE | 2025-12-30 | 2026-01-04 | 2026-01-07 | 2026-01-13 | 2026-01-21 | 2026-01-24 | 2026-01-25 | complete | complete | complete | 3882375.874 | Received | SK Infratech | Completed | Noor Alam
15 | 3 | AP3B/0 | AP4/0 | 1.627 | 45.2242 | TSE | 2026-01-10 | 2026-01-12 | 2026-01-14 | 2026-01-17 | 2026-01-24 | 2026-01-27 | 2026-01-28 | complete | complete | 2026-02-01 | 1559751.5181 | Received | Rahim Khan | Completed
16 | 4 | AP-32A | AP-33 | 0.84 | 46.0642 | TSE | 2026-01-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 2026-01-31 | 2026-02-06 | 2026-02-07 | complete | complete | complete | 805280.4396 | Received | SK Infratech | Completed
17 | 5 | AP32/0 | AP32A/0 | 3.284 | 49.3482 | TSE | 2026-01-21 | 2026-01-24 | 2026-01-25 | 2026-01-30 | 2026-01-31 | 2026-02-06 | 2026-02-07 | complete | complete | complete | 3148263.052 | Received | SK Infratech | Completed
18 | 1 | 2A/0 | 3A/0 | 2.837 | 52.1852 | TSE | 2026-02-09 | 2026-02-15 | 2026-02-18 | 2026-02-26 | 2026-02-27 | 2026-03-03 | 2026-03-05 | Half side balance | complete | complete | 2719738.818 | Received | Rahim Khan | Completed
19 | 2 | 3A/0 | 3B/0 | 2.6915 | 54.8766 | TSE | 2026-01-31 | 2026-02-06 | 2026-02-08 | 2026-02-13 | 2026-02-27 | 2026-03-03 | 2026-03-05 | complete | complete | complete | 2580221.1059 | Received | Rahim Khan | Completed
20 | 4 | 1/0 | 2A/0 | 0.29 | 55.1666 | Manual | 2026-02-10 | 2026-02-12 | 2026-02-14 | 2026-02-18 | 2026-03-09 | 2026-03-13 | 2026-03-14 | Balance | complete | complete | 278013.4851 | Received | Rahim Khan | Completed
21 | 3 | 31/0 | 32/0 | 4.333 | 59.4996 | TSE | 2026-01-02 | 2026-02-08 | 2026-02-10 | 2026-02-15 | 2026-03-02 | 2026-03-10 | 2026-03-11 | complete | complete | complete | 4153904.9343 | Received | SK Infratech | Completed
22 | 1 | 30/0 | 31/0 | 4.124 | 63.6236 | TSE | 2026-02-16 | 2026-02-25 | 2026-02-27 | 2026-03-06 | 2026-03-12 | 2026-03-16 | 2026-03-17 | complete | complete | complete | 3953543.4916 | Received | SK Infratech | Completed
23 | 1 | 9/0 | 10/0 | 4.9649 | 68.5886 | TSE | 2026-03-03 | 2026-03-20 | 2026-03-28 | 2026-04-02 | 2026-04-06 | 2026-04-10 | 2026-04-10 | complete | complete | complete | 4759705.905 | Received | Rahim Khan | Completed
24 | 1 | 29A/0 | 30/0 | 2.669 | 71.2576 | TSE | 2026-04-06 | 2026-04-09 | 2026-04-22 | 2026-04-28 | 2026-04-30 | 2026-05-03 | 2026-05-04 | complete | complete | complete | 2558689.4408 | Received | SK Infratech | Completed
25 | 2 | 10/0 | 11/0 | 1.0042 | 72.2618 | TSE | 2026-03-31 | 2026-04-04 | 2026-04-07 | 2026-04-09 | 2026-05-12 | 2026-05-16 | 2026-05-16 |  | complete | complete | 962677.2949 | Received | Rahim Khan | Completed
26 | 3 | 29/0 | 29A/0 | 2.3792 | 74.641 | TSE | 2026-04-28 | 2026-05-02 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-16 | complete | complete | complete | 2280864.8131 | Received | SK Infratech | Completed
27 | 4 | 27/0 | 28/0 | 2.5483 | 77.1892 | TSE | 2026-05-17 | 2026-05-20 | 2026-05-20 | 2026-05-23 | 2026-05-24 | 2026-05-27 | 2026-05-28 |  | complete | complete | 2442947.6336 | Received | SK Infratech | Completed
28 | 1 | 11/0 | 12/0 | 0.24289 | 77.4321 | Manual | 2026-06-01 | 2026-06-03 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-06 | 2026-06-06 |  | complete | complete | 232850.6738 | Received | Rahim Khan | Completed
29 | 2 | 14/0 | 15/0 | 0.22382 | 77.6559 | Manual | 2026-06-01 | 2026-06-03 | 2026-06-07 | 2026-06-12 | 2026-06-07 | 2026-06-12 | 2026-06-12 |  | complete |  | 214568.8905 | Pending | Gopal Associate | Hotline
30 | 3 | 13/0 | 13A/0 | 0.41688 | 78.0728 | Manual | 2026-03-01 | 2026-03-06 | 2026-06-19 | 2026-06-23 | 2026-06-19 | 2026-06-23 | 2026-06-23 |  | complete |  | 399647.2608 | Received | Rahim Khan | Completed | BSPL | Rough sag arangment (Work Hold) |  | 2 phase
31 | 4 | 13A/0 | 14/0 | 0.48027 | 78.5531 | Manual | 2026-03-01 | 2026-03-06 | 2026-06-19 | 2026-06-23 | 2026-06-19 | 2026-06-23 | 2026-06-23 |  | complete |  | 460419.0913 | Received | Rahim Khan | Completed
32 | 5 | 18/0 | 19/0 | 3.03 | 81.5831 | TSE | 2026-06-07 | 2026-06-11 | 2026-06-13 | 2026-06-18 | 2026-06-25 | 2026-06-28 | 2026-06-28 |  |  | complete | 2904789.387 | Received | Rahim Khan | Completed
33 | 6 | 35/0 | 36/0 | 4.9163 | 86.4994 | TSE | 2026-06-02 | 2026-06-07 | 2026-06-13 | 2026-06-26 | 2026-06-26 | 2026-06-27 | 2026-06-27 |  |  | complete 35/3 ROW | 4713088.7955 | Pending | SK Infratech | Completed
34 | 7 | 24/0 | 25/0 | 0.24403 | 86.7434 | Manual | 2026-06-17 | 2026-06-18 | 2026-06-21 | 2026-06-26 | 2026-06-22 | 2026-06-26 | 2026-06-26 |  | complete |  | 233943.5544 | Pending | Gopal Associate | Completed
35 | 8 | 23A/0 | 24/0 | 0.49669 | 87.2401 | Manual | 2026-06-19 | 2026-06-20 | 2026-06-22 | 2026-06-26 | 2026-06-22 | 2026-06-26 | 2026-07-05 |  | complete |  | 476160.4066 | Pending | Amir Sekh | Completed
36 | 1 | 28/0 | 29/0 | 0.21121 | 87.4513 | Manual | 2025-06-27 | 2026-06-28 | 2026-07-01 | 2026-07-02 | 2026-07-01 | 2026-07-02 | 2026-07-02 | complete | complete |  | 202480.0972 | Pending | SK Infratech | Completed
37 | 2 | 23/0 | 23A/0 | 0.44046 | 87.8918 | Manual | 2026-06-28 | 2026-06-29 | 2026-07-01 | 2026-07-04 | 2026-07-01 | 2026-07-04 | 2026-07-05 |  | complete |  | 422254.5505 | Pending | Amir Sekh | Completed
38 | 3 | 36/0 | 36A/0 | 0.454 | 88.3458 | Manual | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-11 | 2026-07-09 | 2026-07-11 | 2026-07-12 |  | complete |  | 435234.9043 | Pending | SK Infratech | Completed
39 | 4 | 25/0 | 26/0 | 0.23743 | 88.5832 | Manual | 2026-07-07 | 2026-07-07 | 2026-07-01 | 2026-07-16 | 2026-07-14 | 2026-07-16 | 2026-07-16 |  |  |  | 227616.3509 | Pending | Amir Sekh | Completed
40 | 5 | 15/0 | 16/0 | 5.0193 | 93.6026 | TSE | 2026-06-06 | 2026-06-14 | 2026-07-09 | 2026-07-17 | 2026-07-17 | 2026-07-20 | 2026-07-21 |  |  |  | 4811876.5735 | Pending | Rahim Khan | Completed
41 |  | 40/0 | 40A/0 | 4.6659 | 98.2685 | TSE | 2026-06-21 | 2026-07-11 | 2026-07-15 | 2026-07-22 | 2026-07-23 | [7 empty] | SK Infratech | Middle phase final sag WIP
42 |  | 20/0 | 21/0 | 2.5502 | 100.8187 | TSE | 2026-07-13 | [11 empty] | Rahim Khan | Shutdown arrangement, pilot paying out done
43 |  | 22/0 | 23/0 | 0.25905 | 101.0777 | Manual | 2026-07-21 | [11 empty] | Amir Sekh | Conductor bit cutting backstay arrangment lefty
44 |  | 43A/0 | 44/0 | 1.5845 | 102.6623 | TSE | [12 empty] | SK Infratech | Matrial Shifting
Formulas:
Insulator hoisting Start = [Insulator Hoisting Complete]-2
Insulator hoisting Start = [Paying Out Start]-4
Final sag start = [Final sag complete]-3
Final sag start = [Paying Out Completed]
Earthwire Final Sag = [Final sag complete]
Earthwire Final Sag = [Final sag complete]+1
Insulator Hoisting Complete = [Paying Out Start]+3
Insulator Hoisting Complete = [Insulator hoisting Start]+3

## Stretch readiness
Stretch Readiness Status - 765 KV D/C Bikaner III - Neemrana II TL02 TA-413
| Description | Stringing Type | Line length | TSE/Manual Completed | Stringing Compl | Balanced | Remarks
| Stringing | 62 | 117.8561 | 40 | 93.6042 | 24.2518 |  | Bal.km | Bal. section |  | Bal. section | Bal.km
| TSE | 37 | 109.2852 | 27 | 88.9802 | 20.3049 | 2 | 20.3049 | 10 |  | 10 | 20.3049
| Manual | 25 | 8.5709 | 13 | 4.624 | 3.9469 | 0 | 3.9469 | 12 |  | 12 | 3.9469
Sl No. | Section | Section Length (M) | Type | Crossing details | No. of Locations (Including for end twr) | Foundation |  | Erection |  |  | Stringing
[6 empty] | Completed | Balance | Completed | Balance | Month | Remarks
1 | Gantry - AP-1 | 150.014 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26
2 | AP-1 - AP-2A | 290.21 | Manual |  | 1 | 1 | 0 | 1 | 0 | Jan'26 | Completed
3 | AP/2A - AP/3A | 2836.992 | TSE |  | 7 | 7 | 0 | 7 | 0 | Jan'26 | Completed
4 | AP3A/0-AP3B/0 | 2691.467 | TSE |  | 7 | 7 | 0 | 7 | 0 | Jan'26 | Completed
5 | AP3B/0-AP4/0 | 1627.07 | TSE |  | 4 | 4 | 0 | 4 | 0 | Jan'26 | Completed | Stringing for stringing
6 | AP-4 - AP-4A/0 | 709.163 | TSE |  | 2 | 2 | 0 | 2 | 0 | comp | Completed
7 | AP-4A/0 - AP-5 | 2681.611 | TSE |  | 7 | 7 | 0 | 7 | 0 | comp | Completed
8 | AP-5 - AP-5A/0 | 4418.389 | TSE |  | 11 | 11 | 0 | 11 | 0 | comp | Completed
9 | AP-5A/0 - AP-6 | 419.48 | Manual |  | 1 | 1 | 0 | 1 | 0 | comp | Completed
10 | AP-6 - AP-7 | 4901.236 | TSE |  | 13 | 13 | 0 | 13 | 0 | comp | Completed
11 | AP-7 - AP-7A/0 | 2699.284 | TSE |  | 7 | 7 | 0 | 7 | 0 | comp | Completed
12 | AP-7A/0 - AP-8/0 | 2434.77 | TSE |  | 6 | 6 | 0 | 6 | 0 | comp | Completed
13 | AP-8/0 - AP-8A/0 | 4455 | TSE |  | 12 | 12 | 0 | 12 | 0 | comp | Completed
14 | AP-8A/0 - AP-9/0 | 466.63 | Manual |  | 1 | 1 | 0 | 1 | 0 | comp | Completed
15 | AP-9/0 - AP-10/0 | 4964.92 | TSE |  | 12 | 12 | 0 | 12 | 0 | Jan'26 | Completed
16 | AP-10/0 - AP-11/0 | 1004.183 | TSE |  | 3 | 3 | 0 | 3 | 0 | Feb'26 | Completed
17 | AP-11/0 - AP-12/0 | 242.89 | Manual | NH-62 | 1 | 1 | 0 | 1 | 0 | Feb'26 | Completed
18 | AP-12/0 - AP-13/0 | 329.73 | Manual | 132 KV | 1 | 1 | 0 | 1 | 0 | Feb'26 | Ready for stringing
19 | AP-13/0 - AP-13A/0 | 416.88 | Manual |  | 1 | 1 | 0 | 1 | 0 | Feb'26 | Completed
20 | AP-13A/0 - AP-14/0 | 480.27 | Manual |  | 1 | 1 | 0 | 1 | 0 | Feb'26 | Completed
21 | AP-14/0 - AP-15/0 | 223.82 | Manual | 400KV | 1 | 1 | 0 | 1 | 0 | Feb'26 | Completed
22 | AP-15/0 - AP-16/0 | 5019.34 | TSE |  | 13 | 13 | 0 | 12 | 1 | Feb'26 | Completed
23 | AP-16/0 - AP-17/0 | 392.69 | Manual |  | 1 | 1 | 0 | 1 | 0 | Feb'26
24 | AP-17/0 - AP-18/0 | 398.4 | Manual |  | 1 | 1 | 0 | 1 | 0 | Feb'26
25 | AP-18/0 - AP-19/0 | 3030.029 | TSE |  | 8 | 8 | 0 | 8 | 0 | Feb'26 | Completed
26 | AP-19/0 - AP-20/0 | 279.36 | Manual | Railway | 1 | 1 | 0 | 1 | 0 | Feb'26
27 | AP-20/0 - AP-21/0 | 2550.167 | TSE |  | 7 | 7 | 0 | 7 | 0 | mar'26 | WIP
28 | AP-21/0 - AP-22/0 | 2283.535 | TSE |  | 6 | 6 | 0 | 6 | 0 | mar'26
29 | AP-22/0 - AP-23/0 | 259.05 | Manual | 220KV | 1 | 1 | 0 | 1 | 0 | mar'26 | WIP
30 | AP-23/0 - AP-23A/0 | 440.46 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26 | Completed
31 | AP-23A/0 - AP-24/0 | 496.69 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26 | Completed
32 | AP-24/0 - AP-25/0 | 244.03 | Manual | 400KV | 1 | 1 | 0 | 1 | 0 | mar'26 | Completed
33 | AP-25/0 - AP-26/0 | 237.43 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26 | Completed
34 | AP-26/0 - AP-27/0 | 203.48 | Manual | 765KV | 1 | 1 | 0 | 1 | 0 | Feb'26
35 | AP-27/0 - AP-28/0 | 2548.275 | TSE |  | 7 | 7 | 0 | 7 | 0 | Feb'26 | Completed
36 | AP-28/0 - AP-29/0 | 211.21 | Manual | Exp-Way | 1 | 1 | 0 | 1 | 0 | Feb'26 | Completed
37 | AP-29/0 - AP-29A/0 | 2379.204 | TSE |  | 6 | 6 | 0 | 6 | 0 | Feb'26 | Completed
38 | AP-29A/0 - AP-30/0 | 2669.008 | TSE |  | 7 | 7 | 0 | 7 | 0 | Feb'26 | Completed
39 | AP-30/0 - AP-31/0 | 4124.232 | TSE |  | 11 | 11 | 0 | 11 | 0 | Feb'26 | Completed
40 | AP-31/0 - AP-32/0 | 4333.369 | TSE |  | 11 | 11 | 0 | 11 | 0 | Jan'26 | Completed
41 | AP-32/0 - AP-32A/0 | 3283.51 | TSE |  | 8 | 8 | 0 | 8 | 0 | Jan'26 | Completed
42 | AP-32A/0 - AP-33/0 | 840.439 | TSE |  | 2 | 2 | 0 | 2 | 0 | Jan'26 | Completed
43 | AP-33/0 - AP-34/0 | 4049.763 | TSE |  | 10 | 10 | 0 | 10 | 0 | Jan'26 | Completed
44 | AP-34/0 - AP-35/0 | 4898.588 | TSE |  | 13 | 13 | 0 | 13 | 0 | comp | Completed
45 | AP-35/0 - AP-36/0 | 4916.293 | TSE |  | 12 | 12 | 0 | 12 | 0 | mar'26 | Completed
46 | AP-36/0 - AP-36A/0 | 454 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26 | Completed
47 | AP-36A/0 - AP 36B/0 | 826.7 | TSE |  | 2 | 2 | 0 | 1 | 1 | mar'26
48 | AP-36B/0 N - AP-36C/0 N | 420.81 | Manual |  | 1 | 1 | 0 | 0 | 1 | mar'26
49 | AP-36C/0 N - AP-37/0 N | 469.33 | Manual |  | 1 | 1 | 0 | 0 | 1
50 | AP-37/0 N - AP-37A/0 | 2076.28 | TSE |  | 5 | 5 | 0 | 5 | 0 | comp
51 | AP-37A/0 - AP-38/0 | 2583.589 | TSE |  | 7 | 7 | 0 | 7 | 0 |  | Completed
52 | AP-38/0 - AP-39/0 | 4163.677 | TSE |  | 11 | 11 | 0 | 11 | 0 | comp | Completed
53 | AP-39/0 - AP-40/0 | 4716.811 | TSE |  | 12 | 12 | 0 | 12 | 0 | comp | Completed
54 | AP-40/0 - AP-40A/0 | 4665.918 | TSE |  | 12 | 12 | 0 | 12 | 0 | mar'26 | WIP
55 | AP-40A/0 - AP-41/0 | 410.61 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26
56 | AP-41/0 - AP-42/0 | 823.782 | TSE |  | 2 | 2 | 0 | 2 | 0 | mar'26
57 | AP-42/0 - AP-42/3 | 1258.998 | TSE |  | 3 | 3 | 0 | 3 | 0 | mar'26
58 | AP-42/3 - AP-43/0 | 424.891 | Manual |  | 1 | 1 | 0 | 1 | 0 | mar'26
59 | AP-43/0 - AP-43/5 | 1851.866 | TSE |  | 5 | 5 | 0 | 5 | 0 | mar'26
60 | AP-43/5-AP-44/0 | 1584.546 | TSE |  | 4 | 4 | 0 | 4 | 0 | Feb'26
61 | AP-44/0-AP45/0 | 2383.155 | TSE |  | 6 | 6 | 0 | 6 | 0 | Feb'26
62 | AP-45/0-AP-46/0 | 208.53 | Manual |  | 1 | 1 | 0 | 1 | 0 | Feb'26
|  | 117.8561 |  |  | 306 | 306 | 0 | 302 | 4
Sl no. | Type | Total Length (Km) |  |  |  | 313
1 | TSE | 109.2852
2 | Manual | 8.5709
Total=>> |  | 117.8561
Description | Stringing Type | Line length | TSE/Manual Completed | Line length | Balance Section | Balance(km)
TSE | 37 | 110.1701 | 21 | 70.083 | 16 | 40.0871
Manual | 25 | 7.6807 | 3 | 1.1763 | 22 | 6.5044
Stringing | 62 | 117.8508 | 24 | 71.2593 | 38 | 46.5915
Ved

## Erection
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Erection | [6 empty] | 14471.3488 | 1319.5343 |  | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Gang name | Weight | Revenue | Name of Supervisor | Remarks | JMC Status
1 | 1 | 29A/2 | DA+6 | 2024-09-12 | 2024-09-21 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
2 | 2 | 29/5 | DA+0 | 2024-09-21 | 2024-09-27 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Received
3 | 1 | 29/3 | DA+0 | 2024-09-28 | 2024-10-03 | Bhagwan construction | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Received
4 | 2 | 29/4 | DA+3 | 2024-10-03 | 2024-10-08 | Bhagwan construction | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Received
5 | 3 | 29A/6 | DA+9 | 2024-10-03 | 2024-10-14 | Bhagwan construction | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
6 | 4 | 30/1 | DA+0 | 2024-10-09 | 2024-10-17 | Bhagwan construction | 36.1598 | 3.3689 | Kartik Mahto | Completed | Received
7 | 5 | 29A/1 | DA+6 | 2024-10-14 | 2024-10-25 | Bhagwan construction | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
8 | 1 | 34/8 | DA+0 | 2024-11-12 | 2024-11-24 | Vasu dev singh-1 | 36.1598 | 3.3689 | Raju Mahto | Completed | Received
9 | 2 | 34/12 | DA+3 | 2024-11-14 | 2024-11-25 | Vasu dev singh-2 | 37.9311 | 3.534 | Mustak | Completed | Received
10 | 1 | 34/4 | DA+6 | 2024-11-25 | 2024-12-04 | Vasu dev singh-1 | 43.8044 | 4.0812 | Raju Mahto | Completed | Received
11 | 2 | 34/7 | DA+0 | 2024-11-26 | 2024-12-12 | Vasu dev singh-2 | 36.1598 | 3.3689 | Raju Mahto | Completed | Received
12 | 3 | 34/3 | DA+1.5 | 2024-12-05 | 2024-12-16 | Vasu dev singh-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed | Received
13 | 4 | 8/1 | DA-3 | 2024-12-07 | 2024-12-16 | Punam Devi-2 | 34.7898 | 3.2413 | Sanjay Kumar | Completed | Received
14 | 5 | 34/9 | DA+1.5 | 2024-12-13 | 2024-12-21 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed | Received
15 | 6 | 35/7 | DA+3 | 2024-12-13 | 2024-12-22 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
16 | 7 | 7A/5 | DA+3 | 2024-12-17 | 2024-12-24 | Punam Devi-2 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Received
17 | 8 | 36A/1 | DA+3 | 2024-12-13 | 2024-12-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
18 | 9 | 7/1 | DA-3 | 2024-12-15 | 2024-12-26 | Punam Devi-1 | 34.7898 | 3.2413 | Raju Mahto | Completed | Received
19 | 10 | 35/8 | DA+6 | 2024-12-23 | 2024-12-28 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Received
20 | 11 | 34/5 | DA+9 | 2024-12-17 | 2024-12-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
21 | 12 | 34/10 | DA-3 | 2024-12-22 | 2024-12-29 | Vasu dev singh-2 | 34.7898 | 3.2413 | Mustak & Abul | Completed | Received
22 | 13 | 7A/4 | DA+3 | 2024-12-24 | 2024-12-31 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Received
23 | 1 | 7/2 | DA+6 | 2024-12-27 | 2025-01-03 | Punam Devi-1 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Received
24 | 2 | 35/11 | DA+3 | 2024-12-24 | 2025-01-03 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
25 | 3 | 35/6 | DA+6 | 2024-12-29 | 2025-01-05 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Received
26 | 4 | 34/11 | DA+1.5 | 2024-12-30 | 2025-01-07 | Vasu dev singh-2 | 37.1383 | 3.4601 | Mustak & Abul | Completed | Received
27 | 5 | 7A/3 | DA+3 | 2025-01-01 | 2025-01-08 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Received
28 | 6 | 34/6 | DA+3 | 2024-12-30 | 2025-01-09 | Vasu dev singh-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Received
29 | 7 | 8/5 | DA+9 | 2025-01-04 | 2025-01-09 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Received
30 | 8 | 36A/2 | DA+9 | 2025-01-04 | 2025-01-11 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Received |  |  | Dismental
31 | 9 | 35/5 | DA+9 | 2025-01-06 | 2025-01-13 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Received
32 | 10 | 8/6 | DA+3 | 2025-01-10 | 2025-01-15 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
33 | 11 | 7A/2 | DA+3 | 2025-01-08 | 2025-01-16 | Punam Devi-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Received
34 | 12 | 35/1 | DA+6 | 2025-01-07 | 2025-01-19 | Vasu dev singh-2 | 43.8044 | 4.0812 | Mustak & Abul | Completed | Received
35 | 13 | 35/4 | DA+9 | 2025-01-14 | 2025-01-19 | Punam Devi-2 | 45.697 | 4.2575 | Kartik Mahto | Completed | Received
36 | 14 | 8/7 | DA+3 | 2025-01-16 | 2025-01-20 | Punam Devi-1 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
37 | 15 | 34/2 | DA+9 | 2025-01-10 | 2025-01-21 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
38 | 16 | 37/4 | DA+9 | 2025-01-11 | 2025-01-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Received
39 | 17 | 7A/1 | DA+1.5 | 2025-01-17 | 2025-01-22 | Punam Devi-2 | 37.1383 | 3.4601 | Raju Mahto | Completed | Received
40 | 18 | 35/9 | DA+1.5 | 2025-01-17 | 2025-01-24 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Received
41 | 19 | 8/8 | DA+9 | 2025-01-20 | 2025-01-25 | Punam Devi-1 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Received
42 | 20 | 34/1 | DA+9 | 2025-01-21 | 2025-01-29 | Vasu dev singh-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
43 | 21 | 38/3 | DA+3 | 2025-01-24 | 2025-01-29 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
44 | 22 | 8/9 | DA+3 | 2025-01-25 | 2025-01-30 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
45 | 23 | 37/5 | DA+3 | 2025-01-22 | 2025-01-30 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
46 | 24 | 7A/0 | DB1+6 | 2025-01-22 | 2025-01-31 | Punam Devi-2 | 65.0278 | 6.0585 | Raju Mahto | Completed | Received
47 | 25 | 34/0 | DB1+6 | 2025-01-17 | 2025-01-31 | Vasu dev singh-1 | 65.0278 | 6.0585 | Mustak & Abul | Completed | Received
48 | 1 | 8/10 | DA+0 | 2025-01-30 | 2025-02-03 | Punam Devi-4 | 36.1598 | 3.3689 | Gangadin sahoo | Completed | Received
49 | 2 | 38/6 | DA+6 | 2025-01-29 | 2025-02-04 | Punam Devi-1 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Received
50 | 3 | 37A/2 | DA+1.5 | 2025-01-29 | 2025-02-07 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Received
51 | 4 | 33/6 | DA+6 | 2025-01-29 | 2025-02-08 | Vasu dev singh-2 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
52 | 5 | 8/2 | DA+6 | 2025-02-03 | 2025-02-08 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Received
53 | 6 | 7/6 | DA-1.5 | 2025-01-31 | 2025-02-10 | Punam Devi-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Received
54 | 7 | 38/4 | DA+1.5 | 2025-02-05 | 2025-02-10 | Punam Devi-1 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Received
55 | 8 | 8/0 | DB1+0 | 2025-02-09 | 2025-02-14 | Punam Devi-4 | 55.4509 | 5.1663 | Gangadin sahoo | Completed | Received
56 | 9 | 38/5 | DA+3 | 2025-02-11 | 2025-02-15 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
57 | 10 | 37A/1 | DA+3 | 2025-02-08 | 2025-02-16 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
58 | 11 | 33/5 | DA+0 | 2025-01-31 | 2025-02-18 | Vasu dev singh-1 | 36.1598 | 3.3689 | Mustak & Abul | Completed | Received
59 | 12 | 38/9 | DA+0 | 2025-02-15 | 2025-02-18 | Punam Devi-1 | 36.1598 | 3.3689 | Kartik Mahto | Completed | Received
60 | 13 | 7/5 | DA+6 | 2025-02-11 | 2025-02-19 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Received
61 | 14 | 8/3 | DA+9 | 2025-02-14 | 2025-02-19 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Received
62 | 15 | 35/0 | DB2+0 | 2025-02-09 | 2025-02-23 | Vasu dev singh-2 | 59.5006 | 5.5436 | Manoj Kumar Gupta | Completed | Received
63 | 16 | 38/10 | DA+3 | 2025-02-18 | 2025-02-24 | Punam Devi-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
64 | 17 | 8/4 | DA+6 | 2025-02-20 | 2025-02-24 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Received
65 | 18 | 37A/3 | DA+3 | 2025-02-16 | 2025-02-25 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
66 | 19 | 7/4 | DA+6 | 2025-02-20 | 2025-02-27 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Received
67 | 20 | 9/1 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-4 | 37.9311 | 3.534 | Raju Mahto | Completed | Received
68 | 21 | 37A/5 | DA+3 | 2025-02-24 | 2025-02-28 | Punam Devi-1 | 37.9311 | 3.534 | Prabhakar | Completed | Received
69 | 1 | 33/8 | DA+3 | 2025-02-18 | 2025-03-04 | Vasu dev singh-1 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
70 | 2 | 9/3 | DA+0 | 2025-03-01 | 2025-03-04 | Punam Devi-4 | 36.1598 | 3.3689 | Raju Mahto | Completed | Received
71 | 3 | 38/1 | DA+0 | 2025-03-01 | 2025-03-06 | Punam Devi-1 | 36.1598 | 3.3689 | Prabhakar | Completed | Received
72 | 4 | 37A/4 | DA+9 | 2025-02-25 | 2025-03-06 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Received
73 | 5 | 37A/6 | DA+3 | 2025-02-24 | 2025-03-08 | Vasu dev singh-2 | 37.9311 | 3.534 | Prabhakar | Completed | Received
74 | 6 | 9/4 | DA+6 | 2025-03-05 | 2025-03-09 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Received
75 | 7 | 37A/0 | DB1+0 | 2025-02-28 | 2025-03-11 | Punam Devi-2 | 55.4509 | 5.1663 | Kartik Mahto | Completed | Received
76 | 8 | 38/2 | DA+0 | 2025-03-07 | 2025-03-11 | Punam Devi-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Received
77 | 9 | 39/7 | DA+3 | 2025-03-07 | 2025-03-13 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
78 | 10 | 9/2 | DA+3 | 2025-03-10 | 2025-03-13 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
79 | 11 | 15/2 | DA+3 | 2025-03-14 | 2025-03-18 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
80 | 12 | 38/7 | DA+9 | 2025-03-12 | 2025-03-18 | Punam Devi-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
81 | 13 | 39/2 | DA+3 | 2025-03-12 | 2025-03-19 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
82 | 14 | 39/5 | DA+1.5 | 2025-03-14 | 2025-03-20 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Received
83 | 15 | 39/0 | DB2+0 | 2025-03-09 | 2025-03-21 | Vasu dev singh-2 | 59.5006 | 5.5436 | Raju Mahto | Completed | Received
84 | 16 | 15/3 | DA+3 | 2025-03-19 | 2025-03-22 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
85 | 17 | 38/8 | DA+1.5 | 2025-03-19 | 2025-03-24 | Punam Devi-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed | Received
86 | 18 | 39/3 | DA+1.5 | 2025-03-20 | 2025-03-25 | Punam Devi-2 | 37.1383 | 3.4601 | Kartik Mahto | Completed | Received
87 | 19 | 39/4 | DA+3 | 2025-03-21 | 2025-03-27 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
88 | 20 | 15/4 | DA+6 | 2025-03-23 | 2025-03-27 | Punam Devi-4 | 43.8044 | 4.0812 | Gangadin sahoo | Completed | Received
89 | 21 | 39/1 | DA-1.5 | 2025-03-22 | 2025-03-29 | Vasu dev singh-2 | 35.6018 | 3.317 | Raju Mahto | Completed | Received
90 | 22 | 39/9 | DA+6 | 2025-03-25 | 2025-03-30 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
91 | 23 | 40/2 | DA+6 | 2025-03-26 | 2025-03-31 | Punam Devi-2 | 43.8044 | 4.0812 | Kartik Mahto | Completed | Received
92 | 24 | 15/5 | DA+3 | 2025-03-26 | 2025-03-31 | Punam Devi-4 | 37.9311 | 3.534 | Gangadin sahoo | Completed | Received
93 | 25 | 39/8 | DA+1.5 | 2024-03-26 | 2025-03-31 | Punam Devi-3 | 37.1383 | 3.4601 | Haridas | Completed | Received
94 | 1 | 39/10 | DA+3 | 2025-03-31 | 2025-04-05 | Punam Devi-3 | 37.9311 | 3.534 | Haridas | Completed | Received
95 | 2 | 15/6 | DA+9 | 2025-03-31 | 2025-04-06 | Punam Devi-4 | 45.697 | 4.2575 | Gangadin sahoo | Completed | Received
96 | 3 | 39/11 | DA+6 | 2025-03-30 | 2025-04-09 | Punam Devi-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
97 | 4 | 40/3 | DA+3 | 2025-03-31 | 2025-04-09 | Punam Devi-2 | 37.9311 | 3.534 | Kartik Mahto | Completed | Received
98 | 5 | 38/0 | DB1+3 | 2025-03-29 | 2025-04-11 | Vasu dev singh-2 | 57.9632 | 5.4003 | Manoj Gupta | Completed | Received
99 | 6 | 40/5 | DA+9 | 2025-04-05 | 2025-04-14 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Received
100 | 7 | 40/4 | DA+6 | 2025-04-09 | 2025-04-18 | Punam Devi-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Received
101 | 8 | 39/6 | DA+1.5 | 2025-04-09 | 2025-04-18 | Punam Devi-1 | 37.1383 | 3.4601 | Haridas | Completed | Received
102 | 9 | 40/6 | DA+9 | 2025-04-14 | 2025-04-22 | Punam Devi-3 | 45.697 | 4.2575 | Haridas | Completed | Received
103 | 10 | 36A/0 | DB1+9 | 2025-04-18 | 2025-04-30 | Punam Devi-2 | 66.7809 | 6.2219 | Raju Mahto | Completed | Received
104 | 11 | 40/0 | DB1+6 | 2025-04-18 | 2025-04-30 | Punam Devi-1 | 65.0278 | 6.0585 | Haridas | Completed | Received
105 | 1 | 32/6 | DA+9 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed | Received
106 | 2 | 32/1 | DA+6 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed | Received
107 | 3 | 7/3 | DA+9 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 4.2575 | Sanjay Kumar | Completed | Received
108 | 4 | 32/5 | DA+9 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.2575 | Manoj Gupta | Completed | Received
109 | 5 | 6/1 | DA+9 | 2025-07-16 | 2025-07-26 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed | Received
110 | 6 | 32/2 | DA+9 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed | Received
111 | 7 | 7/0 | DB2+0 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.5436 | Sanjay Kumar | Completed | Received
112 | 8 | 32/7 | DA+3 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 3.534 | Manoj Gupta | Completed | Received
113 | 1 | 31/0 | DB1+0 | 2025-07-16 | 2025-08-01 | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | Completed | Received
114 | 2 | 42/0 | DB2+0 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 5.5436 | Manirul | Completed | Received
115 | 3 | 8/11 | DA+9 | 2025-07-15 | 2025-08-03 | Jwala Singh-1 | 45.697 | 4.2575 | Rudra Prasad | Completed | Received
116 | 4 | 30/10 | DA+3 | 2025-07-18 | 2025-08-03 | SK.Samiul -2 | 37.9311 | 3.534 | Haridas | Completed | Received
117 | 5 | 32/3 | DA+6 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.0812 | Suraj Kumar | Completed | Received
118 | 6 | 42/1 | DA+3 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 3.534 | Manirul | Completed | Received
119 | 7 | 40/1 | DA+9 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 4.2575 | Susheel Kumar | Completed | Received
120 | 8 | 6/2 | DA+6 | 2025-08-04 | 2025-08-08 | Jwala Singh-1 | 43.8044 | 4.0812 | Sanjay Kumar | Completed | Received
121 | 9 | 32A/0 | DB1+9 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 6.2219 | Manoj Kumar Gupta | Completed | Received
122 | 10 | 35/2 | DA+6 | 2025-08-01 | 2025-08-09 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed | Received
123 | 11 | 6/12 | DA+1.5 | 2025-08-01 | 2025-08-09 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed | Received
124 | 12 | 31/1 | DA+3 | 2025-08-02 | 2025-08-10 | SK Samiul -1 | 37.9311 | 3.534 | Haridas | Completed | Received
125 | 13 | 31/2 | DA+1.5 | 2025-08-04 | 2025-08-11 | SK.Samiul -2 | 37.1383 | 3.4601 | Haridas | Completed | Received
126 | 14 | 42/2 | DA+9 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 4.2575 | Manirul | Completed | Received
127 | 15 | 40/9 | DA+9 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 4.2575 | Manirul | Completed | Received
128 | 16 | 6/5 | DA+9 | 2025-08-02 | 2025-08-13 | Pritam Enterprises-2 | 45.697 | 4.2575 | Sanjay Kumar | Completed | Received
129 | 17 | 32/4 | DA+9 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed | Received
130 | 18 | 6/3 | DA+3 | 2025-08-08 | 2025-08-14 | Jwala Singh-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Received
131 | 19 | 8A/0 | DB1+12 | 2025-08-07 | 2025-08-14 | Punam Kumari-2 | 70.7883 | 6.5952 | Sanjay Kumar | Completed | Received
132 | 20 | 33/2 | DA+9 | 2025-08-09 | 2025-08-17 | Punam Kumari-1 | 45.697 | 4.2575 | Manoj Kumar Gupta | Completed | Received
133 | 21 | 6/10 | DA+1.5 | 2025-08-09 | 2025-08-18 | Pritam Enterprises-1 | 37.1383 | 3.4601 | Sanjay Kumar | Completed | Received
134 | 22 | 9/5 | DA+3 | 2025-08-15 | 2025-08-19 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed | Received
135 | 23 | 42A/0 | DB1+9 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 6.2219 | Manirul | Completed | Received |  |  | Rename 42/3
136 | 24 | 5/6 | DA+3 | 2025-08-08 | 2025-08-20 | Pritam Enterprises-4 | 37.9311 | 3.534 | Deshraj | Completed | Received
137 | 25 | 40/7 | DA+3 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 3.534 | Susheel Kumar | Completed | Received
138 | 26 | 1/0 | DD60+0 | 2025-08-07 | 2025-08-21 | Pritam Enterprises-3 | 83.1335 | 7.7454 | Nishit Mondal | Completed | Received
139 | 27 | 6/0 | DB1+9 | 2025-08-13 | 2025-08-21 | Jwala Singh-2 | 66.7809 | 6.2219 | Rudra Prasad | Completed | Received
140 | 28 | 6/6 | DA-3 | 2025-08-14 | 2025-08-21 | Pritam Enterprises-2 | 34.7898 | 3.2413 | Indrajeet Patel | Completed | Received
141 | 29 | 6/4 | DA+9 | 2025-08-15 | 2025-08-21 | Jwala Singh-1 | 45.697 | 4.2575 |  | Completed | Received
142 | 30 | 30/9 | DA-3 | 2025-08-12 | 2025-08-21 | SK.Samiul -2 | 34.7898 | 3.2413 | Haridas | Completed | Received
143 | 31 | 31/3 | DA+3 | 2025-08-12 | 2025-08-22 | SK Samiul -1 | 37.9311 | 3.534 | Khooblal Mahto | Completed | Received
144 | 32 | 33/9 | DA+1.5 | 2025-08-18 | 2025-08-22 | Punam Kumari-1 | 37.1383 | 3.4601 | Manoj Kumar Gupta | Completed | Received
145 | 33 | 6/11 | DA-1.5 | 2025-08-19 | 2025-08-25 | Pritam Enterprises-1 | 35.6018 | 3.317 | Sanjay Kumar | Completed | Received
146 | 34 | 9/6 | DA+3 | 2025-08-20 | 2025-08-25 | Punam Kumari-2 | 37.9311 | 3.534 | Narayan Mahto | Completed | Received
147 | 35 | 43/2 | DA+6 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 4.0812 | Manirul | Completed | Received
148 | 36 | 31/10 | DA+4.5 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.999 | Suraj Kumar | Completed | Received
149 | 37 | 2A/1 | DA+0 | 2025-08-21 | 2025-08-27 | Pritam Enterprises-3 | 36.1598 | 3.3689 | Nishit Mondal | Completed | Received
150 | 38 | 4A/4 | DA+6 | 2025-08-18 | 2025-08-28 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed | Received
151 | 39 | 5/5 | DA+6 | 2025-08-20 | 2025-08-28 | Pritam Enterprises-4 | 43.8044 | 4.0812 | Deshraj | Completed | Received
152 | 40 | 6/7 | DA+1.5 | 2025-08-22 | 2025-08-28 | Pritam Enterprises-2 | 37.1383 | 3.4601 | Indrajeet Patel | Completed | Received
153 | 41 | 5/10 | DA+9 | 2025-08-22 | 2025-08-28 | Jwala Singh-1 | 45.697 | 4.2575 | Aman Singh | Completed | Received
154 | 42 | 9/7 | DA+9 | 2025-08-23 | 2025-08-29 | Punam Kumari-2 | 45.697 | 4.2575 | Narayan Mahto | Completed | Received
155 | 43 | 33/7 | DA+6 | 2025-08-23 | 2025-08-30 | Punam Kumari-1 | 43.8044 | 4.0812 | Manoj Kumar Gupta | Completed | Received
156 | 44 | 31/4 | DA-1.5 | 2025-08-22 | 2025-08-31 | SK.Samiul -2 | 35.6018 | 3.317 | Haridas | Completed | Received | Dwg no | BOM no
157 | 1 | 5A/0 | DB1+12 | 2025-08-22 | 2025-09-01 | Jwala Singh-2 | 70.7883 | 6.5952 | Rudra Prasad | Completed | Received | O22017-T-TL-0D-GA-0208 | TA413/DB1/BM-10
158 | 2 | 32A/1 | DA+6 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 4.0812 | Raju Mahto | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
159 | 3 | 6/9 | DA+6 | 2025-08-23 | 2025-09-02 | Pritam Enterprises-2 | 43.8044 | 4.0812 | Sanjay Kumar | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
160 | 4 | 2A/2 | DA+3 | 2025-08-28 | 2025-09-02 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
161 | 5 | 43/3 | DA-1.5 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.317 | Manirul | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
162 | 6 | 31/5 | DA+6 | 2025-08-23 | 2025-09-03 | SK Samiul -1 | 43.8044 | 4.0812 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
163 | 7 | 31/9 | DA+1.5 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.4601 | Suraj Kumar | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
164 | 8 | 44/1 | DA+3 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
165 | 9 | 33/3 | DA+3 | 2025-08-31 | 2025-09-04 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
166 | 10 | 5/9 | DA+6 | 2025-08-29 | 2025-09-05 | Jwala Singh-1 | 43.8044 | 4.0812 | Indrajeet Patel | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
167 | 11 | 6/8 | DA+3 | 2025-08-29 | 2025-09-06 | Pritam Enterprises-2 | 37.9311 | 3.534 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
168 | 12 | 9/0 | DB1+12 | 2025-08-30 | 2025-09-06 | Punam Kumari-2 | 70.7883 | 6.5952 | Narayan Mahto | Completed | Received | O22017-T-TL-0D-GA-0208 | TA413/DB1/BM-10
169 | 13 | 4A/3 | DA+9 | 2025-08-29 | 2025-09-06 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
170 | 14 | 43/4 | DA+0 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 3.3689 | Manirul | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
171 | 15 | 5/4 | DA-1.5 | 2025-08-29 | 2025-09-08 | Pritam Enterprises-4 | 35.6018 | 3.317 | Deshraj | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
172 | 16 | 2A/3 | DA+3 | 2025-09-03 | 2025-09-08 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
173 | 17 | 4A/5 | DA+9 | 2025-08-25 | 2025-09-08 | Govind Mahto-2 | 45.697 | 4.2575 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
174 | 18 | 30/6 | DA+6 | 2025-08-29 | 2025-09-08 | Punam Kumari-3 | 43.8044 | 4.0812 | kartik | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
175 | 19 | 5/7 | DA+9 | 2025-09-02 | 2025-09-09 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
176 | 20 | 44/2 | DA+3 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 3.534 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
177 | 21 | 33/4 | DA+3 | 2025-09-05 | 2025-09-09 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Gupta | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
178 | 22 | 33/1 | DA+9 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 4.2575 | Bhupendra choudhary | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
179 | 23 | 3A/1 | DA+3 | 2025-09-03 | 2025-09-11 | Pritam Enterprises-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
180 | 24 | 43/6 | DA+3 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 3.534 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
181 | 25 | 4/1 | DA+6 | 2025-09-06 | 2025-09-12 | Jwala Singh-1 | 43.8044 | 4.0812 | Kamal Ravidas | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07 | REname 4/5
182 | 26 | 30/7 | DA-3 | 2025-09-09 | 2025-09-13 | Punam Kumari-3 | 34.7898 | 3.2413 | Kartik | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
183 | 27 | 32/0 | DB2+0 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.5436 | Suraj Kumar | Completed | Received | O20017-T- TL-0D-GA-020 | TA413/DB2/BM-04
184 | 28 | 30/4 | DA+9 | 2025-09-09 | 2025-09-15 | Punam Kumari-4 | 45.697 | 4.2575 | Kartik | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
185 | 29 | 18/0 | DB2+6 | 2025-09-07 | 2025-09-15 | Punam Kumari-2 | 69.376 | 6.4637 | Kamal Ravidas | Completed | Received | O20017-T-TL-0D-GA-0206 | TA413/DB2/BM-06
186 | 30 | 2A/4 | DA+3 | 2025-09-09 | 2025-09-15 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
187 | 31 | 5/8 | DA+6 | 2025-09-10 | 2025-09-15 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
188 | 32 | 44/3 | DA+3 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 3.534 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
189 | 33 | 3A/5 | DA+3 | 2025-09-07 | 2025-09-15 | Pritam Enterprises-2 | 37.9311 | 3.534 | Akabar Ali | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
190 | 34 | 4A/2 | DA+6 | 2025-09-07 | 2025-09-16 | Govind Mahto-1 | 43.8044 | 4.0812 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
191 | 35 | 31/7 | DA+0 | 2025-09-10 | 2025-09-16 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Gupta | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
192 | 36 | 31/6 | DA+9 | 2025-09-04 | 2025-09-18 | SK Samiul -1 | 45.697 | 4.2575 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
193 | 37 | 4A/6 | DA+9 | 2025-09-09 | 2025-09-18 | Govind Mahto-2 | 45.697 | 4.2575 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
194 | 38 | 43/8 | DA+9 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 4.2575 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
195 | 39 | 44/4 | DA+0 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
196 | 40 | 3A/2 | DA+3 | 2025-09-12 | 2025-09-19 | Pritam Enterprises-1 | 37.9311 | 3.534 | Sanjay Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
197 | 41 | 40A/0 | DB1+9 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 6.2219 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
198 | 42 | 33/0 | DB1+9 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 6.2219 | Raju Mahto | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
199 | 43 | 18/1 | DA+3 | 2025-09-16 | 2025-09-20 | Punam Kumari-2 | 37.9311 | 3.534 | Kamal Ravidas | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
200 | 44 | 31/8 | DA+0 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 3.3689 | Suraj Kumar | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
201 | 45 | 30/8 | DA+3 | 2025-09-14 | 2025-09-22 | Punam Kumari-3 | 37.9311 | 3.534 | Abrar Ali | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
202 | 46 | 2A/5 | DA+3 | 2025-09-16 | 2025-09-23 | Pritam Enterprises-3 | 37.9311 | 3.534 | Nishit Mondal | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
203 | 47 | 44/5 | DA+0 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
204 | 48 | 3A/6 | DA+0 | 2025-09-16 | 2025-09-24 | Pritam Enterprises-2 | 36.1598 | 3.3689 | Akabar Ali | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
205 | 49 | 4A/0 | DB1+3 | 2025-09-13 | 2025-09-24 | Jwala Singh-1 | 57.9632 | 5.4003 | Kamal Ravidas | Completed | Received | O22017-T-TL-0D-GA-0205 | TA413/DB1/BM-05
206 | 50 | 30/0 | DB1+0 | 2025-09-11 | 2025-09-25 | Punam Kumari-4 | 55.4509 | 5.1663 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0203 | TA413/DB1/BM-04
207 | 51 | 5/1 | DA+6 | 2025-09-13 | 2025-09-25 | Jwala Singh-2 | 43.8044 | 4.0812 | Rudra Prasad | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
208 | 52 | 4A/1 | DA+6 | 2025-09-18 | 2025-09-25 | Govind Mahto-1 | 43.8044 | 4.0812 | Rahul Ravidas | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
209 | 53 | 20/1 | DA-3 | 2025-09-19 | 2025-09-25 | Punam Kumari-1 | 34.7898 | 3.2413 | Manoj Kumar Gupta | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
210 | 54 | 18/2 | DA+1.5 | 2025-09-21 | 2025-09-25 | Punam Kumari-2 | 37.1383 | 3.4601 | Narayan Mahto | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
211 | 55 | 12/0 | DB1+9 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 6.2219 | Bhupendra choudhary | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
212 | 56 | 3A/3 | DA+0 | 2025-09-20 | 2025-09-27 | Pritam Enterprises-1 | 36.1598 | 3.3689 | Sanjay Kumar | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
213 | 57 | 43/7 | DA+0 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 3.3689 | Khooblal Mahto | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
214 | 58 | 44/0 | DB1+6 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.0585 | Manoj Kumar Choudhary | Completed | Received | O22017-T-TL-0D-GA-0206 | TA413/DB1/BM-06
215 | 59 | 40/11 | DA+9 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 4.2575 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
216 | 60 | 5/0 | DB1+6 | 2025-09-19 | 2025-09-30 | Govind Mahto-2 | 65.0278 | 6.0585 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0206 | TA413/DB1/BM-06
217 | 61 | 20/2 | DA-3 | 2025-09-26 | 2025-09-30 | Punam Kumari-1 | 34.7898 | 3.2413 | Rahul Ravidas | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
218 | 62 | 18/3 | DA+6 | 2025-09-26 | 2025-09-30 | Punam Kumari-2 | 43.8044 | 4.0812 | Najirul | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
219 | 63 | 2A/6 | DA+6 | 2025-09-24 | 2025-09-30 | Pritam Enterprises-3 | 43.8044 | 4.0812 | Narayan Mahto | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
220 | 64 | 5/3 | DA+9 | 2025-09-09 | 2025-09-30 | Pritam Enterprises-4 | 45.697 | 4.2575 | Sanjay Kumar | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
221 | 65 | 5/2 | DA+9 | 2025-09-26 | 2025-09-30 | Jwala Singh-2 | 45.697 | 4.2575 | Rudra Prasad | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
222 | 4 | 30/2 | DA+9 | 2025-09-24 | 2025-10-04 | SK Samiul -1 | 45.697 | 4.2575 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
223 | 5 | 41/1 | DA+9 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.2575 | Suraj Kumar | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
224 | 6 | 29A/5 | DA+6 | 2025-09-26 | 2025-10-04 | Punam Kumari-4 | 43.8044 | 4.0812 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
225 | 7 | 15/8 | DA+1.5 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 3.4601 | Bhupendra choudhary | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
226 | 8 | 18/4 | DA-3 | 2025-10-01 | 2025-10-06 | Punam Kumari-2 | 34.7898 | 3.2413 | Nabirul Islam | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
227 | 9 | 3B/2 | DA+9 | 2025-09-26 | 2025-10-07 | Govind Mahto-1 | 45.697 | 4.2575 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
228 | 10 | 45/0 | DB1+9 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 6.2219 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
229 | 11 | 40/10 | DA+3 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.534 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
230 | 12 | 29A/4 | DA+3 | 2025-10-05 | 2025-10-10 | Punam Kumari-4 | 37.9311 | 3.534 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
231 | 13 | 3A/4 | DA+0 | 2025-10-01 | 2025-10-10 | Pritam Enterprises-3 | 36.1598 | 3.3689 | Abhiya | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
232 | 14 | 18/5 | DA+0 | 2025-10-07 | 2025-10-10 | Punam Kumari-2 | 36.1598 | 3.3689 | Najirul | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
233 | 15 | 3B/0 | DB1+9 | 2025-09-25 | 2025-10-12 | Pritam Enterprises-2 | 66.7809 | 6.2219 | Akabar Ali | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
234 | 16 | 4/0 | DB2+9 | 2025-09-25 | 2025-10-12 | Jwala Singh-1 | 72.1555 | 6.7226 | Kamal Ravidas | Completed | Received | O20017-T-TL-0D-GA-0207 | TA413/DB2/BM-07
235 | 17 | 46/0 | DB1+12 | 2025-09-30 | 2025-10-12 | Fouzi Ratto | 70.7883 | 6.5952 | Manoj Kumar Choudhary | Completed | Received | O22017-T-TL-0D-GA-0208 | TA413/DB1/BM-10
236 | 18 | 29/1 | DA+6 | 2025-10-07 | 2025-10-12 | Jwala Singh-2 | 43.8044 | 4.0812 | Raju Mahto | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
237 | 19 | 18/6 | DA+9 | 2025-10-11 | 2025-10-15 | Punam Kumari-2 | 45.697 | 4.2575 | Najirul | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
238 | 20 | 20/0 | DD60+3 | 2025-10-01 | 2025-10-15 | Punam Kumari-1 | 87.0213 | 8.1076 | Rahul Ravidas | Completed | Received | O20017-T-TL-0D-GA-0405 | TA413/DD2/BM-05
239 | 21 | 3B/1 | DA+3 | 2025-10-09 | 2025-10-16 | Govind Mahto-1 | 37.9311 | 3.534 | Rundra | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
240 | 22 | 10/0 | DB1+6 | 2025-10-02 | 2025-10-17 | Pritam Enterprises-1 | 65.0278 | 6.0585 | Sanjay Kumar | Completed | Received | O22017-T-TL-0D-GA-0206 | TA413/DB1/BM-06
241 | 23 | 40/8 | DA-1.5 | 2025-10-10 | 2025-10-19 | Kartik Mahto | 35.6018 | 3.317 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
242 | 24 | 41/0 | DB1+9 | 2025-10-08 | 2025-10-22 | Amar Kumar Singh | 66.7809 | 6.2219 | Suraj Kumar | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
243 | 25 | 29A/0 | DB1+0 | 2025-10-06 | 2025-10-22 | SK Samiul -1 | 55.4509 | 5.1663 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0203 | TA413/DB1/BM-04
244 | 26 | 30/3 | DA+3 | 2025-10-12 | 2025-10-22 | Jwala Singh-2 | 37.9311 | 3.534 | Raju Mahto | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
245 | 27 | 18/7 | DA+1.5 | 2025-10-16 | 2025-10-22 | Punam Kumari-2 | 37.1383 | 3.4601 | Najirul | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
246 | 28 | 20/6 | DA-3 | 2025-10-17 | 2025-10-23 | Govind Mahto-1 | 34.7898 | 3.2413 | Rundra | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
247 | 29 | 29/0 | DC1+0 | 2025-10-08 | 2025-10-25 | Pritam Enterprises-4 | 62.4437 | 5.8178 | Raju Mahto | Completed | Received | O22017-T-TL-0D-GA-0303 | TA413/DC1/BM-04
248 | 30 | 3A/0 | DD45+3 | 2025-10-11 | 2025-10-26 | Pritam Enterprises-3 | 77.0769 | 7.1811 | Abhiya | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DD1/BM-05
249 | 31 | 23/0 | DB2+9 | 2025-10-12 | 2025-10-27 | Bhairaw Mahto | 72.1555 | 6.7226 | Dhalchand | Completed | Received | O20017-T-TL-0D-GA-0207 | TA413/DB2/BM-07
250 | 32 | 19/0 | DD60+3 | 2025-10-16 | 2025-10-28 | Punam Kumari-1 | 87.0213 | 8.1076 | Manoj Kumar Choudhary | Completed | Received | O20017-T-TL-0D-GA-0405 | TA413/DD2/BM-05
251 | 33 | 9/11 | DA+3 | 2025-10-18 | 2025-10-28 | Pritam Enterprises-1 | 37.9311 | 3.534 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
252 | 34 | 21/0 | DB1+0 | 2025-10-20 | 2025-10-29 | Kartik Mahto | 55.4509 | 5.1663 | Akbar Ali | Completed | Received | O22017-T-TL-0D-GA-0203 | TA413/DB1/BM-04
253 | 35 | 21/1 | DA+0 | 2025-10-24 | 2025-10-29 | Govind Mahto-1 | 36.1598 | 3.3689 | Rundra | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
254 | 36 | 15/0 | DD60+25 | 2025-10-05 | 2025-10-30 | Govind Mahto-2 | 137.0461 | 12.7684 | Aman Singh | Completed | Received | O20017-T-TL-0D-GA-0413 | TA413/DD2/BM-10
255 | 37 | 27/5 | DA-1.5 | 2025-10-23 | 2025-10-30 | Jwala Singh-2 | 35.6018 | 3.317 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
256 | 38 | 10/1 | DA+3 | 2025-10-12 | 2025-10-31 | Jwala Singh-1 | 37.9311 | 3.534 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
257 | 39 | 20/5 | DA+0 | 2025-10-28 | 2025-10-31 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Choudhary | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
258 | 1 | 20/3 | DA+1.5 | 2025-10-30 | 2025-11-05 | Govind Mahto-1 | 37.1383 | 3.4601 | Rundra | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
259 | 2 | 9/10 | DA+3 | 2025-10-31 | 2025-11-05 | Govind Mahto-2 | 37.9311 | 3.534 | Aman Singh | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
260 | 3 | 20/4 | DA+3 | 2025-11-01 | 2025-11-06 | Punam Kumari-1 | 37.9311 | 3.534 | Manoj Kumar Choudhary | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
261 | 4 | 26/0 | DD60+35 | 2025-10-10 | 2025-11-07 | Ved Prakash | 173.5609 | 16.1704 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0503 | TA413/DD2/BM-12
262 | 5 | 3B/3 | DA+6 | 2025-10-27 | 2025-11-08 | Pritam Enterprises-3 | 43.8044 | 4.0812 | Abhiya | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
263 | 6 | 10/2 | DA+3 | 2025-11-01 | 2025-11-09 | Jwala Singh-1 | 37.9311 | 3.534 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
264 | 7 | 9/9 | DA+0 | 2025-11-06 | 2025-11-12 | Govind Mahto-2 | 36.1598 | 3.3689 | Narayan Mahto | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
265 | 8 | 28/0 | DC2-3 | 2025-10-31 | 2025-11-12 | Jwala Singh-2 | 64.8843 | 6.0452 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0308 | TA413/DC2/BM-10
266 | 9 | 21/5 | DA+0 | 2025-11-07 | 2025-11-12 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Choudhary | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
267 | 10 | 21/2 | DA+6 | 2025-11-06 | 2025-11-13 | Govind Mahto-1 | 43.8044 | 4.0812 | Rundra | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
268 | 11 | 22/0 | DC2+15 | 2025-10-28 | 2025-11-13 | Bhairaw Mahto | 96.8799 | 9.0261 | Dhalchand | Completed | Received | O20017-T-TL-OD-GA-0312 | TA413/DC2/BM-08
269 | 12 | 15/7 | DA+0 | 2025-11-10 | 2025-11-15 | Jwala Singh-1 | 36.1598 | 3.3689 | Akil Hussain | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
270 | 13 | 27/4 | DA+1.5 | 2025-10-27 | 2025-11-15 | Pritam Enterprises-4 | 37.1383 | 3.4601 | Nabirul Islam | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
271 | 14 | 21/4 | DA+0 | 2025-11-13 | 2025-11-20 | Punam Kumari-1 | 36.1598 | 3.3689 | Manoj Kumar Choudhary | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
272 | 15 | 27/6 | DA-3 | 2025-11-13 | 2025-11-20 | Jwala Singh-2 | 34.7898 | 3.2413 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
273 | 16 | 15/10 | DA-1.5 | 2025-11-16 | 2025-11-21 | Jwala Singh-1 | 35.6018 | 3.317 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
274 | 17 | 11/0 | DD45+0 | 2025-11-13 | 2025-11-26 | Govind Mahto-2 | 73.2445 | 6.8241 | Narayan Mahto | Completed | Received | O22017-T-TL-0D-GA-0403 | TA413/DD1/BM-04
275 | 18 | 24/0 | DD60+18 | 2025-11-13 | 2025-11-27 | Fouzi Ratto | 124.95 | 11.6414 | Khooblal Mahto | Completed | Received | O20017-T-TL-0D-GA-0408 | TA413/DD2/BM-09
276 | 19 | 27/2 | DA-1.5 | 2025-11-21 | 2025-11-27 | Jwala Singh-2 | 35.6018 | 3.317 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
277 | 20 | 23A/0 | DB1+9 | 2025-11-14 | 2025-11-27 | Govind Mahto-1 | 66.7809 | 6.2219 | Rahul Ravidas | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
278 | 21 | 21/3 | DA+6 | 2025-11-21 | 2025-11-27 | Punam Kumari-1 | 43.8044 | 4.0812 | Manoj Kumar Choudhary | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
279 | 22 | 15/9 | DA+0 | 2025-11-22 | 2025-11-28 | Jwala Singh-1 | 36.1598 | 3.3689 | Akil Hussain | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
280 | 23 | 27/0 | DD60+35 | 2025-11-08 | 2025-11-29 | Ved Prakash | 173.5609 | 16.1704 | Susheel Kumar | Completed | Received | O22017-T-TL-0D-GA-0503 | TA413/DD2/BM-12
281 | 24 | 25/0 | DD60+18 | 2025-11-12 | 2025-11-29 | Pritam Enterprises-3 | 124.95 | 11.6414 | Haridas | Completed | Received | O20017-T-TL-0D-GA-0408 | TA413/DD2/BM-09
282 | 1 | 15/1 | DA+6 | 2025-11-27 | 2025-12-03 | Govind Mahto-2 | 43.8044 | 4.0812 | Narayan Mahto | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
283 | 2 | 27/3 | DA+1.5 | 2025-11-28 | 2025-12-05 | Jwala Singh-2 | 37.1383 | 3.4601 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0110 | TA413/DA/BM-08
284 | 3 | 15/12 | DA+6 | 2025-11-29 | 2025-12-06 | Jwala Singh-1 | 43.8044 | 4.0812 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
285 | 4 | 9/8 | DA+0 | 2025-12-04 | 2025-12-12 | Govind Mahto-2 | 36.1598 | 3.3689 | Narayan Mahto | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
286 | 5 | 27/1 | DA+9 | 2025-12-05 | 2025-12-14 | Jwala Singh-2 | 45.697 | 4.2575 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0107 | TA413/DA/BM-06
287 | 6 | 14/0 | DD60+18 | 2025-11-30 | 2025-12-17 | Ved Prakash | 124.95 | 11.6414 | Rudra Prasad | Completed | Received | O20017-T-TL-0D-GA-0408 | TA413/DD2/BM-09
288 | 7 | 29/2 | DA+0 | 2025-12-12 | 2025-12-20 | Jwala Singh-1 | 36.1598 | 3.3689 | Manoj Gupta | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
289 | 8 | 43A/0 | DCT+0 | 2025-11-30 | 2025-12-21 | Pritam Enterprises-2 | 82.998 | 7.7328 | Haridas | Completed | Received | O20017-T-TL-0D-GA-0503 | TA413/DCT/BM-04 | Rename 43/5
290 | 9 | 15/11 | DA+0 | 2025-12-07 | 2025-12-21 | Govind Mahto-1 | 36.1598 | 3.3689 | Abhay Ojha | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
291 | 10 | 17/0 | DC1+3 | 2025-11-16 | 2025-12-23 | Pritam Enterprises-1 | 65.8725 | 6.1372 | Akil Hussain | Completed | Received | O22017-T-TL-0D-GA-0305 | TA413/DC1/BM-05
292 | 11 | 30/5 | DA+0 | 2025-12-21 | 2025-12-26 | Jwala Singh-1 | 36.1598 | 3.3689 | Manoj Gupta | Completed | Received | 022017-T-TL-0D-GA-0103 | TA413/DA/BM-04
293 | 12 | 43/1 | DA-1.5 | 2025-12-22 | 2025-12-31 | Pritam Enterprises-2 | 35.6018 | 3.317 | Haridas | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
294 | 13 | 13/0 | DD60+9 | 2025-12-18 | 2025-12-31 | Ved Prakash | 101.9526 | 9.4988 | Rudra Prasad | Completed | Received | O20017-T-TL-0D-GA-0407 | TA413/DD2/BM-07
295 | 1 | 29A/3 | DA+6 | 2025-12-27 | 2026-01-06 | Jwala Singh-1 | 43.8044 | 4.0812 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0106 | TA413/DA/BM-07
296 | 2 | 35/3 | DA-3 | 2026-01-07 | 2026-01-11 | Jwala Singh-1 | 34.7898 | 3.2413 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0108 | TA413/DA/BM-11
297 | 3 | 13A/0 | DB1+9 | 2026-01-01 | 2026-01-20 | Ved Prakash | 66.7809 | 6.2219 | Abhay Ojha | Completed | Received | O22017-T-TL-0D-GA-0207 | TA413/DB1/BM-07
298 | 4 | 37/2 | DA+3 | 2026-01-12 | 2026-01-22 | Jwala Singh-1 | 37.9311 | 3.534 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
299 | 5 | 2A/0 | DD45+0 | 2026-01-01 | 2026-01-25 | Pritam Enterprises-2 | 73.2445 | 6.8241 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0403 | TA413/DD1/BM-04
300 | 6 | 37/3 | DA-1.5 | 2026-01-23 | 2026-01-29 | Jwala Singh-1 | 35.6018 | 3.317 | Manoj Gupta | Completed | Received | O22017-T-TL-0D-GA-0109 | TA413/DA/BM-10
301 | 1 | 36/0 | DB2+3 | 2026-01-22 | 2026-02-04 | Ved Prakash | 62.1162 | 5.7873 | Khooblal Mahto | Completed | Received | O20017-T- TL-0D-GA-020 | TA413/DB2/BM-05
302 | 2 | 43/0 | DB1+0 | 2026-02-01 | 2026-02-14 | Jwala Singh | 55.4509 | 5.1663 | Manoj Gpta | Completed | Received | O22017-T-TL-0D-GA-0203 | TA413/DB1/BM-04
303 | 3 | 35/10 | DA+3 | 2026-02-07 | 2026-02-16 | Ved Prakash | 37.9311 | 3.534 | Khooblal Mahto | Completed | Received | O22017-T-TL-0D-GA-0105 | TA413/DA/BM-05
304 | 1 | 16/0 | DC2+0 | 2026-06-02 | 2026-06-19 | Amit Kumar Singh | 67.2617 | 6.2667 | Khooblal Mahto/Narayan | Completed
305 | 1 | 37/0-N | DB2+9 | 2026-07-12 |  | R.S construction | 72.1555 |  |  | WIP
306 |  | 36B/0-N | DB2+9 |  |  |  | 72.1555
307 |  | 36C/0-N | DC2+15 |  |  |  | 96.8803
|  | SL No | Tower Type | Per Tower Unit Weight (As per approved BOM)
|  |  |  | HT Steel (MT) | Mild Steel (MT) | PW (MT) | Bolts & Nuts (MT) | Total Weight of Tower (MT) |  | Construction Revenue
Tower with extensions Up to +9M
|  | 1 | DA+0 | 24.6977 | 9.9267 | 0.030435 | 1.505 | 36.1598 |  | 336894.6611
|  | 2 | DA+3 | 25.5188 | 10.8319 | 0.030629 | 1.5497 | 37.9311 |  | 353397.8779
|  | 3 | DA+6 | 29.4516 | 12.6215 | 0.030759 | 1.7006 | 43.8044 |  | 408118.8097
|  | 4 | DA+9 | 30.2474 | 13.6585 | 0.031055 | 1.76 | 45.697 |  | 425751.8425
|  | 5 | DA-1.5 | 24.4036 | 9.6764 | 0.030223 | 1.4915 | 35.6018 |  | 331695.9203
|  | 6 | DA-3 | 23.9488 | 9.3496 | 0.030211 | 1.4612 | 34.7898 |  | 324131.0934
|  | 7 | DA+4.5 | 28.9333 | 12.2838 | 0.030687 | 1.674 | 42.9218 |  | 399895.7201
|  | 8 | DA+1.5 | 25.2614 | 10.3136 | 0.030519 | 1.5328 | 37.1383 |  | 346011.8226
|  | 9 | DB1+0 | 42.0844 | 10.8263 | 0.059184 | 2.4809 | 55.4509 |  | 516626.7066
|  | 10 | DB1+3 | 43.7466 | 11.6153 | 0.061852 | 2.5394 | 57.9632 |  | 540033.5901
|  | 11 | DB1+6 | 49.1264 | 12.9888 | 0.074512 | 2.838 | 65.0278 |  | 605853.4125
|  | 12 | DB1+9 | 49.7414 | 14.0342 | 0.074608 | 2.9307 | 66.7809 |  | 622186.9697
|  | 13 | DB2+0 | 44.6465 | 12.2854 | 0.066186 | 2.5025 | 59.5006 |  | 554357.831
|  | 14 | DB2+3 | 46.2811 | 13.2142 | 0.069438 | 2.5514 | 62.1162 |  | 578726.2869
|  | 15 | DB2+6 | 51.442 | 14.984 | 0.081 | 2.869 | 69.376 |  | 646365.0918
|  | 16 | DB2+9 | 52.842 | 16.267 | 0.082046 | 2.9645 | 72.1555 |  | 672261.6213
|  | 17 | DC1+0 | 47.9692 | 11.8414 | 0.061932 | 2.5712 | 62.4437 |  | 581778.0178
|  | 18 | DC1+3 | 50.1786 | 12.959 | 0.06504 | 2.6698 | 65.8725 |  | 613723.3938
|  | 19 | DC2+0 | 51.8467 | 12.8185 | 0.062996 | 2.5335 | 67.2617 |  | 626666.7579
|  | 20 | DC2-3 | 50.4134 | 11.9351 | 0.061876 | 2.474 | 64.8843 |  | 604516.623
|  | 21 | DD45+0 | 55.8134 | 14.8039 | 0.058151 | 2.569 | 73.2445 |  | 682407.7346
|  | 22 | DD45+3 | 60.9578 | 13.3682 | 0.059057 | 2.692 | 77.0769 |  | 718113.4431
|  | 23 | DD60+0 | 62.4268 | 17.6311 | 0.067222 | 3.0084 | 83.1335 |  | 774541.7604
|  | 24 | DD60+3 | 66.1099 | 17.6755 | 0.069954 | 3.166 | 87.0213 |  | 810763.9014
|  | 25 | DD60+9 | 73.4565 | 24.8501 | 0.07859 | 3.5674 | 101.9526 |  | 949875.9872
|  | 26 | DB1+12 | 49.5411 | 18.1668 | 0.08738 | 2.993 | 70.7883 |  | 659522.9389
|  | 27 | DC2+15 | 71.12 | 22.269 | 0.097336 | 3.3936 | 96.8799 |  | 902614.5275
|  | 28 | DD60+18 | 84.6016 | 36.0432 | 0.10177 | 4.2034 | 124.95 |  | 1164138.7108
|  | 29 | DD60+25 | 90.6026 | 41.946 | 0.10993 | 4.3876 | 137.0461 |  | 1276836.6981
|  | 30 | DD60+35 | 130.9692 | 37.3037 | 0.10993 | 5.1781 | 173.5609 |  | 1617039.2474
|  | 31 | DCT+0M (TP) | 59.5334 | 19.752 | 0.11 | 2.868 | 82.2634 |  | 766434.74
Formulas:
Start = [Complete, row above]
Start = [Complete, row above]+1

## L2 Plan vs Actual (hidden)
Project :- TL02 for Bikaner-III - Neemrana-II 765 KV DC Line Part-I associated with Transmission system for excavation of power from Rajasthan REZ Ph-IV (Part-I) (Bikaner Complex: 7.7 GW)
Ref. :- CC/T/W-TW/DOM/A04/23/10569/NOA-1 & 2/24-103421/01 & 02 Date. 12/03/2024
Line Length :- 112 KM |  |  |  | Status as on | 24.07.2026
S.No. | Activity / Description | UOM | Qty | Start Date | End Date | L2 | Cumm. Till date | Balance | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
[6 empty] | Till date |  |  | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01
Supplies
1 | Line Materials | % | 100 | 2024-03-20 | 2025-03-22
a | Vendor Finalisation | % | 100 | 2024-03-20 | 2024-04-24
b | Submission / Approval of Drawings | % | 100 | 2024-04-01 | 2024-04-29 |  |  |  | 2024-04-01: 100%
c | Receipt at site of Stubs & Earthing | EA | 287 | 2024-04-18 | 2024-11-20 | 287 |  |  | 2024-04-01: 25; 2024-05-01: 50; 2024-06-01: 50; 2024-07-01: 50; 2024-09-01: 80; 2024-11-01: 32
| Stubs - Actual Status | [5 empty] | 313 | -26 | 2024-04-01: 0; 2024-05-01: 5; 2024-06-01: 130; 2024-07-01: 10; 2024-09-01: 40; 2024-10-01: 16; 2024-12-01: 44; 2025-01-01: 34
| Earthing Rod - Actual Status | [5 empty] | 309 | -22 | 2024-05-01: 107; 2024-06-01: 13; 2024-07-01: 10; 2024-08-01: 45; 2024-11-01: 25; 2025-01-01: 79
d | Receipt at site of Towers | EA | 287 | 2024-05-22 | 2025-02-20 | 287 |  | -5 | 2024-05-01: 40; 2024-06-01: 40; 2024-08-01: 40; 2024-09-01: 30; 2024-10-01: 30; 2024-12-01: 70; 2025-02-01: 37
|  |  | 13873.345 |  |  | 13873.58 |  | 898.58 | 2024-05-01: 1933.6; 2024-06-01: 1933.6; 2024-08-01: 1933.6; 2024-09-01: 1450.2; 2024-10-01: 1450.2; 2024-12-01: 3383.8; 2025-02-01: 1788.58
| Actual Status of Tower | EA |  |  |  |  | 292 | -5 | 2024-07-01: 40; 2024-08-01: 80; 2024-09-01: 45; 2024-10-01: 21; 2024-11-01: 16; 2024-12-01: 21; 2025-01-01: 8; 2025-02-01: 2
| Actual Status of Tower | MT |  |  |  |  | 12975 | 898.345 | 2024-05-01: 234.638; 2024-06-01: 1507.35; 2024-07-01: 1340.159; 2024-08-01: 1578.296; 2024-09-01: 1417.352; 2024-10-01: 570.26; 2024-11-01: 615.531; 2024-12-01: 1100; 2025-01-01: 1231.414
e | Receipt of Insulators at site | EA | 10480 | 2024-07-09 | 2024-12-20 | 10480 |  | 580 | 2024-07-01: 4192; 2024-10-01: 3144; 2024-12-01: 3144
| Actual Status | [5 empty] | 9900 | 580 | 2024-07-01: 4192
f | Receipt of Hardware Fittings & Accessories at site | % | 100 | 2024-07-09 | 2024-12-20 | 100% |  | 100% | 2024-07-01: 40%; 2024-10-01: 30%; 2024-12-01: 30%
| Actual Status | [5 empty] | 0 | 100
g | Receipt of Conductors at site | Km | 4095 | 2024-05-10 | 2025-03-22 | 4095 |  | 0.015 | 2024-05-01: 200; 2024-06-01: 500; 2024-07-01: 400; 2024-08-01: 300; 2024-09-01: 400; 2024-10-01: 300; 2024-11-01: 300; 2024-12-01: 400; 2025-01-01: 400; 2025-02-01: 400; 2025-03-01: 495
| Actual Status | [5 empty] | 4094.985 | 0.015 | 2024-05-01: 264; 2024-06-01: 59.8; 2024-07-01: 524.239; 2024-08-01: 99.987; 2024-09-01: 249.458; 2024-10-01: 499.972; 2024-11-01: 249.898; 2024-12-01: 499.861; 2025-01-01: 474.987; 2025-02-01: 1025.168
h | Receipt of Conductors Accessories at site | % | 100% | 2024-07-12 | 2024-12-25 | 100% |  | 0% | 2024-07-01: 40%; 2024-10-01: 30%; 2024-12-01: 30%
| Actual Status | [5 empty] | 100% | 0% | 2024-08-01: 40%; 2024-11-01: 30%; 2025-01-01: 30%
i | Receipt of Earth Wire & its Accessories at site | % | 100% | 2024-06-27 | 2024-12-25 | 100% |  | 0% | 2024-06-01: 40%; 2024-09-01: 40%; 2024-12-01: 20%
| Actual Status | [5 empty] | 100% | 0% | 2024-07-01: 40%; 2024-08-01: 40%; 2025-01-01: 20%
j | Receipt of OPGW & its Accessories at site | % | 100% | 2024-09-09 | 2024-12-25 | 100% |  | 100% | 2024-09-01: 70%; 2024-12-01: 30%
| Actual Status | [5 empty] | 0% | 100%
k | Receipt of Aviation materials | % | 100% | 2025-01-01 | 2025-01-31 | 0% |  | 0 | 2025-01-01: 100%
| Actual Status | [5 empty] | 0% | 100%
Service
1 | Establishment of Site Office/Store, Mobilization | % | 100 | 2024-03-20 | 2024-04-29
2 | Route Alignment Submission and Approval | Km | 112 | 2024-04-02 | 2024-04-20 |  |  |  | 2024-04-01: 112
| Actual Status |  | 115 |  |  |  | 115 |  | 2024-05-01: 115
3 | Detailed survey Submission and Approval | Km | 112 | 2024-04-22 | 2024-08-28 | 112 |  | -3 | 2024-04-01: 10; 2024-05-01: 22; 2024-06-01: 34; 2024-07-01: 34; 2024-08-01: 12
| Actual Status |  | 115 |  |  |  | 115 |  | 2024-05-01: 32.706; 2024-06-01: 31.918; 2024-08-01: 50.376
4 | Check survey Submission and Approval | Km | 112 | 2024-04-27 | 2024-10-27 | 112 |  | -2.972 | 2024-04-01: 5; 2024-05-01: 12; 2024-06-01: 20; 2024-07-01: 20; 2024-08-01: 20; 2024-09-01: 20; 2024-10-01: 15
| Actual Status |  | 114.972 |  |  |  | 114.972 |  | 2024-05-01: 5.969; 2024-06-01: 9.941; 2024-07-01: 33.643; 2024-08-01: 29.496; 2024-09-01: 5.08; 2024-10-01: 7.984; 2024-11-01: 15.688; 2024-12-01: 2.258; 2025-01-01: 4.913
5 | Submission of Forest proposal (If any) | % | 100 | 2024-06-01 | 2024-06-30 | 100% |  | 0% | 2024-06-01: 100%
| Actual Status |  | 100% |  |  |  | 100% |  | 2024-06-01: 100%
6 | Foundation | EA | 287 | 2024-05-19 | 2025-07-22 | 287 |  | -26 |  |  | 6 | 18 | 18 | 20 | 22 | 22 | 25 | 25 | 30 | 30 | 25 | 15 | 15 | 10 | 6
| Actual Status |  | 313 |  |  |  | 313 |  |  |  | 0 | 14 | 20 | 23 | 40 | 36 | 24 | 32 | 35 | 31 | 19 | 23 | 10 | 4 | 2
7 | Tower Erection | EA | 287 | 2024-06-14 | 2025-09-25 | 287 |  | -7 |  |  |  | 4 | 15 | 15 | 22 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 20 | 20 | 20 | 12 | 7
| Actual Status |  | 294 |  |  |  | 294 |  |  |  |  | 0 | 0 |  | 2 | 5 | 2 | 13 | 25 | 21 | 25 | 11 |  |  | 8 | 44 | 62 | 39 | 24 | 13
8 | Stringing ¦ Conductor | Km | 112 | 2024-08-16 | 2025-10-28 | 112 |  | 72.451 | [5 empty] | 4 | 4 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 10 | 8 | 8 | 8 | 4 | 4
| Actual Status |  | 39.549 |  |  |  | 39.549 |  | 2025-03-01: 4.899; 2025-04-01: 11.464; 2025-09-01: 5.134; 2025-10-01: 4.922; 2025-11-01: 4.901; 2025-12-01: 8.229
9 | Stringing ¦¦ OPGW | Km | 112 | 2024-04-04 | 2025-11-30 | 112 |  | 98.388 | 2025-04-01: 15; 2025-05-01: 20; 2025-06-01: 20; 2025-07-01: 20; 2025-08-01: 10; 2025-09-01: 10; 2025-10-01: 10; 2025-11-01: 7
| Actual Status |  | 13.612 |  |  |  | 13.612 |  | 2025-04-01: 13.612
10 | Testing & Commisioning | % | 100 | 2025-10-01 | 2025-12-11 | 0% |  | 0 | 2025-10-01: 40%; 2025-11-01: 50%; 2025-12-01: 10%
| Actual Status |  | 0 |  |  |  | 0
Note on N11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: B type Stub

## Survey summary (hidden)
Survey and Profile Drawing Status |  |  |  | Detail Survey | [5 empty] | Check Survey
S.No. | Section | Length | Detail Survey | Detail Survey data to Engg | Profile by Engg | TS Site Check | Final Profile | Submission to PGCIL | Approval by PGCIL | Check Survey | Re-Profile by Engg. | Submission to PGCIL | Approval
1 | AP 0 - AP 3 | 0.77215 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 2024-05-22 | 2024-08-12 | 2024-08-12 | 2024-08-12
2 | AP 3 - AP 4 | 4.8607 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-08-09 | 2024-08-12 |  | 2024-08-12 | 2024-08-12
3 | AP 4 - AP 5 | 5.0666 | 2024-05-08 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-25 | 2024-05-25 | 2024-05-28 | 2024-08-22 |  | 2024-08-22 | 2024-07-19
4 | AP 5 - AP 6 | 4.8379 | 2024-05-08 | 2024-05-15 | 2024-05-17 | 2024-06-04 | 2024-06-04 | 2024-06-05 | 2024-06-13 | 2024-07-27 |  | 1900-01-01 | 2024-07-30
5 | AP 6 - AP 7 | 4.9012 | 2024-05-08 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-08-22 |  | 2024-08-22 | 2024-08-19
6 | AP 7 - AP 8 | 5.1341 | 2024-05-08 | 2024-05-15 | 2024-05-17 | 2024-05-22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-07-27 |  | 2024-07-27 | 2024-07-30
7 | AP 8 - AP 9 | 4.9216 | 2024-05-06 | 2024-05-08 | 2024-05-09 | 2024-05-17 | 2024-05-17 | 2024-05-18 | 2024-05-28 | 2024-06-05 |  | 2024-06-13 | 2024-06-13
8 | AP 9 - AP 11 | 5.9691 | 2024-05-04 | 2024-05-08 | 2024-05-09 | 2024-05-13 | 2024-05-14 | 2024-05-16 | 2024-05-16 | 2024-05-15 | 2024-05-15 | 2024-05-16 | 2024-05-16
9 | AP 11 - AP 15 | 1.6936 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-05-26 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-07-24 |  | 2024-07-24 | 2024-12-06
10 | AP 15 - AP 16 | 5.0193 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-05-26 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-06-11 |  | 2024-06-11 | 2024-06-11
11 | AP 16 - AP 19 | 3.821 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-04 | 2024-06-05 | 2024-06-05 | 2024-06-13 | 2024-10-18 |  | 2024-10-18 | 2024-10-18
12 | AP 19 - AP 20 | 0.27936 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-04 | 2024-06-05 | 2024-06-05 | 2024-06-13 | 2024-08-24 |  | 2024-08-24
13 | AP 20 - AP 21 | 2.5502 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-04 | 2024-06-05 | 2024-06-05 | 2024-06-13 | 2024-06-22 |  | 2024-06-22 | 2024-07-11
14 | AP 21 - AP 22 | 2.2835 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-04 | 2024-06-05 | 2024-06-05 | 2024-06-13 | 2025-02-05 |  | 2025-02-05
15 | AP 23 - AP 27 | 1.881 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-24 |  | 2024-07-24 | 06.12.2024
16 | AP 27 - AP 28 | 2.5483 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-03 |  | 2024-07-04 | 2024-07-11
17 | AP 28 - AP 29 | 0.21121 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-24 |  | 2024-07-24 | 2025-02-05
18 | AP 29 - AP 30 | 5.0482 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-17 |  | 2024-07-17 | 2024-07-18
19 | AP 30 - AP 31 | 4.1242 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2024-07-17
20 | AP 31 - AP 32 | 4.3334 | 2024-05-13 | 2024-05-15 | 2024-05-21 | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-13 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-11
21 | AP 32 - AP 33 | 4.1239 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 01-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-12 |  | 2024-08-12 | 2024-08-12
22 | AP 33 - AP 34 | 4.0498 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 01-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-12 |  | 2024-08-12 | 2024-08-12
23 | AP 34 - AP 35 | 4.8986 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 03-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-12 |  | 2024-08-12 | 2024-08-12
24 | AP 35 - AP 37 | 6.6618 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 03-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-12 |  | 2024-08-12 | 2024-08-12
25 | AP 37 - AP 38 | 5.08 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 06-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-16 |  | 2024-09-16 | 2024-09-16
26 | AP 38 - AP 39 | 4.163 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 06-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-10-18 |  | 2024-10-18 | 2024-10-18
27 | AP 39 - AP 40 | 4.717 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 06-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-11-01 |  | 2024-11-01 | 2024-11-01
28 | AP 40 - AP 41 | 5.0265 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 07-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-11-01 |  | 2024-11-01 | 2024-11-01
29 | AP 41 - AP 44 | 5.9441 | 2024-05-22 | 2024-05-30 | 2024-06-06 | 07-07-2024 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-11-01 |  | 2024-11-01 | 2024-11-01
30 | AP 44 - AP 46 | 2.5917 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 | 2025-02-20 |  | 2025-02-20 | 2025-02-20
| Total Length | 117.513 | 117.513 | 117.513 | 117.513 | 117.513 | 117.513 | 117.513 | 117.513 | 116.7409 | 14.4267 | 116.7409 | 114.178
| Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77215 | 103.0863 | 0.77215 | 3.335
[8 empty] | Bal. Approval pending | 0 |  |  | Bal. Approval pending | 2.5629
2.283

## Detailed Survey (hidden)
KEC International Limited
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 378 Crore
Detailed Survey | [8 empty] | 24.07.2026
Sl.No. | SPAN |  | Profile Status | Route Length | Section Length (Km) | Submitted For Approval | Approved Date | Profile approval date | Remarks
| From Section | To Section
1 | Gnatry BKN -III | 1/0 |  | 0.15 | 0.15 | 2025-02-21 | 2025-02-21 | 2025-02-21
2 | 1/0 | 2A/0 |  | 0.29021 | 0.29021 | 2025-02-21 | 2025-02-21 | 2025-02-21
3 | 2A/0 | 3A/0 |  | 2.837 | 2.837 | 2025-02-21 | 2025-02-21 | 2025-02-21 | STATE HIGHWAY SH-3
4 | 3A/0 | 3B/0 |  | 2.691 | 2.691 | 2025-02-21 | 2025-02-21 | 2025-02-21
5 | 3B/0 | 4/0 |  | 1.627 | 1.627 | 2025-02-21 | 2025-02-21 | 2025-02-21
6 | 4/0 | 4A/0 |  | 0.70916 | 0.70916 | 2024-07-19 | 2024-07-19 | 2024-07-19
7 | 4A/0 | 5/0 |  | 2.6816 | 2.6816 | 2024-07-19 | 2024-07-19 | 2024-07-19
8 | 5/0 | 5A/0 |  | 4.4184 | 4.4184 | 2024-07-30 | 2024-07-30 | 2024-07-30
9 | 5A/0 | 6/0 | Submiteed | 0.41948 | 0.41948 | 2024-06-05 | 2024-06-17 | 2024-06-17
10 | 6/0 | 7/0 | Submiteed | 4.9099 | 4.9099 | 2024-05-28 | 2024-05-28 | 2024-05-28
11 | 7/0 | 8/0 | Submiteed | 5.0833 | 5.0833 | 2024-05-28 | 2024-05-28 | 2024-05-28
12 | 8/0 | 9/0 | Submiteed | 4.9957 | 4.9957 | 2024-05-18 | 2024-05-25 | 2024-05-25
13 | 9/0 | 10/0 | Submiteed | 4.9231 | 4.9231 | 2024-05-15 | 2024-05-16 | 2024-05-16
14 | 10/0 | 11/0 | Submiteed | 1.0051 | 1.0051 | 2024-05-15 | 2024-05-16 | 2024-05-16
15 | 11/0 | 12/0 | Submiteed | 0.2468 | 0.2468 | 2024-05-27 | 2024-05-27 | 2024-05-29 | NATIONAL HIGHWAY NH-62
16 | 12/0 | 13/0 | Submiteed | 0.3292 | 0.3292 | 2024-05-27 | 2024-05-27 | 2024-05-29 | 132KV SC LINE
17 | 13/0 | 14/0 | Submiteed | 0.8979 | 0.8979 | 2024-05-27 | 2024-05-27 | 2024-05-29
18 | 14/0 | 15/0 |  | 0.224 | 0.224 | 2024-05-27 | 2024-05-27 | 2024-05-29 | 400KV DC LINE
19 | 15/0 | 16/0 | Submiteed | 5.0201 | 5.0201 | 2024-05-27 | 2024-05-27 | 2024-05-29 | CANAL
20 | 16/0 | 17/0 |  | 0.3861 | 0.3861 | 2024-06-05 | 2024-07-26 | 2024-07-26
21 | 17/0 | 18/0 |  | 0.4114 | 0.4114 | 2024-06-05 | 2024-07-26 | 2024-07-26
22 | 18/0 | 19/0 |  | 3.0234 | 3.0234 | 2024-06-05 | 2024-07-26 | 2024-07-26
23 | 19/0 | 20/0 |  | 0.2795 | 0.2795 | 2024-06-05 | 2024-07-26 | 2024-07-26 | RAILWAY TRACK (SINGLE LINE ) ELECTRTIC
24 | 20/0 | 21/0 |  | 2.5514 | 2.5514 | 2024-06-05 | 2024-07-26 | 2024-07-26
25 | 21/0 | 22/0 |  | 2.2835 | 2.2835 | 2024-06-05 | 2024-07-26 | 2024-07-26
26 | 22/0 | 23/0 |  | 0.2594 | 0.2594 | 2024-06-05 | 2024-07-26 | 2024-07-26 | 220 KV S/C RVPN
27 | 23/0 | 24/0 |  | 0.9285 | 0.9285 | 2024-06-12 | 2024-07-26 | 2024-07-26
28 | 24/0 | 25/0 |  | 0.2521 | 0.2521 | 2024-06-12 | 2024-07-26 | 2024-07-26 | 400 KV S/C RVPN(STP-BKN)
29 | 25/0 | 26/0 |  | 0.2374 | 0.2374 | 2024-06-12 | 2024-07-26 | 2024-07-26
30 | 26/0 | 27/0 |  | 0.204 | 0.204 | 2024-06-12 | 2024-07-26 | 2024-07-26 | 765 KV D/C POWER GRID(BKN-MGA)
31 | 27/0 | 28/0 |  | 2.5476 | 2.5476 | 2024-06-12 | 2024-07-26 | 2024-07-26
32 | 28/0 | 29/0 |  | 0.2118 | 0.2118 | 2024-06-12 | 2024-07-26 | 2024-07-26 | Amritsar Jamnagar Expressway
33 | 29/0 | 30/0 |  | 4.9547 | 4.9547 | 2024-06-12 | 2024-07-26 | 2024-07-26
34 | 30/0 | 31/0 |  | 4.2189 | 4.2189 | 2024-06-12 | 2024-07-26 | 2024-07-26
35 | 31/0 | 32/0 |  | 4.3323 | 4.3323 | 2024-06-12 | 2024-07-26 | 2024-07-26
36 | 32/0 | 33/0 |  | 4.1241 | 4.1241 | 2024-07-29 | 2024-08-12 | 2024-08-12 | STATE HIGHWAY SH-93
37 | 33/0 | 34/0 |  | 4.0498 | 4.0498 | 2024-07-29 | 2024-07-29 | 2024-07-29
38 | 34/0 | 35/0 |  | 4.8986 | 4.8986 | 2024-07-29 | 2024-07-29 | 2024-07-29
39 | 35/0 | 36/0 |  | 4.9164 | 4.9164 | 2024-07-29 | 2024-07-29 | 2024-07-29
40 | 36/0 | 37/0 |  | 1.7455 | 1.7455 | 2024-07-29 | 2024-07-29 | 2024-07-29
41 | 37/0 | 37A/0 |  | 2.4964 | 2.4964 | 2024-07-29 | 2024-07-29 | 2024-07-29
42 | 37A/0 | 38/0 |  | 2.5836 | 2.5836 | 2024-07-29 | 2024-07-29 | 2024-07-29
43 | 38/0 | 39/0 |  | 4.1637 | 4.1637 | 2024-07-29 | 2024-07-29 | 2024-07-29
44 | 39/0 | 40/0 |  | 4.7168 | 4.7168 | 2024-07-29 | 2024-07-29 | 2024-07-29
45 | 40/0 | 40A/0 |  | 4.6659 | 4.6659 | 2024-07-29 | 2024-07-29 | 2024-07-29
46 | 40A/0 | 41/0 |  | 0.41061 | 0.41061 | 2024-07-29 | 2024-07-29 | 2024-07-29
47 | 41/0 | 42/0 |  | 0.82378 | 0.82378 | 2024-07-29 | 2024-07-29 | 2024-07-29
48 | 42/0 | 43/0 |  | 1.6839 | 1.6839 | 2024-07-29 | 2024-07-29 | 2024-07-29
49 | 43/0 | 44/0 |  | 3.4364 | 3.4364 | 2024-07-29 | 2024-07-29 | 2024-07-29
50 | 44/0 | 46/0 |  | 2.5917 | 2.5917 | 2025-02-20 | 2025-02-20 | 2025-02-20
Total |  |  |  | 117.848 | 117.848

## Check Survey (hidden)
KEC International Limited
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 378 Crore
Check Survey | [5 empty] | 24.07.2026
Sl.No. | SPAN |  | Section Length (Km) | Submitted For Approval | Approval date | Remarks
| From Section | To Section
1 | Gnatry BKN -III | 1/0 | 0.15 | 2025-02-21 | 2025-02-21
2 | 1/0 | 2A/0 | 0.29021 | 2025-02-21 | 2025-02-21
3 | 2A/0 | 3A/0 | 2.837 | 2025-02-21 | 2025-02-21
4 | 3A/0 | 3B/0 | 2.691 | 2025-02-21 | 2025-02-21
5 | 3B/0 | 4/0 | 1.627 | 2025-02-21 | 2025-02-21
6 | 4/0 | 4A/0 | 0.709 | 2024-07-19 | 2024-07-19
7 | 4A/0 | 5/0 | 2.682 | 2024-07-19 | 2024-07-19
8 | 5/0 | 5A/0 | 4.418 | 2024-07-30 | 2024-07-30
9 | 5A/0 | 6/0 | 0.41948 | 2024-07-27 | 2024-07-30
10 | 6/0 | 7/0 | 4.9099 | 2024-08-22 | 2024-08-19
11 | 7/0 | 8/0 | 5.0833 | 2024-07-27 | 2024-07-30
12 | 8/0 | 9/0 | 4.9957 | 2024-06-13 | 2024-06-13
13 | 9/0 | 10/0 | 4.9231 | 2024-05-16 | 2024-05-16
14 | 10/0 | 11/0 | 1.0051 | 2024-05-16 | 2024-05-16
15 | 11/0 | 12/0 | 0.2468 | 2024-07-24 |  | NH - 62
16 | 12/0 | 13/0 | 0.3292 | 2024-07-24 | 2024-12-06 | 132 KV S/C BKN-LKS T/L
17 | 13/0 | 14/0 | 0.8979 | 2025-01-25
18 | 14/0 | 15/0 | 0.224 | 2024-07-24 | 2025-01-21 | 400 KV D/C SUR-BKN
19 | 15/0 | 16/0 | 5.0201 | 2024-06-11 | 2024-06-11
20 | 16/0 | 17/0 | 0.3861 | 2024-10-18 | 2024-10-18
21 | 17/0 | 18/0 | 0.4114 | 2024-10-18 | 2024-10-18
22 | 18/0 | 19/0 | 3.0234 | 2024-10-18 | 2024-10-18
23 | 19/0 | 20/0 | 0.2795 | 2024-07-24 |  | Railway Line Electrified SingleTrack
24 | 20/0 | 21/0 | 2.5514 | 2024-06-22 | 2024-07-11
25 | 21/0 | 22/0 | 2.2835 | 2025-02-05
26 | 22/0 | 23/0 | 0.2594 | 2024-07-24 | 2024-12-06 | 220 KV S/C SUR-BKN
27 | 23/0 | 24/0 | 0.9285 | 2024-07-24 | 2024-12-06
28 | 24/0 | 25/0 | 0.2521 | 2024-07-24 | 2024-12-06 | 400 KV S/C STP-BKN T/L
29 | 25/0 | 26/0 | 0.2374 | 2024-07-24 | 2024-12-06
30 | 26/0 | 27/0 | 0.204 | 2024-07-24 | 2024-12-06 | 765 KV D/C BKN-MGA T/L
31 | 27/0 | 28/0 | 2.5476 | 2024-07-03 | 2024-07-11
32 | 28/0 | 29/0 | 0.2118 | 2024-07-24 |  | Expressway Crossing (NH754A)
33 | 29/0 | 30/0 | 4.9547 | 2024-07-17 | 2024-07-18
34 | 30/0 | 31/0 | 4.2189 | 2024-07-17 | 2024-07-17
35 | 31/0 | 32/0 | 4.3323 | 2024-07-02 | 2024-07-04
36 | 32/0 | 33/0 | 4.1241 | 2024-08-12 | 2024-08-12
37 | 33/0 | 34/0 | 4.0498 | 2024-08-12 | 2024-08-12
38 | 34/0 | 35/0 | 4.8986 | 2024-08-12 | 2024-08-12
39 | 35/0 | 36/0 | 4.9164 | 2024-08-12 | 2024-08-12
40 | 36/0 | 37/0 | 1.7455 | 2024-08-12 | 2024-08-12
41 | 37/0 | 37A/0 | 2.4964 | 2024-09-16 | 2024-09-16
42 | 37A/0 | 38/0 | 2.5836 | 2024-09-16 | 2024-09-16
43 | 38/0 | 39/0 | 4.1637 | 2024-10-18 | 2024-10-18
44 | 39/0 | 40/0 | 4.7168 | 2024-11-01 | 2024-11-01
45 | 40/0 | 40A/0 | 4.6659 | 2024-11-01 | 2024-11-01
46 | 40A/0 | 41/0 | 0.41061 | 2024-11-01 | 2024-11-01
47 | 41/0 | 42/0 | 0.82378 | 2024-11-01 | 2024-11-01
48 | 42/0 | 43/0 | 1.6839 | 2024-11-01 | 2024-11-01
49 | 43/0 | 44/0 | 3.4364 | 2024-11-01 | 2024-11-01
50 | 44/0 | 46/0 | 2.5917 | 2025-02-20 | 2025-02-20
Total |  |  | 117.8479

## Earthing
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Earthing | [8 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Name of the Contractor | Name of Supervisor | Rev Month | Remarks
1 | 1 | 8/10 | DA+0 | Sandy | 2024-08-18 | 2024-08-18 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
2 | 2 | 8/9 | DA+3 | Sandy | 2024-08-18 | 2024-08-18 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
3 | 3 | 8/8 | DA+9 | Sandy | 2024-08-18 | 2024-08-18 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
4 | 4 | 8/5 | DA+9 | Sandy | 2024-08-20 | 2024-08-20 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
5 | 5 | 8/6 | DA+3 | Sandy | 2024-08-20 | 2024-08-20 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
6 | 6 | 8/7 | DA+3 | Sandy | 2024-08-20 | 2024-08-20 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
7 | 7 | 9/3 | DA+0 | Sandy | 2024-08-24 | 2024-08-24 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
8 | 8 | 9/4 | DA+6 | Sandy | 2024-08-24 | 2024-08-24 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
9 | 9 | 9/1 | DA+3 | Sandy | 2024-08-26 | 2024-08-26 | Sanjay Construction | Reshpaul Tyagi | Aug'2024 | Completed
10 | 10 | 7A/2 | DA+3 | Sandy | 2024-09-06 | 2024-09-06 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
11 | 11 | 5/8 | DA+6 | Sandy | 2024-09-10 | 2024-09-10 | Sanjay Construction | Ankit Yadav | Sep'2024 | Completed
12 | 12 | 5/10 | DA+9 | Sandy | 2024-09-09 | 2024-09-09 | Sanjay Construction | Ankit Yadav | Sep'2024 | Completed
13 | 13 | 6/2 | DA+6 | Sandy | 2024-09-10 | 2024-09-10 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
14 | 14 | 6/1 | DA+9 | Sandy | 2024-09-10 | 2024-09-10 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
15 | 15 | 6/12 | DA+1.5 | Sandy | 2024-09-15 | 2024-09-15 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
16 | 16 | 6/11 | DA-1.5 | Sandy | 2024-09-15 | 2024-09-15 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
17 | 17 | 7A/3 | DA+3 | Sandy | 2024-09-15 | 2024-09-15 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
18 | 18 | 4A/3 | DA+9 | Sandy | 2024-09-16 | 2024-09-16 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
19 | 19 | 5/6 | DA+3 | Sandy | 2024-09-20 | 2024-09-20 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
20 | 20 | 5/7 | DA+9 | Sandy | 2024-09-20 | 2024-09-20 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
21 | 21 | 6/3 | DA+3 | Sandy | 2024-09-12 | 2024-09-12 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
22 | 22 | 4A/4 | DA+6 | Sandy | 2024-09-13 | 2024-09-13 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
23 | 23 | 4A/5 | DA+9 | Sandy | 2024-09-12 | 2024-09-12 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
24 | 24 | 7A/5 | DA+3 | Sandy | 2024-09-05 | 2024-09-05 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
25 | 25 | 7A/4 | DA+3 | Sandy | 2024-09-05 | 2024-09-05 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
26 | 26 | 7A/1 | DA+1.5 | Sandy | 2024-09-05 | 2024-09-05 | Sanjay Construction | Reshpaul Tyagi | Sep'2024 | Completed
27 | 1 | 6/4 | DA+9 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
28 | 2 | 6/6 | DA-3 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
29 | 3 | 6/9 | DA+6 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
30 | 4 | 6/10 | DA+1.5 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
31 | 5 | 7/1 | DA-3 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
32 | 6 | 7/3 | DA+9 | Sandy | 2024-10-11 | 2024-10-11 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
33 | 7 | 4A/1 | DA+6 | Sandy | 2024-10-12 | 2024-10-12 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
34 | 8 | 5/4 | DA-1.5 | Sandy | 2024-10-12 | 2024-10-12 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
35 | 9 | 5/2 | DA+9 | Sandy | 2024-10-12 | 2024-10-12 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
36 | 10 | 5/3 | DA+9 | Sandy | 2024-10-12 | 2024-10-12 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
37 | 11 | 15/2 | DA+3 | Sandy | 2014-10-13 | 2014-10-13 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
38 | 12 | 15/3 | DA+3 | Sandy | 2014-10-13 | 2014-10-13 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
39 | 13 | 15/4 | DA+6 | Sandy | 2014-10-13 | 2014-10-13 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
40 | 14 | 15/6 | DA+9 | Sandy | 2014-10-13 | 2014-10-13 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
41 | 15 | 15/9 | DA+0 | Sandy | 2024-10-14 | 2024-10-14 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
42 | 16 | 15/11 | DA+0 | Sandy | 2024-10-14 | 2024-10-14 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
43 | 17 | 15/8 | DA+1.5 | Sandy | 2024-10-14 | 2024-10-14 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
44 | 18 | 15/7 | DA+0 | Sandy | 2024-10-15 | 2024-10-15 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
45 | 19 | 15/5 | DA+3 | Sandy | 2024-10-15 | 2024-10-15 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
46 | 20 | 27/6 | DA-3 | Sandy | 2024-10-15 | 2024-10-15 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
47 | 21 | 30/1 | DA+0 | Sandy | 2024-10-15 | 2024-10-15 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
48 | 22 | 27/1 | DA+9 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
49 | 23 | 27/2 | DA-1.5 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
50 | 24 | 27/3 | DA+1.5 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
51 | 25 | 27/4 | DA+1.5 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
52 | 26 | 27/5 | DA-1.5 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
53 | 27 | 29/1 | DA+6 | Sandy | 2024-10-16 | 2024-10-16 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
54 | 28 | 29/3 | DA+0 | Sandy | 2024-10-17 | 2024-10-17 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
55 | 29 | 29/4 | DA+3 | Sandy | 2024-10-17 | 2024-10-17 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
56 | 30 | 29/5 | DA+0 | Sandy | 2024-10-17 | 2024-10-17 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
57 | 31 | 29A/2 | DA+6 | Sandy | 2024-10-17 | 2024-10-17 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
58 | 32 | 29A/6 | DA+9 | Sandy | 2024-10-18 | 2024-10-18 | Sanjay Construction | Suraj /Vikram | Oct'2024 | Completed
59 | 33 | 29A/3 | DA+6 | Sandy | 2024-10-19 | 2024-10-19 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
60 | 34 | 29A/5 | DA+6 | Sandy | 2024-10-19 | 2024-10-19 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
61 | 35 | 31/3 | DA+3 | Sandy | 2024-10-19 | 2024-10-19 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
62 | 36 | 31/6 | DA+9 | Sandy | 2024-10-19 | 2024-10-19 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
63 | 37 | 31/8 | DA+0 | Sandy | 2024-10-19 | 2024-10-19 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
64 | 38 | 31/7 | DA+0 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
65 | 39 | 31/9 | DA+1.5 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
66 | 40 | 32/3 | DA+6 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
67 | 41 | 34/1 | DA+9 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
68 | 42 | 33/3 | DA+3 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
69 | 43 | 33/4 | DA+3 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
70 | 44 | 33/6 | DA+6 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
71 | 45 | 33/7 | DA+6 | Sandy | 2024-10-20 | 2024-10-20 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
72 | 46 | 34/2 | DA+9 | Sandy | 2024-10-22 | 2024-10-22 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
73 | 47 | 34/3 | DA+1.5 | Sandy | 2024-10-22 | 2024-10-22 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
74 | 48 | 34/5 | DA+9 | Sandy | 2024-10-22 | 2024-10-22 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
75 | 49 | 34/6 | DA+3 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
76 | 50 | 34/7 | DA+0 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
77 | 51 | 34/9 | DA+1.5 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
78 | 52 | 34/11 | DA+1.5 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
79 | 53 | 34/12 | DA+3 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
80 | 54 | 35/1 | DA+6 | Sandy | 2024-10-23 | 2024-10-23 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
81 | 55 | 35/5 | DA+9 | Sandy | 2024-10-24 | 2024-10-24 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
82 | 56 | 35/6 | DA+6 | Sandy | 2024-10-24 | 2024-10-24 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
83 | 57 | 35/7 | DA+3 | Sandy | 2024-10-24 | 2024-10-24 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
84 | 58 | 32/4 | DA+9 | Sandy | 2024-10-24 | 2024-10-24 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
85 | 59 | 36A/1 | DA+3 | Sandy | 2024-10-25 | 2024-10-25 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
86 | 60 | 36A/2 | DA+9 | Sandy | 2024-10-25 | 2024-10-25 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
87 | 61 | 37/1 | DA+3 | Sandy | 2024-10-25 | 2024-10-25 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
88 | 62 | 37/2 | DA+3 | Sandy | 2024-10-25 | 2024-10-25 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
89 | 63 | 37/3 | DA-1.5 | Sandy | 2024-10-25 | 2024-10-25 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
90 | 64 | 29A/1 | DA+6 | Sandy | 2024-10-26 | 2024-10-26 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
91 | 65 | 29A/4 | DA+3 | Sandy | 2024-10-26 | 2024-10-26 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
92 | 66 | 31/10 | DA+4.5 | Sandy | 2024-10-26 | 2024-10-26 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
93 | 67 | 34/4 | DA+6 | Sandy | 2024-10-26 | 2024-10-26 | Sanjay Construction | Suraj Kumar | Oct'2024 | Completed
94 | 68 | 6/0 | DB1+9 | Sandy | 27/10/202 | 27/10/202 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
95 | 69 | 5/9 | DA+6 | Sandy | 2024-10-27 | 2024-10-27 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
96 | 70 | 4A/0 | DB1+3 | Sandy | 2024-10-27 | 2024-10-27 | Sanjay Construction | Reshpaul Tyagi | Oct'2024 | Completed
97 | 1 | 17/0 | DC1+3 | Sandy | 2024-12-23 | 2024-12-23 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
98 | 2 | 18/1 | DA+3 | Sandy | 2024-12-24 | 2024-12-24 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
99 | 3 | 18/2 | DA+1.5 | Sandy | 2024-12-24 | 2024-12-24 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
100 | 4 | 18/3 | DA+6 | Sandy | 2024-12-24 | 2024-12-24 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
101 | 5 | 18/4 | DA-3 | Sandy | 2024-12-25 | 2024-12-25 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
102 | 6 | 18/5 | DA+0 | Sandy | 2024-12-25 | 2024-12-25 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
103 | 7 | 18/0 | DB2+6 | Sandy | 2024-12-25 | 2024-12-25 | HSK Construction | Reshpaul Tyagi | Dec'24 | Completed
104 | 8 | 38/1 | DA+0 | Sandy | 2024-12-26 | 2024-12-26 | HSK Construction | Jai Prakash | Dec'24 | Completed
105 | 9 | 38/2 | DA+0 | Sandy | 2024-12-26 | 2024-12-26 | HSK Construction | Jai Prakash | Dec'24 | Completed
106 | 10 | 38/5 | DA+3 | Sandy | 2024-12-26 | 2024-12-26 | HSK Construction | Jai Prakash | Dec'24 | Completed
107 | 11 | 38/6 | DA+6 | Sandy | 2024-12-26 | 2024-12-26 | HSK Construction | Jai Prakash | Dec'24 | Completed
108 | 12 | 38/7 | DA+9 | Sandy | 2024-12-27 | 2024-12-27 | HSK Construction | Jai Prakash | Dec'24 | Completed
109 | 13 | 38/8 | DA+1.5 | Sandy | 2024-12-27 | 2024-12-27 | HSK Construction | Jai Prakash | Dec'24 | Completed
110 | 14 | 38/9 | DA+0 | Sandy | 2024-12-27 | 2024-12-27 | HSK Construction | Jai Prakash | Dec'24 | Completed
111 | 15 | 38/10 | DA+3 | Sandy | 2024-12-27 | 2024-12-27 | HSK Construction | Jai Prakash | Dec'24 | Completed
112 | 16 | 39/0 | DB2+0 | Sandy | 2024-12-28 | 2024-12-28 | HSK Construction | Jai Prakash | Dec'24 | Completed
113 | 17 | 39/1 | DA-1.5 | Sandy | 2024-12-28 | 2024-12-28 | HSK Construction | Jai Prakash | Dec'24 | Completed
114 | 18 | 39/2 | DA+3 | Sandy | 2024-12-28 | 2024-12-28 | HSK Construction | Jai Prakash | Dec'24 | Completed
115 | 19 | 7/0 | DB2+0 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
116 | 20 | 7/2 | DA+6 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
117 | 21 | 7/4 | DA+6 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
118 | 22 | 7/5 | DA+6 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
119 | 23 | 8/1 | DA-3 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
120 | 24 | 8/2 | DA+6 | Sandy | 2024-12-29 | 2024-12-29 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
121 | 25 | 9/2 | DA+3 | Sandy | 2024-12-31 | 2024-12-31 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
122 | 26 | 9/5 | DA+3 | Sandy | 2024-12-31 | 2024-12-31 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
123 | 27 | 9/10 | DA+3 | Sandy | 2024-12-31 | 2024-12-31 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
124 | 28 | 9/11 | DA+3 | Sandy | 2024-12-31 | 2024-12-31 | Sanjay Construction | Reshpaul Tyagi | Dec'24 | Completed
125 | 1 | 37A/2 | DA+1.5 | Sandy | 2025-01-01 | 2025-01-01 | HSK Construction | Jai Prakash | Jan'25 | Completed
126 | 2 | 37A/3 | DA+3 | Sandy | 2025-01-01 | 2025-01-01 | HSK Construction | Jai Prakash | Jan'25 | Completed
127 | 3 | 37A/4 | DA+9 | Sandy | 2025-01-01 | 2025-01-01 | HSK Construction | Jai Prakash | Jan'25 | Completed
128 | 4 | 37A/5 | DA+3 | Sandy | 2025-01-01 | 2025-01-01 | HSK Construction | Jai Prakash | Jan'25 | Completed
129 | 5 | 37A/6 | DA+3 | Sandy | 2025-01-01 | 2025-01-01 | HSK Construction | Jai Prakash | Jan'25 | Completed
130 | 6 | 37A/1 | DA+3 | Sandy | 2025-01-02 | 2025-01-02 | HSK Construction | Jai Prakash | Jan'25 | Completed
131 | 7 | 37A/0 | DB1+0 | Sandy | 2025-01-02 | 2025-01-02 | HSK Construction | Jai Prakash | Jan'25 | Completed
132 | 8 | 37/5 | DA+3 | Sandy | 2025-01-02 | 2025-01-02 | HSK Construction | Jai Prakash | Jan'25 | Completed
133 | 9 | 37/4 | DA+9 | Sandy | 2025-01-02 | 2025-01-02 | HSK Construction | Jai Prakash | Jan'25 | Completed
134 | 10 | 39/3 | DA+1.5 | Sandy | 2025-01-03 | 2025-01-03 | HSK Construction | Jai Prakash | Jan'25 | Completed
135 | 11 | 40/2 | DA+6 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
136 | 12 | 40/3 | DA+3 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
137 | 13 | 40/4 | DA+6 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
138 | 14 | 40/5 | DA+9 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
139 | 15 | 40/6 | DA+9 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
140 | 16 | 40/7 | DA+3 | Sandy | 04.01.2025 | 04.01.2025 | HSK Construction | Jai Prakash | Jan'25 | Completed
141 | 1 | 33/5 | DA+0 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
142 | 2 | 33/8 | DA+3 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
143 | 3 | 33/9 | DA+1.5 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
144 | 4 | 34/0 | DB1+6 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
145 | 5 | 34/8 | DA+0 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
146 | 6 | 35/0 | DB2+0 | Sandy | 2025-02-13 | 2025-02-13 | HSK Construction | Jai Prakash | Feb'25 | Completed
147 | 7 | 35/4 | DA+9 | Sandy | 2025-02-14 | 2025-02-14 | HSK Construction | Jai Prakash | Feb'25 | Completed
148 | 8 | 35/8 | DA+6 | Sandy | 2025-02-14 | 2025-02-14 | HSK Construction | Jai Prakash | Feb'25 | Completed
149 | 9 | 35/9 | DA+1.5 | Sandy | 2025-02-14 | 2025-02-14 | HSK Construction | Jai Prakash | Feb'25 | Completed
150 | 10 | 35/11 | DA+3 | Sandy | 2025-02-14 | 2025-02-14 | HSK Construction | Jai Prakash | Feb'25 | Completed
151 | 11 | 36/0 | DB2+3 | Sandy | 2025-02-14 | 2025-02-14 | HSK Construction | Jai Prakash | Feb'25 | Completed
152 | 12 | 30/0 | DB1+0 | Sandy | 2025-02-16 | 2025-02-16 | HSK Construction | Jai Prakash | Feb'25 | Completed
153 | 13 | 30/4 | DA+9 | Sandy | 2025-02-16 | 2025-02-16 | HSK Construction | Jai Prakash | Feb'25 | Completed
154 | 14 | 30/5 | DA+0 | Sandy | 2025-02-16 | 2025-02-16 | HSK Construction | Jai Prakash | Feb'25 | Completed
155 | 15 | 30/2 | DA+9 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
156 | 16 | 30/3 | DA+3 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
157 | 17 | 30/6 | DA+6 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
158 | 18 | 30/7 | DA-3 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
159 | 19 | 30/8 | DA+3 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
160 | 20 | 30/9 | DA-3 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
161 | 21 | 30/10 | DA+3 | Sandy | 2024-02-17 | 2024-02-17 | HSK Construction | Jai Prakash | Feb'25 | Completed
162 | 22 | 31/0 | DB1+0 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
163 | 23 | 31/1 | DA+3 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
164 | 24 | 31/2 | DA+1.5 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
165 | 25 | 31/4 | DA-1.5 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
166 | 26 | 31/5 | DA+6 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
167 | 27 | 32/0 | DB2+0 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
168 | 28 | 32/1 | DA+6 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
169 | 29 | 32/2 | DA+9 | Sandy | 2025-02-18 | 2025-02-18 | HSK Construction | Jai Prakash | Feb'25 | Completed
170 | 1 | 39/4 | DA+3 | Sandy | 2025-03-30 | 2025-03-30 | Sanjay Construction | Abul | March'25 | Completed
171 | 2 | 39/5 | DA+1.5 | Sandy | 2025-03-30 | 2025-03-30 | Sanjay Construction | Abul | March'25 | Completed
172 | 3 | 39/6 | DA+1.5 | Sandy | 2025-03-30 | 2025-03-30 | Sanjay Construction | Abul | March'25 | Completed
173 | 4 | 39/7 | DA+3 | Sandy | 2025-03-31 | 2025-03-31 | Sanjay Construction | Abul | March'25 | Completed
174 | 5 | 39/9 | DA+6 | Sandy | 2025-03-31 | 2025-03-31 | Sanjay Construction | Abul | March'25 | Completed
175 | 6 | 39/10 | DA+3 | Sandy | 2025-03-31 | 2025-03-31 | Sanjay Construction | Abul | March'25 | Completed
176 | 7 | 39/11 | DA+6 | Sandy | 2025-03-31 | 2025-03-31 | Sanjay Construction | Abul | March'25 | Completed
177 | 8 | 40/0 | DB1+6 | Sandy | 2025-03-31 | 2025-03-31 | Sanjay Construction | Abul | March'25 | Completed
178 | 1 | 40/8 | DA-1.5 | Sandy | 2025-04-01 | 2025-04-01 | Sanjay Construction | Abul | April'25 | Completed
179 | 2 | 40/9 | DA+9 | Sandy | 2025-04-01 | 2025-04-01 | Sanjay Construction | Abul | April'25 | Completed
180 | 3 | 40/10 | DA+3 | Sandy | 2025-04-03 | 2025-04-03 | Sanjay Construction | Abul | April'25 | Completed
181 | 4 | 40/11 | DA+9 | Sandy | 2025-04-03 | 2025-04-03 | Sanjay Construction | Abul | April'25 | Completed
182 | 5 | 40A/0 | DB1+9 | Sandy | 2025-04-03 | 2025-04-03 | Sanjay Construction | Abul | April'25 | Completed
183 | 6 | 41/0 | DB1+9 | Sandy | 2025-04-03 | 2025-04-03 | Sanjay Construction | Abul | April'25 | Completed
184 | 7 | 42/0 | DB2+0 | Sandy | 2025-04-04 | 2025-04-04 | Sanjay Construction | Abul | April'25 | Completed
185 | 8 | 42/1 | DA+3 | Sandy | 2025-04-04 | 2025-04-04 | Sanjay Construction | Abul | April'25 | Completed
186 | 9 | 42/2 | DA+9 | Sandy | 2025-04-04 | 2025-04-04 | Sanjay Construction | Abul | April'25 | Completed
187 | 10 | 42A/0 | DB1+9 | Sandy | 2025-04-04 | 2025-04-04 | Sanjay Construction | Abul | April'25 | Completed
188 | 11 | 43/2 | DA+6 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
189 | 12 | 43/3 | DA-1.5 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
190 | 13 | 43/4 | DA+0 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
191 | 14 | 43/6 | DA+3 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
192 | 15 | 43/7 | DA+0 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
193 | 16 | 43/8 | DA+9 | Sandy | 2025-04-05 | 2025-04-05 | Sanjay Construction | Abul | April'25 | Completed
194 | 17 | 44/1 | DA+3 | Sandy | 2025-04-06 | 2025-04-06 | Sanjay Construction | Abul | April'25 | Completed
195 | 18 | 44/2 | DA+3 | Sandy | 2025-04-06 | 2025-04-06 | Sanjay Construction | Abul | April'25 | Completed
196 | 19 | 44/3 | DA+3 | Sandy | 2025-04-06 | 2025-04-06 | Sanjay Construction | Abul | April'25 | Completed
197 | 20 | 44/4 | DA+0 | Sandy | 2025-04-06 | 2025-04-06 | Sanjay Construction | Abul | April'25 | Completed
198 | 21 | 44/5 | DA+0 | Sandy | 2025-04-06 | 2025-04-06 | Sanjay Construction | Abul | April'25 | Completed
199 | 22 | 39/8 | DA+1.5 | Sandy | 2025-04-07 | 2025-04-07 | Sanjay Construction | Abul | April'25 | Completed
200 | 23 | 38/3 | DA+3 | Sandy | 2025-04-07 | 2025-04-07 | Sanjay Construction | Abul | April'25 | Completed
201 | 24 | 38/4 | DA+1.5 | Sandy | 2025-04-07 | 2025-04-07 | Sanjay Construction | Abul | April'25 | Completed
202 | 25 | 9/6 | DA+3 | Sandy | 2025-04-08 | 2025-04-08 | Sanjay Construction | Abul | April'25 | Completed
203 | 26 | 9/7 | DA+9 | Sandy | 2025-04-08 | 2025-04-08 | Sanjay Construction | Abul | April'25 | Completed
204 | 27 | 9/8 | DA+0 | Sandy | 2025-04-08 | 2025-04-08 | Sanjay Construction | Abul | April'25 | Completed
205 | 28 | 10/0 | DB1+6 | Sandy | 2025-04-09 | 2025-04-09 | Sanjay Construction | Chetram | April'25 | Completed
206 | 29 | 9/9 | DA+0 | Sandy | 2025-04-09 | 2025-04-09 | Sanjay Construction | Chetram | April'25 | Completed
207 | 30 | 10/1 | DA+3 | Sandy | 2025-04-09 | 2025-04-09 | Sanjay Construction | Chetram | April'25 | Completed
208 | 31 | 8/0 | DB1+0 | Sandy | 2025-04-10 | 2025-04-10 | HSK Construction | Suraj | April'25 | Completed
209 | 32 | 8/3 | DA+9 | Sandy | 2025-04-10 | 2025-04-10 | HSK Construction | Suraj | April'25 | Completed
210 | 33 | 8/4 | DA+6 | Sandy | 2025-04-10 | 2025-04-10 | HSK Construction | Suraj | April'25 | Completed
211 | 34 | 7A/0 | DB1+6 | Sandy | 2025-04-11 | 2025-04-11 | HSK Construction | Suraj | April'25 | Completed
212 | 35 | 6/8 | DA+3 | Sandy | 2025-04-11 | 2025-04-11 | HSK Construction | Suraj | April'25 | Completed
213 | 36 | 34/10 | DA-3 | Sandy | 2025-04-11 | 2025-04-11 | Sanjay Construction | Manoj Gupta | April'25 | Completed
214 | 37 | 33/1 | DA+9 | Sandy | 2025-04-11 | 2025-04-11 | Sanjay Construction | Manoj Gupta | April'25 | Completed
215 | 38 | 33/2 | DA+9 | Sandy | 2025-04-11 | 2025-04-11 | Sanjay Construction | Manoj Gupta | April'25 | Completed
216 | 39 | 33/0 | DB1+9 | Sandy | 2025-04-12 | 2025-04-12 | Sanjay Construction | Manoj Gupta | April'25 | Completed
217 | 40 | 32/5 | DA+9 | Sandy | 2025-04-12 | 2025-04-12 | Sanjay Construction | Manoj Gupta | April'25 | Completed
218 | 41 | 32/6 | DA+9 | Sandy | 2025-04-12 | 2025-04-12 | Sanjay Construction | Manoj Gupta | April'25 | Completed
219 | 42 | 32/7 | DA+3 | Sandy | 2025-04-12 | 2025-04-12 | Sanjay Construction | Manoj Gupta | April'25 | Completed
220 | 43 | 6/5 | DA+9 | Sandy | 2025-04-12 | 2025-04-12 | HSK Construction | Suraj | April'26 | Completed
221 | 44 | 5/5 | DA+6 | Sandy | 2025-04-12 | 2025-04-12 | HSK Construction | Suraj | April'27 | Completed
222 | 45 | 5A/0 | DB1+12 | Sandy | 2025-04-12 | 2025-04-12 | HSK Construction | Suraj | April'28 | Completed
223 | 46 | 32A/1 | DA+6 | Sandy | 2025-04-13 | 2025-04-13 | Sanjay Construction | Manoj Gupta | April'25 | Completed
224 | 47 | 29A/0 | DB1+0 | Sandy | 2025-04-13 | 2025-04-13 | Sanjay Construction | Manoj Gupta | April'25 | Completed
225 | 48 | 29/2 | DA+0 | Sandy | 2025-04-13 | 2025-04-13 | Sanjay Construction | Manoj Gupta | April'25 | Completed
226 | 49 | 32A/0 | DB1+9 | Sandy | 2025-04-14 | 2025-04-14 | Sanjay Construction | Manoj Gupta | April'25 | Completed
227 | 50 | 29/0 | DC1+0 | Sandy | 2025-04-14 | 2025-04-14 | Sanjay Construction | Manoj Gupta | April'25 | Completed
228 | 51 | 28/0 | DC2-3 | Sandy | 2025-04-14 | 2025-04-14 | Sanjay Construction | Manoj Gupta | April'25 | Completed
229 | 52 | 27/0 | DD60+35 | Sandy | 2025-04-14 | 2025-04-14 | Sanjay Construction | Manoj Gupta | April'25 | Completed
230 | 53 | 26/0 | DD60+35 | Sandy | 2025-04-15 | 2025-04-15 | Sanjay Construction | Manoj Gupta | April'25 | Completed
231 | 54 | 25/0 | DD60+18 | Sandy | 2025-04-15 | 2025-04-15 | Sanjay Construction | Manoj Gupta | April'25 | Completed
232 | 55 | 24/0 | DD60+18 | Sandy | 2025-04-15 | 2025-04-15 | Sanjay Construction | Manoj Gupta | April'25 | Completed
233 | 56 | 23A/0 | DB1+9 | Sandy | 2025-04-16 | 2025-04-16 | Sanjay Construction | Manoj Gupta | April'25 | Completed
234 | 57 | 23/0 | DB2+9 | Sandy | 2025-04-16 | 2025-04-16 | Sanjay Construction | Manoj Gupta | April'25 | Completed
235 | 58 | 22/0 | DC2+15 | Sandy | 2025-04-16 | 2025-04-16 | Sanjay Construction | Manoj Gupta | April'25 | Completed
236 | 59 | 21/5 | DA+0 | Sandy | 2025-04-16 | 2025-04-16 | Sanjay Construction | Manoj Gupta | April'25 | Completed
237 | 60 | 21/4 | DA+0 | Sandy | 2025-04-17 | 2025-04-17 | Sanjay Construction | Suraj | April'25 | Completed
238 | 61 | 20/2 | DA-3 | Sandy | 2025-04-17 | 2025-04-17 | Sanjay Construction | Suraj | April'25 | Completed
239 | 62 | 20/1 | DA-3 | Sandy | 2025-04-17 | 2025-04-17 | Sanjay Construction | Suraj | April'25 | Completed
240 | 63 | 18/7 | DA+1.5 | Sandy | 2025-04-18 | 2025-04-18 | Sanjay Construction | Suraj | April'25 | Completed
241 | 64 | 18/6 | DA+9 | Sandy | 2025-04-18 | 2025-04-18 | Sanjay Construction | Suraj | April'25 | Completed
242 | 65 | 15/10 | DA-1.5 | Sandy | 2025-04-18 | 2025-04-18 | Sanjay Construction | Suraj | April'25 | Completed
243 | 66 | 15/0 | DD60+25 | Sandy | 2025-04-19 | 2025-04-19 | Sanjay Construction | Suraj | April'25 | Completed
244 | 67 | 15/1 | DA+6 | Sandy | 2025-04-19 | 2025-04-19 | Sanjay Construction | Suraj | April'25 | Completed
245 | 68 | 13/0 | DD60+9 | Sandy | 2025-04-19 | 2025-04-19 | Sanjay Construction | Suraj | April'25 | Completed
246 | 69 | 2A/2 | DA+3 | Sandy | 2025-04-28 | 2025-04-28 | Sanjay Construction | Sanjay | April'25 | Completed
247 | 70 | 2A/3 | DA+3 | Sandy | 2025-04-28 | 2025-04-28 | Sanjay Construction | Sanjay | April'25 | Completed
248 | 71 | 2A/4 | DA+3 | Sandy | 2025-04-29 | 2025-04-29 | Sanjay Construction | Sanjay | April'25 | Completed
249 | 72 | 2A/5 | DA+3 | Sandy | 2025-04-29 | 2025-04-29 | Sanjay Construction | Sanjay | April'25 | Completed
250 | 73 | 2A/6 | DA+6 | Sandy | 2025-04-29 | 2025-04-29 | Sanjay Construction | Sanjay | April'25 | Completed
251 | 74 | 3A/0 | DD45+3 | Sandy | 2025-04-30 | 2025-04-30 | Sanjay Construction | Sanjay | April'25 | Completed
252 | 75 | 3A/1 | DA+3 | Sandy | 2025-04-30 | 2025-04-30 | Sanjay Construction | Sanjay | April'25 | Completed
253 | 1 | 3A/2 | DA+3 | Sandy | 2025-05-01 | 2025-05-01 | Sanjay Construction | Sanjay | May'25 | Completed
254 | 2 | 3A/3 | DA+0 | Sandy | 2025-05-01 | 2025-05-01 | Sanjay Construction | Sanjay | May'25 | Completed
255 | 3 | 3A/4 | DA+0 | Sandy | 2025-05-01 | 2025-05-01 | Sanjay Construction | Sanjay | May'25 | Completed
256 | 4 | 3A/5 | DA+3 | Sandy | 2025-05-03 | 2025-05-03 | Sanjay Construction | Sanjay | May'25 | Completed
257 | 5 | 3A/6 | DA+0 | Sandy | 2025-05-03 | 2025-05-03 | Sanjay Construction | Sanjay | May'25 | Completed
258 | 6 | 3B/0 | DB1+9 | Sandy | 2025-05-03 | 2025-05-03 | Sanjay Construction | Sanjay | May'25 | Completed
259 | 7 | 3B/1 | DA+3 | Sandy | 2025-05-03 | 2025-05-03 | Sanjay Construction | Sanjay | May'25 | Completed
260 | 8 | 3B/2 | DA+9 | Sandy | 2025-05-03 | 2025-05-03 | Sanjay Construction | Sanjay | May'25 | Completed
261 | 9 | 8/11 | DA+9 | Sandy | 2025-05-04 | 2025-05-04 | Sanjay Construction | Sanjay | May'25 | Completed
262 | 10 | 8A/0 | DB1+12 | Sandy | 2025-05-04 | 2025-05-04 | Sanjay Construction | Sanjay | May'25 | Completed
263 | 11 | 10/2 | DA+3 | Sandy | 2025-05-05 | 2025-05-05 | Sanjay Construction | Sanjay | May'25 | Completed
264 | 12 | 13A/0 | DB1+9 | Sandy | 2025-05-05 | 2025-05-05 | Sanjay Construction | Sanjay | May'25 | Completed
265 | 13 | 14/0 | DD60+18 | Sandy | 2025-05-05 | 2025-05-05 | Sanjay Construction | Sanjay | May'25 | Completed
266 | 14 | 3B/3 | DA+6 | Sandy | 2025-05-06 | 2025-05-06 | Sanjay Construction | Sanjay | May'25 | Completed
267 | 15 | 4/0 | DB2+9 | Sandy | 2025-05-06 | 2025-05-06 | Sanjay Construction | Sanjay | May'25 | Completed
268 | 16 | 4/1 | DA+6 | Sandy | 2025-05-06 | 2025-05-06 | Sanjay Construction | Sanjay | May'25 | Completed
269 | 17 | 4A/2 | DA+6 | Sandy | 2025-05-06 | 2025-05-06 | Sanjay Construction | Sanjay | May'25 | Completed
270 | 18 | 4A/6 | DA+9 | Sandy | 2025-05-07 | 2025-05-07 | Sanjay Construction | Sanjay | May'25 | Completed
271 | 19 | 5/0 | DB1+6 | Sandy | 2025-05-07 | 2025-05-07 | Sanjay Construction | Sanjay | May'25 | Completed
272 | 20 | 5/1 | DA+6 | Sandy | 2025-05-07 | 2025-05-07 | Sanjay Construction | Sanjay | May'25 | Completed
273 | 21 | 6/7 | DA+1.5 | Sandy | 2025-05-07 | 2025-05-07 | Sanjay Construction | Sanjay | May'25 | Completed
274 | 22 | 7/6 | DA-1.5 | Sandy | 2025-05-07 | 2025-05-07 | Sanjay Construction | Sanjay | May'25 | Completed
275 | 23 | 9/0 | DB1+12 | Sandy | 2025-05-08 | 2025-05-08 | Sanjay Construction | Sanjay | May'25 | Completed
276 | 24 | 21/2 | DA+6 | Sandy | 2025-05-08 | 2025-05-08 | Sanjay Construction | Sanjay | May'25 | Completed
277 | 25 | 21/3 | DA+6 | Sandy | 2025-05-08 | 2025-05-08 | Sanjay Construction | Sanjay | May'25 | Completed
278 | 1 | 11/0 | DD45+0 | Sandy | 2025-07-01 | 2025-07-01 | Sanjay Construction | Sanjay | Jul'25 | Completed
279 | 2 | 12/0 | DB1+9 | Sandy | 2025-07-01 | 2025-07-01 | Sanjay Construction | Sanjay | Jul'25 | Completed
280 | 3 | 20/3 | DA+1.5 | Sandy | 2025-07-02 | 2025-07-02 | Sanjay Construction | Sanjay | Jul'25 | Completed
281 | 4 | 20/4 | DA+3 | Sandy | 2025-07-02 | 2025-07-02 | Sanjay Construction | Sanjay | Jul'25 | Completed
282 | 5 | 20/5 | DA+0 | Sandy | 2025-07-02 | 2025-07-02 | Sanjay Construction | Sanjay | Jul'25 | Completed
283 | 6 | 20/0 | DD60+3 | Sandy | 2025-07-04 | 2025-07-04 | Sanjay Construction | Sanjay | Jul'25 | Completed
284 | 7 | 20/6 | DA-3 | Sandy | 2025-07-04 | 2025-07-04 | Sanjay Construction | Sanjay | Jul'25 | Completed
285 | 8 | 21/0 | DB1+0 | Sandy | 2025-07-04 | 2025-07-04 | Sanjay Construction | Sanjay | Jul'25 | Completed
286 | 9 | 21/1 | DA+0 | Sandy | 2025-07-04 | 2025-07-04 | Sanjay Construction | Sanjay | Jul'25 | Completed
287 | 10 | 19/0 | DD60+3 | Sandy | 2025-07-05 | 2025-07-05 | Sanjay Construction | Sanjay | Jul'25 | Completed
288 | 11 | 37/0 | DB2+3 | Sandy | 2025-07-06 | 2025-07-06 | Sanjay Construction | Sanjay | Jul'25 | Completed
289 | 12 | 38/0 | DB1+3 | Sandy | 2025-07-06 | 2025-07-06 | Sanjay Construction | Sanjay | Jul'25 | Completed
290 | 13 | 1/0 | DD60+0 | Sandy | 2025-07-15 | 2025-07-15 | Sanjay Construction | Rudra Prasad | Jul'25 | Completed
291 | 14 | 2A/0 | DD45+0 | Sandy | 2025-07-15 | 2025-07-15 | Sanjay Construction | Rudra Prasad | Jul'25 | Completed
292 | 15 | 2A/1 | DA+0 | Sandy | 2025-07-15 | 2025-07-15 | Sanjay Construction | Rudra Prasad | Jul'25 | Completed
293 | 1 | 40/1 | DA+9 | Sandy | 2025-11-06 | 2025-11-06 | Sanjay Construction | Susheel | Nov'25 | Completed
294 | 2 | 41/1 | DA+9 | Sandy | 2025-11-06 | 2025-11-06 | Sanjay Construction | Susheel | Nov'25 | Completed
295 | 3 | 43A/0 | DCT | Sandy | 2025-11-06 | 2025-11-06 | Sanjay Construction | Susheel | Nov'25 | Completed
296 | 4 | 44/0 | DB1+6 | Sandy | 2025-11-07 | 2025-11-07 | Sanjay Construction | Susheel | Nov'25 | Completed
297 | 5 | 45/0 | DB1+9 | Sandy | 2025-11-07 | 2025-11-07 | Sanjay Construction | Susheel | Nov'25 | Completed
298 | 6 | 46/0 | DB1+12 | Sandy | 2025-11-07 | 2025-11-07 | Sanjay Construction | Susheel | Nov'25 | Completed
299 | 1 | 43/0 | DB1+0 | Sandy | 2026-02-02 | 2026-02-02 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
300 | 2 | 43/1 | DA-1.5 | Sandy | 2026-02-02 | 2026-02-02 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
301 | 3 | 36B/0-N | DB2+9 | Sandy | 2026-02-02 | 2026-02-02 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
302 | 4 | 35/3 | DA-3 | Sandy | 2026-02-03 | 2026-02-03 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
303 | 5 | 35/10 | DA+3 | Sandy | 2026-02-03 | 2026-02-03 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
304 | 6 | 15/12 | DA+6 | Sandy | 2026-02-03 | 2026-02-03 | Sanjay Construction | Rudra Prasad | Feb'26 | Completed
305 | 1 | 36C/0-N | DC2+15 | Sandy | 2026-03-18 | 2026-03-18 | Sanjay Construction | Susheel Kumar | Mar'26 | Completed
306 | 2 | 37/0-N | DB2+9 | Sandy | 2026-03-19 | 2026-03-19 | Sanjay Construction | Susheel Kumar | Mar'26 | Completed
307 | 3 | 16/0 | DC2+0 | Sandy | 2026-03-20 | 2026-03-20 | Sanjay Construction | Susheel Kumar | Mar'26 | Completed
308 | 1 | 35/2 | DA+6 | Sandy | 2026-06-09 | 2026-06-09 | Sanjay Construction | Sanjay Kumar | Jul'26 | Completed
309 |  | 36A/0 | DB1+9
Formulas:
Complete = [Start]

## Tack Welding
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Tack Welding | [7 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Name of the Contractor | Name of Supervisor | Remarks | Painting
1 | 1 | 34/4 | DA+6 | 2025-01-12 | 2025-01-12 | MB Sharma | Manoj Kumar Gupta | Completed
2 | 2 | 34/7 | DA+0 | 2025-01-13 | 2025-01-13 | MB Sharma | Manoj Kumar Gupta | Completed
3 | 3 | 34/10 | DA-3 | 2025-01-14 | 2025-01-14 | MB Sharma | Manoj Kumar Gupta | Completed
4 | 4 | 34/3 | DA+1.5 | 2025-01-15 | 2025-01-15 | MB Sharma | Manoj Kumar Gupta | Completed
5 | 5 | 34/6 | DA+3 | 2025-01-16 | 2025-01-16 | MB Sharma | Manoj Kumar Gupta | Completed
6 | 6 | 34/5 | DA+9 | 2025-01-19 | 2025-01-19 | MB Sharma | Manoj Kumar Gupta | Completed
7 | 7 | 34/9 | DA+1.5 | 2025-01-21 | 2025-01-21 | MB Sharma | Manoj Kumar Gupta | Completed
8 | 8 | 34/12 | DA+3 | 2025-01-22 | 2025-01-22 | MB Sharma | Manoj Kumar Gupta | Completed
9 | 9 | 34/2 | DA+9 | 2025-01-25 | 2025-01-25 | MB Sharma | Manoj Kumar Gupta | Completed
10 | 10 | 34/11 | DA+1.5 | 2025-01-27 | 2025-01-27 | MB Sharma | Manoj Kumar Gupta | Completed
11 | 11 | 35/1 | DA+6 | 2025-01-29 | 2025-01-29 | MB Sharma | Manoj Kumar Gupta | Completed
12 | 12 | 35/5 | DA+9 | 2025-01-30 | 2025-01-30 | MB Sharma | Manoj Kumar Gupta | Completed
13 | 13 | 35/7 | DA+3 | 2025-01-31 | 2025-01-31 | MB Sharma | Manoj Kumar Gupta | Completed
14 | 1 | 34/1 | DA+9 | 2025-02-02 | 2025-02-02 | MB Sharma | Manoj Kumar Gupta | Completed
15 | 2 | 35/8 | DA+6 | 2025-02-03 | 2025-02-03 | MB Sharma | Manoj Kumar Gupta | Completed
16 | 3 | 34/8 | DA+0 | 2025-02-04 | 2025-02-04 | MB Sharma | Manoj Kumar Gupta | Completed
17 | 4 | 29/3 | DA+0 | 2025-02-06 | 2024-02-06 | MB Sharma | Manoj Kumar Gupta | Completed
18 | 5 | 29/4 | DA+3 | 2025-02-07 | 2025-02-07 | MB Sharma | Manoj Kumar Gupta | Completed
19 | 6 | 29/5 | DA+0 | 2025-02-08 | 2025-02-08 | MB Sharma | Manoj Kumar Gupta | Completed
20 | 7 | 29A/1 | DA+6 | 2025-02-09 | 2025-02-09 | MB Sharma | Manoj Kumar Gupta | Completed
21 | 8 | 29A/2 | DA+6 | 2025-02-09 | 2025-02-09 | MB Sharma | Manoj Kumar Gupta | Completed
22 | 9 | 29A/6 | DA+9 | 2025-02-10 | 2025-02-10 | MB Sharma | Manoj Kumar Gupta | Completed
23 | 10 | 30/1 | DA+0 | 2025-02-10 | 2025-02-10 | MB Sharma | Manoj Kumar Gupta | Completed
24 | 11 | 7A/2 | DA+3 | 2025-02-09 | 2025-02-09 | MB Sharma | Gangadin Sahoo | Completed
25 | 12 | 7A/3 | DA+3 | 2025-02-10 | 2025-02-10 | MB Sharma | Gangadin Sahoo | Completed
26 | 13 | 7/1 | DA-3 | 2025-02-10 | 2025-02-10 | MB Sharma | Gangadin Sahoo | Completed
27 | 14 | 7A/4 | DA+3 | 2025-02-11 | 2025-02-11 | MB Sharma | Gangadin Sahoo | Completed
28 | 15 | 7A/5 | DA+3 | 2025-02-11 | 2025-02-11 | MB Sharma | Gangadin Sahoo | Completed
29 | 16 | 8/1 | DA-3 | 2025-02-12 | 2025-02-12 | MB Sharma | Gangadin Sahoo | Completed
30 | 17 | 8/2 | DA+6 | 2025-02-13 | 2025-02-13 | MB Sharma | Gangadin Sahoo | Completed
31 | 18 | 8/5 | DA+9 | 2025-02-14 | 2025-02-14 | MB Sharma | Gangadin Sahoo | Completed
32 | 19 | 8/6 | DA+3 | 2025-02-15 | 2025-02-15 | MB Sharma | Gangadin Sahoo | Completed
33 | 20 | 8/7 | DA+3 | 2025-02-16 | 2025-02-16 | MB Sharma | Gangadin Sahoo | Completed
34 | 21 | 8/8 | DA+9 | 2025-02-17 | 2025-02-17 | MB Sharma | Gangadin Sahoo | Completed
35 | 22 | 8/9 | DA+3 | 2025-02-17 | 2025-02-17 | MB Sharma | Gangadin Sahoo | Completed
36 | 23 | 8/10 | DA+0 | 2025-02-17 | 2025-02-17 | MB Sharma | Gangadin Sahoo | Completed
37 | 24 | 8/0 | DB1+0 | 2025-02-18 | 2025-02-18 | MB Sharma | Gangadin Sahoo | Completed
38 | 25 | 7A/0 | DB1+6 | 2025-02-21 | 2025-02-21 | MB Sharma | Gangadin Sahoo | Completed
39 | 26 | 34/0 | DB1+6 | 2025-02-23 | 2025-02-23 | MB Sharma | Gangadin Sahoo | Completed
40 | 1 | 8/3 | DA+9 | 2025-03-18 | 2025-03-18 | MB Sharma | Gangadin Sahoo | Completed
41 | 2 | 8/4 | DA+6 | 2025-03-18 | 2025-03-18 | MB Sharma | Gangadin Sahoo | Completed
42 | 3 | 35/0 | DB2+0 | 2025-03-20 | 2025-03-20 | MB Sharma | Rahul Kumar | Completed
43 | 4 | 37A/0 | DB1+0 | 2025-03-22 | 2025-03-22 | MB Sharma | Rahul Kumar | Completed
44 | 5 | 37A/6 | DA+3 | 2025-03-22 | 2025-03-22 | MB Sharma | Rahul Kumar | Completed
45 | 6 | 37A/4 | DA+9 | 2025-03-23 | 2025-03-23 | MB Sharma | Rahul Kumar | Completed
46 | 7 | 37A/1 | DA+3 | 2025-03-24 | 2025-03-24 | MB Sharma | Rahul Kumar | Completed
47 | 8 | 37A/2 | DA+1.5 | 2025-03-24 | 2025-03-24 | MB Sharma | Rahul Kumar | Completed
48 | 9 | 37A/3 | DA+3 | 2025-03-25 | 2025-03-25 | MB Sharma | Rahul Kumar | Completed
49 | 10 | 37A/5 | DA+3 | 2025-03-25 | 2025-03-25 | MB Sharma | Rahul Kumar | Completed
50 | 11 | 9/4 | DA+6 | 2025-03-25 | 2025-03-25 | MB Sharma | Rahul Kumar | Completed
51 | 12 | 9/3 | DA+0 | 2025-03-25 | 2025-03-25 | MB Sharma | Rahul Kumar | Completed
52 | 13 | 9/2 | DA+3 | 2025-03-27 | 2025-03-27 | MB Sharma | Rahul Kumar | Completed
53 | 14 | 9/1 | DA+3 | 2025-03-27 | 2025-03-27 | MB Sharma | Rahul Kumar | Completed
54 | 15 | 38/1 | DA+0 | 2025-03-31 | 2025-03-31 | MB Sharma | Rahul Kumar | Completed
55 | 1 | 38/2 | DA+0 | 2025-04-05 | 2025-04-05 | MB Sharma | Rahul Kumar | Completed
56 | 2 | 38/3 | DA+3 | 2025-04-06 | 2025-04-06 | MB Sharma | Rahul Kumar | Completed
57 | 3 | 38/4 | DA+1.5 | 2025-04-06 | 2025-04-06 | MB Sharma | Rahul Kumar | Completed
58 | 4 | 38/5 | DA+3 | 2025-04-09 | 2025-04-09 | MB Sharma | Rahul Kumar | Completed
59 | 5 | 38/6 | DA+6 | 2025-04-09 | 2025-04-09 | MB Sharma | Rahul Kumar | Completed
60 | 6 | 38/8 | DA+1.5 | 2025-04-09 | 2025-04-09 | MB Sharma | Rahul Kumar | Completed
61 | 7 | 38/9 | DA+0 | 2025-04-09 | 2025-04-09 | MB Sharma | Rahul Kumar | Completed
62 | 8 | 38/10 | DA+3 | 2025-04-09 | 2025-04-09 | MB Sharma | Rahul Kumar | Completed
63 | 9 | 33/6 | DA+6 | 2025-04-28 | 2025-04-28 | MB Sharma | Manoj Kumar Gupta | Completed
64 | 1 | 7/2 | DA+6 | 2025-04-29 | 2025-04-29 | MB Sharma | Manoj Kumar Gupta | Completed
65 | 2 | 7/5 | DA+6 | 2025-04-29 | 2025-04-29 | MB Sharma | Manoj Kumar Gupta | Completed
66 | 3 | 7/6 | DA-1.5 | 2025-04-30 | 2025-04-30 | MB Sharma | Manoj Kumar Gupta | Completed
67 | 4 | 33/5 | DA+0 | 2025-04-30 | 2025-04-30 | MB Sharma | Manoj Kumar Gupta | Completed
68 | 5 | 33/8 | DA+3 | 2025-05-01 | 2025-05-01 | MB Sharma | Manoj Kumar Gupta | Completed
69 | 6 | 38/0 | DB1+3 | 2025-05-02 | 2025-05-02 | MB Sharma | Manoj Kumar Gupta | Completed
70 | 7 | 39/0 | DB2+0 | 2025-05-03 | 2025-05-03 | MB Sharma | Manoj Kumar Gupta | Completed
71 | 8 | 39/1 | DA-1.5 | 2025-05-03 | 2025-05-03 | MB Sharma | Manoj Kumar Gupta | Completed
72 | 9 | 39/2 | DA+3 | 2025-05-04 | 2025-05-04 | MB Sharma | Manoj Kumar Gupta | Completed
73 | 10 | 39/3 | DA+1.5 | 2025-05-05 | 2025-05-05 | MB Sharma | Manoj Kumar Gupta | Completed
74 | 11 | 39/4 | DA+3 | 2025-05-06 | 2025-05-06 | MB Sharma | Manoj Kumar Gupta | Completed
75 | 12 | 39/5 | DA+1.5 | 2025-05-06 | 2025-05-06 | MB Sharma | Manoj Kumar Gupta | Completed
76 | 13 | 39/6 | DA+1.5 | 2025-05-08 | 2025-05-08 | MB Sharma | Manoj Kumar Gupta | Completed
77 | 14 | 15/2 | DA+3 | 2025-05-12 | 2025-05-12 | MB Sharma | Manoj Kumar | Completed
78 | 15 | 15/3 | DA+3 | 2025-05-12 | 2025-05-12 | MB Sharma | Manoj Kumar | Completed
79 | 16 | 15/5 | DA+3 | 2025-05-13 | 2025-05-13 | MB Sharma | Manoj Kumar | Completed
80 | 17 | 15/6 | DA+9 | 2025-05-15 | 2025-05-15 | MB Sharma | Manoj Kumar | Completed
81 | 18 | 39/7 | DA+3 | 2025-05-21 | 2025-05-21 | MB Sharma | Manoj Kumar | Completed
82 | 19 | 39/8 | DA+1.5 | 2025-05-21 | 2025-05-21 | MB Sharma | Manoj Kumar | Completed
83 | 20 | 39/9 | DA+6 | 2025-05-22 | 2025-05-22 | MB Sharma | Manoj Kumar Gupta | Completed
84 | 21 | 39/10 | DA+3 | 2025-05-23 | 2025-05-23 | MB Sharma | Manoj Kumar Gupta | Completed
85 | 22 | 39/11 | DA+6 | 2025-05-24 | 2025-05-24 | MB Sharma | Manoj Kumar Gupta | Completed
86 | 23 | 40/2 | DA+6 | 2025-05-25 | 2025-05-25 | MB Sharma | Manoj Kumar Gupta | Completed
87 | 24 | 40/3 | DA+3 | 2025-05-27 | 2025-05-27 | MB Sharma | Manoj Kumar Gupta | Completed
88 | 25 | 40/4 | DA+6 | 2025-05-28 | 2025-05-28 | MB Sharma | Manoj Kumar Gupta | Completed
89 | 26 | 40/5 | DA+9 | 2025-05-29 | 2025-05-29 | MB Sharma | Manoj Kumar Gupta | Completed
90 | 27 | 40/6 | DA+9 | 2025-05-30 | 2025-05-30 | MB Sharma | Manoj Kumar Gupta | Completed
91 | 1 | 7/0 | DB2+0 | 2025-09-27 | 2025-09-27 | MB Sharma | Shuvam Gupta | Completed
92 | 2 | 7/3 | DA+9 | 2025-09-28 | 2025-09-28 | MB Sharma | Shuvam Gupta | Completed
93 | 1 | 7A/1 | DA+1.5 | 2025-10-01 | 2025-10-02 | MB Sharma | Shuvam Gupta | Completed
94 | 2 | 8/11 | DA+9 | 2025-10-03 | 2025-10-04 | MB Sharma | Shuvam Gupta | Completed
95 | 3 | 8A/0 | DB1+12 | 2025-10-05 | 2025-10-06 | MB Sharma | Shuvam Gupta | Completed
96 | 4 | 32/4 | DA+9 | 2025-10-13 | 2025-10-13 | MB Sharma | Kartik Jhorar | Completed
97 | 5 | 32/0 | DB2+0 | 2025-10-14 | 2025-10-14 | MB Sharma | Kartik Jhorar | Completed
98 | 6 | 32/7 | DA+3 | 2025-10-15 | 2025-10-15 | MB Sharma | Kartik Jhorar | Completed
99 | 7 | 32/6 | DA+9 | 2025-10-14 | 2025-10-14 | MB Sharma | Kartik Jhorar | Completed
100 | 8 | 32/3 | DA+6 | 2025-10-14 | 2025-10-14 | MB Sharma | Kartik Jhorar | Completed
101 | 9 | 32/5 | DA+9 | 2025-10-16 | 2025-10-16 | MB Sharma | Kartik Jhorar | Completed
102 | 10 | 32A/0 | DB1+9 | 2025-10-18 | 2025-10-18 | MB Sharma | Kartik Jhorar | Completed
103 | 1 | 6/0 | DB1+9 | 2025-11-10 | 2025-11-11 | MB Sharma | Tarique Anwar | Completed
104 | 2 | 6/1 | DA+9 | 2025-11-11 | 2025-11-11 | MB Sharma | Tarique Anwar | Completed
105 | 3 | 6/2 | DA+6 | 2025-11-12 | 2025-11-12 | MB Sharma | Tarique Anwar | Completed
106 | 4 | 6/3 | DA+3 | 2025-11-13 | 2025-11-14 | MB Sharma | Tarique Anwar | Completed
107 | 5 | 6/4 | DA+9 | 2025-11-15 | 2025-11-15 | MB Sharma | Tarique Anwar | Completed
108 | 6 | 6/5 | DA+9 | 2025-11-16 | 2025-11-17 | MB Sharma | Tarique Anwar | Completed
109 | 7 | 6/6 | DA-3 | 2025-11-18 | 2025-11-18 | MB Sharma | Tarique Anwar | Completed
110 | 8 | 6/7 | DA+1.5 | 2025-11-19 | 2025-11-19 | MB Sharma | Tarique Anwar | Completed
111 | 9 | 6/8 | DA+3 | 2025-11-20 | 2025-11-20 | MB Sharma | Tarique Anwar | Completed
112 | 10 | 6/9 | DA+6 | 2025-11-21 | 2025-11-21 | MB Sharma | Tarique Anwar | Completed
113 | 11 | 6/10 | DA+1.5 | 2025-11-22 | 2025-11-22 | MB Sharma | Tarique Anwar | Completed
114 | 12 | 6/11 | DA-1.5 | 2025-11-23 | 2025-11-23 | MB Sharma | Tarique Anwar | Completed
115 | 13 | 6/12 | DA+1.5 | 2025-11-23 | 2025-11-23 | MB Sharma | Tarique Anwar | Completed
116 | 14 | 5/10 | DA+9 | 2025-11-26 | 2025-11-27 | MB Sharma | Tarique Anwar | Completed
117 | 1 | 5/1 | DA+6 | 2025-12-01 | 2025-12-02 | MB Sharma | Sanjay Jumar | Completed
118 | 2 | 5/2 | DA+9 | 2025-12-03 | 2025-12-04 | MB Sharma | Sanjay Jumar | Completed
119 | 3 | 5/3 | DA+9 | 2025-12-21 | 2025-12-21 | MB Sharma |  | Completed
120 | 4 | 5/4 | DA-1.5 | 2025-12-23 | 2025-12-23 | MB Sharma |  | Completed
121 | 5 | 5/5 | DA+6 | 2025-12-25 | 2025-12-25 | MB Sharma |  | Completed
122 | 6 | 4A/3 | DA+9 | 2025-12-27 | 2025-12-27 | MB Sharma |  | Completed
123 | 7 | 4A/2 | DA+6 | 2025-12-28 | 2025-12-28 | MB Sharma |  | Completed
124 | 8 | 4A/1 | DA+6 | 2025-12-29 | 2025-12-29 | MB Sharma |  | Completed
125 | 9 | 4A/4 | DA+6 | 2025-12-30 | 2025-12-30 | MB Sharma |  | Completed
126 | 10 | 4A/5 | DA+9 | 2025-12-31 | 2025-12-31 | MB Sharma |  | Completed
127 | 1 | 4A/6 | DA+9 | 2026-01-01 | 2026-01-01 | MB Sharma |  | Completed
128 | 2 | 31/7 | DA+0 | 2026-01-02 | 2026-01-02 | MB Sharma |  | Completed
129 | 3 | 31/8 | DA+0 | 2026-01-03 | 2026-01-03 | MB Sharma |  | Completed
130 | 4 | 31/10 | DA+4.5 | 2026-01-04 | 2026-01-04 | MB Sharma |  | Completed
131 | 5 | 31/9 | DA+1.5 | 2026-01-05 | 2026-01-05 | MB Sharma |  | Completed
132 | 6 | 31/6 | DA+9 | 2026-01-07 | 2026-01-07 | MB Sharma |  | Completed
133 | 7 | 31/5 | DA+6 | 2026-01-08 | 2026-01-08 | MB Sharma |  | Completed
134 | 8 | 31/4 | DA-1.5 | 2026-01-09 | 2026-01-09 | MB Sharma |  | Completed
135 | 9 | 31/3 | DA+3 | 2026-01-10 | 2026-01-10 | MB Sharma |  | Completed
136 | 10 | 31/2 | DA+1.5 | 2026-01-11 | 2026-01-11 | MB Sharma |  | Completed
137 | 11 | 31/1 | DA+3 | 2026-01-12 | 2026-01-12 | MB Sharma |  | Completed
138 | 12 | 31/0 | DB1+0 | 2026-01-13 | 2026-01-14 | MB Sharma |  | Completed
139 | 13 | 33/3 | DA+3 | 2026-01-19 | 2026-01-20 | MB Sharma |  | Completed
140 | 14 | 33/2 | DA+9 | 2026-01-20 | 2026-01-21 | MB Sharma |  | Completed
141 | 15 | 33/7 | DA+6 | 2026-01-22 | 2026-01-22 | MB Sharma |  | Completed
142 | 1 | 1/0 | DD60+0 | 2026-02-01 | 2026-02-01 | MB Sharma |  | Completed | Not completed
143 | 2 | 2A/0 | DD45+0 | 2026-02-02 | 2026-02-02 | MB Sharma |  | Completed | Not completed
144 | 3 | 2A/1 | DA+0 | 2026-02-03 | 2026-02-03 | MB Sharma |  | Completed | Not completed
145 | 4 | 2A/2 | DA+3 | 2026-02-03 | 2026-02-03 | MB Sharma |  | Completed | Not completed
146 | 5 | 2A/3 | DA+3 | 2026-02-04 | 2026-02-04 | MB Sharma |  | Completed | Not completed
147 | 6 | 2A/4 | DA+3 | 2026-02-04 | 2026-02-04 | MB Sharma |  | Completed | Not completed
148 | 7 | 2A/5 | DA+3 | 2026-02-05 | 2026-02-05 | MB Sharma |  | Completed | Not completed
149 | 8 | 2A/6 | DA+6 | 2026-02-06 | 2026-02-06 | MB Sharma |  | Completed | Not completed
150 | 9 | 3A/1 | DA+3 | 2026-02-07 | 2026-02-07 | MB Sharma |  | Completed | Not completed
151 | 10 | 3A/2 | DA+3 | 2026-02-08 | 2026-02-08 | MB Sharma |  | Completed | Not completed
152 | 11 | 3A/3 | DA+0 | 2026-02-09 | 2026-02-09 | MB Sharma |  | Completed
153 | 12 | 3A/4 | DA+0 | 2026-02-10 | 2026-02-10 | MB Sharma |  | Completed
154 | 13 | 3A/5 | DA+3 | 2026-02-11 | 2026-02-11 | MB Sharma |  | Completed
155 | 14 | 3A/6 | DA+0 | 2026-02-12 | 2026-02-12 | MB Sharma |  | Completed
156 | 15 | 3B/0 | DB1+9 | 2026-02-13 | 2026-02-13 | MB Sharma |  | Completed | Not completed
157 | 16 | 3B/1 | DA+3 | 2026-02-14 | 2026-02-14 | MB Sharma |  | Completed
158 | 17 | 3B/2 | DA+9 | 2026-02-15 | 2026-02-15 | MB Sharma |  | Completed
159 | 18 | 3B/3 | DA+6 | 2026-02-16 | 2026-02-16 | MB Sharma |  | Completed
160 | 19 | 4/0 | DB2+9 | 2026-02-17 | 2026-02-17 | MB Sharma |  | Completed | Not completed
161 | 20 | 4/1 | DA+6 | 2026-02-18 | 2026-02-18 | MB Sharma |  | Completed | Not completed
162 | 21 | 4A/0 | DB1+3 | 2026-02-19 | 2026-02-19 | MB Sharma |  | Completed | Not completed
163 | 22 | 5/0 | DB1+6 | 2026-02-20 | 2026-02-20 | MB Sharma |  | Completed | Not completed
164 | 23 | 5/8 | DA+6 | 2026-02-21 | 2026-02-21 | MB Sharma |  | Completed
165 | 24 | 5/9 | DA+6 | 2026-02-22 | 2026-02-22 | MB Sharma |  | Completed
166 | 25 | 5A/0 | DB1+12 | 2026-02-23 | 2026-02-23 | MB Sharma |  | Completed
167 | 26 | 7/4 | DA+6 | 2026-02-24 | 2026-02-24 | MB Sharma |  | Completed
168 | 27 | 9/0 | DB1+12 | 2026-02-25 | 2026-02-25 | MB Sharma |  | Completed
169 | 28 | 15/4 | DA+6 | 2026-02-26 | 2026-02-26 | MB Sharma |  | Completed
170 | 29 | 27/0 | DD60+35 | 2026-02-27 | 2026-02-27 | MB Sharma |  | Completed | Not completed
171 | 30 | 29/1 | DA+6 | 2026-02-28 | 2026-02-28 | MB Sharma |  | Completed
172 | 1 | 30/0 | DB1+0 | 2026-03-01 | 2026-03-01 | MB Sharma |  | Completed
173 | 2 | 30/2 | DA+9 | 2026-03-02 | 2026-03-02 | MB Sharma |  | Completed | Not completed
174 | 3 | 30/3 | DA+3 | 2026-03-05 | 2026-03-05 | MB Sharma |  | Completed
175 | 4 | 30/4 | DA+9 | 2026-03-05 | 2026-03-05 | MB Sharma |  | Completed | Not completed
176 | 5 | 30/5 | DA+0 | 2026-03-05 | 2026-03-05 | MB Sharma |  | Completed | Not completed
177 | 6 | 30/6 | DA+6 | 2026-03-06 | 2026-03-06 | MB Sharma |  | Completed | Not completed
178 | 7 | 30/7 | DA-3 | 2026-03-06 | 2026-03-06 | MB Sharma |  | Completed | Not completed
179 | 8 | 30/8 | DA+3 | 2026-03-07 | 2026-03-07 | MB Sharma |  | Completed | Not completed
180 | 9 | 30/9 | DA-3 | 2026-03-07 | 2026-03-07 | MB Sharma |  | Completed | Not completed
181 | 10 | 30/10 | DA+3 | 2026-03-08 | 2026-03-08 | MB Sharma |  | Completed | Not completed
182 | 11 | 32/1 | DA+6 | 2026-03-08 | 2026-03-08 | MB Sharma |  | Completed
183 | 12 | 32/2 | DA+9 | 2026-03-09 | 2026-03-09 | MB Sharma |  | Completed
184 | 13 | 32A/1 | DA+6 | 2026-03-09 | 2026-03-09 | MB Sharma |  | Completed
185 | 14 | 33/0 | DB1+9 | 2026-03-10 | 2026-03-10 | MB Sharma |  | Completed
186 | 15 | 33/1 | DA+9 | 2026-03-10 | 2026-03-10 | MB Sharma |  | Completed
187 | 16 | 33/4 | DA+3 | 2026-03-11 | 2026-03-11 | MB Sharma |  | Completed
188 | 17 | 33/9 | DA+1.5 | 2026-03-11 | 2026-03-11 | MB Sharma |  | Completed
189 | 18 | 35/4 | DA+9 | 2026-03-12 | 2026-03-12 | MB Sharma |  | Completed
190 | 19 | 35/6 | DA+6 | 2026-03-12 | 2026-03-12 | MB Sharma |  | Completed
191 | 20 | 35/9 | DA+1.5 | 2026-03-13 | 2026-03-13 | MB Sharma |  | Completed
192 | 21 | 36A/0 | DB1+9 | 2026-03-13 | 2026-03-13 | MB Sharma |  | Completed
193 | 22 | 36A/1 | DA+3 | 2026-03-14 | 2026-03-14 | MB Sharma |  | Completed
194 | 23 | 37/5 | DA+3 | 2026-03-14 | 2026-03-14 | MB Sharma |  | Completed
195 | 24 | 40/0 | DB1+6 | 2026-03-15 | 2026-03-15 | MB Sharma |  | Completed
196 | 25 | 45/0 | DB1+9 | 2026-03-15 | 2026-03-15 | MB Sharma |  | Completed
197 | 26 | 9/5 | DA+3 | 2026-03-16 | 2026-03-16 | MB Sharma |  | Completed | Not completed
198 | 27 | 9/6 | DA+3 | 2026-03-16 | 2026-03-16 | MB Sharma |  | Completed | Not completed
199 | 28 | 9/7 | DA+9 | 2026-03-17 | 2026-03-17 | MB Sharma |  | Completed | Not completed
200 | 29 | 10/0 | DB1+6 | 2026-03-17 | 2026-03-17 | MB Sharma |  | Completed | Not completed
201 | 30 | 9/11 | DA+3 | 2026-03-18 | 2026-03-18 | MB Sharma |  | Completed | Not completed
202 | 31 | 11/0 | DD45+0 | 2026-03-18 | 2026-03-18 | MB Sharma |  | Completed | Not completed
203 | 32 | 12/0 | DB1+9 | 2026-03-19 | 2026-03-19 | MB Sharma |  | Completed | Not completed
204 | 33 | 13A/0 | DB1+9 | 2026-03-19 | 2026-03-19 | MB Sharma |  | Completed | Not completed
205 | 34 | 14/0 | DD60+18 | 2026-03-20 | 2026-03-20 | MB Sharma |  | Completed | Not completed
206 | 35 | 5/6 | DA+3 | 2026-03-20 | 2026-03-20 | MB Sharma |  | Completed | Not completed
207 | 36 | 3A/0 | DD45+3 | 2026-03-21 | 2026-03-21 | MB Sharma |  | Completed | Not completed
208 | 37 | 9/8 | DA+0 | 22-3-2026 | 22-3-2026 | MB Sharma |  | Completed
209 | 38 | 9/9 | DA+0 | 2026-03-23 | 2026-03-23 | MB Sharma |  | Completed
210 | 39 | 9/10 | DA+3 | 2026-03-24 | 2026-03-24 | MB Sharma |  | Completed
211 | 40 | 5/7 | DA+9 | 2026-03-25 | 2026-03-25 | MB Sharma |  | Completed
212 | 1 | 29A/5 | DA+6 | 2026-03-31 | 2026-04-01 | MB Sharma |  | Completed
213 | 2 | 29A/4 | DA+3 | 2026-04-02 | 2026-04-03 | MB Sharma |  | Completed
214 | 3 | 29A/3 | DA+6 | 2026-04-04 | 2026-04-05 | MB Sharma |  | Completed
215 | 4 | 29A/0 | DB1+0 | 2026-04-06 | 2026-04-07 | MB Sharma |  | Completed
216 | 5 | 23/0 | DB2+9 | 2026-04-08 | 2026-04-09 | MB Sharma |  | Completed
217 | 6 | 29/2 | DA+0 | 2026-04-10 | 2026-04-10 | MB Sharma |  | Completed
218 | 7 | 23A/0 | DB1+9 | 2026-04-11 | 2026-04-12 | MB Sharma |  | Completed
219 | 8 | 10/1 | DA+3 | 2026-04-13 | 2026-04-13 | MB Sharma |  | Completed
220 | 9 | 10/2 | DA+3 | 2026-04-14 | 2026-04-14 | MB Sharma |  | Completed
221 | 10 | 29/0 | DC1+0 | 2026-04-14 | 2026-04-14 | MB Sharma |  | Completed
222 | 11 | 15/7 | DA+0 | 2026-04-29 | 2026-04-29 | M.S Enterprises |  | Completed
223 | 12 | 15/8 | DA+1.5 | 2026-04-30 | 2026-04-30 | M.S Enterprises |  | Completed
224 | 13 | 15/9 | DA+0 | 2026-04-30 | 2026-04-30 | M.S Enterprises |  | Completed
225 | 1 | 15/10 | DA-1.5 | 2026-04-30 | 2026-05-02 | M.S Enterprises |  | Completed
226 | 2 | 15/12 | DA+6 | 2026-05-02 | 2026-05-03 | M.S Enterprises |  | Completed
227 | 3 | 17/0 | DC1+3 | 2026-05-04 | 2026-05-04 | M.S Enterprises |  | Completed
228 | 4 | 18/0 | DB2+6 | 2026-05-05 | 2026-05-05 | M.S Enterprises |  | Completed
229 | 5 | 18/1 | DA+3 | 2026-05-06 | 2026-05-06 | M.S Enterprises |  | Completed
230 | 6 | 18/2 | DA+1.5 | 2026-05-06 | 2026-05-06 | M.S Enterprises |  | Completed
231 | 7 | 18/3 | DA+6 | 2026-05-07 | 2026-05-07 | M.S Enterprises |  | Completed
232 | 8 | 18/4 | DA-3 | 2026-05-07 | 2026-05-07 | M.S Enterprises |  | Completed
233 | 9 | 18/5 | DA+0 | 2026-05-08 | 2026-05-08 | M.S Enterprises |  | Completed
234 | 10 | 18/7 | DA+1.5 | 2026-05-09 | 2026-05-09 | M.S Enterprises |  | Completed
235 | 11 | 19/0 | DD60+3 | 2026-05-09 | 2026-05-09 | M.S Enterprises |  | Completed
236 | 12 | 27/6 | DA-3 | 2026-05-10 | 2026-05-10 | M.S Enterprises |  | Completed
237 | 13 | 27/5 | DA-1.5 | 2026-05-10 | 2026-05-10 | M.S Enterprises |  | Completed
238 | 14 | 27/3 | DA+1.5 | 2026-05-11 | 2026-05-11 | M.S Enterprises |  | Completed
239 | 15 | 27/1 | DA+9 | 2026-05-12 | 2026-05-12 | M.S Enterprises |  | Completed
240 | 16 | 27/2 | DA-1.5 | 2026-05-12 | 2026-05-12 | M.S Enterprises |  | Completed
241 | 17 | 27/4 | DA+1.5 | 2026-05-13 | 2026-05-14 | M.S Enterprises |  | Completed
242 | 18 | 24/0 | DD60+18 | 2026-05-15 | 2026-05-15 | M.S Enterprises |  | Completed
243 | 19 | 20/0 | DD60+3 | 2026-05-16 | 2026-05-16 | M.S Enterprises |  | Completed
244 | 20 | 18/6 | DA+9 | 2026-05-17 | 2026-05-17 | M.S Enterprises |  | Completed
245 | 21 | 15/0 | DD60+25 | 2026-05-18 | 2026-05-18 | M.S Enterprises |  | Completed
246 | 22 | 15/1 | DA+6 | 2026-05-19 | 2026-05-19 | M.S Enterprises |  | Completed
247 | 23 | 20/1 | DA-3 | 2026-05-19 | 2026-05-19 | M.S Enterprises |  | Completed
248 | 23 | 20/2 | DA-3 | 2026-05-20 | 2026-05-20 | M.S Enterprises |  | Completed
249 | 24 | 20/3 | DA+1.5 | 2026-05-20 | 2026-05-20 | M.S Enterprises |  | Completed
250 | 25 | 38/7 | DA+9 | 2026-05-21 | 2026-05-21 | M.S Enterprises |  | Completed
251 | 26 | 15/11 | DA+0 | 2026-05-22 | 2026-05-22 | M.S Enterprises |  | Completed
252 | 27 | 21/1 | DA+0 | 2026-05-23 | 2026-05-23 | M.S Enterprises |  | Completed
253 | 28 | 21/2 | DA+6 | 2026-05-23 | 2026-05-23 | M.S Enterprises |  | Completed
254 | 29 | 21/3 | DA+6 | 2026-05-24 | 2026-05-24 | M.S Enterprises |  | Completed
255 | 30 | 21/4 | DA+0 | 2026-05-25 | 2026-05-25 | M.S Enterprises |  | Completed
256 | 31 | 21/5 | DA+0 | 2026-05-25 | 2026-05-25 | M.S Enterprises |  | Completed
257 | 1 | 28/0 | DC2-3 | 2026-06-02 | 2026-06-03 | M.S Enterprises |  | Completed
258 | 2 | 35/2 | DA+6 | 2026-06-04 | 2026-06-05 | M.S Enterprises |  | Completed
259 | 3 | 35/3 | DA-3 | 2026-06-06 | 2026-06-06 | M.S Enterprises |  | Completed
260 | 4 | 35/10 | DA+3 | 2026-06-07 | 2026-06-07 | M.S Enterprises |  | Completed
261 | 5 | 35/11 | DA+3 | 2026-06-08 | 2026-06-08 | M.S Enterprises |  | Completed
262 | 6 | 36/0 | DB2+3 | 2026-06-09 | 2026-06-09 | M.S Enterprises |  | Completed
263 | 7 | 37/3 | DA-1.5 | 2026-06-10 | 2026-06-10 | M.S Enterprises |  | Completed
264 | 8 | 37/4 | DA+9 | 2026-06-12 | 2026-06-12 | M.S Enterprises |  | Completed
265 | 9 | 44/2 | DA+3 | 2026-06-13 | 2026-06-13 | M.S Enterprises |  | Completed
266 | 10 | 26/0 | DD60+35 | 2026-06-14 | 2026-06-14 | M.S Enterprises |  | Completed
267 | 11 | 22/0 | DC2+15 | 2026-06-15 | 2026-06-15 | MB Sharma |  | Completed
268 | 12 | 21/0 | DB1+0 | 2026-06-17 | 2026-06-17 | MB Sharma |  | Completed
269 | 13 | 25/0 | DD60+18 | 2026-06-18 | 2026-06-20 | M.S Enterprises |  | Completed
270 | 14 | 16/0 | DC2+0 | 2026-06-27 | 2026-06-27 | M.S Enterprises |  | Completed
271 | 15 | 40/1 | DA+9 | 2026-06-29 | 2026-06-29 | M.S Enterprises |  | Completed
272 | 16 | 40/7 | DA+3 | 2026-06-30 | 2026-06-30 | M.S Enterprises |  | Completed
273 | 17 | 40/9 | DA+9 | 2026-07-01 | 2026-07-01 | M.S Enterprises |  | Completed
274 | 18 | 40/10 | DA+3 | 2026-07-01 | 2026-07-01 | M.S Enterprises |  | Completed
275 | 19 | 40/8 | DA-1.5 | 2026-07-10 | 2026-07-11 | M.S Enterprises |  | Completed
276 | 20 | 40/11 | DA+9 | 2026-07-12 | 2026-07-13 | M.S Enterprises |  | Completed
277 | 21 | 20/5 | DA+0 | 2026-07-14 | 2026-07-15 | MB Sharma |  | Completed
278 | 22 | 20/6 | DA-3 | 2026-07-16 | 2026-07-17 | MB Sharma |  | Completed
279 | 23 | 13/0 | DD60+9 | 2026-07-18 | 2026-07-19 | MB Sharma |  | Completed
280 | 24 | 20/4 | DA+3 | 2026-07-24 | 2026-07-24 | MB Sharma |  | Completed
Formulas:
Start = [Start, row above]
Start = [Complete, row above]+1
Complete = [Start]
Complete = [Start]+1

## Final checking
Client Name : PowerGrid Bikaner Neemrana Transmission Limited (Power Grid Corporation of India)
765 kV DC BIKANER-III NEEMRANA-II Transmission Line TA-413 | [11 empty] | 7
|  |  | Bal |  | 0 | 2 | 3 | 23 | 16 | 70
S. No. | No of | Location | Type of | DS Status as on | 306 | 304 | 303 | 280 | 287 | 232 | Remarks
| AP | Tower No. | Tower |  | Foundation | Earthing | Tower Erection | Tack welding | Final Checking | Stringing
|  | Gantry | Gantry
1 | AP-1 | 1/0 | DD60+0 | Approved | Completed | Completed | Completed | Done | Done | Done
2 | AP-2A | 2A/0 | DD45+0 | Approved | Completed | Completed | Completed | Done | Done | Done
3 | AP-3 | 2A/1 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
4 |  | 2A/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
5 |  | 2A/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
6 |  | 2A/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
7 |  | 2A/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
8 |  | 2A/6 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
9 |  | 3A/0 | DD45+3 | Approved | Completed | Completed | Completed | Done | Done | Done
10 |  | 3A/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
11 |  | 3A/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
12 |  | 3A/3 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
13 |  | 3A/4 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
14 |  | 3A/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
15 | AP-4 | 3A/6 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
16 |  | 3B/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
17 |  | 3B/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
18 |  | 3B/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
19 |  | 3B/3 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
20 |  | 4/0 | DB2+9 | Approved | Completed | Completed | Completed | Done | Done | Done
21 |  | 4/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
22 | AP- 4A/0 | 4A/0 | DB1+3 | Approved | Completed | Completed | Completed | Done | Done | Done
23 |  | 4A/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
24 |  | 4A/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
25 |  | 4A/3 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
26 |  | 4A/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
27 |  | 4A/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
28 |  | 4A/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
29 | AP5 | 5/0 | DB1+6 | Approved | Completed | Completed | Completed | Done | Done | Done
30 |  | 5/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
31 |  | 5/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
32 |  | 5/3 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
33 |  | 5/4 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
34 |  | 5/5 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
35 |  | 5/6 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
36 |  | 5/7 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
37 |  | 5/8 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
38 |  | 5/9 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
39 |  | 5/10 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
40 | AP-5A | 5A/0 | DB1+12 | Approved | Completed | Completed | Completed | Done | Done | Done
41 | AP-6 | 6/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
42 |  | 6/1 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
43 |  | 6/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
44 |  | 6/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
45 |  | 6/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
46 |  | 6/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
47 |  | 6/6 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
48 |  | 6/7 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
49 |  | 6/8 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
50 |  | 6/9 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
51 |  | 6/10 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
52 |  | 6/11 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
53 |  | 6/12 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
54 | AP-7 | 7/0 | DB2+0 | Approved | Completed | Completed | Completed | Done | Done | Done
55 |  | 7/1 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
56 |  | 7/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
57 |  | 7/3 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
58 |  | 7/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
59 |  | 7/5 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
60 |  | 7/6 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
61 | AP-7A | 7A/0 | DB1+6 | Approved | Completed | Completed | Completed | Done | Done | Done
62 |  | 7A/1 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
63 |  | 7A/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
64 |  | 7A/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
65 |  | 7A/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
66 |  | 7A/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
67 | AP-8 | 8/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
68 |  | 8/1 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
69 |  | 8/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
70 |  | 8/3 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
71 |  | 8/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
72 |  | 8/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
73 |  | 8/6 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
74 |  | 8/7 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
75 |  | 8/8 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
76 |  | 8/9 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
77 |  | 8/10 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
78 |  | 8/11 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
79 | AP-8A | 8A/0 | DB1+12 | Approved | Completed | Completed | Completed | Done | Done | Done
80 | AP-9 | 9/0 | DB1+12 | Approved | Completed | Completed | Completed | Done | Done | Done
81 |  | 9/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
82 |  | 9/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
83 |  | 9/3 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
84 |  | 9/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
85 |  | 9/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
86 |  | 9/6 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
87 |  | 9/7 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
88 |  | 9/8 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
89 |  | 9/9 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
90 |  | 9/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
91 |  | 9/11 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
92 | AP-10 | 10/0 | DB1+6 | Approved | Completed | Completed | Completed | Done | Done | Done
93 |  | 10/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
94 |  | 10/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
95 | AP-11 | 11/0 | DD45+0 | Approved | Completed | Completed | Completed | Done | Done | Done
96 | AP-12 | 12/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
97 | AP-13 | 13/0 | DD60+9 | Approved | Completed | Completed | Completed | Done | Done | Done
98 | AP-13A | 13A/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
99 | AP-14 | 14/0 | DD60+18 | Approved | Completed | Completed | Completed | Done | Done | Done
100 | AP-15 | 15/0 | DD60+25 | Approved | Completed | Completed | Completed | Done | Done | WIP
101 |  | 15/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | WIP
102 |  | 15/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done
103 |  | 15/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | WIP
104 |  | 15/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | WIP
105 |  | 15/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | WIP
106 |  | 15/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
107 |  | 15/7 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | WIP
108 |  | 15/8 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | WIP
109 |  | 15/9 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | WIP
110 |  | 15/10 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | WIP
111 |  | 15/11 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | WIP
112 |  | 15/12 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | WIP
113 | AP-16 | 16/0 | DC2+0 | Approved | Completed | Completed | Completed | Done | Done
114 | AP-17 | 17/0 | DC1+3 | Approved | Completed | Completed | Completed | Done | Done
115 | AP-18 | 18/0 | DB2+6 | Approved | Completed | Completed | Completed | Done | Done | Done
116 |  | 18/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
117 |  | 18/2 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
118 |  | 18/3 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
119 |  | 18/4 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
120 |  | 18/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
121 |  | 18/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
122 |  | 18/7 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
123 | AP-19 | 19/0 | DD60+3 | Approved | Completed | Completed | Completed | Done | Done | Done
124 | AP-20 | 20/0 | DD60+3 | Approved | Completed | Completed | Completed | Done | Done
125 |  | 20/1 | DA-3 | Approved | Completed | Completed | Completed | Done | Done
126 |  | 20/2 | DA-3 | Approved | Completed | Completed | Completed | Done | Done
127 |  | 20/3 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done
128 |  | 20/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done
129 |  | 20/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done
130 |  | 20/6 | DA-3 | Approved | Completed | Completed | Completed | Done | Done
131 | AP-21 | 21/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done
132 |  | 21/1 | DA+0 | Approved | Completed | Completed | Completed | Done | Done
133 |  | 21/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done
134 |  | 21/3 | DA+6 | Approved | Completed | Completed | Completed | Done | Done
135 |  | 21/4 | DA+0 | Approved | Completed | Completed | Completed | Done | Done
136 |  | 21/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done
137 | AP-22 | 22/0 | DC2+15 | Approved | Completed | Completed | Completed | Done | Done
138 | AP-23 | 23/0 | DB2+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
139 | AP-23A | 23A/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
140 | AP-24 | 24/0 | DD60+18 | Approved | Completed | Completed | Completed | Done | Done | Done
141 | AP-25 | 25/0 | DD60+18 | Approved | Completed | Completed | Completed | Done | Done | Done
142 | AP-26 | 26/0 | DD60+35 | Approved | Completed | Completed | Completed | Done | Done | Done
143 | AP-27 | 27/0 | DD60+35 | Approved | Completed | Completed | Completed | Done | Done | Done
144 |  | 27/1 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
145 |  | 27/2 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
146 |  | 27/3 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
147 |  | 27/4 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
148 |  | 27/5 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
149 |  | 27/6 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
150 | AP-28 | 28/0 | DC2-3 | Approved | Completed | Completed | Completed | Done | Done | Done
151 | AP-29 | 29/0 | DC1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
152 |  | 29/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
153 |  | 29/2 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
154 |  | 29/3 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
155 |  | 29/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
156 |  | 29/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
157 | AP-29A/0 | 29A/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
158 |  | 29A/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
159 |  | 29A/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
160 |  | 29A/3 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
161 |  | 29A/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
162 |  | 29A/5 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
163 |  | 29A/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
164 | AP-30 | 30/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
165 |  | 30/1 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
166 |  | 30/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
167 |  | 30/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
168 |  | 30/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
169 |  | 30/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
170 |  | 30/6 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
171 |  | 30/7 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
172 |  | 30/8 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
173 |  | 30/9 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
174 |  | 30/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
175 | AP-31 | 31/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
176 |  | 31/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
177 |  | 31/2 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
178 |  | 31/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
179 |  | 31/4 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
180 |  | 31/5 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
181 |  | 31/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
182 |  | 31/7 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
183 |  | 31/8 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
184 |  | 31/9 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
185 |  | 31/10 | DA+4.5 | Approved | Completed | Completed | Completed | Done | Done | Done
186 | AP-32 | 32/0 | DB2+0 | Approved | Completed | Completed | Completed | Done | Done | Done
187 |  | 32/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
188 |  | 32/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
189 |  | 32/3 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
190 |  | 32/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
191 |  | 32/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
192 |  | 32/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
193 |  | 32/7 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
194 | AP-32A/0 | 32A/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
195 |  | 32A/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
196 | AP-33 | 33/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | Done | Done
197 |  | 33/1 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
198 |  | 33/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
199 |  | 33/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
200 |  | 33/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
201 |  | 33/5 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
202 |  | 33/6 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
203 |  | 33/7 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
204 |  | 33/8 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
205 |  | 33/9 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
206 | AP-34 | 34/0 | DB1+6 | Approved | Completed | Completed | Completed | Done | Done | Done
207 |  | 34/1 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
208 |  | 34/2 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
209 |  | 34/3 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
210 |  | 34/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
211 |  | 34/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
212 |  | 34/6 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
213 |  | 34/7 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
214 |  | 34/8 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
215 |  | 34/9 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
216 |  | 34/10 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
217 |  | 34/11 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
218 |  | 34/12 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
219 | AP-35 | 35/0 | DB2+0 | Approved | Completed | Completed | Completed | Done | Done | Done
220 |  | 35/1 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
221 |  | 35/2 | DA+6 | Approved | Completed |  | Completed | Done | Done | Done
222 |  | 35/3 | DA-3 | Approved | Completed | Completed | Completed | Done | Done | Done
223 |  | 35/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
224 |  | 35/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
225 |  | 35/6 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
226 |  | 35/7 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
227 |  | 35/8 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
228 |  | 35/9 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
229 |  | 35/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
230 |  | 35/11 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
231 | AP-36 | 36/0 | DB2+3 | Approved | Completed | Completed | Completed | Done | Done | Done
232 |  | 36A/0 | DB1+9 | Approved | Completed |  | Completed | Done | Done
233 |  | 36A/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done
234 |  | 36B/0-N | DB2+9 | Approved | Completed | Completed
235 |  | 36C/0-N | DC2+15 | Approved | Completed | Completed
236 |  | 37/0-N | DB2+9 | Approved | Completed | Completed
237 |  | 37/2 | DA+3 | Approved | Completed | Completed | Completed |  | Done
238 |  | 37/3 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done
239 |  | 37/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done
240 |  | 37/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done
241 | AP-37A | 37A/0 | DB1+0 | Approved | Completed | Completed | Completed | Done | Done | Done
242 |  | 37A/1 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
243 |  | 37A/2 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
244 |  | 37A/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
245 |  | 37A/4 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
246 |  | 37A/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
247 |  | 37A/6 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
248 | AP-38 | 38/0 | DB1+3 | Approved | Completed | Completed | Completed | Done | Done | Done
249 |  | 38/1 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
250 |  | 38/2 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
251 |  | 38/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
252 |  | 38/4 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
253 |  | 38/5 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
254 |  | 38/6 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
255 |  | 38/7 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | Done
256 |  | 38/8 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
257 |  | 38/9 | DA+0 | Approved | Completed | Completed | Completed | Done | Done | Done
258 |  | 38/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
259 | AP-39 | 39/0 | DB2+0 | Approved | Completed | Completed | Completed | Done | Done | Done
260 |  | 39/1 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
261 |  | 39/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
262 |  | 39/3 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
263 |  | 39/4 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
264 |  | 39/5 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
265 |  | 39/6 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
266 |  | 39/7 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
267 |  | 39/8 | DA+1.5 | Approved | Completed | Completed | Completed | Done | Done | Done
268 |  | 39/9 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
269 |  | 39/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | Done
270 |  | 39/11 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | Done
271 | AP-40 | 40/0 | DB1+6 | Approved | Completed | Completed | Completed | Done | Done | Done
272 |  | 40/1 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
273 |  | 40/2 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | WIP
274 |  | 40/3 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | WIP
275 |  | 40/4 | DA+6 | Approved | Completed | Completed | Completed | Done | Done | WIP
276 |  | 40/5 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
277 |  | 40/6 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
278 |  | 40/7 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | WIP
279 |  | 40/8 | DA-1.5 | Approved | Completed | Completed | Completed | Done | Done
280 |  | 40/9 | DA+9 | Approved | Completed | Completed | Completed | Done | Done | WIP
281 |  | 40/10 | DA+3 | Approved | Completed | Completed | Completed | Done | Done | WIP
282 |  | 40/11 | DA+9 | Approved | Completed | Completed | Completed | Done | Done
283 | AP-40A | 40A/0 | DB1+9 | Approved | Completed | Completed | Completed |  | WIP
284 | AP-41 | 41/0 | DB1+9 | Approved | Completed | Completed | Completed |  | ROW
285 |  | 41/1 | DA+9 | Approved | Completed | Completed | Completed |  | ROW
286 | AP-42 | 42/0 | DB2+0 | Approved | Completed | Completed | Completed |  | ROW
287 |  | 42/1 | DA+3 | Approved | Completed | Completed | Completed |  | ROW
288 |  | 42/2 | DA+9 | Approved | Completed | Completed | Completed |  | ROW
289 |  | 42A/0 | DB1+9 | Approved | Completed | Completed | Completed |  | ROW
290 | AP-43 | 43/0 | DB1+0 | Approved | Completed | Completed | Completed |  | ROW
291 |  | 43/1 | DA-1.5 | Approved | Completed | Completed | Completed |  | Done
292 |  | 43/2 | DA+6 | Approved | Completed | Completed | Completed |  | WIP
293 |  | 43/3 | DA-1.5 | Approved | Completed | Completed | Completed |  | WIP
294 |  | 43/4 | DA+0 | Approved | Completed | Completed | Completed |  | ROW
295 |  | 43A/0 | DC2+0 | Approved | Completed | Completed | Completed |  | ROW
296 |  | 43/6 | DA+3 | Approved | Completed | Completed | Completed |  | Done
297 |  | 43/7 | DA+0 | Approved | Completed | Completed | Completed |  | Done
298 |  | 43/8 | DA+9 | Approved | Completed | Completed | Completed |  | ROW
299 | AP-44 | 44/0 | DB1+6 | Approved | Completed | Completed | Completed |  | ROW
300 |  | 44/1 | DA+3 | Approved | Completed | Completed | Completed |  | Done
301 |  | 44/2 | DA+3 | Approved | Completed | Completed | Completed | Done | Done
302 |  | 44/3 | DA+3 | Approved | Completed | Completed | Completed |  | ROW
303 |  | 44/4 | DA+0 | Approved | Completed | Completed | Completed |  | Done
304 |  | 44/5 | DA+0 | Approved | Completed | Completed | Completed |  | Done
305 | AP45 | 45/0 | DB1+9 | Approved | Completed | Completed | Completed | Done | ROW |  | PLC
306 | AP46 | 46/0 | DB1+12 | Approved | Completed | Completed | Completed |  | Done |  | PLC
Note on D105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18

## Bird Guard
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Bird Guard (Set Of Three) | [7 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Completion date | Bird Guard | Name of the Contractor | Name of Supervisor | Remarks
1 | 1 | 2A/1 | DA+0 | 2026-05-15 | DONE | Jetha Ram | Sanjay Kumar
2 | 2 | 2A/2 | DA+3 | 2026-05-15 | DONE | Jetha Ram | Sanjay Kumar
3 | 3 | 2A/3 | DA+3 | 2026-05-16 | DONE | Jetha Ram | Sanjay Kumar
4 | 4 | 2A/4 | DA+3 | 2026-05-16 | DONE | Jetha Ram | Sanjay Kumar
5 | 5 | 2A/5 | DA+3 | 2026-05-17 | DONE | Jetha Ram | Sanjay Kumar
6 | 6 | 2A/6 | DA+6 | 2026-05-17 | DONE | Jetha Ram | Sanjay Kumar
7 | 7 | 3A/1 | DA+3 | 2026-05-17 | DONE | Jetha Ram | Sanjay Kumar
8 | 8 | 30/1 | DA+0 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
9 | 9 | 30/2 | DA+9 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
10 | 10 | 30/3 | DA+3 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
11 | 11 | 30/4 | DA+9 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
12 | 12 | 30/5 | DA+0 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
13 | 13 | 30/6 | DA+6 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
14 | 14 | 30/7 | DA-3 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
15 | 15 | 30/8 | DA+3 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
16 | 16 | 30/9 | DA-3 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
17 | 17 | 30/10 | DA+3 | 2026-05-19 | DONE | Mahendra Banjara | Sanjay Kumar
18 | 18 | 31/1 | DA+3 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
19 | 19 | 31/2 | DA+1.5 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
20 | 20 | 31/3 | DA+3 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
21 | 21 | 31/4 | DA-1.5 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
22 | 22 | 31/5 | DA+6 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
23 | 23 | 31/6 | DA+9 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
24 | 24 | 31/7 | DA+0 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
25 | 25 | 31/8 | DA+0 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
26 | 26 | 31/9 | DA+1.5 | 2026-05-20 | DONE | Mahendra Banjara | Sanjay Kumar
27 | 27 | 31/10 | DA+4.5 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
28 | 28 | 32/1 | DA+6 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
29 | 29 | 32/2 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
30 | 30 | 32/3 | DA+6 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
31 | 31 | 32/4 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
32 | 32 | 32/5 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
33 | 33 | 32/6 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
34 | 34 | 32/7 | DA+3 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
35 | 35 | 32A/1 | DA+6 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
36 | 36 | 33/1 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
37 | 37 | 33/2 | DA+9 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
38 | 38 | 33/3 | DA+3 | 2026-05-21 | DONE | Mahendra Banjara | Sanjay Kumar
39 | 39 | 9/3 | DA+0 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
40 | 40 | 9/4 | DA+6 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
41 | 41 | 9/5 | DA+3 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
42 | 42 | 9/6 | DA+3 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
43 | 43 | 9/7 | DA+9 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
44 | 44 | 9/8 | DA+0 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
45 | 45 | 9/9 | DA+0 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
46 | 46 | 9/10 | DA+3 | 2026-05-21 | DONE | Jetha Ram | Sanjay Kumar
47 | 47 | 9/2 | DA+3 | 2026-05-22 | DONE | Jetha Ram | Sanjay Kumar
48 | 48 | 9/1 | DA+3 | 2026-05-22 | DONE | Jetha Ram | Sanjay Kumar
49 | 49 | 8/11 | DA+9 | 2026-05-22 | DONE | Jetha Ram | Sanjay Kumar
50 | 50 | 33/4 | DA+3 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
51 | 51 | 33/5 | DA+0 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
52 | 52 | 33/6 | DA+6 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
53 | 53 | 33/7 | DA+6 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
54 | 54 | 33/8 | DA+3 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
55 | 55 | 33/9 | DA+1.5 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
56 | 56 | 34/1 | DA+9 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
57 | 57 | 34/2 | DA+9 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
58 | 58 | 34/3 | DA+1.5 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
59 | 59 | 34/4 | DA+6 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
60 | 60 | 34/5 | DA+9 | 2026-05-22 | DONE | Mahendra Banjara | Sanjay Kumar
61 | 61 | 34/6 | DA+3 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
62 | 62 | 34/7 | DA+0 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
63 | 63 | 34/8 | DA+0 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
64 | 64 | 34/9 | DA+1.5 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
65 | 65 | 34/10 | DA-3 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
66 | 66 | 34/11 | DA+1.5 | 2026-05-23 | DONE | Mahendra Banjara | Sanjay Kumar
67 | 67 | 39/4 | DA+3 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
68 | 68 | 39/5 | DA+1.5 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
69 | 69 | 39/6 | DA+1.5 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
70 | 70 | 39/7 | DA+3 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
71 | 71 | 39/8 | DA+1.5 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
72 | 72 | 39/9 | DA+6 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
73 | 73 | 39/10 | DA+3 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
74 | 74 | 39/11 | DA+6 | 2026-05-24 | DONE | Mahendra Banjara | Sanjay Kumar
75 | 75 | 38/5 | DA+3 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
76 | 76 | 38/6 | DA+6 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
77 | 77 | 38/7 | DA+9 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
78 | 78 | 38/8 | DA+1.5 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
79 | 79 | 38/9 | DA+0 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
80 | 80 | 38/10 | DA+3 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
81 | 81 | 39/1 | DA-1.5 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
82 | 82 | 39/2 | DA+3 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
83 | 83 | 39/3 | DA+1.5 | 2026-05-25 | DONE | Mahendra Banjara | Sanjay Kumar
84 | 84 | 37A/1 | DA+3 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
85 | 85 | 37A/2 | DA+1.5 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
86 | 86 | 37A/3 | DA+3 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
87 | 87 | 37A/4 | DA+9 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
88 | 88 | 37A/5 | DA+3 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
89 | 89 | 37A/6 | DA+3 | 2026-05-26 | DONE | Mahendra Banjara | Sanjay Kumar
90 | 90 | 3A/2 | DA+3 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
91 | 91 | 3A/3 | DA+0 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
92 | 92 | 3A/4 | DA+0 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
93 | 93 | 3A/5 | DA+3 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
94 | 94 | 3A/6 | DA+0 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
95 | 95 | 3B/1 | DA+3 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
96 | 96 | 3B/2 | DA+9 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
97 | 97 | 3B/3 | DA+6 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
98 | 98 | 4/1 | DA+6 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
99 | 99 | 4A/1 | DA+6 | 2026-05-26 | DONE | Jetha Ram | Sanjay Kumar
100 | 100 | 8/1 | DA-3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
101 | 101 | 8/2 | DA+6 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
102 | 102 | 8/5 | DA+9 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
103 | 103 | 8/6 | DA+3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
104 | 104 | 8/7 | DA+3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
105 | 105 | 8/8 | DA+9 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
106 | 106 | 8/9 | DA+3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
107 | 107 | 8/10 | DA+0 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
108 | 108 | 7A/1 | DA+1.5 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
109 | 109 | 7A/2 | DA+3 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
110 | 110 | 7A/3 | DA+3 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
111 | 111 | 7A/4 | DA+3 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
112 | 112 | 7A/5 | DA+3 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
113 | 113 | 7/1 | DA-3 | 2026-05-30 | DONE | Mahendra Banjara | Sanjay Kumar
114 | 114 | 7/2 | DA+6 | 2026-05-30 | DONE | Mahendra Banjara | Sanjay Kumar
115 | 115 | 7/3 | DA+9 | 2026-05-30 | DONE | Mahendra Banjara | Sanjay Kumar
116 | 116 | 7/5 | DA+6 | 2026-05-30 | DONE | Mahendra Banjara | Sanjay Kumar
117 | 117 | 7/6 | DA-1.5 | 2026-05-30 | DONE | Mahendra Banjara | Sanjay Kumar
118 | 118 | 6/8 | DA+3 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
119 | 119 | 6/7 | DA+1.5 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
120 | 120 | 6/6 | DA-3 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
121 | 1 | 6/1 | DA+9 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
122 | 2 | 6/2 | DA+6 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
123 | 3 | 6/3 | DA+3 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
124 | 4 | 6/4 | DA+9 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
125 | 5 | 6/5 | DA+9 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
126 | 6 | 5/7 | DA+9 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
127 | 7 | 5/8 | DA+6 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
128 | 8 | 5/9 | DA+6 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
129 | 9 | 5/10 | DA+9 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
130 | 10 | 5/6 | DA+3 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
131 | 11 | 5/5 | DA+6 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
132 | 12 | 5/4 | DA-1.5 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
133 | 13 | 5/3 | DA+9 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
134 | 14 | 4A/3 | DA+9 | 2026-07-06 | DONE | Md. Arshad | Sanjay Kumar
135 | 15 | 4A/4 | DA+6 | 2026-07-06 | DONE | Md. Arshad | Sanjay Kumar
136 | 16 | 4A/5 | DA+9 | 2026-07-07 | DONE | Md. Arshad | Sanjay Kumar
137 | 17 | 4A/6 | DA+9 | 2026-07-07 | DONE | Md. Arshad | Sanjay Kumar

## Aviation Paint
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Aviation Paint | [7 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Completion date | Paint | Name of the Contractor | Name of Supervisor | Remarks
1 | 1 | 10/1 | DA+3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
2 | 2 | 10/2 | DA+3 | 2026-05-28 | DONE | Mahendra Banjara | Sanjay Kumar
3 | 3 | 9/4 | DA+6 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
4 | 4 | 9/2 | DA+3 | 2026-05-29 | DONE | Mahendra Banjara | Sanjay Kumar
5 | 5 | 9/11 | DA+3 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
6 | 6 | 9/10 | DA+3 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
7 | 7 | 9/9 | DA+0 | 2026-05-31 | DONE | Mahendra Banjara | Sanjay Kumar
8 | 8 | 10/0 | DB1+6 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
9 | 9 | 9/7 | DA+9 | 2026-06-01 | DONE | Mahendra Banjara | Sanjay Kumar
10 | 10 | 9/1 | DA+3 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
11 | 11 | 9/3 | DA+0 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
12 | 12 | 9/5 | DA+3 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
13 | 13 | 9/6 | DA+3 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
14 | 14 | 9/8 | DA+0 | 2026-06-02 | DONE | Mahendra Banjara | Sanjay Kumar
15 | 15 | 6/5 | DA+9 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
16 | 16 | 6/6 | DA-3 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
17 | 17 | 6/7 | DA+1.5 | 2026-06-03 | DONE | Mahendra Banjara | Sanjay Kumar
18 | 18 | 6/4 | DA+9 | 2026-06-03 | DONE | Bajrang Nath | Sanjay Kumar
19 | 19 | 6/3 | DA+3 | 2026-06-03 | DONE | Bajrang Nath | Sanjay Kumar
20 | 20 | 8A/0 | DB1+12 | 2026-06-04 | DONE | Mahendra Banjara | Sanjay Kumar
21 | 21 | 9/0 | DB1+12 | 2026-06-04 | DONE | Mahendra Banjara | Sanjay Kumar
22 | 22 | 6/8 | DA+3 | 2026-06-04 | DONE | Mahendra Banjara | Sanjay Kumar
23 | 23 | 2A/2 | DA+3 | 2026-06-04 | DONE | Shri Balaji | Sanjay Kumar
24 | 24 | 6/2 | DA+6 | 2026-06-04 | DONE | Bajrang Nath | Sanjay Kumar
25 | 25 | 6/1 | DA+9 | 2026-06-04 | DONE | Bajrang Nath | Sanjay Kumar
26 | 26 | 6/9 | DA+6 | 2026-06-05 | DONE | Mahendra Banjara | Sanjay Kumar
27 | 27 | 8/10 | DA+0 | 2026-06-05 | DONE | Mahendra Banjara | Sanjay Kumar
28 | 28 | 8/11 | DA+9 | 2026-06-05 | DONE | Mahendra Banjara | Sanjay Kumar
29 | 29 | 8/8 | DA+9 | 2026-06-05 | DONE | Mahendra Banjara | Sanjay Kumar
30 | 30 | 6/0 | DB1+9 | 2026-06-05 | DONE | Bajrang Nath | Sanjay Kumar
31 | 31 | 8/6 | DA+3 | 2026-06-06 | DONE | Mahendra Banjara | Sanjay Kumar
32 | 32 | 8/9 | DA+3 | 2026-06-06 | DONE | Mahendra Banjara | Sanjay Kumar
33 | 33 | 8/5 | DA+9 | 2026-06-06 | DONE | Mahendra Banjara | Sanjay Kumar
34 | 34 | 8/7 | DA+3 | 2026-06-06 | DONE | Mahendra Banjara | Sanjay Kumar
35 | 35 | 5/10 | DA+9 | 2026-06-06 | DONE | Bajrang Nath | Sanjay Kumar
36 | 36 | 8/4 | DA+6 | 2026-06-07 | DONE | Mahendra Banjara | Sanjay Kumar
37 | 37 | 1/0 | DD60+0 | 2026-06-07 | DONE | Shri Balaji | Sanjay Kumar
38 | 38 | 5/9 | DA+6 | 2026-06-07 | DONE | Bajrang Nath | Sanjay Kumar
39 | 39 | 5/8 | DA+6 | 2026-06-07 | DONE | Bajrang Nath | Sanjay Kumar
40 | 40 | 5/6 | DA+3 | 2026-06-07 | DONE | Bajrang Nath | Sanjay Kumar
41 | 41 | 5A/0 | DB1+12 | 2026-06-07 | DONE | Bajrang Nath | Sanjay Kumar
42 | 42 | 5/5 | DA+6 | 2026-06-08 | DONE | Bajrang Nath | Sanjay Kumar
43 | 43 | 5/7 | DA+9 | 2026-06-08 | DONE | Bajrang Nath | Sanjay Kumar
44 | 44 | 7/5 | DA+6 | 2026-06-08 | DONE | Mahendra Banjara | Sanjay Kumar
45 | 45 | 7/6 | DA-1.5 | 2026-06-08 | DONE | Mahendra Banjara | Sanjay Kumar
46 | 46 | 7/4 | DA+6 | 2026-06-08 | DONE | Mahendra Banjara | Sanjay Kumar
47 | 47 | 6/10 | DA+1.5 | 2026-06-07 | DONE | Mahendra Banjara | Sanjay Kumar
48 | 48 | 6/11 | DA-1.5 | 2026-06-08 | DONE | Mahendra Banjara | Sanjay Kumar
49 | 49 | 6/12 | DA+1.5 | 2026-06-08 | DONE | Mahendra Banjara | Sanjay Kumar
50 | 50 | 5/4 | DA-1.5 | 2026-06-09 | DONE | Bajrang Nath | Sanjay Kumar
51 | 51 | 5/3 | DA+9 | 2026-06-09 | DONE | Bajrang Nath | Sanjay Kumar
52 | 52 | 5/2 | DA+9 | 2026-06-09 | DONE | Bajrang Nath | Sanjay Kumar
53 | 53 | 11/0 | DD45+0 | 2026-06-09 | DONE | Mahendra Banjara | Sanjay Kumar
54 | 54 | 12/0 | DB1+9 | 2026-06-09 | DONE | Mahendra Banjara | Sanjay Kumar
55 | 55 | 8/1 | DA-3 | 2026-06-10 | DONE | Mahendra Banjara | Sanjay Kumar
56 | 56 | 8/2 | DA+6 | 2026-06-10 | DONE | Mahendra Banjara | Sanjay Kumar
57 | 57 | 8/3 | DA+9 | 2026-06-10 | DONE | Mahendra Banjara | Sanjay Kumar
58 | 58 | 5/1 | DA+6 | 2026-06-10 | DONE | Bajrang Nath | Sanjay Kumar
59 | 59 | 5/0 | DB1+6 | 2026-06-11 | DONE | Bajrang Nath | Sanjay Kumar
60 | 60 | 4A/6 | DA+9 | 2026-06-11 | DONE | Bajrang Nath | Sanjay Kumar
61 | 61 | 4A/5 | DA+9 | 2026-06-12 | DONE | Bajrang Nath | Sanjay Kumar
62 | 62 | 4A/4 | DA+6 | 2026-06-12 | DONE | Bajrang Nath | Sanjay Kumar
63 | 63 | 8/0 | DB1+0 | 2026-06-12 | DONE | Mahendra Banjara | Sanjay Kumar
64 | 64 | 7A/4 | DA+3 | 2026-06-12 | DONE | Mahendra Banjara | Sanjay Kumar
65 | 65 | 3B/3 | DA+6 | 2026-06-12 | DONE | Mahendra Banjara | Sanjay Kumar
66 | 66 | 3B/2 | DA+9 | 2026-06-12 | DONE | Mahendra Banjara | Sanjay Kumar
67 | 67 | 7/3 | DA+9 | 2026-06-14 | DONE | Mahendra Banjara | Pramod
68 | 68 | 7/2 | DA+6 | 2026-06-14 | DONE | Mahendra Banjara | Pramod
69 | 69 | 7/1 | DA-3 | 2026-06-14 | DONE | Mahendra Banjara | Pramod
70 | 70 | 4A/2 | DA+6 | 2026-06-14 | DONE | Bajrang Nath | Pramod
71 | 71 | 4A/3 | DA+9 | 2026-06-14 | DONE | Bajrang Nath | Pramod
72 | 72 | 14/0 | DD60+18 | 2026-06-15 | DONE | Mahendra Banjara | Pramod
73 | 73 | 15/0 | DD60+25 | 2026-06-15 | DONE | Mahendra Banjara | Pramod
74 | 74 | 4A/0 | DB1+3 | 2026-06-15 | DONE | Bajrang Nath | Pramod
75 | 75 | 4A/1 | DA+6 | 2026-06-15 | DONE | Bajrang Nath | Pramod
76 | 76 | 3B/0 | DB1+9 | 2026-06-16 | DONE | Mahendra Banjara | Pramod
77 | 77 | 3B/1 | DA+3 | 2026-06-16 | DONE | Mahendra Banjara | Pramod
78 | 78 | 4/0 | DB2+9 | 2026-06-16 | DONE | Bajrang Nath | Pramod
79 | 79 | 4/1 | DA+6 | 2026-06-16 | DONE | Bajrang Nath | Pramod | 4/5-4/1
80 | 80 | 3A/0 | DD45+3 | 2026-06-17 | DONE | Mahendra Banjara | Pramod
81 | 81 | 3A/1 | DA+3 | 2026-06-17 | DONE | Mahendra Banjara | Pramod
82 | 82 | 3A/2 | DA+3 | 2026-06-18 | DONE | Bajrang Nath | Pramod
83 | 83 | 3A/3 | DA+0 | 2026-06-18 | DONE | Bajrang Nath | Pramod
84 | 84 | 3A/4 | DA+0 | 2026-06-18 | DONE | Bajrang Nath | Pramod
85 | 85 | 3A/5 | DA+3 | 2026-06-18 | DONE | Bajrang Nath | Pramod
86 | 86 | 3A/6 | DA+0 | 2026-06-19 | DONE | Bajrang Nath | Pramod
87 | 87 | 2A/0 | DD45+0 | 2026-06-19 | DONE | Shri Balaji | Pramod
88 | 88 | 7/0 | DB2+0 | 2026-06-19 | DONE | Mahendra Banjara | Pramod
89 | 89 | 2A/6 | DA+6 | 2026-06-21 | DONE | Mahendra Banjara | Pramod
90 | 90 | 2A/5 | DA+3 | 2026-06-21 | DONE | Mahendra Banjara | Pramod
91 | 91 | 2A/3 | DA+3 | 2026-06-21 | DONE | Mahendra Banjara | Pramod
92 | 92 | 7A/3 | DA+3 | 2026-06-22 | DONE | Mahendra Banjara | Pramod
93 | 93 | 7A/2 | DA+3 | 2026-06-22 | DONE | Mahendra Banjara | Pramod
94 | 94 | 7A/1 | DA+1.5 | 2026-06-22 | DONE | Mahendra Banjara | Pramod
95 | 95 | 7A/0 | DB1+6 | 2026-06-22 | DONE | Mahendra Banjara | Pramod
96 | 96 | 13/0 | DD60+9 | 2026-06-26 | DONE | Mahendra Banjara | Sanjay Kumar
97 | 97 | 13A/0 | DB1+9 | 2026-06-26 | DONE | Mahendra Banjara | Sanjay Kumar
98 | 98 | 2A/4 | DA+3 | 2026-06-27 | DONE | Shri Balaji | Sanjay Kumar
99 | 99 | 2A/1 | DA+0 | 2026-06-27 | DONE | Shri Balaji | Sanjay Kumar
100 | 100 | 7A/5 |  |  |  |  | ROW

## Accessories
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Accessories | [11 empty] | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Danger Plate | Number Plate | Phase Plate | Circuit Plate | Completion Date | Anti Climbing device | Name of the Contractor | Name of Supervisor | Remarks
1 | 1 | 1/0 | DD60+0 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
2 | 2 | 2A/0 | DD45+0 | [8 empty] | HOLE Missing
3 | 3 | 2A/1 | DA+0 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
4 | 4 | 2A/2 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
5 | 5 | 2A/3 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
6 | 6 | 2A/4 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
7 | 7 | 2A/5 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
8 | 8 | 2A/6 | DA+6 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
9 | 9 | 3A/0 | DD45+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
10 | 10 | 3A/1 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
11 | 11 | 3A/2 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
12 | 12 | 3A/3 | DA+0 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
13 | 13 | 3A/4 | DA+0 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
14 | 14 | 3A/5 | DA+3 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
15 | 15 | 3A/6 | DA+0 | Done | Done | Done | Done | 2026-06-16 |  | Jetharam
16 | 16 | 3B/0 | DB1+9 | [8 empty] | HOLE Missing
17 | 17 | 3B/1 | DA+3 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
18 | 18 | 3B/2 | DA+9 | [8 empty] | HOLE Missing
19 | 19 | 3B/3 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
20 | 20 | 4/0 | DB2+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
21 | 21 | 4/1 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
22 | 22 | 4A/0 | DB1+3 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
23 | 23 | 4A/1 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
24 | 24 | 4A/2 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
25 | 25 | 4A/3 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
26 | 26 | 4A/4 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
27 | 27 | 4A/5 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
28 | 28 | 4A/6 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
29 | 29 | 5/0 | DB1+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
30 | 30 | 5/1 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
31 | 31 | 5/2 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
32 | 32 | 5/3 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
33 | 33 | 5/4 | DA-1.5 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
34 | 34 | 5/5 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
35 | 35 | 5/6 | DA+3 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
36 | 36 | 5/7 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
37 | 37 | 5/8 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
38 | 38 | 5/9 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
39 | 39 | 5/10 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
40 | 40 | 5A/0 | DB1+12 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
41 | 41 | 6/0 | DB1+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
42 | 42 | 6/1 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
43 | 43 | 6/2 | DA+6 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
44 | 44 | 6/3 | DA+3 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
45 | 45 | 6/4 | DA+9 | Done | Done | Done | Done | 2026-06-17 |  | Jetharam
46 | 46 | 6/5 | DA+9 | [8 empty] | HOLE Missing
47 | 47 | 6/6 | DA-3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
48 | 48 | 6/7 | DA+1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
49 | 49 | 6/8 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
50 | 50 | 6/9 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
51 | 51 | 6/10 | DA+1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
52 | 52 | 6/11 | DA-1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
53 | 53 | 6/12 | DA+1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
54 | 54 | 7/0 | DB2+0 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
55 | 55 | 7/1 | DA-3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
56 | 56 | 7/2 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
57 | 57 | 7/3 | DA+9 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
58 | 58 | 7/4 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
59 | 59 | 7/5 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
60 | 60 | 7/6 | DA-1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
61 | 61 | 7A/0 | DB1+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
62 | 62 | 7A/1 | DA+1.5 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
63 | 63 | 7A/2 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
64 | 64 | 7A/3 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
65 | 65 | 7A/4 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
66 | 66 | 7A/5 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
67 | 67 | 8/0 | DB1+0 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
68 | 68 | 8/1 | DA-3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
69 | 69 | 8/2 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
70 | 70 | 8/3 | DA+9 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
71 | 71 | 8/4 | DA+6 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
72 | 72 | 8/5 | DA+9 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
73 | 73 | 8/6 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
74 | 74 | 8/7 | DA+3 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
75 | 75 | 8/8 | DA+9 | Done | Done | Done | Done | 2026-06-18 |  | Jetharam
76 | 76 | 8/9 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
77 | 77 | 8/10 | DA+0 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
78 | 78 | 8/11 | DA+9 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
79 | 79 | 8A/0 | DB1+12 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
80 | 80 | 9/1 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
81 | 81 | 9/2 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
82 | 82 | 9/3 | DA+0 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
83 | 83 | 9/4 | DA+6 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
84 | 84 | 9/5 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
85 | 85 | 9/6 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
86 | 86 | 9/7 | DA+9 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
87 | 87 | 9/8 | DA+0 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
88 | 88 | 9/9 | DA+0 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
89 | 89 | 9/10 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
90 | 90 | 9/11 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
91 | 91 | 10/1 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
92 | 92 | 10/2 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
93 | 93 | 13/0 | DD60+9 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
94 | 94 | 13A/0 | DB1+9 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
95 | 95 | 14/0 | DD60+18 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
96 | 96 | 15/0 | DD60+25 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
97 | 97 | 15/1 | DA+6 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
98 | 98 | 15/2 | DA+3 | Done | Done | Done | Done | 2026-06-19 |  | Jetharam
99 | 99 | 15/3 | DA+3 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
100 | 100 | 15/4 | DA+6 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
101 | 101 | 15/5 | DA+3 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
102 | 102 | 15/6 | DA+9 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
103 | 103 | 15/7 | DA+0 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
104 | 104 | 15/8 | DA+1.5 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
105 | 105 | 15/9 | DA+0 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
106 | 106 | 15/10 | DA-1.5 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
107 | 107 | 15/11 | DA+0 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
108 | 108 | 15/12 | DA+6 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
109 | 109 | 17/0 | DC1+3 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
110 | 110 | 18/0 | DB2+6 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
111 | 111 | 18/1 | DA+3 | Done | Done | Done | Done | 2026-06-20 |  | Jetharam
112 | 112 | 18/2 | DA+1.5 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
113 | 113 | 18/3 | DA+6 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
114 | 114 | 18/4 | DA-3 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
115 | 115 | 18/5 | DA+0 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
116 | 116 | 18/6 | DA+9 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
117 | 117 | 18/7 | DA+1.5 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
118 | 118 | 19/0 | DD60+3 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
119 | 119 | 20/0 | DD60+3 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
120 | 120 | 20/1 | DA-3 | Done | Done | Done | Done | 2026-06-21 |  | Jetharam
121 | 121 | 20/2 | DA-3 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
122 | 122 | 20/3 | DA+1.5 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
123 | 123 | 20/4 | DA+3 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
124 | 124 | 20/5 | DA+0 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
125 | 125 | 20/6 | DA-3 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
126 | 126 | 21/1 | DA+0 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
127 | 127 | 21/2 | DA+6 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
128 | 128 | 21/3 | DA+6 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
129 | 129 | 21/4 | DA+0 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
130 | 130 | 21/5 | DA+0 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
131 | 131 | 22/0 | DC2+15 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
132 | 132 | 23/0 | DB2+9 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
133 | 133 | 23A/0 | DB1+9 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
134 | 134 | 24/0 | DD60+18 | Done | Done | Done | Done | 2026-06-22 |  | Jetharam
135 | 135 | 25/0 | DD60+18 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
136 | 136 | 26/0 | DD60+35 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
137 | 137 | 27/0 | DD60+35 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
138 | 138 | 27/2 | DA-1.5 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
139 | 139 | 27/3 | DA+1.5 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
140 | 140 | 27/4 | DA+1.5 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
141 | 141 | 27/6 | DA-3 | Done | Done | Done | Done | 2026-06-23 |  | Jetharam
142 | 142 | 28/0 | DC2-3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
143 | 143 | 29/0 | DC1+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
144 | 144 | 29/1 | DA+6 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
145 | 145 | 29/2 | DA+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
146 | 146 | 29/3 | DA+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
147 | 147 | 29/4 | DA+3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
148 | 148 | 29/5 | DA+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
149 | 149 | 29A/1 | DA+6 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
150 | 150 | 29A/2 | DA+6 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
151 | 151 | 29A/3 | DA+6 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
152 | 152 | 29A/4 | DA+3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
153 | 153 | 29A/5 | DA+6 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
154 | 154 | 29A/6 | DA+9 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
155 | 155 | 30/1 | DA+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
156 | 156 | 30/2 | DA+9 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
157 | 157 | 30/5 | DA+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
158 | 158 | 30/7 | DA-3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
159 | 159 | 30/8 | DA+3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
160 | 160 | 30/9 | DA-3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
161 | 161 | 30/10 | DA+3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
162 | 162 | 31/0 | DB1+0 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
163 | 163 | 31/1 | DA+3 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
164 | 164 | 31/2 | DA+1.5 | Done | Done | Done | Done | 2026-06-24 |  | Jetharam
165 | 165 | 31/3 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
166 | 166 | 31/4 | DA-1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
167 | 167 | 31/5 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
168 | 168 | 31/6 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
169 | 169 | 31/7 | DA+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
170 | 170 | 31/8 | DA+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
171 | 171 | 31/9 | DA+1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
172 | 172 | 31/10 | DA+4.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
173 | 173 | 32/0 | DB2+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
174 | 174 | 32/1 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
175 | 175 | 32/2 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
176 | 176 | 32/3 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
177 | 177 | 32/4 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
178 | 178 | 32/5 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
179 | 179 | 32/6 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
180 | 180 | 32/7 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
181 | 181 | 32A/0 | DB1+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
182 | 182 | 33/0 | DB1+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
183 | 183 | 33/1 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
184 | 184 | 33/2 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
185 | 185 | 33/3 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
186 | 186 | 33/4 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
187 | 187 | 33/5 | DA+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
188 | 188 | 33/6 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
189 | 189 | 33/7 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
190 | 190 | 33/8 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
191 | 191 | 33/9 | DA+1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
192 | 192 | 34/0 | DB1+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
193 | 193 | 34/1 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
194 | 194 | 34/2 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
195 | 195 | 34/3 | DA+1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
196 | 196 | 34/4 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
197 | 197 | 34/5 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
198 | 198 | 34/6 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
199 | 199 | 34/8 | DA+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
200 | 200 | 34/9 | DA+1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
201 | 201 | 34/10 | DA-3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
202 | 202 | 34/11 | DA+1.5 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
203 | 203 | 34/12 | DA+3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
204 | 204 | 35/0 | DB2+0 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
205 | 205 | 35/1 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
206 | 206 | 35/2 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
207 | 207 | 35/3 | DA-3 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
208 | 208 | 35/4 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
209 | 209 | 35/5 | DA+9 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
210 | 210 | 35/6 | DA+6 | Done | Done | Done | Done | 2026-06-25 |  | Jetharam
211 | 211 | 35/7 | DA+3 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
212 | 212 | 35/8 | DA+6 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
213 | 213 | 35/9 | DA+1.5 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
214 | 214 | 35/10 | DA+3 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
215 | 215 | 35/11 | DA+3 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
216 | 216 | 36/0 | DB2+3 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
217 | 217 | 36A/0 | DB1+9 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
218 | 218 | 36A/1 | DA+3 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
219 | 219 | 37/3 | DA-1.5 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
220 | 220 | 37/4 | DA+9 | Done | Done | Done | Done | 2026-06-26 |  | Jetharam
221 | 221 | 37/5 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
222 | 222 | 37A/0 | DB1+0 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
223 | 223 | 37A/1 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
224 | 224 | 37A/2 | DA+1.5 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
225 | 225 | 37A/3 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
226 | 226 | 37A/6 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
227 | 227 | 38/0 | DB1+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
228 | 228 | 38/2 | DA+0 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
229 | 229 | 38/3 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
230 | 230 | 39/3 | DA+1.5 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
231 | 231 | 39/4 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
232 | 232 | 39/5 | DA+1.5 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
233 | 233 | 39/6 | DA+1.5 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
234 | 234 | 39/7 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
235 | 235 | 39/8 | DA+1.5 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
236 | 236 | 39/9 | DA+6 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
237 | 237 | 39/10 | DA+3 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
238 | 238 | 39/11 | DA+6 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
239 | 239 | 40/0 | DB1+6 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
240 | 240 | 40/1 | DA+9 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
241 | 241 | 40/2 | DA+6 | Done | Done | Done | Done | 2026-06-27 |  | Jetharam
242 | 242 | 40/3 | DA+3 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam
243 | 243 | 40/4 | DA+6 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam
244 | 244 | 40/5 | DA+9 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam
245 | 245 | 40/6 | DA+9 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam
246 | 246 | 40/7 | DA+3 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam
247 | 247 | 40/9 | DA+9 | Done | Done | Done | Done | 2026-06-28 |  | Jetharam

## OPGW
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of OPGW Stringing | [11 empty] | 24.07.2026
Cum. Sr.No. | Month Sr.No. | Section |  |  |  |  | Paying Out Start | Paying Out Completed | Final sag | Name of the Contractor | Remarks | Joint Box for 24 fibre OPGW
|  | From | To | Section Length in Km's | Drum Length in Km's | Cum. Drum Length in Km's
1 | 1 | 34/0 | 34/12 | 4.547 | 4.719 | 4.547 | 2025-04-19 | 2025-04-19 | 2025-04-19 | B K Construction | Completed
2 | 2 | 37A/0 | 38/5 | 4.455 | 4.666 | 9.002 | 2025-04-21 | 2025-04-21 | 2025-04-21 | B K Construction | Completed
3 | 3 | 38/5 | 39/6 | 4.61 | 5 | 13.612 | 2025-04-24 | 2025-04-24 | 2025-04-24 | B K Construction | Completed
4 | 4 | 7A/0 | 8/6 | 4.6 | 5 | 18.212 | 2025-10-24 | 2025-10-25 | 2025-10-26 | B K Construction | Completed | 7A/0 (22/2/26)
5 | 1 | 6/8 | 7A/0 | 4.505 | 4.723 | 22.717 | 2026-01-05 | 2026-01-07 | 2026-01-08 | B K Construction | Completed
6 | 2 | 5/8 | 6/8 | 4.775 | 5 | 27.492 | 2026-01-09 | 2026-01-12 | 2026-01-13 | B K Construction | Completed | 5/8 (23/2/26) 6/8 (23/2/26)
7 | 3 | 4A/3 | 5/8 | 4.665 | 5 | 32.157 | 2026-01-14 | 2026-01-16 | 2026-01-17 | B K Construction | Completed
8 | 4 | 3A/4 | 4A/3 | 4.6457 | 5 | 36.8027 | 2026-01-18 | 2026-01-19 | 2026-01-21 | B K Construction | Completed | 4A/3 (24/2/26)
9 | 1 | 32A/1 | 34/0 | 4.4882 | 4.709 | 41.2909 | 2026-02-09 | 2026-02-09 | 2026-02-09 | B K Construction | Completed | 34/0 (14/2/2026) , 32A/1 (15/2/26)
10 | 2 | 31/9 | 32A/1 | 4.447 | 4.665 | 45.7379 | 2026-02-11 | 2026-02-12 | 2026-02-13 | B K Construction | Completed | 31/9 (17/2/26)
11 | 3 | 30/8 | 31/9 | 4.74 | 5 | 50.4779 | 2026-02-14 | 2026-02-15 | 2026-02-16 | B K Construction | Completed | 30/8 (19/2/26)
12 | 4 | 29A/3 | 30/8 | 4.45 | 4.669 | 54.9279 | 2026-02-16 | 2026-02-17 | 2026-02-18 | B K Construction | Completed
13 | 5 | GY | 3A/4 | 4.8342 | 5 | 59.7621 | 2026-02-20 | 2026-02-21 | 2026-02-22 | B K Construction | Completed | 3A/4 (24/2/26)
14 | 1 | 9/5 | 13/0 | 4.498 | 4.632 | 64.2601 | 2026-06-24 | 2026-06-24 | 2026-06-25 | B K Construction | Completed
15 | 2 | 8/6 | 9/5 | 4.8 | 5 | 69.0601 | 2026-06-26 | 2026-06-27 | 2026-06-28 | B K Construction | Completed
16 | 3 | 34/12 | 35/11 | 4.775 | 5 | 73.8351 | 2026-07-05 | 2026-07-06 | 2026-07-07 | B K Construction | Completed
|  |  |  | 73.8351 | 77.783
Formulas:
Final sag = [Paying Out Completed]+1
Paying Out Completed = [Paying Out Start]+1

## Foundation
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Details of Foundation | [7 empty] | 109701.665 | 1387.59 | 15180.04 | 855.2224 | 349.7789 | 2969.7 |  |  | 24.07.2026
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Name of the Contractor | Excavation | M10 | M20 | Steel | Stub | Revenue (In Lakhs) | Name of Supervisor | Stub setting | Remarks
1 | 1 | 9/4 | DA+6 | Sandy | 2024-05-29 | 2024-06-06 | Sahu Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Pradip Das | Completed | 314.284
2 | 2 | 10/1 | DA+3 | Sandy | 2024-05-30 | 2024-06-07 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Das | Completed | 314.284
3 | 3 | 10/2 | DA+3 | Sandy | 2024-06-07 | 2024-06-09 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Das | Completed | 314.284
4 | 4 | 9/11 | DA+3 | Sandy | 2024-06-09 | 2024-06-11 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Das | Completed | 314.284
5 | 5 | 9/5 | DA+3 | Sandy | 2024-06-12 | 2024-06-17 | Sahu Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Pradip Singh | Completed | 314.284
6 | 6 | 15/2 | DA+3 | Sandy | 2024-06-13 | 2024-06-17 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Singh | Completed | 314.284
7 | 7 | 15/3 | DA+3 | Sandy | 2024-06-16 | 2024-06-18 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Singh | Completed | 314.284
8 | 8 | 15/4 | DA+6 | Sandy | 2024-06-18 | 2024-06-21 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Singh | Completed | 314.284
9 | 9 | 9/3 | DA+0 | Sandy | 2024-06-18 | 2024-06-23 | Sahu Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Harshit Kumar | Pradip Singh | Completed | 287.984
10 | 10 | 15/5 | DA+3 | Sandy | 2024-06-21 | 2024-06-24 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Singh | Completed | 314.284
11 | 11 | 8/5 | DA+9 | Sandy | 2024-06-17 | 2024-06-26 | Daksh Enterprise | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradip Singh | Completed | 314.284
12 | 12 | 15/6 | DA+9 | Sandy | 2024-06-24 | 2024-06-27 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradip Singh | Completed | 314.284
13 | 13 | 9/10 | DA+3 | Sandy | 2024-06-23 | 2024-06-28 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradip Singh | Completed | 314.284
14 | 14 | 9/2 | DA+3 | Sandy | 2024-06-25 | 2024-06-29 | Sahu Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Pradip Singh | Completed | 314.284
15 | 1 | 15/9 | DA+0 | Sandy | 2024-06-27 | 2024-07-03 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Amit Kumar | Completed | 287.984
16 | 2 | 8/6 | DA+3 | Sandy | 2024-06-28 | 2024-07-03 | Daksh Enterprise | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
17 | 3 | 15/8 | DA+1.5 | Sandy | 2024-07-03 | 2024-07-06 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Nitish | Completed | 314.284
18 | 4 | 31/9 | DA+1.5 | Sandy | 2024-07-04 | 2024-07-06 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram/Mustak | Shantanu | Completed | 314.284
19 | 5 | 8/7 | DA+3 | Sandy | 2024-07-04 | 2024-07-09 | Daksh Enterprise | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Nitish | Completed | 314.284
20 | 6 | 9/1 | DA+3 | Sandy | 2024-07-02 | 2024-07-10 | Sahu Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Amit Kumar (C&D) | Completed | 314.284
21 | 7 | 31/8 | DA+0 | Sandy | 2024-07-06 | 2024-07-10 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram/Mustak | Shantanu | Completed | 287.984
22 | 8 | 15/10 | DA-1.5 | Sandy | 2024-07-07 | 2024-07-10 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Pradeep Singh | Completed | 287.984
23 | 9 | 15/7 | DA+0 | Sandy | 2024-06-27 | 2024-07-11 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Anil MG | Completed | 287.984
24 | 10 | 31/7 | DA+0 | Sandy | 2024-07-11 | 2024-07-15 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Harshit Kumar | Pradeep Singh | Completed | 287.984
25 | 11 | 15/11 | DA+0 | Sandy | 2024-07-11 | 2024-07-18 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Nitish & Tanmai Dey | Completed | 287.984
26 | 12 | 8/8 | DA+9 | Sandy | 2024-07-10 | 2024-07-19 | Daksh Enterprise | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Nistish | Completed | 314.284
27 | 13 | 8/1 | DA-3 | Sandy | 2024-07-15 | 2024-07-20 | Priyanshi Power Project | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Nistish | Completed | 287.984
28 | 14 | 31/6 | DA+9 | Sandy | 2024-07-16 | 2024-07-22 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
29 | 15 | 29/4 | DA+3 | Sandy | 2024-07-20 | 2024-07-24 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
30 | 16 | 8/9 | DA+3 | Sandy | 2024-07-20 | 2024-07-25 | Daksh Enterprise | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Nistish | Completed | 314.284
31 | 17 | 8/2 | DA+6 | Sandy | 2024-07-21 | 2024-07-25 | Priyanshi Power Project | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Nistish | Completed | 314.284
32 | 18 | 31/10 | DA+4.5 | Sandy | 2024-07-24 | 2024-07-28 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Pradeep Singh | Completed | 314.284
33 | 19 | 29/3 | DA+0 | Sandy | 2024-07-24 | 2024-07-29 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Tanmoy | Completed | 287.984
34 | 20 | 31/3 | DA+3 | Sandy | 2024-07-29 | 2024-07-31 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Shantanu | Completed | 314.284
35 | 1 | 30/1 | DA+0 | Sandy | 2024-07-21 | 2024-08-01 | Vishwas/Bala ji | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Tanmoy | Completed | 287.984
36 | 2 | 31/1 | DA+3 | Sandy | 2024-07-31 | 2024-08-03 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Shantanu | Completed | 314.284
37 | 3 | 29/5 | DA+0 | Sandy | 2024-07-31 | 2024-08-03 | Choudhary construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Shantanu | Completed | 287.984
38 | 4 | 5/3 | DA+9 | Sandy | 2024-07-29 | 2024-08-08 | Goyal Industries | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Nistish | Completed | 314.284
39 | 5 | 29A/2 | DA+6 | Sandy | 2024-08-04 | 2024-08-08 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Shantanu | Completed | 314.284
40 | 6 | 7/1 | DA-3 | Sandy | 2024-07-28 | 2024-08-10 | Ram Enterprises | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Reshpaul Tyagi | Nistish | Completed | 287.984
41 | 7 | 8/10 | DA+0 | Sandy | 2024-08-09 | 2024-08-13 | Choudhary construction-2 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Manoj Gupta | Nistish | Completed | 287.984
42 | 8 | 29A/1 | DA+6 | Sandy | 2024-08-09 | 2024-08-14 | Choudhary construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Shantanu | Completed | 314.284
43 | 9 | 27/4 | DA+1.5 | Sandy | 2024-08-09 | 2024-08-16 | Vishwas/Bala ji | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Saheb guchait | Completed | 314.284
44 | 10 | 7A/5 | DA+3 | Sandy | 2024-08-12 | 2024-08-17 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
45 | 11 | 5/8 | DA+6 | Sandy | 2024-08-13 | 2024-08-18 | Goyal Industries -2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Tanmoy | Completed | 314.284
46 | 12 | 29A/3 | DA+6 | Sandy | 2024-08-12 | 2024-08-20 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
47 | 13 | 32/3 | DA+6 | Sandy | 2024-08-14 | 2024-08-20 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
48 | 14 | 7A/4 | DA+3 | Sandy | 2024-08-21 | 2024-08-23 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
49 | 15 | 29A/4 | DA+3 | Sandy | 2024-08-18 | 2024-08-24 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
50 | 16 | 5/4 | DA-1.5 | Sandy | 2024-08-08 | 2024-08-25 | Goyal Industries | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Manoj Gupta | Nistish | Completed | 287.984
51 | 17 | 32/4 | DA+9 | Sandy | 2024-08-21 | 2024-08-26 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
52 | 18 | 29A/5 | DA+6 | Sandy | 2025-08-24 | 2024-08-27 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
53 | 19 | 6/2 | DA+6 | Sandy | 2025-08-24 | 2024-08-27 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
54 | 20 | 27/5 | DA-1.5 | Sandy | 2024-08-17 | 2024-08-28 | Vishwas/Bala ji | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Saheb guchait | Saheb guchait | Completed | 287.984
55 | 21 | 6/1 | DA+9 | Sandy | 2024-08-28 | 2024-08-30 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
56 | 22 | 33/6 | DA+6 | Sandy | 2024-08-27 | 2024-08-30 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
57 | 23 | 29A/6 | DA+9 | Sandy | 2024-08-04 | 2024-08-31 | Vishwas/Bala ji | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
58 | 1 | 7A/1 | DA+1.5 | Sandy | 2024-08-29 | 2024-09-01 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
59 | 2 | 4A/5 | DA+9 | Sandy | 2024-08-29 | 2024-09-01 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
60 | 3 | 5/10 | DA+9 | Sandy | 2024-09-01 | 2024-09-04 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
61 | 4 | 33/7 | DA+6 | Sandy | 2024-08-31 | 2024-09-04 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
62 | 5 | 6/12 | DA+1.5 | Sandy | 2024-08-29 | 2024-09-05 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
63 | 6 | 7A/2 | DA+3 | Sandy | 2024-09-01 | 2024-09-06 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
64 | 7 | 4A/4 | DA+6 | Sandy | 2024-09-01 | 2024-09-06 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
65 | 8 | 6/3 | DA+3 | Sandy | 2024-09-04 | 2024-09-07 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
66 | 9 | 33/4 | DA+3 | Sandy | 2024-09-04 | 2024-09-09 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
67 | 10 | 4A/3 | DA+9 | Sandy | 2024-09-07 | 2024-09-09 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
68 | 11 | 7A/3 | DA+3 | Sandy | 2024-09-08 | 2024-09-10 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
69 | 12 | 29/1 | DA+6 | Sandy | 2024-09-02 | 2024-09-10 | Vishwas/Bala ji | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Saheb guchait | Completed | 314.284
70 | 13 | 4A/6 | DA+9 | Sandy | 2024-09-09 | 2024-09-12 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Saheb guchait | Completed | 314.284
71 | 14 | 5/7 | DA+9 | Sandy | 2024-09-08 | 2024-09-12 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
72 | 15 | 34/12 | DA+3 | Sandy | 2024-09-01 | 2024-09-13 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
73 | 16 | 33/3 | DA+3 | Sandy | 2024-09-08 | 2024-09-13 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
74 | 17 | 6/11 | DA-1.5 | Sandy | 2024-09-08 | 2024-09-14 | Protek infra | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Reshpaul Tyagi | Nistish | Completed | 287.984
75 | 18 | 5/6 | DA+3 | Sandy | 2024-09-13 | 2024-09-15 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
76 | 19 | 36A/1 | DA+3 | Sandy | 2024-09-11 | 2024-09-15 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
77 | 20 | 34/1 | DA+9 | Sandy | 2024-09-13 | 2024-09-15 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
78 | 21 | 4A/2 | DA+6 | Sandy | 2024-09-14 | 2024-09-16 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
79 | 22 | 34/3 | DA+1.5 | Sandy | 2024-09-15 | 2024-09-18 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
80 | 23 | 36A/2 | DA+9 | Sandy | 2024-09-15 | 2024-09-19 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Manoj Gupta | Pradeep Singh | Completed | 314.284
81 | 24 | 34/11 | DA+1.5 | Sandy | 2024-09-13 | 2024-09-20 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Pradeep Singh | Completed | 314.284
82 | 25 | 6/4 | DA+9 | Sandy | 2024-09-18 | 2024-09-20 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Nistish | Completed | 314.284
83 | 26 | 27/2 | DA-1.5 | Sandy | 2024-09-15 | 2024-09-20 | Vishwas/Bala ji | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Saheb guchait | Saheb guchait | Completed | 287.984
84 | 27 | 4A/1 | DA+6 | Sandy | 2024-09-17 | 2024-09-21 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
85 | 28 | 34/4 | DA+6 | Sandy | 2024-09-18 | 2024-09-21 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
86 | 29 | 6/6 | DA-3 | Sandy | 2024-09-20 | 2024-09-23 | Choudhary construction-2 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Harshit Kumar | Nistish | Completed | 287.984
87 | 30 | 37/1 | DA+3 | Sandy | 2024-09-19 | 2024-09-23 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Pradeep Singh | Pradeep Singh | Completed | 314.284
88 | 31 | 5/2 | DA+9 | Sandy | 2024-09-20 | 2024-09-23 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
89 | 32 | 34/5 | DA+9 | Sandy | 2024-09-21 | 2024-09-25 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
90 | 33 | 35/1 | DA+6 | Sandy | 2024-09-21 | 2024-09-26 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Saheb guchait | Completed | 314.284
91 | 34 | 4/1 | DA+6 | Sandy | 2024-09-24 | 2024-09-27 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nistish | Completed | 314.284
92 | 35 | 37/2 | DA+3 | Sandy | 2024-09-24 | 2024-09-27 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
93 | 36 | 34/6 | DA+3 | Sandy | 2024-09-25 | 2024-09-28 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
94 | 37 | 27/1 | DA+9 | Sandy | 2024-09-21 | 2024-09-28 | Vishwas/Bala ji | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Saheb guchait | Saheb guchait | Completed | 314.284
95 | 38 | 6/10 | DA+1.5 | Sandy | 2024-09-15 | 2024-09-29 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
96 | 39 | 34/8 | DA+0 | Sandy | 2024-09-27 | 2024-09-30 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Pradeep Singh | Completed | 287.984
97 | 40 | 37/3 | DA-1.5 | Sandy | 2024-09-26 | 2024-09-30 | Choudhary construction-1 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Pradeep Singh | Completed | 287.984
98 | 1 | 7/0 | DB2+0 | Sandy | 2024-09-25 | 2024-10-01 | Choudhary construction-2 | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16 | Harshit Kumar | Nistish | Completed | 717.348
99 | 2 | 4A/0 | DB1+3 | Sandy | 2024-09-29 | 2024-10-01 | Bharat Singh Anjana | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Chetram | Nistish | Completed | 589.972
100 | 3 | 6/9 | DA+6 | Sandy | 2024-09-30 | 2024-10-01 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
101 | 4 | 35/5 | DA+9 | Sandy | 2024-09-27 | 2024-10-03 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Saheb guchait | Completed | 314.284
102 | 5 | 34/7 | DA+0 | Sandy | 2024-09-30 | 2024-10-04 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Shuvam Gupta | Pradeep Singh | Completed | 287.984
103 | 6 | 36A/0 | DB1+9 | Sandy | 2024-09-30 | 2024-10-05 | Choudhary construction-1 | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Radha krishnan | Pradeep Singh | Completed | 589.972
104 | 7 | 3/8 | DA+0 | Sandy | 2024-10-01 | 2024-10-05 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Nistish | Completed | 287.984
105 | 8 | 5/9 | DA+6 | Sandy | 2024-10-02 | 2024-10-07 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
106 | 9 | 34/9 | DA+1.5 | Sandy | 2024-10-04 | 2024-10-07 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
107 | 10 | 7/3 | DA+9 | Sandy | 2024-10-04 | 2024-10-08 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
108 | 11 | 27/3 | DA+1.5 | Sandy | 2024-09-30 | 2024-10-08 | Bajrang nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Saheb guchait | Saheb guchait | Completed | 314.284
109 | 12 | 35/6 | DA+6 | Sandy | 2024-10-03 | 2024-10-09 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Suraj | Saheb guchait | Completed | 314.284
110 | 13 | 3/9 | DA+0 | Sandy | 2024-10-06 | 2024-10-09 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Nistish | Completed | 287.984
111 | 14 | 34/10 | DA-3 | Sandy | 2024-10-07 | 2024-10-12 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Munna | Pradeep Singh | Completed | 287.984
112 | 15 | 7/4 | DA+6 | Sandy | 2024-10-08 | 2024-10-12 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Saheb guchait | Completed | 314.284
113 | 16 | 3/10 | DA+9 | Sandy | 2024-10-10 | 2024-10-12 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Shantanu | Completed | 314.284
114 | 17 | 27/6 | DA-3 | Sandy | 2024-10-08 | 2024-10-14 | Bajrang nath | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Vikram | Pradeep Singh | Completed | 287.984
115 | 18 | 37/0 | DB2+3 | Sandy | 2024-10-05 | 2024-10-14 | Choudhary construction-1 | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Radha krishnan | Pradeep Singh | Completed | 723.096
116 | 19 | 6/7 | DA+1.5 | Sandy | 2024-10-13 | 2024-10-16 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Saheb guchait | Completed | 314.284
117 | 20 | 34/2 | DA+9 | Sandy | 2024-10-12 | 2024-10-16 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Munna | Pradeep Singh | Completed | 314.284
118 | 21 | 3/11 | DA+0 | Sandy | 2024-10-13 | 2024-10-16 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Shantanu | Completed | 287.984
119 | 22 | 35/7 | DA+3 | Sandy | 2024-10-09 | 2024-10-17 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
120 | 23 | 6/0 | DB1+9 | Sandy | 2024-10-11 | 2024-10-18 | Protek infra | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Reshpaul Tyagi | Saheb guchait | Completed | 589.972
121 | 24 | 6/5 | DA+9 | Sandy | 2024-10-17 | 2024-10-19 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Harshit Kumar | Saheb guchait | Completed | 314.284
122 | 25 | 3/7 | DA+3 | Sandy | 2024-10-18 | 2024-10-19 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Shantanu | Completed | 314.284
123 | 26 | 37A/4 | DA+9 | Sandy | 2024-10-14 | 2024-10-21 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
124 | 27 | 3/6 | DA+3 | Sandy | 2024-10-20 | 2024-10-22 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
125 | 28 | 33/5 | DA+0 | Sandy | 2024-10-17 | 2024-10-22 | Anmol Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Munna | Pradeep Singh | Completed | 287.984
126 | 29 | 5/5 | DA+6 | Sandy | 2024-10-19 | 2024-10-23 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik Mahto | Saheb guchait | Completed | 314.284
127 | 30 | 29/2 | DA+0 | Sandy | 2024-10-17 | 2024-10-25 | Bajrang nath | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Saheb guchait | Completed | 287.984
128 | 31 | 33/8 | DA+3 | Sandy | 2024-10-22 | 2024-10-25 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
129 | 32 | 37A/5 | DA+3 | Sandy | 2024-10-22 | 2024-10-25 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil | Saheb guchait | Completed | 314.284
130 | 33 | 35/9 | DA+1.5 | Sandy | 2024-10-25 | 2024-10-27 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Vikram | Saheb guchait | Completed | 314.284
131 | 34 | 3/4 | DA+6 | Sandy | 2024-10-25 | 2024-10-29 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Reshpaul Tyagi | Nistish | Completed | 314.284
132 | 35 | 35/8 | DA+6 | Sandy | 2024-10-17 | 2024-10-29 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik Mahto | Pradeep Singh | Completed | 314.284
133 | 36 | 37A/3 | DA+3 | Sandy | 2024-10-25 | 2024-10-30 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil | Pradeep Singh | Completed | 314.284
134 | 1 | 29A/0 | DB1+0 | Sandy | 2024-10-26 | 2024-11-07 | Bajrang nath | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Radha krishnan | Pradeep Singh | Completed | 585.184
135 | 2 | 6/8 | DA+3 | Sandy | 2024-10-25 | 2024-11-08 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ankit Yadav | Nistish | Completed | 314.284
136 | 3 | 37A/2 | DA+1.5 | Sandy | 2024-11-02 | 2024-11-08 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil | Pradeep Singh | Completed | 314.284
137 | 4 | 35/11 | DA+3 | Sandy | 2024-10-28 | 2024-11-09 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Vikram | Pradeep Singh | Completed | 314.284
138 | 5 | 33/9 | DA+1.5 | Sandy | 2024-11-05 | 2024-11-11 | Anmol Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
139 | 6 | 18/0 | DB2+6 | Sandy | 2024-10-27 | 2024-11-12 | Bharat Singh Anjana | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Sanjay | Nishit | Completed | 723.096
140 | 7 | 37A/1 | DA+3 | Sandy | 2024-11-08 | 2024-11-12 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | sushil | Saheb guchait | Completed | 314.284
141 | 8 | 18/1 | DA+3 | Sandy | 2024-11-11 | 2024-11-16 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay | Nishit | Completed | 314.284
142 | 9 | 37/4 | DA+9 | Sandy | 2024-11-13 | 2024-11-17 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | sushil | Saheb guchait | Completed | 314.284
143 | 10 | 18/2 | DA+1.5 | Sandy | 2024-11-17 | 2024-11-19 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay | Nishit | Completed | 314.284
144 | 11 | 36/0 | DB2+3 | Sandy | 2024-11-09 | 2024-11-20 | Ruhela Brothers | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Vikram | Pradeep Singh | Completed | 723.096
145 | 12 | 38/8 | DA+1.5 | Sandy | 2024-11-07 | 2024-11-20 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
146 | 13 | 37/5 | DA+3 | Sandy | 2024-11-18 | 2024-11-21 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
147 | 14 | 38/9 | DA+0 | Sandy | 2024-11-15 | 2024-11-21 | vishwas construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Saheb guchait | Completed | 287.984
148 | 15 | 7A/0 | DB1+6 | Sandy | 2024-11-08 | 2024-11-22 | Protek infra | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Raju Mahto | Nishit | Completed | 589.972
149 | 16 | 34/0 | DB1+6 | Sandy | 2024-11-11 | 2024-11-23 | Anmol Construction | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Suraj Kumar | Pradeep Singh | Completed | 589.972
150 | 17 | 38/10 | DA+3 | Sandy | 2024-11-21 | 2024-11-23 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
151 | 18 | 18/3 | DA+6 | Sandy | 2024-11-21 | 2024-11-24 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay Kumar | Nishit | Completed | 314.284
152 | 19 | 38/7 | DA+9 | Sandy | 2024-11-21 | 2024-11-26 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
153 | 20 | 35/4 | DA+9 | Sandy | 2024-11-21 | 2024-11-27 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Vikram | Pradeep Singh | Completed | 314.284
154 | 21 | 37A/0 | DB1+0 | Sandy | 2024-11-20 | 2024-11-27 | Choudhary construction-1 | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Sushil Kumar | Saheb guchait | Completed | 585.184
155 | 22 | 18/4 | DA-3 | Sandy | 2024-11-25 | 2024-11-29 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Sanjay Kumar | Nishit | Completed | 287.984
156 | 23 | 38/6 | DA+6 | Sandy | 2024-11-23 | 2024-11-29 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
157 | 24 | 38/5 | DA+3 | Sandy | 2024-11-27 | 2024-11-30 | Vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
158 | 1 | 7/2 | DA+6 | Sandy | 2024-11-24 | 2024-12-01 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Raju Mahto | Nishit | Completed | 314.284
159 | 2 | 38/0 | DB1+3 | Sandy | 2024-11-26 | 2024-12-04 | Choudhary construction-1 | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Sushil Kumar | Saheb guchait | Completed | 589.972
160 | 3 | 18/6 | DA+9 | Sandy | 2024-11-30 | 2024-12-04 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay Kumar | Nishit | Completed | 314.284
161 | 4 | 35/0 | DB2+0 | Sandy | 2024-11-27 | 2024-12-06 | Ruhela Brothers | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16 | Vikram | Pradeep Singh | Completed | 717.348
162 | 5 | 38/3 | DA+3 | Sandy | 2024-11-29 | 2024-12-06 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
163 | 6 | 18/5 | DA+0 | Sandy | 2024-11-05 | 2024-12-07 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Nishit | Completed | 287.984
164 | 7 | 37A/6 | DA+3 | Sandy | 2024-12-05 | 2024-12-08 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
165 | 8 | 38/4 | DA+1.5 | Sandy | 2024-12-06 | 2024-12-08 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
166 | 9 | 30/3 | DA+3 | Sandy | 2024-12-02 | 2024-12-10 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Vikram | Pradeep Singh | Completed | 314.284
167 | 10 | 40/2 | DA+6 | Sandy | 2024-12-07 | 2024-12-12 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
168 | 11 | 38/2 | DA+0 | Sandy | 2024-12-09 | 2024-12-12 | vishwas construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Saheb guchait | Completed | 287.984
169 | 12 | 38/1 | DA+0 | Sandy | 2024-12-11 | 2024-12-13 | vishwas construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Saheb guchait | Completed | 287.984
170 | 13 | 40/3 | DA+3 | Sandy | 2024-12-12 | 2024-12-14 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
171 | 14 | 39/1 | DA-1.5 | Sandy | 2024-11-30 | 2024-12-15 | Bajarang Nath | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Saheb guchait | Completed | 287.984
172 | 15 | 7/5 | DA+6 | Sandy | 2024-11-30 | 2024-12-17 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Suraj Kumar | Nishit | Completed | 314.284
173 | 16 | 30/0 | DB1+0 | Sandy | 2024-12-11 | 2024-12-18 | Ruhela Brothers | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Vikram | Pradeep Singh | Completed | 585.184
174 | 17 | 40/7 | DA+3 | Sandy | 2024-12-15 | 2024-12-19 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
175 | 18 | 17/0 | DC1+3 | Sandy | 2024-12-12 | 2024-12-19 | Bharat Singh Anjana | 609.84 | 7.94 | 94.04 | 4.794 | 2.3488 | 17.8 | Chetram | Nishit | Completed | 787.256
176 | 19 | 40/6 | DA+9 | Sandy | 2024-12-18 | 2024-12-21 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
177 | 20 | 39/0 | DB2+0 | Sandy | 2024-12-11 | 2024-12-21 | vishwas construction | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16 | Radha krishnan | Saheb guchait | Completed | 717.348
178 | 21 | 39/2 | DA+3 | Sandy | 2024-12-13 | 2024-12-21 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
179 | 22 | 30/2 | DA+9 | Sandy | 2024-12-19 | 2024-12-22 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Vikram | Pradeep Singh | Completed | 314.284
180 | 23 | 39/4 | DA+3 | Sandy | 2024-12-15 | 2024-12-23 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
181 | 24 | 40/8 | DA-1.5 | Sandy | 2024-12-20 | 2024-12-25 | Choudhary construction-1 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Sushil Kumar | Saheb guchait | Completed | 287.984
182 | 25 | 41/1 | DA+9 | Sandy | 2024-12-18 | 2024-12-27 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Abul | Saheb guchait | Completed | 314.284
183 | 26 | 16/0 | DC2+0 | Sandy | 2024-12-19 | 2024-12-28 | Bharat Singh Anjana | 693.86 | 9.09 | 115.43 | 5.691 | 2.3488 | 21.43 | Chetram | Nishit | Completed | 963.436
184 | 27 | 40/5 | DA+9 | Sandy | 2024-12-24 | 2024-12-29 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
185 | 28 | 39/3 | DA+1.5 | Sandy | 2024-12-20 | 2024-12-29 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik | Saheb guchait | Completed | 314.284
186 | 29 | 30/4 | DA+9 | Sandy | 2024-12-22 | 2024-12-29 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ajahar | Saheb guchait/ Praddep | Completed | 314.284
187 | 30 | 7/6 | DA-1.5 | Sandy | 2024-12-19 | 2024-12-30 | Protek infra | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Reshpaul Tyagi | Nishit | Completed | 287.984
188 | 31 | 40/4 | DA+6 | Sandy | 2024-12-28 | 2024-12-31 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
189 | 32 | 15/12 | DA+6 | Sandy | 2024-12-27 | 2024-12-31 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Nikhil Singh | Nishit | Completed | 314.284
190 | 1 | 42/0 | DB2+0 | Sandy | 2024-12-27 | 2025-01-03 | Karni Kripa Trading Company | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16 | Abul | Saheb guchait | Completed | 717.348
191 | 2 | 30/5 | DA+0 | Sandy | 2024-12-27 | 2025-01-03 | Ruhela Brothers | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ajahar | Saheb guchait | Completed | 287.984
192 | 3 | 39/5 | DA+1.5 | Sandy | 2024-12-27 | 2025-01-05 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik | Saheb guchait | Completed | 314.284
193 | 4 | 40/9 | DA+9 | Sandy | 2024-12-31 | 2025-01-05 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
194 | 5 | 8/3 | DA+9 | Sandy | 2024-12-18 | 2025-01-06 | Maa Laxmi Enterprises | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Aman | Nishit | Completed | 314.284
195 | 6 | 30/6 | DA+6 | Sandy | 2025-01-04 | 2025-01-07 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ajahar | Saheb guchait | Completed | 314.284
196 | 7 | 42/1 | DA+3 | Sandy | 2025-01-03 | 2025-01-08 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Abul | Saheb guchait | Completed | 314.284
197 | 8 | 39/6 | DA+1.5 | Sandy | 2025-01-05 | 2025-01-09 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik | Saheb guchait | Completed | 314.284
198 | 9 | 40/10 | DA+3 | Sandy | 2025-01-05 | 2025-01-09 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
199 | 10 | 30/7 | DA-3 | Sandy | 2025-01-07 | 2025-01-10 | Ruhela Brothers | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ajahar | Saheb guchait | Completed | 287.984
200 | 11 | 8/0 | DB1+0 | Sandy | 2025-12-02 | 2025-01-13 | Protek infra | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Nikhil Singh | Nishit | Completed | 585.184
201 | 12 | 42/2 | DA+9 | Sandy | 2025-01-08 | 2025-01-13 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Abul | Saheb guchait | Completed | 314.284
202 | 13 | 30/8 | DA+3 | Sandy | 2025-01-07 | 2025-01-13 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ajahar | Saheb guchait | Completed | 314.284
203 | 14 | 40/11 | DA+9 | Sandy | 2025-01-09 | 2025-01-13 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sushil Kumar | Saheb guchait | Completed | 314.284
204 | 15 | 22/0 | DC2+15 | Sandy | 2025-12-02 | 2025-01-15 | Bharat Singh Anjana | 689.93 | 9.03 | 112.22 | 5.8468 | 2.2349 | 21.18 | Aman | Nishit | Completed | 937.492
205 | 16 | 30/9 | DA-3 | Sandy | 2025-01-13 | 2025-01-17 | Ruhela Brothers | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ajahar | Saheb guchait | Completed | 287.984
206 | 17 | 39/7 | DA+3 | Sandy | 2025-01-09 | 2025-01-17 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Kartik | Saheb guchait | Completed | 314.284
207 | 18 | 41/0 | DB1+9 | Sandy | 2025-01-13 | 2025-01-19 | Karni Kripa Trading Company | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Abul | Saheb guchait | Completed | 589.972
208 | 19 | 40A/0 | DB1+9 | Sandy | 2025-01-13 | 2025-01-20 | Choudhary construction-1 | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Ajahar | Saheb guchait | Completed | 589.972
209 | 20 | 10/0 | DB1+6 | Sandy | 2025-01-13 | 2025-01-21 | Protek infra | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Nikhil Singh | Nishit | Completed | 589.972
210 | 21 | 30/10 | DA+3 | Sandy | 2025-01-17 | 2025-01-21 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Jaiprakash | Pradeep Singh | Completed | 314.284
211 | 22 | 43/7 | DA+0 | Sandy | 2025-01-15 | 2025-01-21 | Choudhary construction-2 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ganesh | Saheb guchait | Completed | 287.984
212 | 23 | 23/0 | DB2+9 | Sandy | 2025-01-15 | 2025-01-22 | Bharat Singh Anjana | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Aman | Nishit | Completed | 723.096
213 | 24 | 43/3 | DA-1.5 | Sandy | 2025-01-20 | 2025-01-23 | Choudhary construction-1 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ajahar | Saheb guchait | Completed | 287.984
214 | 25 | 39/8 | DA+1.5 | Sandy | 2025-01-17 | 2025-01-24 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Muniram | Saheb guchait | Completed | 314.284
215 | 26 | 8/4 | DA+6 | Sandy | 2025-01-06 | 2025-01-24 | Maa Laxmi Enterprises | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Aman | Nishit | Completed | 314.284
216 | 27 | 43/0 | DB1+0 | Sandy | 2025-01-19 | 2025-01-25 | Karni Kripa Trading Company | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Radha krishnan | Saheb guchait | Completed | 585.184
217 | 28 | 43/8 | DA+9 | Sandy | 2025-01-21 | 2025-01-25 | Choudhary construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ganesh | Saheb guchait | Completed | 314.284
218 | 29 | 15/1 | DA+6 | Sandy | 2025-01-22 | 2025-01-27 | Protek infra | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Nikhil Singh | Nishit | Completed | 314.284
219 | 30 | 43/4 | DA+0 | Sandy | 2025-01-23 | 2025-01-28 | Choudhary construction-1 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Ajahar | Saheb guchait | Completed | 287.984
220 | 31 | 31/0 | DB1+0 | Sandy | 2025-01-20 | 2025-01-29 | Ruhela Brothers | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Jaiprakash | Pradeep Singh | Completed | 585.184
221 | 32 | 23A/0 | DB1+9 | Sandy | 2025-01-23 | 2025-01-30 | Bharat Singh Anjana | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Aman | Nishit | Completed | 589.972
222 | 33 | 42A/0 | DB1+9 | Sandy | 2025-01-27 | 2025-01-31 | Karni Kripa Trading Company | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Radha krishnan | Saheb guchait | Completed | 589.972
223 | 34 | 39/9 | DA+6 | Sandy | 2025-01-24 | 2025-01-31 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Muniram | Saheb guchait | Completed | 314.284
224 | 35 | 32/1 | DA+6 | Sandy | 2025-01-24 | 2025-01-31 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Pradeep Singh | Completed | 314.284
225 | 1 | 31/2 | DA+1.5 | Sandy | 2025-01-29 | 2025-02-01 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Jaiprakash | Pradeep Singh | Completed | 314.284
226 | 2 | 43/6 | DA+3 | Sandy | 2025-01-28 | 2025-02-02 | Choudhary construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Ajahar | Saheb guchait | Completed | 314.284
227 | 3 | 18/7 | DA+1.5 | Sandy | 2025-01-30 | 2025-02-04 | Bharat Singh Anjana | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nishit | Completed | 314.284
228 | 4 | 44/0 | DB1+6 | Sandy | 2025-01-25 | 2025-02-04 | Choudhary construction-2 | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Ganesh | Saheb guchait | Completed | 589.972
229 | 5 | 32/2 | DA+9 | Sandy | 2025-01-31 | 2025-02-04 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | sushil | Pradeep Singh | Completed | 314.284
230 | 6 | 43/1 | DA-1.5 | Sandy | 2025-02-01 | 2025-02-05 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Aman | Saheb guchait | Completed | 287.984
231 | 7 | 31/4 | DA-1.5 | Sandy | 2025-02-01 | 2025-02-07 | Ruhela Brothers | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Jaiprakash | Pradeep Singh | Completed | 287.984
232 | 8 | 43/2 | DA+6 | Sandy | 2025-02-06 | 2025-02-08 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Aman | Saheb guchait | Completed | 314.284
233 | 9 | 43A/0 | DC2+0 | Sandy | 2025-01-31 | 2025-02-09 | Choudhary construction-1 | 693.86 | 9.09 | 115.43 | 5.691 | 2.3488 | 21.43 | Ajahar | Saheb guchait | Completed | 963.436
234 | 10 | 32/0 | DB2+0 | Sandy | 2025-02-05 | 2025-02-09 | vishwas construction | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16 | Sushil | Saheb guchait | Completed | 717.348
235 | 11 | 31/5 | DA+6 | Sandy | 2025-02-07 | 2025-02-10 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Jaiprakash | Saheb guchait | Completed | 314.284
236 | 12 | 13/0 | DD60+9 | Sandy | 2025-01-27 | 2025-02-11 | Protek infra | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99 | Aman | Chinmoy samnta | Completed | 1587.98
237 | 13 | 39/10 | DA+3 | Sandy | 2025-01-31 | 2025-02-11 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Munna | Saheb guchait | Completed | 314.284
238 | 14 | 20/2 | DA-3 | Sandy | 2025-02-05 | 2025-02-12 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Mari Mutthu | Completed | 287.984
239 | 15 | 8/11 | DA+9 | Sandy | 2025-01-27 | 2025-02-13 | Maa Laxmi Enterprises | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay kumar | Nishit | Completed | 314.284
240 | 16 | 21/5 | DA+0 | Sandy | 2025-02-07 | 2025-02-16 | Choudhary construction-2 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Munna | Mari Mutthu | Completed | 287.984
241 | 17 | 20/1 | DA-3 | Sandy | 2025-02-12 | 2025-02-16 | Bharat Singh Anjana | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Chetram | Mari Mutthu/Saheb | Completed | 287.984
242 | 18 | 32/7 | DA+3 | Sandy | 2025-02-10 | 2025-02-17 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Susheel | Saheb guchait | Completed | 314.284
243 | 19 | 13A/0 | DB1+9 | Sandy | 2025-02-11 | 2025-02-18 | Protek infra | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Aman | Chinmoy samnta | Completed | 589.972
244 | 20 | 32A/0 | DB1+9 | Sandy | 2024-02-13 | 2025-02-18 | vishwas construction-1 | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Shuvam Gupta | Saheb guchait | Completed | 589.972
245 | 21 | 9/6 | DA+3 | Sandy | 2025-02-11 | 2025-02-19 | Veer Teja | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Suraji | Pradeep Singh | Completed | 314.284
246 | 22 | 33/2 | DA+9 | Sandy | 2024-02-13 | 2025-02-20 | vishwas construction-2 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
247 | 23 | 21/4 | DA+0 | Sandy | 2025-02-16 | 2025-02-22 | Choudhary construction-2 | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Munna | 2 pradeep 2 Nisit | Completed | 287.984
248 | 24 | 32A/1 | DA+6 | Sandy | 2025-02-17 | 2025-02-22 | vishwas construction-1 | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Shuvam Gupta | Saheb guchait | Completed | 314.284
249 | 25 | 29/0 | DC1+0 | Sandy | 2025-02-11 | 2025-02-23 | Ruhela Brothers | 606.15 | 7.89 | 93.55 | 4.8168 | 2.3488 | 17.75 | Susheel | Saheb guchait | Completed | 783.116
250 | 26 | 39/11 | DA+6 | Sandy | 2025-02-11 | 2025-02-24 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Saheb guchait | Completed | 314.284
251 | 27 | 9/9 | DA+0 | Sandy | 2025-02-13 | 2025-02-25 | Sati Maa Treading | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Sanjay kumar | Pradeep Singh | Completed | 287.984
252 | 28 | 27/0 | DD60+35 | Sandy | 2025-02-14 | 2025-02-25 | Choudhary construction-1 | 999.64 | 13.28 | 186.31 | 11.581 | 3.38 | 36.39 | Munna | Pradeep Singh | Completed | 1548.912
253 | 29 | 28/0 | DC2-3 | Sandy | 2025-02-17 | 2025-02-26 | Ruhela Brothers | 693.86 | 9.09 | 115.43 | 5.691 | 2.3488 | 21.43 | Susheel | Saheb guchait | Completed | 963.436
254 | 30 | 9/7 | DA+9 | Sandy | 2025-02-16 | 2025-02-26 | Veer Teja | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay kumar | Pradeep Singh | Completed | 314.284
255 | 31 | 24/0 | DD60+18 | Sandy | 2025-02-04 | 2025-02-27 | Bharat Singh Anjana | 1042.68 | 13.88 | 194 | 12.18 | 3.1593 | 37.98 | Chetram | Mari Mutthu/ Pradeep /Nishit | Completed | 1613.072
256 | 1 | 44/1 | DA+3 | Sandy | 2025-02-24 | 2025-03-01 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
257 | 2 | 9/8 | DA+0 | Sandy | 2025-02-23 | 2025-03-05 | Veer Teja | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Sanjay kumar | Nishit | Completed | 287.984
258 | 3 | 26/0 | DD60+35 | Sandy | 2025-02-17 | 2025-03-05 | Choudhary construction | 999.64 | 13.28 | 186.31 | 11.581 | 3.38 | 36.39 | Munna | Chinmoy samnta | Completed | 1548.912
259 | 4 | 15/0 | DD60+25 | Sandy | 2025-02-17 | 2025-03-06 | Protek infra | 1042.68 | 13.88 | 194 | 12.18 | 3.1593 | 37.98 | Aman | Nishit | Completed | 1613.072
260 | 5 | 44/2 | DA+3 | Sandy | 2025-03-02 | 2025-03-06 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
261 | 6 | 25/0 | DD60+18 | Sandy | 2025-02-23 | 2025-03-08 | Bharat Singh Anjana | 1042.68 | 13.88 | 194 | 12.18 | 3.1593 | 37.98 | Chetram | Nishit | Completed | 1613.072
262 | 7 | 40/0 | DB1+6 | Sandy | 2025-02-25 | 2025-03-08 | Bajarang Nath | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Radha krishnan | Pradeep Singh | Completed | 589.972
263 | 8 | 44/4 | DA+0 | Sandy | 2025-03-11 | 2025-03-12 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Nishit | Completed | 287.984
264 | 9 | 44/3 | DA+3 | Sandy | 2025-03-06 | 2025-03-13 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Radha krishnan | Pradeep Singh | Completed | 314.284
265 | 10 | 5/0 | DB1+6 | Sandy | 2025-03-06 | 2025-03-16 | Veer Teja | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Sanjay kumar | Nishit | Completed | 589.972
266 | 11 | 44/5 | DA+0 | Sandy | 2025-03-15 | 2025-03-17 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Radha krishnan | Nishit | Completed | 287.984
267 | 12 | 2A/2 | DA+3 | Sandy | 2025-03-18 | 2025-03-23 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nishit | Completed | 314.284
268 | 13 | 5/1 | DA+6 | Sandy | 2025-03-13 | 2025-03-23 | Veer Teja | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay kumar | Nishit | Completed | 314.284
269 | 14 | 3B/2 | DA+9 | Sandy | 2025-03-19 | 2025-03-23 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Munna | Nishit | Completed | 314.284
270 | 15 | 3B/1 | DA+3 | Sandy | 2025-03-23 | 2025-03-26 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Munna | Nishit | Completed | 314.284
271 | 16 | 2A/3 | DA+3 | Sandy | 2025-03-20 | 2025-03-27 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nishit | Completed | 314.284
272 | 17 | 40/1 | DA+9 | 2MRC Sandy | 2025-03-08 | 2025-03-30 | Bajarang Nath | 323.91 | 4.07 | 47.75 | 3.949 | 1.366 | 10.51 | Kartik Jhorar | Nishit | Completed | 399.908
273 | 18 | 3B/0 | DB1+9 | Sandy | 2025-03-26 | 2025-03-30 | Karni Kripa Trading Company | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Rudra | Nishit | Completed | 589.972
274 | 19 | 2A/4 | DA+3 | Sandy | 2025-03-27 | 2025-03-30 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nishit | Completed | 314.284
275 | 1 | 5A/0 | DB1+12 | Sandy | 2025-03-23 | 2025-04-01 | Veer Teja | 462.88 | 5.94 | 67.91 | 3.1508 | 1.752 | 12.64 | Sanjay kumar | Nishit | Completed | 569.416
276 | 2 | 3A/6 | DA+0 | Sandy | 2025-03-30 | 2025-04-03 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Rudra | Nishit | Completed | 287.984
277 | 3 | 2A/5 | DA+3 | Sandy | 2025-03-30 | 2025-04-05 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | chetram | Nishit | Completed | 314.284
278 | 4 | 3A/1 | DA+3 | Sandy | 2025-04-04 | 2025-04-08 | vishwas construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | chetram | Nishit | Completed | 314.284
279 | 5 | 3A/5 | DA+3 | Sandy | 2025-04-03 | 2025-04-08 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Rudra | Nishit | Completed | 314.284
280 | 6 | 32/5 | DA+9 | 2MRC Sandy | 2025-03-10 | 2025-04-08 | vishwas construction | 323.91 | 4.07 | 47.75 | 3.949 | 1.366 | 10.51 | Susheel | Nishit | Completed | 399.908
281 | 7 | 3A/4 | DA+0 | Sandy | 2025-04-08 | 2025-04-10 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Rudra | Nishit | Completed | 287.984
282 | 8 | 32/6 | DA+9 | 2MRC Sandy | 2025-03-06 | 2025-04-11 | vishwas construction 2 | 323.91 | 4.07 | 47.75 | 3.949 | 1.366 | 10.51 | Susheel | Pradeep Singh | Completed | 399.908
283 | 9 | 3A/3 | DA+0 | Sandy | 2025-04-10 | 2025-04-12 | Karni Kripa Trading Company | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Rudra | Nishit | Completed | 287.984
284 | 10 | 35/3 | DA-3 | Sandy | 2025-03-21 | 2025-04-12 | Ruhela Brothers | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Susheel | saheb guchait | Completed | 287.984
285 | 11 | 33/1 | DA+9 | 2MRC Sandy | 2025-03-01 | 2025-04-14 | vishwas construction 2 | 323.91 | 4.07 | 47.75 | 3.949 | 1.366 | 10.51 | Abul | Pradeep Singh | Completed | 399.908
286 | 12 | 35/2 | DA+6 | Sandy | 2025-04-09 | 2025-04-15 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Susheel | Saheeb | Completed | 314.284
287 | 13 | 3A/2 | DA+3 | Sandy | 2025-04-10 | 2025-04-15 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Rudra | Nishit | Completed | 314.284
288 | 14 | 14/0 | DD60+18 | 2MRC Sandy | 2025-03-27 | 2025-04-16 | Protek infra | 1071.875 | 14.28 | 144.04 | 18.759 | 4.978 | 38.62 | Sanjay | Nishit | Completed | 1215.152
289 | 15 | 33/0 | DB1+9 | 2MRC Sandy | 2025-02-23 | 2025-04-17 | vishwas construction 2 | 484.04 | 6.23 | 78.87 | 4.753 | 2.709 | 15.56 | Susheel | Pradeep Singh | Completed | 658.372
290 | 16 | 3A/0 | DD45+3 | Sandy | 2025-04-08 | 2025-04-18 | Vishwas Construction 1 | 876 | 11.58 | 118.71 | 10.694 | 2.4947 | 27.19 | chetram | Nishit | Completed | 1000.632
291 | 17 | 3B/3 | DA+6 | Sandy | 2025-04-16 | 2025-04-19 | Karni Kripa Trading Company | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Rudra | Nishit | Completed | 314.284
292 | 18 | 21/3 | DA+6 | Sandy | 2025-03-20 | 2025-04-22 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | suraj | saheb guchait | Completed | 314.284
293 | 19 | 2A/6 | DA+6 | Sandy | 2025-04-19 | 2025-04-23 | Vishwas Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Chetram | Nishit | Completed | 314.284
294 | 20 | 21/2 | DA+6 | Sandy | 2025-03-20 | 2025-04-24 | Bajarang Nath | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | suraj | saheb guchait | Completed | 314.284
295 | 21 | 8A/0 | DB1+12 | Sandy | 2025-04-16 | 2025-04-25 | Protek infra | 462.88 | 5.94 | 67.91 | 3.1508 | 1.752 | 12.64 | Aman | Nishit | Completed | 569.416
296 | 22 | 4/0 | DB2+9 | Sandy | 2025-04-20 | 2025-04-25 | Karni Kripa Trading Company | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Rudra | Nishit | Completed | 723.096
297 | 23 | 21/1 | DA+0 | Sandy | 2025-04-23 | 2025-04-29 | Bajarang Nath | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Rudra | saheb guchait | Completed | 287.984
298 | 1 | 35/10 | DA+3 | Sandy | 2025-04-25 | 2025-05-02 | Ruhela Brothers | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Rudra | saheb guchait | Completed | 314.284
299 | 2 | 9/0 | DB1+12 | Sandy | 2025-04-11 | 2025-05-03 | Dev narayan traders | 462.88 | 5.94 | 67.91 | 3.1508 | 1.752 | 12.64 | Aman | Nishit | Completed | 569.416
300 | 3 | 45/0 | DB1+9 | Sandy | 2025-04-29 | 2025-05-05 | Karni Kripa Trading Company | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Rudra | saheb guchait | Completed | 589.972
301 | 4 | 46/0 | DB1+12 | Sandy | 2025-05-05 | 2025-05-07 | Karni Kripa Trading Company | 462.88 | 5.94 | 67.91 | 3.1508 | 1.752 | 12.64 | Rudra | saheb guchait | Completed | 569.416
302 | 5 | 20/6 | DA-3 | Sandy | 2025-04-26 | 2025-05-09 | Vishwas Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Suraj | Nishit | Completed | 287.984
303 | 6 | 21/0 | DB1+0 | Sandy | 2025-04-28 | 2025-05-13 | Bajarang Nath | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01 | Aman | Nishit | Completed | 585.184
304 | 7 | 20/5 | DA+0 | Sandy | 2025-05-05 | 2025-05-13 | Vishwas Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Suraj | Nishit | Completed | 287.984
305 | 8 | 20/4 | DA+3 | Sandy | 2025-05-10 | 2025-05-18 | Vishwas Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Aman | Nishit | Completed | 314.284
306 | 9 | 20/3 | DA+1.5 | Sandy | 2025-05-18 | 2025-05-22 | Vishwas Construction | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39 | Sanjay | Nishit | Completed | 314.284
307 | 10 | 19/0 | DD60+3 | Sandy | 2025-05-18 | 2025-05-26 | Karni Kripa Trading Company | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99 | Aman/ Suraj | Nishit | Completed | 1587.98
308 | 1 | 20/0 | DD60+3 | Sandy | 2025-05-18 | 2025-06-02 | Karni Kripa Trading Company | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99 | Suraj | Nishit | Completed | 1587.98
309 | 2 | 11/0 | DD45+0 | Sandy | 2025-05-27 | 2025-06-08 | Protek infra | 852 | 11.25 | 116.5 | 10.088 | 2.4947 | 26.28 | Suraj | Nishit | Completed | 981.5
310 | 3 | 12/0 | DB1+9 | Sandy | 2025-06-08 | 2025-06-14 | Protek infra | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2 | Suraj | Nishit | Completed | 589.972
311 | 4 | 1/0 | DD60+0 | Sandy | 2025-06-12 | 2025-06-27 | Vishwas Construction | 997.27 | 13.25 | 185.89 | 10.698 | 3.1593 | 35.48 | Rudra | Chinmoy samnta | Completed | 1545.42
312 | 1 | 2A/1 | DA+0 | Sandy | 2025-06-27 | 2025-07-05 | Vishwas Construction | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49 | Rudra | Nishit | Completed | 287.984
313 | 2 | 2A/0 | DD45+0 | Sandy | 2025-07-05 | 2025-07-14 | Vishwas Construction | 852 | 11.25 | 116.5 | 10.088 | 2.4947 | 26.28 | Rudra | Nishit | Completed | 981.5
314 | 1 | 36B/0-N | DB2+9 | Sandy | 2026-01-10 | 2026-01-23 | Bajarang Nath | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Susheel Kumar | Nishit | Completed | 723.096
315 | 2 | 36C/0-N | DC2+15 | Sandy | 2026-01-24 | 2026-02-08 | Bajarang Nath | 689.93 | 9.03 | 112.22 | 5.8468 | 2.2349 | 21.18 | Susheel Kumar | Nishit | Completed | 937.492
316 | 3 | 37/0-N | DB2+9 | Sandy | 2026-02-22 | 2026-03-05 | Bajarang Nath | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2 | Susheel Kumar | Nishit | Completed | 723.096
|  |  | Vlook up Data:- |  |  |  |  | Excavation | M10 | M20 | Steel | Stubs | Revenue
|  |  | DA-3 |  |  |  |  | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49
|  |  | DA-1.5 |  |  |  |  | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49
|  |  | DA+0 |  |  |  |  | 271.04 | 3.36 | 34.15 | 1.599 | 0.866 | 6.49
|  |  | DA+1.5 |  |  |  |  | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39
|  |  | DA+3 |  |  |  |  | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39
|  |  | DA+4.5 |  |  |  |  | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39
|  |  | DA+6 |  |  |  |  | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39
|  |  | DA+9 |  |  |  |  | 289.84 | 3.61 | 37.3 | 2.093 | 0.866 | 7.39
|  |  | DB1+0 |  |  |  |  | 479.12 | 6.16 | 69.76 | 3.26 | 1.768 | 13.01
|  |  | DB1+3 |  |  |  |  | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2
|  |  | DB1+6 |  |  |  |  | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2
|  |  | DB1+9 |  |  |  |  | 484.04 | 6.23 | 70.32 | 3.372 | 1.768 | 13.2
|  |  | DB1+12 |  |  |  |  | 462.88 | 5.94 | 67.91 | 3.1508 | 1.752 | 12.64
|  |  | DB2+0 |  |  |  |  | 560.96 | 7.27 | 85.67 | 4.1548 | 1.768 | 16
|  |  | DB2+2 |  |  |  |  | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2
|  |  | DB2+3 |  |  |  |  | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2
|  |  | DB2+6 |  |  |  |  | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2
|  |  | DB2+9 |  |  |  |  | 566.29 | 7.34 | 86.35 | 4.2604 | 1.768 | 16.2
|  |  | DC1+0 |  |  |  |  | 606.15 | 7.89 | 93.55 | 4.8168 | 2.3488 | 17.75
|  |  | DC1+3 |  |  |  |  | 609.84 | 7.94 | 94.04 | 4.794 | 2.3488 | 17.8
|  |  | DC1+6 |  |  |  |  | 609.84 | 7.94 | 94.04 | 4.794 | 2.3488 | 17.8
|  |  | DC1+9 |  |  |  |  | 609.84 | 7.94 | 94.04 | 4.794 | 2.3488 | 17.8
|  |  | DC2+0 |  |  |  |  | 693.86 | 9.09 | 115.43 | 5.691 | 2.3488 | 21.43
|  |  | DC2-3 |  |  |  |  | 693.86 | 9.09 | 115.43 | 5.691 | 2.3488 | 21.43
|  |  | DC2+3 |  |  |  |  | 713.71 | 9.36 | 115.67 | 6.206 | 2.3488 | 22.01
|  |  | DC2+6 |  |  |  |  | 713.71 | 9.36 | 115.67 | 6.206 | 2.3488 | 22.01
|  |  | DC2+9 |  |  |  |  | 713.71 | 9.36 | 115.67 | 6.206 | 2.3488 | 22.01
|  |  | DC2+15 |  |  |  |  | 689.93 | 9.03 | 112.22 | 5.8468 | 2.2349 | 21.18
|  |  | DD45-3 |  |  |  |  | 852 | 11.25 | 116.5 | 10.088 | 2.4947 | 26.28
|  |  | DD45+0 |  |  |  |  | 852 | 11.25 | 116.5 | 10.088 | 2.4947 | 26.28
|  |  | DD45+3 |  |  |  |  | 876 | 11.58 | 118.71 | 10.694 | 2.4947 | 27.19
|  |  | DD45+6 |  |  |  |  | 876 | 11.58 | 118.71 | 10.694 | 2.4947 | 27.19
|  |  | DD45+9 |  |  |  |  | 876 | 11.58 | 118.71 | 10.694 | 2.4947 | 27.19
|  |  | DD60+0 |  |  |  |  | 997.27 | 13.25 | 185.89 | 10.698 | 3.1593 | 35.48
|  |  | DD60+3 |  |  |  |  | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99
|  |  | DD60+6 |  |  |  |  | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99
|  |  | DD60+9 |  |  |  |  | 1025.83 | 13.65 | 190.99 | 11.554 | 3.1593 | 36.99
|  |  | DD60+18 |  |  |  |  | 1042.68 | 13.88 | 194 | 12.18 | 3.1593 | 37.98
|  |  | DD60+25 |  |  |  |  | 1042.68 | 13.88 | 194 | 12.18 | 3.1593 | 37.98
|  |  | DD60+35 |  |  |  |  | 999.64 | 13.28 | 186.31 | 11.581 | 3.38 | 36.39
|  |  | DA 2M RC |  |  |  |  | 323.91 | 4.07 | 47.75 | 3.949 | 1.366 | 10.51
|  |  | DB 2M RC |  |  |  |  | 484.04 | 6.23 | 78.87 | 4.753 | 2.709 | 15.56
|  |  | DD60+18 2M RC |  |  |  |  | 1071.875 | 14.28 | 144.04 | 18.759 | 4.978 | 38.62
Formulas:
Complete = [Start]+4

## JUMPER Details
Jumper details of Project
SL. No. | Loc No. | Type of Tower | Short name | Jumper length | Jumper status can be completed | Jumper status | Done by
1 | 1/0 | DD60+0 | DD60 | 918
2 | 2A/0 | DD45+0 | DD45 | 918 |  | Completed | Rahim Khan
3 | 3A/0 | DD45+3 | DD45 | 918 |  | Completed | Rahim Khan
4 | 3B/0 | DB1+9 | DB1 | 828 |  | Completed | Rahim Khan
5 | 4/0 | DB2+9 | DB2 | 828 |  | Completed | Rahim Khan
6 | 4A/0 | DB1+3 | DB1 | 828 |  | Completed | Rahim Khan
7 | 5/0 | DB1+6 | DB1 | 828 |  | Completed | Rahim Khan
8 | 5A/0 | DB1+12 | DB1 | 828 |  | Completed | Rahim Khan
9 | 6/0 | DB1+9 | DB1 | 828 |  | Completed | Rahim Khan
10 | 7/0 | DB2+0 | DB2 | 828 |  | Completed | Rahim Khan
11 | 7A/0 | DB1+6 | DB1 | 828 |  | Completed | Rahim Khan
12 | 8/0 | DB1+0 | DB1 | 828 |  | Completed | Rahim Khan
13 | 8A/0 | DB1+12 | DB1 | 828 |  | Completed | Rahim Khan
14 | 9/0 | DB1+12 | DB1 | 828 |  | Completed | Rahim Khan
15 | 10/0 | DB1+6 | DB1 | 828 |  | Completed | Rahim Khan
16 | 11/0 | DD45+0 | DD45 | 918 |  | Completed | Rahim Khan
17 | 12/0 | DB1+9 | DB1 | 828
18 | 13/0 | DD60+9 | DD60 | 918
19 | 13A/0 | DB1+9 | DB1 | 828
20 | 14/0 | DD60+25 | DD60 | 918
21 | 15/0 | DD60+25 | DD60 | 918
22 | 16/0 | DC2+0 | DC2
23 | 17/0 | DC1+3 | DC1
24 | 18/0 | DB2+6 | DB2 | 828
25 | 19/0 | DD60+3 | DD60 | 918
26 | 20/0 | DD60+3 | DD60 | 918
27 | 21/0 | DB1+0 | DB1 | 828
28 | 22/0 | DC2+15 | DC2
29 | 23/0 | DB2+9 | DB2 | 828
30 | 23A/0 | DB1+9 | DB1 | 828
31 | 24/0 | DD60+18 | DD60 | 918
32 | 25/0 | DD60+18 | DD60 | 918
33 | 26/0 | DD60+35 | DD60 | 918
34 | 27/0 | DD60+35 | DD60 | 918
35 | 28/0 | DC2+0 | DC2
36 | 29/0 | DC1+0 | DC1
37 | 29A/0 | DB1+0 | DB1 | 828 |  | Completed | SK infra
38 | 30/0 | DB1+0 | DB1 | 828 |  | Completed | SK infra
39 | 31/0 | DB1+0 | DB1 | 828 |  | Completed | SK infra
40 | 32/0 | DB2+0 | DB2 | 828 |  | Completed | SK infra
41 | 32A/0 | DB1+9 | DB1 | 828 |  | Completed | SK infra
42 | 33/0 | DB1+9 | DB1 | 828 |  | Completed | SK infra
43 | 34/0 | DB1+6 | DB1 | 828 |  | Completed | SK infra
44 | 35/0 | DB2+0 | DB2 | 828
45 | 36/0 | DB2+3 | DB2 | 828
46 | 36A/0 | DB1+9 | DB1 | 828
47 | 36B/0-N | DB2+9 | DB2 | 828
48 | 36C/0-N | DC2+15 | DC2
49 | 37/0-N | DB2+9 | DB2 | 828
50 | 37A/0 | DB1+0 | DB1 | 828
51 | 38/0 | DB1+3 | DB1 | 828 |  | Completed | SK infra
52 | 39/0 | DB2+0 | DB2 | 828 |  | Completed | SK infra
53 | 40/0 | DB1+6 | DB1 | 828
54 | 40A/0 | DB1+9 | DB1 | 828
55 | 41/0 | DB1+9 | DB1 | 828
56 | 42/0 | DB2+0 | DB2 | 828
57 | 42A/0 | DB1+9 | DB1 | 828
58 | 43/0 | DB1+0 | DB1 | 828
59 | 43A/0 | DC2+0(DCT) | DCT
60 | 44/0 | DB1+6 | DB1 | 828
61 | 45/0 | DB1+9 | DB1 | 828
62 | 46/0 | DB1+12 | DB1 | 828

## Crossing status
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Sl. | From | To | Sections in (mtrs) | Name of Crossing | Owner | Approval status | Status |  |  | Remarks
No | [6 empty] | FDN | ERE | STR
Power Line Crossing–6 nos
1 | AP 12 | AP 13 | 329.728 | 132 KV S/C BKN-LKS T/L | RVPN | Approved | AP12-Completed AP13-Completed | AP12-Completed AP13-Completed
2 | AP 14 | AP 15 | 223.816 | 400 KV D/C SUR-BKN | ADANI | Approved | AP14-Completed AP15-Completed | AP14-Completed AP15-Completed | Completed
3 | AP 22 | AP 23 | 259.048 | 220 KV S/C SUR-BKN | RVPN | Approved | AP22-Completed AP23-Completed | AP22-Completed AP23-Completed | WIP
4 | AP 24 | AP 25 | 244.029 | 400 KV S/C STP-BKN T/L | RVPN | Approved | AP24-Completed AP25-Completed | AP24-Completed AP25-Completed | Completed
5 | AP 26 | AP 27 | 203.479 | 765 KV D/C BKN-MGA T/L | PGCIL | Approved | AP26-Completed AP27-Completed | AP26-Completed AP27-Completed
6 | AP45 | AP46 | 208 | 132 KV D/C Halsar-Patlisar T/L | RVPN | Approved | AP45-Completed AP46-Completed | AP45-Complete AP46-Complete
NH Crossing-2 nos
7 | AP 11 | AP 12 | 242.893 | NH - 62 |  | Approved | AP-11-Completed AP 12-Completed | AP-11-Completed AP 12-Completed | Completed
8 | AP 28 | AP 29 | 211.209 | Amristar - Jamnagar Expressway NH-754 A |  | Approved | AP-28-Completed AP 29-Completed | AP-28-Completed AP 29-Completed | Completed
SH Crossing-2 nos
9 | AP 2 | AP 3 | 311.126 | SH - 03
10 | AP 32 | AP 33 | 4333.369 | SH - 93
Railway Crossing-1 nos
11 | AP 19 | AP 20 | 279.36 | Single Line Electrified Line |  | Approved | AP-19-Completed AP 20- Completed | AP-19-Completed AP 20- Completed
Cannal Crossing-1 nos
12 | AP 15 | AP 16 | 5020 | Canal
3/3
3/4
3/5
3/6
3/7
3/8
3/9

## ROW Tracker
ROW STATUS | [7 empty] | 24.07.2026
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 LOA Value: 378 Crore
ROW Details
S.No | Loc. No. | T/Type | Activity | Date of 1st approach | Date of last approach | Date of Resolution | Duration of ROW (Days) | Nature of hindrance | Brief description on resolution | Name of Farmer | Mobile no. | Vill. Name | Tehsil
1 | 10/1 | DA+3 | Foundation | 2024-06-03 | 2024-06-06 | 2024-06-07 | 4 | Land owner stopped the work and not allowing to work till finalisation of compentation amount. | Resolved | Bhagirath | 9784543356 | Jaisa, Dhirera(PO) | Lunkaransar
2 | 10/2 | DA+3 | Foundation | 2024-06-03 | 2024-06-06 | 2024-06-07 | 4 | Land owner stopped the work and not allowing to work till finalisation of compentation amount. | Resolved | Devi Lal | 9950185902 | Jaisa, Dhirera(PO) | Lunkaransar
3 | 15/2 | DA+3 | Foundation | 2024-06-14 | 2024-06-17 | 2024-06-17 | 3 | Land owner stopped the work and not allowing to work till finalisation of compentation amount. | Resolved | Muniram Moond | 9929783632 | Meharana | Lunkaransar
4 | 15/6 | DA+9 | Back filling | 2024-06-29 | 2024-07-10 | 2024-07-10 | 11 | Area damage measurement isssue | Resolved | Mukharam | 9950488419 | Dheereran | Lunkaransar
5 | 15/7 | DA+0 | Foundation | 2024-06-29 | 2024-07-10 | 2024-07-10 | 11 | Area damage measurement isssue | Resolved | Hetram godara | 8003383931 | Dheereran | Lunkaransar
6 | 31/8 | DA+0 | Foundation | 2024-07-05 | 2024-07-06 | 2024-07-06 | 1 | Row in foundation work due to Obstruction by land owner | Resolved
7 | 8/8 | DA+9 | Foundation | 2024-07-05 | 2024-07-08 | 2024-07-09 | 4 | Row in foundation work due to Obstruction by land owner | Resolved
8 | 15/11 | DA+0 | Foundation | 2024-07-08 | 2024-07-10 | 2024-07-10 | 2 | Row in foundation work due to Obstruction by land owner | Resolved | Om Prakash Godhra (2 Leg) MukhRam (2 Leg) | 6377579215 9587202243 | Dheereran | Lunkaransar
9 | 31/10 | DA+4.5 | Foundation | 2024-07-05 | 2024-07-23 | 2024-07-23 | 18 | Row in foundation work due to Obstruction by land owner | Resolved | Jetharam Sharma | 9443165335
10 | 27/4 | DA+1.5 | Foundation | 2024-07-19 | 2024-08-06 | 2024-08-06 | 18 | Row in foundation work due to Obstruction by land owner | Resolved
11 | 20/1 | DA-3 | Foundation | 2024-06-20 | 2025-02-04 | 2025-02-04 | 229 | Row in foundation work due to Obstruction by land owner | Resolved | Shivpal Singh & Villagers | 6350519091 | Dulmera | Lunkaransar
12 | 20/2 | DA-3 | Foundation | 2024-06-20 | 2025-02-04 | 2025-02-04 | 229 | Row in foundation work due to Obstruction by land owner | Resolved
13 | 20/3 | DA+1.5 | Foundation | 2024-06-20 | 2025-05-14 | 2025-05-14 | 328 | Row in foundation work due to Obstruction by land owner | Resolved
14 | 20/4 | DA+3 | Foundation | 2024-06-20 | 2025-05-10 | 2025-05-10 | 324 | Row in foundation work due to Obstruction by land owner | Resolved
15 | 20/5 | DA+0 | Foundation | 2024-06-20 | 2025-05-05 | 2025-05-05 | 319 | Row in foundation work due to Obstruction by land owner | Resolved | Dungar Ram | 9509364739 | Kujti | Lunkaransar
16 | 20/6 | DA-3 | Foundation | 2024-06-20 | 2025-04-20 | 2025-04-20 | 304 | Row in foundation work due to Obstruction by land owner | Resolved
17 | 21/0 | DB1+0 | Foundation | 2024-08-09 | 2025-04-28 | 2025-04-28 | 262 | Row in foundation work due to Obstruction by land owner | Resolved
18 | 21/1 | DA+0 | Foundation | 2024-08-09 | 2025-04-23 | 2025-04-23 | 257 | Row in foundation work due to Obstruction by land owner | Resolved
19 | 21/2 | DA+6 | Foundation | 2024-08-09 | 2025-03-20 | 2025-03-20 | 223 | Row in foundation work due to Obstruction by land owner | Resolved
20 | 21/3 | DA+6 | Foundation | 2024-08-09 | 2025-02-19 | 2025-02-19 | 194 | Row in foundation work due to Obstruction by land owner | Resolved
21 | 21/4 | DA+0 | Foundation | 2024-08-09 | 2025-02-06 | 2025-02-06 | 181 | Row in foundation work due to Obstruction by land owner | Resolved
22 | 21/5 | DA+0 | Foundation | 2024-08-09 | 2025-02-06 | 2025-02-06 | 181 | Row in foundation work due to Obstruction by land owner | Resolved
23 | 22/0 | DC2+15 | Foundation | 2024-08-09 | 2024-12-29 | 2024-12-29 | 142 | Row in foundation work due to Obstruction by land owner | Resolved
24 | 9/6 | DA+3 | Foundation | 2024-07-07 | 2025-02-11 | 2025-02-11 | 219 | Row in foundation work due to Obstruction by land owner | Resolved | Pukhraj Godara | 9413384744 | Jessan | Lunkaransar
25 | 9/7 | DA+9 | Foundation | 2024-07-07 | 2025-02-11 | 2025-02-11 | 219 | Row in foundation work due to Obstruction by land owner | Resolved
26 | 9/8 | DA+0 | Foundation | 2024-07-07 | 2025-02-22 | 2025-02-22 | 230 | Row in foundation work due to Obstruction by land owner | Resolved
27 | 9/9 | DA+0 | Foundation | 2024-07-07 | 2025-02-11 | 2025-02-11 | 219 | Row in foundation work due to Obstruction by land owner | Resolved
28 | 27/2 | DA-1.5 | Foundation | 2024-07-19 | 2024-09-14 | 2024-09-14 | 57 | Row in foundation work due to Obstruction by land owner | Resolved | Tiku Ram Sinwar | 9461942441 | Sahjrasar | Lunkaransar
29 | 27/3 | DA+1.5 | Foundation | 2024-07-19 | 2024-09-29 | 2024-09-29 | 72 | Row in foundation work due to Obstruction by land owner | Resolved | Ramakant Saraswat | 9876037318 | Sahjrasar | Lunkaransar
30 | 27/5 | DA-1.5 | Foundation | 2024-07-19 | 2024-08-17 | 2024-08-17 | 29 | Row in foundation work due to Obstruction by land owner | Resolved | Choru Ram | 9928935365 | Sahjrasar | Lunkaransar
31 | 27/6 | DA-3 | Foundation | 2024-07-19 | 2024-10-06 | 2024-10-06 | 79 | Row in foundation work due to Obstruction by land owner | Resolved | Mukesh S/O Patram | 7297945033 | Sahjrasar | Lunkaransar
32 | 8/3 | DA+9 | Foundation | 2024-07-24 | 2024-12-07 | 2024-12-07 | 136 | Row in foundation work due to Obstruction by land owner | Resolved | Mangilal | 9983260872 | Doodiyali | Lunkaransar
33 | 8/4 | DA+6 | Foundation | 2024-07-24 | 2024-12-10 | 2024-12-10 | 139 | Row in foundation work due to Obstruction by land owner | Resolved | Ram Pratap | 9799581738 | Jasrasar | Lunkaransar
34 | 7A/5 | DA+3 | Foundation | 2024-07-25 | 2024-08-10 | 2024-08-10 | 16 | Row in foundation work due to Obstruction by land owner | Resolved | Bhagirth Tarad | 9351238162 | Haphasra | Lunkaransar
35 | 29/2 | DA+0 | Foundation | 2024-07-26 | 2024-10-16 | 2024-10-16 | 82 | Row in foundation work due to Obstruction by land owner | Resolved | Baldev Raj | 9414141385 | Sahjrasar | Lunkaransar
36 | 29/5 | DA+0 | Foundation | 2024-07-27 | 2024-07-29 | 2024-07-29 | 2 | Row in foundation work due to Obstruction by land owner | Resolved | Kishor Nai | 9828203300
37 | 8/11 | DA+9 | Foundation | 2024-07-28 | 2025-01-26 | 2025-01-26 | 182 | ROW for Approch (Kund) | Resolved | Bhagwana Ram | 9680661751 | Sodewali | Lunkaransar
38 | 15/4 | DA+6 | Foundation | 2024-06-12 | 2024-12-24 | 2024-12-24 | 195 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
39 | 15/1 | DA+6 | Foundation | 2024-06-12 | 2024-12-24 | 2024-12-24 | 195 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved | Jagdish Jyani | 9950997590 | Jessan | Lunkaransar
40 | 15/12 | DA+6 | Foundation | 2024-07-17 | 2024-12-24 | 2024-12-24 | 160 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved | Bhawani Shanker | 9660960166 | Dhirera | Lunkaransar
41 | 29A/1 | DA+6 | Foundation | 2024-07-31 | 2024-08-04 | 2024-08-04 | 4 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved | Bajrang das S/o Ramrakh das Poonam das s/o Nayak das | 9001870250 | Sahjrasar | Lunkaransar
42 | 29A/2 | DA+6 | Foundation | 2024-07-31 | 2024-08-04 | 2024-08-04 | 4 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved | Bajrang das S/o Ramrakh das | 9001870250 | Sahjrasar | Lunkaransar
43 | 29A/4 | DA+3 | Foundation | 2024-08-02 | 2024-08-17 | 2024-08-17 | 15 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
44 | 29A/5 | DA+6 | Foundation | 2024-08-02 | 2024-08-20 | 2024-08-20 | 18 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
45 | 5/2 | DA+9 | Foundation | 2024-08-02 | 2024-09-19 | 2024-09-19 | 48 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
46 | 5/4 | DA-1.5 | Foundation | 2024-08-02 | 2024-08-06 | 2024-08-06 | 4 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
47 | 7/2 | DA+6 | Foundation | 2024-08-02 | 2024-11-21 | 2024-11-21 | 111 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
48 | 7/3 | DA+9 | Foundation | 2024-08-02 | 2024-10-03 | 2024-10-03 | 62 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
49 | 31/4 | DA-1.5 | Foundation | 2024-08-02 | 2024-08-02 | 2024-08-07 | 5 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
50 | 7A/4 | DA+3 | Foundation | 2024-08-18 | 2024-08-21 | 2024-08-21 | 3 | Foundation works stopped by local villegers at this location | Resolved
51 | 32/1 | DA+6 | Foundation | 2024-08-20 | 2024-09-25 | 2024-09-25 | 36 | Works stopped due to ROW by land owners. | Resolved | Suresh Rathi | 9417442909 | Kalu
52 | 7A/3 | DA+3 | Foundation | 2024-08-20 | 2024-09-06 | 2024-09-06 | 17 | Land owners is not agree to construct tower in their land | Resolved
53 | 7A/2 | DA+3 | Foundation | 2024-08-20 | 2024-08-31 | 2024-08-31 | 11 | Land owners is not agree to construct tower in their land | Resolved
54 | 7A/1 | DA+1.5 | Foundation | 2024-08-20 | 2024-08-26 | 2024-08-26 | 6 | Land owners is not agree to construct tower in their land | Resolved
55 | 33/2 | DA+9 | Foundation | 2024-08-26 | 2024-11-08 | 2024-11-08 | 74 | Land owners is not agree to construct tower in their land | Resolved | Bhagwana Ram | 9694236631 | Nathusar | Lunkarasar
56 | 33/8 | DA+3 | Foundation | 2024-08-26 | 2024-10-22 | 2024-10-22 | 57 | Landowner demanded to high compensation | Resolved | Chhelu charan | 8107475410 | Nathusar | Lunkarasar
57 | 33/9 | DA+1.5 | Foundation | 2024-08-26 | 2024-10-22 | 2024-10-22 | 57 | Landowner demanded to high compensation | Resolved | Jivraj Charan | 9549065761 | Nathusar | Lunkarasar
58 | 33/5 | DA+0 | Foundation | 2024-08-31 | 2024-09-09 | 2024-10-17 | 47 | Landowner demanded to high compensation | Resolved | Hardevaram | 9024013985 | Ranwasar | Lunkarasar
59 | 29/1 | DA+6 | Foundation | 2024-08-28 | 2024-09-02 | 2024-09-02 | 5 | Landowner demanded to high compensation | Resolved | Pappu Das | 8290697615 | Sahajrasar | Lunkaransar
60 | 27/1 | DA+9 | Foundation | 2024-08-31 | 2024-09-20 | 2024-09-20 | 20 | Landowner demanded to high compensation | Resolved | Mohanram Jangir | 8904727514 | Sahajrasar | Lunkaransar
61 | 36A/1 | DA+3 | Foundation | 2024-09-10 | 2024-09-11 | 2024-09-11 | 1 | Landowner demanded to high compensation | Resolved | Jetharam | 9137269295 | Somasar | Lunkaransar
62 | 3/5 | DA+3 | Excavation | 2024-10-01 | 2025-02-01 | 2025-02-05 | 127 | Landowner not allowing to work in their field | Resolved | Route Diverted
63 | 4/0 | DB2+9 | Foundation | 2024-09-26 | 2025-04-19 | 2025-04-19 | 205 | Landowner not allowing to work in their field | Resolved | Route Diverted
64 | 4/1 | DA+6 | Foundation | 2024-09-26 | 2025-02-01 | 2025-02-05 | 132 | Foundation kept on hold Due to Sunsure Objection | Resolved | Route Diverted
65 | 4/2 | DA+3 | Foundation | 2024-09-26 | 2025-02-01 | 2025-02-05 | 132 | Foundation kept on hold Due to Sunsure Objection | Resolved | Route Diverted
66 | 4/3 | DA+3 | Foundation | 2024-09-26 | 2025-02-01 | 2025-02-05 | 132 | Foundation kept on hold Due to Sunsure Objection | Resolved | Route Diverted
67 | 4/4 | DA+6 | Foundation | 2024-09-26 | 2025-02-01 | 2025-02-05 | 132 | Foundation kept on hold Due to Sunsure Objection | Resolved | Route Diverted
68 | 5/0 | DB1+6 | Foundation | 2024-09-15 | 2025-03-05 | 2025-03-05 | 171 | Landowner not allowing to work in their field | Resolved
69 | 5/1 | DA+6 | Foundation | 2024-09-15 | 2025-03-11 | 2025-03-11 | 177 | Landowner not allowing to work in their field | Resolved
70 | 5/5 | DA+6 | Foundation | 2024-09-15 | 2024-10-18 | 2024-10-18 | 33 | Landowner not allowing to work in their field | Resolved
71 | 6/0 | DB1+9 | Foundation | 2024-09-20 | 07-10-24 | 07-10-24 | 17 | Landowner not allowing to work in their field | Resolved
72 | 6/5 | DA+9 | Foundation | 2024-09-20 | 2024-10-16 | 2024-10-16 | 26 | Landowner demanded to high compensation | Resolved
73 | 6/7 | DA+1.5 | Foundation | 2024-09-23 | 2024-10-11 | 2024-10-11 | 18 | Landowner demanded to high compensation | Resolved
74 | 6/8 | DA+3 | Foundation | 2024-09-23 | 2024-10-26 | 2024-10-26 | 33 | Landowner demanded to high compensation | Resolved
75 | 35/2 | DA+6 | Foundation | 2024-09-27 | 2024-10-24 | 2024-10-24 | 27 | Landowner demanded to high compensation | Resolved | Ashuram Sinvar | 8696414081 | Nathusar | Lunkaransar
76 | 37/4 | DA+9 | Foundation | 2024-10-03 | 2024-11-11 | 2024-11-11 | 39 | Landowner demanded to high compensation | Resolved | OM Das | 9649766361 | Panpaliya | Lunkaransar
77 | 37/5 | DA+3 | Foundation | 2024-10-03 | 2024-11-16 | 2024-11-16 | 44 | Landowner demanded to high compensation | Resolved | Narsi Das | 7568731460 | Panpaliya | Lunkaransar
78 | 34/0 | DB1+6 | Foundation | 2024-10-16 | 2024-11-10 | 2024-11-10 | 25 | Landowner demanded to high compensation | Resolved
79 | 3/0 | DB2+0 | Foundation | 2024-10-16 | 2025-02-01 | 2025-02-05 | 112 | Row due to Sunsure Objection | Resolved | Route Diverted
80 | 3/1 | DA+3 | Foundation | 2024-10-16 | 2025-02-01 | 2025-02-05 | 112 | Row due to Sunsure Objection | Resolved | Route Diverted
81 | 3/2 | DA+6 | Foundation | 2024-10-16 | 2025-02-01 | 2025-02-05 | 112 | Row due to Sunsure Objection | Resolved | Route Diverted
82 | 3/3 | DA+3 | Foundation | 2024-10-16 | 2025-02-01 | 2025-02-05 | 112 | Row due to Sunsure Objection | Resolved | Route Diverted
83 | 42/1 | DA+3 | Foundation | 2024-12-11 | 2025-01-02 | 2025-01-02 | 22 | Landowner demanded to high compensation | Resolved
84 | 43/0 | DB1+0 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner not allowing to work in their field | Resolved
85 | 43/1 | DA-1.5 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
86 | 43/2 | DA+6 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
87 | 43/3 | DA-1.5 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
88 | 43/4 | DA+0 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
89 | 43A/0 | DC2+0 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
90 | 43/6 | DA+3 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
91 | 43/7 | DA+0 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
92 | 43/8 | DA+9 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
93 | 44/0 | DB1+6 | Foundation | 2024-12-11 | 2024-12-25 | 2024-12-25 | 14 | Landowner demanded to high compensation | Resolved
94 | 35/3 | DA-3 | Foundation | 2025-02-10 | 2025-03-20 | 2025-03-20 | 38 | Landowner not allowing to work in their field due to approch issue | Resolved
95 | 25/0 | DD60+18 | Foundation | 2025-02-09 | 2025-02-23 | 2025-02-23 | 14 | Landowner demanded to high compensation | Resolved
96 | 26/0 | DD60+35 | Foundation | 2025-02-09 | 2025-02-16 | 2025-02-16 | 7 | Landowner demanded to high compensation | Resolved
97 | 27/0 | DD60+35 | Foundation | 2025-02-09 | 2025-02-13 | 2025-02-13 | 4 | Landowner demanded to high compensation | Resolved
98 | 4/5 to 7/0 |  | Foundation | 2024-11-07 | 2025-02-06 | 2025-02-06 | 91 | during meeting with PGCIL ON dtd 06-02-25. We can work in the section from 4A/5 to 7/0 | Resolved
99 | Gantry to 4/4 |  | Survey | 2024-11-05 | 2025-01-13 | 2025-02-19 | 106 | Further work on hold from Gantry to 4A/4 -25 Locations affected (12 locations for Foundation work and 25 locations for tower erection work) due to Sunsure objection. | Resolved
100 | AP-34 to AP 35 |  | Stringing | 2025-02-09 | 2025-02-20 | 2025-02-20 | 11 | Gang idled since 09th Feb to 20 FEB'25 due to no availibility of Shut down on time . | Resolved
101 | 44/1-AP46 |  | Foundation | 2025-02-08 | 2025-02-20 | 2025-02-20 | 12 | Gang idled since 09th Feb to 20 FEB'25 due to non availibility of working front. | Resolved
102 | 35/10 | DA+3 | Foundation | 2025-02-24 | 2025-10-24 | 2025-10-24 | 242 | ROW in Pit marking as Landowner not allowing for foundation. | Resolved
104 | AP'38/0-AP 39/0 |  | Stringing | 2025-03-21 | 2025-04-01 | 2025-04-01 | 11 | ROW Due to Farmer demand the Erection Payment. | Resolved | 38/5-Mahinder Singh 38/6-Raga Ram 38/10-Heernath 38/9-Gulab 38/8-Uda Ram 38/7-Karni Singh | 8094847479 6377448078 6378768222 9772445832 982834769 7665467026 | Patemdesar
105 | 38/4 | DA+1.5 | Stringing | 2025-03-21 | 2025-03-27 | 2025-03-27 | 6 | ROW Due to Farmer demand the Erection Payment. | Resolved
106 | 38/5 | DA+3 | Stringing | 2025-03-21 | 2025-03-27 | 2025-03-27 | 6 | ROW Due to Farmer demand the Erection Payment. | Resolved
107 | 36/0 | DB2+3 | Erection | 2025-02-21 | 2026-01-21 | 2026-01-21 | 334 | Landowner demanded to high compensation | Resolved | Mala Ram | 9828813423
108 | 37/2 | DA+3 | Erection | 2025-02-21 | 2026-01-10 | 2026-01-10 | 323 | Landowner demanded to high compensation | Resolved | Bhugna Ram | 9672784822
109 | 37/3 | DA-1.5 | Erection | 2025-02-21 | 2026-01-10 | 2026-01-10 | 323 | Landowner demanded to high compensation | Resolved | Shashi Ram Saran | 8890266896
110 | 37/0 | #N/A | Erection | 2025-02-21 |  |  |  | Landowner demanded to high compensation |  | Kisan Soma Sar | 8302174002
111 | 2A/6 | DA+6 | Foundation | 2025-03-29 | 2025-04-19 | 2025-04-19 | 21 | Landowner Not Allowed The Fdn Work | Resolved | Munni Nath | 8824821647
112 | 4/0 | DB2+9 | Foundation | 2025-03-29 | 2025-04-19 | 2025-04-19 | 0 | Landowner Not Allowed The Fdn Work | Resolved | Shi Ram | 9829622661
113 | 1/0,2A/0,2A/1 |  | Foundation | 2025-04-15 | 02-05-2025 | 02-05-2025 | 17 | Hold due to Gantry | Resolved
114 | 45/0 | DB1+9 | Foundation | 2025-04-26 | 2025-04-29 | 2025-04-29 | 3 | High Compensation Demand | Resolved | Gopal | 9950238877 | Bandnau
115 | 1/0 | DD60+0 | Foundation | 2025-05-03 | 2025-06-06 | 2025-06-06 | 34 | The farmer did not agree to install the tower in their field." | Resolved
116 | 2A/0 | DD45+0 | Foundation | 2025-04-15 | 2025-07-05 | 2025-07-05 | 81 | The farmer did not agree to install the tower in their field." | Resolved
117 | 2A/1 | DA+0 | Foundation | 2025-05-03 | 2025-06-27 | 2025-06-27 | 55 | The farmer did not agree to install the tower in their field." | Resolved
118 | 37/1 | #N/A | Erection | 2025-02-21 |  |  |  | Landowner demanded to high compensation
119 | 35/10 | DA+3 | Erection | 2025-07-05 | 2026-02-03 | 2026-02-03 | 213 | Landowner demanded to high compensation | Resolved
120 | 35/3 | DA-3 | Erection | 2025-07-05 | 2025-08-09 | 2025-11-28 | 146 | Landowner demanded to high compensation | Resolved
121 | 35/2 | DA+6 | Erection | 2025-07-05 | 2025-07-28 | 2025-07-28 | 23 | Landowner demanded to high compensation | Resolved
122 | 33/9 | DA+1.5 | Erection | 2025-07-05 | 2025-08-17 | 2025-08-17 | 43 | Landowner demanded to high compensation | Resolved
123 | 33/7 | DA+6 | Erection | 2025-07-05 | 2025-07-22 | 2025-07-22 | 17 | Landowner demanded to high compensation | Resolved
124 | 33/4 | DA+3 | Erection | 2025-07-05 | 2025-09-04 | 2025-09-04 | 61 | Landowner demanded to high compensation | Resolved
125 | 33/3 | DA+3 | Erection | 2025-07-05 | 2025-08-29 | 2025-08-29 | 55 | Landowner demanded to high compensation | Resolved
126 | 33/2 | DA+9 | Erection | 2025-07-05 | 2025-08-09 | 2025-08-09 | 35 | Landowner demanded to high compensation | Resolved
127 | 33/1 | DA+9 | Erection | 2025-07-05 | 2025-08-24 | 2025-08-24 | 50 | Landowner demanded to high compensation | Resolved
128 | 33/0 | DB1+9 | Erection | 2025-07-05 | 2025-09-02 | 2025-09-02 | 59 | Landowner demanded to high compensation | Resolved
129 | 32A/1 | DA+6 | Erection | 2025-07-05 | 2025-08-13 | 2025-08-13 | 39 | Landowner demanded to high compensation | Resolved
130 | 32A/0 | DB1+9 | Erection | 2025-07-05 | 2025-07-31 | 2025-07-31 | 26 | Landowner demanded to high compensation | Resolved
131 | 31/3 | DA+3 | Erection | 2025-08-04 | 2025-08-12 | 2025-08-12 | 8 | Crop issue farmer not allow to work at site | Resolved
132 | 17/0 | DC1+3 | Erection | 2025-10-06 | 2025-11-19 | 2025-11-24 | 49 | Material unloaded at site team idle 45 Manpower from dated 06.10.2025 due to Guy rope ROW | Resolved
133 | 2A/0 | DD45+0 | Erection | 2025-08-22 | 2025-12-30 | 2025-12-30 | 130 | The demand for ₹8 lakh as advance payment is creating unnecessary hindrance and delaying the proceedings | Resolved
134 | 9/8 | DA+0 | Erection | 2025-08-01 | 2025-12-03 | 2025-12-03 | 124 | Verification regarding dispute between two lands/owners. | Resolved
135 | 11/0 | DD45+0 | Erection | 2025-08-01 | 2025-11-12 | 2025-11-12 | 103 | Cultivation | Resolved
136 | 13/0 | DD60+9 | Erection | 2025-09-03 | 2025-12-16 | 2025-12-16 | 104 | The demand for ₹10 lakh as advance payment is creating unnecessary hindrance and delaying the proceedings | Resolved
137 | 13A/0 | DB1+9 | Erection | 2025-09-03 | 2025-12-17 | 2025-12-17 | 105 | High Compensation Demand by Farmers | Resolved
138 | 14/0 | DD60+18 | Erection | 2025-09-03 | 2025-11-30 | 2025-11-30 | 88 | The demand for ₹13 to 14 lakh as advance payment is creating unnecessary hindrance and delaying the proceedings | Resolved
139 | 15/1 | DA+6 | Erection | 2025-09-03 | 2025-11-26 | 2025-11-26 | 84 | Non-release of payment AT 15/0 approach. | Resolved
140 | 15/9 | DA+0 | Erection | 2025-09-03 | 2025-11-22 | 2025-11-22 | 80 | Foundation payment pending due to non submission of documents by the landowners | Resolved
141 | 15/10 | DA-1.5 | Erection | 2025-09-03 | 2025-11-16 | 2025-11-16 | 74 | Cultivation | Resolved
142 | 15/11 | DA+0 | Erection | 2025-09-03 | 2025-12-05 | 2025-12-05 | 93 | delayed due to non-release of payment for approach road for foundation time | Resolved
143 | 15/12 | DA+6 | Erection | 2025-09-03 | 2025-11-25 | 2025-11-25 | 83 | The demand for ₹14 lakh as advance payment is creating unnecessary hindrance and delaying the proceedings | Resolved
144 | 16/0 | DC2+0 | Erection | 2025-09-03 | 2026-02-06 | 2026-04-12 | 221 | Work is delayed due to pending cost approval for the water pump and pond. | Resolved
145 | 21/3 | DA+6 | Erection | 2025-09-12 | 2025-11-19 | 2025-11-19 | 68 | Foundation payment pending due to non submission of documents by the landowners | Resolved
146 | 23A/0 | DB1+9 | Erection | 2025-09-12 | 2025-11-14 | 2025-11-14 | 63 | ROW | Resolved
147 | 27/1 | DA+9 | Erection | 2025-09-03 | 2025-11-16 | 2025-12-04 | 92 | ROW | Resolved
148 | 27/2 | DA-1.5 | Erection | 2025-09-03 | 2025-11-20 | 2025-11-20 | 78 | Work is to start first on loc no 27/1 and 27/3, and only afterward on loc no. 27/2. | Resolved
149 | 27/3 | DA+1.5 | Erection | 2025-09-03 | 2025-11-16 | 2025-11-27 | 85 | ROW | Resolved
150 | 29/2 | DA+0 | Erection | 2025-09-03 | 2025-12-10 | 2025-12-10 | 98 | cultivation , | Resolved
151 | 29A/3 | DA+6 | Erection | 2025-09-03 | 2025-11-25 | 2025-11-25 | 83 | cultivation | Resolved
152 | 30/5 | DA+0 | Erection | 2025-09-27 | 20-12-2025 | 20-12-2025 | 84 | cultivation | Resolved
153 | 43/0 | DB1+0 | Erection | 2025-08-03 | 2025-11-28 | 2025-11-28 | 117 | Work at the site has been delayed due to a high compensation demand from the landowner. The landowner is demanding approximately ₹9,00,000 for land and crop | Resolved
154 | 43/1 | DA-1.5 | Erection | 2025-08-03 | 2025-11-28 | 2025-11-28 | 117 | Work at the site has been delayed due to a high compensation demand from the landowner. The landowner is demanding approximately ₹9,00,000 for land and crop | Resolved
155 | 32/2 | DA+9 | Stringing | 2025-11-02 | 2025-11-18 | 2025-11-18 | 16 | Landowner demanded to high compensation | Resolved
156 | 33/5 | DA+0 | Stringing | 2025-11-02 | 2025-11-14 | 2026-01-03 | 62 | Landowner demanded to high compensation | Resolved
157 | 32A/1 | DA+6 | Stringing | 2025-11-02 | 2025-12-30 | 2025-12-30 | 58 | Landowner demanded to high compensation | Resolved
158 | N37/0 | DC2+15 | Foundation | 2025-12-24 | 2025-12-30 | 2025-12-30 | 6 | Tower dismantling should be commence, once land owner agreed | Resolved
159 | N37A/0 | DB2+9 | Foundation | 2026-02-03 | 2026-02-10 | 2026-02-10 | 7 | Due to the landowner demanding advance payment | Resolved
160 | 35/10 | DA+3 | Erection | 2026-02-05 | 2026-02-10 | 2026-02-10 | 5 | Due to the landowner demanding advance payment after administrative clearance | Resolved
161 | 3A/0 | DD45+3 | Stringing | 2026-02-04 | 2026-02-09 | 2026-02-09 | 5 | ROW work is delayed due to the landowner demanding higher compensation | Resolved
162 | 3B/0 | DB1+9 | Stringing | 2026-02-04 | 2026-02-08 | 2026-02-08 | 4 | ROW work is delayed due to the landowner demanding higher compensation | Resolved
163 | 43/0 | DB1+0 | Erection | 2026-02-07 | 2026-02-10 | 2026-02-10 | 3 | Due to pending payment from the landowner, the work has been delayed by 03 days | Resolved
164 | 31/9 | DA+1.5 | Stringing | 2026-02-04 | 2026-02-09 | 2026-02-09 | 5 | Old Payment pending | Resolved
165 | 33/6 | DA+6 | Stringing | 2026-01-25 | 2026-02-24 | 2026-02-24 | 30 | land owner not allowed to enter in the premises to erect the tower, | Resolved
166 | 33/7 | DA+6 | Stringing | 2026-01-25 | 2026-02-22 | 2026-02-22 | 28 | land owner not allowed to enter in the premises to erect the tower, | Resolved
167 | 3A/1 | DA+3 | Stringing | 2026-02-11 | 2026-02-12 | 2026-02-12 | 1 | land owner not allowed to enter in the premises | Resolved | Kayam Khan | 9929888158 | Kelan | Chhatargarh
168 | 3A/2 | DA+3 | Stringing | 2026-02-11 | 2026-02-12 | 2026-02-12 | 1 | land owner not allowed to enter in the premises | Resolved | Kayam Khan | 9929888158 | Kelan | Chhatargarh
169 | 40/1 | DA+9 | Final checking | 2026-02-07 |  |  |  | land owner not allowed to enter in the premises
170 | 40/8 | DA-1.5 | Final checking | 2026-02-07 |  | 2026-07-04 | 147 | land owner not allowed to enter in the premises | Resolved
171 | 40A/0 | DB1+9 | Final checking | 2026-02-07 |  |  |  | land owner not allowed to enter in the premises
172 | 40/10 | DA+3 | Final checking | 2026-02-07 |  |  |  | land owner not allowed to enter in the premises
173 | 15/9 | DA+0 | Final checking | 2026-02-07 |  |  |  | land owner not allowed to enter in the premises
174 | 13/0 | DD60+9 | Final checking | 2026-02-10 | 2026-03-17 | 2026-03-17 | 35 | land owner not allowed to enter in the premises | Resolved
175 | 13/0 | DD60+9 | Stringing | 2026-03-22 |  | 2026-03-27 | 5 | land owner not allowed to enter in the premises | Resolved
176 | 13A/0 | DB1+9 | Stringing | 2026-02-11 | 2026-03-27 | 2026-03-27 | 44 | land owner not allowed to enter in the premises | Resolved
177 | 30/3 | DA+3 | Stringing | 2026-02-18 | 2026-03-06 | 2026-03-06 | 16 | land owner not allowed to enter in the premises | Resolved
178 | 30/4 | DA+9 | Stringing | 2026-02-18 | 2026-02-22 | 2026-02-22 | 4 | land owner not allowed to enter in the premises | Resolved
179 | 30/5 | DA+0 | Stringing | 2026-02-18 | 2026-03-05 | 2026-03-05 | 15 | land owner not allowed to enter in the premises | Resolved
180 | 30/2 | DA+9 | Stringing | 2026-02-18 | 2026-03-07 | 2026-03-07 | 17 | land owner not allowed to enter in the premises | Resolved
181 | 9/1 | DA+3 | Stringing | 2026-02-12 | 2026-03-16 | 2026-03-26 | 42 | land owner not allowed to enter in the premises | Resolved
182 | 29A/4 | DA+3 | Stringing | 2026-02-09 |  |  |  | 29A/3 Guy rope payment issue | Resolved
183 | 29A/1 | DA+6 | Stringing | 2026-03-10 |  | 2026-04-07 | 28 | landowner of a corridor/ROW (Right of Way) area is being denied entry into the premises | Resolved
184 | 29A/2 | DA+6 | Stringing | 2026-03-10 |  | 2026-04-07 | 28 | landowner of a corridor/ROW (Right of Way) area is being denied entry into the premises | Resolved
185 | 29A/1 & 29A/2 |  | Stringing | 2026-04-21 |  | 2026-04-22 | 1 | House coming in corricodoe farmer demanding first payment | Resolved
186 | 29A/5 & 29A/6 |  | Stringing | 2026-04-22 |  | 2026-04-26 | 4 |  | Resolved
187 | 15/11 15/2 |  | Final checking | 2026-04-15 |  |  |  | Land Owner payment issue
188 | 29/5 | DA+0 | Stringing | 2026-04-28 |  |  |  | Land Owner payment issue
189 | 20/4 | DA+3 | Final checking | 2026-05-03 |  | 2026-05-20 | 17 | ROW due to erection payment not yet done | Resolved
190 | 20/5 | DA+0 | Final checking | 2026-05-03 |  |  |  | ROW due to erection payment not yet done
191 | 20/6 | DA-3 | Final checking | 2026-05-15 |  | 2026-06-25 | 41 | Land Owner payment issue | Resolved
192 | 21/0 | DB1+0 | Stringing | 2026-05-15 |  |  |  | Land Owner payment issue
193 | 21/2 | DA+6 | Tightning | 2026-05-15 |  | 2026-05-20 | 5 | Land Owner payment issue | Resolved
194 | 21/2 | DA+6 | Stringing | 2026-05-21 |  |  |  | Land Owner payment issue
195 | 15/0 | DD60+25 | Stringing | 2026-05-12 |  |  |  | Land Owner payment issue
196 | 15/1 | DA+6 | Stringing | 2026-05-16 |  |  |  | Land Owner payment issue
197 | 15/2 | DA+3 | Stringing | 2026-05-16 | 2026-06-06 | 2026-07-01 | 46 | Land Owner payment issue | Resolved
198 | 15/12 | DA+6 | Stringing | 2026-05-16 |  |  |  | Land Owner payment issue | Resolved
199 | 15/11 | DA+0 | Stringing | 2026-05-12 |  | 2026-05-20 | 8 | Land Owner payment issue | Resolved
200 | 27/5 | DA-1.5 | Stringing | 2026-05-18 |  | 2026-05-19 | 1 | Land Owner payment issue | Resolved
201 | 27/6 | DA-3 | Stringing | 2026-05-08 |  | 2026-05-19 | 11 | Land Owner payment issue | Resolved
202 | 35/7 | DA+3 | Stringing | 2026-06-06 |  | 2026-06-13 | 7 | Severe ROW | Resolved
203 | 13/0 | DD60+9 | Aviation Paint | 2026-06-11 | 2026-06-19 | 2026-06-19 | 8 | ROW due to Payment Issue 3.00PM | Resolved
204 | 13A/0 | DB1+9 | Aviation Paint | 2026-06-11 | 2026-06-19 | 2026-06-19 | 8 | ROW due to Payment Issue 3.00PM | Resolved
205 | 13/0 -14/0 |  | Stringing | 2026-06-14 | 2026-06-19 | 2026-06-19 | 5 | ROW Due to high compansation demond
206 | 35/9 | DA+1.5 | Stringing | 2026-06-20 | 2026-06-23 | 2026-06-23 | 3 | ROW coridor issue | Resolved | Bhawani Singh | 9649092645 | Somasar | Lunkaransar
207 | 35/10 | DA+3 | Stringing | 2026-06-20 | 2026-06-23 | 2026-06-23 | 3 | ROW coridor issue | Resolved | Bhawani Singh | 9649092645 | Somasar | Lunkaransar
208 | 20/5 | DA+0 | Stringing
#N/A
Formulas:
Date of last approach = [Date of 1st approach]
Date of Resolution = [Date of last approach]+5
Date of Resolution = [Date of last approach]

## S-Curve FDN (hidden)
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Month | L2-FDN | Act-Foundation | Cum. L2 Fdn | Cum. Fdn Actual
2024-05-01 | 6 |  | 6 | 0
2024-06-01 | 18 | 14 | 24 | 14
2024-07-01 | 18 | 20 | 42 | 34
2024-08-01 | 20 | 23 | 62 | 57
2024-09-01 | 22 | 40 | 84 | 97
2024-10-01 | 22 | 36 | 106 | 133
2024-11-01 | 25 | 24 | 131 | 157
2024-12-01 | 25 | 32 | 156 | 189
2025-01-01 | 30 | 35 | 186 | 224
2025-02-01 | 30 | 31 | 216 | 255
2025-03-01 | 25 | 19 | 241 | 274
2025-04-01 | 15 | 23 | 256 | 297
2025-05-01 | 15 | 10 | 271 | 307
2025-06-01 | 10 | 6 | 281 | 313
2025-07-01 | 6 |  | 287 | 313

## S-Curve Erection (hidden)
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Month | L2-Ere | Act-Erection | Cum. L2 Ere | Cum. Ere. Actual
2024-06-01 | 4 |  | 4 | 0
2024-07-01 | 15 |  | 19 | 0
2024-08-01 | 15 |  | 34 | 0
2024-09-01 | 22 | 2 | 56 | 2
2024-10-01 | 20 | 5 | 76 | 7
2024-11-01 | 22 | 2 | 98 | 9
2024-12-01 | 22 | 13 | 120 | 22
2025-01-01 | 22 | 25 | 142 | 47
2025-02-01 | 22 | 21 | 164 | 68
2025-03-01 | 22 | 25 | 186 | 93
2025-04-01 | 22 | 11 | 208 | 104
2025-05-01 | 20 | 0 | 228 | 104
2025-06-01 | 20 | 0 | 248 | 104
2025-07-01 | 20 | 8 | 268 | 112
2025-08-01 | 12 | 44 | 280 | 156
2025-09-01 | 7 | 65 | 287 | 221
2025-10-01 | 0 | 36 | 287 | 257
2025-11-01 | 0 | 24 | 287 | 281
2025-12-01 | 0 | 13 | 287 | 294

## S-Curve Stringing (hidden)
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Month | L2-Str | Act-Str | Cum. L2 Str | Cum. Str Actual
2024-08-01 | 4 |  | 4 | 0
2024-09-01 | 4 |  | 8 | 0
2024-10-01 | 8 |  | 16 | 0
2024-11-01 | 8 |  | 24 | 0
2024-12-01 | 8 |  | 32 | 0
2025-01-01 | 8 |  | 40 | 0
2025-02-01 | 10 |  | 50 | 0
2025-03-01 | 10 | 4.899 | 60 | 4.899
2025-04-01 | 10 | 6.747 | 70 | 11.646
2025-05-01 | 10 | 4.716 | 80 | 16.362
2025-06-01 | 8 |  | 88 | 16.362
2025-07-01 | 8 |  | 96 | 16.362
2025-08-01 | 8 |  | 104 | 16.362
2025-09-01 | 4 | 5.134 | 108 | 21.496
2025-10-01 | 4 | 4.922 | 112 | 26.418
2025-11-01 | 0 | 4.901 | 112 | 31.319
2025-12-01 | 0 |  | 112 | 31.319
2026-01-01 | 0 |  | 112 | 31.319

## Supply Status
SUPPLY STATUS SUMMARY | [7 empty] | 24.07.2026
Name of Line: 765 KV D/C Bikaner III - Neemrana II TL02 | [6 empty] | SUPPLY STATUS
Sl. No. | Description | UOM | LOA Qty | Final Est. Qty | L2 Sch till Oct'25 | Cum. Completed |  | Balance
[6 empty] | Qty. | % | Qty.
I | SUPPLY
1 | Stubs | Sets | 287 | 316 | 287 | 316 | 100% | 0
2 | Towers | Nos | 287 | 306 | 287 | 306 | 100% | 0
3 | Conductor | KM | 4095 | 4285.056 | 4095 | 4285.056 | 100% | 0
4 | Conductor Accessories H/W | % | 100% | 100% | 100% | 100% | 100% | 0
5 | Earthwire | KM | 114 | 121.471 | 100% | 121.471 | 100% | 0
6 | Earthwire Acessories for 7/3.66mm | % | 100% | 100% | 100% | 100% | 100% | 0
7 | Insulator | Nos | 10480 | 11844 | 10480 | 11844 | 100% | 0
8 | OPGW drums | KM | 118.557 | 123.542 | 100% | 117.33 | 94.97% | 6.212
9 | OPGW H/W fittings | % | 100% | 100% | 100% | 100% | 100% | 0
TOWER SUPPLY STATUS SUMMARY
Sl. No. | Description | UOM | LOA Qty | Final Est.Qty | Received Qty | Balance Qty. | Percenatge | Remarks
|  |  |  | A | B | C=(A-B) | %
I | SUPPLY of Stubs
1) | Stubs
1 | DA up to 9MBE | Set | 241 | 246 | 246 | 0 | 100%
2 | DB1 up to 9MBE | Set | 26 | 27 | 27 | 0 | 100% |  | 8
3 | DB1 up to 12MBE | Set | 3 | 4 | 4 | 0 | 100%
4 | DB2 up to 9MBE | Set | 10 | 12 | 12 | 0 | 100%
5 | DC1 up to 9MBE | Set | 2 | 2 | 2 | 0 | 100%
6 | DC2 up to 9MBE | Set | 4 | 3 | 3 | 0 | 100%
7 | DC2 +15 MTR | Set | 1 | 2 | 2 | 0 | 100%
8 | DD TYPE (45) | Set | 2 | 3 | 3 | 0 | 100%
9 | DD TYPE (60) | Set | 4 | 4 | 4 | 0 | 100%
10 | DD TYPE (18&25) | Set | 4 | 4 | 4 | 0 | 100%
11 | DD TYPE (30&35) | Set | 2 | 2 | 2 | 0 | 100%
| DA Sub- Total |  | 299 | 309 | 309 | 0
2 i) | SUPPLY of TOWER
DA(0-2)
1 | DA-3 MTR BODY EXT | Nos | 241 | 12 | 10 | 2 | 83.33%
2 | DA-1.5 MTR BODY EXT | Nos |  | 12 | 7 | 5 | 58.33%
3 | DA+0 MTR BODY EXT | Nos |  | 33 | 115 | -82 | 348.5%
4 | DA+1.5 MTR BODY EXT | Nos |  | 24 | 17 | 7 | 70.83%
5 | DA+3 MTR BODY EXT | Nos |  | 70 | 60 | 10 | 85.71%
6 | DA+4.5 MTR BODY EXT | Nos |  | 1 |  | 1 | 0%
7 | DA+6 MTR BODY EXT | Nos |  | 47 | 44 | 3 | 93.62%
8 | DA+9 MTR BODY EXT | Nos |  | 47 | 38 | 9 | 80.85%
| DA Sub- Total |  | 241 | 246 | 291 | -45
1 | DB1
i | DB1+0 | SET | 12 | 7 | 11 |  | 157.1%
ii | DB1+3 | SET |  | 2 |  |  | 0%
iii | DB1+6 | SET |  | 6 | 3 |  | 50%
iv | DB1+9 | SET |  | 12 | 4 |  | 33.33%
v | DB1+12 | SET |  | 4 |  |  | 0%
2 | DB2
i | DB2+0 | SET |  | 6 | 4 |  | 66.67%
ii | DB2+3 | SET |  | 2 |  |  | 0%
iii | DB2+6 | SET |  | 1 |  |  | 0%
iv | DB2+9 | SET |  | 1 |  |  | 0%
| DB Sub- Total |  | 12 | 41 | 18 | 0
1 | DC1
i | DC1-3 | SET | 5 | 0
ii | DC1+0 | SET |  | 1
iii | DC1+3 | SET |  | 1
iv | DC1+6 | SET |  | 0
v | DC1+9 | SET |  | 0
2 | DC2
i | DC2-3 | SET |  | 0
ii | DC2+0 | SET |  | 3 | 2
iii | DC2+3 | SET |  | 0
iv | DC2+6 | SET |  | 0
v | DC2+9 | SET |  | 0
Vi | DC2+15 | SET |  | 1
| DC Sub- Total |  | 5 | 6 | 2 | 0 | 0
DD45
i | DD45-1.5 | SET | 29 | 0
ii | DD45+0 | SET |  | 2
iii | DD45+3 | SET |  | 0
iv | DD45+6 | SET |  | 0
v | DD45+9 | SET |  | 0
vi | DD45+18 | SET |  | 0
vii | DD45+25 | SET |  | 0
2 | DD60
i | DD60-3 | SET |  | 0
ii | DD60+0 | SET |  | 1 | 5
iii | DD60+3 | SET |  | 2 | 2
iv | DD60+6 | SET |  | 0
v | DD60+9 | SET |  | 1 | 1
vi | DD60+18 | SET |  | 2 | 2
vii | DD60+25 | SET |  | 2 | 2
viii | DD60+35 | SET |  | 2
| DD Sub- Total |  | 29 | 12 | 0 | 0 | 0
| Grand Sub- Total |  | 287 | 305 | 311 | -45 | 0

## Hardware Supply
KEC International Limited
TA413 : 765 KV D/C Bikaner III - Neemrana II TL02
Status of Line Materials, conductor and Tower Accessories
24.07.2026
Sl.No. | Description | Unit | As per LOA | As per Latest Estimate | Receipt Qty. | Balance Required Qty. | Supplier | REMARKS
A | Insulator
i | 160 KN Insulator | Nos | 5968 | 6084 | 6084 | 0 | DECCAN ENTERPRISES |  | 100% |  |  | 10480 | 192 | 1.832%
ii | 210 KN Insulator | Nos | 4512 | 5952 | 5760 | 192 | DECCAN ENTERPRISES |  | 96.77%
B | AL-59 Zebra Conductor | Kms | 4095 | 4285.056 | 4285 | 0.056 | APAR INDUSTRIES LTD |  | 100% | Drum | 0.056
C | G S Earthwire 7/3.66mm size | Kms | 114 | 121.471 | 121.471 | 0 | GEEKAY WIRES PVT. LTD |  | 100% | Drum
D | Hardware Fittings
i | Double ISuspension String | Sets | 1446 | 1476 | 1476 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
ii | Single ISuspension String (Pilot) | Sets | 88 | 86 | 86 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
iii | Quadruple Tension String | Sets | 564 | 744 | 720 | 24 | MOSDORFER INDIA PVT. LTD |  | 96.77%
E | Accessories for Conductor AL-59 Zebra
i | MID SPAN COMPRESSION JOINT FOR AL59 ZEBRA CONDUCTOR | Nos | 2048 | 2048 | 2048 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
ii | REPAIR SLEEVE FOR AL59 ZEBRA CONDUCTOR | Nos | 683 | 683 | 683 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
iii | PREFORMED RETAINING ROD TYPE SPACER DAMPER | Nos | 12054 | 13068 | 13002 | 66 | MOSDORFER INDIA PVT. LTD |  | 99.49%
iv | HEXAGONAL RIGID SPACER-765KV AC WITH AL59 HEX ZEBRA | Nos | 1380 | 2335 | 2225 | 110 | MOSDORFER INDIA PVT. LTD |  | 95.29%
F | Earthwire Acessories for 7/3.66mm
ii | FLEXIBLE AL BOND-7/3.66MM E/W | Nos | 335 | 368 | 366 | 2 | MOSDORFER INDIA PVT. LTD |  | 99.46%
iii | Vibration damper -7/3.66mm Earth Wire | Nos | 670 | 736 | 732 | 4 | MOSDORFER INDIA PVT. LTD |  | 99.46%
iv | Suspension clamp assembly -7/3.66mm Earth Wire | Nos | 241 | 246 | 246 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
v | Tension clamp assembly-7/3.66mm Earth Wire | Nos | 92 | 124 | 120 | 4 | MOSDORFER INDIA PVT. LTD |  | 96.77%
vi | MID SPAN COMPRESSION JOINT FOR EW | Nos | 63 | 63 | 63 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
G | OPGW / Hardware Fittings
i | OPGW Cable | Km | 118.557 | 123.542 | 117.33 | 6.212 | APAR INDUSTRIES LTD |  | 94.97% |  |  | 117.33
ii | DOWN LEAD CLAMP ASSY | Nos | 1167 | 933 | 933 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
iii | SUSPENSION CLAMP ASSY | Nos | 237 | 226 | 226 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
iv | TENSION FITTINGS ASSEMBLY ON SUSPENSION | Nos | 5 | 20 | 20 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
v | TENSION FITTINGS ASSEMBLY FOR 24F OPGW (SPLICING) | Nos | 20 | 20 | 20 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
vi | TENSION ASSEMBLY - DOUBLE TENSION PASS THROUGH | Nos | 21 | 53 | 53 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
vii | TENSION ASSEMBLY - DEAD END FOR 24 FIBER OPGW | Nos | 1 | 1 | 1 | 0 | MOSDORFER INDIA PVT. LTD |  | 100%
viii | Vibration Damper for 24 fibre OPGW | Nos | 1228 | 859 | 859 | 0 | MOSDORFER INDIA PVT. LTD | 2 Nos Provided to Powergrid | 100%
IX | Joint Box | EA | 25 | 27 | 25 | 2 |  |  | 92.59%
H | EARTHING
i) | Supply of Pipe Type Earthing | EA | 200 | 309 | 309 | 0 | KEC INTERNATIONAL LTD |  | 100%
ii) | Supply of Counterpoise type (120 m length) | EA | 80 | 10 | 10 | 0 | KEC INTERNATIONAL LTD |  |  |  |  | 896
iii) | ROD TYPE EARTHING | EA | 200 | 313 | 313 | 0 | KEC INTERNATIONAL LTD |  |  |  |  | 23
v | Supply of Shieldwire Earthing including PG clamps, downlead clamps butexcluding Earthwire bits for Pipe type earthing | EA | 12 | 15 | 14 | 1 | MOSDORFER INDIA PVT. LTD
I | TOWER ACCESSORIES
i) | Danger Plate For 765Kv | EA | 287 | 306 | 306 | 0 | LOHAR ENGINEERS
ii) | Number Plate For 765Kv | EA | 287 | 306 | 306 | 0 | LOHAR ENGINEERS
iii) | Phase Plate (Set Of Three) RYB | SET | 574 | 612 | 612 | 0 | LOHAR ENGINEERS
iv | Circuit Plate (Set Of Two) | SET | 287 | 306 | 306 | 0 | LOHAR ENGINEERS
v | Supply Of Anti-Climbing Devices Ofbarbed Wire Type | SET | 287 | 306 | 306 | 0 | LOHAR ENGINEERS
vi | Bird Guard (Set Of Three) | SET | 482 | 492 | 492 | 0 | LOHAR ENGINEERS | BG2- 1 short and BG4 1bdl short and BG2- 1 qty billing pending
vii | Supply Of Span Marker For Aviation | EA | 100 | 100 | 50 | 50
viii | Supply Of Obstruction Lights (As Per Is5613)-1 Medium Intensity + 2 Lowintensity | SET | 96 | 96 | 48 | 48
ix | Supply Of Obstruction Lights (As Per Is5613)-1 Medium Intensity + 4 Lowintensity | SET | 4 | 4 | 4 | 0

## Tower Abstract sheet
Overall Tower location details As per Previous Estimate | [5 empty] | Overall Tower location details As per Latest Estimate
S. No. | Location | Type of | Structure details tower for tower qty |  |  | S. No. | Location | Type of |  | Structure details tower for tower qty
| Tower No. | Tower | TOT | Tower Qty | Total Qty |  | Tower No. | Tower |  | TOT | Tower Qty | Total Qty (after oilpipe line diversion) | Total Qty (before oilpipe line diversion)
0 | Gantry | Gantry | DA+0 | 30 | 241 | 0 | Gantry | Gantry |  | DA+0 | 33 | 244 | 246
1 | 1/0 | DD60+0 | DA+1.5 | 24 |  | 1 | 1/0 | DD60+0 |  | DA-1.5 | 12
2 | 2/0 | DD45+0 | DA+3 | 66 |  | 2 | 2A/0 | DD45+0 |  | DA-3 | 12
3 | 3/0 | DB2+0 | DA+4.5 | 1 |  | 3 | 2A/1 | DA+0 |  | DA+1.5 | 24
4 | 3/1 | DA+3 | DA+6 | 49 |  | 4 | 2A/2 | DA+3 |  | DA+3 | 69
5 | 3/2 | DA+6 | DA+9 | 47 |  | 5 | 2A/3 | DA+3 |  | DA+4.5 | 1
6 | 3/3 | DA+3 | DA-1.5 | 12 |  | 6 | 2A/4 | DA+3 |  | DA+6 | 47
7 | 3/4 | DA+6 | DA-3 | 12 |  | 7 | 2A/5 | DA+3 |  | DA+9 | 46
8 | 3/5 | DA+3 | DB1+0 | 7 | 29 | 8 | 2A/6 | DA+6 |  | DB1+0 | 7 | 31 | 31
9 | 3/6 | DA+3 | DB1+3 | 2 |  | 9 | 3A/0 | DD45+3 |  | DB1+3 | 2
10 | 3/7 | DA+3 | DB1+6 | 6 |  | 10 | 3A/1 | DA+3 |  | DB1+6 | 6
11 | 3/8 | DA+0 | DB1+9 | 11 |  | 11 | 3A/2 | DA+3 |  | DB1+9 | 12
12 | 3/9 | DA+0 | DB1+12 | 3 |  | 12 | 3A/3 | DA+0 |  | DB1+12 | 4
13 | 3/10 | DA+9 | DB2+0 | 6 | 10 | 13 | 3A/4 | DA+0 |  | DB2+0 | 5 | 11 | 10
14 | 3/11 | DA+0 | DB2+3 | 2 |  | 14 | 3A/5 | DA+3 |  | DB2+3 | 1
15 | 4/0 | DB1+9 | DB2+6 | 1 |  | 15 | 3A/6 | DA+0 |  | DB2+6 | 1
16 | 4/1 | DA+6 | DB2+9 | 1 |  | 16 | 3B/0 | DB1+9 |  | DB2+9 | 4
17 | 4/2 | DA+3 | DC1+0 | 1 | 2 | 17 | 3B/1 | DA+3 |  | DC1+0 | 1 | 2 | 2
18 | 4/3 | DA+3 | DC1+3 | 1 |  | 18 | 3B/2 | DA+9 |  | DC1+3 | 1
19 | 4/4 | DA+6 | DC2+0 | 1 | 3 | 19 | 3B/3 | DA+6 |  | DC2+0 | 2 | 5 | 4
20 | 4/5 | DA+6 | DC2-3 | 1 |  | 20 | 4/0 | DB2+9 |  | DC2-3 | 1
21 | 4A/0 | DB1+3 | DC2+15 | 1 |  | 21 | 4/1 | DA+6 |  | DC2+15 | 2
22 | 4A/1 | DA+6 | DCT | 1 | 1 | 22 | 4A/0 | DB1+3 |  | DD45+0 | 2 | 3 | 3
23 | 4A/2 | DA+6 | DD45+0 | 2 | 2 | 23 | 4A/1 | DA+6 |  | DD45+3 | 1
24 | 4A/3 | DA+9 | DD60+0 | 1 | 10 | 24 | 4A/2 | DA+6 |  | DD60+0 | 1 | 10 | 10
25 | 4A/4 | DA+6 | DD60+3 | 2 |  | 25 | 4A/3 | DA+9 |  | DD60+3 | 2
26 | 4A/5 | DA+9 | DD60+9 | 1 |  | 26 | 4A/4 | DA+6 |  | DD60+9 | 1
27 | 4A/6 | DA+9 | DD60+18 | 3 |  | 27 | 4A/5 | DA+9 |  | DD60+18 | 3
28 | 5/0 | DB1+6 | DD60+25 | 1 |  | 28 | 4A/6 | DA+9 |  | DD60+25 | 1
29 | 5/1 | DA+6 | DD60+35 | 2 |  | 29 | 5/0 | DB1+6 |  | DD60+35 | 2
30 | 5/2 | DA+9 | Total Qty |  | 298 | 30 | 5/1 | DA+6 |  | Total Qty |  | 306 | 306
31 | 5/3 | DA+9 |  |  |  | 31 | 5/2 | DA+9
32 | 5/4 | DA-1.5 |  |  |  | 32 | 5/3 | DA+9
33 | 5/5 | DA+6 |  |  |  | 33 | 5/4 | DA-1.5
34 | 5/6 | DA+3 |  |  |  | 34 | 5/5 | DA+6
35 | 5/7 | DA+9 |  |  |  | 35 | 5/6 | DA+3
36 | 5/8 | DA+6 |  |  |  | 36 | 5/7 | DA+9
37 | 5/9 | DA+6 |  |  |  | 37 | 5/8 | DA+6
38 | 5/10 | DA+9 |  |  |  | 38 | 5/9 | DA+6
39 | 5A/0 | DB1+12 |  |  |  | 39 | 5/10 | DA+9
40 | 6/0 | DB1+9 |  |  |  | 40 | 5A/0 | DB1+12
41 | 6/1 | DA+9 |  |  |  | 41 | 6/0 | DB1+9
42 | 6/2 | DA+6 |  |  |  | 42 | 6/1 | DA+9
43 | 6/3 | DA+3 |  |  |  | 43 | 6/2 | DA+6
44 | 6/4 | DA+9 |  |  |  | 44 | 6/3 | DA+3
45 | 6/5 | DA+9 |  |  |  | 45 | 6/4 | DA+9
46 | 6/6 | DA-3 |  |  |  | 46 | 6/5 | DA+9
47 | 6/7 | DA+1.5 |  |  |  | 47 | 6/6 | DA-3
48 | 6/8 | DA+3 |  |  |  | 48 | 6/7 | DA+1.5
49 | 6/9 | DA+6 |  |  |  | 49 | 6/8 | DA+3
50 | 6/10 | DA+1.5 |  |  |  | 50 | 6/9 | DA+6
51 | 6/11 | DA-1.5 |  |  |  | 51 | 6/10 | DA+1.5
52 | 6/12 | DA+1.5 |  |  |  | 52 | 6/11 | DA-1.5
53 | 7/0 | DB2+0 |  |  |  | 53 | 6/12 | DA+1.5
54 | 7/1 | DA-3 |  |  |  | 54 | 7/0 | DB2+0
55 | 7/2 | DA+6 |  |  |  | 55 | 7/1 | DA-3
56 | 7/3 | DA+9 |  |  |  | 56 | 7/2 | DA+6
57 | 7/4 | DA+6 |  |  |  | 57 | 7/3 | DA+9
58 | 7/5 | DA+6 |  |  |  | 58 | 7/4 | DA+6
59 | 7/6 | DA-1.5 |  |  |  | 59 | 7/5 | DA+6
60 | 7A/0 | DB1+6 |  |  |  | 60 | 7/6 | DA-1.5
61 | 7A/1 | DA+1.5 |  |  |  | 61 | 7A/0 | DB1+6
62 | 7A/2 | DA+3 |  |  |  | 62 | 7A/1 | DA+1.5
63 | 7A/3 | DA+3 |  |  |  | 63 | 7A/2 | DA+3
64 | 7A/4 | DA+3 |  |  |  | 64 | 7A/3 | DA+3
65 | 7A/5 | DA+3 |  |  |  | 65 | 7A/4 | DA+3
66 | 8/0 | DB1+0 |  |  |  | 66 | 7A/5 | DA+3
67 | 8/1 | DA-3 |  |  |  | 67 | 8/0 | DB1+0
68 | 8/2 | DA+6 |  |  |  | 68 | 8/1 | DA-3
69 | 8/3 | DA+9 |  |  |  | 69 | 8/2 | DA+6
70 | 8/4 | DA+6 |  |  |  | 70 | 8/3 | DA+9
71 | 8/5 | DA+9 |  |  |  | 71 | 8/4 | DA+6
72 | 8/6 | DA+3 |  |  |  | 72 | 8/5 | DA+9
73 | 8/7 | DA+3 |  |  |  | 73 | 8/6 | DA+3
74 | 8/8 | DA+9 |  |  |  | 74 | 8/7 | DA+3
75 | 8/9 | DA+3 |  |  |  | 75 | 8/8 | DA+9
76 | 8/10 | DA+0 |  |  |  | 76 | 8/9 | DA+3
77 | 8/11 | DA+9 |  |  |  | 77 | 8/10 | DA+0
78 | 8A/0 | DB1+12 |  |  |  | 78 | 8/11 | DA+9
79 | 9/0 | DB1+12 |  |  |  | 79 | 8A/0 | DB1+12
80 | 9/1 | DA+3 |  |  |  | 80 | 9/0 | DB1+12
81 | 9/2 | DA+3 |  |  |  | 81 | 9/1 | DA+3
82 | 9/3 | DA+0 |  |  |  | 82 | 9/2 | DA+3
83 | 9/4 | DA+6 |  |  |  | 83 | 9/3 | DA+0
84 | 9/5 | DA+3 |  |  |  | 84 | 9/4 | DA+6
85 | 9/6 | DA+3 |  |  |  | 85 | 9/5 | DA+3
86 | 9/7 | DA+9 |  |  |  | 86 | 9/6 | DA+3
87 | 9/8 | DA+0 |  |  |  | 87 | 9/7 | DA+9
88 | 9/9 | DA+0 |  |  |  | 90 | 9/8 | DA+0
89 | 9/10 | DA+3 |  |  |  | 89 | 9/9 | DA+0
90 | 9/11 | DA+3 |  |  |  | 90 | 9/10 | DA+3
91 | 10/0 | DB1+6 |  |  |  | 91 | 9/11 | DA+3
92 | 10/1 | DA+3 |  |  |  | 92 | 10/0 | DB1+6
93 | 10/2 | DA+3 |  |  |  | 93 | 10/1 | DA+3
94 | 11/0 | DD45+0 |  |  |  | 94 | 10/2 | DA+3
95 | 12/0 | DB1+9 |  |  |  | 95 | 11/0 | DD45+0
96 | 13/0 | DD60+9 |  |  |  | 96 | 12/0 | DB1+9
97 | 13A/0 | DB1+9 |  |  |  | 97 | 13/0 | DD60+9
98 | 14/0 | DD60+18 |  |  |  | 98 | 13A/0 | DB1+9
99 | 15/0 | DD60+25 |  |  |  | 99 | 14/0 | DD60+18
100 | 15/1 | DA+6 |  |  |  | 100 | 15/0 | DD60+25
101 | 15/2 | DA+3 |  |  |  | 101 | 15/1 | DA+6
102 | 15/3 | DA+3 |  |  |  | 102 | 15/2 | DA+3
103 | 15/4 | DA+6 |  |  |  | 103 | 15/3 | DA+3
104 | 15/5 | DA+3 |  |  |  | 104 | 15/4 | DA+6
105 | 15/6 | DA+9 |  |  |  | 105 | 15/5 | DA+3
106 | 15/7 | DA+0 |  |  |  | 106 | 15/6 | DA+9
107 | 15/8 | DA+1.5 |  |  |  | 107 | 15/7 | DA+0
108 | 15/9 | DA+0 |  |  |  | 108 | 15/8 | DA+1.5
109 | 15/10 | DA-1.5 |  |  |  | 109 | 15/9 | DA+0
110 | 15/11 | DA+0 |  |  |  | 110 | 15/10 | DA-1.5
111 | 15/12 | DA+6 |  |  |  | 111 | 15/11 | DA+0
112 | 16/0 | DC2+0 |  |  |  | 112 | 15/12 | DA+6
113 | 17/0 | DC1+3 |  |  |  | 113 | 16/0 | DC2+0
114 | 18/0 | DB2+6 |  |  |  | 114 | 17/0 | DC1+3
115 | 18/1 | DA+3 |  |  |  | 115 | 18/0 | DB2+6
116 | 18/2 | DA+1.5 |  |  |  | 116 | 18/1 | DA+3
117 | 18/3 | DA+6 |  |  |  | 117 | 18/2 | DA+1.5
118 | 18/4 | DA-3 |  |  |  | 118 | 18/3 | DA+6
119 | 18/5 | DA+0 |  |  |  | 119 | 18/4 | DA-3
120 | 18/6 | DA+9 |  |  |  | 120 | 18/5 | DA+0
121 | 18/7 | DA+1.5 |  |  |  | 121 | 18/6 | DA+9
122 | 19/0 | DD60+3 |  |  |  | 122 | 18/7 | DA+1.5
123 | 20/0 | DD60+3 |  |  |  | 123 | 19/0 | DD60+3
124 | 20/1 | DA-3 |  |  |  | 124 | 20/0 | DD60+3
125 | 20/2 | DA-3 |  |  |  | 125 | 20/1 | DA-3
126 | 20/3 | DA+1.5 |  |  |  | 126 | 20/2 | DA-3
127 | 20/4 | DA+3 |  |  |  | 127 | 20/3 | DA+1.5
128 | 20/5 | DA+0 |  |  |  | 128 | 20/4 | DA+3
129 | 20/6 | DA-3 |  |  |  | 129 | 20/5 | DA+0
130 | 21/0 | DB1+0 |  |  |  | 130 | 20/6 | DA-3
131 | 21/1 | DA+0 |  |  |  | 131 | 21/0 | DB1+0
132 | 21/2 | DA+6 |  |  |  | 132 | 21/1 | DA+0
133 | 21/3 | DA+6 |  |  |  | 133 | 21/2 | DA+6
134 | 21/4 | DA+0 |  |  |  | 134 | 21/3 | DA+6
135 | 21/5 | DA+0 |  |  |  | 135 | 21/4 | DA+0
136 | 22/0 | DC2+15 |  |  |  | 136 | 21/5 | DA+0
137 | 23/0 | DB2+9 |  |  |  | 137 | 22/0 | DC2+15
138 | 23A/0 | DB1+9 |  |  |  | 138 | 23/0 | DB2+9
139 | 24/0 | DD60+18 |  |  |  | 139 | 23A/0 | DB1+9
140 | 25/0 | DD60+18 |  |  |  | 140 | 24/0 | DD60+18
141 | 26/0 | DD60+35 |  |  |  | 141 | 25/0 | DD60+18
142 | 27/0 | DD60+35 |  |  |  | 142 | 26/0 | DD60+35
143 | 27/1 | DA+9 |  |  |  | 143 | 27/0 | DD60+35
144 | 27/2 | DA-1.5 |  |  |  | 144 | 27/1 | DA+9
145 | 27/3 | DA+1.5 |  |  |  | 145 | 27/2 | DA-1.5
146 | 27/4 | DA+1.5 |  |  |  | 146 | 27/3 | DA+1.5
147 | 27/5 | DA-1.5 |  |  |  | 147 | 27/4 | DA+1.5
148 | 27/6 | DA-3 |  |  |  | 148 | 27/5 | DA-1.5
149 | 28/0 | DC2-3 |  |  |  | 149 | 27/6 | DA-3
150 | 29/0 | DC1+0 |  |  |  | 150 | 28/0 | DC2-3
151 | 29/1 | DA+6 |  |  |  | 151 | 29/0 | DC1+0
152 | 29/2 | DA+0 |  |  |  | 152 | 29/1 | DA+6
153 | 29/3 | DA+0 |  |  |  | 153 | 29/2 | DA+0
154 | 29/4 | DA+3 |  |  |  | 154 | 29/3 | DA+0
155 | 29/5 | DA+0 |  |  |  | 155 | 29/4 | DA+3
156 | 29A/0 | DB1+0 |  |  |  | 156 | 29/5 | DA+0
157 | 29A/1 | DA+6 |  |  |  | 157 | 29A/0 | DB1+0
158 | 29A/2 | DA+6 |  |  |  | 158 | 29A/1 | DA+6
159 | 29A/3 | DA+6 |  |  |  | 159 | 29A/2 | DA+6
160 | 29A/4 | DA+3 |  |  |  | 160 | 29A/3 | DA+6
161 | 29A/5 | DA+6 |  |  |  | 161 | 29A/4 | DA+3
162 | 29A/6 | DA+9 |  |  |  | 162 | 29A/5 | DA+6
163 | 30/0 | DB1+0 |  |  |  | 163 | 29A/6 | DA+9
164 | 30/1 | DA+0 |  |  |  | 164 | 30/0 | DB1+0
165 | 30/2 | DA+9 |  |  |  | 165 | 30/1 | DA+0
166 | 30/3 | DA+3 |  |  |  | 166 | 30/2 | DA+9
167 | 30/4 | DA+9 |  |  |  | 167 | 30/3 | DA+3
168 | 30/5 | DA+0 |  |  |  | 168 | 30/4 | DA+9
169 | 30/6 | DA+6 |  |  |  | 169 | 30/5 | DA+0
170 | 30/7 | DA-3 |  |  |  | 170 | 30/6 | DA+6
171 | 30/8 | DA+3 |  |  |  | 171 | 30/7 | DA-3
172 | 30/9 | DA-3 |  |  |  | 172 | 30/8 | DA+3
173 | 30/10 | DA+3 |  |  |  | 173 | 30/9 | DA-3
174 | 31/0 | DB1+0 |  |  |  | 174 | 30/10 | DA+3
175 | 31/1 | DA+3 |  |  |  | 175 | 31/0 | DB1+0
176 | 31/2 | DA+1.5 |  |  |  | 176 | 31/1 | DA+3
177 | 31/3 | DA+3 |  |  |  | 177 | 31/2 | DA+1.5
178 | 31/4 | DA-1.5 |  |  |  | 178 | 31/3 | DA+3
179 | 31/5 | DA+6 |  |  |  | 179 | 31/4 | DA-1.5
180 | 31/6 | DA+9 |  |  |  | 180 | 31/5 | DA+6
181 | 31/7 | DA+0 |  |  |  | 181 | 31/6 | DA+9
182 | 31/8 | DA+0 |  |  |  | 182 | 31/7 | DA+0
183 | 31/9 | DA+1.5 |  |  |  | 183 | 31/8 | DA+0
184 | 31/10 | DA+4.5 |  |  |  | 184 | 31/9 | DA+1.5
185 | 32/0 | DB2+0 |  |  |  | 185 | 31/10 | DA+4.5
186 | 32/1 | DA+6 |  |  |  | 186 | 32/0 | DB2+0
187 | 32/2 | DA+9 |  |  |  | 187 | 32/1 | DA+6
188 | 32/3 | DA+6 |  |  |  | 188 | 32/2 | DA+9
189 | 32/4 | DA+9 |  |  |  | 189 | 32/3 | DA+6
190 | 32/5 | DA+9 |  |  |  | 190 | 32/4 | DA+9
191 | 32/6 | DA+9 |  |  |  | 191 | 32/5 | DA+9
192 | 32/7 | DA+3 |  |  |  | 192 | 32/6 | DA+9
193 | 32A/0 | DB1+9 |  |  |  | 193 | 32/7 | DA+3
194 | 32A/1 | DA+6 |  |  |  | 194 | 32A/0 | DB1+9
195 | 33/0 | DB1+9 |  |  |  | 195 | 32A/1 | DA+6
196 | 33/1 | DA+9 |  |  |  | 196 | 33/0 | DB1+9
197 | 33/2 | DA+9 |  |  |  | 197 | 33/1 | DA+9
198 | 33/3 | DA+3 |  |  |  | 198 | 33/2 | DA+9
199 | 33/4 | DA+3 |  |  |  | 199 | 33/3 | DA+3
200 | 33/5 | DA+0 |  |  |  | 200 | 33/4 | DA+3
201 | 33/6 | DA+6 |  |  |  | 201 | 33/5 | DA+0
202 | 33/7 | DA+6 |  |  |  | 202 | 33/6 | DA+6
203 | 33/8 | DA+3 |  |  |  | 203 | 33/7 | DA+6
204 | 33/9 | DA+1.5 |  |  |  | 204 | 33/8 | DA+3
205 | 34/0 | DB1+6 |  |  |  | 205 | 33/9 | DA+1.5
206 | 34/1 | DA+9 |  |  |  | 206 | 34/0 | DB1+6
207 | 34/2 | DA+9 |  |  |  | 207 | 34/1 | DA+9
208 | 34/3 | DA+1.5 |  |  |  | 208 | 34/2 | DA+9
209 | 34/4 | DA+6 |  |  |  | 209 | 34/3 | DA+1.5
210 | 34/5 | DA+9 |  |  |  | 210 | 34/4 | DA+6
211 | 34/6 | DA+3 |  |  |  | 211 | 34/5 | DA+9
212 | 34/7 | DA+0 |  |  |  | 212 | 34/6 | DA+3
213 | 34/8 | DA+0 |  |  |  | 213 | 34/7 | DA+0
214 | 34/9 | DA+1.5 |  |  |  | 214 | 34/8 | DA+0
215 | 34/10 | DA-3 |  |  |  | 215 | 34/9 | DA+1.5
216 | 34/11 | DA+1.5 |  |  |  | 216 | 34/10 | DA-3
217 | 34/12 | DA+3 |  |  |  | 217 | 34/11 | DA+1.5
218 | 35/0 | DB2+0 |  |  |  | 218 | 34/12 | DA+3
219 | 35/1 | DA+6 |  |  |  | 219 | 35/0 | DB2+0
220 | 35/2 | DA+6 |  |  |  | 220 | 35/1 | DA+6
221 | 35/3 | DA-3 |  |  |  | 221 | 35/2 | DA+6
222 | 35/4 | DA+9 |  |  |  | 222 | 35/3 | DA-3
223 | 35/5 | DA+9 |  |  |  | 223 | 35/4 | DA+9
224 | 35/6 | DA+6 |  |  |  | 224 | 35/5 | DA+9
225 | 35/7 | DA+3 |  |  |  | 225 | 35/6 | DA+6
226 | 35/8 | DA+6 |  |  |  | 226 | 35/7 | DA+3
227 | 35/9 | DA+1.5 |  |  |  | 227 | 35/8 | DA+6
228 | 35/10 | DA+3 |  |  |  | 228 | 35/9 | DA+1.5
229 | 35/11 | DA+3 |  |  |  | 229 | 35/10 | DA+3
230 | 36/0 | DB2+3 |  |  |  | 230 | 35/11 | DA+3
231 | 36/1 | DB1+9 |  |  |  | 231 | 36/0 | DB2+3
232 | 36/2 | DA+3 |  |  |  | 232 | 36A/0 | DB1+9
233 | 36/3 | DA+9 |  |  |  | 233 | 36A/1 | DA+3
234 | 37/0 | DB2+3 |  |  |  | 234 | 36B/0 N | DB2+9
235 | 37/1 | DA+3 |  |  |  | 235 | 36C/0 N | DC2+15
236 | 37/2 | DA+3 |  |  |  | 236 | 37/0 N | DB2+9
237 | 37/3 | DA-1.5 |  |  |  | 237 | 37/2 | DA+3
238 | 37/4 | DA+9 |  |  |  | 238 | 37/3 | DA-1.5
239 | 37/5 | DA+3 |  |  |  | 239 | 37/4 | DA+9
240 | 37A/0 | DB1+0 |  |  |  | 240 | 37/5 | DA+3
241 | 37A/1 | DA+3 |  |  |  | 241 | 37A/0 | DB1+0
242 | 37A/2 | DA+1.5 |  |  |  | 242 | 37A/1 | DA+3
243 | 37A/3 | DA+3 |  |  |  | 243 | 37A/2 | DA+1.5
244 | 37A/4 | DA+9 |  |  |  | 244 | 37A/3 | DA+3
245 | 37A/5 | DA+3 |  |  |  | 245 | 37A/4 | DA+9
246 | 37A/6 | DA+3 |  |  |  | 246 | 37A/5 | DA+3
247 | 38/0 | DB1+3 |  |  |  | 247 | 37A/6 | DA+3
248 | 38/1 | DA+0 |  |  |  | 248 | 38/0 | DB1+3
249 | 38/2 | DA+0 |  |  |  | 249 | 38/1 | DA+0
250 | 38/3 | DA+3 |  |  |  | 250 | 38/2 | DA+0
251 | 38/4 | DA+1.5 |  |  |  | 251 | 38/3 | DA+3
252 | 38/5 | DA+3 |  |  |  | 252 | 38/4 | DA+1.5
253 | 38/6 | DA+6 |  |  |  | 253 | 38/5 | DA+3
254 | 38/7 | DA+9 |  |  |  | 254 | 38/6 | DA+6
255 | 38/8 | DA+1.5 |  |  |  | 255 | 38/7 | DA+9
256 | 38/9 | DA+0 |  |  |  | 256 | 38/8 | DA+1.5
257 | 38/10 | DA+3 |  |  |  | 257 | 38/9 | DA+0
258 | 39/0 | DB2+0 |  |  |  | 258 | 38/10 | DA+3
259 | 39/1 | DA-1.5 |  |  |  | 259 | 39/0 | DB2+0
260 | 39/2 | DA+3 |  |  |  | 260 | 39/1 | DA-1.5
261 | 39/3 | DA+1.5 |  |  |  | 261 | 39/2 | DA+3
262 | 39/4 | DA+3 |  |  |  | 262 | 39/3 | DA+1.5
263 | 39/5 | DA+1.5 |  |  |  | 263 | 39/4 | DA+3
264 | 39/6 | DA+1.5 |  |  |  | 264 | 39/5 | DA+1.5
265 | 39/7 | DA+3 |  |  |  | 265 | 39/6 | DA+1.5
266 | 39/8 | DA+1.5 |  |  |  | 266 | 39/7 | DA+3
267 | 39/9 | DA+6 |  |  |  | 267 | 39/8 | DA+1.5
268 | 39/10 | DA+3 |  |  |  | 268 | 39/9 | DA+6
269 | 39/11 | DA+6 |  |  |  | 269 | 39/10 | DA+3
270 | 40/0 | DB1+6 |  |  |  | 270 | 39/11 | DA+6
271 | 40/1 | DA+9 |  |  |  | 271 | 40/0 | DB1+6
272 | 40/2 | DA+6 |  |  |  | 272 | 40/1 | DA+9
273 | 40/3 | DA+3 |  |  |  | 273 | 40/2 | DA+6
274 | 40/4 | DA+6 |  |  |  | 274 | 40/3 | DA+3
275 | 40/5 | DA+9 |  |  |  | 275 | 40/4 | DA+6
276 | 40/6 | DA+9 |  |  |  | 276 | 40/5 | DA+9
277 | 40/7 | DA+3 |  |  |  | 277 | 40/6 | DA+9
278 | 40/8 | DA-1.5 |  |  |  | 278 | 40/7 | DA+3
279 | 40/9 | DA+9 |  |  |  | 279 | 40/8 | DA-1.5
280 | 40/10 | DA+3 |  |  |  | 280 | 40/9 | DA+9
281 | 40/11 | DA+9 |  |  |  | 281 | 40/10 | DA+3
282 | 40A/0 | DB1+9 |  |  |  | 282 | 40/11 | DA+9
283 | 41/0 | DB1+9 |  |  |  | 283 | 40A/0 | DB1+9
284 | 41/1 | DA+9 |  |  |  | 284 | 41/0 | DB1+9
285 | 42/0 | DB2+0 |  |  |  | 285 | 41/1 | DA+9
286 | 42/1 | DA+3 |  |  |  | 286 | 42/0 | DB2+0
287 | 42/2 | DA+9 |  |  |  | 287 | 42/1 | DA+3
288 | 42/3 | DB1+9 |  |  |  | 288 | 42/2 | DA+9
289 | 43/0 | DB1+0 |  |  |  | 289 | 42A/0 | DB1+9
290 | 43/1 | DA-1.5 |  |  |  | 290 | 43/0 | DB1+0
291 | 43/2 | DA+6 |  |  |  | 291 | 43/1 | DA-1.5
292 | 43/3 | DA-1.5 |  |  |  | 292 | 43/2 | DA+6
293 | 43/4 | DA+0 |  |  |  | 293 | 43/3 | DA-1.5
294 | 43/5 | DC2+0 |  |  |  | 294 | 43/4 | DA+0
295 | 43/6 | DA+3 |  |  |  | 295 | 43A/0 | DC2+0 | DCT
296 | 43/7 | DA+0 |  |  |  | 296 | 43/6 | DA+3
297 | 43/8 | DA+9 |  |  |  | 297 | 43/7 | DA+0
298 | 44/0 | DB1+6 |  |  |  | 298 | 43/8 | DA+9
[6 empty] | 299 | 44/0 | DB1+6
[6 empty] | 300 | 44/1 | DA+3
[6 empty] | 301 | 44/2 | DA+3
[6 empty] | 302 | 44/3 | DA+3
[6 empty] | 303 | 44/4 | DA+0
[6 empty] | 304 | 44/5 | DA+0
[6 empty] | 305 | 45/0 | DB1+9
[6 empty] | 306 | 46/0 | DB1+12
Note on M23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 Nos DCT tower
Note on M31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18
Note on K103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18

## Statutory Proposals (hidden)
OWNER: M/S. M/S. POWERGRID BIKANER NEEMRANA TRANSMISSION LIMITED (POWER GRID CORPORATION OF INDIA)
CONTRACTOR: M/S. KEC INTERNATIONAL LIMITED.
PROJECT: CONSTRUCTION OF 765KV D/C Bikaner III to Neemrana II Transmission Line
STATUTORY PROPOSALS STATUS
Sl.No | Description of Crossing |  |  | Crossing Authority | Proposal Submission Status | Present status | Contact Details | Remarks
POWER LINE CROSSINGS
1 | AP-12 | AP-13 | 132 KV S/C BKN-LKS T/L | RVPN | SUBMITTED ON DT: 24.07.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to RVPN Authority on dated 21.10.2024 Site Joint visit done on date 12.11.2024 NOC obtained - 06.12.2024
2 | AP-14 | AP-15 | 400 KV D/C SUR-BKN | Adani Power | SUBMITTED ON DT: 24.07.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to Concern Adani Authority and soft copy on dated 28.10.2024 Site Joint visit done on dtd 26.11.2024 NOC obtained on dtd: 21.01.2025
3 | AP-22 | AP-23 | 220 KV S/C SUR-BKN | RVPN | SUBMITTED ON DT: 24.07.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to RVPN Authority on dated 21.10.2024 Site joint visit done on date-13.11.2024 NOC obtained - 06.12.2024
4 | AP-24 | AP-25 | 400 KV S/C STP-BKN T/L | RVPN | SUBMITTED ON DT: 24.07.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to RVPN Authority on dated 21.10.2024 Site joint visit done on date-13.11.2024 NOC obtained - 06.12.2024
5 | AP-26 | AP-27 | 765 KV D/C BKN-MGA T/L | PGCIL | SUBMITTED ON DT: 24.07.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to PGCIL Authority on dated 21.10.2024 Mail obtained from PGCIL- 23.12.2024
6 | AP45 | AP46 | 132 KV D/C Halsar-Patlisar T/L | RVPN | SUBMITTED ON DT: 01.03.2025 | Documents Prepared and Submitted through mail to PGCIL on dtd 01.03.2025 |  | Site Joint visit done on date 22.03.2025 NOC Obtained on 09.04.2025
RAILWAY CROSSINGS
1 | AP-19 | AP-20 | Railway Line Electrified SingleTrack | NORTH WEST RAILWAY ZONE | SUBMITTED ON DT: 24.08.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 Final demand is under process |  | Proposal Submitted to DEE office on dated 21-10-2024 Site joint visit done on date-28-11-2024 (Mail Obtained 16-05-2025 )
FOREST CROSSING/CLEARANCE
1 | Forest Depart Bikaner/Raj. |  | Forest | Forest Department | SUBMITTED ON DT: 15.06.2024 | Stage -I approval approved |  | Stage -I approval approved
2 | Forest Depart Churu/Raj. |  | Forest | Forest Department | SUBMITTED ON DT: 15.06.2024 | Stage -I approval approved |  | Stage -I approval approved
CANAL CROSSINGS
1 | 15/8 | 15/9 | Canal crossing | - | SUBMITTED ON DT: 17.10.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 17.10.2024 |  | Approved
NATIONAL HIGHWAY CROSSING
1 | AP-11 | AP-12 | NH - 62 | BIKANER DIVISION | SUBMITTED ON DT: 21.08.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to RVPN Authority on dated 04.11.2024 Site joint visit done on date-08.01.2025 (NOC Obtained on 23.05.2025)
2 | AP-28 | AP-29 | NH - 754A | BIKANER DIVISION | SUBMITTED ON DT: 21.08.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 24.07.2024 |  | Proposal Submitted to Haiways Authority on dtd 01.10.24 & Hard copy submitted Site Joint visit done on dtd 19.11.2024 (Mail Obtained 05-02-2025 )
STATE HIGHWAY CROSSING
1 | AP 2A/0 | AP 3A/0 | SH - 03 | BIKANER DIVISION | Documentation preparation under process | Under preparation |  | Shall be submitted on dt: 28.09.2024
2 | AP 32 | AP 33 | SH - 93 | BIKANER DIVISION | Documentation preparation under process | Under preparation |  | Shall be submitted on dt: 28.09.2024
OIL PIPELINE CROSSING
1 | LOC 36A/2 | AP 37 | Crude Oil pipeline | BIKANER DIVISION | SUBMITTED ON DT: 21.08.2024 | Documents Prepared and Submitted through mail to PGCIL on dtd 17.10.2024 |  | HMPL pipe crossing NOC is pending due to obeservation regarding crossing angle (70 Degree and as per CEA guideline it should be minimum 75 degree),Matter taken up with CEA
Sl.No | Summary |  |  | Total Nos | Proposal Submitted | Approval/NOC Obtained | Contact Details | Remarks
1 | POWERLINE CROSSINGS |  |  | 6 | 6 | 6 |  | Approved
2 | NATIONAL HIGHWAY CROSSINGS |  |  | 2 | 2 | 2 |  | Approved
3 | RAILWAY CROSSING |  |  | 1 | 1 | 1 |  | Approved
4 | FOREST CLEARANCE |  |  | 1 | 1 | 1 |  | Stage-2 approved
5 | Defence Aviation |  |  | 1 | 1 | 1 |  | NOC obtained
6 | CANAL CROSSING |  |  | 1 | 1 | 1 |  | Documents Prepared and Submitted through mail on dtd 17.10.2024
5 | CIVIL AVIATION |  |  | 1 | 1 | 1 |  | NOC obtained
6 | PTCC |  |  | 1 | 1 | Porposal submiited 0n 17.04.25. |  | Submitted 17.04.25 Under approval
7 | OIL Pipeline |  |  | 1 | 1 | 1 |  | Documents Prepared and Submitted on dtd 17.10.2024 Revised proposal submitted dtd 31/10/2025
8 | Sec-164: |  |  | 1 | 1 | 1 |  | Received on 16.04.2025
Total |  |  |  | 16 | 16 | 15
| 2025-05-18 | [7 empty] | 1 | 1 | 1 | 1

## Tower Abstarct (hidden)
Over all Tower Location details
S. No. | No of | Location | Type of | Approved details survey | Remarks
| AP | Tower No. | Tower | 24.07.2026
1 | AP-0 | Gantry | Gantry | Approved
2 | AP-1 | 1/0 | DD60+0 | Hold
3 | AP-2 | 2/0 | DD45+0 | Hold
4 | AP-3 | 3/0 | DB2+0 | Approved
5 |  | 3/1 | DA+3 | Approved
6 |  | 3/2 | DA+6 | Approved
7 |  | 3/3 | DA+3 | Approved
8 |  | 3/4 | DA+6 | Approved
9 |  | 3/5 | DA+3 | Approved
10 |  | 3/6 | DA+3 | Approved
11 |  | 3/7 | DA+3 | Approved
12 |  | 3/8 | DA+0 | Approved
13 |  | 3/9 | DA+0 | Approved
14 |  | 3/10 | DA+9 | Approved
15 |  | 3/11 | DA+0 | Approved
16 | AP-4 | 4/0 | DB1+9 | Approved
17 |  | 4/1 | DA+6 | Approved
18 |  | 4/2 | DA+3 | Approved
19 |  | 4/3 | DA+3 | Approved
20 |  | 4/4 | DA+6 | Approved
21 |  | 4/5 | DA+6 | Approved
22 | AP- 4A/0 | 4A/0 | DB1+3 | Approved
23 |  | 4A/1 | DA+6 | Approved
24 |  | 4A/2 | DA+6 | Approved
25 |  | 4A/3 | DA+9 | Approved
26 |  | 4A/4 | DA+6 | Approved
27 |  | 4A/5 | DA+9 | Approved
28 |  | 4A/6 | DA+9 | Approved
29 | AP-5 | 5/0 | DB1+6 | Approved
30 |  | 5/1 | DA+6 | Approved
31 |  | 5/2 | DA+9 | Approved
32 |  | 5/3 | DA+9 | Approved |  | 0
33 |  | 5/4 | DA-1.5 | Approved
34 |  | 5/5 | DA+6 | Approved
35 |  | 5/6 | DA+3 | Approved
36 |  | 5/7 | DA+9 | Approved
37 |  | 5/8 | DA+6 | Approved
38 |  | 5/9 | DA+6 | Approved
39 |  | 5/10 | DA+9 | Approved
40 | AP-5A | 5A/0 | DB1+12 | Approved
41 | AP-6 | 6/0 | DB1+9 | Approved
42 |  | 6/1 | DA+9 | Approved
43 |  | 6/2 | DA+6 | Approved
44 |  | 6/3 | DA+3 | Approved
45 |  | 6/4 | DA+9 | Approved
46 |  | 6/5 | DA+9 | Approved
47 |  | 6/6 | DA-3 | Approved
48 |  | 6/7 | DA+1.5 | Approved
49 |  | 6/8 | DA+3 | Approved
50 |  | 6/9 | DA+6 | Approved
51 |  | 6/10 | DA+1.5 | Approved
52 |  | 6/11 | DA-1.5 | Approved
53 |  | 6/12 | DA+1.5 | Approved
54 | AP-7 | 7/0 | DB2+0 | Approved
55 |  | 7/1 | DA-3 | Approved
56 |  | 7/2 | DA+6 | Approved
57 |  | 7/3 | DA+9 | Approved
58 |  | 7/4 | DA+6 | Approved
59 |  | 7/5 | DA+6 | Approved
60 |  | 7/6 | DA-1.5 | Approved
61 | AP-7A | 7A/0 | DB1+6 | Approved
62 |  | 7A/1 | DA+1.5 | Approved
63 |  | 7A/2 | DA+3 | Approved
64 |  | 7A/3 | DA+3 | Approved
65 |  | 7A/4 | DA+3 | Approved
66 |  | 7A/5 | DA+3 | Approved
67 | AP-8 | 8/0 | DB1+0 | Approved
68 |  | 8/1 | DA-3 | Approved
69 |  | 8/2 | DA+6 | Approved
70 |  | 8/3 | DA+9 | Approved
71 |  | 8/4 | DA+6 | Approved
72 |  | 8/5 | DA+9 | Approved
73 |  | 8/6 | DA+3 | Approved
74 |  | 8/7 | DA+3 | Approved
75 |  | 8/8 | DA+9 | Approved
76 |  | 8/9 | DA+3 | Approved
77 |  | 8/10 | DA+0 | Approved
78 |  | 8/11 | DA+9 | Approved
79 | AP-8A | 8A/0 | DB1+12 | Approved
80 | AP-9 | 9/0 | DB1+12 | Approved
81 |  | 9/1 | DA+3 | Approved
82 |  | 9/2 | DA+3 | Approved
83 |  | 9/3 | DA+0 | Approved
84 |  | 9/4 | DA+6 | Approved
85 |  | 9/5 | DA+3 | Approved
86 |  | 9/6 | DA+3 | Approved
87 |  | 9/7 | DA+9 | Approved
88 |  | 9/8 | DA+0 | Approved
89 |  | 9/9 | DA+0 | Approved
90 |  | 9/10 | DA+3 | Approved
91 |  | 9/11 | DA+3 | Approved
92 | AP-10 | 10/0 | DB1+6 | Approved
93 |  | 10/1 | DA+3 | Approved
94 |  | 10/2 | DA+3 | Approved
95 | AP-11 | 11/0 | DD45+0 | Hold | Hold for NH
96 | AP-12 | 12/0 | DB1+9 | approved | Hold For PLC
97 | AP-13 | 13/0 | DD60+9 | Hold | Hold For PLC
98 | AP-13A | 13A/0 | DB1+9 | Approved
99 | AP-14 | 14/0 | DD60+18 | Hold | Hold For PLC
100 | AP-15 | 15/0 | DD60+25 | Hold | Hold For PLC
101 |  | 15/1 | DA+6 | Approved
102 |  | 15/2 | DA+3 | Approved
103 |  | 15/3 | DA+3 | Approved
104 |  | 15/4 | DA+6 | Approved
105 |  | 15/5 | DA+3 | Approved
106 |  | 15/6 | DA+9 | Approved
107 |  | 15/7 | DA+0 | Approved
108 |  | 15/8 | DA+1.5 | Approved
109 |  | 15/9 | DA+0 | Approved
110 |  | 15/10 | DA-1.5 | Approved
111 |  | 15/11 | DA+0 | Approved
112 |  | 15/12 | DA+6 | Approved
113 | AP-16 | 16/0 | DC2+0 | Approved
114 | AP-17 | 17/0 | DC1+3 | Approved
115 | AP-18 | 18/0 | DB2+6 | Approved
116 |  | 18/1 | DA+3 | Approved
117 |  | 18/2 | DA+1.5 | Approved
118 |  | 18/3 | DA+6 | Approved
119 |  | 18/4 | DA-3 | Approved
120 |  | 18/5 | DA+0 | Approved
121 |  | 18/6 | DA+9 | Approved
122 |  | 18/7 | DA+1.5 | Approved
123 | AP-19 | 19/0 | DD60+3 | Hold | Hold for RLY
124 | AP-20 | 20/0 | DD60+3 | Hold | Hold for RLY
125 |  | 20/1 | DA-3 | Approved
126 |  | 20/2 | DA-3 | Approved
127 |  | 20/3 | DA+1.5 | Approved
128 |  | 20/4 | DA+3 | Approved
129 |  | 20/5 | DA+0 | Approved
130 |  | 20/6 | DA-3 | Approved
131 | AP-21 | 21/0 | DB1+0 | Approved
132 |  | 21/1 | DA+0 | Approved
133 |  | 21/2 | DA+6 | Approved
134 |  | 21/3 | DA+6 | Approved
135 |  | 21/4 | DA+0 | Approved
136 |  | 21/5 | DA+0 | Approved
137 | AP-22 | 22/0 | DC2+15 | Approved | Hold For PLC
138 | AP-23 | 23/0 | DB2+9 | Approved | Hold For PLC
139 | AP-23A | 23A/0 | DB1+9 | Approved
140 | AP-24 | 24/0 | DD60+18 | Approved | Hold For PLC
141 | AP-25 | 25/0 | DD60+18 | Approved | Hold For PLC
142 | AP-26 | 26/0 | DD60+35 | Approved | Hold For PLC
143 | AP-27 | 27/0 | DD60+35 | Approved | Hold For PLC
144 |  | 27/1 | DA+9 | Approved
145 |  | 27/2 | DA-1.5 | Approved
146 |  | 27/3 | DA+1.5 | Approved
147 |  | 27/4 | DA+1.5 | Approved
148 |  | 27/5 | DA-1.5 | Approved
149 |  | 27/6 | DA-3 | Approved
150 | AP-28 | 28/0 | DC2-3 | Hold | Hold for NH
151 | AP-29 | 29/0 | DC1+0 | Hold | Hold for NH
152 |  | 29/1 | DA+6 | Approved
153 |  | 29/2 | DA+0 | Approved
154 |  | 29/3 | DA+0 | Approved
155 |  | 29/4 | DA+3 | Approved
156 |  | 29/5 | DA+0 | Approved
157 | AP-29A/0 | 29A/0 | DB1+0 | Approved
158 |  | 29A/1 | DA+6 | Approved
159 |  | 29A/2 | DA+6 | Approved
160 |  | 29A/3 | DA+6 | Approved
161 |  | 29A/4 | DA+3 | Approved
162 |  | 29A/5 | DA+6 | Approved
163 |  | 29A/6 | DA+9 | Approved
164 | AP-30 | 30/0 | DB1+0 | Approved
165 |  | 30/1 | DA+0 | Approved
166 |  | 30/2 | DA+9 | Approved
167 |  | 30/3 | DA+3 | Approved
168 |  | 30/4 | DA+9 | Approved
169 |  | 30/5 | DA+0 | Approved
170 |  | 30/6 | DA+6 | Approved
171 |  | 30/7 | DA-3 | Approved
172 |  | 30/8 | DA+3 | Approved
173 |  | 30/9 | DA-3 | Approved
174 |  | 30/10 | DA+3 | Approved
175 | AP-31 | 31/0 | DB1+0 | Approved
176 |  | 31/1 | DA+3 | Approved
177 |  | 31/2 | DA+1.5 | Approved
178 |  | 31/3 | DA+3 | Approved
179 |  | 31/4 | DA-1.5 | Approved
180 |  | 31/5 | DA+6 | Approved
181 |  | 31/6 | DA+9 | Approved
182 |  | 31/7 | DA+0 | Approved
183 |  | 31/8 | DA+0 | Approved
184 |  | 31/9 | DA+1.5 | Approved
185 |  | 31/10 | DA+4.5 | Approved
186 | AP-32 | 32/0 | DB2+0 | Approved
187 |  | 32/1 | DA+6 | Approved
188 |  | 32/2 | DA+9 | Approved
189 |  | 32/3 | DA+6 | Approved
190 |  | 32/4 | DA+9 | Approved
191 |  | 32/5 | DA+9 | Approved
192 |  | 32/6 | DA+9 | Approved
193 |  | 32/7 | DA+3 | Approved
194 | AP-32A/0 | 32A/0 | DB1+9 | Approved
195 |  | 32A/1 | DA+6 | Approved
196 | AP-33 | 33/0 | DB1+9 | Approved
197 |  | 33/1 | DA+9 | Approved
198 |  | 33/2 | DA+9 | Approved
199 |  | 33/3 | DA+3 | Approved
200 |  | 33/4 | DA+3 | Approved
201 |  | 33/5 | DA+0 | Approved
202 |  | 33/6 | DA+6 | Approved
203 |  | 33/7 | DA+6 | Approved
204 |  | 33/8 | DA+3 | Approved
205 |  | 33/9 | DA+1.5 | Approved
206 | AP-34 | 34/0 | DB1+6 | Approved
207 |  | 34/1 | DA+9 | Approved
208 |  | 34/2 | DA+9 | Approved
209 |  | 34/3 | DA+1.5 | Approved
210 |  | 34/4 | DA+6 | Approved
211 |  | 34/5 | DA+9 | Approved
212 |  | 34/6 | DA+3 | Approved
213 |  | 34/7 | DA+0 | Approved
214 |  | 34/8 | DA+0 | Approved
215 |  | 34/9 | DA+1.5 | Approved
216 |  | 34/10 | DA-3 | Approved
217 |  | 34/11 | DA+1.5 | Approved
218 |  | 34/12 | DA+3 | Approved
219 | AP-35 | 35/0 | DB2+0 | Approved
220 |  | 35/1 | DA+6 | Approved
221 |  | 35/2 | DA+6 | Approved
222 |  | 35/3 | DA-3 | Approved
223 |  | 35/4 | DA+9 | Approved
224 |  | 35/5 | DA+9 | Approved
225 |  | 35/6 | DA+6 | Approved
226 |  | 35/7 | DA+3 | Approved
227 |  | 35/8 | DA+6 | Approved
228 |  | 35/9 | DA+1.5 | Approved
229 |  | 35/10 | DA+3 | Approved
230 |  | 35/11 | DA+3 | Approved
231 | AP-36 | 36/0 | DB2+3 | Approved
232 |  | 36/1 | DB1+9 | Approved
233 |  | 36/2 | DA+3 | Approved
234 |  | 36/3 | DA+9 | Approved
235 | AP-37 | 37/0 | DB2+3 | Approved
236 |  | 37/1 | DA+3 | Approved
237 |  | 37/2 | DA+3 | Approved
238 |  | 37/3 | DA-1.5 | Approved
239 |  | 37/4 | DA+9 | Approved
240 |  | 37/5 | DA+3 | Approved
241 | AP-37A | 37A/0 | DB1+0 | Approved
242 |  | 37A/1 | DA+3 | Approved
243 |  | 37A/2 | DA+1.5 | Approved
244 |  | 37A/3 | DA+3 | Approved
245 |  | 37A/4 | DA+9 | Approved
246 |  | 37A/5 | DA+3 | Approved
247 |  | 37A/6 | DA+3 | Approved
248 | AP-38 | 38/0 | DB1+3 | Approved
249 |  | 38/1 | DA+0 | Approved
250 |  | 38/2 | DA+0 | Approved
251 |  | 38/3 | DA+3 | Approved
252 |  | 38/4 | DA+1.5 | Approved
253 |  | 38/5 | DA+3 | Approved
254 |  | 38/6 | DA+6 | Approved
255 |  | 38/7 | DA+9 | Approved
256 |  | 38/8 | DA+1.5 | Approved
257 |  | 38/9 | DA+0 | Approved
258 |  | 38/10 | DA+3 | Approved
259 | AP-39 | 39/0 | DB2+0 | Approved
260 |  | 39/1 | DA-1.5 | Approved
261 |  | 39/2 | DA+3 | Approved
262 |  | 39/3 | DA+1.5 | Approved
263 |  | 39/4 | DA+3 | Approved
264 |  | 39/5 | DA+1.5 | Approved
265 |  | 39/6 | DA+1.5 | Approved
266 |  | 39/7 | DA+3 | Approved
267 |  | 39/8 | DA+1.5 | Approved
268 |  | 39/9 | DA+6 | Approved
269 |  | 39/10 | DA+3 | Approved
270 |  | 39/11 | DA+6 | Approved
271 | AP-40 | 40/0 | DB1+6 | Approved
272 |  | 40/1 | DA+9 | Approved
273 |  | 40/2 | DA+6 | Approved
274 |  | 40/3 | DA+3 | Approved
275 |  | 40/4 | DA+6 | Approved
276 |  | 40/5 | DA+9 | Approved
277 |  | 40/6 | DA+9 | Approved
278 |  | 40/7 | DA+3 | Approved
279 |  | 40/8 | DA-1.5 | Approved
280 |  | 40/9 | DA+9 | Approved
281 |  | 40/10 | DA+3 | Approved
282 |  | 40/11 | DA+9 | Approved
283 | AP-40A | 40A/0 | DB1+9 | Approved
284 | AP-41 | 41/0 | DB1+9 | Approved
285 |  | 41/1 | DA+9 | Approved
286 | AP-42 | 42/0 | DB2+0 | Approved
287 |  | 42/1 | DA+3 | Approved
288 |  | 42/2 | DA+9 | Approved
289 |  | 42/3 | DB1+9 | Approved
290 | AP-43 | 43/0 | DB1+0 | Approved
291 |  | 43/1 | DA-1.5 | Approved
292 |  | 43/2 | DA+6 | Approved
293 |  | 43/3 | DA-1.5 | Approved
294 |  | 43/4 | DA+0 | Approved
295 | DCT | 43/5 | DC2+0 | Approved | 'TP tower modified cross arms
296 |  | 43/6 | DA+3 | Approved
297 |  | 43/7 | DA+0 | Approved
298 |  | 43/8 | DA+9 | Approved
299 | AP-44 | 44/0 | DB1+6 | Approved
Note on F103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18
Note on E154: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DC2+0 to DC-3

## Location Summary
Over all Tower Location details
S. No. | No of | Location | Type of |  | RC |  | Span | Cumm. | DS Status as on | 306 | 304 | 304 | 116 | 26 | Remarks
| AP | Tower No. | Tower |  |  |  | Length (m) | Span (km) | 2026-05-23 | Foundation | Earthing | Tower Erection | Tack welding | SPT
0 |  | Gantry | Gantry |  |  |  |  | 0
[6 empty] | Gantry | 150.014
1 | AP-1 | 1/0 | DD60+0 | T |  |  |  | 0.15 | Approved | Completed | Completed | Completed
[6 empty] | 1/0 | 290.21
2 | AP-2A | 2A/0 | DD45+0 | T |  |  |  | 0.4402 | Approved | Completed | Completed | Completed
[6 empty] | 2A/0 | 378
3 | AP-3 | 2A/1 | DA+0 |  |  |  |  | 0.8182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/1 | 381
4 |  | 2A/2 | DA+3 |  |  |  |  | 1.1992 | Approved | Completed | Completed | Completed
[6 empty] | 2A/2 | 419
5 |  | 2A/3 | DA+3 |  |  |  |  | 1.6182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/3 | 422
6 |  | 2A/4 | DA+3 |  |  |  |  | 2.0402 | Approved | Completed | Completed | Completed
[6 empty] | 2A/4 | 399
7 |  | 2A/5 | DA+3 |  |  |  |  | 2.4392 | Approved | Completed | Completed | Completed
[6 empty] | 2A/5 | 423
8 |  | 2A/6 | DA+6 |  |  |  |  | 2.8622 | Approved | Completed | Completed | Completed
[6 empty] | 2A/6 | 414.992
9 |  | 3A/0 | DD45+3 | T |  |  |  | 3.2772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/0 | 409
10 |  | 3A/1 | DA+3 |  |  |  |  | 3.6862 | Approved | Completed | Completed | Completed
[6 empty] | 3A/1 | 402
11 |  | 3A/2 | DA+3 |  |  |  |  | 4.0882 | Approved | Completed | Completed | Completed
[6 empty] | 3A/2 | 409
12 |  | 3A/3 | DA+0 |  |  |  |  | 4.4972 | Approved | Completed | Completed | Completed |  | Completed |  | 274
[6 empty] | 3A/3 | 337
13 |  | 3A/4 | DA+0 |  |  |  |  | 4.8342 | Approved | Completed | Completed | Completed
[6 empty] | 3A/4 | 365
14 |  | 3A/5 | DA+3 |  |  |  |  | 5.1992 | Approved | Completed | Completed | Completed
[6 empty] | 3A/5 | 378
15 | AP-4 | 3A/6 | DA+0 |  |  |  |  | 5.5772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/6 | 391.467
16 |  | 3B/0 | DB1+9 |  |  |  |  | 5.9687 | Approved | Completed | Completed | Completed
[6 empty] | 3B/0 | 356
17 |  | 3B/1 | DA+3 |  |  |  |  | 6.3247 | Approved | Completed | Completed | Completed
[6 empty] | 3B/1 | 439
18 |  | 3B/2 | DA+9 |  |  |  |  | 6.7637 | Approved | Completed | Completed | Completed
[6 empty] | 3B/2 | 377
19 |  | 3B/3 | DA+6 |  |  |  |  | 7.1407 | Approved | Completed | Completed | Completed
[6 empty] | 3B/3 | 455.07 | [8 empty] | 39
20 |  | 4/0 | DB2+9 |  |  |  |  | 7.5958 | Approved | Completed | Completed | Completed
[6 empty] | 4/0 | 344.163
21 |  | 4/1 | DA+6 |  |  |  |  | 7.94 | Approved | Completed | Completed | Completed |  |  | NO CHANGE S
[6 empty] | 4/1 | 365
22 | AP- 4A/0 | 4A/0 | DB1+3 |  |  |  |  | 8.305 | Approved | Completed | Completed | Completed
[6 empty] | 4A/0 | 340
23 |  | 4A/1 | DA+6 |  |  |  |  | 8.645 | Approved | Completed | Completed | Completed
[6 empty] | 4A/1 | 420
24 |  | 4A/2 | DA+6 |  |  |  |  | 9.065 | Approved | Completed | Completed | Completed
[6 empty] | 4A/2 | 415
25 |  | 4A/3 | DA+9 |  |  |  |  | 9.48 | Approved | Completed | Completed | Completed
[6 empty] | 4A/3 | 365
26 |  | 4A/4 | DA+6 |  |  |  |  | 9.845 | Approved | Completed | Completed | Completed
[6 empty] | 4A/4 | 330
27 |  | 4A/5 | DA+9 |  |  |  |  | 10.175 | Approved | Completed | Completed | Completed
[6 empty] | 4A/5 | 457
28 |  | 4A/6 | DA+9 |  |  |  |  | 10.632 | Approved | Completed | Completed | Completed
[6 empty] | 4A/6 | 354.611
29 | AP5 | 5/0 | DB1+6 |  |  |  |  | 10.9866 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 5/0 | 428.389
30 |  | 5/1 | DA+6 |  |  |  |  | 11.415 | Approved | Completed | Completed | Completed
[6 empty] | 5/1 | 340
31 |  | 5/2 | DA+9 |  |  |  |  | 11.755 | Approved | Completed | Completed | Completed
[6 empty] | 5/2 | 375
32 |  | 5/3 | DA+9 |  |  |  |  | 12.13 | Approved | Completed | Completed | Completed
[6 empty] | 5/3 | 365
33 |  | 5/4 | DA-1.5 |  |  |  |  | 12.495 | Approved | Completed | Completed | Completed
[6 empty] | 5/4 | 460
34 |  | 5/5 | DA+6 |  |  |  |  | 12.955 | Approved | Completed | Completed | Completed
[6 empty] | 5/5 | 380
35 |  | 5/6 | DA+3 |  |  |  |  | 13.335 | Approved | Completed | Completed | Completed
[6 empty] | 5/6 | 410
36 |  | 5/7 | DA+9 |  |  |  |  | 13.745 | Approved | Completed | Completed | Completed
[6 empty] | 5/7 | 400
37 |  | 5/8 | DA+6 |  |  |  |  | 14.145 | Approved | Completed | Completed | Completed
[6 empty] | 5/8 | 420
38 |  | 5/9 | DA+6 |  |  |  |  | 14.565 | Approved | Completed | Completed | Completed
[6 empty] | 5/9 | 345
39 |  | 5/10 | DA+9 |  |  |  |  | 14.91 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 5/10 | 495
40 | AP-5A | 5A/0 | DB1+12 |  |  |  |  | 15.405 | Approved | Completed | Completed | Completed
[6 empty] | 5A/0 | 419.48
41 | AP-6 | 6/0 | DB1+9 |  |  |  |  | 15.8245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/0 | 350.52
42 |  | 6/1 | DA+9 |  |  |  |  | 16.175 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/1 | 445
43 |  | 6/2 | DA+6 |  |  |  |  | 16.62 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/2 | 390
44 |  | 6/3 | DA+3 |  |  |  |  | 17.01 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/3 | 350
45 |  | 6/4 | DA+9 |  |  |  |  | 17.36 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/4 | 490
46 |  | 6/5 | DA+9 |  |  |  |  | 17.85 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/5 | 350
47 |  | 6/6 | DA-3 |  |  |  |  | 18.2 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/6 | 347
48 |  | 6/7 | DA+1.5 |  |  |  |  | 18.547 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/7 | 373
49 |  | 6/8 | DA+3 |  |  |  |  | 18.92 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/8 | 380
50 |  | 6/9 | DA+6 |  |  |  |  | 19.3 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/9 | 335
51 |  | 6/10 | DA+1.5 |  |  |  |  | 19.635 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/10 | 315
52 |  | 6/11 | DA-1.5 |  |  |  |  | 19.95 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/11 | 410
53 |  | 6/12 | DA+1.5 |  |  |  |  | 20.36 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 6/12 | 365.716
54 | AP-7 | 7/0 | DB2+0 |  |  |  |  | 20.7257 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7/0 | 319.284
55 |  | 7/1 | DA-3 |  |  |  |  | 21.045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/1 | 465
56 |  | 7/2 | DA+6 |  |  |  |  | 21.51 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/2 | 375
57 |  | 7/3 | DA+9 |  |  |  |  | 21.885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/3 | 355
58 |  | 7/4 | DA+6 |  |  |  |  | 22.24 | Approved | Completed | Completed | Completed
[6 empty] | 7/4 | 420
59 |  | 7/5 | DA+6 |  |  |  |  | 22.66 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/5 | 315
60 |  | 7/6 | DA-1.5 |  |  |  |  | 22.975 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/6 | 450
61 | AP-7A | 7A/0 | DB1+6 |  |  |  |  | 23.425 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/0 | 435
62 |  | 7A/1 | DA+1.5 |  |  |  |  | 23.86 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/1 | 385
63 |  | 7A/2 | DA+3 |  |  |  |  | 24.245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/2 | 390
64 |  | 7A/3 | DA+3 |  |  |  |  | 24.635 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/3 | 405
65 |  | 7A/4 | DA+3 |  |  |  |  | 25.04 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7A/4 | 390
66 |  | 7A/5 | DA+3 |  |  |  |  | 25.43 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/5 | 429.77
67 | AP-8 | 8/0 | DB1+0 |  |  |  |  | 25.8598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/0 | 350
68 |  | 8/1 | DA-3 |  |  |  |  | 26.2098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/1 | 330
69 |  | 8/2 | DA+6 |  |  |  |  | 26.5398 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/2 | 390
70 |  | 8/3 | DA+9 |  |  |  |  | 26.9298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/3 | 400
71 |  | 8/4 | DA+6 |  |  |  |  | 27.3298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/4 | 338
72 |  | 8/5 | DA+9 |  |  |  |  | 27.6678 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/5 | 357
73 |  | 8/6 | DA+3 |  |  |  |  | 28.0248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/6 | 335
74 |  | 8/7 | DA+3 |  |  |  |  | 28.3598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/7 | 415
75 |  | 8/8 | DA+9 |  |  |  |  | 28.7748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/8 | 375
76 |  | 8/9 | DA+3 |  |  |  |  | 29.1498 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/9 | 375
77 |  | 8/10 | DA+0 |  |  |  |  | 29.5248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/10 | 375
78 |  | 8/11 | DA+9 |  |  |  |  | 29.8998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/11 | 415
79 | AP-8A | 8A/0 | DB1+12 |  |  |  |  | 30.3148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8A/0 | 466.63
80 | AP-9 | 9/0 | DB1+12 |  |  |  |  | 30.7814 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 9/0 | 418.372
81 |  | 9/1 | DA+3 |  |  |  |  | 31.1998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/1 | 410
82 |  | 9/2 | DA+3 |  |  |  |  | 31.6098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/2 | 395
83 |  | 9/3 | DA+0 |  |  |  |  | 32.0048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/3 | 395
84 |  | 9/4 | DA+6 |  |  |  |  | 32.3998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/4 | 425
85 |  | 9/5 | DA+3 |  |  |  |  | 32.8248 | Approved | Completed | Completed | Completed
[6 empty] | 9/5 | 415
86 |  | 9/6 | DA+3 |  |  |  |  | 33.2398 | Approved | Completed | Completed | Completed
[6 empty] | 9/6 | 405
87 |  | 9/7 | DA+9 |  |  |  |  | 33.6448 | Approved | Completed | Completed | Completed
[6 empty] | 9/7 | 435
90 |  | 9/8 | DA+0 |  |  |  |  | 34.0798 | Approved | Completed | Completed | Completed
[6 empty] | 9/8 | 405
89 |  | 9/9 | DA+0 |  |  |  |  | 34.4848 | Approved | Completed | Completed | Completed
[6 empty] | 9/9 | 435
90 |  | 9/10 | DA+3 |  |  |  |  | 34.9198 | Approved | Completed | Completed | Completed
[6 empty] | 9/10 | 395
91 |  | 9/11 | DA+3 |  |  |  |  | 35.3148 | Approved | Completed | Completed | Completed
[6 empty] | 9/11 | 431.548
92 | AP-10 | 10/0 | DB1+6 |  |  |  |  | 35.7463 | Approved | Completed | Completed | Completed
[6 empty] | 10/0 | 363.452
93 |  | 10/1 | DA+3 |  |  |  |  | 36.1098 | Approved | Completed | Completed | Completed
[6 empty] | 10/1 | 295
94 |  | 10/2 | DA+3 |  |  |  |  | 36.4048 | Approved | Completed | Completed | Completed
[6 empty] | 10/2 | 345.731
95 | AP-11 | 11/0 | DD45+0 |  |  |  |  | 36.7505 | Approved | Completed | Completed | Completed
[6 empty] | 11/0 | 242.89 | [7 empty] | NH
96 | AP-12 | 12/0 | DB1+9 |  |  |  |  | 36.9934 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 12/0 | 329.73 | [7 empty] | 132 KV PL
97 | AP-13 | 13/0 | DD60+9 |  |  |  |  | 37.3231 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 13/0 | 416.88
98 | AP-13A | 13A/0 | DB1+9 |  |  |  |  | 37.74 | Approved | Completed | Completed | Completed
[6 empty] | 13A/0 | 480.27
99 | AP-14 | 14/0 | DD60+18 |  | 2 |  |  | 38.2203 | Approved | Completed | Completed | Completed
[6 empty] | 14/0 | 223.82 | [7 empty] | 400 KV PL
100 | AP-15 | 15/0 | DD60+25 |  |  |  |  | 38.4441 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 15/0 | 405.915
101 |  | 15/1 | DA+6 |  |  |  |  | 38.85 | Approved | Completed | Completed | Completed
[6 empty] | 15/1 | 405
102 |  | 15/2 | DA+3 |  |  |  |  | 39.255 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/2 | 420
103 |  | 15/3 | DA+3 |  |  |  |  | 39.675 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/3 | 415
104 |  | 15/4 | DA+6 |  |  |  |  | 40.09 | Approved | Completed | Completed | Completed
[6 empty] | 15/4 | 410
105 |  | 15/5 | DA+3 |  |  |  |  | 40.5 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/5 | 285
106 |  | 15/6 | DA+9 |  |  |  |  | 40.785 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/6 | 355
107 |  | 15/7 | DA+0 |  |  |  |  | 41.14 | Approved | Completed | Completed | Completed
[6 empty] | 15/7 | 355
108 |  | 15/8 | DA+1.5 |  |  |  |  | 41.495 | Approved | Completed | Completed | Completed
[6 empty] | 15/8 | 410
109 |  | 15/9 | DA+0 |  |  |  |  | 41.905 | Approved | Completed | Completed | Completed
[6 empty] | 15/9 | 430
110 |  | 15/10 | DA-1.5 |  |  |  |  | 42.335 | Approved | Completed | Completed | Completed
[6 empty] | 15/10 | 385
111 |  | 15/11 | DA+0 |  |  |  |  | 42.72 | Approved | Completed | Completed | Completed
[6 empty] | 15/11 | 455
112 |  | 15/12 | DA+6 |  |  |  |  | 43.175 | Approved | Completed | Completed | Completed
[6 empty] | 15/12 | 288.425
113 | AP-16 | 16/0 | DC2+0 |  |  |  |  | 43.4634 | Approved | Completed | Completed | Completed
[6 empty] | 16/0 | 392.69 | [7 empty] | 11KV LINE
114 | AP-17 | 17/0 | DC1+3 |  |  |  |  | 43.8561 | Approved | Completed | Completed | Completed
[6 empty] | 17/0 | 398.4 | [7 empty] | 11KV LINE
115 | AP-18 | 18/0 | DB2+6 |  |  |  |  | 44.2545 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 18/0 | 307.595
116 |  | 18/1 | DA+3 |  |  |  |  | 44.5621 | Approved | Completed | Completed | Completed
[6 empty] | 18/1 | 390
117 |  | 18/2 | DA+1.5 |  |  |  |  | 44.9521 | Approved | Completed | Completed | Completed
[6 empty] | 18/2 | 380
118 |  | 18/3 | DA+6 |  |  |  |  | 45.3321 | Approved | Completed | Completed | Completed
[6 empty] | 18/3 | 405
119 |  | 18/4 | DA-3 |  |  |  |  | 45.7371 | Approved | Completed | Completed | Completed
[6 empty] | 18/4 | 335
120 |  | 18/5 | DA+0 |  |  |  |  | 46.0721 | Approved | Completed | Completed | Completed
[6 empty] | 18/5 | 425
121 |  | 18/6 | DA+9 |  |  |  |  | 46.4971 | Approved | Completed | Completed | Completed
[6 empty] | 18/6 | 402
122 |  | 18/7 | DA+1.5 |  |  |  |  | 46.8991 | Approved | Completed | Completed | Completed
[6 empty] | 18/7 | 385.434
123 | AP-19 | 19/0 | DD60+3 |  |  |  |  | 47.2845 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 19/0 | 279.36 | [7 empty] | Rly
124 | AP-20 | 20/0 | DD60+3 |  |  |  |  | 47.5639 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 20/0 | 388.515
125 |  | 20/1 | DA-3 |  |  |  |  | 47.9524 | Approved | Completed | Completed | Completed
[6 empty] | 20/1 | 330
126 |  | 20/2 | DA-3 |  |  |  |  | 48.2824 | Approved | Completed | Completed | Completed
[6 empty] | 20/2 | 340
127 |  | 20/3 | DA+1.5 |  |  |  |  | 48.6224 | Approved | Completed | Completed | Completed
[6 empty] | 20/3 | 420
128 |  | 20/4 | DA+3 |  |  |  |  | 49.0424 | Approved | Completed | Completed | Completed
[6 empty] | 20/4 | 396
129 |  | 20/5 | DA+0 |  |  |  |  | 49.4384 | Approved | Completed | Completed | Completed
[6 empty] | 20/5 | 355
130 |  | 20/6 | DA-3 |  |  |  |  | 49.7934 | Approved | Completed | Completed | Completed
[6 empty] | 20/6 | 320.652
131 | AP-21 | 21/0 | DB1+0 |  |  |  |  | 50.1141 | Approved | Completed | Completed | Completed
[6 empty] | 21/0 | 326.348
132 |  | 21/1 | DA+0 |  |  |  |  | 50.4404 | Approved | Completed | Completed | Completed
[6 empty] | 21/1 | 427
133 |  | 21/2 | DA+6 |  |  |  |  | 50.8674 | Approved | Completed | Completed | Completed
[6 empty] | 21/2 | 410
134 |  | 21/3 | DA+6 |  |  |  |  | 51.2774 | Approved | Completed | Completed | Completed
[6 empty] | 21/3 | 405
135 |  | 21/4 | DA+0 |  |  |  |  | 51.6824 | Approved | Completed | Completed | Completed
[6 empty] | 21/4 | 300
136 |  | 21/5 | DA+0 |  |  |  |  | 51.9824 | Approved | Completed | Completed | Completed
[6 empty] | 21/5 | 415.187
137 | AP-22 | 22/0 | DC2+15 |  |  |  |  | 52.3976 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 22/0 | 259.05 | [7 empty] | 220 kv PL
138 | AP-23 | 23/0 | DB2+9 |  |  |  |  | 52.6567 | Approved | Completed | Completed | Completed
[6 empty] | 23/0 | 440.46
139 | AP-23A | 23A/0 | DB1+9 |  |  |  |  | 53.0972 | Approved | Completed | Completed | Completed
[6 empty] | 23A/0 | 496.69
140 | AP-24 | 24/0 | DD60+18 |  |  |  |  | 53.5939 | Approved | Completed | Completed | Completed
[6 empty] | 24/0 | 244.03 | [7 empty] | 400 kv PL
141 | AP-25 | 25/0 | DD60+18 |  |  |  |  | 53.8379 | Approved | Completed | Completed | Completed
[6 empty] | 25/0 | 237.43
142 | AP-26 | 26/0 | DD60+35 |  |  |  |  | 54.0753 | Approved | Completed | Completed | Completed
[6 empty] | 26/0 | 203.48 | [7 empty] | 765 kv PL
143 | AP-27 | 27/0 | DD60+35 |  |  |  |  | 54.2788 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 27/0 | 453.688
144 |  | 27/1 | DA+9 |  |  |  |  | 54.7325 | Approved | Completed | Completed | Completed
[6 empty] | 27/1 | 345
145 |  | 27/2 | DA-1.5 |  |  |  |  | 55.0775 | Approved | Completed | Completed | Completed
[6 empty] | 27/2 | 360
146 |  | 27/3 | DA+1.5 |  |  |  |  | 55.4375 | Approved | Completed | Completed | Completed
[6 empty] | 27/3 | 410
147 |  | 27/4 | DA+1.5 |  |  |  |  | 55.8475 | Approved | Completed | Completed | Completed
[6 empty] | 27/4 | 350
148 |  | 27/5 | DA-1.5 |  |  |  |  | 56.1975 | Approved | Completed | Completed | Completed
[6 empty] | 27/5 | 355
149 |  | 27/6 | DA-3 |  |  |  |  | 56.5525 | Approved | Completed | Completed | Completed
[6 empty] | 27/6 | 274.587
150 | AP-28 | 28/0 | DC2-3 |  |  |  |  | 56.8271 | Approved | Completed | Completed | Completed
[6 empty] | 28/0 | 211.21 | [7 empty] | NH
151 | AP-29 | 29/0 | DC1+0 |  |  |  |  | 57.0383 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 29/0 | 384.204
152 |  | 29/1 | DA+6 |  |  |  |  | 57.4225 | Approved | Completed | Completed | Completed
[6 empty] | 29/1 | 430
153 |  | 29/2 | DA+0 |  |  |  |  | 57.8525 | Approved | Completed | Completed | Completed
[6 empty] | 29/2 | 370
154 |  | 29/3 | DA+0 |  |  |  |  | 58.2225 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/3 | 390
155 |  | 29/4 | DA+3 |  |  |  |  | 58.6125 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/4 | 435
156 |  | 29/5 | DA+0 |  |  |  |  | 59.0475 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/5 | 370
157 | AP-29A/0 | 29A/0 | DB1+0 |  |  |  |  | 59.4175 | Approved | Completed | Completed | Completed
[6 empty] | 29A/0 | 455
158 |  | 29A/1 | DA+6 |  |  |  |  | 59.8725 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/1 | 325
159 |  | 29A/2 | DA+6 |  |  |  |  | 60.1975 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/2 | 395
160 |  | 29A/3 | DA+6 |  |  |  |  | 60.5925 | Approved | Completed | Completed | Completed
[6 empty] | 29A/3 | 345
161 |  | 29A/4 | DA+3 |  |  |  |  | 60.9375 | Approved | Completed | Completed | Completed
[6 empty] | 29A/4 | 345
162 |  | 29A/5 | DA+6 |  |  |  |  | 61.2825 | Approved | Completed | Completed | Completed
[6 empty] | 29A/5 | 440
163 |  | 29A/6 | DA+9 |  |  |  |  | 61.7225 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/6 | 364.008
164 | AP-30 | 30/0 | DB1+0 |  |  |  |  | 62.0865 | Approved | Completed | Completed | Completed
[6 empty] | 30/0 | 295.993
165 |  | 30/1 | DA+0 |  |  |  |  | 62.3825 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 30/1 | 425
166 |  | 30/2 | DA+9 |  |  |  |  | 62.8075 | Approved | Completed | Completed | Completed
[6 empty] | 30/2 | 315
167 |  | 30/3 | DA+3 |  |  |  |  | 63.1225 | Approved | Completed | Completed | Completed
[6 empty] | 30/3 | 380
168 |  | 30/4 | DA+9 |  |  |  |  | 63.5025 | Approved | Completed | Completed | Completed
[6 empty] | 30/4 | 430
169 |  | 30/5 | DA+0 |  |  |  |  | 63.9325 | Approved | Completed | Completed | Completed
[6 empty] | 30/5 | 380
170 |  | 30/6 | DA+6 |  |  |  |  | 64.3125 | Approved | Completed | Completed | Completed
[6 empty] | 30/6 | 335
171 |  | 30/7 | DA-3 |  |  |  |  | 64.6475 | Approved | Completed | Completed | Completed
[6 empty] | 30/7 | 395
172 |  | 30/8 | DA+3 |  |  |  |  | 65.0425 | Approved | Completed | Completed | Completed
[6 empty] | 30/8 | 390
173 |  | 30/9 | DA-3 |  |  |  |  | 65.4325 | Approved | Completed | Completed | Completed
[6 empty] | 30/9 | 350
174 |  | 30/10 | DA+3 |  |  |  |  | 65.7825 | Approved | Completed | Completed | Completed
[6 empty] | 30/10 | 428.239
175 | AP-31 | 31/0 | DB1+0 |  |  |  |  | 66.2107 | Approved | Completed | Completed | Completed
[6 empty] | 31/0 | 376.761
176 |  | 31/1 | DA+3 |  |  |  |  | 66.5875 | Approved | Completed | Completed | Completed
[6 empty] | 31/1 | 410
177 |  | 31/2 | DA+1.5 |  |  |  |  | 66.9975 | Approved | Completed | Completed | Completed
[6 empty] | 31/2 | 430
178 |  | 31/3 | DA+3 |  |  |  |  | 67.4275 | Approved | Completed | Completed | Completed
[6 empty] | 31/3 | 380
179 |  | 31/4 | DA-1.5 |  |  |  |  | 67.8075 | Approved | Completed | Completed | Completed
[6 empty] | 31/4 | 445
180 |  | 31/5 | DA+6 |  |  |  |  | 68.2525 | Approved | Completed | Completed | Completed
[6 empty] | 31/5 | 385
181 |  | 31/6 | DA+9 |  |  |  |  | 68.6375 | Approved | Completed | Completed | Completed
[6 empty] | 31/6 | 420
182 |  | 31/7 | DA+0 |  |  |  |  | 69.0575 | Approved | Completed | Completed | Completed
[6 empty] | 31/7 | 415
183 |  | 31/8 | DA+0 |  |  |  |  | 69.4725 | Approved | Completed | Completed | Completed
[6 empty] | 31/8 | 310
184 |  | 31/9 | DA+1.5 |  |  |  |  | 69.7825 | Approved | Completed | Completed | Completed
[6 empty] | 31/9 | 445
185 |  | 31/10 | DA+4.5 |  |  |  |  | 70.2275 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 31/10 | 316.608
186 | AP-32 | 32/0 | DB2+0 |  |  |  |  | 70.5441 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/0 | 385.51
187 |  | 32/1 | DA+6 |  |  |  |  | 70.9296 | Approved | Completed | Completed | Completed
[6 empty] | 32/1 | 410
188 |  | 32/2 | DA+9 |  |  |  |  | 71.3396 | Approved | Completed | Completed | Completed
[6 empty] | 32/2 | 390
189 |  | 32/3 | DA+6 |  |  |  |  | 71.7296 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/3 | 450
190 |  | 32/4 | DA+9 |  |  |  |  | 72.1796 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/4 | 370
191 |  | 32/5 | DA+9 |  | 2 |  |  | 72.5496 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/5 | 439
192 |  | 32/6 | DA+9 |  | 2 |  |  | 72.9886 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/6 | 360
193 |  | 32/7 | DA+3 |  |  |  |  | 73.3486 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/7 | 479
194 | AP-32A/0 | 32A/0 | DB1+9 |  |  |  |  | 73.8276 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32A/0 | 402
195 |  | 32A/1 | DA+6 |  |  |  |  | 74.2296 | Approved | Completed | Completed | Completed
[6 empty] | 32A/1 | 438.439
196 | AP-33 | 33/0 | DB1+9 |  | 2 |  |  | 74.668 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 33/0 | 430.56
197 |  | 33/1 | DA+9 |  | 2 |  |  | 75.0986 | Approved | Completed | Completed | Completed
[6 empty] | 33/1 | 406
198 |  | 33/2 | DA+9 |  |  |  |  | 75.5046 | Approved | Completed | Completed | Completed
[6 empty] | 33/2 | 435
199 |  | 33/3 | DA+3 |  |  |  |  | 75.9396 | Approved | Completed | Completed | Completed
[6 empty] | 33/3 | 405
200 |  | 33/4 | DA+3 |  |  |  |  | 76.3446 | Approved | Completed | Completed | Completed
[6 empty] | 33/4 | 420
201 |  | 33/5 | DA+0 |  |  |  |  | 76.7646 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/5 | 405
202 |  | 33/6 | DA+6 |  |  |  |  | 77.1696 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/6 | 415
203 |  | 33/7 | DA+6 |  |  |  |  | 77.5846 | Approved | Completed | Completed | Completed
[6 empty] | 33/7 | 355
204 |  | 33/8 | DA+3 |  |  |  |  | 77.9396 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/8 | 380
205 |  | 33/9 | DA+1.5 |  |  |  |  | 78.3196 | Approved | Completed | Completed | Completed
[6 empty] | 33/9 | 398.203
206 | AP-34 | 34/0 | DB1+6 |  |  |  |  | 78.7178 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 34/0 | 441.798
207 |  | 34/1 | DA+9 |  |  |  |  | 79.1596 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/1 | 395
208 |  | 34/2 | DA+9 |  |  |  |  | 79.5546 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/2 | 375
209 |  | 34/3 | DA+1.5 |  |  |  |  | 79.9296 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/3 | 445
210 |  | 34/4 | DA+6 |  |  |  |  | 80.3746 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/4 | 395
211 |  | 34/5 | DA+9 |  |  |  |  | 80.7696 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/5 | 435
212 |  | 34/6 | DA+3 |  |  |  |  | 81.2046 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/6 | 330
213 |  | 34/7 | DA+0 |  |  |  |  | 81.5346 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/7 | 330
214 |  | 34/8 | DA+0 |  |  |  |  | 81.8646 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/8 | 400
215 |  | 34/9 | DA+1.5 |  |  |  |  | 82.2646 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/9 | 310
216 |  | 34/10 | DA-3 |  |  |  |  | 82.5746 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/10 | 325
217 |  | 34/11 | DA+1.5 |  |  |  |  | 82.8996 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/11 | 365
218 |  | 34/12 | DA+3 |  |  |  |  | 83.2646 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/12 | 351.79
219 | AP-35 | 35/0 | DB2+0 |  |  |  |  | 83.6164 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 35/0 | 393.209
220 |  | 35/1 | DA+6 |  |  |  |  | 84.0096 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/1 | 435
221 |  | 35/2 | DA+6 |  |  |  |  | 84.4446 | Approved | Completed |  | Completed
[6 empty] | 35/2 | 405
222 |  | 35/3 | DA-3 |  |  |  |  | 84.8496 | Approved | Completed | Completed | Completed
[6 empty] | 35/3 | 405
223 |  | 35/4 | DA+9 |  |  |  |  | 85.2546 | Approved | Completed | Completed | Completed
[6 empty] | 35/4 | 435
224 |  | 35/5 | DA+9 |  |  |  |  | 85.6896 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/5 | 345
225 |  | 35/6 | DA+6 |  |  |  |  | 86.0346 | Approved | Completed | Completed | Completed
[6 empty] | 35/6 | 395
226 |  | 35/7 | DA+3 |  |  |  |  | 86.4296 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/7 | 440
227 |  | 35/8 | DA+6 |  |  |  |  | 86.8696 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/8 | 400
228 |  | 35/9 | DA+1.5 |  |  |  |  | 87.2696 | Approved | Completed | Completed | Completed
[6 empty] | 35/9 | 440
229 |  | 35/10 | DA+3 |  |  |  |  | 87.7096 | Approved | Completed | Completed | Completed
[6 empty] | 35/10 | 330
230 |  | 35/11 | DA+3 |  |  |  |  | 88.0396 | Approved | Completed | Completed | Completed
[6 empty] | 35/11 | 493.084
231 | AP-36 | 36/0 | DB2+3 |  |  |  |  | 88.5327 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 36/0 | 454
232 |  | 36A/0 | DB1+9 |  |  |  |  | 88.9867 | Approved | Completed |  | Completed
[6 empty] | 36A/0 | 451
233 |  | 36A/1 | DA+3 |  |  |  |  | 89.4377 | Approved | Completed | Completed | Completed
[6 empty] | 36A/1 | 375.7
234 |  | 36B/0 N | DB2+9 |  |  |  |  | 89.8134 | Approved | Completed | Completed | Completed
[6 empty] | 36B/0 N | 420.81
235 | AP-37 | 36C/0 N | DC2+15 |  |  |  |  | 90.2342 | Approved | Completed | Completed
[6 empty] | 36C/0 N | 469.33
236 |  | 37/0 N | DB2+9 |  |  |  |  | 90.7035 | Approved | Completed | Completed
[6 empty] | 37/0 N | 411.28
237 |  | 37/2 | DA+3 |  |  |  |  | 91.1148 | Approved | Completed | Completed | Completed
[6 empty] | 37/2 | 405
238 |  | 37/3 | DA-1.5 |  |  |  |  | 91.5198 | Approved | Completed | Completed | Completed
[6 empty] | 37/3 | 430
239 |  | 37/4 | DA+9 |  |  |  |  | 91.9498 | Approved | Completed | Completed | Completed
[6 empty] | 37/4 | 410
240 |  | 37/5 | DA+3 |  |  |  |  | 92.3598 | Approved | Completed | Completed | Completed
[6 empty] | 37/5 | 420
241 | AP-37A | 37A/0 | DB1+0 |  |  |  |  | 92.7798 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/0 | 280
242 |  | 37A/1 | DA+3 |  |  |  |  | 93.0598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/1 | 345
243 |  | 37A/2 | DA+1.5 |  |  |  |  | 93.4048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/2 | 330
244 |  | 37A/3 | DA+3 |  |  |  |  | 93.7348 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/3 | 455
245 |  | 37A/4 | DA+9 |  |  |  |  | 94.1898 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 37A/4 | 340
246 |  | 37A/5 | DA+3 |  |  |  |  | 94.5298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/5 | 435
247 |  | 37A/6 | DA+3 |  |  |  |  | 94.9648 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/6 | 398.589
248 | AP-38 | 38/0 | DB1+3 |  |  |  |  | 95.3634 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/0 | 426.411
249 |  | 38/1 | DA+0 |  |  |  |  | 95.7898 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/1 | 390
250 |  | 38/2 | DA+0 |  |  |  |  | 96.1798 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/2 | 335
251 |  | 38/3 | DA+3 |  |  |  |  | 96.5148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/3 | 440
252 |  | 38/4 | DA+1.5 |  |  |  |  | 96.9548 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/4 | 280
253 |  | 38/5 | DA+3 |  |  |  |  | 97.2348 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/5 | 450
254 |  | 38/6 | DA+6 |  |  |  |  | 97.6848 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/6 | 285
255 |  | 38/7 | DA+9 |  |  |  |  | 97.9698 | Approved | Completed | Completed | Completed
[6 empty] | 38/7 | 445
256 |  | 38/8 | DA+1.5 |  |  |  |  | 98.4148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/8 | 360
257 |  | 38/9 | DA+0 |  |  |  |  | 98.7748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/9 | 430
258 |  | 38/10 | DA+3 |  |  |  |  | 99.2048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/10 | 322.266
259 | AP-39 | 39/0 | DB2+0 |  |  |  |  | 99.5271 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 39/0 | 392.73
260 |  | 39/1 | DA-1.5 |  |  |  |  | 99.9198 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/1 | 395
261 |  | 39/2 | DA+3 |  |  |  |  | 100.3148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/2 | 385
262 |  | 39/3 | DA+1.5 |  |  |  |  | 100.6998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/3 | 340
263 |  | 39/4 | DA+3 |  |  |  |  | 101.0398 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/4 | 395
264 |  | 39/5 | DA+1.5 |  |  |  |  | 101.4348 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/5 | 410
265 |  | 39/6 | DA+1.5 |  |  |  |  | 101.8448 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/6 | 415
266 |  | 39/7 | DA+3 |  |  |  |  | 102.2598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/7 | 415
267 |  | 39/8 | DA+1.5 |  |  |  |  | 102.6748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/8 | 350
268 |  | 39/9 | DA+6 |  |  |  |  | 103.0248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/9 | 425
269 |  | 39/10 | DA+3 |  |  |  |  | 103.4498 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/10 | 350
270 |  | 39/11 | DA+6 |  |  |  |  | 103.7998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/11 | 444.081
271 | AP-40 | 40/0 | DB1+6 |  |  |  |  | 104.2439 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 40/0 | 260.918
272 |  | 40/1 | DA+9 |  | 2 |  |  | 104.5048 | Approved | Completed | Completed | Completed
[6 empty] | 40/1 | 385
273 |  | 40/2 | DA+6 |  |  |  |  | 104.8898 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/2 | 435
274 |  | 40/3 | DA+3 |  |  |  |  | 105.3248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/3 | 385
275 |  | 40/4 | DA+6 |  |  |  |  | 105.7098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/4 | 455
276 |  | 40/5 | DA+9 |  |  |  |  | 106.1648 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/5 | 370
277 |  | 40/6 | DA+9 |  |  |  |  | 106.5348 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/6 | 400
278 |  | 40/7 | DA+3 |  |  |  |  | 106.9348 | Approved | Completed | Completed | Completed
[6 empty] | 40/7 | 350
279 |  | 40/8 | DA-1.5 |  |  |  |  | 107.2848 | Approved | Completed | Completed | Completed
[6 empty] | 40/8 | 470
280 |  | 40/9 | DA+9 |  |  |  |  | 107.7548 | Approved | Completed | Completed | Completed
[6 empty] | 40/9 | 355
281 |  | 40/10 | DA+3 |  |  |  |  | 108.1098 | Approved | Completed | Completed | Completed
[6 empty] | 40/10 | 485
282 |  | 40/11 | DA+9 |  |  |  |  | 108.5948 | Approved | Completed | Completed | Completed
[6 empty] | 40/11 | 315
283 | AP-40A | 40A/0 | DB1+9 |  |  |  |  | 108.9098 | Approved | Completed | Completed | Completed
[6 empty] | 40A/0 | 410.61
284 | AP-41 | 41/0 | DB1+9 |  |  |  |  | 109.3204 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 41/0 | 358
285 |  | 41/1 | DA+9 |  |  |  |  | 109.6784 | Approved | Completed | Completed | Completed
[6 empty] | 41/1 | 465.782
286 | AP-42 | 42/0 | DB2+0 |  |  |  |  | 110.1442 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 42/0 | 419.998
287 |  | 42/1 | DA+3 |  |  |  |  | 110.5642 | Approved | Completed | Completed | Completed
[6 empty] | 42/1 | 375
288 |  | 42/2 | DA+9 |  |  |  |  | 110.9392 | Approved | Completed | Completed | Completed
[6 empty] | 42/2 | 464
289 |  | 42A/0 | DB1+9 |  |  |  |  | 111.4032 | Approved | Completed | Completed | Completed
[6 empty] | 42A/0 | 424.891
290 | AP-43 | 43/0 | DB1+0 |  |  |  |  | 111.8281 | Approved | Completed | Completed | Completed
[6 empty] | 43/0 | 341.866
291 |  | 43/1 | DA-1.5 |  |  |  |  | 112.17 | Approved | Completed | Completed | Completed
[6 empty] | 43/1 | 375
292 |  | 43/2 | DA+6 |  |  |  |  | 112.545 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 43/2 | 375
293 |  | 43/3 | DA-1.5 |  |  |  |  | 112.92 | Approved | Completed | Completed | Completed
[6 empty] | 43/3 | 355
294 |  | 43/4 | DA+0 |  |  |  |  | 113.275 | Approved | Completed | Completed | Completed
[6 empty] | 43/4 | 405
295 |  | 43A/0 | DC2+0 |  |  |  |  | 113.68 | Approved | Completed | Completed | Completed |  |  | TP tower modified cross arms
[6 empty] | 43A/0 | 375
296 |  | 43/6 | DA+3 |  |  |  |  | 114.055 | Approved | Completed | Completed | Completed
[6 empty] | 43/6 | 385
297 |  | 43/7 | DA+0 |  |  |  |  | 114.44 | Approved | Completed | Completed | Completed
[6 empty] | 43/7 | 415
298 |  | 43/8 | DA+9 |  |  |  |  | 114.855 | Approved | Completed | Completed | Completed
[6 empty] | 43/8 | 409.546
299 | AP-44 | 44/0 | DB1+6 |  |  |  |  | 115.2645 | Approved | Completed | Completed | Completed
[6 empty] | 44/0 | 400
300 |  | 44/1 | DA+3 |  |  |  |  | 115.6645 | Approved | Completed | Completed | Completed
[6 empty] | 44/1 | 427
301 |  | 44/2 | DA+3 |  |  |  |  | 116.0915 | Approved | Completed | Completed | Completed
[6 empty] | 44/2 | 366
302 |  | 44/3 | DA+3 |  |  |  |  | 116.4575 | Approved | Completed | Completed | Completed
[6 empty] | 44/3 | 350
303 |  | 44/4 | DA+0 |  |  |  |  | 116.8075 | Approved | Completed | Completed | Completed
[6 empty] | 44/4 | 383
304 |  | 44/5 | DA+0 |  |  |  |  | 117.1905 | Approved | Completed | Completed | Completed
[6 empty] | 44/5 | 457.155
305 | AP45 | 45/0 | DB1+9 |  |  |  |  | 117.6477 | Approved | Completed | Completed | Completed |  |  | PLC
[6 empty] | 45/0 | 208.53
306 | AP46 | 46/0 | DB1+12 |  |  |  |  | 117.8562 | Approved | Completed | Completed | Completed |  |  | PLC
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+0 to gantry
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DC2+0 to DD60+0
Note on C46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4-5 TO 4/1
Note on D202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18
Note on C582: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 42/3-42A/0
Note on C594: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 43/5- 43A/0

## Foundation Daily Progress (hidden)
Foundation Daily Progress Register | [5 empty] | A |  |  | B |  |  | C |  |  | D
As on | 24.07.2026 |  |  |  | Sub-Total | 309 | 310 | 313 | 316 | 309 | 312 | 313 | 309 | 313 | 311 | 310 | 314
S.No. | Date | Loc. No. | Type of Tower | Type of Classification | Competed | F | P | C | F | P | C | F | P | C | F | P | C | Slump | Test Cube |  |  | Date of Casting | Due date of Testing | Slump | Frustum | Pyramid | Chimney | Total | Vlook up Data:-
1 | 2024-05-30 | 9/4 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 |  |  | 55 | F(D) | F(A) | F(A) | 2024-05-30 | 2024-06-27 | 55 | 11.054 | 0 | 0 | 11.054 | DA-3 | 4.726 | 2.755 | 1.054
2 | 2024-06-01 | 10/1 | DA+3 | Sandy | Competed | 1 | [5 empty] | 1 | [5 empty] | 55 | Pit-A(F) | Pit-A(F) | Pit-A(F) | 2024-06-01 | 2024-06-29 | 55 | 11.054 | 0 | 0 | 11.054 | DA-1.5 | 4.726 | 2.755 | 1.054
3 | 2024-06-02 | 10/1 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  | 50 | Pit-C(P) | Pit-C(P) | Pit-C(P) | 2024-06-02 | 2024-06-30 | 40 | 11.054 | 5.51 | 2.086 | 18.65 | DA+0 | 4.726 | 2.755 | 1.054
4 | 2024-06-03 | 9/4 | DA+6 | Sandy | Competed |  | 1 |  | 1 | [6 empty] | 1 |  | 52 | F(B) | P(A) | P(D) | 2024-06-03 | 2024-07-01 | 52 | 5.527 | 5.51 | 0 | 11.037 | DA+1.5 | 5.527 | 2.755 | 1.043
5 | 2024-06-04 | 9/4 | DA+6 | Sandy | Competed |  |  | 1 | [8 empty] | 1 | 40 | C(A) | C(D) | C(D) | 2024-06-04 | 2024-07-02 | 40 | 0 | 0 | 2.086 | 2.086 | DA+3 | 5.527 | 2.755 | 1.043
6 | 2024-06-05 | 9/4 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  | 40 | F(C ) | P(C ) | P(B ) | 2024-06-05 | 2024-07-03 | 40 | 5.527 | 5.51 | 2.086 | 13.123 | DA+6 | 5.527 | 2.755 | 1.043
7 | 2024-06-07 | 10/1 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 55 | C(D) | C(D) | C(D) | 2024-06-07 | 2024-07-05 | 55 | 0 | 5.51 | 2.086 | 7.596 | DA+9 | 5.527 | 2.755 | 1.043
8 | 2024-06-08 | 10/2 | DA+3 | Sandy | Competed | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  |  | 55 | Pit-B(C) | Pit-B(C) | Pit-B(C) | 2024-06-08 | 2024-07-06 | 55 | 22.108 | 5.51 | 2.086 | 29.704 | DB1+0
9 | 2024-06-09 | 10/2 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 50 | Pit-C(P) | Pit-C(P) | Pit-C(P) | 2024-06-09 | 2024-07-07 | 50 | 0 | 5.51 | 2.086 | 7.596 | DB1+3
10 | 2024-06-10 | 9/11 | DA+3 | Sandy | Competed | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 58 | B(C ) | A(C ) | A(F) | 2024-06-10 | 2024-07-08 | 58 | 11.054 | 5.51 | 2.086 | 18.65 | DB1+6
11 | 2024-06-11 | 9/11 | DA+3 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 40 | Pit-D(C) | Pit-D(C) | Pit-D(C) | 2024-06-11 | 2024-07-09 | 40 | 11.054 | 5.51 | 2.086 | 18.65 | DB1+9
12 | 2024-06-12 | 9/5 | DA+3 | Sandy | Competed | [9 empty] | 1 |  |  | 44 | F(D) | F(D) | F(D) | 2024-06-12 | 2024-07-10 | 44 | 5.527 | 0 | 0 | 5.527 | DB1+12
13 | 2024-06-13 | 9/5 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 |  | 40 | F(C ) | F(C ) | F(C ) | 2024-06-13 | 2024-07-11 | 40 | 5.527 | 2.755 | 0 | 8.282 | DB2+0
14 | 2024-06-13 | 15/2 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 |  |  | 40 | C(F) | D(F) | D(F) | 2024-06-13 | 2024-07-11 | 40 | 11.054 | 0 | 0 | 11.054 | DB2+3
15 | 2024-06-14 | 9/5 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 | 50 | C(D) | P(C ) | P(C ) | 2024-06-14 | 2024-07-12 | 50 | 0 | 2.755 | 2.086 | 4.841 | DB2+6
16 | 2024-06-14 | 15/2 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 35 | A(F) | A(F) | A(F) | 2024-06-14 | 2024-07-12 | 35 | 11.054 | 0 | 0 | 11.054 | DB2+9
17 | 2024-06-15 | 9/5 | DA+3 | Sandy | Competed | 1 | [11 empty] | 40 | F(A) | F(A) | F(A) | 2024-06-15 | 2024-07-13 | 40 | 5.527 | 0 | 0 | 5.527 | DC1+0
18 | 2024-06-15 | 15/2 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [6 empty] | 40 | A(C ) | B(C ) | B(C ) | 2024-06-15 | 2024-07-13 | 40 | 0 | 5.51 | 2.086 | 7.596 | DC1+3
19 | 2024-06-16 | 9/5 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 | 1 | [7 empty] | 50 | F(B) | F(B) | F(B) | 2024-06-16 | 2024-07-14 | 50 | 5.527 | 5.51 | 1.043 | 12.08 | DC1+6
20 | 2024-06-16 | 15/3 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 50 | Pit-A(F) | Pit-A(F) | Pit-A(F) | 2024-06-16 | 2024-07-14 | 50 | 22.108 | 0 | 0 | 22.108 | DC1+9
21 | 2024-06-17 | 9/5 | DA+3 | Sandy | Competed | [5 empty] | 1 | [6 empty] | 40 | C(B) | C(B) | C(B) | 2024-06-17 | 2024-07-15 | 40 | 0 | 0 | 1.043 | 1.043 | DC2+0
22 | 2024-06-17 | 15/2 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 | 52 | C(P) | D(C ) | D(C ) | 2024-06-17 | 2024-07-15 | 42 | 0 | 5.51 | 2.086 | 7.596 | DC2+3
23 | 2024-06-17 | 15/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [6 empty] | 60 | Pit-A(C) | Pit-A(C) | Pit-A(C) | 2024-06-17 | 2024-07-15 | 40 | 0 | 5.51 | 2.086 | 7.596 | DC2+6
24 | 2024-06-17 | 8/5 | DA+9 | Sandy | Competed |  |  |  | 1 | [8 empty] | 68 | Pit-B(FS) | Pit-B(FS) | Pit-B(FS) | 2024-06-17 | 2024-07-15 | 68 | 5.527 | 0 | 0 | 5.527 | DC2+9
25 | 2024-06-18 | 15/3 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 | 55 | Pit-C(P) | Pit-D(P) | Pit-D(P) | 2024-06-18 | 2024-07-16 | 45 | 0 | 5.51 | 2.086 | 7.596 | DC2+15
26 | 2024-06-18 | 8/5 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 |  |  | 58 | Pit-C,D(FS) | Pit-C,D(FS) | Pit-C,D(FS) | 2024-06-18 | 2024-07-16 | 58 | 11.054 | 0 | 0 | 11.054 | DD45-3
27 | 2024-06-19 | 9/3 | DA+0 | Sandy | Competed | [6 empty] | 1 | [5 empty] | 60 | F(C) | F(C) | F(C) | 2024-06-19 | 2024-07-17 | 60 | 4.726 | 0 | 0 | 4.726 | DD45+0
28 | 2024-06-19 | 15/4 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 |  |  | 50 | Pit-A(F) | Pit-A(F) | Pit-A(F) | 2024-06-19 | 2024-07-17 | 50 | 11.054 | 0 | 0 | 11.054 | DD45+3
29 | 2024-06-20 | 9/3 | DA+0 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 50 | F(B) | F(B) | P(C ) | 2024-06-20 | 2024-07-18 | 50 | 4.726 | 2.755 | 1.054 | 8.535 | DD45+6
30 | 2024-06-20 | 15/4 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 50 | Pit-B(F) | Pit-A(P) | Pit-D(C) | 2024-06-20 | 2024-07-18 | 50 | 11.054 | 5.51 | 2.086 | 18.65 | DD45+9
31 | 2024-06-21 | 9/3 | DA+0 | Sandy | Competed | 1 |  |  |  | 1 | 1 | [6 empty] | 50 | P(B) | P(B) | P(B) | 2024-06-21 | 2024-07-19 | 50 | 4.726 | 2.755 | 1.054 | 8.535 | DD60+0
32 | 2024-06-21 | 15/4 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  | 55 | Pit-B(P) | Pit-C(C) | Pit-B(C) | 2024-06-21 | 2024-07-19 | 45 | 0 | 5.51 | 2.086 | 7.596 | DD60+3
33 | 2024-06-22 | 15/5 | DA+3 | Sandy | Competed | 1 |  |  | 1 | 1 | [7 empty] | 40 | Pit-A(F) | Pit-B(F) | Pit-B(F) | 2024-06-22 | 2024-07-20 | 40 | 11.054 | 2.755 | 0 | 13.809 | DD60+6
34 | 2024-06-22 | 9/3 | DA+0 | Sandy | Competed |  | 1 | [7 empty] | 1 |  |  | 45 | F(D) | F(D) | P(A) | 2024-06-22 | 2024-07-20 | 45 | 4.726 | 2.755 | 0 | 7.481 | DD60+9
35 | 2024-06-23 | 15/5 | DA+3 | Sandy | Competed | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 58 | Pit-B(C) | Pit-A(C) | Pit-A(C) | 2024-06-23 | 2024-07-21 | 38 | 11.054 | 5.51 | 3.129 | 19.693 | DD60+18
36 | 2024-06-23 | 9/3 | DA+0 | Sandy | Competed |  |  | 1 | [7 empty] | 1 | 1 | 50 | P(D) | P(D) | C(A) | 2024-06-23 | 2024-07-21 | 50 | 0 | 2.755 | 2.108 | 4.863 | DD60+25
37 | 2024-06-23 | 8/5 | DA+9 | Sandy | Competed | [7 empty] | 1 |  |  | 1 |  | 68 | Pit-C,D(P) | Pit-C,D(P) | Pit-C,D(P) | 2024-06-23 | 2024-07-21 | 68 | 0 | 5.51 | 0 | 5.51 | DD60+35
38 | 2024-06-24 | 8/5 | DA+9 | Sandy | Competed | 1 | [7 empty] | 1 |  |  | 1 | 50 | A-FS,D,C-CH | A-FS,D,C-CH | A-FS,D,C-CH | 2024-06-24 | 2024-07-22 | 50 | 5.527 | 0 | 2.086 | 7.613
39 | 2024-06-24 | 15/5 | DA+3 | Sandy | Competed |  | 1 | 1 | [9 empty] | 50 | Pit-D(F) | Pit-D(P) | Pit-D(C) | 2024-06-24 | 2024-07-22 | 50 | 0 | 2.755 | 1.043 | 3.798
40 | 2024-06-25 | 8/5 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [6 empty] | 50 | Pit-A(P) | Pit-B(P) | Pit-B(C) | 2024-06-25 | 2024-07-23 | 50 | 0 | 5.51 | 2.086 | 7.596
41 | 2024-06-25 | 9/10 | DA+3 | Sandy | Competed |  |  |  | 1 | [8 empty] | 65 | Pit-B(F) | Pit-B(F) | Pit-B(F) | 2024-06-25 | 2024-07-23 | 65 | 5.527 | 0 | 0 | 5.527
42 | 2024-06-25 | 28/0 | DC2-3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-06-25 | 2024-07-23
43 | 2024-06-26 | 15/6 | DA+9 | Sandy | Competed | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | 1 |  | 55 | Pit-A(F) | Pit-B(F) | Pit-C(F) | 2024-06-26 | 2024-07-24 | 55 | 22.108 | 5.51 | 0 | 27.618
44 | 2024-06-26 | 9/10 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 55 | Pit-D(F) | Pit-B(P) | Pit-B(C) | 2024-06-26 | 2024-07-24 | 55 | 5.527 | 5.51 | 2.086 | 13.123
45 | 2024-06-26 | 9/2 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 58 | F(A) | F(A) | F(A) | 2024-06-26 | 2024-07-24 | 58 | 11.054 | 0 | 0 | 11.054
46 | 2024-06-27 | 15/6 | DA+9 | Sandy | Competed |  | 1 | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 | 50 | Pit-A(P) | Pit-C(C) | Pit-D(C) | 2024-06-27 | 2024-07-25 | 50 | 0 | 5.51 | 4.172 | 9.682
47 | 2024-06-27 | 9/10 | DA+3 | Sandy | Competed | 1 | [5 empty] | 1 | [5 empty] | 65 | Pit A-F | Pit A-F | Pit C-F | 2024-06-27 | 2024-07-25 | 65 | 11.054 | 0 | 0 | 11.054
48 | 2024-06-27 | 9/2 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [5 empty] | 50 | P(B) | P(B) | P(A) | 2024-06-27 | 2024-07-25 | 50 | 5.527 | 5.51 | 2.086 | 13.123
49 | 2024-06-28 | 9/2 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  |  |  | 48 | C(C ) | P(C ) | P(C ) | 2024-06-28 | 2024-07-26 | 48 | 0 | 2.755 | 1.043 | 3.798
50 | 2024-06-28 | 15/7 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 |  |  | 40 | A(F) | A(F) | D(F) | 2024-06-28 | 2024-07-26 | 40 | 9.452 | 0 | 0 | 9.452
51 | 2024-06-28 | 9/10 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 45 | Pit-A(P) | Pit-C(P) | Pit-C(P) | 2024-06-28 | 2024-07-26 | 45 | 0 | 5.51 | 2.086 | 7.596
52 | 2024-06-29 | 15/7 | DA+0 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 50 | A(P) | B(F) | C(F) | 2024-06-29 | 2024-07-27 | 50 | 9.452 | 5.51 | 2.108 | 17.07
53 | 2024-06-29 | 8/6 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 |  |  | 50 | C(F) | C(F) | D(F) | 2024-06-29 | 2024-07-27 | 50 | 11.054 | 0 | 0 | 11.054
54 | 2024-06-29 | 9/2 | DA+3 | Sandy | Competed | [9 empty] | 1 | 1 | 1 | 65 | F(D) | F(D) | F(D) | 2024-06-29 | 2024-07-27 | 65 | 5.527 | 2.755 | 1.043 | 9.325
55 | 2024-06-30 | 8/6 | DA+3 | Sandy | Competed | 1 | [6 empty] | 1 |  |  | 1 |  | 50 | A(F) | C(P) | D(P) | 2024-06-30 | 2024-07-28 | 50 | 5.527 | 5.51 | 0 | 11.037
56 | 2024-07-01 | 15/9 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 |  |  | 45 | A(F) | D(F) | D(F) | 2024-07-01 | 2024-07-29 | 45 | 9.452 | 0 | 0 | 9.452
57 | 2024-07-01 | 8/6 | DA+3 | Sandy | Competed | [8 empty] | 1 |  |  | 1 | 50 | C(C ) | C(C ) | D(C ) | 2024-07-01 | 2024-07-29 | 50 | 0 | 0 | 2.086 | 2.086
58 | 2024-07-02 | 15/9 | DA+0 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 | 40 | B(F) | C(F) | A(C) | 2024-07-02 | 2024-07-30 | 40 | 9.452 | 5.51 | 2.108 | 17.07
59 | 2024-07-02 | 9/1 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 |  |  | 50 | D(F) | D(F) | C(F) | 2024-07-02 | 2024-07-30 | 50 | 11.054 | 0 | 0 | 11.054
60 | 2024-07-03 | 8/6 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 46 | B(C) | A(P) | B(P) | 2024-07-03 | 2024-07-31 | 46 | 5.527 | 5.51 | 2.086 | 13.123
61 | 2024-07-03 | 9/1 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 | 45 | D(P) | C(P) | C(P) | 2024-07-03 | 2024-07-31 | 45 | 0 | 5.51 | 2.086 | 7.596
62 | 2024-07-03 | 15/9 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  | 50 | B(P) | C(P) | C(C) | 2024-07-03 | 2024-07-31 | 50 | 0 | 5.51 | 2.108 | 7.618
63 | 2024-07-05 | 15/8 | DA+1.5 | Sandy | Competed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 50 | A(F) | B(F) | C(F) | 2024-07-05 | 2024-08-02 | 50 | 16.581 | 5.51 | 2.086 | 24.177
64 | 2024-07-05 | 31/9 | DA+1.5 | Sandy | Competed | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 40 | F(A) | F(D) | F(C) | 2024-07-05 | 2024-08-02 | 40 | 22.108 | 11.02 | 0 | 33.128
65 | 2024-07-06 | 8/7 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 48 | Pit-A,B-FS | Pit-A,B-FS | F(C) | 2024-07-06 | 2024-08-03 | 48 | 11.054 | 0 | 0 | 11.054
66 | 2024-07-06 | 15/8 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | 1 | 1 | 45 | D(F) | D(C ) | C(C) | 2024-07-06 | 2024-08-03 | 45 | 5.527 | 5.51 | 2.086 | 13.123
67 | 2024-07-06 | 31/9 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 55 | C(A) | C(B) | C(C) | 2024-07-06 | 2024-08-03 | 55 | 0 | 0 | 4.172 | 4.172
68 | 2024-07-07 | 8/7 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  |  |  | 1 |  |  | 48 | A,B-CH | A,B-P | D-FS | 2024-07-07 | 2024-08-04 | 48 | 5.527 | 5.51 | 2.086 | 13.123
69 | 2024-07-07 | 31/8 | DA+0 | Sandy | Competed | [9 empty] | 1 |  |  | 50 | D(F) | D(F) | D(F) | 2024-07-07 | 2024-08-04 | 50 | 4.726 | 0 | 0 | 4.726
70 | 2024-07-08 | 8/7 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 |  | 40 | D(P) | C(F) | C(F) | 2024-07-08 | 2024-08-05 | 40 | 5.527 | 2.755 | 0 | 8.282
71 | 2024-07-08 | 9/1 | DA+3 | Sandy | Competed | 1 | [11 empty] | 55 | A(F) | A(F) | A(F) | 2024-07-08 | 2024-08-05 | 55 | 5.527 | 0 | 0 | 5.527
72 | 2024-07-08 | 15/10 | DA-1.5 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 55 | A(F) | B(F) | B(F) | 2024-07-08 | 2024-08-05 | 55 | 18.904 | 0 | 0 | 18.904
73 | 2024-07-08 | 31/8 | DA+0 | Sandy | Competed | 1 | [5 empty] | 1 | [5 empty] | 65 | A(F) | A(F) | C(F) | 2024-07-08 | 2024-08-05 | 65 | 9.452 | 0 | 0 | 9.452
74 | 2024-07-09 | 8/7 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 | 57 | D(C) | C(P) | C(C) | 2024-07-09 | 2024-08-06 | 57 | 0 | 2.755 | 2.086 | 4.841
75 | 2024-07-09 | 9/1 | DA+3 | Sandy | Competed |  | 1 | [10 empty] | 40 | A(P) | A(P) | A(P) | 2024-07-09 | 2024-08-06 | 40 | 0 | 2.755 | 0 | 2.755
76 | 2024-07-09 | 15/10 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [6 empty] | 60 | A(P) | B(P) | B(C ) | 2024-07-09 | 2024-08-06 | 60 | 0 | 5.51 | 2.108 | 7.618
77 | 2024-07-09 | 31/8 | DA+0 | Sandy | Competed |  | 1 |  | 1 |  |  |  | 1 |  |  | 1 |  | 55 | B(F) | C(P) | A(P) | 2024-07-09 | 2024-08-06 | 55 | 4.726 | 8.265 | 0 | 12.991
78 | 2024-07-10 | 9/1 | DA+3 | Sandy | Competed |  |  | 1 | 1 | 1 | 1 | [6 empty] | 40 | B(F) | B(F) | B(F) | 2024-07-10 | 2024-08-07 | 40 | 5.527 | 2.755 | 2.086 | 10.368
79 | 2024-07-10 | 15/10 | DA-1.5 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 | 50 | C(P) | C(C ) | D(C ) | 2024-07-10 | 2024-08-07 | 40 | 0 | 5.51 | 2.108 | 7.618
80 | 2024-07-10 | 31/8 | DA+0 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  |  | 1 |  |  | 1 | 55 | B(P) | A(C ) | D(C ) | 2024-07-10 | 2024-08-07 | 55 | 0 | 2.755 | 4.216 | 6.971
81 | 2024-07-11 | 15/7 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  | 55 | B(P) | B(C ) | C(C ) | 2024-07-11 | 2024-08-08 | 55 | 0 | 5.51 | 2.108 | 7.618
82 | 2024-07-12 | 31/7 | DA+0 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 60 | B(F) | B(F) | A(F) | 2024-07-12 | 2024-08-09 |  | 9.452 | 0 | 0 | 9.452
83 | 2024-07-13 | 31/7 | DA+0 | Sandy | Competed |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 60 | B(P) | D(F) | D(F) | 2024-07-13 | 2024-08-10 |  | 4.726 | 5.51 | 0 | 10.236
84 | 2024-07-14 | 8/8 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 50 | A-FS | A-FS | B-FS | 2024-07-14 | 2024-08-11 |  | 11.054 | 0 | 0 | 11.054
85 | 2024-07-14 | 31/7 | DA+0 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 |  | 60 | D(P) | D(P) | C(F) | 2024-07-14 | 2024-08-11 |  | 4.726 | 2.755 | 0 | 7.481
86 | 2024-07-15 | 8/8 | DA+9 | Sandy | Competed |  |  |  |  | 1 | [7 empty] | 60 | B-P | B-P | P-B | 2024-07-15 | 2024-08-12 |  | 0 | 2.755 | 0 | 2.755
87 | 2024-07-15 | 15/11 | DA+0 | Sandy | Competed | 1 |  |  | 1 | [8 empty] | 60 | A(F) | A(F) | B(F) | 2024-07-15 | 2024-08-12 |  | 9.452 | 0 | 0 | 9.452
88 | 2024-07-15 | 31/7 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 | 55 | B(C) | A(C) | C(P) | 2024-07-15 | 2024-08-12 |  | 0 | 2.755 | 4.216 | 6.971
89 | 2024-07-16 | 8/8 | DA+9 | Sandy | Competed |  | 1 | 1 |  |  | 1 | 1 | [5 empty] | 60 | C-FS | A-P | A-B-CH | 2024-07-16 | 2024-08-13 |  | 5.527 | 2.755 | 2.086 | 10.368
90 | 2024-07-16 | 15/11 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [6 empty] | 58 | A(P) | B(C) | A(C) | 2024-07-16 | 2024-08-13 |  | 0 | 5.51 | 2.108 | 7.618
91 | 2024-07-17 | 8/1 | DA-3 | Sandy | Competed | 1 | [8 empty] | 1 |  |  | 50 | D-F | D-F | A-F | 2024-07-17 | 2024-08-14 |  | 9.452 | 0 | 0 | 9.452
92 | 2024-07-17 | 8/8 | DA+9 | Sandy | Competed | [9 empty] | 1 |  |  | 57 | D-FS | D-FS | D-FS | 2024-07-17 | 2024-08-14 |  | 5.527 | 0 | 0 | 5.527
93 | 2024-07-17 | 15/11 | DA+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 |  |  | 57 | C(F) | D(F) | D(F) | 2024-07-17 | 2024-08-14 |  | 9.452 | 0 | 0 | 9.452
94 | 2024-07-18 | 8/1 | DA-3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-07-18 | 2024-08-15 |  | 0 | 5.51 | 2.108 | 7.618
95 | 2024-07-18 | 15/11 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 | 55 | D(C) | C(C) | C(C) | 2024-07-18 | 2024-08-15 |  | 0 | 5.51 | 2.108 | 7.618
96 | 2024-07-19 | 8/1 | DA-3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-07-19 | 2024-08-16 |  | 9.452 | 0 | 0 | 9.452
97 | 2024-07-19 | 8/8 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-07-19 | 2024-08-16 |  | 0 | 5.51 | 2.086 | 7.596
98 | 2024-07-19 | 31/6 | DA+9 | Sandy | WIP | 1 | 1 | [7 empty] | 1 | 1 | [5 empty] | 2024-07-19 | 2024-08-16 |  | 11.054 | 5.51 | 0 | 16.564
99 | 2024-07-20 | 8/1 | DA-3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-07-20 | 2024-08-17 |  | 0 | 5.51 | 2.108 | 7.618
100 | 2024-07-21 | 31/6 | DA+9 | Sandy | WIP | [16 empty] | 2024-07-21 | 2024-08-18 |  | 0 | 0 | 0 | 0
101 | 2024-07-21 | 8/2 | DA+6 | Sandy | Competed | [9 empty] | 1 | 1 | [5 empty] | 2024-07-21 | 2024-08-18
102 | 2024-07-21 | 8/9 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-07-21 | 2024-08-18
103 | 2024-07-21 | 29/4 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-07-21 | 2024-08-18
104 | 2024-07-21 | 31/6 | DA+9 | Sandy | WIP |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  |  | 2024-07-21 | 2024-08-18
105 | 2024-07-22 | 29/4 | DA+3 | Sandy | Competed | 1 | [6 empty] | 1 |  |  | 1 | [5 empty] | 2024-07-22 | 2024-08-19
106 | 2024-07-22 | 31/6 | DA+9 | Sandy | Competed |  |  |  | 1 | 1 | 1 |  |  | 1 | [7 empty] | 2024-07-22 | 2024-08-19
107 | 2024-07-23 | 8/2 | DA+6 | Sandy | Competed | 1 | [5 empty] | 1 | 1 |  |  |  | 1 |  |  |  |  | 2024-07-23 | 2024-08-20
108 | 2024-07-23 | 8/9 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 | [6 empty] | 1 | 1 |  |  |  |  | 2024-07-23 | 2024-08-20
109 | 2024-07-23 | 29/4 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 2024-07-23 | 2024-08-20
110 | 2024-07-24 | 8/2 | DA+6 | Sandy | Competed |  | 1 | 1 | [5 empty] | 1 | [7 empty] | 2024-07-24 | 2024-08-21
111 | 2024-07-24 | 8/9 | DA+3 | Sandy | Competed |  |  |  |  | 1 |  | 1 | [9 empty] | 2024-07-24 | 2024-08-21
112 | 2024-07-24 | 29/4 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-07-24 | 2024-08-21
113 | 2024-07-24 | 31/10 | DA+4.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-07-24 | 2024-08-21
114 | 2024-07-25 | 8/2 | DA+6 | Sandy | Competed |  |  |  | 1 | 1 | 1 | [10 empty] | 2024-07-25 | 2024-08-22
115 | 2024-07-25 | 8/9 | DA+3 | Sandy | Competed | [5 empty] | 1 |  | 1 | 1 | [7 empty] | 2024-07-25 | 2024-08-22
116 | 2024-07-25 | 31/10 | DA+4.5 | Sandy | Competed | 1 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2024-07-25 | 2024-08-22
117 | 2024-07-26 | 29/3 | DA+0 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-07-26 | 2024-08-23
118 | 2024-07-26 | 31/10 | DA+4.5 | Sandy | Competed |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-07-26 | 2024-08-23
119 | 2024-07-27 | 29/3 | DA+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-07-27 | 2024-08-24
120 | 2024-07-27 | 30/1 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-07-27 | 2024-08-24
121 | 2024-07-27 | 31/10 | DA+4.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-07-27 | 2024-08-24
122 | 2024-07-28 | 29/3 | DA+0 | Sandy | Competed |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [5 empty] | 2024-07-28 | 2024-08-25
123 | 2024-07-28 | 30/1 | DA+0 | Sandy | Competed |  | 1 | [8 empty] | 1 | [5 empty] | 2024-07-28 | 2024-08-25
124 | 2024-07-28 | 31/10 | DA+4.5 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-07-28 | 2024-08-25
125 | 2024-07-29 | 29/3 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-07-29 | 2024-08-26
126 | 2024-07-29 | 30/1 | DA+0 | Sandy | Competed |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2024-07-29 | 2024-08-26
127 | 2024-07-29 | 31/3 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-07-29 | 2024-08-26
128 | 2024-07-30 | 31/3 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-07-30 | 2024-08-27
129 | 2024-07-30 | 30/1 | DA+0 | Sandy | Competed |  |  |  |  | 1 |  |  | 1 | 1 | [7 empty] | 2024-07-30 | 2024-08-27
130 | 2024-07-31 | 31/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-07-31 | 2024-08-28
131 | 2024-07-31 | 29/5 | DA+0 | Sandy | Competed | 1 | [15 empty] | 2024-07-31 | 2024-08-28
132 | 2024-08-01 | 30/1 | DA+0 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2024-08-01 | 2024-08-29
133 | 2024-08-01 | 29/5 | DA+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-08-01 | 2024-08-29
134 | 2024-08-02 | 31/1 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-08-02 | 2024-08-30
135 | 2024-08-02 | 7/1 | DA-3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-08-02 | 2024-08-30
136 | 2024-08-02 | 29/5 | DA+0 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-02 | 2024-08-30
137 | 2024-08-03 | 31/1 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-03 | 2024-08-31
138 | 2024-08-03 | 29/5 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-08-03 | 2024-08-31
139 | 2024-08-03 | 7/1 | DA-3 | Sandy | Competed | 1 | [15 empty] | 2024-08-03 | 2024-08-31
140 | 2024-08-03 | 5/3 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-03 | 2024-08-31
141 | 2024-08-04 | 5/3 | DA+9 | Sandy | Competed |  | 1 | [7 empty] | 1 | [6 empty] | 2024-08-04 | 2024-09-01
142 | 2024-08-05 | 5/3 | DA+9 | Sandy | Competed |  |  | 1 |  | 1 |  | 1 | [9 empty] | 2024-08-05 | 2024-09-02
143 | 2024-08-05 | 29A/2 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2024-08-05 | 2024-09-02
144 | 2024-08-06 | 5/3 | DA+9 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-08-06 | 2024-09-03
145 | 2024-08-06 | 29A/2 | DA+6 | Sandy | Competed |  | 1 | 1 | [6 empty] | 1 | [6 empty] | 2024-08-06 | 2024-09-03
146 | 2024-08-06 | 29A/6 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-06 | 2024-09-03
147 | 2024-08-06 | 7/1 | DA-3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-08-06 | 2024-09-03
148 | 2024-08-07 | 5/3 | DA+9 | Sandy | Competed | [7 empty] | 1 | [8 empty] | 2024-08-07 | 2024-09-04
149 | 2024-08-07 | 29A/2 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-08-07 | 2024-09-04
150 | 2024-08-07 | 29A/6 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-08-07 | 2024-09-04
151 | 2024-08-07 | 7/1 | DA-3 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | [8 empty] | 2024-08-07 | 2024-09-04
152 | 2024-08-08 | 5/3 | DA+9 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2024-08-08 | 2024-09-05
153 | 2024-08-08 | 29A/2 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-08-08 | 2024-09-05
154 | 2024-08-09 | 7/1 | DA-3 | Sandy | Competed |  |  |  |  | 1 |  |  |  | 1 | 1 | [6 empty] | 2024-08-09 | 2024-09-06
155 | 2024-08-09 | 8/10 | DA+0 | Sandy | Competed | 1 | [15 empty] | 2024-08-09 | 2024-09-06
156 | 2024-08-10 | 5/4 | DA-1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-10 | 2024-09-07
157 | 2024-08-10 | 7/1 | DA-3 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-08-10 | 2024-09-07
158 | 2024-08-10 | 8/10 | DA+0 | Sandy | Competed |  | 1 |  |  |  |  | 1 | [9 empty] | 2024-08-10 | 2024-09-07
159 | 2024-08-11 | 8/10 | DA+0 | Sandy | Competed |  |  | 1 | 1 |  |  |  | 1 |  | 1 | [6 empty] | 2024-08-11 | 2024-09-08
160 | 2024-08-11 | 27/4 | DA+1.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-08-11 | 2024-09-08
161 | 2024-08-11 | 29A/1 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-08-11 | 2024-09-08
162 | 2024-08-12 | 5/4 | DA-1.5 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2024-08-12 | 2024-09-09
163 | 2024-08-12 | 8/10 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-08-12 | 2024-09-09
164 | 2024-08-12 | 27/4 | DA+1.5 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 2024-08-12 | 2024-09-09
165 | 2024-08-12 | 29A/1 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-12 | 2024-09-09
166 | 2024-08-13 | 5/8 | DA+6 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-13 | 2024-09-10
167 | 2024-08-13 | 8/10 | DA+0 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2024-08-13 | 2024-09-10
168 | 2024-08-13 | 27/4 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-08-13 | 2024-09-10
169 | 2024-08-13 | 29A/1 | DA+6 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2024-08-13 | 2024-09-10
170 | 2024-08-14 | 29A/1 | DA+6 | Sandy | Competed |  | 1 | 1 |  |  | 1 | [10 empty] | 2024-08-14 | 2024-09-11
171 | 2024-08-14 | 5/8 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-08-14 | 2024-09-11
172 | 2024-08-14 | 27/4 | DA+1.5 | Sandy | Competed | 1 | [15 empty] | 2024-08-14 | 2024-09-11
173 | 2024-08-16 | 5/4 | DA-1.5 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  |  | 1 | [6 empty] | 2024-08-16 | 2024-09-13
174 | 2024-08-16 | 7A/5 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | 1 | [5 empty] | 2024-08-16 | 2024-09-13
175 | 2024-08-16 | 29A/3 | DA+6 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-16 | 2024-09-13
176 | 2024-08-16 | 27/4 | DA+1.5 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-08-16 | 2024-09-13
177 | 2024-08-17 | 5/8 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-08-17 | 2024-09-14
178 | 2024-08-17 | 7A/5 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-08-17 | 2024-09-14
179 | 2024-08-17 | 29A/3 | DA+6 | Sandy | Competed |  | 1 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2024-08-17 | 2024-09-14
180 | 2024-08-18 | 5/8 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-18 | 2024-09-15
181 | 2024-08-18 | 29A/3 | DA+6 | Sandy | Competed |  |  | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 2024-08-18 | 2024-09-15
182 | 2024-08-18 | 27/5 | DA-1.5 | Sandy | Competed | 1 | [15 empty] | 2024-08-18 | 2024-09-15
183 | 2024-08-18 | 32/3 | DA+6 | Sandy | Competed | 1 | 1 |  |  |  |  | 1 |  |  | 1 | [6 empty] | 2024-08-18 | 2024-09-15
184 | 2024-08-19 | 32/3 | DA+6 | Sandy | Competed |  |  | 1 | 1 | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-19 | 2024-09-16
185 | 2024-08-20 | 29A/3 | DA+6 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2024-08-20 | 2024-09-17
186 | 2024-08-20 | 32/3 | DA+6 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2024-08-20 | 2024-09-17
187 | 2024-08-20 | 29A/4 | DA+3 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-08-20 | 2024-09-17
188 | 2024-08-22 | 7A/4 | DA+3 | Sandy | Competed | 1 | 1 |  | 1 | 1 |  | 1 |  |  | 1 | [6 empty] | 2024-08-22 | 2024-09-19
189 | 2024-08-22 | 27/5 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-08-22 | 2024-09-19
190 | 2024-08-22 | 29A/4 | DA+3 | Sandy | Competed |  |  |  |  | 1 |  | 1 |  |  |  | 1 | [5 empty] | 2024-08-22 | 2024-09-19
191 | 2024-08-22 | 32/4 | DA+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-08-22 | 2024-09-19
192 | 2024-08-23 | 7A/4 | DA+3 | Sandy | Competed |  |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-23 | 2024-09-20
193 | 2024-08-23 | 27/5 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-08-23 | 2024-09-20
194 | 2024-08-23 | 29A/4 | DA+3 | Sandy | Competed | 1 |  |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  |  | 2024-08-23 | 2024-09-20
195 | 2024-08-23 | 32/4 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2024-08-23 | 2024-09-20
196 | 2024-08-24 | 29A/4 | DA+3 | Sandy | Competed |  | 1 | 1 | [5 empty] | 1 | [7 empty] | 2024-08-24 | 2024-09-21
197 | 2024-08-24 | 32/4 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2024-08-24 | 2024-09-21
198 | 2024-08-25 | 5/4 | DA-1.5 | Sandy | Competed | [6 empty] | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-25 | 2024-09-22
199 | 2024-08-25 | 6/2 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-08-25 | 2024-09-22
200 | 2024-08-25 | 27/5 | DA-1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-08-25 | 2024-09-22
201 | 2024-08-25 | 29A/5 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-08-25 | 2024-09-22
202 | 2024-08-25 | 32/4 | DA+9 | Sandy | Competed |  | 1 |  | 1 |  |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-08-25 | 2024-09-22
203 | 2024-08-26 | 6/2 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-26 | 2024-09-23
204 | 2024-08-26 | 27/5 | DA-1.5 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-08-26 | 2024-09-23
205 | 2024-08-26 | 29A/5 | DA+6 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-08-26 | 2024-09-23
206 | 2024-08-26 | 32/4 | DA+9 | Sandy | Competed |  |  | 1 |  | 1 | 1 | [10 empty] | 2024-08-26 | 2024-09-23
207 | 2024-08-27 | 29A/5 | DA+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-08-27 | 2024-09-24
208 | 2024-08-27 | 27/5 | DA-1.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-08-27 | 2024-09-24
209 | 2024-08-28 | 27/5 | DA-1.5 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-08-28 | 2024-09-25
210 | 2024-08-28 | 6/1 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-08-28 | 2024-09-25
211 | 2024-08-28 | 33/6 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-08-28 | 2024-09-25
212 | 2024-08-29 | 6/1 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-29 | 2024-09-26
213 | 2024-08-29 | 33/6 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-08-29 | 2024-09-26
214 | 2024-08-30 | 6/1 | DA+9 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2024-08-30 | 2024-09-27
215 | 2024-08-30 | 29A/6 | DA+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-08-30 | 2024-09-27
216 | 2024-08-30 | 33/6 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-08-30 | 2024-09-27
217 | 2024-08-30 | 7A/1 | DA+1.5 | Sandy | Competed |  |  |  | 1 | 1 |  | 1 |  |  | 1 | [6 empty] | 2024-08-30 | 2024-09-27
218 | 2024-08-30 | 4A/5 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-08-30 | 2024-09-27
219 | 2024-08-30 | 6/12 | DA+1.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-08-30 | 2024-09-27
220 | 2024-08-31 | 29A/6 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-08-31 | 2024-09-28
221 | 2024-08-31 | 7A/1 | DA+1.5 | Sandy | Competed | 1 |  |  |  |  | 1 |  | 1 | [8 empty] | 2024-08-31 | 2024-09-28
222 | 2024-08-31 | 4A/5 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-08-31 | 2024-09-28
223 | 2024-08-31 | 6/12 | DA+1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-08-31 | 2024-09-28
224 | 2024-09-01 | 5/10 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-09-01 | 2024-09-29
225 | 2024-09-01 | 7A/1 | DA+1.5 | Sandy | Competed |  | 1 | 1 | [5 empty] | 1 |  | 1 | 1 |  |  |  |  | 2024-09-01 | 2024-09-29
226 | 2024-09-01 | 4A/5 | DA+9 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-01 | 2024-09-29
227 | 2024-09-01 | 6/12 | DA+1.5 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-09-01 | 2024-09-29
228 | 2024-09-02 | 5/10 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 |  | 1 |  |  | 1 | [6 empty] | 2024-09-02 | 2024-09-30
229 | 2024-09-02 | 33/7 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-02 | 2024-09-30
230 | 2024-09-02 | 6/12 | DA+1.5 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-09-02 | 2024-09-30
231 | 2024-09-03 | 5/10 | DA+9 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-09-03 | 2024-10-01
232 | 2024-09-03 | 7A/2 | DA+3 | Sandy | Competed | 1 | [15 empty] | 2024-09-03 | 2024-10-01
233 | 2024-09-03 | 6/12 | DA+1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-09-03 | 2024-10-01
234 | 2024-09-04 | 4A/4 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-09-04 | 2024-10-02
235 | 2024-09-04 | 5/10 | DA+9 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-04 | 2024-10-02
236 | 2024-09-04 | 33/7 | DA+6 | Sandy | Competed | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-04 | 2024-10-02
237 | 2024-09-04 | 29/1 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-04 | 2024-10-02
238 | 2024-09-04 | 7A/2 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-04 | 2024-10-02
239 | 2024-09-04 | 6/12 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-09-04 | 2024-10-02
240 | 2024-09-05 | 29/1 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-05 | 2024-10-03
241 | 2024-09-05 | 7A/2 | DA+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-09-05 | 2024-10-03
242 | 2024-09-05 | 4A/4 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-09-05 | 2024-10-03
243 | 2024-09-05 | 6/12 | DA+1.5 | Sandy | Competed | 1 | 1 | 1 | [13 empty] | 2024-09-05 | 2024-10-03
244 | 2024-09-06 | 6/3 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-06 | 2024-10-04
245 | 2024-09-06 | 29/1 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-09-06 | 2024-10-04
246 | 2024-09-06 | 33/4 | DA+3 | Sandy | Competed | 1 | [15 empty] | 2024-09-06 | 2024-10-04
247 | 2024-09-06 | 7A/2 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-09-06 | 2024-10-04
248 | 2024-09-06 | 4A/4 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-09-06 | 2024-10-04
249 | 2024-09-07 | 6/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-07 | 2024-10-05
250 | 2024-09-07 | 29/1 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2024-09-07 | 2024-10-05
251 | 2024-09-08 | 29/1 | DA+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-09-08 | 2024-10-06
252 | 2024-09-08 | 33/4 | DA+3 | Sandy | Competed |  | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 | [5 empty] | 2024-09-08 | 2024-10-06
253 | 2024-09-08 | 7A/3 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-08 | 2024-10-06
254 | 2024-09-08 | 4A/3 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-08 | 2024-10-06
255 | 2024-09-08 | 6/11 | DA-1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-09-08 | 2024-10-06
256 | 2024-09-08 | 34/12 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-08 | 2024-10-06
257 | 2024-09-09 | 5/7 | DA+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-09-09 | 2024-10-07
258 | 2024-09-09 | 33/4 | DA+3 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-09 | 2024-10-07
259 | 2024-09-09 | 7A/3 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 |  |  | 1 | 1 |  | 1 | [5 empty] | 2024-09-09 | 2024-10-07
260 | 2024-09-09 | 4A/3 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-09 | 2024-10-07
261 | 2024-09-09 | 6/11 | DA-1.5 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2024-09-09 | 2024-10-07
262 | 2024-09-09 | 34/12 | DA+3 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-09-09 | 2024-10-07
263 | 2024-09-10 | 29/1 | DA+6 | Sandy | Competed | [9 empty] | 1 | 1 | 1 |  |  |  |  | 2024-09-10 | 2024-10-08
264 | 2024-09-10 | 7A/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  | 1 | [5 empty] | 1 |  |  |  |  | 2024-09-10 | 2024-10-08
265 | 2024-09-10 | 6/11 | DA-1.5 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-09-10 | 2024-10-08
266 | 2024-09-10 | 34/12 | DA+3 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-09-10 | 2024-10-08
267 | 2024-09-11 | 5/7 | DA+9 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-09-11 | 2024-10-09
268 | 2024-09-11 | 33/3 | DA+3 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-09-11 | 2024-10-09
269 | 2024-09-11 | 4A/6 | DA+9 | Sandy | Competed | 1 | 1 |  | 1 |  |  | 1 | [9 empty] | 2024-09-11 | 2024-10-09
270 | 2024-09-11 | 6/11 | DA-1.5 | Sandy | Competed | 1 | [15 empty] | 2024-09-11 | 2024-10-09
271 | 2024-09-12 | 5/7 | DA+9 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-09-12 | 2024-10-10
272 | 2024-09-12 | 33/3 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | 1 |  |  | 1 | [5 empty] | 2024-09-12 | 2024-10-10
273 | 2024-09-12 | 4A/6 | DA+9 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-12 | 2024-10-10
274 | 2024-09-12 | 6/11 | DA-1.5 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-09-12 | 2024-10-10
275 | 2024-09-12 | 34/12 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-09-12 | 2024-10-10
276 | 2024-09-13 | 33/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-13 | 2024-10-11
277 | 2024-09-13 | 34/12 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-13 | 2024-10-11
278 | 2024-09-14 | 5/6 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-14 | 2024-10-12
279 | 2024-09-14 | 34/1 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-09-14 | 2024-10-12
280 | 2024-09-14 | 36A/1 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-14 | 2024-10-12
281 | 2024-09-14 | 4A/2 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-14 | 2024-10-12
282 | 2024-09-14 | 6/11 | DA-1.5 | Sandy | Competed |  |  |  | 1 | 1 | 1 | [10 empty] | 2024-09-14 | 2024-10-12
283 | 2024-09-15 | 5/6 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-15 | 2024-10-13
284 | 2024-09-15 | 34/1 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-15 | 2024-10-13
285 | 2024-09-15 | 36A/1 | DA+3 | Sandy | Competed |  |  |  | 1 | 1 | 1 | [10 empty] | 2024-09-15 | 2024-10-13
286 | 2024-09-15 | 4A/2 | DA+6 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2024-09-15 | 2024-10-13
287 | 2024-09-15 | 34/11 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-09-15 | 2024-10-13
288 | 2024-09-16 | 27/2 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-09-16 | 2024-10-14
289 | 2024-09-16 | 4A/2 | DA+6 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-09-16 | 2024-10-14
290 | 2024-09-16 | 34/11 | DA+1.5 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-09-16 | 2024-10-14
291 | 2024-09-16 | 36A/2 | #N/A | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-16 | 2024-10-14
292 | 2024-09-17 | 27/2 | DA-1.5 | Sandy | Competed |  |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2024-09-17 | 2024-10-15
293 | 2024-09-17 | 34/3 | DA+1.5 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-17 | 2024-10-15
294 | 2024-09-17 | 36A/2 | #N/A | Sandy | Competed | 1 |  |  |  | 1 |  |  | 1 | [8 empty] | 2024-09-17 | 2024-10-15
295 | 2024-09-18 | 6/4 | DA+9 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-18 | 2024-10-16
296 | 2024-09-18 | 27/2 | DA-1.5 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-09-18 | 2024-10-16
297 | 2024-09-18 | 34/3 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-18 | 2024-10-16
298 | 2024-09-18 | 36A/2 | #N/A | Sandy | Competed |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | [6 empty] | 2024-09-18 | 2024-10-16
299 | 2024-09-18 | 34/11 | DA+1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-09-18 | 2024-10-16
300 | 2024-09-19 | 6/4 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-19 | 2024-10-17
301 | 2024-09-19 | 27/2 | DA-1.5 | Sandy | Competed | 1 | [5 empty] | 1 | [9 empty] | 2024-09-19 | 2024-10-17
302 | 2024-09-19 | 36A/2 | #N/A | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-09-19 | 2024-10-17
303 | 2024-09-19 | 6/10 | DA+1.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-09-19 | 2024-10-17
304 | 2024-09-19 | 34/11 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2024-09-19 | 2024-10-17
305 | 2024-09-20 | 6/4 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-09-20 | 2024-10-18
306 | 2024-09-20 | 27/2 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | 1 | [7 empty] | 2024-09-20 | 2024-10-18
307 | 2024-09-20 | 34/4 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-20 | 2024-10-18
308 | 2024-09-20 | 4A/1 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-20 | 2024-10-18
309 | 2024-09-20 | 6/10 | DA+1.5 | Sandy | Competed |  |  |  | 1 | 1 |  |  | 1 | [8 empty] | 2024-09-20 | 2024-10-18
310 | 2024-09-20 | 34/11 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-09-20 | 2024-10-18
311 | 2024-09-20 | 5/2 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-09-20 | 2024-10-18
312 | 2024-09-21 | 6/6 | DA-3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-21 | 2024-10-19
313 | 2024-09-21 | 34/4 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-21 | 2024-10-19
314 | 2024-09-21 | 37/1 | #N/A | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-21 | 2024-10-19
315 | 2024-09-21 | 4A/1 | DA+6 | Sandy | Competed | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-21 | 2024-10-19
316 | 2024-09-22 | 6/6 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | [6 empty] | 2024-09-22 | 2024-10-20
317 | 2024-09-22 | 34/5 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-09-22 | 2024-10-20
318 | 2024-09-22 | 37/1 | #N/A | Sandy | Competed |  | 1 | 1 |  | 1 |  |  | 1 |  |  | 1 | 1 |  |  |  |  | 2024-09-22 | 2024-10-20
319 | 2024-09-22 | 6/10 | DA+1.5 | Sandy | Competed | 1 |  |  |  |  | 1 |  |  | 1 | 1 | [6 empty] | 2024-09-22 | 2024-10-20
320 | 2024-09-22 | 5/2 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-22 | 2024-10-20
321 | 2024-09-23 | 6/6 | DA-3 | Sandy | Competed | [8 empty] | 1 |  | 1 | 1 |  |  |  |  | 2024-09-23 | 2024-10-21
322 | 2024-09-23 | 27/1 | DA+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-09-23 | 2024-10-21
323 | 2024-09-23 | 34/5 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2024-09-23 | 2024-10-21
324 | 2024-09-23 | 37/1 | #N/A | Sandy | Competed | [5 empty] | 1 |  |  | 1 | [7 empty] | 2024-09-23 | 2024-10-21
325 | 2024-09-23 | 35/1 | DA+6 | Sandy | Competed | 1 | 1 | [7 empty] | 1 | 1 | [5 empty] | 2024-09-23 | 2024-10-21
326 | 2024-09-23 | 5/2 | DA+9 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-23 | 2024-10-21
327 | 2024-09-24 | 27/1 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | [8 empty] | 2024-09-24 | 2024-10-22
328 | 2024-09-24 | 34/5 | DA+9 | Sandy | Competed |  |  | 1 | 1 |  | 1 | 1 | [9 empty] | 2024-09-24 | 2024-10-22
329 | 2024-09-24 | 35/1 | DA+6 | Sandy | Competed |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 2024-09-24 | 2024-10-22
330 | 2024-09-25 | 27/1 | DA+9 | Sandy | Competed |  |  |  |  | 1 |  |  |  | 1 | 1 | [6 empty] | 2024-09-25 | 2024-10-23
331 | 2024-09-25 | 34/5 | DA+9 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-09-25 | 2024-10-23
332 | 2024-09-25 | 37/2 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-09-25 | 2024-10-23
333 | 2024-09-25 | 35/1 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-09-25 | 2024-10-23
334 | 2024-09-26 | 7/0 | DB2+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-09-26 | 2024-10-24
335 | 2024-09-26 | 27/1 | DA+9 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-09-26 | 2024-10-24
336 | 2024-09-26 | 34/6 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-09-26 | 2024-10-24
337 | 2024-09-26 | 37/2 | DA+3 | Sandy | Competed |  | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 | [5 empty] | 2024-09-26 | 2024-10-24
338 | 2024-09-26 | 35/1 | DA+6 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | [7 empty] | 2024-09-26 | 2024-10-24
339 | 2024-09-26 | 4/5 | #N/A | Sandy | Competed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 2024-09-26 | 2024-10-24
340 | 2024-09-27 | 7/0 | DB2+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-09-27 | 2024-10-25
341 | 2024-09-27 | 27/1 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2024-09-27 | 2024-10-25
342 | 2024-09-27 | 34/6 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 |  |  |  | 1 | [5 empty] | 2024-09-27 | 2024-10-25
343 | 2024-09-27 | 37/2 | DA+3 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-27 | 2024-10-25
344 | 2024-09-27 | 6/10 | DA+1.5 | Sandy | Competed |  | 1 | [8 empty] | 1 | [5 empty] | 2024-09-27 | 2024-10-25
345 | 2024-09-27 | 4/5 | #N/A | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-09-27 | 2024-10-25
346 | 2024-09-28 | 7/0 | DB2+0 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-09-28 | 2024-10-26
347 | 2024-09-28 | 27/1 | DA+9 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-09-28 | 2024-10-26
348 | 2024-09-28 | 34/6 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-09-28 | 2024-10-26
349 | 2024-09-28 | 37/3 | DA-1.5 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-09-28 | 2024-10-26
350 | 2024-09-29 | 7/0 | DB2+0 | Sandy | Competed |  |  |  | 1 |  |  |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-29 | 2024-10-27
351 | 2024-09-29 | 34/8 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-29 | 2024-10-27
352 | 2024-09-29 | 37/3 | DA-1.5 | Sandy | Competed |  | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | 1 |  |  |  |  | 2024-09-29 | 2024-10-27
353 | 2024-09-29 | 6/10 | DA+1.5 | Sandy | Competed |  |  | 1 | [8 empty] | 1 |  |  |  |  | 2024-09-29 | 2024-10-27
354 | 2024-09-29 | 4A/0 | DB1+3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-09-29 | 2024-10-27
355 | 2024-09-29 | 6/9 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-29 | 2024-10-27
356 | 2024-09-30 | 7/0 | DB2+0 | Sandy | Competed | 1 | [15 empty] | 2024-09-30 | 2024-10-28
357 | 2024-09-30 | 34/8 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-30 | 2024-10-28
358 | 2024-09-30 | 37/3 | DA-1.5 | Sandy | Competed | [5 empty] | 1 |  |  | 1 | [7 empty] | 2024-09-30 | 2024-10-28
359 | 2024-09-30 | 6/9 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-30 | 2024-10-28
360 | 2024-09-30 | 35/5 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  | 1 | 1 | [8 empty] | 2024-09-30 | 2024-10-28
361 | 2024-09-30 | 4A/0 | DB1+3 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2024-09-30 | 2024-10-28
362 | 2024-09-01 | 7/0 | DB2+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-01 | 2024-09-29
363 | 2024-09-01 | 6/9 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-01 | 2024-09-29
364 | 2024-09-01 | 35/5 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | 1 | [6 empty] | 2024-09-01 | 2024-09-29
365 | 2024-09-01 | 4A/0 | DB1+3 | Sandy | Competed | 1 | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-01 | 2024-09-29
366 | 2024-09-03 | 27/3 | DA+1.5 | Sandy | WIP | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-03 | 2024-10-01
367 | 2024-09-03 | 34/7 | DA+0 | Sandy | Competed | 1 | 1 |  | 1 |  |  | 1 | 1 |  | 1 | [6 empty] | 2024-09-03 | 2024-10-01
368 | 2024-09-03 | 36A/0 | DB1+9 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-09-03 | 2024-10-01
369 | 2024-09-03 | 35/5 | DA+9 | Sandy | Competed | 1 | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-09-03 | 2024-10-01
370 | 2024-09-04 | 27/3 | DA+1.5 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-09-04 | 2024-10-02
371 | 2024-09-04 | 34/7 | DA+0 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  |  | 1 |  | 1 | 1 |  |  |  |  | 2024-09-04 | 2024-10-02
372 | 2024-09-04 | 36A/0 | DB1+9 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-09-04 | 2024-10-02
373 | 2024-09-04 | 3/8 | DA+0 | Sandy | Competed | [6 empty] | 1 | 1 |  | 1 | 1 | [5 empty] | 2024-09-04 | 2024-10-02
374 | 2024-09-05 | 27/3 | DA+1.5 | Sandy | Competed | 1 | [7 empty] | 1 |  |  | 1 |  |  |  |  | 2024-09-05 | 2024-10-03
375 | 2024-09-05 | 36A/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-09-05 | 2024-10-03
376 | 2024-09-05 | 5/9 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-05 | 2024-10-03
377 | 2024-09-05 | 35/6 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-05 | 2024-10-03
378 | 2024-09-05 | 3/8 | DA+0 | Sandy | Competed | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-05 | 2024-10-03
379 | 2024-09-06 | 7/3 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2024-09-06 | 2024-10-04
380 | 2024-09-06 | 27/3 | DA+1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-09-06 | 2024-10-04
381 | 2024-09-06 | 34/9 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-06 | 2024-10-04
382 | 2024-09-06 | 5/9 | DA+6 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2024-09-06 | 2024-10-04
383 | 2024-09-06 | 35/6 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-06 | 2024-10-04
384 | 2024-09-07 | 7/3 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | [5 empty] | 2024-09-07 | 2024-10-05
385 | 2024-09-07 | 34/9 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-09-07 | 2024-10-05
386 | 2024-09-07 | 5/9 | DA+6 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-09-07 | 2024-10-05
387 | 2024-09-07 | 35/6 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2024-09-07 | 2024-10-05
388 | 2024-09-07 | 3/9 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-09-07 | 2024-10-05
389 | 2024-09-08 | 7/3 | DA+9 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-09-08 | 2024-10-06
390 | 2024-09-08 | 27/3 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-09-08 | 2024-10-06
391 | 2024-09-08 | 37/0 | #N/A | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-09-08 | 2024-10-06
392 | 2024-09-08 | 3/9 | DA+0 | Sandy | Competed |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [5 empty] | 2024-09-08 | 2024-10-06
393 | 2024-09-08 | 35/6 | DA+6 | Sandy | Competed |  | 1 | [14 empty] | 2024-09-08 | 2024-10-06
394 | 2024-09-09 | 7/4 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-09-09 | 2024-10-07
395 | 2024-09-09 | 34/10 | DA-3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-09-09 | 2024-10-07
396 | 2024-09-09 | 37/0 | #N/A | Sandy | Competed | 1 |  |  |  | 1 | 1 | [10 empty] | 2024-09-09 | 2024-10-07
397 | 2024-09-09 | 35/6 | DA+6 | Sandy | Competed |  |  | 1 | 1 | 1 | 1 | [10 empty] | 2024-09-09 | 2024-10-07
398 | 2024-09-09 | 3/9 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-09-09 | 2024-10-07
399 | 2024-09-10 | 7/4 | DA+6 | Sandy | Competed |  | 1 |  |  |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-09-10 | 2024-10-08
400 | 2024-09-10 | 27/6 | DA-3 | Sandy | WIP | [9 empty] | 1 | [6 empty] | 2024-09-10 | 2024-10-08
401 | 2024-09-10 | 34/10 | DA-3 | Sandy | Competed | 1 | [6 empty] | 1 | [8 empty] | 2024-09-10 | 2024-10-08
402 | 2024-09-10 | 37/0 | #N/A | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-09-10 | 2024-10-08
403 | 2024-10-11 | 7/4 | DA+6 | Sandy | Competed |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 2024-10-11 | 2024-11-08
404 | 2024-10-11 | 27/6 | DA-3 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-10-11 | 2024-11-08
405 | 2024-10-11 | 34/10 | DA-3 | Sandy | Competed |  | 1 |  | 1 |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 2024-10-11 | 2024-11-08
406 | 2024-10-11 | 35/7 | DA+3 | Sandy | Competed | 1 | [15 empty] | 2024-10-11 | 2024-11-08
407 | 2024-10-11 | 3/10 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-10-11 | 2024-11-08
408 | 2024-10-12 | 7/4 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | 2024-10-12 | 2024-11-09
409 | 2024-10-12 | 34/10 | DA-3 | Sandy | Competed |  |  | 1 |  | 1 | 1 | [10 empty] | 2024-10-12 | 2024-11-09
410 | 2024-10-12 | 37/0 | #N/A | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-10-12 | 2024-11-09
411 | 2024-10-12 | 6/0 | DB1+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-10-12 | 2024-11-09
412 | 2024-10-12 | 35/7 | DA+3 | Sandy | Competed |  | 1 | 1 | [6 empty] | 1 | [6 empty] | 2024-10-12 | 2024-11-09
413 | 2024-10-12 | 3/10 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-12 | 2024-11-09
414 | 2024-10-13 | 27/6 | DA-3 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 2024-10-13 | 2024-11-10
415 | 2024-10-13 | 37/0 | #N/A | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2024-10-13 | 2024-11-10
416 | 2024-10-13 | 6/0 | DB1+9 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2024-10-13 | 2024-11-10
417 | 2024-10-13 | 35/7 | DA+3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-10-13 | 2024-11-10
418 | 2024-10-14 | 6/7 | DA+1.5 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-10-14 | 2024-11-11
419 | 2024-10-14 | 27/6 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-10-14 | 2024-11-11
420 | 2024-10-14 | 34/2 | DA+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-10-14 | 2024-11-11
421 | 2024-10-14 | 37/0 | #N/A | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-10-14 | 2024-11-11
422 | 2024-10-14 | 35/7 | DA+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-10-14 | 2024-11-11
423 | 2024-10-14 | 3/11 | DA+0 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-10-14 | 2024-11-11
424 | 2024-10-15 | 6/7 | DA+1.5 | Sandy | Competed |  |  |  | 1 |  |  | 1 | 1 |  |  | 1 | [5 empty] | 2024-10-15 | 2024-11-12
425 | 2024-10-15 | 34/2 | DA+9 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2024-10-15 | 2024-11-12
426 | 2024-10-15 | 6/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-10-15 | 2024-11-12
427 | 2024-10-15 | 35/7 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-10-15 | 2024-11-12
428 | 2024-10-15 | 3/11 | DA+0 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2024-10-15 | 2024-11-12
429 | 2024-10-16 | 6/7 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-10-16 | 2024-11-13
430 | 2024-10-16 | 34/2 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-16 | 2024-11-13
431 | 2024-10-16 | 6/0 | DB1+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-10-16 | 2024-11-13
432 | 2024-10-16 | 3/11 | DA+0 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-10-16 | 2024-11-13
433 | 2024-10-17 | 37A/4 | DA+9 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-10-17 | 2024-11-14
434 | 2024-10-17 | 6/0 | DB1+9 | Sandy | Competed | 1 |  |  |  | 1 | [11 empty] | 2024-10-17 | 2024-11-14
435 | 2024-10-17 | 35/7 | DA+3 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | [7 empty] | 2024-10-17 | 2024-11-14
436 | 2024-10-18 | 6/5 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-10-18 | 2024-11-15
437 | 2024-10-18 | 33/5 | DA+0 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-10-18 | 2024-11-15
438 | 2024-10-18 | 37A/4 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-10-18 | 2024-11-15
439 | 2024-10-18 | 6/0 | DB1+9 | Sandy | Competed |  | 1 | 1 |  |  | 1 | [10 empty] | 2024-10-18 | 2024-11-15
440 | 2024-10-18 | 3/7 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-10-18 | 2024-11-15
441 | 2024-10-19 | 6/5 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-19 | 2024-11-16
442 | 2024-10-19 | 29/2 | DA+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-10-19 | 2024-11-16
443 | 2024-10-19 | 33/5 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-10-19 | 2024-11-16
444 | 2024-10-19 | 37A/4 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2024-10-19 | 2024-11-16
445 | 2024-10-19 | 35/8 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-10-19 | 2024-11-16
446 | 2024-10-19 | 3/7 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-19 | 2024-11-16
447 | 2024-10-20 | 29/2 | DA+0 | Sandy | Competed | 1 | [6 empty] | 1 | [8 empty] | 2024-10-20 | 2024-11-17
448 | 2024-10-20 | 37A/4 | DA+9 | Sandy | Competed |  | 1 |  |  |  |  | 1 | [9 empty] | 2024-10-20 | 2024-11-17
449 | 2024-10-20 | 35/8 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-20 | 2024-11-17
450 | 2024-10-21 | 29/2 | DA+0 | Sandy | Competed |  | 1 | [6 empty] | 1 | [7 empty] | 2024-10-21 | 2024-11-18
451 | 2024-10-21 | 33/5 | DA+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | 1 | [5 empty] | 2024-10-21 | 2024-11-18
452 | 2024-10-21 | 37A/4 | DA+9 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 | 1 | [7 empty] | 2024-10-21 | 2024-11-18
453 | 2024-10-21 | 5/5 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-10-21 | 2024-11-18
454 | 2024-10-21 | 35/8 | DA+6 | Sandy | Competed | 1 | 1 | [14 empty] | 2024-10-21 | 2024-11-18
455 | 2024-10-21 | 3/6 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-10-21 | 2024-11-18
456 | 2024-10-22 | 29/2 | DA+0 | Sandy | Competed |  |  | 1 | 1 | [12 empty] | 2024-10-22 | 2024-11-19
457 | 2024-10-22 | 33/5 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-10-22 | 2024-11-19
458 | 2024-10-22 | 5/5 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 | [9 empty] | 2024-10-22 | 2024-11-19
459 | 2024-10-22 | 35/8 | DA+6 | Sandy | Competed |  |  | 1 | [13 empty] | 2024-10-22 | 2024-11-19
460 | 2024-10-22 | 3/6 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-22 | 2024-11-19
461 | 2024-10-23 | 33/8 | DA+3 | Sandy | WIP |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-10-23 | 2024-11-20
462 | 2024-10-23 | 5/5 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-23 | 2024-11-20
463 | 2024-10-23 | 35/9 | DA+1.5 | Sandy | Competed | 1 | [15 empty] | 2024-10-23 | 2024-11-20
464 | 2024-10-23 | 37A/5 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | 1 | [8 empty] | 2024-10-23 | 2024-11-20
465 | 2024-10-24 | 29/2 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | 1 | [5 empty] | 2024-10-24 | 2024-11-21
466 | 2024-10-24 | 33/8 | DA+3 | Sandy | WIP |  |  |  |  | 1 |  |  | 1 |  | 1 | [6 empty] | 2024-10-24 | 2024-11-21
467 | 2024-10-24 | 37A/5 | DA+3 | Sandy | Competed |  | 1 | 1 | [5 empty] | 1 | 1 | [6 empty] | 2024-10-24 | 2024-11-21
468 | 2024-10-24 | 35/9 | DA+1.5 | Sandy | Competed |  | 1 | 1 | 1 | [12 empty] | 2024-10-24 | 2024-11-21
469 | 2024-10-25 | 29/2 | DA+0 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2024-10-25 | 2024-11-22
470 | 2024-10-25 | 33/8 | DA+3 | Sandy | Competed | 1 | 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-10-25 | 2024-11-22
471 | 2024-10-25 | 37A/5 | DA+3 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-10-25 | 2024-11-22
472 | 2024-10-25 | 35/9 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-10-25 | 2024-11-22
473 | 2024-10-26 | 37A/3 | DA+3 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-10-26 | 2024-11-23
474 | 2024-10-26 | 35/9 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-10-26 | 2024-11-23
475 | 2024-10-26 | 3/4 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-10-26 | 2024-11-23
476 | 2024-10-27 | 29A/0 | DB1+0 | Sandy | Competed | 1 | [15 empty] | 2024-10-27 | 2024-11-24
477 | 2024-10-27 | 37A/3 | DA+3 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2024-10-27 | 2024-11-24
478 | 2024-10-27 | 35/9 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-10-27 | 2024-11-24
479 | 2024-10-28 | 29A/0 | DB1+0 | Sandy | Competed |  | 1 | [14 empty] | 2024-10-28 | 2024-11-25
480 | 2024-10-28 | 37A/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 | [9 empty] | 2024-10-28 | 2024-11-25
481 | 2024-10-28 | 6/8 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-10-28 | 2024-11-25
482 | 2024-10-28 | 3/4 | DA+6 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-10-28 | 2024-11-25
483 | 2024-10-28 | 35/8 | DA+6 | Sandy | Competed |  |  |  | 1 | 1 | [11 empty] | 2024-10-28 | 2024-11-25
484 | 2024-10-29 | 29A/0 | DB1+0 | Sandy | Competed |  |  | 1 | [6 empty] | 1 | [6 empty] | 2024-10-29 | 2024-11-26
485 | 2024-10-29 | 37A/3 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 2024-10-29 | 2024-11-26
486 | 2024-10-29 | 6/8 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-29 | 2024-11-26
487 | 2024-10-29 | 35/8 | DA+6 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2024-10-29 | 2024-11-26
488 | 2024-10-29 | 3/4 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-10-29 | 2024-11-26
489 | 2024-10-30 | 29A/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-10-30 | 2024-11-27
490 | 2024-10-30 | 37A/3 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-10-30 | 2024-11-27
491 | 2024-11-04 | 29A/0 | DB1+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-11-04 | 2024-12-02
492 | 2024-11-04 | 35/11 | DA+3 | Sandy | WIP |  |  |  | 1 | [12 empty] | 2024-11-04 | 2024-12-02
493 | 2024-11-05 | 29A/0 | DB1+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-05 | 2024-12-03
494 | 2024-11-05 | 37A/2 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-11-05 | 2024-12-03
495 | 2024-11-05 | 35/11 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 | [10 empty] | 2024-11-05 | 2024-12-03
496 | 2024-11-06 | 29A/0 | DB1+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-11-06 | 2024-12-04
497 | 2024-11-06 | 37A/2 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-11-06 | 2024-12-04
498 | 2024-11-06 | 6/8 | DA+3 | Sandy | Competed | 1 | 1 | [14 empty] | 2024-11-06 | 2024-12-04
499 | 2024-11-06 | 35/11 | DA+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-06 | 2024-12-04
500 | 2024-11-07 | 29A/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-07 | 2024-12-05
501 | 2024-11-07 | 37A/2 | DA+1.5 | Sandy | Competed |  | 1 |  |  | 1 | 1 | [10 empty] | 2024-11-07 | 2024-12-05
502 | 2024-11-07 | 6/8 | DA+3 | Sandy | Competed |  |  | 1 | 1 | [12 empty] | 2024-11-07 | 2024-12-05
503 | 2024-11-07 | 18/0 | DB2+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-11-07 | 2024-12-05
504 | 2024-11-08 | 37A/2 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-08 | 2024-12-06
505 | 2024-11-08 | 6/8 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-08 | 2024-12-06
506 | 2024-11-08 | 35/11 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-11-08 | 2024-12-06
507 | 2024-11-08 | 33/9 | DA+1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-11-08 | 2024-12-06
508 | 2024-11-09 | 35/11 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-09 | 2024-12-07
509 | 2024-11-09 | 18/0 | DB2+6 | Sandy | Competed | 1 | [9 empty] | 1 | [5 empty] | 2024-11-09 | 2024-12-07
510 | 2024-11-09 | 33/9 | DA+1.5 | Sandy | Competed | 1 | [15 empty] | 2024-11-09 | 2024-12-07
511 | 2024-11-10 | 37A/1 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-11-10 | 2024-12-08
512 | 2024-11-10 | 18/0 | DB2+6 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2024-11-10 | 2024-12-08
513 | 2024-11-10 | 33/9 | DA+1.5 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-11-10 | 2024-12-08
514 | 2024-11-11 | 37A/1 | DA+3 | Sandy | Competed | 1 | [6 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-11 | 2024-12-09
515 | 2024-11-11 | 18/0 | DB2+6 | Sandy | Competed |  | 1 | 1 | 1 | [12 empty] | 2024-11-11 | 2024-12-09
516 | 2024-11-11 | 33/9 | DA+1.5 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-11-11 | 2024-12-09
517 | 2024-11-12 | 37A/1 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-11-12 | 2024-12-10
518 | 2024-11-12 | 7A/0 | DB1+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-11-12 | 2024-12-10
519 | 2024-11-12 | 36/0 | DB2+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-12 | 2024-12-10
520 | 2024-11-12 | 18/0 | DB2+6 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-12 | 2024-12-10
521 | 2024-11-14 | 38/8 | DA+1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-14 | 2024-12-12
522 | 2024-11-14 | 37/4 | DA+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-11-14 | 2024-12-12
523 | 2024-11-14 | 7A/0 | DB1+6 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-11-14 | 2024-12-12
524 | 2024-11-14 | 36/0 | DB2+3 | Sandy | Competed | 1 | [15 empty] | 2024-11-14 | 2024-12-12
525 | 2024-11-14 | 18/1 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-11-14 | 2024-12-12
526 | 2024-11-15 | 38/8 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2024-11-15 | 2024-12-13
527 | 2024-11-15 | 37/4 | DA+9 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2024-11-15 | 2024-12-13
528 | 2024-11-15 | 36/0 | DB2+3 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2024-11-15 | 2024-12-13
529 | 2024-11-15 | 18/1 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-15 | 2024-12-13
530 | 2024-11-16 | 38/8 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2024-11-16 | 2024-12-14
531 | 2024-11-16 | 37/4 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2024-11-16 | 2024-12-14
532 | 2024-11-16 | 7A/0 | DB1+6 | Sandy | Competed | 1 | [6 empty] | 1 |  |  | 1 | [5 empty] | 2024-11-16 | 2024-12-14
533 | 2024-11-16 | 36/0 | DB2+3 | Sandy | Competed | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 2024-11-16 | 2024-12-14
534 | 2024-11-16 | 18/1 | DA+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-16 | 2024-12-14
535 | 2024-11-16 | 34/0 | DB1+6 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-11-16 | 2024-12-14
536 | 2024-11-17 | 38/8 | DA+1.5 | Sandy | Competed | 1 | [15 empty] | 2024-11-17 | 2024-12-15
537 | 2024-11-17 | 37/4 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-11-17 | 2024-12-15
538 | 2024-11-17 | 7A/0 | DB1+6 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-11-17 | 2024-12-15
539 | 2024-11-17 | 36/0 | DB2+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-17 | 2024-12-15
540 | 2024-11-17 | 18/2 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-11-17 | 2024-12-15
541 | 2024-11-17 | 34/0 | DB1+6 | Sandy | Competed | 1 | [6 empty] | 1 | [8 empty] | 2024-11-17 | 2024-12-15
542 | 2024-11-18 | 37/5 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-11-18 | 2024-12-16
543 | 2024-11-18 | 7A/0 | DB1+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-18 | 2024-12-16
544 | 2024-11-18 | 36/0 | DB2+3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-11-18 | 2024-12-16
545 | 2024-11-18 | 18/2 | DA+1.5 | Sandy | Competed |  | 1 |  |  | 1 |  | 1 |  |  | 1 | [6 empty] | 2024-11-18 | 2024-12-16
546 | 2024-11-18 | 34/0 | DB1+6 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2024-11-18 | 2024-12-16
547 | 2024-11-18 | 38/9 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-11-18 | 2024-12-16
548 | 2024-11-19 | 38/8 | DA+1.5 | Sandy | Competed |  | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 |  |  |  |  | 2024-11-19 | 2024-12-17
549 | 2024-11-19 | 37/5 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-19 | 2024-12-17
550 | 2024-11-19 | 36/0 | DB2+3 | Sandy | Competed | [6 empty] | 1 | 1 | [8 empty] | 2024-11-19 | 2024-12-17
551 | 2024-11-19 | 18/2 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-19 | 2024-12-17
552 | 2024-11-19 | 34/0 | DB1+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-19 | 2024-12-17
553 | 2024-11-19 | 38/9 | DA+0 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-11-19 | 2024-12-17
554 | 2024-11-20 | 38/8 | DA+1.5 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2024-11-20 | 2024-12-18
555 | 2024-11-20 | 37/5 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-11-20 | 2024-12-18
556 | 2024-11-20 | 36/0 | DB2+3 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2024-11-20 | 2024-12-18
557 | 2024-11-20 | 34/0 | DB1+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-11-20 | 2024-12-18
558 | 2024-11-20 | 38/9 | DA+0 | Sandy | Competed |  |  |  |  | 1 |  |  | 1 |  |  |  | 1 |  |  |  |  | 2024-11-20 | 2024-12-18
559 | 2024-11-21 | 37/5 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-11-21 | 2024-12-19
560 | 2024-11-21 | 7A/0 | DB1+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-21 | 2024-12-19
561 | 2024-11-21 | 18/3 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2024-11-21 | 2024-12-19
562 | 2024-11-21 | 34/0 | DB1+6 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2024-11-21 | 2024-12-19
563 | 2024-11-21 | 38/9 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 | [7 empty] | 2024-11-21 | 2024-12-19
564 | 2024-11-21 | 38/10 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-11-21 | 2024-12-19
565 | 2024-11-22 | 38/10 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2024-11-22 | 2024-12-20
566 | 2024-11-22 | 37A/0 | DB1+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-11-22 | 2024-12-20
567 | 2024-11-22 | 7A/0 | DB1+6 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-22 | 2024-12-20
568 | 2024-11-22 | 18/3 | DA+6 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 | [9 empty] | 2024-11-22 | 2024-12-20
569 | 2024-11-22 | 34/0 | DB1+6 | Sandy | Competed |  |  |  | 1 | [7 empty] | 1 |  |  |  |  | 2024-11-22 | 2024-12-20
570 | 2024-11-23 | 34/0 | DB1+6 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-23 | 2024-12-21
571 | 2024-11-23 | 35/4 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-11-23 | 2024-12-21
572 | 2024-11-23 | 37A/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-11-23 | 2024-12-21
573 | 2024-11-23 | 38/10 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-11-23 | 2024-12-21
574 | 2024-11-23 | 18/3 | DA+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 | [5 empty] | 2024-11-23 | 2024-12-21
575 | 2024-11-24 | 37A/0 | DB1+0 | Sandy | Competed | 1 | [6 empty] | 1 | 1 | [7 empty] | 2024-11-24 | 2024-12-22
576 | 2024-11-24 | 35/4 | DA+9 | Sandy | Competed |  | 1 | [14 empty] | 2024-11-24 | 2024-12-22
577 | 2024-11-24 | 18/3 | DA+6 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2024-11-24 | 2024-12-22
578 | 2024-11-24 | 38/7 | DA+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-11-24 | 2024-12-22
579 | 2024-11-25 | 37A/0 | DB1+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-25 | 2024-12-23
580 | 2024-11-25 | 7/2 | DA+6 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-11-25 | 2024-12-23
581 | 2024-11-25 | 35/4 | DA+9 | Sandy | Competed |  |  | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-11-25 | 2024-12-23
582 | 2024-11-25 | 18/4 | DA-3 | Sandy | Competed | 1 | [15 empty] | 2024-11-25 | 2024-12-23
583 | 2024-11-25 | 38/7 | DA+9 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2024-11-25 | 2024-12-23
584 | 2024-11-26 | 37A/0 | DB1+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-26 | 2024-12-24
585 | 2024-11-26 | 7/2 | DA+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-11-26 | 2024-12-24
586 | 2024-11-26 | 35/4 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2024-11-26 | 2024-12-24
587 | 2024-11-26 | 18/4 | DA-3 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-11-26 | 2024-12-24
588 | 2024-11-26 | 38/7 | DA+9 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-11-26 | 2024-12-24
589 | 2024-11-27 | 37A/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-11-27 | 2024-12-25
590 | 2024-11-27 | 7/2 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-27 | 2024-12-25
591 | 2024-11-27 | 35/4 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-11-27 | 2024-12-25
592 | 2024-11-27 | 18/4 | DA-3 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2024-11-27 | 2024-12-25
593 | 2024-11-27 | 38/6 | DA+6 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2024-11-27 | 2024-12-25
594 | 2024-11-28 | 38/0 | DB1+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-11-28 | 2024-12-26
595 | 2024-11-28 | 7/2 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-11-28 | 2024-12-26
596 | 2024-11-28 | 18/4 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 2024-11-28 | 2024-12-26
597 | 2024-11-28 | 38/6 | DA+6 | Sandy | Competed |  | 1 |  | 1 |  |  |  | 1 |  |  | 1 | [5 empty] | 2024-11-28 | 2024-12-26
598 | 2024-11-29 | 18/4 | DA-3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-11-29 | 2024-12-27
599 | 2024-11-29 | 38/6 | DA+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2024-11-29 | 2024-12-27
600 | 2024-11-29 | 38/5 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-11-29 | 2024-12-27
601 | 2024-11-30 | 38/0 | DB1+3 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2024-11-30 | 2024-12-28
602 | 2024-11-30 | 7/2 | DA+6 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2024-11-30 | 2024-12-28
603 | 2024-11-30 | 35/0 | DB2+0 | Sandy | Competed | 1 | [15 empty] | 2024-11-30 | 2024-12-28
604 | 2024-11-30 | 38/5 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-11-30 | 2024-12-28
605 | 2024-12-01 | 38/0 | DB1+3 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | [6 empty] | 2024-12-01 | 2024-12-29
606 | 2024-12-01 | 7/2 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-01 | 2024-12-29
607 | 2024-12-01 | 35/0 | DB2+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-12-01 | 2024-12-29
608 | 2024-12-01 | 18/6 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-01 | 2024-12-29
609 | 2024-12-02 | 38/0 | DB1+3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2024-12-02 | 2024-12-30
610 | 2024-12-02 | 35/0 | DB2+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-12-02 | 2024-12-30
611 | 2024-12-02 | 18/6 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-02 | 2024-12-30
612 | 2024-12-03 | 38/0 | DB1+3 | Sandy | Competed | 1 | [15 empty] | 2024-12-03 | 2024-12-31
613 | 2024-12-03 | 35/0 | DB2+0 | Sandy | Competed | [7 empty] | 1 |  | 1 | [6 empty] | 2024-12-03 | 2024-12-31
614 | 2024-12-03 | 18/6 | DA+9 | Sandy | Competed | 1 |  |  |  | 1 | [11 empty] | 2024-12-03 | 2024-12-31
615 | 2024-12-03 | 38/4 | DA+1.5 | Sandy | Competed | 1 | 1 |  | 1 | 1 | [11 empty] | 2024-12-03 | 2024-12-31
616 | 2024-12-04 | 38/0 | DB1+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-12-04 | 2025-01-01
617 | 2024-12-04 | 35/0 | DB2+0 | Sandy | Competed | [8 empty] | 1 |  | 1 | 1 |  |  |  |  | 2024-12-04 | 2025-01-01
618 | 2024-12-04 | 18/6 | DA+9 | Sandy | Competed |  | 1 | 1 |  |  | 1 | [10 empty] | 2024-12-04 | 2025-01-01
619 | 2024-12-04 | 38/4 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2024-12-04 | 2025-01-01
620 | 2024-12-04 | 38/3 | DA+3 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-12-04 | 2025-01-01
621 | 2024-12-05 | 37A/6 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-12-05 | 2025-01-02
622 | 2024-12-05 | 35/0 | DB2+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-05 | 2025-01-02
623 | 2024-12-05 | 38/3 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 |  | 1 |  |  |  | 1 | [5 empty] | 2024-12-05 | 2025-01-02
624 | 2024-12-06 | 37A/6 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2024-12-06 | 2025-01-03
625 | 2024-12-06 | 35/0 | DB2+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-12-06 | 2025-01-03
626 | 2024-12-06 | 18/5 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-12-06 | 2025-01-03
627 | 2024-12-06 | 38/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 |  |  |  |  | 2024-12-06 | 2025-01-03
628 | 2024-12-07 | 37A/6 | DA+3 | Sandy | Competed | [9 empty] | 1 | 1 | 1 |  |  |  |  | 2024-12-07 | 2025-01-04
629 | 2024-12-07 | 30/3 | DA+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-07 | 2025-01-04
630 | 2024-12-07 | 18/5 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-07 | 2025-01-04
631 | 2024-12-07 | 38/4 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-07 | 2025-01-04
632 | 2024-12-08 | 37A/6 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-08 | 2025-01-05
633 | 2024-12-08 | 7/5 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-08 | 2025-01-05
634 | 2024-12-08 | 30/3 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-12-08 | 2025-01-05
635 | 2024-12-08 | 38/4 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-08 | 2025-01-05
636 | 2024-12-08 | 38/2 | DA+0 | Sandy | Competed | 1 | [5 empty] | 1 | [9 empty] | 2024-12-08 | 2025-01-05
637 | 2024-12-09 | 7/5 | DA+6 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-12-09 | 2025-01-06
638 | 2024-12-09 | 30/3 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-12-09 | 2025-01-06
639 | 2024-12-09 | 38/2 | DA+0 | Sandy | Competed |  | 1 |  | 1 | [5 empty] | 1 | [6 empty] | 2024-12-09 | 2025-01-06
640 | 2024-12-09 | 39/1 | DA-1.5 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-12-09 | 2025-01-06
641 | 2024-12-10 | 40/2 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2024-12-10 | 2025-01-07
642 | 2024-12-10 | 7/5 | DA+6 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-12-10 | 2025-01-07
643 | 2024-12-10 | 30/3 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-10 | 2025-01-07
644 | 2024-12-10 | 38/1 | DA+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-10 | 2025-01-07
645 | 2024-12-10 | 38/2 | DA+0 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-10 | 2025-01-07
646 | 2024-12-10 | 39/1 | DA-1.5 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-12-10 | 2025-01-07
647 | 2024-12-11 | 40/2 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-12-11 | 2025-01-08
648 | 2024-12-11 | 30/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-12-11 | 2025-01-08
649 | 2024-12-11 | 38/1 | DA+0 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-11 | 2025-01-08
650 | 2024-12-11 | 38/2 | DA+0 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2024-12-11 | 2025-01-08
651 | 2024-12-11 | 39/1 | DA-1.5 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-12-11 | 2025-01-08
652 | 2024-12-12 | 40/2 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-12 | 2025-01-09
653 | 2024-12-12 | 30/0 | DB1+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-12 | 2025-01-09
654 | 2024-12-12 | 38/1 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-12-12 | 2025-01-09
655 | 2024-12-12 | 38/2 | DA+0 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2024-12-12 | 2025-01-09
656 | 2024-12-12 | 39/1 | DA-1.5 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2024-12-12 | 2025-01-09
657 | 2024-12-12 | 40/3 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-12-12 | 2025-01-09
658 | 2024-12-13 | 40/3 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2024-12-13 | 2025-01-10
659 | 2024-12-13 | 7/5 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2024-12-13 | 2025-01-10
660 | 2024-12-13 | 30/0 | DB1+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-12-13 | 2025-01-10
661 | 2024-12-13 | 17/0 | DC1+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-13 | 2025-01-10
662 | 2024-12-13 | 38/1 | DA+0 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-13 | 2025-01-10
663 | 2024-12-13 | 39/1 | DA-1.5 | Sandy | Competed | 1 | [15 empty] | 2024-12-13 | 2025-01-10
664 | 2024-12-14 | 40/3 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-14 | 2025-01-11
665 | 2024-12-14 | 7/5 | DA+6 | Sandy | Competed |  | 1 | [14 empty] | 2024-12-14 | 2025-01-11
666 | 2024-12-14 | 30/0 | DB1+0 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2024-12-14 | 2025-01-11
667 | 2024-12-14 | 17/0 | DC1+3 | Sandy | Competed |  |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2024-12-14 | 2025-01-11
668 | 2024-12-14 | 39/1 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-14 | 2025-01-11
669 | 2024-12-15 | 40/7 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-15 | 2025-01-12
670 | 2024-12-15 | 30/0 | DB1+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-12-15 | 2025-01-12
671 | 2024-12-15 | 17/0 | DC1+3 | Sandy | Competed | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 2024-12-15 | 2025-01-12
672 | 2024-12-15 | 39/0 | DB2+0 | Sandy | Competed | 1 | [15 empty] | 2024-12-15 | 2025-01-12
673 | 2024-12-15 | 39/1 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-12-15 | 2025-01-12
674 | 2024-12-16 | 40/7 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-16 | 2025-01-13
675 | 2024-12-16 | 7/5 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-16 | 2025-01-13
676 | 2024-12-16 | 30/0 | DB1+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-16 | 2025-01-13
677 | 2024-12-16 | 17/0 | DC1+3 | Sandy | Competed | 1 | [10 empty] | 1 |  |  |  |  | 2024-12-16 | 2025-01-13
678 | 2024-12-16 | 39/0 | DB2+0 | Sandy | Competed |  | 1 | [14 empty] | 2024-12-16 | 2025-01-13
679 | 2024-12-17 | 40/7 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-12-17 | 2025-01-14
680 | 2024-12-17 | 7/5 | DA+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 | [10 empty] | 2024-12-17 | 2025-01-14
681 | 2024-12-17 | 17/0 | DC1+3 | Sandy | Competed |  | 1 | [14 empty] | 2024-12-17 | 2025-01-14
682 | 2024-12-17 | 39/0 | DB2+0 | Sandy | Competed |  |  | 1 | 1 |  |  | 1 | [9 empty] | 2024-12-17 | 2025-01-14
683 | 2024-12-18 | 40/7 | DA+3 | Sandy | Competed |  |  |  |  | 1 |  |  | 1 | [8 empty] | 2024-12-18 | 2025-01-15
684 | 2024-12-18 | 30/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2024-12-18 | 2025-01-15
685 | 2024-12-18 | 17/0 | DC1+3 | Sandy | Competed |  |  | 1 |  |  |  | 1 | [9 empty] | 2024-12-18 | 2025-01-15
686 | 2024-12-18 | 39/0 | DB2+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2024-12-18 | 2025-01-15
687 | 2024-12-18 | 39/2 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-18 | 2025-01-15
688 | 2024-12-19 | 40/7 | DA+3 | Sandy | Competed | [5 empty] | 1 |  |  | 1 | [7 empty] | 2024-12-19 | 2025-01-16
689 | 2024-12-19 | 30/2 | DA+9 | Sandy | Competed | 1 | [5 empty] | 1 | [9 empty] | 2024-12-19 | 2025-01-16
690 | 2024-12-19 | 17/0 | DC1+3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-19 | 2025-01-16
691 | 2024-12-19 | 39/0 | DB2+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-19 | 2025-01-16
692 | 2024-12-19 | 39/2 | DA+3 | Sandy | Competed |  | 1 |  | 1 | [12 empty] | 2024-12-19 | 2025-01-16
693 | 2024-12-19 | 40/6 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-12-19 | 2025-01-16
694 | 2024-12-20 | 40/6 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 |  | 1 |  |  | 1 | [6 empty] | 2024-12-20 | 2025-01-17
695 | 2024-12-20 | 39/0 | DB2+0 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2024-12-20 | 2025-01-17
696 | 2024-12-20 | 39/2 | DA+3 | Sandy | Competed |  |  | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-12-20 | 2025-01-17
697 | 2024-12-21 | 40/6 | DA+9 | Sandy | Competed |  |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-21 | 2025-01-18
698 | 2024-12-21 | 7/6 | DA-1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-21 | 2025-01-18
699 | 2024-12-21 | 30/2 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | [6 empty] | 2024-12-21 | 2025-01-18
700 | 2024-12-21 | 16/0 | DC2+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2024-12-21 | 2025-01-18
701 | 2024-12-21 | 39/0 | DB2+0 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2024-12-21 | 2025-01-18
702 | 2024-12-21 | 39/2 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-12-21 | 2025-01-18
703 | 2024-12-21 | 39/4 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-12-21 | 2025-01-18
704 | 2024-12-22 | 30/2 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2024-12-22 | 2025-01-19
705 | 2024-12-22 | 16/0 | DC2+0 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2024-12-22 | 2025-01-19
706 | 2024-12-22 | 39/4 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 |  |  | 1 |  | 1 | [6 empty] | 2024-12-22 | 2025-01-19
707 | 2024-12-23 | 40/8 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2024-12-23 | 2025-01-20
708 | 2024-12-23 | 7/6 | DA-1.5 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2024-12-23 | 2025-01-20
709 | 2024-12-23 | 16/0 | DC2+0 | Sandy | Competed | [6 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 2024-12-23 | 2025-01-20
710 | 2024-12-23 | 8/3 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2024-12-23 | 2025-01-20
711 | 2024-12-23 | 41/1 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-23 | 2025-01-20
712 | 2024-12-23 | 39/4 | DA+3 | Sandy | Competed |  | 1 | 1 |  |  | 1 |  |  | 1 |  | 1 | 1 |  |  |  |  | 2024-12-23 | 2025-01-20
713 | 2024-12-24 | 40/8 | DA-1.5 | Sandy | Competed | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 2024-12-24 | 2025-01-21
714 | 2024-12-24 | 16/0 | DC2+0 | Sandy | Competed | [7 empty] | 1 | [8 empty] | 2024-12-24 | 2025-01-21
715 | 2024-12-24 | 39/3 | DA+1.5 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-24 | 2025-01-21
716 | 2024-12-24 | 41/1 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 |  | 1 | [5 empty] | 2024-12-24 | 2025-01-21
717 | 2024-12-25 | 40/8 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | 1 | [7 empty] | 2024-12-25 | 2025-01-22
718 | 2024-12-25 | 30/4 | DA+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-25 | 2025-01-22
719 | 2024-12-25 | 16/0 | DC2+0 | Sandy | Competed |  |  |  | 1 |  |  |  |  | 1 | [7 empty] | 2024-12-25 | 2025-01-22
720 | 2024-12-25 | 8/3 | DA+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2024-12-25 | 2025-01-22
721 | 2024-12-25 | 39/3 | DA+1.5 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-25 | 2025-01-22
722 | 2024-12-25 | 41/1 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 2024-12-25 | 2025-01-22
723 | 2024-12-26 | 40/5 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2024-12-26 | 2025-01-23
724 | 2024-12-26 | 7/6 | DA-1.5 | Sandy | Competed | 1 | [7 empty] | 1 |  |  | 1 |  |  |  |  | 2024-12-26 | 2025-01-23
725 | 2024-12-26 | 30/4 | DA+9 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-26 | 2025-01-23
726 | 2024-12-26 | 16/0 | DC2+0 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2024-12-26 | 2025-01-23
727 | 2024-12-26 | 8/3 | DA+9 | Sandy | Competed |  | 1 | [14 empty] | 2024-12-26 | 2025-01-23
728 | 2024-12-26 | 41/1 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2024-12-26 | 2025-01-23
729 | 2024-12-27 | 40/5 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-12-27 | 2025-01-24
730 | 2024-12-27 | 7/6 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2024-12-27 | 2025-01-24
731 | 2024-12-27 | 16/0 | DC2+0 | Sandy | Competed | 1 |  |  |  |  | 1 | [10 empty] | 2024-12-27 | 2025-01-24
732 | 2024-12-27 | 41/1 | DA+9 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-12-27 | 2025-01-24
733 | 2024-12-28 | 40/5 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-28 | 2025-01-25
734 | 2024-12-28 | 7/6 | DA-1.5 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2024-12-28 | 2025-01-25
735 | 2024-12-28 | 30/4 | DA+9 | Sandy | Competed |  |  |  | 1 | 1 | 1 | 1 | [9 empty] | 2024-12-28 | 2025-01-25
736 | 2024-12-28 | 16/0 | DC2+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2024-12-28 | 2025-01-25
737 | 2024-12-28 | 39/3 | DA+1.5 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2024-12-28 | 2025-01-25
738 | 2024-12-29 | 40/5 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-29 | 2025-01-26
739 | 2024-12-29 | 30/4 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2024-12-29 | 2025-01-26
740 | 2024-12-29 | 8/3 | DA+9 | Sandy | Competed | [7 empty] | 1 |  | 1 | [6 empty] | 2024-12-29 | 2025-01-26
741 | 2024-12-29 | 39/3 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2024-12-29 | 2025-01-26
742 | 2024-12-29 | 42/0 | DB2+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-29 | 2025-01-26
743 | 2024-12-29 | 40/4 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2024-12-29 | 2025-01-26
744 | 2024-12-30 | 40/4 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-30 | 2025-01-27
745 | 2024-12-30 | 7/6 | DA-1.5 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2024-12-30 | 2025-01-27
746 | 2024-12-30 | 30/5 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2024-12-30 | 2025-01-27
747 | 2024-12-30 | 15/12 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2024-12-30 | 2025-01-27
748 | 2024-12-30 | 42/0 | DB2+0 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2024-12-30 | 2025-01-27
749 | 2024-12-31 | 40/4 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2024-12-31 | 2025-01-28
750 | 2024-12-31 | 15/12 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2024-12-31 | 2025-01-28
751 | 2025-01-01 | 30/5 | DA+0 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-01 | 2025-01-29
752 | 2025-01-01 | 39/5 | DA+1.5 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-01 | 2025-01-29
753 | 2025-01-01 | 42/0 | DB2+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-01 | 2025-01-29
754 | 2025-01-02 | 30/5 | DA+0 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | [8 empty] | 2025-01-02 | 2025-01-30
755 | 2025-01-02 | 39/5 | DA+1.5 | Sandy | Competed |  | 1 | [8 empty] | 1 | [5 empty] | 2025-01-02 | 2025-01-30
756 | 2025-01-02 | 42/0 | DB2+0 | Sandy | Competed |  |  |  |  | 1 |  | 1 | [9 empty] | 2025-01-02 | 2025-01-30
757 | 2025-01-02 | 8/3 | DA+9 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2025-01-02 | 2025-01-30
758 | 2025-01-03 | 40/9 | DA+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-03 | 2025-01-31
759 | 2025-01-03 | 30/5 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | 2025-01-03 | 2025-01-31
760 | 2025-01-03 | 8/3 | DA+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-03 | 2025-01-31
761 | 2025-01-03 | 39/5 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2025-01-03 | 2025-01-31
762 | 2025-01-03 | 42/0 | DB2+0 | Sandy | Competed | [5 empty] | 1 |  | 1 | 1 | [7 empty] | 2025-01-03 | 2025-01-31
763 | 2025-01-04 | 40/9 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-04 | 2025-02-01
764 | 2025-01-04 | 8/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-01-04 | 2025-02-01
765 | 2025-01-04 | 30/6 | DA+6 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-04 | 2025-02-01
766 | 2025-01-04 | 8/3 | DA+9 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-01-04 | 2025-02-01
767 | 2025-01-04 | 39/5 | DA+1.5 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-04 | 2025-02-01
768 | 2025-01-05 | 40/9 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-05 | 2025-02-02
769 | 2025-01-05 | 30/6 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2025-01-05 | 2025-02-02
770 | 2025-01-05 | 22/0 | DC2+15 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-05 | 2025-02-02
771 | 2025-01-05 | 8/3 | DA+9 | Sandy | Competed |  |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 2025-01-05 | 2025-02-02
772 | 2025-01-05 | 39/5 | DA+1.5 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-05 | 2025-02-02
773 | 2025-01-05 | 42/1 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-01-05 | 2025-02-02
774 | 2025-01-06 | 40/10 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-06 | 2025-02-03
775 | 2025-01-06 | 8/0 | DB1+0 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | [8 empty] | 2025-01-06 | 2025-02-03
776 | 2025-01-06 | 30/6 | DA+6 | Sandy | Competed | [7 empty] | 1 |  | 1 | 1 | [5 empty] | 2025-01-06 | 2025-02-03
777 | 2025-01-06 | 22/0 | DC2+15 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2025-01-06 | 2025-02-03
778 | 2025-01-06 | 8/3 | DA+9 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2025-01-06 | 2025-02-03
779 | 2025-01-06 | 39/6 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-06 | 2025-02-03
780 | 2025-01-06 | 42/1 | DA+3 | Sandy | Competed |  |  |  |  | 1 |  |  | 1 | [8 empty] | 2025-01-06 | 2025-02-03
781 | 2025-01-07 | 40/10 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2025-01-07 | 2025-02-04
782 | 2025-01-07 | 8/0 | DB1+0 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2025-01-07 | 2025-02-04
783 | 2025-01-07 | 30/6 | DA+6 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-01-07 | 2025-02-04
784 | 2025-01-07 | 22/0 | DC2+15 | Sandy | Competed | 1 |  |  |  |  | 1 | [10 empty] | 2025-01-07 | 2025-02-04
785 | 2025-01-07 | 39/6 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-01-07 | 2025-02-04
786 | 2025-01-07 | 42/1 | DA+3 | Sandy | Competed | 1 |  |  |  |  | 1 |  |  | 1 | 1 | [6 empty] | 2025-01-07 | 2025-02-04
787 | 2025-01-08 | 40/10 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | [6 empty] | 2025-01-08 | 2025-02-05
788 | 2025-01-08 | 30/7 | DA-3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-01-08 | 2025-02-05
789 | 2025-01-08 | 39/6 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-01-08 | 2025-02-05
790 | 2025-01-08 | 42/1 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-01-08 | 2025-02-05
791 | 2025-01-09 | 40/10 | DA+3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-01-09 | 2025-02-06
792 | 2025-01-09 | 8/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-01-09 | 2025-02-06
793 | 2025-01-09 | 30/7 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | [5 empty] | 2025-01-09 | 2025-02-06
794 | 2025-01-09 | 39/6 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-09 | 2025-02-06
795 | 2025-01-09 | 40/11 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-09 | 2025-02-06
796 | 2025-01-10 | 40/11 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 2025-01-10 | 2025-02-07
797 | 2025-01-10 | 8/0 | DB1+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-01-10 | 2025-02-07
798 | 2025-01-10 | 30/7 | DA-3 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-01-10 | 2025-02-07
799 | 2025-01-10 | 42/2 | DA+9 | Sandy | Competed | 1 | [5 empty] | 1 | [9 empty] | 2025-01-10 | 2025-02-07
800 | 2025-01-11 | 40/11 | DA+9 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-01-11 | 2025-02-08
801 | 2025-01-11 | 30/8 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-11 | 2025-02-08
802 | 2025-01-12 | 40/11 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2025-01-12 | 2025-02-09
803 | 2025-01-12 | 8/0 | DB1+0 | Sandy | Competed | 1 | [15 empty] | 2025-01-12 | 2025-02-09
804 | 2025-01-12 | 30/8 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-12 | 2025-02-09
805 | 2025-01-12 | 8/4 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2025-01-12 | 2025-02-09
806 | 2025-01-12 | 42/2 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | [6 empty] | 2025-01-12 | 2025-02-09
807 | 2025-01-13 | 40/11 | DA+9 | Sandy | WIP | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2025-01-13 | 2025-02-10
808 | 2025-01-13 | 8/0 | DB1+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-01-13 | 2025-02-10
809 | 2025-01-13 | 30/8 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-13 | 2025-02-10
810 | 2025-01-13 | 8/4 | DA+6 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-01-13 | 2025-02-10
811 | 2025-01-13 | 42/2 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2025-01-13 | 2025-02-10
812 | 2025-01-13 | 22/0 | DC2+15 | Sandy | Competed |  | 1 |  |  |  |  | 1 | [9 empty] | 2025-01-13 | 2025-02-10
813 | 2025-01-13 | 39/7 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-13 | 2025-02-10
814 | 2025-01-14 | 40A/0 | DB1+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-01-14 | 2025-02-11
815 | 2025-01-14 | 22/0 | DC2+15 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 |  | 1 | [6 empty] | 2025-01-14 | 2025-02-11
816 | 2025-01-14 | 39/7 | DA+3 | Sandy | Competed |  | 1 |  | 1 | 1 | [11 empty] | 2025-01-14 | 2025-02-11
817 | 2025-01-15 | 40A/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | [6 empty] | 2025-01-15 | 2025-02-12
818 | 2025-01-15 | 30/9 | DA-3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-15 | 2025-02-12
819 | 2025-01-15 | 22/0 | DC2+15 | Sandy | Competed | [8 empty] | 1 |  | 1 | 1 |  |  |  |  | 2025-01-15 | 2025-02-12
820 | 2025-01-15 | 41/0 | DB1+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-01-15 | 2025-02-12
821 | 2025-01-16 | 40A/0 | DB1+9 | Sandy | Competed |  |  |  | 1 | [6 empty] | 1 | 1 |  |  |  |  | 2025-01-16 | 2025-02-13
822 | 2025-01-16 | 30/9 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | [6 empty] | 2025-01-16 | 2025-02-13
823 | 2025-01-16 | 23/0 | DB2+9 | Sandy | Competed | 1 | [15 empty] | 2025-01-16 | 2025-02-13
824 | 2025-01-16 | 39/7 | DA+3 | Sandy | Competed |  |  | 1 |  |  | 1 | 1 |  |  | 1 | [6 empty] | 2025-01-16 | 2025-02-13
825 | 2025-01-16 | 41/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-16 | 2025-02-13
826 | 2025-01-17 | 40A/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2025-01-17 | 2025-02-14
827 | 2025-01-17 | 10/0 | DB1+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-17 | 2025-02-14
828 | 2025-01-17 | 23/0 | DB2+9 | Sandy | Competed |  | 1 | [14 empty] | 2025-01-17 | 2025-02-14
829 | 2025-01-17 | 41/0 | DB1+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-17 | 2025-02-14
830 | 2025-01-17 | 30/9 | DA-3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-17 | 2025-02-14
831 | 2025-01-17 | 8/4 | DA+6 | Sandy | Competed |  | 1 | [5 empty] | 1 | [8 empty] | 2025-01-17 | 2025-02-14
832 | 2025-01-17 | 39/7 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-17 | 2025-02-14
833 | 2025-01-17 | 43/7 | DA+0 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-17 | 2025-02-14
834 | 2025-01-18 | 40A/0 | DB1+9 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2025-01-18 | 2025-02-15
835 | 2025-01-18 | 10/0 | DB1+6 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | [5 empty] | 2025-01-18 | 2025-02-15
836 | 2025-01-18 | 23/0 | DB2+9 | Sandy | Competed |  |  | 1 | 1 | [12 empty] | 2025-01-18 | 2025-02-15
837 | 2025-01-18 | 8/4 | DA+6 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2025-01-18 | 2025-02-15
838 | 2025-01-18 | 41/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-01-18 | 2025-02-15
839 | 2025-01-19 | 40A/0 | DB1+9 | Sandy | Competed | 1 | [15 empty] | 2025-01-19 | 2025-02-16
840 | 2025-01-19 | 10/0 | DB1+6 | Sandy | Competed |  |  |  | 1 | [7 empty] | 1 |  |  |  |  | 2025-01-19 | 2025-02-16
841 | 2025-01-19 | 30/10 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-01-19 | 2025-02-16
842 | 2025-01-19 | 23/0 | DB2+9 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2025-01-19 | 2025-02-16
843 | 2025-01-19 | 39/8 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-19 | 2025-02-16
844 | 2025-01-19 | 41/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-01-19 | 2025-02-16
845 | 2025-01-19 | 43/7 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2025-01-19 | 2025-02-16
846 | 2025-01-20 | 40A/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-01-20 | 2025-02-17
847 | 2025-01-20 | 10/0 | DB1+6 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2025-01-20 | 2025-02-17
848 | 2025-01-20 | 30/10 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2025-01-20 | 2025-02-17
849 | 2025-01-20 | 23/0 | DB2+9 | Sandy | Competed | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 2025-01-20 | 2025-02-17
850 | 2025-01-20 | 8/4 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-20 | 2025-02-17
851 | 2025-01-20 | 43/7 | DA+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-01-20 | 2025-02-17
852 | 2025-01-21 | 43/3 | DA-1.5 | Sandy | Competed |  |  |  | 1 | [5 empty] | 1 | [6 empty] | 2025-01-21 | 2025-02-18
853 | 2025-01-21 | 10/0 | DB1+6 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-01-21 | 2025-02-18
854 | 2025-01-21 | 30/10 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-01-21 | 2025-02-18
855 | 2025-01-21 | 23/0 | DB2+9 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-21 | 2025-02-18
856 | 2025-01-21 | 8/4 | DA+6 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2025-01-21 | 2025-02-18
857 | 2025-01-21 | 43/7 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-21 | 2025-02-18
858 | 2025-01-22 | 43/3 | DA-1.5 | Sandy | Competed | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-22 | 2025-02-19
859 | 2025-01-22 | 23/0 | DB2+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-01-22 | 2025-02-19
860 | 2025-01-22 | 39/8 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-01-22 | 2025-02-19
861 | 2025-01-22 | 43/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-01-22 | 2025-02-19
862 | 2025-01-23 | 43/3 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 | 1 | [7 empty] | 2025-01-23 | 2025-02-20
863 | 2025-01-23 | 15/1 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-23 | 2025-02-20
864 | 2025-01-23 | 31/0 | DB1+0 | Sandy | Competed | 1 | [15 empty] | 2025-01-23 | 2025-02-20
865 | 2025-01-23 | 8/4 | DA+6 | Sandy | Competed | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 2025-01-23 | 2025-02-20
866 | 2025-01-23 | 39/8 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-01-23 | 2025-02-20
867 | 2025-01-23 | 43/0 | DB1+0 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-23 | 2025-02-20
868 | 2025-01-23 | 43/8 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-01-23 | 2025-02-20
869 | 2025-01-24 | 15/1 | DA+6 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-01-24 | 2025-02-21
870 | 2025-01-24 | 31/0 | DB1+0 | Sandy | Competed |  | 1 | 1 | [6 empty] | 1 | [6 empty] | 2025-01-24 | 2025-02-21
871 | 2025-01-24 | 8/4 | DA+6 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-01-24 | 2025-02-21
872 | 2025-01-24 | 39/8 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-01-24 | 2025-02-21
873 | 2025-01-24 | 43/0 | DB1+0 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-01-24 | 2025-02-21
874 | 2025-01-24 | 43/8 | DA+9 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-24 | 2025-02-21
875 | 2025-01-25 | 43/4 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-25 | 2025-02-22
876 | 2025-01-25 | 15/1 | DA+6 | Sandy | Competed |  | 1 |  |  |  |  | 1 |  |  |  | 1 | [5 empty] | 2025-01-25 | 2025-02-22
877 | 2025-01-25 | 23A/0 | DB1+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-25 | 2025-02-22
878 | 2025-01-25 | 39/9 | DA+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-01-25 | 2025-02-22
879 | 2025-01-25 | 43/0 | DB1+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-01-25 | 2025-02-22
880 | 2025-01-25 | 43/8 | DA+9 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-01-25 | 2025-02-22
881 | 2025-01-27 | 43/4 | DA+0 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-27 | 2025-02-24
882 | 2025-01-27 | 23A/0 | DB1+9 | Sandy | Competed | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-01-27 | 2025-02-24
883 | 2025-01-27 | 31/0 | DB1+0 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-27 | 2025-02-24
884 | 2025-01-27 | 39/9 | DA+6 | Sandy | Competed | 1 | [9 empty] | 1 | [5 empty] | 2025-01-27 | 2025-02-24
885 | 2025-01-27 | 15/1 | DA+6 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  |  |  |  | 2025-01-27 | 2025-02-24
886 | 2025-01-28 | 43/4 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-28 | 2025-02-25
887 | 2025-01-28 | 23A/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-01-28 | 2025-02-25
888 | 2025-01-28 | 42/3 | #N/A | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-28 | 2025-02-25
889 | 2025-01-28 | 39/9 | DA+6 | Sandy | Competed |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2025-01-28 | 2025-02-25
890 | 2025-01-28 | 31/0 | DB1+0 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 2025-01-28 | 2025-02-25
891 | 2025-01-29 | 23A/0 | DB1+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-01-29 | 2025-02-26
892 | 2025-01-29 | 31/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-01-29 | 2025-02-26
893 | 2025-01-29 | 39/9 | DA+6 | Sandy | Competed |  |  | 1 | [13 empty] | 2025-01-29 | 2025-02-26
894 | 2025-01-29 | 42/3 | #N/A | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-01-29 | 2025-02-26
895 | 2025-01-29 | 32/1 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-01-29 | 2025-02-26
896 | 2025-01-30 | 43/6 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2025-01-30 | 2025-02-27
897 | 2025-01-30 | 23A/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-01-30 | 2025-02-27
898 | 2025-01-30 | 31/2 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 | [5 empty] | 1 | [6 empty] | 2025-01-30 | 2025-02-27
899 | 2025-01-30 | 8/11 | DA+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-01-30 | 2025-02-27
900 | 2025-01-30 | 39/9 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-01-30 | 2025-02-27
901 | 2025-01-30 | 42/3 | #N/A | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-01-30 | 2025-02-27
902 | 2025-01-30 | 32/1 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-30 | 2025-02-27
903 | 2025-01-31 | 43/6 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2025-01-31 | 2025-02-28
904 | 2025-01-31 | 31/2 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-01-31 | 2025-02-28
905 | 2025-01-31 | 8/11 | DA+9 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-01-31 | 2025-02-28
906 | 2025-01-31 | 39/9 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-31 | 2025-02-28
907 | 2025-01-31 | 42/3 | #N/A | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-31 | 2025-02-28
908 | 2025-01-31 | 44/0 | DB1+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-01-31 | 2025-02-28
909 | 2025-01-31 | 32/1 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-01-31 | 2025-02-28
910 | 2025-02-01 | 43/6 | DA+3 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-02-01 | 2025-03-01
911 | 2025-02-01 | 18/7 | DA+1.5 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-01 | 2025-03-01
912 | 2025-02-01 | 31/2 | DA+1.5 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-01 | 2025-03-01
913 | 2025-02-01 | 8/11 | DA+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-01 | 2025-03-01
914 | 2025-02-01 | 44/0 | DB1+6 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2025-02-01 | 2025-03-01
915 | 2025-02-01 | 13/0 | DD60+9 | Sandy | Competed | 1 | [15 empty] | 2025-02-01 | 2025-03-01
916 | 2025-02-01 | 32/2 | DA+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-02-01 | 2025-03-01
917 | 2025-02-02 | 43/6 | DA+3 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-02-02 | 2025-03-02
918 | 2025-02-02 | 18/7 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 | [5 empty] | 2025-02-02 | 2025-03-02
919 | 2025-02-02 | 44/0 | DB1+6 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 | [9 empty] | 2025-02-02 | 2025-03-02
920 | 2025-02-02 | 32/2 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2025-02-02 | 2025-03-02
921 | 2025-02-03 | 43/5 | #N/A | Sandy | Competed | 1 | [15 empty] | 2025-02-03 | 2025-03-03
922 | 2025-02-03 | 18/7 | DA+1.5 | Sandy | Competed |  | 1 |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  |  |  | 2025-02-03 | 2025-03-03
923 | 2025-02-03 | 31/4 | DA-1.5 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-02-03 | 2025-03-03
924 | 2025-02-03 | 43/1 | DA-1.5 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2025-02-03 | 2025-03-03
925 | 2025-02-03 | 44/0 | DB1+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 | [10 empty] | 2025-02-03 | 2025-03-03
926 | 2025-02-03 | 32/2 | DA+9 | Sandy | Competed | [7 empty] | 1 |  | 1 | [6 empty] | 2025-02-03 | 2025-03-03
927 | 2025-02-04 | 43/5 | #N/A | Sandy | Competed |  | 1 | [7 empty] | 1 | [6 empty] | 2025-02-04 | 2025-03-04
928 | 2025-02-04 | 18/7 | DA+1.5 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-02-04 | 2025-03-04
929 | 2025-02-04 | 8/11 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2025-02-04 | 2025-03-04
930 | 2025-02-04 | 39/10 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-02-04 | 2025-03-04
931 | 2025-02-04 | 43/1 | DA-1.5 | Sandy | Competed | [16 empty] | 2025-02-04 | 2025-03-04
932 | 2025-02-04 | 43/1 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2025-02-04 | 2025-03-04
933 | 2025-02-04 | 44/0 | DB1+6 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-04 | 2025-03-04
934 | 2025-02-04 | 13/0 | DD60+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-04 | 2025-03-04
935 | 2025-02-04 | 32/2 | DA+9 | Sandy | Competed | [8 empty] | 1 |  | 1 | 1 |  |  |  |  | 2025-02-04 | 2025-03-04
936 | 2025-02-05 | 43/5 | #N/A | Sandy | Competed |  |  | 1 |  |  |  | 1 | [9 empty] | 2025-02-05 | 2025-03-05
937 | 2025-02-05 | 13/0 | DD60+9 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-05 | 2025-03-05
938 | 2025-02-05 | 39/10 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-02-05 | 2025-03-05
939 | 2025-02-05 | 43/1 | DA-1.5 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-02-05 | 2025-03-05
940 | 2025-02-05 | 32/0 | DB2+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-05 | 2025-03-05
941 | 2025-02-06 | 13/0 | DD60+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-06 | 2025-03-06
942 | 2025-02-06 | 43/5 | #N/A | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2025-02-06 | 2025-03-06
943 | 2025-02-06 | 31/4 | DA-1.5 | Sandy | Competed |  | 1 | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  |  |  |  | 2025-02-06 | 2025-03-06
944 | 2025-02-06 | 39/10 | DA+3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-06 | 2025-03-06
945 | 2025-02-06 | 32/0 | DB2+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-02-06 | 2025-03-06
946 | 2025-02-07 | 43/5 | #N/A | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-02-07 | 2025-03-07
947 | 2025-02-07 | 31/4 | DA-1.5 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | 2025-02-07 | 2025-03-07
948 | 2025-02-07 | 39/10 | DA+3 | Sandy | Competed | [7 empty] | 1 | [8 empty] | 2025-02-07 | 2025-03-07
949 | 2025-02-07 | 43/2 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-02-07 | 2025-03-07
950 | 2025-02-07 | 32/0 | DB2+0 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-07 | 2025-03-07
951 | 2025-02-08 | 43/5 | #N/A | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-08 | 2025-03-08
952 | 2025-02-08 | 43/2 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-08 | 2025-03-08
953 | 2025-02-08 | 13/0 | DD60+9 | Sandy | Competed |  |  |  |  | 1 | [5 empty] | 1 | [5 empty] | 2025-02-08 | 2025-03-08
954 | 2025-02-08 | 32/0 | DB2+0 | Sandy | Competed | 1 | [6 empty] | 1 | 1 | [7 empty] | 2025-02-08 | 2025-03-08
955 | 2025-02-09 | 43/5 | #N/A | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-02-09 | 2025-03-09
956 | 2025-02-09 | 20/2 | DA-3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-02-09 | 2025-03-09
957 | 2025-02-09 | 31/5 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-02-09 | 2025-03-09
958 | 2025-02-09 | 13/0 | DD60+9 | Sandy | Competed | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 2025-02-09 | 2025-03-09
959 | 2025-02-09 | 32/0 | DB2+0 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-02-09 | 2025-03-09
960 | 2025-02-10 | 20/2 | DA-3 | Sandy | Competed |  | 1 |  |  |  |  | 1 |  |  |  | 1 | [5 empty] | 2025-02-10 | 2025-03-10
961 | 2025-02-10 | 31/5 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-10 | 2025-03-10
962 | 2025-02-10 | 8/11 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2025-02-10 | 2025-03-10
963 | 2025-02-10 | 39/10 | DA+3 | Sandy | Competed | [8 empty] | 1 | 1 | [6 empty] | 2025-02-10 | 2025-03-10
964 | 2025-02-10 | 13/0 | DD60+9 | Sandy | Competed |  | 1 | [5 empty] | 1 | [8 empty] | 2025-02-10 | 2025-03-10
965 | 2025-02-11 | 20/2 | DA-3 | Sandy | Competed |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 2025-02-11 | 2025-03-11
966 | 2025-02-11 | 8/11 | DA+9 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-11 | 2025-03-11
967 | 2025-02-11 | 39/10 | DA+3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-02-11 | 2025-03-11
968 | 2025-02-11 | 13/0 | DD60+9 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2025-02-11 | 2025-03-11
969 | 2025-02-11 | 32/7 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 | [9 empty] | 2025-02-11 | 2025-03-11
970 | 2025-02-12 | 20/2 | DA-3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | 2025-02-12 | 2025-03-12
971 | 2025-02-12 | 8/11 | DA+9 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2025-02-12 | 2025-03-12
972 | 2025-02-12 | 32/7 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-02-12 | 2025-03-12
973 | 2025-02-12 | 21/5 | DA+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-02-12 | 2025-03-12
974 | 2025-02-13 | 20/1 | DA-3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-13 | 2025-03-13
975 | 2025-02-13 | 29/0 | DC1+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-13 | 2025-03-13
976 | 2025-02-13 | 8/11 | DA+9 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-02-13 | 2025-03-13
977 | 2025-02-13 | 13A/0 | DB1+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-02-13 | 2025-03-13
978 | 2025-02-13 | 32/7 | DA+3 | Sandy | Competed |  | 1 | [7 empty] | 1 | [6 empty] | 2025-02-13 | 2025-03-13
979 | 2025-02-13 | 21/5 | DA+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-13 | 2025-03-13
980 | 2025-02-14 | 20/1 | DA-3 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-14 | 2025-03-14
981 | 2025-02-14 | 29/0 | DC1+0 | Sandy | Competed | 1 |  |  |  | 1 | 1 | [10 empty] | 2025-02-14 | 2025-03-14
982 | 2025-02-14 | 13A/0 | DB1+9 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2025-02-14 | 2025-03-14
983 | 2025-02-14 | 21/5 | DA+0 | Sandy | Competed |  | 1 | 1 | 1 | [6 empty] | 1 | 1 |  |  |  |  | 2025-02-14 | 2025-03-14
984 | 2025-02-14 | 9/6 | DA+3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-14 | 2025-03-14
985 | 2025-02-14 | 32A/0 | DB1+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-02-14 | 2025-03-14
986 | 2025-02-15 | 13A/0 | DB1+9 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-02-15 | 2025-03-15
987 | 2025-02-15 | 9/6 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | [6 empty] | 2025-02-15 | 2025-03-15
988 | 2025-02-15 | 32A/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | 1 | [6 empty] | 1 | 1 |  |  |  |  | 2025-02-15 | 2025-03-15
989 | 2025-02-16 | 20/1 | DA-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-02-16 | 2025-03-16
990 | 2025-02-16 | 29/0 | DC1+0 | Sandy | Competed |  | 1 | 1 | [6 empty] | 1 | [6 empty] | 2025-02-16 | 2025-03-16
991 | 2025-02-16 | 13A/0 | DB1+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-16 | 2025-03-16
992 | 2025-02-16 | 32/7 | DA+3 | Sandy | Competed | [16 empty] | 2025-02-16 | 2025-03-16
993 | 2025-02-16 | 21/5 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-02-16 | 2025-03-16
994 | 2025-02-16 | 9/6 | DA+3 | Sandy | Competed |  |  |  | 1 | [6 empty] | 1 | 1 |  |  |  |  | 2025-02-16 | 2025-03-16
995 | 2025-02-17 | 29/0 | DC1+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-17 | 2025-03-17
996 | 2025-02-17 | 13A/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2025-02-17 | 2025-03-17
997 | 2025-02-17 | 32/7 | DA+3 | Sandy | Competed |  |  | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-02-17 | 2025-03-17
998 | 2025-02-17 | 27/0 | DD60+35 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-17 | 2025-03-17
999 | 2025-02-17 | 32A/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2025-02-17 | 2025-03-17
1000 | 2025-02-18 | 9/9 | DA+0 | Sandy | Competed | 1 | [15 empty] | 2025-02-18 | 2025-03-18
1001 | 2025-02-18 | 13A/0 | DB1+9 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-02-18 | 2025-03-18
1002 | 2025-02-18 | 27/0 | DD60+35 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2025-02-18 | 2025-03-18
1003 | 2025-02-18 | 9/6 | DA+3 | Sandy | Competed | 1 |  |  |  | 1 | 1 | [10 empty] | 2025-02-18 | 2025-03-18
1004 | 2025-02-18 | 32A/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-18 | 2025-03-18
1005 | 2025-02-19 | 29/0 | DC1+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-02-19 | 2025-03-19
1006 | 2025-02-19 | 9/9 | DA+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-02-19 | 2025-03-19
1007 | 2025-02-19 | 39/11 | DA+6 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-19 | 2025-03-19
1008 | 2025-02-19 | 33/2 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-02-19 | 2025-03-19
1009 | 2025-02-19 | 9/6 | DA+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-02-19 | 2025-03-19
1010 | 2025-02-19 | 9/7 | DA+9 | Sandy | Competed | 1 | [15 empty] | 2025-02-19 | 2025-03-19
1011 | 2025-02-20 | 24/0 | DD60+18 | Sandy | Competed | 1 | [15 empty] | 2025-02-20 | 2025-03-20
1012 | 2025-02-20 | 9/9 | DA+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-20 | 2025-03-20
1013 | 2025-02-20 | 39/11 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-20 | 2025-03-20
1014 | 2025-02-20 | 33/2 | DA+9 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-20 | 2025-03-20
1015 | 2025-02-20 | 27/0 | DD60+35 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-20 | 2025-03-20
1016 | 2025-02-20 | 21/4 | DA+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-20 | 2025-03-20
1017 | 2025-02-20 | 9/7 | DA+9 | Sandy | Competed |  | 1 | 1 | 1 | [12 empty] | 2025-02-20 | 2025-03-20
1018 | 2025-02-20 | 28/0 | DC2-3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-20 | 2025-03-20
1019 | 2025-02-21 | 24/0 | DD60+18 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-02-21 | 2025-03-21
1020 | 2025-02-21 | 9/9 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-21 | 2025-03-21
1021 | 2025-02-21 | 32A/1 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-02-21 | 2025-03-21
1022 | 2025-02-21 | 27/0 | DD60+35 | Sandy | Competed | 1 | [15 empty] | 2025-02-21 | 2025-03-21
1023 | 2025-02-21 | 21/4 | DA+0 | Sandy | Competed |  |  | 1 |  | 1 | 1 | 1 |  |  | 1 | [6 empty] | 2025-02-21 | 2025-03-21
1024 | 2025-02-21 | 9/7 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 | [9 empty] | 2025-02-21 | 2025-03-21
1025 | 2025-02-21 | 28/0 | DC2-3 | Sandy | Competed | 1 | [15 empty] | 2025-02-21 | 2025-03-21
1026 | 2025-02-22 | 24/0 | DD60+18 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-22 | 2025-03-22
1027 | 2025-02-22 | 9/9 | DA+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-22 | 2025-03-22
1028 | 2025-02-22 | 39/11 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2025-02-22 | 2025-03-22
1029 | 2025-02-22 | 32A/1 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-22 | 2025-03-22
1030 | 2025-02-22 | 27/0 | DD60+35 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-22 | 2025-03-22
1031 | 2025-02-22 | 21/4 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-02-22 | 2025-03-22
1032 | 2025-02-22 | 9/7 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-22 | 2025-03-22
1033 | 2025-02-22 | 28/0 | DC2-3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-02-22 | 2025-03-22
1034 | 2025-02-23 | 24/0 | DD60+18 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-02-23 | 2025-03-23
1035 | 2025-02-23 | 29/0 | DC1+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-23 | 2025-03-23
1036 | 2025-02-23 | 9/9 | DA+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-02-23 | 2025-03-23
1037 | 2025-02-23 | 39/11 | DA+6 | Sandy | Competed |  | 1 |  | 1 | [12 empty] | 2025-02-23 | 2025-03-23
1038 | 2025-02-23 | 15/0 | DD60+25 | Sandy | Competed | 1 | [15 empty] | 2025-02-23 | 2025-03-23
1039 | 2025-02-23 | 27/0 | DD60+35 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-02-23 | 2025-03-23
1040 | 2025-02-24 | 24/0 | DD60+18 | Sandy | Competed | [6 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 2025-02-24 | 2025-03-24
1041 | 2025-02-24 | 9/9 | DA+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-24 | 2025-03-24
1042 | 2025-02-24 | 39/11 | DA+6 | Sandy | Competed |  |  | 1 |  | 1 | 1 | [10 empty] | 2025-02-24 | 2025-03-24
1043 | 2025-02-24 | 15/0 | DD60+25 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-02-24 | 2025-03-24
1044 | 2025-02-24 | 9/7 | DA+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-24 | 2025-03-24
1045 | 2025-02-24 | 28/0 | DC2-3 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-02-24 | 2025-03-24
1046 | 2025-02-25 | 24/0 | DD60+18 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-25 | 2025-03-25
1047 | 2025-02-25 | 9/9 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-02-25 | 2025-03-25
1048 | 2025-02-25 | 15/0 | DD60+25 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-02-25 | 2025-03-25
1049 | 2025-02-25 | 27/0 | DD60+35 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-02-25 | 2025-03-25
1050 | 2025-02-25 | 9/8 | DA+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-25 | 2025-03-25
1051 | 2025-02-25 | 9/7 | DA+9 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-02-25 | 2025-03-25
1052 | 2025-02-26 | 24/0 | DD60+18 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-26 | 2025-03-26
1053 | 2025-02-26 | 44/1 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-02-26 | 2025-03-26
1054 | 2025-02-26 | 9/8 | DA+0 | Sandy | Competed | 1 | [15 empty] | 2025-02-26 | 2025-03-26
1055 | 2025-02-26 | 9/7 | DA+9 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-02-26 | 2025-03-26
1056 | 2025-02-26 | 28/0 | DC2-3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-26 | 2025-03-26
1057 | 2025-02-27 | 15/0 | DD60+25 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-02-27 | 2025-03-27
1058 | 2025-02-27 | 24/0 | DD60+18 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-02-27 | 2025-03-27
1059 | 2025-02-27 | 26/0 | DD60+35 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-02-27 | 2025-03-27
1060 | 2025-02-27 | 33/0 | DB1+9 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-02-27 | 2025-03-27
1061 | 2025-02-27 | 44/1 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-02-27 | 2025-03-27
1062 | 2025-02-27 | 33/0 | DB1+9 | Sandy | Competed | 1 | [5 empty] | 1 |  |  |  | 1 | 0.5 |  |  |  |  | 2025-02-27 | 2025-03-27
1063 | 2025-02-28 | 44/1 | DA+3 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-02-28 | 2025-03-28
1064 | 2025-02-28 | 26/0 | DD60+35 | Sandy | Competed |  |  |  |  | 1 |  | 1 | [9 empty] | 2025-02-28 | 2025-03-28
1065 | 2025-02-28 | 9/8 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-02-28 | 2025-03-28
1066 | 2025-03-01 | 40/0 | DB1+6 | Sandy | Competed | 1 | [15 empty] | 2025-03-01 | 2025-03-29
1067 | 2025-03-01 | 33/0 | DB1+9 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 0.5 | [7 empty] | 2025-03-01 | 2025-03-29
1068 | 2025-03-01 | 44/1 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-01 | 2025-03-29
1069 | 2025-03-01 | 26/0 | DD60+35 | Sandy | Competed | 1 |  |  |  |  | 1 | [10 empty] | 2025-03-01 | 2025-03-29
1070 | 2025-03-01 | 15/0 | DD60+25 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-03-01 | 2025-03-29
1071 | 2025-03-02 | 40/0 | DB1+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-03-02 | 2025-03-30
1072 | 2025-03-02 | 33/0 | DB1+9 | Sandy | Competed |  | 1 | 0.5 | [13 empty] | 2025-03-02 | 2025-03-30
1073 | 2025-03-02 | 26/0 | DD60+35 | Sandy | Competed |  | 1 | [5 empty] | 1 | [8 empty] | 2025-03-02 | 2025-03-30
1074 | 2025-03-02 | 15/0 | DD60+25 | Sandy | Competed |  |  |  |  | 1 | [11 empty] | 2025-03-02 | 2025-03-30
1075 | 2025-03-02 | 9/8 | DA+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-03-02 | 2025-03-30
1076 | 2025-03-03 | 40/0 | DB1+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-03-03 | 2025-03-31
1077 | 2025-03-03 | 33/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 0.5 | [10 empty] | 2025-03-03 | 2025-03-31
1078 | 2025-03-03 | 26/0 | DD60+35 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | 1 | [6 empty] | 2025-03-03 | 2025-03-31
1079 | 2025-03-03 | 9/8 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-03-03 | 2025-03-31
1080 | 2025-03-04 | 40/0 | DB1+6 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-03-04 | 2025-04-01
1081 | 2025-03-04 | 33/1 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-03-04 | 2025-04-01
1082 | 2025-03-04 | 44/2 | DA+3 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2025-03-04 | 2025-04-01
1083 | 2025-03-04 | 26/0 | DD60+35 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-03-04 | 2025-04-01
1084 | 2025-03-04 | 15/0 | DD60+25 | Sandy | Competed | [5 empty] | 1 |  |  |  | 1 | [6 empty] | 2025-03-04 | 2025-04-01
1085 | 2025-03-04 | 9/8 | DA+0 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-03-04 | 2025-04-01
1086 | 2025-03-05 | 40/0 | DB1+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-03-05 | 2025-04-02
1087 | 2025-03-05 | 33/1 | DA+9 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 0.5 |  | 1 | 0.5 |  |  |  |  | 2025-03-05 | 2025-04-02
1088 | 2025-03-05 | 44/2 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-05 | 2025-04-02
1089 | 2025-03-05 | 26/0 | DD60+35 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-03-05 | 2025-04-02
1090 | 2025-03-05 | 15/0 | DD60+25 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-03-05 | 2025-04-02
1091 | 2025-03-05 | 9/8 | DA+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-03-05 | 2025-04-02
1092 | 2025-03-05 | 25/0 | DD60+18 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-03-05 | 2025-04-02
1093 | 2025-03-06 | 40/0 | DB1+6 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-03-06 | 2025-04-03
1094 | 2025-03-06 | 33/1 | DA+9 | Sandy | Competed |  | 1 | 0.5 |  | 1 | 0.5 | [10 empty] | 2025-03-06 | 2025-04-03
1095 | 2025-03-06 | 44/2 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-03-06 | 2025-04-03
1096 | 2025-03-06 | 15/0 | DD60+25 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-03-06 | 2025-04-03
1097 | 2025-03-06 | 25/0 | DD60+18 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | [5 empty] | 2025-03-06 | 2025-04-03
1098 | 2025-03-07 | 40/0 | DB1+6 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-03-07 | 2025-04-04
1099 | 2025-03-07 | 44/3 | DA+3 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-03-07 | 2025-04-04
1100 | 2025-03-07 | 25/0 | DD60+18 | Sandy | Competed |  |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2025-03-07 | 2025-04-04
1101 | 2025-03-08 | 40/0 | DB1+6 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-03-08 | 2025-04-05
1102 | 2025-03-08 | 32/6 | DA+9 | Sandy | WIP | 1 | [8 empty] | 1 | [6 empty] | 2025-03-08 | 2025-04-05
1103 | 2025-03-08 | 44/3 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-03-08 | 2025-04-05
1104 | 2025-03-08 | 25/0 | DD60+18 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-03-08 | 2025-04-05
1105 | 2025-03-09 | 32/6 | DA+9 | Sandy | WIP |  | 1 | 0.5 | 1 |  |  | 1 |  |  |  | 1 | 0.5 |  |  |  |  | 2025-03-09 | 2025-04-06
1106 | 2025-03-09 | 44/3 | DA+3 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-03-09 | 2025-04-06
1107 | 2025-03-09 | 5/0 | DB1+6 | Sandy | Competed | 1 | [15 empty] | 2025-03-09 | 2025-04-06
1108 | 2025-03-10 | 32/6 | DA+9 | Sandy | WIP |  |  |  |  | 1 | 0.5 |  | 1 | 0.5 | [7 empty] | 2025-03-10 | 2025-04-07
1109 | 2025-03-10 | 5/0 | DB1+6 | Sandy | Competed |  | 1 |  |  |  |  | 1 | [9 empty] | 2025-03-10 | 2025-04-07
1110 | 2025-03-11 | 32/5 | DA+9 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-03-11 | 2025-04-08
1111 | 2025-03-11 | 5/0 | DB1+6 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 | [8 empty] | 2025-03-11 | 2025-04-08
1112 | 2025-03-11 | 44/4 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-03-11 | 2025-04-08
1113 | 2025-03-12 | 32/5 | DA+9 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 0.5 |  | 1 | 0.5 |  |  |  |  | 2025-03-12 | 2025-04-09
1114 | 2025-03-12 | 44/3 | DA+3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-03-12 | 2025-04-09
1115 | 2025-03-12 | 5/0 | DB1+6 | Sandy | Competed | [8 empty] | 1 | 1 | [6 empty] | 2025-03-12 | 2025-04-09
1116 | 2025-03-12 | 44/4 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-12 | 2025-04-09
1117 | 2025-03-13 | 32/5 | DA+9 | Sandy | Competed | 1 | 1 | 0.5 | [13 empty] | 2025-03-13 | 2025-04-10
1118 | 2025-03-13 | 44/3 | DA+3 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-03-13 | 2025-04-10
1119 | 2025-03-13 | 5/0 | DB1+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-03-13 | 2025-04-10
1120 | 2025-03-15 | 32/5 | DA+9 | Sandy | Competed |  |  |  |  | 1 | 0.5 | [10 empty] | 2025-03-15 | 2025-04-12
1121 | 2025-03-15 | 5/0 | DB1+6 | Sandy | Competed |  |  |  |  | 1 | [5 empty] | 1 | 1 |  |  |  |  | 2025-03-15 | 2025-04-12
1122 | 2025-03-16 | 44/5 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-03-16 | 2025-04-13
1123 | 2025-03-16 | 5/0 | DB1+6 | Sandy | Competed | [5 empty] | 1 | [10 empty] | 2025-03-16 | 2025-04-13
1124 | 2025-03-17 | 44/5 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-17 | 2025-04-14
1125 | 2025-03-17 | 5/1 | DA+6 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-03-17 | 2025-04-14
1126 | 2025-03-18 | 5/1 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-03-18 | 2025-04-15
1127 | 2025-03-19 | 5/1 | DA+6 | Sandy | Competed | 1 | [15 empty] | 2025-03-19 | 2025-04-16
1128 | 2025-03-19 | 2A/2 | DA+3 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-03-19 | 2025-04-16
1129 | 2025-03-20 | 40/1 | DA+9 | Sandy | WIP | 1 | [15 empty] | 2025-03-20 | 2025-04-17
1130 | 2025-03-20 | 5/1 | DA+6 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-03-20 | 2025-04-17
1131 | 2025-03-20 | 2A/2 | DA+3 | Sandy | Competed |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | [5 empty] | 2025-03-20 | 2025-04-17
1132 | 2025-03-21 | 40/1 | DA+9 | Sandy | WIP |  | 1 |  | 1 | [12 empty] | 2025-03-21 | 2025-04-18
1133 | 2025-03-21 | 2A/2 | DA+3 | Sandy | Competed |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 2025-03-21 | 2025-04-18
1134 | 2025-03-21 | 3B/2 | DA+9 | Sandy | WIP | 1 |  |  | 1 | [12 empty] | 2025-03-21 | 2025-04-18
1135 | 2025-03-22 | 40/1 | DA+9 | Sandy | WIP |  |  | 1 |  | 1 | [11 empty] | 2025-03-22 | 2025-04-19
1136 | 2025-03-22 | 5/1 | DA+6 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-03-22 | 2025-04-19
1137 | 2025-03-22 | 2A/3 | DA+3 | Sandy | WIP | 1 |  |  | 1 | [12 empty] | 2025-03-22 | 2025-04-19
1138 | 2025-03-22 | 3B/2 | DA+9 | Sandy | WIP |  | 1 |  |  | 1 |  | 1 |  |  | 1 | [6 empty] | 2025-03-22 | 2025-04-19
1139 | 2025-03-23 | 40/1 | DA+9 | Sandy | WIP | [9 empty] | 1 | [6 empty] | 2025-03-23 | 2025-04-20
1140 | 2025-03-23 | 5/1 | DA+6 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-03-23 | 2025-04-20
1141 | 2025-03-23 | 2a/2 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | 2025-03-23 | 2025-04-20
1142 | 2025-03-23 | 3B/2 | DA+9 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-23 | 2025-04-20
1143 | 2025-03-24 | 40/1 | DA+9 | Sandy | WIP | [5 empty] | 1 |  |  |  |  | 1 | [5 empty] | 2025-03-24 | 2025-04-21
1144 | 2025-03-24 | 3b/1 | DA+3 | Sandy | WIP | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2025-03-24 | 2025-04-21
1145 | 2025-03-24 | 2A/3 | DA+3 | Sandy | Competed |  | 1 |  |  |  |  | 1 | [9 empty] | 2025-03-24 | 2025-04-21
1146 | 2025-03-25 | 3B/1 | DA+3 | Sandy | WIP |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-25 | 2025-04-22
1147 | 2025-03-25 | 2A/3 | DA+3 | Sandy | Competed |  |  | 1 |  | 1 | 1 |  | 1 | [8 empty] | 2025-03-25 | 2025-04-22
1148 | 2025-03-26 | 3B/1 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-03-26 | 2025-04-23
1149 | 2025-03-26 | 2A/3 | DA+3 | Sandy | Competed | [8 empty] | 1 | 1 | 1 | [5 empty] | 2025-03-26 | 2025-04-23
1150 | 2025-03-27 | 40/1 | DA+9 | Sandy | WIP |  |  | 1 | [13 empty] | 2025-03-27 | 2025-04-24
1151 | 2025-03-27 | 5A/0 | DB1+12 | Sandy | WIP | 1 |  |  | 1 | [12 empty] | 2025-03-27 | 2025-04-24
1152 | 2025-03-27 | 2A/3 | DA+3 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-03-27 | 2025-04-24
1153 | 2025-03-28 | 40/1 | DA+9 | Sandy | WIP | [6 empty] | 1 | [9 empty] | 2025-03-28 | 2025-04-25
1154 | 2025-03-28 | 5A/0 | DB1+12 | Sandy | WIP |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-03-28 | 2025-04-25
1155 | 2025-03-28 | 3B/0 | DB1+9 | Sandy | WIP |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-03-28 | 2025-04-25
1156 | 2025-03-28 | 2A/4 | DA+3 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2025-03-28 | 2025-04-25
1157 | 2025-03-29 | 40/1 | DA+9 | Sandy | WIP | [5 empty] | 1 |  | 1 | 1 | [7 empty] | 2025-03-29 | 2025-04-26
1158 | 2025-03-29 | 5A/0 | DB1+12 | Sandy | WIP | [9 empty] | 1 | [6 empty] | 2025-03-29 | 2025-04-26
1159 | 2025-03-29 | 3B/0 | DB1+9 | Sandy | WIP | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  |  |  | 2025-03-29 | 2025-04-26
1160 | 2025-03-29 | 2A/4 | DA+3 | Sandy | Competed |  |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-03-29 | 2025-04-26
1161 | 2025-03-30 | 40/1 | DA+9 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-03-30 | 2025-04-27
1162 | 2025-03-30 | 3B/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-03-30 | 2025-04-27
1163 | 2025-03-30 | 2A/4 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-03-30 | 2025-04-27
1164 | 2025-03-31 | 5A/0 | DB1+12 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | [5 empty] | 2025-03-31 | 2025-04-28
1165 | 2025-04-01 | 5A/0 | DB1+12 | Sandy | Competed | [7 empty] | 1 | 1 |  |  | 1 |  |  |  |  | 2025-04-01 | 2025-04-29
1166 | 2025-04-01 | 3A/6 | DA+0 | Sandy | WIP | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-29
1167 | 2025-04-01 | 2A/5 | DA+3 | Sandy | WIP | 1 |  |  | 1 | [12 empty] | 2025-04-01 | 2025-04-29
1168 | 2025-04-02 | 3A/6 | DA+0 | Sandy | WIP |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [5 empty] | 2025-04-02 | 2025-04-30
1169 | 2025-04-02 | 2A/5 | DA+3 | Sandy | WIP |  | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | [6 empty] | 2025-04-02 | 2025-04-30
1170 | 2025-04-03 | 3A/6 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 2025-04-03 | 2025-05-01
1171 | 2025-04-03 | 2A/5 | DA+3 | Sandy | WIP | [7 empty] | 1 |  |  | 1 | [5 empty] | 2025-04-03 | 2025-05-01
1172 | 2025-04-04 | 35/3 | DA-3 | Sandy | WIP | [9 empty] | 1 | [6 empty] | 2025-04-04 | 2025-05-02
1173 | 2025-04-05 | 35/3 | DA-3 | Sandy | WIP | 1 | [9 empty] | 1 | [5 empty] | 2025-04-05 | 2025-05-03
1174 | 2025-04-05 | 14/0 | DD60+18 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-04-05 | 2025-05-03
1175 | 2025-04-05 | 2A/5 | DA+3 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-04-05 | 2025-05-03
1176 | 2025-04-05 | 3A/5 | DA+3 | Sandy | WIP | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-04-05 | 2025-05-03
1177 | 2025-04-06 | 35/3 | DA-3 | Sandy | WIP |  | 1 | [14 empty] | 2025-04-06 | 2025-05-04
1178 | 2025-04-06 | 3A/1 | DA+3 | Sandy | Competed | 1 | [5 empty] | 1 |  |  | 1 | [6 empty] | 2025-04-06 | 2025-05-04
1179 | 2025-04-06 | 14/0 | DD60+18 | Sandy | Competed | [11 empty] | 0.5 |  |  |  |  | 2025-04-06 | 2025-05-04
1180 | 2025-04-06 | 3A/5 | DA+3 | Sandy | WIP | 1 |  |  | 1 | [12 empty] | 2025-04-06 | 2025-05-04
1181 | 2025-04-07 | 3A/1 | DA+3 | Sandy | Competed |  | 1 | 1 | 1 |  |  |  | 1 | 1 | [7 empty] | 2025-04-07 | 2025-05-05
1182 | 2025-04-07 | 14/0 | DD60+18 | Sandy | Competed | [6 empty] | 1 |  |  |  |  | 0.5 |  |  |  |  | 2025-04-07 | 2025-05-05
1183 | 2025-04-07 | 3A/5 | DA+3 | Sandy | WIP |  | 1 |  |  | 1 |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-07 | 2025-05-05
1184 | 2025-04-08 | 35/3 | DA-3 | Sandy | Competed |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 2025-04-08 | 2025-05-06
1185 | 2025-04-08 | 3A/1 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2025-04-08 | 2025-05-06
1186 | 2025-04-08 | 3A/5 | DA+3 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-04-08 | 2025-05-06
1187 | 2025-04-08 | 32/5 | DA+9 (RC) | Sandy | Competed |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  |  |  | 2025-04-08 | 2025-05-06
1188 | 2025-04-09 | 3A/4 | DA+0 | Sandy | WIP | 1 | 1 |  | 1 | 1 |  | 1 |  |  | 1 | [6 empty] | 2025-04-09 | 2025-05-07
1189 | 2025-04-10 | 14/0 | DD60+18 | Sandy | Competed | [8 empty] | 0.5 | [7 empty] | 2025-04-10 | 2025-05-08
1190 | 2025-04-10 | 3A/4 | DA+0 | Sandy | Competed |  |  | 1 |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-10 | 2025-05-08
1191 | 2025-04-11 | 35/3 | DA-3 | Sandy | Competed |  |  |  | 1 | 1 |  |  | 1 | [8 empty] | 2025-04-11 | 2025-05-09
1192 | 2025-04-11 | 3A/0 | DD45+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-04-11 | 2025-05-09
1193 | 2025-04-11 | 14/0 | DD60+18 | Sandy | Competed | 1 | [15 empty] | 2025-04-11 | 2025-05-09
1194 | 2025-04-11 | 21/3 | DA+6 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-04-11 | 2025-05-09
1195 | 2025-04-11 | 3A/3 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-04-11 | 2025-05-09
1196 | 2025-04-11 | 32/6 | DA+9 | Sandy | Competed |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  |  |  | 2025-04-11 | 2025-05-09
1197 | 2025-04-12 | 35/3 | DA-3 | Sandy | Competed | [5 empty] | 1 |  |  | 1 | [7 empty] | 2025-04-12 | 2025-05-10
1198 | 2025-04-12 | 21/3 | DA+6 | Sandy | Competed |  | 1 |  |  | 1 |  | 1 | [9 empty] | 2025-04-12 | 2025-05-10
1199 | 2025-04-12 | 3A/3 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-12 | 2025-05-10
1200 | 2025-04-12 | 35/2 | DA+6 | Sandy | WIP |  |  |  | 1 | [12 empty] | 2025-04-12 | 2025-05-10
1201 | 2025-04-13 | 35/2 | DA+6 | Sandy | WIP | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [6 empty] | 2025-04-13 | 2025-05-11
1202 | 2025-04-13 | 3A/0 | DD45+3 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-04-13 | 2025-05-11
1203 | 2025-04-13 | 14/0 | DD60+18 | Sandy | Competed |  |  | 0.5 | 1 | [12 empty] | 2025-04-13 | 2025-05-11
1204 | 2025-04-14 | 35/2 | DA+6 | Sandy | Competed |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-04-14 | 2025-05-12
1205 | 2025-04-14 | 14/0 | DD60+18 | Sandy | Competed | [5 empty] | 0.5 | [10 empty] | 2025-04-14 | 2025-05-12
1206 | 2025-04-14 | 3A/2 | DA+3 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-04-14 | 2025-05-12
1207 | 2025-04-14 | 33/1 | DA+9 | Sandy | Competed |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  |  |  | 2025-04-14 | 2025-05-12
1208 | 2025-04-15 | 35/2 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 | [7 empty] | 2025-04-15 | 2025-05-13
1209 | 2025-04-15 | 3A/0 | DD45+3 | Sandy | Competed | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 2025-04-15 | 2025-05-13
1210 | 2025-04-15 | 14/0 | DD60+18 | Sandy | Competed |  |  | 0.5 | [5 empty] | 0.5 | [7 empty] | 2025-04-15 | 2025-05-13
1211 | 2025-04-15 | 3A/2 | DA+3 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-15 | 2025-05-13
1212 | 2025-04-16 | 3A/0 | DD45+3 | Sandy | Competed | 1 | [15 empty] | 2025-04-16 | 2025-05-14
1213 | 2025-04-16 | 14/0 | DD60+18 | Sandy | Competed | [5 empty] | 0.5 | [10 empty] | 2025-04-16 | 2025-05-14
1214 | 2025-04-17 | 3A/0 | DD45+3 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-04-17 | 2025-05-15
1215 | 2025-04-17 | 33/0 | DB1+9 | Sandy | Competed |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  |  |  |  | 2025-04-17 | 2025-05-15
1216 | 2025-04-18 | 3A/0 | DD45+3 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2025-04-18 | 2025-05-16
1217 | 2025-04-18 | 3B/3 | DA+6 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-04-18 | 2025-05-16
1218 | 2025-04-19 | 3B/3 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-19 | 2025-05-17
1219 | 2025-04-20 | 8A/0 | DB1+12 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-04-20 | 2025-05-18
1220 | 2025-04-20 | 21/3 | DA+6 | Sandy | Competed |  |  | 1 |  |  | 1 |  |  |  | 1 | [6 empty] | 2025-04-20 | 2025-05-18
1221 | 2025-04-20 | 21/2 | DA+6 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-04-20 | 2025-05-18
1222 | 2025-04-21 | 2A/6 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-04-21 | 2025-05-19
1223 | 2025-04-21 | 8A/0 | DB1+12 | Sandy | Competed | [7 empty] | 1 | 1 | 1 | [6 empty] | 2025-04-21 | 2025-05-19
1224 | 2025-04-21 | 21/3 | DA+6 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | [5 empty] | 2025-04-21 | 2025-05-19
1225 | 2025-04-22 | 2A/6 | DA+6 | Sandy | Competed |  | 1 | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-04-22 | 2025-05-20
1226 | 2025-04-22 | 21/3 | DA+6 | Sandy | Competed | [8 empty] | 1 |  |  | 1 |  |  |  |  | 2025-04-22 | 2025-05-20
1227 | 2025-04-22 | 21/2 | DA+6 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-04-22 | 2025-05-20
1228 | 2025-04-22 | 9/0 | DB1+12 | Sandy | WIP | 1 | [15 empty] | 2025-04-22 | 2025-05-20
1229 | 2025-04-22 | 4/0 | DB2+9 | Sandy | Competed | 1 |  |  | 1 | [12 empty] | 2025-04-22 | 2025-05-20
1230 | 2025-04-23 | 2A/6 | DA+6 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-04-23 | 2025-05-21
1231 | 2025-04-23 | 8A/0 | DB1+12 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2025-04-23 | 2025-05-21
1232 | 2025-04-23 | 21/2 | DA+6 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | 1 | [9 empty] | 2025-04-23 | 2025-05-21
1233 | 2025-04-23 | 4/0 | DB2+9 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2025-04-23 | 2025-05-21
1234 | 2025-04-24 | 4/0 | DB2+9 | Sandy | Competed |  |  | 1 |  |  | 1 | 1 |  |  | 1 | [6 empty] | 2025-04-24 | 2025-05-22
1235 | 2025-04-24 | 8A/0 | DB1+12 | Sandy | Competed |  | 1 | 1 | 1 | [12 empty] | 2025-04-24 | 2025-05-22
1236 | 2025-04-24 | 21/2 | DA+6 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-24 | 2025-05-22
1237 | 2025-04-25 | 8A/0 | DB1+12 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-04-25 | 2025-05-23
1238 | 2025-04-25 | 4/0 | DB2+9 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-04-25 | 2025-05-23
1239 | 2025-04-26 | 21/1 | DA+0 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-04-26 | 2025-05-24
1240 | 2025-04-27 | 21/1 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | 1 | [6 empty] | 2025-04-27 | 2025-05-25
1241 | 2025-04-28 | 21/1 | DA+0 | Sandy | Competed | 1 | [9 empty] | 1 | 1 |  |  |  |  | 2025-04-28 | 2025-05-26
1242 | 2025-04-29 | 21/1 | DA+0 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-04-29 | 2025-05-27
1243 | 2025-04-29 | 9/0 | DB1+12 | Sandy | WIP |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [6 empty] | 2025-04-29 | 2025-05-27
1244 | 2025-04-30 | 35/10 | DA+3 | Sandy | Competed | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 2025-04-30 | 2025-05-28
1245 | 2025-05-01 | 9/0 | DB1+12 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-05-01 | 2025-05-29
1246 | 2025-05-01 | 35/10 | DA+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-05-01 | 2025-05-29
1247 | 2025-05-01 | 45/0 | DB1+9 | Sandy | Competed | 1 | [15 empty] | 2025-05-01 | 2025-05-29
1248 | 2025-05-02 | 35/10 | DA+3 | Sandy | Competed | 1 | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-05-02 | 2025-05-30
1249 | 2025-05-02 | 45/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | 1 | [12 empty] | 2025-05-02 | 2025-05-30
1250 | 2025-05-02 | 9/0 | DB1+12 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-05-02 | 2025-05-30
1251 | 2025-05-03 | 45/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 |  |  | 1 | [6 empty] | 2025-05-03 | 2025-05-31
1252 | 2025-05-03 | 9/0 | DB1+12 | Sandy | Competed |  |  |  |  | 1 | 1 | [10 empty] | 2025-05-03 | 2025-05-31
1253 | 2025-05-04 | 20/6 | DA-3 | Sandy | Competed | 1 | [15 empty] | 2025-05-04 | 2025-06-01
1254 | 2025-05-04 | 45/0 | DB1+9 | Sandy | Competed | [7 empty] | 1 |  |  | 1 | 1 |  |  |  |  | 2025-05-04 | 2025-06-01
1255 | 2025-05-05 | 20/6 | DA-3 | Sandy | Competed |  | 1 |  |  |  |  | 1 |  |  | 1 | [6 empty] | 2025-05-05 | 2025-06-02
1256 | 2025-05-05 | 45/0 | DB1+9 | Sandy | Competed | [8 empty] | 1 | [7 empty] | 2025-05-05 | 2025-06-02
1257 | 2025-05-05 | 46/0 | DB1+12 | Sandy | Competed | [6 empty] | 1 |  |  | 1 | [6 empty] | 2025-05-05 | 2025-06-02
1258 | 2025-05-06 | 46/0 | DB1+12 | Sandy | Competed | 1 |  |  | 1 |  |  |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-05-06 | 2025-06-03
1259 | 2025-05-07 | 20/6 | DA-3 | Sandy | Competed | [10 empty] | 1 | [5 empty] | 2025-05-07 | 2025-06-04
1260 | 2025-05-07 | 46/0 | DB1+12 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-05-07 | 2025-06-04
1261 | 2025-05-08 | 21/0 | DB1+0 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-05-08 | 2025-06-05
1262 | 2025-05-08 | 20/6 | DA-3 | Sandy | Competed |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 2025-05-08 | 2025-06-05
1263 | 2025-05-09 | 20/6 | DA-3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-05-09 | 2025-06-06
1264 | 2025-05-09 | 21/0 | DB1+0 | Sandy | Competed |  | 1 | [8 empty] | 1 | [5 empty] | 2025-05-09 | 2025-06-06
1265 | 2025-05-10 | 20/5 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-05-10 | 2025-06-07
1266 | 2025-05-10 | 21/0 | DB1+0 | Sandy | Competed |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 2025-05-10 | 2025-06-07
1267 | 2025-05-11 | 21/0 | DB1+0 | Sandy | Competed |  |  |  |  | 1 |  | 1 | [9 empty] | 2025-05-11 | 2025-06-08
1268 | 2025-05-11 | 20/5 | DA+0 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | [8 empty] | 2025-05-11 | 2025-06-08
1269 | 2025-05-12 | 20/5 | DA+0 | Sandy | Competed | [8 empty] | 1 |  | 1 | [5 empty] | 2025-05-12 | 2025-06-09
1270 | 2025-05-13 | 21/0 | DB1+0 | Sandy | Competed | [5 empty] | 1 |  | 1 | 1 | [7 empty] | 2025-05-13 | 2025-06-10
1271 | 2025-05-13 | 20/5 | DA+0 | Sandy | Competed |  | 1 | 1 | [8 empty] | 1 |  |  |  |  | 2025-05-13 | 2025-06-10
1272 | 2025-05-13 | 20/4 | DA+3 | Sandy | Competed | 1 | [15 empty] | 2025-05-13 | 2025-06-10
1273 | 2025-05-15 | 20/4 | DA+3 | Sandy | Competed |  | 1 | [7 empty] | 1 | [6 empty] | 2025-05-15 | 2025-06-12
1274 | 2025-05-17 | 20/4 | DA+3 | Sandy | Competed |  |  | 1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-05-17 | 2025-06-14
1275 | 2025-05-18 | 20/4 | DA+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-05-18 | 2025-06-15
1276 | 2025-05-21 | 20/3 | DA+1.5 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-05-21 | 2025-06-18
1277 | 2025-05-22 | 20/3 | DA+1.5 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-05-22 | 2025-06-19
1278 | 2025-05-22 | 19/0 | DD60+3 | Sandy | Competed | 1 | [15 empty] | 2025-05-22 | 2025-06-19
1279 | 2025-05-23 | 19/0 | DD60+3 | Sandy | Competed |  | 1 | 1 | [6 empty] | 1 | [6 empty] | 2025-05-23 | 2025-06-20
1280 | 2025-05-24 | 19/0 | DD60+3 | Sandy | Competed | [6 empty] | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-05-24 | 2025-06-21
1281 | 2025-05-25 | 19/0 | DD60+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-05-25 | 2025-06-22
1282 | 2025-05-26 | 19/0 | DD60+3 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-05-26 | 2025-06-23
1283 | 2025-05-29 | 20/0 | DD60+3 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-05-29 | 2025-06-26
1284 | 2025-05-30 | 20/0 | DD60+3 | Sandy | Competed | [9 empty] | 1 | [6 empty] | 2025-05-30 | 2025-06-27
1285 | 2025-05-30 | 11/0 | DD45+0 | Sandy | Competed | [6 empty] | 1 | 1 | [8 empty] | 2025-05-30 | 2025-06-27
1286 | 2025-05-31 | 20/0 | DD60+3 | Sandy | Competed |  |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  |  |  | 2025-05-31 | 2025-06-28
1287 | 2025-06-01 | 20/0 | DD60+3 | Sandy | Competed | 1 | [6 empty] | 1 | 1 | [7 empty] | 2025-06-01 | 2025-06-29
1288 | 2025-06-01 | 11/0 | DD45+0 | Sandy | Competed | 1 | 1 | [14 empty] | 2025-06-01 | 2025-06-29
1289 | 2025-06-02 | 20/0 | DD60+3 | Sandy | Competed |  | 1 | 1 | [13 empty] | 2025-06-02 | 2025-06-30
1290 | 2025-06-03 | 11/0 | DD45+0 | Sandy | Competed |  |  | 1 | [5 empty] | 1 | [7 empty] | 2025-06-03 | 2025-07-01
1291 | 2025-06-05 | 11/0 | DD45+0 | Sandy | Competed | [9 empty] | 1 | 1 | [5 empty] | 2025-06-05 | 2025-07-03
1292 | 2025-06-07 | 11/0 | DD45+0 | Sandy | Competed |  |  |  | 1 | 1 | [11 empty] | 2025-06-07 | 2025-07-05
1293 | 2025-06-08 | 11/0 | DD45+0 | Sandy | Competed | [5 empty] | 1 | [5 empty] | 1 |  |  |  |  | 2025-06-08 | 2025-07-06
1294 | 2025-06-10 | 12/0 | DB1+9 | Sandy | Competed | 1 | [8 empty] | 1 | [6 empty] | 2025-06-10 | 2025-07-08
1295 | 2025-06-11 | 12/0 | DB1+9 | Sandy | Competed |  | 1 | 1 | [7 empty] | 1 | 1 |  |  |  |  | 2025-06-11 | 2025-07-09
1296 | 2025-06-13 | 12/0 | DB1+9 | Sandy | Competed |  |  |  | 1 |  |  | 1 | [9 empty] | 2025-06-13 | 2025-07-11
1297 | 2025-06-14 | 12/0 | DB1+9 | Sandy | Competed |  |  |  |  | 1 | 1 |  | 1 | 1 | [7 empty] | 2025-06-14 | 2025-07-12
1298 | 2025-06-16 | 1/0 | DD60+0 | Sandy | Competed |  |  |  | 1 | [12 empty] | 2025-06-16 | 2025-07-14
1299 | 2025-06-18 | 1/0 | DD60+0 | Sandy | Competed | 1 | [15 empty] | 2025-06-18 | 2025-07-16
1300 | 2025-06-20 | 1/0 | DD60+0 | Sandy | Competed |  | 1 |  |  | 1 | [11 empty] | 2025-06-20 | 2025-07-18
1301 | 2025-06-21 | 1/0 | DD60+0 | Sandy | Competed |  |  | 1 |  |  | 1 | [10 empty] | 2025-06-21 | 2025-07-19
1302 | 2025-06-22 | 1/0 | DD60+0 | Sandy | Competed | [6 empty] | 1 | [9 empty] | 2025-06-22 | 2025-07-20
1303 | 2025-06-25 | 1/0 | DD60+0 | Sandy | Competed | [7 empty] | 1 | [8 empty] | 2025-06-25 | 2025-07-23
1304 | 2025-06-26 | 1/0 | DD60+0 | Sandy | Competed | [8 empty] | 1 | 1 | [6 empty] | 2025-06-26 | 2025-07-24
1305 | 2025-06-27 | 1/0 | DD60+0 | Sandy | Competed | [10 empty] | 1 | 1 |  |  |  |  | 2025-06-27 | 2025-07-25
1306 | 2025-07-01 | 2A/1 | DA+0 | Sandy | Competed | 1 |  |  | 1 |  |  | 1 |  |  | 1 | [6 empty] | 2025-07-01 | 2025-07-29
1307 | 2025-07-03 | 2A/1 | DA+0 | Sandy | Competed |  | 1 | 1 |  | 1 | 1 | [10 empty] | 2025-07-03 | 2025-07-31
1308 | 2025-07-05 | 2A/1 | DA+0 | Sandy | Competed | [7 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 2025-07-05 | 2025-08-02
1309 | 2025-07-08 | 2A/0 | DD45+0 | Sandy | Competed |  |  |  | 1 | 1 | [11 empty] | 2025-07-08 | 2025-08-05
1310 | 2025-07-09 | 2A/0 | DD45+0 | Sandy | Competed | [6 empty] | 1 | 1 | [8 empty] | 2025-07-09 | 2025-08-06
1311 | 2025-07-10 | 2A/0 | DD45+0 | Sandy | Competed | [5 empty] | 1 |  |  | 1 | [7 empty] | 2025-07-10 | 2025-08-07
1312 | 2025-07-11 | 2A/0 | DD45+0 | Sandy | Competed | [9 empty] | 1 | 1 | [5 empty] | 2025-07-11 | 2025-08-08
1313 | 2025-07-12 | 2A/0 | DD45+0 | Sandy | Competed | [11 empty] | 1 |  |  |  |  | 2025-07-12 | 2025-08-09
1314 | 2025-07-13 | 2A/0 | DD45+0 | Sandy | Competed | 1 | 1 | [14 empty] | 2025-07-13 | 2025-08-10
1315 | 2025-07-14 | 2A/0 | DD45+0 | Sandy | Competed |  |  | 1 | [13 empty] | 2025-07-14 | 2025-08-11
Formulas:
Date of Casting = [Date]
Due date of Testing = [Date]+28
Note on K1312: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: STEPBOX

## Tower PRS abstract (hidden)
TA-413 Tower Schedule
Total |  | 287 | 298 | 306 | 306 | 309 | -3 | 306 | 309 | -3
[5 empty] | As per approved Detail survey TS |  |  | As per Approved Detail survey TS
S.No. | Type of Structure | As per LOA | As per Previous Estimate | As per Latest Estimate | Detail survey | PR released | Balance | Approved | PR released | Balance
1 | DA-3 | 241 | 241 | 246 | 12 | 12 | 0 | 12 | 12 | 0
2 | DA-1.5 |  |  |  | 12 | 12 | 0 | 12 | 12 | 0
3 | DA+0 |  |  |  | 33 | 33 | 0 | 33 | 33 | 0
4 | DA+1.5 |  |  |  | 24 | 24 | 0 | 24 | 24 | 0
5 | DA+3 |  |  |  | 69 | 70 | -1 | 69 | 70 | -1
6 | DA+4.5 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
7 | DA+6 |  |  |  | 47 | 49 | -2 | 47 | 49 | -2
8 | DA+9 |  |  |  | 46 | 47 | -1 | 46 | 47 | -1
9 | DB1+0 | 12 | 29 | 31 | 7 | 7 | 0 | 7 | 7 | 0
10 | DB1+3 |  |  |  | 2 | 2 | 0 | 2 | 2 | 0
11 | DB1+6 |  |  |  | 6 | 6 | 0 | 6 | 6 | 0
12 | DB1+9 |  |  |  | 12 | 12 | 0 | 12 | 12 | 0
13 | DB1+12 |  |  |  | 4 | 4 | 0 | 4 | 4 | 0
14 | DB2+0 |  | 10 | 10 | 5 | 5 | 0 | 5 | 5 | 0
15 | DB2+3 |  |  |  | 1 | 2 | -1 | 1 | 2 | -1
16 | DB2+6 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
17 | DB2+9 |  |  |  | 4 | 2 | 2 | 4 | 2 | 2
18 | DC1+0 | 5 | 2 | 2 | 1 | 1 | 0 | 1 | 1 | 0
19 | DC1+3 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
20 | DC1+6 |  |  |  | 0 |  | 0 | 0 | 0 | 0
21 | DC1+9 |  |  |  | 0 |  | 0 | 0 | 0 | 0
22 | DC2+0 |  | 4 | 4 | 2 | 2 | 0 | 2 | 2 | 0
23 | DC2-3 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
24 | DC2+6 |  |  |  | 0 |  | 0 | 0 | 0 | 0
25 | DC2+9 |  |  |  | 0 |  | 0 | 0 | 0 | 0
26 | DC2+15 |  |  |  | 2 | 1 | 1 | 2 | 1 | 1
27 | DD45-3 | 5 | 2 | 3 | 0 |  | 0 | 0 | 0 | 0
28 | DD45+0 |  |  |  | 2 | 2 | 0 | 2 | 2 | 0
29 | DD45+3 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
30 | DD45+6 |  |  |  | 0 |  | 0 | 0 | 0 | 0
31 | DD45+9 |  |  |  | 0 |  | 0 | 0 | 0 | 0
32 | DD60+0 | 24 | 10 | 10 | 1 | 1 | 0 | 1 | 1 | 0
33 | DD60+3 |  |  |  | 2 | 2 | 0 | 2 | 2 | 0
34 | DD60+6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
35 | DD60+9 |  |  |  | 1 | 1 | 0 | 1 | 1 | 0
36 | DD60+18 |  |  |  | 3 | 3 | 0 | 3 | 3 | 0
37 | DD60+25 |  |  |  | 1 | 2 | -1 | 1 | 2 | -1
38 | DD60+35 |  |  |  | 2 | 2 | 0 | 2 | 2 | 0
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1nos Incl DCT tower

## Stretch readiness (2) (hidden)
Stretch Readiness Status - 765 KV D/C Bikaner III - Neemrana II TL02 TA-413
| Description | Line length |  | Section ready for stringing |  | Completed |  | Balance Available section |  | Balance Work
| Stringing | 117.8508
| TSE | 110.1701
| Manual | 7.6807
0 | Section | Section Length | Type | Crossing details | No. of Locations (Including for end twr) | Foundation |  |  | Erection |  |  | Stringing |  |  |  | Remarks | Stretch Ready | Stringing status
[7 empty] | Balance |  |  | Balance |  | Paying out |  | Final Sag
[6 empty] | Completed | Balance | Bal. Loc. | Completed | Balance | Bal. Loc. | Completed | Balance | Completed | Balance
1 | Gantry - AP-1 | 150.014 | Manual |  | 1 | 0 | 1 | 1/0 | 0 | 1 | 1/0
2 | AP-1 - AP-2A | 290.21 | Manual |  | 1 | 0 | 1 | 2A/0 | 0 | 1 | 2A/0
3 | AP/2A - AP/3A | 2836.992 | TSE |  | 7 | 5 | 2 | 2A/1 ,2A/6 | 0 | 7 | 2A/1 ,2A/2 ,2A/3 ,2A/4,2A/6 ,2A/5 ,3A/0
4 | AP3A/0-AP3B/0 | 2691.467 | TSE |  | 7 | 7 | 0 |  | 0 | 7 | 3A/1 ,3A/2 ,3A/3 ,3A/4 ,3A/5 ,3A/6 ,3B/0
5 | AP3B/0-AP4/0 | 1627.07 | TSE |  | 4 | 2 | 2 | 3B/3 ,4/0 | 0 | 4 | 3B/1 , 3B/2 ,3B/3 ,4/0
6 | AP-4 - AP-4A/0 | 709.163 | TSE |  | 2 | 2 | 0 |  | 0 | 2 | 4/5 ,4A/0
7 | AP-4A/0 - AP-5 | 2681.611 | TSE |  | 7 | 7 | 0 |  | 0 | 7 | 4A/1 ,4A/2 ,4A/3 ,4A/4 ,4A/5 ,4A/6 ,5/0
8 | AP-5 - AP-5A/0 | 4418.389 | TSE |  | 11 | 11 | 0 |  | 0 | 11 | 5/1,2,3,4,5,6,7,8,9,10,5A/0
9 | AP-5A/0 - AP-6 | 419.48 | Manual |  | 1 | 1 | 0 |  | 0 | 1 | 6/0
10 | AP-6 - AP-7 | 4901.236 | TSE |  | 13 | 13 | 0 |  | 0 | 13 | 6/1 ,2,3,4,5,6,7,8,9,10,11,12,7/0
11 | AP-7 - AP-7A/0 | 2699.284 | TSE |  | 7 | 7 | 0 |  | 6 | 1 | 7/3
12 | AP-7A/0 - AP-8/0 | 2434.77 | TSE |  | 6 | 6 | 0 |  | 6 | 0
13 | AP-8/0 - AP-8A/0 | 4455 | TSE |  | 12 | 11 | 1 | 8A/0 | 10 | 2
14 | AP-8A/0 - AP-9/0 | 466.629 | Manual |  | 1 | 0 | 1 | 9/0 | 0 | 1
15 | AP-9/0 - AP-10/0 | 4964.92 | TSE |  | 12 | 12 | 0 |  | 4 | 8
16 | AP-10/0 - AP-11/0 | 1004.183 | TSE |  | 3 | 2 | 1 | 11/0 |  | 3
17 | AP-11/0 - AP-12/0 | 242.893 | Manual | NH-62 | 1 | 0 | 1 | 12/0 |  | 1
18 | AP-12/0 - AP-13/0 | 329.728 | Manual | 132 KV | 1 | 1 | 0 |  |  | 1
19 | AP-13/0 - AP-13A/0 | 416.878 | Manual |  | 1 | 1 | 0 |  |  | 1
20 | AP-13A/0 - AP-14/0 | 480.269 | Manual |  | 1 | 0 | 1 | 14/0 |  | 1
21 | AP-14/0 - AP-15/0 | 223.816 | Manual | 400KV | 1 | 1 | 0 |  |  | 1
22 | AP-15/0 - AP-16/0 | 5019.34 | TSE |  | 13 | 13 | 0 |  | 4 | 9
23 | AP-16/0 - AP-17/0 | 392.694 | Manual |  | 1 | 1 | 0 |  |  | 1
24 | AP-17/0 - AP-18/0 | 398.404 | Manual |  | 1 | 1 | 0 |  |  | 1
25 | AP-18/0 - AP-19/0 | 3030.029 | TSE |  | 8 | 7 | 1 | 19/0 |  | 8
26 | AP-19/0 - AP-20/0 | 279.36 | Manual | Railway | 1 | 0 | 1 | 20/0 |  | 1
27 | AP-20/0 - AP-21/0 | 2550.167 | TSE |  | 7 | 2 | 5 | 20/3 ,20/4 ,20/5 ,20/6 ,21/0 |  | 7
28 | AP-21/0 - AP-22/0 | 2283.535 | TSE |  | 6 | 3 | 3 | 22/1 ,22/2 ,22/3 |  | 6
29 | AP-22/0 - AP-23/0 | 259.048 | Manual | 220KV | 1 | 1 | 0 |  |  | 1
30 | AP-23/0 - AP-23A/0 | 440.455 | Manual |  | 1 | 1 | 0 |  |  | 1
31 | AP-23A/0 - AP-24/0 | 496.685 | Manual |  | 1 | 1 | 0 |  |  | 1
32 | AP-24/0 - AP-25/0 | 244.029 | Manual | 400KV | 1 | 1 | 0 |  |  | 1
33 | AP-25/0 - AP-26/0 | 237.428 | Manual |  | 1 | 1 | 0 |  |  | 1
34 | AP-26/0 - AP-27/0 | 203.479 | Manual | 765KV | 1 | 1 | 0 |  |  | 1
35 | AP-27/0 - AP-28/0 | 2548.275 | TSE |  | 7 | 7 | 0 |  |  | 7
36 | AP-28/0 - AP-29/0 | 211.209 | Manual | Exp-Way | 1 | 1 | 0 |  |  | 1
37 | AP-29/0 - AP-29A/0 | 2379.204 | TSE |  | 6 | 6 | 0 |  | 3 | 3
38 | AP-29A/0 - AP-30/0 | 2669.007 | TSE |  | 7 | 7 | 0 |  | 3 | 4
39 | AP-30/0 - AP-31/0 | 4124.232 | TSE |  | 11 | 11 | 0 |  | 1 | 10
40 | AP-31/0 - AP-32/0 | 4333.369 | TSE |  | 11 | 11 | 0 |  |  | 11
41 | AP-32/0 - AP-32A/0 | 3283.51 | TSE |  | 8 | 6 | 2 |  |  | 8
42 | AP-32A/0 - AP-33/0 | 840.439 | TSE |  | 2 | 1 | 1 | 33/0 | 0 | 2 | 32A/1 ,33/0
43 | AP-33/0 - AP-34/0 | 4049.764 | TSE |  | 10 | 9 | 1 | 33/1 | 4 | 6 | 33/1 ,33/2 ,33/3 ,33/4 ,33/7 ,33/9
44 | AP-34/0 - AP-35/0 | 4898.588 | TSE |  | 13 | 13 | 0 |  | 13 | 0
45 | AP-35/0 - AP-36/0 | 4916.293 | TSE |  | 12 | 9 | 3 | 35/2 ,35/3 , 35/10 | 8 | 4 | 35/2 ,35/3 ,35/10 ,36/0
46 | AP-36/0 - AP-36A/0 | 453.999 | Manual |  | 1 | 1 | 0 |  | 0 | 1 | 36A/0
47 | AP-36A/0 - AP-37/0 | 1291.523 | TSE |  | 3 | 3 | 0 |  | 2 | 1 | 37/0
48 | AP-37/0 - AP-37A/0 | 2496.394 | TSE |  | 6 | 6 | 0 |  | 3 | 3 | 37/1 ,37/2 ,37/3
49 | AP-37A/0 - AP-38/0 | 2583.589 | TSE |  | 7 | 7 | 0 |  | 6 | 1 | 38/0
50 | AP-38/0 - AP-39/0 | 4163.677 | TSE |  | 11 | 11 | 0 |  | 11 | 0
51 | AP-39/0 - AP-40/0 | 4716.811 | TSE |  | 12 | 12 | 0 |  | 8 | 4 | 39/6 ,39/10 ,39/11 ,40/0
52 | AP-40/0 - AP-40A/0 | 4665.918 | TSE |  | 12 | 12 | 0 |  | 1 | 11
53 | AP-40A/0 - AP-41/0 | 410.607 | Manual |  | 1 | 1 | 0 |  | 0 | 1
54 | AP-41/0 - AP-42/0 | 823.782 | TSE |  | 2 | 2 | 0 |  | 0 | 2
55 | AP-42/0 - AP-42/3 | 1258.998 | TSE |  | 3 | 3 | 0 |  | 0 | 3
56 | AP-42/3 - AP-43/0 | 424.891 | Manual |  | 1 | 1 | 0 |  | 0 | 1 | 43/0
57 | AP-43/0 - AP-44/0 | 3436.412 | TSE |  | 9 | 9 | 0 |  | 0 | 9 | 43/1 ,43/2 ,43/3 ,43/4 ,43/5,43/6 ,43/7 ,43/8 ,48/0
58 | AP-44/0-AP45/0 | 2383.155 | TSE |  | 6 | 5 | 1 | 45/0 | 0 | 6 | 44/1,44/2,44/3,44/4,44/5,45/0
59 | AP-45/0-AP-46/0 | 208.53 | Manual |  | 1 | 0 | 1 | 46/0 | 0 | 1 | 46/0
|  | 117850.831 |  |  | 306 | 276 | 30 |  | 93 | 213
Sl no. | Type | Total Length (Km)
1 | TSE | 110.1701
2 | Manual | 7.6807
Total=>> |  | 117.8508

## Area (hidden)
Location no | TOT | Span | Area (m^2) | Span Area
|  | A | B | C=Span*67 mtr | WORKING SHEET
4A/0 | DB1+3 |  | 34895460.7886 |  | DA+6 TOWER |  |  | DA+9 TOWER
|  | 340 |  | 22780 | Length |  |  | Length
4A/1 | DA+6 |  | 1163.4223 |  |  | J1 | 30.4662 |  | J1 | 31.921.63
|  | 419.999 |  | 28139.933 |  | G1 | 4.55 |  | G1 | 4.55
4A/2 | DA+6 |  | 1163.4223 |  |  | K=(+1M EXTENSION BOTH SIDE) | 2 |  | K=(+1M EXTENSION BOTH SIDE) | 2
|  | 415 |  | 27805 |  | Total (G1+K+JI) | 37.0162 |  | Total (G1+K+JI) | 6.55
4A/3 | DA+9 |  | 213.6731 |  | Breadth |  |  | Breadth
|  | 365 |  | 24455 |  | J2 | 24.8801 |  | J2 | 26.0718
4A/4 | DA+6 |  | 1163.4223 |  |  | G1 | 4.55 |  | G1 | 4.55
|  | 330 |  | 22110 |  | K=(+1M EXTENSION BOTH SIDE) | 2 |  | K=(+1M EXTENSION BOTH SIDE) | 2
4A/5 | DA+9 |  | 213.6731 |  |  | Total (J2+G1+K) | 31.4301 |  | Total (J2+G1+K) | 32.6218
|  | 457 |  | 30619
4A/6 | DA+9 |  | 213.6731 |  |  | Area of DA+6 Tower (L*B) | 1163.4223 |  | Area of DA+6 Tower (L*B) | 213.6731
|  | 354.612 |  | 23759.004
5/0 | DB1+6 |  | 34911639.1621 |  | DB1+3 |  |  | DB1+6
[5 empty] | Length |  |  | Length
[6 empty] | J | 25.238 |  | J | 26.6072
[6 empty] | G1 | 5880 |  | G1 | 5880
[6 empty] | K=(+1M EXTENSION BOTH SIDE) | 2 |  | K=(+1M EXTENSION BOTH SIDE) | 2
[6 empty] | Total (G1+K+JI) | 5907.238 |  | Total (G1+K+JI) | 5908.6072
[5 empty] | Breadth |  |  | Breadth
[6 empty] | J | 25.238 |  | J | 26.6072
[6 empty] | G1 | 5880 |  | G1 | 5880
[6 empty] | K=(+1M EXTENSION BOTH SIDE) | 2 |  | K=(+1M EXTENSION BOTH SIDE) | 2
[6 empty] | Total (J2+G1+K) | 5907.238 |  | Total (J2+G1+K) | 5908.6072
[6 empty] | Area of DB1+3 Tower (L*B) | 34895460.7886 |  | Area of DB1+6 Tower (L*B) | 34911639.1621