## ProdDailyExpandedSingles
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-23 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-24 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-28 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-31 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-07 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-08 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-09 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-09 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-10 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-10 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-10 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-11 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-11 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-11 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-11 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-12 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-12 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-12 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-13 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-13 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-13 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-15 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-16 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-17 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-18 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-20 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-22 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-22 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-23 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-24 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-25 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-26 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-26 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-27 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-27 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-28 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-28 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-12 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-13 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-28 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-29 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-30 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-30 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-31 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-03-31 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-06 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-07 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-08 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-08 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-09 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-09 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-10 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-10 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-10 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-11 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-11 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-11 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-13 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-13 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-14 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-15 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-16 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-16 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-16 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-17 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-17 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-18 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-18 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-19 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-19 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-20 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-20 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-21 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-21 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-22 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-22 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-23 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-24 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-25 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-26 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-02 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-03 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-05 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-06 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-07 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-07 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-08 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-09 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-10 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-11 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-11 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-12 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-13 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-13 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-13 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-14 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-14 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-15 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-15 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-15 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-16 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-16 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-17 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-17 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-17 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-18 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-18 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-19 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-19 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-20 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-20 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-21 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-21 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-22 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-22 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-24 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-25 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-26 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-27 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-27 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-28 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-29 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-30 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-31 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-31 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-01 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-02 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-03 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-04 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-05 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-05 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-06 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-06 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-07 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-07 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-08 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-08 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-08 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-09 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-09 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-09 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-10 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-10 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-10 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-11 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-11 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-11 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-11 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-12 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-12 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-13 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-13 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-13 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-13 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-13 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-14 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-14 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-14 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-14 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-15 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-15 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-15 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-15 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-16 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-16 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-16 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-16 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-17 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-17 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-17 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-17 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-18 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-18 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-18 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-18 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-19 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-19 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-19 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-19 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-19 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-20 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-20 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-20 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-20 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-20 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-20 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-21 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-21 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-21 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-21 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-21 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-21 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-21 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-22 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-22 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-22 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-22 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-22 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-22 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-22 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-23 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-23 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-23 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-23 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-23 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-23 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-23 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-24 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-24 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-24 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-24 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-24 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-25 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-25 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-25 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-25 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-25 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-25 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-26 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-26 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-26 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-26 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-26 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-26 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-27 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-27 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-27 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-27 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-27 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-28 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-28 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-28 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-28 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-28 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-28 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-29 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-29 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-29 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-29 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-29 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-29 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-30 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-30 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-30 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-30 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-07-01 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-01 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-02 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-02 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-03 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-03 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-04 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-04 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-05 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-06 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-07 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-08 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-09 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-09 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-09 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-10 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-10 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-10 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-11 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-11 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-11 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-12 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-12 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-12 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-13 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-13 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-14 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-14 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-15 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-15 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-16 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-16 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-17 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-17 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-18 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-18 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-19 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-19 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-20 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-20 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-21 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-21 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-21 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-22 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-22 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-22 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-22 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-23 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-23 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-23 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-24 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-24 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-24 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-25 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-25 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-25 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-26 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-26 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-26 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-27 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-27 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-27 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-28 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-28 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-28 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-29 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-29 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-29 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-30 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-30 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-30 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-31 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-31 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-31 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-08-01 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-01 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-01 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-02 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-02 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-02 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-03 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-03 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-03 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-04 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-04 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-05 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-05 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-05 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-06 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-06 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-06 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-06 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-07 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-07 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-07 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-07 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-08 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-08 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-08 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-08 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-09 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-09 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-10 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-10 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-10 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-11 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-11 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-11 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-12 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-12 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-12 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-12 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-13 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-13 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-13 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-13 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-14 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-14 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-14 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-14 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-14 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-15 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-15 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-15 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-15 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-15 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-16 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-16 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-16 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-16 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-16 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-17 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-17 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-17 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-17 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-17 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-18 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-18 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-18 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-19 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-19 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-19 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-19 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-20 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-20 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-20 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-20 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-21 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-21 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-21 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-21 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-22 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-22 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-22 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-22 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-23 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-23 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-23 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-23 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-23 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-23 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-24 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-24 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-24 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-24 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-24 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-24 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-25 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-25 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-25 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-25 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-25 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-25 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-25 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-26 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-26 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-26 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-26 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-26 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-26 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-27 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-27 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-27 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-27 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-27 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-27 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-28 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-28 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-28 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-28 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-28 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-28 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-29 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-29 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-29 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-29 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-29 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-29 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-30 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-30 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-30 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-30 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-30 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-30 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-31 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-31 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-31 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-01 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-01 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-01 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-02 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-02 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-02 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-03 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-03 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-03 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-04 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-04 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-04 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-04 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-05 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-05 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-05 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-05 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-05 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-06 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-06 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-06 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-06 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-07 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-07 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-07 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-08 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-08 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-08 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-09 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-09 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-09 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-10 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-10 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-10 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-10 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-11 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-11 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-11 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-11 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-12 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-12 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-12 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-12 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-13 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-13 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-13 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-13 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-14 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-14 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-14 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-14 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-15 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-15 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-16 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-16 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-16 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-17 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-17 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-17 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-17 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-18 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-18 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-18 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-19 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-19 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-19 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-20 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-20 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-20 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-21 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-21 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-21 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-21 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-22 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-22 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-22 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-23 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-23 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-24 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-24 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-25 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-25 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-25 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-26 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-26 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-27 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-27 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-27 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-28 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-28 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-29 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-30 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-01 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-01 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-02 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-02 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-03 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-03 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-04 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-04 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-05 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-05 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-06 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-06 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2025-10-07 | 2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-10-07 | 2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-10-08 | 2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
2024-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-04-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-05-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-06-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-07-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-08-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-12 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-13 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-14 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-15 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-16 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-17 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-18 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-19 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-20 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-21 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-21 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-22 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-23 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-24 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-25 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-26 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-27 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-28 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-29 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-09-30 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-09-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-01 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-02 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-03 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-03 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-03 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-04 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-05 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-06 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-07 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-08 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-08 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-09 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-09 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-10 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-10 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-11 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-11 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-12 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-12 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-13 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-13 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-14 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-14 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-14 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-15 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-15 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-16 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-16 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-17 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-17 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-18 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-19 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-20 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-21 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-22 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-23 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-24 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-25 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-10-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-10-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-12 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-13 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-14 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-15 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-15 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-16 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-16 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-17 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-17 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-18 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-18 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-19 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-19 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-20 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-20 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-21 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-21 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-22 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-22 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-23 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-23 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-24 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-24 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-25 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-25 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-26 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-26 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-27 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-27 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-28 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-28 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-29 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-29 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-11-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-11-30 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-30 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-01 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-01 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-02 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-02 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-03 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-03 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-04 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-12-04 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-05 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-05 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-06 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-06 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-07 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-07 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-07 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-08 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-08 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-08 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-09 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-09 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-09 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-10 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-10 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-10 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-11 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-11 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-11 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-12 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-12 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-12 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-13 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-13 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-13 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-13 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-13 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-14 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-14 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-14 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-14 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-14 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-15 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-15 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-15 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-15 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-15 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-15 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-16 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-16 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-16 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-16 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-16 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-16 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-17 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-17 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-17 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-17 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-17 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-17 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-18 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-18 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-18 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-18 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-18 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-18 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-19 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-19 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-19 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-19 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-19 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-19 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-20 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-20 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-20 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-20 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-20 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-20 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-21 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-21 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-21 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-21 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-21 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-21 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-22 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-22 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-22 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-22 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-22 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-22 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-23 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-23 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-23 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-23 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-23 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-23 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-24 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-24 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-24 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-24 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-24 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-24 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-24 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-25 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-25 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-25 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-25 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-25 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-25 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-26 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-26 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-26 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-26 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-26 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-27 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-27 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-27 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-27 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-28 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-28 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-28 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-28 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-29 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-29 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-29 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-29 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-30 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-30 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-30 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2024-12-30 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-31 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-31 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-31 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2024-12-31 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-01 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-01 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-01 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-01 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-02 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-02 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-02 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-02 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2025-01-03 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-03 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2025-01-03 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-03 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-04 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-04 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-04 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-04 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-04 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-04 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-05 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-05 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2025-01-05 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-05 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-05 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-05 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-06 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-06 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-06 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-06 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-06 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-06 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-07 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-07 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-07 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-07 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-07 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-07 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-07 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-08 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2025-01-08 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-08 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-08 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-08 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-08 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-09 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-09 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-09 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-09 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-09 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-10 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-10 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-10 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-10 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-10 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-11 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-11 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-11 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-11 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-11 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-11 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-11 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-12 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-12 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-12 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-12 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-12 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-12 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-13 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-13 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-13 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-13 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-13 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-13 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-14 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-14 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-14 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-14 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-14 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-15 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-15 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-15 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-15 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-15 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-16 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-16 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-16 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-16 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-16 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-17 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-17 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-17 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-17 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-17 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-17 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-17 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-18 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-18 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-18 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-18 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-18 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-18 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-18 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-19 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-19 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-19 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-19 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-19 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-19 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-19 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-20 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-20 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-20 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-20 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-20 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-20 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-20 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-21 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-21 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-21 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-21 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-21 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-21 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-21 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-22 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-22 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-22 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-22 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-22 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-22 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-23 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-23 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-23 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-23 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-24 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-24 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-24 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-24 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-25 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-25 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-25 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-25 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-26 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-26 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-26 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-26 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-27 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-27 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-27 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-27 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-28 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-28 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-28 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-28 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-29 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-29 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-29 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-29 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-29 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-29 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-01-30 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-30 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-30 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-30 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-30 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-30 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-01-31 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-31 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-31 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-01-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-01-31 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-31 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-31 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-01-31 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-01 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-01 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-01 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-01 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-01 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-02 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-02 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-02 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-02 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-02 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-03 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-03 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-03 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-02-03 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-03 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-03 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-04 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-02-04 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-04 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-04 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-04 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-05 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-05 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-05 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-05 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-05 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-05 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-06 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-06 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-06 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-06 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-06 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-07 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-07 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-02-07 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-07 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-07 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-08 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-08 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-08 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-02-08 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-08 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-09 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-09 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-09 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-09 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-09 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-10 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-10 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-10 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-10 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-10 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-11 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-11 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-11 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-11 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-12 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-12 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-12 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-12 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-13 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-13 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-13 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-13 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-14 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-14 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-14 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-14 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-14 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-15 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-15 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-15 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-15 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-15 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-16 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-16 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-16 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-02-16 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-16 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-16 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-16 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-17 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-17 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-17 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-17 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-17 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-17 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-18 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-18 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-18 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-18 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-18 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-18 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-18 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-18 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-19 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-19 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-19 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-19 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-19 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-19 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-20 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-20 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-20 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-20 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-20 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-20 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-21 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-21 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-21 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-21 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-21 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-21 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-22 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-22 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-22 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-22 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-22 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-22 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-23 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-23 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-23 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-23 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-23 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-23 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-24 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-24 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-24 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-24 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-24 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-24 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-25 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-25 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-25 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-25 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-25 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-26 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-26 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-26 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-26 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-27 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-27 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-27 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-27 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-28 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-02-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-02-28 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-28 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-02-28 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-01 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-01 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-01 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-01 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-01 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-02 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-02 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-02 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-02 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-03 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-03 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-03 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-03 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-04 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-04 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-04 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-04 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-05 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-05 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-05 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-05 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-05 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-06 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-03-06 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-06 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-03-06 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-06 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-07 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-07 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-07 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-07 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-07 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-08 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-08 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-08 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-08 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-08 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-09 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-09 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-09 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-09 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-03-09 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-10 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-10 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-10 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-10 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-11 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-11 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-11 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-11 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-12 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-12 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-12 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-12 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-13 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-13 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-13 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-13 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-14 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-14 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-14 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-14 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-14 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-15 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-15 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-15 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-15 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-15 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-16 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-16 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-16 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-16 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-16 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-17 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-17 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-17 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-17 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-17 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-18 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-18 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-18 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-18 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-18 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-19 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-19 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-19 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-20 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-20 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-20 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-21 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-21 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-21 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-22 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-22 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-22 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-23 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-23 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-23 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-23 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-24 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-24 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-24 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-24 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-25 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-25 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-25 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-25 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-26 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-26 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-26 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-27 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-27 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-27 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-28 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-28 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-29 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-29 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-29 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-03-30 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-30 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-30 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-03-31 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-31 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-31 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2025-03-31 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-03-31 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-01 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-01 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-01 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-01 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-01 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-02 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-02 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-02 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-02 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-02 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-03 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-03 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-03 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-03 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-03 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-04 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-04 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-04 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-04 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-04 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-05 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-05 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-04-05 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-05 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-05 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-06 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-06 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-06 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-06 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-04-06 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-07 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-07 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-07 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-07 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-08 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-08 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-08 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-08 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-09 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-09 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-09 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-09 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-10 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-10 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-11 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-11 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-12 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-13 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-14 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-14 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-15 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-16 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-17 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-18 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-19 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-20 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-21 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-22 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-06 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-06 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-07 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-07 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-08 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-08 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-08 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-09 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-09 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-09 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-09 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-10 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-10 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-10 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-10 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-11 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-11 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-11 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-11 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-12 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-12 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-12 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-12 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-13 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-13 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-13 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-13 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-14 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-14 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-14 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-14 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-15 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-15 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-15 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-15 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-15 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-16 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-16 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-16 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-16 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-16 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-16 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-16 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-17 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-17 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-17 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-17 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-17 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-17 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-17 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-18 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-18 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-18 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-18 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-18 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-18 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-18 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-18 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-19 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-19 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-19 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-19 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-19 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-19 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-19 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-19 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-20 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-20 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-20 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-20 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-20 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-20 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-20 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-20 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-21 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-21 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-21 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-21 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-21 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-21 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-21 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-21 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-21 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-22 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-22 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-22 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-22 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-22 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-22 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-22 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-22 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-23 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-23 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-23 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-23 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-23 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-23 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-23 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-23 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-24 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-24 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-24 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-24 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-24 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-24 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-24 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-24 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-25 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-25 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-25 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-25 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-25 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-25 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-25 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-25 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-26 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-26 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-26 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-26 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-26 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-26 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-26 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-27 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-27 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-27 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-27 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-27 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-27 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-27 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-28 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-28 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-28 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-28 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-28 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-28 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-28 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-29 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-29 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-29 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-29 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-29 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-29 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-29 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-30 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-30 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-30 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-30 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-30 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-30 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-30 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-31 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-07-31 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-07-31 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-31 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-31 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-31 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-31 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-01 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-01 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-01 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-08-01 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-01 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-01 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-01 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-08-01 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-02 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-02 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-02 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-02 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-02 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-02 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-02 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-02 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-03 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-03 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-03 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-03 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-03 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-03 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-03 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-03 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-08-04 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-04 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-04 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-04 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-04 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-04 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-05 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-05 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-05 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-05 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-05 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-05 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-05 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-06 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-06 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-06 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-06 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-06 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-07 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-07 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-07 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-07 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-07 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-07 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-07 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-08 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-08 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-08 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-08 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-08 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-08 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-08 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-08 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-08 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-09 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-09 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-09 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-09 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-09 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-09 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-09 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-09 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-09 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-09 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-09 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-10 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-10 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-10 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-10 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-10 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-10 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-10 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-10 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-10 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-10 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-10 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-11 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-11 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-11 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-11 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-11 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-11 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-11 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-11 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-11 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-11 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-12 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-12 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-12 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-12 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-12 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-12 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-12 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-12 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-12 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-13 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-13 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-13 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-13 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-13 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-13 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-13 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-13 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-13 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-13 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-14 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-14 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-14 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-14 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-14 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-14 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-14 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-14 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-14 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-14 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-14 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-14 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-15 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-15 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-15 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-15 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-15 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-15 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-15 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-15 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-15 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-15 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-15 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-16 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-16 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-16 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-16 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-16 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-16 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-16 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-16 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-16 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-16 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-16 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-16 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-17 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-17 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-17 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-17 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-17 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-17 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-17 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-17 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-17 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-17 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-17 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-17 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-18 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-18 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-18 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-18 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-18 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-18 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-18 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-18 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-18 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-18 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-18 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-18 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-18 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-19 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-19 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-19 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-19 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-19 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-19 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-19 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-19 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-19 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-19 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-19 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-19 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-19 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-20 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-20 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-20 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-20 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-20 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-20 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-20 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-20 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-20 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-20 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-20 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-20 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-20 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-20 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-21 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-21 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-21 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-21 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-21 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-21 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-21 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-21 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-21 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-21 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-21 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-21 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-21 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-21 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-22 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-22 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-22 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-22 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-22 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-22 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-22 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-22 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-22 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-22 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-22 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-22 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-22 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-23 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-23 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-23 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-23 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-23 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-23 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-23 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-23 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-23 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-23 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-23 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-23 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-23 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-23 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-23 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-23 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-23 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-24 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-24 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-24 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-24 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-24 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-24 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-24 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-24 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-24 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-24 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-24 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-24 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-24 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-24 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-24 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-24 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-24 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-25 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-25 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-25 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-25 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-25 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-25 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-25 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-25 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-25 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-25 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-25 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-25 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-25 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-25 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-25 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-25 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-25 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-25 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-26 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-26 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-26 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-26 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-26 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-26 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-26 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-26 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-26 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-26 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-26 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-26 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-27 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-27 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-27 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-27 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-27 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-27 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-27 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-27 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-27 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-27 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-27 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-27 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-28 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-28 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-28 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-28 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-28 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-28 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-28 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-28 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-28 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-28 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-28 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-28 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-29 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-29 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-29 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-29 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-29 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-29 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-29 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-29 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-29 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-29 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-29 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-29 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-29 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-29 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-29 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-30 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-30 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-30 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-30 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-30 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-30 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-30 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-30 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-30 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-30 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-30 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-30 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-30 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-30 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-30 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-30 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-31 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-31 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-31 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-08-31 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-31 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-31 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-31 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-31 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-31 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-31 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-08-31 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-08-31 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-31 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-08-31 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-31 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-31 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-01 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-01 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-09-01 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-01 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-01 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-01 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-09-01 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-09-01 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-01 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-09-01 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-01 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-01 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-01 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-01 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-01 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-02 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-02 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-09-02 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-02 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-02 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-02 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-02 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-09-02 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-02 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-09-02 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-02 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-02 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-02 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-02 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-03 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-03 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-09-03 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-03 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-03 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-03 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-03 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-03 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-03 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-03 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-03 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-03 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-03 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-03 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-03 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-03 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-09-04 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-04 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-04 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-04 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-04 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-04 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-04 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-04 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-04 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-04 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-04 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-04 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-04 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-09-04 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-04 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-04 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-04 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-05 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-05 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-05 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-05 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-05 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-05 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-09-05 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-05 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-05 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-05 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-05 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-05 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-05 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-05 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-05 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-05 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-05 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-06 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-06 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-06 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-06 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-06 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-06 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-06 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-06 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-06 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-06 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-09-06 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-06 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-06 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-06 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-09-06 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-06 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-06 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-07 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-07 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-07 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-09-07 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-07 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-07 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-07 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-07 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-07 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-07 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-07 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-07 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-07 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-07 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-07 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-07 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-07 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-08 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-08 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-08 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-09-08 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-08 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-08 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-08 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-08 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-08 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-09-08 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-08 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-08 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-08 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-08 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-08 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-09 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-09 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-09 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-09 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-09 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-09 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-09 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-09 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-09 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-09 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-09 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-09 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-09 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-09-09 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-09 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-09 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-09 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-10 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-10 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-10 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-10 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-10 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-10 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-10 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-10 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-10 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-10 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-10 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-10 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-10 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-10 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-10 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-10 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-11 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-11 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-11 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-11 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-11 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-11 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-11 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-11 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-11 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-11 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-11 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-11 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-11 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-11 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-11 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-11 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-12 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-12 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-12 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-12 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-12 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-12 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-12 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-12 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-12 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-12 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-12 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-12 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-12 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-12 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-12 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-13 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-13 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-13 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-13 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-13 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-13 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-13 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-13 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-13 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-13 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-13 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-13 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-13 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-13 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-14 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-14 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-14 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-14 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-14 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-14 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-14 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-14 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-14 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-14 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-14 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-14 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-14 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-14 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-14 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-15 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-15 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-15 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-15 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-15 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-15 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-15 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-15 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-15 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-15 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-15 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-15 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-15 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-15 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-15 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-15 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-16 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-16 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-16 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-16 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-16 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-16 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-16 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-16 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-16 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-16 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-16 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-16 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-16 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-16 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-16 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-16 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-16 | 2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 11.4243 | TA413 | 44/4 | Completed
2025-09-17 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-17 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-17 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-17 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-17 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-17 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-17 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-17 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-17 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-17 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-17 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-17 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-17 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-17 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-17 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-17 | 2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 11.4243 | TA413 | 44/4 | Completed
2025-09-18 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-18 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-18 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-18 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-18 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-18 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-18 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-18 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-18 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-18 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-18 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-18 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-18 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-18 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-18 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-18 | 2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 11.4243 | TA413 | 44/4 | Completed
2025-09-19 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-19 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-19 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-19 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-19 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-19 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-19 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-19 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-19 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-19 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-19 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 11.4243 | TA413 | 44/4 | Completed
2025-09-20 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-20 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-20 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-20 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-20 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-20 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-20 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-20 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-20 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-20 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-21 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-21 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-21 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-21 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-21 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-21 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-21 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-21 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-21 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-22 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-22 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-22 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-22 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-22 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-22 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-22 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-22 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-22 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-22 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-23 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-23 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-23 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-23 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-23 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-23 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-23 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-23 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-23 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-24 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-24 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-24 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-24 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-24 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-24 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-24 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-24 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-24 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-24 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-25 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-25 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-25 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-25 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-25 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-25 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-25 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-25 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-26 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-26 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-26 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-26 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-26 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-26 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-27 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-27 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-27 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-27 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-27 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-28 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-28 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-28 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-28 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-28 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-28 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-29 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-29 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-29 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-29 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-29 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-30 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-30 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-30 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-30 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-30 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-01 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-01 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-01 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-01 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-01 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-02 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-02 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-02 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-02 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-02 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-02 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-03 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-03 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-03 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-03 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-03 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-03 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-10-04 | 2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-04 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-04 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-04 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-04 | 2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-10-04 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-05 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-05 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-05 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-05 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-05 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-06 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-06 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-06 | 2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-10-06 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-06 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-10-07 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-07 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-07 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-07 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-07 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-08 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-08 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-08 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-08 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-08 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-09 | 2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-09 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-09 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-09 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-09 | 2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-10-10 | 2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-10 | 2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-10-10 | 2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2024-01-28 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-29 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-30 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-01-31 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-01 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-01 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-02 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-02 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-03 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-03 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-03 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-04 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-04 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-04 | 2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-05 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-05 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-05 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-06 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-06 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-06 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-07 | 2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-07 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-07 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-08 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-08 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-08 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-09 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-09 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-09 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-09 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-10 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-10 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-10 | 2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-10 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-11 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-11 | 2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-11 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-11 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-12 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-12 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-12 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-12 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-13 | 2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-13 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-13 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-13 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-13 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-14 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-14 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-14 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-14 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-15 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-15 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-15 | 2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-15 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-15 | 2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-15 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-16 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-16 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-16 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-16 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-17 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-17 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-17 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-17 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-17 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-18 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-18 | 2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-18 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-18 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-18 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-18 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-19 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-19 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-19 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-19 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-19 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-20 | 2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-20 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-20 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-20 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-20 | 2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-20 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-20 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-21 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-21 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-21 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-21 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-21 | 2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-21 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-22 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-22 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-22 | 2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-22 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-22 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-22 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-23 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-23 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-23 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-23 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-23 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-24 | 2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-24 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-24 | 2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-24 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-24 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-24 | 2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-24 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-24 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-25 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-25 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-25 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-25 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-25 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-26 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-26 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-26 | 2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-26 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-26 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-26 | 2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-26 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-27 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-27 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-27 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-27 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-27 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-28 | 2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-28 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-28 | 2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-28 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-28 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-29 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-02-29 | 2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-29 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-02-29 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-02-29 | 2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-29 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-02-29 | 2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-03-01 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-01 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-01 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-01 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-02 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-02 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-02 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-02 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-03 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-03 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-03 | 2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-03-03 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-04 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-04 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-04 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-04 | 2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-03-05 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-05 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-05 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-06 | 2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-06 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-06 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-06 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-07 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-07 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-07 | 2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-03-07 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-08 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-08 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-08 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-09 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-09 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-09 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-10 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-10 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-10 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-11 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-11 | 2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-11 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-11 | 2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-12 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-12 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-12 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-13 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-13 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-13 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-14 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-14 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-14 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-15 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-15 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-15 | 2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-15 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-16 | 2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-16 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-16 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-16 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-17 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-17 | 2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-17 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-18 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-18 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-18 | 2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-18 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-19 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-19 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-19 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-20 | 2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-20 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-20 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-20 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-21 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-21 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-21 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-21 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-22 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-22 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-22 | 2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-22 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-22 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-23 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-23 | 2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-23 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-23 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-23 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-24 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-24 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-24 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-24 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-25 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-25 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-25 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-25 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-26 | 2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-26 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-26 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-26 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-26 | 2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-26 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-27 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-27 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-27 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-27 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-28 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-28 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-28 | 2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-28 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-29 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-29 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-29 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-30 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-30 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-30 | 2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-30 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-03-31 | 2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-31 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-03-31 | 2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-31 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-03-31 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-01 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-01 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-01 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-01 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-02 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-02 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-02 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-02 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-03 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-03 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-03 | 2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-04-03 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-03 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-04 | 2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-04-04 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-04 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-04 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-05 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-05 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-05 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-06 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-06 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-06 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-06 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-06 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-07 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-07 | 2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-07 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-07 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-07 | 2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-07 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-08 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-08 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-08 | 2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-08 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-09 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-09 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-09 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-10 | 2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-10 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-10 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-10 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-11 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-11 | 2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-11 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-12 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-12 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-13 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-13 | 2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-13 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-14 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-14 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-15 | 2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-15 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-15 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-16 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-16 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-16 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-16 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-17 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-17 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-17 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-17 | 2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-17 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-18 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-18 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-18 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-18 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-18 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-19 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-19 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-19 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-19 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-19 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-20 | 2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-20 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-20 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-20 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-20 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-21 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-21 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-21 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-21 | 2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-21 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-21 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-22 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-22 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-22 | 2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-22 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-22 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-22 | 2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-22 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-23 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-23 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-23 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-23 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-23 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-24 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-24 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-24 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-24 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-24 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-25 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-25 | 2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-25 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-25 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-25 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-26 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-26 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-26 | 2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-26 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-27 | 2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-27 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-27 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-27 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-27 | 2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-27 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-28 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-28 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-28 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-28 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-29 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-29 | 2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-29 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-04-29 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-29 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-30 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-30 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-04-30 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-30 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-01 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-01 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-01 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-01 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-02 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-02 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-02 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-02 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-03 | 2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-05-03 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-03 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-03 | 2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-05-03 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-04 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-04 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-04 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-05 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-05 | 2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-05 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-05 | 2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-05-05 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-06 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-06 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-06 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-07 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-07 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-07 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-08 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-08 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-08 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-09 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-09 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-09 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-10 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-10 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-10 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-11 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-11 | 2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-11 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-11 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-12 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-12 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-12 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-12 | 2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-12 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-13 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-13 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-13 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-13 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-14 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-14 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-14 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-14 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-15 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-15 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-15 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-15 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-16 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-16 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-16 | 2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-16 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-16 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-17 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-17 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-17 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-17 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-18 | 2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-18 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-18 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-18 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-18 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-19 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-19 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-19 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-19 | 2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-19 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-20 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-20 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-20 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-20 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-21 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-21 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-21 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-21 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-22 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-22 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-22 | 2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-22 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-23 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-23 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-23 | 2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-23 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-24 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-24 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-24 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-25 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-25 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-25 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-26 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-26 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-26 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-27 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-27 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-27 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-28 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-28 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-28 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-29 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-29 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-29 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-29 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-30 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-30 | 2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-30 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-30 | 2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-31 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-05-31 | 2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-06-01 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-01 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-02 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-02 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-03 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-03 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-04 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-04 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-05 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-05 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-06 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-06 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-07 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-07 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-08 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-08 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-09 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-09 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-10 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-10 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-11 | 2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-11 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-12 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-12 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-13 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-13 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-14 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-14 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-15 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-15 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-16 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-16 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-17 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-17 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-18 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-18 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-19 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-19 | 2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-20 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-21 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-22 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-23 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-24 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-25 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-26 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-06-27 | 2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-07-04 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-05 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-06 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-07 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-08 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-09 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-10 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-11 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-12 | 2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-15 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-16 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-17 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-18 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-19 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-20 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-21 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-22 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-23 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-24 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-25 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-07-26 | 2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-08-13 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-14 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-15 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-16 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-17 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-18 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-19 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-21 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-22 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-24 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-24 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-25 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-25 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-26 | 2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-26 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-27 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-27 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-28 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-28 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-28 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-28 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-29 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-29 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-29 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-29 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-30 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-30 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-30 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-30 | 2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-30 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-08-31 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-08-31 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-31 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-08-31 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-08-31 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-01 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-01 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-01 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-01 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-01 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-02 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-02 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-02 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-02 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-02 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-03 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-03 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-03 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-03 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-03 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-04 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-04 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-04 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-04 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-04 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-05 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-05 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-05 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-05 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-05 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-06 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-06 | 2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-09-06 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-06 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-06 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-06 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-07 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-07 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-07 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-07 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-07 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-08 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-08 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-08 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-08 | 2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-09-08 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-08 | 2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-09-09 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-09 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-09 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-09 | 2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-09 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-10 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-10 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-10 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-10 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-10 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-11 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-11 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-11 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-11 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-11 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-12 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-12 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-12 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-12 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-12 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-13 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-13 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-13 | 2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-13 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-13 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-14 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-14 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-14 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-14 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-15 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-15 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-15 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-15 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-16 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-16 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-16 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-16 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-17 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-17 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-17 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-17 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-18 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-18 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-18 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-18 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-18 | 2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-09-19 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-19 | 2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-19 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-19 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-19 | 2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-19 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-19 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-20 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-20 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-20 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-20 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-20 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-21 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-21 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-21 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-21 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-21 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-21 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-22 | 2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-22 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-22 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-22 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-22 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-22 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-23 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-23 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-23 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-23 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-23 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-23 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-24 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-24 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-24 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-24 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-24 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-24 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-25 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-25 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-25 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-25 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-25 | 2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-25 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-25 | 2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-26 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-26 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-26 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-26 | 2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-26 | 2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-26 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-27 | 2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-27 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-27 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-27 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-27 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-27 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-27 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-28 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-28 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-28 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-28 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-28 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-28 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-28 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-28 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-28 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-29 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-29 | 2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-29 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-29 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-29 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-29 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-29 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-29 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-29 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-30 | 2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-30 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-30 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-09-30 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-30 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-30 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-09-30 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-30 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-01 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-01 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-01 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-01 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-01 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-01 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-01 | 2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-10-01 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-02 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-02 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-02 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-02 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-02 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-02 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-02 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-02 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-03 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-03 | 2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-10-03 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-03 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-03 | 2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-10-03 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-03 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-03 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-04 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-04 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-04 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-04 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-04 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-04 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-04 | 2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-10-05 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-05 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-05 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-05 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-05 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-05 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-05 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-05 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-06 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-06 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-06 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-06 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-06 | 2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-10-06 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-06 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-06 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-07 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-07 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-07 | 2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-07 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-07 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-07 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-07 | 2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-07 | 2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-07 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-07 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-08 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-08 | 2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-08 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-08 | 2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-08 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-08 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-08 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-08 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-09 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-09 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-09 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-09 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-09 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-09 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-10 | 2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-10 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-10 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-10 | 2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-10 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-10 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-10 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-11 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-11 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-11 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-11 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-11 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-11 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-12 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-12 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-12 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-12 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-12 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-12 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-12 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-13 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-13 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-13 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-13 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-13 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-13 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-13 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-13 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-14 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-14 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-14 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-14 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-14 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-14 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-14 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-14 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-15 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-15 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-15 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-15 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-15 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-15 | 2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-15 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-15 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-16 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-16 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-16 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-16 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-16 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-16 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-16 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-16 | 2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-17 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-17 | 2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-17 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-17 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-17 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-17 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-17 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-17 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-18 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-18 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-18 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-18 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-18 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-18 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-18 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-18 | 2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-18 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-18 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-19 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-19 | 2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-19 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-19 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-19 | 2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-19 | 2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-10-19 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-19 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-19 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-19 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-19 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-20 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-20 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-20 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-20 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-20 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-20 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-20 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-20 | 2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-20 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-20 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-21 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-21 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-21 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-21 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-21 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-21 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-21 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-21 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-21 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-21 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-21 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-22 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-22 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-22 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-22 | 2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-22 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-22 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-22 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-22 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-22 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-22 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-22 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-23 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-23 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-23 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-23 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-23 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-23 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-23 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-23 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-23 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-23 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-23 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-24 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-24 | 2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-24 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-24 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-24 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-24 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-24 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-24 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-24 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-24 | 2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-24 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-24 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-25 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-25 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-25 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-25 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-25 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-25 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-25 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-25 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-25 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-25 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-26 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-26 | 2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-26 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-26 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-26 | 2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-26 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-26 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-26 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-26 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-26 | 2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-27 | 2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-27 | 2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-27 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-27 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-27 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-27 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-27 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-27 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-28 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-28 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-28 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-28 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-28 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-28 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-29 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-29 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-29 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-29 | 2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-29 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-29 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-30 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-30 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-30 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-30 | 2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-30 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-10-31 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-31 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-31 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-10-31 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-11-01 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-01 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-11-01 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-01 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-01 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-02 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-02 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-02 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-02 | 2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-11-02 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-02 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-02 | 2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-02 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-03 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-03 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-03 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-03 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-03 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-03 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-03 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-04 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-04 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-04 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-04 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-04 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-04 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-04 | 2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-04 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-04 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-05 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-05 | 2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-11-05 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-05 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-05 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-05 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-05 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-05 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-05 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-06 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-06 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-06 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-06 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-06 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-06 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-06 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-06 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-07 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-07 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-07 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-07 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-07 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-07 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-07 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-07 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-07 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-08 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-08 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-08 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-08 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-08 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-08 | 2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-08 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-08 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-08 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-09 | 2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-09 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-09 | 2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-09 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-09 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-09 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-09 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-09 | 2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-09 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-10 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-10 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-10 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-10 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-10 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-10 | 2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-10 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-11 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-11 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-11 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-11 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-11 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-11 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-11 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-11 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-12 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-12 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-12 | 2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-12 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-12 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-12 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-12 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-12 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-12 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-13 | 2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-13 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-13 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-13 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-13 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-13 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-13 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-13 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-13 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-13 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-14 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-14 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-14 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-14 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-14 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-14 | 2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-14 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-14 | 2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-14 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-15 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-15 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-15 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-15 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-15 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-15 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-15 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-15 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-16 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-16 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-16 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-16 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-16 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-16 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-16 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-16 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-17 | 2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-17 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-17 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-17 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-17 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-17 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-17 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-17 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-17 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-18 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-18 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-18 | 2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-18 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-18 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-18 | 2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-18 | 2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-18 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-18 | 2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-19 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-19 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-19 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-19 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-19 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-19 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-20 | 2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-20 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-20 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-20 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-20 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-20 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-21 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-21 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-21 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-21 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-21 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-22 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-22 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-22 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-22 | 2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-22 | 2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-22 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-23 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-23 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-23 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-23 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-23 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-24 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-24 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-24 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-24 | 2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-24 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-24 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-24 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-25 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-25 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-25 | 2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-25 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-25 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-25 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-25 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-26 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-26 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-26 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-26 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-26 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-26 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-26 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-27 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-27 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-27 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-27 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-27 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-27 | 2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-27 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-27 | 2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-28 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-28 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-28 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-28 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-28 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-28 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-28 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-29 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-29 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-29 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-29 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-29 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-29 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-29 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-30 | 2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-30 | 2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-30 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-11-30 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-11-30 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-11-30 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-30 | 2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-30 | 2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-12-01 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-01 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-01 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-01 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-01 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-02 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-02 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-02 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-02 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-02 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-02 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-03 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-03 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-03 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-03 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-03 | 2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-12-03 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-03 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-04 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-04 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-04 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-04 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-04 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-04 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-05 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-05 | 2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-05 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-05 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-05 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-05 | 2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-12-06 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-06 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-06 | 2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-06 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-06 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-07 | 2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-07 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-07 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-07 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-08 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-08 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-08 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-09 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-09 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-09 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-09 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-09 | 2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-12-10 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-10 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-10 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-10 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-11 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-11 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-11 | 2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-11 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-12 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-12 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-12 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-13 | 2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-13 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-13 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-14 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-14 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-15 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-15 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-16 | 2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-16 | 2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-20 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-21 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-22 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-23 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-24 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-25 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-26 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-26 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-26 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-27 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-27 | 2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-27 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-28 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-28 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-28 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-29 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-29 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-29 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-30 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-30 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-30 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2024-12-31 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-31 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-31 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-01 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-01 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-01 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-02 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-02 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-02 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-03 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-03 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-03 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-03 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-04 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-04 | 2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2025-01-04 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-04 | 2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2025-01-04 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-05 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-05 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-05 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-05 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-06 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-06 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-06 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-06 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-07 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-07 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-07 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-07 | 2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-08 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-08 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-08 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-08 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-09 | 2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-09 | 2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-09 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-09 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-10 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-10 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-10 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-10 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-11 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-11 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-11 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-11 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-11 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-11 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-12 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-12 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-12 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-12 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-12 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-12 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-13 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-13 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-13 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-13 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-13 | 2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-13 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-14 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-14 | 2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-14 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-14 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-14 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-14 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-15 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-15 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-15 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-15 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-15 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-15 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-16 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-16 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-16 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-16 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-16 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-16 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-17 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-17 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-17 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-17 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-17 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-17 | 2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-18 | 2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-18 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-18 | 2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-18 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-18 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-19 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-19 | 2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-19 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-19 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-19 | 2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-20 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-20 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-20 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-21 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-21 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-21 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-21 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-22 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-22 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-22 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-22 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-23 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-23 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-23 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-23 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-24 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-24 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-24 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-24 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-25 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-25 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-25 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-25 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-26 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-26 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-26 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-26 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-27 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-27 | 2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-27 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-27 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-28 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-28 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-28 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-28 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-29 | 2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-29 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-29 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-29 | 2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-29 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-30 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-30 | 2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-30 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-31 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-01-31 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-31 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-01-31 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-01 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-01 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-02-01 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-01 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-02 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-02 | 2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-02-02 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-02 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-02 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-03 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-03 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-03 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-03 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-04 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-04 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-04 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-04 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-05 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-05 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-05 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-05 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-05 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-06 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-06 | 2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-02-06 | 2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-06 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-06 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-07 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-07 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-07 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-07 | 2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-02-08 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-08 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-08 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-08 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-09 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-09 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-09 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-09 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-10 | 2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-10 | 2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-10 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-10 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-11 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-11 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-11 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-11 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-12 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-12 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-12 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-12 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-13 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-13 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-13 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-13 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-14 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-14 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-14 | 2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-14 | 2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-15 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-15 | 2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-15 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-16 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-16 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-16 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-17 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-17 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-17 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-18 | 2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-18 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-18 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-19 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-19 | 2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-19 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-20 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-20 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-20 | 2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-21 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-21 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-22 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-22 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-23 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-23 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-24 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-24 | 2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-25 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-25 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-26 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-26 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-26 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-02-27 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-27 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-27 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-02-28 | 2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-28 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-02-28 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-01 | 2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-03-01 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-01 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-02 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-02 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-02 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-03 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-03 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-03 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-04 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-04 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-04 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-05 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-05 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-05 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-06 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-06 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-06 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-07 | 2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-03-07 | 2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-07 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-08 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-09 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-09 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-09 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-09 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-10 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-10 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-10 | 2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-10 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-11 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-11 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-11 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-12 | 2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-12 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-12 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-13 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-13 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-13 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-14 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-14 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-14 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-15 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-15 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-15 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-15 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-16 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-16 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-16 | 2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-16 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-17 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-17 | 2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-17 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-18 | 2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-18 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-18 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-19 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-19 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-19 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-20 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-20 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-20 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-20 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-21 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-21 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-21 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-21 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-22 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-22 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-22 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-22 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-23 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-23 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-23 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-23 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-24 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-24 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-24 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-24 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-25 | 2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-25 | 2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-25 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-25 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-26 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-26 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-26 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-26 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-27 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-27 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-27 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-27 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-28 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-28 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-28 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-28 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-29 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-29 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-29 | 2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-29 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-30 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-30 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-30 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-03-31 | 2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-31 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-03-31 | 2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-31 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-03-31 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-01 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-01 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-04-01 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-02 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-02 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-02 | 2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-04-02 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-03 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-03 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-03 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-03 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-04 | 2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-04 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-04 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-04 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-05 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-05 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-05 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-06 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-06 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-06 | 2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-06 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-07 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-07 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-07 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-08 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-08 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-08 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-09 | 2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-09 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-09 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-10 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-10 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-11 | 2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-04-11 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-12 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-12 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-13 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-13 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-14 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-14 | 2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-15 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-16 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-17 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-18 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-19 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-20 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-21 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-22 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-23 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-24 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-25 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-26 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-27 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-27 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-28 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-28 | 2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-29 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-04-30 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-01 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-02 | 2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-12 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-13 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-14 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-15 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-16 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-17 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-18 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-19 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-19 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-20 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-20 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-20 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-21 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-21 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-21 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-22 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-22 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-22 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-23 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-23 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-23 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-24 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-24 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-24 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-25 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-25 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-25 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-26 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-26 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-26 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-27 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-27 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-27 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-28 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-28 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-28 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-29 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-29 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-29 | 2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-30 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-30 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-05-31 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-05-31 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-01 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-01 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-02 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-02 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-03 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-03 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-04 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-04 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-04 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-05 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-05 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-05 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-06 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-06 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-06 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-07 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-07 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-07 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-08 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-08 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-08 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-09 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-09 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-09 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-10 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-10 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-10 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-11 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-11 | 2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-11 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-11 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-12 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-12 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-12 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-13 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-13 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-13 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-14 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-14 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-14 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-15 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-15 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-15 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-16 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-16 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-16 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-16 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-17 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-17 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-17 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-17 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-17 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-18 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-18 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-18 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-18 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-18 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-19 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-19 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-19 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-19 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-19 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-20 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-20 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-20 | 2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-20 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-20 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-21 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-21 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-21 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-21 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-22 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-22 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-22 | 2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-06-22 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-22 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-23 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-23 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-23 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-23 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-24 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-24 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-24 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-24 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-25 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-25 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-25 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-25 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-26 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-26 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-26 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-26 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-27 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-27 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-27 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-06-27 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-27 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-28 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-28 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-28 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-06-28 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-06-28 | 2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-28 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-29 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-29 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-29 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-06-29 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-06-29 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-30 | 2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-30 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-06-30 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-06-30 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-06-30 | 2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-07-01 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-01 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-01 | 2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-07-01 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-07-01 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-02 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-02 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-02 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-07-02 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-03 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-03 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-03 | 2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-07-03 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-03 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-04 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-04 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-04 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-04 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-05 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-05 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-05 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-05 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-06 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-06 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-06 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-06 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-07 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-07 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-07 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-07 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-07 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-08 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-08 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-08 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-08 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-08 | 2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-08 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-09 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-09 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-09 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-09 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-09 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-10 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-10 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-10 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-10 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-10 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-10 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-11 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-11 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-11 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-11 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-11 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-11 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-11 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-12 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-12 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-12 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-12 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-12 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-12 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-12 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-13 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-13 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-13 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-13 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-13 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-13 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-13 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-14 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-14 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-14 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-14 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-14 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-14 | 2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-14 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-14 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-14 | 2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-07-15 | 2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-15 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-15 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-15 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-15 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-15 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-15 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-16 | 2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-16 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-16 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-16 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-16 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-16 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-16 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-17 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-17 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-17 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-17 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-17 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-17 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-18 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-18 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-18 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-18 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-18 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-18 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-19 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-19 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-19 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-19 | 2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-19 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-19 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-19 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3
2025-07-20 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-20 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-20 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-20 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-20 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-20 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3
2025-07-21 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-21 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-21 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-21 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-21 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-21 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2
2025-07-21 | 2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-21 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-21 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3
2025-07-22 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-22 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-22 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-22 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-22 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-22 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2
2025-07-22 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-22 | 2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3
2025-07-23 | 2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-23 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-23 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-23 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-23 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-23 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-23 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2
2025-07-23 | 2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-23 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2
2025-07-23 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-24 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-24 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-24 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-24 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-24 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-24 | 2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2
2025-07-24 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2
2025-07-24 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-25 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-25 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-25 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-25 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-25 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-25 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-25 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-25 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3
2025-07-25 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2
2025-07-25 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-26 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-26 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-26 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-26 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-26 | 2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-26 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-26 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-26 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3
2025-07-26 | 2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2
2025-07-26 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-26 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1
2025-07-26 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-07-27 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-27 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-27 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-27 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-27 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-27 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-27 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-27 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-27 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-27 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1
2025-07-27 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-07-28 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-28 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-28 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-28 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-28 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-28 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-28 | 2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-28 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-28 | 2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-28 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1
2025-07-28 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-07-28 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-07-28 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-07-29 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-29 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-29 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-29 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-29 | 2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-29 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-29 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-29 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-29 | 2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1
2025-07-29 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-07-29 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-07-29 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-07-29 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-07-30 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-30 | 2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-30 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-30 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-07-30 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-30 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-30 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-07-30 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-07-30 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-30 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-30 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-07-30 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-07-30 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-07-30 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-07-31 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-31 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-07-31 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-07-31 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-07-31 | 2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-31 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-07-31 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-07-31 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-31 | 2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-31 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-07-31 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-07-31 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-07-31 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-07-31 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-01 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-08-01 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-01 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-01 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-01 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-08-01 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-01 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-01 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-01 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-01 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-01 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-08-01 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-01 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-08-01 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-02 | 2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-08-02 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-02 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-02 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-02 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-08-02 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-02 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-02 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-02 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-02 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-02 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-08-02 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-02 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-08-02 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-03 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-03 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-03 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-03 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-08-03 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-03 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-03 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-03 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-03 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-03 | 2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-08-03 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-03 | 2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-08-03 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-04 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-04 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-04 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-04 | 2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-08-04 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-04 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-04 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-04 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-04 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-04 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-04 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-04 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-04 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-04 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-04 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-04 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-05 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-05 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-05 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-05 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-05 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-05 | 2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-05 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-05 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-05 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-05 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-05 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-05 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-05 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-05 | 2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-05 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-06 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-06 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-06 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-06 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-06 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-06 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-06 | 2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-08-06 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-06 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-06 | 2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-08-06 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-06 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-06 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-06 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-06 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-06 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-07 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-07 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-07 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-07 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-07 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-07 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-07 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-07 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-07 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-07 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-07 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-07 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-07 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-07 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-07 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-08 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-08 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-08 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-08 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-08 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-08 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-08 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-08 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-08 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-08 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-08 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-08 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-08 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-08 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-08 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-09 | 2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-09 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-09 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-09 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-09 | 2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-08-09 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-09 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-09 | 2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-09 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-09 | 2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-08-09 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-09 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-09 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-09 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-09 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-09 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-09 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-10 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-10 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-10 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-10 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-10 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-10 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-10 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-10 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-10 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-10 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-10 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-10 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-10 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-10 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-10 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-11 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-11 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-11 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-11 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-11 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-11 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-11 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-11 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-11 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-11 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-11 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-11 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-11 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-11 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-11 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-12 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-12 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-12 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-12 | 2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-12 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-12 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-12 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-12 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-12 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-12 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-12 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-12 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-12 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-12 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-12 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-12 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-12 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-13 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-13 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-13 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-13 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-13 | 2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-13 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-13 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-13 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-13 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-13 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-13 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-13 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-13 | 2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-08-13 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-13 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-13 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-13 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-13 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-14 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-14 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-14 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-14 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-14 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-14 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-14 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-14 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-14 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-14 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-14 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-14 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-14 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-14 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-14 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-14 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-15 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-15 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-15 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-15 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-15 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-15 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-15 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-15 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-15 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-15 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-15 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-15 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-15 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-15 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-15 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-15 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-16 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-16 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-16 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-16 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-16 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-16 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-16 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-16 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-16 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-16 | 2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-16 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-16 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-16 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-16 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-16 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-16 | 2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-16 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-17 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-17 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-17 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-17 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-17 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-17 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-17 | 2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-17 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-08-17 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-17 | 2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-17 | 2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-17 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-17 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-17 | 2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-17 | 2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-17 | 2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-17 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-17 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-17 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-17 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-17 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-18 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-18 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-18 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-18 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-18 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-18 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-18 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-18 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-08-18 | 2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-18 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-18 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-18 | 2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-18 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-18 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-18 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-18 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-18 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-19 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-19 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-19 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-19 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-19 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-19 | 2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-19 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-19 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-19 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-19 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-08-19 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-19 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-19 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-19 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-19 | 2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-08-19 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-19 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-20 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-20 | 2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-20 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-20 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-20 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-20 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-20 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-20 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-20 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-20 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-08-20 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-20 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-20 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-20 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-20 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-20 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-21 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-21 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-21 | 2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-21 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-21 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-21 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-21 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-21 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-21 | 2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-08-21 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-21 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-21 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-21 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-21 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-21 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-21 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-21 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-22 | 2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-22 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-22 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-22 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-22 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-22 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-22 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-22 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-22 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-22 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-22 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-22 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-22 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-22 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-22 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-22 | 2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-22 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-22 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-23 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-23 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-23 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-23 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-23 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-23 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-23 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-23 | 2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-23 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-23 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-23 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-23 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-23 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-23 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-23 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-23 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-23 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-23 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-24 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-24 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-24 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-24 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-24 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-24 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-24 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-24 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-24 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-24 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-24 | 2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-24 | 2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-24 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-24 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-24 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-24 | 2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-24 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-24 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-24 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-25 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-25 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-25 | 2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-25 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-25 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-25 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-25 | 2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-25 | 2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-25 | 2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-25 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-25 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-25 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-25 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-25 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-25 | 2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-25 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-25 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-25 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-25 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-26 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-26 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-26 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-26 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-26 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-26 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-26 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-26 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-26 | 2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-26 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-26 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-26 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-26 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-26 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-26 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-26 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-26 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-26 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-26 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-27 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-27 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-27 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-27 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-27 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-27 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-27 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-27 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-27 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-27 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-27 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-27 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-27 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-27 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-27 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-27 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-27 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-27 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-28 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-28 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-28 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-28 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-28 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-28 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-28 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-28 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-28 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-28 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-28 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-28 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-28 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-28 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-28 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-28 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-28 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-28 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-29 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-29 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-29 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-29 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-29 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-29 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-08-29 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-08-29 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-29 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3
2025-08-29 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-29 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-29 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-29 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-29 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-29 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-08-29 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-29 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-08-29 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-29 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-29 | 2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-29 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-29 | 2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-29 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-30 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-30 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-30 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-30 | 2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-30 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-08-30 | 2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-30 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-08-30 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-08-30 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-30 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3
2025-08-30 | 2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-30 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-30 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-30 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-30 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-30 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-08-30 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-30 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-08-30 | 2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-30 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-30 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-08-30 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-30 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-08-31 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-08-31 | 2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-31 | 2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-31 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-08-31 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-08-31 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-08-31 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-31 | 2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3
2025-08-31 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-31 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-31 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-31 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-08-31 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-08-31 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-31 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-08-31 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-31 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-08-31 | 2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-31 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-01 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-01 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-01 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-01 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-01 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-09-01 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-01 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-09-01 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-09-01 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-09-01 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-01 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-01 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-01 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-09-01 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-09-01 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-01 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-01 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-01 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-02 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-02 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-02 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-02 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-02 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-09-02 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-02 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-09-02 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-02 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-09-02 | 2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-09-02 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-02 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-02 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-02 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-09-02 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-09-02 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-02 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-02 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0
2025-09-02 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-02 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-03 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-03 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-03 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-03 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-03 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-09-03 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-03 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-03 | 2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-09-03 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-03 | 2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-09-03 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-03 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-03 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-03 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-03 | 2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-09-03 | 2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-09-03 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-03 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-03 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-03 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-03 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0
2025-09-03 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-03 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-04 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-04 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-04 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-04 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-04 | 2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-09-04 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-04 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-04 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-04 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-04 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-04 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-04 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-04 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-04 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-04 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-04 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-04 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0
2025-09-04 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-04 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-05 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-05 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-05 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-05 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-05 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-05 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-05 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-05 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-05 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-05 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-05 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-05 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-05 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-05 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-05 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-05 | 2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0
2025-09-05 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-05 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-05 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-06 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-06 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-06 | 2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-09-06 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-06 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-06 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-06 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-06 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-06 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-06 | 2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-06 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-06 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-06 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-06 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-06 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-06 | 2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-09-06 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-06 | 2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-07 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-07 | 2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-07 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-07 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-07 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-07 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-07 | 2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-09-07 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-07 | 2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-09-07 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-07 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-07 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-07 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-07 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-07 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-07 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-07 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-07 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-08 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-08 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-08 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-08 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-08 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-08 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-08 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-08 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-08 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-08 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-08 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-08 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-08 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-08 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-08 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-09 | 2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-09 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-09 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-09 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-09 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-09 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-09 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-09 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4
2025-09-09 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-09 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-09 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-09 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-09 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-09 | 2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-09-09 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-09 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-09 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-09 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-09 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-10 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-10 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-10 | 2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-10 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-10 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-10 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-10 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-10 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-10 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4
2025-09-10 | 2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-10 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-10 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-10 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-10 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-10 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-10 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-10 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-10 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-10 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-10 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-11 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-11 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-11 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-11 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-11 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-11 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-11 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-11 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4
2025-09-11 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-11 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-11 | 2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-11 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-11 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-11 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-11 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-11 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-11 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-11 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-12 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-12 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-12 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-12 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-12 | 2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-12 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-12 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-12 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-12 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-12 | 2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4
2025-09-12 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-12 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-12 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-12 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-12 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-12 | 2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-12 | 2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-12 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-12 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-13 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-13 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-13 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-13 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-13 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-13 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-13 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-13 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-13 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-13 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-13 | 2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-09-13 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-13 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-13 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-13 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-13 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-14 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-14 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-14 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-14 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-14 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-14 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-14 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-14 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-14 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-14 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-14 | 2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-14 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-14 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-14 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-14 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-15 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-15 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-15 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-15 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-15 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-15 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-15 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-15 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-15 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-15 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-15 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-15 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-15 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-15 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-15 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-16 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-16 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-16 | 2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-16 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-16 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-16 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-16 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-16 | 2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-16 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-16 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-16 | 2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-09-16 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-16 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-16 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-16 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-16 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-16 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-17 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-17 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-17 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-17 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-17 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-17 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-17 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-17 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-17 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-17 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-17 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-17 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-17 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-17 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-18 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-18 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-18 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-18 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-18 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-18 | 2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-18 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-18 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-18 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-18 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-18 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-18 | 2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-18 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-18 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-19 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-19 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-19 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-19 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-19 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-19 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-19 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-19 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5
2025-09-19 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-19 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-19 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-19 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2
2025-09-19 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-19 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-20 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-20 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-20 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-20 | 2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-20 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-20 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-20 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-20 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-20 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-20 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5
2025-09-20 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-20 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-20 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-20 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2
2025-09-20 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-20 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-21 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-21 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-21 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-21 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-21 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-21 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-21 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-21 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-21 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5
2025-09-21 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-21 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-21 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-21 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2
2025-09-21 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-21 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-22 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-22 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-22 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-22 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-22 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-22 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-22 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-22 | 2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-22 | 2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5
2025-09-22 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-22 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-22 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-22 | 2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2
2025-09-22 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-22 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-22 | 2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-22 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-23 | 2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-23 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-23 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-23 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-23 | 2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-23 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-23 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-23 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-23 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-23 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-23 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-23 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-23 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-24 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-24 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-24 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-24 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-24 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-24 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-24 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-24 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-24 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-24 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-24 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-25 | 2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-09-25 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-25 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-25 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-25 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-25 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-25 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-25 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-25 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-25 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-25 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-25 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-26 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-26 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-26 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-26 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-26 | 2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-26 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-26 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-26 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-26 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-26 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-26 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-27 | 2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-27 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-27 | 2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-27 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-09-27 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-27 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-27 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-27 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-27 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-27 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-27 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-28 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-28 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-09-28 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-28 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-28 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-28 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-28 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-28 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-28 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-29 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-29 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-09-29 | 2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-29 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-29 | 2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-29 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-09-29 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-29 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-29 | 2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-29 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-30 | 2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-30 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-09-30 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-30 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-09-30 | 2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-30 | 2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-30 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-01 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-01 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-10-01 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-01 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-02 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-02 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-10-02 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-02 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-03 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-03 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-03 | 2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-10-03 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-03 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-04 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-04 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-04 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-04 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-05 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-05 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-05 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-05 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-06 | 2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-10-06 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-06 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-06 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-07 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-07 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-07 | 2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-10-08 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-08 | 2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-09 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2025-10-10 | 2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-24 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-25 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-26 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-27 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-28 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-29 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-30 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-31 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-01 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-02 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-03 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-04 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-05 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-06 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-07 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-08 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-12 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-13 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-14 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-15 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-16 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-17 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-18 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-20 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-21 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-21 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-22 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-22 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-23 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-23 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-24 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-24 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-25 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-25 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-27 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-27 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-28 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-28 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-29 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-30 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-01 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-02 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-03 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-04 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-30 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-31 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-03 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-04 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-05 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-16 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-21 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-22 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-23 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-24 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-25 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-25 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-26 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-26 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-27 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-27 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-28 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-29 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-29 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-30 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-30 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-01 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-01 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-01 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-01 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-02 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-02 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-02 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-02 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-03 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-03 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-03 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-03 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-04 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-04 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-04 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-04 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-05 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-05 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-05 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-06 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-06 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-06 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-07 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-07 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-08 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-08 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-10-09 | 2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-10-09 | 2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-22 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-23 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-28 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-29 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-30 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-31 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-02 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-03 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-04 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-14 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-15 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-18 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-19 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-20 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-07 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-08 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-08 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-09 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-09 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-10 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-10 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-11 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-12 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-12 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-13 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-13 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-13 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-14 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-14 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-14 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-15 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-15 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-16 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-17 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-18 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-19 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-20 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-20 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-21 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-21 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-22 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-23 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-23 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-24 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-24 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-25 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-25 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-26 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-27 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-27 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-28 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-28 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-28 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-29 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-29 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-03-31 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-31 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-01 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-01 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-02 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-02 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-03 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-03 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-04 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-04 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-05 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-05 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-06 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-07 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-07 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-08 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-09 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-09 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-09 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-10 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-10 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-10 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-11 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-11 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-11 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-13 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-13 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-14 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-14 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-15 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-16 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-16 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-17 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-17 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-18 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-19 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-20 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-20 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-21 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-21 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-22 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-23 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-23 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-24 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-24 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-24 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-25 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-25 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-25 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-26 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-26 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-27 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-27 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-27 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-28 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-28 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-28 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-29 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-29 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-29 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-30 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-30 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-30 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-01 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-01 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-01 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-02 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-02 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-03 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-03 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-04 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-04 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-05 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-05 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-06 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-06 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-06 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-07 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-09 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-09 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-10 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-10 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-11 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-11 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-12 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-13 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-13 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-14 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-14 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-15 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-15 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-16 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-16 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-17 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-17 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-17 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-17 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-18 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-18 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-18 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-18 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-19 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-19 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-19 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-19 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-20 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-20 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-20 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-21 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-21 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-21 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-22 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-22 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-23 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-23 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-23 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-23 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-24 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-24 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-24 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-24 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-25 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-25 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-25 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-25 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-25 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-26 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-26 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-26 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-26 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-26 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-27 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-27 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-27 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-27 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-28 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-28 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-28 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-28 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-29 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-29 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-29 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-29 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-29 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-30 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-30 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-30 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-30 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-30 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-31 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-31 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-31 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-05-31 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-31 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-01 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-01 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-01 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-01 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-02 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-02 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-02 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-02 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-02 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-03 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-03 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-03 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-03 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-03 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-04 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-04 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-04 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-04 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-04 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-05 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-05 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-05 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-05 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-05 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-06 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-06 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-06 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-06 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-07 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-07 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-07 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-07 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-08 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-08 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-08 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-09 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-09 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-09 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-09 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-09 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-10 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-10 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-10 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-10 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-10 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-11 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-11 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-11 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-12 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-12 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-12 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-12 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-13 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-13 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-13 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-13 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-14 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-14 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-14 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-14 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-15 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-15 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-15 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-15 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-16 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-16 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-16 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-16 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-17 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-17 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-18 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-18 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-19 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-19 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-20 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-20 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-21 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-21 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-21 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-22 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-22 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-22 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-23 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-23 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-24 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-25 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-26 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-26 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-27 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-27 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-28 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-28 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-28 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-29 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-29 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-29 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-30 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-30 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-30 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-01 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-01 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-02 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-02 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-03 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-03 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-04 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-04 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-05 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-05 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-06 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-06 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-07 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-07 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-07 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-08 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-08 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-09 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-09 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-10 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-10 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-11 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-11 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-11 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-12 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-12 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-12 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-13 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-13 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-14 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-14 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-15 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-15 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-16 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-16 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-17 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-17 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-18 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-19 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-19 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-20 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-20 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-21 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-21 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-22 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-22 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-23 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-23 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-24 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-24 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-25 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-25 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-26 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-26 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-27 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-27 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-28 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-28 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-29 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-30 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-31 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-31 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-02 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-03 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-09 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-10 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-10 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-11 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-11 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-12 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-12 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-13 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-14 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-14 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-15 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-15 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-16 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-16 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-17 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-18 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-18 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-19 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-19 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-20 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-20 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-20 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-21 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-21 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-21 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-21 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-22 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-22 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-22 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-23 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-23 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-23 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-23 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-24 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-24 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-24 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-24 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-24 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-25 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-25 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-25 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-25 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-26 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-26 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-26 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-26 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-27 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-27 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-28 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-28 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-28 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-29 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-29 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-29 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-30 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-30 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-30 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-31 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-31 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-01 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-01 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-02 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-02 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-03 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-03 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-03 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-04 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-04 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-04 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-05 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-05 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-05 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-06 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-06 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-07 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-07 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-08 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-08 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-09 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-09 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-09 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-10 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-11 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-12 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-12 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-12 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-12 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-13 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-13 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-13 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-14 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-14 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-14 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-14 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-15 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-15 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-15 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-15 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-16 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-16 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-16 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-16 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-17 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-17 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-17 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-17 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-18 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-18 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-19 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-19 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-19 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-19 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-20 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-20 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-20 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-20 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-20 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-21 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-21 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-21 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-21 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-21 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-22 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-22 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-22 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-22 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-22 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-22 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-23 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-23 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-23 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-23 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-23 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-23 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-24 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-24 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-24 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-24 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-24 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-24 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-25 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-25 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-25 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-25 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-25 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-26 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-26 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-26 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-26 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-27 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-27 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-27 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-27 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-27 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-27 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-28 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-28 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-28 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-28 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-28 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-28 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-29 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-29 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-29 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-30 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-30 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-30 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-10-01 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-01 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-02 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-02 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-02 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-03 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-03 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-03 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-04 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-04 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-04 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-04 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-05 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-05 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-05 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-06 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-06 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-06 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-07 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-07 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-07 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-08 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-08 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-08 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-09 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-09 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-10 | 2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-10-10 | 2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416 | 6/2 | COMPLETED
2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416 | 38/3 | COMPLETED
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-10-07 | Kongres Kumar 1 | 42.3742 | 3.0267 | TA416 | 64/3 | COMPLETED
2025-09-25 | 2025-10-07 | Punam Kumari | 67.112 | 5.1625 | TA416 | 54/0 | COMPLETED
2025-09-25 | 2025-10-08 | Amit Choudhury | 64.4817 | 4.6058 | TA416 | 46/0 | COMPLETED
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
2025-09-29 |  | M S Mdpl | 60 |  | TA416 | 54/0 | Material shifting work under progress.
2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | Completed
2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | Completed
2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | Completed
2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | Completed
2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | Completed
2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | Completed
2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | Completed
2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | Completed
2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | Completed
2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | Completed
2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | Completed
2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | Completed
2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | Completed
2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | Completed
2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | Completed
2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | Completed
2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | Completed
2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | Completed
2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | Completed
2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | Completed
2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | Completed
2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | Completed
2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | Completed
2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | Completed
2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | Completed
2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | Completed
2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | Completed
2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | Completed
2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | Completed
2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | Completed
2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | Completed
2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | Completed
2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | Completed
2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | Completed
2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | Completed
2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | Completed
2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | Completed
2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | Completed
2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | Completed
2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | Completed
2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | Completed
2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | Completed
2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | Completed
2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | Completed
2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | Completed
2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | Completed
2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | Completed
2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | Completed
2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | Completed
2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | Completed
2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | Completed
2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | Completed
2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | Completed
2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | Completed
2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | Completed
2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | Completed
2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | Completed
2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | Completed
2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | Completed
2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | Completed
2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | Completed
2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | Completed
2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | Completed
2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | Completed
2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | Completed
2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | Completed
2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | Completed
2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | Completed
2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | Completed
2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | Completed
2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | Completed
2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | Completed
2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | Completed
2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | Completed
2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | Completed
2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | Completed
2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | Completed
2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | Completed
2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | Completed
2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | Completed
2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | Completed
2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | Completed
2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | Completed
2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | Completed
2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | Completed
2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | Completed
2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | Completed
2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | Completed
2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | Completed
2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | Completed
2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | Completed
2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | Completed
2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | Completed
2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | Completed
2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | Completed
2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | Completed
2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | Completed
2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | Completed
2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | Completed
2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | Completed
2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | Completed
2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | Completed
2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | Completed
2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | Completed
2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | Completed
2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | Completed
2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | Completed
2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | Completed
2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | Completed
2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | Completed
2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | Completed
2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | Completed
2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | Completed
2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | Completed
2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | Completed
2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | Completed
2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | Completed
2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | Completed
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed
2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | Completed
2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | Completed
2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | Completed
2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | Completed
2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | Completed
2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | Completed
2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | Completed
2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | Completed
2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | Completed
2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | Completed
2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | Completed
2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | Completed
2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | Completed
2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | Completed
2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | Completed
2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | Completed
2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | Completed
2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | Completed
2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | Completed
2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | Completed
2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | Completed
2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | Completed
2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | Completed
2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | Completed
2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | Completed
2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | Completed
2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | Completed
2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | Completed
2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | Completed
2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | Completed
2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | Completed
2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | Completed
2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | Completed
2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | Completed
2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | Completed
2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | Completed
2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | Completed
2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | Completed
2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | Completed
2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | Completed
2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | Completed
2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | Completed
2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | Completed
2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | Completed
2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | Completed
2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | Completed
2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | Completed
2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | Completed
2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | Completed
2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | Completed
2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | Completed
2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | Completed
2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | Completed
2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | Completed
2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | Completed
2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | Completed
2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | Completed
2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | Completed
2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | Completed
2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | Completed
2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | Completed
2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | Completed
2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | Completed
2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | Completed
2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | Completed
2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | Completed
2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | Completed
2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | Completed
2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | Completed
2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | Completed
2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | Completed
2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | Completed
2025-09-04 | 2025-09-18 | Sk Samiul 1 | 37.9311 | 2.5287 | TA413 | 31/6 | Completed
2025-09-09 | 2025-09-18 | Govind Mahto 2 | 43.8044 | 4.3804 | TA413 | 4A/6 | Completed
2025-09-14 | 2025-09-19 | Fouzi Ratto | 36.1598 | 6.0266 | TA413 | 43/8 | Completed
2025-09-16 | 2025-09-19 | Ved Prakash | 45.697 | 11.4243 | TA413 | 44/4 | Completed
2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 45.697 | 5.7121 | TA413 | 3A/2 | Completed
2025-09-04 | 2025-09-20 | Kartik Mahto | 45.697 | 2.6881 | TA413 | 40A/0 | Completed
2025-09-03 | 2025-09-20 | Amar Kumar Singh | 36.1598 | 2.0089 | TA413 | 33/0 | Completed
2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | Completed
2025-09-15 | 2025-09-21 | Amit Kumar Singh | 66.7809 | 9.5401 | TA413 | 31/8 | Completed
2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | Completed
2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | Completed
2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | Completed
2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | Completed
2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | Completed
2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | Completed
2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | Completed
2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | Completed
2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | Completed
2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | Completed
2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | Completed
2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | Completed
2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | Completed
2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | Completed
2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | Completed
2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | Completed
2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | Completed
2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | Completed
2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | Completed
2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | Completed
2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | Completed
2025-09-24 | 2025-10-04 | Sk Samiul 1 | 45.697 | 4.1543 | TA413 | 30/2 | Completed
2025-09-24 | 2025-10-04 | Amar Kumar Singh | 45.697 | 4.1543 | TA413 | 41/1 | Completed
2025-09-26 | 2025-10-04 | Punam Kumari 4 | 43.8044 | 4.8672 | TA413 | 29A/5 | Completed
2025-09-27 | 2025-10-04 | Bhairaw Mahto | 37.1383 | 4.6423 | TA413 | 15/8 | Completed
2025-10-01 | 2025-10-06 | Punam Kumari 2 | 34.7898 | 5.7983 | TA413 | 18/4 | Completed
2025-09-26 | 2025-10-07 | Govind Mahto 1 | 45.697 | 3.8081 | TA413 | 3B/2 | Completed
2025-09-28 | 2025-10-09 | Ved Prakash | 66.7809 | 5.5651 | TA413 | 45/0 | Completed
2025-09-30 | 2025-10-09 | Kartik Mahto | 37.9311 | 3.7931 | TA413 | 40/10 | Completed
2025-10-05 | 2025-10-10 | Punam Kumari 4 | 37.9311 | 6.3218 | TA413 | 29A/4 | Completed
2025-10-01 | 2025-10-10 | Pritam Enterprises 3 | 36.1598 | 3.616 | TA413 | 3A/4 | Completed
2025-10-07 | 2025-10-10 | Punam Kumari 2 | 36.1598 | 9.0399 | TA413 | 18/5 | Completed
2025-09-25 |  | Pritam Enterprises 2 | 66.7809 |  | TA413 | 3B/0 | WIP
2025-09-25 |  | Jwala Singh 1 | 72.1555 |  | TA413 | 4/0 | WIP
2025-09-30 |  | Fouzi Ratto | 70.7883 |  | TA413 | 46/0 | WIP
2025-10-05 |  | Govind Mahto 2 | 137.0461 |  | TA413 | 15/0 | WIP
2025-10-01 |  | Punam Kumari 1 | 87.0213 |  | TA413 | 20/0 | WIP
2025-10-02 |  | Pritam Enterprises 1 | 65.0278 |  | TA413 | 10/0 | WIP
2025-10-08 |  | Pritam Enterprises 4 | 62.4437 |  | TA413 | 29/0 | WIP
2025-10-07 |  | Jwala Singh 2 | 43.8044 |  | TA413 | 29/1 | WIP
2025-10-06 |  | Sk Samiul 1 | 55.4509 |  | TA413 | 29A/0 | WIP
2025-10-05 |  | Amar Kumar Singh | 66.7809 |  | TA413 | 41/0 | WIP
2025-10-05 |  | Bhairaw Mahto | 65.8725 |  | TA413 | 17/0 | ROW
2025-10-09 |  | Govind Mahto 1 | 37.9311 |  | TA413 | 3B/1 | WIP
2025-10-10 |  | Ved Prakash | 173.5609 |  | TA413 | 26/0 | WIP
2025-10-10 |  | Kartik Mahto | 35.6018 |  | TA413 | 40/8 | WIP
|  | Punam Kumari 4 |  |  | TA413 | No front | WIP
2025-10-11 |  | Pritam Enterprises 3 | 77.0769 |  | TA413 | 3A/0 | WIP
2025-10-11 |  | Punam Kumari 2 | 45.697 |  | TA413 | 18/6 | WIP
|  | Nan |  |  | TA413
|  | Nan |  |  | TA413
|  | Nan |  |  | TA413
|  | Nan |  |  | TA413
|  | Nan |  |  | TA413 | SL No
|  | Pw Mt |  |  | TA413 |  | Construction Revenue
|  | Nan |  |  | TA413 | Tower with extensions Up to +9M
1970-01-01 | 1970-01-01 | 0 030435 | 1.505 |  | TA413 | 1 | 336894.66109103995
1970-01-01 | 1970-01-01 | 0 030628999999999997 | 1.5497 |  | TA413 | 2 | 353397.87792192
1970-01-01 | 1970-01-01 | 0 030759 | 1.7006 |  | TA413 | 3 | 408118.80970016
1970-01-01 | 1970-01-01 | 0 031055 | 1.76 |  | TA413 | 4 | 425751.84245048004
1970-01-01 | 1970-01-01 | 0 030223 | 1.4915 |  | TA413 | 5 | 331695.92027207994
1970-01-01 | 1970-01-01 | 0 030211 | 1.4612 |  | TA413 | 6 | 324131.0934004
1970-01-01 | 1970-01-01 | 0 030687 | 1.674 |  | TA413 | 7 | 399895.72013196
1970-01-01 | 1970-01-01 | 0 030518999999999998 | 1.5328 |  | TA413 | 8 | 346011.82257615996
1970-01-01 | 1970-01-01 | 0 059184 | 2.4809 |  | TA413 | 9 | 516626.7066308401
1970-01-01 | 1970-01-01 | 0 061852 | 2.5394 |  | TA413 | 10 | 540033.5900996401
1970-01-01 | 1970-01-01 | 0 074512 | 2.838 |  | TA413 | 11 | 605853.4124983599
1970-01-01 | 1970-01-01 | 0 07460800000000001 | 2.9307 |  | TA413 | 12 | 622186.96967284
1970-01-01 | 1970-01-01 | 0 06618600000000001 | 2.5025 |  | TA413 | 13 | 554357.83097552
1970-01-01 | 1970-01-01 | 0 069438 | 2.5514 |  | TA413 | 14 | 578726.2868670401
1970-01-01 | 1970-01-01 | 0 081 | 2.869 |  | TA413 | 15 | 646365.09184
1970-01-01 | 1970-01-01 | 0 08204600000000001 | 2.9645 |  | TA413 | 16 | 672261.6212936001
1970-01-01 | 1970-01-01 | 0 061932 | 2.5712 |  | TA413 | 17 | 581778.01780904
1970-01-01 | 1970-01-01 | 0 06503999999999999 | 2.6698 |  | TA413 | 18 | 613723.39383056
1970-01-01 | 1970-01-01 | 0 062996 | 2.5335 |  | TA413 | 19 | 626666.7578995199
1970-01-01 | 1970-01-01 | 0 061876 | 2.474 |  | TA413 | 20 | 604516.62297832
1970-01-01 | 1970-01-01 | 0 058150999999999994 | 2.569 |  | TA413 | 21 | 682407.73458832
1970-01-01 | 1970-01-01 | 0 059057000000000005 | 2.692 |  | TA413 | 22 | 718113.44313488
1970-01-01 | 1970-01-01 | 0 067222 | 3.0084 |  | TA413 | 23 | 774541.76037784
1970-01-01 | 1970-01-01 | 0 069954 | 3.166 |  | TA413 | 24 | 810763.9013656001
1970-01-01 | 1970-01-01 | 0 07859000000000001 | 3.5674 |  | TA413 | 25 | 949875.98724928
1970-01-01 | 1970-01-01 | 0 08738 | 2.993 |  | TA413 | 26 | 659522.9388825999
1970-01-01 | 1970-01-01 | 0 09733599999999998 | 3.3936 |  | TA413 | 27 | 902614.5275160001
1970-01-01 | 1970-01-01 | 0 10176600000000001 | 4.2034 |  | TA413 | 28 | 1164138.7107916798
1970-01-01 | 1970-01-01 | 0 10993 | 4.3876 |  | TA413 | 29 | 1276836.69812608
1970-01-01 | 1970-01-01 | 0 10993 | 5.1781 |  | TA413 | 30 | 1617039.24735808
1970-01-01 | 1970-01-01 | 0 11 | 2.868 |  | TA413 | 31 | 766434.7400023598
|  | Nan |  |  | TB408
|  | Nan |  |  | TB408
2024-01-28 | 2024-02-04 | Suraj Const | 38.8476 | 4.856 | TB408 | 60/7
2024-02-01 | 2024-02-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 59/13
2024-02-03 | 2024-02-10 | Sunny Const | 38.8476 | 4.856 | TB408 | 63/6
2024-02-05 | 2024-02-11 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/5
2024-02-08 | 2024-02-13 | Chinta Devi | 45.413 | 7.5688 | TB408 | 59/14
2024-02-09 | 2024-02-15 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/8
2024-02-11 | 2024-02-15 | Sunny Const | 38.8476 | 7.7695 | TB408 | 63/7
2024-02-12 | 2024-02-18 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/6
2024-02-13 | 2024-02-20 | Chinta Devi | 45.413 | 5.6766 | TB408 | 59/12
2024-02-15 | 2024-02-20 | Sunny Const | 38.8476 | 6.4746 | TB408 | 63/8
2024-02-15 | 2024-02-21 | Suraj Const | 37.5044 | 5.3578 | TB408 | 60/10
2024-02-17 | 2024-02-22 | Sobha Devi | 37.5044 | 6.2507 | TB408 | 62/5
2024-02-18 | 2024-02-24 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 59/7
2024-02-20 | 2024-02-24 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 59/10
2024-02-20 | 2024-02-24 | Sunny Const | 37.5044 | 7.5009 | TB408 | 64/1
2024-02-21 | 2024-02-26 | Suraj Const | 38.8476 | 6.4746 | TB408 | 60/11
2024-02-22 | 2024-02-26 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/4
2024-02-24 | 2024-02-28 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 59/9
2024-02-26 | 2024-02-28 | Sobha Devi | 37.5044 | 12.5015 | TB408 | 62/3
2024-02-24 | 2024-02-29 | Ganesh Const | 60.0968 | 10.0161 | TB408 | 59/8
2024-02-24 | 2024-02-29 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/4
2024-02-26 | 2024-02-29 | Suraj Const | 37.5044 | 9.3761 | TB408 | 60/6
2024-02-29 | 2024-03-03 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/2
2024-02-29 | 2024-03-04 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/5
2024-02-29 | 2024-03-06 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/2
2024-03-04 | 2024-03-07 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 62/7
2024-02-29 | 2024-03-11 | Ganesh Const | 47.1844 | 3.932 | TB408 | 59/16
2024-03-06 | 2024-03-11 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/4
2024-03-07 | 2024-03-11 | Sobha Devi | 37.5044 | 7.5009 | TB408 | 62/8
2024-03-11 | 2024-03-15 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 62/9
2024-03-11 | 2024-03-16 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 65/3
2024-03-11 | 2024-03-17 | Ganesh Const | 38.8476 | 5.5497 | TB408 | 60/5
2024-03-15 | 2024-03-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 62/10
2024-03-16 | 2024-03-20 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/5
2024-03-18 | 2024-03-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 61/6
2024-03-18 | 2024-03-23 | Ganesh Const | 38.8476 | 6.4746 | TB408 | 60/4
2024-03-20 | 2024-03-26 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/6
2024-03-21 | 2024-03-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/6
2024-03-22 | 2024-03-28 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 61/7
2024-03-26 | 2024-03-30 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/7
2024-03-23 | 2024-03-31 | Ganesh Const | 38.8476 | 4.3164 | TB408 | 60/3
2024-03-26 | 2024-03-31 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 65/9
2024-03-30 | 2024-04-03 | Sunny Const | 38.8476 | 7.7695 | TB408 | 64/8
2024-03-31 | 2024-04-04 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 65/11
2024-03-31 | 2024-04-07 | Ganesh Const | 38.8476 | 4.856 | TB408 | 60/2
2024-04-01 | 2024-04-07 | Suraj Const | 38.8476 | 5.5497 | TB408 | 63/5
2024-04-03 | 2024-04-08 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/9
2024-04-06 | 2024-04-10 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 67/1
2024-04-06 | 2024-04-11 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 61/0
2024-04-07 | 2024-04-13 | Suraj Const | 37.5044 | 5.3578 | TB408 | 63/4
2024-04-10 | 2024-04-15 | Chinta Devi | 37.5044 | 6.2507 | TB408 | 67/2
2024-04-13 | 2024-04-17 | Suraj Const | 38.8476 | 7.7695 | TB408 | 63/3
2024-04-15 | 2024-04-20 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 64/10
2024-04-16 | 2024-04-21 | Sunny Const | 38.8476 | 6.4746 | TB408 | 64/2
2024-04-16 | 2024-04-22 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/2
2024-04-17 | 2024-04-22 | Suraj Const | 37.5044 | 6.2507 | TB408 | 63/2
2024-04-18 | 2024-04-25 | Ganesh Const | 45.413 | 5.6766 | TB408 | 60/1
2024-04-21 | 2024-04-26 | Sunny Const | 37.5044 | 6.2507 | TB408 | 64/3
2024-04-21 | 2024-04-27 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 65/0
2024-04-22 | 2024-04-27 | Suraj Const | 38.8476 | 6.4746 | TB408 | 63/1
2024-04-22 | 2024-04-29 | Sobha Devi | 45.413 | 5.6766 | TB408 | 61/1
2024-04-27 | 2024-05-03 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 65/1
2024-04-27 | 2024-05-03 | Suraj Const | 38.8476 | 5.5497 | TB408 | 62/11
2024-04-27 | 2024-05-05 | Sunny Const | 57.5972 | 6.3997 | TB408 | 64/0
2024-04-29 | 2024-05-05 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 60/9
2024-05-05 | 2024-05-11 | Sobha Devi | 45.413 | 6.4876 | TB408 | 61/3
2024-05-03 | 2024-05-12 | Suraj Const | 66.3811 | 6.6381 | TB408 | 63/0
2024-05-11 | 2024-05-16 | Sobha Devi | 38.8476 | 6.4746 | TB408 | 61/4
2024-05-05 | 2024-05-18 | Ganesh | 66.3811 | 4.7415 | TB408 | 60/0
2024-05-12 | 2024-05-19 | Suraj Const | 47.1844 | 5.898 | TB408 | 61/10
2024-05-16 | 2024-05-22 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 61/5
2024-05-19 | 2024-05-23 | Suraj Const | 37.5044 | 7.5009 | TB408 | 61/9
2024-05-18 | 2024-05-30 | Ganesh | 45.413 | 3.4933 | TB408 | 59/15
2024-05-23 | 2024-05-30 | Suraj Const | 45.413 | 5.6766 | TB408 | 61/8
2024-05-12 | 2024-05-31 | Mansukh Lal | 37.5044 | 1.8752 | TB408 | 55/3
2024-05-29 | 2024-06-11 | Bhuvneshwar | 37.5044 | 2.6789 | TB408 | 57/3
2024-06-01 | 2024-06-19 | Mansukh Lal | 37.5044 | 1.9739 | TB408 | 55/4
2024-06-12 | 2024-06-27 | Bhuvneshwar | 37.5044 | 2.344 | TB408 | 57/4
2024-07-04 | 2024-07-12 | Bhuvneshwar | 38.8476 | 4.3164 | TB408 | 62/1
2024-07-15 | 2024-07-26 | Bhuvneshwar | 38.8476 | 3.2373 | TB408 | 62/6
2024-08-13 | 2024-08-20 | Sobha Devi | 38.8476 | 4.856 | TB408 | 57/6
2024-08-20 | 2024-08-26 | Sobha Devi | 38.8476 | 5.5497 | TB408 | 57/5
2024-08-23 | 2024-08-30 | Yogendra Mahto | 38.8476 | 4.856 | TB408 | 10/18
2024-08-28 | 2024-09-06 | Jagdish Mahto | 37.5044 | 3.7504 | TB408 | 10/3
2024-08-30 | 2024-09-08 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 10/17
2024-08-31 | 2024-09-08 | Sobha Devi | 57.5972 | 6.3997 | TB408 | 62/0
2024-08-28 | 2024-09-09 | Uma Const | 37.5044 | 2.885 | TB408 | 50/9
2024-09-06 | 2024-09-13 | Nirmal Mahto | 38.8476 | 4.856 | TB408 | 16/3
2024-09-09 | 2024-09-18 | Yogendra Mahto | 37.5044 | 3.7504 | TB408 | 10/19
2024-08-27 | 2024-09-19 | Ganesh Sinha | 47.1844 | 1.966 | TB408 | 52/5
2024-09-10 | 2024-09-19 | Uma Const | 37.5044 | 3.7504 | TB408 | 50/10
2024-09-18 | 2024-09-22 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/2
2024-09-19 | 2024-09-25 | Yogendra Mahto | 38.8476 | 5.5497 | TB408 | 10/20
2024-09-08 | 2024-09-25 | Kaushalya Const | 47.1844 | 2.6214 | TB408 | 48/1
2024-09-21 | 2024-09-26 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 15/1
2024-09-19 | 2024-09-26 | Uma Const | 37.5044 | 4.688 | TB408 | 51/1
2024-09-23 | 2024-09-27 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/4
2024-09-25 | 2024-09-29 | Jagdish Mahto | 37.5044 | 7.5009 | TB408 | 10/6
2024-09-19 | 2024-09-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/6
2024-09-27 | 2024-10-01 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/7
2024-09-28 | 2024-10-03 | Nirmal Mahto | 37.5044 | 6.2507 | TB408 | 16/4
2024-09-28 | 2024-10-03 | Jailal Ageria | 38.8476 | 6.4746 | TB408 | 14A/1
2024-09-26 | 2024-10-04 | Uma Const | 37.5044 | 4.1672 | TB408 | 51/2
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14
2024-09-27 | 2024-10-07 | Rafikul Islam | 37.5044 | 3.4095 | TB408 | 11A/2
2024-10-02 | 2024-10-07 | Sobha Devi | 57.5972 | 9.5995 | TB408 | 50/0
2024-10-01 | 2024-10-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 52/7
2024-10-05 | 2024-10-08 | Jagdish Mahto | 37.5044 | 9.3761 | TB408 | 10/9
2024-10-04 | 2024-10-08 | Deglal Mahto | 37.5044 | 7.5009 | TB408 | 18/1
2024-10-07 | 2024-10-10 | Bina Devi | 38.8476 | 9.7119 | TB408 | 10/21
2024-10-05 | 2024-10-10 | Nirmal Mahto | 38.8476 | 6.4746 | TB408 | 17/1
2024-10-07 | 2024-10-15 | Sobha Devi | 45.413 | 5.0459 | TB408 | 50/1
2024-10-07 | 2024-10-16 | Uma Const | 47.1844 | 4.7184 | TB408 | 50/8
2024-10-12 | 2024-10-17 | Jagdish Mahto | 38.8476 | 6.4746 | TB408 | 10/4
2024-10-13 | 2024-10-18 | Sobha Devi | 45.413 | 7.5688 | TB408 | 50/3
2024-10-11 | 2024-10-19 | Nirmal Mahto | 45.413 | 5.0459 | TB408 | 17/2
2024-09-28 | 2024-10-19 | Kaushalya Const | 66.3811 | 3.0173 | TB408 | 48/0
2024-10-08 | 2024-10-19 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 52/8
2024-10-10 | 2024-10-20 | Sanjeev Kumar | 37.5044 | 3.4095 | TB408 | 73/2
2024-10-19 | 2024-10-22 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/8
2024-10-18 | 2024-10-24 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/2
2024-10-20 | 2024-10-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 64/11
2024-10-20 | 2024-10-26 | Nirmal Mahto | 37.5044 | 5.3578 | TB408 | 16/2
2024-10-19 | 2024-10-26 | Deglal Mahto | 66.3811 | 8.2976 | TB408 | 19/0
2024-10-17 | 2024-10-26 | Uma Const | 45.413 | 4.5413 | TB408 | 59/11
2024-10-18 | 2024-10-27 | Jailal Ageria | 66.3811 | 6.6381 | TB408 | 16/0
2024-10-21 | 2024-10-27 | Bina Devi | 37.5044 | 5.3578 | TB408 | 17/3
2024-10-21 | 2024-10-29 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 73/1
2024-10-24 | 2024-10-30 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/4
2024-10-23 | 2024-11-01 | Jirwa Devi | 37.5044 | 3.7504 | TB408 | 55/6
2024-10-16 | 2024-11-02 | Rafikul Islam | 57.5972 | 3.1998 | TB408 | 11A/0
2024-10-27 | 2024-11-02 | Uma Const | 38.8476 | 5.5497 | TB408 | 59/3
2024-11-01 | 2024-11-04 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 50/7
2024-11-02 | 2024-11-05 | Jagdish Mahto | 38.8476 | 9.7119 | TB408 | 10/11
2024-10-18 | 2024-11-08 | Rafikul Islam | 38.8476 | 1.7658 | TB408 | 11A/1
2024-11-03 | 2024-11-09 | Bina Devi | 38.8476 | 5.5497 | TB408 | 16/5
2024-11-05 | 2024-11-09 | Jailal Ageria | 37.5044 | 7.5009 | TB408 | 16/1
2024-11-01 | 2024-11-09 | Uma Const | 38.8476 | 4.3164 | TB408 | 59/4
2024-11-04 | 2024-11-10 | Sobha Devi | 47.1844 | 6.7406 | TB408 | 50/6
2024-11-01 | 2024-11-12 | Jirwa Devi | 37.5044 | 3.1254 | TB408 | 55/5
2024-11-09 | 2024-11-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/9
2024-11-04 | 2024-11-14 | Nirmal Mahto | 60.0968 | 5.4633 | TB408 | 17/0
2024-11-11 | 2024-11-14 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/7
2024-11-13 | 2024-11-17 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 73/8
2024-11-10 | 2024-11-18 | Rafikul Islam | 37.5044 | 4.1672 | TB408 | 11/5
2024-11-11 | 2024-11-18 | Jailal Ageria | 38.8476 | 4.856 | TB408 | 13/2
2024-11-07 | 2024-11-18 | Yogendra Mahto | 47.1844 | 3.932 | TB408 | 43/9
2024-11-15 | 2024-11-18 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/6
2024-11-17 | 2024-11-20 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 73/6
2024-11-02 | 2024-11-22 | Kaushalya Const | 45.413 | 2.1625 | TB408 | 47/10
2024-11-18 | 2024-11-22 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/4
2024-11-12 | 2024-11-24 | Jirwa Devi | 38.8476 | 2.9883 | TB408 | 59/2
2024-11-13 | 2024-11-25 | Ganesh Sinha | 47.1844 | 3.6296 | TB408 | 52/10
2024-11-19 | 2024-11-27 | Yogendra Mahto | 47.1844 | 5.2427 | TB408 | 43/8
2024-11-23 | 2024-11-27 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 49/5
2024-11-22 | 2024-11-30 | Bina Devi | 38.8476 | 4.3164 | TB408 | 17/5
2024-11-24 | 2024-11-30 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/9
2024-11-27 | 2024-11-30 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/2
2024-11-24 | 2024-11-30 | Sanjeev Kumar | 38.8476 | 5.5497 | TB408 | 72/3
2024-11-25 | 2024-12-03 | Jirwa Devi | 38.8476 | 4.3164 | TB408 | 59/1
2024-11-26 | 2024-12-05 | Ganesh Sinha | 38.8476 | 3.8848 | TB408 | 52/9
2024-12-02 | 2024-12-05 | Sobha Devi | 38.8476 | 9.7119 | TB408 | 49/3
2024-11-28 | 2024-12-06 | Jailal Ageria | 47.1844 | 5.2427 | TB408 | 11A/7
2024-12-01 | 2024-12-07 | Deglal Mahto | 38.8476 | 5.5497 | TB408 | 11A/3
2024-12-06 | 2024-12-09 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 49/1
2024-11-30 | 2024-12-11 | Jagdish Mahto | 57.5972 | 4.7998 | TB408 | 10/12
2024-12-09 | 2024-12-13 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/3
2024-12-09 | 2024-12-16 | Deglal Mahto | 45.413 | 5.6766 | TB408 | 11A/6
2024-12-03 | 2024-12-16 | Jirwa Devi | 66.3811 | 4.7415 | TB408 | 59/0
2024-12-20 | 2024-12-27 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/8
2024-12-25 | 2025-01-04 | Deglal Mahto | 38.8476 | 3.5316 | TB408 | 11A/5
2024-12-28 | 2025-01-04 | Sanjeev Kumar | 37.5044 | 4.688 | TB408 | 65/7
2024-12-25 | 2025-01-07 | Yogendra Mahto | 57.5972 | 4.1141 | TB408 | 43/0
2025-01-03 | 2025-01-09 | Chinta Devi | 57.5972 | 8.2282 | TB408 | 73/0
2025-01-04 | 2025-01-09 | Ganesh Sinha | 38.8476 | 6.4746 | TB408 | 53/8
2025-01-05 | 2025-01-13 | Sunny Const | 57.5972 | 6.3997 | TB408 | 74/0
2025-01-10 | 2025-01-14 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/4
2025-01-08 | 2025-01-17 | Yogendra Mahto | 38.8476 | 3.8848 | TB408 | 43/1
2025-01-11 | 2025-01-18 | Bina Devi | 38.8476 | 4.856 | TB408 | 43/7
2025-01-10 | 2025-01-18 | Ganesh Sinha | 38.8476 | 4.3164 | TB408 | 53/7
2025-01-15 | 2025-01-19 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 73/5
2025-01-14 | 2025-01-19 | Sunny Const | 37.5044 | 6.2507 | TB408 | 73/7
2025-01-21 | 2025-01-27 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 72/0
2025-01-19 | 2025-01-29 | Bina Devi | 38.8476 | 3.5316 | TB408 | 43/6
2025-01-11 | 2025-01-29 | Sanjeev Kumar | 78.132 | 4.1122 | TB408 | 66/0
2025-01-19 | 2025-01-30 | Ganesh Sinha | 45.413 | 3.7844 | TB408 | 53/6
2025-01-28 | 2025-02-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 72/1
2025-01-29 | 2025-02-06 | Sanjeev Kumar | 37.5044 | 4.1672 | TB408 | 65/10
2025-02-02 | 2025-02-06 | Chinta Devi | 37.5044 | 7.5009 | TB408 | 72/2
2025-01-31 | 2025-02-07 | Sunny Const | 66.3811 | 8.2976 | TB408 | 51/0
2025-01-31 | 2025-02-10 | Bina Devi | 45.413 | 4.1285 | TB408 | 1A/1
2025-02-07 | 2025-02-10 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 71/8
2025-02-08 | 2025-02-14 | Sunny Const | 66.3811 | 9.483 | TB408 | 52/0
2025-02-05 | 2025-02-14 | Sobha Devi | 86.1293 | 8.6129 | TB408 | 49/0
2025-02-11 | 2025-02-15 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/7
2025-02-11 | 2025-02-18 | Bina Devi | 37.5044 | 4.688 | TB408 | 1A/2
2025-02-16 | 2025-02-19 | Chinta Devi | 37.5044 | 9.3761 | TB408 | 71/6
2025-02-15 | 2025-02-20 | Sobha Devi | 47.1844 | 7.8641 | TB408 | 50/5
2025-02-20 | 2025-02-24 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/5
2025-02-19 | 2025-02-28 | Bina Devi | 37.5044 | 3.7504 | TB408 | 1A/3
2025-02-25 | 2025-03-01 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/4
2025-03-01 | 2025-03-07 | Ganesh Sinha | 38.8476 | 5.5497 | TB408 | 53/5
2025-03-02 | 2025-03-07 | Chinta Devi | 45.413 | 7.5688 | TB408 | 71/3
2025-02-26 | 2025-03-10 | Jirwa Devi | 69.2287 | 5.3253 | TB408 | 58/0
2025-03-08 | 2025-03-12 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 71/2
2025-03-08 | 2025-03-16 | Sanjeev Kumar | 38.8476 | 4.3164 | TB408 | 70/3
2025-03-09 | 2025-03-17 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 53/4
2025-03-13 | 2025-03-18 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 71/1
2025-03-18 | 2025-03-25 | Ganesh Sinha | 45.413 | 5.6766 | TB408 | 53/3
2025-03-19 | 2025-03-25 | Chinta Devi | 60.0968 | 8.5853 | TB408 | 71/0
2025-03-20 | 2025-03-29 | Sanjeev Kumar | 38.8476 | 3.8848 | TB408 | 70/5
2025-03-26 | 2025-03-31 | Ganesh Sinha | 37.5044 | 6.2507 | TB408 | 53/2
2025-03-26 | 2025-03-31 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/11
2025-03-31 | 2025-04-02 | Sobha Devi | 38.8476 | 12.9492 | TB408 | 47/9
2025-03-31 | 2025-04-04 | Chinta Devi | 38.8476 | 7.7695 | TB408 | 70/10
2025-04-03 | 2025-04-06 | Sobha Devi | 37.5044 | 9.3761 | TB408 | 47/8
2025-04-06 | 2025-04-09 | Chinta Devi | 38.8476 | 9.7119 | TB408 | 70/9
2025-04-02 | 2025-04-11 | Ganesh Sinha | 47.1844 | 4.7184 | TB408 | 53/1
2025-03-13 | 2025-04-14 | Sunny Const | 86.1293 | 2.61 | TB408 | 68/0
2025-04-12 | 2025-04-28 | Ganesh Sinha | 70.7017 | 4.1589 | TB408 | 53/0
2025-04-27 | 2025-05-02 | Chinta Devi | 38.8476 | 6.4746 | TB408 | 70/4
2025-05-20 | 2025-05-29 | Sunny Construction | 81.4946 | 8.1495 | TB408 | 67/0
2025-05-10 | 2025-06-11 | Bhairo Mahto | 38.8476 | 1.1772 | TB408 | 1A/4
2025-06-11 | 2025-06-20 | Bhairo Mahto | 37.5044 | 3.7504 | TB408 | 1A/6
2025-06-17 | 2025-06-22 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 70/7
2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6
2025-06-04 | 2025-06-30 | Anil Kumar Kewat | 38.8476 | 1.4388 | TB408 | 1A/7
2025-06-22 | 2025-06-30 | Satyam Enterprises Vijay | 38.8476 | 4.3164 | TB408 | 70/2
2025-06-27 | 2025-07-01 | Jwala Singh | 38.8476 | 7.7695 | TB408 | 8/9
2025-06-28 | 2025-07-03 | Jwala Singh Suraj Kumar | 38.8476 | 6.4746 | TB408 | 69/1
2025-07-01 | 2025-07-08 | Satyam Enterprises Vijay | 38.8476 | 4.856 | TB408 | 70/1
2025-07-07 | 2025-07-19 | Jwala Singh | 38.8476 | 2.9883 | TB408 | 8/10
2025-07-03 | 2025-07-14 | Jwala Singh Suraj Kumar | 66.3811 | 5.5318 | TB408 | 70/0
2025-07-08 | 2025-07-14 | Satyam Enterprises Vijay | 38.8476 | 5.5497 | TB408 | 70/8
2025-06-11 | 2025-07-15 | Anil Kumar Kewat | 37.5044 | 1.0716 | TB408 | 1A/8
2025-07-11 | 2025-07-16 | Arawali 2 | 37.5044 | 6.2507 | TB408 | 2/8
2025-07-14 | 2025-07-21 | Jwala Singh Suraj Kumar | 57.5972 | 7.1997 | TB408 | 69/0
2025-07-19 | 2025-07-22 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/3
2025-07-16 | 2025-07-23 | Arawali 2 | 37.5044 | 4.688 | TB408 | 2/9
2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3
2025-07-21 | 2025-07-24 | Hazarilal Yadav Poonam Kumari | 38.8476 | 9.7119 | TB408 | 26/2
2025-07-10 | 2025-07-26 | Bhairo Mahto Kewat | 37.5044 | 2.2061 | TB408 | 1A/5
2025-07-23 | 2025-07-26 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/2
2025-07-25 | 2025-07-28 | Hazarilal Yadav Poonam Kumari | 37.5044 | 9.3761 | TB408 | 26/3
2025-07-23 | 2025-07-28 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/4
2025-07-26 | 2025-07-29 | Satyam Enterprises | 37.5044 | 9.3761 | TB408 | 44/1
2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0
2025-07-23 | 2025-07-30 | Arawali 2 | 38.8476 | 4.856 | TB408 | 2/7
2025-07-27 | 2025-07-31 | Pusplata Praful | 37.5044 | 7.5009 | TB408 | 25/4
2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2
2025-07-27 | 2025-07-31 | Pusplata Kailash | 38.8476 | 7.7695 | TB408 | 27/3
2025-07-29 | 2025-08-03 | Satyam Enterprises | 60.0968 | 10.0161 | TB408 | 44/0
2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0
2025-07-30 | 2025-08-04 | Jwala Singh | 38.8476 | 6.4746 | TB408 | 29/1
2025-07-28 | 2025-08-03 | Satyam Enterprises | 47.1844 | 6.7406 | TB408 | 44/7
2025-07-26 | 2025-08-05 | Vinay Construction | 38.8476 | 3.5316 | TB408 | 47/7
2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5
2025-08-01 | 2025-08-06 | Pusplata Kailash | 38.8476 | 6.4746 | TB408 | 30/3
2025-07-28 | 2025-08-06 | Satyam Enterprises | 70.7017 | 7.0702 | TB408 | 44/10
2025-07-31 | 2025-08-09 | Pusplata Praful | 37.5044 | 3.7504 | TB408 | 25/3
2025-08-04 | 2025-08-09 | Satyam Enterprises | 47.1844 | 7.8641 | TB408 | 44/5
2025-07-25 | 2025-08-09 | Bhairo Mahto | 37.5044 | 2.344 | TB408 | 4/1
2025-08-04 | 2025-08-09 | Jwala Singh | 37.5044 | 6.2507 | TB408 | 8/12
2025-07-30 | 2025-08-12 | Jwala Singh | 57.5972 | 4.1141 | TB408 | 29/0
2025-08-07 | 2025-08-13 | Shobha Devi | 45.413 | 6.4876 | TB408 | 55/8
2025-07-29 | 2025-08-13 | Priyanka Devi Subodh | 66.3811 | 4.1488 | TB408 | 2/0
2025-08-09 | 2025-08-16 | Satyam Enterprises | 60.0968 | 7.5121 | TB408 | 44/6
2025-08-04 | 2025-08-16 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/2
2025-08-10 | 2025-08-17 | Rahul Kumar | 38.8476 | 4.856 | TB408 | 40/3
2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0
2025-08-13 | 2025-08-17 | Shobha Devi | 37.5044 | 7.5009 | TB408 | 55/7
2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3
2025-08-06 | 2025-08-17 | Pusplata Kailash | 38.8476 | 3.2373 | TB408 | 30/5
2025-08-09 | 2025-08-17 | Pusplata Ramchandra | 38.8476 | 4.3164 | TB408 | 27/4
2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11
2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4
2025-08-12 | 2025-08-19 | Jwala Singh | 47.1844 | 5.898 | TB408 | 28/5
2025-08-04 | 2025-08-19 | Usha Tower | 38.8476 | 2.428 | TB408 | 2/5
2025-07-07 | 2025-08-20 | Bhairo Mahto Kewat | 86.1293 | 1.914 | TB408 | 1/0
2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1
2025-08-17 | 2025-08-21 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 30/6
2025-07-30 | 2025-08-22 | Bhairo Mahto | 37.5044 | 1.5627 | TB408 | 4/2
2025-08-06 | 2025-08-22 | Vinay Construction | 38.8476 | 2.2852 | TB408 | 47/4
2025-08-16 | 2025-08-23 | Pusplata Dharamveer | 38.8476 | 4.856 | TB408 | 27/1
2025-08-17 | 2025-08-24 | Satyam Enterprises | 47.1844 | 5.898 | TB408 | 44/9
2025-08-17 | 2025-08-24 | Sunny Construction | 37.5044 | 4.688 | TB408 | 55/1
2025-08-18 | 2025-08-24 | Rahul Kumar | 38.8476 | 5.5497 | TB408 | 40/2
2025-08-19 | 2025-08-25 | Jwala Singh | 37.5044 | 5.3578 | TB408 | 28/2
2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0
2025-08-20 | 2025-08-25 | Pusplata Ashok | 37.5044 | 6.2507 | TB408 | 4/4
2025-08-21 | 2025-08-25 | Sobha Devi | 38.8476 | 7.7695 | TB408 | 57/2
2025-08-19 | 2025-08-25 | Chinta Devi | 37.5044 | 5.3578 | TB408 | 44/11
2025-08-22 | 2025-08-26 | Pusplata Kailash | 37.5044 | 7.5009 | TB408 | 31/1
2025-08-17 | 2025-08-29 | Vinay Construction | 47.1844 | 3.6296 | TB408 | 47/3
2025-08-21 | 2025-08-29 | Sobha Devi | 37.5044 | 4.1672 | TB408 | 57/1
2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1
2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10
2025-08-22 | 2025-08-30 | Ganesh Sinha | 37.5044 | 4.1672 | TB408 | 36/2
2025-08-17 | 2025-08-30 | Jirwa Devi | 47.1844 | 3.3703 | TB408 | 52/3
2025-08-23 | 2025-08-31 | Bhairo Mahto | 38.8476 | 4.3164 | TB408 | 8/1
2025-08-17 | 2025-08-31 | Sunny Construction | 47.1844 | 3.1456 | TB408 | 54/5
2025-08-29 | 2025-08-31 | Pusplata Ashok | 37.5044 | 12.5015 | TB408 | 4/3
2025-08-25 | 2025-08-31 | Chinta Devi | 47.1844 | 6.7406 | TB408 | 45/1
2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0
2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3
2025-08-26 | 2025-09-02 | Pusplata Kailash | 37.5044 | 4.688 | TB408 | 31/2
2025-08-23 | 2025-09-03 | Pusplata Dharamveer | 66.3811 | 5.5318 | TB408 | 27/0
2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5
2025-08-29 | 2025-09-04 | Jwala Singh | 38.8476 | 5.5497 | TB408 | 8/4
2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0
2025-08-30 | 2025-09-06 | Ganesh Sinha | 37.5044 | 4.688 | TB408 | 36/3
2025-08-22 | 2025-09-06 | Vinay Construction | 38.8476 | 2.428 | TB408 | 47/6
2025-09-01 | 2025-09-06 | Sunny Construction | 47.1844 | 7.8641 | TB408 | 54/4
2025-08-26 | 2025-09-06 | Pusplata Rajaram | 57.5972 | 4.7998 | TB408 | 26/0
2025-09-01 | 2025-09-07 | Chinta Devi | 38.8476 | 5.5497 | TB408 | 47/1
2025-09-02 | 2025-09-07 | Priyanka Devi Sudheer | 37.5044 | 6.2507 | TB408 | 20/2
2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0
2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4
2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6
2025-09-03 | 2025-09-10 | Pusplata Kailash | 38.8476 | 4.856 | TB408 | 32/1
2025-09-01 | 2025-09-10 | Jirwa Devi | 47.1844 | 4.7184 | TB408 | 52/4
2025-09-03 | 2025-09-11 | Satyam Enterprises Vijay | 37.5044 | 4.1672 | TB408 | 34/3
2025-09-09 | 2025-09-12 | Priyanka Devi Sudheer | 38.8476 | 9.7119 | TB408 | 21/4
2025-09-03 | 2025-09-12 | Jwala Singh 1 | 57.5972 | 5.7597 | TB408 | 28/0
2025-09-05 | 2025-09-12 | Usha Tower | 37.5044 | 4.688 | TB408 | 6/2
2025-09-07 | 2025-09-12 | Sunny Construction | 45.413 | 7.5688 | TB408 | 54/3
2025-09-03 | 2025-09-13 | Sheetal Singh 1 | 38.8476 | 3.5316 | TB408 | 2/1
2025-08-30 | 2025-09-14 | Shobha Devi | 143.6019 | 8.9751 | TB408 | 56/0
2025-09-07 | 2025-09-16 | Pusplata Rajaram | 37.5044 | 3.7504 | TB408 | 26/1
2025-08-29 | 2025-09-16 | Nirmal Mahto | 38.8476 | 2.0446 | TB408 | 36/1
2025-09-07 | 2025-09-16 | Ganesh Sinha | 45.413 | 4.5413 | TB408 | 36/4
2025-09-13 | 2025-09-18 | Sunny Construction | 38.8476 | 6.4746 | TB408 | 54/1
2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5
2025-09-10 | 2025-09-20 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/2
2025-09-09 | 2025-09-22 | Priyanka Devi Subodh | 38.8476 | 2.7748 | TB408 | 2/2
2025-09-19 | 2025-09-22 | Priyanka Devi Sudheer | 45.413 | 11.3533 | TB408 | 21/5
2025-09-19 | 2025-09-22 | Sunny Construction | 38.8476 | 9.7119 | TB408 | 54/2
2025-09-09 | 2025-09-22 | Vivek Ganju | 37.5044 | 2.6789 | TB408 | 43/3
2025-09-10 | 2025-09-23 | Jwala Singh 1 | 37.5044 | 2.6789 | TB408 | 29/3
2025-09-12 | 2025-09-23 | Bhairo Mahto | 38.8476 | 3.2373 | TB408 | 8/2
2025-09-09 | 2025-09-25 | Chinta Devi | 143.6019 | 8.4472 | TB408 | 47/0
2025-08-29 | 2025-09-26 | Pusplata Ramchandra | 38.8476 | 1.3396 | TB408 | 27/11
2025-09-16 | 2025-09-27 | Nirmal Mahto | 57.5972 | 4.7998 | TB408 | 36/0
2025-09-16 | 2025-09-27 | Ganesh Sinha | 57.5972 | 4.7998 | TB408 | 37/0
2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0
2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5
2025-09-15 | 2025-09-29 | Shobha Devi | 143.6019 | 9.5735 | TB408 | 57/0
2025-09-20 | 2025-09-30 | Jirwa Devi | 45.413 | 4.1285 | TB408 | 52/1
2025-09-22 | 2025-09-30 | Sunny Construction | 67.8737 | 7.5415 | TB408 | 54/0
2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3
2025-09-25 | 2025-10-03 | Sheetal Singh 1 | 37.5044 | 4.1672 | TB408 | 6/1
2025-09-27 | 2025-10-06 | Nirmal Mahto | 37.5044 | 3.7504 | TB408 | 35/5
2025-09-22 | 2025-10-07 | Vivek Ganju | 37.5044 | 2.344 | TB408 | 42/6
2025-09-29 | 2025-10-08 | Shobha Devi | 66.3811 | 6.6381 | TB408 | 40/0
2025-10-03 | 2025-10-10 | Priyanka Devi Subodh | 37.5044 | 4.688 | TB408 | 10/1
|  | Nan |  |  | TB408
|  | Gang Name |  |  | TB408
2025-10-09 |  | Shobha Devi |  |  | TB408
2025-09-30 |  | Jirwa Devi |  |  | TB408
2025-09-30 |  | Sunny Construction |  |  | TB408
2025-09-29 |  | Chinta Devi |  |  | TB408
2025-10-07 |  | Nirmal Mahto |  |  | TB408
|  | Priyanka Devi Subodh |  |  | TB408
2025-10-07 |  | Panva Devi |  |  | TB408
2025-10-10 |  | Ganesh Sinha |  |  | TB408
2025-10-10 |  | Vinay Construction |  |  | TB408
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-01 | 2025-10-09 | Subash | 72.63 | 8.07 | TA421 | 1/0 | Completed
2025-09-27 | 2025-10-09 | Hassan | 36.37 | 2.7977 | TA421 | 39/2 | Completed
2025-09-13 |  | Praveen | 43.079 |  | TA421 | 39/7 | Top Section under Progress
|  | Rajiv Yadhav | 37.931 |  | TA421 | 43/5 | Material Shifting Done
2025-10-07 |  | D K Verma | 36.37 |  | TA421 | 43/3 | 3rd Section Under Progress
2025-10-07 |  | Khatun | 39.17 |  | TA421 | 9/3 | 3rd Section Under Completed
|  | Rajiv Yadhav | 44.851 |  | TA421 | 39/9 | Material Shifting Done
2025-10-10 |  | Hassan | 37.931 |  | TA421 | 36/7 | Material Shifting Done
2025-10-10 |  | Subash | 37.72 |  | TA421 | 4/3 | Ground Assembling Completed
|  | Nan | 6298.0423 |  | TA505 |  | 134
2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-10-10 | Jhemon Mahato 2 | 85.264 | 4.7369 | TA505 | 144A/0 | Completed
2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress
2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress
2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-02 | 2025-10-10 | Pankaj Singh Mp | 36.1598 | 4.0178 | TA505 | 167/2 | Completed
2025-10-08 |  | Paramanand 1 | 35.602 |  | TA505 | 160/1 | In-Progress
2025-10-09 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 169/5 | In-Progress
2025-10-10 |  | Jhemon Mahato 2 | 37.931 |  | TA505 | 140/1 | In-Progress
2025-10-10 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/3 | In-Progress

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status | Issues
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
2025-09-29 |  | M S Mdpl | 60 |  | TA416 | 54/0 | Material shifting work under progress. | Missing start/end date (not expanded)
2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416 | 6/2 | COMPLETED | Completion on/after 2025-10-14 (not expanded)
2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416 | 38/3 | COMPLETED | Completion on/after 2025-10-14 (not expanded)
2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED | Single-occurrence gang (not expanded)
2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-25 |  | Pritam Enterprises 2 | 66.7809 |  | TA413 | 3B/0 | WIP | Missing start/end date (not expanded)
2025-09-25 |  | Jwala Singh 1 | 72.1555 |  | TA413 | 4/0 | WIP | Missing start/end date (not expanded)
2025-09-30 |  | Fouzi Ratto | 70.7883 |  | TA413 | 46/0 | WIP | Missing start/end date (not expanded)
2025-10-05 |  | Govind Mahto 2 | 137.0461 |  | TA413 | 15/0 | WIP | Missing start/end date (not expanded)
2025-10-01 |  | Punam Kumari 1 | 87.0213 |  | TA413 | 20/0 | WIP | Missing start/end date (not expanded)
2025-10-02 |  | Pritam Enterprises 1 | 65.0278 |  | TA413 | 10/0 | WIP | Missing start/end date (not expanded)
2025-10-08 |  | Pritam Enterprises 4 | 62.4437 |  | TA413 | 29/0 | WIP | Missing start/end date (not expanded)
2025-10-07 |  | Jwala Singh 2 | 43.8044 |  | TA413 | 29/1 | WIP | Missing start/end date (not expanded)
2025-10-06 |  | Sk Samiul 1 | 55.4509 |  | TA413 | 29A/0 | WIP | Missing start/end date (not expanded)
2025-10-05 |  | Amar Kumar Singh | 66.7809 |  | TA413 | 41/0 | WIP | Missing start/end date (not expanded)
2025-10-05 |  | Bhairaw Mahto | 65.8725 |  | TA413 | 17/0 | ROW | Missing start/end date (not expanded)
2025-10-09 |  | Govind Mahto 1 | 37.9311 |  | TA413 | 3B/1 | WIP | Missing start/end date (not expanded)
2025-10-10 |  | Ved Prakash | 173.5609 |  | TA413 | 26/0 | WIP | Missing start/end date (not expanded)
2025-10-10 |  | Kartik Mahto | 35.6018 |  | TA413 | 40/8 | WIP | Missing start/end date (not expanded)
|  | Punam Kumari 4 |  |  | TA413 | No front | WIP | Missing start/end date (not expanded)
2025-10-11 |  | Pritam Enterprises 3 | 77.0769 |  | TA413 | 3A/0 | WIP | Missing start/end date (not expanded)
2025-10-11 |  | Punam Kumari 2 | 45.697 |  | TA413 | 18/6 | WIP | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 | SL No |  | Missing start/end date (not expanded)
|  | Pw Mt |  |  | TA413 |  | Construction Revenue | Missing start/end date (not expanded)
|  | Nan |  |  | TA413 | Tower with extensions Up to +9M |  | Missing start/end date (not expanded)
1970-01-01 | 1970-01-01 | 0 030435 | 1.505 |  | TA413 | 1 | 336894.66109103995 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030628999999999997 | 1.5497 |  | TA413 | 2 | 353397.87792192 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030759 | 1.7006 |  | TA413 | 3 | 408118.80970016 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 031055 | 1.76 |  | TA413 | 4 | 425751.84245048004 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030223 | 1.4915 |  | TA413 | 5 | 331695.92027207994 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030211 | 1.4612 |  | TA413 | 6 | 324131.0934004 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030687 | 1.674 |  | TA413 | 7 | 399895.72013196 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030518999999999998 | 1.5328 |  | TA413 | 8 | 346011.82257615996 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 059184 | 2.4809 |  | TA413 | 9 | 516626.7066308401 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061852 | 2.5394 |  | TA413 | 10 | 540033.5900996401 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 074512 | 2.838 |  | TA413 | 11 | 605853.4124983599 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 07460800000000001 | 2.9307 |  | TA413 | 12 | 622186.96967284 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 06618600000000001 | 2.5025 |  | TA413 | 13 | 554357.83097552 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 069438 | 2.5514 |  | TA413 | 14 | 578726.2868670401 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 081 | 2.869 |  | TA413 | 15 | 646365.09184 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 08204600000000001 | 2.9645 |  | TA413 | 16 | 672261.6212936001 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061932 | 2.5712 |  | TA413 | 17 | 581778.01780904 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 06503999999999999 | 2.6698 |  | TA413 | 18 | 613723.39383056 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 062996 | 2.5335 |  | TA413 | 19 | 626666.7578995199 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061876 | 2.474 |  | TA413 | 20 | 604516.62297832 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 058150999999999994 | 2.569 |  | TA413 | 21 | 682407.73458832 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 059057000000000005 | 2.692 |  | TA413 | 22 | 718113.44313488 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 067222 | 3.0084 |  | TA413 | 23 | 774541.76037784 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 069954 | 3.166 |  | TA413 | 24 | 810763.9013656001 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 07859000000000001 | 3.5674 |  | TA413 | 25 | 949875.98724928 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 08738 | 2.993 |  | TA413 | 26 | 659522.9388825999 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 09733599999999998 | 3.3936 |  | TA413 | 27 | 902614.5275160001 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10176600000000001 | 4.2034 |  | TA413 | 28 | 1164138.7107916798 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 4.3876 |  | TA413 | 29 | 1276836.69812608 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 5.1781 |  | TA413 | 30 | 1617039.24735808 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 11 | 2.868 |  | TA413 | 31 | 766434.7400023598 | Non-positive duration (Start > End or 0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030435 | 1.505 |  | TA413 | 1 | 336894.66109103995 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030628999999999997 | 1.5497 |  | TA413 | 2 | 353397.87792192 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030759 | 1.7006 |  | TA413 | 3 | 408118.80970016 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 031055 | 1.76 |  | TA413 | 4 | 425751.84245048004 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030223 | 1.4915 |  | TA413 | 5 | 331695.92027207994 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030211 | 1.4612 |  | TA413 | 6 | 324131.0934004 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030687 | 1.674 |  | TA413 | 7 | 399895.72013196 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030518999999999998 | 1.5328 |  | TA413 | 8 | 346011.82257615996 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 059184 | 2.4809 |  | TA413 | 9 | 516626.7066308401 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 061852 | 2.5394 |  | TA413 | 10 | 540033.5900996401 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 074512 | 2.838 |  | TA413 | 11 | 605853.4124983599 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 07460800000000001 | 2.9307 |  | TA413 | 12 | 622186.96967284 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 06618600000000001 | 2.5025 |  | TA413 | 13 | 554357.83097552 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 069438 | 2.5514 |  | TA413 | 14 | 578726.2868670401 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 081 | 2.869 |  | TA413 | 15 | 646365.09184 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 08204600000000001 | 2.9645 |  | TA413 | 16 | 672261.6212936001 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 061932 | 2.5712 |  | TA413 | 17 | 581778.01780904 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 06503999999999999 | 2.6698 |  | TA413 | 18 | 613723.39383056 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 062996 | 2.5335 |  | TA413 | 19 | 626666.7578995199 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 061876 | 2.474 |  | TA413 | 20 | 604516.62297832 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 058150999999999994 | 2.569 |  | TA413 | 21 | 682407.73458832 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 059057000000000005 | 2.692 |  | TA413 | 22 | 718113.44313488 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 067222 | 3.0084 |  | TA413 | 23 | 774541.76037784 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 069954 | 3.166 |  | TA413 | 24 | 810763.9013656001 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 07859000000000001 | 3.5674 |  | TA413 | 25 | 949875.98724928 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 08738 | 2.993 |  | TA413 | 26 | 659522.9388825999 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 09733599999999998 | 3.3936 |  | TA413 | 27 | 902614.5275160001 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 10176600000000001 | 4.2034 |  | TA413 | 28 | 1164138.7107916798 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 4.3876 |  | TA413 | 29 | 1276836.69812608 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 5.1781 |  | TA413 | 30 | 1617039.24735808 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 11 | 2.868 |  | TA413 | 31 | 766434.7400023598 | Start before 2021-01-01 (not expanded)
1970-01-01 | 1970-01-01 | 0 030435 | 1.505 |  | TA413 | 1 | 336894.66109103995 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030628999999999997 | 1.5497 |  | TA413 | 2 | 353397.87792192 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030759 | 1.7006 |  | TA413 | 3 | 408118.80970016 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 031055 | 1.76 |  | TA413 | 4 | 425751.84245048004 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030223 | 1.4915 |  | TA413 | 5 | 331695.92027207994 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030211 | 1.4612 |  | TA413 | 6 | 324131.0934004 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030687 | 1.674 |  | TA413 | 7 | 399895.72013196 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 030518999999999998 | 1.5328 |  | TA413 | 8 | 346011.82257615996 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 059184 | 2.4809 |  | TA413 | 9 | 516626.7066308401 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061852 | 2.5394 |  | TA413 | 10 | 540033.5900996401 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 074512 | 2.838 |  | TA413 | 11 | 605853.4124983599 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 07460800000000001 | 2.9307 |  | TA413 | 12 | 622186.96967284 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 06618600000000001 | 2.5025 |  | TA413 | 13 | 554357.83097552 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 069438 | 2.5514 |  | TA413 | 14 | 578726.2868670401 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 081 | 2.869 |  | TA413 | 15 | 646365.09184 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 08204600000000001 | 2.9645 |  | TA413 | 16 | 672261.6212936001 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061932 | 2.5712 |  | TA413 | 17 | 581778.01780904 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 06503999999999999 | 2.6698 |  | TA413 | 18 | 613723.39383056 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 062996 | 2.5335 |  | TA413 | 19 | 626666.7578995199 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 061876 | 2.474 |  | TA413 | 20 | 604516.62297832 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 058150999999999994 | 2.569 |  | TA413 | 21 | 682407.73458832 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 059057000000000005 | 2.692 |  | TA413 | 22 | 718113.44313488 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 067222 | 3.0084 |  | TA413 | 23 | 774541.76037784 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 069954 | 3.166 |  | TA413 | 24 | 810763.9013656001 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 07859000000000001 | 3.5674 |  | TA413 | 25 | 949875.98724928 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 08738 | 2.993 |  | TA413 | 26 | 659522.9388825999 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 09733599999999998 | 3.3936 |  | TA413 | 27 | 902614.5275160001 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10176600000000001 | 4.2034 |  | TA413 | 28 | 1164138.7107916798 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 4.3876 |  | TA413 | 29 | 1276836.69812608 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 10993 | 5.1781 |  | TA413 | 30 | 1617039.24735808 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
1970-01-01 | 1970-01-01 | 0 11 | 2.868 |  | TA413 | 31 | 766434.7400023598 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | Completed | Single-occurrence gang (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Gang Name |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-10-09 |  | Shobha Devi |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-09-30 |  | Jirwa Devi |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-09-30 |  | Sunny Construction |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-09-29 |  | Chinta Devi |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-10-07 |  | Nirmal Mahto |  |  | TB408 |  |  | Missing start/end date (not expanded)
|  | Priyanka Devi Subodh |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-10-07 |  | Panva Devi |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-10-10 |  | Ganesh Sinha |  |  | TB408 |  |  | Missing start/end date (not expanded)
2025-10-10 |  | Vinay Construction |  |  | TB408 |  |  | Missing start/end date (not expanded)
2024-09-27 | 2024-10-06 | Khublal Mahto | 38.8476 | 3.8848 | TB408 | 10/14 |  | Single-occurrence gang (not expanded)
2025-05-19 | 2025-06-28 | Satyam Enterprises Santosh | 38.8476 | 0.9475 | TB408 | 70/6 |  | Single-occurrence gang (not expanded)
2025-07-14 | 2025-07-23 | Priyanka Devi 2 | 37.5044 | 3.7504 | TB408 | 18/3 |  | Single-occurrence gang (not expanded)
2025-07-01 | 2025-07-29 | Bhairo Mahto Priyanka Devi Subodh | 86.1293 | 2.97 | TB408 | 1A/0 |  | Single-occurrence gang (not expanded)
2025-07-21 | 2025-07-31 | Dharmendra Munnilal Pusplata | 38.8476 | 3.5316 | TB408 | 27/2 |  | Single-occurrence gang (not expanded)
2025-07-25 | 2025-08-02 | Arawali 1 | 86.1293 | 9.5699 | TB408 | 12/0 |  | Single-occurrence gang (not expanded)
2025-08-01 | 2025-08-05 | Priyanka Devi | 37.5044 | 7.5009 | TB408 | 19/5 |  | Single-occurrence gang (not expanded)
2025-08-06 | 2025-08-17 | Sintu Pawan Satyam Enterprises | 66.3811 | 5.5318 | TB408 | 45/0 |  | Single-occurrence gang (not expanded)
2025-08-04 | 2025-08-17 | Sheetal Singh | 38.8476 | 2.7748 | TB408 | 2/3 |  | Single-occurrence gang (not expanded)
2025-08-12 | 2025-08-18 | Satyam Manish | 38.8476 | 5.5497 | TB408 | 43/11 |  | Single-occurrence gang (not expanded)
2025-08-13 | 2025-08-18 | Pusplata Pankaj | 38.8476 | 6.4746 | TB408 | 17/4 |  | Single-occurrence gang (not expanded)
2025-08-10 | 2025-08-21 | Gauri Shankar | 70.7017 | 5.8918 | TB408 | 41/1 |  | Single-occurrence gang (not expanded)
2025-08-18 | 2025-08-25 | Pusplata | 66.3811 | 8.2976 | TB408 | 18/0 |  | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-30 | Pusplata Deepak | 37.5044 | 6.2507 | TB408 | 30/1 |  | Single-occurrence gang (not expanded)
2025-08-25 | 2025-08-30 | Satyam Enterprises Pawan | 38.8476 | 6.4746 | TB408 | 43/10 |  | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-03 | Pusplata Santosh Pankaj Singh | 66.3811 | 7.3757 | TB408 | 14A/0 |  | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-03 | Priyanka Devi Santosh | 37.5044 | 4.1672 | TB408 | 20/3 |  | Single-occurrence gang (not expanded)
2025-08-29 | 2025-09-03 | Satyam Enterprises Manish | 38.8476 | 6.4746 | TB408 | 43/5 |  | Single-occurrence gang (not expanded)
2025-09-02 | 2025-09-05 | Sudheer 2 Priyanka Devi | 57.5972 | 14.3993 | TB408 | 21/0 |  | Single-occurrence gang (not expanded)
2025-08-26 | 2025-09-07 | Pusplata Praphul | 89.9096 | 6.9161 | TB408 | 24/0 |  | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-09 | Sheetal Singh 2 | 38.8476 | 2.2852 | TB408 | 2/4 |  | Single-occurrence gang (not expanded)
2025-08-24 | 2025-09-09 | Anvi Construction | 38.8476 | 2.2852 | TB408 | 2/6 |  | Single-occurrence gang (not expanded)
2025-09-12 | 2025-09-18 | Jwala Singh 2 | 38.8476 | 5.5497 | TB408 | 8/5 |  | Single-occurrence gang (not expanded)
2025-09-20 | 2025-09-29 | Priyanka Devi Sontosh | 57.5972 | 5.7597 | TB408 | 20/0 |  | Single-occurrence gang (not expanded)
2025-09-07 | 2025-09-29 | Vinay Construction Chinta Devi | 37.5044 | 1.6306 | TB408 | 47/5 |  | Single-occurrence gang (not expanded)
2025-09-10 | 2025-09-30 | Shri Shyam Construction | 45.413 | 2.1625 | TB408 | 21/3 |  | Single-occurrence gang (not expanded)
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed | Missing start/end date (not expanded)
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed | Missing start/end date (not expanded)
2025-09-13 |  | Praveen | 43.079 |  | TA421 | 39/7 | Top Section under Progress | Missing start/end date (not expanded)
|  | Rajiv Yadhav | 37.931 |  | TA421 | 43/5 | Material Shifting Done | Missing start/end date (not expanded)
2025-10-07 |  | D K Verma | 36.37 |  | TA421 | 43/3 | 3rd Section Under Progress | Missing start/end date (not expanded)
2025-10-07 |  | Khatun | 39.17 |  | TA421 | 9/3 | 3rd Section Under Completed | Missing start/end date (not expanded)
|  | Rajiv Yadhav | 44.851 |  | TA421 | 39/9 | Material Shifting Done | Missing start/end date (not expanded)
2025-10-10 |  | Hassan | 37.931 |  | TA421 | 36/7 | Material Shifting Done | Missing start/end date (not expanded)
2025-10-10 |  | Subash | 37.72 |  | TA421 | 4/3 | Ground Assembling Completed | Missing start/end date (not expanded)
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed | Single-occurrence gang (not expanded)
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed | Single-occurrence gang (not expanded)
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed | Single-occurrence gang (not expanded)
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed | Single-occurrence gang (not expanded)
2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed | Single-occurrence gang (not expanded)
|  | Nan | 6298.0423 |  | TA505 |  | 134 | Missing start/end date (not expanded)
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress | Missing start/end date (not expanded)
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress | Missing start/end date (not expanded)
2025-10-08 |  | Paramanand 1 | 35.602 |  | TA505 | 160/1 | In-Progress | Missing start/end date (not expanded)
2025-10-09 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 169/5 | In-Progress | Missing start/end date (not expanded)
2025-10-10 |  | Jhemon Mahato 2 | 37.931 |  | TA505 | 140/1 | In-Progress | Missing start/end date (not expanded)
2025-10-10 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/3 | In-Progress | Missing start/end date (not expanded)
|  | Nan | 6298.0423 |  | TA505 |  | 134 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed | Single-occurrence gang (not expanded)
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed | Single-occurrence gang (not expanded)
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed | Single-occurrence gang (not expanded)
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed | Single-occurrence gang (not expanded)
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed | Single-occurrence gang (not expanded)

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
DPR TA-416 __ Dt.-08-10-25 (PGCIL).xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1.0, 2.0, 3.0, 4.0
DPR - TA-413.xlsx | TA413 | Erection Compiled | 0 | cumm. sr.no, month sr.no, location no, type of tower, starting date, completion date, gang name, tower weight, revenue, name of supervisor, status, prop. name
DPR - TB - 408 10-10-2025.xlsx | TB408 | Erection Compiled | 3 | sl no, month sl.no, location no, tower type, classification, starting date, completion date, gang name, gang strength, tower weight, status, nan, nan, nan, nan, nan, nan, nan, nan, nan
DPR TA 421 .xlsx | TA421 | Erection Compiled | 1 | sl no, location no, tower type, classification, starting date, tower weight, status, completion date, gang name, gang strength
DPR TA-505 10-10-2025.xlsx | TA505 | Erection Compiled | 3 | nan, sr. no, location no, tower type, tower weight, rev(inr), month of execution, gang name, status, starting date, completion date, no of compl. days, region, remarks if any

## ProjectDetails
project_code | project_name | client_name | noa_start | loa_end | project_mgr | regional_mgr | planning_eng | pch | section_inch | supervisor | _source_file | Project Name
TA 418 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 2024-02-07 | 2025-11-06 | Mr Sanjay Gupta | Mr Rajiv Sharma | Sanjib Samantaray | Mr Arun Felbin | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, Saidur, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | DPR TA-416 __ Dt.-08-10-25 (PGCIL).xlsx | TA416
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Anil Kumar Sharma | Mr. Tushar Grover | Mr. Santosh Mishra | Mr. Sanjay Gupta | Surendra Kumar Patel, Kartik Jhorar, Shuvam Gupta, Govind Bhardwaj | Suraj Chaudhary, Rudra Prasad, Aman Kumar Singh, Manoj Gupta, Raju Mahto, Khublal Mahto, Sushil Kumar, Haridashn, Manoj Kumar chaudhary, Nabirul Islam, Sanjay Kumar, Rahul Ravidas, Narayan Mahto, Akbar Ali, Kamal Ravidas, Manirul Islam, Tarique Anwar, Raju Prasad, Abhay Ojha | DPR - TA-413.xlsx | TA413
TB408 | 765 KV Beawer Transmission Line, PKG F | Resonia Limited | 2023-12-06 | 2025-10-30 | Mr. Partha Pal | Mr. Sandeep Singh Kumar | Mr. Raghav Ranjan | Mr. Sanjay Kumar Gupta | Sumit Kumar, Vivek Shukla, Vivek Kumar, Vijay Yadav, Ram Tirath Singh | Pradeep Kumar, Vikas Kumar, Ganesh Singh, Dineshwar Mahto, Kamla Pal Prasad, Bisun Saw, Shakib Hussain, Umesh Prasad, Prince Kumar Nirala, Pramod Kumar Sahoo, Jainath Mahto, Rajesh Pal, Ramji Tanti, Rakesh Pramanik, Sam Mahammad, Suresh Kumar Pal, Hulas Kumar Mahto, Akash Dadarao Thul, Vaibhav Sharma, Dasharath Mahto, Mukesh Kumar, Dashrath Mahto, Kartik Mahato, Gangadin Sahu, Dev Narayan Mahto, Ashok Kumar, Debananda Ray, Dev Prakash, Jai Lal Mahto, Jitendra Kumar, Deo Prakash, Tribhuwan Mahto, Umesh Kumar Mahto, Rahul Sharma, Karan Pal Singh, Pritish Kumar Pradhan, Akshay Lal, Laxman, Jaylal Mahto | DPR - TB - 408 10-10-2025.xlsx | TB408
TA 421 | 765KV D/C HEXA BIDAR PS - MAHESHWARAM (PG) TL | Power Grid Bidar | 2024-02-15 | 2025-11-14 | Mr. Appala Naidu | Mr. Ajith Kumar | Mr. Bharath A D | Mr.Arun Felbin | Mr.Manikandan, Mr. Satyam Tiwari | Mr. Ramasish, Mr. Godvin John, Mr. Karunakar Nayak, Mr. Sudalaimuthu, Mr. Susanthpal, Mr. Srinivasan, Mr. Bhim Mahto, Mr. Ganesan, Mr. Ballu Thakur, Mr. Chandrasekar, Mr.Chandrasekharan, Mr. Anand | DPR TA 421 .xlsx | TA421
TA 505 | 765 Kv D/C Beawar-Mandsaur T/L | PBMTL | 2024-07-22 | 2026-06-21 | Mr. Sushil Kr Tiwari | Mr. Vijay Kute | Mr. Partha Pratim Pal | Mr. Arun Felbin | Mr.Deepak Anand, Mr.Bapan Mandal, Mr.Panneri Satish, Mr.Vinod Hankare | Nunuchand Mahto, Birkha Subba, Dilip Kumar, Teklal Mahato, Munid Meena, Mortuj Ali, Devdas Malik, Jayprakash Nishad, Kumar Singh, K. Sanjeevan, Mridul Baruah, Binda Shah, Prasanta Sahana, Lalit Sahoo, Sujit Roy, Ramprasad, Gourshankar, Vipin Mall, Aadesh | DPR TA-505 10-10-2025.xlsx | TA505

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Completion date must be before 2025-10-14 (future completions go to 'Data Issues').
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gangs that performed erection only once (per Project+Gang) are not expanded and are logged in 'Data Issues'.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' â†’ 'Xyz 4').
- Sheets:
â€¢ ProdDailyExpanded : per-day expanded rows used by the dashboard
â€¢ ProdDailyExpandedSingles : per-day expanded rows including single-occurrence gangs
â€¢ RawData : per-erection rows (unexpanded), for traceability
â€¢ Data Issues : row-level data problems (reason in 'Issues' column)
â€¢ Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
â€¢ Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.

## MicroPlanResponsibilities
project_key | project_name | entity_type | entity_name | location_no | revenue_planned | revenue_realised | tower_weight | tower_type | manpower | power_tools_issued | material_feeding | starting_date | completion_date | tack_welding | final_checking
ta413 | TA413 | Gang | Govind Mahto-01 | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Gang | Govind Mahto-01 | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Govind Mahto-01 | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Govind Mahto-01 | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Jawla Singh-1 | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Gang | Jawla Singh-1 | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Jawla Singh-1 | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Gang | Jawla Singh-1 | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Gang | Jwala Singh -2 | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Jwala Singh -2 | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Jwala Singh -2 | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Gang | Govind Mahto-02 | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Govind Mahto-02 | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Govind Mahto-02 | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Bhairaw Mahto | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Gang | Bhairaw Mahto | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Bhairaw Mahto | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Pritam Enterprises-2 | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Gang | Pritam Enterprises-2 | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Pritam Enterprises-2 | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Pritam Enterprises-3 | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Gang | Pritam Enterprises-3 | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Gang | Pritam Enterprises-3 | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Gang | Pritam Enterprises-3 | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Pritam Enterprises-4 | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Gang | SK.Samiul -1 | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Gang | SK.Samiul -1 | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Gang | SK.Samiul -1 | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Punam kumari-1 | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Gang | Punam kumari-1 | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Punam kumari-1 | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Punam kumari-1 | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Gang | Punam kumari-2 | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Gang | Punam kumari-2 | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Gang | Punam kumari-2 | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Punam kumari-2 | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Fouzi Ratto | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Fouzi Ratto | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Fouzi Ratto | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Sherra Const. | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Gang | Sherra Const. | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Sherra Const. | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Amar Singh | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Gang | Amar Singh | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Amar Singh | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Gang | Kartik Mahto | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Kartik Mahto | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Gang | Kartik Mahto | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Section Incharge | Shuvam Gupta | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Shuvam Gupta | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Section Incharge | Shuvam Gupta | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Section Incharge | Kartik Jhorar | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Section Incharge | Kartik Jhorar | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Kartik Jhorar | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Kartik Jhorar | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Kartik Jhorar | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Kartik Jhorar | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Section Incharge | Kartik Jhorar | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Kartik Jhorar | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Kartik Jhorar | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Section Incharge | Kartik Jhorar | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Section Incharge | Kartik Jhorar | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Kartik Jhorar | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Section Incharge | Shuvam Gupta | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta413 | TA413 | Supervisor | Aman Kr Singh | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Supervisor | Aman Kr Singh | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Aman Kr Singh | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Aman Kr Singh | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Kamal Ravidas | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Supervisor | Kamal Ravidas | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Kamal Ravidas | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Supervisor | Kamal Ravidas | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Supervisor | Rudra Kumar | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Rudra Kumar | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Rudra Kumar | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Supervisor | Sanjay Kumar | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Sanjay Kumar | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Sanjay Kumar | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Akbar Ali | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Supervisor | Akbar Ali | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Akbar Ali | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Rudra Prasad | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Supervisor | Rudra Prasad | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Supervisor | Rudra Prasad | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Supervisor | Rudra Prasad | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Abhiya Ojha | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Supervisor | Haridasn | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Supervisor | Haridasn | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Supervisor | Haridasn | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Supervisor | Nabirul Islam | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Supervisor | Nabirul Islam | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Supervisor | Nabirul Islam | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Nabirul Islam | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Khooblal | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Khooblal | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Khooblal | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Raju Mahto | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Supervisor | Raju Mahto | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Raju Mahto | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Supervisor | Shuseel | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Shuseel | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Supervisor | Shuseel | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta416 | TA416 | Gang | Maa Construction | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Maa Construction | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Gang | Gourishankar | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Gang | Gourishankar | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Gang | Reeta Bharti | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Unity India | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Gang | Unity India | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Ananya Trader-1 | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Amit choudhury | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Gang | Amit choudhury | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Punam Kumari-1 | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Gang | Punam Kumari-1 | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Sainik Trader | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Sainik Trader | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Sainik Trader | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Spotify-1 | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Spotify-1 | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Spotify-1 | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Punam Kumari-2 | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Punam Kumari-2 | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Punam Kumari-2 | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Spotify-1 | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Spotify-1 | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Spotify-1 | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Pankaj | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Pankaj | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Mahon Mahto | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Mahon Mahto | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Gang | Mahon Mahto | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Gang | Kongres | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Kongres | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Gang | Kongres | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | Prabin Patra | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | Prabin Patra | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Section Incharge | Prabin Patra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Section Incharge | Prabin Patra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Section Incharge | Prabin Patra | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Section Incharge | D N Prasad | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Section Incharge | D N Prasad | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Section Incharge | D N Prasad | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Section Incharge | D N Prasad | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Section Incharge | D N Prasad | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Section Incharge | D N Prasad | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Churamani | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Churamani | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Supervisor | Bijendra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Supervisor | Bijendra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Supervisor | Rupesh | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Maqbul | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Supervisor | Maqbul | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Saidur | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Ali raza | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Supervisor | Ali raza | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Somenath | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Supervisor | Somenath | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Afeludin | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Afeludin | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Afeludin | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Akhtarul | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Akhtarul | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Akhtarul | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | madhusudan | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | madhusudan | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | madhusudan | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | Akhtarul | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Akhtarul | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Akhtarul | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | Maqbul | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Maqbul | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Ritlal | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | Ritlal | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Supervisor | Ritlal | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Supervisor | Ritlal | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | Ritlal | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Supervisor | Ritlal | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta421 | TA421 | Gang | Subash | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Gang | Subash | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Gang | Subash | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Gang | Subash | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Gang | Subash | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Gang | Subash | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Gang | Subash | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Gang | Shakila Khatun | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Gang | Shakila Khatun | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Gang | Shakila Khatun | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Gang | Shakila Khatun | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Gang | Shakila Khatun | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Gang | Shakila Khatun | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Gang | Sabhnam Praveen | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Gang | Sabhnam Praveen | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Gang | Sabhnam Praveen | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Gang | Rajiv Yadhav | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Gang | Rajiv Yadhav | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Gang | D K Verma | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Gang | D K Verma | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Gang | D K Verma | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Gang | D K Verma | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Gang | D K Verma | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Manikandan | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Section Incharge | Mr. Manikandan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Section Incharge | Mr. Manikandan | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Supervisor | Mr. Srinivasan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Supervisor | Mr. Anand | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Supervisor | Mr. Anand | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Supervisor | Mr. Anand | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Supervisor | Mr. Ram Asish | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Supervisor | Mr. Ram Asish | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
tb408 | TB408 | Gang | Sheetal Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Gang | Jirwa Devi | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Gang | Jirwa Devi | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Gang | Jirwa Devi | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Gang | Nimal Mahto | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Gang | Nimal Mahto | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Gang | Nimal Mahto | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Gang | Nimal Mahto | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Gang | Shobha Devi | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Gang | Shobha Devi | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Gang | Shobha Devi | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Gang | Shobha Devi | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Gang | Shobha Devi | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Gang | Vivek Ganju | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Gang | Vivek Ganju | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Gang | Vivek Ganju | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Gang | Vivek Ganju | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Gang | Vivek Ganju | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Gang | Vivek Ganju | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Gang | Chinta Devi | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Gang | Chinta Devi | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Gang | Chinta Devi | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Gang | Chinta Devi | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Gang | Sunny Construction | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Gang | Sunny Construction | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Section Incharge | Sumit Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Section Incharge | Vijay Yadav | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Section Incharge | Vijay Yadav | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Supervisor | Vaibhav Sharma | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Supervisor | Gangadin Sahu | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Supervisor | Gangadin Sahu | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Supervisor | Ganesh Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Supervisor | Ganesh Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Supervisor | Ganesh Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Supervisor | Ganesh Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Supervisor | Ganesh Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Supervisor | Ganesh Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Supervisor | Umesh Prasad | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Supervisor | Umesh Prasad | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Supervisor | Umesh Prasad | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Supervisor | Umesh Prasad | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Supervisor | Umesh Prasad | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Supervisor | Shakib Hussain | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Supervisor | Shakib Hussain | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Supervisor | Shakib Hussain | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Supervisor | Shakib Hussain | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Supervisor | Shakib Hussain | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Supervisor | Shakib Hussain | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
ta505 | TA505 | Gang | Jwala Singh | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Jwala Singh | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Jwala Singh | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Gang | Jwala Singh | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | New Gang-1 | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Gang | New Gang-1 | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Gang | New Gang-1 | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Gang | New Gang-2 | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Gang | New Gang-2 | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Gang | New Gang-2 | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Gang | Shila Devi | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Gang | Shila Devi | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Gang | Shila Devi | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Shila Devi | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Jyoti Enterprises | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Jyoti Enterprises | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Gang | Jyoti Enterprises | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Deglal Mahto | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Deglal Mahto | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Gang | Deglal Mahto | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Gang | Deglal Mahto | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Anil Kumar | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Gang | Anil Kumar | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Gang | Anil Kumar | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Toshan Mahto | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Gang | Toshan Mahto | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Gang | Toshan Mahto | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Gang | Toshan Mahto | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Gang | Toshan Mahto | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Gang | Parmanand (MP) | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Parmanand (MP) | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Parmanand (MP) | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Parmanand (MP) | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Jagannath Mahto | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Jagannath Mahto | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Jagannath Mahto | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Jagannath Mahto | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Gang | Jagannath Mahto | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Gang | Pankaj Singh | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Pankaj Singh | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Gang | Pankaj Singh | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Gang | Pankaj Singh | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Gang | Pankaj Singh | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Gang | Deglal Mahto (MP) | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Deglal Mahto (MP) | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Section Incharge | Deepak Anand | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Deepak Anand | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Deepak Anand | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Section Incharge | Deepak Anand | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Section Incharge | Deepak Anand | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Section Incharge | Deepak Anand | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Section Incharge | Deepak Anand | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Section Incharge | Deepak Anand | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Section Incharge | Deepak Anand | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Section Incharge | Deepak Anand | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Deepak Anand | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Section Incharge | Deepak Anand | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Deepak Anand | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Section Incharge | Deepak Anand | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Section Incharge | Deepak Anand | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Section Incharge | Bapan Mandal | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Section Incharge | Bapan Mandal | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Bapan Mandal | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Section Incharge | Bapan Mandal | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Section Incharge | Bapan Mandal | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Section Incharge | Bapan Mandal | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Section Incharge | Bapan Mandal | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Section Incharge | Vinod Hankare | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Vinod Hankare | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Vinod Hankare | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Vinod Hankare | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Supervisor | None | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 126/1 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Supervisor | None | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Supervisor | None | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Supervisor | None | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Supervisor | None | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Supervisor | None | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Supervisor | None | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Supervisor | None | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Supervisor | None | 141/0 | 801300.3 | 0 | 73.245 | DD45+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Supervisor | None | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Supervisor | None | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Supervisor | None | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Supervisor | None | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Supervisor | None | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Supervisor | None | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Supervisor | None | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Supervisor | None | 142/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Supervisor | None | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Supervisor | None | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Supervisor | None | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 160/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Supervisor | None | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Supervisor | None | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Supervisor | None | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Supervisor | None | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Supervisor | None | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Supervisor | None | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Supervisor | None | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Supervisor | None | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Supervisor | None | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28

## MicroPlanIndex
file_path | project_name | project_key | rows_cleaned | status | error
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 57 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-416 Oct'25.xlsx | TA416 | ta416 | 34 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-421 Oct'25.xlsx | TA421 | ta421 | 28 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TB-408 Oct'25.xlsx | TB408 | tb408 | 29 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan TA-505 Oct '25.xlsx | TA505 | ta505 | 49 | ok

## ProjectBaselines
project_name | baseline_mt_per_day
TA413 | 4.0537
TA416 | 5.199
TA421 | 5.0107
TA505 | 4.6653
TB408 | 4.9031

## ProjectBaselinesMonthly
project_name | month | baseline_mt_per_day
TA413 | 2024-03-01 | 0.1001
TA413 | 2024-04-01 | 0.1001
TA413 | 2024-05-01 | 0.1001
TA413 | 2024-06-01 | 0.1001
TA413 | 2024-07-01 | 0.1001
TA413 | 2024-08-01 | 0.1001
TA413 | 2024-09-01 | 2.0209
TA413 | 2024-10-01 | 2.5312
TA413 | 2024-11-01 | 1.7275
TA413 | 2024-12-01 | 3.1396
TA413 | 2025-01-01 | 4.4262
TA413 | 2025-02-01 | 4.2735
TA413 | 2025-03-01 | 4.9392
TA413 | 2025-04-01 | 4.6709
TA413 | 2025-07-01 | 3.5102
TA413 | 2025-08-01 | 4.8257
TA413 | 2025-09-01 | 4.9685
TA413 | 2025-10-01 | 4.8835
TA416 | 2024-09-01 | 2.8576
TA416 | 2024-10-01 | 5.8167
TA416 | 2024-11-01 | 4.4124
TA416 | 2024-12-01 | 5.6059
TA416 | 2025-01-01 | 5.1656
TA416 | 2025-02-01 | 6.1061
TA416 | 2025-03-01 | 5.9361
TA416 | 2025-04-01 | 5.7914
TA416 | 2025-05-01 | 5.7481
TA416 | 2025-06-01 | 5.6916
TA416 | 2025-07-01 | 4.9901
TA416 | 2025-08-01 | 3.6849
TA416 | 2025-09-01 | 4.077
TA416 | 2025-10-01 | 4.2805
TA421 | 2024-07-01 | 3.672
TA421 | 2024-08-01 | 4.7784
TA421 | 2024-09-01 | 3.3037
TA421 | 2024-10-01 | 3.1822
TA421 | 2024-11-01 | 5.3057
TA421 | 2024-12-01 | 4.7551
TA421 | 2025-01-01 | 4.3011
TA421 | 2025-02-01 | 6.0631
TA421 | 2025-03-01 | 6.0729
TA421 | 2025-04-01 | 6.8335
TA421 | 2025-05-01 | 5.6346
TA421 | 2025-06-01 | 4.8808
TA421 | 2025-07-01 | 4.7147
TA421 | 2025-08-01 | 4.6851
TA421 | 2025-09-01 | 5.7693
TA421 | 2025-10-01 | 4.654
TA505 | 2025-01-01 | 8.7033
TA505 | 2025-02-01 | 9.5658
TA505 | 2025-03-01 | 5.0819
TA505 | 2025-04-01 | 5.4988
TA505 | 2025-05-01 | 4.9125
TA505 | 2025-06-01 | 3.9847
TA505 | 2025-07-01 | 3.4247
TA505 | 2025-08-01 | 4.5955
TA505 | 2025-09-01 | 4.2429
TA505 | 2025-10-01 | 4.3016
TB408 | 2024-01-01 | 4.856
TB408 | 2024-02-01 | 6.6192
TB408 | 2024-03-01 | 6.4794
TB408 | 2024-04-01 | 6.459
TB408 | 2024-05-01 | 4.8666
TB408 | 2024-06-01 | 2.2712
TB408 | 2024-07-01 | 3.6998
TB408 | 2024-08-01 | 4.2842
TB408 | 2024-09-01 | 4.2975
TB408 | 2024-10-01 | 5.1626
TB408 | 2024-11-01 | 5.0289
TB408 | 2024-12-01 | 5.2785
TB408 | 2025-01-01 | 5.2036
TB408 | 2025-02-01 | 6.7774
TB408 | 2025-03-01 | 5.3184
TB408 | 2025-04-01 | 5.3161
TB408 | 2025-05-01 | 2.8225
TB408 | 2025-06-01 | 2.2497
TB408 | 2025-07-01 | 4.6057
TB408 | 2025-08-01 | 4.6251
TB408 | 2025-09-01 | 4.6499
TB408 | 2025-10-01 | 4.4382