## Stringing Compiled
s no | sec | From AP |  | To AP | span m | Method | balance fdn | balance erc | Section Readiness | starting date | completion date | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | completion month | jmc no | Gang Name | hindrance | remarks | district | _source_file
1 | JMB | 112/0 | ~ | 113/0 | 375.84 | Manual | 0 | 0 | Ready |  |  | 2024-08-12 | 2024-08-15 | 375.84 | 2024-08-17 | 2024-08-19 | 375.84 | Completed | 2024-08-01 | 1 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
2 | JMB | 111/0 | ~ | 112/0 | 341.9 | Manual | 0 | 0 | Ready |  |  | 2024-09-23 | 2024-09-24 | 341.9 | 2024-10-02 | 2024-10-04 | 341.9 | Completed | 2024-10-01 | 4 | Gokul Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
3 | JMB | 110/0 | ~ | 111/0 | 312.14 | Manual | 0 | 0 | Ready |  |  | 2024-09-11 | 2024-09-12 | 312.14 | 2024-10-04 | 2024-10-06 | 312.14 | Completed | 2024-10-01 | 3 | Gokul Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
4 | JMB | 113/0 | ~ | 114/0 | 297.05 | Manual | 0 | 0 | Ready |  |  | 2024-09-26 | 2024-09-29 | 297.05 | 2024-10-01 | 2024-10-06 | 297.05 | Completed | 2024-10-01 | 6 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
5 | JMB | 109/0 | ~ | 110/0 | 342.42 | Manual | 0 | 0 | Ready |  |  | 2024-09-06 | 2024-09-09 | 342.42 | 2024-10-10 | 2024-10-13 | 342.42 | Completed | 2024-10-01 | 2 | Gokul Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
6 | JMB | 116/0 | ~ | 116A/0 | 243.41 | Manual | 0 | 0 | Ready |  |  | 2024-10-15 | 2024-10-18 | 243.41 | 2024-10-26 | 2024-10-27 | 243.41 | Completed | 2024-10-01 | 7 | Gokul Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
7 | JMB | 108/0 | ~ | 109/0 | 277.2 | Manual | 0 | 0 | Ready |  |  | 2024-10-17 | 2024-10-20 | 277.2 | 2024-10-25 | 2024-10-28 | 277.2 | Completed | 2024-10-01 | 8 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
8 | JMB | 107/0 | ~ | 108/0 | 558.88 | Manual | 0 | 0 | Ready |  |  | 2024-10-30 | 2024-11-02 | 558.88 | 2024-11-04 | 2024-11-07 | 558.88 | Completed | 2024-11-01 | 9 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
9 | JMB | 133/0 | ~ | 133A/0 | 2267.72 | TSE | 0 | 0 | Ready |  |  | 2024-10-29 | 2024-11-02 | 2267.72 | 2024-11-03 | 2024-11-07 | 2267.72 | Completed | 2024-11-01 | 5 | Rejaul |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
10 | JMB | 121/0 | ~ | 122/0 | 525.49 | Manual | 0 | 0 | Ready |  |  | 2024-11-02 | 2024-11-03 | 525.49 | 2024-11-18 | 2024-11-19 | 525.49 | Completed | 2024-11-01 | 10 | Gokul Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
11 | JMB | 129A/0 | ~ | 130/0 | 1182.12 | TSE | 0 | 0 | Ready |  |  | 2024-11-16 | 2024-11-18 | 1182.12 | 2024-11-21 | 2024-11-22 | 1182.12 | Completed | 2024-11-01 | 12 | Rejaul |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
12 | JMB | 106B/0 | ~ | 107/0 | 1148.24 | TSE | 0 | 0 | Ready |  |  | 2024-11-15 | 2024-11-16 | 1148.24 | 2024-11-20 | 2024-11-23 | 1148.24 | Completed | 2024-11-01 | 11 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
13 | JMB | 122/0 | ~ | 123/0 | 328.32 | Hotline | 0 | 0 | Ready |  |  | 2024-11-23 | 2024-11-26 | 328.32 | 2024-11-28 | 2024-11-30 | 328.32 | Completed | 2024-11-01 | 13 | Dhervendra Electricals |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
14 | JMB | 118/0 | ~ | 119/0 | 294.43 | Manual | 0 | 0 | Ready |  |  | 2024-11-23 | 2024-11-25 | 294.43 | 2024-12-02 | 2024-12-03 | 294.43 | Completed | 2024-12-01 | 14 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
15 | JMB | 117/0 | ~ | 118/0 | 285.24 | Manual | 0 | 0 | Ready |  |  | 2024-12-08 | 2024-12-13 | 285.24 | 2024-12-18 | 2024-12-20 | 285.24 | Completed | 2025-01-01 | 16 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
16 | JMB | 119/0 | ~ | 120/0 | 1372.87 | TSE | 0 | 0 | Ready |  |  | 2024-12-19 | 2024-12-20 | 1372.87 | 2024-12-21 | 2024-12-22 | 1372.87 | Completed | 2025-02-01 | 18 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
17 | JMB | 116B/0 | ~ | 117/0 | 437 | Manual | 0 | 0 | Ready |  |  | 2024-11-17 | 2024-12-18 | 437 | 2024-12-23 | 2024-12-24 | 437 | Completed | 2025-03-01 | 17 | Yakub Ali + Enamul |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
18 | JMB | 144/0 | ~ | 144A/0 | 2391.06 | TSE | 0 | 0 | Ready |  |  | 2024-12-16 | 2024-12-19 | 2391.06 | 2024-12-22 | 2024-12-24 | 2391.06 | Completed | 2025-04-01 | 15 | Gokul Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
19 | JMB | 120/0 | ~ | 121/0 | 264.71 | Hotline | 0 | 0 | Ready |  |  | 2024-12-28 | 2025-01-01 | 264.71 | 2024-12-28 | 2025-01-01 | 264.71 | Completed | 2025-01-01 | 19 | Dhervendra Electricals |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
20 | JMB | 114/0 | ~ | 115/0 | 374 | Manual | 0 | 0 | Ready |  |  | 2024-12-26 | 2024-12-28 | 374 | 2024-12-30 | 2025-01-02 | 374 | Completed | 2025-01-01 | 20 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
21 | JMB | 115/0 | ~ | 116/0 | 226 | Manual | 0 | 0 | Ready |  |  | 2024-12-26 | 2024-12-28 | 226 | 2024-12-31 | 2025-01-02 | 226 | Completed | 2025-01-01 | 21 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
22 | JMB | 133A/0 | ~ | 134/0 | 2037.5 | TSE | 0 | 0 | Ready |  |  | 2024-12-27 | 2025-01-01 | 2037.5 | 2025-01-02 | 2025-01-04 | 2037.5 | Completed | 2025-01-01 | 22 | Rejaul + Rafikul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
23 | JMB | 123/0 | ~ | 124/0 | 843 | Manual | 0 | 0 | Ready |  |  | 2024-12-29 | 2024-12-30 | 843 | 2025-01-05 | 2025-01-06 | 843 | Completed | 2025-01-01 | 23 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
24 | JMB | 116A/0 | ~ | 116B/0 | 675 | Manual | 0 | 0 | Ready |  |  | 2025-01-09 | 2025-01-11 | 675 | 2025-01-12 | 2025-01-13 | 675 | Completed | 2025-01-01 | 24 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
25 | JMB | 144A/0 | ~ | 145/0 | 397.58 | Hotline | 0 | 0 | Ready |  |  | 2024-01-08 | 2025-01-13 | 397.58 | 2024-01-08 | 2025-01-13 | 397.58 | Completed | 2025-01-01 | 25 | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
26 | JMB | 147/1 | ~ | 147/2 | 330 | Manual | 0 | 0 | Ready |  |  | 2025-01-15 | 2025-01-16 | 330 | 2025-01-15 | 2025-01-16 | 330 | Completed | 2025-01-01 | 26 | Gokul Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
27 | JMB | 127/0 | ~ | 128/0 | 2399.38 | TSE | 0 | 0 | Ready |  |  | 2024-12-11 | 2024-12-13 | 2399.38 | 2025-01-17 | 2025-01-19 | 2399.38 | Completed | 2025-01-01 | 27 | Muslehuddin + Enamul |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
28 | JMB | 126/0 | ~ | 127/0 | 808.43 | Manual | 0 | 0 | Ready |  |  | 2025-01-09 | 2025-01-11 | 808.43 | 2025-01-23 | 2025-01-24 | 808.43 | Completed | 2025-01-01 | 28 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
29 | JMB | 132/0 | ~ | 133/0 | 1280.12 | TSE | 0 | 0 | Ready |  |  | 2025-01-12 | 2025-01-14 | 1280.12 | 2025-01-21 | 2025-01-24 | 1280.12 | Completed | 2025-01-01 | 29 | Rejaul + enamul |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
30 | BAR | 259/0 | ~ | 260/0 | 256 | Hotline | 0 | 0 | Ready |  | 2025-01-18 | 2025-01-23 | 2025-01-24 | 256 | 2025-01-26 | 2025-01-28 | 256 | Completed | 2025-01-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
31 | BAR | 260/0 | ~ | 261/0 | 338 | Manual | 0 | 0 | Ready |  | 2025-01-17 | 2025-01-23 | 2025-01-25 | 338 | 2025-01-26 | 2025-01-28 | 338 | Completed | 2025-01-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
32 | JMB | 125A/0 | ~ | 126/0 | 380.08 | Manual | 0 | 0 | Ready |  |  | 2025-01-16 | 2025-01-18 | 380.08 | 2025-02-04 | 2025-02-05 | 380.08 | Completed | 2025-02-01 | 30 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
33 | JMB | 106A/0 | ~ | 106B/0 | 2016.36 | TSE | 0 | 0 | Ready |  |  | 2025-01-28 | 2025-02-01 | 2016.36 | 2025-02-04 | 2025-02-06 | 2016.36 | Completed | 2025-02-01 | 31 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
34 | JMB | 125/0 | ~ | 125A/0 | 401.32 | Manual | 0 | 0 | Ready |  |  | 2025-01-31 | 2025-02-02 | 401.32 | 2025-02-06 | 2025-02-07 | 401.32 | Completed | 2025-02-01 | 32 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
35 | JMB | 128/0 | ~ | 129/0 | 253.25 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-10 | 253.25 | 2025-02-12 | 2025-02-12 | 253.25 | Completed | 2025-02-01 | 33 | Alam Construction |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
36 | JMB | 129/0 | ~ | 129A/0 | 305.53 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-10 | 305.53 | 2025-02-12 | 2025-02-13 | 305.53 | Completed | 2025-02-01 | 34 | Alam Construction |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
37 | JMB | 135A/0 | ~ | 135A/1 | 339.83 | Manual | 0 | 0 | Ready |  |  | 2025-01-20 | 2025-01-21 | 339.83 | 2025-02-06 | 2025-02-14 | 339.83 | Completed | 2025-02-01 | 35 | SK Zenarul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
38 | JMB | 135A/2 | ~ | 135B/0 | 2234.39 | TSE | 0 | 0 | Ready |  |  | 2025-02-04 | 2025-02-06 | 2234.39 | 2025-02-12 | 2025-02-14 | 2234.39 | Completed | 2025-02-01 | 36 | Rafikul Alam construction + Enamul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
39 | JMB | 135B/0 | ~ | 136/0 | 2985.99 | TSE | 0 | 0 | Ready |  |  | 2025-01-25 | 2025-01-29 | 2985.99 | 2025-02-12 | 2025-02-14 | 2985.99 | Completed | 2025-02-01 | 37 | Rafikul Alam construction + Enamul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
40 | JMB | 106/0 | ~ | 106A/0 | 411.25 | Manual | 0 | 0 | Ready |  |  | 2025-02-02 | 2025-02-05 | 411.25 | 2025-02-14 | 2025-02-15 | 411.25 | Completed | 2025-02-01 | 38 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
41 | BAR | 164/0 | ~ | 165/0 | 2980.78 | TSE | 0 | 0 | Ready |  |  | 2025-02-07 | 2025-02-10 | 2980.78 | 2025-02-12 | 2025-02-15 | 2980.78 | Completed | 2025-02-01 | 39 | Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
42 | JMB | 135A/1 | ~ | 135A/2 | 451.85 | Manual | 0 | 0 | Ready |  |  | 2025-01-29 | 2025-02-02 | 451.85 | 2025-02-07 | 2025-02-16 | 451.85 | Completed | 2025-02-01 | 40 | SK Zenarul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
43 | JMB | 124/0 | ~ | 124A/0 | 395.28 | Manual | 0 | 0 | Ready |  |  | 2025-02-10 | 2025-02-13 | 395.28 | 2025-02-16 | 2025-02-19 | 395.28 | Completed | 2025-02-01 | 41 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
44 | JMB | 124A/0 | ~ | 124A/1 | 253 | Manual | 0 | 0 | Ready |  |  | 2025-02-15 | 2025-02-19 | 253 | 2025-02-15 | 2025-02-19 | 253 | Completed | 2025-02-01 | 42 | Enamul Haque |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
45 | JMB | 124A/1 | ~ | 125/0 | 203.134 | Hotline | 0 | 0 | Ready |  |  | 2025-02-15 | 2025-02-19 | 203.134 | 2025-02-15 | 2025-02-19 | 203.134 | Completed | 2025-02-01 | 42 | Dhervendra Electricals |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
46 | BAR | 257/0 | ~ | 259/0 | 1809 | TSE | 0 | 0 | Ready |  | 2025-02-10 | 2025-02-11 | 2025-02-13 | 1809 | 2025-02-21 | 2025-02-24 | 1809 | Completed | 2025-02-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
47 | JMB | 137A/0 | ~ | 138/0 | 2729.901 | TSE | 0 | 0 | Ready |  |  | 2025-02-21 | 2025-02-25 | 2729.901 | 2025-02-28 | 2025-03-03 | 2729.901 | Completed | 2025-03-01 | 43 | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
48 | JMB | 138/0 | ~ | 139/0 | 1238.994 | TSE | 0 | 0 | Ready |  |  | 2025-02-27 | 2025-03-01 | 1238.994 | 2025-03-02 | 2025-03-04 | 1238.994 | Completed | 2025-03-01 | 44 | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
49 | BAR | 261/0 | ~ | 262/0 | 242 | Hotline | 0 | 0 | Ready |  | 2025-02-28 | 2025-03-02 | 2025-03-04 | 242 | 2025-03-06 | 2025-03-08 | 242 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
50 | JMB | 139/0 | ~ | 139A/0 | 1211.03 | TSE | 0 | 0 | Ready |  |  | 2025-03-02 | 2025-03-04 | 1211.03 | 2025-03-07 | 2025-03-09 | 1211.03 | Completed | 2025-03-01 | 45 | SK Zenarul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
51 | JMB | 130/0 | ~ | 131/0 | 2041.128 | TSE | 0 | 0 | Ready |  |  | 2025-03-03 | 2025-03-05 | 2041.128 | 2025-03-07 | 2025-03-10 | 2041.128 | Completed | 2025-03-01 | 46 | Muslehuddin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
52 | JMB | 131/0 | ~ | 132/0 | 236.46 | Hotline | 0 | 0 | Ready |  |  | 2025-03-06 | 2025-03-10 | 236.46 | 2025-03-06 | 2025-03-10 | 236.46 | Completed | 2025-03-01 | 47 | Dhervendra Electricals |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
53 | JMB | 139A/0 | ~ | 140/0 | 427.14 | Manual | 0 | 0 | Ready |  |  | 2025-02-27 | 2025-03-05 | 427.14 | 2025-03-07 | 2025-03-13 | 427.14 | Completed | 2025-03-01 | 48 | SK Zenarul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
54 | BAR | 262/0 | ~ | 263/0 | 686 | Manual | 0 | 0 | Ready |  | 2025-02-16 | 2025-02-17 | 2025-02-19 | 686 | 2025-03-12 | 2025-03-15 | 686 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
55 | BAR | 263/0 | ~ | 264/0 | 243 | Hotline | 0 | 0 | Ready |  | 2025-03-09 | 2025-03-11 | 2025-03-12 | 243 | 2025-03-13 | 2025-03-15 | 243 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
56 | JMB | 142/0 | ~ | 143/0 | 223.38 | Manual | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-18 | 223.38 | 2025-03-18 | 2025-03-18 | 223.38 | Completed | 2025-03-01 |  | Enamul + Alam Constrution |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
57 | JMB | 143/0 | ~ | 143A/0 | 393.22 | Manual | 0 | 0 | Ready |  |  | 2025-03-08 | 2025-03-09 | 393.22 | 2025-03-20 | 2025-03-21 | 393.22 | Completed | 2025-03-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
58 | BAR | 255/0 | ~ | 257/0 | 1839 | TSE | 0 | 0 | Ready |  | 2025-02-13 | 2025-02-12 | 2025-02-25 | 1839 | 2025-03-20 | 2025-03-21 | 1839 | Completed | 2025-03-01 |  | Kamruddin |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
59 | BAR | 265/0 | ~ | 266/0 | 223 | Hotline | 0 | 0 | Ready |  |  | 2025-03-16 | 2025-03-18 | 223 | 2025-03-19 | 2025-03-21 | 223 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
60 | JMB | 134/0 | ~ | 135/0 | 235.87 | Hotline | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-22 | 235.87 | 2025-03-18 | 2025-03-22 | 235.87 | Completed | 2025-03-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
61 | BAR | 163/0 | ~ | 163/5 | 1894 | TSE | 0 | 0 | Ready |  |  | 2025-02-24 | 2025-02-28 | 1894 | 2025-03-21 | 2025-03-22 | 1894 | Completed | 2025-03-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
62 | BAR | 163/5 | ~ | 163/6 | 339 | Hotline | 0 | 0 | Ready |  |  | 2025-03-21 | 2025-03-22 | 339 | 2025-03-21 | 2025-03-22 | 339 | Completed | 2025-03-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
63 | BAR | 163/6 | ~ | 164/0 | 343 | TSE | 0 | 0 | Ready |  |  | 2025-03-04 | 2025-03-08 | 343 | 2025-03-21 | 2025-03-22 | 343 | Completed | 2025-03-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
64 | BAR | 264/0 | ~ | 265/0 | 441 | Manual | 0 | 0 | Ready |  |  | 2025-03-16 | 2025-03-18 | 441 | 2025-03-19 | 2025-03-22 | 441 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
65 | JMB | 143A/0 | ~ | 143A/2 | 841.2 | Manual | 0 | 0 | Ready |  |  | 2025-03-19 | 2025-03-21 | 841.2 | 2025-03-23 | 2025-03-26 | 841.2 | Completed | 2025-03-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
66 | JMB | 143A/2 | ~ | 143A/3 | 413.09 | Manual | 0 | 0 | Ready |  |  | 2025-03-23 | 2025-03-24 | 413.09 | 2025-03-23 | 2025-03-26 | 413.09 | Completed | 2025-03-01 |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
67 | JMB | 143A/3 | ~ | 144/0 | 1246.06 | TSE | 0 | 0 | Ready |  |  | 2025-03-18 | 2025-03-20 | 1246.06 | 2025-03-23 | 2025-03-26 | 1246.06 | Completed | 2025-03-01 |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
68 | BAR | 266/0 | ~ | 266/1 | 340 | Hotline | 0 | 0 | Ready |  |  | 2025-03-23 | 2025-03-24 | 340 | 2025-03-25 | 2025-03-28 | 340 | Completed | 2025-03-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
69 | BAR | 266/1 | ~ | 267/0 | 835 | Manual | 0 | 0 | Ready |  |  | 2025-03-22 | 2025-03-24 | 835 | 2025-03-25 | 2025-03-28 | 835 | Completed | 2025-03-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
70 | JMB | 136/0 | ~ | 137/0 | 425.58 | Hotline | 0 | 0 | Ready |  |  | 2025-03-26 | 2025-04-01 | 425.58 | 2025-03-26 | 2025-04-01 | 425.58 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
71 | JMB | 137/0 | ~ | 137A/0 | 2827.097 | TSE | 0 | 0 | Ready |  |  | 2025-03-05 | 2025-03-09 | 2827.097 | 2025-03-26 | 2025-04-01 | 2827.097 | Completed | 2025-04-01 |  | Rafikul Alam construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
72 | JMB | 145A/0 | ~ | 146/0 | 1620.89 | TSE | 0 | 0 | Ready |  |  | 2025-04-02 | 2025-04-04 | 1620.89 | 2025-04-07 | 2025-04-08 | 1620.89 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
73 | BAR | 253/0 | ~ | 254/0 | 246 | Hotline | 0 | 0 | Ready |  |  | 2025-04-04 | 2025-04-06 | 246 | 2025-04-07 | 2025-04-08 | 246 | Completed | 2025-04-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
74 | BAR | 254/0 | ~ | 255/0 | 300 | Manual | 0 | 0 | Ready |  |  | 2025-02-26 | 2025-02-28 | 300 | 2025-04-07 | 2025-04-08 | 300 | Completed | 2025-04-01 |  | Monera |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
75 | BAR | 267/0 | ~ | 267A/0 | 511 | Manual | 0 | 0 | Ready |  |  | 2025-04-01 | 2025-04-03 | 511 | 2025-04-07 | 2025-04-10 | 511 | Completed | 2025-04-01 |  | Kamruddin Deepak Sarkar |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
76 | BAR | 267A/0 | ~ | 268/0 | 1440 | TSE | 0 | 0 | Ready |  | 2025-03-25 | 2025-03-27 | 2025-03-29 | 1440 | 2025-04-07 | 2025-04-10 | 1440 | Completed | 2025-04-01 |  | Kamruddin |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
77 | JMB | 141/0 | ~ | 141/1 | 390 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 390 | 2025-04-11 | 2025-04-13 | 390 | Completed | 2025-04-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
78 | JMB | 141/1 | ~ | 141/2 | 370 | Hotline | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 370 | 2025-04-11 | 2025-04-13 | 370 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
79 | JMB | 141/2 | ~ | 142/0 | 805.06 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-09 | 805.06 | 2025-04-11 | 2025-04-13 | 805.06 | Completed | 2025-04-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
80 | JMB | 146/0 | ~ | 147/0 | 475.02 | Hotline | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-15 | 475.02 | 2025-04-12 | 2025-04-15 | 475.02 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
81 | JMB | 147/0 | ~ | 147/1 | 425.52 | Hotline | 0 | 0 | Ready |  |  | 2025-04-11 | 2025-04-15 | 425.52 | 2025-04-11 | 2025-04-15 | 425.52 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
82 | JMB | 147B/0 | ~ | 148/0 | 827.56 | TSE | 0 | 0 | Ready |  |  | 2025-04-04 | 2025-04-05 | 827.56 | 2025-04-13 | 2025-04-15 | 827.56 | Completed | 2025-04-01 |  | Muslehuddinn + GPJ |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
83 | JMB | 152/0 | ~ | 152A/0 | 1779.94 | TSE | 0 | 0 | Ready |  |  | 2025-04-03 | 2025-04-09 | 1779.94 | 2025-04-13 | 2025-04-15 | 1779.94 | Completed | 2025-04-01 |  | Alongir |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
84 | BAR | 270/0 | ~ | 270A/0 | 2821 | TSE | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-14 | 2821 | 2025-04-14 | 2025-04-15 | 2821 | Completed | 2025-04-01 |  | Kamruddin & Deepak |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
85 | JMB | 145/0 | ~ | 145A/0 | 398 | Hotline | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-23 | 398 | 2025-04-18 | 2025-04-23 | 398 | Completed | 2025-04-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
86 | BAR | 268/0 | ~ | 269/0 | 292 | Hotline | 0 | 0 | Ready |  |  | 2025-04-17 | 2025-04-19 | 292 | 2025-04-21 | 2025-04-23 | 292 | Completed | 2025-04-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
87 | BAR | 269/0 | ~ | 270/0 | 1237 | TSE | 0 | 0 | Ready |  |  | 2025-04-05 | 2025-04-08 | 1237 | 2025-04-18 | 2025-04-23 | 1237 | Completed | 2025-04-01 |  | Kamruddin & Maidul rahman |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
88 | BAR | 270A/0 | ~ | 271/0 | 268 | Manual | 0 | 0 | Ready |  |  | 2025-04-12 | 2025-04-15 | 268 | 2025-04-21 | 2025-04-25 | 268 | Completed | 2025-04-01 |  | Alamgir |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
89 | BAR | 271/0 | ~ | 272/0 | 2108 | TSE | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-20 | 2108 | 2025-04-21 | 2025-04-25 | 2108 | Completed | 2025-04-01 |  | Kamruddin & Deepak |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
90 | JMB | 148/0 | ~ | 149/0 | 2993.72 | TSE | 0 | 0 | Ready |  |  | 2025-04-18 | 2025-04-21 | 2993.72 | 2025-04-24 | 2025-04-26 | 2993.72 | Completed | 2025-04-01 |  | Muslehuddin |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
91 | JMB | 149/0 | ~ | 150/0 | 808.76 | TSE | 0 | 0 | Ready |  |  | 2025-04-22 | 2025-04-23 | 808.76 | 2025-04-24 | 2025-04-26 | 808.76 | Completed | 2025-04-01 |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
92 | BAR | 162/0 | ~ | 163/0 | 401.68 | Manual | 0 | 0 | Ready |  |  | 2025-04-07 | 2025-04-13 | 401.68 | 2025-04-23 | 2025-04-26 | 401.68 | Completed | 2025-04-01 |  | Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
93 | JMB | 147A/0 | ~ | 147B/0 | 263 | Manual | 0 | 0 | Ready |  |  | 2025-04-30 | 2025-04-30 | 263 | 2025-04-30 | 2025-04-30 | 263 | Completed | 2025-04-01 |  | Enamul Haque | U/C 220 KV |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
94 | JMB | 135/0 | ~ | 135A/0 | 2997.64 | TSE | 0 | 0 | Ready |  |  | 2025-03-21 | 2025-03-24 | 2997.64 | 2025-04-28 | 2025-05-01 | 2997.64 | Completed | 2025-05-01 |  | RafikulAlam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
95 | BAR | 251/0 | ~ | 252/0 | 222 | Hotline | 0 | 0 | Ready |  |  | 2025-04-29 | 2025-05-01 | 222 | 2025-05-02 | 2025-05-04 | 222 | Completed | 2025-05-01 |  | Dharmendra Electrical |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
96 | JMB | 161/0 | ~ | 162/0 | 279.05 | Hotline | 0 | 0 | Ready |  |  | 2025-04-28 | 2025-05-06 | 279.05 | 2025-04-28 | 2025-05-06 | 279.05 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
97 | BAR | 252/0 | ~ | 253/0 | 317 | Manual | 0 | 0 | Ready |  |  | 2025-04-17 | 2025-04-19 | 317 | 2025-05-04 | 2025-05-06 | 317 | Completed | 2025-05-01 |  | Deepak Sarkar |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
98 | BAR | 250/0 | ~ | 251/0 | 737 | Manual | 0 | 0 | Ready |  |  | 2025-05-04 | 2025-05-05 | 737 | 2025-05-08 | 2025-05-10 | 737 | Completed | 2025-05-01 |  | Deepak Sarkar |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
99 | BAR | 249/0 | ~ | 250/0 | 1368 | TSE | 0 | 0 | Ready |  |  | 2025-04-29 | 2025-05-03 | 1368 | 2025-05-09 | 2025-05-12 | 1368 | Completed | 2025-05-01 |  | Kamruddin |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
100 | JMB | 150A/0 | ~ | 151/0 | 1252.42 | TSE | 0 | 0 | Ready |  |  | 2025-04-26 | 2025-04-29 | 1252.42 | 2025-05-12 | 2025-05-15 | 1252.42 | Completed | 2025-05-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
101 | JMB | 151/0 | ~ | 152/0 | 403.35 | Manual | 0 | 0 | Ready |  |  | 2025-05-11 | 2025-05-15 | 403.35 | 2025-05-11 | 2025-05-15 | 403.35 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
102 | JMB | 147/2 | ~ | 147A/0 | 2020.89 | TSE | 0 | 0 | Ready |  |  | 2025-05-16 | 2025-05-18 | 2020.89 | 2025-05-16 | 2025-05-18 | 2020.89 | Completed | 2025-05-01 |  | Rafikul Alam + Alam Const. + Enamul |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
103 | JMB | 140/0 | ~ | 141/0 | 249 | Manual | 0 | 0 | Ready |  |  | 2025-05-22 | 2025-05-22 | 249 | 2025-05-23 | 2025-05-23 | 249 | Completed | 2025-05-01 |  | Rafikul Alam + Alam Const. + Enamul + Manik sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
104 | JMB | 150/0 | ~ | 150/1 | 367 | Hotline | 0 | 0 | Ready |  |  | 2025-05-23 | 2025-05-25 | 367 | 2025-05-23 | 2025-05-26 | 367 | Completed | 2025-05-01 |  | Dhervendra Electricals |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
105 | JMB | 150/1 | ~ | 150A/0 | 1266.03 | TSE | 0 | 0 | Ready |  |  | 2025-05-06 | 2025-05-11 | 1266.03 | 2025-05-23 | 2025-05-26 | 1266.03 | Completed | 2025-05-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
106 | BAR | 156/0 | ~ | 157/0 | 240.53 | Manual | 0 | 0 | Ready |  |  | 2025-06-03 | 2025-06-04 | 240.53 | 2025-06-03 | 2025-06-04 | 240.53 | Completed | 2025-06-01 |  | Deepak Sarkar + Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
107 | BAR | 272/0 | ~ | 272/5 | 2053 | TSE | 0 | 0 | Ready |  | 2025-03-01 | 2025-03-12 | 2025-03-15 | 2053 | 2025-06-13 | 2025-06-15 | 2053 | Completed | 2025-06-01 |  | Kamruddin & Deepak Sarkar |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
108 | BAR | 155/0 | ~ | 156/0 | 2733.13 | TSE | 0 | 0 | Ready |  |  | 2025-06-06 | 2025-06-11 | 2733.13 | 2025-06-14 | 2025-06-20 | 2733.13 | Completed | 2025-06-01 |  | Deepak Sarkar + Manik Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
109 | JMB | 152A/0 | ~ | 153/0 | 370.34 | Manual | 0 | 0 | Ready | 2025-08-25 | 2025-08-25 | 2025-09-02 | 2025-09-10 | 370.34 | 2025-09-06 | 2025-09-10 | 370.34 | Completed | 2025-09-01 |  | Alam Construction |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
110 | BAR | 158B/0 | ~ | 159/0 | 1253.83 | TSE | 0 | 0 | Ready |  |  | 2025-09-16 | 2025-09-27 | 1253.83 | 2025-10-02 | 2025-10-05 | 1253.83 | Completed | 2025-10-01 |  | Deepak Sarkar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
111 | BAR | 158A/0 | ~ | 158B/0 | 481.57 | Hotline | 0 | 0 | Ready |  |  | 2025-10-07 | 2025-10-21 | 481.57 | 2025-10-07 | 2025-10-21 | 481.57 | Completed | 2025-10-01 |  | Dharmendra 1 |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
112 | BAR | 276/0 | ~ | Gty | 160 | Manual | 0 | 0 | Ready |  |  | 2025-10-18 | 2025-10-21 | 160 | 2025-10-18 | 2025-10-21 | 160 | Completed | 2025-10-01 |  | Bhola |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
113 | BAR | 158/0 | ~ | 158A/0 | 1130.57 | TSE | 0 | 0 | Ready |  |  | 2025-10-09 | 2025-10-13 | 1130.57 | 2025-10-17 | 2025-10-23 | 1130.57 | Completed | 2025-10-01 |  | Deepak Sarkar |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
114 | BAR | 192/0 | ~ | 193/0 | 376 | Manual | 0 | 0 | Ready |  |  | 2025-10-15 | 2025-10-23 | 376 | 2025-10-19 | 2025-10-23 | 376 | Completed | 2025-10-01 |  | Teklal Saw |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
115 | BAR | 193/0 | ~ | 194/0 | 241 | Hotline | 0 | 0 | Ready |  |  | 2025-10-21 | 2025-10-25 | 241 | 2025-10-21 | 2025-10-25 | 241 | Completed | 2025-10-01 |  | Upendra Giri 1 |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
116 | BAR | 157/0 | ~ | 158/0 | 1575.8 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Deepak Sarkar |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx
117 | BAR | 168/0 | ~ | 169/0 | 1044 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Sindhu Const. |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
118 | BAR | 177/0 | ~ | 178/0 | 405 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
119 | BAR | 178/0 | ~ | 179/0 | 278 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx
120 | BAR | 189/0 | ~ | 190/0 | 829 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Md Anwar |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx
121 | BAR | 191/0 | ~ | 191A/0 | 1477 | TSE | 0 | 0 | Ready |  |  | 2025-10-22 | 2025-10-25 | 1477 | 2025-10-25 |  |  | WIP |  |  | Alam Construction |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx
122 | BAR | 191A/0 | ~ | 192/0 | 612 | Manual | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-19 | 612 | 2025-10-24 |  |  | WIP |  |  | Md Anwar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
123 | BAR | 194/0 | ~ | 195/0 | 182 | Manual | 0 | 0 | Ready |  |  | 2025-10-24 |  |  | 2025-10-24 |  |  | WIP |  |  | Enamul Haque |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx
124 | BAR | 195/0 | ~ | 195A/0 | 2481 | TSE | 0 | 0 | Ready |  |  | 2025-10-19 | 2025-10-26 | 2481 |  |  |  | WIP |  |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
125 | BAR | 195A/0 | ~ | 196/0 | 1542 | TSE | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-18 | 1542 |  |  |  | WIP |  |  | Muslehuddin |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
126 | BAR | 196/0 | ~ | 197/0 | 246 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Giyash |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
127 | BAR | 197/0 | ~ | 198/0 | 1740 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Muslehuddin |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx
128 | BAR | 204/0 | ~ | 205/0 | 198 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 2 |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
129 | BAR | 248/0 | ~ | 249/0 | 2525 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Kamaruddin |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
130 | BAR | 274/0 | ~ | 275/0 | 402 | Manual | 0 | 0 | Ready |  |  | 2025-10-23 | 2025-10-25 | 402 |  |  |  | WIP |  |  | Bhola |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
131 | BAR | 275/0 | ~ | 276/0 | 177 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 1 |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx
132 | JMB | 101/0 | ~ | 102/0 | 665 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Bharuch | TA 325 - DPR - 2025-10-26.xlsx
133 | JMB | 102/0 | ~ | 103/0 | 685 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
134 | JMB | 103/0 | ~ | 104/0 | 680.12 | Manual | 103/0, | 103/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
135 | JMB | 104/0 | ~ | 105/0 | 386.59 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
136 | JMB | 105/0 | ~ | 106/0 | 256.45 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
137 | BAR | 153/0 | ~ | 154/0 | 620 | Manual | 154/0, | 154/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
138 | BAR | 154/0 | ~ | 154/1 | 620 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
139 | BAR | 154/1 | ~ | 155/0 | 415 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
140 | BAR | 159/0 | ~ | 159/2 | 720 | Manual | 0 | 159/2 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
141 | BAR | 159/2 | ~ | 160/0 | 1152.2 | TSE | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
142 | BAR | 160/0 | ~ | 161/0 | 229.82 | Hotline | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
143 | BAR | 165/0 | ~ | 165/4 | 1613 | TSE | 165/4 | 165/4 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
144 | BAR | 165/4 | ~ | 165/5 | 538 | Manual | 165/5 | 165/5 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
145 | BAR | 165/5 | ~ | 166/0 | 423 | Manual | 166/0, | 166/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
146 | BAR | 166/0 | ~ | 167/0 | 270 | Hotline | 167/0, | 167/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
147 | BAR | 167/0 | ~ | 167/1 | 342 | Manual | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
148 | BAR | 167/1 | ~ | 168/0 | 1338 | TSE | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
149 | BAR | 169/0 | ~ | 171/0 | 433 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
150 | BAR | 171/0 | ~ | 172/0 | 274 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
151 | BAR | 172/0 | ~ | 173/0 | 1123 | TSE |  | 172/1,173/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
152 | BAR | 173/0 | ~ | 174/0 | 232 | Hotline |  | 173/0, ,174/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
153 | BAR | 174/0 | ~ | 174/1 | 381 | Manual |  | 174/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
154 | BAR | 174/1 | ~ | 175/0 | 289 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
155 | BAR | 175/0 | ~ | 176/0 | 979 | TSE |  | 175/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
156 | BAR | 176/0 | ~ | 177/0 | 232 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
157 | BAR | 179/0 | ~ | 180/0 | 264 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
158 | BAR | 180/0 | ~ | 181/0 | 263 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
159 | BAR | 181/0 | ~ | 182/0 | 1778 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
160 | BAR | 182/0 | ~ | 182A/0 | 246 | Hotline | 0 | 182A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
161 | BAR | 182A/0 | ~ | 183/0 | 430 | Manual | 0 | 182A/0, ,183/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
162 | BAR | 183/0 | ~ | 184/0 | 234 | Hotline | 0 | 183/0, ,184/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
163 | BAR | 184/0 | ~ | 184/1 | 468 | Manual | 0 | 184/0, ,184/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
164 | BAR | 184/1 | ~ | 185/0 | 412 | Manual | 0 | 184/1,185/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
165 | BAR | 185/0 | ~ | 186/0 | 820 | Manual | 0 | 185/1,185/0, 1,86/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
166 | BAR | 186/0 | ~ | 187/0 | 399 | Hotline | 0 | 186/0, ,187/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
167 | BAR | 187/0 | ~ | 188/0 | 1510 | TSE | 0 | 187/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
168 | BAR | 188/0 | ~ | 189/0 | 218 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
169 | BAR | 190/0 | ~ | 191/0 | 329 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
170 | BAR | 198/0 | ~ | 199/0 | 1149 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
171 | BAR | 199/0 | ~ | 200/0 | 221 | Hotline | 0 | 200/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
172 | BAR | 200/0 | ~ | 201/0 | 204 | Hotline | 0 | 200/0, ,201/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
173 | BAR | 201/0 | ~ | 201/1 | 532 | Manual | 0 | 201/0, ,201/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
174 | BAR | 201/1 | ~ | 202/0 | 367 | Manual | 0 | 201/1,202/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
175 | BAR | 202/0 | ~ | 203/0 | 788 | Manual | 0 | 202/0, ,203/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
176 | BAR | 203/0 | ~ | 203/1 | 460 | Manual | 0 | 203/0, ,203/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
177 | BAR | 203/1 | ~ | 204/0 | 425 | Manual | 0 | 203/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
178 | BAR | 205/0 | ~ | 206/0 | 1063 | TSE | 0 | 206/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
179 | BAR | 206/0 | ~ | 208/0 | 412 | Hotline | 0 | 206/0, ,208/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
180 | BAR | 208/0 | ~ | 209/0 | 410 | Manual | 0 | 208/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
181 | BAR | 209/0 | ~ | 210/0 | 699 | Manual | 0 | 209/1,210/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
182 | BAR | 210/0 | ~ | 211/0 | 223 | Hotline | 0 | 210/0, ,211/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
183 | BAR | 211/0 | ~ | 211A/0 | 1158 | TSE | 0 | 211/0, ,211A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
184 | BAR | 211A/0 | ~ | 212/0 | 1024 | TSE | 0 | 211A/0, 211A/1, 211A/2, 212/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
185 | BAR | 212/0 | ~ | 213/0 | 248 | Hotline | 0 | 212/0, ,213/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
186 | BAR | 213/0 | ~ | 214/0 | 771 | Manual | 0 | 213/1,213/0, ,214/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
187 | BAR | 214/0 | ~ | 215/0 | 713 | Manual | 0 | 214/0,214/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
188 | BAR | 215/0 | ~ | 216/0 | 632 | Hotline | 0 | 215/1, ,216/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
189 | BAR | 216/0 | ~ | 217/0 | 456 | Hotline | 0 | 216/0, ,217/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
190 | BAR | 217/0 | ~ | 217A/0 | 347 | Hotline | 0 | 217/0, ,217A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
191 | BAR | 217A/0 | ~ | 218/0 | 1174 | TSE | 0 | 217A/0, ,218/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
192 | BAR | 218/0 | ~ | 219/0 | 822 | Manual | 0 | 218/1, 218/0, 219/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
193 | BAR | 219/0 | ~ | 220/0 | 242 | Hotline | 0 | 219/0, 220/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
194 | BAR | 220/0 | ~ | 221/0 | 735 | Manual | 0 | 220/1,222/0, ,221/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
195 | BAR | 221/0 | ~ | 222/0 | 222 | Hotline | 0 | 221/0, ,222/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
196 | BAR | 222/0 | ~ | 222/1 | 388 | Manual | 0 | 222/0, 222/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
197 | BAR | 222/1 | ~ | 223/0 | 183 | Hotline | 0 | 222/1,223/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
198 | BAR | 223/0 | ~ | 224/0 | 1398 | TSE | 0 | 223/0, 223/2, 223/3 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
199 | BAR | 224/0 | ~ | 225/0 | 235 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
200 | BAR | 225/0 | ~ | 226/0 | 678 | Manual | 0 | 225/1, 226/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
201 | BAR | 226/0 | ~ | 227/0 | 417 | Manual | 0 | 226/0, ,227/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
202 | BAR | 227/0 | ~ | 228/0 | 239 | Manual | 0 | 227/0, ,228/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
203 | BAR | 228/0 | ~ | 229/0 | 196 | Hotline | 0 | 228/0, ,229/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
204 | BAR | 229/0 | ~ | 229/1 | 549 | Manual | 0 | 229/0, ,229/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
205 | BAR | 229/1 | ~ | 230/0 | 1884 | TSE | 0 | 229/1230/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
206 | BAR | 230/0 | ~ | 231/0 | 227 | Hotline | 0 | 230/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
207 | BAR | 231/0 | ~ | 232/0 | 419 | Manual | 0 | 232/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
208 | BAR | 232/0 | ~ | 233/0 | 195 | Hotline | 0 | 232/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
209 | BAR | 233/0 | ~ | 234/0 | 305 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
210 | BAR | 234/0 | ~ | 235/0 | 328 | Hotline | 0 | 235/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
211 | BAR | 235/0 | ~ | 236/0 | 305 | Manual | 0 | 235/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
212 | BAR | 236/0 | ~ | 237/0 | 280 | Hotline | 0 | 237/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
213 | BAR | 237/0 | ~ | 239/0 | 2519 | TSE | 0 | 239/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
214 | BAR | 239/0 | ~ | 240/0 | 248 | Hotline | 0 | 239/0, 240/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
215 | BAR | 240/0 | ~ | 241/0 | 207 | Manual | 0 | 240/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
216 | BAR | 241/0 | ~ | 242/0 | 246 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
217 | BAR | 242/0 | ~ | 243/0 | 1335 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
218 | BAR | 243/0 | ~ | 244/0 | 250 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
219 | BAR | 244/0 | ~ | 244/1 | 494 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
220 | BAR | 244/1 | ~ | 245/0 | 427 | Manual | 0 | 245/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
221 | BAR | 245/0 | ~ | 246/0 | 569 | Manual | 0 | 245/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
222 | BAR | 246/0 | ~ | 247/0 | 240 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx
223 | BAR | 247/0 | ~ | 248/0 | 1957 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx
224 | BAR | 272/5 | ~ | 272A/0 | 1202 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx
225 | BAR | 272A/0 | ~ | 273/0 | 2944 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx
226 | BAR | 273/0 | ~ | 274/0 | 1153 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx
TA 325 - DPR - 2025-10-26.xlsx
|  |  |  | Total | 177.3447 | [19 empty] | TA 325 - DPR - 2025-10-26.xlsx

## Diagnostics
sheet | rows | source_file_count | projects_detected | normalized_columns_ok | present_columns | missing_columns | po_start_date_parsed_count | fs_complete_date_parsed_count | invalid_date_rows | total_length_km | min_length_km | max_length_km
Stringing Compiled | 228 | 8 | TB408, TA421, TA325, TA413, TA416, TA418, TA419, TA505 | TRUE | From AP, To AP, Method, Section Readiness, P/O Starting Date, P/O Completion Date, P/O, F/S Starting Date, F/S/ Completion Date, Length, Status, Gang Name |  | 121 | 115 | 0 | 101.8487 | 0.16 | 2.9976

## Issues
s no | sec | from_ap |  | to_ap | span m | method | balance fdn | balance erc | section_readiness | starting date | completion date | po_start_date | po_completion_date | po | fs_starting_date | fs_complete_date | length_m | status | completion month | jmc no | gang_name | hindrance | remarks | district | _source_file | Issues
116 | BAR | 157/0 | ~ | 158/0 | 1575.8 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Deepak Sarkar |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
117 | BAR | 168/0 | ~ | 169/0 | 1044 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Sindhu Const. |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
118 | BAR | 177/0 | ~ | 178/0 | 405 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
119 | BAR | 178/0 | ~ | 179/0 | 278 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Ruhul Amin |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
120 | BAR | 189/0 | ~ | 190/0 | 829 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Md Anwar |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
121 | BAR | 191/0 | ~ | 191A/0 | 1477 | TSE | 0 | 0 | Ready |  |  | 2025-10-22 | 2025-10-25 | 1477 | 2025-10-25 |  |  | WIP |  |  | Alam Construction |  |  | Vadodara | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
122 | BAR | 191A/0 | ~ | 192/0 | 612 | Manual | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-19 | 612 | 2025-10-24 |  |  | WIP |  |  | Md Anwar |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
123 | BAR | 194/0 | ~ | 195/0 | 182 | Manual | 0 | 0 | Ready |  |  | 2025-10-24 |  |  | 2025-10-24 |  |  | WIP |  |  | Enamul Haque |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
124 | BAR | 195/0 | ~ | 195A/0 | 2481 | TSE | 0 | 0 | Ready |  |  | 2025-10-19 | 2025-10-26 | 2481 |  |  |  | WIP |  |  | Enamul Haque |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
125 | BAR | 195A/0 | ~ | 196/0 | 1542 | TSE | 0 | 0 | Ready |  |  | 2025-10-12 | 2025-10-18 | 1542 |  |  |  | WIP |  |  | Muslehuddin |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
126 | BAR | 196/0 | ~ | 197/0 | 246 | Manual | 0 | 0 | Ready | [8 empty] | WIP |  |  | Giyash |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
127 | BAR | 197/0 | ~ | 198/0 | 1740 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Muslehuddin |  |  | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
128 | BAR | 204/0 | ~ | 205/0 | 198 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 2 |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
129 | BAR | 248/0 | ~ | 249/0 | 2525 | TSE | 0 | 0 | Ready | [8 empty] | WIP |  |  | Kamaruddin |  |  | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
130 | BAR | 274/0 | ~ | 275/0 | 402 | Manual | 0 | 0 | Ready |  |  | 2025-10-23 | 2025-10-25 | 402 |  |  |  | WIP |  |  | Bhola |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid F/S Complete Date
131 | BAR | 275/0 | ~ | 276/0 | 177 | Hotline | 0 | 0 | Ready | [8 empty] | WIP |  |  | Dharmendra 1 |  |  | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
132 | JMB | 101/0 | ~ | 102/0 | 665 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Bharuch | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
133 | JMB | 102/0 | ~ | 103/0 | 685 | Manual | 0 | 102/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
134 | JMB | 103/0 | ~ | 104/0 | 680.12 | Manual | 103/0, | 103/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
135 | JMB | 104/0 | ~ | 105/0 | 386.59 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
136 | JMB | 105/0 | ~ | 106/0 | 256.45 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
137 | BAR | 153/0 | ~ | 154/0 | 620 | Manual | 154/0, | 154/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
138 | BAR | 154/0 | ~ | 154/1 | 620 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
139 | BAR | 154/1 | ~ | 155/0 | 415 | Manual | 0 | 154/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
140 | BAR | 159/0 | ~ | 159/2 | 720 | Manual | 0 | 159/2 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
141 | BAR | 159/2 | ~ | 160/0 | 1152.2 | TSE | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
142 | BAR | 160/0 | ~ | 161/0 | 229.82 | Hotline | 0 | 160/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
143 | BAR | 165/0 | ~ | 165/4 | 1613 | TSE | 165/4 | 165/4 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
144 | BAR | 165/4 | ~ | 165/5 | 538 | Manual | 165/5 | 165/5 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
145 | BAR | 165/5 | ~ | 166/0 | 423 | Manual | 166/0, | 166/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
146 | BAR | 166/0 | ~ | 167/0 | 270 | Hotline | 167/0, | 167/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
147 | BAR | 167/0 | ~ | 167/1 | 342 | Manual | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
148 | BAR | 167/1 | ~ | 168/0 | 1338 | TSE | 167/1 | 167/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
149 | BAR | 169/0 | ~ | 171/0 | 433 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
150 | BAR | 171/0 | ~ | 172/0 | 274 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
151 | BAR | 172/0 | ~ | 173/0 | 1123 | TSE |  | 172/1,173/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
152 | BAR | 173/0 | ~ | 174/0 | 232 | Hotline |  | 173/0, ,174/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
153 | BAR | 174/0 | ~ | 174/1 | 381 | Manual |  | 174/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
154 | BAR | 174/1 | ~ | 175/0 | 289 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
155 | BAR | 175/0 | ~ | 176/0 | 979 | TSE |  | 175/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
156 | BAR | 176/0 | ~ | 177/0 | 232 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
157 | BAR | 179/0 | ~ | 180/0 | 264 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
158 | BAR | 180/0 | ~ | 181/0 | 263 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
159 | BAR | 181/0 | ~ | 182/0 | 1778 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
160 | BAR | 182/0 | ~ | 182A/0 | 246 | Hotline | 0 | 182A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
161 | BAR | 182A/0 | ~ | 183/0 | 430 | Manual | 0 | 182A/0, ,183/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
162 | BAR | 183/0 | ~ | 184/0 | 234 | Hotline | 0 | 183/0, ,184/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
163 | BAR | 184/0 | ~ | 184/1 | 468 | Manual | 0 | 184/0, ,184/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
164 | BAR | 184/1 | ~ | 185/0 | 412 | Manual | 0 | 184/1,185/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
165 | BAR | 185/0 | ~ | 186/0 | 820 | Manual | 0 | 185/1,185/0, 1,86/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
166 | BAR | 186/0 | ~ | 187/0 | 399 | Hotline | 0 | 186/0, ,187/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
167 | BAR | 187/0 | ~ | 188/0 | 1510 | TSE | 0 | 187/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
168 | BAR | 188/0 | ~ | 189/0 | 218 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
169 | BAR | 190/0 | ~ | 191/0 | 329 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
170 | BAR | 198/0 | ~ | 199/0 | 1149 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
171 | BAR | 199/0 | ~ | 200/0 | 221 | Hotline | 0 | 200/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
172 | BAR | 200/0 | ~ | 201/0 | 204 | Hotline | 0 | 200/0, ,201/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
173 | BAR | 201/0 | ~ | 201/1 | 532 | Manual | 0 | 201/0, ,201/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
174 | BAR | 201/1 | ~ | 202/0 | 367 | Manual | 0 | 201/1,202/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
175 | BAR | 202/0 | ~ | 203/0 | 788 | Manual | 0 | 202/0, ,203/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
176 | BAR | 203/0 | ~ | 203/1 | 460 | Manual | 0 | 203/0, ,203/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
177 | BAR | 203/1 | ~ | 204/0 | 425 | Manual | 0 | 203/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
178 | BAR | 205/0 | ~ | 206/0 | 1063 | TSE | 0 | 206/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
179 | BAR | 206/0 | ~ | 208/0 | 412 | Hotline | 0 | 206/0, ,208/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
180 | BAR | 208/0 | ~ | 209/0 | 410 | Manual | 0 | 208/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
181 | BAR | 209/0 | ~ | 210/0 | 699 | Manual | 0 | 209/1,210/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
182 | BAR | 210/0 | ~ | 211/0 | 223 | Hotline | 0 | 210/0, ,211/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
183 | BAR | 211/0 | ~ | 211A/0 | 1158 | TSE | 0 | 211/0, ,211A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
184 | BAR | 211A/0 | ~ | 212/0 | 1024 | TSE | 0 | 211A/0, 211A/1, 211A/2, 212/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
185 | BAR | 212/0 | ~ | 213/0 | 248 | Hotline | 0 | 212/0, ,213/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
186 | BAR | 213/0 | ~ | 214/0 | 771 | Manual | 0 | 213/1,213/0, ,214/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
187 | BAR | 214/0 | ~ | 215/0 | 713 | Manual | 0 | 214/0,214/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
188 | BAR | 215/0 | ~ | 216/0 | 632 | Hotline | 0 | 215/1, ,216/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
189 | BAR | 216/0 | ~ | 217/0 | 456 | Hotline | 0 | 216/0, ,217/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
190 | BAR | 217/0 | ~ | 217A/0 | 347 | Hotline | 0 | 217/0, ,217A/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
191 | BAR | 217A/0 | ~ | 218/0 | 1174 | TSE | 0 | 217A/0, ,218/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
192 | BAR | 218/0 | ~ | 219/0 | 822 | Manual | 0 | 218/1, 218/0, 219/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
193 | BAR | 219/0 | ~ | 220/0 | 242 | Hotline | 0 | 219/0, 220/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
194 | BAR | 220/0 | ~ | 221/0 | 735 | Manual | 0 | 220/1,222/0, ,221/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
195 | BAR | 221/0 | ~ | 222/0 | 222 | Hotline | 0 | 221/0, ,222/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
196 | BAR | 222/0 | ~ | 222/1 | 388 | Manual | 0 | 222/0, 222/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
197 | BAR | 222/1 | ~ | 223/0 | 183 | Hotline | 0 | 222/1,223/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
198 | BAR | 223/0 | ~ | 224/0 | 1398 | TSE | 0 | 223/0, 223/2, 223/3 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
199 | BAR | 224/0 | ~ | 225/0 | 235 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
200 | BAR | 225/0 | ~ | 226/0 | 678 | Manual | 0 | 225/1, 226/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
201 | BAR | 226/0 | ~ | 227/0 | 417 | Manual | 0 | 226/0, ,227/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
202 | BAR | 227/0 | ~ | 228/0 | 239 | Manual | 0 | 227/0, ,228/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
203 | BAR | 228/0 | ~ | 229/0 | 196 | Hotline | 0 | 228/0, ,229/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
204 | BAR | 229/0 | ~ | 229/1 | 549 | Manual | 0 | 229/0, ,229/1 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
205 | BAR | 229/1 | ~ | 230/0 | 1884 | TSE | 0 | 229/1230/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
206 | BAR | 230/0 | ~ | 231/0 | 227 | Hotline | 0 | 230/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
207 | BAR | 231/0 | ~ | 232/0 | 419 | Manual | 0 | 232/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
208 | BAR | 232/0 | ~ | 233/0 | 195 | Hotline | 0 | 232/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
209 | BAR | 233/0 | ~ | 234/0 | 305 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
210 | BAR | 234/0 | ~ | 235/0 | 328 | Hotline | 0 | 235/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
211 | BAR | 235/0 | ~ | 236/0 | 305 | Manual | 0 | 235/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
212 | BAR | 236/0 | ~ | 237/0 | 280 | Hotline | 0 | 237/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
213 | BAR | 237/0 | ~ | 239/0 | 2519 | TSE | 0 | 239/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
214 | BAR | 239/0 | ~ | 240/0 | 248 | Hotline | 0 | 239/0, 240/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
215 | BAR | 240/0 | ~ | 241/0 | 207 | Manual | 0 | 240/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
216 | BAR | 241/0 | ~ | 242/0 | 246 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
217 | BAR | 242/0 | ~ | 243/0 | 1335 | TSE | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
218 | BAR | 243/0 | ~ | 244/0 | 250 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
219 | BAR | 244/0 | ~ | 244/1 | 494 | Manual | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
220 | BAR | 244/1 | ~ | 245/0 | 427 | Manual | 0 | 245/0, | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
221 | BAR | 245/0 | ~ | 246/0 | 569 | Manual | 0 | 245/0 | Not Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
222 | BAR | 246/0 | ~ | 247/0 | 240 | Hotline | 0 | 0 | Ready | [14 empty] | Surat | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
223 | BAR | 247/0 | ~ | 248/0 | 1957 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
224 | BAR | 272/5 | ~ | 272A/0 | 1202 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
225 | BAR | 272A/0 | ~ | 273/0 | 2944 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
226 | BAR | 273/0 | ~ | 274/0 | 1153 | TSE | 0 | 0 | Ready | [14 empty] | Navsari | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
[25 empty] | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date
|  |  |  | Total | 177.3447 | [19 empty] | TA 325 - DPR - 2025-10-26.xlsx | Invalid PO Start Date; Invalid F/S Complete Date

## README_Assumptions
Note | Rules
Compiled from DPR files: stringing sheet consolidation. | Preserve raw columns; diagnostics include column presence and date parsing; PO start to F/S complete inclusive for daily expansion.