## TB-412 SUMMARY
Daily Progress Report Summary
Date-24/06/2026
| Contractual Start Date | 2023-12-27 | Project | TB-412 TL
| Contractual Finish Date | 2025-06-23 | Client | Bihar State Power Transmission corporation Limited
| TOE | 2026-02-28 | NOA Supply: | 18. Dated - | 27/12/2023
|  |  | NOA Service: | 19. Dated - | 2023-12-27
TB-412 Chhapra- TL
Sr no. | Activity | Total Quantity |  | Cumm. Progress up to Last Month (May'26) | Target as per L2 Schedule Cummulative (upto June'26) | Target of Month for (June'2026) | Comp This Month (June'2026) | Cumulative Progress | WIP | Balance | No of Gangs | Remark
|  | LOA | Estimated
1 | Route Alignment (Km) | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 | 150.833 | 0 | 0 | 0 | Completed
2 | Detailed Survey (Km) | 165 | 150.833 | 149.21 | 150.833 | 1.623 | 0 | 149.21 | 0 | 1.623 | 0
3 | Detailed Survey Profiling (Km) | 165 | 150.833 | 147.635 | 150.833 | 3.198 | 0 | 147.635 | 0 | 3.198 | 0
4 | Approved detail survey (Km) | 165 | 150.833 | 142.919 | 150.833 | 7.914 | 0 | 142.919 | 0 | 7.914 | 0
5 | Check Survey (Km) | 165 | 150.833 | 119.962 | 150.833 | 25.288 | 0 | 119.962 | 0 | 30.871 | 0 | U/P
6 | Approved check survey ( Km) | 165 | 150.833 | 102.416 | 150.833 | 36.061 | 0 | 102.416 | 0 | 48.417 | 0
7 | Soil Investigation (Nos) | 165 | 147 | 147 | 147 | 0 | 0 | 147 | 0 | 0 | 0 | Completed
8 | Excavation (Nos) | 564 | 505 | 274 | 505 | 80 | 30 | 304 | 0 | 201 | 0
9 | Foundation (Nos) | 564 | 505 | 264 | 505 | 80 | 32 | 296 | 13 | 196 | 13
10 | Earthing (Nos) | 564 | 505 | 185 | 505 | 80 | 29 | 214 | 0 | 291 | 0
11 | Tower Erection (Nos) | 564 | 505 | 87 | 505 | 70 | 38 | 125 | 8 | 372 | 8
12 | Tack Welding (Nos) | 564 | 505 | 21 | 505 | 55 | 0 | 21 | 0 | 484 | 0
13 | Stringing (Km) | 165 | 150.833 | 0 | 150.833 | 12 | 3.199 | 3.199 | 0.349 | 147.285 | 2
14 | OPGW Stringing (Km) | 165 | 150.833 | 0 | 150.833 | 0 | 0 | 0 | 0 | 150.833 | 0
Key Challenges-
| FOUNDATION | 03 Nos Supervisors required
01 Nos store assistant required
| ERCTION | 02 Nos Gang required urgently
| STRINGING | 02 Nos Gang required urgently

## Summary-
Daily Progress Report
Date-24/06/2026
| Contractual Start Date | 2023-12-27 | Project | TB-412 TL
| Contractual Finish Date | 2025-06-23 | Client | Bihar State Power Transmission corporation Limited
| TOE | 2026-02-28 | NOA Supply: | 18. Dated - | 27/12/2023
|  |  | NOA Service: | 19. Dated - | 2023-12-27
220 KV DC Twin Moose Chhapra - Amnour TL
Sr no. | Activity | Total Quantity |  | Cumm. Progress up to Last Month (May'26) | Target as per L2 Schedule Cummulative (upto June'26) | Target of Month for (June'2026) | Comp This Month (June'2026) | Cumulative Progress | WIP | Balance | No of Gangs | Remark
|  | LOA | Estimated
1 | Route Alignment (Km) | 25 | 6.6 | 6.6 | 6.6 | 0 | 0 | 6.6 | 0 | 0
2 | Detailed Survey (Km) | 25 | 6.6 | 6.6 | 6.6 | 0 | 0 | 6.6 | 0 | 0
3 | Detailed Survey Profiling (Km) | 25 | 6.6 | 6.6 | 6.6 |  |  | 6.6 | 0 | 0 |  | Revised 0.33 KM Profile Submitted to BSPTCL HO from 23.12.2025
4 | Approved detail survey (Km) | 25 | 6.6 | 6.27 | 6.6 | 0.33 | 0 | 6.27 | 0 | 0.33
5 | Check Survey (Km) | 25 | 6.6 | 5.539 | 6.6 | 1.061 | 0 | 5.539 | 0 | 1.061
6 | Approved check survey ( Km) | 25 | 6.6 | 5.539 | 6.6 | 1.061 | 0 | 5.539 | 0 | 1.061
7 | Soil Investigation (Nos) | 25 | 7 | 7 | 7 | 0 | 0 | 7 | 0 | 0 |  | Completed
8 | Excavation (Nos) | 82 | 28 | 23 | 28 | 5 | 0 | 23 | 0 | 5
9 | Foundation (Nos) | 82 | 28 | 21 | 28 | 7 | 2 | 23 | 1 | 4 | 1
10 | Earthing (Nos) | 82 | 28 | 14 | 28 | 7 | 1 | 15 |  | 13
11 | Tower Erection (Nos) | 82 | 28 | 8 | 28 | 10 | 3 | 11 | 2 | 15 | 2
12 | Tack Welding (Nos) | 82 | 28 | 0 | 28 | 10 | 0 | 0 | 0 | 28
13 | Stringing (Km) | 25 | 6.6 | 0 | 6.6 | 2 | 0 | 0 | 0 | 6.6
14 | OPGW Stringing (Km) | 25 | 6.6 | 0 | 6.6 | 0 | 0 | 0 | 0 | 6.6
LILO 400 KV DC QUAD ACSR
Sr no. | Activity | Total Quantity |  | Cumm. Progress up to Last Month (May'26) | Target as per L2 Schedule Cummulative (upto June'26) | Target of Month for (June'2026) | Comp This Month (June'2026) | Cumulative Progress | WIP | Balance | No of Gangs | Remark
|  | LOA | Estimated
1 | Route Alignment (Km) | 40 | 41.273 | 41.273 | 41.273 | 0 | 0 | 41.273 | 0 | 0 | 0
2 | Detailed Survey (Km) | 40 | 41.273 | 41.273 | 41.273 | 0 | 0 | 41.273 | 0 | 0 | 0
3 | Detailed Survey Profiling (Km) | 40 | 41.273 | 39.698 | 41.273 | 1.575 | 0 | 39.698 | 0 | 1.575 | 0 | Pendig for MC tower
4 | Approved detail survey (Km) | 40 | 41.273 | 37.576 | 41.273 | 3.697 | 0 | 37.576 | 0 | 3.697 | 0
5 | Check Survey (Km) | 40 | 41.273 | 32.046 | 41.273 | 9.227 | 0 | 32.046 | 0 | 9.227 | 0
6 | Approved check survey ( Km) | 40 | 41.273 | 14.5 | 41.273 | 20 | 0 | 14.5 | 0 | 26.773 | 0
7 | Soil Investigation (Nos) | 40 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | Completed
8 | Excavation (Nos) | 122 | 129 | 86 | 129 | 20 | 5 | 91 |  | 38 | 0
9 | Foundation (Nos) | 122 | 129 | 80 | 129 | 16 | 6 | 86 | 4 | 39 | 4
10 | Earthing (Nos) | 122 | 129 | 52 | 129 | 16 | 9 | 61 | 0 | 68 | 0
11 | Tower Erection (Nos) | 122 | 129 | 31 | 129 | 25 | 12 | 43 | 3 | 83 | 3
12 | Tack Welding (Nos) | 122 | 129 | 10 | 129 | 25 | 0 | 10 | 0 | 119
13 | Stringing (Km) | 40 | 41.273 | 0 | 41.273 | 5 | 0 | 0 |  | 41.273 | 1 | Gang Reached at store
14 | OPGW Stringing (Km) | 40 | 41.273 | 0 | 41.273 | 0 | 0 | 0 | 0 | 41.273 | 0
220 KV D/C Chhapra -Gopalganj TL
Sr no. | Activity | Total Quantity |  | Cumm. Progress up to Last Month (May'26) | Target as per L2 Schedule Cummulative (upto June'26) | Target of Month for (June'2026) | Comp This Month (June'2026) | Cumulative Progress | WIP | Balance | No of Gangs | Remark
|  | LOA | Estimated
1 | Route Alignment (Km) | 100 | 102.96 | 102.96 | 102.96 | 0 | 0 | 102.96 | 0 | 0 |  | Completed
2 | Detailed Survey (Km) | 100 | 102.96 | 101.337 | 102.96 | 1.623 | 0 | 101.337 | 0 | 1.623
3 | Detailed Survey Profiling (Km) | 100 | 102.96 | 101.337 | 102.96 | 1.623 | 0 | 101.337 | 0 | 1.623 |  | Pendig for MC tower
4 | Approved detail survey (Km) | 100 | 102.96 | 99.073 | 102.96 | 3.887 | 0 | 99.073 | 0 | 3.887 |  | 1.051 km profile submitted to BSPTCL HO
5 | Check Survey (Km) | 100 | 102.96 | 82.377 | 102.96 | 15 | 0 | 82.377 | 0 | 20.583 |  | Under Progress
6 | Approved check survey ( Km) | 100 | 102.96 | 82.377 | 102.96 | 15 | 0 | 82.377 | 0 | 20.583
7 | Soil Investigation (Nos) | 100 | 100 | 100 | 100 | 0 | 0 | 100 | 0 | 0 |  | 21 Loc Approved
8 | Excavation (Nos) | 360 | 348 | 165 | 348 | 55 | 25 | 190 | 0 | 158
9 | Foundation (Nos) | 360 | 348 | 163 | 348 | 57 | 24 | 187 | 8 | 153 | 8
10 | Earthing (Nos) | 360 | 348 | 119 | 348 | 57 | 19 | 138 | 0 | 210
11 | Tower Erection (Nos) | 360 | 348 | 48 | 348 | 35 | 23 | 71 | 3 | 274 | 3
12 | Tack Welding (Nos) | 360 | 348 | 11 | 348 | 20 | 0 | 11 | 0 | 337
13 | Stringing (Km) | 100 | 102.96 | 0 | 102.96 | 5 | 3.199 | 3.199 | 0.349 | 99.412 | 1
14 | OPGW Stringing (Km) | 100 | 102.96 | 0 | 102.96 | 0 | 0 | 0 | 0 | 102.96

## Survey Status (hidden)
TB412 BSPTCL - Survey Status
Sl | Line Name | Activity |  | Length | Location | Remarks / Plan for completion
|  |  |  | km | Nos.
1 | LILO of 400 kv Barh (NTPC)- Motihari (DMTCL) D/C ( QUAD) Transmission line at Chhapra (New) | NOA | - | 40 | 122
|  | Route Alignment | Submitted | 41.27 | 128
|  |  | Approved | 41.27 | 128
|  | Detailed Survey | Completed | 36.884 | 122 | 1.575KM Pending at BSPTCL HO MC TSD Required
|  |  | Submitted | 36.884 | 112
|  |  | Approved | 36.884 | 112
|  | Check Survey | Completed | 32.046 | 52 | Balance Check Survey Under progress
|  |  | Submitted | 14.5 | 0
|  |  | Approved | 14.5 | 0
2 | 220 KV D/C Chapra - Gopalganj Transmission Line with ACSR Zebra Conductor | NOA | - | 100 | 360
|  | Route Alignment | Submitted | 102.96 | 348
|  |  | Approved | 102.96 | 348
|  | Detailed Survey | Completed | 101.44 | 340
|  |  | Submitted | 99.073 | 312 | 1.051 km profile submitted to BSPTCL HO from 15.12.2025
|  |  | Approved | 99.073 | 312
|  | Check Survey | Completed | 82.377 | 276
|  |  | Submitted | 82.377 | 276
|  |  | Approved | 82.377 | 276
3 | Construction of 220 KV D/C Twin Moose Chhapra- Amnaur Transmission line- | NOA | - | 25 | 82
|  | Route Alignment | Submitted | 6.6 | 28
|  |  | Approved | 6.6 | 28
|  | Detailed Survey | Completed | 6.6 | 28
|  |  | Submitted | 6.475 | 25 | 0.33 Revised Profile Submitted to BSPTCL site office from 15.12.2025
|  |  | Approved | 6.475 | 25
|  | Check Survey | Completed | 5.5 | 22
|  |  | Submitted | 5.5 | 22
|  |  | Approved | 5.5 | 22

## Sheet3 (hidden)
PROGRESS SUMMARY PLAN VS ACTUAL
Foundation | Nos. | Comp Till Jan-26 | Comp Till Feb-26 | Plan Feb-26 | Actual Feb-26 | WIP | Gang | Balance | Remarks
400kV LILO | 128 | 25 | 28 | 25 | 3 | 5 | 5 | 95
220kV Gopalganj | 348 | 42 | 50 | 45 | 8 | 5 | 5 | 293
220kV Amnour | 28 | 12 | 12 | 5 | 0 | 0 | 0 | 16
Total Nos | 504 | 79 | 90 | 75 | 11 | 10 | 10 | 404
Erection | Nos. | Comp Till Jan-26 | Comp Till Feb-26 | Plan Feb-26 | Actual Feb-26 | WIP | Gang | Balance | Remarks
400kV LILO | 128 | 0 | 0 | 10 | 0 | 1 | 1 | 127
220kV Gopalganj | 348 | 0 | 0 | 4 | 0 | 0 | 0 | 348
220kV Amnour | 28 | 1 | 2 | 6 | 1 | 1 | 1 | 25
Total Nos | 504 | 1 | 2 | 20 | 1 | 2 | 2 | 500

## DPR Sheet
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : STATUS AS ON |  |  |  |  | Date-24/06/2026
Name of the Project: | TB-412 T/L
Contract No. & Date : | NOA Supply/Service-18,19, Dated 27.12.2023
ROUTE ALIGNMENT PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 41.273 | 41.273 | 0 | 41.273 | 0
220 D/C SZ Chapra-Gopalganj | 102.96 | 102.96 | 0 | 102.96 | 0
220 D/C TM Chapra-Amnour | 6.6 | 6.6 | 0 | 6.6 | 0
TOTAL | 150.833 | 150.833 | 0 | 150.833 | 0
SOIL INVESTIGATION PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 40 | 40 | 0 | 40 | 0
220 D/C SZ Chapra-Gopalganj | 100 | 100 | 0 | 100 | 0
220 D/C TM Chapra-Amnour | 7 | 7 | 0 | 7 | 0
TOTAL | 147 | 147 | 0 | 147 | 0
DETAILED SURVEY PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 41.273 | 37.576 | 0 | 37.576 | 3.697
220 D/C SZ Chapra-Gopalganj | 102.96 | 99.073 | 0 | 99.073 | 3.887
220 D/C TM Chapra-Amnour | 6.6 | 6.27 | 0 | 6.27 | 0.33
TOTAL | 150.833 | 142.919 | 0 | 142.919 | 7.914
CHECK SURVEY PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 41.273 | 14.5 | 0 | 14.5 | 26.773
220 D/C SZ Chapra-Gopalganj | 102.96 | 82.377 | 0 | 82.377 | 20.583
220 D/C TM Chapra-Amnour | 6.6 | 5.539 | 0 | 5.539 | 1.061
TOTAL | 150.833 | 102.416 | 0 | 102.416 | 48.417
FOUNDATION PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 129 | 80 | 6 | 86 | 43
220 D/C SZ Chapra-Gopalganj | 348 | 163 | 24 | 187 | 161
220 D/C TM Chapra-Amnour | 28 | 21 | 2 | 23 | 5
TOTAL | 505 | 264 | 32 | 296 | 209
EARTHING PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 129 | 52 | 9 | 61 | 68
220 D/C SZ Chapra-Gopalganj | 348 | 119 | 19 | 138 | 210
220 D/C TM Chapra-Amnour | 28 | 14 | 1 | 15 | 13
TOTAL | 505 | 185 | 29 | 214 | 291
TOWER ERECTION PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 129 | 31 | 12 | 43 | 86
220 D/C SZ Chapra-Gopalganj | 348 | 48 | 23 | 71 | 277
220 D/C TM Chapra-Amnour | 28 | 8 | 3 | 11 | 17
TOTAL | 505 | 87 | 38 | 125 | 380
STRINGING PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 41.273 | 0 | 0 | 0 | 41.273
220 D/C SZ Chapra-Gopalganj | 102.96 | 0 | 3.199 | 3.199 | 99.761
220 D/C TM Chapra-Amnour | 6.6 | 0 | 0 | 0 | 6.6
TOTAL | 150.833 | 0 | 3.199 | 3.199 | 147.634
OPGW STRINGING PROGRESS SUMMARY
T/L Name | TOTAL QTY (Tentative) | COMPLETED UP TO PREV MONTH | COMP. IN CURRENT MONTH | CUMULATIVE | BAL.QTY
400kV D/C QM LILO | 41.273 | 0 | 0 | 0 | 41.273
220 D/C SZ Chapra-Gopalganj | 102.96 | 0 | 0 | 0 | 102.96
220 D/C TM Chapra-Amnour | 6.6 | 0 | 0 | 0 | 6.6
TOTAL | 150.833 | 0 | 0 | 0 | 150.833
TACK WELDING PROGRESS SUMMARY
400kV D/C QM LILO | 129 | 10 | 0 | 10 | 119
220 D/C SZ Chapra-Gopalganj | 348 | 11 | 0 | 11 | 337
220 D/C TM Chapra-Amnour | 28 | 0 | 0 | 0 | 28
TOTAL | 505 | 21 | 0 | 21 | 484

## WIP
KEC INTERNATIONAL LIMITED
DAILY PROGRESS REPORT : STATUS AS ON | [8 empty] | Date-24/06/2026
Name of the Project: |  |  | TB-412 T/L
Contract No. & Date : |  |  | NOA Supply/Service-18,19, Dated 27.12.2023
FOUNDATION
T/L Name | SR.NO. | GANG NAME | LOC. NO. | T.O.T | T.O.CL | D.O.S | D.O.C | MP | REMARKS
400 KV LOOP IN | 1 | Nav Durga Traders | 27/1 | DA+6 | PS | 2026-05-27 | 2026-06-05 |  | Completed
400 KV LOOP IN | 2 | Nav Durga Traders | 20/0 | DC+0 | PS | 2026-06-05 | 2026-06-10 |  | Completed
400 KV LOOP OUT | 3 | Rajeshwar | 5/0 | DD+0 | PS | 2026-06-05 | 2026-06-14 |  | Completed
400 KV LOOP OUT | 4 | Nav Durga Traders | 10/0 | DD+0 | PS | 2026-06-11 | 2026-06-16 |  | Completed
400 KV LOOP OUT | 5 | Nav Durga Traders | 9/0 | DB+0 | PS | 2026-06-17 | 2026-06-21 |  | Completed
400 KV LOOP OUT | 6 | Nav Durga Traders | 8/0 | DD+0 | PS | 2026-06-17 | 2026-06-24 |  | Completed
400 KV LOOP OUT | 7 | AR | 16/0 | DD+9 | PS | 2026-06-11 |  | 12 | RCC WIP
400 KV LOOP IN | 8 | Nav Durga Traders | 12/0 | DB+3 | PS | 2026-06-21 |  | 12 | PROP SETTING WIP
400 KV LOOP OUT | 9 | Rajeshwar | 5/1 | DD+0 | PS | 2026-06-20 |  | 12 | RCC WIP
400 KV LOOP OUT | 10 | Nav Durga Traders | 7/0 | DB+0 | PS | 2026-06-25 |  | 12 | Excavation WIP
220 TM Chapra-Amnour | 1 | Nav Durga Traders | 18/0 | 2TDD+3 | FS | 2026-06-05 | 2026-06-19 |  | Completed
| 2 | Nav Durga Traders | 17/0 | 2TDD+0 | FS | 2026-06-19 | 2026-06-24 |  | Completed
| 3 | Nav Durga Traders | 16/0 | 2TDD+3 | FS | 2026-06-24 |  | 12 | Excavation WIP
220 SZ Chapra-Gopalganj | 1 | Shakti | 145/0 | DD+0 | PS | 2026-05-30 | 2026-06-04 |  | Completed
| 2 | Hetansh | 151/2 | DA+6 | PS | 2026-06-02 | 2026-06-05 |  | Completed
| 3 | Dharmendra Mishra | 89/1 | DA+3 | FS | 2026-06-02 | 2026-06-07 |  | Completed
| 4 | Shakti | 145/2 | DA+3 | PS | 2026-06-02 | 2026-06-08 |  | Completed
| 5 | Maa | 69/0 | DD+3 | FS | 2026-06-04 | 2026-06-10 |  | Completed
| 6 | Anmol | 105/2 | DA+6 | PS | 2026-06-02 | 2026-06-10 |  | Completed
| 7 | Suman Kumar Singh | 79/0 | DC+6 | FS | 2026-06-02 | 2026-06-12 |  | Completed
| 8 | Dharmendra Mishra | 90/0 | DD+0 1MRC | FS | 2026-06-07 | 2026-06-13 |  | Completed
| 9 | Construction Wala | 106/0 | DD+9 | PS | 2026-06-02 | 2026-06-14 |  | Completed
| 10 | Shakti | 146/0 | DC+6 | PS | 2026-06-09 | 2026-06-14 |  | Completed
| 11 | Hetansh | 151/1 | DA+9 | PS | 2026-06-06 | 2026-06-12 |  | Completed
| 12 | Shakti | 138/0 | DD+25 | PS | 2026-06-09 | 2026-06-16 |  | Completed
| 13 | Dharmendra Mishra | 91/0 | DD+6 1MRC | FS | 2026-06-13 | 2026-06-17 |  | Completed
| 14 | Maa | 70/0 | DB+3 1MRC | FS | 2026-06-11 | 2026-06-19 |  | Completed
| 15 | Hetansh | 151/0 | DD+6 | FS | 2026-06-13 | 2026-06-19 |  | Completed
| 16 | Anmol | 130/2 | DA+0 | PS | 2026-06-15 | 2026-06-19 |  | Completed
| 17 | Hetansh | 137/1 | DB+3 | PS | 2026-06-19 | 2026-06-20 |  | Completed
| 18 | Shakti | 147/0 | DC+9 | PS | 2026-06-17 | 2026-06-20 |  | Completed
| 19 | Dharmendra Mishra | 90/1 | DA+0 1MRC | FS | 2026-06-16 | 2026-06-21 |  | Completed
| 20 | Maa | 70/1 | DA+0 1MRC | FS | 2026-06-19 | 2026-06-22 |  | Completed
| 21 | Shakti | 147A/0 | DD+6 | PS | 2026-06-20 | 2026-06-23 |  | Completed
| 22 | Dharmendra Mishra | 91/1 | DA+9 | PS | 2026-06-16 | 2026-06-24 |  | Completed
| 23 | Anmol | 130/1 | DA+3 | PS | 2026-06-19 | 2026-06-24 |  | Completed
| 24 | Shakti | 148/0 | DC+3 | PS | 2026-06-20 | 2026-06-24 |  | Completed
| 25 | Tarush Projects | 80/0 | DD+0 1MRC | FS | 2026-06-14 |  | 8 | RCC WIP
| 26 | Suman Kumar Singh | 80/2 | DA+3 1MRC | FS | 2026-06-16 |  | 9 | RCC WIP
| 27 | Construction Wala | 104/1 | DA+3 | PS | 2026-06-21 |  | 10 | Excavation WIP
| 28 | Hetansh | 149/1 | DA+3 | FS | 2026-06-19 |  | 8 | RCC WIP
| 29 | Maa | 68/0 | DD+3 | FS | 2026-06-22 |  | 10 | Excavation WIP
| 30 | Dharmendra Mishra | 76/1 | DA+6 | PS | 2026-06-24 |  | 10 | Excavation WIP
| 31 | Anmol | 144/0 | DD+9 | PS | 2026-06-24 |  | 10 | Prop Setting WIP
| 32 | Shakti | 148/1 | DA+3 | PS | 2026-06-24 |  | 10 | Prop Setting WIP
ERECTION
T/L Name | SR.NO. | GANG | LOC. NO. | T.O.T | D.O.S | D.O.C | MP | Remarks
400 KV LOOP OUT | 1 | Rang | 20/0 | DD+0 | 2026-05-28 | 2026-06-01 |  | COMPLETED
400 KV LOOP IN | 2 | Pinki | 27/0 | DB+3 | 2026-05-31 | 2026-06-04 |  | COMPLETED
400 KV LOOP IN | 3 | Rang | 20/1 | DA+6 | 2026-05-31 | 2026-06-05 |  | COMPLETED
220 SZ Chapra-Gopalganj | 4 | Sanjeev | 59/0 | DD+0 | 2026-05-31 | 2026-06-05 |  | COMPLETED
220 SZ Chapra-Gopalganj | 5 | Dhruvika | 54/0 | DD+3 | 2026-05-31 | 2026-06-05 |  | COMPLETED
220 SZ Chapra-Gopalganj | 6 | Exel Power | 119/0 | DD+3 | 2026-06-04 | 2026-06-07 |  | COMPLETED
220 SZ Chapra-Gopalganj | 7 | Sanjeev | 59/1 | DA+3 | 2026-06-04 | 2026-06-07 |  | COMPLETED
400 KV LOOP IN | 8 | Rang | 11/3 | DA+0 | 2026-06-06 | 2026-06-10 |  | COMPLETED
400 KV LOOP OUT | 9 | Nirajan | 43/0 | DD+3 | 2026-05-20 | 2026-06-10 |  | COMPLETED
220 SZ Chapra-Gopalganj | 10 | Sanjeev | 59/2 | DA+3 | 2026-06-04 | 2026-06-10 |  | COMPLETED
220 SZ Chapra-Gopalganj | 11 | Reyansh | 101/2 | DA+0 | 2026-06-07 | 2026-06-10 |  | COMPLETED
220 SZ Chapra-Gopalganj | 12 | Dhruvika | 58/0 | DC+0 | 2026-06-04 | 2026-06-11 |  | COMPLETED
220 TM Chapra-Amnour | 13 | SGSE India Pvt Ltd | 8/0 | DC+0 | 2026-06-04 | 2026-06-13 |  | COMPLETED
220 SZ Chapra-Gopalganj | 14 | Sanjeev | 59/3 | DA+6 | 2026-06-11 | 2026-06-13 |  | COMPLETED
220 SZ Chapra-Gopalganj | 15 | Dhruvika | 58/1 | DA+3 | 2026-06-11 | 2026-06-13 |  | COMPLETED
220 SZ Chapra-Gopalganj | 16 | Reyansh | 101/3 | DA+0 | 2026-06-11 | 2026-06-13 |  | COMPLETED
220 SZ Chapra-Gopalganj | 17 | Exel Power | 117/0 | DD+0 | 2026-06-04 | 2026-06-14 |  | COMPLETED
220 SZ Chapra-Gopalganj | 18 | Reyansh | 101/4 | DA+3 | 2026-06-13 | 2026-06-14 |  | COMPLETED
220 SZ Chapra-Gopalganj | 19 | Sanjeev | 59/4 | DA+6 | 2026-06-14 | 2026-06-16 |  | COMPLETED
400 KV LOOP OUT | 20 | Pinki | 38/0 | DD+6 | 2026-06-04 | 2026-06-16 |  | COMPLETED
400 KV LOOP IN | 21 | Rang | 11/2 | DA+0 | 2026-06-06 | 2026-06-16 |  | COMPLETED
400 KV LOOP IN | 22 | Rang | 11/1 | DA+0 | 2026-06-16 | 2026-06-17 |  | COMPLETED
220 SZ Chapra-Gopalganj | 23 | Reyansh | 102/1 | DA+3 | 2026-06-15 | 2026-06-17 |  | COMPLETED
220 SZ Chapra-Gopalganj | 24 | Dhruvika | 81/0 | DC+0 | 2026-06-14 | 2026-06-17 |  | COMPLETED
220 SZ Chapra-Gopalganj | 25 | Sanjeev | 59/5 | DA+0 | 2026-06-16 | 2026-06-17 |  | COMPLETED
220 SZ Chapra-Gopalganj | 26 | Sanjeev | 60/0 | DB+3 | 2026-06-16 | 2026-06-19 |  | COMPLETED
220 SZ Chapra-Gopalganj | 27 | Reyansh | 102/2 | DA+6 | 2026-06-15 | 2026-06-19 |  | COMPLETED
220 SZ Chapra-Gopalganj | 28 | Reyansh | 102/3 | DA+3 | 2026-06-19 | 2026-06-20 |  | COMPLETED
220 SZ Chapra-Gopalganj | 29 | Dhruvika | 81/1 | DA+3 | 2026-06-19 | 2026-06-21 |  | COMPLETED
400 KV LOOP IN | 30 | SGSE India Pvt Ltd | 27/3 | DA+0 | 2026-06-09 | 2026-06-21 |  | COMPLETED
220 SZ Chapra-Gopalganj | 31 | Sanjeev | 62A/0 | DB+3 | 2026-06-19 | 2026-06-22 |  | COMPLETED
400 KV LOOP OUT | 32 | Pinki | 42/0 | DD+0 | 2026-06-18 | 2026-06-22 |  | COMPLETED
220 SZ Chapra-Gopalganj | 33 | Sanjeev | 62/2 | DA+6 | 2026-06-23 | 2026-06-23 |  | COMPLETED
220 TM Chapra-Amnour | 34 | Nirajan | 7/0 | DD+0 | 2026-06-16 | 2026-06-24 |  | COMPLETED
220 TM Chapra-Amnour | 35 | Yashoda Devi | 6/0 | DC+0 | 2026-06-17 | 2026-06-24 |  | COMPLETED
220 SZ Chapra-Gopalganj | 36 | Reyansh | 102/4 | DA+6 | 2026-06-21 | 2026-06-24 |  | COMPLETED
400 KV LOOP IN | 37 | SGSE India Pvt Ltd | 39/3 | DA+0 | 2026-06-20 | 2026-06-24 |  | COMPLETED
400 KV LOOP OUT | 38 | Rang | 21/0 | DC+9 | 2026-06-18 | 2026-06-24 |  | COMPLETED
400 KV LOOP OUT | 39 | Pinki | 41/1 | DD+0 | 2026-06-25 |  | 10 | Middle Section WIP
220 SZ Chapra-Gopalganj | 40 | Sanjeev | 63/0 | DD+0 | 2026-06-25 |  | 17 | Middle Section WIP
400 KV LOOP IN | 41 | RANG | 20/0 | DD+3 | 2026-06-25 |  | 17 | 2nd Section WIP
220 SZ Chapra-Gopalganj | 42 | Reyansh | 106/1 | DA+0 | 2026-06-25 |  | 25 | 2nd Section WIP
400 KV LOOP OUT | 43 | SGSE India Pvt Ltd | 39/1 | DA+6 | 2026-06-25 |  | 25 | 2nd Section WIP
220 TM Chapra-Amnour | 44 | Yashoda Devi | 6/1 | DA+3 | 2026-06-25 |  | 17 | Ground Assembly WIP
220 SZ Chapra-Gopalganj | 45 | Dhruvika | 80/3 | DA+3 | 2026-06-20 |  | 17 | Top Section WIP
STRINGING
Insulatour Hoisting
T/L Name | SR.NO. | GANG | FROM | TO | Section (Km) | D.O.S | D.O.S | MP | Remarks
220 SZ Chapra-Gopalganj | 1 | Anjum Construction | 98/0 | 99/0 | 0.344 | 2026-06-03 | 2026-06-04 | 21 | Completed
|  | Anjum Construction | 99/0 | 100/0 | 1.373 | 2026-06-05 | 2026-06-06 | 21 | Completed
|  | Anjum Construction | 100/0 | 101/0 | 1.483 | 2026-06-06 | 2026-06-07 | 21 | Completed
|  |  | 82/0 | 83/0 | 0.349 |  |  | Material Shifting WIP
Conductor Paying Out,Rough Sag & Final Sag
T/L Name | SR.NO. | GANG | FROM | TO | Section (Km) | D.O.S | D.O.S | MP | Remarks
220 SZ Chapra-Gopalganj | 1 | Anjum Construction | 98/0 | 99/0 | 0.344 | 2026-06-14 | 2026-06-15 |  | Final Sag Completed
| 2 | Anjum Construction | 99/0 | 100/0 | 1.373 | 2026-06-16 | 2026-06-18 |  | Final Sag Completed
| 3 | Anjum Construction | 100/0 | 101/0 | 1.483 | 2026-06-19 | 2026-06-24 |  | Final Sag Completed
Formulas:
D.O.C = [D.O.S]+9
D.O.S = [D.O.C, row above]

## GANG Mapping MAY-26 (hidden)
FOUNDATION
T/L Name | Total Planned Locations for May'26 | Total Gang Deployed (Nos) | Total Man Power (Nos) | Total Completed Locations for May'26 | WIP | Balanced Locations for May'26 as per planned | Remarks
400kV D/C QM LILO | 25 | 5 | 46 | 11 | 5 | 9
220 D/C SZ Chapra-Gopalganj | 65 | 8 | 68 | 27 | 8 | 30
220 D/C TM Chapra-Amnour | 10 | 2 | 18 | 4 | 2 | 4
TOTAL | 100 | 15 | 132 | 42 | 15 | 43
Foundation Plan of May-2026 for TB-412 TL
S.n | LOC N. | TOT | RC | CLASSIFICATION | START DATE | COMPLETION DATE | GANG | Man Power | Exc. Volume (In CUM) | M10 In CUM | M20 In CUM | Steel in MT | Excavation/CUM | M10/CUM | M20/CUM | Steel Per MT | Revenue | Remarks
1 | 80/3 | DA+3 | 1 | FS | 2026-05-01 | 2026-05-05 | Exel Power | 8 | 140.36 | 1.96 | 14.51 | 0.945 | 204 | 8390 | 9675 | 78403 | 259552.925 | Completed
2 | 80/1 | DA+0 | 1 | PS | 2026-05-05 | 2026-05-10 | Exel Power |  | 84.27 | 1.1 | 11.09 | 0.751 | 204 | 8390 | 9675 | 78403 | 192596.483 | WIP
3 | 80/2 | DA+3 | 1 | FS | 2026-05-10 | 2026-05-15 | Exel Power |  | 140.36 | 1.96 | 14.51 | 0.945 | 204 | 8390 | 9675 | 78403 | 259552.925
4 | 80/0 | DD+0 | 1 | FS | 2026-05-15 | 2026-05-20 | Exel Power |  | 329.49 | 4.88 | 32.62 | 2.607 | 204 | 8390 | 9675 | 78403 | 628154.281
5 | 79/0 | DC+6 |  | PS | 2026-05-20 | 2026-05-25 | Exel Power |  | 166.06 | 2.34 | 16.38 | 0.951 | 204 | 8390 | 9675 | 78403 | 286546.593
6 | 78/0 | DD+9 |  | PS | 2026-05-25 | 2026-05-31 | Exel Power |  | 270.75 | 3.96 | 25.67 | 1.84 | 204 | 8390 | 9675 | 78403 | 481076.17
7 | 64/1 | DA+0 |  | FS | 2026-05-01 | 2026-05-04 | MAA | 8 | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 188025.118 | Completed
8 | 64/2 | DA+0 |  | FS | 2026-05-04 | 2026-05-07 | MAA |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121 | Completed
9 | 63/1 | DA+3 |  | FS | 2026-05-07 | 2026-05-10 | MAA |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
10 | 63/0 | DD+0 |  | FS | 2026-05-10 | 2026-05-13 | MAA |  | 329.49 | 4.88 | 31.12 | 2.312 | 204 | 8390 | 9675 | 78403 | 590512.896
11 | 62A/0 | DB+3 |  | FS | 2026-05-13 | 2026-05-16 | MAA |  | 161.63 | 2.27 | 15.51 | 0.848 | 204 | 8390 | 9675 | 78403 | 268562.814
12 | 62/2 | DA+6 |  | FS | 2026-05-16 | 2026-05-19 | MAA |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
13 | 53/0 | DB+6 | 1 | FS | 2026-05-19 | 2026-05-22 | MAA |  | 161.63 | 2.27 | 18.32 | 1.099 | 204 | 8390 | 9675 | 78403 | 315428.717
14 | 52/0 | DD+6 | 1 | FS | 2026-05-22 | 2026-05-25 | MAA |  | 329.49 | 4.88 | 32.62 | 2.607 | 204 | 8390 | 9675 | 78403 | 628154.281
15 | 51/0 | DD+0 | 1 | FS | 2026-05-25 | 2026-05-31 | MAA |  | 329.49 | 4.88 | 32.62 | 2.607 | 204 | 8390 | 9675 | 78403 | 628154.281
16 | 111A/0 | DD+18 | 1 | FS | 2026-05-01 | 2026-05-03 | Shakti | 12 | 344.76 | 5.12 | 34.77 | 2.726 | 204 | 8390 | 9675 | 78403 | 663414.168 | Completed
17 | 112/0 | DD+18 | 1 | FS | 2026-05-03 | 2026-05-05 | Shakti |  | 344.76 | 5.12 | 34.77 | 2.726 | 204 | 8390 | 9675 | 78403 | 663414.168 | Completed
18 | 144/0 | DD+9 |  | FS | 2026-05-05 | 2026-05-07 | Shakti |  | 329.49 | 4.88 | 31.12 | 2.312 | 204 | 8390 | 9675 | 78403 | 590512.896 | WIP
19 | 145/0 | DD+0 |  | FS | 2026-05-07 | 2026-05-09 | Shakti |  | 329.49 | 4.88 | 31.12 | 2.312 | 204 | 8390 | 9675 | 78403 | 590512.896
20 | 145/1 | DA+0 |  | FS | 2026-05-09 | 2026-05-11 | Shakti |  | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 188025.118
21 | 145/2 | DA+3 |  | PS | 2026-05-11 | 2026-05-13 | Shakti |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
22 | 146/0 | DC+6 |  | FS | 2026-05-13 | 2026-05-15 | Shakti |  | 206.67 | 2.96 | 20.24 | 1.129 | 204 | 8390 | 9675 | 78403 | 351334.067
23 | 147/0 | DC+9 |  | PS | 2026-05-15 | 2026-05-17 | Shakti |  | 166.06 | 2.34 | 16.38 | 0.951 | 204 | 8390 | 9675 | 78403 | 286546.593
24 | AP147A/0 | DD+6 |  | FS | 2026-05-17 | 2026-05-19 | Shakti |  | 329.49 | 4.88 | 31.12 | 2.312 | 204 | 8390 | 9675 | 78403 | 590512.896
25 | 148/0 | DC+3 |  | FS | 2026-05-19 | 2026-05-21 | Shakti |  | 206.67 | 2.96 | 20.24 | 1.129 | 204 | 8390 | 9675 | 78403 | 351334.067
26 | 148/1 | DA+3 |  | PS | 2026-05-21 | 2026-05-23 | Shakti |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
27 | 148/2 | DA+3 |  | PS | 2026-05-23 | 2026-05-25 | Shakti |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
28 | 148/3 | DA+6 |  | PS | 2026-05-25 | 2026-05-27 | Shakti |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
29 | 149/0 | DD+0 |  | FS | 2026-05-27 | 2026-05-29 | Shakti |  | 329.49 | 4.88 | 31.12 | 2.312 | 204 | 8390 | 9675 | 78403 | 590512.896
30 | 149/1 | DA+3 |  | PS | 2026-05-29 | 2026-05-31 | Shakti |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
31 | 132/5 | DA+3 |  | PS | 2026-05-01 | 2026-05-08 | Hetansh | 8 | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689 | Completed
32 | 132/1 | DA+3 |  | PS | 2026-05-08 | 2026-05-15 | Hetansh |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
33 | 132/2 | DA+6 |  | PS | 2026-05-15 | 2026-05-22 | Hetansh |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
34 | 132/3 | DA+6 |  | PS | 2026-05-22 | 2026-05-27 | Hetansh |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 210772.121
35 | 132/4 | DA+9 |  | FS | 2026-05-27 | 2026-05-31 | Hetansh |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 176286.689 | WIP
36 | 154/2 | DA+3 |  | PS | 2026-05-01 | 2026-05-08 | AR | 8 | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 188025.118 | Completed
37 | 154/3 | DA+0 |  | FS | 2026-05-08 | 2026-05-15 | AR |  | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 210772.121 | WIP
38 | 151/2 | DA+6 |  | FS | 2026-05-15 | 2026-05-22 | AR |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 286546.593
39 | 152/0 | DC+3 |  | PS | 2026-05-22 | 2026-05-27 | AR |  | 166.06 | 2.34 | 16.38 | 0.951 | 204 | 8390 | 9675 | 78403 | 176286.689
40 | 152/1 | DA+3 |  | PS | 2026-05-27 | 2026-05-31 | AR |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
41 | 106/3 | DA+0 | 1 | PS | 2026-05-01 | 2026-05-08 | Construction Wala | 8 | 84.27 | 1.1 | 11.09 | 0.751 | 204 | 8390 | 9675 | 78403 | 192596.483 | WIP
42 | 106/2 | DA+0 | 1 | PS | 2026-05-08 | 2026-05-15 | Construction Wala |  | 84.27 | 1.1 | 11.09 | 0.751 | 204 | 8390 | 9675 | 78403 | 192596.483
43 | 95/1 | DA+3 |  | FS | 2026-05-15 | 2026-05-22 | Construction Wala |  | 133.87 | 1.85 | 11.77 | 0.697 | 204 | 8390 | 9675 | 78403 | 211352.621
44 | 95/2 | DA+0 |  | FS | 2026-05-22 | 2026-05-27 | Construction Wala |  | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 188025.118
45 | 95/3 | DA+0 |  | FS | 2026-05-27 | 2026-05-31 | Construction Wala |  | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 188025.118
46 | 105/1 | DA+3 |  | FS | 2026-05-01 | 2026-05-08 | Anmol | 8 | 108 | 1.46 | 10.98 | 0.606 | 204 | 8390 | 9675 | 78403 | 188025.118
47 | 104/5 | DA+3 |  | PS | 2026-05-08 | 2026-05-15 | Anmol |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
48 | 104/4 | DA+0 |  | PS | 2026-05-15 | 2026-05-22 | Anmol |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
49 | 105/2 | DA+6 |  | PS | 2026-05-22 | 2026-05-27 | Anmol |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
50 | 106/0 | DD+9 |  | PS | 2026-05-27 | 2026-05-31 | Anmol |  | 270.75 | 3.96 | 25.67 | 1.84 | 204 | 8390 | 9675 | 78403 | 481076.17
51 | 102/2 | DA+6 | 1 | FS | 2026-05-01 | 2026-05-08 | UKC | 8 | 140.36 | 1.96 | 14.51 | 0.945 | 204 | 8390 | 9675 | 78403 | 259552.925 | WIP
52 | 104/0 | DD+0 |  | PS | 2026-05-08 | 2026-05-15 | UKC |  | 270.75 | 3.96 | 25.67 | 1.84 | 204 | 8390 | 9675 | 78403 | 481076.17
53 | 104/1 | DA+3 |  | PS | 2026-05-15 | 2026-05-22 | UKC |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
54 | 104/2 | DA+6 |  | FS | 2026-05-22 | 2026-05-27 | UKC |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
55 | 104/3 | DA+3 |  | FS | 2026-05-27 | 2026-05-31 | UKC |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
56 | 61/2 | DA+9 |  | PS | 2026-05-03 | 2026-05-05 | Suman Kumar Singh moblized by 03.05.2026 |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
57 | 61/3 | DA+3 |  | PS | 2026-05-05 | 2026-05-08 |  |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
58 | 61/4 | DA+3 |  | PS | 2026-05-08 | 2026-05-11 |  |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
59 | 61/5 | DA+6 |  | PS | 2026-05-11 | 2026-05-14 |  |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
60 | 48/2 | DA+6 |  | PS | 2026-05-14 | 2026-05-17 |  |  | 108 | 1.46 | 9.71 | 0.613 | 204 | 8390 | 9675 | 78403 | 176286.689
61 | 48/1 | DA+3 |  | FS | 2026-05-17 | 2026-05-20 |  |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
62 | 47/1 | DA+6 |  | FS | 2026-05-20 | 2026-05-23 |  |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
63 | 47/2 | DA+0 |  | FS | 2026-05-23 | 2026-05-26 |  |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
64 | 47/3 | DA+9 |  | FS | 2026-05-26 | 2026-05-29 |  |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
65 | 48/0 | DD+3 |  | FS | 2026-05-29 | 2026-05-31 |  |  | 133.87 | 1.85 | 11.71 | 0.697 | 204 | 8390 | 9675 | 78403 | 210772.121
66 | 3/1 | 2TDD+9 |  | PS | 2026-04-29 | 2026-05-06 | Navdurga | 10 | 374.98 | 5.6 | 41.61 | 3.201 | 256 | 10487 | 12093 | 98000 | 971609.81 | Completed
67 | 12/0 | 2TDD+0 |  | PS | 2026-05-06 | 2026-05-13 | Navdurga |  | 238.7 | 3.46 | 23.6 | 1.741 | 256 | 10487 | 12093 | 98000 | 553405.02
68 | 16/0 | 2TDD+3 |  | PS | 2026-05-13 | 2026-05-21 | Navdurga |  | 374.98 | 5.6 | 41.61 | 3.201 | 256 | 10487 | 12093 | 98000 | 971609.81 | ROW
69 | 17/0 | 2TDD+0 |  | PS | 2026-05-21 | 2026-05-25 | Navdurga |  | 374.98 | 5.6 | 41.61 | 3.201 | 256 | 10487 | 12093 | 98000 | 971609.81 | ROW
70 | 18/0 | 2TDD+3 |  | PS | 2026-05-25 | 2026-05-30 | Navdurga |  | 374.98 | 5.6 | 41.61 | 3.201 | 256 | 10487 | 12093 | 98000 | 971609.81 | ROW
71 | 6/0 | DC+0 |  | PS | 2026-04-29 | 2026-05-06 | AR | 8 | 374.98 | 5.6 | 41.61 | 3.201 | 256 | 10487 | 12093 | 98000 | 971609.81 | WIP
72 | 12/1 | 2TDA+6 |  | PS | 2026-05-06 | 2026-05-13 | AR |  | 116.81 | 1.69 | 11.78 | 0.733 | 256 | 10487 | 12093 | 98000 | 261915.93 | WIP
73 | 13/0 | 2TDD+18 |  | FS | 2026-05-13 | 2026-05-21 | Navdurga |  | 462.8 | 7 | 52.1 | 3.601 | 256 | 10487 | 12093 | 98000 | 1174829.1
74 | 14/0 | 2TDD+25 |  | PS | 2026-05-21 | 2026-05-25 | AR |  | 385.5 | 5.77 | 43.5 | 3.201 | 256 | 10487 | 12093 | 98000 | 998941.49
75 | 15/0 | 2TDD+9 |  | FS | 2026-05-25 | 2026-05-30 | AR |  | 449.45 | 6.77 | 64.18 | 4.417 | 256 | 10487 | 12093 | 98000 | 1395050.93
76 | 39/4 LO | DA+3 |  | FS | 2026-04-29 | 2026-05-05 | Navdurga-1 | 12 | 370 | 5.51 | 41.93 | 2.783 | 256 | 10487 | 12093 | 98000 | 932296.86 | Completed
93 | 27/1 LI | DA+6 |  | PS | 2026-05-05 | 2026-05-13 | Dharmendra |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23
78 | 45/0 LO | DD+3 |  | FS | 2026-05-13 | 2026-05-17 | Navdurga-1 |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | WIP
79 | 8/0 LI | DB+0 |  | PS | 2026-05-17 | 2026-05-25 | Navdurga-1 |  | 555 | 8.45 | 70.78 | 5.233 | 256 | 10487 | 12093 | 98000 | 1599471.69
80 | 20/1 LI | DA+6 |  | FS | 2026-05-25 | 2026-05-30 | Navdurga-1 |  | 370 | 5.51 | 41.93 | 2.783 | 256 | 10487 | 12093 | 98000 | 932296.86
81 | 39/5 LO | DA+3 |  | FS | 2026-05-01 | 2026-05-06 | Navdurga-2 | 14 | 370 | 5.51 | 41.93 | 2.783 | 256 | 10487 | 12093 | 98000 | 932296.86 | Completed
82 | 12/0 LI | DB+3 |  | PS | 2026-05-06 | 2026-05-12 | Navdurga-2 |  | 555 | 8.45 | 70.78 | 5.233 | 256 | 10487 | 12093 | 98000 | 1599471.69 | ROW
83 | 26/0 LI | DD+0 |  | PS | 2026-05-12 | 2026-05-20 | Navdurga-2 |  | 908.28 | 14.11 | 135.68 | 12.17 | 256 | 10487 | 12093 | 98000 | 3213929.49 | ROW
84 | 9/0 LO | DB+0 |  | PS | 2026-05-20 | 2026-05-26 | Navdurga-2 |  | 555 | 8.45 | 70.78 | 5.233 | 256 | 10487 | 12093 | 98000 | 1599471.69 | Hold for DS
85 | 10/0 LO | DD+0 |  | PS | 2026-05-26 | 2026-05-31 | Navdurga-2 |  | 908.28 | 14.11 | 135.68 | 12.17 | 256 | 10487 | 12093 | 98000 | 3213929.49 | Hold for DS
86 | 36/1 LO | DA+3 |  | FS | 2026-05-01 | 2026-05-06 | Rajeshwar | 10 | 370 | 5.51 | 41.93 | 2.783 | 256 | 10487 | 12093 | 98000 | 932296.86 | WIP
87 | 37/0 LO | DD+9 |  | FS | 2026-05-06 | 2026-05-12 | Rajeshwar |  | 1083 | 16.93 | 160.88 | 13.832 | 256 | 10487 | 12093 | 98000 | 3755850.75 | WIP
88 | 39/0 LO | DB+0 |  | FS | 2026-05-12 | 2026-05-20 | Rajeshwar |  | 1083 | 16.93 | 160.88 | 13.832 | 256 | 10487 | 12093 | 98000 | 3755850.75
89 | 7/0 LO | DB+0 |  | PS | 2026-05-20 | 2026-05-26 | Rajeshwar |  | 555 | 8.45 | 70.78 | 5.233 | 256 | 10487 | 12093 | 98000 | 1599471.69 | Hold for DS
90 | 8/0 LO | DD+0 |  | PS | 2026-05-26 | 2026-05-31 | Rajeshwar |  | 908.28 | 14.11 | 135.68 | 12.17 | 256 | 10487 | 12093 | 98000 | 3213929.49 | Hold for DS
91 | 25/1 LI | DA+3 |  | PS | 2026-05-01 | 2026-05-06 | Dharmendra | 10 | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | Completed
92 | 26/1 LI | DA+3 |  | PS | 2026-05-06 | 2026-05-12 | Dharmendra |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | Completed
93 | 27/3 LI | DA+0 |  | PS | 2026-05-12 | 2026-05-20 | Dharmendra |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | WIP
94 | 27/2 LI | DA+0 |  | PS | 2026-05-20 | 2026-05-26 | Dharmendra |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | ROW
95 | 27/1 LI | DA+6 |  | PS | 2026-05-26 | 2026-05-31 | Dharmendra |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23 | ROW
96 | 15/1 LI | DA+3 |  | PS | 2026-05-08 | 2026-05-12 | Gang-5 Moblized by 08.05.2026 |  | 306 | 4.51 | 36.02 | 2.419 | 256 | 10487 | 12093 | 98000 | 798284.23
97 | 13/0 LI | DD+6 |  | WET | 2026-05-12 | 2026-05-18 |  |  | 758 | 11.7 | 113.63 | 10.175 | 256 | 10487 | 12093 | 98000 | 2688023.49 | ROW
98 | 14/0 LI | DC+6 |  | WET | 2026-05-18 | 2026-05-22 |  |  | 580 | 8.84 | 80.35 | 6.096 | 256 | 10487 | 12093 | 98000 | 1810265.63 | ROW
99 | 15/0 LI | DC+0 |  | PS | 2026-05-22 | 2026-05-27 |  |  | 693.12 | 10.66 | 95.43 | 7.222 | 256 | 10487 | 12093 | 98000 | 2151021.13 | ROW
100 | 20/0 LI | DC+0 |  | FS | 2026-05-27 | 2026-05-31 |  |  | 817 | 12.64 | 111.89 | 8.189 | 256 | 10487 | 12093 | 98000 | 2497315.45 | ROW
ERECTION
T/L Name | Total Planned Locations for May'26 | Total Gang Deployed (Nos) | Total Man Power (Nos) | Total Completed Locations for May'26 | WIP | Balanced Locations for May'26 as per planned
400kV D/C QM LILO | 15 | 3 | 51 | 10 | 3 | 2
220 D/C SZ Chapra-Gopalganj | 55 | 3 | 47 | 18 | 3 | 34
220 D/C TM Chapra-Amnour | 10 | 1 | 0 | 2 | 1 | 7
TOTAL | 80 | 7 | 98 | 30 | 7 | 43
Erection Plan of May-2026 for TB-412 T/L
SL N. | LOC. N. | TOT | Tower Weight (MT) | START DATE | COMPLETION DATE | GANG | MP | Revenue | Remarks
1 | 55/1 | DA+3 | 5.167 | 2026-05-01 | 2026-05-03 | Dhruvika | 16 | 50626.266 | Completed
2 | 55/0 | DD+0 | 8.086 | 2026-05-03 | 2026-05-05 | Dhruvika |  | 79226.628 | Completed
3 | 54/3 | DA+0 | 4.378 | 2026-05-05 | 2026-05-07 | Dhruvika |  | 42895.644 | Completed
4 | 54/2 | DA+6 | 5.713 | 2026-05-07 | 2026-05-09 | Dhruvika |  | 55975.974 | WIP
5 | 54/1 | DA+3 | 5.167 | 2026-05-09 | 2026-05-11 | Dhruvika |  | 50626.266
6 | 54/0 | DD+3 | 9.791 | 2026-05-11 | 2026-05-13 | Dhruvika |  | 95932.218
7 | 58/0 | DC+0 | 6.563 | 2026-05-13 | 2026-05-16 | Dhruvika |  | 64304.274
8 | 58/1 | DA+3 | 5.167 | 2026-05-16 | 2026-05-19 | Dhruvika |  | 50626.266
9 | 59/0 | DD+0 | 8.086 | 2026-05-19 | 2026-05-22 | Dhruvika |  | 79226.628
10 | 64/0 | DD+3 | 9.791 | 2026-05-22 | 2026-05-25 | Dhruvika |  | 95932.218
11 | 64/1 | DA+0 | 4.378 | 2026-05-25 | 2026-05-28 | Dhruvika |  | 42895.644
12 | 64/2 | DA+0 | 4.378 | 2026-05-28 | 2026-05-31 | Dhruvika |  | 42895.644
13 | 114/1 | DA+3 | 5.167 | 2026-05-01 | 2026-05-03 | SANJEEV | 15 | 50626.266 | Completed
14 | 116/2 | DA+3 | 5.167 | 2026-05-03 | 2026-05-05 | SANJEEV |  | 50626.266 | Completed
15 | 89/0 | DB+0 | 5.97 | 2026-05-05 | 2026-05-07 | SANJEEV |  | 58494.06 | Completed
16 | 88/0 | DC+3 | 8.086 | 2026-05-07 | 2026-05-09 | SANJEEV |  | 79226.628 | Completed
17 | 88/1 | DA+6 | 5.713 | 2026-05-09 | 2026-05-11 | SANJEEV |  | 55975.974 | Completed
18 | 87/2 | DA+6 | 5.713 | 2026-05-11 | 2026-05-13 | SANJEEV |  | 55975.974 | Completed
19 | 87/1 | DA+3 | 5.167 | 2026-05-13 | 2026-05-15 | SANJEEV |  | 50626.266 | Completed
21 | 87/0 | DD+3 | 9.791 | 2026-05-15 | 2026-05-17 | SANJEEV |  | 95932.218 | WIP
20 | 86/0 | DD+0 | 8.086 | 2026-05-15 | 2026-05-17 | SANJEEV |  | 79226.628
21 | 87/0 | DD+3 | 9.791 | 2026-05-17 | 2026-05-19 | SANJEEV |  | 95932.218
22 | 87/1 | DA+3 | 5.167 | 2026-05-19 | 2026-05-21 | SANJEEV |  | 50626.266
23 | 87/2 | DA+6 | 5.713 | 2026-05-21 | 2026-05-23 | SANJEEV |  | 55975.974
24 | 88/0 | DC+3 | 8.086 | 2026-05-23 | 2026-05-25 | SANJEEV |  | 79226.628
25 | 88/1 | DA+6 | 5.713 | 2026-05-25 | 2026-05-29 | SANJEEV |  | 55975.974
26 | 89/0 | DB+0 | 5.97 | 2026-05-29 | 2026-05-31 | SANJEEV |  | 58494.06
27 | 83/1 | DA+0 | 6.563 | 2026-05-01 | 2026-05-04 | Exel Power | 16 | 64304.274 | WIP
28 | 118/3 | DA+9 | 6.325 | 2026-05-04 | 2026-05-07 | Exel Power |  | 61972.35
29 | 119/0 | DD+3 | 9.791 | 2026-05-07 | 2026-05-11 | Exel Power |  | 95932.218
30 | 120/0 | DD+0 | 8.086 | 2026-05-11 | 2026-05-15 | Exel Power |  | 79226.628
31 | 120/1 | DA+6 | 5.713 | 2026-05-15 | 2026-05-18 | Exel Power |  | 55975.974
32 | 121/0 | DD+18 | 15.971 | 2026-05-18 | 2026-05-21 | Exel Power |  | 156483.858
33 | 122/0 | DD+25 | 18.623 | 2026-05-21 | 2026-05-24 | Exel Power |  | 182468.154
34 | 123/0 | DC+9 | 6.325 | 2026-05-24 | 2026-05-27 | Exel Power |  | 61972.35
35 | 123/1 | DA+6 | 5.713 | 2026-05-27 | 2026-05-29 | Exel Power |  | 55975.974
36 | 124/0 | DC+0 | 6.563 | 2026-05-29 | 2026-05-31 | Exel Power |  | 64304.274
37 | 113/0 | DD+3 | 9.791 | 2026-05-05 | 2026-05-08 | New Gang-4 |  | 95932.218 | GANG DEPLOYED BY 05.05.2026
38 | 113/1 | DA+6 | 5.713 | 2026-05-08 | 2026-05-11 | New Gang-4 |  | 55975.974
39 | 113/2 | DA+6 | 5.713 | 2026-05-11 | 2026-05-14 | New Gang-4 |  | 55975.974
40 | 113/3 | DA+0 | 4.378 | 2026-05-14 | 2026-05-17 | New Gang-4 |  | 42895.644
41 | 114/0 | DC+3 | 8.086 | 2026-05-17 | 2026-05-20 | New Gang-4 |  | 79226.628
42 | 131/0 | DB+3 | 6 | 2026-05-20 | 2026-05-23 | New Gang-4 |  | 58788
43 | 131/1 | DA+6 | 5.713 | 2026-05-23 | 2026-05-26 | New Gang-4 |  | 55975.974
44 | 131/2 | DA+3 | 5.167 | 2026-05-26 | 2026-05-28 | New Gang-4 |  | 50626.266
45 | 132/0 | DC+3 | 8.086 | 2026-05-28 | 2026-05-31 | New Gang-4 |  | 79226.628
46 | 101/2 | DA+0 | 4.378 | 2026-05-08 | 2026-05-10 | New Gang-5 |  | 42895.644
47 | 102/1 | DA+3 | 5.167 | 2026-05-10 | 2026-05-12 | New Gang-5 |  | 50626.266
48 | 102/2 | DA+6 | 5.713 | 2026-05-12 | 2026-05-14 | New Gang-5 |  | 55975.974
49 | 102/3 | DA+3 | 5.167 | 2026-05-14 | 2026-05-16 | New Gang-5 |  | 50626.266
50 | 102/4 | DA+6 | 5.713 | 2026-05-16 | 2026-05-18 | New Gang-5 |  | 55975.974
52 | 152/2 | DA+6 | 5.713 | 0 | 1900-01-01 | New Gang-5 |  | 55975.974
53 | 152/3 | DA+6 | 6.325 | 1900-01-01 | 1900-01-04 | New Gang-5 |  | 61972.35
54 | 154/1 | DA+6 | 6.325 | 1900-01-04 | 1900-01-07 | New Gang-5 |  | 61972.35
55 | 154/2 | DA+3 | 5.167 | 1900-01-07 | 1900-01-10 | New Gang-5 |  | 50626.266
56 | 6/1 | 2TDA+3 | 8.334 | 2026-05-08 | 2026-05-11 | Kumar K2 |  | 81656.532
57 | 7/0 | 2TDD+0 | 13.664 | 2026-05-10 | 2026-05-13 |  |  | 133879.872
58 | 7/1 | 2TDA+0 | 6.809 | 2026-05-12 | 2026-05-15 |  |  | 66714.582
59 | 8/0 | DC+0 | 10.594 | 2026-05-14 | 2026-05-17 |  |  | 103800.012
60 | 8/1 | 2TDA+3 | 8.334 | 2026-05-16 | 2026-05-19 |  |  | 81656.532 | WIP
61 | 8/2 | 2TDA+6 | 9.048 | 2026-05-18 | 2026-05-21 |  |  | 88652.304
62 | 9/0 | DC+6 | 14.337 | 2026-05-20 | 2026-05-23 |  |  | 140473.926
63 | 11/0 | DC+0 | 10.594 | 2026-05-22 | 2026-05-25 |  |  | 103800.012
64 | 11/4 | DA+0 | 6.809 | 2026-05-24 | 2026-05-27 |  |  | 66714.582
65 | 3/1 | 2TDD+3 | 16.943 | 2026-05-26 | 2026-05-29 |  |  | 166007.514
66 | 26/1 LO | 4DA+0 | 16.922 | 2026-05-01 | 2026-05-08 | Rang | 25 | 165801.756 | Completed
67 | 26/0 LO | 4DC+0 | 31.21 | 2026-05-08 | 2026-05-15 |  |  | 305795.58 | Completed
68 | 19/3 LI | 4DA+0 | 16.922 | 2026-05-15 | 2026-05-20 |  |  | 165801.756 | Completed
69 | 28/0 LO | 4DD+0 | 37.87 | 2026-05-20 | 2026-05-25 |  |  | 371050.26 | wip
70 | 11/3 LI | 4DA+0 | 16.922 | 2026-05-25 | 2026-05-30 |  |  | 165801.756
71 | 25/0 LO | 4DD+0 | 37.87 | 2026-05-01 | 2026-05-08 | Pinki | 26 | 371050.26 | Completed
72 | 35/0 LO | 4DD+3 | 40.17 | 2026-05-08 | 2026-05-15 |  |  | 393585.66 | Completed
73 | 33/0 LO | 4DD+0 | 37.87 | 2026-05-15 | 2026-05-20 |  |  | 371050.26 | WIP
74 | 33/1 LO | 4DA+0 | 16.922 | 2026-05-20 | 2026-05-25 |  |  | 165801.756
75 | 39/1 LO | 4DA+6 | 20.631 | 2026-05-25 | 2026-05-30 |  |  | 202142.538
76 | 19/2 LI | 4DA+0 | 16.922 | 2026-05-01 | 2026-05-08 | New Gang Deployed by 05.05.2026 |  | 165801.756
77 | 11/1 LI | 4DA+0 | 16.922 | 2026-05-08 | 2026-05-15 |  |  | 165801.756
78 | 26/2 LI | 4DA+6 | 20.631 | 2026-05-15 | 2026-05-20 |  |  | 202142.538
79 | 35/0 LO | 4DD+3 | 40.17 | 2026-05-20 | 2026-05-25 |  |  | 393585.66
80 | 36/0 LO | 4DD+0 | 37.87 | 2026-05-25 | 2026-05-30 |  |  | 371050.26
Formulas:
COMPLETION DATE = [WIP]+4
WIP = [COMPLETION DATE, row above]
WIP = [Total Completed Locations for May'26]+2
Total Completed Locations for May'26 = [WIP, row above]
Total Completed Locations for May'26 = [WIP, row above]-1

## Soil Investigation
Soil Investigation Status
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) TL at Chhapra (New) |  |  |  |  | Status as on | Date-24/06/2026
SL.No. | Tower No. | Soil Investigation date | Classification | Remarks | LINE NAME | Discription | Qty
1 | AP 1 | 2025-08-27 | WET | LOOP IN (21.266RKM) | LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) TL at Chhapra (New) | SCOPE | 40
2 | AP 4 | 2025-08-27 | PS |  |  | COMPLETED | 40
3 | AP 5 | 2025-08-27 | PS |  |  | Report Submiteed | 40
4 | AP 7 | 2025-08-27 | PS |  |  | Report Approved | 40
5 | AP 7A | 2025-08-27 | PS |  |  | Balanced | 0
6 | AP 9 | 2025-08-28 | PS
7 | AP 10 | 2025-08-28 | PS |  | 220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose | SCOPE | 7
8 | AP 11 | 2025-08-27 | PS |  |  | COMPLETED | 7
9 | AP 13 | 2025-08-28 | WET |  |  | Report Submiteed | 7
10 | AP 14 | 2025-08-28 | WET |  |  | Report Approved | 7
11 | AP 15 | 2025-08-28 | PS |  |  | Balanced | 0
12 | AP 17 | 2025-08-29 | PS
13 | AP 18 | 2025-08-29 | PS |  | 220 KV D/C Chhapra - Gopalganj Transmission Line with ACSR Zebra Conductor | SCOPE | 100
14 | AP 20 | 2025-08-29 | FS |  |  | COMPLETED | 100
15 | AP 21 | 2025-08-29 | FS |  |  | Report Submited | 25
16 | AP 24 | 2025-08-29 | PS |  |  | Report Approved | 21
17 | AP 25 | 2025-08-29 | PS |  |  | Report Awaited | 36
18 | AP 26 | 2025-08-30 | PS |  |  | Balanced | 0
19 | AP 28 | 2025-08-30 | PS
20 | AP 32 | 2025-08-30 | FS
21 | AP 1 | 2025-09-05 | WET | LOOP OUT (20.007RKM)
22 | AP 3A | 2025-08-30 | WET
23 | AP 5A | 2025-08-30 | PS
24 | AP 8A | 2025-08-31 | PS
25 | AP 9 | 2025-08-31 | PS
26 | AP 11 | 2025-08-31 | PS
27 | AP 12 | 2025-09-01 | PS
28 | AP 15 | 2025-09-01 | PS
29 | AP 15 A | 2025-09-01 | PS
30 | AP 17 | 2025-09-02 | PS
31 | AP 18 | 2025-09-02 | WET
32 | AP 19 | 2025-09-03 | PS
33 | AP 21 | 2025-09-02 | PS
34 | AP 25 | 2025-09-03 | FS
35 | AP 26 | 2025-09-03 | FS
36 | AP 28 | 2025-09-04 | PS
37 | AP 30 | 2025-09-04 | WET
38 | AP 31 | 2025-09-04 | PS
39 | AP 33 | 2025-09-05 | PS
40 | AP 37 | 2025-09-05 | FS
Total Completed |  | 40
220 KV D/C Chhapra - Gopalganj T L with ACSR Zebra Conductor
SL.No. | Location No. | Soil Investigation date | Classification | Remarks
1 | 7/0 | 2024-06-16 | Wet | Approved from BSPTCL
2 | 8/0 | 2024-06-16 | Wet
3 | 10/0 | 2024-06-16 | Wet
4 | 12/0 | 2024-06-16 | Wet
5 | 14/0 | 2024-06-15 | Wet
6 | 15/0 | 2024-06-15 | FS
7 | 17/0 | 2024-06-17 | Wet
8 | 19/0 | 2024-06-17 | Wet
9 | 22/0 | 2024-06-17 | Wet
10 | 26/0 | 2024-06-17 | Wet
11 | 29/0 | 2024-06-18 | Wet
12 | 32/0 | 2024-06-18 | Wet
13 | 34/0 | 2024-06-18 | Wet
14 | 37/0 | 2024-06-18 | Wet
15 | 38/0 | 2024-06-19 | Wet
16 | 39/0 | 2024-06-19 | Wet
17 | 42/0 | 2024-06-19 | Wet
18 | 44/0 | 2024-06-19 | Wet
19 | 45/0 | 2024-06-20 | Wet
20 | 46/0 | 2024-06-20 | Wet
21 | 47/0 | 2024-06-20 | Wet
22 | AP 6 | 2025-12-14 | PS
23 | AP 9A | 2025-12-14 | FS
24 | AP 11 | 2025-11-25 | PS | Report Submitted to BSPTCL Site Office
25 | AP 13 | 2025-11-25 | FS
26 | AP 18 | 2025-11-25 | PS
27 | AP 22 (NEW) | 2025-11-24 | FS
28 | AP 24 | 2025-11-24 | PS
29 | AP 30 | 2025-11-24 | FS
30 | AP 33 | 2025-11-23 | FS
31 | AP 34 (NEW) | 2025-11-23 | FS
32 | AP 41 | 2025-11-23 | FS
33 | AP 48 | 2025-11-22 | PS
34 | AP 49 | 2025-11-22 | PS
35 | AP 51 | 2025-11-22 | FS
36 | AP 54 | 2025-11-21 | FS | Report Submitted to BSPTCL Site Office
37 | AP 55 | 2025-11-21 | PS
38 | AP 57 | 2025-11-21 | WET
39 | AP 59 | 2025-11-20 | FS
40 | AP 60 | 2025-11-20 | FS
41 | AP 61 | 2025-11-20 | FS
42 | AP 62 | 2025-11-19 | FS
43 | AP 63 | 2025-11-19 | FS
44 | AP 64 | 2025-11-19 | FS
45 | AP 65 | 2025-11-17 | FS
46 | AP 67 | 2025-11-17 | FS
47 | AP 68 | 2025-11-17 | FS
48 | AP 69 | 2025-11-16 | FS
49 | AP 71 | 2025-11-16 | FS
50 | AP 72 | 2025-11-16 | FS
51 | AP 73 | 2025-11-15 | FS
52 | AP 74 | 2025-11-15 | PS
53 | AP 76 | 2025-11-15 | PS
54 | AP 78 | 2025-11-14 | PS
55 | AP 80 | 2025-11-14 | FS
56 | AP 81 | 2025-11-14 | FS
57 | AP 83 | 2025-11-13 | FS
58 | AP 85 | 2025-11-13 | FS
59 | AP 87 | 2025-11-13 | FS
60 | AP 89 | 2025-11-12 | PS
61 | AP 92 | 2025-11-12 | PS
62 | AP 93 | 2025-11-12 | PS
63 | AP 95 | 2025-11-11 | PS | Report Submitted to BSPTCL Site Office
64 | AP 97 | 2025-11-11 | PS
65 | AP 98 | 2025-11-10 | PS
66 | AP 100 | 2025-11-10 | PS
67 | AP 101 | 2025-12-14 | FS | PS
68 | AP 102 | 2025-12-14 | FS
69 | AP 103 | 2025-12-13 | PS
70 | AP 105 | 2025-12-13 | FS
71 | AP 106 | 2025-12-13 | PS
72 | AP 107 | 2025-12-13 | FS
73 | AP 109 | 2025-12-12 | FS
74 | AP 110 | 2025-12-12 | FS
75 | AP 111 | 2025-12-12 | FS
76 | AP 112 | 2025-12-12 | FS
77 | AP 114 | 11-12-025 | FS
78 | AP 117 | 11-12-025 | PS
79 | AP 119 | 11-12-025 | FS
80 | AP 121 | 11-12-025 | FS
81 | AP 122 | 10-12-025 | FS
82 | AP 125 | 10-12-025 | FS
83 | AP 128 | 10-12-025 | FS
84 | AP 129 | 10-12-025 | FS
85 | AP 131 | 2025-12-09 | PS
86 | AP 132 | 2025-12-09 | FS
87 | AP 133 | 2025-12-09 | FS
88 | AP 134 | 2025-12-09 | PS
89 | AP 136 | 2025-12-08 | FS
90 | AP 138 | 2025-12-08 | PS
91 | AP 139 | 2025-12-08 | FS
92 | AP 141 | 2025-12-08 | FS
93 | AP 142 | 2025-12-07 | FS
94 | AP 146 | 2025-12-07 | PS
95 | AP 148 | 2025-12-07 | WET
96 | AP 149 | 2025-12-07 | FS
97 | AP 152 | 2025-12-06 | PS
98 | AP 153 | 2025-12-06 | PS
99 | AP 154 | 2025-12-06 | FS
100 | AP 156 | 2025-12-06 | FS
Total Completed |  | 100
220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose
SL.No. | Location No. | Soil Investigation date | Classification | Remarks
1 | AP 4 | 2025-08-24 | PS
2 | AP7 | 2025-08-25 | WET
3 | AP 9 | 2025-08-25 | PS
4 | AP 11 | 2025-08-25 | PS
5 | AP 13 | 2025-08-27 | FS
6 | AP 14 | 2025-08-26 | PS
7 | AP 15 | 2025-08-26 | FS
Total Completed |  | 7

## Sheet1 (hidden)
220 KV D/C Chhapra - Gopalganj Transmission Line with ACSR Zebra Conductor
SL.No. | Location No. | Soil Investigation date | Type of Soil | GPS Co-ordinates (in degree) |  | Remarks/Crossings
|  |  |  | Latitude | Longitude
1 | AP 54 | 2025-11-21 | FS | 26°14'50.9" | 84°33'51.9"
2 | AP 55 | 2025-11-21 | PS | 26°14'17.5" | 84°34'9.6"
3 | AP 57 | 2025-11-21 | WET | 26°13'56.9" | 84°34'40.8"
4 | AP 59 | 2025-11-20 | FS | 26°13'32" | 84°35'20.1"
5 | AP 60 | 2025-11-20 | FS | 26°12'9.6" | 84°35'24.2"
6 | AP 61 | 2025-11-20 | FS | 26°12'2.6" | 84°35'24.5"
7 | AP 62 | 2025-11-19 | FS | 26°11'7" | 84°35'19"
8 | AP 63 | 2025-11-19 | FS | 26°10'37.2" | 84°35'35.6"
9 | AP 64 | 2025-11-19 | FS | 26°10'21.2" | 84°36'6.6"
10 | AP 65 | 2025-11-17 | PS | 26°10'24.8" | 84°36'44.8"
11 | AP 67 | 2025-11-17 | PS | 26°9'58.2" | 84°36'53.3"
12 | AP 68 | 2025-11-17 | FS | 26°9'25.1" | 84°36'43.7" | 800kV HVDC (GPJ_GKP)
13 | AP 69 | 2025-11-16 | FS | 26°9'19.3" | 84°36'41.9"
14 | AP 71 | 2025-11-16 | FS | 26°8'26.3" | 84°36'37.2" | 400kV D/C (BAR_GKP)
15 | AP 72 | 2025-11-16 | FS | 26°8'17" | 84°36'33.2"
16 | AP 73 | 2025-11-15 | FS | 26°8'10.9" | 84°36'36.4" | Railway Crossing
17 | AP 74 | 2025-11-15 | PS | 26°7'28" | 84°36'34.1"
18 | AP 76 | 2025-11-15 | PS | 26°6'58.1" | 84°36'18.9"
19 | AP 78 | 2025-11-14 | PS | 26°6'32.1" | 84°36'38.3"
20 | AP 80 | 2025-11-14 | FS | 26°6'21.7" | 84°36'54.9"
21 | AP 81 | 2025-11-14 | FS | 26°5'42.3" | 84°36'47"
22 | AP 83 | 2025-11-13 | FS | 26°5'11.7" | 84°36'58.6"
23 | AP 85 | 2025-11-13 | FS | 26°4'43" | 84°37'8.9"
24 | AP 87 | 2025-11-13 | FS | 26°4'43.5" | 84°37'44.3"
25 | AP 89 | 2025-11-12 | PS | 26°4'1.7" | 84°38'18.1"
26 | AP 92 | 2025-11-12 | PS | 26°3'5.9" | 84°39'0.9" | 132kV D/C (CHO_SWN)
27 | AP 93 | 2025-11-12 | PS | 26°2'57.1" | 84°38'55.3"

## Progress 400kV QM (hidden)
Client:- |  | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL)
Line Name:- |  | LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN & LOOP OUT
EPC:- |  | KEC International Limited
S.NO. | LOC. NO. | TYPE OF TOWER | ANGLE OF DEVATION | RAISED CHIMNEY | RAISED CHIMNEY |  |  |  | SPAN | Crossing Detail/Statutary | ROW Status | Foundation Status | Contractor Name | Earthing Status | Erection Status | Contractor Name | Tack Welding Status | VILLAGES | Remarks
[5 empty] | A | B | C | D
1 | 1/0 | 4DD+0 | 45° 33' 45"RT | [5 empty] | 112.764 |  |  | HOLD | [5 empty] | ARNA | LOOP IN
2 | 2/0 | 4DD+0 | 35° 58' 12"RT | [5 empty] | 158.659 |  |  | HOLD | [5 empty] | SANDALPUR | LOOP IN
3 | 3/0 | 4DD+0 | 30° 18' 41"RT | [5 empty] | 296 |  |  | HOLD | [5 empty] | SANDALPUR | LOOP IN
4 | 3/1 | 4DA+0 | [6 empty] | 332 |  |  | HOLD | [5 empty] | SANDALPUR | LOOP IN
5 | 3/2 | 4DA+0 | [6 empty] | 277 |  |  | HOLD | [5 empty] | SANDALPUR | LOOP IN
6 | 3/3 | 4DA+0 | [6 empty] | 340.684 |  |  | HOLD | [5 empty] | MOLNAPUR | LOOP IN
7 | 4/0 | 4DC+0 | 18° 12' 5"RT | [5 empty] | 229.841 | NH-722 |  | HOLD | [5 empty] | MOLNAPUR | LOOP IN
8 | 5/0 | 4DD+0 | 50° 6' 30"LT | [5 empty] | 276.925 |  |  | HOLD | [5 empty] | GANESHPATTI | LOOP IN
9 | 6/0 | 4DD+0 | 53° 5' 45"RT | [5 empty] | 357 |  |  | HOLD | [5 empty] | GANESHPATTI | LOOP IN
10 | 6/1 | 4DA+3 | [6 empty] | 243.767 |  |  | HOLD | [5 empty] | BASAUTI | LOOP IN
11 | 7/0 | 4DB+0 | 8° 59' 29"RT | [5 empty] | 338 |  |  | HOLD | [5 empty] | BASAUTI | LOOP IN
12 | 7/1 | 4DA+0 | [6 empty] | 309 |  |  | WIP | Dharmendra Mishra | WIP |  |  |  | MURLI SIRSIA | LOOP IN
13 | 7/2 | 4DA+0 | [6 empty] | 381.534 |  |  | WIP | AR |  |  |  |  | MURLI SIRSIA | LOOP IN
14 | 8/0 | 4DB+0 | 5° 20' 56"LT | [5 empty] | 331.87 |  |  | Completed | AR |  |  |  |  | MURLI SIRSIA | LOOP IN
15 | 9/0 | 4DC+0 | 18° 23' 40"LT | [5 empty] | 341.212 |  |  | Completed | Kutir Vihar | Completed |  |  |  | MURLI SIRSIA | LOOP IN
16 | 10/0 | 4DB+0 | 2° 36' 19"LT | [5 empty] | 243.495 |  |  | Completed | Kutir Vihar | Completed |  |  |  | MURLI SIRSIA | LOOP IN
17 | 11/0 | 4DD+0 | 30° 45' 23"LT | [5 empty] | 316 |  |  | Completed | Kutir Vihar | Completed |  |  |  | JAGARNATHPUR | LOOP IN
18 | 11/1 | 4DA+0 | [6 empty] | 325 |  |  | Completed | Dharmendra Mishra | Completed |  |  |  | JAGARNATHPUR | LOOP IN
19 | 11/2 | 4DA+0 | [6 empty] | 269 |  |  | Completed | Rajeswar Singh |  |  |  |  | BARKI SIRSIA | LOOP IN
20 | 11/3 | 4DA+0 | [6 empty] | 281.828 |  |  | Completed | Dharmendra Mishra |  |  |  |  | BARKI SIRSIA | LOOP IN
21 | 12/0 | 4DB+3 | 7° 1' 5"LT | [5 empty] | 423 |  | ROW | ROW | [5 empty] | BARKI SIRSIA | LOOP IN
22 | 12/1 | 4DA+9 | [6 empty] | 376.095 |  |  | Completed | Dharmendra Mishra |  |  |  |  | BHIMA BANDH | LOOP IN
23 | 13/0 | 4DD+6 | 53° 3' 22"LT | [5 empty] | 439.076 |  | ROW | ROW | [5 empty] | PIROZPUR | LOOP IN
24 | 14/0 | 4DC+6 | 28° 21' 50"LT | [5 empty] | 317.989 |  | ROW | ROW | [5 empty] | PACHRUKHI | LOOP IN
25 | 15/0 | 4DC+0 | 22° 22' 10"LT | [5 empty] | 350 |  | ROW | ROW | [5 empty] | BHIMA BANDH | LOOP IN
26 | 15/1 | 4DA+3 | [6 empty] | 434.141 |  | ROW | ROW | [5 empty] | LANGARPURA | LOOP IN
27 | 16/0 | 4DD+18 | 42° 12' 40"RT | [5 empty] | 271.003 | 220kV D/C OHTL BGCL (HJP- CHP) | Stub NA | [6 empty] | LANGARPURA | LOOP IN
28 | 17/0 | 4DD+25 | 51° 38' 13"RT | [5 empty] | 190.909 |  | Stub NA | [6 empty] | LANGARPURA | LOOP IN
29 | 18/0 | 4DC+6 | 16° 4' 36"RT | [5 empty] | 411 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | LANGARPURA | LOOP IN
30 | 18/1 | 4DA+3 | [6 empty] | 387 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | PACHRUKHI | LOOP IN
31 | 18/2 | 4DA+6 | [6 empty] | 377.351 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | PACHRUKHI | LOOP IN
32 | 19/0 | 4DB+3 | 12° 30' 39"RT | [5 empty] | 392 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | PACHRUKHI | LOOP IN
33 | 19/1 | 4DA+0 | [6 empty] | 313 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | PACHRUKHI | LOOP IN
34 | 19/2 | 4DA+0 | [6 empty] | 318 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Rang |  | BANKERWA BHAW | LOOP IN
35 | 19/3 | 4DA+0 | [6 empty] | 347 |  |  | Completed | Rajeshwar Singh |  | Completed | Rang |  | BANKERWA BHAW | LOOP IN
36 | 19/4 | 4DA+0 | [6 empty] | 387.515 |  |  | Completed | Nav Durga Traders |  | Completed | Rang |  | BANKERWA BHAW | LOOP IN
37 | 20/0 | 4DC+0 | 16° 3' 32"LT | [5 empty] | 345 |  | ROW | ROW | [5 empty] | BAKSANDA | LOOP IN
38 | 20/1 | 4DA+6 | [6 empty] | 410.293 |  |  | Completed | Nav Durga Traders |  |  |  |  | BAKSANDA | LOOP IN
39 | 21/0 | 4DB+6 | 12° 27' 57"RT | [5 empty] | 391.73 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BISHUNPURA | LOOP IN
40 | 22/0 | 4DD+3 | 48° 46' 50"LT | [5 empty] | 300 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BISHUNPURA | LOOP IN
41 | 22/1 | 4DD+18 | [6 empty] | 458.616 | [8 empty] | UTTIMPUR | LOOP IN
42 | 23/0 | 4DD+9 | 57° 37' 41"RT | 3 | 3 | 3 | 3 | 3 | 306.18 |  | fdn Drawing NA | [6 empty] | LALAPUR | LOOP IN
43 | 24/0 | 4DD+3 | 46° 55' 37"RT | [5 empty] | 385.738 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | PARSA BAZAR (NP) | LOOP IN
44 | 25/0 | 4DD+0 | 49° 55' 28"LT | [5 empty] | 340 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | PARSA BAZAR (NP) | LOOP IN
45 | 25/1 | 4DA+3 | [6 empty] | 407.566 |  |  | Completed | Dharmendra Mishra |  |  |  |  | PARSA BAZAR (NP) | LOOP IN
46 | 26/0 | 4DD+0 | 41° 0' 20"LT | [5 empty] | 324 |  | ROW | 02 Leg Com | [5 empty] | PARSA BAZAR (NP) | LOOP IN
47 | 26/1 | 4DA+3 | [6 empty] | 381 |  |  | Completed | Dharmendra Mishra |  |  |  |  | PARSA BAZAR (NP) | LOOP IN
48 | 26/2 | 4DA+6 | [6 empty] | 369.15 |  |  | Completed | Nav Durga Traders | Completed | WIP | Pinki Devi |  | PARSA BAZAR (NP) | LOOP IN
49 | 27/0 | 4DB+3 | 4° 8' 7"LT | [5 empty] | 414 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | FATEHPUR | LOOP IN
50 | 27/1 | 4DA+6 | [6 empty] | 370 |  | ROW | WIP | Nav Durga Traders |  |  |  |  | FATEHPUR | LOOP IN
51 | 27/2 | 4DA+0 | [6 empty] | 307 |  | ROW | WIP | Nav Durga Traders |  |  |  |  | BANAUTA MAKUND | LOOP IN
52 | 27/3 | 4DA+0 | [6 empty] | 291 |  |  | Completed | Dharmendra Mishra |  |  |  |  | BANAUTA MAKUND | LOOP IN
53 | 27/4 | 4DA+0 | [6 empty] | 334.029 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | BANAUTA MAKUND | LOOP IN
54 | 28/0 | 4DD+3 | 36° 17' 57"RT | [5 empty] | 266 |  |  | Completed | Nav Durga Traders | Completed | Completed | Rang |  | BANAUTA MAKUND | LOOP IN
55 | 28/1 | 4DA+0 | [6 empty] | 255.445 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BANAUTA MAKUND | LOOP IN
56 | 29/0 | 4DD+0 | 37° 36' 50"RT | [5 empty] | 351 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | BANAUTA MAKUND | LOOP IN
57 | 29/1 | 4DA+6 | [6 empty] | 422.029 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | MUJAUNA | LOOP IN
58 | 30/0 | 4DC+3 | 15° 4' 15"LT | [5 empty] | 384.086 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | PATTI MUJAUNA | LOOP IN
59 | 31/0 | 4DD+0 | 53° 31' 11"LT | [5 empty] | 366.151 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | MUJAUNA | LOOP IN
60 | 32/0 | 4DB+6 | 10° 20' 48"LT | [5 empty] | 358 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | PATTI MUJAUNA | LOOP IN
61 | 32/1 | 4DA+6 | [6 empty] | 404.497 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | PATTI MUJAUNA | LOOP IN
62 | 33/0 | 4DD+3 | 39° 19' 42"RT | [5 empty] | 339.162 | [8 empty] | SULTANPUR | LOOP IN
63 | 34/0 | 4DD+0 | 57° 41' 28"RT | [5 empty] | - |  |  | HOLD | [5 empty] | ARIAEN | LOOP IN
64 | 1/0 | 4DD+0 | 33° 21' 33"RT | [5 empty] | 106.18 |  |  | HOLD
65 | 2/0 | 4DD+0 | 43° 35' 18"RT | [5 empty] | 224.288 |  |  | HOLD
66 | 3/0 | 4DB+3 | 12° 23' 41"RT | [5 empty] | 422 |  |  | HOLD
67 | 3/1 | 4DA+9 | [6 empty] | 364.195 |  |  | HOLD
68 | 4/0 | 4DB+3 | 1° 46' 30"LT | [5 empty] | 397.753 |  |  | Completed | Dharmendra Mishra | Completed
69 | 5/0 | 4DD+0 | 52° 53' 51"LT | [5 empty] | 253 |  |  | HOLD
70 | 5/1 | 4DD+0 | [6 empty] | 97.983 |  |  | HOLD
71 | 6/0 | 4DD+0(Aux) | 65° 12' 29"RT | [5 empty] | 184.709 |  |  | HOLD
72 | 7/0 | 4DB+0 | 4° 47' 11"LT | [5 empty] | 165.679 |  |  | HOLD
73 | 8/0 | 4DD+0 | 48° 49' 53"LT | [5 empty] | 181.223 |  |  | HOLD
74 | 9/0 | 4DB+0 | 7° 53' 54"LT | [5 empty] | 205.952 | [8 empty] | BASAUTA
75 | 10/0 | 4DD+0 | 53° 51' 6"RT | [5 empty] | 311.523 | [8 empty] | UMARPUR
76 | 11/0 | 4DD+0 | 44° 45' 6"RT | [5 empty] | 241.033 |  |  | HOLD | [5 empty] | UMARPUR
77 | 12/0 | 4DB+0 | 6° 16' 34"LT | [5 empty] | 130.699 |  |  | HOLD | [5 empty] | HELA
78 | 13/0 | 4DD+0 | 43° 40' 22"LT | [5 empty] | 318.825 |  |  | HOLD | [5 empty] | HELA
79 | 14/0 | 4DC+0 | 24° 18' 58"RT | [5 empty] | 205.018 |  |  | HOLD | [5 empty] | ARNA
80 | 15/0 | 4DD+0 | 46° 36' 23"LT | [5 empty] | 136.578 |  |  | HOLD | [5 empty] | ARNA
81 | 16/0 | 4DC+6 | 27° 22' 26"RT | [5 empty] | 134.69 |  |  | HOLD | [5 empty] | BARIARPUR
82 | 17/0 | 4DD+18 | 43° 34' 28"LT | [5 empty] | 254 |  |  | HOLD
83 | 18A/0 | 4DD+3 | 52° 35' 58"RT | [5 empty] | 209.69 |  |  | WIP | Rajeshwar Singh
84 | 19/0 | 4DC+0 | 27° 52' 30"RT | [5 empty] | 268.08 |  |  | Completed | Rajeshwar Singh
85 | 20/0 | 4DD+0 | 61° 28' 55"LT | [5 empty] | 323.24 |  |  | Completed | Dharmendra Mishra |  | WIP | RANG
86 | 21/0 | 4DC+9 | 25° 14' 32"RT | [5 empty] | 360.98 |  |  | Completed | Rajeshwar Singh
87 | 22/0 | 4DB+6 | 4° 22' 25"RT | [5 empty] | 253.41 |  |  | Completed | Rajeshwar Singh
88 | 23/0 | 4DB+0 | 10° 6' 21"RT | [5 empty] | 315 |  |  | Completed | Rajeshwar Singh |  |  |  |  | BHELDI G.P.
89 | 23/1 | 4DA+0 | [6 empty] | 297.881 |  |  | Completed | Rajeshwar Singh |  |  |  |  | LANGARPURA
90 | 24/0 | 4DD+0 | 32° 37' 58"LT | [5 empty] | 420 |  |  | Completed | Rajeshwar Singh | Completed |  |  |  | LANGARPURA
91 | 24/1 | 4DA+6 | [6 empty] | 356 |  |  | Completed | Rajeshwar Singh | Completed | Completed | rang |  | LANGARPURA
92 | 24/2 | 4DA+0 | [6 empty] | 358 |  |  | Completed | Rajeshwar Singh | Completed | Completed | rang |  | PACHRUKHI
93 | 24/3 | 4DA+0 | [6 empty] | 317.518 |  |  | Completed | Rajeshwar Singh | Completed | Completed | rang |  | PACHRUKHI
94 | 25/0 | 4DD+0 | 38° 17' 16"RT | [5 empty] | 269 |  |  | Completed | Rajeshwar Singh | Completed | Completed | Pinki Devi |  | PACHRUKHI
95 | 25/1 | 4DA+0 | [6 empty] | 240.129 |  |  | Completed | Rajeshwar Singh | Completed |  |  |  | PACHRUKHI
96 | 26/0 | 4DC+0 | 25° 56' 57"LT | [5 empty] | 351 |  |  | Completed | Rajeshwar Singh | Completed | Completed | rang |  | BANKERWA BHAW
97 | 26/1 | 4DA+0 | [6 empty] | 357.009 |  |  | Completed | Rajeshwar Singh | Completed | Completed | rang |  | BANKERWA BHAW
98 | 27/0 | 4DB+3 | 14° 17' 42"RT | [5 empty] | 397.805 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BANKERWA BHAW
99 | 28/0 | 4DD+0 | 57° 18' 15"LT | [5 empty] | 299 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | BAKSANDA
100 | 28/1 | 4DA+6 | [6 empty] | 382 |  |  | Completed | Nav Durga Traders |  | Completed | Pinki Devi |  | BAKSANDA
101 | 29/0 | 4DD+3 | 32° 6' 47"RT | [5 empty] | 348.042 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | BAKSANDA
102 | 30/0 | 4DD+0 | 41° 49' 34"LT | [5 empty] | 278.545 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | UTTIMPUR
103 | 31/0 | 4DD+0 | 56° 43' 6"RT | [5 empty] | 213.957 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | LALAPUR
104 | 32/0 | 4DD+0 | 42° 22' 50"LT | 1 | 0 | 0 | 0 | 0 | 243.723 | [8 empty] | LALAPUR
105 | 33/0 | 4DD+0 | 45° 21' 58"RT | [5 empty] | 330.001 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi |  | SAGUNI
106 | 33/1 | 4DA+0 | [6 empty] | 283.112 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi
107 | 34/0 | 4DD+3 | 58° 46' 47"LT | [5 empty] | 375 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi
108 | 34/1 | 4DA+9 | [6 empty] | 406.013 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi
109 | 35/0 | 4DD+3 | 58° 34' 27"RT | [5 empty] | 398.938 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi
110 | 36/0 | 4DD+0 | 46° 15' 39"RT | [5 empty] | 335 |  |  | Completed | Nav Durga Traders | Completed | Completed | Pinki Devi
111 | 36/1 | 4DA+3 | [6 empty] | 402.897
112 | 37/0 | 4DD+9 | 56° 10' 21"LT | [5 empty] | 385.199 |  |  | Completed | Nav Durga Traders
113 | 38/0 | 4DD+6 | 33° 13' 52"LT | [5 empty] | 378.47 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | FATEHPUR
114 | 39/0 | 4DB+0 | 11° 2' 36"LT | [5 empty] | 413 | [8 empty] | FATEHPUR
115 | 39/1 | 4DA+6 | [6 empty] | 386 |  |  | Completed | Nav Durga Traders |  |  |  |  | FATEHPUR
116 | 39/2 | 4DA+3 | [6 empty] | 398 |  |  | Completed | Nav Durga Traders |  |  |  |  | BANAUTA MAKUND
117 | 39/3 | 4DA+0 | [6 empty] | 401 |  |  | Completed | Nav Durga Traders |  |  |  |  | BANAUTA MAKUND
118 | 39/4 | 4DA+3 | [6 empty] | 367 |  |  | Completed | Nav Durga Traders |  |  |  |  | ANJNI
119 | 39/5 | 4DA+3 | [6 empty] | 432.743 |  |  | Completed | Nav Durga Traders |  |  |  |  | BANAUTA
120 | 40/0 | 4DB+6 | 8° 19' 26"LT | [5 empty] | 337.077 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BANAUTA
121 | 41/0 | 4DC+0 | 21° 51' 59"RT | [5 empty] | 315 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BANAUTA
122 | 41/1 | 4DA+0 | [6 empty] | 316.645 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | BANAUTA
123 | 42/0 | 4DD+0 | 53° 20' 50"RT | [5 empty] | 377.05 |  |  | Completed | Dharmendra Mishra | Completed |  |  |  | BANAUTA
124 | 43/0 | 4DD+3 | 55° 59' 58"RT | [5 empty] | 346.103 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | EKDERWA MASURIYA
125 | 44/0 | 4DD+0 | 35° 35' 57"LT | [5 empty] | 340.88 |  |  | Completed | Nav Durga Traders | Completed |  |  |  | KOHRA
126 | 45/0 | 4DD+3 | 56° 35' 11"LT | [5 empty] | 338.926 |  |  | Completed | Nav Durga Traders |  |  |  |  | KOHRA
127 | 46/0 | 4DD+3 | 50° 14' 1"LT | [5 empty] | 299.953 |  |  | HOLD
128 | 47/0 | 4DD+0 | 46° 58' 38"LT | [5 empty] | - |  |  | HOLD
40.3377
[11 empty] | FOUNDATION SUMMARY |  | ERECTION SUMMARY
[11 empty] | Scope | 128 | Scope | 128
[11 empty] | Completed | 76 | Completed | 30
[11 empty] | WIP | 5 | WIP | 2
[11 empty] | Frount Available | 10 | Frount Available | 96
[11 empty] | Hold | 30 | Hold | 0
[11 empty] | ROW | 9 | ROW | 0
[11 empty] | Earthing Completed | 52 | Tack Welding Completed | 0

## VC 400 KV QM
2026-06-24
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN & LOOP OUT
M/S KEC INTERNATIONAL LIMITED
Progress Visual Chart
HOLD
| Foundation Cumulative |  |  |  |  | Nos. |  | 86/129 | [7 empty] | MC,Design and Special Tower & DS
| Earthing Cumulative |  |  |  |  | Nos. |  | 61/129 | [7 empty] | ROW
| Erection Cumulative |  |  |  |  | Nos. |  | 43/129 | [6 empty] | Statutary | RLY XING
| Stringing Payingout (RS) |  |  |  |  | Km. |  | 0.00/41.381 |  |  |  |  | 40.456 |  |  | NH
| Stringing Final sag Cumulative |  |  |  |  | Km. |  | 0.00/41.381 | [7 empty] | PL
IOCL
2026-06-24
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN
M/S KEC INTERNATIONAL LIMITED
Progress Visual Chart
LEGENDS
[14 empty] | TE Dt | STG |  |  |  | Major Power Line Crossing |  |  | Railway Crossing |  | River Crossing |  | Highway Crossing (EH & NH)
|  | Foundation Cumulative |  |  |  |  | Nos. |  | 40/63 | [5 empty] | Dt |  |  | STG UP
|  | Earthing Cumulative |  |  |  |  | Nos. |  | 31/63 |  |  | ERECTION
|  | Erection Cumulative |  |  |  |  | Nos. |  | 21/63 |  |  |  |  | Date | SPAN
|  | Stringing Payingout (RS) |  |  |  |  | Km. |  | 0.00/21.279 |  |  | FOUNDATION |  | Type
|  | Stringing Final sag Cumulative |  |  |  |  | Km. |  | 0.00/21.279
[8 empty] | ` |  |  |  | Tower+Extn |  | X+Y |  | Earthing |  | U/P
[15 empty] | Suspn Tower | Angle Tower
[12 empty] | TOWER NO |  | YY
[22 empty] | Cum Length | Fdn Comp | Ear Comp | TE Comp | STG Comp
| 146.26 |  | 112.78 |  | 158.66 |  | 296 |  | 332 |  | 277 |  | 340.68 |  | 229.84 |  | 276.93 |  | 357 |  | New Proposed Railway | 2527.15 | 0 | 0 | 0 | 0
Ext.TWR |  | 1/0 |  | 2/0 |  | 3/0 |  | 3/1 |  | 3/2 |  | 3/3 |  | 4/0 |  | 5/0 |  | 6/0 |  | 6/1
|  | 4DD+0 |  | 4DD+0 |  | 4DD+0 |  | 4DA+0 |  | 4DA+0 |  | 4DA+0 |  | 4DD+6 | NH - 722 | 4DD+6 |  | 4DD+0 |  | 4DD+9
|  | HOLD MC |  | HOLD MC |  | HOLD MC |  | HOLD MC |  | HOLD MC |  | HOLD NH |  | HOLD NH |  | HOLD NH |  | HOLD NH |  | HOLD RLW
`
| 243.77 |  | 338 |  | 309 |  | 381.53 |  | 331.87 |  | 341.21 |  | 243.5 |  | 316 |  | 325 | PS 15.01.26 | 269 |  |  | 3098.88 | 9 | 8 | 3 | 0
|  | 7/0 |  | 7/1 |  | 7/2 |  | 8/0 |  | 9/0 |  | 10/0 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3
|  | 4DD+9 |  | 4DA+0 |  | 4DA+0 |  | 4DB+0 |  | 4DC+0 |  | 4DB+0 |  | 4DD+0 |  | 4DA+0 |  | 4DA+0 |  | 4DA+0
HOLD RLW
`
| 281.83 |  | 423 |  | 376.1 |  | 439.08 |  | 317.99 |  | 350 |  | 434.14 |  | 271 |  | 190.91 |  | 411 | PS 09.01.26 |  | 3495.05 | 3 | 2 | 2 | 0
220kV D/C OHTL BGCL (HJP- CHP)
|  | 12/0 |  | 12/1 |  | 13/0 |  | 14/0 |  | 15/0 |  | 15/1 |  | 16/0 |  | 17/0 |  | 18/0 |  | 18/1
|  | 4DB+3 |  | 4DA+9 |  | 4DD+6 |  | 4DC+6 |  | 4DC+0 |  | 4DA+3 |  | 4DD+18 |  | 4DD+25 |  | 4DC+6 |  | 4DA+3
|  | 02 Leg ROW |  |  |  | ROW |  | ROW |  | ROW |  | ROW |  | HOLD Design |  | HOLD Design
`
| 387 | PS | 377.35 | PS 05.01.26 | 392 | PS 28.12.25 | 313 | PS 17.12.25 | 318 |  | 347 | PS 23.12.25 | 387.52 |  | 345 |  | 410.29 |  | 391.73 |  |  | 3668.89 | 10 | 6 | 7 | 0
11.12.25
|  | 18/2 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4 |  | 20/0 |  | 20/1 |  | 21/0 |  | 22/0
|  | 4DA+6 |  | 4DB+3 |  | 4DA+0 |  | 4DA+0 |  | 4DA+0 |  | 4DA+0 |  | 4DC+0 |  | 4DA+6 |  | 4DB+6 |  | 4DD+3
`
| 300 |  | 458.62 |  | 306.18 | PS 31.01.26 | 385.74 | PS 25.01.26 | 340 |  | 407.57 |  | 324 |  | 381 |  | 369.15 | PS 15.01.26 | 414 |  |  | 3686.26 | 7 | 5 | 4 | 0
|  | 22/1 |  | 23/0 |  | 24/0 |  | 25/0 |  | 25/1 |  | 26/0 |  | 26/1 |  | 26/2 |  | 27/0 |  | 27/1
|  | 4DD+`8 |  | 4DD+9 |  | 4DD+3 |  | 4DD+0 |  | 4DA+3 |  | 4DD+0 |  | 4DA+3 |  | 4DA+6 |  | 4DB+3 |  | 4DA+6
|  | HOLD Design |  | 3 MRC | [7 empty] | ROW 02 Pit RCC Done
HOLD Design
| 370 |  | 307 |  | 291 | PS 15.12.25 | 334.03 | PS 24.12.25 | 266 | PS 05.01.26 | 255.45 | PS 06.01.26 | 351 | PS 19.12.25 | 422.03 | PS 30.11.25 | 384.09 | PS 11.12.25 | 366.15 | FS 30.12.25 |  | 3346.75 | 10 | 9 | 4 | 0
|  | 27/2 |  | 27/3 |  | 27/4 |  | 28/0 |  | 28/1 |  | 29/0 |  | 29/1 |  | 30/0 |  | 31/0 |  | 32/0
|  | 4DA+0 |  | 4DA+0 |  | 4DA+0 |  | 4DD+3 |  | 4DA+0 |  | 4DD+0 |  | 4DA+6 |  | 4DC+3 |  | 4DD+0 |  | 4DB+6
| 358 | FS 12.01.26 | 404.5 |  | 339.16 |  | 354 | [14 empty] | 1455.66 | 1 | 1 | 1 | 0
|  | 32/1 |  | 33/0 |  | 34/0 |  | Ext TWR
|  | 4DA+6 |  | 4DD+3 |  | 4DD+0
|  |  |  | HOLD Spl Tower |  | HOLD Spl Tower | [8 empty] | TOTAL | [6 empty] | 21.2786 | 40 | 31 | 21 | 0
2026-06-24
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP OUT
M/S KEC INTERNATIONAL LIMITED
Progress Visual Chart
LEGENDS
[14 empty] | TE Dt | STG |  |  |  | Major Power Line Crossing |  |  | Railway Crossing |  | River Crossing |  | Highway Crossing (EH & NH)
|  | Foundation Cumulative |  |  |  |  | Nos. |  | 46/66 | [5 empty] | Dt |  |  | STG UP
|  | Earthing Cumulative |  |  |  |  | Nos. |  | 30/66 |  |  | ERECTION
|  | Erection Cumulative |  |  |  |  | Nos. |  | 22/66 |  |  |  |  | Date | SPAN
|  | Stringing Payingout (RS) |  |  |  |  | Km. |  | 0.00/20.102 |  |  | FOUNDATION |  | Type
|  | Stringing Final sag Cumulative |  |  |  |  | Km. |  | 0.00/20.102
[8 empty] | ` |  |  |  | Tower+Extn |  | X+Y |  | Earthing |  | U/P
[15 empty] | Suspn Tower | Angle Tower
[12 empty] | TOWER NO |  | YY
[22 empty] | Cum Length | Fdn Comp | Ear Comp | TE Comp | STG Comp
`
| 105.77 |  | 106.18 |  | 224.288 |  | 422 |  | 364.195 |  | 397.75 |  | 253 |  | 97.98 |  | 184.71 |  | 165.68 |  |  | 2321.553 | 3 | 1 | 0 | 0
Ext.TWR |  | 1/0 |  | 2/0 |  | 3/0 |  | 3/1 |  | 4/0 |  | 5/0 |  | 5/1 |  | 6/0 |  | 7/0 |  | 8/0
|  | DD+0 |  | DD+0 |  | DB+3 |  | DA+9 |  | DB+3 |  | DD+0 |  | DD+0 |  | 4DD+0(Aux) |  | 4DB+0 |  | 4DD+0
|  | HOLD MC |  | HOLD MC |  | HOLD MC |  | HOLD MC | [7 empty] | HOLD DRW
`
| 181.22 |  | 205.95 |  | 311.52 |  | 218.54 |  | 153.03 |  | 364.73 |  | 224.22 |  | 210.619 |  | 176.79 |  | 190.21 |  | 146.15 | 2382.979 | 2 | 1 | 0 | 0
220kV D/C OHTL BGCL (HJP- CHP)
|  | 9/0 |  | 10/0 |  | 11/0 |  | 12/0 |  | 13/0 |  | 14/0 | New Proposed Railway | 15/0 |  | 16/0 |  | 17/0 |  | 18/0
|  | 4DB+0 |  | 4DD+0 |  | 4DD+0 |  | 4DD+3 | NH-722 | 4DD+3 |  | 4DD+9 |  | 4DD+9 |  | 4DD+9 |  | DD+18 |  | DD+18
[6 empty] | HOLD NH |  | HOLD NH |  | HOLD NH |  | HOLD NH/RLY |  | HOLD RLY |  |  |  | HOLD Design |  | HOLD Design
`
| 79.03 |  | 255.14 |  | 322.94 |  | 360.98 |  | 253.41 |  | 315 |  | 297.88 |  | 420 |  | 356 | PS 03.02.26 | 358 |  |  | 3018.38 | 11 | 6 | 5 | 0
18A/0 |  | 19/0 |  | 20/0 |  | 21/0 |  | 22/0 |  | 23/0 |  | 23/1 |  | 24/0 |  | 24/1 |  | 24/2 |  | 24/3
4DD+9 |  | DC+0 |  | 4DD+0 |  | DC+9 |  | 4DB+6 |  | 4DB+0 |  | 4DA+0 |  | 4DD+0 |  | 4DA+6 |  | 4DA+0 |  | 4DA+0
`
| 317.52 |  | 269 |  | 240.13 |  | 351 |  | 357.01 |  | 397.81 |  | 299 | PS 22.01.26 | 382.3 | PS 31.01.26 | 348.04 |  | 278.55 |  |  | 3240.36 | 10 | 9 | 7 | 0
|  | 25/0 |  | 25/1 |  | 26/0 |  | 26/1 |  | 27/0 |  | 28/0 |  | 28/1 |  | 29/0 |  | 30/0 |  | 31/0
|  | 4DD+0 |  | 4DA+0 |  | 4DC+0 |  | 4DA+0 |  | 4DB+3 |  | 4DD+0 |  | 4DA+6 |  | 4DD+3 |  | 4DD+0 |  | 4DD+0
`
| 213.96 |  | 243.72 |  | 330 |  | 283.11 |  | 375 |  | 406.01 |  | 398 |  | 335 |  | 402.9 |  | 385.2 |  |  | 3372.9 | 8 | 7 | 7 | 0
|  | 32/0 |  | 33/0 |  | 33/1 |  | 34/0 |  | 34/1 |  | 35/0 |  | 36/0 |  | 36/1 |  | 37/0 |  | 38/0
|  | 4DD+0 |  | 4DD+0 |  | DA+0 |  | DD+3 |  | 4DA+9 |  | 4DD+3 |  | DD+0 |  | 4DA+3 |  | 4DD+9 |  | 4DD+6
1 MRC HOLD
HOLD Design
`
| 378.47 |  | 413 |  | 386 |  | 398 |  | 401 |  | 367 |  | 432.74 | PS 22.01.26 | 337.08 |  | 315 |  | 316.65 |  |  | 3744.94 | 9 | 4 | 2 | 0
|  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4 |  | 39/5 |  | 40/0 |  | 41/0 |  | 41/1 |  | 42/0
|  | 4DB+0 |  | 4DA+6 |  | 4DA+3 |  | 4DA+0 |  | 4DA+3 |  | 4DA+3 |  | 4DB+6 |  | 4DC+0 |  | 4DA+0 |  | 4DD+0
| 377.05 |  | 346.1 |  | 340.88 |  | 338.93 |  | 299.95 |  | 318 | [10 empty] | 2020.91 | 3 | 2 | 1 | 0
|  | 43/0 |  | 44/0 |  | 45/0 |  | 46/0 |  | 47/0 |  | Ext TWR
|  | 4DD+3 |  | 4DD+0 |  | 4DD+3 |  | 4DD+3 |  | 4DD+3
[8 empty] | HOLD Spl Tower |  | HOLD Spl Tower
[15 empty] | TOTAL | [6 empty] | 20.102 | 46 | 30 | 22 | 0

## Progress 220KV TM
Client:- |  | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL)
Line Name:- |  | 220kV Chhapra(New) Amnour DCDS with Twin Moose Conductor
EPC:- |  | KEC International Limited
S.NO. | LOC. NO. | TYPE OF TOWER | ANGLE OF DEVATION | RAISED CHIMNEY | RAISED CHIMNEY |  |  |  | SPAN | Crossing Detail/Statutary | ROW Status | Foundation Status | Contractor Name | Earthing Status | Erection Status | Contractor Name | Tack Welding Status | VILLAGES
[5 empty] | A | B | C | D
1 | 1/0 | 2TNMD+0 | 4° 59' 40"RT |  | 0 | 0 | 0 | 0 | 102.49 |  |  | HOLD | [5 empty] | KASTA
2 | 2/0 | 2TNMD+0 | 29° 43' 51"RT |  | 0 | 0 | 0 | 0 | 217.2 |  |  | COMPLETED | Nav Durga Traders | COMPLETED |  |  |  | KASTA
3 | 3/0 | 2TNMD+0 | 29° 2' 31"RT |  | 0 | 0 | 0 | 0 | 331.422 |  |  | COMPLETED | Nav Durga Traders |  |  |  |  | KASTA
4 | 3/1 | 2TDD+9 | 15° 32' 23"RT |  | 0 | 0 | 0 | 0 | 186 | Dabra River |  | COMPLETED | Nav Durga Traders |  |  |  |  | KASTA
5 | 6/0 | 2TDC+0 | 24° 37' 47"RT |  | 0 | 0 | 0 | 0 | 217.97 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | YASHODA DEVI |  | KASTA
6 | 6/1 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 330.8 | Dabra River |  | COMPLETED | Nav Durga Traders | COMPLETED | WIP | YASHODA DEVI |  | KASTA
7 | 7/0 | 2TDD+0 | 32° 58' 11"RT |  | 0 | 0 | 0 | 0 | 218 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SGSE |  | MADARPUR
8 | 7/1 | 2TDA+0 |  |  | 0 | 0 | 0 | 0 | 220.351 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | kumar k2 |  | GOSI CHHAPRA
9 | 8/0 | 2TDC+0 | 23° 15' 49"LT |  | 0 | 0 | 0 | 0 | 190 |  |  | COMPLETED | Nav Durga Traders |  | completed | RABISH |  | GOSI CHHAPRA
10 | 8/1 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 260 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | kumar k2 |  | GOSI CHHAPRA
11 | 8/2 | 2TDA+6 |  |  | 0 | 0 | 0 | 0 | 323.052 | Dabra River |  | COMPLETED | Nav Durga Traders | COMPLETED |  |  |  | MADARPUR
12 | 9/0 | 2TDC+6 | 28° 36' 34"RT |  | 0 | 0 | 0 | 0 | 246.023 |  |  | COMPLETED | Nav Durga Traders | COMPLETED |  |  |  | MADARPUR
13 | 10/0 | 2TDD+0 | 32° 7' 44"RT |  | 0 | 0 | 0 | 0 | 255 | Dabra River |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | GAWANDRI
14 | 10/1 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 152 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | MALAHI
15 | 10/2 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 294.498 | Dabra River |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | MALAHI
16 | 11/0 | 2TDC+0 | 22° 19' 24"RT |  | 0 | 0 | 0 | 0 | 269 |  |  | COMPLETED | AR |  |  |  |  | HAKMA
17 | 11/1 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 333 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | HAKMA
18 | 11/2 | 2TDA+3 |  |  | 0 | 0 | 0 | 0 | 257 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | HAKMA
19 | 11/3 | 2TDA+0 |  |  | 0 | 0 | 0 | 0 | 297 |  |  | COMPLETED | Nav Durga Traders | COMPLETED | completed | SR Enterprises |  | SHIKARPUR
20 | 11/4 | 2TDA+0 |  |  | 0 | 0 | 0 | 0 | 291.09 |  |  | COMPLETED | Nav Durga Traders | COMPLETED |  |  |  | SHIKARPUR
21 | 12/0 | 2TDD+0 | 31° 35' 34"LT |  | 0 | 0 | 0 | 0 | 235 |  | ROW | [6 empty] | TARWAR
22 | 12/1 | 2TDA+6 |  |  | 0 | 0 | 0 | 0 | 358.489 | [8 empty] | TARWAR
23 | 13/0 | 2TDD+18 | 1° 10' 58"RT |  | 0 | 0 | 0 | 0 | 231.686 | 220kV D/C OHTL BGCL HJP-CHP |  | COMPLETED | Nav Durga Traders |  |  |  |  | TARWAR
24 | 14/0 | 2TDD+25 | 31° 48' 49"LT |  | 0 | 0 | 0 | 0 | 209.429 |  |  | COMPLETED | Nav Durga Traders |  |  |  |  | TARWAR
25 | 15/0 | 2TDD+9 | 59° 5' 38"LT | 2 | 2 | 2 | 2 | 2 | 104.552 | 220kV D/C OHTL BSPTCL ANR-MZP | [7 empty] | TARWAR
26 | 16/0 | 2TDD+3 | 59° 0' 51"LT |  | 0 | 0 | 0 | 0 | 88.059 |  |  | WIP | Nav Durga Traders
27 | 17/0 | 2TDD+0 | 39° 49' 50"RT |  | 0 | 0 | 0 | 0 | 72.888 |  |  | COMPLETED | Nav Durga Traders
28 | 18/0 | 2TDD+3 | 54° 21' 38"RT |  | 0 | 0 | 0 | 0 |  |  |  | COMPLETED | Nav Durga Traders
[9 empty] | 6.292 |  | FOUNDATION SUMMARY |  | ERECTION SUMMARY
[11 empty] | Scope | 28 | Scope | 28
[11 empty] | Completed | 23 | Completed | 11
[11 empty] | WIP | 1 | WIP | 1
[11 empty] | Frount Available | 3 | Frount Available | 16
[11 empty] | Hold | 1 | Hold | 0
[11 empty] | ROW | 1 | ROW | 0
[11 empty] | Earthing Completed | 15 | Tack Welding Completed | 0

## VC 220 TM
2026-06-24
220kV Chhapra(New) Amnour DCDS with Twin Moose Conductor
M/S KEC INTERNATIONAL LIMITED
Progress Visual Chart
LEGENDS
[14 empty] | TE Dt | STG |  |  |  | Major Power Line Crossing |  | Railway Crossing | River Crossing | Highway Crossing (SH & NH)
|  | Foundation Cumulative |  |  |  |  | Nos. |  | 23/28 | [5 empty] | Dt |  |  | STG UP
|  | Earthing Cumulative |  |  |  |  | Nos. |  | 15/28 |  |  | ERECTION
|  | Erection Cumulative |  |  |  |  | Nos. |  | 11/28 |  |  |  |  | Date | SPAN
|  | Stringing Payingout (RS) |  |  |  |  | Km. |  | 0.00/6.61 |  |  | FOUNDATION |  | Type
|  | Stringing Final sag Cumulative |  |  |  |  | Km. |  | 0.00/6.61
[8 empty] | ` |  |  |  | Tower+Extn |  | X+Y | Suspn Tower | Earthing |  | U/P
Angle Tower
[12 empty] | TOWER NO |  | X/Y
[21 empty] | Cum Length | Fdn Comp | Ear Comp | TE Comp | STG Comp
|  |  | 102.49 |  | 217.2 |  | 331.422 |  | 186 |  | 217.97 |  | 253 | WET | 330.8 | WET 16.11.25 | 218 | WET | 220.351 |  | 2077.233 | 8 | 4 | 4 | 0 | 1022
[14 empty] | 23.09.25 |  |  |  | 18.09.25
|  | GANTRY |  | 1/0 |  | 2/0 |  | 3/0 |  | 3/1 |  | 6/0 |  | 6/1 | Dabra | 7/0 |  | 7/1 |  | 8/0
|  |  |  | 2TNMD+0 |  | 2TNMD+0 |  | 2TNMD+0 |  | 2TDD+9 |  | 2TDC+0 |  | 2TDA+3 | River | 2TDD+0 |  | 2TDA+0 |  | 2TDC+0
HOLD
`
| 190 | WET | 260 | WET | 323 |  | 246 | PS 30.11.25 | 255 | PS 03.12.25 | 152 | PS | 294.5 |  | 269 | PS | 333 | PS | 257 | PS | 2579.5 | 10 | 10 | 7 | 0 | 1720.5
|  | 20.11.25 |  | 11.11.25 | [7 empty] | 24.11.25 |  |  |  | 07.12.25 |  | 11.12.25 |  | 24.12.25
|  | 8/1 |  | 8/2 | Dabra | 9/0 |  | 10/0 | Dabra | 10/1 |  | 10/2 | Dabra | 11/0 |  | 11/1 |  | 11/2 |  | 11/3
|  | 2TDA+3 |  | 2TDA+6 | River | 2TDC+6 |  | 2TDD+0 | River | 2TDA+3 |  | 2TDA+3 | River | 2TDC+0 |  | 2TDA+3 |  | 2TDA+3 |  | 2TDA+0
| 297 | PS 15.12.25 | 291.09 |  | 235 |  | 359 |  | 232 |  | 209 |  | 104.55 |  | 88.06 |  | 72.89 |  | 64.5 |  | 1953.09 | 5 | 1 | 0 | 0 | 232
[7 empty] | 33kV line |  | 220kV D/C OHTL BGCL HJP-CHP |  | 220kV D/C OHTL BSPTCL ANR-MZP
|  | 11/4 |  | 12/0 |  | 12/1 |  | 13/0 |  | 14/0 |  | 15/0 |  | 16/0 |  | 17/0 |  | 18/0 |  | Gantry
|  | 2TDA+0 |  | 2TDD+0 |  | 2TDA+6 |  | 2TDD+18 |  | 2TDD+25 |  | 2TDD+9 |  | 2TDD+3 |  | 2TDD+0 |  | 2TDD+3
|  |  |  | ROW | [7 empty] | 2 MRC
BREDA HOLD
[5 empty] | ROW | [9 empty] | TOTAL | [5 empty] | 6.6098 | 23 | 15 | 11 | 0
TOWER ABSTRACT 220kV D/C TM CHAP-AMNR
[7 empty] | SL NO | TOT | NORMAL TOWER WITH EXTENSION | [5 empty] | TOTAL TOWER
[9 empty] | 0M | +3M | +6M | +9M | +18M | +25M
[7 empty] | 1 | 2TDA | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 3 | 2TDB | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 4 | 2TDC | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | 5 | 2TDD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | Total Tower |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## VC 220 SZ
[29 empty] | Date- | 2026-06-24
PJOJECT SUMMARY | [15 empty] | LEGENDS
[18 empty] | TE Dt | STG |  |  |  | Major Power Line Crossing | Railway Crossing | River Crossing | Highway Crossing (SH & NH)
Foundation Cumulative |  |  |  |  | Nos. |  | 184/336 | [11 empty] | Dt |  |  | STG UP
Earthing Cumulative |  |  |  |  | Nos. |  | 138/336 | [8 empty] | ERECTION
Erection Cumulative |  |  |  |  | Nos. |  | 71/336 | [10 empty] | Date | SPAN
Stringing Payingout (RS) |  |  |  |  | Km. |  | 0.00/101.101 | [8 empty] | FOUNDATION |  | Type
Stringing Final sag Cumulative |  |  |  |  | Km. |  | 0.00/101.101
[6 empty] | ` | [9 empty] | Tower+Extn |  | X+Y | Suspn Tower | Earthing |  | U/P
Angle Tower
[16 empty] | TOWER NO |  | X/Y
[26 empty] | Cum Length | Fdn Comp | Ear Comp | TE Comp | STG Comp
9/0 |  | 9/1 |  | 9A/0 |  | 10/0 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 12/0 |  | 13/0 |  | 13/1 |  | 13/2 |  | 14/0
| 360 |  | 328 |  | 360 |  | 409 |  | 360 |  | 340 |  | 360 |  | 314 |  | 341 |  | 307 | 26-9-24 | 287 | 11-10-24 | 319 | 22-9-24 | 320 | 4405 | 3 | 3 | 0 | 0 | 12 | 12
NMB+0 |  | DA+9 |  | DB+6 |  | DB+6 |  | DB+6 |  | DA+0 |  | DA+6 |  | DA+9 |  | DC+3 |  | DD+6 |  | DA+6 |  | DA+9 |  | DC+3
HOLD |  | HOLD |  | 1.5 MRC |  | ROW |  | HOLD |  | HOLD |  | HOLD |  | HOLD |  | HOLD |  | ROW
14/1 |  | 15/0 |  | 16/0 |  | 17/0 |  | 17/1 |  | 18/0 |  | 18/1 |  | 19/0 |  | 19/1 |  | 21/0 |  | 22/0 |  | 23/0 |  | Gan-1
23-6-24 | 320 | 5-7-24 | 341 | 24-08-24 | 309 | 03-8-24 | 326 | 08-08-2024 | 325 |  | 340 | 23-1024 | 350 | 18-10-24 | 330 |  | 330 | 26-1024 | 369 |  | 375 |  | 72 |  | 50 | 3837 | 9 | 9 | 0 | 0 | 13 | 25
400 kV TL
DA+0 |  | DD+6 |  | DD+6 |  | DD+3 |  | DA+6 |  | DC+6 |  | DA+6 |  | DD+6 |  | DA+6 |  | DC+3 |  | DD+6 |  | DD+0 |  | GANTRY
[16 empty] | ROW |  |  |  | HOLD |  | HOLD |  | HOLD
Gan-2 |  | 24/0 |  | 25/0 |  | 26/0 |  | Gan-3 |  | Gan-4 |  | 27/0 |  | 28/0 |  | 29/0 |  | 30/0 |  | 31/0 |  | 31/1 |  | 31/2
| 48 |  | 263 |  | 231 |  | 84 |  | 50 |  | 56 |  | 333 |  | 337 |  | 342 |  | 307 |  | 344 |  | 265 |  | 265 | 2925 | 0 | 0 | 0 | 0 | 13 | 38
400 kV BARH-MOTIHARI TL
GANTRY |  | DD+0 |  | DC+3 |  | DD+0 |  | GANTRY |  | GANTRY |  | DD+0 |  | DD+6 |  | DB+3 |  | DC+3 |  | DD+6 |  | DA+9 |  | DA+6
HOLD |  | HOLD |  | HOLD | [17 empty] | ROW |  | ROW
33/0 |  | 34/0 |  | 35/0 |  | 36/0 |  | 37/0 |  | 38/0 |  | 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 39/0 |  | 40/0
| 335 |  | 308 |  | 293 |  | 290 | 26-10-25 | 329 | 06-10-24 | 320 | 11-12-25 | 318 |  | 325 |  | 340 |  | 335 |  | 340 |  | 332 |  | 325 | 4190 | 6 | 6 | 0 | 0 | 13 | 51
DC+6 |  | DD+0 |  | DD+0 |  | DD+3 |  | DC+3 |  | DB+6 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DC+0 |  | DC+0
ROW |  | ROW | [11 empty] | HOLD |  | HOLD |  | HOLD |  | HOLD
41/0 |  | 42/0 |  | 43/0 |  | 44/0 |  | 44/1 |  | 44/2 |  | 45/0 |  | 45/1 |  | 45/2 |  | 45/3 |  | 45/4 |  | 44/0 (New) |  | 44/1 New
| 350 |  | 344 |  | 343 | 20-9-25 | 334 | 02 Leg RCC Done | 350 |  | 350 |  | 345 |  | 348 |  | 340 |  | 315 |  | 315 |  | 206 |  | 280.46 | 4220.46 | 1 | 1 | 0 | 0 | 13 | 64 | 19091
DD+3 |  | DD+3 |  | DD+3 |  | DD+3 |  | DA+3 |  | DA+0 |  | DD+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC+0 |  | DA+0
ROW | [7 empty] | ROW |  | ROW |  | ROW |  |  |  | ROW | [5 empty] | HOLD |  | HOLD
44A/0 |  | 44B/0 |  | 44C/0 |  | 45/0 New |  | 45/1 New |  | 45/2 New |  | 46/0 |  | 46/1 |  | 46/2 |  | 46/3 |  | 46/4 |  | 47/0 |  | 47/1
| 274.06 |  | 215.58 |  | 342.41 |  | 308 |  | 308 |  | 290.87 |  | 353 |  | 345 |  | 344 |  | 351 |  | 256.65 |  | 306 |  | 353 | 4047.57 | 0 | 0 | 0 | 0 | 13 | 77
DC+0 |  | DD+0 |  | DD+6 |  | DC+3 |  | DA+3 |  | DA+6 |  | DD+6 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0 |  | DC+3 |  | DA+6
HOLD |  | HOLD |  | HOLD |  | HOLD | [13 empty] | 1 MRC |  | 1 MRC
47/2 |  | 47/3 |  | 48/0 |  | 48/1 |  | 48/2 |  | 49/0 |  | 50/0 |  | 50/1 |  | 51/0 |  | 52/0 |  | 53/0 |  | 54/0 |  | 54/1
| 340 |  | 349.73 |  | 290 |  | 334 |  | 345.07 |  | 337.23 |  | 289 |  | 253.12 |  | 336.03 |  | 345.27 |  | 430.26 |  | 316 |  | 280 | 4245.71 | 2 | 0 | 2 | 0 | 13 | 90
DA+0 |  | DA+9 |  | DD+3 |  | DA+3 |  | DA+6 |  | DD+6 |  | DD+6 |  | DA+0 |  | DD+0 |  | DD+6 |  | DB+6 |  | DD+3 |  | DA+3
[12 empty] | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC
54/2 |  | 54/3 |  | 55/0 |  | 55/1 |  | 56/0 |  | 56/1 |  | 57/0 |  | 57/1 |  | 58/0 |  | 58/1 |  | 59/0 |  | 59/1 |  | 59/2
| 276 |  | 266.21 |  | 251 |  | 242.51 |  | 317 |  | 348.39 |  | 339 |  | 347.05 |  | 331 |  | 339.85 | PS | 366 |  | 328 |  | 305 | 4057.01 | 10 | 10 | 10 | 0 | 13 | 103
DA+6 |  | DA+0 |  | DD+0 |  | DA+3 |  | DC+0 |  | DA+0 |  | DC+3 |  | DA+6 |  | DC+0 |  | DA+3 |  | DD+0 |  | DA+3 |  | DA+3
[10 empty] | ROW |  | ROW |  | ROW |  |  |  | 1 MRC
59/3 |  | 59/4 |  | 59/5 |  | 60/0 |  | 60A/0 |  | 60B/0 |  | 61/0 |  | 61/1 |  | 61/2 |  | 61/3 |  | 61/4 |  | 61/5 |  | 61/6
| 339 |  | 321 |  | 351.07 |  | 271.07 |  | 134.92 |  | 209.03 |  | 165 |  | 322 |  | 223 |  | 360 |  | 296 |  | 346 |  | 207.09 | 3545.18 | 4 | 4 | 4 | 0 | 13 | 116
132KV D/C (MSK-SIW) PGCIL
DA+6 |  | DA+6 |  | DA+0 |  | DB+3 |  | DD+3 |  | DD+6 |  | DD+18 |  | DD+18 |  | DA+9 |  | DA+3 |  | DA+3 |  | DA+6 |  | DD+6 | NH-227A
|  | 1 MRC |  | 1 MRC |  |  |  | 1 MRC |  | 1 MRC |  |  |  | 1 MRC | [5 empty] | 1 MRC |  | HOLD |  | HOLD
62/0 |  | 62A/0 |  | 62/2 |  | 63/0
| 383.88 |  | 306 |  | 287 | [20 empty] | 976.88 | 3 | 0 | 2 | 0 | 4 | 120
DD+3 |  | DB+3 |  | DA+6 |  | DD+0
HOLD
63/0 |  | 63/1 |  | 63/2 |  | 64/0 |  | 64/1 |  | 64/2 |  | 65/0 |  | 66/0 |  | 66/1 |  | 66/2 |  | 67/0 |  | 67/1 |  | 67/2
| 356 |  | 311 |  | 324.56 |  | 356 |  | 340 |  | 357.17 | 27.12.25 | 262.52 | 09.01.26 | 251 | 05.1.26 | 222 | 30.12.25 | 228.52 |  | 333 |  | 363.3 |  | 327.2 | 4032.27 | 10 | 8 | 2 | 0 | 12 | 132
DD+0 |  | DA+3 |  | DA+3 |  | DD+3 |  | DA+0 |  | DA+0 |  | DD+3 |  | DD+3 |  | DA+3 |  | DA+3 |  | DC+3 |  | DA+6 |  | DA+6
[22 empty] | 1 MRC |  | 1 MRC
68/0 |  | 68/1 |  | 68/2 |  | 69/0 |  | 70/0 |  | 70/1 |  | 70/2 |  | 70/3 |  | 71/0 |  | 71A/0 |  | 71B/0 |  | 71C/0 |  | 72/0
| 90 |  | 90 |  | 97 |  | 266.75 |  | 290 |  | 338 |  | 344 |  | 303.12 |  | 90.48 |  | 71.96 |  | 124.51 |  | 92.34 |  | 244.97 | 2443.13 | 3 | 2 | 0 | 0 | 13 | 145
|  |  | 800KV HVDC (GPJ-GKP) | [15 empty] | 400KV D/C (BAR-GKP) | [5 empty] | RLY X-ING
DD+3 |  | GANTRY 220KV |  | GANTRY 220KV |  | DD+3 |  | DB+3 |  | DA+0 |  | DA+3 |  | DA+9 |  | DD+0 |  | GANTRY 220KV |  | GANTRY 220KV |  | DD+6 |  | DD+18
[8 empty] | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC | [5 empty] | HOLD |  | HOLD
73/0 |  | 73/1 |  | 73/2 |  | 73/3 |  | 74/0 |  | 74/1 |  | 75/0 |  | 75/1 |  | 76/0 |  | 76/1 |  | 77/0 |  | 78/0 |  | 79/0
| 275 |  | 367 |  | 331 |  | 299.87 |  | 229 |  | 233.14 |  | 277 |  | 303 |  | 286 |  | 346.18 |  | 325.29 |  | 347.32 |  | 233.33 | 3853.13 | 1 | 0 | 0 | 0 | 13 | 158
DD+9 |  | DA+9 |  | DA+6 |  | DA+9 |  | DD+3 |  | DA+3 |  | DC+0 |  | DA+0 |  | DD+6 |  | DA+6 |  | DC+6 |  | DD+9 |  | DC+6
2 MRC |  | 1 MRC |  | 1 MRC | [5 empty] | ROW |  | ROW | [9 empty] | ROW
HOLD |  | HOLD
80/0 |  | 80/1 |  | 80/2 |  | 80/3 |  | 81/0 |  | 81/1 |  | 82/0 |  | 83/0 |  | 83/1 |  | 84/0 |  | 85/0 |  | 85/1 |  | 86/0
| 338 |  | 320 |  | 290 |  | 284.92 |  | 365 |  | 328.9 | 15.01.26 | 348.96 | FS 31.01.26 | 351 |  | 321.51 |  | 346.3 |  | 274 | 18.01.26 | 336.92 |  | 239 | 4144.51 | 11 | 10 | 9 | 0 | 13 | 171
DD+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC+0 |  | DA+3 |  | DD+9 |  | DD+3 |  | DA+0 |  | DD+0 |  | DD+9 |  | DA+3 |  | DD+0
1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC
86/1 |  | 87/0 |  | 87/1 |  | 87/2 |  | 88/0 |  | 88/1 |  | 89/0 |  | 89/1 |  | 90/0 |  | 90/1 |  | 90/2 |  | 91/0 |  | 91/1
| 200.34 |  | 276 |  | 337 |  | 316.76 |  | 352 |  | 331.24 |  | 358 |  | 341.04 |  | 286 |  | 357 |  | 337.63 |  | 282 |  | 348.04 | 4123.05 | 10 | 7 | 6 | 0 | 13 | 184
DA+3 |  | DD+3 |  | DA+3 |  | DA+6 |  | DC+3 |  | DA+6 |  | DB+0 |  | DA+6 |  | DC+6 |  | DA+0 |  | DA+3 |  | DD+6 |  | DA+9
ROW | [15 empty] | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC
92/0 |  | 93/0 |  | 93/1 |  | 94/0 |  | 95/0 |  | 95/1 |  | 95/2 |  | 95/3 |  | 95/4 |  | 96/0 |  | 96/1 |  | 96/2 |  | 97/0
| 233.78 |  | 334 |  | 257.67 |  | 344.79 |  | 247 |  | 275 |  | 262 |  | 236 |  | 233.07 |  | 256 | 29-2-25 | 326 | 31-12-25 | 359 |  | 393 | 3757.31 | 2 | 2 | 2 | 0 | 13 | 197
132KV D/C (CHO-SWN) BGCIL
DD+25 |  | DD+18 |  | DA+9 |  | DD+0 |  | DD+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+6 |  | DA+6 |  | DB+3
[6 empty] | ROW |  | ROW |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC | [5 empty] | ROW
97/1 |  | 97/2 |  | 98/0 |  | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 100/0 |  | 100/1 |  | 100/2 |  | 100/3 |  | 100/4 |  | 101/0
| 303 | 02-12-25 | 395.2 | 04-12-25 | 343.79 | 11-12-25 | 351 | 07-12-25 | 347 | 9-12-25 | 351 | 14-12-25 | 323.83 |  | 253 | 16-12-25 | 274 | 1-12-25 | 282 | 18-12-25 | 321 | 20-12-25 | 353.24 |  | 207 | 4105.06 | 12 | 11 | 12 | 0 | 13 | 210
DA+3 |  | DA+3 |  | DC+3 |  | DC+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DC+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DC+0
ROW
101/1 |  | 101/2 |  | 101/3 |  | 101/4 |  | 102/0 |  | 102/1 |  | 102/2 |  | 102/3 |  | 102/4 |  | 103/0 |  | 104/0 |  | 104/1 |  | 104/2
25-12-25 | 329 |  | 334 |  | 331 |  | 209.59 |  | 304 |  | 302 |  | 315 |  | 285 |  | 348.77 |  | 281.67 |  | 322 |  | 293 |  | 314 | 3969.03 | 11 | 4 | 8 | 0 | 13 | 223
DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC+0 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD+9 |  | DD+0 |  | DA+3 |  | DA+6
|  |  |  | 1 MRC |  |  |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC
104/3 |  | 104/4 |  | 104/5 |  | 105/0 |  | 105/1 |  | 105/2 |  | 106/0 |  | 106/1 |  | 106/2 |  | 106/3 |  | 107/0 |  | 107/1 |  | 108/0
| 342 |  | 269 |  | 318.97 |  | 251 |  | 302 |  | 338.05 |  | 326 |  | 291 |  | 288 |  | 202.34 | FS 31.01.26 | 250 |  | 186.62 |  | 277 | 3641.98 | 12 | 5 | 3 | 0 | 13 | 236
DA+3 |  | DA+0 |  | DA+3 |  | DC+6 |  | DA+3 |  | DA+6 |  | DD+9 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD+0 |  | DA+3 |  | DD+3
|  | 1 MRC | [13 empty] | 1 MRC |  | 1 MRC
108/1 |  | 109/0 |  | 110/0 |  | 110/1 |  | 110/2 |  | 111/0 |  | 111A/0 |  | 112/0 |  | 113/0 |  | 113/1 |  | 113/2 |  | 113/3 |  | 114/0
216.63
| 229.01 |  |  |  | 260 |  | 296 |  | 287.11 |  | 241.7 |  | 143.96 |  | 360.45 |  | 302 |  | 353 |  | 341 |  | 353.1 |  | 343 | 3510.33 | 9 | 6 | 0 | 0 | 13 | 249
|  |  | NH-331 | [9 empty] | 132KV D/C BSPTCL CPRN-EKMA
DA+3 |  | DD+0 |  | DD+3 |  | DA+3 |  | DA+3 |  | DD+6 |  | DD+18 |  | DD+18 |  | DD+3 |  | DA+6 |  | DA+6 |  | DA+0 |  | DC+3
[10 empty] | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC |  | 1 MRC
114/1 |  | 115/0 |  | 115/1 |  | 116/0 |  | 116/1 |  | 116/2 |  | 116/3 |  | 116/4 |  | 117/0 |  | 117/1 |  | 118/0 |  | 118/1 |  | 118/2
| 352.08 | PS | 330 |  | 349.25 |  | 246 |  | 237 |  | 240 | PS 30.01.26 | 272 | PS 27.01.26 | 342.61 |  | 326 | PS | 328.58 |  | 305 |  | 372 |  | 290 | 3990.52 | 12 | 12 | 9 | 0 | 13 | 262
DA+3 |  | DD+3 |  | DA+6 |  | DD+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+9 |  | DC+0 |  | DA+9 |  | DC+3 |  | DA+6 |  | DA+9
ROW
118/3 |  | 119/0 |  | 120/0 |  | 120/1 |  | 121/0 |  | 122/0 |  | 123/0 |  | 123/1 |  | 124/0 |  | 124/1 |  | 125/0 |  | 126/0 |  | 127/0
| 388.98 | FS | 219.95 |  | 284 |  | 325.21 |  | 273.11 |  | 269.49 |  | 350 |  | 275.46 |  | 346 |  | 314.56 |  | 136.48 |  | 155.65 |  | 211 | 3549.89 | 9 | 8 | 2 | 0 | 13 | 275
[9 empty] | 132KV D/C OHTL BSPTCL | [11 empty] | SH-90
DA+9 |  | DD+3 |  | DD+0 |  | DA+6 |  | DD+18 |  | DD+25 |  | DC+9 |  | DA+6 |  | DC+0 |  | DA+9 |  | DC+3 |  | DD+0 |  | DD+0
[18 empty] | ROW |  | ROW |  | ROW |  | ROW
127/1 |  | 128/0 |  | 129/0 |  | 130/0 |  | 130/1 |  | 130/2 |  | 131/0 |  | 131/1 |  | 131/2 |  | 132/0 |  | 132/1 |  | 132/2 |  | 132/3
| 293.25 |  | 154.27 |  | 340.86 |  | 302 |  | 329 |  | 338.16 |  | 317 |  | 364 |  | 311.74 |  | 308 |  | 335 |  | 320 |  | 356 | 4069.28 | 8 | 7 | 0 | 0 | 13 | 288
Rly-Xing
DA+3 |  | DD+9 |  | DD+9 |  | DC+9 |  | DA+3 |  | DA+0 |  | DB+3 |  | DA+6 |  | DA+3 |  | DC+3 |  | DA+3 |  | DA+6 |  | DA+6
HOLD |  | HOLD |  | HOLD
1 MRC
132/4 |  | 132/5 |  | 132/6 |  | 133/0 |  | 133/1 |  | 133/2 |  | 134/0 |  | 135/0 |  | 136/0 |  | 136/1 |  | 136/2 |  | 137/0 |  | 137/1
| 306 |  | 302 |  | 336.74 |  | 340 |  | 357 |  | 341.48 |  | 376.98 |  | 391.22 |  | 320 |  | 364 |  | 305.4 |  | 283 |  | 279.69 | 4303.51 | 12 | 8 | 0 | 0 | 13 | 301
DA+9 |  | DA+3 |  | DA+3 |  | DD+6 |  | DA+3 |  | DA+3 |  | DC+9 |  | DD+9 |  | DD+6 |  | DA+3 |  | DA+6 |  | DD+0 |  | DB+3
ROW
138/0 |  | 139/0 |  | 140/0 |  | 141/0 |  | 142/0 |  | 142/1 |  | 143/0 |  | 144/0 |  | 145/0 |  | 145/1 |  | 145/2 |  | 146/0 |  | AP147/0
| 221.09 |  | 326.43 | WIP | 367.89 |  | 206.08 |  | 300 |  | 307.98 |  | 303.21 |  | 348.78 |  | 265 |  | 255 |  | 235.13 |  | 347.38 |  | 341.94 | 3825.91 | 9 | 9 | 0 | 0 | 13 | 314
| 132KV D/C OHTL BGCL | [5 empty] | 220KV D/C OHTL BSPTCL
DD+25 |  | DD+25 |  | DD+3 |  | DD+25 |  | DD+25 |  | DB+3 |  | DC+3 |  | DD+9 |  | DD+0 |  | DA+0 |  | DA+3 |  | DC+6 |  | DC+9
ROW
AP147A/0 |  | 148/0 |  | 148/1 |  | 148/2 |  | 148/3 |  | 149/0 |  | 149/1 |  | 150/0 |  | 150/1 |  | 151/0 |  | 151/1 |  | 151/2 |  | 152/0
| 97.17 |  | 280 |  | 315 |  | 347 |  | 351.91 |  | 220 |  | 260.03 |  | 251 |  | 193.67 |  | 325 |  | 341 |  | 343.38 |  | 261 | 3586.16 | 7 | 4 | 0 | 0 | 13 | 327
DD+6 |  | DC+3 |  | DA+3 |  | DA+3 |  | DA+6 |  | DD+0 |  | DA+3 |  | DD+0 |  | DA+3 |  | DD+6 |  | DA+9 |  | DA+6 |  | 2SDC+3
[6 empty] | ROW |  | ROW
152/1 |  | 152/2 |  | 152/3 |  | 153/0 |  | 154/0 |  | 154/1 |  | 154/2 |  | 154/3 |  | 155/0 |  | 156/0 |  | 156/1 |  | 157/0 | 158/0 | 159/0 | GANTRY
| 307 |  | 341 |  | 355.57 |  | 232.9 |  | 364 |  | 280 |  | 253 |  | 291.6 |  | 270.6 |  | 225 |  | 304.23 |  | 254.29 | 177.25 | 89.74 | 3746.18 | 8 | 2 | 0 | 0 | 9 | 336
220KV D/C CPR-VSL BSPTCL
DA+3 |  | DA+6 |  | DA+6 |  | DD+18 |  | DD+18 |  | DA+6 |  | DA+3 |  | DA+0 |  | DD+3 |  | DD+3 |  | DA+9 |  | NMB+0
[18 empty] | HOLD |  | HOLD |  | HOLD
[26 empty] | 101.1011 | 184 | 138 | 71 | 0 | 336
HOLD
SURVEY HOLD
ROW
[6 empty] | Statutary | RLY XING
NH
PL
IOCL

## ROW
Right of Way Issues
Sl No. | Districts | Issues
220 KV D/C Chhapra -Gopalganj TL Single Zebra
1 | Gopalganj | Location No. 13/0 – Dhankhar village, Majha, Gopalganj Sadar – Dharmendra S/o Khedu Prasad (Mob: 9031470755) asking for line diversion.
2 | Gopalganj | Location No. 31/2 – Ahirawlia village, Majha, Gopalganj Sadar – Bittu Singh S/o Jaswant Singh (Mob: 9852021237) asking for line diversion. SDM Gopalganj Sadar issued letter to C.O. Manjha.
3 | Siwan | Location No. 38/4 – Puraina village, Barhariya, Siwan – Amin Gaddi S/o Raja Gaddi (Mob: 6200734293) asking for line diversion. Letter issued to SDM Siwan.
4 | Siwan | Location No. 41/0 – Puraina village, Barhariya, Siwan – Bablu Singh S/o Mukhlal Singh (Mob: 9835999788) asking for line diversion.
5 | Siwan | Location No. 44/1 – Paltuhasa village, Jamo Bazar, Siwan – Ramnath Singh S/o Vikram Singh (Mob: 9810866758) asking for line diversion.
6 | Siwan | Location No. 45/2 – Jogapur village, Jamo Bazar, Siwan – Navsad Alam S/o Dr. Noor Alam (Mob: 9006174820) asking for line diversion.
7 | Siwan | Location No. 66/2 – Chorma village, Bhagwanpur Hat, Maharajganj – Abhishek Singh @ Tuntun S/o Vishundev Singh (Mob: 9473062695) demanding higher crop compensation. Letter issued from SDM Maharajganj to Goriyakothi & Bhagwanpur BDO and police station on 03.02.2026.
8 | Siwan | Location No. 74/1 – Mora Khas village, Bhagwanpur Hat, Maharajganj – Ratnesh Singh @ Sonu S/o Late Surendra Singh (Mob: 8481000021) asking for line diversion.
9 | Siwan | Location No. 75/0 – Banpur village, Bhagwanpur Hat, Maharajganj – Sunil Singh S/o Dinanath Singh (Mob: 9931838464) asking for line diversion.
10 | Siwan | Location No. 57/1 – Chainpur village, Goreyakothi, Maharajganj – Shrinivas Singh asking for land compensation.
11 | Siwan | Location No. 57/0 – Chainpur village, Goreyakothi, Maharajganj – Taukir Miya S/o Serajuddin Ahmad (Mob: 7070530148) asking for land compensation.
12 | Siwan | Location No. 57/0 – Govindapur village, Goreyakothi, Maharajganj – MD Anish S/o Fajelhaq (Mob: 7549177807) asking for land compensation.
13 | Saran | Location No. 94/0 – Basahi village, Janta Bazar, Chapra Sadar – Chandrashekar Pandey S/o Sailendra Pandey (Mob: 8617254343) asking for land compensation.
14 | Saran | Location No. 95/0 – Basahi village, Janta Bazar, Chapra Sadar – Nagendra Mahto S/o Shivjee Mahto (Mob: 9814664078) asking for land compensation.
15 | Siwan | Location No. 78/0 – Tarwar village, Bhagwanpur Hat, Maharajganj – Harendra Thakur (Mob: 7258083557) asking for land compensation. Letter issued from SDM Maharajganj to Bhagwanpur Hat and Jalalpur police station on 09.04.2026.
16 | Siwan | Location No. 86/1 – Rasulpur village, Bhagwanpur Hat, Maharajganj – Atul Kumar S/o Debilal Prasad (Mob: 9771645284) asking for line diversion.
17 | Saran | Location No. 131/0 – Mayatola village, Khaira, Chapra Sadar – Rajesh Ray S/o Late Bukhan Ray (Mob: 7324007820) asking for land compensation. KEC Letter Ref-187 issued to BSPTCL on 11.02.2026.
18 | Saran | Location No. 131/0-132/0 – Mayatola village, Khaira, Chapra Sadar – Birendra Rai (Mob: 9661849386) asking for land compensation.
19 | Saran | Location No. 137/1 – Madhopur village, Garkha, Chapra Sadar – Nagendra Mahto S/o Sartaj Singh (Mob: 9798101771) asking for line diversion. Letter issued from BSPTCL to Police Station Garkha on 07.04.2026.
20 | Saran | Location No. 102/0 – Sahpur village, Baniyapur, Chapra Sadar – Virendra Singh S/o Satyanarayan Singh (Mob: 9134411094), Vijay Singh S/o Satyanarayan Singh (Mob: 8757101652) and Bheem Singh S/o Vijay Singh (Mob: 8981904772) asking for land compensation. Letter issued from BSPTCL to Police Station Baniyapur on 07.04.2026.
21 | Saran | Location No. 102/2 – Chorawan village, Baniyapur, Chapra Sadar – Sunil Prasad S/o Rishidev Prasad (Mob: 7827182297) asking for land compensation.
22 | Saran | Location No. 118/1 – Chhitarauli village, Khaira, Chapra Sadar – Vikash Singh C/o JK Engicon Pvt. Ltd. (Mob: 9572376580) asking for line diversion.
23 | Saran | Location No. 136/0 – Fulwariya Tola Jorani village, Garkha, Chapra Sadar – Dharmendra Ray S/o Avdesh Ray asking for line diversion.
FOR 220 KV D/C Chhapra - Amnour TL Twin Moose
1 | Saran | Location No. 12/0 – Tarwar village, Madaura Sub Division – Raju Singh & Mrigendra Singh (Mob: 7464007290) asking for line diversion. Letter issued from SDM Madaura to BDO Amnor on 21.02.2026.
2 | Saran | Location No. 17/0 – Mura village, Madaura Sub Division – Arun Pandey S/o Janakdev Pandey reported ROW issue at location.
3 | Saran | Location No. 18/0 – Mura village, Madaura Sub Division – Bijendra Pandey S/o Kesav Pandey reported ROW issue at location.
LILO of 400 KV Barh (NTPC) - Motihari (DMTCL) D/C (Quad Moose) transmission line at Chhapra (New)
1 | Saran | Location No. 26 LI – Babhanganwa village, Parsa, Chapra Sadar – Janak Singh S/o Late Rupak Singh (Mob: 9852671518) raised issue regarding shifting of tower. 02 Leg RCC done and letter issued from SDM Chapra to BDO Parsa on 13.02.2026.
2 | Saran | Location No. 20 LI – Baksanda village, Parsa – Kameshwar Singh S/o Satyanarayan Singh (Mob: 7277175252 / 7519311278) reported ROW issue at location.
3 | Saran | Location No. 13/0 LI – Pirozpur village, Parsa – Gopaleshwar Singh (Mob: 9097745422) reported ROW issue. Letter issued from BSPTCL to SDM Chapra on 15.04.2026.
4 | Saran | Location No. 15/0 LI – Bhima Bandh village, Parsa – Bablu Singh (Mob: 9801016674) reported ROW issue at location.
5 | Saran | Location No. 12/0 LI PIT A & PIT B – Firojpur village, Pachrukhi, Parsa – Suresh Singh S/o Terash Singh (Mob: 7488054101) reported ROW issue. Letter issued from BSPTCL to SDM Chapra on 07.05.2026.
6 | Saran | Location No. 12/0 LI PIT D – Bhima Bandh village, Pachrukhi, Parsa – Bageshwar Mahto reported ROW issue at location.
7 | Saran | Location No. 15/1 LI – Laganpura village, Pachrukhi, Parsa – Rajeshwar Rai (Mob: 9199649156) reported ROW issue at location.

## 220 SZ Status (hidden)
Sr No. | Sections | Tower No. | Tower Type | Span | Status
[5 empty] | Foundation | Earthing | Erection | Stringing
1 | Ap-9 | 9/0 | DC+3 | 0
2 |  | 9/1 | DA+9 | 360
3 | AP-9A | 9A/0 | DB+6 | 328
4 | AP -10 | 10/0 | DB+6 | 360
5 | AP -11 | 11/0 | DB+6 | 409
6 |  | 11/1 | DA+0 | 360
7 |  | 11/2 | DA+6 | 340
8 |  | 11/3 | DA+9 | 360
9 | AP-12 | 12/0 | DC+3 | 314
10 | AP-13 | 13/0 | DD+6 | 341
11 |  | 13/1 | DA+6 | 307 | Completed | Completed
12 |  | 13/2 | DA+9 | 287 | Completed | Completed
13 | AP-14 | 14/0 | DC+3 | 319 | Completed | Completed
14 |  | 14/1 | DA+0 | 320 | Completed | Completed
15 | AP-15 | 15/0 | DD+6 | 320 | Completed | Completed
16 | AP-16 | 16/0 | DD+6 | 341 | Completed | Completed
17 | AP-17 | 17/0 | DD+3 | 309 | Completed | Completed
18 |  | 17/1 | DA+6 | 326 | Completed | Completed
19 | AP-18 | 18/0 | DC+6 | 325 | Completed | Completed
20 |  | 18/1 | DA+9 | 340 | Completed | Completed
21 | AP-19 | 19/0 | DD+6 | 350 | Completed | Completed
22 |  | 19/1 | DA+6 | 330
23 | AP-21 | 21/0 | DC+3 | 330 | Completed | Completed
24 | Ap-22 | 22/0 | DD+6 | 369
25 | Ap-23 | 23/0 | DD+0 | 375
26 |  | Gan-1 | GANTRY | 72
27 |  | Gan-2 | GANTRY | 50
28 | Ap-24 | 24/0 | DD+0 | 48
29 | AP-25 | 25/0 | DC+3 | 263
30 | AP-26 | 26/0 | DD+0 | 231
31 |  | Gan-3 | GANTRY | 84
32 |  | Gan-4 | GANTRY | 50
33 | AP-27 | 27/0 | DD+0 | 56
34 | AP-28 | 28/0 | DD+6 | 333
35 | AP-29 | 29/0 | DB+3 | 337
36 | AP-30 | 30/0 | DC+3 | 342
37 | AP-31 | 31/0 | DD+6 | 307
38 |  | 31/1 | DA+9 | 344
39 |  | 31/2 | DA+6 | 265
40 | AP-33 | 33/0 | DC+6 | 265
41 | AP-34 | 34/0 | DD+0 | 335
42 | AP-35 | 35/0 | DD+0 | 308 | Completed
43 | AP-36 | 36/0 | DD+3 | 293 | WIP
44 | AP-37 | 37/0 | DC+3 | 290 | Completed | Completed
45 | AP-38 | 38/0 | DB+6 | 329 | Completed | Completed
46 |  | 38/1 | DA+0 | 320 | WIP
47 |  | 38/2 | DA+0 | 318
48 |  | 38/3 | DA+3 | 325
49 |  | 38/4 | DA+0 | 340
50 |  | 38/5 | DA+3 | 335
51 | AP-39 | 39/0 | DC+0 | 340
52 | AP-40 | 40/0 | DC+0 | 332 | Completed | Completed
53 | AP-41 | 41/0 | DD+3 | 325
54 | AP-42 | 42/0 | DD+3 | 350
55 | AP-43 | 43/0 | DD+3 | 344
56 | AP-44 | 44/0 | DD+3 | 343 | Completed | Completed
57 |  | 44/1 | DA+3 | 334
58 |  | 44/2 | DA+0 | 350
59 | AP-45 | 45/0 | DD+3 | 350
60 |  | 45/1 | DA+3 | 345
61 |  | 45/2 | DA+3 | 348
62 |  | 45/3 | DA+0 | 340
63 |  | 45/4 | DA+0 | 315
64 | AP-46 | 46/0 | DD+3 | 315
65 |  | 46/1 | DA+3 | 359
66 |  | 46/2 | DA+6 | 322
67 | AP-47 | 47/0 | DC+6 | 335
68
69
70
71
72 | AP-63 | 63/0 | 2SDD+0 | 0
73 |  | 63/1 | 2SDA+3 | 356
74 |  | 63/2 | 2SDA+3 | 311
75 | Ap-64 | 64/0 | 2SDD+3 | 324.56
76 |  | 64/1 | 2SDA+0 | 356
77 |  | 64/2 | 2SDA+0 | 340
78 | AP-65 | 65/0 | 2SDD+3 | 357.17
79 | AP-66 | 66/0 | 2SDD+3 | 262.52
80 |  | 66/1 | 2SDA+3 | 251
81 |  | 66/2 | 2SDA+3 | 222
82 | AP-67 | 67/0 | 2SDC+3 | 228.52
83 |  | 67/1 | 2SDA+6 | 333
84 |  | 67/2 | 2SDA+6 | 363.3
85 | AP-68 | 68/0 | 2SDD+3 | 327.2
86 |  | 68/1 | GANTRY 220KV | 90
87 |  | 68/2 | GANTRY 220KV | 90
88 | AP-69 | 69/0 | 2SDD+3 | 97
89 | AP-70 | 70/0 | 2SDB+3 | 266.75
90 |  | 70/1 | 2SDA+3 | 290
91 |  | 70/2 | 2SDA+3 | 338
92 |  | 70/3 | 2SDA+9 | 344
93 | AP-71 | 71/0 | 2SDD+0 | 303.12
94 | AP-71 A | 71A/0 | GANTRY 220KV | 90.48
95 | AP - 71 B | 71B/0 | GANTRY 220KV | 71.96
96 | AP 71C | 71C/0 | 2SDD+6 | 124.51
97 | AP-72 | 72/0 | 2TDD+18 | 92.34
98 | AP-73 | 73/0 | 2SDD+9 | 244.97
99 |  | 73/1 | 2SDA+9 | 275
100 |  | 73/2 | 2SDA+6 | 367
101 |  | 73/3 | 2SDA+9 | 331
102 | AP-74 | 74/0 | 2SDD+3 | 299.87
103 |  | 74/1 | 2SDA+3 | 229
104 | AP-75 | 75/0 | 2SDC+0 | 233.14
105 |  | 75/1 | 2SDA+0 | 280
106 | AP-76 | 76/0 | 2SDD+6 | 293.92
107 |  | 76/1 | 2SDA+6 | 312
108 | AP-77 | 77/0 | 2SDC+6 | 346.18
109 | AP-78 | 78/0 | 2SDD+9 | 325.29
110 | AP-79 | 79/0 | 2SDC+6 | 347.32
111 | AP-80 | 80/0 | 2SDD+0 | 233.33
112 |  | 80/1 | 2SDA+0 | 338
113 |  | 80/2 | 2SDA+3 | 320
114 |  | 80/3 | 2SDA+3 | 290
115 | AP-81 | 81/0 | 2SDC+0 | 284.92
116 |  | 81/1 | 2SDA+3 | 365
117 | AP-82 | 82/0 | 2SDD+9 | 328.9
118 | AP-83 | 83/0 | 2SDD+3 | 348.96
119 |  | 83/1 | 2SDA+0 | 351
120 | AP-84 | 84/0 | 2SDD+0 | 321.51
121 | AP-85 | 85/0 | 2SDD+9 | 346.3
122 |  | 85/1 | 2SDA+3 | 274
123 | AP-86 | 86/0 | 2SDD+0 | 336.92
124 |  | 86/1 | 2SDA+3 | 239
125 | AP-87 | 87/0 | 2SDD+3 | 200.34
126 |  | 87/1 | 2SDA+3 | 276
127 |  | 87/2 | 2SDA+6 | 337
128 | AP-88 | 88/0 | 2SDC+3 | 316.76
129 |  | 88/1 | 2SDA+6 | 352
130 | AP-89 | 89/0 | 2SDB+0 | 331.24
131 |  | 89/1 | 2SDA+6 | 358
132 | AP-90 | 90/0 | 2SDC+6 | 341.04
133 |  | 90/1 | 2SDA+0 | 286
134 |  | 90/2 | 2SDA+3 | 357
135 |  | 91/0 | 2SDD+6 | 337.63
136 |  | 91/1 | 2SDA+9 | 282
137 |  | 92/0 | 2TDD+18 | 348.04
138 | AP-93 | 93/0 | 2TDD+18 | 233.78
139 |  | 93/1 | 2SDA+9 | 334
140 | AP-94 | 94/0 | 2SDD+0 | 257.67
141 | AP-95 | 95/0 | 2SDD+3 | 344.79
142 |  | 95/1 | 2SDA+3 | 247
143 |  | 95/2 | 2SDA+0 | 275
144 |  | 95/3 | 2SDA+0 | 262
145 |  | 95/4 | 2SDA+0 | 236
146 | AP-96 | 96/0 | 2SDD+0 | 233.07
147 |  | 96/1 | 2SDA+6 | 256
148 |  | 96/2 | 2SDA+6 | 326
149 | AP-97 | 97/0 | 2SDB+3 | 359
150 |  | 97/1 | 2SDA+3 | 393
151 |  | 97/2 | 2SDA+3 | 303 | Completed | Completed
152 | AP-98 | 98/0 | 2SDC+3 | 395.2 | Completed | Completed
153 | AP-99 | 99/0 | 2SDC+3 | 343.79 | WIP
154 |  | 99/1 | 2SDA+0 | 351 | Completed | Completed
155 |  | 99/2 | 2SDA+3 | 347 | Completed | Completed
156 |  | 99/3 | 2SDA+6 | 351 | WIP
157 | AP-100 | 100/0 | 2SDC+0 | 323.83
158 |  | 100/1 | 2SDA+6 | 253
159 |  | 100/2 | 2SDA+3 | 274
160 |  | 100/3 | 2SDA+3 | 282
161 |  | 100/4 | 2SDA+3 | 321
162 |  | 101/0 | 2SDC+0 | 353.24
163 |  | 101/1 | 2SDA+0 | 207
164 |  | 101/2 | 2SDA+0 | 329
165 |  | 101/3 | 2SDA+0 | 334
166 |  | 101/4 | 2SDA+3 | 331
167 | AP-102 | 102/0 | 2SDC+0 | 209.59
168 |  | 102/1 | 2SDA+3 | 304
169 |  | 102/2 | 2SDA+6 | 302
170 |  | 102/3 | 2SDA+3 | 315
171 |  | 102/4 | 2SDA+6 | 285
172 | AP-103 | 103/0 | 2SDD+9 | 348.77
173 | AP-104 | 104/0 | 2SDD+0 | 281.67
174 |  | 104/1 | 2SDA+3 | 322
175 |  | 104/2 | 2SDA+6 | 293
176 |  | 104/3 | 2SDA+3 | 314
177 |  | 104/4 | 2SDA+0 | 342
178 |  | 104/5 | 2SDA+3 | 269
179 | AP-105 | 105/0 | 2SDC+6 | 318.97
180 |  | 105/1 | 2SDA+3 | 251
181 |  | 105/2 | 2SDA+6 | 302
182 | AP-106 | 106/0 | 2SDD+9 | 338.05
183 |  | 106/1 | 2SDA+0 | 326
184 |  | 106/2 | 2SDA+0 | 291
185 |  | 106/3 | 2SDA+0 | 288
186 | AP-107 | 107/0 | 2SDD+0 | 202.34
187 |  | 107/1 | 2SDA+3 | 250
188 | AP-108 | 108/0 | 2SDD+3 | 186.62
189 |  | 108/1 | 2SDA+3 | 277
190 | AP-109 | 109/0 | 2SDD+0 | 229.01
191 | AP-110 | 110/0 | 2SDD+3 | 216.63
192 |  | 110/1 | 2SDA+3 | 260
193 |  | 110/2 | 2SDA+3 | 296
194 | AP-111 | 111/0 | 2SDD+6 | 287.11
195 | AP-111A | 111A/0 | 2TDD+18 | 241.7
196 | AP-112 | 112/0 | 2TDD+18 | 143.96
197 | AP-113 | 113/0 | 2SDD+3 | 360.45
198 |  | 113/1 | 2SDA+6 | 302
199 |  | 113/2 | 2SDA+6 | 353
200 |  | 113/3 | 2SDA+0 | 341
201 | AP-114 | 114/0 | 2SDC+3 | 353.1
202 |  | 114/1 | 2SDA+3 | 343
203 | AP-115 | 115/0 | 2SDD+3 | 352.08
204 |  | 115/1 | 2SDA+6 | 330
205 | AP-116 | 116/0 | 2SDD+3 | 349.25
206 |  | 116/1 | 2SDA+3 | 246
207 |  | 116/2 | 2SDA+3 | 237
208 |  | 116/3 | 2SDA+3 | 240
209 |  | 116/4 | 2SDA+9 | 272
210 | AP-117 | 117/0 | 2SDC+0 | 342.61
211 |  | 117/1 | 2SDA+9 | 326
212 | AP-118 | 118/0 | 2SDC+3 | 328.58
213 |  | 118/1 | 2SDA+6 | 305
214 |  | 118/2 | 2SDA+9 | 372
215 |  | 118/3 | 2SDA+9 | 290
216 | AP-119 | 119/0 | 2SDD+3 | 388.98
217 | AP-120 | 120/0 | 2SDD+0 | 219.95
218 |  | 120/1 | 2SDB+3 | 284
219 | AP-121 | 121/0 | 2TDD+25 | 325.21
220 | AP-122 | 122/0 | 2TDD+18 | 273.11
221 | AP-123 | 123/0 | 2SDC+3 | 269.49
222 |  | 123/1 | 2SDA+6 | 350
223 | AP-124 | 124/0 | 2SDC+0 | 275.46
224 |  | 124/1 | 2SDA+9 | 346
225 | AP-125 | 125/0 | 2SDC+3 | 314.56
226 | AP-126 | 126/0 | 2SDD+0 | 136.48
227 | AP-127 | 127/0 | 2SDD+0 | 155.65
228 |  | 127/1 | 2SDA+3 | 211
229 | AP-128 | 128/0 | 2SDD+9 | 293.25
230 | AP-129 | 129/0 | 2SDD+9 | 154.27
231 | AP-130 | 130/0 | 2SDC+9 | 340.86
232 |  | 130/1 | 2SDA+3 | 302
233 |  | 130/2 | 2SDA+0 | 329
234 | AP-131 | 131/0 | 2SDB+3 | 338.16
235 |  | 131/1 | 2SDA+6 | 317
236 |  | 131/2 | 2SDA+3 | 364
237 | AP-132 | 132/0 | 2SDC+3 | 311.74
238 |  | 132/1 | 2SDA+3 | 308
239 |  | 132/2 | 2SDA+6 | 335
240 |  | 132/3 | 2SDA+6 | 320
241 |  | 132/4 | 2SDA+6 | 356
242 |  | 132/5 | 2SDA+3 | 306
243 |  | 132/6 | 2SDA+3 | 302
244 | AP-133 | 133/0 | 2SDD+6 | 336.74
245 |  | 133/1 | 2SDA+3 | 340
246 |  | 133/2 | 2SDA+3 | 357
247 | AP-134 | 134/0 | 2SDC+9 | 341.48
248 | AP-135 | 135/0 | 2SDD+9 | 376.98
249 | AP-136 | 136/0 | 2SDD+6 | 391.22
250 |  | 136/1 | 2SDA+3 | 320
251 |  | 136/2 | 2SDA+6 | 364
252 | AP-137 | 137/0 | 2SDD+0 | 305.4
253 |  | 137/1 | 2SDB+3 | 283
254 | AP-138 | 138/0 | 2TDD+25 | 279.69
255 | AP-139 | 139/0 | 2TDD+25 | 221.09
256 | AP-140 | 140/0 | 2SDD+3 | 326.43
257 | AP-141 | 141/0 | 2TDD+25 | 367.89
258 | AP-142 | 142/0 | 2TDD+25 | 206.08
259 |  | 142/1 | 2SDB+3 | 300
260 | AP-143 | 143/0 | 2SDC+3 | 307.98
261 | AP-144 | 144/0 | 2SDD+9 | 303.21
262 | AP-145 | 145/0 | 2SDD+0 | 348.78
263 |  | 145/1 | 2SDA+0 | 265
264 |  | 145/2 | 2SDA+3 | 255
265 |  | 146/0 | 2SDC+6 | 235.13
266 | AP-147 | 147/0 | 2SDC+9 | 347.38
267 | AP-147A | AP147A/0 | 2SDD+6 | 341.94
268 | AP-148 | 148/0 | 2SDC+3 | 97.17
269 |  | 148/1 | 2SDA+3 | 280
270 |  | 148/2 | 2SDA+3 | 315
271 |  | 148/3 | 2SDA+6 | 347
272 | AP-149 | 149/0 | 2SDD+0 | 351.91
273 |  | 149/1 | 2SDA+3 | 220
274 | AP-150 | 150/0 | 2SDD+0 | 260.03
275 |  | 150/1 | 2SDA+3 | 251
276 | AP-151 | 151/0 | 2SDD+6 | 193.67
277 |  | 151/1 | 2SDA+9 | 325
278 |  | 151/2 | 2SDA+6 | 341
279 | AP-152 | 152/0 | 2SDC+3 | 343.38
280 |  | 152/1 | 2SDA+3 | 261
281 |  | 152/2 | 2SDA+6 | 307
282 |  | 152/3 | 2SDA+6 | 341
283 | AP-153 | 153/0 | 2TDD+18 | 355.57
284 | AP-154 | 154/0 | 2TDD+18 | 232.9
285 |  | 154/1 | 2SDA+6 | 364
286 |  | 154/2 | 2SDA+3 | 280
287 |  | 154/3 | 2SDA+0 | 253
288 | AP-155 | 155/0 | 2SDD+3 | 291.6
289 | AP-156 | 156/0 | 2SDD+3 | 270.6
83944.29

## CS-220kV TM (hidden)
NAME OF LINE : 220kV Chhapra(New) Amnour DCDS with Twin Moose Conductor
Name of Client : BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL) | [34 empty] | W.O.TB 412
Executing Agency : M/S KEC INTERNATIONAL LIMITED | [34 empty] | DATE :09.09.2025
NIT No. : 23/PR/BSPTCL/2023 | [34 empty] | REV-00
NOA No. : 18(Supply), 19(Service) Dated. 27.12.2023
Check Survey Report (AP 5 to AP 15) 5.539KM
AS PER DETAILS SURVEY | [6 empty] | AS PER CHECK SURVEY
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | RAISED CHIMNEY | SPAN (Mtr) | CUMULATIVE SPAN | AP NO. | TOWER NO. | TYPE OF TOWER | HT of Tower (Mtr) | SPAN (Mtr) | CUMULATIVE SPAN | SECTION LENGTH | LEG EXTENSION |  |  | RAISED CHIMNEY | BENCHING VOLUME (Cum) | REVETMENT VOLUME (Cum) | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates (Zone-45R) |  | CROSSING DETAILS & REMARKS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF POLICE STATION
[14 empty] | A | B | C | [7 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Northing (m)
1 | AP 5 | 5/0 | 2TDC+0 |  |  | 0 | AP 5 | 5/0 | 2TDC+0 | 38.33 |  | 0 | 0 | [6 empty] | 55.383 | 16° 36' 15"LT TENTATIVE | 592.312 | 296.156 | 135 | 161 | 296 | 137 | 160 | 297 | 84d53'57.126"E | 25d52'56.338"N | 289518.572 | 2864336.129 |  | KASTA
[5 empty] | 314.773 | [5 empty] | 314.773 | [22 empty] | Cart track
2 | AP 6 | 6/0 | 2TDC+0 |  |  | 314.773 | AP 6 | 6/0 | 2TDC+0 | 38.33 |  | 314.773 | 314.773 | [6 empty] | 54.869 | 24° 37' 47"RT | 567.773 | 283.8865 | 154 | 97 | 251 | 155 | 109 | 264 | 84d53'46.659"E | 25d52'52.472"N | 289225.289 | 2864221.818 |  | KASTA
[5 empty] | 253 | [5 empty] | 253 | [22 empty] | LT line
3 |  | 6/1 | 2TDA+3 |  |  | 567.773 |  | 6/1 | 2TDA+3 | 40.53 |  | 567.773 | [7 empty] | 55.082 |  | 583.8 | 291.9 | 156 | 184 | 340 | 145 | 177 | 322 | 84d53'37.581"E | 25d52'52.818"N | 288972.718 | 2864236.539 |  | KASTA
[5 empty] | 330.8 | [5 empty] | 330.8 | [22 empty] | Cart track, LT line, Dabra river
4 | AP 7 | 7/0 | 2TDD+0 |  |  | 898.573 | AP 7 | 7/0 | 2TDD+0 | 38.33 |  | 898.573 | 583.8 | [6 empty] | 55.472 | 32° 58' 11"RT | 548.8 | 274.4 | 147 | 95 | 242 | 154 | 102 | 257 | 84d53'25.71"E | 25d52'53.271"N | 288642.478 | 2864255.788 |  | MADARPUR
[5 empty] | 218 | [5 empty] | 218
5 |  | 7/1 | 2TDA+0 |  |  | 1116.573 |  | 7/1 | 2TDA+0 | 37.53 |  | 1116.573 | [7 empty] | 56.622 |  | 438.351 | 219.1755 | 123 | 120 | 243 | 116 | 115 | 231 | 84d53'19.327"E | 25d52'57.373"N | 288466.798 | 2864384.864 |  | GOSI CHHAPRA
[5 empty] | 220.351 | [5 empty] | 220.351
6 | AP 8 | 8/0 | 2TDC+0 |  |  | 1336.924 | AP 8 | 8/0 | 2TDC+0 | 38.33 |  | 1336.924 | 438.351 | [6 empty] | 55.876 | 23° 15' 49"LT | 410.351 | 205.1755 | 101 | 55 | 156 | 106 | 72 | 178 | 84d53'12.874"E | 25d53'1.518"N | 288289.224 | 2864515.332 |  | GOSI CHHAPRA
[5 empty] | 190 | [5 empty] | 190
7 |  | 8/1 | 2TDA+3 |  |  | 1526.924 |  | 8/1 | 2TDA+3 | 40.53 |  | 1526.924 | [7 empty] | 56.057 |  | 450 | 225 | 135 | 100 | 235 | 118 | 113 | 231 | 84d53'6.202"E | 25d53'2.814"N | 288104.125 | 2864558.208 | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data) | GOSI CHHAPRA
[5 empty] | 260 | [5 empty] | 260 | [22 empty] | Cart track
8 |  | 8/2 | 2TDA+6 |  |  | 1786.924 |  | 8/2 | 2TDA+6 | 43.53 |  | 1786.924 | [7 empty] | 56.426 |  | 583.052 | 291.526 | 160 | 170 | 330 | 148 | 167 | 314 | 84d52'57.072"E | 25d53'4.587"N | 287850.832 | 2864616.881 |  | MADARPUR
[5 empty] | 323.052 | [5 empty] | 323.052 | [22 empty] | Dabra river, Tar road, Bridge
9 | AP 9 | 9/0 | 2TDC+6 |  |  | 2109.976 | AP 9 | 9/0 | 2TDC+6 | 44.33 |  | 2109.976 | 773.052 | [6 empty] | 55.334 | 28° 36' 34"RT | 569.075 | 284.5375 | 153 | 189 | 342 | 157 | 159 | 316 | 84d52'45.727"E | 25d53'6.79"N | 287536.113 | 2864689.783 |  | MADARPUR
[5 empty] | 246.023 | [5 empty] | 246.023 | [22 empty] | 11kV line
10 | AP 10 | 10/0 | 2TDD+0 |  |  | 2355.999 | AP 10 | 10/0 | 2TDD+0 | 38.33 |  | 2355.999 | 246.023 | [6 empty] | 54.551 | 32° 7' 44"RT | 501.023 | 250.5115 | 57 | 102 | 159 | 88 | 114 | 202 | 84d52'39.03"E | 25d53'12.006"N | 287352.284 | 2864853.289 |  | GAWANDRI
[5 empty] | 255 | [5 empty] | 255 | [22 empty] | Dabra river
11 |  | 10/1 | 2TDA+3 |  |  | 2610.999 |  | 10/1 | 2TDA+3 | 40.53 |  | 2610.999 | [7 empty] | 54.201 |  | 407 | 203.5 | 153 | 70 | 223 | 142 | 73 | 215 | 84d52'36.33"E | 25d53'19.922"N | 287281.058 | 2865098.14 | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data) | MALAHI
[5 empty] | 152 | [5 empty] | 152 | [22 empty] | Cart track, 11kV line
12 |  | 10/2 | 2TDA+3 |  |  | 2762.999 |  | 10/2 | 2TDA+3 | 40.53 |  | 2762.999 | [7 empty] | 54.569 |  | 446.498 | 223.249 | 82 | 172 | 253 | 79 | 161 | 240 | 84d52'34.72"E | 25d53'24.641"N | 287238.601 | 2865244.089 | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data) | MALAHI
[5 empty] | 294.498 | [5 empty] | 294.498 | [22 empty] | 11kV line, Dabra river
13 | AP 11 | 11/0 | 2TDC+0 |  |  | 3057.497 | AP 11 | 11/0 | 2TDC+0 | 38.33 |  | 3057.497 | 701.498 | [6 empty] | 54.659 | 22° 19' 24"RT | 563.498 | 281.749 | 123 | 110 | 233 | 134 | 120 | 254 | 84d52'31.602"E | 25d53'33.784"N | 287156.342 | 2865526.866 |  | HAKMA
[5 empty] | 269 | [5 empty] | 269 | [22 empty] | LT line
14 |  | 11/1 | 2TDA+3 |  |  | 3326.497 |  | 11/1 | 2TDA+3 | 40.53 |  | 3326.497 | [7 empty] | 54.458 |  | 602 | 301 | 159 | 168 | 327 | 149 | 168 | 317 | 84d52'32.473"E | 25d53'42.488"N | 287184.945 | 2865794.341 |  | HAKMA
[5 empty] | 333 | [5 empty] | 333 | [22 empty] | Cart track
15 |  | 11/2 | 2TDA+3 |  |  | 3659.497 |  | 11/2 | 2TDA+3 | 40.53 |  | 3659.497 | [7 empty] | 54.264 |  | 590 | 295 | 165 | 147 | 312 | 166 | 140 | 306 | 84d52'33.552"E | 25d53'53.263"N | 287220.353 | 2866125.453 |  | HAKMA
[5 empty] | 257 | [5 empty] | 257 | [22 empty] | Trar road, LT line
16 |  | 11/3 | 2TDA+0 |  |  | 3916.497 |  | 11/3 | 2TDA+0 | 37.53 |  | 3916.497 | [7 empty] | 55.203 |  | 554 | 277 | 110 | 153 | 263 | 118 | 151 | 269 | 84d52'34.385"E | 25d54'1.579"N | 287247.68 | 2866380.996 |  | SHIKARPUR
[5 empty] | 297 | [5 empty] | 297
17 |  | 11/4 | 2TDA+0 |  |  | 4213.497 |  | 11/4 | 2TDA+0 | 37.53 |  | 4213.497 | [7 empty] | 54.618 |  | 588.09 | 294.045 | 144 | 144 | 288 | 146 | 145 | 291 | 84d52'35.348"E | 25d54'11.189"N | 287279.26 | 2866676.312 |  | SHIKARPUR
[5 empty] | 291.09 | [5 empty] | 291.09 | [22 empty] | Cart track
18 | AP 12 | 12/0 | 2TDD+0 |  |  | 4504.587 | AP 12 | 12/0 | 2TDD+0 | 38.33 |  | 4504.587 | 1447.09 | [6 empty] | 54.903 | 31° 35' 34"LT | 526.09 | 263.045 | 147 | 59 | 206 | 147 | 81 | 227 | 84d52'36.291"E | 25d54'20.608"N | 287310.212 | 2866965.752 |  | TARWAR
[5 empty] | 235 | [5 empty] | 235 | [22 empty] | Cart track, 33kV line
19 |  | 12/1 | 2TDA+6 |  |  | 4739.587 |  | 12/1 | 2TDA+6 | 43.53 |  | 4739.587 | [7 empty] | 54.987 |  | 593.489 | 296.7445 | 176 | 108 | 284 | 155 | 135 | 289 | 84d52'32.535"E | 25d54'27.446"N | 287209.082 | 2867177.879 |  | TARWAR
[5 empty] | 358.489 | [5 empty] | 358.489 | [22 empty] | 33kV line, Tar road, 11kV line, Nala
20 | AP 13 | 13/0 | 2TDD+18 |  |  | 5098.076 | AP 13 | 13/0 | 2TDD+18 | 56.33 |  | 5098.076 | 593.489 | [6 empty] | 54.601 | 1° 10' 58"RT | 590.175 | 295.0875 | 251 | 38 | 289 | 225 | 76 | 302 | 84d52'26.805"E | 25d54'37.877"N | 287054.811 | 2867501.475 |  | TARWAR
[5 empty] | 231.686 | [5 empty] | 231.686 | [22 empty] | 220kV D/C OHTL BGCL HJP-CHP
21 | AP 14 | 14/0 | 2TDD+25 |  |  | 5329.762 | AP 14 | 14/0 | 2TDD+25 | 63.33 |  | 5329.762 | 231.686 | [6 empty] | 54.97 | 31° 48' 49"LT | 441.115 | 220.5575 | 194 | 273 | 467 | 156 | 184 | 340 | 84d52'23.257"E | 25d54'44.686"N | 286959.446 | 2867712.624 |  | TARWAR
[5 empty] | 209.429 | [5 empty] | 209.429 | [22 empty] | 220kV D/C OHTL BSPTCL ANR-MZP
22 | AP 15 | 15/0 | 2TDD+9 | 2 |  | 5539.191 | AP 15 | 15/0 | 2TDD+9 | 47.33 |  | 5539.191 | 209.429 |  |  |  | 2 |  |  | 55.049 | 59° 5' 38"LT TENTATIVE | 313.981 | 156.9905 | -63 | 150 | 86 | 26 | 94 | 120 | 84d52'16.943"E | 25d54'48.387"N | 286785.577 | 2867829.372 | RC = 2m | TARWAR
[7 empty] | Total length = |  |  |  | 5.5392 | Km
For KEC International Ltd | [20 empty] | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED, PATNA (WHOLLY OWNED SUBSIDIARY OF POWERGRID)
Surveyed By |  |  |  |  | Checked By |  |  |  |  | Submitted By | [10 empty] | Checked By |  |  |  |  | Recommended By | [6 empty] | Approved By
Structure Summary
[10 empty] | 2TDA+0 | = | 3
[10 empty] | 2TDA+3 | = | 6
[10 empty] | 2TDA+6 | = | 2
[10 empty] | 2TDA+9 | = | 0
[10 empty] | 2TDB+0 | = | 0
[10 empty] | 2TDB+3 | = | 0
[10 empty] | 2TDB+6 | = | 0
[10 empty] | 2TDB+9 | = | 0
[10 empty] | 2TDC+0 | = | 4
[10 empty] | 2TDC+3 | = | 0
[10 empty] | 2TDC+6 | = | 1
[10 empty] | 2TDC+9 | = | 0
[10 empty] | 2TDD+0 | = | 3
[10 empty] | 2TDD+18 | = | 1
[10 empty] | 2TDD+25 | = | 1
[10 empty] | 2TDD+3 | = | 0
[10 empty] | 2TDD+6 | = | 0
[10 empty] | 2TDD+9 | = | 1
[10 empty] | Total | = | 22

## DS-220 KV TM (hidden)
NAME OF LINE : 220kV Chhapra(New) Amnour DCDS with Twin Moose Conductor
Name of Client : BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL) | [33 empty] | W.O.TB 412
Executing Agency : M/S KEC INTERNATIONAL LIMITED | [33 empty] | DATE :21.08.2025
NIT No. : 23/PR/BSPTCL/2023 | [33 empty] | REV-00
NOA No. : 18(Supply), 19(Service) Dated. 27.12.2023
Details Survey Report (AP 1 to AP 18) 6.475KM
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | Survey Clearance for FDN | HT of Tower (Mtr) | SPAN (Mtr) | CUMULATIVE SPAN | SECTION LENGTH | LEG EXTENSION |  |  |  | RAISED CHIMNEY | BENCHING VOLUME (Cum) | REVETMENT VOLUME (Cum) | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF POLICE STATION | REMARKS
[9 empty] | A | B | C | [8 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Northing (m)
1 | AP 1 | 1/0 | 2TDD+0 | Hold | 38.33 |  | 0 | [8 empty] | 55.382 | 4° 59' 40"RT | 112.78 | 56.39 | 0 | 67 | 67 | 0 | 59 | 59 | 84d54'15.934"E | 25d53'5.602"N | 290046.73 | 2864612.852
[6 empty] | 112.78 | [23 empty] | Substation boundary, Nala
2 | AP 2 | 2/0 | 2TDC+0 | Hold | 38.33 |  | 112.78 | 112.78 | [7 empty] | 54.985 | 29° 43' 51"RT | 225.954 | 112.977 | 46 | 40 | 87 | 53 | 52 | 105 | 84d54'15.225"E | 25d53'1.994"N | 290025.215 | 2864502.143
[6 empty] | 113.174 | [23 empty] | Cart track
3 | AP 3 | 3/0 | 2TDC+0 | Hold | 38.33 |  | 225.954 | 113.174 | [7 empty] | 55.617 | 29° 2' 31"RT | 279.632 | 139.816 | 73 | 80 | 153 | 61 | 82 | 143 | 84d54'12.623"E | 25d52'59.17"N | 289951.372 | 2864416.379
[6 empty] | 166.458 | [23 empty] | Tar road, Nala, 11kV line
4 | AP 4 | 4/0 | 2TDC+0 | Hold | 38.33 |  | 392.412 | 166.458 |  |  |  |  | 2 |  |  | 53.831 | 15° 32' 23"RT | 443.997 | 221.9985 | 87 | 143 | 229 | 85 | 141 | 226 | 84d54'7.047"E | 25d52'57.219"N | 289795.182 | 2864358.821 |  |  |  |  | RC = 2m
[6 empty] | 277.539 | [23 empty] | Dabra river
5 | AP 5 | 5/0 | 2TDC+0 | Hold | 38.33 |  | 669.951 | 277.539 | [7 empty] | 55.383 | 16° 36' 15"LT | 592.312 | 296.156 | 135 | 161 | 296 | 137 | 160 | 297 | 84d53'57.126"E | 25d52'56.338"N | 289518.572 | 2864336.129
[6 empty] | 314.773 | [23 empty] | Cart track
6 | AP 6 | 6/0 | 2TDC+0 | Hold | 38.33 |  | 984.724 | 314.773 | [7 empty] | 54.869 | 24° 37' 47"RT | 567.773 | 283.8865 | 154 | 97 | 251 | 155 | 109 | 264 | 84d53'46.659"E | 25d52'52.472"N | 289225.289 | 2864221.818
[6 empty] | 253 | [23 empty] | LT line
7 |  | 6/1 | 2TDA+3 | OK | 40.53 |  | 1237.724 | [8 empty] | 55.082 |  | 583.8 | 291.9 | 156 | 184 | 340 | 145 | 177 | 322 | 84d53'37.581"E | 25d52'52.818"N | 288972.718 | 2864236.539
[6 empty] | 330.8 | [23 empty] | Cart track, LT line, Dabra river
8 | AP 7 | 7/0 | 2TDD+0 | OK | 38.33 |  | 1568.524 | 583.8 | [7 empty] | 55.472 | 32° 58' 11"RT | 548.8 | 274.4 | 147 | 95 | 242 | 154 | 102 | 257 | 84d53'25.71"E | 25d52'53.271"N | 288642.478 | 2864255.788
218
9 |  | 7/1 | 2TDA+0 | OK | 37.53 |  | 1786.524 | [8 empty] | 56.622 |  | 438.351 | 219.1755 | 123 | 120 | 243 | 116 | 115 | 231 | 84d53'19.327"E | 25d52'57.373"N | 288466.798 | 2864384.864
220.351
10 | AP 8 | 8/0 | 2TDC+0 | OK | 38.33 |  | 2006.875 | 438.351 | [7 empty] | 55.876 | 23° 15' 49"LT | 410.351 | 205.1755 | 101 | 55 | 156 | 106 | 72 | 178 | 84d53'12.874"E | 25d53'1.518"N | 288289.224 | 2864515.332
190
11 |  | 8/1 | 2TDA+3 | OK | 40.53 |  | 2196.875 | [8 empty] | 56.057 |  | 450 | 225 | 135 | 100 | 235 | 118 | 113 | 231 | 84d53'6.202"E | 25d53'2.814"N | 288104.125 | 2864558.208 |  |  |  |  | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data)
[6 empty] | 260 | [23 empty] | Cart track
12 |  | 8/2 | 2TDA+6 | Hold | 43.53 |  | 2456.875 | [8 empty] | 56.426 |  | 583.052 | 291.526 | 160 | 170 | 330 | 148 | 167 | 314 | 84d52'57.072"E | 25d53'4.587"N | 287850.832 | 2864616.881
[6 empty] | 323.052 | [23 empty] | Dabra river, Tar road, Bridge
13 | AP 9 | 9/0 | 2TDC+6 | Hold | 44.33 |  | 2779.927 | 773.052 | [7 empty] | 55.334 | 28° 36' 34"RT | 569.075 | 284.5375 | 153 | 189 | 342 | 157 | 159 | 316 | 84d52'45.727"E | 25d53'6.79"N | 287536.113 | 2864689.783
[6 empty] | 246.023 | [23 empty] | 11kV line
14 | AP 10 | 10/0 | 2TDD+0 | Hold | 38.33 |  | 3025.95 | 246.023 | [7 empty] | 54.551 | 32° 7' 44"RT | 501.023 | 250.5115 | 57 | 102 | 159 | 88 | 114 | 202 | 84d52'39.03"E | 25d53'12.006"N | 287352.284 | 2864853.289
[6 empty] | 255 | [23 empty] | Dabra river
15 |  | 10/1 | 2TDA+3 | OK | 40.53 |  | 3280.95 | [8 empty] | 54.201 |  | 407 | 203.5 | 153 | 70 | 223 | 142 | 73 | 215 | 84d52'36.33"E | 25d53'19.922"N | 287281.058 | 2865098.14 |  |  |  |  | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data)
[6 empty] | 152 | [23 empty] | Cart track, 11kV line
16 |  | 10/2 | 2TDA+3 | OK | 40.53 |  | 3432.95 | [8 empty] | 54.569 |  | 446.498 | 223.249 | 82 | 172 | 253 | 79 | 161 | 240 | 84d52'34.72"E | 25d53'24.641"N | 287238.601 | 2865244.089 |  |  |  |  | (+3m Extension used to maintain minimum weight span of 200m limit as per Tower spotting Data)
[6 empty] | 294.498 | [23 empty] | 11kV line, Dabra river
17 | AP 11 | 11/0 | 2TDC+0 | OK | 38.33 |  | 3727.448 | 701.498 | [7 empty] | 54.659 | 22° 19' 24"RT | 563.498 | 281.749 | 123 | 110 | 233 | 134 | 120 | 254 | 84d52'31.602"E | 25d53'33.784"N | 287156.342 | 2865526.866
[6 empty] | 269 | [23 empty] | LT line
18 |  | 11/1 | 2TDA+3 | OK | 40.53 |  | 3996.448 | [8 empty] | 54.458 |  | 602 | 301 | 159 | 168 | 327 | 149 | 168 | 317 | 84d52'32.473"E | 25d53'42.488"N | 287184.945 | 2865794.341
[6 empty] | 333 | [23 empty] | Cart track
19 |  | 11/2 | 2TDA+3 | OK | 40.53 |  | 4329.448 | [8 empty] | 54.264 |  | 590 | 295 | 165 | 147 | 312 | 166 | 140 | 306 | 84d52'33.552"E | 25d53'53.263"N | 287220.353 | 2866125.453
[6 empty] | 257 | [23 empty] | Trar road, LT line
20 |  | 11/3 | 2TDA+0 | OK | 37.53 |  | 4586.448 | [8 empty] | 55.203 |  | 554 | 277 | 110 | 153 | 263 | 118 | 151 | 269 | 84d52'34.385"E | 25d54'1.579"N | 287247.68 | 2866380.996
297
21 |  | 11/4 | 2TDA+0 | OK | 37.53 |  | 4883.448 | [8 empty] | 54.618 |  | 588.09 | 294.045 | 144 | 144 | 288 | 146 | 145 | 291 | 84d52'35.348"E | 25d54'11.189"N | 287279.26 | 2866676.312
[6 empty] | 291.09 | [23 empty] | Cart track
22 | AP 12 | 12/0 | 2TDD+0 | OK | 38.33 |  | 5174.538 | 1447.09 | [7 empty] | 54.903 | 31° 35' 34"LT | 526.09 | 263.045 | 147 | 59 | 206 | 147 | 81 | 227 | 84d52'36.291"E | 25d54'20.608"N | 287310.212 | 2866965.752
[6 empty] | 235 | [23 empty] | Cart track, 33kV line
23 |  | 12/1 | 2TDA+6 | Hold | 43.53 |  | 5409.538 | [8 empty] | 54.987 |  | 593.489 | 296.7445 | 176 | 108 | 284 | 155 | 135 | 289 | 84d52'32.535"E | 25d54'27.446"N | 287209.082 | 2867177.879
[6 empty] | 358.489 | [23 empty] | 33kV line, Tar road, 11kV line, Nala
24 | AP 13 | 13/0 | 2TDD+18 | Hold | 56.33 |  | 5768.027 | 593.489 | [7 empty] | 54.601 | 1° 10' 58"RT | 590.175 | 295.0875 | 251 | 38 | 289 | 225 | 76 | 302 | 84d52'26.805"E | 25d54'37.877"N | 287054.811 | 2867501.475
[6 empty] | 231.686 | [23 empty] | 220kV D/C OHTL BGCL HJP-CHP
25 | AP 14 | 14/0 | 2TDD+25 | Hold | 63.33 |  | 5999.713 | 231.686 | [7 empty] | 54.97 | 31° 48' 49"LT | 441.115 | 220.5575 | 194 | 273 | 467 | 156 | 184 | 340 | 84d52'23.257"E | 25d54'44.686"N | 286959.446 | 2867712.624
[6 empty] | 209.429 | [23 empty] | 220kV D/C OHTL BSPTCL ANR-MZP
26 | AP 15 | 15/0 | 2TDD+9 | Hold | 47.33 |  | 6209.142 | 209.429 |  |  |  |  | 2 |  |  | 55.049 | 59° 5' 38"LT | 313.981 | 156.9905 | -63 | 150 | 86 | 26 | 94 | 120 | 84d52'16.943"E | 25d54'48.387"N | 286785.577 | 2867829.372 |  |  |  |  | RC = 2m
104.552
27 | AP 16 | 16/0 | 2TDD+3 | Hold | 41.33 |  | 6313.694 | 104.552 | [7 empty] | 54.843 | 59° 0' 51"LT | 192.611 | 96.3055 | -45 | 70 | 25 | 11 | 59 | 70 | 84d52'13.571"E | 25d54'46.89"N | 286690.986 | 2867784.833
88.059
28 | AP 17 | 17/0 | 2TDD+0 | Hold | 38.33 |  | 6401.753 | 88.059 | [7 empty] | 54.436 | 39° 49' 50"RT | 160.947 | 80.4735 | 19 | 4 | 23 | 29 | 22 | 51 | 84d52'13.304"E | 25d54'44.039"N | 286682.13 | 2867697.22
72.888
29 | AP 18 | 18/0 | 2TDD+3 | Hold | 41.33 |  | 6474.641 | 72.888 | [7 empty] | 54.569 | 54° 21' 38"RT | 72.888 | 36.444 | 69 | 0 | 69 | 52 | 0 | 52 | 84d52'11.463"E | 25d54'42.355"N | 286630.051 | 2867646.225
| Total length = |  |  |  |  | 6.4746 | Km
For KEC International Ltd | [18 empty] | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED, PATNA (WHOLLY OWNED SUBSIDIARY OF POWERGRID)
Surveyed By |  |  |  |  | Checked By |  |  |  | Submitted By | Submitted By | Submitted By | Submitted By | Submitted By | [5 empty] | Checked By |  |  |  |  | Recommended By | [5 empty] | Approved By
Structure Summary
[5 empty] | 2TDA+0 | = | 3
[5 empty] | 2TDA+3 | = | 6
[5 empty] | 2TDA+6 | = | 2
[5 empty] | 2TDA+9 | = | 0
[5 empty] | 2TDB+0 | = | 0
[5 empty] | 2TDB+3 | = | 0
[5 empty] | 2TDB+6 | = | 0
[5 empty] | 2TDB+9 | = | 0
[5 empty] | 2TDC+0 | = | 7
[5 empty] | 2TDC+3 | = | 0
[5 empty] | 2TDC+6 | = | 1
[5 empty] | 2TDC+9 | = | 0
[5 empty] | 2TDD+0 | = | 5
[5 empty] | 2TDD+18 | = | 1
[5 empty] | 2TDD+25 | = | 1
[5 empty] | 2TDD+3 | = | 2
[5 empty] | 2TDD+6 | = | 0
[5 empty] | 2TDD+9 | = | 1
[5 empty] | Total | = | 29

## DS 400kV LI (hidden)
NAME OF LINE : LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) (Loop In)
Name of Client : BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL)
Executing Agency : M/S KEC INTERNATIONAL LIMITED | [33 empty] | W.O.TB 412
NIT No. : 23/PR/BSPTCL/2023 | [33 empty] | DT :30.07.2020
NOA No. : 18(Supply), 19(Service) Dated. 27.12.2023 | [33 empty] | REV-00
Details Survey Report (AP 1 to AP 34) 20.778KM
|  | 20.495 | [31 empty] | REV-02
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | Survey Clearance for FDN | HT of Tower (Mtr) | SPAN (Mtr) | SECTION LENGTH | CUMULATIVE SPAN | LEG EXTENSION |  |  |  | RAISED CHIMNEY | BENCHING VOLUME (Cum) | REVETMENT VOLUME (Cum) | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF POLICE STATION | REMARKS
[9 empty] | A | B | C | [8 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Northing (m)
1 | AP 1 | 1/0 | 4DD+0 | Hold | 47.74 |  |  | 0 | [7 empty] | 55.909 | 45° 33' 45"RT | 112.764 | 56.382 | 0 | 66 | 66 | 0 | 61 | 61 | 84d54'16.634"E | 25d53'19.85"N | 290073.213 | 2865051.01 |  | ARNA
[6 empty] | 112.764 | [23 empty] | Hut
2 | AP 2 | 2/0 | 4DD+0 | Hold | 47.74 |  | 112.764 | 112.764 | [7 empty] | 55.625 | 35° 58' 12"RT | 271.423 | 135.7115 | 52 | 84 | 136 | 57 | 83 | 140 | 84d54'19.095"E | 25d53'22.76"N | 290143.136 | 2865139.477 |  | SANDALPUR
158.659
3 | AP 3 | 3/0 | 4DD+0 | Hold | 47.74 |  | 158.659 | 271.423 | [7 empty] | 55.476 | 30° 18' 41"RT | 454.659 | 227.3295 | 79 | 153 | 232 | 81 | 152 | 233 | 84d54'24.555"E | 25d53'24.235"N | 290295.87 | 2865182.431 |  | SANDALPUR
[6 empty] | 296 | [23 empty] | Cart track, Nala, LT line, Hut, Borewell
4 |  | 3/1 | 4DA+0 | Hold | 48.16 |  |  | 567.423 | [7 empty] | 54.966 |  | 628 | 314 | 146 | 168 | 314 | 147 | 168 | 315 | 84d54'34.885"E | 25d53'21.959"N | 290582.307 | 2865107.801 |  | SANDALPUR
332
5 |  | 3/2 | 4DA+0 | Hold | 48.16 |  |  | 899.423 | [7 empty] | 54.7 |  | 609 | 304.5 | 164 | 138 | 302 | 165 | 138 | 303 | 84d54'46.472"E | 25d53'19.405"N | 290903.581 | 2865024.093 |  | SANDALPUR
[6 empty] | 277 | [23 empty] | Cart track, Nala, 11kV line
6 |  | 3/3 | 4DA+0 | Hold | 48.16 |  |  | 1176.423 | [7 empty] | 54.83 |  | 617.684 | 308.842 | 140 | 165 | 305 | 139 | 167 | 306 | 84d54'56.138"E | 25d53'17.275"N | 291171.633 | 2864954.254 |  | MOLNAPUR
[6 empty] | 340.684 | [23 empty] | 2No's Pond
7 | AP 4 | 4/0 | 4DC+0 | Hold | 47.74 |  | 1245.684 | 1517.107 | [7 empty] | 55.869 | 18° 12' 5"RT | 570.525 | 285.2625 | 178 | 109 | 287 | 176 | 112 | 288 | 84d55'8.027"E | 25d53'14.655"N | 291501.31 | 2864868.357 |  | MOLNAPUR
[6 empty] | 229.841 | [23 empty] | NH - 722, 2 No's 11kV lines |  |  |  | 11kV line to be diverted
8 | AP 5 | 5/0 | 4DD+0 | Hold | 47.74 |  | 229.841 | 1746.948 | [7 empty] | 56.286 | 50° 6' 30"LT | 506.766 | 253.383 | 118 | 140 | 258 | 116 | 140 | 256 | 84d55'15.036"E | 25d53'10.709"N | 291694.496 | 2864743.834 |  | GANESHPATTI
[6 empty] | 276.925 | [23 empty] | 2No's Cart track, 2No's 11kV lines, Well |  |  |  | 11kV line to be diverted
9 | AP 6 | 6/0 | 4DD+0 | Hold | 47.74 |  | 276.925 | 2023.873 | [7 empty] | 56.119 | 53° 5' 45"RT | 633.925 | 316.9625 | 137 | 168 | 305 | 138 | 173 | 311 | 84d55'24.485"E | 25d53'13.521"N | 291958.888 | 2864826.2 |  | GANESHPATTI
[6 empty] | 357 | [23 empty] | 11kV lines, Well
10 |  | 6/1 | 4DA+3 | Hold | 51.16 |  |  | 2380.873 | [7 empty] | 55.075 |  | 600.767 | 300.3835 | 193 | 150 | 343 | 189 | 140 | 329 | 84d55'35.003"E | 25d53'6.887"N | 292248.466 | 2864617.409 |  | BASAUTI
[6 empty] | 243.767 | [23 empty] | Nala
11 | AP 7 | 7/0 | 4DB+0 | Hold | 47.74 |  | 600.767 | 2624.64 | [7 empty] | 54.996 | 8° 59' 29"RT | 581.767 | 290.8835 | 94 | 170 | 264 | 104 | 170 | 274 | 84d55'42.185"E | 25d53'2.357"N | 292446.195 | 2864474.842 |  | BASAUTI
[6 empty] | 338 | [23 empty] | Cart track, Tar road, Nala, 11kV line,Hand pump
12 |  | 7/1 | 4DA+0 | Hold | 48.16 |  |  | 2962.64 | [7 empty] | 54.828 |  | 647 | 323.5 | 169 | 156 | 325 | 169 | 156 | 325 | 84d55'50.936"E | 25d52'54.745"N | 292686.097 | 2864236.744 |  | MURLI SIRSIA
[6 empty] | 309 | [23 empty] | 3No's LT lines, Cart track
13 |  | 7/2 | 4DA+0 | ok | 48.16 |  |  | 3271.64 | [7 empty] | 54.601 |  | 690.534 | 345.267 | 153 | 194 | 347 | 154 | 193 | 347 | 84d55'58.935"E | 25d52'47.785"N | 292905.416 | 2864019.074 |  | MURLI SIRSIA
[6 empty] | 381.534 | [23 empty] | Tar road, Bargad tree
14 | AP 8 | 8/0 | 4DB+0 | ok | 47.74 |  | 1028.534 | 3653.174 | [7 empty] | 54.119 | 5° 20' 56"LT | 713.404 | 356.702 | 188 | 165 | 353 | 189 | 165 | 354 | 84d56'8.812"E | 25d52'39.193"N | 293176.218 | 2863750.308 |  | MURLI SIRSIA
[6 empty] | 331.87 | [23 empty] | 2No's 11kV lines, Cart track |  |  |  | 11kV line to be diverted
15 | AP 9 | 9/0 | 4DC+0 | ok | 47.74 |  | 331.87 | 3985.044 | [7 empty] | 54.134 | 18° 23' 40"LT | 673.082 | 336.541 | 165 | 169 | 334 | 165 | 170 | 335 | 84d56'18.136"E | 25d52'32.475"N | 293432.537 | 2863539.504 |  | MURLI SIRSIA
[6 empty] | 341.212 | [23 empty] | 11kV line
16 | AP 10 | 10/0 | 4DB+0 | ok | 47.74 |  | 341.212 | 4326.256 | [7 empty] | 54.248 | 2° 36' 19"LT | 584.707 | 292.3535 | 171 | 118 | 289 | 171 | 119 | 290 | 84d56'29.641"E | 25d52'28.658"N | 293751 | 2863417 |  | MURLI SIRSIA
[6 empty] | 243.495 | [23 empty] | Tar road, LT line
17 | AP 11 | 11/0 | 4DD+0 | ok | 47.74 |  | 243.495 | 4569.751 | [7 empty] | 54.506 | 30° 45' 23"LT | 559.495 | 279.7475 | 123 | 157 | 280 | 122 | 157 | 279 | 84d56'37.98"E | 25d52'26.274"N | 293982 | 2863340 |  | JAGARNATHPUR
[6 empty] | 316 | [23 empty] | 2No's LT lines, Well
18 |  | 11/1 | 4DA+0 | ok | 48.16 |  |  | 4885.751 | [7 empty] | 54.523 |  | 641 | 320.5 | 157 | 161 | 318 | 157 | 162 | 319 | 84d56'49.029"E | 25d52'28.622"N | 294290.721 | 2863407.433 |  | JAGARNATHPUR
[6 empty] | 325 | [23 empty] | Pond, Tar road
19 |  | 11/2 | 4DA+0 | ok | 48.16 |  |  | 5210.751 | [7 empty] | 54.695 |  | 594 | 297 | 164 | 136 | 300 | 164 | 135 | 299 | 84d57'0.392"E | 25d52'31.036"N | 294608.235 | 2863476.787 |  | BARKI SIRSIA
[6 empty] | 269 | [23 empty] | Cart track, 11kV lie, LT line
20 |  | 11/3 | 4DA+0 | ok | 48.16 |  |  | 5479.751 | [7 empty] | 54.582 |  | 550.828 | 275.414 | 134 | 116 | 250 | 134 | 125 | 259 | 84d57'9.797"E | 25d52'33.034"N | 294871.039 | 2863534.19 |  | BARKI SIRSIA
[6 empty] | 281.828 | [23 empty] | 2No's LT line |  |  |  | LT line to be diverted
21 | AP 12 | 12/0 | 4DB+3 | ok | 50.74 |  | 1191.828 | 5761.579 | [7 empty] | 54.762 | 7° 1' 5"LT | 704.828 | 352.414 | 166 | 177 | 343 | 156 | 187 | 343 | 84d57'19.651"E | 25d52'35.127"N | 295146.375 | 2863594.331 |  | BARKI SIRSIA
[6 empty] | 423 | [23 empty] | Cart track, 2No's 11kV lie, LT line, Tar road, Hand pump |  |  |  | LT line to be diverted
22 |  | 12/1 | 4DA+9 | ok | 57.16 |  |  | 6184.579 | [7 empty] | 55.779 |  | 799.095 | 399.5475 | 246 | 204 | 450 | 237 | 199 | 436 | 84d57'33.907"E | 25d52'39.88"N | 295545.507 | 2863734.413 |  | BHIMA BANDH
[6 empty] | 376.095 | [23 empty] | State highway, 11kV lins, Nala
23 | AP 13 | 13/0 | 4DD+6 | ok | 53.74 |  | 799.095 | 6560.674 | [7 empty] | 55.676 | 53° 3' 22"LT | 815.171 | 407.5855 | 169 | 217 | 386 | 174 | 217 | 391 | 84d57'46.581"E | 25d52'44.106"N | 295900.38 | 2863858.962 |  | PIROZPUR
[6 empty] | 439.076 | [23 empty] | LT line, Semal garden, Sagwan garden, 33kV line, Cart track, Nala, Tar road, 11kV line, Mango garden, Foot track |  |  |  | LT line to be diverted
24 | AP 14 | 14/0 | 4DC+6 | ok | 53.74 |  | 439.076 | 6999.75 | [7 empty] | 55.774 | 28° 21' 50"LT | 757.065 | 378.5325 | 218 | 203 | 421 | 218 | 186 | 404 | 84d57'51.117"E | 25d52'57.769"N | 296033.177 | 2864277.474 |  | PACHRUKHI
[6 empty] | 317.989 | [23 empty] | Mango garden, Foot track, Tar road
25 | AP 15 | 15/0 | 4DC+0 | ok | 47.74 |  | 317.989 | 7317.739 | [7 empty] | 55.311 | 22° 22' 10"LT | 667.989 | 333.9945 | 112 | 166 | 278 | 128 | 168 | 296 | 84d57'48.811"E | 25d53'7.888"N | 295973.814 | 2864589.873 |  | BHIMA BANDH
[6 empty] | 350 | [23 empty] | 2No's 11kV lines, LT line, Damage pump house
26 |  | 15/1 | 4DA+3 | Hold | 51.16 |  |  | 7667.739 | [7 empty] | 53.686 |  | 784.141 | 392.0705 | 183 | 145 | 328 | 181 | 165 | 346 | 84d57'41.778"E | 25d53'17.314"N | 295782.532 | 2864882.979 |  | LANGARPURA
[6 empty] | 434.141 | [23 empty] | 4No's 11kV lines
27 | AP 16 | 16/0 | 4DD+18 | Hold | 65.74 |  | 784.141 | 8101.88 | [7 empty] | 54.27 | 42° 12' 40"RT | 705.144 | 352.572 | 293 | 80 | 373 | 273 | 105 | 378 | 84d57'33.053"E | 25d53'29.005"N | 295545.265 | 2865246.549 |  | LANGARPURA
[6 empty] | 271.003 | [23 empty] | 220kV D/C OHTL BGCL (HJP- CHP), LT line
28 | AP 17 | 17/0 | 4DD+25 | Hold | 72.74 |  | 271.003 | 8372.883 | [7 empty] | 54.364 | 51° 38' 13"RT | 461.912 | 230.956 | 198 | 339 | 537 | 173 | 206 | 379 | 84d57'34.44"E | 25d53'37.721"N | 295588.045 | 2865514.154 |  | LANGARPURA
[6 empty] | 190.909 | [23 empty] | 4No's 11kV lines
29 | AP 18 | 18/0 | 4DC+6 | Hold | 53.74 |  | 190.909 | 8563.792 | [7 empty] | 55.085 | 16° 4' 36"RT | 601.909 | 300.9545 | -142 | 223 | 81 | -9 | 219 | 210 | 84d57'40.369"E | 25d53'40.838"N | 295754.563 | 2865607.525 |  | LANGARPURA
[6 empty] | 411 | [23 empty] | LT line, Cart track
30 |  | 18/1 | 4DA+3 | ok | 51.16 |  |  | 8974.792 | [7 empty] | 54.845 |  | 798 | 399 | 190 | 176 | 366 | 195 | 181 | 376 | 84d57'54.688"E | 25d53'44.09"N | 296154.698 | 2865701.403 |  | PACHRUKHI
[6 empty] | 387 | [23 empty] | 11kV line, LT line, Pond
31 |  | 18/2 | 4DA+6 | ok | 54.16 |  |  | 9361.792 | [7 empty] | 55.199 |  | 764.351 | 382.1755 | 212 | 207 | 419 | 207 | 202 | 409 | 84d58'8.172"E | 25d53'47.151"N | 296531.467 | 2865789.8 |  | PACHRUKHI
[6 empty] | 377.351 | [23 empty] | 2No's 11kV lines, 2No's Tar road
32 | AP 19 | 19/0 | 4DB+3 | ok | 50.74 |  | 1175.351 | 9739.143 | [7 empty] | 55.095 | 12° 30' 39"RT | 769.351 | 384.6755 | 172 | 213 | 385 | 177 | 209 | 386 | 84d58'21.319"E | 25d53'50.136"N | 296898.842 | 2865875.992 |  | PACHRUKHI
[6 empty] | 392 | [23 empty] | 11kV line, Cart track, Pump
33 |  | 19/1 | 4DA+0 | ok | 48.16 |  |  | 10131.143 | [7 empty] | 55.002 |  | 705 | 352.5 | 180 | 158 | 338 | 186 | 158 | 344 | 84d58'35.396"E | 25d53'50.487"N | 297290.813 | 2865880.733 |  | PACHRUKHI
[6 empty] | 313 | [23 empty] | LT line
34 |  | 19/2 | 4DA+0 | ok | 48.16 |  |  | 10444.143 | [7 empty] | 54.82 |  | 631 | 315.5 | 155 | 158 | 313 | 156 | 158 | 314 | 84d58'46.635"E | 25d53'50.767"N | 297603.79 | 2865884.519 |  | BANKERWA BHAW
[6 empty] | 318 | [23 empty] | 11kV line
35 |  | 19/3 | 4DA+0 | ok | 48.16 |  |  | 10762.143 | [7 empty] | 55.017 |  | 665 | 332.5 | 160 | 173 | 333 | 160 | 173 | 333 | 84d58'58.054"E | 25d53'51.051"N | 297921.767 | 2865888.365 |  | BANKERWA BHAW
[6 empty] | 347 | [23 empty] | Pond
36 |  | 19/4 | 4DA+0 | ok | 48.16 |  |  | 11109.143 | [7 empty] | 55.197 |  | 734.515 | 367.2575 | 175 | 195 | 370 | 175 | 195 | 370 | 84d59'10.515"E | 25d53'51.36"N | 298268.742 | 2865892.562 |  | BANKERWA BHAW
[6 empty] | 387.515 | [23 empty] | 11kV line
37 | AP 20 | 20/0 | 4DC+0 | ok | 47.74 |  | 1757.515 | 11496.658 | [7 empty] | 54.939 | 16° 3' 32"LT | 732.515 | 366.2575 | 192 | 132 | 324 | 193 | 144 | 337 | 84d59'24.43"E | 25d53'51.706"N | 298656.228 | 2865897.249 |  | BAKSANDA
[6 empty] | 345 | [23 empty] | 2No's 11kV lines, Tar road
38 |  | 20/1 | 4DA+6 | ok | 54.16 |  |  | 11841.658 | [7 empty] | 55.437 |  | 755.293 | 377.6465 | 212 | 203 | 415 | 201 | 204 | 405 | 84d59'36.242"E | 25d53'55.101"N | 298986.587 | 2865996.687 |  | BAKSANDA
[6 empty] | 410.293 | [23 empty] | 11kV line, LT line, Cart track
39 | AP 21 | 21/0 | 4DB+6 | ok | 53.74 |  | 755.293 | 12251.951 | [7 empty] | 56.058 | 12° 27' 57"RT | 802.023 | 401.0115 | 209 | 211 | 420 | 208 | 206 | 414 | 84d59'50.289"E | 25d53'59.138"N | 299379.468 | 2866114.944 |  | BISHUNPURA
[6 empty] | 391.73 | [23 empty] | 2No's 11kV lines
40 | AP 22 | 22/0 | 4DD+3 | ok | 50.74 |  | 391.73 | 12643.681 | [7 empty] | 56.137 | 48° 46' 50"LT | 691.73 | 345.865 | 179 | 36 | 215 | 184 | 80 | 264 | 85d0'4.304"E | 25d54'0.283"N | 299770.103 | 2866144.219 |  | BISHUNPURA
[6 empty] | 300 | [23 empty] | Cart track, 2No's Nala, Tar road, 11kV line
41 |  | 22/1 | 4DD+18 | ok | 65.74 |  |  | 12943.681 | [7 empty] | 55.929 |  | 758.616 | 379.308 | 261 | 257 | 518 | 218 | 253 | 471 | 85d0'10.648"E | 25d54'8.162"N | 299950.37 | 2866384.019 |  | UTTIMPUR
[6 empty] | 458.616 | [23 empty] | 2No's Nala, 2No's Tar road, 33kV line, 11kV line |  |  |  | 11kV line to be diverted
42 | AP 23 | 23/0 | 4DD+9 | ok | 56.74 |  | 758.616 | 13402.297 |  |  |  |  | 3 |  |  | 55.68 | 57° 37' 41"RT | 764.796 | 382.398 | 206 | 219 | 425 | 212 | 196 | 408 | 85d0'20.347"E | 25d54'20.208"N | 300225.947 | 2866750.606 |  | LALAPUR
[6 empty] | 306.18 | [23 empty] | Tar road, 2No's Nala, 11kV lines
43 | AP 24 | 24/0 | 4DD+3 | ok | 50.74 |  | 306.18 | 13708.477 | [7 empty] | 55.944 | 46° 55' 37"RT | 691.918 | 345.959 | 95 | 211 | 306 | 118 | 206 | 324 | 85d0'31.324"E | 25d54'19.568"N | 300531.157 | 2866726.255 |  | PARSA BAZAR (NP)
[6 empty] | 385.738 | [23 empty] | 11kV lins, Pond
44 | AP 25 | 25/0 | 4DD+0 | ok | 47.74 |  | 385.738 | 14094.215 | [7 empty] | 55.629 | 49° 55' 28"LT | 725.738 | 362.869 | 175 | 151 | 326 | 180 | 156 | 336 | 85d0'40.116"E | 25d54'9.88"N | 300771.344 | 2866424.421 |  | PARSA BAZAR (NP)
[6 empty] | 340 | [23 empty] | 11kV line, LT line, House, Nala, Tar road |  |  |  | 11kV line to be diverted
45 |  | 25/1 | 4DA+3 | ok | 51.16 |  |  | 14434.215 | [7 empty] | 55.396 |  | 747.566 | 373.783 | 186 | 216 | 402 | 181 | 213 | 394 | 85d0'52.33"E | 25d54'9.746"N | 301111.217 | 2866415.14 |  | PARSA BAZAR (NP)
407.566
46 | AP 26 | 26/0 | 4DD+0 | ok | 47.74 |  | 747.566 | 14841.781 | [7 empty] | 55.787 | 41° 0' 20"LT | 731.566 | 365.783 | 189 | 141 | 330 | 193 | 147 | 340 | 85d1'6.97"E | 25d54'9.585"N | 301518.631 | 2866404.015 |  | PARSA BAZAR (NP)
[6 empty] | 324 | [23 empty] | 11kV line, LT line, Cart track, Nala, Tar road
47 |  | 26/1 | 4DA+3 | ok | 51.16 |  |  | 15165.781 | [7 empty] | 55.727 |  | 705 | 352.5 | 180 | 179 | 359 | 174 | 183 | 357 | 85d1'15.847"E | 25d54'16.395"N | 301768.848 | 2866609.849 |  | PARSA BAZAR (NP)
[6 empty] | 381 | [23 empty] | Nala, Tar road, 33kV line, 2No's 11kV line, LT line
48 |  | 26/2 | 4DA+6 | ok | 54.16 |  |  | 15546.781 | [7 empty] | 54.917 |  | 750.15 | 375.075 | 203 | 199 | 402 | 199 | 195 | 394 | 85d1'26.285"E | 25d54'24.403"N | 302063.084 | 2866851.894 |  | PARSA BAZAR (NP)
[6 empty] | 369.15 | [23 empty] | 2No's 11kV lines, 2No's LT lines, Nala, Cart track
49 | AP 27 | 27/0 | 4DB+3 | ok | 50.74 |  | 1074.15 | 15915.931 | [7 empty] | 55.44 | 4° 8' 7"LT | 783.15 | 391.575 | 170 | 190 | 360 | 175 | 196 | 371 | 85d1'36.399"E | 25d54'32.162"N | 302348.169 | 2867086.411 |  | FATEHPUR
[6 empty] | 414 | [23 empty] | 3No's 11kV lines, Cart track |  |  |  | 11kV line to be diverted
50 |  | 27/1 | 4DA+6 | ok | 54.16 |  |  | 16329.931 | [7 empty] | 55.763 |  | 784 | 392 | 224 | 222 | 446 | 219 | 210 | 429 | 85d1'47.019"E | 25d54'41.58"N | 302648.092 | 2867371.792 |  | FATEHPUR
[6 empty] | 370 | [23 empty] | 11kV line, Cart track
51 |  | 27/2 | 4DA+0 | ok | 48.16 |  |  | 16699.931 | [7 empty] | 55.453 |  | 677 | 338.5 | 149 | 153 | 302 | 161 | 154 | 315 | 85d1'56.511"E | 25d54'49.997"N | 302916.139 | 2867626.842 |  | BANAUTA MAKUND
[6 empty] | 307 | [23 empty] | 11kV line, Cart track
52 |  | 27/3 | 4DA+0 | ok | 48.16 |  |  | 17006.931 | [7 empty] | 55.495 |  | 598 | 299 | 154 | 148 | 302 | 154 | 147 | 301 | 85d2'4.387"E | 25d54'56.981"N | 303138.546 | 2867838.465 |  | BANAUTA MAKUND
[6 empty] | 291 | [23 empty] | 2No's LT lines, 11kV line
53 |  | 27/4 | 4DA+0 | ok | 48.16 |  |  | 17297.931 | [7 empty] | 55.184 |  | 625.029 | 312.5145 | 143 | 152 | 295 | 144 | 158 | 302 | 85d2'11.852"E | 25d55'3.6"N | 303349.362 | 2868039.058 |  | BANAUTA MAKUND
[6 empty] | 334.029 | [23 empty] | 3No's 11kV lines, LT line, Cart track
54 | AP 28 | 28/0 | 4DD+3 | ok | 50.74 |  | 1716.029 | 17631.96 | [7 empty] | 54.73 | 36° 17' 57"RT | 600.029 | 300.0145 | 185 | 153 | 338 | 180 | 145 | 325 | 85d2'20.422"E | 25d55'11.199"N | 303591.35 | 2868269.313 |  | BANAUTA MAKUND
[6 empty] | 266 | [23 empty] | 2No's LT lines
55 |  | 28/1 | 4DA+0 | ok | 48.16 |  |  | 17897.96 | [7 empty] | 55.532 |  | 521.445 | 260.7225 | 115 | 132 | 247 | 124 | 131 | 255 | 85d2'29.884"E | 25d55'12.422"N | 303855.207 | 2868303.008 |  | BANAUTA MAKUND
[6 empty] | 255.445 | [23 empty] | Tar road, Cart track
56 | AP 29 | 29/0 | 4DD+0 | ok | 47.74 |  | 521.445 | 18153.405 | [7 empty] | 55.266 | 37° 36' 50"RT | 606.445 | 303.2225 | 127 | 139 | 266 | 128 | 150 | 278 | 85d2'38.97"E | 25d55'13.596"N | 304108.595 | 2868335.366 |  | BANAUTA MAKUND
[6 empty] | 351 | [23 empty] | 2No's Tar road, 11kV line, LT line
57 |  | 29/1 | 4DA+6 | ok | 54.16 |  |  | 18504.405 | [7 empty] | 55.739 |  | 773.029 | 386.5145 | 215 | 226 | 441 | 205 | 222 | 427 | 85d2'49.948"E | 25d55'7.983"N | 304411.534 | 2868158.084 |  | MUJAUNA
[6 empty] | 422.029 | [23 empty] | Tar road, Cart track, 11kV line
58 | AP 30 | 30/0 | 4DC+3 | ok | 50.74 |  | 773.029 | 18926.434 | [7 empty] | 55.605 | 15° 4' 15"LT | 806.115 | 403.0575 | 195 | 209 | 404 | 200 | 204 | 404 | 85d3'3.148"E | 25d55'1.234"N | 304775.776 | 2867944.926 |  | PATTI MUJAUNA
384.086
59 | AP 31 | 31/0 | 4DD+0 | ok | 47.74 |  | 384.086 | 19310.52 | [7 empty] | 55.154 | 53° 31' 11"LT | 750.237 | 375.1185 | 171 | 145 | 316 | 177 | 156 | 333 | 85d3'16.514"E | 25d54'58.127"N | 305146.309 | 2867843.797 |  | MUJAUNA
[6 empty] | 366.151 | [23 empty] | 4No's 11kV line, Tar road
60 | AP 32 | 32/0 | 4DB+6 | ok | 53.74 |  | 366.151 | 19676.671 | [7 empty] | 55.36 | 10° 20' 48"LT | 724.151 | 362.0755 | 218 | 180 | 398 | 207 | 180 | 387 | 85d3'26.723"E | 25d55'5.631"N | 305433.838 | 2868070.499 |  | PATTI MUJAUNA
[6 empty] | 358 | [23 empty] | 2No's 11kV lines
61 |  | 32/1 | 4DA+6 | ok | 54.16 |  |  | 20034.671 | [7 empty] | 55.063 |  | 762.497 | 381.2485 | 177 | 218 | 395 | 178 | 214 | 392 | 85d3'35.085"E | 25d55'14.47"N | 305670.584 | 2868339.042 |  | PATTI MUJAUNA
[6 empty] | 404.497 | [23 empty] | 3No's LT lines, 11kV lines, Cart track, Nala
62 | AP 33 | 33/0 | 4DD+3 | Hold | 50.74 |  | 762.497 | 20439.168 | [7 empty] | 55.392 | 39° 19' 42"RT | 743.659 | 371.8295 | 190 | 193 | 383 | 194 | 187 | 381 | 85d3'44.535"E | 25d55'24.456"N | 305938.079 | 2868642.463 |  | SULTANPUR
[6 empty] | 339.162 | [23 empty] | 11kV line, 2No's Nala, 2No's Cart track
63 | AP 34 | 34/0 | 4DD+0 | Hold | 47.74 |  | 339.162 | 20778.33 | [7 empty] | 55.177 | 57° 41' 28"RT | 339.162 | 169.581 | 153 | 182 | 335 | 160 | 182 | 342 | 85d3'56.532"E | 25d55'26.393"N | 306272.809 | 2868697.111 |  | ARIAEN
|  |  | Total length = |  |  | 20.7783 | Km
For KEC International Ltd | [18 empty] | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED, PATNA (WHOLLY OWNED SUBSIDIARY OF POWERGRID)
Surveyed By |  |  |  |  | Checked By |  |  |  | Submitted By | Submitted By | Submitted By | Submitted By | Submitted By | [5 empty] | Checked By |  |  |  |  | Recommended By | [5 empty] | Approved By
Structure Summary
[5 empty] | 4DA+0 | = | 16
[5 empty] | 4DA+3 | = | 5
[5 empty] | 4DA+6 | = | 6
[5 empty] | 4DA+9 | = | 1
[5 empty] | 4DB+0 | = | 3
[5 empty] | 4DB+3 | = | 3
[5 empty] | 4DB+6 | = | 2
[5 empty] | 4DB+9 | = | 0
[5 empty] | 4DC+0 | = | 4
[5 empty] | 4DC+3 | = | 1
[5 empty] | 4DC+6 | = | 2
[5 empty] | 4DC+9 | = | 0
[5 empty] | 4DD+0 | = | 11
[5 empty] | 4DD+18 | = | 2
[5 empty] | 4DD+25 | = | 1
[5 empty] | 4DD+3 | = | 4
[5 empty] | 4DD+6 | = | 1
[5 empty] | 4DD+9 | = | 1
[5 empty] | Total | = | 63

## DS 400 kV LO (hidden)
NAME OF LINE : LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) (Loop OUT)
Name of Client : BIHAR STATE POWER TRANSMISSION COMPANY LIMITED (BSPTCL)
Executing Agency : M/S KEC INTERNATIONAL LIMITED
NIT No. : 23/PR/BSPTCL/2023 | [31 empty] | W.O.TB 412
NOA No. : 18(Supply), 19(Service) Dated. 27.12.2023 | [31 empty] | DATE :01.10.2025 | DT :30.07.2020
Details Survey Report (AP 8 to AP 16) 1.731KM & (AP 22 to AP 33) 5.698KM & (AP 37 to AP 45) 5.194KM | [31 empty] | REV-00 | REV-02
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | HT of Tower (Mtr) | SPAN (Mtr) | CUMULATIVE SPAN | SECTION LENGTH | LEG EXTENSION |  |  |  | RAISED CHIMNEY | BENCHING VOLUME (Cum) | REVETMENT VOLUME (Cum) | R.L (Mtr) | DEVIATION ANGLE (Deg) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS | NAME OF VILLAGE | NAME OF TEHSIL | NAME OF POLICE STATION | REMARKS
[8 empty] | A | B | C | [8 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting (m) | Northing (m)
1 | AP 8 | 8/0 | 4DD+0 | 47.74 |  | 0 | 0 | [7 empty] | 53.046 | 48° 49' 53"LT | 346.902 | 90.6115 | 76 | 94 | 170 | 81 | 93 | 174 | 84d55'25.98"E | 25d53'38.769"N | 292012.814 | 2865602.532 |  | BASAUTA |  |  | TENTATIVE
[5 empty] | 181.223 | [23 empty] | LT Line, 11KV Line, Tar Road, Houses |  |  |  | House Available in 21.64 meter and 17.60 meter.
2 | AP 9 | 9/0 | 4DB+0 | 47.74 |  | 181.223 | 181.223 | [7 empty] | 52.928 | 7° 53' 54"LT | 387.175 | 193.5875 | 91 | 103 | 194 | 92 | 102 | 194 | 84d55'30.355"E | 25d53'43.129"N | 292136.71 | 2865734.787 |  | BASAUTA
[5 empty] | 205.952 | [23 empty] | 11KV Line, 33KV Line, Pond, 2No's Cart Track, Nala
3 | AP 10 | 10/0 | 4DD+0 | 47.74 |  | 387.175 | 205.952 | [7 empty] | 52.775 | 53° 51' 6"RT | 517.475 | 258.7375 | 100 | 154 | 254 | 101 | 153 | 254 | 84d55'34.527"E | 25d53'48.655"N | 292255.524 | 2865903.012 |  | UMARPUR
[5 empty] | 311.523 | [23 empty] | 2No's 11KV Lines. |  |  |  | 11kV Available in 11.07 meter.
4 | AP 11 | 11/0 | 4DD+0 | 47.74 |  | 698.698 | 311.523 | [7 empty] | 52.65 | 44° 45' 6"RT | 552.556 | 276.278 | 152 | 122 | 274 | 152 | 121 | 273 | 84d55'45.712"E | 25d53'48.977"N | 292567.007 | 2865907.99 |  | UMARPUR
[5 empty] | 241.033 | [23 empty] | LT Line, Pond, Tar Road
5 | AP 12 | 12/0 | 4DB+0 | 47.74 |  | 939.731 | 241.033 | [7 empty] | 52.358 | 6° 16' 34"LT | 371.732 | 185.866 | 116 | 59 | 175 | 118 | 64 | 182 | 84d55'52.051"E | 25d53'43.643"N | 292740.87 | 2865741.051 |  | HELA
[5 empty] | 130.699 | [23 empty] | LT Line, 33KV Line, Tar Road |  |  |  | LT Line Available in 17.48 meter.
6 | AP 13 | 13/0 | 4DD+0 | 47.74 |  | 1070.43 | 130.699 | [7 empty] | 52.759 | 43° 40' 22"LT | 449.524 | 224.762 | 75 | 161 | 236 | 70 | 161 | 231 | 84d55'55.817"E | 25d53'41.107"N | 292844.477 | 2865661.378 |  | HELA
[5 empty] | 318.825 | [23 empty] | LT Line, Tar Road, Cart Track, Poultry Farm, Hand Pump |  |  |  | Poultry Farm Available in 21.74 meter.
7 | AP 14 | 14/0 | 4DC+0 | 47.74 |  | 1389.255 | 318.825 | [7 empty] | 52.635 | 24° 18' 58"RT | 523.843 | 261.9215 | 159 | 104 | 263 | 160 | 104 | 264 | 84d56'7.184"E | 25d53'42.373"N | 293161.489 | 2865695.328 |  | ARNA
[5 empty] | 205.018 | [23 empty] | Cart Track
8 | AP 15 | 15/0 | 4DD+0 | 47.74 |  | 1594.273 | 205.018 | [7 empty] | 52.592 | 46° 36' 23"LT | 341.596 | 170.798 | 103 | -47 | 56 | 103 | 29 | 132 | 84d56'14.215"E | 25d53'40.392"N | 293356.247 | 2865631.282 |  | ARNA
[5 empty] | 136.578 | [23 empty] | LT Line, Tar Road
9 | AP 16 | 16/0 | 4DC+6 | 53.74 |  | 1730.851 | 136.578 | [7 empty] | 52.317 | 27° 22' 26"RT | 271.267 | 68.289 | 185 | -176 | 9 | 109 | -14 | 95 | 84d56'18.494"E | 25d53'42.563"N | 293476.384 | 2865696.248 |  | BARIARPUR |  |  | TENTATIVE
10 | AP 22 | 22/0 | 4DB+6 | 53.74 |  | 0 | 0 | [7 empty] | 52.901 | 4° 22' 25"RT | 614.39 | 126.706 | 159 | 184 | 343 | 166 | 158 | 324 | 84d57'8.444"E | 25d53'47.709"N | 294869.231 | 2865832.813 |  | BHELDI G.P. |  |  | TENTATIVE
253.412
11 | AP 23 | 23/0 | 4DB+0 | 47.74 |  | 253.412 | 253.412 | [7 empty] | 52.769 | 10° 6' 21"RT | 568.412 | 284.206 | 69 | 164 | 233 | 95 | 162 | 257 | 84d57'17.534"E | 25d53'47.262"N | 295122.024 | 2865815.115 |  | BHELDI G.P.
[5 empty] | 315 | [23 empty] | 2No's 11KV Lines, Cart Track, Houses |  |  |  | 11kV Available in 11.82 meter.
12 |  | 23/1 | 4DA+0 | 48.16 |  | 568.412 | [8 empty] | 51.823 |  | 612.881 | 306.4405 | 151 | 145 | 296 | 153 | 147 | 300 | 84d57'28.549"E | 25d53'44.922"N | 295427.519 | 2865738.319 |  | LANGARPURA
[5 empty] | 297.881 | [23 empty] | 6No's 11KV Lines, 33KV Line |  |  |  | 11kV Available in 19.27 meter.
13 | AP 24 | 24/0 | 4DD+0 | 47.74 |  | 866.293 | 612.881 | [7 empty] | 52.537 | 32° 37' 58"LT | 717.881 | 358.9405 | 155 | 184 | 339 | 154 | 193 | 347 | 84d57'38.966"E | 25d53'42.709"N | 295716.413 | 2865665.697 |  | LANGARPURA
[5 empty] | 420 | [23 empty] | Cart Track
14 |  | 24/1 | 4DA+6 | 54.16 |  | 1286.293 | [8 empty] | 51.901 |  | 776 | 388 | 238 | 213 | 451 | 231 | 203 | 434 | 84d57'53.196"E | 25d53'47.244"N | 296114.657 | 2865799.12 |  | LANGARPURA
[5 empty] | 356 | [23 empty] | LT Line, 11KV Line
15 |  | 24/2 | 4DA+0 | 48.16 |  | 1642.293 | [8 empty] | 52.107 |  | 714 | 357 | 144 | 176 | 320 | 154 | 177 | 331 | 84d58'5.257"E | 25d53'51.088"N | 296452.216 | 2865912.211 |  | PACHRUKHI
[5 empty] | 358 | [23 empty] | LT Line, Pond, 2No's Tar Road
16 |  | 24/3 | 4DA+0 | 48.16 |  | 2000.293 | [8 empty] | 52.613 |  | 675.518 | 337.759 | 182 | 157 | 339 | 182 | 158 | 340 | 84d58'17.387"E | 25d53'54.954"N | 296791.672 | 2866025.937 |  | PACHRUKHI
[5 empty] | 317.518 | [23 empty] | LT Line
17 | AP 25 | 25/0 | 4DD+0 | 47.74 |  | 2317.811 | 1451.518 | [7 empty] | 52.682 | 38° 17' 16"RT | 586.518 | 293.259 | 158 | 133 | 291 | 158 | 133 | 291 | 84d58'28.145"E | 25d53'58.382"N | 297092.743 | 2866126.804 |  | PACHRUKHI
[5 empty] | 269 | [23 empty] | 2No's LT Lines, 11KV Line, Hand Pump
18 |  | 25/1 | 4DA+0 | 48.16 |  | 2586.811 | [8 empty] | 52.67 |  | 509.129 | 254.5645 | 133 | 124 | 257 | 133 | 123 | 256 | 84d58'37.288"E | 25d53'55.554"N | 297345.895 | 2866035.836 |  | PACHRUKHI
[5 empty] | 240.129 | [23 empty] | 3No's LT Lines, Cart Track |  |  |  | 11kV Available in 1.22 meter.
19 | AP 26 | 26/0 | 4DC+0 | 47.74 |  | 2826.94 | 509.129 | [7 empty] | 52.387 | 25° 56' 57"LT | 591.129 | 295.5645 | 118 | 174 | 292 | 119 | 175 | 294 | 84d58'45.45"E | 25d53'53.029"N | 297571.877 | 2865954.631 |  | BANKERWA BHAW
[5 empty] | 351 | [23 empty] | LT Line |  |  |  | 11kV Available in 15.42 meter.
20 |  | 26/1 | 4DA+0 | 48.16 |  | 3177.94 | [8 empty] | 52.823 |  | 708.009 | 354.0045 | 179 | 160 | 339 | 179 | 166 | 345 | 84d58'57.963"E | 25d53'54.431"N | 297920.834 | 2865992.439 |  | BANKERWA BHAW
[5 empty] | 357.009 | [23 empty] | LT Line, Cart Track
21 | AP 27 | 27/0 | 4DB+3 | 50.74 |  | 3534.949 | 708.009 | [7 empty] | 52.839 | 14° 17' 42"RT | 754.814 | 377.407 | 196 | 218 | 414 | 191 | 213 | 404 | 84d59'10.691"E | 25d53'55.858"N | 298275.766 | 2866030.895 |  | BANKERWA BHAW
[5 empty] | 397.805 | [23 empty] | 11KV Line,Hand Pump |  |  |  | HandPump Available in 19.73 meter.
22 | AP 28 | 28/0 | 4DD+0 | 47.74 |  | 3932.754 | 397.805 | [7 empty] | 52.571 | 57° 18' 15"LT | 696.805 | 348.4025 | 184 | 106 | 290 | 189 | 121 | 310 | 84d59'24.868"E | 25d53'54.231"N | 298669.591 | 2865974.765 |  | BAKSANDA
[5 empty] | 299 | [23 empty] | Tar Road, Hand Pump
23 |  | 28/1 | 4DA+6 | 54.16 |  | 4231.754 | [8 empty] | 52.998 |  | 681.297 | 340.6485 | 197 | 207 | 404 | 183 | 202 | 385 | 84d59'31.762"E | 25d54'1.681"N | 298864.993 | 2866201.082 |  | BAKSANDA
[5 empty] | 382.297 | [23 empty] | 11KV Line, Tar Road
24 | AP 29 | 29/0 | 4DD+3 | 50.74 |  | 4614.051 | 681.297 | [7 empty] | 53.143 | 32° 6' 47"RT | 730.339 | 365.1695 | 174 | 190 | 364 | 180 | 185 | 365 | 84d59'40.577"E | 25d54'11.206"N | 299114.831 | 2866490.447 |  | BAKSANDA
348.042
25 | AP 30 | 30/0 | 4DD+0 | 47.74 |  | 4962.093 | 348.042 | [7 empty] | 53.66 | 41° 49' 34"LT | 626.587 | 313.2935 | 159 | 137 | 296 | 164 | 138 | 302 | 84d59'52.471"E | 25d54'14.692"N | 299447.524 | 2866592.667 |  | UTTIMPUR
[5 empty] | 278.545 | [23 empty] | 3No's 11KV Lines, Tar Road, Nala, House
26 | AP 31 | 31/0 | 4DD+0 | 47.74 |  | 5240.638 | 278.545 | [7 empty] | 53.92 | 56° 43' 6"RT | 492.502 | 246.251 | 141 | 101 | 242 | 140 | 104 | 244 | 84d59'57.508"E | 25d54'22.512"N | 299591.378 | 2866831.19 |  | LALAPUR
[5 empty] | 213.957 | [23 empty] | 11KV Lines |  |  |  | 11kV Line Available in 7.96 meter.
27 | AP 32 | 32/0 | 4DD+0 | 47.74 |  | 5454.595 | 213.957 |  |  |  |  | 1 |  |  | 53.379 | 42° 22' 50"LT | 457.68 | 228.84 | 112 | 131 | 243 | 109 | 127 | 236 | 85d0'5.183"E | 25d54'22.884"N | 299805.179 | 2866839.356 |  | LALAPUR |  |  | RC = 1M
[5 empty] | 243.723 | [23 empty] | 11KV Lines, 33KV Line, Tar Road |  |  |  | 11kV Line Available in 3.53 meter.
28 | AP 33 | 33/0 | 4DD+0 | 47.74 |  | 5698.318 | 243.723 | [7 empty] | 53.442 | 45° 21' 58"RT | 573.723 | 121.8615 | 113 | 161 | 274 | 117 | 163 | 280 | 85d0'11.327"E | 25d54'28.526"N | 299978.812 | 2867010.39 |  | SAGUNI |  |  | TENTATIVE
29 | AP 37 | 37/0 | 4DD+9 | 56.74 |  | 0 | 0 | [7 empty] | 52.973 | 56° 10' 21"LT | 786.096 | 192.5995 | 230 | 210 | 440 | 222 | 207 | 429 | 85d1'20.622"E | 25d54'33.088"N | 301909.493 | 2867121.549 |  | PARSA BAZAR (NP) |  |  | TENTATIVE
[5 empty] | 385.199 | [23 empty] | LT Line, 2No's 11KV Lines, Tar Road Pond, Cart Track
30 | AP 38 | 38/0 | 4DD+6 | 53.74 |  | 385.199 | 385.199 | [7 empty] | 53.235 | 33° 13' 52"LT | 763.669 | 381.8345 | 181 | 224 | 405 | 186 | 215 | 401 | 85d1'34.243"E | 25d54'35.301"N | 302289.608 | 2867183.924 |  | FATEHPUR
[5 empty] | 378.47 | [23 empty] | 3No's LT Lines, 11KV Line, Cart Track
31 | AP 39 | 39/0 | 4DB+0 | 47.74 |  | 763.669 | 378.47 | [7 empty] | 53.277 | 11° 2' 36"LT | 791.47 | 395.735 | 158 | 180 | 338 | 168 | 188 | 356 | 85d1'44.12"E | 25d54'43.752"N | 302568.422 | 2867439.858 |  | FATEHPUR
[5 empty] | 413 | [23 empty] | 2No's LT Lines, 11KV Line, Cart Track
32 |  | 39/1 | 4DA+6 | 54.16 |  | 1176.669 | [8 empty] | 52.687 |  | 799 | 399.5 | 234 | 212 | 446 | 227 | 207 | 434 | 85d1'52.747"E | 25d54'54.671"N | 302813.543 | 2867772.251 |  | FATEHPUR
[5 empty] | 386 | [23 empty] | 11KV Line
33 |  | 39/2 | 4DA+3 | 51.16 |  | 1562.669 | [8 empty] | 52.138 |  | 784 | 392 | 174 | 217 | 391 | 180 | 213 | 393 | 85d2'0.809"E | 25d55'4.876"N | 303042.638 | 2868082.914 |  | BANAUTA MAKUND
[5 empty] | 398 | [23 empty] | 11KV Line
34 |  | 39/3 | 4DA+0 | 48.16 |  | 1960.669 | [8 empty] | 51.659 |  | 799 | 399.5 | 181 | 181 | 362 | 186 | 187 | 373 | 85d2'9.123"E | 25d55'15.398"N | 303278.856 | 2868403.234 |  | BANAUTA MAKUND
[5 empty] | 401 | [23 empty] | Cart Track
35 |  | 39/4 | 4DA+3 | 51.16 |  | 2361.669 | [8 empty] | 52.432 |  | 768 | 384 | 220 | 183 | 403 | 215 | 183 | 398 | 85d2'17.5"E | 25d55'25.999"N | 303516.854 | 2868725.969 |  | ANJNI
[5 empty] | 367 | [23 empty] | LT Line, 11KV Line, Tar Road, Bore Pump
36 |  | 39/5 | 4DA+3 | 51.16 |  | 2728.669 | [8 empty] | 52.557 |  | 799.743 | 399.8715 | 184 | 199 | 383 | 184 | 204 | 388 | 85d2'25.167"E | 25d55'35.701"N | 303734.673 | 2869021.34 |  | BANAUTA
432.743
37 | AP 40 | 40/0 | 4DB+6 | 53.74 |  | 3161.412 | 2397.743 | [7 empty] | 53.261 | 8° 19' 26"LT | 769.82 | 384.91 | 235 | 209 | 444 | 230 | 196 | 426 | 85d2'34.208"E | 25d55'47.141"N | 303991.511 | 2869369.623 |  | BANAUTA
[5 empty] | 337.077 | [23 empty] | 11KV Line, 3No's Tar Road, Nala
38 | AP 41 | 41/0 | 4DC+0 | 47.74 |  | 3498.489 | 337.077 | [7 empty] | 52.931 | 21° 51' 59"RT | 652.077 | 326.0385 | 127 | 162 | 289 | 141 | 160 | 301 | 85d2'39.75"E | 25d55'56.88"N | 304150.189 | 2869667.016 |  | BANAUTA
[5 empty] | 315 | [23 empty] | LT Line
39 |  | 41/1 | 4DA+0 | 48.16 |  | 3813.489 | [8 empty] | 52.226 |  | 631.645 | 315.8225 | 152 | 157 | 309 | 154 | 157 | 311 | 85d2'48.305"E | 25d56'3.582"N | 304391.313 | 2869869.708 |  | BANAUTA
[5 empty] | 316.645 | [23 empty] | Pond
40 | AP 42 | 42/0 | 4DD+0 | 47.74 |  | 4130.134 | 631.645 | [7 empty] | 52.202 | 53° 20' 50"RT | 693.695 | 346.8475 | 156 | 164 | 320 | 157 | 170 | 327 | 85d2'56.905"E | 25d56'10.319"N | 304633.697 | 2870073.459 |  | BANAUTA
[5 empty] | 377.05 | [23 empty] | LT Line, Pond, Cart Track
41 | AP 43 | 43/0 | 4DD+3 | 50.74 |  | 4507.184 | 377.05 | [7 empty] | 52.964 | 55° 59' 58"RT | 723.153 | 361.5765 | 207 | 193 | 400 | 200 | 186 | 386 | 85d3'10.136"E | 25d56'7.679"N | 305000.64 | 2869986.742 |  | EKDERWA MASURIYA
[5 empty] | 346.103 | [23 empty] | Tar Road
42 | AP 44 | 44/0 | 4DD+0 | 47.74 |  | 4853.287 | 346.103 | [7 empty] | 52.769 | 35° 35' 57"LT | 686.983 | 343.4915 | 153 | 153 | 306 | 159 | 160 | 319 | 85d3'14.706"E | 25d55'57.22"N | 305123.003 | 2869662.991 |  | KOHRA
[5 empty] | 340.88 | [23 empty] | Pond, Tar Road, Bore Pump
43 | AP 45 | 45/0 | 4DD+3 | 50.74 |  | 5194.167 | 340.88 | [7 empty] | 53.027 | 56° 35' 11"LT | 679.806 | 170.44 | 194 | 173 | 367 | 188 | 174 | 362 | 85d3'24.997"E | 25d55'51.212"N | 305406.611 | 2869473.872 |  | KOHRA |  |  | TENTATIVE
|  |  | Total length = |  | 12.6233 | Km
For KEC International Ltd | [17 empty] | BIHAR STATE POWER TRANSMISSION COMPANY LIMITED, PATNA (WHOLLY OWNED SUBSIDIARY OF POWERGRID)
Surveyed By |  |  |  | Checked By |  |  |  | Submitted By | Submitted By | Submitted By | Submitted By | Submitted By | [5 empty] | Checked By |  |  |  |  | Recommended By | [5 empty] | Approved By
Structure Summary
|  |  |  | 4DA+0 | = | 7
|  |  |  | 4DA+3 | = | 3
|  |  |  | 4DA+6 | = | 3
|  |  |  | 4DA+9 | = | 0
|  |  |  | 4DB+0 | = | 4
|  |  |  | 4DB+3 | = | 1
|  |  |  | 4DB+6 | = | 2
|  |  |  | 4DB+9 | = | 0
|  |  |  | 4DC+0 | = | 3
|  |  |  | 4DC+3 | = | 0
|  |  |  | 4DC+6 | = | 1
|  |  |  | 4DC+9 | = | 0
|  |  |  | 4DD+0 | = | 14
|  |  |  | 4DD+18 | = | 0
|  |  |  | 4DD+25 | = | 0
|  |  |  | 4DD+3 | = | 3
|  |  |  | 4DD+6 | = | 1
|  |  |  | 4DD+9 | = | 1
|  |  |  | Total | = | 43

## Survey Report (hidden)
TB412 BSPTCL - Survey Status
Sl | Line Name | Activity |  | Length | Location | Remarks / Plan for completion
|  |  |  | km | Nos.
1 | LILO of 400 kv Barh (NTPC)- Motihari (DMTCL) D/C ( QUAD) Transmission line at Chhapra (New) | NOA | - | 40 | 122
|  | Route Alignment | Submitted | 41.27 | 127
|  |  | Approved | 41.27 | 127
|  | Detailed Survey | Completed | 41.27 | 127
|  |  | Submitted | 33.401 | 63 | Loop Out Detail survey 7.869 km PLS data Sended to KEC H.O For Profiling and Tower Shedule.
|  |  | Approved | 18.7 | 53
|  | Check Survey | Completed | 13.583 | 44 | Check Survey Under progress.
|  |  | Submitted | 0 | 0
|  |  | Approved | 0 | 0
2 | 220 KV D/C Chapra - Gopalganj Transmission Line with ACSR Zebra Conductor | NoA | - | 100 | 360
|  | Route Alignment | Submitted | 102.96 | 343
|  |  | Approved | 102.96 | 343
|  | Detailed Survey | Completed | 102.96 | 343
|  |  | Submitted | 20.11 | 67 | Balance Detail survey PLS data Sended to KEC H.O For Profiling and Tower Shedule.
|  |  | Approved | 20.11 | 67
|  | Check Survey | Completed | 20.11 | 67
|  |  | Submitted | 20.11 | 67
|  |  | Approved | 20.11 | 67
3 | Construction of 220 KV D/C Twin Moose Chhapra- Amnaur Transmission line- | NoA | - | 25 | 82
|  | Route Alignment | Submitted | 6.6 | 28
|  |  | Approved | 6.4 | 28 | 6.475 km Approved by Client, balance 0.200 km is hold due to both side gantry co-ordinate fixing.
|  | Detailed Survey | Completed | 6.6 | 29
|  |  | Submitted | 6.6 | 29
|  |  | Approved | 6.4 | 29
|  | Check Survey | Completed | 5.5 | 22
|  |  | Submitted | 5.5 | 22
|  |  | Approved | 5.5 | 22
TB412 BSPTCL - Survey Status
Sl | Line Name | Activity |  | Length | Location | Remarks / Plan for completion
|  |  |  | km | Nos.
1 | LILO of 400 kv Barh (NTPC)- Motihari (DMTCL) D/C ( QUAD) Transmission line at Chhapra (New) | NOA | - | 40 | 122
|  | Route Alignment | Submitted | 41.27 | 127
|  |  | Approved | 39.698 | 122 | 1.575KM Pendig at KEC HO Engineering
|  | Detailed Survey | Completed | 33.401 | 106 | Balanced Detail Survey Under progress
|  |  | Submitted | 33.401 | 106 | 12.623 km submitted to BSPSTL H.O. for approval from 04.11.2025
|  |  | Approved | 20.778 | 63
|  | Check Survey | Completed | 17.238 | 52 | Check Survey Under progress
|  |  | Submitted | 0 | 0
|  |  | Approved | 0 | 0
2 | 220 KV D/C Chapra - Gopalganj Transmission Line with ACSR Zebra Conductor | NOA | - | 100 | 360
|  | Route Alignment | Submitted | 102.96 | 343
|  |  | Approved | 102.96 | 343
|  | Detailed Survey | Completed | 101.442 | 343 | Under Progress
|  |  | Submitted | 92.862 | 315 | 72.752 km to be submitted to BSPTCL HO for approval from 17.11.2025
|  |  | Approved | 20.11 | 67
|  | Check Survey | Completed | 30.046 | 87
|  |  | Submitted | 18.54 | 63 | Check Survey Under progress
|  |  | Approved | 18.54 | 63
3 | Construction of 220 KV D/C Twin Moose Chhapra- Amnaur Transmission line- | NOA | - | 25 | 82
|  | Route Alignment | Submitted | 6.6 | 29
|  |  | Approved | 6.6 | 29
|  | Detailed Survey | Completed | 6.6 | 29
|  |  | Submitted | 6.475 | 27 | Submitted to KEC HO for Profiling
|  |  | Approved | 6.475 | 27
|  | Check Survey | Completed | 5.5 | 22
|  |  | Submitted | 5.5 | 22
|  |  | Approved | 5.5 | 22

## FDN
220 KV D/C Chapra -Gopalganj Transmission Line with ACSR Zebra Conductor
Sr | Location No. | Tower Type | Classification | Agency | DOS | DOC | Completion Month | Cumm. | Status | Remarks
163
1 | 14/1 | DA+0 | FS | Dharmendra Mishra | 2024-06-20 | 2024-06-23 | Jun'2024 | 1 | Completed
2 | 15/0 | DD+6 | FS | Dharmendra Mishra | 2024-07-01 | 2024-07-05 | Jul'2024 | 1 | Completed
3 | 17/0 | DD+3 | WET | Dharmendra Mishra | 2024-07-28 | 2024-08-03 | Aug'2024 | 4 | Completed
4 | 18/0 | DC+6 | WET | Dharmendra Mishra | 2024-08-02 | 2024-08-08 |  |  | Completed
5 | 17/1 | DA+6 | WET | Dharmendra Mishra | 2024-08-08 | 2024-08-13 |  |  | Completed
6 | 16/0 | DD+6 | WET | Dharmendra Mishra | 2024-08-17 | 2024-08-24 |  |  | Completed
7 | 40/0 | DC+0 | WET | Dharmendra Mishra | 2024-08-30 | 2024-09-04 | Sep'2024 | 4 | Completed
8 | 44/0 | DD+3 | WET | Dharmendra Mishra | 2024-09-16 | 2024-09-20 |  |  | Completed
9 | 14/0 | DC+3 | WET | Nav Durga Traders | 2024-09-18 | 2024-09-22 |  |  | Completed
10 | 13/1 | DA+6 | WET | Nav Durga Traders | 2024-09-21 | 2024-09-26 |  |  | Completed
11 | 38/0 | DB+6 | PS | Nav Durga Traders | 2024-10-02 | 2024-10-06 | Oct'2024 | 6 | Completed
12 | 13/2 | DA+9 | PS | Nav Durga Traders | 2024-10-07 | 2024-10-11 |  |  | Completed
13 | 19/0 | DD+6 | PS | Nav Durga Traders | 2024-10-13 | 2024-10-18 |  |  | Completed
14 | 18/1 | DA+6 | PS | Nav Durga Traders | 2024-10-19 | 2024-10-23 |  |  | Completed
15 | 37/0 | DC+3 | PS | Dharmendra Mishra | 2024-10-21 | 2024-10-26 |  |  | Completed
16 | 21/0 | DC+3 | PS | Navdurga Traders | 2024-10-28 | 2024-10-30 |  |  | Completed
17 | 97/2 | DA+3 | PS | Amit Srivastava | 2025-12-01 | 2025-12-02 | Dec'25 | 18 | Completed
18 | 98/0 | DC+3 | PS | Amit Srivastava | 2025-12-01 | 2025-12-04 |  |  | Completed
19 | 99/1 | DA+0 | PS | Amit Srivastava | 2025-12-04 | 2025-12-07 |  |  | Completed
20 | 35/0 | DD+0 | FS | Dharmendra Mishra | 2025-12-01 | 2025-12-08 |  |  | Completed
21 | 99/2 | DA+3 | PS | Amit Srivastava | 2025-12-07 | 2025-12-09 |  |  | Completed
22 | 99/0 | DC+3 | PS | Amit Srivastava | 2025-12-08 | 2025-12-11 |  |  | Completed
23 | 38/1 | DA+0 | WET | Dharmendra Mishra | 2025-12-09 | 2025-12-11 |  |  | Completed
24 | 99/3 | DA+6 | PS | Amit Srivastava | 2025-12-11 | 2025-12-14 |  |  | Completed
25 | 100/1 | DA+6 | PS | Amit Srivastava | 2025-12-14 | 2025-12-16 |  |  | Completed
26 | 100/3 | DA+3 | PS | Amit Srivastava | 2025-12-14 | 2025-12-18 |  |  | Completed
27 | 36/0 | DD+3 | FS | Dharmendra Mishra | 2025-12-11 | 2025-12-19 |  |  | Completed
28 | 100/4 | DA+3 | FS | Amit Srivastava | 2025-12-17 | 2025-12-20 |  |  | Completed
29 | 100/2 | DA+3 | PS | Amit Srivastava | 2025-12-19 | 2025-12-22 |  |  | Completed
30 | 101/1 | DA+0 | PS | Amit Srivastava | 2025-12-22 | 2025-12-25 |  |  | Completed
31 | 65/0 | DD+3 | FS | Dharmendra Mishra | 2025-12-21 | 2025-12-27 |  |  | Completed
32 | 66/2 | DA+3 | PS | Dharmendra Mishra | 2025-12-27 | 2025-12-30 |  |  | Completed
33 | 96/2 | DA+6 | ps | Amit Srivastava | 2025-12-28 | 2025-12-31 |  |  | Completed
34 | 96/1 | DA+6 | ps | Amit Srivastava | 2025-12-26 | 2025-12-29 |  |  | Completed
35 | 66/1 | DA+3 | PS | Dharmendra Mishra | 2025-12-30 | 2026-01-05 | Jan'26 | 8 | Completed
36 | 66/0 | DD+3 | FS | Dharmendra Mishra | 2026-01-04 | 2026-01-09 |  |  | Completed
37 | 82/0 | DD+9 | FS | Dharmendra Mishra | 2026-01-10 | 2026-01-15 |  |  | Completed
38 | 85/1 | DA+3 | PS | Dharmendra Mishra | 2026-01-16 | 2026-01-18 |  |  | Completed
39 | 116/4 | DA+9 | FS | Shakti Construction | 2026-01-22 | 2026-01-27 |  |  | Completed
40 | 116/3 | DA+3 | PS | Shakti Construction | 2026-01-27 | 2026-01-30 |  |  | Completed
41 | 83/0 | DD+3 | FS | Dharmendra Mishra | 2026-01-20 | 2026-01-31 |  |  | Completed
42 | 59/0 | DD+0 | PS | Maa Construction | 2026-01-27 | 2026-01-31 |  |  | Completed
43 | 117/1 | DA+9 | PS | Shakti Construction | 2026-01-27 | 2026-02-03 | Feb'26 | 30 | Completed
44 | 119/0 | DD+3 | FS | Shakti Construction | 2026-01-31 | 2026-02-05 |  |  | Completed
45 | 118/3 | DA+9 | PS | Shakti Construction | 2026-02-02 | 2026-02-05 |  |  | Completed
46 | 116/2 | DA+3 | PS | Shakti Construction | 2026-02-02 | 2026-02-07 |  |  | Completed
47 | 83/1 | DA+0 | FS | Dharmendra Mishra | 2026-02-02 | 2026-02-07 |  |  | Completed
48 | 115/0 | DD+3 | PS | Indra Contruction | 2026-01-27 | 2026-02-07 |  |  | Completed
49 | 55/1 | DA+3 | PS | Maa Construction | 2026-02-02 | 2026-02-08 |  |  | Completed
50 | 116/0 | DD+3 | PS | Shakti Construction | 2026-02-07 | 2026-02-09 |  |  | Completed
51 | 107/0 | DD+0 | FS | UKC | 2026-01-27 | 2026-02-10 |  |  | Completed
52 | 84/0 | DD+0 | FS | Dharmendra Mishra | 2026-02-05 | 2026-02-11 |  |  | Completed
53 | 114/1 | DA+3 | PS | Indra Contruction | 2026-02-05 | 2026-02-12 |  |  | Completed
54 | 107/1 | DA+3 | FS | UKC | 2026-02-10 | 2026-02-15 |  |  | Completed
55 | 55/0 | DD+0 | PS | Maa Construction | 2026-02-05 | 2026-02-15 |  |  | Completed
56 | 85/0 | DD+9 | FS | Dharmendra Mishra | 2026-02-12 | 2026-02-16 |  |  | Completed
57 | 115/1 | DA+6 | PS | Indra Contruction | 2026-02-05 | 2026-02-18 |  |  | Completed
58 | 131/0 | DB+3 | PS | Hetansh | 2026-02-08 | 2026-02-18 |  |  | Completed
59 | 133/0 | DD+6 | FS | Shakti Construction | 2026-02-12 | 2026-02-18 |  |  | Completed
60 | 54/3 | DA+0 | PS | Maa Construction | 2026-02-15 | 2026-02-19 |  |  | Completed
61 | 120/0 | DD+0 | PS | Shakti Construction | 2026-02-09 | 2026-02-20 |  |  | Completed
62 | 108/0 | DD+3 | PS | UKC | 2026-02-15 | 2026-02-21 |  |  | Completed
63 | 86/0 | DD+0 | FS | Dharmendra Mishra | 2026-02-08 | 2026-02-21 |  |  | Completed
64 | 117/0 | DC+0 | PS | Shakti Construction | 2026-02-20 | 2026-02-23 |  |  | Completed
65 | 56/0 | DC+0 | PS | Maa Construction | 2026-02-19 | 2026-02-23 |  |  | Completed
66 | 131/1 | DA+6 | PS | Hetansh | 2026-02-20 | 2026-02-23 |  |  | Completed
67 | 88/1 | DA+6 | PS | Dharmendra Mishra | 2026-02-21 | 2026-02-25 |  |  | Completed
68 | 118/0 | DC+3 | PS | Shakti Construction | 2026-02-23 | 2026-02-25 |  |  | Completed
69 | 100/0 | DC+0 | PS | UKC | 2026-02-20 | 2026-02-26 |  |  | Completed
70 | 131/2 | DA+3 | PS | Hetansh | 2026-02-23 | 2026-02-27 |  |  | Completed
71 | 89/0 | DB+0 | PS | Dharmendra Mishra | 2026-02-25 | 2026-02-28 |  |  | Completed
72 | 58/0 | DC+0 | FS | Maa Construction | 2026-02-23 | 2026-02-28 |  |  | Completed
73 | 101/0 | DC+0 | PS | UKC | 2026-02-27 | 2026-03-03 | Mar'26 | 24 | Completed
74 | 136/2 | DA+6 | PS | Hetansh | 2026-02-27 | 2026-03-03 |  |  | Completed
75 | 88/0 | DC+3 | FS | Dharmendra Mishra | 2026-02-27 | 2026-03-03 |  |  | Completed
76 | 87/2 | DA+6 | FS | Dharmendra Mishra | 2026-03-08 | 2026-03-12 |  |  | Completed
77 | 54/2 | DA+6 | PS | Maa Construction | 2026-03-08 | 2026-03-12 |  |  | Completed
78 | 87/1 | DA+3 | PS | Dharmendra Mishra | 2026-03-12 | 2026-03-15 |  |  | Completed
79 | 59/2 | DA+3 | FS | Maa Construction | 2026-03-13 | 2026-03-16 |  |  | Completed
80 | 118/2 | DA+9 | PS | Shakti Construction | 2026-03-13 | 2026-03-16 |  |  | Completed
81 | 101/2 | DA+0 | FS | UKC | 2026-03-10 | 2026-03-19 |  |  | Completed
82 | 59/3 | DA+6 | FS | Maa Construction | 2026-03-13 | 2026-03-19 |  |  | Completed
83 | 132/0 | DC+3 | FS | Hetansh | 2026-03-10 | 2026-03-20 |  |  | Completed
84 | 87/0 | DD+3 | FS | Dharmendra Mishra | 2026-03-15 | 2026-03-22 |  |  | Completed
85 | 114/0 | DC+3 (1MRC) | FS | Shakti Construction | 2026-03-18 | 2026-03-22 |  |  | Completed
86 | 59/1 | DA+3 | FS | Maa Construction | 2026-03-19 | 2026-03-22 |  |  | Completed
87 | 150/1 | DA+3 | PS | AR Construction | 2026-03-15 | 2026-03-23 |  |  | Completed
88 | 113/3 | DA+0 (1MRC) | PS | Shakti Construction | 2026-03-31 | 2026-03-24 |  |  | Completed
89 | 101/4 | DA+3 | FS | UKC | 2026-03-19 | 2026-03-25 |  |  | Completed
90 | 60/0 | DB+3 | FS | Maa Construction | 2026-03-22 | 2026-03-26 |  |  | Completed
91 | 113/2 | DA+6 (1MRC) | PS | Shakti Construction | 2026-03-24 | 2026-03-27 |  |  | Completed
92 | 150/0 | DD+0 | PS | AR Construction | 2026-03-22 | 2026-03-29 |  |  | Completed
93 | 113/0 | DD+3 (1MRC) | FS | Shakti Construction | 2026-03-24 | 2026-03-30 |  |  | Completed
94 | 59/4 | DA+6 (1MRC) | FS | Maa Construction | 2026-03-26 | 2026-03-31 |  |  | Completed
95 | 137/0 | DD+0 | FS | Hetansh | 2026-03-23 | 2026-03-31 |  |  | Completed
96 | 110/2 | DA+3 | FS | Shakti Construction | 2026-03-24 | 2026-03-31 |  |  | Completed
97 | 152/2 | DA+6 | PS | AR Construction | 2026-03-31 | 2026-04-03 | Apr'26 | 33 | Completed
98 | 59/5 | DA+0 1MRC | FS | Maa Construction | 2026-03-30 | 2026-04-03 |  |  | Completed
99 | 101/3 | DA+0 1MRC | FS | UKC | 2026-04-01 | 2026-04-05 |  |  | Completed
100 | 134/0 | DC+9 | PS | Hetansh | 2026-03-22 | 2026-04-05 |  |  | Completed
101 | 58/1 | DA+3 1MRC | FS | Maa Construction | 2026-04-03 | 2026-04-08 |  |  | Completed
102 | 113/1 | DA+6 1MRC | PS | Shakti Construction | 2026-04-06 | 2026-04-08 |  |  | Completed
103 | 153/0 | DD+18 | PS | AR Construction | 2026-04-03 | 2026-04-09 |  |  | Completed
104 | 111/0 | DD+6 1MRC | FS | Shakti Construction | 2026-04-07 | 2026-04-12 |  |  | Completed
105 | 67/0 | DC+3 | FS | Maa Construction | 2026-04-08 | 2026-04-12 |  |  | Completed
106 | 133/2 | DA+3 | PS | Hetansh | 2026-04-10 | 2026-04-12 |  |  | Completed
107 | 81/1 | DA+3 1MRC | FS | Exel Power | 2026-04-03 | 2026-04-13 |  |  | Completed
108 | 102/1 | DA+3 1MRC | FS | UKC | 2026-04-06 | 2026-04-13 |  |  | Completed
109 | 120/1 | DA+6 | FS | Shakti Construction | 2026-04-12 | 2026-04-14 |  |  | Completed
110 | 133/1 | DA+3 | FS | Hetansh | 2026-04-12 | 2026-04-15 |  |  | Completed
111 | 54/0 | DD+3 1MRC | FS | Maa Construction | 2026-04-11 | 2026-04-16 |  |  | Completed
112 | 81/0 | DC+0 1MRC | FS | Exel Power | 2026-04-13 | 2026-04-16 |  |  | Completed
113 | 154/0 | DD+18 | FS | AR Construction | 2026-04-09 | 2026-04-17 |  |  | Completed
114 | 123/0 | DC+9 | FS | Shakti Construction | 2026-04-13 | 2026-04-19 |  |  | Completed
115 | 102/4 | DA+6 1MRC | PS | UKC | 2026-04-12 | 2026-04-19 |  |  | Completed
116 | 136/1 | DA+3 | FS | Hetansh | 2026-04-15 | 2026-04-20 |  |  | Completed
117 | 123/1 | DA+6 | FS | Shakti Construction | 2026-04-18 | 2026-04-20 |  |  | Completed
118 | 152/3 | DA+6 | PS | AR Construction | 2026-04-17 | 2026-04-23 |  |  | Completed
119 | 54/1 | DA+3 1MRC | FS | Maa Construction | 2026-04-18 | 2026-04-25 |  |  | Completed
120 | 124/0 | DC+0 | FS | Shakti Construction | 2026-04-20 | 2026-04-25 |  |  | Completed
121 | 102/3 | DA+3 1MRC | FS | UKC | 2026-04-12 | 2026-04-26 |  |  | Completed
122 | 135/0 | DD+9 | PS | Hetansh | 2026-04-20 | 2026-04-26 |  |  | Completed
123 | 122/0 | DD+25 | FS | Shakti Construction | 2026-04-23 | 2026-04-26 |  |  | Completed
124 | 154/1 | DA+6 | PS | AR Construction | 2026-04-23 | 2026-04-28 |  |  | Completed
125 | 121/0 | DD+18 | FS | Shakti Construction | 2026-04-23 | 2026-04-29 |  |  | Completed
126 | 64/0 | DD+3 | FS | Maa Construction | 2026-04-25 | 2026-04-29 |  |  | Completed
127 | 132/6 | DA+3 | FS | Hetansh | 2026-04-26 | 2026-04-29 |  |  | Completed
128 | 105/0 | DC+6 | FS | Anmol | 2026-04-18 | 2026-04-30 |  |  | Completed
129 | 102/2 | DA+6 1MRC | FS | UKC | 2026-04-26 | 2026-04-30 |  |  | Completed
130 | 132/5 | DA+3 | FS | Hetansh | 2026-04-28 | 2026-05-02 | May'2026 | 34 | Completed
131 | 64/1 | DA+0 | FS | Maa Construction | 2026-04-28 | 2026-05-03 |  |  | Completed
132 | 111A/0 | DD+18 1MRC | FS | Shakti Construction | 2026-04-30 | 2026-05-05 |  |  | Completed
133 | 80/3 | DA+3 1MRC | FS | Exel Power | 2026-04-18 | 2026-05-08 |  |  | Completed
134 | 154/2 | DA+3 | PS | AR Construction | 2026-04-23 | 2026-05-10 |  |  | Completed
135 | 112/0 | DD+18 1MRC | FS | Shakti Construction | 2026-05-05 | 2026-05-12 |  |  | Completed
136 | 105/1 | DA+3 | FS | Anmol | 2026-04-30 | 2026-05-12 |  |  | Completed
137 | 64/2 | DA+0 | FS | Maa Construction | 2026-04-28 | 2026-05-12 |  |  | Completed
138 | 116/1 | DA+3 | PS | Shakti Construction | 2026-05-05 | 2026-05-13 |  |  | Completed
139 | 154/3 | DA+0 | FS | AR Construction | 2026-05-11 | 2026-05-14 |  |  | Completed
140 | 104/0 | DD+0 | PS | UKC | 2026-04-30 | 2026-05-14 |  |  | Completed
141 | 132/4 | DA+9 | FS | Hetansh | 2026-04-28 | 2026-05-15 |  |  | Completed
142 | 63/2 | DA+3 | FS | Maa Construction | 2026-05-15 | 2026-05-18 |  |  | Completed
143 | 132/3 | DA+6 | FS | Hetansh | 2026-04-28 | 2026-05-18 |  |  | Completed
144 | 152/1 | DA+3 | PS | AR Construction | 2026-05-16 | 2026-05-18 |  |  | Completed
145 | 106/1 | DA+0 | PS | Construction Wala | 2026-05-13 | 2026-05-20 |  |  | Completed
146 | 63/1 | DA+3 | FS | Maa Construction | 2026-05-18 | 2026-05-21 |  |  | Completed
147 | 103/0 | DD+9 1MRC | PS | UKC | 2026-04-30 | 2026-05-21 |  |  | Completed
148 | 139/0 | DD+25 | FS | Shakti Construction | 2026-05-15 | 2026-05-22 |  |  | Completed
149 | 132/1 | DA+3 | FS | Hetansh | 2026-05-20 | 2026-05-23 |  |  | Completed
150 | 104/4 | DA+0 1MRC | FS | Anmol | 2026-05-13 | 2026-05-24 |  |  | Completed
151 | 106/3 | DA+0 1MRC | FS | Construction Wala | 2026-04-24 | 2026-05-24 |  |  | Completed
152 | 63/0 | DD+0 | FS | Maa Construction | 2026-05-18 | 2026-05-24 |  |  | Completed
153 | 152/0 | DC+3 | PS | AR Construction | 2026-05-22 | 2026-05-26 |  |  | Completed
154 | 142/0 | DD+25 | FS | Shakti Construction | 2026-05-25 | 2026-05-27 |  |  | Completed
155 | 130/0 | DC+9 | FS | Hetansh | 2026-05-20 | 2026-05-27 |  |  | Completed
156 | 106/2 | DA+0 1MRC | FS | Construction Wala | 2026-04-24 | 2026-05-30 |  |  | Completed
157 | 62/2 | DA+6 | FS | Maa Construction | 2026-05-26 | 2026-05-30 |  |  | Completed
158 | 80/1 | DA+0 1MRC | FS | Tarush Projects | 2026-05-16 | 2026-05-31 |  |  | Completed
159 | 142/1 | DB+3 | FS | Shakti Construction | 2026-05-26 | 2026-05-31 |  |  | Completed
160 | 62A/0 | DB+3 | FS | Maa Construction | 2026-05-26 | 2026-05-31 |  |  | Completed
161 | 104/5 | DA+3 | FS | Anmol | 2026-05-23 | 2026-05-31 |  |  | Completed
162 | 102/0 | DC+0 1MRC | FS | Construction Wala | 2026-05-28 | 2026-05-31 |  |  | Completed
163 | 145/1 | DA+0 | PS | Shakti Construction | 2026-05-28 | 2026-05-31 |  |  | Completed
220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose
Sr | Location No. | Tower Type | Classification | Agency | DOS | DOC | Completion Month | Cumm. | Status | Remarks
21
1 | 7/1 | DA+0 | WET | Nav Durga Traders | 2025-09-09 | 2025-09-18 | Sep'25 | 2 | completed
2 | 6/1 | DA+3 | WET | Nav Durga Traders | 2025-09-18 | 2025-09-23 |  |  | Completed
3 | 8/2 | 2TDA+6 | WET | Nav Durga Traders-1 | 2025-11-07 | 2025-11-11 | Nov'25 | 5 | Completed
4 | 7/0 | 2TDD+0 | WET | Nav Durga Traders-1 | 2025-11-09 | 2025-11-16 |  |  | Completed
5 | 8/1 | 2TDA+3 | WET | Nav Durga Traders-1 | 2025-11-16 | 2025-11-20 |  |  | Completed
6 | 10/2 | 2TDA+3 | PS | Nav Durga Traders-1 | 2025-11-16 | 2025-11-24 |  |  | Completed
7 | 10/0 | 2TDD+0 | PS | Nav Durga Traders-1 | 2025-11-24 | 2025-11-30 |  |  | Completed
8 | 10/1 | 2TDA+3 | PS | Nav Durga Traders-1 | 2025-12-01 | 2025-12-03 | Dec'25 | 5 | Completed
9 | 11/1 | 2TDA+3 | PS | Nav Durga Traders-1 | 2025-12-03 | 2025-12-07 |  |  | Completed
10 | 11/2 | DA+3 | PS | Nav Durga Traders-1 | 2025-12-07 | 2025-12-11 |  |  | Completed
11 | 11/4 | 2TDA+0 | PS | Nav Durga Traders-1 | 2025-12-11 | 2025-12-15 |  |  | Completed
12 | 11/3 | 2TDA+0 | PS | Nav Durga Traders-1 | 2025-12-15 | 2025-12-24 |  |  | Completed
13 | 9/0 | DC+6 | PS | Nav Durga Traders-1 | 2026-04-13 | 2026-04-25 | 2026-04-01 | 3 | Completed
14 | 8/0 | 2TDC+0 | WET | Nav Durga Traders-1 | 2026-04-25 | 2026-04-30 |  |  | Completed
15 | 11/0 | 2TDC+0 | PS | AR | 2026-04-20 | 2026-04-30 |  |  | Completed
16 | 3/1 | 2TDD+9 | PS | Nav Durga Traders | 2026-04-28 | 2026-05-06 | May'26 | 6 | Completed
17 | 13/0 | DD+18 | FS | Nav Durga Traders | 2026-05-06 | 2026-05-13 |  |  | Completed
18 | 14/0 | DD+25 | PS | Nav Durga Traders | 2026-05-16 | 2026-05-23 |  |  | Completed
19 | 3/0 | 2TNMD+0 | FS | Nav Durga Traders | 2026-05-14 | 2026-05-28 |  |  | Completed
20 | 2/0 | 2TNMD+0 | FS | Nav Durga Traders | 2026-05-25 | 2026-05-31 |  |  | Completed
21 | 6/0 | DC+0 | PS | Nav Durga Traders | 2026-05-26 | 2026-05-31 |  |  | Completed
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN & LOOP OUT
Sr | Location No. | Tower Type | Classification | Agency | DOS | DOC | Completion Month | Cumm. | Status | Remarks
80
1 | 30/0 | 4DC+3 | PS | Nav Durga Traders | 2025-11-04 | 2025-11-30 | Nov'25 | 1 | Completed | LOOP IN
2 | 31/0 | 4DD+0 | PS | Navdurga Traders-1 | 2025-12-01 | 2025-12-12 | Dec'25 | 9 | Completed | LOOP IN
3 | 18/2 | 4DA+6 | PS | Rajeshwar Singh | 2025-12-04 | 2025-12-12 |  |  | Completed | LOOP IN
4 | 27/4 | 4DA+0 | PS | Navdurga Traders-1 | 2025-12-10 | 2025-12-15 |  |  | Completed | LOOP IN
5 | 19/2 | 4DA+0 | PS | Rajeshwar Singh | 2025-12-12 | 2025-12-17 |  |  | Completed | LOOP IN
6 | 29/1 | 4DA+6 | PS | Navdurga Traders-1 | 2025-12-12 | 2025-12-19 |  |  | Completed | LOOP IN
7 | 19/4 | 4DA+0 | PS | Navdurga Traders-2 | 2025-12-16 | 2025-12-23 |  |  | Completed | LOOP IN
8 | 19/1 | DA+0 | PS | Nav Durga Traders | 2025-12-23 | 2025-12-28 |  |  | Completed | LOOP IN
9 | 28/0 | DD+3 | PS | Nav Durga Traders | 2025-12-16 | 2024-12-24 |  |  | Completed | LOOP IN
10 | 32/0 | DB+6 | FS | Nav Durga Traders | 2025-12-20 | 2025-12-30 |  |  | Completed | LOOP IN
11 | 28/1 | DA+0 | PS | Nav Durga Traders | 2025-12-29 | 2026-01-05 | Jan'26 | 15 | Completed | LOOP IN
12 | 19/0 | DB+3 | PS | Rajeshwar Singh | 2025-12-27 | 2026-01-05 |  |  | Completed | LOOP IN
13 | 29/0 | DD+0 | PS | Nav Durga Traders | 2025-12-27 | 2026-01-06 |  |  | Completed | LOOP IN
14 | 18/1 | DA+3 | PS | Raajeshwar Singh | 2026-01-05 | 2026-01-10 |  |  | Completed | LOOP IN
15 | 32/1 | DA+6 | FS | Nav Durga Traders | 2026-01-06 | 2026-01-12 |  |  | Completed | LOOP IN
16 | 11/2 | DA+0 | PS | Rajeshwar Singh | 2026-01-08 | 2026-01-15 |  |  | Completed | LOOP IN
17 | 27/0 | DB+3 | PS | Nav Durga Traders | 2026-01-09 | 2026-01-15 |  |  | Completed | LOOP IN
18 | 28/1 | DA+6 | PS | Nav Durga Traders | 2026-01-15 | 2026-01-22 |  |  | Completed | LOOP OUT
19 | 40/0 | DB+6 | PS | Nav Durga Traders | 2026-01-15 | 2026-01-22 |  |  | Completed | LOOP OUT
20 | 18/0 | DC+6 | PS | Raajeshwar Singh | 2026-01-14 | 2026-01-23 |  |  | Completed | LOOP IN
21 | 25/0 | DD+0 | PS | Nav Durga Traders | 2026-01-10 | 2026-01-25 |  |  | Completed | LOOP IN
22 | 27/0 | DB+3 | PS | Nav Durga Traders | 2026-01-22 | 2026-01-28 |  |  | Completed | LOOP OUT
23 | 24/1 | DA+6 | FS | Raajeshwar Singh | 2026-01-23 | 2026-01-28 |  |  | Completed | LOOP OUT
24 | 29/0 | DD+3 | PS | Nav Durga Traders | 2026-01-22 | 2026-01-31 |  |  | Completed | LOOP OUT
25 | 24/0 | 4DD+3 | PS | Nav Durga Traders | 2026-01-27 | 2026-01-31 |  |  | Completed | LOOP IN | l
26 | 24/2 | DA+0 | FS | Raajeshwar Singh | 2026-01-28 | 2026-02-03 | 2026-02-01 | 12 | Completed | LOOP OUT
27 | 24/3 | DA+0 | FS | Raajeshwar Singh | 2026-02-03 | 2026-02-07 |  |  | Completed | LOOP OUT
28 | 41/0 | DC+0 | FS | Nav Durga Traders | 2026-01-23 | 2026-02-09 |  |  | Completed | LOOP OUT
29 | 34/1 | DA+9 | FS | Nav Durga Traders | 2026-02-09 | 2026-02-14 |  |  | Completed | LOOP OUT
30 | 30/0 | DD+0 | WET | Nav Durga Traders | 2026-01-31 | 2026-02-16 |  |  | Completed | LOOP OUT
31 | 39/3 | DA+0 | FS | Nav Durga Traders | 2026-02-10 | 2026-02-17 |  |  | Completed | LOOP OUT
32 | 24/0 | DD+0 | FS | Raajeshwar Singh | 2026-02-08 | 2026-02-20 |  |  | Completed | LOOP OUT
33 | 25/1 | DA+0 | FS | Raajeshwar Singh | 2026-02-20 | 2026-02-24 |  |  | Completed | LOOP OUT | l
34 | 34/0 | DD+3 | PS | Nav Durga Traders | 2026-02-17 | 2026-02-24 |  |  | Completed | LOOP OUT
35 | 28/0 | DD+0 | PS | Nav Durga Traders | 2026-01-31 | 2026-02-28 |  |  | Completed | LOOP OUT
36 | 31/0 | DD+0 | PS | Nav Durga Traders | 2026-02-17 | 2026-02-28 |  |  | Completed | LOOP OUT
37 | 41/1 | DA+0 | FS | Nav Durga Traders | 2026-02-18 | 2026-02-28 |  |  | Completed | LOOP OUT
38 | 9/0 | DC+0 | PS | Kutir Vihar | 2026-02-28 | 2026-03-09 | Mar'26 | 8 | Completed | LOOP IN | l
39 | 36/0 | DD+0 | PS | Nav Durga Traders | 2026-02-28 | 18-03-206 |  |  | Completed | LOOP OUT
40 | 10/0 | DB+0 | PS | Kutir Vihar | 2026-03-09 | 19-03-206 |  |  | Completed | LOOP IN
41 | 25/0 | DD+0 | FS | Raajeshwar Singh | 2026-03-08 | 22-03-206 |  |  | Completed | LOOP OUT
42 | 35/0 | DD+3 | PS | Nav Durga Traders | 2026-03-15 | 23-03-206 |  |  | Completed | LOOP OUT
43 | 26/0 | 4DC+0 | FS | Raajeshwar Singh | 2026-03-22 | 2026-03-29 |  |  | Completed | LOOP OUT
44 | 11/0 | DD+0 | PS | Kutir Vihar | 2026-03-14 | 2026-03-31 |  |  | Completed | LOOP IN
45 | 22/0 | DD+3 | FS | Nav Durga Traders | 2026-03-19 | 2026-03-31 |  |  | Completed | LOOP IN
46 | 26/1 | DA+0 | PS | Raajeshwar Singh | 2026-03-29 | 2026-04-01 | Apr'26 | 18 | Completed | LOOP OUT
47 | 42/0 | 4DD+0 | FS | Dharmendra Mishra | 2026-03-12 | 2026-04-03 |  |  | Completed | LOOP OUT | l
48 | 43/0 | DD+3 | FS | Nav Durga Traders | 2026-03-19 | 2026-04-04 |  |  | Completed | LOOP OUT
49 | 21/0 | DB+6 | FS | Nav Durga Traders | 2026-03-19 | 2026-04-05 |  |  | Completed | LOOP IN
50 | 23/0 | DB+0 | PS | Raajeshwar Singh | 2026-04-01 | 2026-04-07 |  |  | Completed | LOOP OUT
51 | 33/0 | 4DD+0 | PS | Nav Durga Traders | 2026-04-05 | 2026-04-11 |  |  | Completed | LOOP OUT
52 | 26/2 | DA+6 | PS | Nav Durga Traders | 2026-04-05 | 2026-04-13 |  |  | Completed | LOOP IN
53 | 22/0 | DB+6 | PS | Raajeshwar Singh | 2026-04-07 | 2026-04-13 |  |  | Completed | LOOP OUT
54 | 20/0 | 4DD+0 | PS | Dharmendra Mishra | 2026-04-04 | 2026-04-14 |  |  | Completed | LOOP OUT
55 | 23/1 | DA+0 | PS | Raajeshwar Singh | 2026-04-13 | 2026-04-17 |  |  | Completed | LOOP OUT | l
56 | 44/0 | DD+0 | FS | Nav Durga Traders | 2026-04-13 | 2026-04-18 |  |  | Completed | LOOP OUT | l
57 | 11/1 | DA+0 | PS | Dharmendra Mishra | 2026-04-14 | 2026-04-20 |  |  | Completed | LOOP IN
58 | 38/0 | DD+6 | FS | Nav Durga Traders | 2026-04-13 | 2026-04-25 |  |  | Completed | LOOP OUT
59 | 11/3 | DA+0 | PS | Dharmendra Mishra | 2026-04-20 | 2026-04-25 |  |  | Completed | LOOP IN | l
60 | 33/1 | DA+0 | PS | Nav Durga Traders | 2026-04-13 | 2026-04-26 |  |  | Completed | LOOP OUT
61 | 19/3 | DA+0 | PS | Raajeshwar Singh | 2026-04-17 | 2026-04-27 |  |  | Completed | LOOP IN
62 | 12/1 | DA+9 | WET | Dharmendra Mishra | 2026-04-25 | 2026-04-28 |  |  | Completed | LOOP IN
63 | 39/1 | DA+6 | FS | Nav Durga Traders | 2026-04-25 | 2026-04-28 |  |  | Completed | LOOP OUT
64 | 39/2 | DA+3 | FS | Nav Durga Traders | 2026-04-25 | 2026-04-30 |  |  | Completed | LOOP OUT
65 | 21/0 | DC+9 | PS | Raajeshwar Singh | 2026-04-28 | 2026-04-30 |  |  | Completed | LOOP OUT
66 | 39/4 | DA+3 | FS | Nav Durga Traders | 2026-04-28 | 2026-05-03 | May'26 | 15 | Completed | LOOP OUT
67 | 25/1 | DA+3 | PS | Dharmendra | 2026-04-28 | 2026-05-03 |  |  | Completed | LOOP IN
68 | 39/5 | DA+3 | FS | Nav Durga Traders | 2026-04-28 | 2026-05-05 |  |  | Completed | LOOP OUT
69 | 26/1 | DA+3 | PS | Dharmendra | 2026-05-04 | 2026-05-08 |  |  | Completed | LOOP IN
70 | 37/0 | DD+9 | FS | Nav Durga Traders | 2026-05-06 | 2026-05-13 |  |  | Completed | LOOP OUT
71 | 27/3 | DA+0 | PS | Dharmendra | 2026-05-04 | 2026-05-13 |  |  | Completed | LOOP IN
72 | 45/0 | DD+3 | FS | Nav Durga Traders | 2026-05-06 | 2026-05-19 |  |  | Completed | LOOP OUT
73 | 20/1 | DA+6 | FS | Nav Durga Traders | 2026-05-18 | 2026-05-21 |  |  | Completed | LOOP IN
74 | 4/0 | DB+3 | PS | Dharmendra | 2026-05-13 | 2026-05-22 |  |  | Completed | LOOP OUT
75 | 19/0 | DC+0 | PS | Rajeshwar Singh | 2026-05-11 | 2026-05-23 |  |  | Completed | LOOP OUT
76 | 8/0 | DB+0 | PS | AR | 2026-05-16 | 2026-05-25 |  |  | Completed | LOOP IN
77 | 27/2 | DA+0 | PS | Nav Durga Traders | 2026-05-23 | 2026-05-31 |  |  | Completed | LOOP IN
78 | 7/1 | DA+0 | PS | Dharmendra | 2026-05-23 | 2026-05-31 |  |  | Completed | LOOP IN
79 | 18A/0 | DD+3 | PS | Rajeshwar Singh | 2026-05-25 | 2026-05-31 |  |  | Completed | LOOP OUT
80 | 7/2 | DA+0 | PS | AR | 2026-05-25 | 2026-05-31 |  |  | Completed | LOOP IN
Formulas:
DOS = [DOC, row above]
DOS = [DOS, row above]
DOC = [DOC, row above]+3
DOC = [DOS]+3

## Earthing Pending (hidden)
220 kV Chhapra-Gopalganj TL
SL No. | Location No. | TOT | Clasification | Sub contractor | FDN Comp Date
1 | 108/0 | DD+3 | PS | UKC | 2026-02-21
2 | 100/0 | DC+0 | PS | UKC | 2026-02-26
3 | 87/0 | DD+3 | FS | Dharmendra Mishra | 2026-03-22
4 | 113/0 | DD+3 (1MRC) | FS | Shakti Construction | 2026-03-30
5 | 110/2 | DA+3 | FS | Shakti Construction | 2026-03-31
6 | 113/1 | DA+6 1MRC | PS | Shakti Construction | 2026-04-08
7 | 153/0 | DD+18 | PS | AR Construction | 2026-04-09
8 | 133/2 | DA+3 | PS | Hetansh | 2026-04-12
9 | 102/1 | DA+3 1MRC | FS | UKC | 2026-04-13
10 | 120/1 | DA+6 | FS | Shakti Construction | 2026-04-14
11 | 133/1 | DA+3 | FS | Hetansh | 2026-04-15
12 | 54/0 | DD+3 1MRC | FS | Maa Construction | 2026-04-16
13 | 154/0 | DD+18 | FS | AR Construction | 2026-04-17
14 | 102/4 | DA+6 1MRC | PS | UKC | 2026-04-19
15 | 136/1 | DA+3 | FS | Hetansh | 2026-04-20
16 | 152/3 | DA+6 | PS | AR Construction | 2026-04-23
17 | 54/1 | DA+3 1MRC | FS | Maa Construction | 2026-04-25
18 | 102/3 | DA+3 1MRC | FS | UKC | 2026-04-26
19 | 135/0 | DD+9 | PS | Hetansh | 2026-04-26
20 | 154/1 | DA+6 | PS | AR Construction | 2026-04-28
21 | 64/0 | DD+3 | FS | Maa Construction | 2026-04-29
22 | 132/6 | DA+3 | FS | Hetansh | 2026-04-29
23 | 105/0 | DC+6 | FS | Anmol | 2026-04-30
24 | 102/2 | DA+6 1MRC | FS | UKC | 2026-04-30
25 | 132/5 | DA+3 | FS | Hetansh | 2026-05-02
26 | 111A/0 | DD+18 1MRC | FS | Shakti | 2026-05-05
27 | 80/3 | DA+3 1MRC | FS | Exel Power | 2026-05-08
28 | 154/2 | DA+6 | PS | AR Construction | 2026-05-10
29 | 112/0 | DD+18 1MRC | FS | Shakti | 2026-05-11
220 TM Chhapra-Amnour TL
1 | 8/1 | 2TDA+3 | WET | Nav Durga Traders-1 | 2025-11-20
2 | 8/0 | 2TDC+0 | WET | Nav Durga Traders-1 | 2026-04-30
3 | 11/0 | 2TDC+0 | PS | AR | 2026-04-30
4 | 3/1 | 2TDD+9 | PS | Nav Durga Traders-1 | 2026-05-06
400 KV LILO
1 | 19/4 LI | 4DA+0 | PS | Navdurga Traders-2 | 2025-12-23
2 | 11/2 LI | DA+0 | PS | Rajeshwar Singh | 2026-01-15
3 | 28/1 LO | DA+6 | PS | Nav Durga Traders | 2026-01-22
4 | 39/3 LO | DA+0 | FS | Nav Durga Traders | 2026-02-17
5 | 23/0 LO | DB+0 | PS | Raajeshwar Singh | 2026-04-07
6 | 22/0 LO | DB+6 | PS | Raajeshwar Singh | 2026-04-13
7 | 20/0 LO | 4DD+0 | PS | Dharmendra Mishra | 2026-04-14
8 | 23/1 LO | DA+0 | PS | Raajeshwar Singh | 2026-04-17
9 | 11/3 LI | DA+0 | PS | Dharmendra Mishra | 2026-04-25
10 | 19/3 LI | DA+0 | PS | Raajeshwar Singh | 2026-04-27
11 | 12/1 LI | DA+9 | WET | Dharmendra Mishra | 2026-04-28
12 | 39/1 LO | DA+6 | FS | Nav Durga Traders | 2026-04-28
13 | 39/2 LO | DA+3 | FS | Nav Durga Traders | 2026-04-30
14 | 21/0 LO | DC+9 | PS | Raajeshwar Singh | 2026-04-30
15 | 39/4 LO | DA+3 | FS | Nav Durga Traders | 2026-05-03
16 | 25/1 LI | DA+3 | PS | Dharmendra Mishra | 2026-05-03
17 | 39/5 LO | DA+3 | FS | Nav Durga Traders | 2026-05-05
18 | 26/1 LI | DA+3 | PS | Dharmendra Mishra | 2026-05-08

## Erection
ERECTION PROGRESS STATUS
220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose
Sr | Location No. | Tower Type | Tower Weight (MT) | Start Date | Completion Date | Agency | Completion Month | Cumm. | Status | Remarks
8
1 | 10/1 | DA+3 | 8.334 | 2026-01-27 | 2026-01-31 | S R Enterprises | Jan'2026 | 1 | Completed
2 | 10/2 | DA+3 | 8.334 | 2026-02-03 | 2026-02-06 | S R Enterprises | Feb'2026 | 5 | Completed
3 | 10/0 | DD+0 | 13.664 | 2026-02-07 | 2026-02-14 | S R Enterprises |  |  | Completed
4 | 11/1 | DA+3 | 8.334 | 2026-02-14 | 2026-02-16 | S R Enterprises |  |  | Completed
5 | 11/3 | DA+0 | 6.808 | 2026-02-16 | 2026-02-18 | S R Enterprises |  |  | Completed
6 | 11/2 | DA+3 | 8.334 | 2026-02-18 | 2026-02-18 | S R Enterprises |  |  | Completed
7 | 8/1 | DA+3 | 8.334 | 2026-05-19 | 2026-05-21 | K2 KUMAR | May'2026 | 2 | Completed
8 | 7/1 | DA+0 | 6.809 | 2026-05-26 | 2026-05-28 | K2 KUMAR |  |  | Completed
68.951
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN & LOOP OUT
Sr | Location No. | Tower Type | Tower Weight (MT) | Start Date | Completion Date | Agency |  |  | Status | Remarks
31
1 | 32/1 | DA+6 | 20.631 | 2026-02-07 | 2026-02-14 | Pinki Devi | Feb'2026 | 3 | Completed | LOOP IN
2 | 27/4 | DA+0 | 16.922 | 2026-02-14 | 2026-02-17 | Pinki Devi |  |  | Completed | LOOP IN
3 | 29/0 | DD+0 | 37.87 | 2026-02-17 | 2026-02-25 | Pinki Devi |  |  | Completed | LOOP IN
4 | 28/0 | DD+3 | 40.17 | 2026-02-17 | 2026-03-10 | Pinki Devi | Mar'26 | 7 | Completed | LOOP IN
5 | 19/0 | DB+3 | 28.063 | 2026-03-08 | 2026-03-15 | Rang Construction |  |  | Completed | LOOP IN
6 | 24/1 | DA+6 | 20.631 | 2026-03-10 | 2026-03-20 | Rang Construction |  |  | Completed | LOOP OUT
7 | 34/0 | DD+3 | 40.17 | 2026-03-13 | 2026-03-22 | Pinki Devi |  |  | Completed | LOOP OUT
8 | 24/2 | DA+0 | 16.922 | 2026-03-15 | 2026-03-24 | Rang Construction |  |  | Completed | LOOP OUT
9 | 24/0 | DD+3 | 40.17 | 2026-03-21 | 2026-03-30 | Pinki Devi |  |  | Completed | LOOP IN
10 | 18/0 | DC+6 | 38.079 | 2026-03-25 | 2026-03-31 | Rang Construction |  |  | Completed | LOOP IN
11 | 34/1 | DA+9 | 21.756 | 2026-03-31 | 2026-04-03 | Pinki Devi | Apr'26 | 10 | Completed | LOOP OUT
12 | 19/1 | DA+0 | 16.922 | 2026-04-03 | 2026-04-09 | Rang Construction |  |  | Completed | LOOP IN
13 | 25/0 | DD+0 | 37.87 | 2026-04-03 | 2026-04-09 | Pinki Devi |  |  | Completed | LOOP IN
14 | 18/2 | DA+6 | 20.631 | 2026-04-07 | 2026-04-13 | Rang Construction |  |  | Completed | LOOP IN
15 | 29/0 | DD+3 | 40.17 | 2026-04-09 | 2026-04-16 | Pinki Devi |  |  | Completed | LOOP OUT
16 | 18/1 | DA+3 | 18.405 | 2026-04-13 | 2026-04-18 | Rang Construction |  |  | Completed | LOOP IN
17 | 24/3 | DA+0 | 16.922 | 2026-04-18 | 2026-04-22 | Rang Construction |  |  | Completed | LOOP OUT
18 | 28/1 | DA+6 | 20.631 | 2026-04-16 | 2026-04-22 | Pinki Devi |  |  | Completed | LOOP OUT
19 | 19/4 | DA+0 | 16.922 | 2026-04-23 | 2026-04-26 | Rang Construction |  |  | Completed | LOOP IN
20 | 30/0 | DD+0 | 37.87 | 2026-04-23 | 2026-04-28 | Pinki Devi |  |  | Completed | LOOP OUT
21 | 26/1 | DA+0 | 16.922 | 2026-03-31 | 2026-05-01 | Rang Construction | May'26 | 11 | Completed | LOOP OUT
22 | 25/0 | DD+0 | 37.87 | 2026-04-03 | 2026-05-03 | Pinki Devi |  |  | Completed | LOOP OUT
23 | 26/0 | DC+0 | 31.21 | 2026-04-03 | 2026-05-08 | Rang Construction |  |  | Completed | LOOP OUT
24 | 35/0 | DD+3 | 40.17 | 2026-04-07 | 2026-05-09 | Pinki Devi |  |  | Completed | LOOP OUT
25 | 19/3 | DA+0 | 16.922 | 2026-04-09 | 2026-05-11 | Rang Construction |  |  | Completed | LOOP IN
26 | 33/0 | DD+0 | 37.87 | 2026-04-13 | 2026-05-15 | Pinki Devi |  |  | Completed | LOOP OUT
27 | 33/1 | DA+0 | 16.922 | 2026-04-18 | 2026-05-20 | Pinki Devi |  |  | Completed | LOOP OUT
28 | 28/0 | DD+0 | 37.87 | 2026-04-16 | 2026-05-21 | Rang Construction |  |  | Completed | LOOP OUT
29 | 19/2 | DA+0 | 16.922 | 2026-04-23 | 2026-05-24 | Rang Construction |  |  | Completed | LOOP IN
30 | 36/0 | DD+0 | 37.87 | 2026-05-31 | 2026-05-31 | Pinki Devi |  |  | Completed | LOOP OUT
31 | 26/2 | DA+6 | 20.631 | 2026-05-31 | 2026-05-31 | Pinki Devi |  |  | Completed | LOOP IN
858.906
220 KV D/C Chapra -Gopalganj Transmission Line with ACSR Zebra Conductor
Sr | Location No. | Tower Type | Tower Weight (MT) | Start Date | Completion Date | Agency |  |  | Status | Remarks
48
1 | 96/1 | DA+6 | 5.713 | 2026-03-16 | 2026-03-18 | Sanjiv Kumar | Mar'26 | 7 | Completed
2 | 96/2 | DA+6 | 5.713 | 2026-03-18 | 2026-03-20 | Sanjiv Kumar |  |  | Completed
3 | 99/0 | DC+3 | 8.086 | 2026-03-20 | 2026-03-25 | Sanjiv Kumar |  |  | Completed
4 | 98/0 | DC+3 | 8.086 | 2026-03-25 | 2026-03-27 | Sanjiv Kumar |  |  | Completed
5 | 99/3 | DA+6 | 5.713 | 2026-03-27 | 2026-03-29 | Sanjiv Kumar |  |  | Completed
6 | 99/2 | DA+6 | 5.713 | 2026-03-29 | 2026-03-30 | Sanjiv Kumar |  |  | Completed
7 | 99/1 | DA+0 | 4.378 | 2026-03-30 | 2026-03-31 | Sanjiv Kumar |  |  | Completed
8 | 100/0 | DC+0 | 6.563 | 2026-03-31 | 2026-04-02 | Sanjiv Kumar | Apr'26 | 21 | Completed
9 | 100/1 | DA+6 | 5.713 | 2026-04-02 | 2026-04-04 | Sanjiv Kumar |  |  | Completed
10 | 100/4 | DA+3 | 5.167 | 2026-04-04 | 2026-04-06 | Sanjiv Kumar |  |  | Completed
11 | 118/0 | DC+3 | 8.086 | 2026-04-02 | 2026-04-07 | ZFAPL |  |  | Completed
12 | 100/3 | DA+3 | 5.167 | 2026-04-06 | 2026-04-08 | Sanjiv Kumar |  |  | Completed
13 | 100/2 | DA+3 | 5.167 | 2026-04-08 | 2026-04-10 | Sanjiv Kumar |  |  | Completed
14 | 65/0 | DD+3 | 9.791 | 2026-04-02 | 2026-04-12 | Druvika |  |  | Completed
15 | 101/0 | DC+0 | 6.563 | 2026-04-10 | 2026-04-12 | Sanjiv Kumar |  |  | Completed
16 | 101/1 | DA+0 | 4.378 | 2026-04-12 | 2026-04-14 | Sanjiv Kumar |  |  | Completed
17 | 116/4 | DA+9 | 6.325 | 2026-04-07 | 2026-04-15 | ZFAPL |  |  | Completed
18 | 97/2 | DA+3 | 5.167 | 2026-04-14 | 2026-04-15 | Sanjiv Kumar |  |  | Completed
19 | 107/0 | DD+0 | 8.086 | 2026-04-15 | 2026-04-19 | Sanjiv Kumar |  |  | Completed
20 | 66/0 | DD+3 | 9.791 | 2026-04-12 | 2026-04-20 | Druvika |  |  | Completed
21 | 108/0 | DD+3 | 9.791 | 2026-04-18 | 2026-04-21 | Sanjiv Kumar |  |  | Completed
22 | 107/1 | DA+3 | 5.167 | 2026-04-21 | 2026-04-22 | Sanjeev Kumar |  |  | Completed
23 | 116/0 | DD+3 | 9.791 | 2026-04-23 | 2026-04-25 | Sanjeev Kumar |  |  | Completed
24 | 115/1 | DA+6 | 5.713 | 2026-04-23 | 2026-04-28 | Sanjeev Kumar |  |  | Completed
25 | 56/0 | DC+0 | 6.563 | 2026-04-12 | 2026-04-28 | Druvika |  |  | Completed
26 | 83/0 | DD+3 | 9.791 | 2026-04-06 | 2026-04-28 | Exel Power |  |  | Completed
27 | 117/1 | DA+9 | 6.325 | 2026-04-15 | 2026-04-29 | Sanjeev Kumar |  |  | Completed
28 | 115/0 | DD+3 | 9.791 | 2026-04-30 | 2026-04-30 | Sanjeev Kumar |  |  | Completed
29 | 114/1 | DA+3 | 5.167 | 2026-04-29 | 2026-05-02 | Sanjeev Kumar | May'26 | 20 | Completed
30 | 55/1 | DA+3 | 5.167 | 2026-04-30 | 2026-05-03 | Dhuvika |  |  | Completed
31 | 116/2 | DA+3 | 5.167 | 2026-05-03 | 2026-05-06 | Sanjeev Kumar |  |  | Completed
32 | 55/0 | DD+3 | 9.791 | 2026-05-04 | 2026-05-07 | Dhuvika |  |  | Completed
33 | 89/0 | DB+0 | 5.97 | 2026-05-07 | 2026-05-10 | Sanjeev Kumar |  |  | Completed
34 | 88/0 | DC+3 | 8.086 | 2026-05-09 | 2026-05-12 | Sanjeev Kumar |  |  | Completed
35 | 54/3 | DA+0 | 4.378 | 2026-05-10 | 2026-05-13 | Dhuvika |  |  | Completed
36 | 88/1 | DA+6 | 5.713 | 2026-05-10 | 2026-05-13 | Sanjeev Kumar |  |  | Completed
37 | 87/2 | DA+6 | 5.713 | 2026-05-12 | 2026-05-15 | Sanjeev Kumar |  |  | Completed
38 | 87/1 | DA+3 | 5.167 | 2026-05-13 | 2026-05-16 | Sanjeev Kumar |  |  | Completed
39 | 82/0 | DD+9 | 11.469 | 2026-05-14 | 2026-05-17 | Exel Power |  |  | Completed
40 | 87/0 | DD+3 | 9.791 | 2026-05-15 | 2026-05-18 | Sanjeev Kumar |  |  | Completed
41 | 83/1 | DA+0 | 4.378 | 2026-05-17 | 2026-05-20 | Sanjeev Kumar |  |  | Completed
42 | 84/0 | DD+0 | 8.086 | 2026-05-18 | 2026-05-21 | Exel Power |  |  | Completed
43 | 85/0 | DD+9 | 11.469 | 2026-05-20 | 2026-05-23 | Sanjeev Kumar |  |  | Completed
44 | 54/2 | DA+6 | 5.713 | 2026-05-22 | 2026-05-25 | Dhuvika |  |  | Completed
45 | 86/0 | DD+0 | 8.086 | 2026-05-23 | 2026-05-26 | Sanjeev Kumar |  |  | Completed
46 | 85/1 | DA+3 | 5.167 | 2026-05-23 | 2026-05-26 | Exel Power |  |  | Completed
47 | 54/1 | DA+3 | 5.167 | 2026-05-28 | 2026-05-31 | Dhuvika |  |  | Completed
48 | 118/3 | DA+9 | 6.325 | 2026-05-28 | 2026-05-31 | Exel Power |  |  | Completed
328.268
Formulas:
Start Date = [Completion Date, row above]

## Earthing
220 KV D/C Chapra -Gopalganj Transmission Line with ACSR Zebra Conductor
Sr No. | Location No. | Tower Type | Classification | Earthing Type | Date of Earthing | Agency | Status | Remarks
112
1 | 15/0 | DD+6 | WET | PIPE TYPE EARTHING | 2024-07-06 | Dharmendra Mishra | Completed
2 | 14/1 | DA+0 | FS | PIPE TYPE EARTHING | 2024-07-06 | Dharmendra Mishra | Completed
3 | 14/0 | DC+3 | WET | PIPE TYPE EARTHING | 2024-10-17 | Nav Durga Traders | Completed
4 | 13/2 | DA+9 | PS | PIPE TYPE EARTHING | 2024-10-17 | Nav Durga Traders | Completed
5 | 13/1 | DA+6 | WET | PIPE TYPE EARTHING | 2024-10-17 | Nav Durga Traders | Completed
6 | 16/0 | DD+6 | WET | PIPE TYPE EARTHING | 2024-09-13 | Dharmendra Mishra | Completed
7 | 17/0 | DD+3 | WET | PIPE TYPE EARTHING | 2024-08-03 | Dharmendra Mishra | Completed
8 | 17/1 | DA+6 | WET | PIPE TYPE EARTHING | 2024-09-14 | Dharmendra Mishra | Completed
9 | 18/1 | DA+6 | PS | PIPE TYPE EARTHING | 2024-10-24 | Nav Durga Traders | Completed
10 | 19/0 | DD+6 | PS | PIPE TYPE EARTHING | 2024-10-24 | Nav Durga Traders | Completed
11 | 37/0 | DC+3 | PS | PIPE TYPE EARTHING | 2024-10-26 | Dharmendra Mishra | Completed
12 | 40/0 | DC+0 | WET | PIPE TYPE EARTHING | 2024-09-06 | Dharmendra Mishra | Completed
13 | 44/0 | DD+3 | WET | PIPE TYPE EARTHING | 2024-09-12 | Dharmendra Mishra | Completed
14 | 18/0 | DC+6 | WET | PIPE TYPE EARTHING | 2024-08-10 | Dharmendra Mishra | Completed
15 | 21/0 | DC+3 | PS | PIPE TYPE EARTHING | 2024-10-30 | Nav Durga Traders | Completed
16 | 38/0 | DB+6 | PS | PIPE TYPE EARTHING | 2024-10-30 | Nav Durga Traders | Completed
17 | 97/2 | 2SDA+3 | PS | PIPE TYPE EARTHING | 2025-12-02 | Amit Srivastava | Completed
18 | 99/1 | 2SDA+0 | PS | PIPE TYPE EARTHING | 2025-12-07 | Amit Srivastava | Completed
19 | 98/0 | 2SDC+3 | PS | PIPE TYPE EARTHING | 2025-12-08 | Amit Srivastava | Completed
20 | 99/2 | DA+3 | PS | PIPE TYPE EARTHING | 2025-12-10 | Amit Srivastava | Completed
21 | 38/1 | DA+0 | WET | PIPE TYPE EARTHING | 2025-12-14 | Dharmendra Mishra | Completed
22 | 99/0 | DC+3 | PS | PIPE TYPE EARTHING | 2025-12-14 | Amit Srivastava | Completed
23 | 100/1 | DA+6 | PS | PIPE TYPE EARTHING | 2025-12-17 | Amit Srivastava | Completed
24 | 99/3 | DA+6 | PS | PIPE TYPE EARTHING | 2025-12-19 | Amit Srivastava | Completed
25 | 36/0 | DD+3 | FS | PIPE TYPE EARTHING | 2025-12-20 | Dharmendra Mishra | Completed
26 | 100/2 | DA+3 | PS | PIPE TYPE EARTHING | 2025-12-24 | Amit Srivastava | Completed
27 | 100/3 | DA+3 | PS | PIPE TYPE EARTHING | 2025-12-25 | Amit Srivastava | Completed
28 | 65/0 | DD+3 | FS | PIPE TYPE EARTHING | 2025-12-27 | Dharmendra Mishra | Completed
29 | 35/0 | 2SDD+0 | FS | PIPE TYPE EARTHING | 2025-12-30 | Dharmendra Mishra | Completed
30 | 100/4 | DA+3 | ps | PIPE TYPE EARTHING | 2026-01-03 | Amit Srivastava | Completed
31 | 101/1 | DA+3 | ps | PIPE TYPE EARTHING | 2026-01-03 | Amit Srivastava | Completed
32 | 96/1 | DA+3 | ps | PIPE TYPE EARTHING | 2026-01-03 | Amit Srivastava | Completed
33 | 66/2 | DA+3 | ps | PIPE TYPE EARTHING | 2025-12-30 | Dharmendra Mishra | Completed
34 | 96/2 | DA+6 | ps | PIPE TYPE EARTHING | 2026-01-03 | Amit Srivastava | Completed
35 | 66/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-01-06 | Dharmendra Mishra | Completed
36 | 66/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-01-11 | Dharmendra Mishra | Completed
37 | 82/0 | DD+9 | FS | PIPE TYPE EARTHING | 2026-01-16 | Dharmendra Mishra | Completed
38 | 85/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-01-19 | Dharmendra Mishra | Completed
39 | 116/4 | DA+9 | FS | PIPE TYPE EARTHING | 2026-01-30 | Dharmendra Mishra | Completed
40 | 119/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-02-06 | Shakti Construction-2 | Completed
41 | 118/3 | DA+9 | PS | PIPE TYPE EARTHING | 2026-02-06 | Shakti Construction-2 | Completed
42 | 59/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-02-06 | Shakti Construction-2 | Completed
43 | 116/2 | DA+3 | PS | PIPE TYPE EARTHING | 2026-02-07 | Shakti Construction-2 | Completed
44 | 117/1 | DA+9 | PS | PIPE TYPE EARTHING | 2026-02-11 | Shakti Construction-2 | Completed
45 | 116/3 | DA+3 | PS | PIPE TYPE EARTHING | 2026-02-11 | Shakti Construction-2 | Completed
46 | 55/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-02-11 | Maa Construction | Completed
47 | 116/0 | DD+3 | PS | PIPE TYPE EARTHING | 2026-02-12 | Shakti Construction-2 | Completed
48 | 55/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-02-16 | Maa Construction | Completed
49 | 107/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-02-18 | UKC | Completed
50 | 114/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-02-19 | Indra Contruction | Completed
51 | 115/1 | DA+6 | PS | PIPE TYPE EARTHING | 2026-02-19 | Indra Contruction | Completed
52 | 133/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-02-19 | Shakti Construction-2 | Completed
53 | 54/3 | DA+0 | PS | PIPE TYPE EARTHING | 2026-02-20 | Maa Construction | Completed
54 | 85/0 | DD+9 | FS | PIPE TYPE EARTHING | 2026-02-21 | Dharmendra Mishra | Completed
55 | 83/1 | DA+0 | FS | PIPE TYPE EARTHING | 2026-02-21 | Dharmendra Mishra | Completed
56 | 86/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-02-21 | Dharmendra Mishra | Completed
57 | 56/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-02-21 | Maa Construction | Completed
58 | 83/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-02-21 | Dharmendra Mishra | Completed
59 | 115/0 | DD+3 | PS | PIPE TYPE EARTHING | 2026-02-21 | Indra Contruction | Completed
60 | 84/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-02-21 | Dharmendra Mishra | Completed
61 | 107/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-02-21 | UKC | Completed
62 | 117/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-02-25 | Shakti Construction-2 | Completed
63 | 88/1 | DA+6 | PS | PIPE TYPE EARTHING | 2026-02-26 | Dharmendra Mishra | Completed
64 | 118/0 | DC+3 | PS | PIPE TYPE EARTHING | 2026-02-26 | Shakti Construction-2 | Completed
65 | 120/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-02-27 | Shakti Construction-2 | Completed
66 | 58/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-02-28 | Maa Construction | Completed
67 | 131/0 | DB+3 | PS | PIPE TYPE EARTHING | 2026-02-27 | Hetansh | Completed
68 | 131/1 | DA+6 | PS | PIPE TYPE EARTHING | 2026-02-27 | Hetansh | Completed
69 | 131/2 | DA+3 | PS | PIPE TYPE EARTHING | 2026-02-27 | Hetansh | Completed
70 | 89/0 | DB+0 | PS | PIPE TYPE EARTHING | 2026-02-28 | Dharmendra Mishra | Completed
71 | 54/2 | DA+6 | PS | PIPE TYPE EARTHING | 2026-03-13 | Maa Construction | Completed
72 | 88/0 | DC+3 | PS | PIPE TYPE EARTHING | 2026-03-13 | Dharmendra Mishra | Completed
73 | 87/2 | DA+6 | FS | PIPE TYPE EARTHING | 2026-03-13 | Dharmendra Mishra | Completed
74 | 87/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-03-16 | Dharmendra Mishra | Completed
75 | 59/2 | DA+3 | PS | PIPE TYPE EARTHING | 2026-03-16 | Maa Construction | Completed
76 | 118/2 | DA+9 | PS | PIPE TYPE EARTHING | 2026-03-19 | Shakti Construction-2 | Completed
77 | 59/3 | DA+6 | FS | PIPE TYPE EARTHING | 2026-03-19 | Maa Construction | Completed
78 | 114/0 | DC+3 (1MRC) | FS | PIPE TYPE EARTHING | 2026-03-22 | Shakti Construction-2 | Completed
79 | 59/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-03-23 | Maa Construction | Completed
80 | 150/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-03-23 | AR Construction | Completed
81 | 113/3 | DA+6 (1MRC) | PS | PIPE TYPE EARTHING | 2026-03-24 | Shakti Construction-2 | Completed
82 | 60/0 | DB+3 | FS | PIPE TYPE EARTHING | 2026-03-25 | Maa Construction | Completed
83 | 113/2 | DA+6 (1MRC) | PS | PIPE TYPE EARTHING | 2026-03-29 | Shakti Construction-2 | Completed
84 | 59/4 | DA+6 (1MRC) | FS | PIPE TYPE EARTHING | 2026-03-31 | Maa Construction | Completed
85 | 150/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-03-31 | AR Construction | Completed
86 | 152/2 | DA+6 | PS | PIPE TYPE EARTHING | 2026-04-03 | AR Construction | Completed
87 | 59/5 | DA+0 1MRC | FS | PIPE TYPE EARTHING | 2026-04-03 | Maa Construction | Completed
88 | 101/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-04-05 | UKC | Completed
89 | 101/2 | DA+0 | FS | PIPE TYPE EARTHING | 2026-04-06 | UKC | Completed
90 | 101/4 | DA+3 | FS | PIPE TYPE EARTHING | 2026-04-06 | UKC | Completed
91 | 101/3 | DA+0 1MRC | FS | PIPE TYPE EARTHING | 2026-04-06 | UKC | Completed
92 | 136/2 | DA+6 | PS | PIPE TYPE EARTHING | 2026-04-06 | UKC | Completed
93 | 132/0 | DC+3 | FS | PIPE TYPE EARTHING | 2026-04-06 | Hetansh | Completed
94 | 137/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-04-06 | Hetansh | Completed
95 | 134/0 | DC+9 | PS | PIPE TYPE EARTHING | 2026-04-06 | Hetansh | Completed
96 | 58/1 | DA+3 1MRC | FS | PIPE TYPE EARTHING | 2026-04-12 | Maa Construction | Completed
97 | 67/0 | DC+3 | FS | PIPE TYPE EARTHING | 2026-04-12 | Maa Construction | Completed
98 | 111/0 | DD+6 1MRC | FS | PIPE TYPE EARTHING | 2026-04-13 | Shakti Construction-2 | Completed
99 | 123/0 | DC+9 | FS | PIPE TYPE EARTHING | 2026-04-24 | Shakti Construction-2 | Completed
100 | 123/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-04-24 | Shakti Construction-2 | Completed
101 | 124/0 | DC+0 | FS | PIPE TYPE EARTHING | 2026-04-27 | Shakti Construction-2 | Completed
102 | 122/0 | DD+25 | FS | PIPE TYPE EARTHING | 2026-04-30 | Shakti Construction-2 | Completed
103 | 121/0 | DD+18 | FS | PIPE TYPE EARTHING | 2026-04-30 | Shakti Construction-2 | Completed
104 | 64/1 | DA+0 | FS | PIPE TYPE EARTHING | 2026-05-03 | Maa Construction | Completed
105 | 64/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-05-03 | Maa Construction | Completed
106 | 111A/0 | DD+18 1MRC | FS | PIPE TYPE EARTHING | 2026-05-09 | Shakti Construction-2 | Completed
107 | 81/1 | DA+3 1MRC | FS | PIPE TYPE EARTHING | 2026-05-10 | Exel Power | Completed
108 | 80/3 | DA+3 1MRC | FS | PIPE TYPE EARTHING | 2026-05-10 | Exel Power | Completed
109 | 81/0 | DC+0 1MRC | FS | PIPE TYPE EARTHING | 2026-05-10 | Exel Power | Completed
110 | 154/2 | DA+3 | PS | PIPE TYPE EARTHING | 2026-05-11 | AR Construction | Completed
111 | 112/0 | DD+18 1MRC | FS | PIPE TYPE EARTHING | 2026-05-12 | Shakti Construction-2 | Completed
112 | 63/2 | DA+3 | FS | PIPE TYPE EARTHING | 2026-05-17 | Maa Construction | Completed
113 | 116/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-05-17 | Shakti Construction-2 | Completed
114 | 106/1 | DA+0 | PS | PIPE TYPE EARTHING | 2026-05-23 | Construction Wala | Completed
115 | 132/5 | DA+3 | FS | PIPE TYPE EARTHING | 2026-05-24 | Hetansh | Completed
116 | 132/4 | DA+9 | FS | PIPE TYPE EARTHING | 2026-05-24 | Hetansh | Completed
117 | 132/3 | DA+6 | FS | PIPE TYPE EARTHING | 2026-05-24 | Hetansh | Completed
118 | 132/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-05-24 | Hetansh | Completed
119 | 106/3 | DA+0 1MRC | FS | PIPE TYPE EARTHING | 2026-05-26 | Construction Wala | Completed
120 | 106/2 | DA+0 1MRC | FS | PIPE TYPE EARTHING | 2026-06-02 | Construction Wala | Completed
121 | 130/0 | DC+9 | FS | PIPE TYPE EARTHING | 2026-06-02 | Hetansh | Completed
122 | 142/0 | DD+25 | FS | PIPE TYPE EARTHING | 2026-06-03 | Shakti Construction-2 | Completed
123 | 142/1 | DB+3 | FS | PIPE TYPE EARTHING | 2026-06-03 | Shakti Construction-2 | Completed
124 | 136/1 | DA+3 | FS | PIPE TYPE EARTHING | 2026-06-04 | Hetansh | Completed
125 | 135/0 | DD+9 | PS | PIPE TYPE EARTHING | 2026-06-04 | Hetansh | Completed
126 | 145/1 | DA+0 | PS | PIPE TYPE EARTHING | 2026-06-09 | Shakti Construction-2 | Completed
127 | 145/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-06-09 | Shakti Construction-2 | Completed
128 | 145/2 | DA+3 | PS | PIPE TYPE EARTHING | 2026-06-12 | Shakti Construction-2 | Completed
129 | 90/0 | DD+0 1MRC | FS | PIPE TYPE EARTHING | 2026-06-13 | Dharmendra Mishra | Completed
130 | 69/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-06-13 | Maa Construction | Completed
220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose
Sr | Location No. | Tower Type | Classification | Earthing Type | Date of Earthing | Agency | Status | Remarks
15
1 | 7/1 | DA+0 | WET | PIPE TYPE EARTHING | 2025-09-19 | Nav Durga Traders | completed
2 | 6/1 | DA+3 | WET | PIPE TYPE EARTHING | 2025-09-24 | Nav Durga Traders | Completed
3 | 8/2 | 2TDA+6 | WET | PIPE TYPE EARTHING | 2025-11-11 | Nav Durga Traders | Completed
4 | 7/0 | 2TDD+0 | WET | PIPE TYPE EARTHING | 2025-11-22 | Nav Durga Traders | Completed
5 | 10/2 | 2TDA+3 | PS | PIPE TYPE EARTHING | 2025-11-30 | Nav Durga Traders | Completed
6 | 10/0 | 2TDD+0 | PS | PIPE TYPE EARTHING | 2025-12-07 | Nav Durga Traders | Completed
7 | 10/1 | 2TDA+3 | PS | PIPE TYPE EARTHING | 2025-12-07 | Nav Durga Traders | Completed
8 | 11/1 | 2TDA+3 | PS | PIPE TYPE EARTHING | 2025-12-09 | Nav Durga Traders | Completed
9 | 11/2 | DA+3 | PS | PIPE TYPE EARTHING | 2025-12-11 | Nav Durga Traders | Completed
10 | 11/4 | 2TDA+0 | PS | PIPE TYPE EARTHING | 2025-12-19 | Nav Durga Traders | Completed
11 | 11/3 | 2TDA+0 | PS | PIPE TYPE EARTHING | 2025-12-28 | Nav Durga Traders | Completed
12 | 8/1 | DA+3 | WET | PIPE TYPE EARTHING | 2026-01-05 | Nav Durga Traders | Completed
13 | 9/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-04-26 | Nav Durga Traders | Completed
14 | 11/0 | 2TDC+0 | PS | PIPE TYPE EARTHING | 2026-05-05 | AR | Completed
15 | 6/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-06-06 | Nav Durga Traders | Completed
LILO of 400 KV Barh (NTPC) Motihari (DMTCL) D/C (Quad Moose) Transmission Line at Chhapra (New) LOOP IN & LOOP OUT
Sr | Location No. | Tower Type | Classification | Earthing Type | Date of Earthing | Agency | Status | Remarks
57
1 | 30/0 | 4DC+3 | PS | PIPE TYPE EARTHING | 2025-12-09 | Nav Durga Traders | Completed | LOOP IN
2 | 31/0 | 4DD+0 | PS | PIPE TYPE EARTHING | 2025-12-12 | Navdurga Traders-1 | Completed | LOOP IN
3 | 18/2 | 4DA+6 | PS | PIPE TYPE EARTHING | 2025-12-15 | Rajeshwar Singh | Completed | LOOP IN
4 | 27/4 | 4DA+0 | PS | PIPE TYPE EARTHING | 2025-12-19 | Navdurga Traders-1 | Completed | LOOP IN
5 | 19/2 | 4DA+0 | PS | PIPE TYPE EARTHING | 2025-12-21 | Rajeshwar Singh | Completed | LOOP IN
6 | 29/1 | 4DA+6 | PS | PIPE TYPE EARTHING | 2025-12-22 | Navdurga Traders-1 | Completed | LOOP IN
7 | 19/1 | DA+0 | PS | PIPE TYPE EARTHING | 2025-12-23 | Navdurga Traders-2 | Completed | LOOP IN
8 | 28/0 | DD+3 | PS | PIPE TYPE EARTHING | 2025-12-28 | Nav Durga Traders | Completed | LOOP IN
9 | 19/0 | DB+3 | PS | PIPE TYPE EARTHING | 2026-01-05 | Rajeshwar Singh | Completed | LOOP IN
10 | 29/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-01-06 | Nav Durga Traders | Completed | LOOP IN
11 | 27/0 | DB+3 | PS | PIPE TYPE EARTHING | 2026-01-15 | Rajeswar Singh | Completed | LOOP IN
12 | 32/1 | DA+6 | FS | PIPE TYPE EARTHING | 2026-01-08 | Navdurga Traders | Completed | LOOP IN
13 | 28/1 | DA+0 | PS | PIPE TYPE EARTHING | 2026-01-09 | Nav Durga Traders | Completed | LOOP IN
14 | 32/0 | DB+6 | FS | PIPE TYPE EARTHING | 2026-01-09 | Nav Durga Traders | Completed | LOOP IN
15 | 27/0 | DB+3 | PS | PIPE TYPE EARTHING | 2026-01-23 | Nav Durga Traders | Completed | LOOPOUT
16 | 40/0 | DB+6 | PS | PIPE TYPE EARTHING | 2026-01-23 | Nav Durga Traders | Completed | LOOPOUT
17 | 18/1 | DA+3 | PS | PIPE TYPE EARTHING | 2026-01-25 | Raajeshwar Singh | Completed | LOOP IN
18 | 18/0 | DC+6 | PS | PIPE TYPE EARTHING | 2026-01-25 | Raajeshwar Singh | Completed | LOOP IN
19 | 24/1 | DA+6 | FS | PIPE TYPE EARTHING | 2026-01-29 | Raajeshwar Singh | Completed | LOOPOUT
20 | 24/2 | DA+0 | FS | PIPE TYPE EARTHING | 2026-02-01 | Raajeshwar Singh | Completed | LOOPOUT
21 | 24/3 | DA+0 | FS | PIPE TYPE EARTHING | 2026-02-05 | Raajeshwar Singh | Completed | LOOPOUT
22 | 24/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-02-09 | Raajeshwar Singh | Completed | LOOPOUT
23 | 24/0 | 4DD+3 | PS | PIPE TYPE EARTHING | 2026-02-09 | Nav Durga Traders | Completed | LOOP IN
24 | 25/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-02-09 | Nav Durga Traders | Completed | LOOP IN
25 | 41/0 | DC+0 | FS | PIPE TYPE EARTHING | 2026-02-10 | Nav Durga Traders | Completed | LOOPOUT
26 | 29/0 | DD+3 | PS | PIPE TYPE EARTHING | 2026-02-10 | Nav Durga Traders | Completed | LOOPOUT
27 | 25/1 | DA+0 | FS | PIPE TYPE EARTHING | 2026-02-24 | Raajeshwar Singh | Completed | LOOPOUT
28 | 34/1 | DA+9 | FS | PIPE TYPE EARTHING | 2026-02-27 | Nav Durga Traders | Completed | LOOPOUT
29 | 34/0 | DD+3 | PS | PIPE TYPE EARTHING | 2026-02-27 | Nav Durga Traders | Completed | LOOPOUT
30 | 41/1 | DA+0 | FS | PIPE TYPE EARTHING | 2026-02-28 | Nav Durga Traders | Completed | LOOPOUT
31 | 30/0 | DD+0 | WET | PIPE TYPE EARTHING | 2026-03-02 | Nav Durga Traders | Completed | LOOPOUT
32 | 28/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-03-02 | Nav Durga Traders | Completed | LOOPOUT
33 | 31/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-03-03 | Nav Durga Traders | Completed | LOOPOUT
34 | 9/0 | DC+0 | PS | PIPE TYPE EARTHING | 2026-03-13 | Kutir Vihar | Completed | LOOP IN
35 | 10/0 | DB+0 | PS | PIPE TYPE EARTHING | 2026-03-22 | Kutir Vihar | Completed | LOOP IN
37 | 25/0 | DD+0 | FS | PIPE TYPE EARTHING | 2026-03-27 | Raajeshwar Singh | Completed | LOOPOUT
36 | 11/0 | DB+0 | FS | PIPE TYPE EARTHING | 2026-03-31 | Kutir Vihar | Completed | LOOP IN
38 | 26/0 | 4DC+0 | FS | PIPE TYPE EARTHING | 2026-04-01 | Raajeshwar Singh | Completed | LOOPOUT
39 | 26/1 | DA+0 | PS | PIPE TYPE EARTHING | 2026-04-01 | Raajeshwar Singh | Completed | LOOPOUT
40 | 42/0 | 4DD+0 | FS | PIPE TYPE EARTHING | 2026-04-03 | Dharmendra Mishra | Completed | LOOPOUT
41 | 35/0 | DD+3 | PS | PIPE TYPE EARTHING | 2026-04-04 | Nav Durga Traders | Completed | LOOPOUT
42 | 36/0 | DD+0 | PS | PIPE TYPE EARTHING | 2026-04-04 | Nav Durga Traders | Completed | LOOPOUT
43 | 22/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-04-05 | Nav Durga Traders | Completed | LOOP IN
44 | 43/0 | DD+3 | FS | PIPE TYPE EARTHING | 2026-04-05 | Nav Durga Traders | Completed | LOOPOUT
45 | 21/0 | DB+6 | FS | PIPE TYPE EARTHING | 2026-04-05 | Nav Durga Traders | Completed | LOOP IN
46 | 33/0 | 4DD+0 | PS | PIPE TYPE EARTHING | 2026-04-14 | Nav Durga Traders | Completed | LOOPOUT
47 | 26/2 | 4DA+6 | PS | PIPE TYPE EARTHING | 2026-04-15 | Nav Durga Traders | Completed | LOOP IN
48 | 44/0 | 4DD+6 | FS | PIPE TYPE EARTHING | 2026-04-20 | Nav Durga Traders | Completed | LOOPOUT
49 | 33/1 | 4DA+0 | PS | PIPE TYPE EARTHING | 2026-04-26 | Nav Durga Traders | Completed | LOOPOUT
50 | 11/1 | 4DA+0 | PS | PIPE TYPE EARTHING | 2026-04-26 | Dharmendra Mishra | Completed | LOOP IN
51 | 38/0 | 4DD+6 | FS | PIPE TYPE EARTHING | 2026-04-25 | Nav Durga Traders | Completed | LOOPOUT
52 | 4/0 | DB+3 | PS | PIPE TYPE EARTHING | 2026-05-25 | Dharmendra | Completed | LOOPOUT
53 | 7/1 | DA+0 | PS | PIPE TYPE EARTHING | 2026-06-02 | Dharmendra | Completed | LOOP IN
54 | 27/2 | DA+0 | PS | PIPE TYPE EARTHING | 2026-06-06 | Nav Durga Traders | Completed | LOOP IN
55 | 27/1 | DA+6 | PS | PIPE TYPE EARTHING | 2026-06-06 | Nav Durga Traders | Completed | LOOP IN
56 | 8/0 | DB+0 | PS | PIPE TYPE EARTHING | 2026-06-11 | AR | Completed | LOOP IN
57 | 7/2 | DA+0 | PS | PIPE TYPE EARTHING | 2026-06-11 | AR | Completed | LOOP IN
Formulas:
Date of Earthing = [Date of Earthing, row above]+4

## Earthing Balance (hidden)
220 KV D/C Chapra -Gopalganj Transmission Line with ACSR Zebra Conductor
Sr No. | Location No. | Tower Type | Classification | Sub Contractor Name | Remarks
2 | 100/0 | DC+0 | PS | UKC
37 | 102/0 | DC+0 1MRC | FS | Construction Wala
9 | 102/1 | DA+3 1MRC | FS | UKC
21 | 102/2 | DA+6 1MRC | FS | UKC
17 | 102/3 | DA+3 1MRC | FS | UKC
14 | 102/4 | DA+6 1MRC | PS | UKC
28 | 103/0 | DD+9 1MRC | PS | UKC
25 | 104/0 | DD+0 | PS | UKC
30 | 104/4 | DA+0 1MRC | FS | Anmol
36 | 104/5 | DA+3 | FS | Anmol
20 | 105/0 | DC+6 | FS | Anmol
22 | 105/1 | DA+3 | FS | Anmol
40 | 105/2 | DA+6 | FS | Anmol
42 | 106/0 | DD+9 | PS | Construction Wala
1 | 108/0 | DD+3 | PS | UKC
5 | 110/2 | DA+3 | FS | Shakti
4 | 113/0 | DD+3 (1MRC) | FS | Shakti
6 | 113/1 | DA+6 1MRC | PS | Shakti
10 | 120/1 | DA+6 | FS | Shakti Construction
19 | 132/6 | DA+3 | FS | Hetansh
11 | 133/1 | DA+3 | FS | Hetansh
8 | 133/2 | DA+3 | PS | Hetansh
29 | 139/0 | DD+25 | FS | Shakti
43 | 146/0 | DC+6 | PS | shakti
38 | 151/1 | DA+6 | PS | Hetansh
32 | 152/0 | DC+3 | PS | AR Construction
26 | 152/1 | DA+3 | PS | AR Construction
15 | 152/3 | DA+6 | PS | AR Construction
7 | 153/0 | DD+18 | PS | AR Construction
13 | 154/0 | DD+18 | FS | AR Construction
18 | 154/1 | DA+6 | PS | AR Construction
24 | 154/3 | DA+0 | FS | AR Construction
12 | 54/0 | DD+3 1MRC | FS | Maa
16 | 54/1 | DA+3 1MRC | FS | Maa
33 | 62/2 | DA+6 | FS | Maa
35 | 62A/0 | DB+3 | FS | Maa
31 | 63/0 | DD+0 | FS | Maa
27 | 63/1 | DA+3 | FS | Maa
23 | 64/2 | DA+0 | FS | Maa
41 | 79/0 | DC+6 | FS | Suman Singh
34 | 80/1 | DA+0 1MRC | FS | Tarush
3 | 87/0 | DD+3 | FS | Dharmendra Mishra
39 | 89/1 | DA+3 | PS | Dharmendra Mishra
220 KV Chhapra(NEW) to Amnour DCDS Transmission Line with Twin Moose
Sr No. | Location No. | Tower Type | Classification | Sub Contractor Name | Remarks
1 | 8/0 | 2TDC+0 | WET | Navdurga
2 | 3/1 | 2TDD+9 | PS | Navdurga
3 | 13/0 | DD+18 | FS | Navdurga
4 | 14/0 | DD+25 | PS | Navdurga
5 | 3/0 | 2TNMD+0 | FS | Navdurga
6 | 2/0 | 2TNMD+0 | FS | Navdurga
400 KV LILO
Sr No. | Location No. | Tower Type | Classification | Sub Contractor Name | Remarks
1 | 19/4 LI | 4DA+0 | PS | Navdurga Traders-2
2 | 11/2 LI | DA+0 | PS | Rajeshwar Singh
3 | 28/1 LO | DA+6 | PS | Nav Durga Traders
4 | 39/3 LO | DA+0 | FS | Nav Durga Traders
5 | 23/0 LO | DB+0 | PS | Raajeshwar Singh
6 | 22/0 LO | DB+6 | PS | Raajeshwar Singh
7 | 20/0 LO | 4DD+0 | PS | Dharmendra Mishra
8 | 23/1 LO | DA+0 | PS | Raajeshwar Singh
9 | 11/3 LI | DA+0 | PS | Dharmendra Mishra
10 | 19/3 LI | DA+0 | PS | Raajeshwar Singh
11 | 12/1 LI | DA+9 | WET | Dharmendra Mishra
12 | 39/1 LO | DA+6 | FS | Nav Durga Traders
13 | 39/2 LO | DA+3 | FS | Nav Durga Traders
14 | 21/0 LO | DC+9 | PS | Raajeshwar Singh
15 | 39/4 LO | DA+3 | FS | Nav Durga Traders
16 | 25/1 LI | DA+3 | PS | Dharmendra Mishra
17 | 39/5 LO | DA+3 | FS | Nav Durga Traders
18 | 26/1 LI | DA+3 | PS | Dharmendra Mishra
19 | 37/0 | DD+9 | FS | Nav Durga Traders
20 | 27/3 | DA+0 | PS | Dharmendra
21 | 45/0 | DD+3 | FS | Nav Durga Traders
22 | 20/1 | DA+6 | FS | Nav Durga Traders
23 | 18A/0 | DD+3 | PS | Rajeshwar Singh
24 | 20/0 LI | DC+0 | PS | Nav Durga Traders
25 | 5/0 LO | DD+0 | PS | Rajeshwar Singh

## Statutary
Details of SH,NH & Railway Line crossing Proposals of TB-412 TL | [6 empty] | 24.06.2026
SH & NH Crossings
S. No. | TL Name | Name of NH being crossed | between AP nos. | Proposal to be submitted by M/s KEC on dated | Responsible Person | Remarks
1 | 400 LILO | NH-722 | AP4-AP5 (LOOP IN) | Profile prepared; will be submitted to BSPTCL on 20.05.2026 | Ravi Ranjan & Umashankar | After Visit of Project director NHAI revised proposal submition required
2 |  | NH-722 | AP12-AP13 (LOOP OUT) | Submitted on NH-Chapra as on 25.03.2026; Revised proposal under discussion with BSPTCL.
3 | 220SZ CHP-GOP | SH-47 Siwan-Barharia (Under Construction NH-227A) | AP37-AP38 |  |  | Foundation Completed
4 |  | Under Construction NH-227A | 61/6-AP-62/0 | Submitted to Chapra NHAI office ON 11-06-2026 | Swarashish Sasmal & Uttam Rai | Joint Site Visit with NHAI schedule by 28.06.2026
5 |  | NH-331 | AP109-AP110
Railway Line Crossings
S. No. | TL Name | Name of name Railway line being crossed | between AP nos. | Proposal to be submitted by M/s KEC on dated | Responsible Person | Remarks
1 | 400 LILO | Railway Crossing (Under Construction) LOOP IN | AP-6-1 to AP-7 | Proposal not required to be submitted as discussed with BSPTCL. Detailed survey profile submitted | Ravi Ranjan | Corridore details are received from Railway on 17.03.2026 Revise detailed survey submitted to BSPTCL site office on 08.05.2026
2 |  | Railway Crossing (Under Construction) LOOP OUT | AP-14 to AP-15
3 | 220SZ CHP-GOP | Railway Crossing | AP-6/0 to AP-7 | In M/C section | Swarashish
4 |  | Railway Crossing, OHE Pole - 17/31 & 17/29 | AP-72 to AP-73 | Submitted to BSPTCL Site on 11-05-2026 |  | Proposal Signed by BSPTCL EEE and Letter issue to DRM Varanasi Division
5 |  | Railway Track | AP-128 to AP-129
Pipe Line Crossings
S. No. | TL Name | Name of name Railway line being crossed | between AP nos. | Proposal to be submitted by M/s KEC on dated | Responsible Person | Remarks
1 | 220SZ CHP-GOP | IOCL | AP-60A to AP-60B | Will be submitted by 30.06.2026 | Swarashish
Details of Power Line Crossing Proposals of TB-412 TL
S. No. | TL Name | Name of Powerline being crossed | Between AP nos. | Proposal to be submitted by M/s KEC on dated | Responsible Person | Remarks
1 | 220TM CHP-AMN | 220kV D/C OHTL BGCL HJP-CHP | AP13- AP14 | Proposal Submitted to BSPTCL SIte 09.02.2026 | Ravi Ranjan | Approved
2 |  | 220kV D/C OHTL BSPTCL ANR-MZP | AP14-AP15
3 | 400 LILO | 220kV D/C OHTL BGCL (HJP- CHP) | AP16-AP17 (LOOP IN)
4 |  | 220kV D/C OHTL BGCL (HJP- CHP) | AP17-AP18 (LOOP OUT)
5 | 220SZ CHP-GOP | 400 KV DC MTH-Gorakhpur TL Tow.No.179-180 DMTCL | 23/0 To 24/0 GANTRY1-GANTY2 |  | Swarasish | Route diverted due to pond,Detail survey pending due to ROW
6 |  | 400 KV DC Barh-MTH TL Tow.30-31 DMTCL | 26/0 TO 27/0 GANTRY3-GANTY4 |  | Swarasish & Uttam
7 |  | 132KV D/C (MSK-SIW) BSPTCL | AP61-AP61/1 | Proposal Submitted to BSPTCL SIte 09.02.2026 |  | Approved
8 |  | 800KV HVDC (GPJ-GKP) TWR No-86,87 | 68/1-68/2 | Submitted to PGCIL Muzzafarpur on 02.04.2026 | Uttam | Approved
9 |  | 400KV D/C (BAR-GKP) TWR No - 430, 431 PGCIL | 71A/0-71B/0
10 |  | 132KV D/C (CHO-SWN) BGCL Line TWR No - 92 & 93, 66kV S/C H.F. | AP92-AP93 | Proposal Submitted to BSPTCL Site 09.02.2026 | Uttam | Approved
11 |  | 132KV D/C BSPTCL CPRN-EKMA Line TWE - 71 & 70 | AP111A-AP112
12 |  | 132KV D/C OHTL BSPTCL TWR-34/2 & 35/0 | AP121-AP122
13 |  | 132KV D/C OHTL BGCL TWR- 47&48 | AP138-AP139
14 |  | 220KV D/C OHTL BSPTCL TWR- 37&38 | AP141-AP142
15 |  | 220KV D/C CPR-VSL BSPTCL Line TWR- 23&24 | AP153-AP154

## Power line Crossings (hidden)
DETAILS OF POWER LINE CROSSING
Sr. No. | Crossing Location |  | Crossing Span | Details of crossing | Owner | Status of proposal |  | Foundation | [5 empty] | Erection |  |  |  |  | Stringing | [5 empty] | Remarks/ Critical Needs
[8 empty] | Target |  | Requirement |  |  |  | Target |  | Material Availability |  |  | Target |  | Material Availability
| From | To |  |  |  | Submission | Approval | Start | End | Stub | Steel | Cement | Gang | Start | End | Tower | BNA | Gang | Start | End | Conductor | Insulator | H/ware | Gang
1 | AP-121 | AP-122 | 290 | 220 kV D/C Bansur 220 Kv Sub Station - Khelana T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | Comp | MANTU YADAV
2 | AP-127 | AP-128 | 298 | 132 Kv S/C Bansur 132 kv Sub Station- Bansur 220 kv Sub Station TL | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | Comp | INDADUL
3 | AP-129 | AP-130 | 302 | 132 kv D/C 1:- CktI Bansur 220 kv Sub Station - Bansur 132 kv Sub Station T/L, 2:- CktII Bansur 220 kv Sub Station -Narayanpur T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | Comp | U.K. Enterprise
4 | AP-147 | AP-148 | 250 | 220 kv S/C Alwar - Bansur 220 kv Sub Station T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp |  | Comp | Comp | Comp | Comp |  | Comp | Comp | Comp | Comp | Comp | MANTU YADAV
5 | AP-155 | AP-156 | 293 | 132 KV S/C Khairthal - Mundawar T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp |  | Comp | Comp | Comp | Comp | Comp | MANTU YADAV
6 | AP-166 | AP-167 | 274 | 132 KV S/C Kishangarh - Pur Kot Kasim T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp | Comp | MANTU YADAV
7 | AP-167 | AP-168 | 289 | 220 KV D/C 1.Ckt-Kishangarh-Khushkhera & 2.Ckt- Alwar-Bhiwandi T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp |  | Comp | Comp | Comp | Comp | Comp | MANTU YADAV
8 | AP-168 | AP-169 | 248 | SH-25 & 132 KV S/C Kishangarh- Tijara T/L | RVPNL | Submitted | Approved by RVPNL | Comp | Comp | Comp | Comp | Comp | - | Comp | Comp | Comp | Comp |  | Comp | Comp | Comp | Comp | Comp | MANTU YADAV