## DPR-Summary
LINE NAME- 765 kV D/C HEXA BEAWAR MANDSAUR TRANSMISSION LINE
CLIENT-POWERGRID BEAWAR MANDSAUR TRANSMISSION LIMITED
DAILY PROGRESS REPORT (TA-505)
NOA Date :- 22-July-2024 |  |  |  | Completion Date :- 21-June-2026 |  |  |  |  | Date:- 2nd March 2026.
SUPPLY VALUE = 458.32 Cr. |  |  |  | SERVICE VALUE = 94.23 Cr. |  |  |  |  | F&I VALUE = 9.48 Cr.
PARTICULARS | UOM | Total | Comp | Balance | March'26 |  | WIP | Cumulative | April'26 | May'26 | Remarks
|  | Qty | Till | as on | Plan | Actual |  |  | Plan | Plan
|  |  | 2026-02-01 | 1st Feb-26
Detail Survey | KM | 139.6 | 139.6 | 0
Check Survey | KM | 139.6 | 139.6 | 0
Stub Supply | SET | 379 | 371 | 8 |  | 0 |  | 371
FOUNDATION | NOS | 379 | 356 | 23 | 15 | 0 | 15 | 356 | 8 |  | 10 Locations are under severe RoW.
No of Gangs |  |  |  |  | 3
Tower Supply | SETS | 379 | 359 | 20 |  |  |  | 359
TOWER ERECTION | NOS | 379 | 300 | 79 | 26 | 1 | 8 | 301 | 50
No of Gangs |  |  |  |  | 8
AL59 Zebra Conductor Supply | KM | 4970.6 | 4090 | 880.6 |  |  |  | 4090
Earthwire Supply | KM | 138 | 138 | 0 |  |  |  | 138
Insulator Supply | EA | 16332 | 12823 | 3509 |  | 2689 |  | 15512
Hardware Fittings Supply | % | 100% | 90% | 10% |  |  |  | 90%
Stringing (Final Sag) | KM | 139.6 | 6.55 | 133.05 | 20 |  |  | 6.55 | 30
Stringing (Rough Sag) | KM | 139.6 | 6.55 | 133.05 | 20 |  |  | 6.55 | 30
TSE Gangs |  |  |  |  | 1
Manual Gangs |  |  |  |  | 1
Revetment | CUM
Gang

## Sheet1 (hidden)
TYPE OF TOWERS | NO OF TOWERS
DA+0 DFR | 24
DA+0 DRY | 13
DA+0 WET | 4
DA+0 WFR | 18
DA+3/6/9 DRY | 11
DA+3/6/9 DFR | 25
DA+3/6/9 WET | 5
DA+3/6/9 WFR | 17
TOTAL DA TYPE | 117
DB1+0 DRY | 2
DB1+3/6/9 DFR | 1
DB1+3/6/9 WET | 2
DB2+0 DFR | 2
DB2+0 DRY | 1
DB2+0 WFR | 1
TOTAL DB TYPE | 9
DC1+0 DFR | 1
DC1+0 WFR | 1
DC1+3/6/9 DFR | 1
DC2+0 WET | 1
DC2+3/6/9 DFR | 1
DC2+3/6/9 DRY | 1
DC2+3/6/9 WFR | 1
TOTAL DC TYPE | 7
DD45+0 DFR | 2
DD45+9 DFR | 1
DD45+9 WFR | 1
DD60+18 DFR | 1
DD60+9 WFR | 2
TOTAL DD TYPE | 7
TOTAL TOWERS | 140

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TA 505 | 765 Kv D/C Beawar-Mandsaur T/L | PBMTL | 22-07-2024 | 21-06-2026 | Mr. Partha Pratim Pal | Mr. Nabajit Baruah | Mr. Nabajit Baruah | Mr. Sushil Kr Tiwari | Mr.Deepak Anand | Nunuchand Mahto
[9 empty] | Mr.Bapan Mandal | Birkha Subba
[9 empty] | Mr.Panneri Satish | Dilip Kumar
[9 empty] | Mr. Varun Mishra | Teklal Mahato
Munid Meena
Mortuj Ali
Devdas Malik
Jayprakash Nishad
Kumar Singh
K. Sanjeevan
Mridul Baruah
Binda Shah
Prasanta Sahana
Lalit Sahoo
Mahendra Narnaware
Ramprasad
Gourshankar
Vipin Mall
Aadesh
Parmeswar Mahto
Rajkumar S

## Foundation
765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE
PROGRESS SUMMARY DETAIL
NOA Date: 22-July-2024 | [6 empty] | Completion Date : 21-June-2026 |  |  |  | Date : 27-05-25
SUPPLY VALUE = 458 Cr. | [6 empty] | SERVICE VALUE = 94.23 Cr. |  |  |  | F&I VALUE = 9.48 Cr. | [5 empty] | 561.71
Sr. No. | Activity |  | UOM |  | Total Qty. | L2 Qty. | Completed | Balance | Submitted | WIP | Remarks
1 | Details Survey |  | Kms |  | 136.705 | 126 | 126.324 | 10.381 | 10.381
2 | Check Survey |  | Kms |  | 136.705 | 126 | 108.679 | 28.026
3 | Soil Testing |  | Nos |  | 34 | 34
4 | Foundation |  | Nos |  | 371 | 165 | 356 | 15 |  | 0
| Gang |  | Nos |  |  |  | 13
| Manpower |  | Nos
5 | Earthing |  | Nos |  | 346 |  | 94 | 252
6 | Erection |  | Nos |  | 371 | 98 | 301 | 70 |  | 0
| Gang |  | Nos |  |  |  | 4
| Manpower |  | Nos
7 | Stringing |  | Nos |  | 136.705 | 0 | 0 | 136.705
| Gang |  | Nos
| Manpower |  | Nos
Issue : i. DS - pending for approval ii. CS - pending for approval
Supply : Stub : DA : 177 Set, DB : 21 Set, DC : 16 Set, DD45 : 9 Set, DD60 : 13 set Earthing : CP : 84 Set, Pipe : 40 Nos, Rod : 40 Nos Tower : DA BB=107 Set,+0M=52, +3M=35,+6M=19, +9M=3, -1.5=6, -3=14
KEC INTERNATIONAL LIMITED
FOUNDATION DETAIL OF 765KV D/C BEAWAR-MANDSAUR TR LINE
Sr. No | Loc No. | Type of Tower | TOF | Region | Selector | Cement (Bags) |  |  | Conc Vol |  | Excv Vol(m3) | R/F (KG) | Wt of Stub(MT) | Rev(Inr) | Month of Execution | Sub Contractor | Status | Excavation |  | Casting |  | Remarks if any
[6 empty] | RCC | PCC | Toal Cement | M 20(m3) | M 10(m3) | [7 empty] | Start | Completion | Start | Completion
Total = | [5 empty] | 125897.632 | 6532.0004 | 132429.6324 | 15724.169 | 1463.911 | 96505.589 | 1032821.91 | 395.4325 | 307074973.8626 |  |  | 356
| 101/2 | DA+9 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-10-01 | RST | Complete | 2024-09-11 | 2024-09-26 | 2024-10-02 | 2024-10-06 |  | 1
| 100/0 | DD45+0 | WET | RAJ |  | 1239.68 | 70.18 | 1309.86 | 154.96 | 15.95 | 1192.7 | 15096 | 2.495 |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-16
| 101/0 | DC1+3 | DFR | RAJ |  | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 | 2025-05-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-31
| 101/1 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | RST | Complete | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-14 |  | 2
| 101/3 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-10-01 | RST | Complete | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-11 |  | 1
| 101/4 | DA+6 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-10-01 | RST | Complete | 2024-09-16 | 2024-09-21 | 2024-10-19 | 2024-10-21 |  | 1
| 101/5 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-10-01 | RST | Complete | 2024-09-22 | 2024-09-26 | 2024-10-23 | 2024-10-25 |  | 1
| 101/6 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | RST | Complete | 2024-10-24 | 2024-10-26 | 2024-10-30 | 2024-11-02 |  | 1
| 101/7 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | RST | Complete | 2024-11-10 | 2024-11-14 | 2024-11-17 | 2024-11-18 |  | 2
| 101/8 | DA-3 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2024-11-01 | RST | Complete | 2024-10-28 | 2024-11-02 | 2024-11-07 | 2024-11-08 |  | 2
| 102/0 | DC2+3 | DRY | RAJ | DC2+9 DRY | 856 | 38 | 894 | 106.91 | 8.53 | 653.08 | 5502 | 2.3488 | 2257063.7747 | 2024-12-01 | RST | Complete | 2024-11-22 | 2024-11-25 | 2024-12-11 | 2024-12-14 |  | 3
| 103/0 | DC1+6 | DFR | RAJ |  | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 | 2025-05-12 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-22
| 103/1 | DA+0 | DRY | RAJ |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-05-07 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-11
| 103/2 | DA+0 | DRY | RAJ |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-13
45 | 103/3 | DA+0 | DFR | RAJ |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-08
| 103/4 | DA+0 | DRY | RAJ |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | APRIL-25 | Rajesh Suwalkar | Complete |  |  |  | 2025-04-22
1 | 103/5 | DA+3 | DFR | RAJ |  | 287.84 | 13.222 | 301.062 | 35.98 | 3.005 | 172.05 | 2466.9 | 0.957 |  | 2025-11-01 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-14 | Hold
| 103/5A | DD60+0 | DFR | RAJ |  | 988.64 | 48.18 | 1036.82 | 123.58 | 10.95 | 692 | 10940 | 3.159 | 3395120.3851 | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-03
| 103/5A1 | DA-3 | DFR | RAJ |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-05
2 | 103/6A | DD45+0 | DRY | RAJ |  | 864 | 45.364 | 909.364 | 108 | 10.31 | 783 | 9428 | 2.4947 | 2836089.3524 | 2025-05-03 | Sumit Const/Om Prakash | Complete | 2025-01-18 |  |  | 2025-05-18 | Hold
| 103/7 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Rajesh Suwalkar | Complete | 2025-01-05 | 2025-01-10 | 2025-01-11 | 2025-01-15
| 103/8 | DA+3 | DRY | RAJ |  | 267.36 | 13.86 | 281.22 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 705045.3467 | 2025-05-12 | Sumit Const/Om Prakash | Complete | 2025-05-22 |  |  | 2025-05-24
| 103/9 | DA+3 | WET | RAJ |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-19
11 | 104/0 | DD45+3 | DFR | RAJ | DD45+9 DFR | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 | 2025-02-01 | Rajesh Suwalkar | Complete | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-07
| 104/1 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-11-01 | RST | Complete | 2024-11-17 | 2024-11-19 | 2024-11-25 | 2024-11-27 |  | 2
| 104/2 | DA-3 | WET | RAJ | DA+0 WET | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 | 2024-12-01 | Ashutosh Infra | Complete | 2024-11-15 | 2024-11-18 | 2024-11-29 | 2024-12-03 |  | 3
| 105/0 | DC1+0 | WFR | RAJ | DC1+0 WFR | 916 | 42 | 958 | 114.5 | 9.44 | 591.37 | 5795 | 2.3488 | 2671411.6827 | 2024-11-01 | RST | Complete | 2024-11-20 | 2024-11-21 | 2024-11-29 | 2024-11-30 |  | 3
| 105/1 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Ashutosh Infra | Complete | 2024-10-10 | 2024-11-04 | 2024-11-12 | 2024-11-19 |  | 2
| 106/0 | DD60+0 | DFR | RAJ |  | 988.64 | 48.18 | 1036.82 | 123.58 | 10.95 | 692 | 10940 | 3.159 | 3395120.3851 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-22
| 108/0 | DD45+0 | DRY | RAJ |  | 864 | 45.364 | 909.364 | 108 | 10.31 | 783 | 9428 | 2.4947 | 2836089.3524 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-27
| 108/1 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-12-01 | Lotus Const. | Complete | 2024-10-20 | 2024-11-27 | 2024-12-08 | 2024-12-13 |  | 3
| 108/2 | DA-3 | WET | RAJ | DA+0 WET | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 | 2024-11-01 | Lotus Const. | Complete | 2024-10-26 | 2024-11-16 | 2024-11-29 | 2024-11-30 |  | 2
| 108/3 | DA-3 | WET | RAJ | DA+0 WET | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 | 2024-12-01 | Rajesh Suwalkar | Complete | 2024-12-07 | 2024-12-11 | 2024-12-14 | 2024-12-19 |  | 3
| 108/4 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-10-01 | Manirul Khan/Tower Foundation | Complete | 2024-10-17 | 2024-10-20 | 2024-10-27 | 2024-10-28 |  | 2
| 109/0 | DC1+0 | DFR | RAJ | DC1+0 DFR | 611 | 28 | 639 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 | 2024-12-01 | Rajesh Suwalkar | Complete | 2024-12-22 | 2024-12-25 | 2024-12-29 | 2024-12-31 |  | 4
| 109/1 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-10-01 | Rajesh Suwalkar | Complete | 2024-10-03 | 2024-10-13 | 2024-10-26 | 2024-10-29 |  | 2
| 109/2 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-10-01 | Rajesh Suwalkar | Complete | 2024-09-09 | 2024-09-25 | 2024-10-01 | 2024-10-07 |  | 1
| 109/3 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Rajesh Suwalkar | Complete | 2024-11-08 | 2024-11-23 | 2024-11-29 | 2024-11-30 |  | 3
1 | 109/4 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2025-02-01 | Rajesh Suwalkar | Complete | 2025-02-10 | 2025-02-16 | 2025-02-15 | 2025-02-17
| 110/0 | DC2+3 | WFR | RAJ | DC2+9 WFR | 1065 | 50 | 1115 | 133.07 | 11.19 | 707.57 | 8267 | 2.3488 | 3282540.8247 | 2024-12-01 | Aadinath | Complete | 2024-11-25 | 2024-11-29 | 2024-12-12 | 2024-12-17 |  | 3
| 110/1 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Surya Enterprise | Complete | 2024-10-08 | 2024-10-22 | 2024-11-18 | 2024-11-22 |  | 2
| 110/2 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Aadinath | Complete | 2024-11-10 | 2024-11-19 | 2024-11-25 | 2024-11-29 |  | 3
| 110/3 | DA+3 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2024-11-01 | Aadinath | Complete | 2024-11-06 | 2024-11-10 | 2024-11-14 | 2024-11-17 |  | 2
| 110/4 | DA+3 | DFR | RAJ |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-06-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-06-07
| 110/5 | DA+3 | WET | RAJ | DA+9 WET | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 | 2024-11-01 | Soham Const. | Complete | 2024-11-06 | 2024-11-10 | 2024-11-21 | 2024-11-23
| 110/6 | DA+0 | WFR | RAJ | DA+9 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-10-01 | Soham Const. | Complete | 2024-10-06 | 2024-10-10 | 2024-10-22 | 2024-10-24 |  | 1
| 110/7 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | Soham Const. | Complete | 2024-10-15 | 2024-11-14 | 2024-11-27 | 2024-11-29 |  | 2
| 110/8 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Soham Const. | Complete | 2024-10-14 | 2024-11-10 | 2024-11-14 | 2024-11-15 |  | 2
2 | 110A/0 | DB2+0 | DFR | RAJ | DB2+0 DFR | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 | 2025-02-01 | Om Prakash | Complete | 2025-02-15 | 2025-02-18 | 2025-02-19 | 2025-02-20
| 110A/1 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | Reshmi Devi | Complete | 2024-10-25 | 2024-11-04 | 2024-11-08 | 2024-11-10 |  | 2
| 110A/2 | DA-1.5 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-10-01 | Surya Enterprise | Complete | 2024-09-28 | 2024-09-30 | 2024-10-07 | 2024-10-11 |  | 1
| 111/0 | DB1+6 | DFR | RAJ | DB1+9 DFR | 471 | 22 | 493 | 58.84 | 4.94 | 296.18 | 2692 | 1.768 | 1324196.9091 | 2025-01-01 | Om Prakash | Complete | 2024-12-29 | 2025-01-02 | 2025-01-03 | 2025-01-04
1 | 111/1 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | Garg Const. | Complete | 2024-10-18 | 2024-10-25 | 2024-10-30 | 2024-11-04 |  | 2
2 | 111/2 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-11-01 | Garg Const. | Complete | 2024-11-01 | 2024-11-13 | 2024-11-15 | 2024-11-18 |  | 2
3 | 111/3 | DA+0 | WET | RAJ | DA+0 WET | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 | 2024-12-01 | Garg Const. | Complete | 2024-11-08 | 2024-11-30 | 2024-11-02 | 2024-12-08 |  | 3
4 | 111/4 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Garg Const. | Complete | 2024-11-27 | 2024-12-12 | 2024-12-14 | 2024-12-16 |  | 3
| 112/0 | DD60+18 | DFR | RAJ | DD60+18 DFR | 1020 | 51 | 1071 | 127.5 | 11.49 | 728 | 11839 | 2.564 | 3567510.026 | 2025-01-01 | Om Prakash | Complete | 2025-01-02 | 2025-01-22 | 2025-01-24 | 2025-01-27
| 113/0 | DD60+9 | WFR | RAJ |  | 1357.44 | 71.28 | 1428.72 | 169.68 | 16.2 | 1042.48 | 21650.28 | 5.559 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-28
| 113/1 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-11-01 | Reshmi Devi | Complete | 2024-11-13 | 2024-11-18 | 2024-11-20 | 2024-11-22 |  | 2
| 113/2 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-11-01 | Reshmi Devi | Complete | 2024-10-29 | 2024-11-12 | 2024-11-14 | 2024-11-14 |  | 2
| 113/3 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-11-01 | Reshmi Devi | Complete | 2024-11-10 | 2024-11-26 | 2024-11-27 | 2024-11-29 |  | 2
| 113/4 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-12-01 | Surya Enterprise | Complete | 2024-12-03 | 2024-12-04 | 2024-12-07 | 2024-12-09 |  | 3
| 113/5 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Reshmi Devi | Complete | 2024-11-22 | 2024-11-30 | 2024-12-04 | 2024-12-05 |  | 3
| 113/6 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Reshmi Devi | Complete | 2024-12-01 | 2024-12-10 | 2024-12-10 | 2024-12-12 |  | 3
| 114/0 | DC2+0 | WET | RAJ | DC2+0 WET | 1233 | 58 | 1291 | 154.01 | 13.15 | 990.19 | 10225 | 2.3488 | 3510320.9327 | 2024-12-01 | Om Prakash | Complete | 2024-12-03 | 2024-12-05 | 2024-12-11 | 2024-12-19 |  | 3
| 114/1 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Jitendra/JSC | Complete | 2024-12-04 | 2024-12-27 | 2024-12-29 | 2024-12-31
| 114/10 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-11-01 | Om Prakash | Complete | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-20 |  | 2
| 114/2 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-12-01 | Jitendra/JSC | Complete | 2024-12-03 | 2024-12-11 | 2024-12-12 | 2024-12-14 |  | 3
| 114/3 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2024-12-01 | Jitendra/JSC | Complete | 2024-11-22 | 2024-11-26 | 2024-12-03 | 2024-12-07 |  | 3
| 114/4 | DA+3 | WFR | RAJ | DA+3 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2025-09-14 | Vikash Cont. | Complete |  |  |  | 2025-09-19
| 114/5 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Yash Infra | Complete | 2024-12-03 | 2024-12-05 | 2024-12-06 | 2024-12-07 |  | 3
| 114/6 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-11-01 | Yash Infra | Complete | 2024-11-19 | 2024-11-26 | 2024-11-29 | 2024-11-30 |  | 2
| 114/7 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-11-01 | Yash Infra | Complete | 2024-11-14 | 2024-11-22 | 2024-11-25 | 2024-11-28 |  | 2
| 114/8 | DA+6 | WET | RAJ | DA+9 WET | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 | 2024-11-01 | Om Prakash | Complete | 2024-11-14 | 2024-11-20 | 2024-11-22 | 2024-11-23 |  | 2
| 114/9 | DA+3 | WET | RAJ | DA+9 WET | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 | 2024-11-01 | Om Prakash | Complete | 2024-11-17 | 2024-11-22 | 2024-11-26 | 2024-11-27 |  | 2
33 | 115/0 | DD60+3 | DFR | RAJ |  | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 | 3508292.3251 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-03 | 2 PIT EXCAVATION DONE.
30 | 116/0 | DD45+3 | DFR | RAJ | DD45+9 DFR | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-07 | PIT Marking Done.
| 116/1 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-12-01 | Om Prakash | Complete | 2024-12-17 | 2024-12-25 | 2024-12-26 | 2024-12-26 |  | 4
| 116/2 | DA+3 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-12-01 | Om Prakash | Complete | 2024-11-18 | 2024-11-29 | 2024-11-29 | 2024-12-01
9 | 118/0 | DD60+6 | WFR | RAJ | DD60+9 WFR | 1484 | 72 | 1556 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 | 5088278.7391 | 2025-02-01 | Om Prakash/s | Complete | 2025-02-18 | 2025-02-24 | 2025-02-24 | 2025-02-27
31 | 119/0 | DC2+0 | DFR | RAJ |  | 755.6 | 32.296 | 787.896 | 94.45 | 7.34 | 453.17 | 4557 | 2.3488 | 2124325.9997 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-15 | PIT Marking Done.
32 | 120/0 | DD45+3 | DFR | RAJ | DD45+9 DFR | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-12 | PIT Marking Done.
| 120/1 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-01-01 | UDS | Complete | 2024-11-27 | 2024-11-30 | 2025-01-06 | 2025-01-12
| 120/2 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-01-01 | UDS | Complete | 2024-12-25 | 2025-01-27 | 2025-01-29 | 2025-01-30
| 120/3 | DA+9 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2025-01-01 | UDS | Complete | 2024-11-28 | 2024-11-30 | 2025-01-23 | 2025-01-24
| 121/0 | DB1+6 | DRY | RAJ |  | 516.08 | 24.332 | 540.412 | 64.51 | 5.53 | 432.79 | 2988 | 1.768 | 1344129.8151 | 2025-06-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-06-02
| 122/0 | DD60+3 | WFR | RAJ |  | 1483.2 | 71.28 | 1554.48 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-26
| 123/0 | DD60+6 | WFR | RAJ |  | 1483.2 | 71.28 | 1554.48 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-03
| 123/1 | DA+0 | WET | RAJ |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2467 | 0.866 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-08
| 123/2 | DA+0 | WFR | RAJ |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-22
| 123/3 | DA-3 | WFR | RAJ |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-12
| 124/0 | DD45+3 | WFR | RAJ | [10 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-09
| 125/0 | DD60+3 | WFR | RAJ | [10 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-04
| 125/1 | DA+0 | WFR | RAJ |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-15
| 126/0 | DB2+0 | DFR | RAJ | DB2+0 DFR | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 | 2024-12-01 | Om Prakash | Complete | 2024-12-03 | 2024-12-06 | 2024-12-14 | 2024-12-16
| 126/1 | DA+9 (RC) | WFR | RAJ |  | 387.88 | 19.932 | 407.812 | 48.485 | 4.53 | 269.795 | 3205.12 | 0.957 |  | 2025-10-14 | Vikash Cont. | Complete |  |  |  | 2025-10-05
| 126/2 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Om Prakash | Complete | 2025-01-09 | 2025-01-17 | 2025-01-18 | 2025-01-18
| 126/3 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Om Prakash | Complete | 2025-01-11 | 2025-01-16 | 2025-01-20 | 2025-01-20
| 126/4 | DA+9 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Om Prakash | Complete | 2024-12-12 | 2024-12-14 | 2024-12-17 | 2024-12-17 |  | 3
| 127/0 | DD45+0 | DFR | RAJ | DD45+0 DFR | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.495 | 2635411.7904 | 2024-12-01 | Om Prakash | Complete | 2024-12-19 | 2024-12-21 | 2024-12-25 | 2024-12-29 |  | 4
| 127/1 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-14 | 2024-12-18 | 2024-12-20
| 127/2 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-11 | 2024-12-13 | 2024-12-15 |  | 3
| 127/3 | DA+6 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-05 | 2024-12-07 | 2024-12-10 |  | 3
| 128/0 | DC2+9 | DFR | RAJ | DC2+9 DFR | 772 | 34 | 806 | 96.5 | 7.54 | 466 | 4756 | 2.3488 | 2183199.4487 | 2025-01-01 | Om Prakash | Complete | 2025-01-24 | 2025-01-27 | 2025-01-29 | 2025-01-31
| 129A/0 | DD45+0 | DFR | RAJ |  | 740.24 | 39.732 | 779.972 | 92.53 | 9.03 | 564 | 8669 | 2.495 |  | 2025-12-14 | RST | Complete |  |  |  | 2025-12-23
16 | 129A/1 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Om Prakash | Complete | 2025-02-07 | 2025-02-09 | 2025-02-11 | 2025-02-11
17 | 129A/2 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Om Prakash | Complete | 2025-02-03 | 2025-02-08 | 2025-02-10 | 2025-02-10
15 | 129A/3 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-02-01 | Om Prakash | Complete | 2025-01-02 | 2025-02-02 | 2025-02-06 | 2025-02-06
18 | 130/0 | DB2+0 | WFR | RAJ | DB2+0 WFR | 805 | 39 | 844 | 100.6 | 8.84 | 552.01 | 5686.38 | 1.768 | 2438641.2023 | 2025-02-01 | Om Prakash | Complete | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-02-14
| 130/1 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-01-01 | Om Prakash | Complete | 2025-01-28 | 2025-01-30 | 2025-01-31 | 2025-01-31
5 | 130/2 | DA-1.5 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-02-01 | Om Prakash | Complete | 2025-02-02 | 2025-02-07 | 2025-02-08 | 2025-02-09
| 131/0 | DD45+9 | WFR | RAJ | DD45+9 WFR | 1212 | 60 | 1272 | 151.38 | 13.48 | 860.33 | 12577 | 2.4947 | 4121357.0384 | 2025-01-01 | Om Prakash | Complete | 2025-01-05 | 2025-01-16 | 2025-01-12 | 2025-01-17
| 132/0 | DD60+6 | DRY | RAJ |  | 1145.12 | 57.024 | 1202.144 | 143.14 | 12.96 | 976 | 12968 | 3.159 | 3663688.3031 | APRIL-25 | RST | Complete |  |  |  | 2025-04-22
| 135/0 | DD45+0 | DFR | RAJ | DD45+0 DFR | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.4947 | 2635411.7904 | 2025-03-01 | RST | Complete | 2025-02-27 | 2025-03-02 | 2025-03-04 | 2025-03-05
19 | 135/1 | DA+3 | DFR | RAJ | DA+0 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-02-08 | 2025-02-10 | 2025-02-16 | 2025-02-17
22 | 135/2 | DA+9 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-02-10 | 2025-02-12 | 2025-02-18 | 2025-02-21
26 | 135/3 | DA+9 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-02-15 | 2025-02-18 | 2025-02-21 | 2025-02-22
| 136/0 | DC2+3 | DFR | RAJ |  | 772 | 33.176 | 805.176 | 96.5 | 7.54 | 466 | 4754 | 2.3488 | 1765260.9827 | APRIL-25 | RST | Complete |  |  |  | 2024-04-28
3 | 136/1 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-02-19 | 2025-02-20 | 2025-02-24 | 2025-02-25
| 136/2 | DA+3 | DFR | RAJ |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-05-03 | RST | Complete |  |  |  | 2025-05-03
| 136/5 | DA+3 | DFR | RAJ | DA+3 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-02-24 | 2025-02-25 | 2025-02-27 | 2025-02-27
| 138/0 | DB1+3 | DFR | RAJ |  | 441.04 | 23.056 | 464.096 | 55.13 | 5.24 | 316.48 | 5978.28 | 2.003 |  | 2025-11-14 | RST | Complete |  |  |  | 2025-11-29
| 138/1 | DA-3 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-10
| 138/3 | DA+3 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete | 2026-02-10 |  |  | 2026-02-12
| 139/0 | DB2+0 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete | 2026-01-31 |  |  | 2026-02-04
| 139/1 | DB1+3 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete | 2026-02-04 |  |  | 2026-02-06
16 | 140/0 | DC1+9 | DFR | RAJ | DC1+9 DFR(RAJ) | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 | 2025-03-01 | RST | Complete | 2025-03-06 |  |  | 2025-03-12
9 | 140/1 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | RST | Complete | 2025-01-16 | 2025-01-27 | 2025-02-04 | 2025-02-05
| 141/0 | DD45+0 | DFR | RAJ |  | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.495 | 2635411.7904 | 2025-05-08 | RST | Complete |  |  |  | 2025-05-13
| 142/0 | DD45+3 | DRY | RAJ |  | 882.48 | 46.904 | 929.384 | 110.31 | 10.66 | 809 | 9896 | 2.4947 | 2836089.3524 | 2025-05-12 | RST | Complete |  |  |  | 2025-05-20
18 | 144A/0 | DD45+6 | WET | RAJ | DD45+6 WET(RAJ) | 1264.64 | 72.248 | 1336.888 | 158.08 | 16.42 | 1226.53 | 15882 | 2.4947 | 4266794 | 2025-03-01 | RST | Complete |  |  |  | 2025-03-22
| 144A/1 | DA+0 | WFR | RAJ | DA+0 WFR | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 | 2025-01-01 | RST | Complete | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-16
27 | 144A/2 | DA+3 | DRY | RAJ | DA+3 DRY (RAJ) | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2025-03-01 | RST | Complete |  |  |  | 2025-03-28 | 4 Pit EXCAVATION DONE
| 144A/3 | DB1+3 | WET | RAJ | DB1+9 WET | 759 | 41 | 800 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 | 2154107.4571 | 2025-01-01 | RST | Complete | 2025-01-02 | 2025-01-04 | 2025-01-18 | 2025-01-19
| 145/0 | DD60+18 | WFR | RAJ |  | 1497.12 | 72.38 | 1569.5 | 187.14 | 16.45 | 1059.44 | 18021 | 2.564 | 5283315.042 | 2025-09-14 | RST | Complete |  |  |  | 2025-09-14
| 146/1 | DA+9 | DFR | RAJ-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-25
39 | 147/0 | DB2+6 | DFR | RAJ |  | 566.48 | 25.564 | 592.044 | 70.81 | 5.81 | 356.96 | 3466 | 1.7681 | 1649958.0771 | 2025-03-01 | RST | Complete |  |  |  | 2025-03-31
| 147/1 | DA+9 | WET | RAJ | DA+9 WET | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 | 2025-01-01 | RST | Complete | 2024-12-14 | 2024-12-16 | 2025-01-04 | 2025-01-05
46 | 147A/0 | DB1+0 | DFR | RAJ |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 | APRIL-25 | RST | Complete |  |  |  | 2025-04-10
| 147A/1 | DA-1.5 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2024-12-01 | RST | Complete | 2024-12-11 | 2024-12-13 | 2024-12-27 | 2024-12-27 |  | 4
| 147A/2 | DA+6 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-12-01 | RST | Complete | 2024-12-01 | 2024-12-03 | 2024-12-29 | 2024-12-31 |  | 4
| 147A/3 | DA+6 | DFR | RAJ | DA+6 DFR (RAJ) | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | APRIL-25 | RST | Complete |  |  |  | 2025-04-10
| 147A/4 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | RST | Complete | 2024-12-01 | 2024-12-05 | 2024-12-18 | 2024-12-19 |  | 3
| 147A/5 | DA+9 | WFR | RAJ | DA+9 WFR | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 | 2024-12-01 | RST | Complete | 2024-12-10 | 2024-12-13 | 2024-12-22 | 2024-12-24
| 148/0 | DD60+6 | WFR | RAJ | DD60+9 WFR | 1484 | 72 | 1556 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 | 5088278.7391 | 2025-01-01 | RST | Complete | 2025-01-02 | 2025-01-22 | 2025-01-28 | 2025-01-31
3 | 148/1 | DA+0 | DRY | RAJ |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | APRIL-25 | RST | Complete |  |  |  | 2025-04-12 | PIT Marking Done.
14 | 148A/0 | DB1+6 | WET | RAJ | DB1+9 WET | 759 | 41 | 800 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 | 2154107.4571 | 2025-02-01 | RST | Complete | 2025-02-02 | 2025-02-04 | 2025-02-09 | 2025-02-13
| 148B/1 | DA+0 | DFR | RAJ-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-29
| 148B/2 | DA+6 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-15
| 149/0 | DD45+9 | DFR | MP-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-13
| 149/1 | DA+3 | DFR | MP-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-18
| 149/2 | DA+9 | DFR | MP-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-16
| 149A/0 | DC2+18 | DFR | MP-Forest | [10 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-31
| 149B/0 | DB1+25 | WFR | RAJ |  | 632.8 | 31.988 | 664.788 | 79.1 | 7.27 | 448.4 | 4194 | 1.753 |  | 2025-12-14 | RST | Complete |  |  |  | 2025-12-31
| 149B/1 | DB2+15 | WFR | RAJ |  | 759.04 | 36.256 | 795.296 | 94.88 | 8.24 | 512.32 | 4906 | 1.714 |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-09
| 149B/2 | DA+6 | DFR | RAJ |  | 274.64 | 13.1428 | 287.7828 | 34.33 | 2.987 | 170.915 | 2277.88 | 0.968 |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-15
| 149B/3 | DA+3 (RC) | DFR | RAJ |  | 292.96 | 13.398 | 306.358 | 36.62 | 3.045 | 175.709 | 2610.33 | 1.014 | 752440.0941 | 2025-09-14 | RST | Complete |  |  |  | 2025-09-27
| 149B/4 | DA+0 (RC) | DFR | RAJ |  | 261.32 | 11.946 | 273.266 | 32.665 | 2.715 | 152.99 | 2587.74 | 1.139 |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-17
| 150/0 | DC1+0 | DFR | RAJ |  | 611 | 28 | 639 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 | 2025-05-14 | RST | Complete |  |  |  | 2025-05-31
| 150/1 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Yash Infra | Complete | 2025-01-02 | 2025-01-04 | 2025-01-09 | 2025-01-12
| 150/2 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Yash Infra | Complete | 2025-01-04 | 2025-01-17 | 2025-01-19 | 2025-01-22
| 150/3 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Yash Infra | Complete | 2024-12-12 | 2024-12-17 | 2024-12-19 | 2024-12-21 |  | 3
| 150/4 | DA+6 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2024-12-01 | Yash Infra | Complete | 2024-12-15 | 2024-12-19 | 2024-12-22 | 2024-12-24 |  | 4
| 150/5 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Yash Infra | Complete | 2024-12-15 | 2024-12-27 | 2024-12-27 | 2024-12-28 |  | 4
| 151/0 | DD45+3 | DFR | RAJ |  | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 | 2025-06-14 | RST | Complete |  |  |  | 2025-06-29
| 152/0 | DD60+3 | DFR | RAJ |  | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 | 3508292.3251 | 2025-06-14 | RST | Complete |  |  |  | 2025-06-11
| 152/1 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Aadinath | Complete | 2024-12-14 | 2024-12-15 | 2024-12-29 | 2024-12-30
| 152/2 | DA-3 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2024-12-01 | Aadinath | Complete | 2024-12-14 | 2024-12-15 | 2024-12-25 | 2024-12-26 |  | 4
| 152/3 | DA-1.5 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-01-01 | Aadinath | Complete | 2024-12-17 | 2024-12-18 | 2025-01-24 | 2025-01-25
| 152A/0 | DB1+0 | DRY | RAJ | DB1+0 DRY | 512 | 25 | 537 | 63.98 | 5.47 | 428.13 | 2899 | 1.768 | 1325884.4911 | 2025-01-01 | Reshmi Devi | Complete | 2025-01-01 | 2025-01-02 | 2025-01-14 | 2025-01-17
| 152A/1 | DA-3 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-01-01 | Reshmi Devi | Complete | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-10
| 152A/10 | DA+0 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-01-01 | Saktawat | Complete | 2025-01-18 | 2025-01-22 | 2025-01-25 | 2025-01-25
5 | 152A/11 | DA-1.5 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Garg Const. | Complete | 2024-12-22 | 2025-01-16 | 2025-01-20 | 2025-01-21
| 152A/12 | DA-3 | DFR | RAJ |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-06-14 | Yash Infra | Complete |  |  |  | 2025-06-13
| 152A/2 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Reshmi Devi | Complete | 2025-01-21 | 2025-01-22 | 2025-01-27 | 2025-01-28
| 152A/3 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Reshmi Devi | Complete | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-22 |  | 3
| 152A/4 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2024-12-01 | Reshmi Devi | Complete | 2024-12-19 | 2024-12-25 | 2024-12-26 | 2024-12-27 |  | 4
| 152A/5 | DA+3 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2025-01-01 | Reshmi Devi | Complete | 2024-12-25 | 2024-12-28 | 2024-12-31 | 2025-01-02
| 152A/6 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Reshmi Devi | Complete | 2024-12-25 | 2025-01-22 | 2025-01-23 | 2025-01-23
7 | 152A/7 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Garg Const. | Complete | 2024-12-24 | 2025-01-01 | 2025-01-04 | 2025-01-05
| 152A/8 | DA+6 | WET | RAJ | DA+9 WET | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 | 2025-01-01 | Saktawat | Complete | 2024-12-28 | 2024-12-28 | 2025-01-08 | 2025-01-16
| 152A/9 | DA+6 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2024-12-01 | Lotus Const. | Complete | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 |  | 4
| 153/0 | DB1+6 | WET | RAJ |  | 758.8 | 40.216 | 799.016 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-13
| 154/0 | DB2+9 | WFR | RAJ |  | 804.8 | 38.896 | 843.696 | 100.6 | 8.84 | 552.01 | 5671.38 | 1.768 |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-14
| 154/1 | DA-1.5 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Yash Infra | Complete | 2025-01-23 | 2025-01-27 | 2025-01-29 | 2025-01-30
6 | 154/2 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Yash Infra | Complete | 2025-01-14 | 2025-01-16 | 2025-01-31 | 2025-02-04
| 154/3 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Lotus Const. | Complete | 2024-12-22 | 2025-02-08 | 2025-02-03 | 2025-02-28
| 154/4 | DA+3 | DRY | RAJ |  | 267.36 | 13.86 | 281.22 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 705045.3467 | 2025-09-14 | RST | Complete |  |  |  | 2025-09-30
13 | 154/5 | DA+0 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-02-01 | Yash Infra | Complete | 2025-01-31 | 2025-02-03 | 2025-02-07 | 2025-02-08
| 155/0 | DC2+0 | DRY | RAJ |  | 835.52 | 36.476 | 871.996 | 104.44 | 8.29 | 635.99 | 5172 | 2.349 |  | 2025-10-14 | Vikash Cont. | Complete |  |  |  | 2025-10-17
8 | 155/1 | DA+0 | DRY | RAJ | DA+0 DRY | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 | 2025-02-01 | Garg Const. | Complete | 2025-02-02 | 2025-02-12 | 2025-02-16 | 2025-02-24
9 | 155/2 | DA+3 | DRY | RAJ | DA+9 DRY | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 | 2025-02-01 | Garg Const. | Complete | 2025-02-17 | 2025-02-18 | 2025-02-25 | 2025-02-28
| 155/3 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-01-01 | Soham Const. | Complete | 2024-12-25 | 2024-12-29 | 2025-01-20 | 2025-01-21
6 | 155/4 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Garg Const. | Complete | 2024-12-26 | 2025-02-06 | 2025-02-07 | 2025-02-10
| 155/5 | DA+3 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-01-01 | Soham Const. | Complete | 2024-12-23 | 2024-12-29 | 2025-01-13 | 2025-01-15
4 | 156/0 | DC1+0 | DFR | RAJ | DC1+0 DFR | 610.8 | 27.808 | 638.608 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 | 2025-07-01 | RST | Complete | 2025-02-03 |  |  | 2025-07-15 | Excavation WIP (Blasting) Hold
7 | 156/1 | DA+6 | DFR | RAJ | DA+9 DFR | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-02-01 | Aadinath | Complete | 2025-01-09 | 2025-02-06 | 2025-02-08 | 2025-02-12
| 156/2 | DA+3 |  |  |  | 0 | 0 | 0 | [6 empty] | 2025-11-14
8 | 156/3 | DA+0 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Aadinath | Complete | 2025-01-15 | 2025-02-19 | 2025-02-19 | 2025-02-22
12 | 156/4 | DA-3 | DFR | RAJ | DA+0 DFR | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-02-01 | Reshmi Devi | Complete | 2025-01-28 | 2025-02-03 | 2025-02-05 | 2025-02-05
| 156/6 | DA+0 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | Vikash Cont. | Complete | 2026-02-06 |  |  | 2026-02-07
| 158/0 | DC2+18 | DFR | MP-Forest |  | 784.48 | 33.836 | 818.316 | 98.06 | 7.69 | 475.74 | 5381 | 2.386 |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-31
| 158/1 | DA+6 | DFR | MP-Forest |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.866 |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-31
| 158/2 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-12 | Yash Infra | Complete |  |  |  | 2025-05-16
| 158/3 | DA-1.5 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-04 | Yash Infra | Complete |  |  |  | 2025-05-09
21 | 159/0 | DB2+0 | DRY | MP | DB2+0 DRY(MP) | 565 | 26 | 591 | 70.56 | 5.83 | 454.86 | 5149 | 1.7681 | 1662016.3703 | 2025-02-01 | Reshmi Devi | Complete | 2025-02-09 | 2025-02-16 | 2025-02-22 | 2025-02-24
21 | 159/1 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-19
| 159/2 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-02 | Yash Infra | Complete |  |  |  | 2025-05-04
20 | 159/3 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-02-01 | Reshmi Devi | Complete | 2025-02-08 | 2025-02-08 | 2025-02-16 | 2025-02-16
23 | 160/0 | DB1+0 | DRY | MP | DB1+0 DRY(MP) | 406 | 22 | 428 | 50.64 | 4.8 | 378.56 | 4711.55 | 1.7681 | 1326238.3039 | 2025-02-01 | Yash Infra | Complete | 2025-02-16 | 2025-02-18 | 2025-01-23 | 2025-02-25
| 160/1 | DA-1.5 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Yash Infra | Complete | 2025-02-24 | 2025-03-02 | 2025-03-04 | 2025-03-04
| 160/2 | DA-1.5 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-02-01 | Yash Infra | Complete | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-02-28
24 | 160/3 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-02-01 | Yash Infra | Complete | 2025-02-10 | 2025-02-11 | 2025-02-15 | 2025-02-15
10 | 160/4 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Yash Infra | Complete | 2025-03-02 | 2025-03-03 |  | 2025-03-08
11 | 160/5 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Yash Infra | Complete |  |  |  | 2025-03-31 | 4 PIT Excavation Done.
40 | 161/0 | DB2+3 | DRY | MP |  | 566.8 | 25.872 | 592.672 | 70.85 | 5.88 | 454.86 | 5149 | 1.7681 | 1649958.0771 | APRIL-25 | Yash Infra | Complete |  |  |  | 2025-04-28
26 | 161/1 | DA+3 | DRY | MP | DA+3 DRY (MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-26 | 4 PIT Excavation Done.
| 161/2 | DA+3 | DRY | MP | DA+3 DRY(MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Reshmi Devi | Complete | 2025-03-02 | 2025-03-03 | 2025-03-06 | 2025-03-06
38 | 161/3 | DA+3 | DRY | MP | DA+3 DRY (MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-31
8 | 161/4 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-02-01 | Reshmi Devi | Complete | 2025-02-14 | 2025-02-18 | 2025-02-26 | 2025-02-27
8 | 161/5 | DA+6 | DRY | MP | DA+6 DRY (MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Reshmi Devi | Complete | 2025-03-02 | 2025-03-04 | 2025-03-09 | 2025-03-11
| 162/0 | DB2+0 | DRY | MP |  | 0 | 0 | 0 | [6 empty] | 2026-01-01 | Reshmi Devi | Complete |  |  |  | 2026-01-07 | 2 Pit Excavation Done. (ROW)
| 162/1 | DA+0 | DRY | MP | [10 empty] | 2026-01-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2026-01-24
| 162/2 | DA+0 | DRY | MP | [10 empty] | 2026-01-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2026-01-08
| 163/0 | DB1+18 | DFR | MP | [10 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-23
| 164/0 | DC2+18 | DFR | MP | [10 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-19
| 164/1 | DA+9 | DFR | MP | [10 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-25
23 | 164/2 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Puniya Const. | Complete |  |  |  | 2025-03-31 | 4 Pit Excavation done.
5 | 164/3 | DA+3 | DRY | MP | DA+3 DRY (MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Puniya Const. | Complete |  |  |  | 2024-03-28 | 4 Pit Steel Binding Done.
6 | 164/4 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Puniya Const. | Complete | 2025-02-26 | 2025-03-06 |  | 2025-03-16
25 | 164/5 | DA+6 | DRY | MP | DA+9 DRY(MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-02-01 | Saktawar | Complete | 2025-02-14 | 2025-02-16 | 2025-02-24 | 2025-02-26
7 | 164/6 | DA+3 | DRY | MP | DA+3 DRY(MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Saktawat | Complete | 2025-02-22 | 2025-02-26 |  | 2025-03-07
17 | 164/7 | DA+3 | DRY | MP | DA+3 DRY(MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-08 | 4 Pit Excavation done.
17 | 164/8 | DA+3 | DRY | MP |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-15
22 | 165/0 | DB1+6 | DFR | MP |  | 470.72 | 21.868 | 492.588 | 58.84 | 4.97 | 298.13 | 3428 | 1.928 |  | 2025-10-14 | Garg Const. | Complete |  |  |  | 2025-10-22
| 165/1 | DA+6 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | APRIL-25 | Puniya Const. | Complete |  |  |  | 2025-04-30
23 | 165/2 | DA+0 | DFR | MP |  | 259.216 | 11.4488 | 270.6648 | 32.402 | 2.602 | 149.96 | 2496.13 | 1.003 |  | 2025-11-14 | Garg Const. | Complete |  |  |  | 2025-11-07
| 165/3 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Puniya Const. | Complete |  |  |  | 2025-04-18
| 165/4 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-13
| 165/5 | DA-3 | DRY | MP |  | 192.32 | 10.78 | 203.1 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-29
| 165/6 | DA-3 | DRY | MP | DA-3 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-09
| 166/0 | DC1+0 | DFR | MP |  | 610.8 | 27.808 | 638.608 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-24
15 | 166/1 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-09 | Garg Const. | Complete |  |  |  | 2025-05-13
14 | 166/2 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-28
13 | 166/3 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-20
11 | 166/4 | DA+3 | DRY | MP | DA+3 DRY (MP) | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-03-01 | Garg Const. | Complete |  |  |  | 2025-03-28 | 3 Pit Steel Binding done.
12 | 166/5 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | Garg Const. | Complete |  |  |  | 2025-03-31 | EXCAVATION STARTED.
10 | 166/6 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-13 | PIT Marking Done.
14 | 166/7 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Shree Shyam | Complete |  |  |  |  | PIT Marking Done.
13 | 166/8 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | Shree Shyam | Complete |  |  |  | 2025-04-08 | 4 PIT Excavation DONE.
15 | 166/9 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | APRIL-25 | Shree Shyam | Complete |  |  |  | 2025-04-20 | PIT Marking Done.
| 167/0 | DB1+0 | DRY | MP |  | 405.12 | 21.12 | 426.24 | 50.64 | 4.8 | 378.56 | 4711.55 | 1.7681 | 1326238.3039 | 2025-05-01 | Shree Shyam | Complete |  |  |  | 2025-05-03
| 167/1 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | Shree Shyam | Complete |  |  |  | 2025-05-09
| 167/2 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-12 | Saktawar | Complete |  |  |  | 2025-05-27
| 167/3 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-01 | Saktawar | Complete |  |  |  | 2025-05-29
| 167/4 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-26
| 167/5 | DA-3 | DFR | MP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-30
| 168/0 | DC2+0 | WFR | MP |  | 1044.32 | 48.18 | 1092.5 | 130.54 | 10.95 | 691.74 | 8037 | 2.349 |  | 2025-10-14 | Saktawar | Complete |  |  |  | 2025-10-25
| 169/0 | DC1+3 | WFR | MP |  | 922.96 | 41.888 | 964.848 | 115.37 | 9.52 | 596.84 | 5822 | 2.349 |  | 2025-11-14 | Saktawar | Complete |  |  |  | 2025-11-20
34 | 169/1 | DA-1.5 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-24 | PIT Marking Done.
19 | 169/2 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-14 | 2 PIT Excavation & Blasting WIP.
20 | 169/3 | DA+0 | DRY | MP | DA+0 DRY(MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-07 | 2 PIT Excavation Done & balance 2 Pits Excavation & blasting WIP.
| 169/4 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | MANOJ KUMAR | Complete |  |  |  | 2025-05-04
| 169/5 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-01 | MANOJ KUMAR | Complete |  |  |  | 2025-05-11
| 169/6 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | MANOJ KUMAR | Complete |  |  |  | 2025-05-25
21 | 169/7 | DA-1.5 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-07-14 | Garg Const. | Complete |  |  |  | 2025-07-17
| 169/9 | DA-3 | WFR | MP |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  | 2025-12-14 | Saktawar | Complete |  |  |  | 2025-12-08
| 170/0 | DB1+0 | DFR | MP |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 | 2025-05-03 | SHUKLA CONST | Complete |  |  |  | 2025-05-16
44 | 170/1 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-11
43 | 170/10 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | JSR | Complete |  |  |  | 2025-04-12
25 | 170/2 | DA+0 | DFR | MP | DA+0 DFR (MP) | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-03-01 | SHUKLA CONST | Complete |  |  |  | 2025-03-30 | PIT Marking Done.
24 | 170/3 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | SHUKLA CONST | Complete |  |  |  | 2025-03-29 | 2 Pit Excavation done & 2 Pit WIP.
37 | 170/4 | DA-3 | DFR | MP | DA-3 DFR (MP) | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2024-04-04
44 | 170/5 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-22
| 170/6 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-28
28 | 170/7 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | JSR | Complete |  |  |  | 2025-04-17 | PIT Marking Done.
29 | 170/8 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-03-01 | JSR | Complete |  |  |  | 2025-03-31 | PIT Marking Done.
35 | 170/9 | DA+0 | DRY | MP | DA+0 DRY (MP) | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | JSR | Complete |  |  |  | 2025-04-07
| 171/0 | DB1+0 | DFR | MP |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 | 2025-06-14 | MANOJ KUMAR | Complete |  |  |  | 2025-06-08
| 171/1 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | JSR | Complete |  |  |  | 2025-04-22
| 171/10 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-11-14 | NEELKAMAL | Complete |  |  |  | 2015-11-27
| 171/2 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | APRIL-25 | JSR | Complete |  |  |  | 2025-04-26
| 171/3 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-06-14 | Puniya Const. | Complete |  |  |  | 2025-06-08
| 171/4 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | Puniya Const. | Complete |  |  |  | 2025-05-21
| 171/6 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-06-14 | NEELKAMAL | Complete |  |  |  | 2025-06-29
| 171/7 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-06-14 | NEELKAMAL | Complete |  |  |  | 2025-06-03
| 171/8 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-01 | NEELKAMAL | Complete |  |  |  | 2025-05-17
| 171/9 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | NEELKAMAL | Complete |  |  |  | 2025-05-04
| 172/0 | DB1+0 | DFR | MP |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 | 2025-06-14 | SRI BALAJI | Complete |  |  |  | 2025-06-09
41 | 172/1 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-26
42 | 172/2 | DA+0 | DFR | MP | DA+0 DFR (MP) | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-10
| 172/3 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-18
| 172/4 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-05-21
| 172/5 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-05-14 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-05-30
| 172/6 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | Shree Shyam | Complete |  |  |  | 2025-05-23
| 173/0 | DB2+0 | DFR | MP |  | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 | 2025-06-14 | Shree Shyam | Complete |  |  |  | 2025-06-05
| 173/1 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-26
| 173/2 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-20
| 173/3 | DA+3 | DRY | MP |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-12
| 173/4 | DA+3 | DRY | MP |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-16
19 | 174A/0 | DC1+3 | DRY | MP |  | 605.28 | 27.984 | 633.264 | 75.66 | 6.36 | 493.97 | 5327.42 | 2.3488 | 1817219.9087 | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-13
18 | 174A/1 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-04
20 | 174A/2 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-28
| 174A/3 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-04 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-05-10
17 | 174A/4 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | Garg Const. | Complete |  |  |  | 2025-05-23
16 | 174A/5 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-13 | Garg Const. | Complete |  |  |  | 2025-05-29
| 174B/0 | DB2+0 | WET | MP | [10 empty] | 2026-01-14 | Garg Const. | Complete |  |  |  | 2026-01-22
| 175/0 | DB1+0 | WFR | MP |  | 644.24 | 32.736 | 676.976 | 80.53 | 7.44 | 459.56 | 4404 | 1.768 |  | 2025-12-14 | Garg Const. | Complete |  |  |  | 2025-12-30
| 175/1 | DA+0 | WET | MP |  | 315.84 | 19.624 | 335.464 | 39.48 | 4.46 | 352.81 | 2945.01 | 0.866 |  | 2025-12-14 | Garg Const. | Complete |  |  |  | 2025-12-15
24 | 175/2 | DA+0 | WFR | MP |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  | 2025-11-14 | Garg Const. | Complete |  |  |  | 2025-11-26
| 175/3 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-26
| 175/4 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-24
| 176/0 | DC1+3 | DFR | MP |  | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 | 2025-05-01 | SRI BALAJI | Complete |  |  |  | 2025-05-04
| 176/1 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-30
| 176/2 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-05-03 | SRI BALAJI | Complete |  |  |  | 2025-05-06
| 176/3 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-04 | SRI BALAJI | Complete |  |  |  | 2025-05-10
| 177/0 | DB2+0 | DFR | MP |  | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 | 2025-05-10 | SRI BALAJI | Complete |  |  |  | 2026-05-15
| 177/1 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-17
| 177/2 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-21
| 177/3 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-23
| 177/4 | DA+3 | DRY | MP |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-27
| 177/5 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-29
| 177/6 | DA-3 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-14 | SRI BALAJI | Complete |  |  |  | 2025-05-31
| 177/7 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-06-14 | SRI BALAJI | Complete |  |  |  | 2025-06-03
| 177/8 | DA+0 | DRY | MP |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 | 2025-05-12 | Reshmi Devi | Complete | 2025-05-25 |  |  | 2025-05-25
| 178/0 | DB2+0 | DRY | MP |  | 565 | 26 | 591 | 70.56 | 5.83 | 454.86 | 5149 | 1.7681 | 1662016.3703 | 2025-05-11 | Reshmi Devi | Complete |  |  |  | 2025-05-18
| 178/1 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-05-03 | Reshmi Devi | Complete |  |  |  | 2025-05-08
| 178/2 | DA+6 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 |  | 2025-10-14 | Reshmi Devi | Complete |  |  |  | 2025-10-16
| 178/3 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-05-13 | Reshmi Devi | Complete |  |  |  | 2025-05-30
| 178/4 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-04
| 178/5 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-12
| 179/1 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-23
| 179/2 | DA+3 | DFR | MP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-29
| 179/4 | DA-3 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-09-14 | Infinity Const | Complete |  |  |  | 2025-09-26
| 179/5 | DA+0 | DFR | MP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.866 |  | 2025-12-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2025-12-10
| 179/6 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-09-14 | Infinity Const | Complete |  |  |  | 2025-09-12
| 179/7 | DA+0 | DFR | MP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 | 2025-08-14 | Infinity Const | Complete |  |  |  | 2025-08-29
| 179/9 | DA+3 | DFR | MP |  | 0 | 0 | 0 | [6 empty] | 2026-01-14 | Infinity Const | Complete |  |  |  | 2026-01-11
| 180/0 | DC2+15 | DRY | MP |  | 642.72 | 32.736 | 675.456 | 80.34 | 7.44 | 573.44 | 7856 | 2.235 |  | 2025-10-14 | Reshmi Devi | Complete |  |  |  | 2025-10-30
| 181/0 | DD60+9 | DFR | MP |  | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 |  | 2025-12-14 | Reshmi Devi | Complete |  |  |  | 2025-12-24
| 181/1 | DA+0 | DFR | MP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-18
| 181/2 | DA-3 |  |  |  | 0 | 0 | 0 | [6 empty] | 2025-11-14
| 181/4 | DA-3 | DFR | MP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-27
| 181/5 | DA-3 | WFR | MP |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  | 2025-12-14 | Reshmi Devi | Complete |  |  |  | 2025-12-06
| 181/6 | DA+0 | DFR | MP |  | 233.656 | 11.4708 | 245.1268 | 29.207 | 2.607 | 146.96 | 1798 | 0.912 |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-10
| 182/0 | DD60+6 | DFR | MP | [10 empty] | 2026-01-01 | Reshmi Devi | Complete |  |  |  | 2026-01-25
| 99/1 | DA+6 | DFR | RAJ |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-11
| 99/2 | DA+6 | WET | RAJ |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-09
| 99/3 | DA+0 | WFR | RAJ |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-06
| 99/4 | DA+0 | WET | RAJ |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-01
| 99/5 | DA+0 | WET | RAJ |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-03
| 99/6 | DA+0 | WFR | RAJ |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-25
| 99/7 | DA+0 | WET | RAJ |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-16
| 99/8 | DA+6 | WET | RAJ |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-17
| 146/0 | DD60+18 | WFR | RAJ | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-19
| 148C/0 | DB1+9 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-21
| 142/1 | DA-3 | DFR | RAJ-Forest | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-24
| 148B/0 | DB1+0 | DFR | RAJ | [10 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-28

## Sheet5 (hidden)
Loc NO | TOT | Classification | Type of Earthing
100/0 | DD45+0 | WET | Pipe Type
101/0 | DC1+3 | DFR | Counter Poise
101/1 | DA+3 | WFR | Counter Poise
101/2 | DA+9 | WFR | Counter Poise
101/3 | DA+3 | WFR | Counter Poise
101/4 | DA+6 | WFR | Counter Poise
101/5 | DA+0 | WFR | Counter Poise
101/6 | DA+3 | WFR | Counter Poise
101/7 | DA+3 | WFR | Counter Poise
101/8 | DA-3 | DRY | Pipe Type
102/0 | DC2+3 | DRY | Pipe Type
103/0 | DC1+6 | DFR | Counter Poise
103/1 | DA+0 | DRY | Pipe Type
103/2 | DA+0 | DRY | Pipe Type
103/3 | DA+0 | DFR | Counter Poise
103/4 | DA+0 | DRY | Pipe Type
103/5 | DA+3 | DFR | Counter Poise
103/5A | DD60+0 | DFR | Counter Poise
103/5A1 | DA-3 | DFR | Counter Poise
103/6A | DD45+0 | DRY | Pipe Type
103/7 | DA+6 | DFR | Counter Poise
103/8 | DA+3 | DRY | Pipe Type
103/9 | DA+3 | WET | Pipe Type
104/0 | DD45+3 | DFR | Counter Poise
104/1 | DA-3 | DFR | Counter Poise
104/2 | DA-3 | WET | Pipe Type
105/0 | DC1+0 | WFR | Counter Poise
105/1 | DA+0 | WFR | Counter Poise
106/0 | DD60+0 | DFR | Counter Poise
108/0 | DD45+0 | DRY | Pipe Type
108/1 | DA-3 | DFR | Counter Poise
108/2 | DA-3 | WET | Pipe Type
108/3 | DA-3 | WET | Pipe Type
108/4 | DA+0 | WFR | Counter Poise
109/0 | DC1+0 | DFR | Counter Poise
109/1 | DA-1.5 | WFR | Counter Poise
109/2 | DA-1.5 | WFR | Counter Poise
109/3 | DA+0 | WFR | Counter Poise
109/4 | DA+3 | WFR | Counter Poise
110/0 | DC2+3 | WFR | Counter Poise
110/1 | DA-1.5 | WFR | Counter Poise
110/2 | DA+0 | WFR | Counter Poise
110/3 | DA+3 | DRY | Pipe Type
110/4 | DA+3 | DFR | Counter Poise
110/5 | DA+3 | WET | Pipe Type
110/6 | DA+0 | WFR | Counter Poise
110/7 | DA+3 | WFR | Counter Poise
110/8 | DA+0 | WFR | Counter Poise
110A/0 | DB2+0 | DFR | Counter Poise
110A/1 | DA+3 | WFR | Counter Poise
110A/2 | DA-1.5 | DFR | Counter Poise
111/0 | DB1+6 | DFR | Counter Poise
111/1 | DA+3 | WFR | Counter Poise
111/2 | DA+3 | WFR | Counter Poise
111/3 | DA+0 | WET | Pipe Type
111/4 | DA+3 | DFR | Counter Poise
112/0 | DD60+18 | DFR | Counter Poise
113/0 | DD60+9 | WFR | Counter Poise
113/1 | DA-3 | DFR | Counter Poise
113/2 | DA-1.5 | WFR | Counter Poise
113/3 | DA-3 | DFR | Counter Poise
113/4 | DA+0 | DFR | Counter Poise
113/5 | DA+6 | DFR | Counter Poise
113/6 | DA+6 | DFR | Counter Poise
114/0 | DC2+0 | WET | Pipe Type
114/1 | DA+3 | DFR | Counter Poise
114/10 | DA+6 | DFR | Counter Poise
114/2 | DA+0 | WFR | Counter Poise
114/3 | DA+0 | WFR | Counter Poise
114/4 | DA+3 | WFR | Counter Poise
114/5 | DA+6 | DFR | Counter Poise
114/6 | DA-3 | DFR | Counter Poise
114/7 | DA+3 | DFR | Counter Poise
114/8 | DA+6 | WET | Pipe Type
114/9 | DA+3 | WET | Pipe Type
115/0 | DD60+3 | DFR | Counter Poise
116/0 | DD45+3 | DFR | Counter Poise
116/1 | DA+3 | WFR | Counter Poise
116/2 | DA+3 | WFR | Counter Poise
118/0 | DD60+6 | WFR | Counter Poise
119/0 | DC2+0 | DFR | Counter Poise
120/0 | DD45+3 | DFR | Counter Poise
99/1 | DA+6 | DFR | Counter Poise
99/2 | DA+6 | WET | Pipe Type
99/3 | DA+0 | WFR | Counter Poise
99/4 | DA+0 | WET | Pipe Type
99/5 | DA+0 | WET | Pipe Type
99/6 | DA+0 | WFR | Counter Poise
99/7 | DA+0 | WET | Pipe Type
99/8 | DA+6 | WET | Pipe Type

## Erection Compiled
Date : 02-03-2026
Sr. No | Location No. | Tower Type | Tower Weight | Rev(Inr) | Month of Execution | Gang Name | Status | Starting Date | Completion Date | No of Compl. Days | Region | Remarks
|  |  | 14416.7239 | 157718959.4441 |  |  | 301
1 | 101/2 | DA+9 | 45.697 | 499925.4207 | 2025-01-01 | Jwala Singh | Completed | 2025-01-14 | 2025-01-19 | 5 | Raj
2 | 101/1 | DA+3 | 37.9311 | 414966.1027 | 2025-01-01 | Jwala Singh | Completed | 2025-01-21 | 2025-01-24 | 3 | Raj
3 | 101/3 | DA+3 | 37.9311 | 414966.1027 | 2025-01-01 | Jwala Singh | Completed | 2025-01-24 | 2025-01-27 | 3 | Raj
4 | 101/4 | DA+6 | 43.8044 | 479220.3986 | 2025-01-01 | Jwala Singh | Completed | 2025-01-27 | 2025-01-31 | 4 | Raj
5 | 101/5 | DA+0 | 36.1598 | 395587.7306 | 2025-02-01 | Jwala Singh | Completed | 2025-02-01 | 2025-02-04 | 3 | Raj
6 | 101/6 | DA+3 | 37.9311 | 414966.1027 | 2025-02-01 | Jwala Singh | Completed | 2025-02-05 | 2025-02-08 | 3 | Raj
7 | 101/7 | DA+3 | 37.9311 | 414966.1027 | 2025-02-01 | Jwala Singh | Completed | 2025-02-09 | 2025-02-12 | 3 | Raj
8 | 101/8 | DA-3 | 34.7898 | 380600.5214 | 2025-02-01 | Jwala Singh | Completed | 2025-02-13 | 2025-02-15 | 2 | Raj
9 | 110/7 | DA+3 | 37.9311 | 414966.1027 | 2025-02-01 | Jwala Singh | Completed | 2025-02-17 | 2025-02-20 | 3 | Raj
10 | 110/5 | DA+3 | 37.9311 | 414966.1027 | 2025-02-01 | Jwala Singh | Completed | 2025-02-21 | 2025-02-24 | 3 | Raj
11 | 109/2 | DA-1.5 | 35.602 | 389485.88 | 2025-02-01 | Jwala Singh | Completed | 2025-02-25 | 2025-02-28 | 3 | Raj
12 | 109/1 | DA-1.5 | 35.602 | 389485.88 | 2025-03-01 | Jwala Singh | Completed | 2025-03-01 | 2025-03-04 | 3 | Raj
13 | 110/1 | DA-1.5 | 35.602 | 389485.88 | 2025-03-01 | Jwala Singh | Completed | 2025-03-05 | 2025-03-07 | 2 | Raj
14 | 109/3 | DA+0 | 36.1598 | 395587.7306 | 2025-03-01 | Jwala Singh | Completed | 2025-03-06 | 2025-03-11 | 5 | Raj
15 | 114/6 | DA-3 | 34.79 | 380602.6 | 2025-03-01 | Gokul/Rajwanshi | Completed | 2025-03-07 | 2025-03-29 | 22 | Raj
16 | 113/4 | DA+0 | 36.1598 | 395587.7306 | 2025-03-01 | Eagle Enterprises | Completed | 2025-03-12 | 2025-03-28 | 16 | Raj
17 | 109/4 | DA+3 | 37.9311 | 414966.1027 | 2025-03-01 | Jwala Singh | Completed | 2025-03-11 | 2025-03-15 | 4 | Raj
18 | 110/6 | DA+0 | 36.1598 | 395587.7306 | 2025-03-01 | Jwala Singh | Completed | 2025-03-15 | 2025-03-19 | 4 | Raj
19 | 110/2 | DA+0 | 36.1598 | 395587.7306 | 2025-03-01 | Jwala Singh | Completed | 2025-03-19 | 2025-03-22 | 3 | Raj
20 | 110/3 | DA+3 | 37.9311 | 414966.1027 | 2025-03-01 | Jwala Singh | Completed | 2025-03-22 | 2025-03-26 | 4 | Raj
21 | 110A/1 | DA+3 | 37.9311 | 414966.1027 | 2025-03-01 | Jwala Singh | Completed | 2025-03-26 | 2025-03-30 | 4 | Raj
22 | 113/5 | DA+6 | 43.8044 | 479220.3986 | 2025-03-01 | Eagle Enterprises | Completed | 2025-03-29 | 2025-03-31 | 2 | Raj
23 | 114/5 | DA+6 | 43.8044 | 479220.3986 | 2025-04-01 | Gokul/Rajwanshi | Completed | 2025-03-30 | 2025-04-16 | 17 | Raj
24 | 110/8 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Jwala Singh | Completed | 2025-03-30 | 2025-04-03 | 4 | Raj
25 | 114/9 | DA+3 | 37.9311 | 414966.1027 | 2025-04-01 | Jwala Singh-2 | Completed | 2025-03-30 | 2025-04-06 | 7 | Raj
26 | 113/3 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Eagle Enterprises | Completed | 2025-04-01 | 2025-04-10 | 9 | Raj
27 | 108/4 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Jwala Singh | Completed | 2025-04-03 | 2025-04-07 | 4 | Raj
28 | 114/10 | DA+6 | 43.8044 | 479220.3986 | 2025-04-01 | Jwala Singh-2 | Completed | 2025-04-06 | 2025-04-12 | 6 | Raj
29 | 108/3 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Jwala Singh | Completed | 2025-04-08 | 2025-04-11 | 3 | Raj
30 | 113/2 | DA-1.5 | 35.602 | 389485.88 | 2025-04-01 | Eagle Enterprises/Paramand | Completed | 2025-04-11 | 2025-04-17 | 6 | Raj
31 | 108/2 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Jwala Singh | Completed | 2025-04-12 | 2025-04-15 | 3 | Raj
32 | 114/2 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Jwala Singh-2 | Completed | 2025-04-12 | 2025-04-18 | 6 | Raj
33 | 108/1 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Jwala Singh | Completed | 2025-04-15 | 2025-04-18 | 3 | Raj
34 | 114/3 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Gokul/Rajwanshi | Completed | 2025-04-17 | 2025-04-24 | 7 | Raj
35 | 113/1 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Eagle Enterprises/Paramand | Completed | 2025-04-18 | 2025-04-23 | 5 | Raj
36 | 114/7 | DA+3 | 37.9311 | 414966.1027 | 2025-04-01 | Jwala Singh-2 | Completed | 2025-04-18 | 2025-04-22 | 4 | Raj
37 | 104/1 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Jwala Singh | Completed | 2025-04-18 | 2025-04-21 | 3 | Raj
38 | 104/2 | DA-3 | 34.79 | 380602.6 | 2025-04-01 | Jwala Singh | Completed | 2025-04-22 | 2025-04-25 | 3 | Raj
39 | 159/1 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Paramanand | Completed | 2025-04-22 | 2025-05-08 | 16 | MP
40 | 120/2 | DA-1.5 | 35.602 | 389485.88 | 2025-04-01 | Jwala Singh-2 | Completed | 2025-04-22 | 2025-04-27 | 5 | Raj
41 | 114/1 | DA+3 | 37.9311 | 414966.1027 | 2025-04-01 | Gokul/Rajwanshi | Completed | 2025-04-25 | 2025-04-30 | 5 | Raj
42 | 113/6 | DA+6 | 43.8044 | 479220.3986 | 2025-05-01 | Eagle Enterprises/Paramand | Completed | 2025-04-24 | 2025-05-02 | 8 | Raj
43 | 105/1 | DA+0 | 36.1598 | 395587.7306 | 2025-04-01 | Jwala Singh | Completed | 2025-04-26 | 2025-04-29 | 3 | Raj
44 | 120/1 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-04-27 | 2025-05-02 | 5 | Raj
45 | 111/4 | DA+9 | 45.697 | 499925.4207 | 2025-05-01 | Jwala Singh | Completed | 2025-04-30 | 2025-05-06 | 6 | Raj
46 | 116/2 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Gokul/Rajwanshi | Completed | 2025-05-02 | 2025-05-08 | 6 | Raj
47 | 120/3 | DA+9 | 45.697 | 499925.4207 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-02 | 2025-05-07 | 5 | Raj
48 | 111/1 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Eagle Enterprises/Paramand | Completed | 2025-05-02 | 2025-05-09 | 7 | Raj
49 | 111/3 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Jwala Singh | Completed | 2025-05-06 | 2025-05-11 | 5 | Raj
50 | 127/2 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-08 | 2025-05-12 | 4 | Raj
51 | 116/1 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Gokul/Rajwanshi | Completed | 2025-05-08 | 2025-05-15 | 7 | Raj
52 | 160/5 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Paramanand-1 | Completed | 2025-05-08 | 2025-05-23 | 15 | MP
53 | 161/4 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Paramanand-2 | Completed | 2025-05-08 | 2025-05-27 | 19 | MP
54 | 111/2 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Eagle Enterprises/Paramand | Completed | 2025-05-09 | 2025-05-18 | 9 | Raj
55 | 152A/3 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Jwala Singh | Completed | 2025-05-14 | 2025-05-16 | 2 | Raj
56 | 127/1 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-13 | 2025-05-16 | 3 | Raj
57 | 154/5 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Gokul/Rajwanshi | Completed | 2025-05-16 | 2025-05-22 | 6 | Raj
58 | 152A/1 | DA-1.5 | 35.602 | 389485.88 | 2025-05-01 | Jwala Singh | Completed | 2025-05-17 | 2025-05-21 | 4 | Raj
59 | 129A/3 | DA+0 | 36.1598 | 395587.7306 | 2025-06-01 | Eagle Enterprises/Paramand | Completed | 2025-05-19 | 2025-06-07 | 19 | Raj
60 | 126/4 | DA+9 | 45.697 | 499925.4207 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-17 | 2025-05-22 | 5 | Raj
61 | 152A/2 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Jwala Singh | Completed | 2025-05-22 | 2025-05-26 | 4 | Raj
62 | 155/3 | DA+0 | 36.1598 | 395587.7306 | 2025-05-01 | Gokul/Rajwanshi | Completed | 2025-05-23 | 2025-05-27 | 4 | Raj
63 | 126/2 | DA-3 | 34.79 | 380602.6 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-23 | 2025-05-26 | 3 | Raj
64 | 160/4 | DA+0 | 36.1598 | 395587.7306 | 2025-06-01 | Paramanand-1 | Completed | 2025-05-24 | 2025-06-07 | 14 | MP
65 | 161/3 | DA+3 | 37.9311 | 414966.1027 | 2025-06-01 | Paramanand-2 | Completed | 2025-05-28 | 2025-06-23 | 26 | MP
66 | 155/5 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Gokul/Rajwanshi | Completed | 2025-05-28 | 2025-05-31 | 3 | Raj
67 | 152A/4 | DA+3 | 37.9311 | 414966.1027 | 2025-05-01 | Jwala Singh | Completed | 2025-05-27 | 2025-05-30 | 3 | Raj
68 | 127/3 | DA+6 | 43.8044 | 479220.3986 | 2025-05-01 | Jwala Singh-2 | Completed | 2025-05-27 | 2025-05-31 | 4 | Raj
69 | 152A/8 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh | Completed | 2025-05-31 | 2025-06-05 | 5 | Raj
70 | 147A/4 | DA+3 | 37.9311 | 414966.1027 | 2025-06-01 | Jwala Singh-2 | Completed | 2025-06-01 | 2025-06-06 | 5 | Raj
71 | 155/4 | DA+0 | 36.1598 | 395587.7306 | 2025-06-01 | Gokul/Rajwanshi | Completed | 2025-06-01 | 2025-06-07 | 6 | Raj
72 | 150/5 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh | Completed | 2025-06-06 | 2025-06-10 | 4 | Raj
73 | 147A/2 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh-2 | Completed | 2025-06-07 | 2025-06-10 | 3 | Raj
74 | 129A/1 | DA+0 | 36.1598 | 395587.7306 | 2025-06-01 | Eagle Enterprises/Paramand | Completed | 2025-06-08 | 2025-06-23 | 15 | Raj
75 | 156/1 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Gokul/Rajwanshi | Completed | 2025-06-08 | 2025-06-15 | 7 | Raj
76 | 160/3 | DA+0 | 36.1598 | 395587.7306 | 2025-07-01 | Paramanand-1 | Completed | 2025-06-08 | 2025-07-31 | 53 | MP
77 | 150/3 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh | Completed | 2025-06-11 | 2025-06-16 | 5 | Raj
78 | 147A/3 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh-2 | Completed | 2025-06-11 | 2025-06-15 | 4 | Raj
79 | 147/1 | DA+9 | 45.697 | 499925.4207 | 2025-07-01 | Eagle Enterprises/Paramand | Completed | 2025-06-26 | 2025-07-12 | 16 | Raj | JWALA SINGH COMPLETED THE LOCS.
80 | 156/4 | DA-3 | 34.79 | 380602.6 | 2025-06-01 | Gokul/Rajwanshi | Completed | 2025-06-16 | 2025-06-22 | 6 | Raj
81 | 152A/9 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh | Completed | 2025-06-17 | 2025-06-25 | 8 | Raj
82 | 154/2 | DA-3 | 34.79 | 380602.6 | 2025-06-01 | Gokul/Rajwanshi | Completed | 2025-06-24 | 2025-06-30 | 6 | Raj
83 | 150/4 | DA+6 | 43.8044 | 479220.3986 | 2025-06-01 | Jwala Singh | Completed | 2025-06-27 | 2025-06-30 | 3 | Raj
84 | 154/1 | DA-1.5 | 35.602 | 389485.88 | 2025-07-01 | Gokul/Rajwanshi | Completed | 2025-07-01 | 2025-07-07 | 6 | Raj
85 | 150/2 | DA+3 | 37.9311 | 414966.1027 | 2025-07-01 | Jwala Singh | Completed | 2025-07-01 | 2025-07-06 | 5 | Raj
86 | 150/1 | DA+6 | 43.8044 | 479220.3986 | 2025-07-01 | Jwala Singh | Completed | 2025-07-07 | 2025-07-17 | 10 | Raj
87 | 154/3 | DA-3 | 34.79 | 380602.6 | 2025-07-01 | Gokul/Rajwanshi | Completed | 2025-07-08 | 2025-07-14 | 6 | Raj
88 | 103/7 | DA+6 | 43.8044 | 479220.3986 | 2025-07-01 | Gokul/Rajwanshi | Completed | 2025-07-15 | 2025-07-24 | 9 | Raj
89 | 150/0 | DC1+0 | 62.444 | 683137.36 | 2025-07-01 | Jwala Singh | Completed | 2025-07-18 | 2025-07-28 | 10 | Raj
90 | 103/8 | DA+3 | 37.9311 | 414966.1027 | 2025-07-01 | Gokul/Rajwanshi | Completed | 2025-07-25 | 2025-07-31 | 6 | Raj
91 | 127/0 | DD45+0 | 73.245 | 801300.3 | 2025-08-01 | Shila Devi | Completed | 2025-08-01 | 2025-08-16 | 15 | Raj
92 | 106/0 | DD60+0 | 83.134 | 909485.96 | 2025-08-01 | Jwala Singh | Completed | 2025-08-04 | 2025-08-12 | 8 | Raj
93 | 103/5A1 | DA-3 | 34.79 | 380602.6 | 2025-08-01 | Gokul/Rajwanshi | Completed | 2025-08-04 | 2025-08-08 | 4 | Raj
94 | 110/4 | DA+3 | 37.9311 | 414966.1027 | 2025-08-01 | Anil Kumar/Rudra Const. | Completed | 2025-08-12 | 2025-08-30 | 18 | Raj
95 | 103/6A | DD45+0 | 73.245 | 801300.3 | 2025-08-01 | Gokul/Rajwanshi | Completed | 2025-08-09 | 2025-08-21 | 12 | Raj
96 | 158/3 | DA-1.5 | 35.602 | 389485.88 | 2025-09-01 | Paramanand-1 | Completed | 2025-08-25 | 2025-09-12 | 18 | MP
97 | 108/0 | DD45+0 | 73.245 | 801300.3 | 2025-08-01 | Jwala Singh | Completed | 2025-08-12 | 2025-08-22 | 10 | Raj
98 | 126/0 | DB2+0 | 59.501 | 650940.94 | 2025-08-01 | Shila Devi | Completed | 2025-08-17 | 2025-08-26 | 9 | Raj
99 | 111/0 | DB1+6 | 65.028 | 711406.32 | 2025-09-01 | Jyoti Const. | Completed | 2025-08-18 | 2025-09-09 | 22 | Raj
100 | 103/5A | DD60+0 | 83.134 | 909485.96 | 2025-09-01 | Gokul/Rajwanshi | Completed | 2025-08-21 | 2025-09-09 | 19 | Raj
101 | 119/0 | DC2+0 | 67.262 | 735846.28 | 2025-09-01 | Deglal Mahato | Completed | 2025-08-25 | 2025-09-07 | 13 | Raj
102 | 135/0 | DD45+0 | 73.245 | 801300.3 | 2025-09-01 | Jhemon Mahato-1 | Completed | 2025-08-25 | 2025-09-07 | 13 | Raj
103 | 136/1 | DA+3 | 37.9311 | 414966.1027 | 2025-09-01 | Jhemon Mahato-2 | Completed | 2025-08-25 | 2025-09-11 | 17 | Raj
104 | 104/0 | DD45+3 | 77.077 | 843222.38 | 2025-09-01 | Jwala Singh | Completed | 2025-08-23 | 2025-09-05 | 13 | Raj
105 | 130/0 | DB2+0 | 59.501 | 650940.94 | 2025-09-01 | Shila Devi | Completed | 2025-08-27 | 2025-09-09 | 13 | Raj
106 | 147A/5 | DA+9 | 45.697 | 499925.18 | 2025-09-01 | Toshan Mahato | Completed | 2025-09-01 | 2025-09-19 | 18 | Raj
107 | 156/0 | DC1+0 | 62.444 | 683137.36 | 2025-10-01 | Anil Kumar | Completed | 2025-09-12 | 2025-10-04 | 22 | Raj
108 | 103/0 | DC1+6 | 72.474 | 792865.56 | 2025-09-01 | Jwala Singh | Completed | 2025-09-10 | 2025-09-20 | 10 | Raj
109 | 135/2 | DA+9 | 45.697 | 499925.18 | 2025-09-01 | Jhemon Mahato-1 | Completed | 2025-09-08 | 2025-09-18 | 10 | Raj
110 | 120/0 | DD45+3 | 77.077 | 843222.38 | 2025-09-01 | Deglal Mahato | Completed | 2025-09-08 | 2025-09-18 | 10 | Raj
111 | 110A/2 | DA-1.5 | 35.602 | 389485.88 | 2025-09-01 | Jyoti Const. | Completed | 2025-09-10 | 2025-09-19 | 9 | Raj
112 | 103/3 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Gokul/Rajwanshi | Completed | 2025-09-10 | 2025-09-16 | 6 | Raj
113 | 144A/1 | DA+0 | 36.1598 | 395587.7306 | 2025-09-01 | Jhemon Mahato-2 | Completed | 2025-09-12 | 2025-09-22 | 10 | Raj
114 | 169/6 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Deglal Mahato (MP) | Completed | 2025-09-11 | 2025-09-21 | 10 | MP
115 | 114/8 | DA+6 | 43.8044 | 479220.3986 | 2025-09-01 | Deglal Mahato | Completed | 2025-09-19 | 2025-09-23 | 4 | Raj
116 | 103/1 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Gokul/Rajwanshi | Completed | 2025-09-18 | 2025-09-24 | 6 | Raj
117 | 131/0 | DD45+9 | 88.468 | 967839.92 | 2025-09-01 | Shila Devi | Completed | 2025-09-10 | 2025-09-25 | 15 | Raj
118 | 161/2 | DA+3 | 37.931 | 414965.14 | 2025-09-01 | Jagannaath Saw (MP) | Completed | 2025-09-10 | 2025-09-25 | 15 | MP
119 | 159/2 | DA+0 | 36.1598 | 395587.7306 | 2025-09-01 | Paramanand-1 | Completed | 2025-09-13 | 2025-09-25 | 12 | MP
120 | 167/5 | DA-3 | 34.79 | 380602.6 | 2025-09-01 | Pankaj Singh (MP) | Completed | 2025-09-14 | 2025-09-25 | 11 | MP
121 | 166/1 | DA-3 | 34.79 | 380602.6 | 2025-09-01 | Gokul Sarkar (MP) | Completed | 2025-09-14 | 2025-09-28 | 14 | MP
122 | 136/0 | DC2+3 | 70.74 | 773895.6 | 2025-09-01 | Jhemon Mahato-1 | Completed | 2025-09-19 | 2025-09-28 | 9 | Raj
123 | 105/0 | DC1+0 | 62.444 | 683137.36 | 2025-09-01 | Jwala Singh | Completed | 2025-09-21 | 2025-09-28 | 7 | Raj
124 | 110A/0 | DB2+0 | 59.501 | 650940.94 | 2025-09-01 | Jyoti Const. | Completed | 2025-09-20 | 2025-09-30 | 10 | Raj
125 | 147A/1 | DA-1.5 | 35.602 | 389485.88 | 2025-09-01 | Toshan Mahato | Completed | 2025-09-20 | 2025-09-29 | 9 | Raj
126 | 169/3 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Deglal Mahato (MP) | Completed | 2025-09-22 | 2025-09-29 | 7 | MP
127 | 144A/0 | DD45+6 | 85.264 | 932788.16 | 2025-10-01 | Jhemon Mahato-2 | Completed | 2025-09-23 | 2025-10-10 | 17 | Raj
128 | 115/0 | DD60+3 | 87.021 | 952009.74 | 2025-10-01 | Deglal Mahato | Completed | 2025-09-24 | 2025-10-04 | 10 | Raj
129 | 103/2 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Gokul/Rajwanshi | Completed | 2025-09-25 | 2025-09-30 | 5 | Raj
130 | 160/2 | DA-1.5 | 35.602 | 389485.88 | 2025-10-01 | Paramanand-1 | Completed | 2025-09-26 | 2025-10-07 | 11 | MP
131 | 130/1 | DA+0 | 36.16 | 395590.4 | 2025-09-01 | Shila Devi | Completed | 2025-09-26 | 2025-09-30 | 4 | Raj
132 | 160/0 | DB1+0 | 55.451 | 606633.94 | 2025-10-01 | Jagannaath Saw (MP) | Completed | 2025-09-26 | 2025-10-12 | 16 | Raj
133 | 148/1 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Toshan Mahato | Completed | 2025-09-30 | 2025-10-12 | 12 | Raj
134 | 169/4 | DA+0 | 36.16 | 395590.4 | 2025-10-01 | Deglal Mahato (MP) | Completed | 2025-09-30 | 2025-10-08 | 8 | Raj
135 | 112/0 | DD60+18 | 124.95 | 1366953 | 2025-10-01 | Jyoti Const. | Completed | 2025-10-01 | 2025-10-26 | 25 | Raj
136 | 128/0 | DC2+9 | 81.828 | 895198.32 | 2025-10-01 | Shila Devi | Completed | 2025-10-01 | 2025-10-12 | 11 | Raj
137 | 167/4 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Pankaj Singh (MP) | Completed | 2025-09-26 | 2025-10-01 | 5 | MP
138 | 167/2 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Pankaj Singh (MP) | Completed | 2025-10-02 | 2025-10-10 | 8 | MP
139 | 160/1 | DA-1.5 | 35.602 | 389485.88 | 2025-10-01 | Paramanand-1 | Completed | 2025-10-08 | 2025-10-16 | 8 | MP
140 | 169/5 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Deglal Mahato (MP) | Completed | 2025-10-09 | 2025-10-16 | 7 | MP
141 | 140/1 | DA+3 | 37.931 | 414965.14 | 2025-10-01 | Jhemon Mahato-2 | Completed | 2025-10-10 | 2025-10-18 | 8 | Raj
142 | 167/3 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Pankaj Singh (MP) | Completed | 2025-10-10 | 2025-10-15 | 5 | MP
143 | 101/0 | DC1+3 | 65.87 | 720617.8 | 2025-10-01 | Jwala Singh | Completed | 2025-10-01 | 2025-10-12 | 11 | Raj
144 | 102/0 | DC2+3 | 70.74 | 773895.6 | 2025-10-01 | Jwala Singh | Completed | 2025-10-13 | 2025-10-26 | 13 | Raj
145 | 147A/0 | DB1+0 | 55.451 | 606633.94 | 2025-10-01 | Toshan Mahato | Completed | 2025-10-13 | 2025-10-24 | 11 | Raj
146 | 158/2 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Jagannaath Saw (MP) | Completed | 2025-10-13 | 2025-10-18 | 5 | MP
147 | 152A/5 | DA+3 | 37.931 | 414965.14 | 2025-10-01 | Anil Kumar | Completed | 2025-10-05 | 2025-10-18 | 13 | Raj
148 | 116/0 | DD45+3 | 77.077 | 843222.38 | 2025-10-01 | Deglal Mahato | Completed | 2025-10-05 | 2025-10-13 | 8 | Raj
149 | 121/0 | DB1+6 | 65.028 | 711406.32 | 2025-10-01 | Deglal Mahato | Completed | 2025-10-14 | 2025-10-21 | 7 | Raj
150 | 169/7 | DA-1.5 | 35.602 | 389485.88 | 2025-10-01 | Deglal Mahato (MP) | Completed | 2025-10-16 | 2025-10-21 | 5 | MP
151 | 167/0 | DB1+0 | 55.451 | 606633.94 | 2025-10-01 | Pankaj Singh (MP) | Completed | 2025-10-16 | 2025-10-25 | 9 | MP
152 | 161/0 | DB2+3 | 62.116 | 679549.04 | 2025-11-01 | Paramanand-1 | Completed | 2025-10-16 | 2025-11-08 | 23 | MP
153 | 159/0 | DB2+0 | 59.501 | 650940.94 | 2025-11-01 | Jagannaath Saw (MP) | Completed | 2025-10-19 | 2025-11-02 | 14 | MP
154 | 144A/3 | DB1+3 | 57.96 | 634082.4 | 2025-11-01 | Jhemon Mahato-2 | Completed | 2025-10-19 | 2025-11-02 | 14 | Raj
155 | 169/2 | DA+0 | 36.1598 | 395587.7306 | 2025-10-01 | Deglal Mahato (MP) | Completed | 2025-10-22 | 2025-10-30 | 8 | MP
156 | 114/0 | DC2+0 | 67.262 | 735846.28 | 2025-10-01 | Deglal Mahato | Completed | 2025-10-22 | 2025-10-31 | 9 | Raj
157 | 148A/0 | DB1+6 | 65.028 | 711406.32 | 2025-11-01 | Toshan Mahato | Completed | 2025-10-25 | 2025-11-10 | 16 | Raj
158 | 149B/3 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Jyoti Const. | Completed | 2025-10-27 | 2025-11-11 | 15 | Raj
159 | 103/4 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Jwala Singh | Completed | 2025-10-27 | 2025-11-05 | 9 | Raj
160 | 167/1 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Pankaj Singh (MP) | Completed | 2025-10-26 | 2025-11-03 | 8 | MP
161 | 172/6 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Crane Erc.Team (MP) | Completed | 2025-10-27 | 2025-11-24 | 28 | MP
162 | 169/1 | DA-1.5 | 35.602 | 389485.88 | 2025-11-01 | Deglal Mahato (MP) | Completed | 2025-10-31 | 2025-11-06 | 6 | MP
163 | 126/1 | DA+9 | 45.697 | 499925.4207 | 2025-11-01 | Deglal Mahato | Completed | 2025-11-01 | 2025-11-09 | 8 | Raj
164 | 135/1 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Jhemon Mahato-2 | Completed | 2025-11-03 | 2025-11-10 | 7 | Raj
165 | 165/6 | DA-3 | 34.79 | 380602.6 | 2025-11-01 | Jagannaath Saw (MP) | Completed | 2025-11-03 | 2025-11-07 | 4 | MP
166 | 166/9 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Pankaj Singh (MP) | Completed | 2025-11-04 | 2025-11-13 | 9 | MP
167 | 109/0 | DC1+0 | 62.444 | 683137.36 | 2025-11-01 | Jwala Singh | Completed | 2025-11-06 | 2025-11-18 | 12 | Raj
168 | 170/8 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Deglal Mahato (MP) | Completed | 2025-11-07 | 2025-11-13 | 6 | MP
169 | 166/0 | DC1+0 | 62.444 | 683137.36 | 2025-11-01 | Jagannaath Saw (MP) | Completed | 2025-11-08 | 2025-11-15 | 7 | MP
170 | 126/3 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Deglal Mahato | Completed | 2025-11-10 | 2025-11-16 | 6 | Raj
171 | 164/5 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Paramanand-1 | Completed | 2025-11-09 | 2025-12-12 | 33 | MP
172 | 174A/0 | DC1+3 | 65.87 | 720617.8 | 2025-11-01 | Prayag Shah (MP) | Completed | 2025-11-10 | 2025-11-23 | 13 | MP
173 | 145/0 | DD60+18 | 124.95 | 1366953 | 2025-12-01 | Toshan Mahato | Completed | 2025-11-11 | 2025-12-09 | 28 | Raj
174 | 136/5 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Jhemon Mahato-2 | Completed | 2025-11-11 | 2025-11-22 | 11 | MP
175 | 149B/2 | DA+6 | 43.8044 | 479220.3986 | 2025-11-01 | Jyoti Const. | Completed | 2025-11-12 | 2025-11-25 | 13 | Raj
176 | 166/8 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Pankaj Singh (MP) | Completed | 2025-11-14 | 2025-11-18 | 4 | MP
177 | 170/7 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Deglal Mahato (MP) | Completed | 2025-11-14 | 2025-11-20 | 6 | MP
178 | 129A/2 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Shila Devi | Completed | 2025-11-12 | 2025-11-22 | 10 | Raj
179 | 165/0 | DB1+6 | 65.028 | 711406.32 | 2025-11-01 | Jagannaath Saw (MP) | Completed | 2025-11-16 | 2025-11-24 | 8 | MP
180 | 114/4 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Deglal Mahato | Completed | 2025-11-17 | 2025-11-24 | 7 | Raj
181 | 173/1 | DA-3 | 34.79 | 380602.6 | 2025-11-01 | Crane Erc.Team (MP) | Completed | 2025-10-27 | 2025-11-17 | 21 | MP
182 | 172/3 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Crane Erc.Team (MP) | Completed | 2025-11-18 | 2025-11-28 | 10 | MP
183 | 100/0 | DD45+0 | 73.245 | 801300.3 | 2025-11-01 | Jwala Singh | Completed | 2025-11-19 | 2025-11-29 | 10 | Raj
184 | 166/7 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Pankaj Singh (MP) | Completed | 2025-11-19 | 2025-11-24 | 5 | MP
185 | 170/1 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Deglal Mahato (MP) | Completed | 2025-11-21 | 2025-11-27 | 6 | MP
186 | 136/2 | DA+3 | 37.931 | 414965.14 | 2025-11-01 | Jhemon Mahato-2 | Completed | 2025-11-23 | 2025-11-30 | 7 | Raj
187 | 130/2 | DA-1.5 | 35.602 | 389485.88 | 2025-11-01 | Shila Devi | Completed | 2025-11-23 | 2025-11-28 | 5 | Raj
188 | 174A/2 | DA+0 | 36.1598 | 395587.7306 | 2025-11-01 | Prayag Shah (MP) | Completed | 2025-11-24 | 2025-11-30 | 6 | MP
189 | 166/6 | DA-3 | 34.79 | 380602.6 | 2025-11-01 | Pankaj Singh (MP) | Completed | 2025-11-25 | 2025-11-29 | 4 | MP
190 | 164/8 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Jagannaath Saw (MP) | Completed | 2025-11-25 | 2025-12-03 | 8 | MP
191 | 103/5 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Deglal Mahato | Completed | 2025-11-25 | 2025-12-02 | 7 | Raj
192 | 149B/4 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jyoti Const. | Completed | 2025-11-26 | 2025-12-05 | 9 | Raj
193 | 170/0 | DB1+0 | 55.451 | 606633.94 | 2025-12-01 | Deglal Mahato (MP) | Completed | 2025-11-28 | 2025-12-08 | 10 | MP
194 | 172/2 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Crane Erc.Team (MP) | Completed | 2025-11-29 | 2025-12-06 | 7 | MP
195 | 152/0 | DD60+6 | 97.17 | 1063039.8 | 2025-12-01 | Shila Devi | Completed | 2025-11-29 | 2025-12-11 | 12 | Raj
196 | 99/8 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Jwala Singh | Completed | 2025-11-30 | 2025-12-04 | 4 | Raj
197 | 166/5 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Pankaj Singh (MP) | Completed | 2025-11-30 | 2025-12-03 | 3 | MP
198 | 174A/3 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Prayag Shah (MP) | Completed | 2025-12-01 | 2025-12-08 | 7 | MP
199 | 140/0 | DC1+9 | 75.28 | 823563.2 | 2025-12-01 | Jhemon Mahato-2 | Completed | 2025-12-01 | 2025-12-24 | 23 | Raj
200 | 103/9 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Deglal Mahato | Completed | 2025-12-03 | 2025-12-10 | 7 | Raj
201 | 178/3 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Gokul Sarkar (MP) | Completed | 2025-12-03 | 2025-12-11 | 8 | MP
202 | 178/5 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Gokul Sarkar (MP)-2 | Completed | 2025-12-03 | 2025-12-11 | 8 | MP
203 | 177/0 | DB2+0 | 59.501 | 650940.94 | 2025-12-01 | Jwala Singh 2 | Completed | 2025-12-04 | 2025-12-19 | 15 | MP
204 | 164/7 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Jagannaath Saw (MP) | Completed | 2025-12-04 | 2025-12-11 | 7 | MP
205 | 166/4 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Pankaj Singh (MP) | Completed | 2025-12-04 | 2025-12-09 | 5 | MP
206 | 99/5 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jwala Singh | Completed | 2025-12-05 | 2025-12-09 | 4 | Raj
207 | 154/4 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Jyoti Const. | Completed | 2025-12-06 | 2025-12-16 | 10 | Raj
208 | 172/1 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Crane Erc.Team (MP) | Completed | 2025-12-07 | 2025-12-12 | 5 | MP
209 | 168/0 | DC2+0 | 67.262 | 735846.28 | 2025-12-01 | Deglal Mahato (MP) | Completed | 2025-12-09 | 2025-12-19 | 10 | MP
210 | 172/4 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Prayag Shah (MP) | Completed | 2025-12-09 | 2025-12-31 | 22 | MP
211 | 99/4 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jwala Singh | Completed | 2025-12-10 | 2025-12-13 | 3 | Raj
212 | 148/0 | DD60+6 | 97.17 | 1063039.8 | 2025-12-01 | Toshan Mahato | Completed | 2025-12-10 | 2025-12-31 | 21 | Raj
213 | 169/0 | DC1+3 | 65.87 | 720617.8 | 2025-12-01 | Pankaj Singh (MP) | Completed | 2025-12-10 | 2025-12-18 | 8 | MP
214 | 118/0 | DD60+6 | 97.17 | 1063039.8 | 2025-12-01 | Deglal Mahato | Completed | 2025-12-11 | 2025-12-21 | 10 | Raj
215 | 152A/0 | DB1+0 | 55.451 | 606633.94 | 2025-12-01 | Shila Devi | Completed | 2025-12-12 | 2025-12-19 | 7 | Raj
216 | 178/4 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Gokul Sarkar (MP) | Completed | 2025-12-12 | 2025-12-19 | 7 | MP
217 | 164/6 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Jagannaath Saw (MP) | Completed | 2025-12-12 | 2025-12-17 | 5 | MP
218 | 181/6 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Gokul Sarkar (MP)-2 | Completed | 2025-12-12 | 2025-12-20 | 8 | MP
219 | 173/2 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Crane Erc.Team (MP) | Completed | 2025-12-13 | 2025-12-21 | 8 | MP
220 | 99/6 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jwala Singh | Completed | 2025-12-13 | 2025-12-17 | 4 | Raj
221 | 152/1 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Jyoti Const. | Completed | 2025-12-17 | 2025-12-27 | 10 | Raj
222 | 132/0 | DD60+6 | 97.17 | 1063039.8 | 2025-12-01 | Jhemon Mahato-1 | Completed | 2025-12-17 | 2025-12-30 | 13 | Raj
223 | 99/3 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jwala Singh | Completed | 2025-12-18 | 2025-12-22 | 4 | Raj
224 | 164/4 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jagannaath Saw (MP) | Completed | 2025-12-18 | 2025-12-24 | 6 | MP
225 | 171/10 | DA+0 | 36.1598 | 395587.7306 | [6 empty] | MP | RoW
226 | 152A/6 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Shila Devi | Completed | 2025-12-20 | 2025-12-24 | 4 | Raj
227 | 169/9 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Deglal Mahato (MP) | Completed | 2025-12-20 | 2025-12-27 | 7 | MP
228 | 177/1 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Jwala Singh 2 | Completed | 2025-12-21 | 2025-12-27 | 6 | MP
229 | 181/1 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Gokul Sarkar (MP) | Completed | 2025-12-21 | 2025-12-26 | 5 | MP
230 | 179/5 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Gokul Sarkar (MP)-2 | Completed | 2025-12-21 | 2025-12-28 | 7 | MP
231 | 173/0 | DB2+0 | 59.501 | 650940.94 | 2025-12-01 | Crane Erc.Team (MP) | Completed | 2025-12-22 | 2025-12-30 | 8 | MP
232 | 123/0 | DD60+6 | 97.17 | 1063039.8 | 2026-01-01 | Deglal Mahato | Completed | 2025-12-22 | 2026-01-04 | 13 | Raj
233 | 99/7 | DA+0 | 36.1598 | 395587.7306 | 2025-12-01 | Jwala Singh | Completed | 2025-12-22 | 2025-12-26 | 4 | Raj
234 | 152A/7 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Shila Devi | Completed | 2025-12-25 | 2025-12-31 | 6 | Raj
235 | 164/3 | DA+3 | 37.931 | 414965.14 | 2025-12-01 | Jagannaath Saw (MP) | Completed | 2025-12-25 | 2025-12-30 | 5 | MP
236 | 99/1 | DA+6 | 43.8044 | 479220.3986 | 2025-12-01 | Jwala Singh | Completed | 2025-12-27 | 2025-12-31 | 4 | Raj
237 | 179/4 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Gokul Sarkar (MP) | Completed | 2025-12-27 | 2025-12-31 | 4 | MP
238 | 152/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Jyoti Const. | Completed | 2025-12-28 | 2026-01-03 | 6 | Raj
239 | 170/3 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Deglal Mahato (MP) | Completed | 2025-12-28 | 2026-01-03 | 6 | MP
240 | 177/3 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Jwala Singh 2 | Completed | 2025-12-28 | 2026-01-02 | 5 | MP
241 | 179/1 | DA+3 | 37.931 | 414965.14 | 2026-01-01 | Gokul Sarkar (MP)-2 | Completed | 2025-12-29 | 2026-01-06 | 8 | MP
242 | 129A/0 | DD45+0 | 73.245 | 801300.3 | 2026-01-01 | Jhemon Mahato-1 | Completed | 2025-12-31 | 2026-01-11 | 11 | Raj
243 | 161/5 | DA+6 | 43.8044 | 479220.3986 | 2026-01-01 | Jagannaath Saw (MP) | Completed | 2025-12-31 | 2026-01-08 | 8 | MP
244 | 173/3 | DA+3 | 37.931 | 414965.14 | 2026-01-01 | Crane Erc.Team (MP) | Completed | 2025-12-31 | 2026-01-08 | 8 | MP
245 | 99/2 | DA+6 | 43.8044 | 479220.3986 | 2026-01-01 | Jwala Singh | Completed | 2026-01-02 | 2026-01-05 | 3 | Raj
246 | 142/0 | DD45+3 | 77.08 | 843255.2 | 2026-01-01 | Toshan Mahato | Completed | 2026-01-02 | 2026-01-23 | 21 | Raj
247 | 154/0 | DB2+9 | 72.16 | 789430.4 | 2026-01-01 | Shila Devi | Completed | 2026-01-02 | 2026-01-10 | 8 | Raj
248 | 173/4 | DA+3 | 37.931 | 414965.14 | 2026-01-01 | Prayag Shah (MP) | Completed | 2026-01-02 | 2026-01-14 | 12 | MP
249 | 179/2 | DA+3 | 37.931 | 414965.14 | 2026-01-01 | Gokul Sarkar (MP) | Completed | 2026-01-02 | 2026-01-06 | 4 | MP
250 | 174A/1 | DA-3 | 34.79 | 380602.6 | 2025-12-01 | Prayag Shah (MP) | Completed | 2025-12-10 | 2025-12-18 | 8 | MP
251 | 177/4 | DA+3 | 37.931 | 414965.14 | 2026-01-01 | Jwala Singh 2 | Completed | 2026-01-03 | 2026-01-11 | 8 | MP
252 | 151/0 | DD45+3 | 77.08 | 843255.2 | 2026-01-01 | Jyoti Const. | Completed | 2026-01-04 | 2026-01-17 | 13 | Raj
253 | 170/4 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Deglal Mahato (MP) | Completed | 2026-01-04 | 2026-01-10 | 6 | MP
254 | 123/1 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Deglal Mahato | Completed | 2026-01-05 | 2026-01-14 | 9 | Raj
255 | 113/0 | DD60+9 | 101.95 | 1115333 | 2026-01-01 | Jwala Singh | Completed | 2026-01-06 | 2026-01-19 | 13 | Raj
256 | 181/5 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Gokul Sarkar (MP)-2 | Completed | 2026-01-07 | 2026-01-11 | 4 | MP
257 | 165/4 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Jagannaath Saw (MP) | Completed | 2026-01-09 | 2026-01-18 | 9 | MP
258 | 175/0 | DB1+0 | 55.451 | 606633.94 | 2026-01-01 | Crane Erc.Team (MP) | Completed | 2026-01-09 | 2026-01-31 | 22 | MP
259 | 153/0 | DB1+6 | 65.028 | 711406.32 | 2026-01-01 | Shila Devi | Completed | 2026-01-11 | 2026-01-18 | 7 | Raj
260 | 158/1 | DA+6 | 43.8044 | 479220.3986 | 2026-01-01 | Deglal Mahato (MP) | Completed | 2026-01-11 | 2026-01-19 | 8 | MP
261 | 181/4 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Gokul Sarkar (MP) | Completed | 2026-01-07 | 2026-01-11 | 4 | MP
262 | 181/0 | DD60+9 | 101.95 | 1115333 | 2026-01-01 | Gokul Sarkar (MP) | Completed | 2026-01-12 | 2026-01-31 | 19 | MP
263 | 179/6 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Gokul Sarkar (MP)-2 | Completed | 2026-01-12 | 2026-01-20 | 8 | MP
264 | 177/5 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Jwala Singh 2 | Completed | 2026-01-12 | 2026-01-18 | 6 | MP
265 | 125/1 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Jhemon Mahato-1 | Completed | 2026-01-12 | 2026-01-20 | 8 | Raj
266 | 171/9 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Prayag Shah (MP) | Completed | 2026-01-15 | 2026-01-25 | 10 | MP
267 | 123/3 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Deglal Mahato | Completed | 2026-01-15 | 2026-01-20 | 5 | Raj
268 | 149/0 | DD45+9 | 88.468 | 967839.92 | 2026-01-01 | Shila Devi | Completed | 2026-01-19 | 2026-01-31 | 12 | MP-Forest
269 | 165/5 | DA-3 | 34.79 | 380602.6 | 2026-01-01 | Jagannaath Saw (MP) | Completed | 2026-01-19 | 2026-01-27 | 8 | MP
270 | 177/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Jwala Singh 2 | Completed | 2026-01-19 | 2026-01-24 | 5 | MP
271 | 141/0 | DD45+0 | 73.245 | 801300.3 | 2026-01-01 | Jyoti Const. | Completed | 2026-01-18 | 2026-01-30 | 12 | Raj
272 | 110/0 | DC2+3 | 70.74 | 773895.6 | 2026-01-01 | Jwala Singh | Completed | 2026-01-20 | 2026-01-31 | 11 | Raj
273 | 162/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Deglal Mahato (MP) | Completed | 2026-01-20 | 2026-01-27 | 7 | MP
274 | 123/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Deglal Mahato | Completed | 2026-01-21 | 2026-01-28 | 7 | Raj
275 | 125/0 | DD60+3 | 87.021 | 952009.74 | 2026-01-01 | Jhemon Mahato-1 | Completed | 2026-01-21 | 2026-01-31 | 10 | Raj
276 | 178/0 | DB2+0 | 59.501 | 650940.94 | 2026-02-01 | Gokul Sarkar (MP)-2 | Completed | 2026-01-21 | 2026-02-03 | 13 | MP
277 | 149/2 | DA+9 | 45.697 | 499925.4207 | 2026-02-01 | Toshan Mahato | Completed | 2026-01-24 | 2026-02-05 | 12 | MP-Forest
278 | 175/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Crane Erc.Team (MP) | Completed | 2026-01-10 | 2026-01-24 | 14 | MP
279 | 172/0 | DB1+0 | 55.451 | 606633.94 | 2026-02-01 | Prayag Shah (MP) | Completed | 2026-01-27 | 2026-02-07 | 11 | MP
280 | 164/2 | DA+0 | 36.1598 | 395587.7306 | 2026-01-01 | Jagannaath Saw (MP) | Completed | 2026-01-28 | 2026-01-31 | 3 | MP
281 | 162/1 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Deglal Mahato (MP) | Completed | 2026-01-28 | 2026-02-05 | 8 | MP
282 | 122/0 | DD60+3 | 87.021 | 952009.74 | 2026-02-01 | Deglal Mahato | Completed | 2026-01-29 | 2026-02-08 | 10 | Raj
283 | 146/1 | DA+9 | 45.697 | 499925.4207 | 2026-02-01 | Jyoti Const. | Completed | 2026-01-31 | 2026-02-13 | 13 | Raj
284 | 148B/1 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Jwala Singh | Completed | 2026-02-01 | 2026-02-11 | 10 | RAJ-Forest
285 | 124/0 | DD45+3 | 77.08 | 843255.2 | 2026-02-01 | Jhemon Mahato-1 | Completed | 2026-02-01 | 2026-02-12 | 11 | Raj
286 | 149/1 | DA+3 | 37.931 | 414965.14 | 2026-02-01 | Shila Devi | Completed | 2026-02-01 | 2026-02-09 | 8 | Raj
287 | 164/1 | DB2+0 | 59.501 | 650940.94 | 2026-02-01 | Jagannaath Saw (MP) | Completed | 2026-02-01 | 2026-02-11 | 10 | MP | Crane Utilized
288 | 175/1 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Soni Enterprise (MP) | Completed | 2026-02-01 | 2026-02-16 | 15 | MP
289 | 179/9 | DA+3 | 37.931 | 414965.14 | 2026-02-01 | Gokul Sarkar (MP) | Completed | 2026-02-01 | 2026-02-09 | 8 | MP
290 | 178/1 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Gokul Sarkar (MP)-2 | Completed | 2026-02-03 | 2026-02-10 | 7 | MP
291 | 149B/1 | DB2+15 | 85.492 | 935282.48 | 2026-02-01 | Toshan Mahato | Completed | 2026-02-06 | 2026-02-26 | 20 | Raj
292 | 163/0 | DB1+18 | 82.465 | 902167.1 | 2026-02-01 | Deglal Mahato (MP) | Completed | 2026-02-06 | 2026-02-22 | 16 | MP | Crane Utilized
293 | 174A/5 | DA-3 | 34.79 | 380602.6 | 2026-02-01 | Prayag Shah (MP) | Completed | 2026-02-08 | 2026-02-15 | 7 | MP
294 | 156/6 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Deglal Mahato | Completed | 2026-02-08 | 2026-02-17 | 9 | MP
295 | 149A/0 | DC2+18 | 99.78 | 1091593.2 | 2026-02-01 | Shila Devi | Completed | 2026-02-10 | 2026-02-23 | 13 | MP-Forest
296 | 179/7 | DA+3 | 37.931 | 414965.14 | 2026-02-01 | [5 empty] | MP | ROW
297 | 178/2 | DA+6 | 43.8044 | 479220.3986 | 2026-02-01 | Prayag Shah (MP) | Completed | 2026-02-15 | 2026-02-22 | 7 | MP
298 | 139/1 | DB1+3 | 57.96 | 634082.4 | 2026-02-01 | Jwala Singh | Completed | 2026-02-12 | 2026-02-21 | 9 | RAJ-Forest
299 | 138/1 | DA-3 | 34.79 | 380602.6 | 2026-02-01 | Jyoti Const. | Completed | 2026-02-15 | 2026-02-24 | 9 | RAJ-Forest
300 | 156/3 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Deglal Mahato | Completed | 2026-02-18 | 2026-02-24 | 6 | Raj
301 | 139/0 | DB2+0 | 59.501 | 650940.94 | 2026-02-01 | Jwala Singh | Completed | 2026-02-22 | 2026-02-28 | 6 | RAJ-Forest
302 | 166/2 | DA+0 | 36.1598 | 395587.7306 | 2026-02-01 | Jagannaath Saw (MP) | Completed | 2026-02-14 | 2026-02-20 | 6 | MP
303 | 164/0 | DC2+18 | 99.78 | 1091593.2 | 2026-02-01 | Jagannaath Saw (MP) | In-Progress | 2026-02-16 |  |  | MP | Crane Utilized
304 | 172/5 | DA+3 | 37.931 | 414965.14 | 2026-02-01 | Prayag Shah (MP) | In-Progress | 2026-02-24 |  |  | MP
305 | 165/2 | DA+0 | 36.1598 | 395587.7306 | 2026-03-01 | Deglal Mahato (MP) | Completed | 2026-02-23 | 2026-03-03 | 8 | MP
306 | 148B/2 | DA+6 | 43.8044 | 479220.3986 | 2026-02-01 | Shila Devi | In-Progress | 2026-02-24 |  |  | RAJ-Forest
307 | 147/0 | DB2+6 |  |  | 2026-02-01 | Deglal Mahato | In-Progress | 2026-02-26 |  |  | Raj
308 | 142/1 | DA-3 | 34.79 | 380602.6 | 2026-02-01 | Toshan Mahato | In-Progress | 2026-02-27 |  |  | Raj
309 | 138/3 | DA+3 | 37.931 | 414965.14 | 2026-03-01 | Jwala Singh | In-Progress |  |  |  | Raj
310 | 165/1 | DA+6 | 43.8044 | 479220.3986 | 2026-03-01 | Deglal Mahato (MP) | In-Progress | 2026-03-03 |  |  | MP

## Balance Erc-RAJ (hidden)
Balance Erection Status (Rajasthan)
SL No | Loc No | TOT | Tower Availability | Current Status | Remarks
1 | 99/1 | DA+6 | NO | Erectable | Tower Parts not available-Supply in PGCIL Scope.
2 | 99/2 | DA+6 | NO | Erectable
3 | 99/3 | DA+0 | NO | Erectable
4 | 99/4 | DA+0 | NO | Erectable
5 | 99/5 | DA+0 | NO | Erectable
6 | 99/6 | DA+0 | NO | Erectable
7 | 99/7 | DA+6 | YES | WIP
8 | 103/9 | DA+3 | Yes | Planned
9 | 110/0 | DC2+3 |  | Water logged
10 | 118/0 | DD60+6 | NO |  | Tower Parts availability-Last Week of November-25.
11 | 122/0 | DD60+3 | Yes | Planned
12 | 132/0 | DD60+6 | NO |  | Tower Parts availability-Last Week of November-25.
13 | 135/3 | DA+9 | Yes | Water logged
14 | 140/0 | DC1+9 | Yes | Planned
15 | 141/0 | DD45+0 | Yes | Planned | Approach Issue.
16 | 142/0 | DD45+3 | Yes | 11 Kv Line shifting required
17 | 144A/2 | DA+3 | Yes | Opium Planted
18 | 147/0 | DB2+6 | Yes | Chia Planted | Land Owner objection
19 | 148/0 | DD60+6 | NO |  | Tower Parts availability-Last Week of November-25.
20 | 149B/1 | DB2+15 | NO |  | Tower Parts availability-December-25.
21 | 149B/4 | DA+0 | Yes | WIP
22 | 151/0 | DD45+3 | Yes | Garlic Planted
23 | 152/1 | DA+6 | Yes | Opium Planted
24 | 152/2 | DA+0 | Yes | Opium Planted | Managable
25 | 152/3 | DA-1.5 | Yes | Opium Planted
26 | 152A/0 | DB1+0 | Yes | Planned
27 | 152A/6 | DA+0 | Yes | Planned | 33 kV Line SD required
28 | 152A/7 | DA+6 | Yes | Planned | 33 kV Line SD required
29 | 152A/10 | DA+0 | Yes | Planned | 33 kV Line SD required
30 | 152A/11 | DA-1.5 | Yes | Opium Planted
31 | 152A/12 | DA-3 | Yes | Opium Planted
32 | 154/4 | DA+3 | Yes | Planned
33 | 155/0 | DC2+0 | Yes | Opium Planted in adjacent land
34 | 155/1 | DA+0 | Yes | Approach Issue
35 | 155/2 | DA+3 | Yes | Approach Issue/Opium
36 | 156/3 | DA+0 | Yes | ROW | Compensation Issue

## ERC ROW-MP (hidden)
Balance Erection Status (MP)
SL No | Loc No | TOT | Tower Availability | Current Status | Remarks
1 | 159/3 | DA+0 | Yes | Shutdown Issue
2 | 161/1 | DA+3 | Yes | Opium Planted
3 | 161/5 | DA+6
4 | 164/2 | DA+0 | Yes | Shutdown Issue
5 | 164/3 | DA+3
6 | 164/4 | DA+0 | Yes | Shutdown Issue
7 | 164/6 | DA+3
8 | 164/7 | DA+3
9 | 165/1 | DA+6 | Yes | Line Shifting Reqd
10 | 165/2 | DA+0 | Yes | Shutdown Issue
11 | 165/3 | DA+0 | Yes | Opium Planted
12 | 165/4 | DA-3 | Yes | Approach Issue
13 | 165/5 | DA-3 | Yes | Approach Issue
14 | 166/2 | DA+0 | Yes | Compensation Issue
15 | 166/3 | DA+0 | Yes | Opium Planted
16 | 166/4 | DA+3
17 | 168/0 | DC2+0 | Yes | Opium Planted
18 | 169/0 | DC1+3
19 | 170/2 | DA+0
20 | 170/3 | DA+0 | Yes | Opium Planted
21 | 170/4 | DA-3 | Yes | ROW | Tower Erectable after Crop Harvesting.
22 | 170/5 | DA+0
23 | 170/6 | DA-3 | Yes | ROW | Tower Erectable after Crop Harvesting.
24 | 170/9 | DA+0 | Yes | Opium Planted
25 | 170/10 | DA+0 | Yes | Opium Planted
26 | 171/0 | DB1+0 | No | Approach Issue
27 | 171/1 | DA-3 | Yes | Opium Planted
28 | 171/2 | DA+0 | Yes | Opium Planted
29 | 171/3 | DA+0 | Yes | ROW | Tower Erectable after Crop Harvesting.
30 | 171/4 | DA+0 | Yes | ROW | Tower Erectable after Crop Harvesting.
31 | 171/6 | DA+0
32 | 171/7 | DA+0
33 | 171/8 | DA-3
34 | 171/9 | DA+0
35 | 171/10 | DA+0
36 | 172/0 | DB1+0
37 | 172/1 | DA-3
38 | 172/4 | DA+0
39 | 172/5 | DA+3 | Yes | Compensation Issue
40 | 173/0 | DB2+0
41 | 173/2 | DA+3
42 | 173/3 | DA+3
43 | 173/4 | DA+3
44 | 174A/1 | DA-3
45 | 174A/4 | DA-3
46 | 174A/5 | DA-3
47 | 175/2 | DA+0
48 | 175/3 | DA+0
49 | 175/4 | DA-3
50 | 176/0 | DC1+3 | No | Approach Issue
51 | 176/1 | DA+3
52 | 176/2 | DA+3
53 | 176/3 | DA+0
54 | 177/0 | DB2+0
55 | 177/1 | DA+3
56 | 177/2 | DA+0
57 | 177/3 | DA+0
58 | 177/4 | DA+3
59 | 177/5 | DA-3
60 | 177/6 | DA-3
61 | 177/7 | DA+0
62 | 177/8 | DA+0
63 | 178/0 | DB2+0
64 | 178/1 | DA+0
65 | 178/2 | DA+6
66 | 178/3 | DA+3
67 | 178/4 | DA-3
68 | 178/5 | DA+0
69 | 179/1 | DA+3
70 | 179/2 | DA+3
71 | 179/4 | DA-3
72 | 179/6 | DA+0
73 | 179/7 | DA+0
74 | 180/0 | DC2+15
75 | 181/1 | DA+0
76 | 181/4 | DA-3
77 | 181/6 | DA+0

## Stringing Compiled
|  |  | Number of TSE | 1
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | Number of Fitters | Hindrance | Remarks
1 | 100/0 To 101/0 | 100/0 | 101/0 | 419 | Manual | Ready | Done | 2026-01-20 | 2026-01-25 | Done | 2026-02-05 | 2026-02-07 |  |  |  | 419 | Done | Alimuddin | 54
2 | 101/0 To 102/0 | 101/0 | 102/0 | 3470 | TSE | Ready | Done | 2026-01-27 | 2026-02-02 | Done | 2026-02-10 | 2026-02-15 |  |  |  | 3470 | Done | Alimuddin | 54
3 | 102/0 To 103/0 | 102/0 | 103/0 | 461 | Manual | Ready | Done | 2026-02-08 | 2026-02-12 | Done | 2026-02-18 | 2026-02-22 |  |  |  | 461 | Done | Alimuddin | 54
4 | 103/0 To 103/5A | 103/0 | 103/5A | 2200 | TSE | Ready | Done | 2026-02-16 | 2026-02-22 | Done | 2026-02-26 | 2026-02-28 |  |  |  | 2200 | Done | Alimuddin | 54
5 | 103/5A To 103/6A | 103/5A | 103/6A | 567 | TSE | Ready | Done | 2026-02-24 | 2026-02-26 | Done | [7 empty] | Alimuddin | 54
6 | 104/0 To 105/0 | 104/0 | 105/0 | 967 | TSE | Ready | WIP | [10 empty] | Alimuddin | 54
7 | 113/0 To 114/0 | 113/0 | 114/0 | 2565 | TSE | Ready | Done | [10 empty] | Sanwaririya Enterprises | 30
|  |  | Total | 10.649 | [11 empty] | 6.55

## Visual Chart
V I S U A L C H A R T
| DATE : |  | 2026-03-02
| Name of Line : |  |  | 765 KV D/C HEXA BEAWAR MANDSAUR T/L
| Project Code: |  |  |  | TA505
| Name of Executing Agency: |  |  |  | M/s. KEC INTERNATIONAL LTD.
[31 empty] | FDN | Ear | ERE | TW | STR
COMMON TOWER
[21 empty] | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 4 | 0 | 4
[25 empty] | 1 |  | 1
[21 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 1
[18 empty] | BAJEL PART |  | 0 | BAJEL | 360 |  | 420 |  | 410 |  | 382
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[21 empty] | DB2+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0
RAJASTHAN REGION
[14 empty] | D |  | D |  |  |  | D |  | D |  | D |  | D |  | D |  | D
|  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 100/0 |  | 101/0 |  | 101/1 |  | 101/2 |  | 101/3 |  | 101/4 |  | 101/5 |  | 101/6 |  | 101/7 |  | 101/8 |  | 102/0
[6 empty] | 1 |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | 1 |  | 2 |  | 3 |  | 4 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
| 338 |  | 370 |  | 380 |  | 400 |  | 418 |  | 418.579 |  | 425 | Completed | 312 | Completed | 381 | Completed | 455 | Completed | 376 | Completed | 401 | Completed | 428 | Completed | 357 | Completed | 335.158 | Completed | 15 | 10 | 15 | 8 | 3888.737
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD45+0 |  | DC1+3 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA-3 |  | DC2+3
[14 empty] | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | DRY |  | DRY
RAJASTHAN REGION
RC
|  | 103/0 |  | 103/1 |  | 103/2 |  | 103/3 |  | 103/4 |  | 103/5 |  | 103/5A |  | 103/5A1 |  | 103/6A |  | 103/7 |  | 103/8 |  | 103/9 |  | 104/0 |  | 104/1 |  | 104/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  |  |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25
| 461.164 |  | 373 |  | 334.67 |  | 321.15 |  | 391 |  | 388 |  | 392 |  | 293 |  | 274 |  | 218 | Completed | 422 |  | 339 |  | 423.633 | Completed | 335.192 | Completed | 326.577 | Completed | 15 | 8 | 15 | 3 | 2660.984
|  |  |  | 0 |  | 0 |  |  |  | 0 |  | X | [7 empty] | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | Completed
|  | DC1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD60+0 |  | DA-3 |  | DD45+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DD45+3 |  | DA-3 |  | DA-3
[12 empty] | Benching | [5 empty] | Benching |  | DFR | [5 empty] | DFR |  | DFR |  | WET
RAJASTHAN REGION
|  | HR |  |  |  |  | GAS PIPE LINE
|  | 105/0 |  | 105/1 |  | 106/0 |  | 108/0 |  | 108/1 |  | 108/2 |  | 108/3 |  | 108/4 |  | 109/0 |  | 109/1 |  | 109/2 |  | 109/3 |  | 109/4 |  | 110/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0
25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
| 304.947 | Completed | 379.11 | Completed | 375.442 |  | 212.418 |  | 326.001 | Completed | 332 | Completed | 285 | Completed | 345 | Completed | 380.282 | Completed | 384.998 | Completed | 360 | Completed | 378 | Completed | 387 | Completed | 439.322 | Completed |  |  | 14 | 11 | 14 | 9
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DC1+0 |  | DA+0 |  | DD60+0 |  | DD45+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DC1+0 |  | DA-1.5 |  | DA-1.5 |  | DA+0 |  | DA+3 |  | DC2+3
|  | WFR |  | WFR | [5 empty] | DFR |  | WET |  | WET |  | WFR |  | DFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR
RAJASTHAN REGION
|  | 110/1 |  | 110/2 |  | 110/3 |  | 110/4 |  | 110/5 |  | 110/6 |  | 110/7 |  | 110/8 |  | 110A/0 |  | 110A/1 |  | 110A/2 |  | 111/0 |  | 111/1 |  | 111/2
|  | Jwala Singh |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53
| 386.733 | Completed | 358.962 | Completed | 399.964 | Completed | 375.845 |  | 417.796 | Completed | 403.677 | Completed | 414.519 | Completed | 415.771 | Completed | 339.11 | Completed | 398.31 | Completed | 390.626 | Completed | 441.234 | Completed | 415.0029 | Completed | 416.9999 | Completed |  |  | 14 | 11 | 14 | 1
|  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA-1.5 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA-1.5 |  | DB1+6 |  | DA+3 |  | DA+3
|  | WFR |  | WFR |  | DRY |  |  |  | WET |  | WFR |  | WFR |  | WFR |  | DFR |  | WFR |  | DFR |  | DFR |  | WFR |  | WFR
Benching
RAJASTHAN REGION
[7 empty] | 400 kV | RC
|  | 111/3 |  | 111/4 |  | 112/0 |  | 113/0 |  | 113/1 |  | 113/2 |  | 113/3 |  | 113/4 |  | 113/5 |  | 113/6 |  | 114/0 |  | 114/1 |  | 114/2 |  | 114/3
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67
| 405.0008 | Completed | 333 | Completed | 383.6369 | Completed | 225.782 |  | 390 | Completed | 343 | Completed | 327 | Completed | 364 | Completed | 308 | Completed | 465 | Completed | 367.662 | Completed | 399.998 | Completed | 426 | Completed | 362 | Completed |  |  | 14 | 13 | 14 | 3
|  | Completed |  | Completed |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+9 |  | DD60+18 |  | DD60+9 |  | DA-3 |  | DA-1.5 |  | DA-3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+0
|  | WET |  | DFR |  | DFR |  |  |  | DFR |  | WFR |  | DFR |  | DFR |  | DFR |  | DFR |  | WET |  | DFR |  | WFR |  | WFR
RAJASTHAN REGION
[17 empty] | 132 kV | [7 empty] | 220kV
|  | 114/4 |  | 114/5 |  | 114/6 |  | 114/7 |  | 114/8 |  | 114/9 |  | 114/10 |  | 115/0 |  | 116/0 |  | 116/1 |  | 116/2 |  | 117/0 |  | 118/0 |  | 119/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81
| 382 |  | 441 | Completed | 309 | Completed | 331 | Completed | 431 | Completed | 396 | Completed | 444 | Completed | 381.622 |  | 200.194 |  | 323.899 | Completed | 403 | Completed | 419.713 | ROW | 239.882 | Completed | 421.011 |  |  |  | 13 | 12 | 13 | 7
|  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed | [5 empty] | Completed |  | Completed |  | 0 |  | 0
|  | DA+3 |  | DA+6 |  | DA-3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD60+3 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DD45+6 |  | DD60+6 |  | DC2+0
|  |  |  | DFR |  | DFR |  | DFR |  | WET |  | WET |  | DFR | [5 empty] | WFR |  | WFR |  |  |  | WFR
Benching
RAJASTHAN REGION
| 220kV | [11 empty] | RLW | [9 empty] | NH
|  | 120/0 |  | 120/1 |  | 120/2 |  | 120/3 |  | 121/0 |  | 122/0 |  | 123/0 |  | 123/1 |  | 123/2 |  | 123/3 |  | 124/0 |  | 125/0 |  | 125/1 |  | 126/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95
| 193.168 |  | 416.997 | Completed | 363 | Completed | 339 | Completed | 473.767 |  | 360.17 |  | 272 |  | 301.25 |  | 349 |  | 299 |  | 318 |  | 244 |  | 343 |  | 399 | Completed |  |  | 14 | 5 | 14 | 2
|  |  |  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed
|  | DD45+3 |  | DA+0 |  | DA-1.5 |  | DA+9 |  | DB1+6 |  | DD60+3 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA-3 |  | DD45+3 |  | DD60+3 |  | DA+0 |  | DB2+0
|  |  |  | WFR |  | WFR |  | WFR | [19 empty] | DFR
RAJASTHAN REGION
RAJ FOREST
|  | RC |  |  |  |  | Proposed 132kV | [12 empty] | RC |  | ULE/RC
|  | 126/1 |  | 126/2 |  | 126/3 |  | 126/4 |  | 127/0 |  | 127/1 |  | 127/2 |  | 127/3 |  | 128/0 |  | 129/0 |  | 129/1 |  | 129A/0 |  | 129A/1 |  | 129A/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
| 412 |  | 420 | Completed | 339 | Completed | 461 | Completed | 324.66 | Completed | 342 | Completed | 392 | Completed | 371 | Completed | 335.587 | Completed | 421.973 | WIP | 330 | WIP | 474.912 |  | 321 | Completed | 400.55 | Completed |  |  | 12 | 7 | 12 | 2
|  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+9 |  | DA-3 |  | DA+3 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DC2+9 |  | DB1+3 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DA+0
|  | Benching |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | Benching |  | Benching |  |  |  | DFR |  | DFR
Benching
RAJASTHAN REGION
[14 empty] | RAJ FOREST | [12 empty] | Temple
[14 empty] | ULE/RC |  | RC
|  | 129A/3 |  | 130/0 |  | 130/1 |  | 130/2 |  | 131/0 |  | 132/0 |  | 133/0 |  | 134/0 |  | 135/0 |  | 135/1 |  | 135/2 |  | 135/3 |  | 136/0 |  | 136/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123
| 342 | Completed | 280 | Completed | 387.996 | Completed | 319 | Completed | 429.453 | Completed | 484.387 |  | 372.194 | WIP | 552.223 | WIP | 396.823 | Completed | 357.996 | Completed | 401 | Completed | 395.009 | Completed | 445.379 |  | 396.995 | Completed |  |  | 12 | 3 | 11 | 3
|  | 0 |  | Completed |  |  |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DB2+0 |  | DA+0 |  | DA-1.5 |  | DD45+9 |  | DD60+6 |  | DB2+3 |  | DC1+0 |  | DD45+0 |  | DA+3 |  | DA+9 |  | DA+9 |  | DC2+3 |  | DA+3
|  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  |  |  | Benching |  | Benching |  | DFR |  | DFR |  | DFR |  | DFR |  |  |  | DFR
Benching
RAJASTHAN REGION
RAJ FOREST
[6 empty] | TP Tower |  |  |  | RC |  | RC |  | ULE/RC |  |  |  | RC |  | RC
|  | 136/2 |  | 136/3 |  | 136/4 |  | 136/5 |  | 137/0 |  | 137A/0 |  | 138/0 |  | 138/1 |  | 138/2 |  | 138/3 |  | 139/0 |  | 139/1 |  | 140/0 |  | 140/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
123 |  |  |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137
| 374.005 |  | 433 | ROW | 390 | ROW | 406.995 | Completed | 411.482 | ROW | 566.681 |  | 326.632 |  | 371.997 |  | 441 | WIP | 445 |  | 332.731 |  | 241.999 |  | 473.131 |  | 439.999 | Completed |  |  | 9 | 0 | 7
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DD60+9 |  | DC2+25 |  | DB1+3 |  | DA-3 |  | DB1+9 |  | DA+3 |  | DB2+0 |  | DB1+3 |  | DC1+9 |  | DA+3
[8 empty] | DFR |  |  |  | Benching |  | Benching | [5 empty] | Benching | [5 empty] | DFR |  | DFR
RAJASTHAN REGION
[6 empty] | RAJ FOREST | [15 empty] | RAJ FOREST
|  |  | 132 kV |  |  | RC |  | ULE/RC |  | ULE | [10 empty] | 400 kV | RC
|  | 141/0 |  | 142/0 |  | 142/1 |  | 143/0 |  | 144/0 |  | 144A/0 |  | 144A/1 |  | 144A/2 |  | 144A/3 |  | 145/0 |  | 146/0 |  | 146/1 |  | 147/0 |  | 147/1
| ` | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | RoW |  | 146 |  | 147 |  | 148 |  | 149 |  | RoW |  | 151
| 398.255 |  | 211.135 |  | 224 |  | 293.493 | WIP | 332.856 |  | 412.345 |  | 429.003 | Completed | 389 |  | 418 | Completed | 365.834 |  | 236.061 |  | 424.998 |  | 413.45 |  | 458 | Completed |  |  | 12 | 1 | 8 | 2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DD45+0 |  | DD45+3 |  | DA-3 |  | DD45+0 |  | DC1+0 |  | DD45+6 |  | DA+0 |  | DA+3 |  | DB1+3 |  | DD60+18 |  | DD60+18 |  | DA+9 |  | DB2+6 |  | DA+9
[6 empty] | Benching |  | Benching |  | Benching |  | WET |  | WFR |  |  |  | WET |  |  |  | Benching | [5 empty] | WET
RAJASTHAN REGION
[22 empty] | RAJ FOREST |  |  |  |  | MP FOREST
[20 empty] | ULE/RC |  | RC |  |  |  | ULE/RC
|  | 147A/0 |  | 147A/1 |  | 147A/2 |  | 147A/3 |  | 147A/4 |  | 147A/5 |  | 148/0 |  | 148/1 |  | 148A/0 |  | 148B/0 |  | 148B/1 |  | 148B/2 |  | 148C/0 |  | 149/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165
| 378.052 |  | 319 | Completed | 365 | Completed | 441 |  | 394 | Completed | 314 | Completed | 473.22 | Completed | 337 |  | 337.574 | Completed | 402.808 |  | 344 |  | 383 |  | 376.826 |  | 481.108 |  |  |  | 14 | 1 | 11
|  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DB1+0 |  | DA-1.5 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+9 |  | DD60+6 |  | DA+0 |  | DB1+6 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DB1+9 |  | DD45+9
|  |  |  | DFR |  | WFR |  |  |  | DFR |  | WFR |  | WFR |  |  |  | WET |  | Benching |  | Benching |  |  |  | Benching
| RAJASTHAN REGION | [25 empty] | MP REGION
| MP FOREST | [10 empty] | RC |  | RC |  | RC
|  | 149/1 |  | 149/2 |  | 149A/0 |  | 149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | 149B/4 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150/4 |  | 150/5
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179
| 317 |  | 341 |  | 329.47 |  | 523.193 |  | 328 |  | 389 |  | 396 |  | 350 |  | 397.48 |  | 323.998 | Completed | 426 | Completed | 374 | Completed | 461 | Completed | 372 | Completed |  |  | 14 | 0 | 13
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+9 |  | DC2+18 |  | DB1+25 |  | DB2+15 |  | DA+6 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+6
[12 empty] | Benching |  | Benching |  | Benching |  |  |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR
| MP REGION | [5 empty] | RAJASTHAN REGION
132 kV
|  | 151/0 |  | 152/0 |  | 152/1 |  | 152/2 |  | 152/3 |  | 152A/0 |  | 152A/1 |  | 152A/2 |  | 152A/3 |  | 152A/4 |  | 152A/5 |  | 152A/6 |  | 152A/7 |  | 152A/8
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
179 | [9 empty] | RoW |  |  |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193
| 440.645 |  | 220.202 |  | 386.001 | Completed | 425 | Completed | 380 | Completed | 354.388 | Completed | 357.996 | Completed | 300 | Completed | 407 | Completed | 373 | Completed | 414 | Completed | 357 | Completed | 423 | Completed | 381 | Completed |  |  | 14 | 12 | 13
|  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DD45+3 |  | DD60+6 |  | DA+6 |  | DA+0 |  | DA-1.5 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6
[6 empty] | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | DFR |  | WET
RAJASTHAN REGION
220 kV
|  | 152A/9 |  | 152A/10 |  | 152A/11 |  | 152A/12 |  | 153/0 |  | 154/0 |  | 154/1 |  | 154/2 |  | 154/3 |  | 154/4 |  | 154/5 |  | 155/0 |  | 155/1 |  | 155/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
193 |  | 194 |  |  |  | RoW |  | RoW |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | RoW |  | RoW |  | RoW
| 456 | Completed | 381 | Completed | 382 | Completed | 341 |  | 352.374 |  | 226.42 |  | 352 | Completed | 332 | Completed | 255 | Completed | 377 |  | 325 | Completed | 368.885 |  | 351.004 | Completed | 409 | Completed |  |  | 14 | 8 | 8
|  | 0 |  | Completed |  | Completed |  | 0 | [5 empty] | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | Completed |  | Completed
|  | DA+6 |  | DA+0 |  | DA-1.5 |  | DA-3 |  | DB1+6 |  | DB2+9 |  | DA-1.5 |  | DA-3 |  | DA-3 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+3
|  | DRY |  | DRY |  | DFR | [7 empty] | DFR |  | DFR |  | DFR |  |  |  | DRY |  |  |  | DRY |  | DRY
RAJASTHAN REGION
[20 empty] | RAJ FOREST |  |  |  | MP FOREST
|  | 155/3 |  | 155/4 |  | 155/5 |  | 156/0 |  | 156/1 |  | 156/2 |  | 156/3 |  | 156/4 |  | 156/5 |  | 156/6 |  | 157/0 |  | 158/0 |  | 158/1 |  | 158/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  |  |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221
| 405 | Completed | 376 | Completed | 439 | Completed | 326.845 |  | 382.999 | Completed | 416 | WIP | 410 | Completed | 336 | Completed | 353 | WIP | 372 |  | 396.128 | WIP | 360.998 |  | 466 |  | 366 |  |  |  | 11 | 10 | 10
|  | Completed |  | Completed |  | Completed |  | 0 |  |  |  | 0 |  | Completed |  |  |  | 0 |  | c |  | 0
|  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+9 |  | DC2+18 |  | DA+6 |  | DA+0
|  | DFR |  | DFR |  | DFR |  | 0 |  | DFR |  |  |  | DFR |  | DFR | [5 empty] | RC
| RAJASTHAN REGION | [22 empty] | MP REGION
|  | 158/3 |  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 160/0 |  | 160/1 |  | 160/2 |  | 160/3 |  | 160/4 |  | 160/5 |  | 161/0 |  | 161/1 |  | 161/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | RoW |  | 235
| 375 |  | 374.761 | Completed | 390.999 |  | 397 |  | 336 | Completed | 383.419 | Completed | 323.001 | Completed | 335 | Completed | 337 | Completed | 339 |  | 351 |  | 377.051 |  | 413.999 |  | 418.004 | Completed |  |  | 14 | 14 | 12
|  |  |  | Completed | [5 empty] | Completed | [7 empty] | Completed
|  | DA-1.5 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-1.5 |  | DA-1.5 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+3 |  | DA+3 |  | DA+3
|  |  |  | DRY | [5 empty] | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | 0 | [5 empty] | DRY
MP REGION
132 KV
|  | 161/3 |  | 161/4 |  | 161/5 |  | 162/0 |  | 162/1 |  | 162/2 |  | 163/0 |  | 164/0 |  | 164/1 |  | 164/2 |  | 164/3 |  | 164/4 |  | 164/5 |  | 164/6
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249
| 417 |  | 383 | Completed | 426 |  | 410.673 |  | 385.997 |  | 305 |  | 423 |  | 302.489 |  | 361 |  | 370.997 |  | 402.003 |  | 398 |  | 420 | Completed | 400 |  |  |  | 14 | 11 | 12
|  |  |  | Completed |  |  |  | c |  | c |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DB1+18 |  | DC2+18 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3
|  |  |  | DRY |  | 0 |  | 0 | [13 empty] | 0 |  | 0 |  | DRY |  | DRY
MP REGION
[6 empty] | RC |  |  |  | RC
|  | 164/7 |  | 164/8 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4 |  | 165/5 |  | 165/6 |  | 166/0 |  | 166/1 |  | 166/2 |  | 166/3 |  | 166/4
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | RoW |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  |  |  | RoW |  | 263
| 419.997 |  | 417.003 |  | 422.12 |  | 277.7 |  | 384.58 |  | 413.93 |  | 387.12 |  | 341.06 |  | 320.95 |  | 330.56 |  | 314 |  | 341.999 |  | 374.001 |  | 344 |  |  |  | 14 | 14 | 11
|  | DA+3 |  | DA+6 |  | DB1+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DC1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3
|  | 0 |  |  |  | Benching |  |  |  | Benching
MP REGION
132 kV
|  | 166/5 |  | 166/6 |  | 166/7 |  | 166/8 |  | 166/9 |  | 167/0 |  | 167/1 |  | 167/2 |  | 167/3 |  | 167/4 |  | 167/5 |  | 168/0 |  | 169/0 |  | 169/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  |  |  | 276 |  | 277
| 394 |  | 355 |  | 349 |  | 367 |  | 390 |  | 388.874 |  | 359.996 |  | 372 |  | 388 |  | 378 |  | 284 |  | 304.535 |  | 212.961 |  | 368.004 |  |  |  | 14 | 14 | 14
|  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC2+0 |  | DC1+3 |  | DA-1.5
|  |  |  | 0 |  | 0 |  | 0 |  | 0
ss
MP REGION
|  | 169/2 |  | 169/3 |  | 169/4 |  | 169/5 |  | 169/6 |  | 169/7 |  | 169/8 |  | 169/9 |  | 170/0 |  | 170/1 |  | 170/2 |  | 170/3 |  | 170/4 |  | 170/5
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 | [5 empty] | 291
| 378 |  | 386 |  | 377 |  | 343 |  | 384 |  | 351 |  | 348 | WIP | 327 |  | 326.874 |  | 380.002 |  | 383 |  | 370 |  | 355 |  | 350 |  |  |  | 13 | 13 | 11
[12 empty] | c |  | 0
|  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-1.5 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0
MP REGION
|  | 170/6 |  | 170/7 |  | 170/8 |  | 170/9 |  | 170/10 |  | 171/0 |  | 171/1 |  | 171/2 |  | 171/3 |  | 171/4 |  | 171/5 |  | 171/6 |  | 171/7 |  | 171/8
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
291 |  | RoW |  | 293 |  | 294 |  | RoW |  | RoW |  | 297 |  | RoW |  | RoW |  | RoW |  | RoW |  | 302 |  | 303 |  | 304 |  | 305
| 352 |  | 352 |  | 344 |  | 377 |  | 353 |  | 395.454 |  | 344.996 |  | 364 |  | 366 |  | 367 |  | 364 | ROW | 353 |  | 366 |  | 344 |  |  |  | 13 | 10 | 2
|  | 0 |  | 0 | [17 empty] | 0 |  | 0
|  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3
MP REGION
|  | 171/9 |  | 171/10 |  | 172/0 |  | 172/1 |  | 172/2 |  | 172/3 |  | 172/4 |  | 172/5 |  | 172/6 |  | 173/0 |  | 173/1 |  | 173/2 |  | 173/3 |  | 173/4
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | RoW |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
| 356 |  | 375 |  | 376.62 |  | 353 |  | 352 |  | 349 |  | 356 |  | 345 |  | 400 |  | 319.379 |  | 343.76 |  | 322.5 |  | 453.99 |  | 359.96 |  |  |  | 14 | 13 | 12
0
|  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA+3 |  | DA+3 |  | DA+3
MP REGION
|  | 174A/0 |  | 174A/1 |  | 174A/2 |  | 174A/3 |  | 174A/4 |  | 174A/5 |  | 174B/0 |  | 175/0 |  | 175/1 |  | 175/2 |  | 175/3 |  | 175/4 |  | 176/0 |  | 176/1
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | RoW |  | 333
| 447.53 |  | 399 |  | 353 |  | 355 |  | 331 |  | 335 |  | 336 |  | 244 |  | 354 |  | 341 |  | 323 |  | 333 |  | 323.564 |  | 414.996 |  |  |  | 14 | 12 | 8
[14 empty] | 0 |  | 0 |  | c |  | 0
|  | DC1+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DB2+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC1+3 |  | DA+3
MP REGION
RC
|  | 176/2 |  | 176/3 |  | 177/0 |  | 177/1 |  | 177/2 |  | 177/3 |  | 177/4 |  | 177/5 |  | 177/6 |  | 177/7 |  | 177/8 |  | 178/0 |  | 178/1 |  | 178/2
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347
| 423.004 |  | 345 |  | 381.403 |  | 396.002 |  | 371 |  | 329 |  | 366 |  | 340 |  | 347 |  | 352 |  | 381 |  | 389.734 |  | 374.998 |  | 365.998 |  |  |  | 14 | 14 | 9
|  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+6
Benching
MP REGION
|  | 178/3 |  | 178/4 |  | 178/5 |  | 179/0 |  | 179/1 |  | 179/2 |  | 179/3 |  | 179/4 |  | 179/5 |  | 179/6 |  | 179/7 |  | 179/8 |  | 179/9 |  | 180/0
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | #N/A |  | #N/A |  | #N/A
347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361
| 464 |  | 352.004 |  | 330 |  | 378.94 | ROW | 365 |  | 406 |  | 408.999 | ROW | 383.001 |  | 311 |  | 360 |  | 378 |  | 339 | ROW | 329 |  | 340.121 |  |  |  | 11 | 9 | 9
[8 empty] | 0 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | C
|  | DA+3 |  | DA-3 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+15
MP REGION
| 132 KV | [14 empty] | RC | [6 empty] | ss
|  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3 |  | 181/4 |  | 181/5 |  | 181/6 |  | 182/0 |  | 182B/0(DE)
|  | 0 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A
361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  |  |  | 372
| 209.655 |  | 363 |  | 346 | ROW | 307 | ROW | 301 |  | 320 |  | 325 |  | 320 |  | 300 | ROW | 94 | Gantry | [10 empty] | 6 | 6 | 5
[6 empty] | 0 |  | 0 | [7 empty] | c |  | 0 |  |  |  | 0
|  | DD60+9 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DD60+6 |  | DD60+0 |  | MANDSAUR
MP REGION
[16 empty] | Benching |  | AUX X-ARM
[28 empty] | TOTAL |  |  | 356 | 242 | 301 | 40 | 6549.721
| LEGEND: | [16 empty] | PROGRESS AT A GLANCE :
[6 empty] | Stringing WIP |  | STRINGING COMPLETED |  |  |  | Front Clear For Stringing |  | Check Survey COMP. |  |  |  | SR. NO. |  | ACTIVITY |  |  | UNIT | TOTAL |  | COMPLETED |  | BALANCE |  |  | `
|  |  |  | EREC. COMP. | [8 empty] | EREC. U/P
|  |  |  | FDN. COMP. |  |  |  | SPAN |  | SPAN |  |  | FDN. U/P |  |  |  |  | 1 |  | Foundation |  |  | Nos. | 379 |  | 356 |  | 23
Material Feeding U/P
|  |  |  | EAR.COMP. | [13 empty] | 2 |  | Erection |  |  | Nos. | 379 |  | 301 |  | 78
Tack. Comp.
[18 empty] | 3 |  | Stringing (Final Sag) |  |  | Km. | 139.591 |  | 6.5497 |  | 133.0413
s
[18 empty] | 4 |  | Earthing |  |  | Nos. | 379 |  | 242 |  | 137
| NH/SH Xing |  | RAILWAY Xing |  |  | 11/33 KV X-ING | [5 empty] | RIVER X-ING |  |  | Metal Road
[9 empty] | 66/132/ 220/400KV CROSSING | [8 empty] | 5 |  | Tack Welding |  |  | Nos. | 379 |  | 40 |  | 339
[20 empty] | Revetment |  |  | Nos. |  |  |  |  | 0

## Erection Productivity
Project Code | Project Name | SPOC | Apr'25 |  | May'25 |  | Jun'25 |  | Jul'25 |  | Aug'25 |  | Sep'25 |  | Oct'25 |  | Nov'25 |  | Dec'25 |  | Jan'26 |  | Feb'26
TA-505 | PGCIL_Part-D - TL02_for 765kV TL Beawar | Partha Pratim Pal | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
|  |  | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT) | (in MT)
|  |  | 1352 | 698 | 1742 | 922 | 1188 | 641 | 752 | 379 | 770 | 435 | 2414 | 1533 | 2482 | 1491 | 3021 | 1502 | 3205 | 2344 | 2616 | 2039 | 1975 | 1258

## Earthing Status (hidden)
765 kV D/C BEAWAR MANDSAUR TRANSMISSION LINE
PROGRESS SUMMARY DETAIL
NOA Date: 22-July-2024 | [8 empty] | Completion Date : 21-June-2026 |  |  |  | Date : 27-05-25
SUPPLY VALUE = 458 Cr. | [8 empty] | SERVICE VALUE = 94.23 Cr. |  |  |  | F&I VALUE = 9.48 Cr. | [6 empty] | 561.71
Sr. No. | Activity |  | UOM |  | Total Qty. |  |  | L2 Qty. | Completed | Balance | Submitted | WIP | Remarks
1 | Details Survey |  | Kms |  | 136.705 |  |  | 126 | 126.324 | 10.381 | 10.381
2 | Check Survey |  | Kms |  | 136.705 |  |  | 126 | 108.679 | 28.026
3 | Soil Testing |  | Nos |  | 34 |  |  | 34
4 | Foundation |  | Nos |  | 371 |  |  | 165 | 355 | 16 |  | 0
| Gang |  | Nos | [5 empty] | 13
| Manpower |  | Nos
5 | Earthing |  | Nos |  | 346 |  |  |  | 94 | 252
6 | Erection |  | Nos |  | 371 |  |  | 98 | 301 | 70 |  | 0
| Gang |  | Nos | [5 empty] | 4
| Manpower |  | Nos
7 | Stringing |  | Nos |  | 136.705 |  |  | 0 | 0 | 136.705
| Gang |  | Nos
| Manpower |  | Nos
Issue : i. DS - pending for approval ii. CS - pending for approval
Supply : Stub : DA : 177 Set, DB : 21 Set, DC : 16 Set, DD45 : 9 Set, DD60 : 13 set Earthing : CP : 84 Set, Pipe : 40 Nos, Rod : 40 Nos Tower : DA BB=107 Set,+0M=52, +3M=35,+6M=19, +9M=3, -1.5=6, -3=14
KEC INTERNATIONAL LIMITED
FOUNDATION DETAIL OF 765KV D/C BEAWAR-MANDSAUR TR LINE
Sr. No | Loc No. | Type of Tower | TOF | Region | Earthing Status | Type of Earthing (Pipe Type/CP) | JMC Status | Cement (Bags) |  |  | Conc Vol |  | Excv Vol(m3) | R/F (KG) | Wt of Stub(MT) | Rev(Inr) | Earthing Vendor | Month of Execution | Foundation Sub Contractor | Foundation Status | Excavation |  | Foundation | Foundation completion | Remarks if any
[8 empty] | RCC | PCC | Toal Cement | M 20(m3) | M 10(m3) | [8 empty] | Start | Completion | Start
Total = | [7 empty] | 125897.632 | 6532.0004 | 132429.6324 | 15724.169 | 1463.911 | 96505.589 | 1032821.91 | 395.4325 | 307074973.8626 |  |  |  | 355
| 101/2 | DA+9 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-10-01 | RST | Complete | 2024-09-11 | 2024-09-26 | 2024-10-02 | 2024-10-06 |  | 1
| 100/0 | DD45+0 | WET | RAJ | Done | Pipe Type |  | 1239.68 | 70.18 | 1309.86 | 154.96 | 15.95 | 1192.7 | 15096 | 2.495 |  |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-16
| 101/0 | DC1+3 | DFR | RAJ | Done | CP |  | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 |  | 2025-05-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-31
| 101/1 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | RST | Complete | 2024-11-02 | 2024-11-08 | 2024-11-13 | 2024-11-14 |  | 2
| 101/3 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-10-01 | RST | Complete | 2024-10-01 | 2024-10-06 | 2024-10-08 | 2024-10-11 |  | 1
| 101/4 | DA+6 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-10-01 | RST | Complete | 2024-09-16 | 2024-09-21 | 2024-10-19 | 2024-10-21 |  | 1
| 101/5 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-10-01 | RST | Complete | 2024-09-22 | 2024-09-26 | 2024-10-23 | 2024-10-25 |  | 1
| 101/6 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | RST | Complete | 2024-10-24 | 2024-10-26 | 2024-10-30 | 2024-11-02 |  | 1
| 101/7 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | RST | Complete | 2024-11-10 | 2024-11-14 | 2024-11-17 | 2024-11-18 |  | 2
| 101/8 | DA-3 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2024-11-01 | RST | Complete | 2024-10-28 | 2024-11-02 | 2024-11-07 | 2024-11-08 |  | 2
| 102/0 | DC2+3 | DRY | RAJ | Done | Pipe Type |  | 856 | 38 | 894 | 106.91 | 8.53 | 653.08 | 5502 | 2.3488 | 2257063.7747 |  | 2024-12-01 | RST | Complete | 2024-11-22 | 2024-11-25 | 2024-12-11 | 2024-12-14 |  | 3
| 103/0 | DC1+6 | DFR | RAJ | Done | CP | Done | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 |  | 2025-05-12 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-22
| 103/1 | DA+0 | DRY | RAJ |  |  |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-05-07 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-11
| 103/2 | DA+0 | DRY | RAJ |  |  |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-13
45 | 103/3 | DA+0 | DFR | RAJ | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-08
| 103/4 | DA+0 | DRY | RAJ |  |  |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | APRIL-25 | Rajesh Suwalkar | Complete |  |  |  | 2025-04-22
1 | 103/5 | DA+3 | DFR | RAJ |  |  |  | 287.84 | 13.222 | 301.062 | 35.98 | 3.005 | 172.05 | 2466.9 | 0.957 |  |  | 2025-11-01 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-14 | Hold
| 103/5A | DD60+0 | DFR | RAJ | Done | CP | Done | 988.64 | 48.18 | 1036.82 | 123.58 | 10.95 | 692 | 10940 | 3.159 | 3395120.3851 |  | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-03
| 103/5A1 | DA-3 | DFR | RAJ | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-05-05
2 | 103/6A | DD45+0 | DRY | RAJ | Done | Pipe Type | Done | 864 | 45.364 | 909.364 | 108 | 10.31 | 783 | 9428 | 2.4947 | 2836089.3524 |  | 2025-05-03 | Sumit Const/Om Prakash | Complete | 2025-01-18 |  |  | 2025-05-18 | Hold
| 103/7 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Rajesh Suwalkar | Complete | 2025-01-05 | 2025-01-10 | 2025-01-11 | 2025-01-15
| 103/8 | DA+3 | DRY | RAJ |  |  |  | 267.36 | 13.86 | 281.22 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 705045.3467 |  | 2025-05-12 | Sumit Const/Om Prakash | Complete | 2025-05-22 |  |  | 2025-05-24
| 103/9 | DA+3 | WET | RAJ |  |  |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-19
11 | 104/0 | DD45+3 | DFR | RAJ | Done | CP |  | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 |  | 2025-02-01 | Rajesh Suwalkar | Complete | 2025-01-27 | 2025-02-02 | 2025-02-05 | 2025-02-07
| 104/1 | DA-3 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-11-01 | RST | Complete | 2024-11-17 | 2024-11-19 | 2024-11-25 | 2024-11-27 |  | 2
| 104/2 | DA-3 | WET | RAJ | Done | Pipe Type |  | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 |  | 2024-12-01 | Ashutosh Infra | Complete | 2024-11-15 | 2024-11-18 | 2024-11-29 | 2024-12-03 |  | 3
| 105/0 | DC1+0 | WFR | RAJ |  |  |  | 916 | 42 | 958 | 114.5 | 9.44 | 591.37 | 5795 | 2.3488 | 2671411.6827 |  | 2024-11-01 | RST | Complete | 2024-11-20 | 2024-11-21 | 2024-11-29 | 2024-11-30 |  | 3
| 105/1 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Ashutosh Infra | Complete | 2024-10-10 | 2024-11-04 | 2024-11-12 | 2024-11-19 |  | 2
| 106/0 | DD60+0 | DFR | RAJ |  |  |  | 988.64 | 48.18 | 1036.82 | 123.58 | 10.95 | 692 | 10940 | 3.159 | 3395120.3851 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-22
| 108/0 | DD45+0 | DRY | RAJ |  |  |  | 864 | 45.364 | 909.364 | 108 | 10.31 | 783 | 9428 | 2.4947 | 2836089.3524 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-27
| 108/1 | DA-3 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-12-01 | Lotus Const. | Complete | 2024-10-20 | 2024-11-27 | 2024-12-08 | 2024-12-13 |  | 3
| 108/2 | DA-3 | WET | RAJ | Done | Pipe Type |  | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 |  | 2024-11-01 | Lotus Const. | Complete | 2024-10-26 | 2024-11-16 | 2024-11-29 | 2024-11-30 |  | 2
| 108/3 | DA-3 | WET | RAJ | Done | Pipe Type |  | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 |  | 2024-12-01 | Rajesh Suwalkar | Complete | 2024-12-07 | 2024-12-11 | 2024-12-14 | 2024-12-19 |  | 3
| 108/4 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-10-01 | Manirul Khan/Tower Foundation | Complete | 2024-10-17 | 2024-10-20 | 2024-10-27 | 2024-10-28 |  | 2
| 109/0 | DC1+0 | DFR | RAJ | Done | CP |  | 611 | 28 | 639 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 |  | 2024-12-01 | Rajesh Suwalkar | Complete | 2024-12-22 | 2024-12-25 | 2024-12-29 | 2024-12-31 |  | 4
| 109/1 | DA-1.5 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-10-01 | Rajesh Suwalkar | Complete | 2024-10-03 | 2024-10-13 | 2024-10-26 | 2024-10-29 |  | 2
| 109/2 | DA-1.5 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-10-01 | Rajesh Suwalkar | Complete | 2024-09-09 | 2024-09-25 | 2024-10-01 | 2024-10-07 |  | 1
| 109/3 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Rajesh Suwalkar | Complete | 2024-11-08 | 2024-11-23 | 2024-11-29 | 2024-11-30 |  | 3
1 | 109/4 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2025-02-01 | Rajesh Suwalkar | Complete | 2025-02-10 | 2025-02-16 | 2025-02-15 | 2025-02-17
| 110/0 | DC2+3 | WFR | RAJ | Done | CP |  | 1065 | 50 | 1115 | 133.07 | 11.19 | 707.57 | 8267 | 2.3488 | 3282540.8247 |  | 2024-12-01 | Aadinath | Complete | 2024-11-25 | 2024-11-29 | 2024-12-12 | 2024-12-17 |  | 3
| 110/1 | DA-1.5 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Surya Enterprise | Complete | 2024-10-08 | 2024-10-22 | 2024-11-18 | 2024-11-22 |  | 2
| 110/2 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Aadinath | Complete | 2024-11-10 | 2024-11-19 | 2024-11-25 | 2024-11-29 |  | 3
| 110/3 | DA+3 | DRY | RAJ | Done | Pipe Type |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2024-11-01 | Aadinath | Complete | 2024-11-06 | 2024-11-10 | 2024-11-14 | 2024-11-17 |  | 2
| 110/4 | DA+3 | DFR | RAJ |  |  |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-06-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-06-07
| 110/5 | DA+3 | WET | RAJ |  |  |  | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 |  | 2024-11-01 | Soham Const. | Complete | 2024-11-06 | 2024-11-10 | 2024-11-21 | 2024-11-23
| 110/6 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-10-01 | Soham Const. | Complete | 2024-10-06 | 2024-10-10 | 2024-10-22 | 2024-10-24 |  | 1
| 110/7 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | Soham Const. | Complete | 2024-10-15 | 2024-11-14 | 2024-11-27 | 2024-11-29 |  | 2
| 110/8 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Soham Const. | Complete | 2024-10-14 | 2024-11-10 | 2024-11-14 | 2024-11-15 |  | 2
2 | 110A/0 | DB2+0 | DFR | RAJ |  |  |  | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 |  | 2025-02-01 | Om Prakash | Complete | 2025-02-15 | 2025-02-18 | 2025-02-19 | 2025-02-20
| 110A/1 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | Reshmi Devi | Complete | 2024-10-25 | 2024-11-04 | 2024-11-08 | 2024-11-10 |  | 2
| 110A/2 | DA-1.5 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-10-01 | Surya Enterprise | Complete | 2024-09-28 | 2024-09-30 | 2024-10-07 | 2024-10-11 |  | 1
| 111/0 | DB1+6 | DFR | RAJ | Done | CP |  | 471 | 22 | 493 | 58.84 | 4.94 | 296.18 | 2692 | 1.768 | 1324196.9091 |  | 2025-01-01 | Om Prakash | Complete | 2024-12-29 | 2025-01-02 | 2025-01-03 | 2025-01-04
1 | 111/1 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | Garg Const. | Complete | 2024-10-18 | 2024-10-25 | 2024-10-30 | 2024-11-04 |  | 2
2 | 111/2 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-11-01 | Garg Const. | Complete | 2024-11-01 | 2024-11-13 | 2024-11-15 | 2024-11-18 |  | 2
3 | 111/3 | DA+0 | WET | RAJ | Done | Pipe Type |  | 383 | 23 | 406 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 | 1054575.3581 |  | 2024-12-01 | Garg Const. | Complete | 2024-11-08 | 2024-11-30 | 2024-11-02 | 2024-12-08 |  | 3
4 | 111/4 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Garg Const. | Complete | 2024-11-27 | 2024-12-12 | 2024-12-14 | 2024-12-16 |  | 3
| 112/0 | DD60+18 | DFR | RAJ | Done | CP | Done | 1020 | 51 | 1071 | 127.5 | 11.49 | 728 | 11839 | 2.564 | 3567510.026 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-02 | 2025-01-22 | 2025-01-24 | 2025-01-27
| 113/0 | DD60+9 | WFR | RAJ |  |  |  | 1357.44 | 71.28 | 1428.72 | 169.68 | 16.2 | 1042.48 | 21650.28 | 5.559 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-28
| 113/1 | DA-3 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-11-01 | Reshmi Devi | Complete | 2024-11-13 | 2024-11-18 | 2024-11-20 | 2024-11-22 |  | 2
| 113/2 | DA-1.5 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-11-01 | Reshmi Devi | Complete | 2024-10-29 | 2024-11-12 | 2024-11-14 | 2024-11-14 |  | 2
| 113/3 | DA-3 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-11-01 | Reshmi Devi | Complete | 2024-11-10 | 2024-11-26 | 2024-11-27 | 2024-11-29 |  | 2
| 113/4 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-12-01 | Surya Enterprise | Complete | 2024-12-03 | 2024-12-04 | 2024-12-07 | 2024-12-09 |  | 3
| 113/5 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Reshmi Devi | Complete | 2024-11-22 | 2024-11-30 | 2024-12-04 | 2024-12-05 |  | 3
| 113/6 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Reshmi Devi | Complete | 2024-12-01 | 2024-12-10 | 2024-12-10 | 2024-12-12 |  | 3
| 114/0 | DC2+0 | WET | RAJ | Done | Pipe Type | Done | 1233 | 58 | 1291 | 154.01 | 13.15 | 990.19 | 10225 | 2.3488 | 3510320.9327 |  | 2024-12-01 | Om Prakash | Complete | 2024-12-03 | 2024-12-05 | 2024-12-11 | 2024-12-19 |  | 3
| 114/1 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Jitendra/JSC | Complete | 2024-12-04 | 2024-12-27 | 2024-12-29 | 2024-12-31
| 114/10 | DA+6 | DFR | RAJ | Done | CP | Done | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-11-01 | Om Prakash | Complete | 2024-11-16 | 2024-11-17 | 2024-11-19 | 2024-11-20 |  | 2
| 114/2 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-12-01 | Jitendra/JSC | Complete | 2024-12-03 | 2024-12-11 | 2024-12-12 | 2024-12-14 |  | 3
| 114/3 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2024-12-01 | Jitendra/JSC | Complete | 2024-11-22 | 2024-11-26 | 2024-12-03 | 2024-12-07 |  | 3
| 114/4 | DA+3 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2025-09-14 | Vikash Cont. | Complete |  |  |  | 2025-09-19
| 114/5 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Yash Infra | Complete | 2024-12-03 | 2024-12-05 | 2024-12-06 | 2024-12-07 |  | 3
| 114/6 | DA-3 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-11-01 | Yash Infra | Complete | 2024-11-19 | 2024-11-26 | 2024-11-29 | 2024-11-30 |  | 2
| 114/7 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-11-01 | Yash Infra | Complete | 2024-11-14 | 2024-11-22 | 2024-11-25 | 2024-11-28 |  | 2
| 114/8 | DA+6 | WET | RAJ | Done | Pipe Type | Done | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 |  | 2024-11-01 | Om Prakash | Complete | 2024-11-14 | 2024-11-20 | 2024-11-22 | 2024-11-23 |  | 2
| 114/9 | DA+3 | WET | RAJ | Done | Pipe Type | Done | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 |  | 2024-11-01 | Om Prakash | Complete | 2024-11-17 | 2024-11-22 | 2024-11-26 | 2024-11-27 |  | 2
33 | 115/0 | DD60+3 | DFR | RAJ | Done | CP | Done | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 | 3508292.3251 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-03 | 2 PIT EXCAVATION DONE.
30 | 116/0 | DD45+3 | DFR | RAJ | Done | CP | Done | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-07 | PIT Marking Done.
| 116/1 | DA+3 | WFR | RAJ | Done | CP | Done | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-12-01 | Om Prakash | Complete | 2024-12-17 | 2024-12-25 | 2024-12-26 | 2024-12-26 |  | 4
| 116/2 | DA+3 | WFR | RAJ | Done | CP | Done | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-12-01 | Om Prakash | Complete | 2024-11-18 | 2024-11-29 | 2024-11-29 | 2024-12-01
9 | 118/0 | DD60+6 | WFR | RAJ |  | CP |  | 1484 | 72 | 1556 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 | 5088278.7391 |  | 2025-02-01 | Om Prakash/s | Complete | 2025-02-18 | 2025-02-24 | 2025-02-24 | 2025-02-27
31 | 119/0 | DC2+0 | DFR | RAJ | Done | CP | Done | 755.6 | 32.296 | 787.896 | 94.45 | 7.34 | 453.17 | 4557 | 2.3488 | 2124325.9997 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-15 | PIT Marking Done.
32 | 120/0 | DD45+3 | DFR | RAJ | Done | CP | Done | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 |  | APRIL-25 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-04-12 | PIT Marking Done.
| 120/1 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-01-01 | UDS | Complete | 2024-11-27 | 2024-11-30 | 2025-01-06 | 2025-01-12
| 120/2 | DA-1.5 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-01-01 | UDS | Complete | 2024-12-25 | 2025-01-27 | 2025-01-29 | 2025-01-30
| 120/3 | DA+9 | WFR | RAJ | Done | CP |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2025-01-01 | UDS | Complete | 2024-11-28 | 2024-11-30 | 2025-01-23 | 2025-01-24
| 121/0 | DB1+6 | DRY | RAJ |  |  |  | 516.08 | 24.332 | 540.412 | 64.51 | 5.53 | 432.79 | 2988 | 1.768 | 1344129.8151 |  | 2025-06-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-06-02
| 122/0 | DD60+3 | WFR | RAJ |  |  |  | 1483.2 | 71.28 | 1554.48 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-26
| 123/0 | DD60+6 | WFR | RAJ |  |  |  | 1483.2 | 71.28 | 1554.48 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-03
| 123/1 | DA+0 | WET | RAJ |  |  |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2467 | 0.866 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-08
| 123/2 | DA+0 | WFR | RAJ |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-22
| 123/3 | DA-3 | WFR | RAJ |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-12
| 124/0 | DD45+3 | WFR | RAJ | [13 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-09
| 125/0 | DD60+3 | WFR | RAJ | [13 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-04
| 125/1 | DA+0 | WFR | RAJ |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  |  | 2025-12-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-12-15
| 126/0 | DB2+0 | DFR | RAJ | Done | CP | Done | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 |  | 2024-12-01 | Om Prakash | Complete | 2024-12-03 | 2024-12-06 | 2024-12-14 | 2024-12-16
| 126/1 | DA+9 (RC) | WFR | RAJ | Done | CP |  | 387.88 | 19.932 | 407.812 | 48.485 | 4.53 | 269.795 | 3205.12 | 0.957 |  |  | 2025-10-14 | Vikash Cont. | Complete |  |  |  | 2025-10-05
| 126/2 | DA-3 | DFR | RAJ | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-09 | 2025-01-17 | 2025-01-18 | 2025-01-18
| 126/3 | DA+3 | DFR | RAJ | Done | CP | Done | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-11 | 2025-01-16 | 2025-01-20 | 2025-01-20
| 126/4 | DA+9 | DFR | RAJ | Done | CP | Done | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Om Prakash | Complete | 2024-12-12 | 2024-12-14 | 2024-12-17 | 2024-12-17 |  | 3
| 127/0 | DD45+0 | DFR | RAJ | Done | CP | Done | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.495 | 2635411.7904 |  | 2024-12-01 | Om Prakash | Complete | 2024-12-19 | 2024-12-21 | 2024-12-25 | 2024-12-29 |  | 4
| 127/1 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-14 | 2024-12-18 | 2024-12-20
| 127/2 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-11 | 2024-12-13 | 2024-12-15 |  | 3
| 127/3 | DA+6 | DRY | RAJ |  | Pipe Type |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2024-12-01 | Soham Const. | Complete | 2024-12-03 | 2024-12-05 | 2024-12-07 | 2024-12-10 |  | 3
| 128/0 | DC2+9 | DFR | RAJ | Done | CP | Done | 772 | 34 | 806 | 96.5 | 7.54 | 466 | 4756 | 2.3488 | 2183199.4487 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-24 | 2025-01-27 | 2025-01-29 | 2025-01-31
| 129A/0 | DD45+0 | DFR | RAJ |  |  |  | 740.24 | 39.732 | 779.972 | 92.53 | 9.03 | 564 | 8669 | 2.495 |  |  | 2025-12-14 | RST | Complete |  |  |  | 2025-12-23
16 | 129A/1 | DA+0 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Om Prakash | Complete | 2025-02-07 | 2025-02-09 | 2025-02-11 | 2025-02-11
17 | 129A/2 | DA+0 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Om Prakash | Complete | 2025-02-03 | 2025-02-08 | 2025-02-10 | 2025-02-10
15 | 129A/3 | DA+0 | WFR | RAJ |  |  |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-02-01 | Om Prakash | Complete | 2025-01-02 | 2025-02-02 | 2025-02-06 | 2025-02-06
18 | 130/0 | DB2+0 | WFR | RAJ | Done | CP |  | 805 | 39 | 844 | 100.6 | 8.84 | 552.01 | 5686.38 | 1.768 | 2438641.2023 |  | 2025-02-01 | Om Prakash | Complete | 2025-02-08 | 2025-02-12 | 2025-02-12 | 2025-02-14
| 130/1 | DA+0 | WFR | RAJ | Done | CP |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-28 | 2025-01-30 | 2025-01-31 | 2025-01-31
5 | 130/2 | DA-1.5 | WFR | RAJ |  |  |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-02-01 | Om Prakash | Complete | 2025-02-02 | 2025-02-07 | 2025-02-08 | 2025-02-09
| 131/0 | DD45+9 | WFR | RAJ | Done | CP |  | 1212 | 60 | 1272 | 151.38 | 13.48 | 860.33 | 12577 | 2.4947 | 4121357.0384 |  | 2025-01-01 | Om Prakash | Complete | 2025-01-05 | 2025-01-16 | 2025-01-12 | 2025-01-17
| 132/0 | DD60+6 | DRY | RAJ |  |  |  | 1145.12 | 57.024 | 1202.144 | 143.14 | 12.96 | 976 | 12968 | 3.159 | 3663688.3031 |  | APRIL-25 | RST | Complete |  |  |  | 2025-04-22
| 135/0 | DD45+0 | DFR | RAJ |  |  |  | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.4947 | 2635411.7904 |  | 2025-03-01 | RST | Complete | 2025-02-27 | 2025-03-02 | 2025-03-04 | 2025-03-05
19 | 135/1 | DA+3 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-02-08 | 2025-02-10 | 2025-02-16 | 2025-02-17
22 | 135/2 | DA+9 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-02-10 | 2025-02-12 | 2025-02-18 | 2025-02-21
26 | 135/3 | DA+9 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-02-15 | 2025-02-18 | 2025-02-21 | 2025-02-22
| 136/0 | DC2+3 | DFR | RAJ |  |  |  | 772 | 33.176 | 805.176 | 96.5 | 7.54 | 466 | 4754 | 2.3488 | 1765260.9827 |  | APRIL-25 | RST | Complete |  |  |  | 2024-04-28
3 | 136/1 | DA+6 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-02-19 | 2025-02-20 | 2025-02-24 | 2025-02-25
| 136/2 | DA+3 | DFR | RAJ |  |  |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-05-03 | RST | Complete |  |  |  | 2025-05-03
| 136/5 | DA+3 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-02-24 | 2025-02-25 | 2025-02-27 | 2025-02-27
| 138/0 | DB1+3 | DFR | RAJ |  |  |  | 441.04 | 23.056 | 464.096 | 55.13 | 5.24 | 316.48 | 5978.28 | 2.003 |  |  | 2025-11-14 | RST | Complete |  |  |  | 2025-11-29
| 138/1 | DA-3 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-10
| 138/3 | DA+3 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete | 2026-02-10 |  |  | 2026-02-12
| 139/0 | DB2+0 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete | 2026-01-31 |  |  | 2026-02-04
| 139/1 | DB1+3 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete | 2026-02-04 |  |  | 2026-02-06
16 | 140/0 | DC1+9 | DFR | RAJ |  |  |  | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 |  | 2025-03-01 | RST | Complete | 2025-03-06 |  |  | 2025-03-12
9 | 140/1 | DA+3 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | RST | Complete | 2025-01-16 | 2025-01-27 | 2025-02-04 | 2025-02-05
| 141/0 | DD45+0 | DFR | RAJ |  |  |  | 741 | 40 | 781 | 92.53 | 9.03 | 564 | 8669 | 2.495 | 2635411.7904 |  | 2025-05-08 | RST | Complete |  |  |  | 2025-05-13
| 142/0 | DD45+3 | DRY | RAJ |  |  |  | 882.48 | 46.904 | 929.384 | 110.31 | 10.66 | 809 | 9896 | 2.4947 | 2836089.3524 |  | 2025-05-12 | RST | Complete |  |  |  | 2025-05-20
18 | 144A/0 | DD45+6 | WET | RAJ | Done | Pipe Type |  | 1264.64 | 72.248 | 1336.888 | 158.08 | 16.42 | 1226.53 | 15882 | 2.4947 | 4266794 |  | 2025-03-01 | RST | Complete |  |  |  | 2025-03-22
| 144A/1 | DA+0 | WFR | RAJ |  |  |  | 333 | 19 | 352 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 | 984923.6361 |  | 2025-01-01 | RST | Complete | 2025-01-08 | 2025-01-08 | 2025-01-15 | 2025-01-16
27 | 144A/2 | DA+3 | DRY | RAJ |  |  |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2025-03-01 | RST | Complete |  |  |  | 2025-03-28 | 4 Pit EXCAVATION DONE
| 144A/3 | DB1+3 | WET | RAJ |  |  |  | 759 | 41 | 800 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 | 2154107.4571 |  | 2025-01-01 | RST | Complete | 2025-01-02 | 2025-01-04 | 2025-01-18 | 2025-01-19
| 145/0 | DD60+18 | WFR | RAJ |  |  |  | 1497.12 | 72.38 | 1569.5 | 187.14 | 16.45 | 1059.44 | 18021 | 2.564 | 5283315.042 |  | 2025-09-14 | RST | Complete |  |  |  | 2025-09-14
| 146/1 | DA+9 | DFR | RAJ-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-25
39 | 147/0 | DB2+6 | DFR | RAJ |  |  |  | 566.48 | 25.564 | 592.044 | 70.81 | 5.81 | 356.96 | 3466 | 1.7681 | 1649958.0771 |  | 2025-03-01 | RST | Complete |  |  |  | 2025-03-31
| 147/1 | DA+9 | WET | RAJ |  |  |  | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 |  | 2025-01-01 | RST | Complete | 2024-12-14 | 2024-12-16 | 2025-01-04 | 2025-01-05
46 | 147A/0 | DB1+0 | DFR | RAJ |  |  |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 |  | APRIL-25 | RST | Complete |  |  |  | 2025-04-10
| 147A/1 | DA-1.5 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2024-12-01 | RST | Complete | 2024-12-11 | 2024-12-13 | 2024-12-27 | 2024-12-27 |  | 4
| 147A/2 | DA+6 | WFR | RAJ |  |  |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-12-01 | RST | Complete | 2024-12-01 | 2024-12-03 | 2024-12-29 | 2024-12-31 |  | 4
| 147A/3 | DA+6 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | APRIL-25 | RST | Complete |  |  |  | 2025-04-10
| 147A/4 | DA+3 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | RST | Complete | 2024-12-01 | 2024-12-05 | 2024-12-18 | 2024-12-19 |  | 3
| 147A/5 | DA+9 | WFR | RAJ |  |  |  | 383 | 20 | 403 | 47.77 | 4.46 | 264.87 | 2353 | 0.86628 | 1126247.4001 |  | 2024-12-01 | RST | Complete | 2024-12-10 | 2024-12-13 | 2024-12-22 | 2024-12-24
| 148/0 | DD60+6 | WFR | RAJ |  |  |  | 1484 | 72 | 1556 | 185.4 | 16.2 | 1042.46 | 15889 | 3.159 | 5088278.7391 |  | 2025-01-01 | RST | Complete | 2025-01-02 | 2025-01-22 | 2025-01-28 | 2025-01-31
3 | 148/1 | DA+0 | DRY | RAJ |  |  |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | APRIL-25 | RST | Complete |  |  |  | 2025-04-12 | PIT Marking Done.
14 | 148A/0 | DB1+6 | WET | RAJ |  |  |  | 759 | 41 | 800 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 | 2154107.4571 |  | 2025-02-01 | RST | Complete | 2025-02-02 | 2025-02-04 | 2025-02-09 | 2025-02-13
| 148B/1 | DA+0 | DFR | RAJ-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-29
| 148B/2 | DA+6 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-15
| 149/0 | DD45+9 | DFR | MP-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-13
| 149/1 | DA+3 | DFR | MP-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-18
| 149/2 | DA+9 | DFR | MP-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-16
| 149A/0 | DC2+18 | DFR | MP-Forest | [13 empty] | 2026-01-14 | RST | Complete |  |  |  | 2026-01-31
| 149B/0 | DB1+25 | WFR | RAJ |  |  |  | 632.8 | 31.988 | 664.788 | 79.1 | 7.27 | 448.4 | 4194 | 1.753 |  |  | 2025-12-14 | RST | Complete |  |  |  | 2025-12-31
| 149B/1 | DB2+15 | WFR | RAJ |  |  |  | 759.04 | 36.256 | 795.296 | 94.88 | 8.24 | 512.32 | 4906 | 1.714 |  |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-09
| 149B/2 | DA+6 | DFR | RAJ |  |  |  | 274.64 | 13.1428 | 287.7828 | 34.33 | 2.987 | 170.915 | 2277.88 | 0.968 |  |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-15
| 149B/3 | DA+3 (RC) | DFR | RAJ |  |  |  | 292.96 | 13.398 | 306.358 | 36.62 | 3.045 | 175.709 | 2610.33 | 1.014 | 752440.0941 |  | 2025-09-14 | RST | Complete |  |  |  | 2025-09-27
| 149B/4 | DA+0 (RC) | DFR | RAJ |  |  |  | 261.32 | 11.946 | 273.266 | 32.665 | 2.715 | 152.99 | 2587.74 | 1.139 |  |  | 2025-10-14 | RST | Complete |  |  |  | 2025-10-17
| 150/0 | DC1+0 | DFR | RAJ |  |  |  | 611 | 28 | 639 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 |  | 2025-05-14 | RST | Complete |  |  |  | 2025-05-31
| 150/1 | DA+6 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Yash Infra | Complete | 2025-01-02 | 2025-01-04 | 2025-01-09 | 2025-01-12
| 150/2 | DA+3 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Yash Infra | Complete | 2025-01-04 | 2025-01-17 | 2025-01-19 | 2025-01-22
| 150/3 | DA+6 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Yash Infra | Complete | 2024-12-12 | 2024-12-17 | 2024-12-19 | 2024-12-21 |  | 3
| 150/4 | DA+6 | DRY | RAJ |  |  |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2024-12-01 | Yash Infra | Complete | 2024-12-15 | 2024-12-19 | 2024-12-22 | 2024-12-24 |  | 4
| 150/5 | DA+6 | DFR | RAJ |  |  |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Yash Infra | Complete | 2024-12-15 | 2024-12-27 | 2024-12-27 | 2024-12-28 |  | 4
| 151/0 | DD45+3 | DFR | RAJ |  |  |  | 756 | 42 | 798 | 94.46 | 9.33 | 584 | 9095 | 2.4947 | 2723053.0864 |  | 2025-06-14 | RST | Complete |  |  |  | 2025-06-29
| 152/0 | DD60+3 | DFR | RAJ |  |  |  | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 | 3508292.3251 |  | 2025-06-14 | RST | Complete |  |  |  | 2025-06-11
| 152/1 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Aadinath | Complete | 2024-12-14 | 2024-12-15 | 2024-12-29 | 2024-12-30
| 152/2 | DA-3 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2024-12-01 | Aadinath | Complete | 2024-12-14 | 2024-12-15 | 2024-12-25 | 2024-12-26 |  | 4
| 152/3 | DA-1.5 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-01-01 | Aadinath | Complete | 2024-12-17 | 2024-12-18 | 2025-01-24 | 2025-01-25
| 152A/0 | DB1+0 | DRY | RAJ | Done | Pipe Type |  | 512 | 25 | 537 | 63.98 | 5.47 | 428.13 | 2899 | 1.768 | 1325884.4911 |  | 2025-01-01 | Reshmi Devi | Complete | 2025-01-01 | 2025-01-02 | 2025-01-14 | 2025-01-17
| 152A/1 | DA-3 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-01-01 | Reshmi Devi | Complete | 2025-01-01 | 2025-01-02 | 2025-01-08 | 2025-01-10
| 152A/10 | DA+0 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-01-01 | Saktawat | Complete | 2025-01-18 | 2025-01-22 | 2025-01-25 | 2025-01-25
5 | 152A/11 | DA-1.5 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Garg Const. | Complete | 2024-12-22 | 2025-01-16 | 2025-01-20 | 2025-01-21
| 152A/12 | DA-3 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-06-14 | Yash Infra | Complete |  |  |  | 2025-06-13
| 152A/2 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Reshmi Devi | Complete | 2025-01-21 | 2025-01-22 | 2025-01-27 | 2025-01-28
| 152A/3 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Reshmi Devi | Complete | 2024-12-15 | 2024-12-20 | 2024-12-21 | 2024-12-22 |  | 3
| 152A/4 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2024-12-01 | Reshmi Devi | Complete | 2024-12-19 | 2024-12-25 | 2024-12-26 | 2024-12-27 |  | 4
| 152A/5 | DA+3 | DRY | RAJ | Done | Pipe Type |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2025-01-01 | Reshmi Devi | Complete | 2024-12-25 | 2024-12-28 | 2024-12-31 | 2025-01-02
| 152A/6 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Reshmi Devi | Complete | 2024-12-25 | 2025-01-22 | 2025-01-23 | 2025-01-23
7 | 152A/7 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Garg Const. | Complete | 2024-12-24 | 2025-01-01 | 2025-01-04 | 2025-01-05
| 152A/8 | DA+6 | WET | RAJ | Done | Pipe Type |  | 419 | 24 | 443 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 | 1161364.3121 |  | 2025-01-01 | Saktawat | Complete | 2024-12-28 | 2024-12-28 | 2025-01-08 | 2025-01-16
| 152A/9 | DA+6 | DRY | RAJ |  |  |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2024-12-01 | Lotus Const. | Complete | 2024-12-23 | 2024-12-25 | 2024-12-29 | 2024-12-29 |  | 4
| 153/0 | DB1+6 | WET | RAJ | Done | Pipe Type |  | 758.8 | 40.216 | 799.016 | 94.85 | 9.14 | 697.81 | 5870 | 1.768 |  |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-13
| 154/0 | DB2+9 | WFR | RAJ | Done | CP |  | 804.8 | 38.896 | 843.696 | 100.6 | 8.84 | 552.01 | 5671.38 | 1.768 |  |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-14
| 154/1 | DA-1.5 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Yash Infra | Complete | 2025-01-23 | 2025-01-27 | 2025-01-29 | 2025-01-30
6 | 154/2 | DA-3 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Yash Infra | Complete | 2025-01-14 | 2025-01-16 | 2025-01-31 | 2025-02-04
| 154/3 | DA-3 | DFR | RAJ |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Lotus Const. | Complete | 2024-12-22 | 2025-02-08 | 2025-02-03 | 2025-02-28
| 154/4 | DA+3 | DRY | RAJ | Done | Pipe Type |  | 267.36 | 13.86 | 281.22 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 705045.3467 |  | 2025-09-14 | RST | Complete |  |  |  | 2025-09-30
13 | 154/5 | DA+0 | DRY | RAJ |  |  |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-02-01 | Yash Infra | Complete | 2025-01-31 | 2025-02-03 | 2025-02-07 | 2025-02-08
| 155/0 | DC2+0 | DRY | RAJ | Done | Pipe Type |  | 835.52 | 36.476 | 871.996 | 104.44 | 8.29 | 635.99 | 5172 | 2.349 |  |  | 2025-10-14 | Vikash Cont. | Complete |  |  |  | 2025-10-17
8 | 155/1 | DA+0 | DRY | RAJ | Done | Pipe Type |  | 236 | 13 | 249 | 29.49 | 2.86 | 233.05 | 1526 | 0.86628 | 645061.9481 |  | 2025-02-01 | Garg Const. | Complete | 2025-02-02 | 2025-02-12 | 2025-02-16 | 2025-02-24
9 | 155/2 | DA+3 | DRY | RAJ | Done | Pipe Type |  | 268 | 14 | 282 | 33.42 | 3.15 | 255.26 | 1904 | 0.86628 | 745277.5161 |  | 2025-02-01 | Garg Const. | Complete | 2025-02-17 | 2025-02-18 | 2025-02-25 | 2025-02-28
| 155/3 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-01-01 | Soham Const. | Complete | 2024-12-25 | 2024-12-29 | 2025-01-20 | 2025-01-21
6 | 155/4 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Garg Const. | Complete | 2024-12-26 | 2025-02-06 | 2025-02-07 | 2025-02-10
| 155/5 | DA+3 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-01-01 | Soham Const. | Complete | 2024-12-23 | 2024-12-29 | 2025-01-13 | 2025-01-15
4 | 156/0 | DC1+0 | DFR | RAJ |  |  |  | 610.8 | 27.808 | 638.608 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 |  | 2025-07-01 | RST | Complete | 2025-02-03 |  |  | 2025-07-15 | Excavation WIP (Blasting) Hold
7 | 156/1 | DA+6 | DFR | RAJ | Done | CP |  | 252 | 13 | 265 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-02-01 | Aadinath | Complete | 2025-01-09 | 2025-02-06 | 2025-02-08 | 2025-02-12
| 156/2 | DA+3 | [5 empty] | 0 | 0 | 0 | [7 empty] | 2025-11-14
8 | 156/3 | DA+0 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Aadinath | Complete | 2025-01-15 | 2025-02-19 | 2025-02-19 | 2025-02-22
12 | 156/4 | DA-3 | DFR | RAJ | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-02-01 | Reshmi Devi | Complete | 2025-01-28 | 2025-02-03 | 2025-02-05 | 2025-02-05
| 156/6 | DA+0 |  | RAJ-Forest | [13 empty] | 2026-02-14 | Vikash Cont. | Complete | 2026-02-06 |  |  | 2026-02-07
| 158/0 | DC2+18 | DFR | MP-Forest | Done | CP |  | 784.48 | 33.836 | 818.316 | 98.06 | 7.69 | 475.74 | 5381 | 2.386 |  |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-31
| 158/1 | DA+6 | DFR | MP-Forest | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.866 |  |  | 2025-12-14 | Vikash Cont. | Complete |  |  |  | 2025-12-31
| 158/2 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-12 | Yash Infra | Complete |  |  |  | 2025-05-16
| 158/3 | DA-1.5 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-04 | Yash Infra | Complete |  |  |  | 2025-05-09
21 | 159/0 | DB2+0 | DRY | MP | Done | Pipe Type |  | 565 | 26 | 591 | 70.56 | 5.83 | 454.86 | 5149 | 1.7681 | 1662016.3703 |  | 2025-02-01 | Reshmi Devi | Complete | 2025-02-09 | 2025-02-16 | 2025-02-22 | 2025-02-24
21 | 159/1 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-19
| 159/2 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-02 | Yash Infra | Complete |  |  |  | 2025-05-04
20 | 159/3 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-02-01 | Reshmi Devi | Complete | 2025-02-08 | 2025-02-08 | 2025-02-16 | 2025-02-16
23 | 160/0 | DB1+0 | DRY | MP | Done | Pipe Type |  | 406 | 22 | 428 | 50.64 | 4.8 | 378.56 | 4711.55 | 1.7681 | 1326238.3039 |  | 2025-02-01 | Yash Infra | Complete | 2025-02-16 | 2025-02-18 | 2025-01-23 | 2025-02-25
| 160/1 | DA-1.5 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Yash Infra | Complete | 2025-02-24 | 2025-03-02 | 2025-03-04 | 2025-03-04
| 160/2 | DA-1.5 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-02-01 | Yash Infra | Complete | 2025-02-19 | 2025-02-21 | 2025-02-27 | 2025-02-28
24 | 160/3 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-02-01 | Yash Infra | Complete | 2025-02-10 | 2025-02-11 | 2025-02-15 | 2025-02-15
10 | 160/4 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Yash Infra | Complete | 2025-03-02 | 2025-03-03 |  | 2025-03-08
11 | 160/5 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Yash Infra | Complete |  |  |  | 2025-03-31 | 4 PIT Excavation Done.
40 | 161/0 | DB2+3 | DRY | MP | Done | Pipe Type |  | 566.8 | 25.872 | 592.672 | 70.85 | 5.88 | 454.86 | 5149 | 1.7681 | 1649958.0771 |  | APRIL-25 | Yash Infra | Complete |  |  |  | 2025-04-28
26 | 161/1 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-26 | 4 PIT Excavation Done.
| 161/2 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Reshmi Devi | Complete | 2025-03-02 | 2025-03-03 | 2025-03-06 | 2025-03-06
38 | 161/3 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Reshmi Devi | Complete |  |  |  | 2025-03-31
8 | 161/4 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-02-01 | Reshmi Devi | Complete | 2025-02-14 | 2025-02-18 | 2025-02-26 | 2025-02-27
8 | 161/5 | DA+6 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Reshmi Devi | Complete | 2025-03-02 | 2025-03-04 | 2025-03-09 | 2025-03-11
| 162/0 | DB2+0 | DRY | MP |  |  |  | 0 | 0 | 0 | [7 empty] | 2026-01-01 | Reshmi Devi | Complete |  |  |  | 2026-01-07 | 2 Pit Excavation Done. (ROW)
| 162/1 | DA+0 | DRY | MP | [13 empty] | 2026-01-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2026-01-24
| 162/2 | DA+0 | DRY | MP | Done | Pipe Type | [11 empty] | 2026-01-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2026-01-08
| 163/0 | DB1+18 | DFR | MP | [13 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-23
| 164/0 | DC2+18 | DFR | MP | [13 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-19
| 164/1 | DA+9 | DFR | MP | [13 empty] | 2026-01-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2026-01-25
23 | 164/2 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Puniya Const. | Complete |  |  |  | 2025-03-31 | 4 Pit Excavation done.
5 | 164/3 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Puniya Const. | Complete |  |  |  | 2024-03-28 | 4 Pit Steel Binding Done.
6 | 164/4 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Puniya Const. | Complete | 2025-02-26 | 2025-03-06 |  | 2025-03-16
25 | 164/5 | DA+6 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-02-01 | Saktawar | Complete | 2025-02-14 | 2025-02-16 | 2025-02-24 | 2025-02-26
7 | 164/6 | DA+3 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Saktawat | Complete | 2025-02-22 | 2025-02-26 |  | 2025-03-07
17 | 164/7 | DA+3 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-08 | 4 Pit Excavation done.
17 | 164/8 | DA+3 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-15
22 | 165/0 | DB1+6 | DFR | MP | Done | CP |  | 470.72 | 21.868 | 492.588 | 58.84 | 4.97 | 298.13 | 3428 | 1.928 |  |  | 2025-10-14 | Garg Const. | Complete |  |  |  | 2025-10-22
| 165/1 | DA+6 | DFR | MP | Done | CP | Done | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | APRIL-25 | Puniya Const. | Complete |  |  |  | 2025-04-30
23 | 165/2 | DA+0 | DFR | MP | Done | CP |  | 259.216 | 11.4488 | 270.6648 | 32.402 | 2.602 | 149.96 | 2496.13 | 1.003 |  |  | 2025-11-14 | Garg Const. | Complete |  |  |  | 2025-11-07
| 165/3 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Puniya Const. | Complete |  |  |  | 2025-04-18
| 165/4 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-13
| 165/5 | DA-3 | DRY | MP | Done | Pipe Type | Done | 192.32 | 10.78 | 203.1 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-29
| 165/6 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-09
| 166/0 | DC1+0 | DFR | MP | Done | CP |  | 610.8 | 27.808 | 638.608 | 76.35 | 6.32 | 385.79 | 3898 | 2.3488 | 1761921.9257 |  | APRIL-25 | Reshmi Devi | Complete |  |  |  | 2025-04-24
15 | 166/1 | DA-3 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-09 | Garg Const. | Complete |  |  |  | 2025-05-13
14 | 166/2 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-28
13 | 166/3 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-20
11 | 166/4 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-03-01 | Garg Const. | Complete |  |  |  | 2025-03-28 | 3 Pit Steel Binding done.
12 | 166/5 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | Garg Const. | Complete |  |  |  | 2025-03-31 | EXCAVATION STARTED.
10 | 166/6 | DA-3 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Garg Const. | Complete |  |  |  | 2025-04-13 | PIT Marking Done.
14 | 166/7 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Shree Shyam | Complete |  |  |  |  | PIT Marking Done.
13 | 166/8 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | Shree Shyam | Complete |  |  |  | 2025-04-08 | 4 PIT Excavation DONE.
15 | 166/9 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | APRIL-25 | Shree Shyam | Complete |  |  |  | 2025-04-20 | PIT Marking Done.
| 167/0 | DB1+0 | DRY | MP | Done | Pipe Type | Done | 405.12 | 21.12 | 426.24 | 50.64 | 4.8 | 378.56 | 4711.55 | 1.7681 | 1326238.3039 |  | 2025-05-01 | Shree Shyam | Complete |  |  |  | 2025-05-03
| 167/1 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | Shree Shyam | Complete |  |  |  | 2025-05-09
| 167/2 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-12 | Saktawar | Complete |  |  |  | 2025-05-27
| 167/3 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-01 | Saktawar | Complete |  |  |  | 2025-05-29
| 167/4 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-26
| 167/5 | DA-3 | DFR | MP | Done | CP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | Saktawar | Complete |  |  |  | 2025-04-30
| 168/0 | DC2+0 | WFR | MP | Done | CP |  | 1044.32 | 48.18 | 1092.5 | 130.54 | 10.95 | 691.74 | 8037 | 2.349 |  |  | 2025-10-14 | Saktawar | Complete |  |  |  | 2025-10-25
| 169/0 | DC1+3 | WFR | MP | Done | CP |  | 922.96 | 41.888 | 964.848 | 115.37 | 9.52 | 596.84 | 5822 | 2.349 |  |  | 2025-11-14 | Saktawar | Complete |  |  |  | 2025-11-20
34 | 169/1 | DA-1.5 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-24 | PIT Marking Done.
19 | 169/2 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-14 | 2 PIT Excavation & Blasting WIP.
20 | 169/3 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | MANOJ KUMAR | Complete |  |  |  | 2025-04-07 | 2 PIT Excavation Done & balance 2 Pits Excavation & blasting WIP.
| 169/4 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | MANOJ KUMAR | Complete |  |  |  | 2025-05-04
| 169/5 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-01 | MANOJ KUMAR | Complete |  |  |  | 2025-05-11
| 169/6 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | MANOJ KUMAR | Complete |  |  |  | 2025-05-25
21 | 169/7 | DA-1.5 | DFR | MP |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-07-14 | Garg Const. | Complete |  |  |  | 2025-07-17
| 169/9 | DA-3 | WFR | MP | Done | CP |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  |  | 2025-12-14 | Saktawar | Complete |  |  |  | 2025-12-08
| 170/0 | DB1+0 | DFR | MP | Done | CP |  | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 |  | 2025-05-03 | SHUKLA CONST | Complete |  |  |  | 2025-05-16
44 | 170/1 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-11
43 | 170/10 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | JSR | Complete |  |  |  | 2025-04-12
25 | 170/2 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-03-01 | SHUKLA CONST | Complete |  |  |  | 2025-03-30 | PIT Marking Done.
24 | 170/3 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | SHUKLA CONST | Complete |  |  |  | 2025-03-29 | 2 Pit Excavation done & 2 Pit WIP.
37 | 170/4 | DA-3 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2024-04-04
44 | 170/5 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-22
| 170/6 | DA-3 | DRY | MP |  |  |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | SHUKLA CONST | Complete |  |  |  | 2025-04-28
28 | 170/7 | DA+0 | DRY | MP |  |  |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | JSR | Complete |  |  |  | 2025-04-17 | PIT Marking Done.
29 | 170/8 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-03-01 | JSR | Complete |  |  |  | 2025-03-31 | PIT Marking Done.
35 | 170/9 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | JSR | Complete |  |  |  | 2025-04-07
| 171/0 | DB1+0 | DFR | MP | Done | CP | Done | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 |  | 2025-06-14 | MANOJ KUMAR | Complete |  |  |  | 2025-06-08
| 171/1 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | JSR | Complete |  |  |  | 2025-04-22
| 171/10 | DA+0 | DFR | MP |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-11-14 | NEELKAMAL | Complete |  |  |  | 2015-11-27
| 171/2 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | APRIL-25 | JSR | Complete |  |  |  | 2025-04-26
| 171/3 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-06-14 | Puniya Const. | Complete |  |  |  | 2025-06-08
| 171/4 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | Puniya Const. | Complete |  |  |  | 2025-05-21
| 171/6 | DA+0 | DFR | MP |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-06-14 | NEELKAMAL | Complete |  |  |  | 2025-06-29
| 171/7 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-06-14 | NEELKAMAL | Complete |  |  |  | 2025-06-03
| 171/8 | DA-3 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-01 | NEELKAMAL | Complete |  |  |  | 2025-05-17
| 171/9 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | NEELKAMAL | Complete |  |  |  | 2025-05-04
| 172/0 | DB1+0 | DFR | MP | Done | CP | Done | 466.88 | 21.472 | 488.352 | 58.36 | 4.88 | 292.33 | 2716 | 1.768 | 1317205.2181 |  | 2025-06-14 | SRI BALAJI | Complete |  |  |  | 2025-06-09
41 | 172/1 | DA-3 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-26
42 | 172/2 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-10
| 172/3 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-04-18
| 172/4 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-05-21
| 172/5 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-05-14 | RajaRam/Sri Radhya | Complete |  |  |  | 2025-05-30
| 172/6 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | Shree Shyam | Complete |  |  |  | 2025-05-23
| 173/0 | DB2+0 | DFR | MP | Done | CP |  | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 |  | 2025-06-14 | Shree Shyam | Complete |  |  |  | 2025-06-05
| 173/1 | DA-3 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-26
| 173/2 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-20
| 173/3 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-12
| 173/4 | DA+3 | DRY | MP | Done | Pipe Type | Done | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | APRIL-25 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-04-16
19 | 174A/0 | DC1+3 | DRY | MP | Done | Pipe Type |  | 605.28 | 27.984 | 633.264 | 75.66 | 6.36 | 493.97 | 5327.42 | 2.3488 | 1817219.9087 |  | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-13
18 | 174A/1 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-04
20 | 174A/2 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-06-14 | Garg Const. | Complete |  |  |  | 2025-06-28
| 174A/3 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-04 | Surinder Singh/Aditya Const. | Complete |  |  |  | 2025-05-10
17 | 174A/4 | DA-3 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | Garg Const. | Complete |  |  |  | 2025-05-23
16 | 174A/5 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-13 | Garg Const. | Complete |  |  |  | 2025-05-29
| 174B/0 | DB2+0 | WET | MP | Done | Pipe Type | [11 empty] | 2026-01-14 | Garg Const. | Complete |  |  |  | 2026-01-22
| 175/0 | DB1+0 | WFR | MP |  |  |  | 644.24 | 32.736 | 676.976 | 80.53 | 7.44 | 459.56 | 4404 | 1.768 |  |  | 2025-12-14 | Garg Const. | Complete |  |  |  | 2025-12-30
| 175/1 | DA+0 | WET | MP |  |  |  | 315.84 | 19.624 | 335.464 | 39.48 | 4.46 | 352.81 | 2945.01 | 0.866 |  |  | 2025-12-14 | Garg Const. | Complete |  |  |  | 2025-12-15
24 | 175/2 | DA+0 | WFR | MP |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  |  | 2025-11-14 | Garg Const. | Complete |  |  |  | 2025-11-26
| 175/3 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-26
| 175/4 | DA-3 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-24
| 176/0 | DC1+3 | DFR | MP | Done | CP | Done | 614.16 | 27.984 | 642.144 | 76.77 | 6.36 | 388.74 | 3855 | 2.3488 | 1765261 |  | 2025-05-01 | SRI BALAJI | Complete |  |  |  | 2025-05-04
| 176/1 | DA+3 | DFR | MP | Done | CP | Done | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | APRIL-25 | SRI BALAJI | Complete |  |  |  | 2025-04-30
| 176/2 | DA+3 | DFR | MP | Done | CP | Done | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-05-03 | SRI BALAJI | Complete |  |  |  | 2025-05-06
| 176/3 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-04 | SRI BALAJI | Complete |  |  |  | 2025-05-10
| 177/0 | DB2+0 | DFR | MP | Done | CP | Done | 562 | 26 | 588 | 70.22 | 5.81 | 352.73 | 3400 | 1.7681 | 1595805.5121 |  | 2025-05-10 | SRI BALAJI | Complete |  |  |  | 2026-05-15
| 177/1 | DA+3 | DFR | MP | Done | CP | Done | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-17
| 177/2 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-21
| 177/3 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-23
| 177/4 | DA+3 | DRY | MP | Done | Pipe Type |  | 214 | 12 | 226 | 26.74 | 2.68 | 219.54 | 2473.94 | 0.86628 | 705045.3467 |  | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-27
| 177/5 | DA-3 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-12 | SRI BALAJI | Complete |  |  |  | 2025-05-29
| 177/6 | DA-3 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-14 | SRI BALAJI | Complete |  |  |  | 2025-05-31
| 177/7 | DA+0 | DRY | MP | Done | Pipe Type | Done | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-06-14 | SRI BALAJI | Complete |  |  |  | 2025-06-03
| 177/8 | DA+0 | DRY | MP | Done | Pipe Type |  | 193 | 11 | 204 | 24.04 | 2.45 | 194.78 | 1979.14 | 0.86628 | 608271.6679 |  | 2025-05-12 | Reshmi Devi | Complete | 2025-05-25 |  |  | 2025-05-25
| 178/0 | DB2+0 | DRY | MP | Done | Pipe Type | Done | 565 | 26 | 591 | 70.56 | 5.83 | 454.86 | 5149 | 1.7681 | 1662016.3703 |  | 2025-05-11 | Reshmi Devi | Complete |  |  |  | 2025-05-18
| 178/1 | DA+0 | DFR | MP | Done | CP | Done | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-05-03 | Reshmi Devi | Complete |  |  |  | 2025-05-08
| 178/2 | DA+6 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 |  |  | 2025-10-14 | Reshmi Devi | Complete |  |  |  | 2025-10-16
| 178/3 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-05-13 | Reshmi Devi | Complete |  |  |  | 2025-05-30
| 178/4 | DA-3 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-04
| 178/5 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-12
| 179/1 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-23
| 179/2 | DA+3 | DFR | MP | Done | CP |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 | 752440.0941 |  | 2025-09-14 | Reshmi Devi | Complete |  |  |  | 2025-09-29
| 179/4 | DA-3 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-09-14 | Infinity Const | Complete |  |  |  | 2025-09-26
| 179/5 | DA+0 | DFR | MP |  |  |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.866 |  |  | 2025-12-14 | Madhusudanam Enterprises. | Complete |  |  |  | 2025-12-10
| 179/6 | DA+0 | DFR | MP | Done | CP |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-09-14 | Infinity Const | Complete |  |  |  | 2025-09-12
| 179/7 | DA+0 | DFR | MP |  |  |  | 221 | 12 | 233 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 | 650458.1121 |  | 2025-08-14 | Infinity Const | Complete |  |  |  | 2025-08-29
| 179/9 | DA+3 | DFR | MP |  |  |  | 0 | 0 | 0 | [7 empty] | 2026-01-14 | Infinity Const | Complete |  |  |  | 2026-01-11
| 180/0 | DC2+15 | DRY | MP | Done | Pipe Type |  | 642.72 | 32.736 | 675.456 | 80.34 | 7.44 | 573.44 | 7856 | 2.235 |  |  | 2025-10-14 | Reshmi Devi | Complete |  |  |  | 2025-10-30
| 181/0 | DD60+9 | DFR | MP | Done | CP |  | 1008.24 | 49.764 | 1058.004 | 126.03 | 11.31 | 716 | 11510 | 3.159 |  |  | 2025-12-14 | Reshmi Devi | Complete |  |  |  | 2025-12-24
| 181/1 | DA+0 | DFR | MP | Done | CP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 |  |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-18
| 181/2 | DA-3 |  |  |  | CP |  | 0 | 0 | 0 | [7 empty] | 2025-11-14
| 181/4 | DA-3 | DFR | MP | Done | CP |  | 220.88 | 11.484 | 232.364 | 27.61 | 2.61 | 146.96 | 1450 | 0.86628 |  |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-27
| 181/5 | DA-3 | WFR | MP | Done | CP |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.866 |  |  | 2025-12-14 | Reshmi Devi | Complete |  |  |  | 2025-12-06
| 181/6 | DA+0 | DFR | MP | Done | CP |  | 233.656 | 11.4708 | 245.1268 | 29.207 | 2.607 | 146.96 | 1798 | 0.912 |  |  | 2025-11-14 | Reshmi Devi | Complete |  |  |  | 2025-11-10
| 182/0 | DD60+6 | DFR | MP | [13 empty] | 2026-01-01 | Reshmi Devi | Complete |  |  |  | 2026-01-25
| 99/1 | DA+6 | DFR | RAJ |  |  |  | 251.2 | 12.716 | 263.916 | 31.4 | 2.89 | 164.7 | 1802 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-11
| 99/2 | DA+6 | WET | RAJ |  |  |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-09
| 99/3 | DA+0 | WFR | RAJ |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-06
| 99/4 | DA+0 | WET | RAJ |  |  |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-01
| 99/5 | DA+0 | WET | RAJ |  |  |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-03
| 99/6 | DA+0 | WFR | RAJ |  |  |  | 332.32 | 18.612 | 350.932 | 41.54 | 4.23 | 250.46 | 1909 | 0.86628 |  |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-25
| 99/7 | DA+0 | WET | RAJ |  |  |  | 382.96 | 22.616 | 405.576 | 47.87 | 5.14 | 403.72 | 2476 | 0.86628 |  |  | 2025-11-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-11-16
| 99/8 | DA+6 | WET | RAJ |  |  |  | 418.88 | 23.892 | 442.772 | 52.36 | 5.43 | 425.04 | 2850 | 0.86628 |  |  | 2025-10-14 | Sumit Const/Om Prakash | Complete |  |  |  | 2025-10-17
| 146/0 | DD60+18 |  | RAJ | [13 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-19
| 148C/0 | DB1+9 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-21
| 142/1 | DA-3 |  | RAJ-Forest | [13 empty] | 2026-02-14 | RST | Complete |  |  |  | 2026-02-24

## Sheet4 (hidden)
V I S U A L C H A R T
| DATE : |  | 2025-11-20
| Name of Line : |  |  | 765 KV D/C HEXA BEAWAR MANDSAUR T/L
| Project Code: |  |  |  | TA505
| Name of Executing Agency: |  |  |  | M/s. KEC INTERNATIONAL LTD.
[31 empty] | FDN | Ear | ERE | STR
COMMON TOWER
[21 empty] | 99/0 |  | 99/1 |  | 99/2 |  | 99/3 |  | 99/4 |  | 4 | 0 | 0
[25 empty] | 1 |  | 1
[21 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 1
[18 empty] | BAJEL PART |  | 0 | BAJEL | 360 |  | 420 |  | 410 |  | 382
[21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
[21 empty] | DB2+0 |  | DA+6 |  | DA+6 |  | DA+0 |  | DA+0
RAJASTHAN REGION
[14 empty] | D |  | D |  |  |  | D |  | D |  | D |  | D |  | D |  | D
|  | 99/5 |  | 99/6 |  | 99/7 |  | 99/8 |  | 100/0 |  | 101/0 |  | 101/1 |  | 101/2 |  | 101/3 |  | 101/4 |  | 101/5 |  | 101/6 |  | 101/7 |  | 101/8 |  | 102/0
[6 empty] | 1 |  | 1 | [5 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1
|  | 1 |  | 2 |  | 3 |  | 4 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
| 338 |  | 370 |  | 380 |  | 400 |  | 418 |  | 418.579 |  | 425 | Completed | 312 | Completed | 381 | Completed | 455 | Completed | 376 | Completed | 401 | Completed | 428 | Completed | 357 | Completed | 335.158 | Completed | 15 | 5 | 10
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD45+0 |  | DC1+3 |  | DA+3 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA-3 |  | DC2+3
[14 empty] | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  | DRY |  | DRY
RAJASTHAN REGION
RC
|  | 103/0 |  | 103/1 |  | 103/2 |  | 103/3 |  | 103/4 |  | 103/5 |  | 103/5A |  | 103/5A1 |  | 103/6A |  | 103/7 |  | 103/8 |  | 103/9 |  | 104/0 |  | 104/1 |  | 104/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  |  |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25
| 461.164 |  | 373 |  | 334.67 |  | 321.15 |  | 391 |  | 388 |  | 392 |  | 293 |  | 274 |  | 218 | Completed | 422 |  | 339 |  | 423.633 | Completed | 335.192 | Completed | 326.577 | Completed | 15 | 3 | 13
|  |  |  | 0 |  | 0 |  |  |  | 0 |  | X | [7 empty] | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | Completed
|  | DC1+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DD60+0 |  | DA-3 |  | DD45+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DD45+3 |  | DA-3 |  | DA-3
[12 empty] | Benching | [5 empty] | Benching |  | DFR | [5 empty] | DFR |  | DFR |  | WET
RAJASTHAN REGION
|  | HR |  |  |  |  | GAS PIPE LINE
|  | 105/0 |  | 105/1 |  | 106/0 |  | 108/0 |  | 108/1 |  | 108/2 |  | 108/3 |  | 108/4 |  | 109/0 |  | 109/1 |  | 109/2 |  | 109/3 |  | 109/4 |  | 110/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1 |  | 1 |  | 0 |  | 0 |  | 0
25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39
| 304.947 | Completed | 379.11 | Completed | 375.442 |  | 212.418 |  | 326.001 | Completed | 332 | Completed | 285 | Completed | 345 | Completed | 380.282 | Completed | 384.998 | Completed | 360 | Completed | 378 | Completed | 387 | Completed | 439.322 | Completed |  |  | 14 | 11 | 13
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DC1+0 |  | DA+0 |  | DD60+0 |  | DD45+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DC1+0 |  | DA-1.5 |  | DA-1.5 |  | DA+0 |  | DA+3 |  | DC2+3
|  | WFR |  | WFR | [5 empty] | DFR |  | WET |  | WET |  | WFR |  | DFR |  | WFR |  | WFR |  | WFR |  | WFR |  | WFR
RAJASTHAN REGION
|  | 110/1 |  | 110/2 |  | 110/3 |  | 110/4 |  | 110/5 |  | 110/6 |  | 110/7 |  | 110/8 |  | 110A/0 |  | 110A/1 |  | 110A/2 |  | 111/0 |  | 111/1 |  | 111/2
|  | Jwala Singh |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53
| 386.733 | Completed | 358.962 | Completed | 399.964 | Completed | 375.845 |  | 417.796 | Completed | 403.677 | Completed | 414.519 | Completed | 415.771 | Completed | 339.11 | Completed | 398.31 | Completed | 390.626 | Completed | 441.234 | Completed | 415.0029 | Completed | 416.9999 | Completed |  |  | 14 | 11 | 14
|  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA-1.5 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA-1.5 |  | DB1+6 |  | DA+3 |  | DA+3
|  | WFR |  | WFR |  | DRY |  |  |  | WET |  | WFR |  | WFR |  | WFR |  | DFR |  | WFR |  | DFR |  | DFR |  | WFR |  | WFR
Benching
RAJASTHAN REGION
[7 empty] | 400 kV | RC
|  | 111/3 |  | 111/4 |  | 112/0 |  | 113/0 |  | 113/1 |  | 113/2 |  | 113/3 |  | 113/4 |  | 113/5 |  | 113/6 |  | 114/0 |  | 114/1 |  | 114/2 |  | 114/3
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
53 |  | 54 |  | 55 |  | 56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67
| 405.0008 | Completed | 333 | Completed | 383.6369 | Completed | 225.782 |  | 390 | Completed | 343 | Completed | 327 | Completed | 364 | Completed | 308 | Completed | 465 | Completed | 367.662 | Completed | 399.998 | Completed | 426 | Completed | 362 | Completed |  |  | 13 | 13 | 13
|  | Completed |  | Completed |  | Completed |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+9 |  | DD60+18 |  | DD60+9 |  | DA-3 |  | DA-1.5 |  | DA-3 |  | DA+0 |  | DA+6 |  | DA+6 |  | DC2+0 |  | DA+3 |  | DA+0 |  | DA+0
|  | WET |  | DFR |  | DFR |  |  |  | DFR |  | WFR |  | DFR |  | DFR |  | DFR |  | DFR |  | WET |  | DFR |  | WFR |  | WFR
RAJASTHAN REGION
[17 empty] | 132 kV | [7 empty] | 220kV
|  | 114/4 |  | 114/5 |  | 114/6 |  | 114/7 |  | 114/8 |  | 114/9 |  | 114/10 |  | 115/0 |  | 116/0 |  | 116/1 |  | 116/2 |  | 117/0 |  | 118/0 |  | 119/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
67 |  | 68 |  | 69 |  | 70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81
| 382 |  | 441 | Completed | 309 | Completed | 331 | Completed | 431 | Completed | 396 | Completed | 444 | Completed | 381.622 |  | 200.194 |  | 323.899 | Completed | 403 | Completed | 419.713 | ROW | 239.882 | Completed | 421.011 |  |  |  | 13 | 8 | 11
|  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed | [5 empty] | Completed |  | Completed |  | 0 |  | 0
|  | DA+3 |  | DA+6 |  | DA-3 |  | DA+3 |  | DA+6 |  | DA+3 |  | DA+6 |  | DD60+3 |  | DD45+3 |  | DA+3 |  | DA+3 |  | DD45+6 |  | DD60+6 |  | DC2+0
|  |  |  | DFR |  | DFR |  | DFR |  | WET |  | WET |  | DFR | [5 empty] | WFR |  | WFR |  |  |  | WFR
Benching
RAJASTHAN REGION
| 220kV | [11 empty] | RLW | [9 empty] | NH
|  | 120/0 |  | 120/1 |  | 120/2 |  | 120/3 |  | 121/0 |  | 122/0 |  | 123/0 |  | 123/1 |  | 123/2 |  | 123/3 |  | 124/0 |  | 125/0 |  | 125/1 |  | 126/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
81 |  | 82 |  | 83 |  | 84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95
| 193.168 |  | 416.997 | Completed | 363 | Completed | 339 | Completed | 473.767 |  | 360.17 |  | 272 | WIP | 301.25 |  | 349 |  | 299 | Hold | 318 | Hold | 244 | Hold | 343 | Hold | 399 | Completed |  |  | 6 | 4 | 6
|  | 0 |  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed
|  | DD45+3 |  | DA+0 |  | DA-1.5 |  | DA+9 |  | DB1+6 |  | DD60+3 |  | DD60+6 |  | DA+0 |  | DA+0 |  | DA-3 |  | DD45+3 |  | DD60+3 |  | DA+0 |  | DB2+0
|  |  |  | WFR |  | WFR |  | WFR | [19 empty] | DFR
RAJASTHAN REGION
RAJ FOREST
|  | RC |  |  |  |  | Proposed 132kV | [12 empty] | RC |  | ULE/RC
|  | 126/1 |  | 126/2 |  | 126/3 |  | 126/4 |  | 127/0 |  | 127/1 |  | 127/2 |  | 127/3 |  | 128/0 |  | 129/0 |  | 129/1 |  | 129A/0 |  | 129A/1 |  | 129A/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
95 |  | 96 |  | 97 |  | 98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109
| 412 |  | 420 | Completed | 339 | Completed | 461 | Completed | 324.66 | Completed | 342 | Completed | 392 | Completed | 371 | Completed | 335.587 | Completed | 421.973 | Hold | 330 | Hold | 474.912 | Hold | 321 | Completed | 400.55 | Completed |  |  | 11 | 6 | 10
|  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+9 |  | DA-3 |  | DA+3 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DC2+9 |  | DB1+3 |  | DB1+9 |  | DD45+0 |  | DA+0 |  | DA+0
|  | Benching |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | Benching |  | Benching |  |  |  | DFR |  | DFR
Benching
RAJASTHAN REGION
[14 empty] | RAJ FOREST | [12 empty] | Temple
[14 empty] | ULE/RC |  | RC
|  | 129A/3 |  | 130/0 |  | 130/1 |  | 130/2 |  | 131/0 |  | 132/0 |  | 133/0 |  | 134/0 |  | 135/0 |  | 135/1 |  | 135/2 |  | 135/3 |  | 136/0 |  | 136/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
109 |  | 110 |  | 111 |  | 112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123
| 342 | Completed | 280 | Completed | 387.996 | Completed | 319 | Completed | 429.453 | Completed | 484.387 |  | 372.194 | Hold | 552.223 | Hold | 396.823 | Completed | 357.996 | Completed | 401 | Completed | 395.009 | Completed | 445.379 |  | 396.995 | Completed |  |  | 12 | 2 | 9
|  | 0 |  | Completed |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DB2+0 |  | DA+0 |  | DA-1.5 |  | DD45+9 |  | DD60+6 |  | DB2+3 |  | DC1+0 |  | DD45+0 |  | DA+3 |  | DA+9 |  | DA+9 |  | DC2+3 |  | DA+3
|  | WFR |  | WFR |  | WFR |  | WFR |  | WFR |  |  |  | Benching |  | Benching |  | DFR |  | DFR |  | DFR |  | DFR |  |  |  | DFR
Benching
RAJASTHAN REGION
RAJ FOREST
[6 empty] | TP Tower |  |  |  | RC |  | RC |  | ULE/RC |  |  |  | RC |  | RC
|  | 136/2 |  | 136/3 |  | 136/4 |  | 136/5 |  | 137/0 |  | 137A/0 |  | 138/0 |  | 138/1 |  | 138/2 |  | 138/3 |  | 139/0 |  | 139/1 |  | 140/0 |  | 140/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
123 |  | RoW |  | 125 |  | 126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137
| 374.005 |  | 433 | ROW | 390 | ROW | 406.995 | Completed | 411.482 | ROW | 566.681 |  | 326.632 | WIP | 371.997 | Hold | 441 | Hold | 445 | Hold | 332.731 | Hold | 241.999 | Hold | 473.131 |  | 439.999 | Completed |  |  | 4 | 0 | 1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DD60+9 |  | DC2+25 |  | DB1+3 |  | DA-3 |  | DB1+9 |  | DA+3 |  | DB2+0 |  | DB1+3 |  | DC1+9 |  | DA+3
[8 empty] | DFR |  |  |  | Benching |  | Benching | [5 empty] | Benching | [5 empty] | DFR |  | DFR
RAJASTHAN REGION
[6 empty] | RAJ FOREST | [15 empty] | RAJ FOREST
|  |  | 132 kV |  |  | RC |  | ULE/RC |  | ULE | [10 empty] | 400 kV | RC
|  | 141/0 |  | 142/0 |  | 142/1 |  | 143/0 |  | 144/0 |  | 144A/0 |  | 144A/1 |  | 144A/2 |  | 144A/3 |  | 145/0 |  | 146/0 |  | 146/1 |  | 147/0 |  | 147/1
| ` | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
137 |  | 138 |  | 139 |  | 140 |  | 141 |  | 142 |  | 143 |  | 144 |  | RoW |  | 146 |  | 147 |  | 148 |  | 149 |  | RoW |  | 151
| 398.255 |  | 211.135 |  | 224 | Hold | 293.493 | Hold | 332.856 | Hold | 412.345 |  | 429.003 | Completed | 389 |  | 418 | Completed | 365.834 |  | 236.061 | Hold | 424.998 | Hold | 413.45 |  | 458 | Completed |  |  | 9 | 1 | 4
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DD45+0 |  | DD45+3 |  | DA-3 |  | DD45+0 |  | DC1+0 |  | DD45+6 |  | DA+0 |  | DA+3 |  | DB1+3 |  | DD60+18 |  | DD60+18 |  | DA+9 |  | DB2+6 |  | DA+9
[6 empty] | Benching |  | Benching |  | Benching |  | WET |  | WFR |  |  |  | WET |  |  |  | Benching | [5 empty] | WET
RAJASTHAN REGION
[22 empty] | RAJ FOREST |  |  |  |  | MP FOREST
[20 empty] | ULE/RC |  | RC |  |  |  | ULE/RC
|  | 147A/0 |  | 147A/1 |  | 147A/2 |  | 147A/3 |  | 147A/4 |  | 147A/5 |  | 148/0 |  | 148/1 |  | 148A/0 |  | 148B/0 |  | 148B/1 |  | 148B/2 |  | 148C/0 |  | 149/0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
151 |  | 152 |  | 153 |  | 154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165
| 378.052 |  | 319 | Completed | 365 | Completed | 441 |  | 394 | Completed | 314 | Completed | 473.22 | Completed | 337 |  | 337.574 | Completed | 402.808 | WIP | 344 | Hold | 383 | Hold | 376.826 | Hold | 481.108 | Hold |  |  | 9 | 1 | 8
|  | 0 |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DB1+0 |  | DA-1.5 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+9 |  | DD60+6 |  | DA+0 |  | DB1+6 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DB1+9 |  | DD45+9
|  |  |  | DFR |  | WFR |  |  |  | DFR |  | WFR |  | WFR |  |  |  | WET |  | Benching |  | Benching |  |  |  | Benching
| RAJASTHAN REGION | [25 empty] | MP REGION
| MP FOREST | [10 empty] | RC |  | RC |  | RC
|  | 149/1 |  | 149/2 |  | 149A/0 |  | 149B/0 |  | 149B/1 |  | 149B/2 |  | 149B/3 |  | 149B/4 |  | 150/0 |  | 150/1 |  | 150/2 |  | 150/3 |  | 150/4 |  | 150/5
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
165 |  | 166 |  | 167 |  | 168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179
| 317 | Hold | 341 | Hold | 329.47 | Hold | 523.193 | WIP | 328 |  | 389 |  | 396 |  | 350 |  | 397.48 |  | 323.998 | Completed | 426 | Completed | 374 | Completed | 461 | Completed | 372 | Completed |  |  | 10 | 0 | 7
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+9 |  | DC2+18 |  | DB1+25 |  | DB2+15 |  | DA+6 |  | DA+3 |  | DA+0 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+6
[12 empty] | Benching |  | Benching |  | Benching |  |  |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR
| MP REGION | [5 empty] | RAJASTHAN REGION
132 kV
|  | 151/0 |  | 152/0 |  | 152/1 |  | 152/2 |  | 152/3 |  | 152A/0 |  | 152A/1 |  | 152A/2 |  | 152A/3 |  | 152A/4 |  | 152A/5 |  | 152A/6 |  | 152A/7 |  | 152A/8
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
179 |  | 180 |  | 181 |  | RoW |  | RoW |  | RoW |  | RoW |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193
| 440.645 |  | 220.202 |  | 386.001 | Completed | 425 | Completed | 380 | Completed | 354.388 | Completed | 357.996 | Completed | 300 | Completed | 407 | Completed | 373 | Completed | 414 | Completed | 357 | Completed | 423 | Completed | 381 | Completed |  |  | 14 | 12 | 6
|  | 0 |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DD45+3 |  | DD60+6 |  | DA+6 |  | DA+0 |  | DA-1.5 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6
[6 empty] | DFR |  | DRY |  | DRY |  | DRY |  | DRY |  | DFR |  | DFR |  | DFR |  | DRY |  | DFR |  | DFR |  | WET
RAJASTHAN REGION
220 kV
|  | 152A/9 |  | 152A/10 |  | 152A/11 |  | 152A/12 |  | 153/0 |  | 154/0 |  | 154/1 |  | 154/2 |  | 154/3 |  | 154/4 |  | 154/5 |  | 155/0 |  | 155/1 |  | 155/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
193 |  | 194 |  | RoW |  | RoW |  | RoW |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | RoW |  | RoW |  | RoW
| 456 | Completed | 381 | Completed | 382 | Completed | 341 |  | 352.374 | WIP | 226.42 | WIP | 352 | Completed | 332 | Completed | 255 | Completed | 377 |  | 325 | Completed | 368.885 |  | 351.004 | Completed | 409 | Completed |  |  | 12 | 4 | 5
|  | 0 |  | Completed |  | Completed |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | Completed |  | Completed
|  | DA+6 |  | DA+0 |  | DA-1.5 |  | DA-3 |  | DB1+6 |  | DB2+9 |  | DA-1.5 |  | DA-3 |  | DA-3 |  | DA+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+3
|  | DRY |  | DRY |  | DFR | [7 empty] | DFR |  | DFR |  | DFR |  |  |  | DRY |  |  |  | DRY |  | DRY
RAJASTHAN REGION
[20 empty] | RAJ FOREST |  |  |  | MP FOREST
|  | 155/3 |  | 155/4 |  | 155/5 |  | 156/0 |  | 156/1 |  | 156/2 |  | 156/3 |  | 156/4 |  | 156/5 |  | 156/6 |  | 157/0 |  | 158/0 |  | 158/1 |  | 158/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
207 |  | 208 |  | 209 |  | 210 |  | 211 |  | 212 |  | 213 |  | RoW |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221
| 405 | Completed | 376 | Completed | 439 | Completed | 326.845 |  | 382.999 | Completed | 416 | WIP | 410 | Completed | 336 | Completed | 353 |  | 372 | Hold | 396.128 | HOLD | 360.998 | Hold | 466 | Hold | 366 |  |  |  | 8 | 4 | 7
|  | Completed |  | Completed |  | Completed |  | 0 |  |  |  | 0 |  | Completed |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+9 |  | DC2+18 |  | DA+6 |  | DA+0
|  | DFR |  | DFR |  | DFR |  | 0 |  | DFR |  |  |  | DFR |  | DFR | [5 empty] | RC
| RAJASTHAN REGION | [22 empty] | MP REGION
|  | 158/3 |  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 160/0 |  | 160/1 |  | 160/2 |  | 160/3 |  | 160/4 |  | 160/5 |  | 161/0 |  | 161/1 |  | 161/2
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
221 |  | 222 |  | 223 |  | 224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235
| 375 |  | 374.761 | Completed | 390.999 |  | 397 |  | 336 | Completed | 383.419 | Completed | 323.001 | Completed | 335 | Completed | 337 | Completed | 339 |  | 351 |  | 377.051 |  | 413.999 |  | 418.004 | Completed |  |  | 14 | 3 | 12
|  |  |  | Completed | [5 empty] | Completed | [7 empty] | Completed
|  | DA-1.5 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-1.5 |  | DA-1.5 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB2+3 |  | DA+3 |  | DA+3
|  |  |  | DRY | [5 empty] | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | DRY |  | 0 | [5 empty] | DRY
MP REGION
132 KV
|  | 161/3 |  | 161/4 |  | 161/5 |  | 162/0 |  | 162/1 |  | 162/2 |  | 163/0 |  | 164/0 |  | 164/1 |  | 164/2 |  | 164/3 |  | 164/4 |  | 164/5 |  | 164/6
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
235 |  | 236 |  | 237 |  | 238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249
| 417 |  | 383 | Completed | 426 |  | 410.673 | ROW | 385.997 | ROW | 305 | ROW | 423 | ROW | 302.489 | ROW | 361 | ROW | 370.997 |  | 402.003 |  | 398 |  | 420 | Completed | 400 |  |  |  | 8 | 1 | 2
|  |  |  | Completed |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA+0 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DB1+18 |  | DC2+18 |  | DA+9 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3
|  |  |  | DRY |  | 0 |  | 0 | [13 empty] | 0 |  | 0 |  | DRY |  | DRY
MP REGION
[6 empty] | RC |  |  |  | RC
|  | 164/7 |  | 164/8 |  | 165/0 |  | 165/1 |  | 165/2 |  | 165/3 |  | 165/4 |  | 165/5 |  | 165/6 |  | 166/0 |  | 166/1 |  | 166/2 |  | 166/3 |  | 166/4
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
249 |  | 250 |  | 251 |  | 252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263
| 419.997 |  | 417.003 |  | 422.12 |  | 277.7 |  | 384.58 |  | 413.93 |  | 387.12 |  | 341.06 |  | 320.95 |  | 330.56 |  | 314 |  | 341.999 |  | 374.001 |  | 344 |  |  |  | 14 | 0 | 3
[6 empty] | 0 |  |  |  | 0
|  | DA+3 |  | DA+6 |  | DB1+6 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DC1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3
|  | 0 |  |  |  | Benching |  |  |  | Benching
MP REGION
132 kV
|  | 166/5 |  | 166/6 |  | 166/7 |  | 166/8 |  | 166/9 |  | 167/0 |  | 167/1 |  | 167/2 |  | 167/3 |  | 167/4 |  | 167/5 |  | 168/0 |  | 169/0 |  | 169/1
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
263 |  | 264 |  | 265 |  | 266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277
| 394 |  | 355 |  | 349 |  | 367 |  | 390 |  | 388.874 |  | 359.996 |  | 372 |  | 388 |  | 378 |  | 284 |  | 304.535 |  | 212.961 |  | 368.004 |  |  |  | 14 | 0 | 9
[24 empty] | 0 |  | 0
|  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC2+0 |  | DC1+3 |  | DA-1.5
|  |  |  | 0 |  | 0 |  | 0 |  | 0
ss
MP REGION
|  | 169/2 |  | 169/3 |  | 169/4 |  | 169/5 |  | 169/6 |  | 169/7 |  | 169/8 |  | 169/9 |  | 170/0 |  | 170/1 |  | 170/2 |  | 170/3 |  | 170/4 |  | 170/5
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
277 |  | 278 |  | 279 |  | 280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 |  | 290 |  | 291
| 378 |  | 386 |  | 377 |  | 343 |  | 384 |  | 351 |  | 348 | ROW | 327 | WIP | 326.874 |  | 380.002 |  | 383 |  | 370 |  | 355 |  | 350 |  |  |  | 12 | 0 | 6
[12 empty] | 0 |  | 0 |  | 0
|  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-1.5 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0
MP REGION
|  | 170/6 |  | 170/7 |  | 170/8 |  | 170/9 |  | 170/10 |  | 171/0 |  | 171/1 |  | 171/2 |  | 171/3 |  | 171/4 |  | 171/5 |  | 171/6 |  | 171/7 |  | 171/8
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
291 |  | 292 |  | 293 |  | 294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305
| 352 |  | 352 |  | 344 |  | 377 |  | 353 |  | 395.454 |  | 344.996 |  | 364 |  | 366 |  | 367 |  | 364 | 0 | 353 |  | 366 |  | 344 |  |  |  | 13 | 0 | 2 |  | 1
|  | 0 |  | 0 | [17 empty] | 0 |  | 0
|  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3
MP REGION
|  | 171/9 |  | 171/10 |  | 172/0 |  | 172/1 |  | 172/2 |  | 172/3 |  | 172/4 |  | 172/5 |  | 172/6 |  | 173/0 |  | 173/1 |  | 173/2 |  | 173/3 |  | 173/4
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
305 |  | 306 |  | 307 |  | 308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319
| 356 |  | 375 | WIP | 376.62 |  | 353 |  | 352 |  | 349 |  | 356 |  | 345 |  | 400 |  | 319.379 |  | 343.76 |  | 322.5 |  | 453.99 |  | 359.96 |  |  |  | 13 | 0 | 1
0
|  | DA+0 |  | DA+0 |  | DB1+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA-3 |  | DA+3 |  | DA+3 |  | DA+3
MP REGION
|  | 174A/0 |  | 174A/1 |  | 174A/2 |  | 174A/3 |  | 174A/4 |  | 174A/5 |  | 174B/0 |  | 175/0 |  | 175/1 |  | 175/2 |  | 175/3 |  | 175/4 |  | 176/0 |  | 176/1
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
319 |  | 320 |  | 321 |  | 322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333
| 447.53 |  | 399 |  | 353 |  | 355 |  | 331 |  | 335 |  | 336 | HOLD | 244 | HOLD | 354 |  | 341 | WIP | 323 |  | 333 |  | 323.564 |  | 414.996 |  |  |  | 10 | 0 | 0
|  | 0 | [11 empty] | 0 |  | 0 |  | 0 |  | 0
|  | DC1+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA-3 |  | DB2+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DC1+3 |  | DA+3
MP REGION
RC
|  | 176/2 |  | 176/3 |  | 177/0 |  | 177/1 |  | 177/2 |  | 177/3 |  | 177/4 |  | 177/5 |  | 177/6 |  | 177/7 |  | 177/8 |  | 178/0 |  | 178/1 |  | 178/2
|  | #N/A | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
333 |  | 334 |  | 335 |  | 336 |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347
| 423.004 |  | 345 |  | 381.403 |  | 396.002 |  | 371 |  | 329 |  | 366 |  | 340 |  | 347 |  | 352 |  | 381 |  | 389.734 |  | 374.998 |  | 365.998 |  |  |  | 14 | 0 | 0
0
|  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DB2+0 |  | DA+0 |  | DA+6
Benching
MP REGION
|  | 178/3 |  | 178/4 |  | 178/5 |  | 179/0 |  | 179/1 |  | 179/2 |  | 179/3 |  | 179/4 |  | 179/5 |  | 179/6 |  | 179/7 |  | 179/8 |  | 179/9 |  | 180/0
|  | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 | #N/A | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | #N/A |  | #N/A |  | #N/A
347 |  | 348 |  | 349 |  | 350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361
| 464 |  | 352.004 |  | 330 |  | 378.94 | ROW | 365 |  | 406 |  | 408.999 | ROW | 383.001 |  | 311 | ROW | 360 |  | 378 |  | 339 | ROW | 329 | WIP | 340.121 |  |  |  | 9 | 0 | 0
|  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | DA+3 |  | DA-3 |  | DA+0 |  | DC2+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+15
MP REGION
| 132 KV | [14 empty] | RC
|  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3 |  | 181/4 |  | 181/5 |  | 181/6 |  | 182/0 |  | 182B/0(DE)
|  | 0 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | #N/A |  | #N/A
361 |  | 362 |  | 363 |  | 364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  |  |  | 372
| 209.655 | ROW | 363 |  | 346 | ROW - 1 PIT | 307 | ROW | 301 | WIP | 320 | ROW | 325 |  | 320 |  | 300 |  | 94 | Gantry | [10 empty] | 2 | 0 | 0
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
|  | DD60+9 |  | DA+0 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA-3 |  | DA+0 |  | DD60+6 |  | DD60+0 |  | MANDSAUR
MP REGION
[16 empty] | Benching |  | AUX X-ARM
[28 empty] | TOTAL |  |  | 306 |  | 172 | 0
| LEGEND: | [16 empty] | PROGRESS AT A GLANCE :
[6 empty] | Stringing WIP |  | STRINGING COMPLETED |  |  |  | Front Clear For Stringing |  | Check Survey COMP. |  |  |  | SR. NO. |  | ACTIVITY |  |  | UNIT | TOTAL |  | COMPLETED |  | BALANCE |  |  | `
|  |  |  | EREC. COMP. | [8 empty] | EREC. U/P
|  |  |  | FDN. COMP. |  |  |  | SPAN |  | SPAN |  |  | FDN. U/P |  |  |  |  | 1 |  | Foundation |  |  | Nos. | 379 |  | 306 |  | 73
|  |  |  | EAR.COMP. | [9 empty] | Material Feeding U/P
[18 empty] | 2 |  | Erection |  |  | Nos. | 379 |  | 172 |  | 207
[18 empty] | 3 |  | Stringing (Final Sag) |  |  | Km. | 139.6 |  | 0 |  | 139.6
[18 empty] | 4 |  | Earthing |  |  | Nos. | 379 |  | 218 |  | 161
| NH/SH Xing |  | RAILWAY Xing |  |  | 11/33 KV X-ING | [5 empty] | RIVER X-ING |  |  | Metal Road
[9 empty] | 66/132/ 220/400KV CROSSING | [8 empty] | 5 |  | Benching |  |  | Nos. |  |  |  |  | 0
[20 empty] | Revetment |  |  | Nos. |  |  |  |  | 0

## Sheet3 (hidden)
SL | Loc No | TOT | SL | Loc No | TOT | SL | Loc No | TOT
1 | 103/5 | DA+0 | 1 | 126/1 | DA+9 (RC) | 1 | 178/2 | DA+6
2 | 99/4 | DA+0 | 2 | 149B/1 | DB2+15 | 2 | 165/0 | DB1+6
3 | 99/5 | DA+0 | 3 | 149B/2 | DA+6 | 3 | 168/0 | DC2+0
4 | 99/3 | DA+0 | 4 | 100/0 | DD45+0 | 4 | 180/0 | DC2+15
5 | 99/2 | DA+6 | 5 | 155/0 | DC2+0 | 5 | 178/4 | DA-3
6 | 99/1 | DA+6 | 6 | 99/8 | DA+6 | 6 | 178/5 | DA+0
7 | 99/7 | DA+0 | 7 | 149B/4 | DA+0 (RC) | 7 | 179/1 | DA+3
8 | 103/9 | DA+3 | 8 | 99/6 | DA+0 | 8 | 179/6 | DA+0
9 | 169/0 | DC1+3 |  |  |  | 9 | 145/0 | DD60+18
10 | 169/9 | DA-3 |  |  |  | 10 | 114/4 | DA+3
11 | 175/2 | DA+0 |  |  |  | 11 | 179/4 | DA-3
12 | 138/0 | DB1+3 |  |  |  | 12 | 149B/3 | DA+3 (RC)
13 | 149B/0 | DB1+25 |  |  |  | 13 | 179/2 | DA+3
14 | 122/0 | DD60+3 |  |  |  | 14 | 154/4 | DA+3
15 | 123/0 | DD60+6
16 | 181/2 | DA-3
17 | 179/9 | DA+3
18 | 181/5 | DA-3
19 | 181/4 | DA-3
20 | 153/0 | DB1+6
21 | 154/0 | DB2+9
22 | 156/2 | DA+3