## ProdDailyExpanded
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-23 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-24 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-28 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-31 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-07 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-08 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-09 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-09 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-10 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-10 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-10 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-11 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-11 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-11 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-11 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-12 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-12 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-12 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-13 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-13 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-13 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-15 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-16 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-17 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-18 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-20 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-22 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-22 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-23 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-24 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-25 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-26 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-26 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-27 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-27 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-28 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-28 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-12 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-13 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-28 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-29 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-30 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-30 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-31 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-03-31 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-06 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-07 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-08 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-08 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-09 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-09 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-10 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-10 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-10 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-11 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-11 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-11 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-13 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-13 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-14 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-15 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-16 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-16 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-16 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-17 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-17 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-18 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-18 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-19 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-19 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-20 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-20 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-21 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-21 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-22 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-22 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-23 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-24 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-25 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-26 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-02 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-03 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-05 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-06 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-07 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-07 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-08 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-09 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-10 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-11 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-11 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-12 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-13 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-13 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-13 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-14 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-14 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-15 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-15 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-15 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-16 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-16 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-17 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-17 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-17 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-18 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-18 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-19 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-19 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-20 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-20 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-21 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-21 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-22 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-22 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-24 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-25 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-26 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-27 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-27 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-28 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-29 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-30 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-31 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-31 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-01 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-02 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-03 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-04 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-05 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-05 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-06 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-06 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-07 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-07 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-08 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-08 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-08 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-09 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-09 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-09 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-10 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-10 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-10 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-11 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-11 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-11 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-12 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-12 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-13 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-13 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-13 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-13 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-14 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-14 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-14 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-15 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-15 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-15 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-15 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-16 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-16 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-16 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-16 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-17 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-17 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-17 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-17 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-18 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-18 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-18 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-18 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-19 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-19 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-19 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-19 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-19 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-20 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-20 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-20 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-20 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-20 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-20 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-21 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-21 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-21 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-21 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-21 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-21 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-21 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-22 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-22 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-22 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-22 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-22 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-22 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-22 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-23 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-23 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-23 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-23 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-23 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-23 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-23 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-24 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-24 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-24 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-24 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-24 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-25 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-25 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-25 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-25 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-25 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-25 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-26 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-26 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-26 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-26 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-26 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-26 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-27 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-27 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-27 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-27 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-27 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-28 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-28 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-28 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-28 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-28 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-28 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-29 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-29 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-29 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-29 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-29 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-29 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-30 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-30 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-30 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-30 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-07-01 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-01 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-02 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-02 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-03 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-03 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-04 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-04 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-05 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-06 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-07 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-08 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-09 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-09 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-09 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-10 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-10 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-10 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-11 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-11 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-11 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-12 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-12 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-12 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-13 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-13 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-14 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-14 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-15 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-15 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-16 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-16 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-17 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-17 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-18 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-18 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-19 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-19 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-20 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-20 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-21 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-21 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-21 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-22 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-22 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-22 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-22 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-23 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-23 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-23 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-24 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-24 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-24 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-25 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-25 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-25 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-26 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-26 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-26 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-27 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-27 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-27 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-28 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-28 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-28 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-29 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-29 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-29 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-30 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-30 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-30 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-31 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-31 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-31 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-08-01 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-01 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-01 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-02 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-02 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-02 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-03 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-03 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-03 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-04 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-04 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-05 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-05 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-05 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-06 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-06 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-06 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-06 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-07 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-07 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-07 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-07 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-08 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-08 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-08 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-08 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-09 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-09 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-10 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-10 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-10 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-11 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-11 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-11 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-12 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-12 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-12 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-12 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-13 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-13 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-13 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-13 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-14 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-14 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-14 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-14 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-14 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-15 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-15 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-15 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-15 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-15 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-16 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-16 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-16 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-16 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-16 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-17 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-17 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-17 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-17 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-17 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-18 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-18 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-19 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-19 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-19 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-19 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-20 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-20 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-20 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-20 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-21 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-21 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-21 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-21 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-22 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-22 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-22 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-22 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-23 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-23 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-23 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-23 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-23 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-23 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-24 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-24 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-24 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-24 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-24 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-24 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-25 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-25 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-25 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-25 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-25 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-25 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-25 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-26 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-26 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-26 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-26 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-26 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-26 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-27 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-27 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-27 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-27 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-27 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-27 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-28 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-28 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-28 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-28 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-28 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-28 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-29 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-29 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-29 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-29 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-29 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-29 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-30 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-30 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-30 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-30 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-30 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-30 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-31 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-31 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-31 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-01 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-01 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-01 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-02 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-02 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-02 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-03 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-03 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-03 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-04 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-04 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-04 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-04 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-05 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-05 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-05 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-05 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-06 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-06 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-06 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-07 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-07 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-08 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-08 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-09 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-09 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-10 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-10 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-10 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-11 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-11 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-11 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-12 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-12 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-12 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-13 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-13 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-13 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-14 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-14 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-14 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-15 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-15 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-16 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-16 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-17 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-17 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-17 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-18 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-18 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-18 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-19 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-19 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-19 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-20 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-20 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-20 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-21 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-21 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-21 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-21 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-22 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-22 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-22 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-23 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-23 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-24 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-25 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-25 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-26 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-27 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2024-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-12 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-13 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-14 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-15 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-16 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-17 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-18 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-19 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-20 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-21 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-21 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-22 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-23 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-24 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-25 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-26 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-27 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-28 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-29 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-30 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-01 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-02 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-03 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-09 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-10 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-11 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-12 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-13 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-14 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-15 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-16 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-17 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-20 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-21 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-22 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-23 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-24 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-25 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-13 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-14 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-15 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-16 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-17 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-18 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-19 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-20 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-20 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-21 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-21 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-22 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-22 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-23 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-23 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-24 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-24 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-25 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-25 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-26 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-27 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-28 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-29 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-30 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-01 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-02 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-03 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-04 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-04 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-05 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-05 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-06 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-06 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-07 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-07 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-07 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-08 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-08 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-08 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-09 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-09 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-09 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-10 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-10 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-10 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-11 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-11 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-11 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-12 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-12 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-12 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-13 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-13 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-14 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-14 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-15 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-15 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-15 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-16 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-16 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-16 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-17 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-18 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-19 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-20 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-21 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-22 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-23 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-23 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-23 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-24 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-24 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-24 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-25 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-25 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-25 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-25 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-26 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-26 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-26 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-27 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-27 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-27 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-28 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-28 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-28 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-28 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-29 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-29 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-29 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-29 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-30 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-30 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2024-12-31 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-31 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-01 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-01 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-02 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-02 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-03 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-03 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-04 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-05 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-06 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-07 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-08 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-08 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-09 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-09 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-10 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-11 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-12 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-13 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-14 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-15 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-15 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-16 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-16 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-17 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-18 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-18 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-18 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-19 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-19 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-19 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-20 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-20 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-21 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-21 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-22 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-25 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-26 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-27 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-28 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-29 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-30 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-31 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-01-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-31 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-05 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-06 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-07 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-08 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-09 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-10 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-11 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-12 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-13 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-14 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-15 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-15 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-16 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-16 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-16 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-16 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-17 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-17 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-17 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-18 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-18 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-18 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-19 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-20 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-21 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-22 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-22 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-23 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-23 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-24 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-25 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-25 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-25 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-26 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-26 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-27 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-27 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-02-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-28 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-28 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-01 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-01 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-01 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-02 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-02 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-02 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-03 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-03 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-03 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-04 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-04 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-04 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-05 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-05 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-05 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-06 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-06 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-06 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-07 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-07 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-08 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-08 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-09 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-09 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-10 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-11 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-12 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-13 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-19 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-19 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-20 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-20 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-21 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-23 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-24 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-24 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-25 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-25 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-26 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-26 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-27 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-27 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-28 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-30 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-30 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-30 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-31 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-03-31 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-01 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-01 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-02 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-02 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-03 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-03 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-04 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-04 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-05 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-05 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-06 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-06 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-07 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-07 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-08 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-08 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-09 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-09 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-10 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-11 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-22 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-07 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-08 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-09 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-10 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-11 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-12 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-13 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-14 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-15 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-15 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-16 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-17 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-18 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-19 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-20 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-21 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-22 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-22 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-23 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-23 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-24 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-24 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-25 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-25 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-26 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-26 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-27 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-27 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-27 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-27 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-28 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-28 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-28 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-28 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-29 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-29 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-29 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-29 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-30 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-30 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-30 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-30 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-31 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-31 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-31 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-31 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-01 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-01 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-01 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-08-01 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-02 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-02 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-02 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-03 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-03 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-10 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-11 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-12 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-13 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-13 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-14 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-15 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-15 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-16 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-16 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-17 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-17 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-17 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-18 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-18 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-18 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-19 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-19 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-19 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-19 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-20 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-20 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-20 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-20 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-21 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-21 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-21 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-21 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-22 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-22 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-22 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-23 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-23 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-23 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-24 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-24 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-24 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-25 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-25 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-25 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-26 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-26 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-27 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-27 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-27 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-28 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-28 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-29 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-30 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-30 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-31 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-08-31 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-01 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-01 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-01 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-02 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-02 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-02 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-03 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-03 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-04 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-04 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-05 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-05 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-06 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-06 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-06 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-07 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-07 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-08 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-08 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-08 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-09 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-09 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-09 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-09 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-10 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-10 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-10 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-11 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-11 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-12 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-12 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-13 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-14 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-15 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-16 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-16 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-17 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-18 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-18 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-19 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-19 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-19 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-19 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-20 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-20 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-20 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-21 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-21 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-21 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-22 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-22 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-22 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-23 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-23 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-24 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-24 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-24 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-25 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-25 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-25 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-26 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-26 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-26 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-27 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-27 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-27 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-28 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-28 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-28 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-28 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-29 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-29 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-29 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-29 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-30 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-30 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-16 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-25 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-26 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-10-01 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-02 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-03 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-04 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-22 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-23 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-28 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-29 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-30 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-31 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-02 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-03 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-04 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-14 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-15 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-18 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-19 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-20 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-07 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-08 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-08 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-09 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-09 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-10 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-10 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-11 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-12 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-12 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-13 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-13 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-13 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-14 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-14 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-14 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-15 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-15 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-16 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-17 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-18 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-19 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-20 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-20 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-21 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-21 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-22 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-23 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-23 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-24 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-24 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-25 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-25 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-26 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-27 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-27 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-28 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-28 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-28 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-29 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-29 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-03-31 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-31 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-01 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-01 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-02 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-02 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-03 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-03 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-04 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-04 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-05 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-05 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-06 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-07 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-07 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-08 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-09 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-09 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-09 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-10 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-10 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-10 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-11 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-11 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-11 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-13 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-13 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-14 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-14 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-15 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-16 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-16 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-17 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-17 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-18 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-19 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-20 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-20 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-21 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-21 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-23 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-24 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-24 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-25 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-25 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-26 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-27 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-28 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-28 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-29 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-29 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-30 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-30 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-01 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-01 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-02 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-03 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-03 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-04 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-04 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-05 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-05 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-06 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-06 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-08 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-09 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-09 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-10 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-10 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-11 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-11 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-12 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-13 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-13 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-14 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-14 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-15 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-15 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-16 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-16 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-17 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-17 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-17 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-17 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-18 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-18 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-18 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-18 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-19 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-19 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-19 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-19 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-20 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-20 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-20 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-21 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-21 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-21 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-22 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-22 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-23 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-23 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-23 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-23 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-24 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-24 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-24 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-24 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-25 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-25 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-25 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-25 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-25 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-26 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-26 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-26 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-26 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-26 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-27 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-27 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-27 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-27 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-28 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-28 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-28 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-28 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-29 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-29 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-29 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-29 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-29 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-30 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-30 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-30 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-30 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-30 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-31 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-31 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-31 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-05-31 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-31 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-01 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-01 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-01 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-01 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-02 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-02 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-02 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-02 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-02 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-03 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-03 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-03 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-03 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-03 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-04 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-04 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-04 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-04 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-04 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-05 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-05 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-05 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-05 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-05 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-06 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-06 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-06 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-06 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-07 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-07 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-07 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-07 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-08 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-08 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-08 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-09 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-09 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-09 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-09 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-09 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-10 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-10 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-10 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-10 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-10 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-11 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-11 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-11 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-12 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-12 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-12 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-12 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-13 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-13 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-13 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-13 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-14 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-14 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-14 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-14 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-15 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-15 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-15 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-15 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-16 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-16 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-16 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-16 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-17 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-17 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-18 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-18 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-19 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-19 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-20 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-20 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-21 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-21 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-21 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-22 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-22 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-22 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-23 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-23 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-24 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-25 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-26 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-26 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-27 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-27 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-28 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-28 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-28 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-29 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-29 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-29 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-30 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-30 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-30 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-01 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-01 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-02 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-02 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-03 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-03 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-04 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-04 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-05 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-05 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-06 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-06 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-07 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-07 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-07 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-08 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-08 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-09 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-09 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-10 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-10 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-11 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-11 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-11 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-12 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-12 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-12 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-13 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-13 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-14 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-14 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-15 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-15 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-16 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-16 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-17 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-17 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-18 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-19 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-19 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-20 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-20 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-21 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-21 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-22 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-22 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-23 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-23 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-24 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-24 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-25 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-25 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-26 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-26 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-27 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-27 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-28 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-28 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-29 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-30 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-31 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-31 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-02 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-03 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-09 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-10 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-10 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-11 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-11 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-12 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-12 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-13 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-14 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-14 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-15 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-15 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-16 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-16 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-17 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-18 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-19 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-19 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-20 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-20 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-21 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-21 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-21 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-22 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-22 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-23 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-23 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-23 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-24 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-24 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-24 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-24 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-25 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-25 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-25 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-26 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-26 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-26 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-27 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-28 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-28 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-29 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-29 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-30 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-30 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-31 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-31 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-01 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-01 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-02 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-02 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-03 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-03 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-03 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-04 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-04 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-04 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-05 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-05 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-05 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-06 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-06 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-07 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-07 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-08 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-08 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-09 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-09 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-09 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-10 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-11 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-12 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-12 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-12 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-12 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-13 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-13 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-14 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-14 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-15 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-15 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-16 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-16 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-17 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-17 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-18 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-19 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-19 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-19 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-20 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-20 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-20 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-20 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-21 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-21 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-22 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-22 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-22 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-22 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-23 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-23 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-24 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-24 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-24 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-25 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-25 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-26 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-27 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-27 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-27 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-28 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-28 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-28 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-29 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-30 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-04 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-05 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-06 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-07 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-08 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325 | 133A/1 | Completed
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-15 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-16 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-17 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-18 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-19 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-20 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-21 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-22 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-23 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-24 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-25 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-26 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-27 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-28 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-29 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-30 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-31 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-01 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-02 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-03 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-04 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-05 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-19 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-20 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-21 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-22 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-23 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-24 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-25 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-26 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-27 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-28 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-29 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-30 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-01 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-02 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-03 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-04 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-05 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed

## ProdDailyExpandedSingles
Work Date | Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-09-01 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-02 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-03 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-04 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-05 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-06 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-07 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-08 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-09 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-10 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-11 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-12 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-13 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-14 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-15 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-17 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-18 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-19 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-20 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-21 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-22 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-23 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-24 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-25 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-26 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-27 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-28 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-29 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-09-30 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-01 | 2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-02 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-04 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-05 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-06 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-07 | 2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-09 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-10 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-11 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-12 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-13 | 2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-15 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-16 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-17 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-18 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-19 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-20 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-21 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-21 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-22 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-22 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-23 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-23 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-24 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-25 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-26 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-27 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-28 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-29 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-30 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-10-31 | 2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-01 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-02 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-03 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-04 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-05 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-05 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-06 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-06 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-07 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-07 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-08 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-08 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-09 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-09 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-10 | 2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-10 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-11 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-11 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-12 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-12 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-13 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-13 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-14 | 2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-14 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-15 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-16 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-17 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-18 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-18 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-19 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-19 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-20 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-20 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-21 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-21 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-22 | 2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-22 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-22 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-23 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-23 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-24 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-24 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-25 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-25 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-26 | 2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-27 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-27 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-28 | 2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-28 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-29 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-30 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-30 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-30 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-01 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-01 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-01 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-01 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-02 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-02 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-02 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-02 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-03 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-03 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-12-03 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-03 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-04 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-04 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-04 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-04 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-05 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-12-05 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-05 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-12-05 | 2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-12-06 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-06 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-07 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-07 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-07 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-08 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-08 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-08 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-09 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-09 | 2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-09 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-10 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-11 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-11 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-12 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-12 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-13 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-13 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-13 | 2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-14 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-14 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-14 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-15 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-15 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-15 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-16 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-16 | 2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-16 | 2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-17 | 2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-17 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-18 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-18 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-19 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-19 | 2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-19 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-20 | 2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-20 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-20 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-21 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-21 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-21 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-22 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-22 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-22 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-23 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-23 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-23 | 2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-25 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-25 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-26 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-26 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-27 | 2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-27 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-28 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-29 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-29 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-30 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-30 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-31 | 2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-31 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-31 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-01 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-01 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-02 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-02 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-03 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2025-01-03 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-03 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-04 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-04 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-05 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-05 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-05 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-06 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-06 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-06 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-07 | 2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2025-01-07 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-07 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-08 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-09 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-09 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-09 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-10 | 2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-10 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-10 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-11 | 2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-11 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-12 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-12 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-13 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-13 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-14 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-14 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-15 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-15 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-16 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-16 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-16 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-17 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-17 | 2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-18 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-18 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-19 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-19 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-20 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-20 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-21 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-21 | 2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-21 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-22 | 2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-22 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-23 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-23 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-24 | 2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-24 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-26 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-27 | 2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-28 | 2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-28 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-29 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-30 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-30 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-01-31 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-31 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-01-31 | 2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-01 | 2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-02-01 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-02 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-03 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-03 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-04 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-04 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-04 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-05 | 2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-05 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-05 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-06 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-06 | 2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-06 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-07 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-07 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-07 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-08 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-02-08 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-09 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-09 | 2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-09 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-09 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-10 | 2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-02-10 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-10 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-10 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-10 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-11 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-11 | 2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-11 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-11 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-11 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-12 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-12 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-12 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-12 | 2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-13 | 2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-13 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-13 | 2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-13 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-14 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-15 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-15 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-16 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-17 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-17 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-18 | 2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-18 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-19 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-19 | 2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-20 | 2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-20 | 2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-20 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-20 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-21 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-21 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-22 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-22 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-22 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-22 | 2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-23 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-23 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-23 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-24 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-24 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-24 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-25 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-25 | 2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-25 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-26 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-26 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-26 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-26 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-27 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-27 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-27 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-27 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-02-28 | 2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-28 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-02-28 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-02-28 | 2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-02 | 2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-02 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-03 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-03 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-04 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-04 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-05 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-05 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-06 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-06 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-07 | 2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-07 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-07 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-08 | 2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-03-08 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-08 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-09 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-09 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-10 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-11 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-11 | 2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-12 | 2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-12 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-13 | 2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-14 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-14 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-15 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-15 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-16 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-16 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-17 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-17 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-17 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-18 | 2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-18 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-18 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-19 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-19 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-20 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-20 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-21 | 2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-21 | 2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-22 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-23 | 2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-24 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-25 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-26 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-26 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-27 | 2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-27 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-28 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-28 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-28 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-28 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-29 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-29 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-29 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-29 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-30 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-30 | 2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-30 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-30 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-30 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-31 | 2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-03-31 | 2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-31 | 2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-01 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-01 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-02 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-02 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-02 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-03 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-03 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-03 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-03 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-04 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-04 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-04 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-04 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-05 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-05 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-05 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-05 | 2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-04-06 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-06 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-06 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-06 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-06 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-07 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-07 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-07 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-07 | 2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-04-07 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-08 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-08 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-08 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-08 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-09 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-09 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-09 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-09 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-09 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-10 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-10 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-10 | 2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-10 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-10 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-10 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-11 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-11 | 2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-11 | 2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-11 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-11 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-12 | 2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-12 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-12 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-13 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-13 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-13 | 2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-13 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-14 | 2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-14 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-14 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-15 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-15 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-15 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-15 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-16 | 2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-16 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-16 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-16 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-16 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-17 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-17 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-17 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-17 | 2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-17 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-18 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-18 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-18 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-18 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-19 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-19 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-19 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-19 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-20 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-20 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-20 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-20 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-20 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-21 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-21 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-21 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-21 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-21 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-22 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-22 | 2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-22 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-22 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-22 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-23 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-23 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-23 | 2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-24 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-24 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-24 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-24 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-25 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-25 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-25 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-25 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-26 | 2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-26 | 2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-26 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-26 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-26 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-27 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-27 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-27 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-27 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-28 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-28 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-28 | 2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-28 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-29 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-29 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-30 | 2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-30 | 2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-30 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-01 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-01 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-02 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-02 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-02 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-03 | 2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-03 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-03 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-04 | 2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-04 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-04 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-05 | 2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-05 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-05 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-05 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-05-06 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-06 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-06 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-06 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-06 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-07 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-07 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-07 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-07 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-07 | 2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-08 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-08 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-08 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-08 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-08 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-09 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-09 | 2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-09 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-09 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-09 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-10 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-10 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-10 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-10 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-10 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-11 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-11 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-11 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-11 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-11 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-12 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-12 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-12 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-12 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-12 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-13 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-13 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-13 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-13 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-13 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-13 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-14 | 2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-14 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-14 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-14 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-14 | 2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-14 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-14 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-15 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-15 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-15 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-15 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-15 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-15 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-15 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-16 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-16 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-16 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-16 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-16 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-16 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-16 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-17 | 2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-17 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-17 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-17 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-17 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-17 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-17 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-17 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-18 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-18 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-18 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-18 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-18 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-18 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-18 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-19 | 2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-19 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-19 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-19 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-19 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-19 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-19 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-20 | 2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-20 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-20 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-20 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-20 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-20 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-20 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-20 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-21 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-21 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-21 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-21 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-21 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-21 | 2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-21 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-22 | 2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-22 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-22 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-22 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-22 | 2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-22 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-22 | 2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-22 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-23 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-23 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-23 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-24 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-24 | 2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-24 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-24 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-24 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-24 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-25 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-25 | 2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-25 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-25 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-25 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-25 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-26 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-26 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-26 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-26 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-26 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-27 | 2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-27 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-27 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-27 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-27 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-27 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-27 | 2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-28 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-28 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-28 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-28 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-28 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-29 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-29 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-29 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-29 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-29 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-29 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-30 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-30 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-30 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-30 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-30 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-30 | 2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-30 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-31 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-05-31 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-31 | 2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-31 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-05-31 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-31 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-01 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-01 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-01 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-01 | 2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-06-01 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-01 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-06-02 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-02 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-02 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-02 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-02 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-02 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-03 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-03 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-03 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-03 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-03 | 2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-06-03 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-04 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-04 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-04 | 2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-06-04 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-04 | 2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-06-04 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-05 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-05 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-05 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-05 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-05 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-06 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-06 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-06 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-06 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-06 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-07 | 2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-07 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-07 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-07 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-07 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-08 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-08 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-08 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-08 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-08 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-09 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-09 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-09 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-09 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-09 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-10 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-10 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-10 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-10 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-10 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-10 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-11 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-11 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-11 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-11 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-11 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-11 | 2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-12 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-12 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-12 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-12 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-13 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-13 | 2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-13 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-13 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-13 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-13 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-13 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-14 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-14 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-14 | 2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-14 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-14 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-14 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-15 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-15 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-15 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-15 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-15 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-15 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-16 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-16 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-16 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-16 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-16 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-16 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-17 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-17 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-17 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-17 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-17 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-17 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-18 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-18 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-18 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-18 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-18 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-18 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-19 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-19 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-19 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-19 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-19 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-19 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-20 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-20 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-20 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-20 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-20 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-20 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-06-20 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-21 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-21 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-21 | 2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-21 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-21 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-21 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-21 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-22 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-22 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-22 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-22 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-22 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-22 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-22 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-23 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-23 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-23 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-23 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-23 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-23 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-23 | 2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-24 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-24 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-24 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-24 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-24 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-24 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-25 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-25 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-25 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-25 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-25 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-25 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-25 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-26 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-26 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-26 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-26 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-26 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-26 | 2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-26 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-27 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-27 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-27 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-27 | 2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-27 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-27 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-28 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-28 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-28 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-28 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-28 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-28 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-28 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-29 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-29 | 2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-29 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-29 | 2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-29 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-29 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-29 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-30 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-06-30 | 2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-06-30 | 2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-30 | 2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-30 | 2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-07-01 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-01 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-02 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-02 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-02 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-03 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-03 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-03 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-04 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-04 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-04 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-05 | 2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-05 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-06 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-06 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-07 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-07 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-08 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-08 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-09 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-09 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-09 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-10 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-10 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-10 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-11 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-11 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-11 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-12 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-12 | 2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-12 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-13 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-13 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-14 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-14 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-15 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-15 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-16 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-16 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-17 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-17 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-18 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-18 | 2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-18 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-19 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-19 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-20 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-20 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-21 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-21 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-21 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-22 | 2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-22 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-22 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-22 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-23 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-23 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-23 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-24 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-24 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-24 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-25 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-25 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-25 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-26 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-26 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-26 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-27 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-27 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-27 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-28 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-28 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-28 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-29 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-29 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-29 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-30 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-30 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-30 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-31 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-31 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-07-31 | 2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-08-01 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-01 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-01 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-02 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-02 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-02 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-03 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-03 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-03 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-04 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-04 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-05 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-05 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-05 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-06 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-06 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-06 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-06 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-07 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-07 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-07 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-07 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-08 | 2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-08-08 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-08 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-08 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-09 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-09 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-10 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-10 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-10 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-10 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-11 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-11 | 2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-08-11 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-11 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-12 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-12 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-12 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-12 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-13 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-13 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-13 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-13 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-14 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-14 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-14 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-14 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-14 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-15 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-15 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-15 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-15 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-15 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-16 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-16 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-16 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-16 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-16 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-16 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-17 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-17 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-17 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-17 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-17 | 2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-17 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-18 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-18 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-18 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-19 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-19 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-19 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-19 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-19 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-19 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-20 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-20 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-20 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-20 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-20 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-20 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-21 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-21 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-21 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-21 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-21 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-21 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-22 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-22 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-22 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-22 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-22 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-22 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-23 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-23 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-23 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-23 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-23 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-23 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-23 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-23 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-24 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-24 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-24 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-24 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-24 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-24 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-24 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-24 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-25 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-25 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-25 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-25 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-25 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-25 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-25 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-25 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-25 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-26 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-26 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-26 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-08-26 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-26 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-26 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-26 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-26 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-26 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-27 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-27 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-27 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-27 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-27 | 2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-27 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-27 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-27 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-27 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-28 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-28 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-28 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-28 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-28 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-28 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-28 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-28 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-29 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-29 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-29 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-29 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-29 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-29 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-29 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-29 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-29 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-30 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-30 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-30 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-30 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-30 | 2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-30 | 2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-30 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-30 | 2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-30 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-08-31 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-31 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-31 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-31 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-31 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-08-31 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-01 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-01 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-01 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-01 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-01 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-01 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-02 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-02 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-02 | 2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-09-02 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-02 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-02 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-03 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-03 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-03 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-03 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-03 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-04 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-04 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-04 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-04 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-04 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-04 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-05 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-05 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-05 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-05 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-05 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-05 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-05 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-06 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-06 | 2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-09-06 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-06 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-06 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-06 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-06 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-07 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-07 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-07 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-07 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-07 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-07 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-08 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-08 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-08 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-08 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-08 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-08 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-09 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-09 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-09 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-09 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-09 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-09 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-10 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-10 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-10 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-10 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-10 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-10 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-10 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-11 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-11 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-11 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-11 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-11 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-11 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-11 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-12 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-12 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-12 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-12 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-12 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-12 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-12 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-13 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-13 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-13 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-13 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-13 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-13 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-13 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-14 | 2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-14 | 2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-14 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-14 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-14 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-14 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-14 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-15 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-15 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-15 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-15 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-16 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-16 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-16 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-16 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-16 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-17 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-17 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-17 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-17 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-17 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-17 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-18 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-18 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-18 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-18 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-18 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-18 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-19 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-19 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-19 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-19 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-19 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-19 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-20 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-20 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-20 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-20 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-20 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-20 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-21 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-21 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-21 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-21 | 2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-09-21 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-21 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-21 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-22 | 2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-09-22 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-22 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-22 | 2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-22 | 2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-09-22 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-22 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-23 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-23 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-23 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-23 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-09-24 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-24 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-24 | 2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-24 | 2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-25 | 2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-25 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-26 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-27 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-27 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-28 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2025-09-28 | 2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-09-29 | 2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
2024-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-04-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-05-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-06-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-07-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-08-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-12 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-13 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-14 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-15 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-16 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-17 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-18 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-19 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-20 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-21 | 2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-21 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-22 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-23 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-24 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-25 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-26 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-27 | 2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-28 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-29 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-09-30 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-09-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-01 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-02 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-03 | 2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-03 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-04 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-05 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-06 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-07 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-08 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-09 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-09 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-10 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-10 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-11 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-11 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-12 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-12 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-13 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-13 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-14 | 2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-14 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-14 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-15 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-15 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-16 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-16 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-17 | 2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-17 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-18 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-19 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-20 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-21 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-22 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-23 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-24 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-25 | 2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-10-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-10-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-12 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-13 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-14 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-15 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-15 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-16 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-16 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-17 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-17 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-18 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-18 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-19 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-19 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-20 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-20 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-21 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-21 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-22 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-22 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-23 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-23 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-24 | 2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-24 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-25 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-25 | 2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-26 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-26 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-27 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-27 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-28 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-28 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-29 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-29 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-11-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-11-30 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-30 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-01 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-01 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-02 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-02 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-03 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-03 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-04 | 2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-12-04 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-05 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-05 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-06 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-06 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-07 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-07 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-07 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-08 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-08 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-08 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-09 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-09 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-09 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-10 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-10 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-10 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-11 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-11 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-11 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-12 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-12 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-12 | 2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-13 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-13 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-13 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-14 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-14 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-14 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-15 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-15 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-15 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-15 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-16 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-16 | 2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-16 | 2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-16 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-17 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-17 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-17 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-18 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-18 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-18 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-19 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-19 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-19 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-20 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-20 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-20 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-21 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-21 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-21 | 2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-22 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-22 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-22 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-22 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-23 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-23 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-23 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-23 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-23 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-24 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-24 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-24 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-24 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-24 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-24 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-24 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-25 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-25 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-25 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-25 | 2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-25 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-25 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-25 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-26 | 2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-26 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-26 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-26 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-26 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-27 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-27 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-27 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-27 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-27 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-28 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-28 | 2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-28 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-28 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-28 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-29 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-29 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-29 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-29 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-29 | 2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-29 | 2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-30 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-30 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-30 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-30 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-30 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2024-12-31 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-31 | 2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-31 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2024-12-31 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2024-12-31 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-01 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-01 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-01 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-01 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-01 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-02 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-02 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-02 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-02 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-02 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-03 | 2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2025-01-03 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-03 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-03 | 2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-03 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-04 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-04 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-04 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-04 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-05 | 2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2025-01-05 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-05 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-05 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-06 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-06 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-06 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-06 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-07 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-07 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-07 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-07 | 2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-07 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-08 | 2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2025-01-08 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-08 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-08 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-08 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-08 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-09 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-09 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-09 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-09 | 2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-09 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-10 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-10 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-10 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-10 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-10 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-11 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-11 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-11 | 2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-11 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-11 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-11 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-12 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-12 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-12 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-12 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-12 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-13 | 2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-13 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-13 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-13 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-13 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-14 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-14 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-14 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-14 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-14 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-15 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-15 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-15 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-15 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-15 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-16 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-16 | 2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-16 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-16 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-16 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-16 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-17 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-17 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-17 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-17 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-17 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-17 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-18 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-18 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-18 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-18 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-18 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-18 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-19 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-19 | 2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-19 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-19 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-19 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-19 | 2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-20 | 2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-20 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-20 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-20 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-20 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-21 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-21 | 2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-21 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-21 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-22 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-22 | 2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-22 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-22 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-22 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-23 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-23 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-23 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-23 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-24 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-24 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-24 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-24 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-24 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-25 | 2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-25 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-25 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-25 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-25 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-25 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-26 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-26 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-26 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-26 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-26 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-27 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-27 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-27 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-27 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-27 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-28 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-28 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-28 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-28 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-28 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-29 | 2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-29 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-29 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-29 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-29 | 2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-29 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-30 | 2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-30 | 2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-30 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-30 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-30 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-31 | 2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-01-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-31 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-31 | 2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-31 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-01-31 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-01 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-01 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-01 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-02 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-02 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-02 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-03 | 2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-02-03 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-03 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-03 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-04 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-04 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-04 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-05 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-05 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-05 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-05 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-06 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-06 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-06 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-06 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-07 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-02-07 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-07 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-07 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-08 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-08 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-08 | 2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-02-08 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-08 | 2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-09 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-09 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-09 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-09 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-10 | 2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-10 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-10 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-10 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-11 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-11 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-11 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-11 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-12 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-12 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-12 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-12 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-13 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-13 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-13 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-13 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-14 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-14 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-14 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-14 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-14 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-15 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-15 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-15 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-15 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-15 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-15 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-16 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-16 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-16 | 2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-02-16 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-16 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-16 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-16 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-17 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-17 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-17 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-17 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-17 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-17 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-18 | 2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-18 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-18 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-18 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-18 | 2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-18 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-18 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-19 | 2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-19 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-19 | 2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-19 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-19 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-20 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-20 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-20 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-20 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-21 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-21 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-21 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-21 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-22 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-22 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-22 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-22 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-23 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-23 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-23 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-23 | 2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-24 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-24 | 2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-24 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-24 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-25 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-25 | 2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-25 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-25 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-25 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-26 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-26 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-26 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-26 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-27 | 2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-27 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-27 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-27 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-28 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-02-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-02-28 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-28 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-02-28 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-01 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-01 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-01 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-01 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-01 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-01 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-02 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-02 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-02 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-02 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-02 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-02 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-03 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-03 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-03 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-03 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-03 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-03 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-04 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-04 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-04 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-04 | 2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-04 | 2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-04 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-05 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-05 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-05 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-05 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-05 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-05 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-06 | 2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-03-06 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-06 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-06 | 2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-03-06 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-06 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-07 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-07 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-07 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-07 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-07 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-08 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-08 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-08 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-08 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-08 | 2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-09 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-09 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-09 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-09 | 2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-03-09 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-10 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-10 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-10 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-10 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-10 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-11 | 2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-11 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-11 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-11 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-11 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-12 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-12 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-12 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-12 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-12 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-13 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-13 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-13 | 2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-13 | 2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-13 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-14 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-14 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-14 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-14 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-15 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-15 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-15 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-15 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-16 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-16 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-16 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-16 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-17 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-17 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-17 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-17 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-18 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-18 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-18 | 2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-18 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-19 | 2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-19 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-19 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-19 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-19 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-20 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-20 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-20 | 2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-20 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-20 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-21 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-21 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-21 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-21 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-21 | 2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-22 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-22 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-22 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-22 | 2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-22 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-23 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-23 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-23 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-23 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-23 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-23 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-24 | 2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-24 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-24 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-24 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-24 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-24 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-25 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-25 | 2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-25 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-25 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-25 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-25 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-26 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-26 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-26 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-26 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-26 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-26 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-27 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-27 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-27 | 2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-27 | 2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-27 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-27 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-28 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-28 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-28 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-28 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-29 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-29 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-29 | 2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-29 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-30 | 2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-30 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-30 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-30 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-30 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-03-31 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-03-31 | 2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-03-31 | 2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2025-03-31 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-03-31 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-01 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-01 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-01 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-02 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-02 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-02 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-03 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-03 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-03 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-04 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-04 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-04 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-05 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-04-05 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-05 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-05 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-06 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-06 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-06 | 2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-04-06 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-07 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-07 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-07 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-07 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-08 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-08 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-08 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-08 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-09 | 2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-09 | 2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-04-09 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-09 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-09 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-10 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-10 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-10 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-11 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-11 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-11 | 2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-12 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-12 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-13 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-13 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-14 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-14 | 2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-14 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-15 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-15 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-16 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-16 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-17 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-17 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-18 | 2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-18 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-18 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-19 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-19 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-20 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-20 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-21 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-21 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-22 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-22 | 2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-23 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-24 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-25 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-26 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-27 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-28 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-29 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-04-30 | 2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-07-05 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-06 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-07 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-07 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-08 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-08 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-08 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-09 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-09 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-09 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-09 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-10 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-10 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-10 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-10 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-11 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-11 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-11 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-11 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-12 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-12 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-12 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-12 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-13 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-13 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-13 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-13 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-14 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-14 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-14 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-14 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-15 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-15 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-15 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-15 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-15 | 2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-16 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-16 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-16 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-16 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-16 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-17 | 2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-17 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-17 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-17 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-17 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-18 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-18 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-18 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-18 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-18 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-19 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-19 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-19 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-19 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-19 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-20 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-20 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-20 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-20 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-20 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-21 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-21 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-21 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-21 | 2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-21 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-21 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-22 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-22 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-22 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-22 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-22 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-22 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-23 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-23 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-23 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-23 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-23 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-23 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-24 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-24 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-24 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-24 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-24 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-24 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-25 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-25 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-25 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-25 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-25 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-25 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-26 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-26 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-26 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-26 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-26 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-26 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-26 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-27 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-27 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-27 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-27 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-27 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-27 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-27 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-27 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-28 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-28 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-28 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-28 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-28 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-28 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-28 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-28 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-29 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-29 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-29 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-29 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-29 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-29 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-29 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-29 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-30 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-30 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-30 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-30 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-30 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-30 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-30 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-30 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-31 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-07-31 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-07-31 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-31 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-31 | 2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-31 | 2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-31 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-31 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-01 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-01 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-01 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-01 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-01 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-01 | 2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-08-01 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-02 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-02 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-02 | 2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-02 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-02 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-02 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-02 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-03 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-03 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-03 | 2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-03 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-03 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-03 | 2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-08-04 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-04 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-04 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-04 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-04 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-05 | 2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-05 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-05 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-05 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-05 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-06 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-06 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-06 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-06 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-07 | 2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-07 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-07 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-07 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-07 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-08 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-08 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-08 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-08 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-08 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-09 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-09 | 2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-09 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-09 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-09 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-09 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-10 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-10 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-10 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-10 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-10 | 2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-10 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-11 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-11 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-11 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-11 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-11 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-11 | 2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-12 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-12 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-12 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-12 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-12 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-12 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-13 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-13 | 2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-13 | 2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-13 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-13 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-13 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-13 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-14 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-14 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-14 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-14 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-14 | 2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-14 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-15 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-15 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-15 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-15 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-15 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-15 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-15 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-16 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-16 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-16 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-16 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-16 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-16 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-16 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-17 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-17 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-17 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-17 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-17 | 2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-17 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-17 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-18 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-18 | 2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-18 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-18 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-18 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-18 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-18 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-18 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-19 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-19 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-19 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-19 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-19 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-19 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-19 | 2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-19 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-20 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-20 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-20 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-20 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-20 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-20 | 2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-20 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-20 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-20 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-21 | 2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-21 | 2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-21 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-21 | 2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-21 | 2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-21 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-21 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-21 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-21 | 2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-22 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-22 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-22 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-22 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-22 | 2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-22 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-22 | 2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-22 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-23 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-23 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-23 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-23 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-23 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-23 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-23 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-23 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-24 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-24 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-24 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-24 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-24 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-24 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-24 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-24 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-25 | 2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-25 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-25 | 2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-25 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-25 | 2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-25 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-25 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-25 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-26 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-26 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-26 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-26 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-26 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-26 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-26 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-27 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-27 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-27 | 2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-27 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-27 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-27 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-27 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-28 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-28 | 2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-28 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-28 | 2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-28 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-28 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-28 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-29 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-29 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-29 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-29 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-29 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-29 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-30 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-30 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-30 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-30 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-30 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-30 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-30 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-31 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-31 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-08-31 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-08-31 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-31 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-08-31 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-31 | 2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-31 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-01 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-01 | 2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-01 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-01 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-01 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-01 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-01 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-01 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-02 | 2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-02 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-02 | 2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-02 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-02 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-02 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-02 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-02 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-03 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-03 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-03 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-03 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-03 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-03 | 2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-09-03 | 2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-04 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-04 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-04 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-04 | 2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-09-04 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-04 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-04 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-05 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-09-05 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-05 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-05 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-05 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-05 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-05 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-06 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-06 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-06 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-09-06 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-06 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-06 | 2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-09-06 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-06 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-07 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-07 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-07 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-07 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-07 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-07 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-07 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-07 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-08 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-08 | 2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-09-08 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-08 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-08 | 2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-08 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-08 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-08 | 2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-08 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-09 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-09 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-09 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-09 | 2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-09 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-09 | 2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-09-09 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-09 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-09 | 2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-10 | 2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-10 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-10 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-10 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-10 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-10 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-10 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-10 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-11 | 2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-11 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-11 | 2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-11 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-11 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-11 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-11 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-11 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-12 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-12 | 2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-12 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-12 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-12 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-12 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-12 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-12 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-13 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-13 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-13 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-13 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-13 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-13 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-13 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-13 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-14 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-14 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-14 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-14 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-14 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-14 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-14 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-14 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-14 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-15 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-15 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-15 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-15 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-15 | 2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-15 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-15 | 2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-15 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-15 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-15 | 2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-16 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-16 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-16 | 2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-16 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-16 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-16 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-16 | 2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-16 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-16 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-16 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-16 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-17 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-17 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-17 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-17 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-17 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-17 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-17 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-17 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-17 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-18 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-18 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-18 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-18 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-18 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-18 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-18 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-18 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-18 | 2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-18 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-19 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-19 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-19 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-19 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-19 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-19 | 2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-19 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-19 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-19 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-19 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-19 | 2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-20 | 2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-20 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-20 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-20 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-20 | 2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-20 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-20 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-20 | 2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-20 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-20 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-20 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-21 | 2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-21 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-21 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-21 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-21 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-21 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-21 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-21 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-21 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-21 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-22 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-22 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-22 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-22 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-22 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-22 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-22 | 2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-22 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-22 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-23 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-23 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-23 | 2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-23 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-23 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-23 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-23 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-23 | 2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-24 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-24 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-24 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-24 | 2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-24 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-24 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-24 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-24 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-24 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-25 | 2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-25 | 2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-25 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-25 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-25 | 2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-25 | 2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-25 | 2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-25 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-26 | 2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-26 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-26 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-26 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-26 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-26 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-26 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-27 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-27 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-27 | 2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-27 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-27 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-27 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-28 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-28 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-28 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-28 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-28 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-28 | 2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-29 | 2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-29 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-29 | 2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-29 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-29 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-29 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-30 | 2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2025-09-30 | 2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-30 | 2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-30 | 2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2024-07-10 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-11 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-12 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-13 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-14 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-15 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-16 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-17 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-19 | 2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-19 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-20 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-21 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-22 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-23 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-24 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-25 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-26 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-28 | 2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-28 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-29 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-30 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-07-31 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-01 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-03 | 2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-03 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-04 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-05 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-06 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-07 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-08 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-10 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-11 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-12 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-13 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-14 | 2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-17 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-18 | 2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-20 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-21 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-23 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-23 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-24 | 2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-24 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-24 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-25 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-25 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-26 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-26 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-27 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-27 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-28 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-28 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-29 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-29 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-30 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-30 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-30 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-31 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-31 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-08-31 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-01 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-01 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-01 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-02 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-02 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-02 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-03 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-03 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-03 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-04 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-04 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-04 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-05 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-05 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-05 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-06 | 2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-09-06 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-06 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-07 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-07 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-08 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-08 | 2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-09-09 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-10 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-11 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-12 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-12 | 2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-13 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-14 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-14 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-15 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-15 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-15 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-16 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-16 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-16 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-17 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-17 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-17 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-18 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-18 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-18 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-19 | 2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-19 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-19 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-20 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-20 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-20 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-21 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-21 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-21 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-21 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-22 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-22 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-22 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-22 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-23 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-23 | 2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-23 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-23 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-24 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-24 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-24 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-24 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-25 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-25 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-25 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-25 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-26 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-26 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-26 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-26 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-27 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-27 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-27 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-27 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-27 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-28 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-28 | 2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-28 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-28 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-28 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-29 | 2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-29 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-29 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-29 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-30 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-30 | 2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-30 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-09-30 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-01 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-01 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-01 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-01 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-02 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-02 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-02 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-02 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-02 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-03 | 2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-10-03 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-03 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-03 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-03 | 2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-04 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-04 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-04 | 2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-04 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-05 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-05 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-05 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-06 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-06 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-06 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-06 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-07 | 2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-07 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-07 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-07 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-08 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-08 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-08 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-09 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-09 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-09 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-10 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-10 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-10 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-11 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-11 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-11 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-12 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-12 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-12 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-13 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-13 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-13 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-14 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-14 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-14 | 2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-15 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-15 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-16 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-16 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-17 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-17 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-17 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-18 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-18 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-18 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-18 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-19 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-19 | 2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-19 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-19 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-19 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-20 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-20 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-20 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-20 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-20 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-21 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-21 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-21 | 2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-21 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-21 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-22 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-22 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-22 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-22 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-22 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-23 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-23 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-23 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-23 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-23 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-24 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-24 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-24 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-24 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-24 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-25 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-25 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-25 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-25 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-25 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-25 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-26 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-26 | 2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-26 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-26 | 2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-26 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-26 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-27 | 2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-27 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-27 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-27 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-27 | 2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-28 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-28 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-28 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-28 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-29 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-29 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-29 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-30 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-30 | 2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-30 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-30 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-31 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-10-31 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-31 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-10-31 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-11-01 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-01 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-01 | 2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-02 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-03 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-03 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-03 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-04 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-04 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-04 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-05 | 2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-05 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-05 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-06 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-06 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-11-07 | 2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-07 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-07 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-08 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-08 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-08 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-09 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-09 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-09 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-10 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-10 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-10 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-10 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-10 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-11 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-11 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-11 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-11 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-11 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-12 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-12 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-12 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-12 | 2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-12 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-12 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-13 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-13 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-13 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-13 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-13 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-14 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-14 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-14 | 2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-14 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-14 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-14 | 2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-15 | 2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-15 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-15 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-15 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-16 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-16 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-16 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-17 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-17 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-17 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-18 | 2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-18 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-18 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-18 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-19 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-19 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-20 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-20 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-20 | 2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-21 | 2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-21 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-21 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-22 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-22 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-22 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-23 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-23 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-23 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-24 | 2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-24 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-24 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-25 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-25 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-25 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-26 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-26 | 2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-26 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-27 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-27 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-27 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-28 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-28 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-28 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-29 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-29 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-29 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-30 | 2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-30 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-11-30 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-01 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-01 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-02 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-02 | 2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-12-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-03 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-04 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-04 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-04 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-04 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-05 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-05 | 2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-05 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-05 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-06 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-06 | 2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-06 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-07 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-07 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-07 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-08 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-08 | 2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-08 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-09 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-09 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-10 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-10 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-10 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-11 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-11 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-12 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-12 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-12 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-12 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-13 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-13 | 2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-13 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-13 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-14 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-14 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-14 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-15 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-15 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-15 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-15 | 2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-16 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-16 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-16 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-17 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-17 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-17 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-17 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-18 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-18 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-18 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-18 | 2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-19 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-19 | 2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-19 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-20 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-20 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-20 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-20 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-21 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-21 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-21 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-21 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-22 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-22 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-22 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-22 | 2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-23 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-23 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-23 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-24 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-24 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-24 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-24 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-25 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-25 | 2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-25 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-25 | 2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-26 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-26 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-26 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-27 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-27 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-27 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-28 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-28 | 2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-28 | 2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-29 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-29 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-29 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-30 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-30 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-30 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2024-12-31 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2024-12-31 | 2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-31 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-01 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-01 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-02 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-02 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-02 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-03 | 2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-03 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-04 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-04 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-04 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-04 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-05 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-05 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-05 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-05 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-05 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-06 | 2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-06 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-06 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-06 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-06 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-07 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-07 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-07 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-08 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-08 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-08 | 2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-09 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-09 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-10 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-10 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-10 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-11 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-11 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-11 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-12 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-12 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-12 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-13 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-13 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-13 | 2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-14 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-14 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-15 | 2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-15 | 2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-15 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-16 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-16 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-17 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-17 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-18 | 2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-18 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-19 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-19 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-19 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-20 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-20 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-20 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-21 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-21 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-21 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-22 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-22 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-23 | 2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-23 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-23 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-23 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-24 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-24 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-24 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-24 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-25 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-25 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-25 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-25 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-26 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-26 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-26 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-26 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-27 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-27 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-27 | 2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-27 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-28 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-28 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-28 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-29 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-29 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-29 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-30 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-30 | 2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-30 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-01-31 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-31 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-01-31 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-01 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-01 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-01 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-02 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-02 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-02 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-03 | 2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-04 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-04 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-05 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-05 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-05 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-06 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-06 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-06 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-07 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-07 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-07 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-08 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-08 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-08 | 2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-09 | 2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-02-09 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-11 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-11 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-12 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-13 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-14 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-15 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-15 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-16 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-16 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-16 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-17 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-17 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-17 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-18 | 2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-18 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-18 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-19 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-19 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-19 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-20 | 2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-20 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-20 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-21 | 2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-21 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-22 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-23 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-23 | 2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-24 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-25 | 2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-25 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-25 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-26 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-26 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-27 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-27 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-27 | 2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-28 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-02-28 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-28 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-01 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-01 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-01 | 2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-03-01 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-02 | 2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-02 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-02 | 2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-03 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-03 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-03 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-04 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-04 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-04 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-04 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-05 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-05 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-05 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-06 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-06 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-06 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-06 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-07 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-07 | 2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-07 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-07 | 2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-09 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-09 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-10 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-10 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-10 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-11 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-11 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-11 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-11 | 2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-12 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-12 | 2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-12 | 2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-12 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-13 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-13 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-13 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-13 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-14 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-14 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-14 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-15 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-15 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-15 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-16 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-16 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-16 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-17 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-17 | 2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-17 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-17 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-18 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-18 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-18 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-19 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-19 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-19 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-19 | 2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-20 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-20 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-20 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-20 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-20 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-21 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-21 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-21 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-21 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-21 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-22 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-22 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-22 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-22 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-22 | 2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-23 | 2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-23 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-23 | 2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-23 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-24 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-24 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-24 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-24 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-25 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-25 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-25 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-25 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-26 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-26 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-26 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-26 | 2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-27 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-27 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-27 | 2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-27 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-28 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-28 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-28 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-28 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-29 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-29 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-29 | 2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-29 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-30 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-30 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-30 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-30 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-31 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-31 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-03-31 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-01 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-04-01 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-01 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-02 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-02 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-02 | 2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-04-03 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-03 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-03 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-04 | 2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-04-04 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-04 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-04 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-05 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-05 | 2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-05 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-05 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-06 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-07 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-07 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-07 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-08 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-08 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-08 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-09 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-09 | 2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-09 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-09 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-10 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-10 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-10 | 2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-04-11 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-11 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-11 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-12 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-12 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-12 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-12 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-13 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-13 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-13 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-13 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-14 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-14 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-14 | 2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-14 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-14 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-15 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-15 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-15 | 2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-16 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-16 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-16 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-17 | 2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-17 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-17 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-17 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-18 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-18 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-18 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-19 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-19 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-19 | 2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-20 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-20 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-20 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-20 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-21 | 2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-21 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-21 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-21 | 2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-22 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-22 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-23 | 2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-23 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-24 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-25 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-25 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-26 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-26 | 2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-26 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-27 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-27 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-27 | 2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-28 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-28 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-29 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-29 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-29 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-30 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-04-30 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-04-30 | 2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-05-01 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-01 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-02 | 2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-02 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-02 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-03 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-03 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-03 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-03 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-04 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-04 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-04 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-04 | 2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-05 | 2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-05 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-05 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-06 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-06 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-06 | 2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-07 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-07 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-08 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-08 | 2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-05-08 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-08 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-09 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-09 | 2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-09 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-10 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-10 | 2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-10 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-11 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-11 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-11 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-11 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-11 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-12 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-12 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-12 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-12 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-12 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-12 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-13 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-13 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-13 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-13 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-13 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-13 | 2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-14 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-14 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-14 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-14 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-14 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-15 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-15 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-15 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-15 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-15 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-16 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-16 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-16 | 2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-16 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-16 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-16 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-17 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-17 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-17 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-17 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-17 | 2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-18 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-18 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-18 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-18 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-19 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-19 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-19 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-19 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-19 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-20 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-20 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-20 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-20 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-20 | 2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-21 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-21 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-21 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-21 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-22 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-22 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-22 | 2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-22 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-22 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-23 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-23 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-23 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-23 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-24 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-24 | 2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-24 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-24 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-25 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-25 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-25 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-26 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-26 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-26 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-27 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-27 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-27 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-28 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-28 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-28 | 2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-29 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-29 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-30 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-30 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-30 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-31 | 2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-31 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-05-31 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-01 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-02 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-02 | 2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-03 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-04 | 2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-04 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-05 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-05 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-05 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-06 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-06 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-07 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-07 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-07 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-08 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-08 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-08 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-09 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-09 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-09 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-09 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-10 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-10 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-10 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-10 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-11 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-11 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-11 | 2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-12 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-12 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-12 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-13 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-13 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-13 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-14 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-14 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-14 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-15 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-15 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-15 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-16 | 2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-16 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-16 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-17 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-17 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-18 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-18 | 2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-19 | 2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-20 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-20 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-21 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-21 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-22 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-22 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-23 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-23 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-24 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-24 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-24 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-24 | 2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-25 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-25 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-25 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-26 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-26 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-26 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-26 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-26 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-27 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-27 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-27 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-27 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-27 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-28 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-28 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-28 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-28 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-28 | 2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-29 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-29 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-29 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-29 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-30 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-30 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-30 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-30 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-06-30 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-01 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-01 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-01 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-01 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-01 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-02 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-02 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-02 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-02 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-02 | 2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-07-03 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-03 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-03 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-03 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-07-04 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-04 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-04 | 2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-07-04 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-04 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-05 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-05 | 2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-07-05 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-05 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-05 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-06 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-06 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-06 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-06 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-06 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-07 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-07 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-07 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-07 | 2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-07 | 2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-08 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-08 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-08 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-08 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-09 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-09 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-09 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-09 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-10 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-10 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-10 | 2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
2025-07-10 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-11 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-11 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-11 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-11 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-12 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-12 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-12 | 2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
2025-07-12 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-12 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-13 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-13 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-13 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-13 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-14 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-14 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-14 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-14 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-14 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-14 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-15 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-15 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-15 | 2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-15 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-15 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-15 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-15 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-16 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-16 | 2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-16 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-16 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-16 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-16 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-16 | 2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-17 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-17 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-17 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-17 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-17 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-17 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-18 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-18 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-18 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-18 | 2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-18 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-18 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-18 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-19 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-19 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-19 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-19 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-19 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-19 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-20 | 2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-20 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-20 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-20 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-20 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-20 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-20 | 2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-21 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-21 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-21 | 2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-21 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-21 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-22 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-22 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-22 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-22 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-22 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-23 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-23 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-23 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-23 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-23 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-23 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-23 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-24 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-24 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-24 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-24 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-24 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-24 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-24 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-25 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-25 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-25 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-25 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-25 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-25 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-25 | 2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-26 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-26 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-26 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-26 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-26 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-26 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-27 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-27 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-27 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-27 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-27 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-27 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-27 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-28 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-28 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-28 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-28 | 2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-28 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-28 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-28 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-29 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-29 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-29 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-29 | 2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-29 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-29 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-30 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-30 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-30 | 2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-30 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-30 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-30 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-31 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-07-31 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-07-31 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-31 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-31 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-31 | 2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-08-01 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-01 | 2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-08-01 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-01 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-01 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-02 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-02 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-02 | 2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-08-02 | 2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-08-02 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-03 | 2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-03 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-03 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-03 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-04 | 2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-04 | 2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-08-04 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-04 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-05 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-05 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-05 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-06 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-06 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-06 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-06 | 2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-07 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-07 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-07 | 2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-07 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-08 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-08 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-08 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-09 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-09 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-09 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-09 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-09 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-10 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-10 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-10 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-10 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-10 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-11 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-11 | 2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-11 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-11 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-11 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-12 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-12 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-12 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-12 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-12 | 2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-13 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-13 | 2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-13 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-13 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-14 | 2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-14 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-14 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-14 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-14 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-15 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-15 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-15 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-15 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-16 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-16 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-16 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-16 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-17 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-17 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-17 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-17 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-17 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-18 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-18 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-18 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-18 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-18 | 2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-19 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-19 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-19 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-19 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-20 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-20 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-20 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-20 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-20 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-21 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-21 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-21 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-21 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-21 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-21 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-22 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-22 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-22 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-22 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-22 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-22 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-23 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-23 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-23 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-23 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-23 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-24 | 2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-24 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-24 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-24 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-24 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-24 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-24 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-25 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-25 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-25 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-25 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-25 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-25 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-26 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-26 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-26 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-26 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-26 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-26 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-26 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-27 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-27 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-27 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-27 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-27 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-27 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-27 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-28 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-28 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-28 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-28 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-28 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-28 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-28 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-29 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-29 | 2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-29 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-29 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-29 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-29 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-29 | 2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-30 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-30 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-30 | 2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-30 | 2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-30 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-30 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-31 | 2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-08-31 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-08-31 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-08-31 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-08-31 | 2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-09-01 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-01 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-01 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-01 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-02 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-02 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-02 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-02 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-02 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-02 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-03 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-03 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-03 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-03 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-03 | 2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-03 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-04 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-04 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-04 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-04 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-04 | 2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-09-05 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-05 | 2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-05 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-05 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-05 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-06 | 2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-09-06 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-06 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-06 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-06 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-06 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-07 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-07 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-07 | 2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-07 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-07 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-07 | 2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-08 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-08 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-08 | 2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-09-08 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-09 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-09 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-09 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-09 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-10 | 2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-10 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-10 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-10 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-11 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-11 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-11 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-11 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-12 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-12 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-12 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-12 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-13 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-13 | 2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-13 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-13 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-13 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-14 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-14 | 2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-14 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-15 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-15 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-15 | 2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-15 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-16 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-16 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-16 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-16 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-17 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-17 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-17 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-17 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-18 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-18 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-18 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-18 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-19 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-19 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-19 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-19 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-20 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-20 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-20 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-20 | 2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-21 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-21 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-21 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-22 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-22 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-22 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-22 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-23 | 2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-23 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-23 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-23 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-23 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-24 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-24 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-24 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-24 | 2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-24 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-25 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-25 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-25 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-25 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-26 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-26 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-26 | 2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-26 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-27 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-27 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-27 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-28 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-28 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-28 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-29 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-29 | 2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-29 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-29 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-30 | 2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-30 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-30 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-01 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-01 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-02 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-02 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-03 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-03 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-04 | 2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-10-04 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-05 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-10-06 | 2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-01-14 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-15 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-16 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-17 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-18 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-19 | 2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-22 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-23 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-25 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-26 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-28 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-29 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-30 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-01-31 | 2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-02 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-03 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-04 | 2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-06 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-07 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-08 | 2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-10 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-11 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-12 | 2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-14 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-15 | 2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-18 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-19 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-20 | 2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-22 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-23 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-24 | 2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-02 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-03 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-04 | 2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-07 | 2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-07 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-08 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-08 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-09 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-09 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-10 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-10 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-11 | 2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-12 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-12 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-13 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-13 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-13 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-14 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-14 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-14 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-15 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-15 | 2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-16 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-16 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-16 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-17 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-17 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-17 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-18 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-18 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-18 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-19 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-19 | 2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-20 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-20 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-21 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-21 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-22 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-23 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-23 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-24 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-24 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-25 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-25 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-26 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-27 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-27 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-28 | 2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-28 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-28 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-29 | 2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-29 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-03-31 | 2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-31 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-31 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-01 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-01 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-01 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-02 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-02 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-02 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-02 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-03 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-03 | 2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-04-03 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-03 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-04 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-04 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-04 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-05 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-05 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-05 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-06 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-06 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-07 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-07 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-07 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-08 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-08 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-09 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-09 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-09 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-10 | 2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-10 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-10 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-11 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-11 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-11 | 2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-12 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-12 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-13 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-13 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-13 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-13 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-14 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-14 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-14 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-14 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-15 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-15 | 2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-15 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-16 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-16 | 2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-04-16 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-16 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-17 | 2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-17 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-17 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-18 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-18 | 2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-18 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-19 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-19 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-20 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-20 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-21 | 2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-21 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-22 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-22 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-22 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-22 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-23 | 2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-23 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-23 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-23 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-23 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-24 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-24 | 2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-24 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-24 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-24 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-25 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-25 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-25 | 2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-25 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-26 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-26 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-26 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-26 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-27 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-27 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-27 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-27 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-27 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-28 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-28 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-28 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-28 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-28 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-29 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-29 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-29 | 2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-29 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-29 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-30 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-30 | 2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-30 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-04-30 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-01 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-01 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-01 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-01 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-02 | 2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-05-02 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-05-02 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-03 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-03 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-03 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-04 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-04 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-04 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-05 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-05 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-05 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-06 | 2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-06 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-06 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-06 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-07 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-07 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-07 | 2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-07 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-08 | 2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-08 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-09 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-09 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-09 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-09 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-10 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-10 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-10 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-10 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-11 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-11 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-11 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-11 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-12 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-12 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-12 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-13 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-13 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-13 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-14 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-14 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-14 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-14 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-15 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-15 | 2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-15 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-15 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-15 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-16 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-16 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-16 | 2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-16 | 2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-16 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-17 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-17 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-17 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-17 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-17 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-18 | 2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-18 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-18 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-18 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-18 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-18 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-19 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-19 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-19 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-19 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-19 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-20 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-20 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-20 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-20 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-20 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-20 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-21 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-21 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-21 | 2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-21 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-21 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-21 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-22 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-22 | 2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-22 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-22 | 2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-22 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-23 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-23 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-23 | 2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-23 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-24 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-24 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-24 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-24 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-24 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-25 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-25 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-25 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-25 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-25 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-25 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-26 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-26 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-26 | 2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-26 | 2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-26 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-26 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-27 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-27 | 2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-27 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-27 | 2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-28 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-28 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-28 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-28 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-29 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-29 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-29 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-29 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-29 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-30 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-30 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-30 | 2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-30 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-30 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-31 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-31 | 2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-31 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-05-31 | 2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-31 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-01 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-01 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-01 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-01 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-02 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-02 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-02 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-02 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-02 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-02 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-03 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-03 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-03 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-03 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-03 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-03 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-04 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-04 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-04 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-04 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-04 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-04 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-05 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-05 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-05 | 2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-05 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-05 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-05 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-06 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-06 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-06 | 2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-06 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-06 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-07 | 2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-06-07 | 2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-07 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-07 | 2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-06-07 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-08 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-08 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-08 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-09 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-09 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-09 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-09 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-09 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-10 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-10 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-10 | 2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-10 | 2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-10 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-11 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-11 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-11 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-12 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-12 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-12 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-12 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-12 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-13 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-13 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-13 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-13 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-13 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-14 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-14 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-14 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-14 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-14 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-15 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-15 | 2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-15 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-15 | 2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-15 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-16 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-16 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-16 | 2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-16 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-17 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-17 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-17 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-18 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-18 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-18 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-18 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-19 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-19 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-19 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-19 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-20 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-20 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-20 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-20 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-21 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-21 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-21 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-21 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-22 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-22 | 2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-22 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-22 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-23 | 2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-23 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-23 | 2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-06-24 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-24 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-25 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-25 | 2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-26 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-26 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-27 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-27 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-28 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-28 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-28 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-29 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-29 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-29 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-30 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-30 | 2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-30 | 2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-06-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-01 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-01 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-02 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-02 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-02 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-03 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-03 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-03 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-04 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-04 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-04 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-05 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-05 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-05 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-06 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-06 | 2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-06 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-07 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-07 | 2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-07 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-07 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-08 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-08 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-08 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-09 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-09 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-09 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-09 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-10 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-10 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-10 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-10 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-11 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-11 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-11 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-11 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-12 | 2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-07-12 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-12 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-12 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-13 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-13 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-13 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-14 | 2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-14 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-14 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-15 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-15 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-15 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-16 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-16 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-16 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-17 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-17 | 2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-17 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-18 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-18 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-19 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-19 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-19 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-20 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-20 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-20 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-21 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-21 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-21 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-22 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-22 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-22 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-23 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-23 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-23 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-24 | 2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-24 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-24 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-25 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-25 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-26 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-26 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-26 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-27 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-27 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-27 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-28 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-28 | 2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-28 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-29 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-29 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-30 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-30 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-07-31 | 2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-07-31 | 2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-08-01 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-02 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-03 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-04 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-05 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-05 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-05 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-06 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-06 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-06 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-07 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-07 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-07 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-08 | 2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-08 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-08 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-09 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-09 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-09 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-10 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-10 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-10 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-11 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-11 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-11 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-12 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-12 | 2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-12 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-12 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-13 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-13 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-13 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-13 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-14 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-14 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-14 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-14 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-15 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-15 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-15 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-15 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-16 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-16 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-16 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-16 | 2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-17 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-17 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-17 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-18 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-18 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-18 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-18 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-19 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-19 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-19 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-19 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-19 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-20 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-20 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-20 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-20 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-20 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-21 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-21 | 2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-21 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-21 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-21 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-22 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-22 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-22 | 2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-22 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-22 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-23 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-23 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-23 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-23 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-23 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-24 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-24 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-24 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-24 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-24 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-25 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-25 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-25 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-25 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-25 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-26 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-26 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-26 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-26 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-26 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-26 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-26 | 2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-27 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-27 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-27 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-27 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-27 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-27 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-28 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-28 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-28 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-28 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-28 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-28 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-28 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-29 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-29 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-29 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-29 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-29 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-29 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-29 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-30 | 2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-30 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-30 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-30 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-30 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-30 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-30 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-31 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-31 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-31 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-31 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-31 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-31 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-01 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-01 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-01 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-01 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-01 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-01 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-02 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-02 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-02 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-02 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-02 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-02 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-02 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-03 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-03 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-03 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-03 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-03 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-03 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-03 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-04 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-04 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-04 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-04 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-04 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-04 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-04 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-05 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-05 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-05 | 2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-09-05 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-05 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-05 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-05 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-06 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-06 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-06 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-06 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-06 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-06 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-09-07 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-07 | 2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-07 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-07 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-07 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-07 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-08 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-08 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-08 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-08 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-08 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-08 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-09 | 2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-09-09 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-09 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-09 | 2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-09-09 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-09 | 2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-09 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-10 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-10 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-10 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-10 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-11 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-11 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-11 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-09-11 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-11 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-11 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-11 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-11 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-12 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-12 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-12 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-12 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-12 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-12 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-12 | 2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-09-12 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-12 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-13 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-13 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-13 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-13 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-13 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-13 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-13 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-13 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-13 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-14 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-14 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-14 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-14 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-14 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-14 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-14 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-14 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-14 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-14 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-15 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-15 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-15 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-15 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-15 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-15 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-15 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-15 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-15 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-15 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-15 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-15 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-16 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-16 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-16 | 2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-16 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-16 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-16 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-16 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-16 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-16 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-16 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-16 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-16 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-17 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-17 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-17 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-17 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-17 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-17 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-17 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-17 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-17 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-17 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-17 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-18 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-18 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-18 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-18 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-18 | 2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-18 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-18 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-18 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-18 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-18 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-18 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-18 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-19 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-19 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-19 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-19 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-19 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-19 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-19 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-19 | 2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-19 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-19 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-19 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-19 | 2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-20 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-20 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-20 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-20 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-20 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-20 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-20 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-20 | 2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-20 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-20 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-20 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-21 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-21 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-21 | 2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-21 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-21 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-21 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-21 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-21 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-21 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-21 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-21 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-22 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-22 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-22 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-22 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-22 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-22 | 2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-22 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-22 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-22 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-22 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-22 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-23 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-23 | 2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-23 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-23 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-23 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-23 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-23 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-23 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-23 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-23 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-24 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-24 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-24 | 2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-24 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-24 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-24 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-24 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-24 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-24 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-24 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-25 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-25 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-25 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-25 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-25 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-25 | 2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-25 | 2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-25 | 2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-25 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-26 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-26 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-26 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-26 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-26 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-26 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-26 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-26 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-27 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-27 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-27 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-27 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-27 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-27 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-27 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-27 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-27 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-27 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-27 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-28 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-28 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-28 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-28 | 2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-28 | 2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-28 | 2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-28 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-28 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-28 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-28 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-28 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-29 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-29 | 2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-29 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-29 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-29 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-29 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-29 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-29 | 2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-30 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-30 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-09-30 | 2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-30 | 2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-30 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-09-30 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-30 | 2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-10-01 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-01 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-01 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-02 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-02 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-02 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-03 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-03 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-03 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-04 | 2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-10-04 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-04 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-05 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-05 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-06 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-06 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-07 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-07 | 2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-10-08 | 2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2023-09-30 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-01 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-02 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-03 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-04 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-05 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-06 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-07 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-08 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-09 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-10 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-11 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-12 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-13 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-14 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-15 | 2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-17 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-18 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-19 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-20 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-21 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-22 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-23 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-24 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-25 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-26 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-27 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-28 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-10-29 | 2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2023-11-01 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-02 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-03 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-04 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-05 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-06 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-07 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-08 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-09 | 2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2023-11-11 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-12 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-13 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-14 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-15 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-16 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-17 | 2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2023-11-19 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-20 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-21 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-22 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-23 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-24 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-25 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-26 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-27 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-28 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-29 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-11-30 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-01 | 2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2023-12-02 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-03 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-04 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-05 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-06 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-07 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-08 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-09 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-10 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-11 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-12 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-13 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-14 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2023-12-15 | 2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2024-01-04 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-05 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-06 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-07 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-08 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-09 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-10 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-11 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-12 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-13 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-14 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-15 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-16 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-17 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-18 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-19 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-20 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-21 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-22 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-23 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-24 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-25 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-26 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-27 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2024-01-28 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-29 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-30 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-01-31 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-01 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-02 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-03 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-04 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-04 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-05 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-05 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-05 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-06 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-06 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-06 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-07 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-07 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-07 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-08 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-08 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-08 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-09 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-09 | 2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-09 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-10 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-10 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-11 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-11 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-12 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-12 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-13 | 2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-02-13 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-13 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-14 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-14 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-15 | 2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-02-15 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-16 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-16 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-17 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-17 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-18 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-18 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-19 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-19 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-20 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-20 | 2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-02-20 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-21 | 2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2024-02-21 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-21 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-22 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-22 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-23 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-23 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-24 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-24 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-25 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-25 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-26 | 2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-02-26 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-27 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-27 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-27 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-28 | 2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-02-28 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-28 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-02-29 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-29 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-01 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-01 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-02 | 2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-03-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-03 | 2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-03-03 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-04 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-05 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-06 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-07 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-08 | 2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-09 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-10 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-11 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-12 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-12 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-13 | 2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325 | 133A/1 | Completed
2024-03-13 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-14 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-15 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-16 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-17 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-18 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-19 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-20 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-21 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-22 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-23 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-24 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-25 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-26 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-27 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-28 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-29 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-30 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-03-31 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-01 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-02 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-03 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-04 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-05 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-06 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-07 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-08 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-09 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-10 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-11 | 2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2024-04-13 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-14 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-15 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-16 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-17 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-18 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-19 | 2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-04-20 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-21 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-22 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-23 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-24 | 2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-04-25 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-26 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-27 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-28 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-29 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-04-30 | 2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-05-01 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-02 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-03 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-03 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-04 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-04 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-05 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-05 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-06 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-06 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-07 | 2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-07 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-08 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-08 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-08 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-09 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-09 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-09 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-10 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-10 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-10 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-11 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-11 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-11 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-12 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-12 | 2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-12 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-13 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-13 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-14 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-14 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-15 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-15 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-16 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-16 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-17 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-17 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-18 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2024-05-18 | 2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2024-05-19 | 2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2024-05-19 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-19 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-20 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-20 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-21 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-21 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-22 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-22 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-23 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-23 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-24 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-05-24 | 2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-25 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-25 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-26 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-26 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-27 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-27 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-28 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-28 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-29 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-29 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-30 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-30 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-05-31 | 2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-31 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-05-31 | 2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-01 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-02 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-03 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-04 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-05 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-05 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-06 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-06 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-07 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-07 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-08 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-08 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-09 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-09 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-10 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-06-10 | 2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2024-06-11 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-11 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-12 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-12 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-12 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-06-13 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-13 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-14 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-14 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-14 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-14 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-15 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-15 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-15 | 2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-15 | 2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-16 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-16 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-17 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-17 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-17 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-18 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-18 | 2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-06-18 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-19 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-19 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-20 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-20 | 2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-21 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-22 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-22 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-23 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-23 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-24 | 2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-06-24 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-25 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-25 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-26 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-26 | 2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-06-27 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-28 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-29 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-30 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-01 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-01 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-02 | 2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-07-02 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-02 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-03 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-03 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-04 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-04 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-05 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-05 | 2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-07-06 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-07 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-08 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-08 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-09 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-09 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-09 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-10 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-10 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-10 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-11 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-11 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-11 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-12 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-12 | 2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-12 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-13 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-13 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-13 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-14 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-14 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-14 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-15 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-15 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-15 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-16 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-16 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-16 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-17 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-17 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-17 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-18 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-18 | 2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-07-18 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-19 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-19 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-19 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-20 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-20 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-20 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-20 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-21 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-21 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-21 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-21 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-22 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-22 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-22 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-22 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-23 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-23 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-23 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-23 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-23 | 2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2024-07-24 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-24 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-24 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-24 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-25 | 2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-07-25 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-25 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-25 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-26 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-26 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-26 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-27 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-27 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-27 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-28 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-28 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-28 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-28 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-28 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-29 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-29 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-29 | 2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-07-29 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-29 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-30 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-30 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-30 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-30 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-30 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-07-31 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-31 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-07-31 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-07-31 | 2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-07-31 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-01 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-01 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-01 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-01 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-01 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-02 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-02 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-02 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-02 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-02 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-03 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-03 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-03 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-03 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-03 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-04 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-04 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-04 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-04 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-04 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-05 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-05 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-05 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-05 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-05 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-06 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-06 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-06 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-06 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-06 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-07 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-07 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-07 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-07 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-07 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-08 | 2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-08-08 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-08 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-08 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-08 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-08 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-09 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-09 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-09 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-09 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-09 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-10 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-10 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-10 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-10 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-10 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-11 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-11 | 2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-08-11 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-11 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-11 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-11 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-12 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-12 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-12 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-12 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-12 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-13 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-13 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-13 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-13 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-13 | 2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2024-08-14 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-14 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-14 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-14 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-14 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-15 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-15 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-15 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-15 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-15 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-16 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-16 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-16 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-16 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-16 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-17 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-17 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-17 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-17 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-17 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-18 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-18 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-18 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-18 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-18 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-19 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-19 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-19 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-19 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-19 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-19 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-20 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-20 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-20 | 2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-08-20 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-20 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-20 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-21 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-21 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-21 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-21 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-21 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-21 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-22 | 2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-22 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-22 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-22 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-22 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-22 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-23 | 2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-23 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-23 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-23 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-23 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-24 | 2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-08-24 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-24 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-24 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-25 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-25 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-25 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-26 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-26 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-26 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-27 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-27 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-27 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-28 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-28 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-28 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-29 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-08-29 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-29 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-29 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-30 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-08-30 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-30 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-30 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-30 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-08-31 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-08-31 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-08-31 | 2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-08-31 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-08-31 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-01 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-01 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-01 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-01 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-02 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-02 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-02 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-02 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-02 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-03 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-03 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-03 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-03 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-03 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-04 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-04 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-04 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-04 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-04 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-05 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-05 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-05 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-05 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-05 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-06 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-06 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-06 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-06 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-06 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-07 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-07 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-07 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-07 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-07 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-08 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-08 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-08 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-08 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-08 | 2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2024-09-09 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-09 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-09 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-09 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-09 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-09 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-10 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-10 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-10 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-10 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-10 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-10 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-10 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-11 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-11 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-11 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-11 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-11 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-11 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-12 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-12 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-12 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-12 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-12 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-12 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-12 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-13 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-13 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-13 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-13 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-13 | 2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-13 | 2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-09-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-13 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-14 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-14 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-14 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-14 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-14 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-14 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-14 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-15 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-15 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-15 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-15 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-15 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-15 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-15 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-16 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-16 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-16 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-16 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-16 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-16 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-16 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-16 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-16 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-17 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-17 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-17 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-17 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-17 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-17 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-17 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-17 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-17 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-18 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-18 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-18 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-18 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-18 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-18 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-18 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-18 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-18 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-19 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-19 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-19 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-19 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-19 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-19 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-19 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-19 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-19 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-20 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-20 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-20 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-20 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-20 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-20 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-20 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-20 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-20 | 2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-09-21 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-21 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-21 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-21 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-21 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-21 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-21 | 2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-09-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-21 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-21 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-22 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-22 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-22 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-22 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-22 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-22 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-22 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-22 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-23 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-23 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-23 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-23 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-23 | 2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2024-09-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-23 | 2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-09-23 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-23 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-23 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-23 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-24 | 2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-24 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-24 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-24 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-24 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-24 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-24 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-24 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-25 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-25 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-25 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-25 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-25 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-25 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-25 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-25 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-26 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-26 | 2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-26 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-26 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-26 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-26 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-26 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-26 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-26 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-27 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-27 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-27 | 2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-09-27 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-27 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-27 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-27 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-27 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-27 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-28 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-28 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-28 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-28 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-28 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-28 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-28 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-28 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-28 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-29 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-29 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-29 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-29 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-29 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-29 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-29 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-29 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-29 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-29 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-09-30 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-09-30 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-09-30 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-09-30 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-09-30 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-09-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-09-30 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-30 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-09-30 | 2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-09-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-09-30 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-09-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-01 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-01 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-01 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-01 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-01 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-01 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-01 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-01 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-01 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-01 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-01 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-01 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-02 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-02 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-02 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-02 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-02 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-02 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-02 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-02 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-02 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-02 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-02 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-02 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-03 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-03 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-03 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-03 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-03 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-03 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-03 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-03 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-03 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-03 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-03 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-03 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-04 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-04 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-04 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-04 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-04 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-04 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-04 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-04 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-04 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-04 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-04 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-04 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-04 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-05 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-05 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-05 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-05 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-05 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-05 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-05 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-05 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-05 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-05 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-05 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-05 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-05 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-06 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-06 | 2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-06 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-06 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-06 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-06 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-06 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-06 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-06 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-06 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-06 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-06 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-06 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-07 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-07 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-07 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-07 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-07 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-07 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-07 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-07 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-07 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-07 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-07 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-07 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-08 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-08 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-08 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-08 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-08 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-08 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-08 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-08 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-08 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-08 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-08 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-08 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-08 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-08 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-09 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-09 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-09 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-09 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-09 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-09 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-09 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-09 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-09 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-09 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-09 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-09 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-09 | 2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-09 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-10 | 2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-10 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-10 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-10 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-10 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-10 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-10 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-10 | 2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-10 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-10 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-10 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-10 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-10 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-10 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-11 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-11 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-11 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-11 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-11 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-11 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-11 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-11 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-11 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-11 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-11 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-11 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-12 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-12 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-12 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-12 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-12 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-12 | 2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-10-12 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-12 | 2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-10-12 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-12 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-12 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-12 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-13 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-13 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-13 | 2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-10-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-13 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-13 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-13 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-13 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-13 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-13 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-13 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-13 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-14 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-14 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-14 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-14 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-14 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-14 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-14 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-14 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-14 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-14 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-15 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-15 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-15 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-15 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-15 | 2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-10-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-15 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-15 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-15 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-15 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-15 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-15 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-16 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-16 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-16 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-16 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-16 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-16 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-16 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-16 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-16 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-16 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-17 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-17 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-17 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-17 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-17 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-17 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-17 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-17 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-17 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-17 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-17 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-17 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-18 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-18 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-18 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-18 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-18 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-18 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-18 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-18 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-18 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-18 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-18 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-18 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-19 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-19 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-19 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-19 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-19 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-19 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-19 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-19 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-19 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-19 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-19 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-19 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-20 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-20 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-20 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-20 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-20 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-20 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-20 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-20 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-20 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-20 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-20 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-20 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-21 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-21 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-21 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-21 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-21 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-21 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-21 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-21 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-21 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-21 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-21 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-21 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-22 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-22 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-22 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-22 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-22 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-22 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-22 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-22 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-22 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-22 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-22 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-22 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-23 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-23 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-23 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-23 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-23 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-23 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-23 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-23 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-23 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-23 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-23 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-23 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-23 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-24 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-24 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-24 | 2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-10-24 | 2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-10-24 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-24 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-24 | 2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-10-24 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-24 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-24 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-24 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-24 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-24 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-25 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-25 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-25 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-25 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-25 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-25 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-25 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-25 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-25 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-25 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-25 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-25 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-26 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-26 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-26 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-26 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-26 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-26 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-26 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-26 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-26 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-26 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-26 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-26 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-27 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-27 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-27 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-27 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-27 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-27 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-27 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-27 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-27 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-27 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-27 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-27 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-28 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-28 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-28 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-28 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-28 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-28 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-28 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-28 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-28 | 2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2024-10-28 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-28 | 2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2024-10-28 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-29 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-29 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-29 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-29 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-29 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-29 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-29 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-29 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-29 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-29 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-29 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-10-30 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-30 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-30 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-30 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-30 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-30 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-30 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-30 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-30 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-30 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-30 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-10-30 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-30 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-10-31 | 2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-10-31 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-10-31 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-10-31 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-10-31 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-10-31 | 2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-31 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-10-31 | 2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-10-31 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-10-31 | 2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-10-31 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-31 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-10-31 | 2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-10-31 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-01 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-01 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-01 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-01 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-01 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-01 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-01 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-01 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-02 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-02 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-02 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-02 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-02 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-02 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-02 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-02 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-02 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-02 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-03 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-03 | 2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-03 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-03 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-03 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-03 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-03 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-03 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-03 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-03 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-04 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-04 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-04 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-04 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-04 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-04 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-04 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-04 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-04 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-04 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-05 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-05 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-05 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-05 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-05 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-05 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-05 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-05 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-05 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-05 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-05 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-06 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-06 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-06 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-06 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-06 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-06 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-06 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-06 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-06 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-06 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-06 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-07 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-07 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-07 | 2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-11-07 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-07 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-07 | 2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2024-11-07 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-07 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-07 | 2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-11-07 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-07 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-08 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-08 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-08 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-08 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-08 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-08 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-08 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-08 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-09 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-09 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-09 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-09 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-09 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-09 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-09 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-09 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-09 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-10 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-10 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-10 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-10 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-10 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-10 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-10 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-10 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-10 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-10 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-11 | 2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-11 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-11 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-11 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-11 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-11 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-11 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-11 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-11 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-11 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-12 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-12 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-12 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-12 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-12 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-12 | 2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-12 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-12 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-12 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-12 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-13 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-13 | 2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-11-13 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-13 | 2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-11-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-13 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-13 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-13 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-13 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-13 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-14 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-14 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-14 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-14 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-14 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-14 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-14 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-14 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-15 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-15 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-15 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-15 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-15 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-15 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-15 | 2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2024-11-15 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-16 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-16 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-16 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-16 | 2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-11-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-16 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-16 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-16 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-16 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-16 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-16 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-16 | 2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-17 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-17 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-17 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-17 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-17 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-17 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-17 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-17 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-17 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-17 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-17 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-18 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-18 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-18 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-18 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-18 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-18 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-18 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-18 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-18 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-18 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-18 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-18 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-19 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-19 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-19 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-19 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-19 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-19 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-19 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-19 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-19 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-19 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-19 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-19 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-20 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-20 | 2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2024-11-20 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-20 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-20 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-20 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-20 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-20 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-20 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-20 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-20 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-20 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-20 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-20 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-21 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-21 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-21 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-21 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-21 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-21 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-21 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-21 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-21 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-21 | 2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-21 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-21 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-21 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-22 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-22 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-22 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-22 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-22 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-22 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-22 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-22 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-22 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-22 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-22 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-22 | 2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2024-11-22 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-22 | 2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-22 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-22 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-23 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-23 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-23 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-23 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-23 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-23 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-23 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-23 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-23 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-23 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-23 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-23 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-23 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-23 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-23 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-24 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-24 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-24 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-24 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-24 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-24 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-24 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-24 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-24 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-24 | 2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-24 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-24 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-24 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-24 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-24 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-24 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-25 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-25 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-25 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-25 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-25 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-25 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-25 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-25 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-25 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-25 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-25 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-25 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-25 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-25 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-25 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-26 | 2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-11-26 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-26 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-26 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-26 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-26 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-26 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-26 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-26 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-26 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-26 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-26 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-26 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-26 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-26 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-27 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-27 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-27 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-27 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-27 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-27 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-27 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-27 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-27 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-27 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-27 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-27 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-27 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-27 | 2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-27 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-28 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-28 | 2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-28 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-28 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-28 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-28 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-28 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-28 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-28 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-28 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-28 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-28 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-28 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-28 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-28 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-29 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-29 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-11-29 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-29 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-29 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-29 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-29 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-29 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-29 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-29 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-29 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-29 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-29 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-29 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-29 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-30 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-11-30 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-11-30 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-11-30 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-11-30 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-30 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-11-30 | 2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2024-11-30 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-11-30 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-11-30 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-11-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-30 | 2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-30 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-11-30 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-11-30 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-11-30 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-11-30 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-01 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-01 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-01 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-01 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-01 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-01 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-01 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-12-01 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-01 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-01 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-01 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-01 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-01 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-12-01 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-01 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-02 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-02 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-02 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-02 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-02 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-02 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-02 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-02 | 2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-12-02 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-02 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-02 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-02 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-02 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-02 | 2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2024-12-02 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-02 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-03 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-03 | 2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-12-03 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-03 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-03 | 2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-12-03 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-03 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-03 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-03 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-03 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-03 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-03 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-03 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-03 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-03 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-03 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-03 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-04 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-04 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-04 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-04 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-04 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-04 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-04 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-04 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-04 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-04 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-04 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-04 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-04 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-04 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-04 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-04 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-05 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-05 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-05 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-05 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-05 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-05 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-05 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-05 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-05 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-05 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-05 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-05 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-05 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-05 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-05 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-05 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-06 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-06 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-06 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-06 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-06 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-06 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-06 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-06 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-06 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-06 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-06 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-06 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-06 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-06 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-06 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-06 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-12-07 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-07 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-07 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-07 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-07 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-07 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-07 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-07 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-07 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-07 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-07 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-07 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-07 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-07 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-07 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-07 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-08 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-08 | 2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-08 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-08 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-08 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-08 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-08 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-08 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-08 | 2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-08 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-08 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-08 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-08 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-08 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-08 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-08 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-08 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-09 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-09 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-09 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-09 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-09 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-09 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-09 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-09 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-09 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-09 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-09 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-09 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-09 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-09 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-09 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-09 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-09 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-09 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-10 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-10 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-10 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-10 | 2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-12-10 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-10 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-10 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-10 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-10 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-10 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-10 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-10 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-10 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-10 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-10 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-10 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-10 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-10 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-10 | 2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-12-11 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-11 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-11 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-11 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-11 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-11 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-11 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-11 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-11 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-11 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-11 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-11 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-11 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-11 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-11 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-11 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-11 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-11 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-11 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-12 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-12 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-12 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-12 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-12 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-12 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-12 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-12 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-12 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-12 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-12 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-12 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-12 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-12 | 2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-12 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-12 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-12 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-12 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-12 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-13 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-13 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-13 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-13 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-13 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-13 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-13 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-13 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-13 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-13 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-13 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-13 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-13 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-13 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-13 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-13 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-13 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-13 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-14 | 2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-14 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-14 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-14 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-14 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-14 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-14 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-14 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-14 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-14 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-14 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-14 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-14 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-14 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-14 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-14 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-14 | 2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-14 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-14 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-15 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-15 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-15 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-15 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-15 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-15 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-15 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-15 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-15 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-15 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-15 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-15 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-15 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-15 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-15 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-15 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-15 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-16 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-16 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-16 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-16 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-16 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-16 | 2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2024-12-16 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-16 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-16 | 2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-16 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-16 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-16 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-16 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-16 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-16 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-16 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-16 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-17 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-17 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-17 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-17 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-17 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-17 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-17 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-17 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-17 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-17 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-17 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-17 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-17 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-17 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-17 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-17 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-18 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-18 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-18 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-18 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-18 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-18 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-18 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-18 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-18 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-18 | 2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2024-12-18 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-18 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-18 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-18 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-18 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-18 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-19 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-19 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-19 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-19 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-19 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-19 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-19 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-19 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-19 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-19 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-19 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-19 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-19 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-19 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-19 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-19 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-19 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-20 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-20 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-20 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-20 | 2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-12-20 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-20 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-20 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-20 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-20 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-20 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-20 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-20 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-20 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-20 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-20 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-20 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-20 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-21 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-21 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-21 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-21 | 2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-12-21 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-21 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-21 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-21 | 2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2024-12-21 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-21 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-21 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-21 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-21 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-21 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-21 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-21 | 2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2024-12-21 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-21 | 2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-21 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-21 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-22 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-22 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-22 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-22 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-22 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-22 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-22 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-22 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-22 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-22 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2024-12-22 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-22 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-22 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-22 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-22 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-22 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-22 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-22 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-22 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-23 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-23 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-23 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-23 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-23 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-23 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-23 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-23 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-23 | 2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-12-23 | 2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2024-12-23 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-23 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-23 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-23 | 2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-12-23 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-23 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-23 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-23 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-23 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-23 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-23 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-24 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-24 | 2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-12-24 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-24 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-24 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-24 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-24 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-24 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-24 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-24 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-24 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-24 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-24 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-24 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-24 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-24 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-24 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-24 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-24 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-25 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-25 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-25 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-25 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-25 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-25 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-25 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-25 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-25 | 2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-25 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-25 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-25 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-25 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-25 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-25 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-25 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-25 | 2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-12-25 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-26 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-26 | 2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2024-12-26 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-26 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-26 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-26 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-26 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-26 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-26 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-26 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-26 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-26 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-26 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-26 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-26 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-26 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-26 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-26 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-27 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-27 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-27 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-27 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-27 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-27 | 2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-12-27 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-27 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-27 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-27 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-27 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-27 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-27 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-27 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-27 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-27 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-27 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-27 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-28 | 2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-12-28 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-28 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-28 | 2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-28 | 2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2024-12-28 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-28 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-28 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-28 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-28 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-28 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-28 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-28 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-28 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-28 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-28 | 2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-28 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-28 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-28 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-28 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-29 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-29 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-29 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-29 | 2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2024-12-29 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-29 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-29 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-29 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-29 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-29 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-29 | 2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-12-29 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-29 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-29 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-29 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-29 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-30 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-30 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-30 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-30 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-30 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-30 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-30 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-30 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-30 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-30 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2024-12-30 | 2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-30 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-30 | 2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-12-30 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-30 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2024-12-31 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2024-12-31 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-12-31 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2024-12-31 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2024-12-31 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-12-31 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-12-31 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-12-31 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-12-31 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2024-12-31 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2024-12-31 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2024-12-31 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2024-12-31 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-31 | 2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-01 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-01 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-01 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-01 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-01 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2025-01-01 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-01 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-01 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-01 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-01 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-01 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-01 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-01 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-01 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-02 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-02 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-02 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-02 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-02 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-02 | 2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2025-01-02 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-02 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-02 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-02 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-02 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-02 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-02 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-02 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-02 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-03 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-03 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-03 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-03 | 2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-03 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-03 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-03 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-03 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-03 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-03 | 2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-01-03 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-03 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-03 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-03 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-03 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-04 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-04 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-04 | 2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-04 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-04 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-04 | 2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2025-01-04 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-04 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-04 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-04 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-04 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-04 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-04 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-04 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-05 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-05 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-05 | 2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-05 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-05 | 2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2025-01-05 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-05 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-05 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-05 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-05 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-05 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-05 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-06 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-06 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-06 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-06 | 2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-06 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-06 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-06 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-06 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-06 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-06 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-06 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-07 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-07 | 2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-07 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-07 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-07 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-07 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-07 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-07 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-07 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-07 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-07 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-07 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-08 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-08 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-08 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-08 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-08 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-08 | 2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2025-01-08 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-08 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-08 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-08 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-08 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-09 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-09 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-09 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-09 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-09 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-09 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-09 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-09 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-09 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-09 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-09 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-09 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-09 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-10 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-10 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-10 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-10 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-10 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-10 | 2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2025-01-10 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-10 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-10 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-10 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-10 | 2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-01-10 | 2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-10 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-10 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-10 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-10 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-11 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-11 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-11 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-11 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-11 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-11 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-11 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-11 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-11 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-11 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-11 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-11 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-11 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-11 | 2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2025-01-11 | 2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2025-01-12 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-12 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-12 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-12 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-12 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-12 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-12 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-12 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-12 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-12 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-12 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-12 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-12 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-12 | 2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2025-01-13 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-13 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-13 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-13 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-13 | 2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2025-01-13 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-13 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-13 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-13 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-13 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-13 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-13 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-13 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-13 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-13 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-13 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-14 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-14 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-14 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-14 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-14 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-14 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-14 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-14 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-14 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-14 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-14 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-14 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-14 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-14 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-14 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-15 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-15 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-15 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-15 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-15 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-15 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-15 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-15 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-15 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-15 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-15 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-15 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-15 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-15 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-15 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-16 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-16 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-16 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-16 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-16 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-16 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-16 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-16 | 2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2025-01-16 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-16 | 2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2025-01-16 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-16 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-16 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-16 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-16 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-16 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-16 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-17 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-17 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2025-01-17 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-17 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-17 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-17 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-17 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-17 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-17 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-17 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-17 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-17 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-17 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-17 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-17 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-17 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-17 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-18 | 2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2025-01-18 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-18 | 2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2025-01-18 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-18 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-18 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-18 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-18 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-18 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-18 | 2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2025-01-18 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-18 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-18 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-18 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-18 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-18 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-18 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-18 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-19 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-19 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-19 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-19 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-19 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-19 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-19 | 2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-01-19 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-19 | 2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2025-01-19 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-19 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-19 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-19 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-19 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-19 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-19 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-20 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-20 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-20 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-20 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-20 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-20 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-20 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-20 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-20 | 2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2025-01-20 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-20 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-20 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-20 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-20 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-20 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-21 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-21 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-21 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-21 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-21 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-21 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-21 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-21 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-21 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-21 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-21 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-21 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-21 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-21 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-21 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-21 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-21 | 2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-21 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-21 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-21 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-22 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-22 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-22 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-22 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-22 | 2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-22 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-22 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-22 | 2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-01-22 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-22 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-22 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-22 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-22 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-22 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-22 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-22 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-22 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-22 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-23 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-23 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-23 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-23 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-23 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-23 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-23 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-23 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-23 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-23 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-23 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-23 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-23 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2025-01-23 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-23 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-23 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-23 | 2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-01-24 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-24 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-24 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-24 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-24 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-24 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-24 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-24 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-24 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-24 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-24 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-24 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-24 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-24 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-24 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-24 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-24 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2025-01-25 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-25 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-25 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-25 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-25 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-25 | 2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-01-25 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-25 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-25 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-25 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-25 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-25 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-25 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-25 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-25 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-25 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-25 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-26 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-26 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-26 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-26 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-26 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-26 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-26 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-26 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-26 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-26 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-26 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-26 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-26 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-26 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-26 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-26 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-26 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-27 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-27 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-27 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-27 | 2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-27 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-27 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-27 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-27 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-27 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-27 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-27 | 2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-01-27 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-27 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-27 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-27 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-27 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-27 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-27 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-27 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-27 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-27 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-28 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-28 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-28 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-28 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-28 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-28 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-28 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-28 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-28 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-28 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-28 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-28 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-28 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-28 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-28 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-28 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-28 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-28 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-28 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-28 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-29 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-29 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-29 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-29 | 2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-29 | 2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-29 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-29 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-29 | 2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-29 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-29 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-29 | 2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-29 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-29 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-29 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-29 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-29 | 2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-01-29 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-29 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-29 | 2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-29 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-29 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-30 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-30 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-30 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-01-30 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-30 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-30 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-30 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-30 | 2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-30 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-30 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-30 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-30 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-30 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-30 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-30 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-31 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-01-31 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-31 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-01-31 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-01-31 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-01-31 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-01-31 | 2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-01-31 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-31 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-31 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-01-31 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-01-31 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-31 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-31 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-31 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-01 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-01 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-01 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-01 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-01 | 2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-02-01 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-01 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-01 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-01 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-01 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-01 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-01 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-01 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-01 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-01 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-01 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-01 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-02 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-02 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-02 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-02 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-02 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-02 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-02 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-02 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-02 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-02 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-02 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-02 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-02 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-02 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-02 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-02 | 2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-02-03 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-03 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-03 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-03 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-03 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-03 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-03 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-03 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-03 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-03 | 2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-02-03 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-03 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-03 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-03 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-03 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-03 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-03 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-04 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-04 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-02-04 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-04 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-04 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-04 | 2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-04 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-04 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-04 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-04 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-04 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-04 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-04 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-04 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-04 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-04 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-05 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-05 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-05 | 2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2025-02-05 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-05 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-05 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-05 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-05 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-05 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-05 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-05 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-05 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-05 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-05 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-05 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-05 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-05 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-06 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-06 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-06 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-06 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-06 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-06 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-06 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-06 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-06 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-06 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-06 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-06 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-06 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-06 | 2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-02-06 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-07 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-07 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-02-07 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-07 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-07 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-07 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-07 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-07 | 2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-02-07 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-07 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-07 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-07 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-07 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-07 | 2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-02-07 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-08 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-08 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-08 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-08 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-08 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-08 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-08 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-08 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-08 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-08 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-08 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-08 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-08 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-08 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-09 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-09 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-09 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-09 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-09 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-09 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-09 | 2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-09 | 2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-02-09 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-09 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-02-09 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-09 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-09 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-09 | 2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-02-09 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-09 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-10 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-10 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-10 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-10 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-10 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-10 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-10 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-10 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-10 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-10 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-10 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-10 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-10 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-10 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-11 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-11 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-11 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-11 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-11 | 2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-02-11 | 2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2025-02-11 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-11 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-11 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-11 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-11 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-11 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-11 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-11 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-11 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-11 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-12 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-12 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-12 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-12 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-12 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-12 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-12 | 2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-12 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-12 | 2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2025-02-12 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-12 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-12 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-12 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-12 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-12 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-13 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-13 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-13 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-13 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-13 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-13 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-13 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-13 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-13 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-13 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-13 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-13 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-13 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-13 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-13 | 2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-02-14 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-14 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-14 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-14 | 2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-14 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-14 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-14 | 2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-14 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-14 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-14 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-14 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-14 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-14 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-14 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-14 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-14 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-14 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-15 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-15 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-15 | 2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-15 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-15 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-15 | 2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2025-02-15 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-15 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-15 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-15 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-15 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-15 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-15 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-15 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-16 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-16 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-16 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-16 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-16 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-16 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-16 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-16 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-16 | 2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-16 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-16 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-16 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-16 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-16 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-16 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-17 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-17 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-17 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-17 | 2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-17 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-17 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-17 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-17 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-17 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-17 | 2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2025-02-17 | 2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-17 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-17 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-17 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-17 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-18 | 2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2025-02-18 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-18 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-18 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-18 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-18 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-18 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-18 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-18 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-18 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-18 | 2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-18 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-18 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-19 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-19 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-19 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-19 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-19 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-19 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-19 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-19 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-19 | 2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-19 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-19 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-19 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-20 | 2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-20 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-20 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-20 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-20 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-20 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-20 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-20 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-20 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-20 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-20 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-20 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-20 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-21 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-21 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-21 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-21 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-21 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-21 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-21 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-21 | 2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-02-21 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-21 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-21 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-21 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-21 | 2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2025-02-22 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-22 | 2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-22 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-22 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-22 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-22 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-22 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-22 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-22 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-22 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-22 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-22 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-22 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-22 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-23 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-23 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-23 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-23 | 2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-23 | 2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-02-23 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-23 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-23 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-23 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-23 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-23 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-23 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-23 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-23 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-24 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-24 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-24 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-24 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-24 | 2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2025-02-24 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-24 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-24 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-24 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-24 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-24 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-24 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-24 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-24 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-24 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-25 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-25 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-25 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-25 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-25 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-25 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-25 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-25 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-25 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-25 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-25 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-25 | 2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-25 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-25 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-25 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-25 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-26 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-26 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-26 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-26 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-26 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-26 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-26 | 2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-02-26 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-26 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-26 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-26 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-26 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-26 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-26 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-26 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-26 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-27 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-27 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-27 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-02-27 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-27 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-27 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-27 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-27 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-27 | 2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2025-02-27 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-27 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-27 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-27 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-27 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-27 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-27 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-02-28 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-02-28 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-02-28 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-02-28 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-02-28 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-28 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-28 | 2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-28 | 2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-28 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-02-28 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-28 | 2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-02-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-02-28 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-02-28 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-02-28 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-01 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-01 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-01 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-01 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-01 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-01 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-01 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-01 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-01 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-01 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-01 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-01 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-01 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-01 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-02 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-02 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-02 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-02 | 2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-02 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-02 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-02 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-02 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-02 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-02 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-02 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-02 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-02 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-02 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-02 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-02 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-03 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-03 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-03 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-03 | 2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-03-03 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-03 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-03 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-03 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-03 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-03 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-03 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-03 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-03 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-03 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-03 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-03 | 2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-03-04 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-04 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-04 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-04 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-04 | 2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-03-04 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-04 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-04 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-04 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-04 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-04 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-04 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-04 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-04 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-04 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-05 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-05 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-05 | 2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-05 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-05 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-05 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-05 | 2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-05 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-05 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-05 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-05 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-05 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-05 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-05 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-05 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-05 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-06 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-06 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-06 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-06 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-06 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-06 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-06 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-06 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-06 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-06 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-06 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-06 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-06 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-06 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-06 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-07 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-07 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-07 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-07 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-07 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-07 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-07 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-07 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-07 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-07 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-07 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-07 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-07 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-07 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-07 | 2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-07 | 2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-03-08 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-08 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-08 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-08 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-08 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-08 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-08 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-08 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-08 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-08 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-08 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-08 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-08 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-08 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-08 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-09 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-09 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-09 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-09 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-09 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-09 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-09 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-09 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-09 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-09 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-09 | 2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-03-09 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-09 | 2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-09 | 2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-09 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-09 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-10 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-10 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-10 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-10 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-10 | 2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2025-03-10 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-10 | 2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-03-10 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-10 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-10 | 2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-10 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-10 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-10 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-10 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-10 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-11 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-11 | 2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-03-11 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-11 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-11 | 2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-11 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-11 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-11 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-11 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-11 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-11 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-11 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-11 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-12 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-12 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-12 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-12 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-12 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-12 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-12 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-12 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-12 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-12 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-12 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-12 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-12 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-13 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-13 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-13 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-13 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-13 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-13 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-13 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-13 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-13 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-13 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-13 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-13 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-13 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-13 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-14 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-14 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-14 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-14 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-14 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-14 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-14 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-14 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-14 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-14 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-14 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-14 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-14 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-14 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-15 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-15 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-15 | 2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2025-03-15 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-15 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-15 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-15 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-15 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-15 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-15 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-15 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-15 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-15 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-15 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-15 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-16 | 2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2025-03-16 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-16 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-16 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-16 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-16 | 2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-16 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-16 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-16 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-16 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-16 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-16 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-16 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-16 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-16 | 2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-17 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-17 | 2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-17 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-17 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-17 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-17 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-17 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-17 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-17 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-17 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-17 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-17 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-17 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-17 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-17 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-18 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-18 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-18 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-18 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-18 | 2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-18 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-18 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-18 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-18 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-18 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-18 | 2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2025-03-18 | 2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-03-18 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-18 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-18 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-18 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-19 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-19 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-19 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-19 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-19 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-19 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-19 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-19 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-19 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-19 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-19 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-19 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-19 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-19 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-19 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-19 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-20 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-20 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-20 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-20 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-20 | 2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-20 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-20 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-20 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-20 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-20 | 2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-20 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-20 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-20 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-20 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-20 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-20 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-20 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-20 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-21 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-21 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-21 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-21 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-21 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-21 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-21 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-21 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-21 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-21 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-21 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-21 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-21 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-21 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-21 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-21 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-21 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-21 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-22 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-22 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-22 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-22 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-22 | 2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-22 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-22 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-22 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-22 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-22 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-22 | 2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-03-22 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-22 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-22 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-22 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-22 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-22 | 2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-22 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-22 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-22 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-23 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-23 | 2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-23 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-23 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-23 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-23 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-23 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-23 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-23 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-23 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-23 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-23 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-23 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-23 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-23 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-23 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-23 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-23 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-24 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-24 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-24 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-24 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-24 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-24 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-24 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-24 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-24 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-24 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-24 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-24 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-24 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-24 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-24 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-24 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-25 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-25 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-25 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-25 | 2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-03-25 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-25 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-25 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-25 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-25 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-25 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-25 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-25 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-25 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-25 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-25 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-25 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-25 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-26 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-26 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-26 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-26 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-26 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-26 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-26 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-26 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-26 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-26 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-26 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-26 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-26 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-26 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-26 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-26 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-26 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-26 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-26 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-27 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-27 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-27 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-27 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-27 | 2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2025-03-27 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-27 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-27 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-27 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-27 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-27 | 2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-03-27 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-27 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-27 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-27 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-27 | 2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-27 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-27 | 2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-27 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-28 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-28 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-28 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-28 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-28 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-28 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-28 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-28 | 2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-03-28 | 2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-03-28 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-28 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-28 | 2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-28 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-28 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-28 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-28 | 2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-29 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-29 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-29 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-29 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-29 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-29 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-29 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-29 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-29 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-29 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-29 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-29 | 2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-03-30 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-30 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-30 | 2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-03-30 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-30 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-30 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-30 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-30 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-30 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-03-30 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-30 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-30 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-31 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-03-31 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-03-31 | 2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-31 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-03-31 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-03-31 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-03-31 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-03-31 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-31 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-03-31 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-03-31 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-31 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-01 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-01 | 2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2025-04-01 | 2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2025-04-01 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-01 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-01 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-01 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-01 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-01 | 2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-04-01 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-01 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-01 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-02 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-02 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-02 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-02 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-02 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-02 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-02 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-02 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-02 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-02 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-02 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-02 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-03 | 2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2025-04-03 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-03 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-03 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-03 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-03 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-03 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-03 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-03 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-03 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-03 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-03 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-03 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-04 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-04 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-04 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-04 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-04 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-04 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-04 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-04 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-04 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-04 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-04 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-04 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-04 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-04 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-04 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-05 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-05 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-05 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-05 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-05 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-05 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-05 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-05 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-05 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-05 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-05 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-05 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-05 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-05 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-05 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-05 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-06 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-06 | 2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-06 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-06 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-06 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-06 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-06 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-06 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-06 | 2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-04-06 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-06 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-06 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-06 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-06 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-06 | 2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-06 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-06 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-06 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-07 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-07 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-07 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-07 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-07 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-07 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-07 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-07 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-07 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-07 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-07 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-07 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-07 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-07 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-07 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-07 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-08 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-08 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-08 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-08 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-08 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-08 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-08 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-08 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-08 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-08 | 2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2025-04-08 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-08 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-08 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-08 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-08 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-08 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-08 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-09 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-09 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-09 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-09 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-09 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-09 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-09 | 2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-04-09 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-09 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-09 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-09 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-09 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-09 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-09 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-09 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-09 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-09 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-10 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-10 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-10 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-10 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-10 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-10 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-10 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-10 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-10 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-10 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-10 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-10 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-10 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-10 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-10 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-10 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-11 | 2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-04-11 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-11 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-11 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-11 | 2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-11 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-11 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-11 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-11 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-11 | 2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2025-04-11 | 2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-04-11 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-11 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-11 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-11 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-11 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-11 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-12 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-12 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-12 | 2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-12 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-12 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-12 | 2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-04-12 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-12 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-12 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-12 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-12 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-12 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-12 | 2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-12 | 2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2025-04-13 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-13 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-13 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-13 | 2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-13 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-13 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-13 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-13 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-13 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-13 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-13 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-13 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-14 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-14 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-14 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-14 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-14 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-14 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-14 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-14 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-14 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-14 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-14 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-14 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-15 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-15 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-15 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-15 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-15 | 2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-15 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-15 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-15 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-15 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-15 | 2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-04-15 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-15 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-15 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-16 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-16 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-16 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-16 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-04-16 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-16 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-16 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-16 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-16 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-16 | 2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-04-16 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-16 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-16 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-17 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-17 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-17 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-17 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-17 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-17 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-17 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-17 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-17 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-17 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-17 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-17 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-17 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-18 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-18 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-18 | 2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-04-18 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-18 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-18 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-18 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-18 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-18 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-18 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-18 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-18 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-18 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-18 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-18 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-18 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-18 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-19 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-19 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-19 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-19 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-19 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-19 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-19 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-19 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-19 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-19 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-19 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-19 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-19 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-19 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-19 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-20 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-20 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-20 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-20 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-20 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-20 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-20 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-20 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-20 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-20 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-20 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-20 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-20 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-20 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-20 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-20 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-20 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-21 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-21 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-21 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-21 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-21 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-21 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-21 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-21 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-21 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-21 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-21 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-21 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-21 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-21 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-21 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-21 | 2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-04-21 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-22 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-22 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-22 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-22 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-22 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-22 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-22 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-22 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-22 | 2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-04-22 | 2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-04-22 | 2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2025-04-22 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-22 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-22 | 2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2025-04-22 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-22 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-22 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-23 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-23 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-23 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-23 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-23 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-23 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-23 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-23 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-23 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-23 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-23 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-23 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-23 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-23 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-23 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-24 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-24 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-24 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-24 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-24 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-24 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-24 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-24 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-24 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-24 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-24 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-24 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-24 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-24 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-24 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-24 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-24 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-25 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-25 | 2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-04-25 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-25 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-25 | 2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-25 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-25 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-25 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-25 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-25 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-25 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-25 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-25 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-25 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-25 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-25 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-25 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-26 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-26 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-26 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-26 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-26 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-26 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-26 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-26 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-26 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-26 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-26 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-26 | 2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-04-26 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-26 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-26 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-27 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-27 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-27 | 2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-27 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-27 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-27 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-27 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-27 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-27 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-27 | 2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-27 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-27 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-27 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-27 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-28 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-28 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-28 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-28 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-28 | 2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2025-04-28 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-28 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-28 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-28 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-28 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-28 | 2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-28 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-28 | 2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-04-28 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-29 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-29 | 2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-29 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-04-29 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-29 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-29 | 2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-29 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-29 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-29 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-29 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-29 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-29 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-04-29 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-29 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-04-29 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-29 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-04-30 | 2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-04-30 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-04-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-04-30 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-30 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-30 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-30 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-30 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-30 | 2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-30 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-04-30 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-04-30 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-04-30 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-30 | 2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-05-01 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-01 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-01 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-01 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-01 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-01 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-01 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-01 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-01 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-01 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-01 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-02 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-02 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-02 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-02 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-02 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-02 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-02 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-02 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-02 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-02 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-02 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-03 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-03 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-03 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-03 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-03 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-03 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-03 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-03 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-03 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-03 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-03 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-03 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-03 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-04 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-04 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-04 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-04 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-04 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-04 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-04 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-04 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-04 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-04 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-04 | 2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-05-04 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-04 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-04 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-04 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-05 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-05 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-05 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-05 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-05 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-05 | 2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-05-05 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-05 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-05 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-05 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-05 | 2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-05 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-05 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-05 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-06 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-06 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-06 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
2025-05-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-06 | 2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-06 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-06 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-06 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-06 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-06 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-06 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-06 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-06 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-06 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-07 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-07 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-07 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-07 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-07 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-07 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-07 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-07 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-07 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-07 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-07 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-07 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-08 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-08 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-08 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-08 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-08 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-08 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-08 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-08 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-08 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-08 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-08 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-08 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-08 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-09 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-09 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-09 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-09 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-09 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-09 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-09 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-09 | 2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-05-09 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-09 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-09 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-09 | 2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-05-09 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-09 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-10 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-10 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-10 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-10 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-10 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-10 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-10 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-10 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-10 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-10 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-10 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-10 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-05-11 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-11 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-11 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-05-11 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-05-11 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-11 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-11 | 2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-05-11 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-11 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-11 | 2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-05-11 | 2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-11 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-12 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-12 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-12 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-12 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-12 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-12 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-12 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-12 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-12 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-13 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-13 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-13 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-13 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-13 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-13 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-13 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-13 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-13 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-13 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-13 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-13 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-14 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-14 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-14 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-14 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-14 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-14 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-14 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-14 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-14 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-14 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-14 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-14 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-15 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-15 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-15 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-15 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-15 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-15 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-15 | 2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-05-15 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-15 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-15 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-15 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-15 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-15 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-16 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-16 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-16 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-16 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-16 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-16 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-16 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-16 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-16 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-16 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-16 | 2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-16 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-16 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-17 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-17 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-17 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-17 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-17 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-17 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-17 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-17 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-17 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-17 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-17 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-17 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-18 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-18 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-18 | 2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-05-18 | 2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-05-18 | 2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-05-18 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-18 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-18 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-18 | 2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-05-18 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-18 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-18 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-19 | 2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-05-19 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-19 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-19 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-19 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-19 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-19 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-19 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-19 | 2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-20 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-20 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-20 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-20 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-20 | 2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-05-20 | 2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-20 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-21 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-21 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-21 | 2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-21 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-21 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-22 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-22 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-22 | 2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-22 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-23 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-23 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-23 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-24 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-24 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-24 | 2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-24 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-25 | 2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2025-05-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-25 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-25 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-26 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-26 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-27 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-27 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-28 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-28 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-28 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-29 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-29 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-29 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-29 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-05-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-30 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-30 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-30 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-30 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-05-31 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-05-31 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-05-31 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-05-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-05-31 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-05-31 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-01 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-01 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-01 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-01 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-02 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-02 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-02 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-02 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-03 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-03 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-03 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-03 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-04 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-04 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-04 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-04 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-05 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-05 | 2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
2025-06-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-05 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-05 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-06 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-06 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-06 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-06 | 2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-07 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-07 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-07 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-08 | 2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-06-08 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-08 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-09 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-09 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-10 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-10 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-11 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-11 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-11 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-12 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-12 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-12 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-13 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-13 | 2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-06-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-13 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-14 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-14 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-15 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-15 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-16 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-16 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-17 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-17 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-18 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-18 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-19 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-19 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-20 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-20 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-21 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-21 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-22 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-22 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-23 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-23 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-24 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-24 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-25 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-25 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-26 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-26 | 2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-06-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-27 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-28 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-29 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-06-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-06-30 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-06-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-01 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-02 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-03 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-04 | 2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-07-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-07-31 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-07-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-15 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-16 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-17 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-18 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-19 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-20 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-21 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-22 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-23 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-24 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-24 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-25 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-25 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-26 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-26 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-26 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-27 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-27 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-27 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-28 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-28 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-28 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-29 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-29 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-29 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-30 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-30 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-30 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-08-31 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-08-31 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-08-31 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-31 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-01 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-01 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-01 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-02 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-02 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-02 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-03 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-03 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-03 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-04 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-04 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-04 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-05 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-05 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-05 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-06 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-06 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-06 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-07 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-07 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-07 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-07 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-08 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-08 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-08 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-08 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-09 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-09 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-09 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-09 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-10 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-10 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-10 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-10 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-11 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-11 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-11 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-11 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-12 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-12 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-12 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-12 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-13 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-13 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-13 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-13 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-13 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-14 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-14 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-14 | 2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-09-14 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-14 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-15 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-15 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-15 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-15 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-16 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-16 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-16 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-16 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-17 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-17 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-17 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-17 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-18 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-18 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-18 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-18 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-18 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-19 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-19 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-19 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-19 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-19 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-19 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-20 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-20 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-20 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-20 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-20 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-20 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-21 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-21 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-21 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-21 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-21 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-21 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-22 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-22 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-22 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-22 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-22 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-22 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-23 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-23 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-23 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-23 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-23 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-23 | 2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2025-09-24 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-24 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-24 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-24 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-24 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-24 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-25 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-25 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-25 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-25 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-25 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-25 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-26 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-26 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-26 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-26 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-26 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-26 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-27 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-27 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-27 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-27 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-27 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-27 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-28 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-28 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-28 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-28 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-28 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-28 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-29 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-29 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-29 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-29 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-29 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-29 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-09-30 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-30 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-30 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-30 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-30 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-30 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-10-01 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-01 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-01 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-01 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-01 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-10-01 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-10-02 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-02 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-02 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-02 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-02 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-10-02 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-10-03 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-03 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-03 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-03 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-03 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-10-03 | 2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-10-04 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-04 | 2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-10-04 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-04 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-04 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-04 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-10-05 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-05 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-05 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-05 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-05 | 2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-10-05 | 2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-10-06 | 2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-10-06 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-06 | 2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-10-06 | 2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-10-07 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
2025-10-08 | 2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed

## RawData
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status
2024-09-01 | 2024-09-16 | Dewi Construction Girendra | 43.7758 | 2.736 | TA416 | 2/8 | COMPLETED
2024-09-16 | 2024-09-29 | Dewi Construction Girendra | 43.7758 | 3.1268 | TA416 | 2/4 | COMPLETED
2024-09-16 | 2024-10-01 | Horil Mahto | 43.7758 | 2.736 | TA416 | 39/10 | COMPLETED
2024-10-01 | 2024-10-07 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 20/8 | COMPLETED
2024-10-03 | 2024-10-15 | Horil Mahto | 43.7758 | 3.3674 | TA416 | 39/8 | COMPLETED
2024-10-08 | 2024-10-13 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 20/6 | COMPLETED
2024-10-14 | 2024-10-19 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 20/9 | COMPLETED
2024-10-15 | 2024-10-24 | Horil Mahto | 46.0492 | 4.6049 | TA416 | 39/7 | COMPLETED
2024-10-20 | 2024-10-24 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 20/5 | COMPLETED
2024-10-24 | 2024-10-29 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 20/7 | COMPLETED
2024-10-24 | 2024-10-31 | Horil Mahto | 46.0492 | 5.7561 | TA416 | 39/9 | COMPLETED
2024-11-01 | 2024-11-04 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 20/12 | COMPLETED
2024-11-05 | 2024-11-10 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/6 | COMPLETED
2024-11-01 | 2024-11-14 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 39/6 | COMPLETED
2024-11-10 | 2024-11-17 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 14/5 | COMPLETED
2024-11-17 | 2024-11-22 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 14/4 | COMPLETED
2024-11-10 | 2024-11-24 | Pankaj | 46.0492 | 3.0699 | TA416 | 2/5 | COMPLETED
2024-11-10 | 2024-11-26 | Reeta Bharti | 46.0492 | 2.7088 | TA416 | 19/3 | COMPLETED
2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416 | 6/2 | COMPLETED
2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416 | 38/3 | COMPLETED
2024-11-22 | 2024-11-28 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 14/8 | COMPLETED
2024-11-10 | 2024-11-29 | Amar Singh | 43.7758 | 2.1888 | TA416 | 41/1 | COMPLETED
2024-11-26 | 2024-12-03 | Pankaj | 46.0492 | 5.7561 | TA416 | 2/7 | COMPLETED
2024-11-28 | 2024-12-05 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/2 | COMPLETED
2024-11-29 | 2024-12-05 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/7 | COMPLETED
2024-11-28 | 2024-12-05 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 4/3 | COMPLETED
2024-11-29 | 2024-12-06 | Horil Mahto | 43.7758 | 5.472 | TA416 | 36/12 | COMPLETED
2024-12-01 | 2024-12-09 | Pankaj | 43.7758 | 4.864 | TA416 | 2/6 | COMPLETED
2024-11-30 | 2024-12-10 | Amar Singh | 46.0492 | 4.1863 | TA416 | 41/2 | COMPLETED
2024-12-06 | 2024-12-12 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 14/3 | COMPLETED
2024-12-06 | 2024-12-12 | Pinky Dewi | 43.7758 | 6.2537 | TA416 | 4/4 | COMPLETED
2024-12-06 | 2024-12-13 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 19/4 | COMPLETED
2024-12-10 | 2024-12-16 | Pankaj | 46.0492 | 6.5785 | TA416 | 2/3 | COMPLETED
2024-12-12 | 2024-12-16 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 4/2 | COMPLETED
2024-12-12 | 2024-12-17 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/2 | COMPLETED
2024-12-06 | 2024-12-19 | Horil Mahto | 46.0492 | 3.2892 | TA416 | 38/2 | COMPLETED
2024-12-10 | 2024-12-20 | Amar Singh | 42.3742 | 3.8522 | TA416 | 45/3 | COMPLETED
2024-12-13 | 2024-12-21 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 19/1 | COMPLETED
2024-12-17 | 2024-12-22 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 4/8 | COMPLETED
2024-12-18 | 2024-12-23 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 14/1 | COMPLETED
2024-12-18 | 2024-12-23 | Pankaj | 46.0492 | 7.6749 | TA416 | 7/10 | COMPLETED
2024-12-21 | 2024-12-27 | Amar Singh | 46.0492 | 6.5785 | TA416 | 45/2 | COMPLETED
2024-12-22 | 2024-12-27 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 19/5 | COMPLETED
2024-12-24 | 2024-12-27 | Pinky Dewi | 46.0492 | 11.5123 | TA416 | 4/7 | COMPLETED
2024-12-24 | 2024-12-30 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/9 | COMPLETED
2024-12-20 | 2024-12-31 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 38/4 | COMPLETED
2024-12-24 | 2024-12-31 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 17/1 | COMPLETED
2024-12-24 | 2025-01-03 | Asc Heights | 46.0492 | 4.1863 | TA416 | 31/3 | COMPLETED
2024-12-28 | 2025-01-03 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 4/5 | COMPLETED
2024-12-28 | 2025-01-04 | Amar Singh | 43.7758 | 5.472 | TA416 | 46/1 | COMPLETED
2024-12-31 | 2025-01-07 | Pankaj | 46.0492 | 5.7561 | TA416 | 7/2 | COMPLETED
2024-12-28 | 2025-01-08 | Reeta Bharti | 43.7758 | 3.648 | TA416 | 19/6 | COMPLETED
2025-01-01 | 2025-01-10 | Dewi Construction Girendra | 46.0492 | 4.6049 | TA416 | 17/4 | COMPLETED
2025-01-04 | 2025-01-11 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/4 | COMPLETED
2025-01-03 | 2025-01-11 | Pinky Dewi | 46.0492 | 5.1166 | TA416 | 12/2 | COMPLETED
2025-01-08 | 2025-01-14 | Pankaj | 46.0492 | 6.5785 | TA416 | 7/8 | COMPLETED
2025-01-07 | 2025-01-15 | Amar Singh | 46.0492 | 5.1166 | TA416 | 36/3 | COMPLETED
2025-01-07 | 2025-01-17 | Horil Mahto | 46.0492 | 4.1863 | TA416 | 38/1 | COMPLETED
2025-01-09 | 2025-01-17 | Reeta Bharti | 46.0492 | 5.1166 | TA416 | 19/7 | COMPLETED
2025-01-10 | 2025-01-17 | Dewi Construction Girendra | 43.7758 | 5.472 | TA416 | 17/3 | COMPLETED
2025-01-11 | 2025-01-19 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/2 | COMPLETED
2025-01-12 | 2025-01-21 | Pinky Dewi | 46.0492 | 4.6049 | TA416 | 12/3 | COMPLETED
2025-01-15 | 2025-01-22 | Pankaj | 43.7758 | 5.472 | TA416 | 7/7 | COMPLETED
2025-01-17 | 2025-01-23 | Dewi Construction Girendra | 43.7758 | 6.2537 | TA416 | 17/2 | COMPLETED
2025-01-15 | 2025-01-24 | Amar Singh | 43.7758 | 4.3776 | TA416 | 36/5 | COMPLETED
2025-01-20 | 2025-01-25 | Asc Heights | 46.0492 | 7.6749 | TA416 | 31/6 | COMPLETED
2025-01-21 | 2025-01-25 | Pinky Dewi | 46.0492 | 9.2098 | TA416 | 12/4 | COMPLETED
2025-01-16 | 2025-01-27 | Reeta Bharti | 46.0492 | 3.8374 | TA416 | 19/9 | COMPLETED
2025-01-16 | 2025-01-28 | Horil Mahto | 46.0492 | 3.5422 | TA416 | 35/1 | COMPLETED
2025-01-24 | 2025-01-29 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 17/5 | COMPLETED
2025-01-21 | 2025-01-30 | Pankaj | 43.7758 | 4.3776 | TA416 | 7/6 | COMPLETED
2025-01-25 | 2025-01-30 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/1 | COMPLETED
2025-01-21 | 2025-01-31 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/10 | COMPLETED
2025-01-25 | 2025-02-01 | Pinky Dewi | 46.0492 | 5.7561 | TA416 | 12/5 | COMPLETED
2025-01-25 | 2025-02-02 | Asc Heights | 43.7758 | 4.864 | TA416 | 31/1 | COMPLETED
2025-01-30 | 2025-02-05 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 17/7 | COMPLETED
2025-01-28 | 2025-02-06 | Reeta Bharti | 64.4817 | 6.4482 | TA416 | 20/0 | COMPLETED
2025-02-02 | 2025-02-07 | Amar Singh | 43.7758 | 7.296 | TA416 | 36/2 | COMPLETED
2025-02-02 | 2025-02-08 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 12/9 | COMPLETED
2025-01-29 | 2025-02-09 | Pankaj | 46.0492 | 3.8374 | TA416 | 7/5 | COMPLETED
2025-02-03 | 2025-02-10 | Asc Heights | 43.7758 | 5.472 | TA416 | 31/7 | COMPLETED
2025-01-29 | 2025-02-11 | Horil Mahto | 73.4258 | 5.2447 | TA416 | 35/0 | COMPLETED
2025-02-02 | 2025-02-12 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 33/11 | COMPLETED
2025-02-06 | 2025-02-13 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 21/0 | COMPLETED
2025-02-07 | 2025-02-13 | Reeta Bharti | 43.7758 | 6.2537 | TA416 | 20/2 | COMPLETED
2025-02-08 | 2025-02-15 | Amar Singh | 46.0492 | 5.7561 | TA416 | 35/9 | COMPLETED
2025-02-09 | 2025-02-15 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 8/1 | COMPLETED
2025-02-10 | 2025-02-18 | Pankaj | 43.7758 | 4.864 | TA416 | 7/4 | COMPLETED
2025-02-12 | 2025-02-19 | Reeta Bharti | 43.7758 | 5.472 | TA416 | 20/3 | COMPLETED
2025-02-11 | 2025-02-20 | Asc Heights | 46.0492 | 4.6049 | TA416 | 31/9 | COMPLETED
2025-02-12 | 2025-02-20 | Horil Mahto | 46.0492 | 5.1166 | TA416 | 34/7 | COMPLETED
2025-02-14 | 2025-02-20 | Dewi Construction Girendra | 46.0492 | 6.5785 | TA416 | 33/6 | COMPLETED
2025-02-16 | 2025-02-21 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 8/2 | COMPLETED
2025-02-16 | 2025-02-21 | Amar Singh | 46.0492 | 7.6749 | TA416 | 35/7 | COMPLETED
2025-02-14 | 2025-02-22 | Rudra Construction | 43.7758 | 4.864 | TA416 | 33/9 | COMPLETED
2025-02-20 | 2025-02-25 | Reeta Bharti | 42.3742 | 7.0624 | TA416 | 20/4 | COMPLETED
2025-02-21 | 2025-02-25 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/7 | COMPLETED
2025-02-19 | 2025-02-25 | Pankaj | 43.7758 | 6.2537 | TA416 | 7/1 | COMPLETED
2025-02-21 | 2025-02-27 | Horil Mahto | 43.7758 | 6.2537 | TA416 | 34/6 | COMPLETED
2025-02-20 | 2025-02-27 | Amar Singh | 43.7758 | 5.472 | TA416 | 35/4 | COMPLETED
2025-02-19 | 2025-02-28 | Asc Heights | 64.4817 | 6.4482 | TA416 | 31/0 | COMPLETED
2025-02-22 | 2025-02-28 | Pinky Dewi | 64.4817 | 9.2117 | TA416 | 8/0 | COMPLETED
2025-02-26 | 2025-03-02 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/3 | COMPLETED
2025-02-27 | 2025-03-03 | Amar Singh | 46.0492 | 9.2098 | TA416 | 35/5 | COMPLETED
2025-03-01 | 2025-03-05 | Reeta Bharti | 46.0492 | 9.2098 | TA416 | 4/10 | COMPLETED
2025-03-03 | 2025-03-07 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 33/8 | COMPLETED
2025-02-27 | 2025-03-08 | Pankaj | 64.4817 | 6.4482 | TA416 | 7/0 | COMPLETED
2025-03-01 | 2025-03-08 | Pinky Dewi | 43.7758 | 5.472 | TA416 | 7/11 | COMPLETED
2025-02-28 | 2025-03-08 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/3 | COMPLETED
2025-03-01 | 2025-03-09 | Asc Heights | 46.0492 | 5.1166 | TA416 | 30/4 | COMPLETED
2025-03-01 | 2025-03-11 | Rudra Construction | 46.0492 | 4.1863 | TA416 | 34/1 | COMPLETED
2025-03-08 | 2025-03-11 | Dewi Construction Girendra | 42.3742 | 10.5936 | TA416 | 33/4 | COMPLETED
2025-03-08 | 2025-03-12 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8/3 | COMPLETED
2025-03-01 | 2025-03-13 | Reeta Bharti | 64.4817 | 4.9601 | TA416 | 5/0 | COMPLETED
2025-03-10 | 2025-03-16 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/5 | COMPLETED
2025-03-10 | 2025-03-18 | Horil Mahto | 43.7758 | 4.864 | TA416 | 35/6 | COMPLETED
2025-03-12 | 2025-03-18 | Dewi Construction Girendra | 42.3742 | 6.0535 | TA416 | 33/1 | COMPLETED
2025-03-09 | 2025-03-19 | Pankaj | 46.0492 | 4.1863 | TA416 | 6/1 | COMPLETED
2025-03-13 | 2025-03-21 | Pinky Dewi | 55.3387 | 6.1487 | TA416 | 8/4 | COMPLETED
2025-03-16 | 2025-03-21 | Reeta Bharti | 46.0492 | 7.6749 | TA416 | 5/1 | COMPLETED
2025-03-16 | 2025-03-23 | Asc Heights | 42.3742 | 5.2968 | TA416 | 31/8 | COMPLETED
2025-03-19 | 2025-03-23 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 33/2 | COMPLETED
2025-03-22 | 2025-03-26 | Pinky Dewi | 42.3742 | 8.4748 | TA416 | 8B/1 | COMPLETED
2025-03-20 | 2025-03-27 | Pankaj | 42.3742 | 5.2968 | TA416 | 7/3 | COMPLETED
2025-03-22 | 2025-03-29 | Reeta Bharti | 64.4817 | 8.0602 | TA416 | 6/0 | COMPLETED
2025-03-20 | 2025-03-30 | Horil Mahto | 42.3742 | 3.8522 | TA416 | 35/2 | COMPLETED
2025-03-24 | 2025-03-30 | Asc Heights | 42.3742 | 6.0535 | TA416 | 31/10 | COMPLETED
2025-03-24 | 2025-03-31 | Dewi Construction Girendra | 64.4817 | 8.0602 | TA416 | 34/0 | COMPLETED
2025-03-21 | 2025-03-31 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/8 | COMPLETED
2025-03-22 | 2025-03-31 | Amar Singh | 42.3742 | 4.2374 | TA416 | 35/8 | COMPLETED
2025-03-24 | 2025-03-31 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 39/3 | COMPLETED
2025-03-24 | 2025-03-31 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/5 | COMPLETED
2025-03-28 | 2025-04-05 | Reeta Bharti | 43.7758 | 4.864 | TA416 | 4/6 | COMPLETED
2025-03-28 | 2025-04-07 | Pinky Dewi | 46.0492 | 4.1863 | TA416 | 8B/3 | COMPLETED
2025-03-31 | 2025-04-08 | Gagan Enterprise 1 | 42.3742 | 4.7082 | TA416 | 20/11 | COMPLETED
2025-04-03 | 2025-04-10 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 34/4 | COMPLETED
2025-03-31 | 2025-04-11 | Anand Construction | 46.0492 | 3.8374 | TA416 | 4/1 | COMPLETED
2025-04-01 | 2025-04-11 | M K Infra | 46.0492 | 4.1863 | TA416 | 38/6 | COMPLETED
2025-04-01 | 2025-04-11 | Gagan Enterprise 2 | 75.8584 | 6.8962 | TA416 | 9/0 | COMPLETED
2025-04-01 | 2025-04-11 | Asc Heights | 87.0116 | 7.9101 | TA416 | 32/0 | COMPLETED
2025-04-01 | 2025-04-12 | Ananya Traders 1 | 46.0492 | 3.8374 | TA416 | 39/1 | COMPLETED
2025-04-01 | 2025-04-12 | Horil Mahto | 46.0492 | 3.8374 | TA416 | 53A/4 | COMPLETED
2025-04-08 | 2025-04-13 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 8B/2 | COMPLETED
2025-04-02 | 2025-04-14 | Amar Singh | 64.4817 | 4.9601 | TA416 | 36/0 | COMPLETED
2025-04-09 | 2025-04-15 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 20/10 | COMPLETED
2025-04-05 | 2025-04-16 | Ananya Traders 2 | 46.0492 | 3.8374 | TA416 | 52/6 | COMPLETED
2025-04-12 | 2025-04-16 | Gagan Enterprise 2 | 42.3742 | 8.4748 | TA416 | 10/1 | COMPLETED
2025-04-06 | 2025-04-17 | Reeta Bharti | 86.2562 | 7.188 | TA416 | 4/0 | COMPLETED
2025-04-12 | 2025-04-19 | Ananya Traders 1 | 64.4817 | 8.0602 | TA416 | 39/0 | COMPLETED
2025-04-14 | 2025-04-21 | Pinky Dewi | 53.3239 | 6.6655 | TA416 | 8B/4 | COMPLETED
2025-04-12 | 2025-04-21 | Asc Heights | 42.3742 | 4.2374 | TA416 | 31/5 | COMPLETED
2025-04-12 | 2025-04-22 | Dewi Construction Girendra | 87.0116 | 7.9101 | TA416 | 33/0 | COMPLETED
2025-04-12 | 2025-04-22 | M K Infra | 42.3742 | 3.8522 | TA416 | 38/7 | COMPLETED
2025-04-12 | 2025-04-22 | Amar Singh | 46.0492 | 4.1863 | TA416 | 36/6 | COMPLETED
2025-04-16 | 2025-04-22 | Gagan Enterprise 1 | 53.3239 | 7.6177 | TA416 | 20/1 | COMPLETED
2025-04-15 | 2025-04-23 | Rudra Construction | 43.7758 | 4.864 | TA416 | 25/2 | COMPLETED
2025-04-17 | 2025-04-25 | Ananya Traders 2 | 42.3742 | 4.7082 | TA416 | 52/5 | COMPLETED
2025-04-12 | 2025-04-26 | Anand Construction | 55.3387 | 3.6892 | TA416 | 0/4 | COMPLETED
2025-04-23 | 2025-04-26 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/12 | COMPLETED
2025-04-20 | 2025-04-26 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/2 | COMPLETED
2025-04-23 | 2025-04-28 | Amar Singh | 46.0492 | 7.6749 | TA416 | 36/7 | COMPLETED
2025-04-23 | 2025-04-28 | Dewi Construction Girendra | 46.0492 | 7.6749 | TA416 | 34/2 | COMPLETED
2025-04-17 | 2025-04-28 | Gagan Enterprise 2 | 78.6775 | 6.5565 | TA416 | 10/0 | COMPLETED
2025-04-22 | 2025-04-28 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/6 | COMPLETED
2025-04-26 | 2025-04-29 | Ananya Traders 2 | 42.3742 | 10.5936 | TA416 | 52/4 | COMPLETED
2025-04-23 | 2025-06-01 | M K Infra | 42.3742 | 1.0594 | TA416 | 38/9 | COMPLETED
2025-04-22 | 2025-04-30 | Pinky Dewi | 97.2286 | 10.8032 | TA416 | 8A/0 | COMPLETED
2025-04-27 | 2025-04-30 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/11 | COMPLETED
2025-04-29 | 2025-05-03 | Dewi Construction Girendra | 46.0492 | 9.2098 | TA416 | 34/3 | COMPLETED
2025-04-29 | 2025-05-04 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 39/4 | COMPLETED
2025-04-29 | 2025-05-05 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/8 | COMPLETED
2025-04-30 | 2025-05-06 | Gagan Enterprise 1 | 46.0492 | 6.5785 | TA416 | 19/10 | COMPLETED
2025-04-30 | 2025-05-06 | Asc Heights | 43.7758 | 6.2537 | TA416 | 30/3 | COMPLETED
2025-04-30 | 2025-05-06 | Ananya Traders 2 | 42.3742 | 6.0535 | TA416 | 52/3 | COMPLETED
2025-04-30 | 2025-05-07 | Rudra Construction | 46.0492 | 5.7561 | TA416 | 25/3 | COMPLETED
2025-05-06 | 2025-05-09 | Gagan Enterprise 1 | 42.3742 | 10.5936 | TA416 | 19/8 | COMPLETED
2025-05-04 | 2025-05-10 | Gagan Enterprise 2 | 42.3742 | 6.0535 | TA416 | 12/1 | COMPLETED
2025-05-04 | 2025-05-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 4/9 | COMPLETED
2025-05-05 | 2025-05-11 | Ananya Traders 1 | 42.3742 | 6.0535 | TA416 | 39/5 | COMPLETED
2025-05-07 | 2025-05-12 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/2 | COMPLETED
2025-05-07 | 2025-05-13 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/1 | COMPLETED
2025-05-07 | 2025-05-13 | Amar Singh | 43.7758 | 6.2537 | TA416 | 36/4 | COMPLETED
2025-05-07 | 2025-05-14 | Dewi Construction Girendra | 46.0492 | 5.7561 | TA416 | 56/2 | COMPLETED
2025-05-05 | 2025-05-14 | Pinky Dewi | 97.2286 | 9.7229 | TA416 | 8B/0 | COMPLETED
2025-05-11 | 2025-05-15 | Gagan Enterprise 1 | 42.3742 | 8.4748 | TA416 | 17/8 | COMPLETED
2025-05-13 | 2025-05-17 | Ananya Traders 2 | 42.3742 | 8.4748 | TA416 | 52/9 | COMPLETED
2025-05-14 | 2025-05-19 | Dewi Construction Girendra | 43.7758 | 7.296 | TA416 | 56/1 | COMPLETED
2025-05-14 | 2025-05-19 | Amar Singh | 42.3742 | 7.0624 | TA416 | 36/11 | COMPLETED
2025-05-12 | 2025-05-19 | Ananya Traders 1 | 46.0492 | 5.7561 | TA416 | 38/11 | COMPLETED
2025-05-14 | 2025-05-20 | Asc Heights | 42.3742 | 6.0535 | TA416 | 30/2 | COMPLETED
2025-05-12 | 2025-05-21 | Reeta Bharti | 46.0492 | 4.6049 | TA416 | 2/1 | COMPLETED
2025-05-16 | 2025-05-21 | Ananya Traders 2 | 46.0492 | 7.6749 | TA416 | 52/10 | COMPLETED
2025-05-15 | 2025-05-22 | Pinky Dewi | 42.3742 | 5.2968 | TA416 | 23/3 | COMPLETED
2025-05-11 | 2025-05-22 | Gagan Enterprise 2 | 42.3742 | 3.5312 | TA416 | 12/6 | COMPLETED
2025-05-12 | 2025-05-22 | Amit Const | 53.3239 | 4.8476 | TA416 | 53/1 | COMPLETED
2025-05-20 | 2025-05-24 | Amar Singh | 42.3742 | 8.4748 | TA416 | 36/9 | COMPLETED
2025-05-20 | 2025-05-24 | Ananya Traders 1 | 42.3742 | 8.4748 | TA416 | 38/10 | COMPLETED
2025-05-20 | 2025-05-24 | Dewi Construction Girendra | 42.3742 | 8.4748 | TA416 | 56/3 | COMPLETED
2025-05-16 | 2025-05-25 | Gagan Enterprise 1 | 78.0732 | 7.8073 | TA416 | 15/0 | COMPLETED
2025-05-10 | 2025-05-27 | Rudra Construction | 42.3742 | 2.3541 | TA416 | 23/5 | COMPLETED
2025-05-22 | 2025-05-27 | Ananya Traders 2 | 42.3742 | 7.0624 | TA416 | 52/8 | COMPLETED
2025-05-23 | 2025-05-28 | Pinky Dewi | 42.3742 | 7.0624 | TA416 | 23/4 | COMPLETED
2025-05-23 | 2025-05-30 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/2 | COMPLETED
2025-05-23 | 2025-05-30 | Dewi Construction Girendra | 42.3742 | 5.2968 | TA416 | 56/4 | COMPLETED
2025-05-26 | 2025-05-31 | Gagan Enterprise 1 | 42.3742 | 7.0624 | TA416 | 12/8 | COMPLETED
2025-05-25 | 2025-05-31 | Amar Singh | 42.3742 | 6.0535 | TA416 | 36/10 | COMPLETED
2025-05-28 | 2025-06-02 | Ananya Traders 1 | 46.0492 | 7.6749 | TA416 | 38/5 | COMPLETED
2025-05-28 | 2025-06-03 | Pinky Dewi | 55.3387 | 7.9055 | TA416 | 23/1 | COMPLETED
2025-05-25 | 2025-06-04 | Reeta Bharti | 42.3742 | 3.8522 | TA416 | 0/3 | COMPLETED
2025-05-30 | 2025-06-04 | Dewi Construction Girendra | 42.3742 | 7.0624 | TA416 | 56/5 | COMPLETED
2025-05-27 | 2025-06-07 | Ananya Traders 2 | 97.2286 | 8.1024 | TA416 | 51/0 | COMPLETED
2025-06-04 | 2025-06-09 | Pinky Dewi | 43.7758 | 7.296 | TA416 | 23/2 | COMPLETED
2025-06-02 | 2025-06-10 | Amar Singh | 46.0492 | 5.1166 | TA416 | 33/5 | COMPLETED
2025-06-04 | 2025-06-11 | Reeta Bharti | 42.3742 | 5.2968 | TA416 | 0/1 | COMPLETED
2025-06-08 | 2025-06-13 | Ananya Traders 2 | 43.7758 | 7.296 | TA416 | 50/1 | COMPLETED
2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED
2025-06-12 | 2025-06-18 | Amar Singh | 43.7758 | 6.2537 | TA416 | 34/5 | COMPLETED
2025-06-10 | 2025-06-18 | Amit Const | 46.0492 | 5.1166 | TA416 | 53A/2 | COMPLETED
2025-06-12 | 2025-06-20 | Pinky Dewi | 67.112 | 7.4569 | TA416 | 22/0 | COMPLETED
2025-05-25 | 2025-06-21 | Asc Heights | 143.4621 | 5.1236 | TA416 | 30/0 | COMPLETED
2025-06-12 | 2025-06-23 | Reeta Bharti | 73.4258 | 6.1188 | TA416 | 3/0 | COMPLETED
2025-06-21 | 2025-06-26 | Pinky Dewi | 46.0492 | 7.6749 | TA416 | 21/2 | COMPLETED
2025-06-10 | 2025-06-27 | M K Infra | 46.0492 | 2.5583 | TA416 | 45/1 | COMPLETED
2025-06-20 | 2025-06-29 | Amit Const | 46.0492 | 4.6049 | TA416 | 53A/3 | COMPLETED
2025-06-15 | 2025-06-29 | Ananya Traders 2 | 104.8666 | 6.9911 | TA416 | 48/0 | COMPLETED
2025-06-24 | 2025-06-30 | Reeta Bharti | 42.3742 | 6.0535 | TA416 | 12/7 | COMPLETED
2025-06-27 | 2025-06-30 | Pinky Dewi | 42.3742 | 10.5936 | TA416 | 21/1 | COMPLETED
2025-06-04 | 2025-06-30 | Ananya Traders 1 | 161.3552 | 5.9761 | TA416 | 40/0 | COMPLETED
2025-06-01 | 2025-06-30 | Gagan Enterprise 1 | 188.3779 | 6.2793 | TA416 | 14/0 | COMPLETED
2025-06-24 | 2025-07-05 | Asc Heights | 46.0492 | 3.8374 | TA416 | 28/1 | COMPLETED
2025-07-01 | 2025-07-07 | Pinky Dewi | 46.0492 | 6.5785 | TA416 | 21/3 | COMPLETED
2025-07-01 | 2025-07-12 | Reeta Bharti | 55.3387 | 4.6116 | TA416 | 25/1 | COMPLETED
2025-07-05 | 2025-07-18 | Ananya Traders 1 | 101.692 | 7.2637 | TA416 | 44/0 | COMPLETED
2025-06-28 | 2025-07-22 | Amar Singh | 86.2562 | 3.4502 | TA416 | 56/0 | COMPLETED
2025-07-08 | 2025-07-31 | Reeta Bharti | 97.2286 | 4.0512 | TA416 | 28/0 | COMPLETED
2025-07-20 | 2025-08-08 | Ananya Traders 1 | 143.4621 | 7.1731 | TA416 | 41/0 | COMPLETED
2025-07-09 | 2025-08-11 | Gagan Enterprise 1 | 188.3779 | 5.5405 | TA416 | 13/0 | COMPLETED
2025-07-27 | 2025-08-17 | Punam Kumari | 46.0492 | 2.0931 | TA416 | 53A/6 | COMPLETED
2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED
2025-07-26 | 2025-08-27 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 24/0 | COMPLETED
2025-08-02 | 2025-08-30 | Kongres Kumar 2 | 97.2286 | 3.3527 | TA416 | 65/0 | COMPLETED
2025-08-04 | 2025-08-30 | Sainik Trader | 75.8584 | 2.8096 | TA416 | 18/0 | COMPLETED
2025-08-09 | 2025-08-30 | Radha Construction | 78.0732 | 3.5488 | TA416 | 1/0 | COMPLETED
2025-08-12 | 2025-09-02 | Gagan Enterprise 1 | 97.6534 | 4.4388 | TA416 | 12/0 | COMPLETED
2025-08-18 | 2025-09-04 | Punam Kumari | 55.3387 | 3.0744 | TA416 | 54/1 | COMPLETED
2025-08-10 | 2025-09-06 | Ananya Traders 1 | 118.4303 | 4.2297 | TA416 | 43/0 | COMPLETED
2025-08-16 | 2025-09-14 | Amit Choudhury | 110.6255 | 3.6875 | TA416 | 16/0 | COMPLETED
2025-08-24 | 2025-09-14 | Gouri Shankar | 97.6534 | 4.4388 | TA416 | 11/0 | COMPLETED
2025-09-03 | 2025-09-21 | Radha Construction | 89.7178 | 4.722 | TA416 | 2/0 | COMPLETED
2025-08-31 | 2025-09-22 | Kongres Kumar 2 | 73.4258 | 3.1924 | TA416 | 64/0 | COMPLETED
2025-09-05 | 2025-09-22 | Punam Kumari | 90.1252 | 5.007 | TA416 | 52/0 | COMPLETED
2025-09-07 | 2025-09-22 | Ananya Traders 1 | 90.1252 | 5.6328 | TA416 | 47/0 | COMPLETED
2025-08-06 | 2025-09-22 | Reeta Bharti | 161.3552 | 3.3616 | TA416 | 29/0 | COMPLETED
2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED
2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED
2025-09-15 | 2025-09-24 | Amit Choudhury | 42.3742 | 4.2374 | TA416 | 17/6 | COMPLETED
2025-08-31 | 2025-09-24 | Sainik Trader | 87.0116 | 3.4805 | TA416 | 19/0 | COMPLETED
2025-09-15 | 2025-09-25 | Gouri Shankar | 78.6775 | 7.1525 | TA416 | 26/0 | COMPLETED
2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED
2025-08-28 | 2025-09-29 | Kongres Kumar 1 | 161.3552 | 4.8896 | TA416 | 25/0 | COMPLETED
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
|  | Nan |  |  | TA416
2025-09-29 |  | M S Mdpl | 60 |  | TA416 | 54/0 | Material shifting work under progress.
2024-09-12 | 2024-09-21 | Bhagwan Construction | 43.8044 | 4.3804 | TA413 | 29A/2 | COMPLETED
2024-09-21 | 2024-09-27 | Bhagwan Construction | 36.1598 | 5.1657 | TA413 | 29/5 | COMPLETED
2024-09-28 | 2024-10-03 | Bhagwan Construction | 36.1598 | 6.0266 | TA413 | 29/3 | COMPLETED
2024-10-03 | 2024-10-08 | Bhagwan Construction | 37.9311 | 6.3218 | TA413 | 29/4 | COMPLETED
2024-10-03 | 2024-10-14 | Bhagwan Construction | 45.697 | 3.8081 | TA413 | 29A/6 | COMPLETED
2024-10-09 | 2024-10-17 | Bhagwan Construction | 36.1598 | 4.0178 | TA413 | 30/1 | COMPLETED
2024-10-14 | 2024-10-25 | Bhagwan Construction | 43.8044 | 3.6504 | TA413 | 29A/1 | COMPLETED
2024-11-12 | 2024-11-24 | Vasu Dev Singh 1 | 36.1598 | 2.7815 | TA413 | 34/8 | COMPLETED
2024-11-14 | 2024-11-25 | Vasu Dev Singh 2 | 37.9311 | 3.1609 | TA413 | 34/12 | COMPLETED
2024-11-25 | 2024-12-04 | Vasu Dev Singh 1 | 43.8044 | 4.3804 | TA413 | 34/4 | COMPLETED
2024-11-26 | 2024-12-12 | Vasu Dev Singh 2 | 36.1598 | 2.127 | TA413 | 34/7 | COMPLETED
2024-12-05 | 2024-12-16 | Vasu Dev Singh 1 | 37.1383 | 3.0949 | TA413 | 34/3 | COMPLETED
2024-12-07 | 2024-12-16 | Punam Devi 2 | 34.7898 | 3.479 | TA413 | 8/1 | COMPLETED
2024-12-13 | 2024-12-21 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/9 | COMPLETED
2024-12-13 | 2024-12-22 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 35/7 | COMPLETED
2024-12-17 | 2024-12-24 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/5 | COMPLETED
2024-12-13 | 2024-12-25 | Punam Devi 3 | 37.9311 | 2.9178 | TA413 | 36A/1 | COMPLETED
2024-12-15 | 2024-12-26 | Punam Devi 1 | 34.7898 | 2.8992 | TA413 | 7/1 | COMPLETED
2024-12-23 | 2024-12-28 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 35/8 | COMPLETED
2024-12-17 | 2024-12-29 | Vasu Dev Singh 1 | 45.697 | 3.5152 | TA413 | 34/5 | COMPLETED
2024-12-22 | 2024-12-29 | Vasu Dev Singh 2 | 34.7898 | 4.3487 | TA413 | 34/10 | COMPLETED
2024-12-24 | 2024-12-31 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/4 | COMPLETED
2024-12-27 | 2025-01-03 | Punam Devi 1 | 43.8044 | 5.4756 | TA413 | 7/2 | COMPLETED
2024-12-24 | 2025-01-03 | Punam Devi 3 | 37.9311 | 3.4483 | TA413 | 35/11 | COMPLETED
2024-12-29 | 2025-01-05 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 35/6 | COMPLETED
2024-12-30 | 2025-01-07 | Vasu Dev Singh 2 | 37.1383 | 4.1265 | TA413 | 34/11 | COMPLETED
2025-01-01 | 2025-01-08 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 7A/3 | COMPLETED
2024-12-30 | 2025-01-09 | Vasu Dev Singh 1 | 37.9311 | 3.4483 | TA413 | 34/6 | COMPLETED
2025-01-04 | 2025-01-09 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/5 | COMPLETED
2025-01-04 | 2025-01-11 | Punam Devi 3 | 45.697 | 5.7121 | TA413 | 36A/2 | COMPLETED
2025-01-06 | 2025-01-13 | Punam Devi 2 | 45.697 | 5.7121 | TA413 | 35/5 | COMPLETED
2025-01-10 | 2025-01-15 | Punam Devi 1 | 37.9311 | 6.3218 | TA413 | 8/6 | COMPLETED
2025-01-08 | 2025-01-16 | Punam Devi 2 | 37.9311 | 4.2146 | TA413 | 7A/2 | COMPLETED
2025-01-07 | 2025-01-19 | Vasu Dev Singh 2 | 43.8044 | 3.3696 | TA413 | 35/1 | COMPLETED
2025-01-14 | 2025-01-19 | Punam Devi 2 | 45.697 | 7.6162 | TA413 | 35/4 | COMPLETED
2025-01-16 | 2025-01-20 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 8/7 | COMPLETED
2025-01-10 | 2025-01-21 | Vasu Dev Singh 1 | 45.697 | 3.8081 | TA413 | 34/2 | COMPLETED
2025-01-11 | 2025-01-22 | Punam Devi 3 | 45.697 | 3.8081 | TA413 | 37/4 | COMPLETED
2025-01-17 | 2025-01-22 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 7A/1 | COMPLETED
2025-01-17 | 2025-01-24 | Punam Devi 2 | 37.1383 | 4.6423 | TA413 | 35/9 | COMPLETED
2025-01-20 | 2025-01-25 | Punam Devi 1 | 45.697 | 7.6162 | TA413 | 8/8 | COMPLETED
2025-01-21 | 2025-01-29 | Vasu Dev Singh 1 | 45.697 | 5.0774 | TA413 | 34/1 | COMPLETED
2025-01-24 | 2025-01-29 | Punam Devi 2 | 37.9311 | 6.3218 | TA413 | 38/3 | COMPLETED
2025-01-25 | 2025-01-30 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 8/9 | COMPLETED
2025-01-22 | 2025-01-30 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37/5 | COMPLETED
2025-01-22 | 2025-01-31 | Punam Devi 2 | 65.0278 | 6.5028 | TA413 | 7A/0 | COMPLETED
2025-01-17 | 2025-01-31 | Vasu Dev Singh 1 | 65.0278 | 4.3352 | TA413 | 34/0 | COMPLETED
2025-01-30 | 2025-02-03 | Punam Devi 4 | 36.1598 | 7.232 | TA413 | 8/10 | COMPLETED
2025-01-29 | 2025-02-04 | Punam Devi 1 | 43.8044 | 6.2578 | TA413 | 38/6 | COMPLETED
2025-01-29 | 2025-02-07 | Punam Devi 3 | 37.1383 | 3.7138 | TA413 | 37A/2 | COMPLETED
2025-01-29 | 2025-02-08 | Vasu Dev Singh 2 | 43.8044 | 3.9822 | TA413 | 33/6 | COMPLETED
2025-02-03 | 2025-02-08 | Punam Devi 4 | 43.8044 | 7.3007 | TA413 | 8/2 | COMPLETED
2025-01-31 | 2025-02-10 | Punam Devi 2 | 35.6018 | 3.2365 | TA413 | 7/6 | COMPLETED
2025-02-05 | 2025-02-10 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/4 | COMPLETED
2025-02-09 | 2025-02-14 | Punam Devi 4 | 55.4509 | 9.2418 | TA413 | 8/0 | COMPLETED
2025-02-11 | 2025-02-15 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 38/5 | COMPLETED
2025-02-08 | 2025-02-16 | Punam Devi 3 | 37.9311 | 4.2146 | TA413 | 37A/1 | COMPLETED
2025-01-31 | 2025-02-18 | Vasu Dev Singh 1 | 36.1598 | 1.9031 | TA413 | 33/5 | COMPLETED
2025-02-15 | 2025-02-18 | Punam Devi 1 | 36.1598 | 9.0399 | TA413 | 38/9 | COMPLETED
2025-02-11 | 2025-02-19 | Punam Devi 2 | 43.8044 | 4.8672 | TA413 | 7/5 | COMPLETED
2025-02-14 | 2025-02-19 | Punam Devi 4 | 45.697 | 7.6162 | TA413 | 8/3 | COMPLETED
2025-02-09 | 2025-02-23 | Vasu Dev Singh 2 | 59.5006 | 3.9667 | TA413 | 35/0 | COMPLETED
2025-02-18 | 2025-02-24 | Punam Devi 1 | 37.9311 | 5.4187 | TA413 | 38/10 | COMPLETED
2025-02-20 | 2025-02-24 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 8/4 | COMPLETED
2025-02-16 | 2025-02-25 | Punam Devi 3 | 37.9311 | 3.7931 | TA413 | 37A/3 | COMPLETED
2025-02-20 | 2025-02-27 | Punam Devi 2 | 43.8044 | 5.4756 | TA413 | 7/4 | COMPLETED
2025-02-24 | 2025-02-28 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 9/1 | COMPLETED
2025-02-24 | 2025-02-28 | Punam Devi 1 | 37.9311 | 7.5862 | TA413 | 37A/5 | COMPLETED
2025-02-18 | 2025-03-04 | Vasu Dev Singh 1 | 37.9311 | 2.5287 | TA413 | 33/8 | COMPLETED
2025-03-01 | 2025-03-04 | Punam Devi 4 | 36.1598 | 9.0399 | TA413 | 9/3 | COMPLETED
2025-03-01 | 2025-03-06 | Punam Devi 1 | 36.1598 | 6.0266 | TA413 | 38/1 | COMPLETED
2025-02-25 | 2025-03-06 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 37A/4 | COMPLETED
2025-02-24 | 2025-03-08 | Vasu Dev Singh 2 | 37.9311 | 2.9178 | TA413 | 37A/6 | COMPLETED
2025-03-05 | 2025-03-09 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 9/4 | COMPLETED
2025-02-28 | 2025-03-11 | Punam Devi 2 | 55.4509 | 4.6209 | TA413 | 37A/0 | COMPLETED
2025-03-07 | 2025-03-11 | Punam Devi 1 | 36.1598 | 7.232 | TA413 | 38/2 | COMPLETED
2025-03-07 | 2025-03-13 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/7 | COMPLETED
2025-03-10 | 2025-03-13 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 9/2 | COMPLETED
2025-03-14 | 2025-03-18 | Punam Devi 4 | 37.9311 | 7.5862 | TA413 | 15/2 | COMPLETED
2025-03-12 | 2025-03-18 | Punam Devi 1 | 45.697 | 6.5281 | TA413 | 38/7 | COMPLETED
2025-03-12 | 2025-03-19 | Punam Devi 2 | 37.9311 | 4.7414 | TA413 | 39/2 | COMPLETED
2025-03-14 | 2025-03-20 | Punam Devi 3 | 37.1383 | 5.3055 | TA413 | 39/5 | COMPLETED
2025-03-09 | 2025-03-21 | Vasu Dev Singh 2 | 59.5006 | 4.577 | TA413 | 39/0 | COMPLETED
2025-03-19 | 2025-03-22 | Punam Devi 4 | 37.9311 | 9.4828 | TA413 | 15/3 | COMPLETED
2025-03-19 | 2025-03-24 | Punam Devi 1 | 37.1383 | 6.1897 | TA413 | 38/8 | COMPLETED
2025-03-20 | 2025-03-25 | Punam Devi 2 | 37.1383 | 6.1897 | TA413 | 39/3 | COMPLETED
2025-03-21 | 2025-03-27 | Punam Devi 3 | 37.9311 | 5.4187 | TA413 | 39/4 | COMPLETED
2025-03-23 | 2025-03-27 | Punam Devi 4 | 43.8044 | 8.7609 | TA413 | 15/4 | COMPLETED
2025-03-22 | 2025-03-29 | Vasu Dev Singh 2 | 35.6018 | 4.4502 | TA413 | 39/1 | COMPLETED
2025-03-25 | 2025-03-30 | Punam Devi 1 | 43.8044 | 7.3007 | TA413 | 39/9 | COMPLETED
2025-03-26 | 2025-03-31 | Punam Devi 2 | 43.8044 | 7.3007 | TA413 | 40/2 | COMPLETED
2025-03-26 | 2025-03-31 | Punam Devi 4 | 37.9311 | 6.3218 | TA413 | 15/5 | COMPLETED
2024-03-26 | 2025-03-31 | Punam Devi 3 | 37.1383 | 0.1001 | TA413 | 39/8 | COMPLETED
2025-03-31 | 2025-04-05 | Punam Devi 3 | 37.9311 | 6.3218 | TA413 | 39/10 | COMPLETED
2025-03-31 | 2025-04-06 | Punam Devi 4 | 45.697 | 6.5281 | TA413 | 15/6 | COMPLETED
2025-03-30 | 2025-04-09 | Punam Devi 1 | 43.8044 | 3.9822 | TA413 | 39/11 | COMPLETED
2025-03-31 | 2025-04-09 | Punam Devi 2 | 37.9311 | 3.7931 | TA413 | 40/3 | COMPLETED
2025-03-29 | 2025-04-11 | Vasu Dev Singh 2 | 57.9632 | 4.1402 | TA413 | 38/0 | COMPLETED
2025-04-05 | 2025-04-14 | Punam Devi 3 | 45.697 | 4.5697 | TA413 | 40/5 | COMPLETED
2025-04-09 | 2025-04-18 | Punam Devi 2 | 43.8044 | 4.3804 | TA413 | 40/4 | COMPLETED
2025-04-09 | 2025-04-18 | Punam Devi 1 | 37.1383 | 3.7138 | TA413 | 39/6 | COMPLETED
2025-04-14 | 2025-04-22 | Punam Devi 3 | 45.697 | 5.0774 | TA413 | 40/6 | COMPLETED
2025-04-18 | 2025-04-30 | Punam Devi 2 | 66.7809 | 5.137 | TA413 | 36A/0 | COMPLETED
2025-04-18 | 2025-04-30 | Punam Devi 1 | 65.0278 | 5.0021 | TA413 | 40/0 | COMPLETED
2025-07-06 | 2025-07-15 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/6 | COMPLETED
2025-07-05 | 2025-07-17 | Amit Kumar Singh | 43.8044 | 3.3696 | TA413 | 32/1 | COMPLETED
2025-07-09 | 2025-07-21 | Pritam Enterprises | 45.697 | 3.5152 | TA413 | 7/3 | COMPLETED
2025-07-16 | 2025-07-25 | Punam Kumari | 45.697 | 4.5697 | TA413 | 32/5 | COMPLETED
2025-07-16 | 2025-07-26 | Jwala Singh 1 | 45.697 | 4.1543 | TA413 | 6/1 | COMPLETED
2025-07-18 | 2025-07-26 | Amit Kumar Singh | 45.697 | 5.0774 | TA413 | 32/2 | COMPLETED
2025-07-22 | 2025-07-31 | Pritam Enterprises | 59.5006 | 5.9501 | TA413 | 7/0 | COMPLETED
2025-07-26 | 2025-07-31 | Punam Kumari | 37.9311 | 6.3218 | TA413 | 32/7 | COMPLETED
2025-07-16 | 2025-08-01 | Sk Samiul 1 | 55.4509 | 3.2618 | TA413 | 31/0 | COMPLETED
2025-07-21 | 2025-08-02 | Fouzi Ratto | 59.5006 | 4.577 | TA413 | 42/0 | COMPLETED
2025-07-15 | 2025-08-03 | Jwala Singh 1 | 45.697 | 2.2849 | TA413 | 8/11 | COMPLETED
2025-07-18 | 2025-08-03 | Sk Samiul 2 | 37.9311 | 2.2312 | TA413 | 30/10 | COMPLETED
2025-07-27 | 2025-08-05 | Amit Kumar Singh | 43.8044 | 4.3804 | TA413 | 32/3 | COMPLETED
2025-08-02 | 2025-08-06 | Fouzi Ratto | 37.9311 | 7.5862 | TA413 | 42/1 | COMPLETED
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED
2025-08-04 | 2025-08-08 | Jwala Singh 1 | 43.8044 | 8.7609 | TA413 | 6/2 | COMPLETED
2025-08-01 | 2025-08-09 | Punam Kumari | 66.7809 | 7.4201 | TA413 | 32A/0 | COMPLETED
2025-08-01 | 2025-08-09 | Jwala Singh 2 | 43.8044 | 4.8672 | TA413 | 35/2 | COMPLETED
2025-08-01 | 2025-08-09 | Pritam Enterprises 1 | 37.1383 | 4.1265 | TA413 | 6/12 | COMPLETED
2025-08-02 | 2025-08-10 | Sk Samiul 1 | 37.9311 | 4.2146 | TA413 | 31/1 | COMPLETED
2025-08-04 | 2025-08-11 | Sk Samiul 2 | 37.1383 | 4.6423 | TA413 | 31/2 | COMPLETED
2025-08-07 | 2025-08-11 | Fouzi Ratto | 45.697 | 9.1394 | TA413 | 42/2 | COMPLETED
2025-08-01 | 2025-08-13 | Pinki Devi | 45.697 | 3.5152 | TA413 | 40/9 | COMPLETED
2025-08-02 | 2025-08-13 | Pritam Enterprises 2 | 45.697 | 3.8081 | TA413 | 6/5 | COMPLETED
2025-08-07 | 2025-08-14 | Amit Kumar Singh | 45.697 | 5.7121 | TA413 | 32/4 | COMPLETED
2025-08-08 | 2025-08-14 | Jwala Singh 1 | 37.9311 | 5.4187 | TA413 | 6/3 | COMPLETED
2025-08-07 | 2025-08-14 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 8A/0 | COMPLETED
2025-08-09 | 2025-08-17 | Punam Kumari 1 | 45.697 | 5.0774 | TA413 | 33/2 | COMPLETED
2025-08-09 | 2025-08-18 | Pritam Enterprises 1 | 37.1383 | 3.7138 | TA413 | 6/10 | COMPLETED
2025-08-15 | 2025-08-19 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 9/5 | COMPLETED
2025-08-12 | 2025-08-19 | Fouzi Ratto | 66.7809 | 8.3476 | TA413 | 42/3 | COMPLETED
2025-08-08 | 2025-08-20 | Pritam Enterprises 4 | 37.9311 | 2.9178 | TA413 | 5/6 | COMPLETED
2025-08-14 | 2025-08-20 | Pinki Devi | 37.9311 | 5.4187 | TA413 | 40/7 | COMPLETED
2025-08-07 | 2025-08-21 | Pritam Enterprises 3 | 83.1335 | 5.5422 | TA413 | 1/0 | COMPLETED
2025-08-13 | 2025-08-21 | Jwala Singh 2 | 66.7809 | 7.4201 | TA413 | 6/0 | COMPLETED
2025-08-14 | 2025-08-21 | Pritam Enterprises 2 | 34.7898 | 4.3487 | TA413 | 6/6 | COMPLETED
2025-08-15 | 2025-08-21 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 6/4 | COMPLETED
2025-08-12 | 2025-08-21 | Sk Samiul 2 | 34.7898 | 3.479 | TA413 | 30/9 | COMPLETED
2025-08-12 | 2025-08-22 | Sk Samiul 1 | 37.9311 | 3.4483 | TA413 | 31/3 | COMPLETED
2025-08-18 | 2025-08-22 | Punam Kumari 1 | 37.1383 | 7.4277 | TA413 | 33/9 | COMPLETED
2025-08-19 | 2025-08-25 | Pritam Enterprises 1 | 35.6018 | 5.086 | TA413 | 6/11 | COMPLETED
2025-08-20 | 2025-08-25 | Punam Kumari 2 | 37.9311 | 6.3218 | TA413 | 9/6 | COMPLETED
2025-08-20 | 2025-08-25 | Fouzi Ratto | 43.8044 | 7.3007 | TA413 | 43/2 | COMPLETED
2025-08-15 | 2025-08-25 | Amit Kumar Singh | 42.9218 | 3.902 | TA413 | 31/10 | COMPLETED
2025-08-21 | 2025-08-27 | Pritam Enterprises 3 | 36.1598 | 5.1657 | TA413 | 2A/1 | COMPLETED
2025-08-18 | 2025-08-28 | Govind Mahto 1 | 43.8044 | 3.9822 | TA413 | 4A/4 | COMPLETED
2025-08-20 | 2025-08-28 | Pritam Enterprises 4 | 43.8044 | 4.8672 | TA413 | 5/5 | COMPLETED
2025-08-22 | 2025-08-28 | Pritam Enterprises 2 | 37.1383 | 5.3055 | TA413 | 6/7 | COMPLETED
2025-08-22 | 2025-08-28 | Jwala Singh 1 | 45.697 | 6.5281 | TA413 | 5/10 | COMPLETED
2025-08-23 | 2025-08-29 | Punam Kumari 2 | 45.697 | 6.5281 | TA413 | 9/7 | COMPLETED
2025-08-23 | 2025-08-30 | Punam Kumari 1 | 43.8044 | 5.4756 | TA413 | 33/7 | COMPLETED
2025-08-22 | 2025-08-31 | Sk Samiul 2 | 35.6018 | 3.5602 | TA413 | 31/4 | COMPLETED
2025-08-22 | 2025-09-01 | Jwala Singh 2 | 70.7883 | 6.4353 | TA413 | 5A/0 | COMPLETED
2025-08-14 | 2025-09-02 | Amar Kumar Singh | 43.8044 | 2.1902 | TA413 | 32A/1 | COMPLETED
2025-08-23 | 2025-09-02 | Pritam Enterprises 2 | 43.8044 | 3.9822 | TA413 | 6/9 | COMPLETED
2025-08-28 | 2025-09-02 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/2 | COMPLETED
2025-08-23 | 2025-09-02 | Fouzi Ratto | 35.6018 | 3.2365 | TA413 | 43/3 | COMPLETED
2025-08-23 | 2025-09-03 | Sk Samiul 1 | 43.8044 | 3.6504 | TA413 | 31/5 | COMPLETED
2025-08-23 | 2025-09-03 | Amit Kumar Singh | 37.1383 | 3.0949 | TA413 | 31/9 | COMPLETED
2025-08-25 | 2025-09-03 | Ved Prakash | 37.9311 | 3.7931 | TA413 | 44/1 | COMPLETED
2025-08-31 | 2025-09-04 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/3 | COMPLETED
2025-08-29 | 2025-09-05 | Jwala Singh 1 | 43.8044 | 5.4756 | TA413 | 5/9 | COMPLETED
2025-08-29 | 2025-09-06 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 6/8 | COMPLETED
2025-08-30 | 2025-09-06 | Punam Kumari 2 | 70.7883 | 8.8485 | TA413 | 9/0 | COMPLETED
2025-08-29 | 2025-09-06 | Govind Mahto 1 | 45.697 | 5.0774 | TA413 | 4A/3 | COMPLETED
2025-09-03 | 2025-09-07 | Fouzi Ratto | 36.1598 | 7.232 | TA413 | 43/4 | COMPLETED
2025-08-29 | 2025-09-08 | Pritam Enterprises 4 | 35.6018 | 3.2365 | TA413 | 5/4 | COMPLETED
2025-09-03 | 2025-09-08 | Pritam Enterprises 3 | 37.9311 | 6.3218 | TA413 | 2A/3 | COMPLETED
2025-08-25 | 2025-09-08 | Govind Mahto 2 | 45.697 | 3.0465 | TA413 | 4A/5 | COMPLETED
2025-08-29 | 2025-09-08 | Punam Kumari 3 | 43.8044 | 3.9822 | TA413 | 30/6 | COMPLETED
2025-09-02 | 2025-09-09 | Jwala Singh 2 | 45.697 | 5.7121 | TA413 | 5/7 | COMPLETED
2025-09-04 | 2025-09-09 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/2 | COMPLETED
2025-09-05 | 2025-09-09 | Punam Kumari 1 | 37.9311 | 7.5862 | TA413 | 33/4 | COMPLETED
2025-08-25 | 2025-09-10 | Bhairaw Mahto | 45.697 | 2.6881 | TA413 | 33/1 | COMPLETED
2025-09-03 | 2025-09-11 | Pritam Enterprises 1 | 37.9311 | 4.2146 | TA413 | 3A/1 | COMPLETED
2025-09-08 | 2025-09-11 | Fouzi Ratto | 37.9311 | 9.4828 | TA413 | 43/6 | COMPLETED
2025-09-06 | 2025-09-12 | Jwala Singh 1 | 43.8044 | 6.2578 | TA413 | 4/5 | COMPLETED
2025-09-09 | 2025-09-13 | Punam Kumari 3 | 34.7898 | 6.958 | TA413 | 30/7 | COMPLETED
2025-09-04 | 2025-09-14 | Amit Kumar Singh | 59.5006 | 5.4091 | TA413 | 32/0 | COMPLETED
2025-09-09 | 2025-09-15 | Punam Kumari 4 | 45.697 | 6.5281 | TA413 | 30/4 | COMPLETED
2025-09-07 | 2025-09-15 | Punam Kumari 2 | 69.376 | 7.7084 | TA413 | 18/0 | COMPLETED
2025-09-09 | 2025-09-15 | Pritam Enterprises 3 | 37.9311 | 5.4187 | TA413 | 2A/4 | COMPLETED
2025-09-10 | 2025-09-15 | Jwala Singh 2 | 43.8044 | 7.3007 | TA413 | 5/8 | COMPLETED
2025-09-10 | 2025-09-15 | Ved Prakash | 37.9311 | 6.3218 | TA413 | 44/3 | COMPLETED
2025-09-07 | 2025-09-15 | Pritam Enterprises 2 | 37.9311 | 4.2146 | TA413 | 3A/5 | COMPLETED
2025-09-07 | 2025-09-16 | Govind Mahto 1 | 43.8044 | 4.3804 | TA413 | 4A/2 | COMPLETED
2025-09-10 | 2025-09-16 | Punam Kumari 1 | 36.1598 | 5.1657 | TA413 | 31/7 | COMPLETED
2025-09-04 | 2025-09-18 | Sk Samiul 1 | 45.697 | 3.0465 | TA413 | 31/6 | COMPLETED
2025-09-09 | 2025-09-18 | Govind Mahto 2 | 45.697 | 4.5697 | TA413 | 4A/6 | COMPLETED
2025-09-14 | 2025-09-19 | Fouzi Ratto | 45.697 | 7.6162 | TA413 | 43/8 | COMPLETED
2025-09-16 | 2025-09-19 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/4 | COMPLETED
2025-09-12 | 2025-09-19 | Pritam Enterprises 1 | 37.9311 | 4.7414 | TA413 | 3A/2 | COMPLETED
2025-09-04 | 2025-09-20 | Kartik Mahto | 66.7809 | 3.9283 | TA413 | 40A/0 | COMPLETED
2025-09-03 | 2025-09-20 | Amar Kumar Singh | 66.7809 | 3.7101 | TA413 | 33/0 | COMPLETED
2025-09-16 | 2025-09-20 | Punam Kumari 2 | 37.9311 | 7.5862 | TA413 | 18/1 | COMPLETED
2025-09-15 | 2025-09-21 | Amit Kumar Singh | 36.1598 | 5.1657 | TA413 | 31/8 | COMPLETED
2025-09-14 | 2025-09-22 | Punam Kumari 3 | 37.9311 | 4.2146 | TA413 | 30/8 | COMPLETED
2025-09-16 | 2025-09-23 | Pritam Enterprises 3 | 37.9311 | 4.7414 | TA413 | 2A/5 | COMPLETED
2025-09-20 | 2025-09-23 | Ved Prakash | 36.1598 | 9.0399 | TA413 | 44/5 | COMPLETED
2025-09-16 | 2025-09-24 | Pritam Enterprises 2 | 36.1598 | 4.0178 | TA413 | 3A/6 | COMPLETED
2025-09-13 | 2025-09-24 | Jwala Singh 1 | 57.9632 | 4.8303 | TA413 | 4A/0 | COMPLETED
2025-09-11 | 2025-09-25 | Punam Kumari 4 | 55.4509 | 3.6967 | TA413 | 30/0 | COMPLETED
2025-09-13 | 2025-09-25 | Jwala Singh 2 | 43.8044 | 3.3696 | TA413 | 5/1 | COMPLETED
2025-09-18 | 2025-09-25 | Govind Mahto 1 | 43.8044 | 5.4756 | TA413 | 4A/1 | COMPLETED
2025-09-19 | 2025-09-25 | Punam Kumari 1 | 34.7898 | 4.97 | TA413 | 20/1 | COMPLETED
2025-09-21 | 2025-09-25 | Punam Kumari 2 | 37.1383 | 7.4277 | TA413 | 18/2 | COMPLETED
2025-09-11 | 2025-09-26 | Bhairaw Mahto | 66.7809 | 4.1738 | TA413 | 12/0 | COMPLETED
2025-09-20 | 2025-09-27 | Pritam Enterprises 1 | 36.1598 | 4.52 | TA413 | 3A/3 | COMPLETED
2025-09-24 | 2025-09-28 | Ved Prakash | 36.1598 | 7.232 | TA413 | 43/7 | COMPLETED
2025-09-20 | 2025-09-29 | Fouzi Ratto | 65.0278 | 6.5028 | TA413 | 44/0 | COMPLETED
2025-09-21 | 2025-09-29 | Kartik Mahto | 45.697 | 5.0774 | TA413 | 40/11 | COMPLETED
2025-09-19 | 2025-09-30 | Govind Mahto 2 | 65.0278 | 5.419 | TA413 | 5/0 | COMPLETED
2025-09-26 | 2025-09-30 | Punam Kumari 1 | 34.7898 | 6.958 | TA413 | 20/2 | COMPLETED
2025-09-26 | 2025-09-30 | Punam Kumari 2 | 43.8044 | 8.7609 | TA413 | 18/3 | COMPLETED
2025-09-24 | 2025-09-30 | Pritam Enterprises 3 | 43.8044 | 6.2578 | TA413 | 2A/6 | COMPLETED
2025-09-09 | 2025-09-30 | Pritam Enterprises 4 | 45.697 | 2.0771 | TA413 | 5/3 | COMPLETED
2025-09-26 | 2025-09-30 | Jwala Singh 2 | 45.697 | 9.1394 | TA413 | 5/2 | COMPLETED
2024-07-10 | 2024-07-19 | Khatan | 36.37 | 3.637 | TA421 | 25/4 | Completed
2024-07-18 | 2024-07-28 | Khatan | 36.37 | 3.3064 | TA421 | 26/1 | Completed
2024-07-27 | 2024-08-03 | Khatan | 36.37 | 4.5462 | TA421 | 26/4 | Completed
2024-08-02 | 2024-08-09 | Khatan | 36.37 | 4.5462 | TA421 | 25/1 | Completed
2024-08-09 | 2024-08-14 | Khatan | 36.37 | 6.0617 | TA421 | 26/2 | Completed
2024-08-16 | 2024-08-18 | Khatan | 36.37 | 12.1233 | TA421 | 26/3 | Completed
2024-08-19 | 2024-08-24 | Khatan | 36.37 | 6.0617 | TA421 | 27/1 | Completed
2024-08-22 | 2024-08-29 | Khatan | 36.37 | 4.5462 | TA421 | 24/5 | Completed
2024-08-29 | 2024-09-06 | Khatan | 36.37 | 4.0411 | TA421 | 24/4 | Completed
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed
2024-08-29 | 2024-09-12 | Khatan | 36.37 | 2.4247 | TA421 | 24/3 | Completed
2024-09-14 | 2024-09-19 | Khatan | 36.37 | 6.0617 | TA421 | 27/2 | Completed
2024-09-09 | 2024-09-21 | S K Janarul Sheikh | 36.37 | 2.7977 | TA421 | 21/9 | Completed
2024-09-19 | 2024-09-23 | Khatan | 36.37 | 7.274 | TA421 | 27/4 | Completed
2024-09-24 | 2024-09-28 | Khatan | 36.37 | 7.274 | TA421 | 27/5 | Completed
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed
2024-09-14 | 2024-09-30 | Maa Const | 37.9313 | 2.2313 | TA421 | 12/3 | Completed
2024-09-29 | 2024-10-03 | Khatan | 36.37 | 7.274 | TA421 | 27/6 | Completed
2024-09-26 | 2024-10-03 | S K Janarul Sheikh | 36.37 | 4.5462 | TA421 | 23/2 | Completed
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed
2024-10-03 | 2024-10-07 | Khatan | 36.37 | 7.274 | TA421 | 27/7 | Completed
2024-10-05 | 2024-10-14 | Khatan | 37.9313 | 3.7931 | TA421 | 29/5 | Completed
2024-10-05 | 2024-10-14 | S K Janarul Sheikh | 36.37 | 3.637 | TA421 | 23/4 | Completed
2024-10-01 | 2024-10-17 | Ashok | 36.37 | 2.1394 | TA421 | 21/8 | Completed
2024-10-01 | 2024-10-19 | Maa Const | 37.9313 | 1.9964 | TA421 | 12/4 | Completed
2024-10-16 | 2024-10-21 | Khatun | 37.9313 | 6.3219 | TA421 | 30/4 | Completed
2024-10-21 | 2024-10-26 | Khatan | 37.9313 | 6.3219 | TA421 | 24/8 | Completed
2024-10-01 | 2024-10-26 | Praveen | 37.9313 | 1.4589 | TA421 | 12/9 | Completed
2024-10-17 | 2024-10-27 | Subash | 37.9313 | 3.4483 | TA421 | 22/4 | Completed
2024-10-18 | 2024-10-27 | Ashok | 36.37 | 3.637 | TA421 | 22/1 | Completed
2024-10-19 | 2024-10-30 | Maa Const | 36.37 | 3.0308 | TA421 | 12/2 | Completed
2024-10-27 | 2024-11-01 | Khatun | 36.37 | 6.0617 | TA421 | 24/7 | Completed
2024-10-16 | 2024-11-01 | Subash | 36.37 | 2.1394 | TA421 | 23/3 | Completed
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed
2024-11-01 | 2024-11-07 | Maa Const | 36.37 | 5.1957 | TA421 | 12/5 | Completed
2024-11-02 | 2024-11-07 | Subash | 54.655 | 9.1092 | TA421 | 24/0 | Completed
2024-11-02 | 2024-11-07 | Khatun | 54.66 | 9.11 | TA421 | 25/0 | Completed
2024-10-27 | 2024-11-12 | Praveen | 36.37 | 2.1394 | TA421 | 12/10 | Completed
2024-11-08 | 2024-11-13 | Khatun | 36.37 | 6.0617 | TA421 | 25/2 | Completed
2024-11-07 | 2024-11-14 | Maa Const | 36.37 | 4.5462 | TA421 | 12/6 | Completed
2024-11-09 | 2024-11-14 | Subash | 43.08 | 7.18 | TA421 | 23/1 | Completed
2024-11-05 | 2024-11-15 | Ashok | 54.66 | 4.9691 | TA421 | 22/0 | Completed
2024-11-13 | 2024-11-18 | Khatun | 36.37 | 6.0617 | TA421 | 24/6 | Completed
2024-11-15 | 2024-11-20 | Subash | 43.08 | 7.18 | TA421 | 24/1 | Completed
2024-11-14 | 2024-11-21 | Maa Const | 36.37 | 4.5462 | TA421 | 12/7 | Completed
2024-11-19 | 2024-11-24 | Khatun | 54.66 | 9.11 | TA421 | 26/0 | Completed
2024-11-16 | 2024-11-25 | Ashok | 37.93 | 3.793 | TA421 | 21/4 | Completed
2024-11-21 | 2024-11-26 | Subash | 54.66 | 9.11 | TA421 | 23/0 | Completed
2024-11-22 | 2024-11-30 | Maa Const | 54.66 | 6.0733 | TA421 | 12/0 | Completed
2024-11-24 | 2024-11-30 | Khatun | 54.66 | 7.8086 | TA421 | 27/0 | Completed
2024-11-26 | 2024-12-02 | Subash | 36.37 | 5.1957 | TA421 | 21/2 | Completed
2024-11-12 | 2024-12-05 | Praveen | 37.93 | 1.5804 | TA421 | 12/8 | Completed
2024-12-03 | 2024-12-06 | Subash | 36.37 | 9.0925 | TA421 | 21/6 | Completed
2024-12-03 | 2024-12-08 | Khatun | 36.37 | 6.0617 | TA421 | 27/8 | Completed
2024-12-03 | 2024-12-11 | Subash | 37.93 | 4.2144 | TA421 | 24/2 | Completed
2024-12-09 | 2024-12-13 | Khatun | 36.37 | 7.274 | TA421 | 29/3 | Completed
2024-12-11 | 2024-12-15 | Subash | 37.93 | 7.586 | TA421 | 19/3 | Completed
2024-12-16 | 2024-12-18 | Subash | 36.37 | 12.1233 | TA421 | 19/2 | Completed
2024-12-15 | 2024-12-19 | Khatun | 36.37 | 7.274 | TA421 | 29/8 | Completed
2024-12-19 | 2024-12-22 | Subash | 36.37 | 9.0925 | TA421 | 18/3 | Completed
2024-12-23 | 2024-12-25 | Subash | 36.37 | 12.1233 | TA421 | 18/2 | Completed
2024-12-20 | 2024-12-25 | Khatun | 44.825 | 7.4708 | TA421 | 29/1 | Completed
2024-12-12 | 2024-12-28 | Praveen | 37.93 | 2.2312 | TA421 | 11/11 | Completed
2024-12-26 | 2024-12-28 | Subash | 36.37 | 12.1233 | TA421 | 18/1 | Completed
2024-12-26 | 2024-12-31 | Khatun | 37.93 | 6.3217 | TA421 | 30/3 | Completed
2024-12-27 | 2025-01-03 | Subash | 54.66 | 6.8325 | TA421 | 18/0 | Completed
2024-12-02 | 2025-01-06 | Khatun | 37.93 | 1.0536 | TA421 | 30/2 | Completed
2025-01-03 | 2025-01-08 | Subash | 37.93 | 6.3217 | TA421 | 17/1 | Completed
2024-12-28 | 2025-01-13 | Subash | 36.37 | 2.1394 | TA421 | 21/1 | Completed
2025-01-04 | 2025-01-15 | Khatun | 37.93 | 3.1608 | TA421 | 30/1 | Completed
2025-01-02 | 2025-01-15 | Praveen | 36.37 | 2.5979 | TA421 | 11/10 | Completed
2025-01-14 | 2025-01-18 | Subash | 36.37 | 7.274 | TA421 | 16/6 | Completed
2025-01-16 | 2025-01-19 | Khatun | 36.37 | 9.0925 | TA421 | 29/6 | Completed
2025-01-18 | 2025-01-22 | Subash | 37.93 | 7.586 | TA421 | 16/8 | Completed
2025-01-19 | 2025-01-23 | Khatun | 36.37 | 7.274 | TA421 | 29/2 | Completed
2025-01-22 | 2025-01-27 | Subash | 37.93 | 6.3217 | TA421 | 16/10 | Completed
2025-01-23 | 2025-01-28 | Khatun | 36.37 | 6.0617 | TA421 | 30/5 | Completed
2025-01-16 | 2025-01-30 | Praveen | 36.37 | 2.4247 | TA421 | 11/6 | Completed
2025-01-22 | 2025-01-30 | Subash | 36.37 | 4.0411 | TA421 | 16/9 | Completed
2025-01-28 | 2025-02-03 | Khatun | 37.93 | 5.4186 | TA421 | 31/1 | Completed
2025-01-30 | 2025-02-03 | Subash | 36.37 | 7.274 | TA421 | 16/2 | Completed
2025-02-04 | 2025-02-08 | Subash | 36.37 | 7.274 | TA421 | 13/2 | Completed
2025-02-04 | 2025-02-09 | Khatun | 36.37 | 6.0617 | TA421 | 31/4 | Completed
2025-01-30 | 2025-02-10 | Praveen | 36.37 | 3.0308 | TA421 | 11/5 | Completed
2025-02-09 | 2025-02-12 | Subash | 37.93 | 9.4825 | TA421 | 13/1 | Completed
2025-02-10 | 2025-02-14 | Khatun | 36.37 | 7.274 | TA421 | 31/5 | Completed
2025-02-10 | 2025-02-18 | J Lngh | 36.37 | 4.0411 | TA421 | 25/3 | Completed
2025-02-13 | 2025-02-19 | Subash | 43.08 | 6.1543 | TA421 | 13/3 | Completed
2025-02-15 | 2025-02-20 | Khatun | 37.93 | 6.3217 | TA421 | 31/6 | Completed
2025-02-11 | 2025-02-21 | Praveen | 43.08 | 3.9164 | TA421 | 12/11 | Completed
2025-02-19 | 2025-02-23 | Subash | 37.93 | 7.586 | TA421 | 13/4 | Completed
2025-02-19 | 2025-02-25 | J Lngh | 43.08 | 6.1543 | TA421 | 25/5 | Completed
2025-02-21 | 2025-02-25 | Khatun | 36.37 | 7.274 | TA421 | 31/2 | Completed
2025-02-24 | 2025-02-27 | Subash | 43.08 | 10.77 | TA421 | 13/6 | Completed
2025-02-22 | 2025-03-01 | Praveen | 36.37 | 4.5462 | TA421 | 11/9 | Completed
2025-02-26 | 2025-03-01 | Khatun | 37.93 | 9.4825 | TA421 | 29/7 | Completed
2025-02-28 | 2025-03-02 | Subash | 36.37 | 12.1233 | TA421 | 13/5 | Completed
2025-02-26 | 2025-03-02 | J Lngh | 36.37 | 7.274 | TA421 | 38/1 | Completed
2025-03-03 | 2025-03-07 | Subash | 43.08 | 8.616 | TA421 | 13/7 | Completed
2025-03-02 | 2025-03-07 | Khatun | 54.66 | 9.11 | TA421 | 31/0 | Completed
2025-03-03 | 2025-03-09 | J Lngh | 37.93 | 5.4186 | TA421 | 38/3 | Completed
2025-03-08 | 2025-03-11 | Subash | 54.66 | 13.665 | TA421 | 13/0 | Completed
2025-03-03 | 2025-03-12 | Praveen | 43.08 | 4.308 | TA421 | 22/3 | Completed
2025-03-08 | 2025-03-12 | Khatun | 36.37 | 7.274 | TA421 | 32/1 | Completed
2025-03-10 | 2025-03-13 | J Lngh | 36.37 | 9.0925 | TA421 | 38/4 | Completed
2025-03-12 | 2025-03-16 | Subash | 36.37 | 7.274 | TA421 | 13/8 | Completed
2025-03-13 | 2025-03-17 | Khatun | 36.37 | 7.274 | TA421 | 33/1 | Completed
2025-03-16 | 2025-03-19 | Subash | 37.93 | 9.4825 | TA421 | 13/9 | Completed
2025-03-15 | 2025-03-19 | J Lngh | 36.37 | 7.274 | TA421 | 38/5 | Completed
2025-03-20 | 2025-03-22 | Subash | 36.37 | 12.1233 | TA421 | 13/10 | Completed
2025-03-20 | 2025-03-23 | J Lngh | 36.37 | 9.0925 | TA421 | 38/6 | Completed
2025-03-17 | 2025-03-23 | Khatun | 62.5353 | 8.9336 | TA421 | 32/0 | Completed
2025-03-23 | 2025-03-26 | Subash | 36.37 | 9.0925 | TA421 | 15/1 | Completed
2025-03-13 | 2025-03-27 | Praveen | 43.08 | 2.872 | TA421 | 21/3 | Completed
2025-03-23 | 2025-03-27 | Khatun | 37.93 | 7.586 | TA421 | 32/2 | Completed
2025-03-27 | 2025-03-29 | Subash | 37.93 | 12.6433 | TA421 | 15/2 | Completed
2025-03-24 | 2025-03-29 | J Lngh O 1 | 36.37 | 6.0617 | TA421 | 38/7 | Completed
2025-03-01 | 2025-03-30 | J Lngh O 2 | 37.93 | 1.2643 | TA421 | 36/3 | Completed
2025-03-28 | 2025-04-01 | Khatun | 43.08 | 8.616 | TA421 | 32/3 | Completed
2025-03-29 | 2025-04-02 | Subash | 37.93 | 7.586 | TA421 | 15/4 | Completed
2025-03-29 | 2025-04-04 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/5 | Completed
2025-03-30 | 2025-04-05 | J Lngh O 2 | 36.37 | 5.1957 | TA421 | 36/1 | Completed
2025-04-02 | 2025-04-09 | Khatun | 84.248 | 10.531 | TA421 | 33/0 | Completed
2025-04-03 | 2025-04-10 | Subash | 72.721 | 9.0901 | TA421 | 16/0 | Completed
2025-03-28 | 2025-04-11 | Praveen | 43.08 | 2.872 | TA421 | 19/1 | Completed
2025-04-06 | 2025-04-13 | J Lngh O 2 | 37.93 | 4.7412 | TA421 | 36/2 | Completed
2025-04-10 | 2025-04-14 | Khatun | 43.08 | 8.616 | TA421 | 35/4 | Completed
2025-04-11 | 2025-04-15 | Subash | 36.37 | 7.274 | TA421 | 16/1 | Completed
2025-04-05 | 2025-04-17 | J Lngh O 1 | 62.54 | 4.8108 | TA421 | 38/0 | Completed
2025-04-15 | 2025-04-18 | Khatun | 36.37 | 9.0925 | TA421 | 35/3 | Completed
2025-04-16 | 2025-04-19 | Subash | 37.93 | 9.4825 | TA421 | 16/3 | Completed
2025-04-19 | 2025-04-21 | Subash | 36.37 | 12.1233 | TA421 | 16/4 | Completed
2025-04-14 | 2025-04-21 | J Lngh O 2 | 36.37 | 4.5462 | TA421 | 36/5 | Completed
2025-04-19 | 2025-04-23 | Khatun | 62.54 | 12.508 | TA421 | 29/0 | Completed
2025-04-18 | 2025-04-23 | J Lngh O 1 | 43.08 | 7.18 | TA421 | 37/4 | Completed
2025-04-22 | 2025-04-24 | Subash | 36.37 | 12.1233 | TA421 | 16/5 | Completed
2025-04-12 | 2025-04-26 | Praveen | 43.08 | 2.872 | TA421 | 17/3 | Completed
2025-04-22 | 2025-04-27 | J Lngh O 2 | 37.93 | 6.3217 | TA421 | 36/4 | Completed
2025-04-25 | 2025-04-27 | Subash | 36.37 | 12.1233 | TA421 | 15/3 | Completed
2025-04-24 | 2025-04-28 | Khatun | 62.535 | 12.507 | TA421 | 28/0 | Completed
2025-04-24 | 2025-04-30 | J Lngh O 1 | 36.37 | 5.1957 | TA421 | 37/2 | Completed
2025-04-28 | 2025-04-30 | Subash | 36.37 | 12.1233 | TA421 | 13/11 | Completed
2025-04-29 | 2025-05-02 | Khatun | 37.93 | 9.4825 | TA421 | 27/9 | Completed
2025-05-01 | 2025-05-04 | Subash | 37.93 | 9.4825 | TA421 | 10/7 | Completed
2025-05-02 | 2025-05-05 | J Lngh O 1 | 36.37 | 9.0925 | TA421 | 38/2 | Completed
2025-05-05 | 2025-05-06 | Subash | 36.37 | 18.185 | TA421 | 11/1 | Completed
2025-05-03 | 2025-05-08 | Khatun | 72.72 | 12.12 | TA421 | 21/0 | Completed
2025-04-27 | 2025-05-09 | Praveen | 37.93 | 2.9177 | TA421 | 17/2 | Completed
2025-05-07 | 2025-05-10 | Subash | 43.08 | 10.77 | TA421 | 10/9 | Completed
2025-05-06 | 2025-05-10 | Jwala Singh 01 | 36.37 | 7.274 | TA421 | 37/3 | Completed
2025-05-10 | 2025-05-13 | Subash | 37.93 | 9.4825 | TA421 | 10/4 | Completed
2025-05-10 | 2025-05-14 | Khatun | 54.66 | 10.932 | TA421 | 20/0 | Completed
2025-05-11 | 2025-05-16 | Jwala Singh 01 | 36.37 | 6.0617 | TA421 | 37/6 | Completed
2025-05-14 | 2025-05-17 | Subash | 36.37 | 9.0925 | TA421 | 10/2 | Completed
2025-05-18 | 2025-05-20 | Subash | 37.93 | 12.6433 | TA421 | 10/1 | Completed
2025-05-15 | 2025-05-22 | Khatun | 72.72 | 9.09 | TA421 | 19/0 | Completed
2025-05-11 | 2025-05-24 | Hassan | 37.93 | 2.7093 | TA421 | 36/6 | Completed
2025-05-21 | 2025-05-28 | Subash | 37.93 | 4.7412 | TA421 | 10/3 | Completed
2025-05-08 | 2025-05-31 | Hassan | 36.37 | 1.5154 | TA421 | 35/1 | Completed
2025-05-29 | 2025-06-02 | Subash | 37.93 | 7.586 | TA421 | 10/5 | Completed
2025-05-10 | 2025-06-04 | Praveen | 62.535 | 2.4052 | TA421 | 17/0 | Completed
2025-06-01 | 2025-06-06 | Hassan | 34.946 | 5.8243 | TA421 | 31/3 | Completed
2025-06-03 | 2025-06-11 | Subash | 71.7057 | 7.9673 | TA421 | 30/0 | Completed
2025-06-05 | 2025-06-16 | Hassan | 34.946 | 2.9122 | TA421 | 33/2 | Completed
2025-06-06 | 2025-06-18 | Subash | 64.891 | 4.9916 | TA421 | 29/9 | Completed
2025-06-05 | 2025-06-19 | Praveen | 34.946 | 2.3297 | TA421 | 21/5 | Completed
2025-06-19 | 2025-06-24 | Subash | 43.08 | 7.18 | TA421 | 10/6 | Completed
2025-06-17 | 2025-06-25 | Hassan | 62.535 | 6.9483 | TA421 | 34/0 | Completed
2025-06-25 | 2025-06-28 | Subash | 36.372 | 9.093 | TA421 | 11/2 | Completed
2025-06-29 | 2025-07-02 | Subash | 34.946 | 8.7365 | TA421 | 11/3 | Completed
2025-06-24 | 2025-07-04 | Naziruddin | 76.193 | 6.9266 | TA421 | 15/0 | Completed
2025-06-25 | 2025-07-04 | Hassan | 36.372 | 3.6372 | TA421 | 35/2 | Completed
2025-06-24 | 2025-07-05 | Hassan 2 | 37.931 | 3.1609 | TA421 | 39/4 | Completed
2025-06-20 | 2025-07-07 | Praveen | 54.66 | 3.0367 | TA421 | 20A/0 | Completed
2025-07-03 | 2025-07-07 | Subash | 54.66 | 10.932 | TA421 | 10/0 | Completed
2025-07-04 | 2025-07-10 | Khatun | 31.99 | 4.57 | TA421 | 6/5 | Completed
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed
2025-07-06 | 2025-07-12 | Hassan 2 | 37.931 | 5.4187 | TA421 | 39/3 | Completed
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed
2025-07-11 | 2025-07-15 | Khatun | 31.99 | 6.398 | TA421 | 6/4 | Completed
2025-07-05 | 2025-07-16 | Hassan | 63.16 | 5.2633 | TA421 | 34/2 | Completed
2025-07-13 | 2025-07-16 | Subash | 31.99 | 7.9975 | TA421 | 9/8 | Completed
2025-07-15 | 2025-07-18 | Khatun | 31.99 | 7.9975 | TA421 | 6/3 | Completed
2025-07-17 | 2025-07-20 | Subash | 33.3756 | 8.3439 | TA421 | 9/7 | Completed
2025-07-12 | 2025-07-20 | D K Verma | 37.931 | 4.2146 | TA421 | 42/4 | Completed
2025-07-14 | 2025-07-21 | Naziruddin | 31.99 | 3.9987 | TA421 | 8/6 | Completed
2025-07-19 | 2025-07-21 | Khatun | 31.99 | 10.6633 | TA421 | 6/2 | Completed
2025-07-21 | 2025-07-25 | Subash | 33.38 | 6.676 | TA421 | 9/6 | Completed
2025-07-22 | 2025-07-28 | Khatun | 33.38 | 4.7686 | TA421 | 6/1 | Completed
2025-07-22 | 2025-07-29 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/14 | Completed
2025-07-21 | 2025-07-29 | D K Verma | 37.931 | 4.2146 | TA421 | 42/3 | Completed
2025-07-13 | 2025-07-30 | Hassan 2 | 65.22 | 3.6233 | TA421 | 39/0 | Completed
2025-07-26 | 2025-07-31 | Subash | 31.99 | 5.3317 | TA421 | 9/5 | Completed
2025-07-29 | 2025-08-01 | Khatun | 33.38 | 8.345 | TA421 | 4/21 | Completed
2025-07-08 | 2025-08-02 | Praveen | 34.946 | 1.3441 | TA421 | 16/7 | Completed
2025-07-30 | 2025-08-02 | Naziruddin | 31.99 | 7.9975 | TA421 | 8/8 | Completed
2025-07-17 | 2025-08-03 | Hassan | 64.89 | 3.605 | TA421 | 35/0 | Completed
2025-08-02 | 2025-08-04 | Khatun | 31.99 | 10.6633 | TA421 | 6/6 | Completed
2025-07-30 | 2025-08-04 | D K Verma | 37.931 | 6.3218 | TA421 | 42/5 | Completed
2025-08-01 | 2025-08-06 | Subash | 62.535 | 10.4225 | TA421 | 11/0 | Completed
2025-08-03 | 2025-08-07 | Naziruddin | 33.38 | 6.676 | TA421 | 8/7 | Completed
2025-08-05 | 2025-08-08 | Khatun | 33.38 | 8.345 | TA421 | 8/13 | Completed
2025-08-09 | 2025-08-11 | Khatun | 31.99 | 10.6633 | TA421 | 4/23 | Completed
2025-08-07 | 2025-08-12 | Subash | 37.931 | 6.3218 | TA421 | 10/8 | Completed
2025-08-04 | 2025-08-12 | Hassan | 54.66 | 6.0733 | TA421 | 34/1 | Completed
2025-08-08 | 2025-08-13 | Naziruddin | 31.99 | 5.3317 | TA421 | 8/12 | Completed
2025-08-05 | 2025-08-14 | D K Verma | 36.37 | 3.637 | TA421 | 42/6 | Completed
2025-08-13 | 2025-08-18 | Subash | 31.99 | 5.3317 | TA421 | 9/4 | Completed
2025-08-12 | 2025-08-19 | Khatun | 33.38 | 4.1725 | TA421 | 9/1 | Completed
2025-08-16 | 2025-08-24 | D K Verma | 44.825 | 4.9806 | TA421 | 42/7 | Completed
2025-08-23 | 2025-08-29 | Subash | 37.931 | 5.4187 | TA421 | 12/1 | Completed
2025-08-13 | 2025-08-29 | Hassan | 64.891 | 3.8171 | TA421 | 40/0 | Completed
2025-08-20 | 2025-08-30 | Khatun | 66.21 | 6.0191 | TA421 | 1A/0 | Completed
2025-08-14 | 2025-08-30 | Naziruddin | 51.04 | 3.0024 | TA421 | 9/0 | Completed
2025-08-19 | 2025-08-31 | Subash | 31.99 | 2.4608 | TA421 | 9/2 | Completed
2025-08-25 | 2025-08-31 | D K Verma | 43.08 | 6.1543 | TA421 | 42/1 | Completed
2025-08-31 | 2025-09-03 | Shakila Khatun | 31.99 | 7.9975 | TA421 | 2/3 | Completed
2025-09-01 | 2025-09-04 | Subash | 31.99 | 7.9975 | TA421 | 9/9 | Completed
2025-08-30 | 2025-09-05 | Hassan | 44.825 | 6.4036 | TA421 | 40/1 | Completed
2025-09-01 | 2025-09-06 | D K Verma | 44.825 | 7.4708 | TA421 | 42/8 | Completed
2025-08-31 | 2025-09-07 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/15 | Completed
2025-09-05 | 2025-09-07 | Subash | 31.99 | 10.6633 | TA421 | 4/6 | Completed
2025-09-05 | 2025-09-08 | Shakila Khatun | 51.04 | 12.76 | TA421 | 4/0 | Completed
2025-08-08 | 2025-09-08 | Praveen | 37.931 | 1.1853 | TA421 | 39/5 | Completed
2025-09-08 | 2025-09-09 | Subash | 33.38 | 16.69 | TA421 | 4/7 | Completed
2025-09-07 | 2025-09-10 | D K Verma | 37.931 | 9.4827 | TA421 | 42/9 | Completed
2025-09-06 | 2025-09-13 | Hassan | 62.535 | 7.8169 | TA421 | 41/0 | Completed
2025-09-10 | 2025-09-14 | Subash | 31.99 | 6.398 | TA421 | 4/9 | Completed
2025-09-08 | 2025-09-15 | Naziruddin | 33.38 | 4.1725 | TA421 | 8/9 | Completed
2025-09-09 | 2025-09-16 | Khatun | 51.04 | 6.38 | TA421 | 4/12 | Completed
2025-09-14 | 2025-09-20 | Subash | 33.38 | 4.7686 | TA421 | 4/10 | Completed
2025-09-13 | 2025-09-23 | D K Verma | 64.89 | 5.8991 | TA421 | 42/0 | Completed
2025-09-21 | 2025-09-24 | Subash | 33.38 | 8.345 | TA421 | 4/2 | Completed
2025-09-16 | 2025-09-25 | Hassan | 43.079 | 4.3079 | TA421 | 39/1 | Completed
2025-09-16 | 2025-09-26 | Naziruddin | 33.38 | 3.0345 | TA421 | 4/17 | Completed
2025-09-21 | 2025-09-29 | Khatun | 77.32 | 8.5911 | TA421 | 5/0 | Completed
2025-09-24 | 2025-09-30 | D K Verma | 34.946 | 4.9923 | TA421 | 43/2 | Completed
2025-09-25 | 2025-09-30 | Subash | 31.99 | 5.3317 | TA421 | 2/2 | Completed
2025-09-28 | 2025-10-04 | Khatun | 31.99 | 4.57 | TA421 | 4/18 | Completed
2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed
2025-09-13 |  | Praveen | 43.079 |  | TA421 | 39/7 | Top Section under Progress
2025-09-27 |  | Hassan | 36.37 |  | TA421 | 39/2 | Top Section under Progress
2025-10-01 |  | Subash | 72.63 |  | TA421 | 1/0 | Cage Section Completed
2025-10-07 |  | Rajiv Yadhav | 37.931 |  | TA421 | 43/5 | Material Shifting Done
2025-10-07 |  | D K Verma | 36.37 |  | TA421 | 43/3 | 1st Section under Progress
2025-10-07 |  | Khatun | 39.17 |  | TA421 | 9/3 | 1st Section under Progress
|  | Rajiv Yadhav | 44.851 |  | TA421 | 39/9 | Material Shifting Done
|  | Nan | 6223.9515 |  | TA505 |  | 132
2025-01-14 | 2025-01-19 | Jwala Singh | 45.697 | 7.6162 | TA505 | 101/2 | Completed
2025-01-21 | 2025-01-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/1 | Completed
2025-01-24 | 2025-01-27 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/3 | Completed
2025-01-27 | 2025-01-31 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 101/4 | Completed
2025-02-01 | 2025-02-04 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 101/5 | Completed
2025-02-05 | 2025-02-08 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/6 | Completed
2025-02-09 | 2025-02-12 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 101/7 | Completed
2025-02-13 | 2025-02-15 | Jwala Singh | 34.7898 | 11.5966 | TA505 | 101/8 | Completed
2025-02-17 | 2025-02-20 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/7 | Completed
2025-02-21 | 2025-02-24 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 110/5 | Completed
2025-02-25 | 2025-02-28 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/2 | Completed
2025-03-01 | 2025-03-04 | Jwala Singh | 35.602 | 8.9005 | TA505 | 109/1 | Completed
2025-03-05 | 2025-03-07 | Jwala Singh | 35.602 | 11.8673 | TA505 | 110/1 | Completed
2025-03-06 | 2025-03-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 109/3 | Completed
2025-03-07 | 2025-03-29 | Gokul Rajwanshi | 34.79 | 1.5126 | TA505 | 114/6 | Completed
2025-03-12 | 2025-03-28 | Eagle Enterprises | 36.1598 | 2.127 | TA505 | 113/4 | Completed
2025-03-11 | 2025-03-15 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 109/4 | Completed
2025-03-15 | 2025-03-19 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/6 | Completed
2025-03-19 | 2025-03-22 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 110/2 | Completed
2025-03-22 | 2025-03-26 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110/3 | Completed
2025-03-26 | 2025-03-30 | Jwala Singh | 37.9311 | 7.5862 | TA505 | 110A/1 | Completed
2025-03-29 | 2025-03-31 | Eagle Enterprises | 43.8044 | 14.6015 | TA505 | 113/5 | Completed
2025-03-30 | 2025-04-16 | Gokul Rajwanshi | 43.8044 | 2.4336 | TA505 | 114/5 | Completed
2025-03-30 | 2025-04-03 | Jwala Singh | 36.1598 | 7.232 | TA505 | 110/8 | Completed
2025-03-30 | 2025-04-06 | Jwala Singh 2 | 37.9311 | 4.7414 | TA505 | 114/9 | Completed
2025-04-01 | 2025-04-10 | Eagle Enterprises | 34.79 | 3.479 | TA505 | 113/3 | Completed
2025-04-03 | 2025-04-07 | Jwala Singh | 36.1598 | 7.232 | TA505 | 108/4 | Completed
2025-04-06 | 2025-04-12 | Jwala Singh 2 | 43.8044 | 6.2578 | TA505 | 114/10 | Completed
2025-04-08 | 2025-04-11 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/3 | Completed
2025-04-11 | 2025-04-17 | Eagle Enterprises Paramand | 35.602 | 5.086 | TA505 | 113/2 | Completed
2025-04-12 | 2025-04-15 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 108/2 | Completed
2025-04-12 | 2025-04-18 | Jwala Singh 2 | 36.1598 | 5.1657 | TA505 | 114/2 | Completed
2025-04-15 | 2025-04-18 | Jwala Singh | 34.79 | 8.6975 | TA505 | 108/1 | Completed
2025-04-17 | 2025-04-24 | Gokul Rajwanshi | 36.1598 | 4.52 | TA505 | 114/3 | Completed
2025-04-18 | 2025-04-23 | Eagle Enterprises Paramand | 34.79 | 5.7983 | TA505 | 113/1 | Completed
2025-04-18 | 2025-04-22 | Jwala Singh 2 | 37.9311 | 7.5862 | TA505 | 114/7 | Completed
2025-04-18 | 2025-04-21 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/1 | Completed
2025-04-22 | 2025-04-25 | Jwala Singh | 34.79 | 8.6975 | TA505 | 104/2 | Completed
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed
2025-04-22 | 2025-04-27 | Jwala Singh 2 | 35.602 | 5.9337 | TA505 | 120/2 | Completed
2025-04-25 | 2025-04-30 | Gokul Rajwanshi | 37.9311 | 6.3218 | TA505 | 114/1 | Completed
2025-04-24 | 2025-05-02 | Eagle Enterprises Paramand | 43.8044 | 4.8672 | TA505 | 113/6 | Completed
2025-04-26 | 2025-04-29 | Jwala Singh | 36.1598 | 9.0399 | TA505 | 105/1 | Completed
2025-04-27 | 2025-05-02 | Jwala Singh 2 | 36.1598 | 6.0266 | TA505 | 120/1 | Completed
2025-04-30 | 2025-05-06 | Jwala Singh | 45.697 | 6.5281 | TA505 | 111/4 | Completed
2025-05-02 | 2025-05-08 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 116/2 | Completed
2025-05-02 | 2025-05-07 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 120/3 | Completed
2025-05-02 | 2025-05-09 | Eagle Enterprises Paramand | 37.9311 | 4.7414 | TA505 | 111/1 | Completed
2025-05-06 | 2025-05-11 | Jwala Singh | 36.1598 | 6.0266 | TA505 | 111/3 | Completed
2025-05-08 | 2025-05-12 | Jwala Singh 2 | 36.1598 | 7.232 | TA505 | 127/2 | Completed
2025-05-08 | 2025-05-15 | Gokul Rajwanshi | 37.9311 | 4.7414 | TA505 | 116/1 | Completed
2025-05-08 | 2025-05-23 | Paramanand 1 | 36.1598 | 2.26 | TA505 | 160/5 | Completed
2025-05-08 | 2025-05-27 | Paramanand 2 | 36.1598 | 1.808 | TA505 | 161/4 | Completed
2025-05-09 | 2025-05-18 | Eagle Enterprises Paramand | 37.9311 | 3.7931 | TA505 | 111/2 | Completed
2025-05-14 | 2025-05-16 | Jwala Singh | 37.9311 | 12.6437 | TA505 | 152A/3 | Completed
2025-05-13 | 2025-05-16 | Jwala Singh 2 | 36.1598 | 9.0399 | TA505 | 127/1 | Completed
2025-05-16 | 2025-05-22 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 154/5 | Completed
2025-05-17 | 2025-05-21 | Jwala Singh | 35.602 | 7.1204 | TA505 | 152A/1 | Completed
2025-05-19 | 2025-06-07 | Eagle Enterprises Paramand | 36.1598 | 1.808 | TA505 | 129A/3 | Completed
2025-05-17 | 2025-05-22 | Jwala Singh 2 | 45.697 | 7.6162 | TA505 | 126/4 | Completed
2025-05-22 | 2025-05-26 | Jwala Singh | 36.1598 | 7.232 | TA505 | 152A/2 | Completed
2025-05-23 | 2025-05-27 | Gokul Rajwanshi | 36.1598 | 7.232 | TA505 | 155/3 | Completed
2025-05-23 | 2025-05-26 | Jwala Singh 2 | 34.79 | 8.6975 | TA505 | 126/2 | Completed
2025-05-24 | 2025-06-07 | Paramanand 1 | 36.1598 | 2.4107 | TA505 | 160/4 | Completed
2025-05-28 | 2025-06-23 | Paramanand 2 | 37.9311 | 1.4049 | TA505 | 161/3 | Completed
2025-05-28 | 2025-05-31 | Gokul Rajwanshi | 37.9311 | 9.4828 | TA505 | 155/5 | Completed
2025-05-27 | 2025-05-30 | Jwala Singh | 37.9311 | 9.4828 | TA505 | 152A/4 | Completed
2025-05-27 | 2025-05-31 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 127/3 | Completed
2025-05-31 | 2025-06-05 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 152A/8 | Completed
2025-06-01 | 2025-06-06 | Jwala Singh 2 | 37.9311 | 6.3218 | TA505 | 147A/4 | Completed
2025-06-01 | 2025-06-07 | Gokul Rajwanshi | 36.1598 | 5.1657 | TA505 | 155/4 | Completed
2025-06-06 | 2025-06-10 | Jwala Singh | 43.8044 | 8.7609 | TA505 | 150/5 | Completed
2025-06-07 | 2025-06-10 | Jwala Singh 2 | 43.8044 | 10.9511 | TA505 | 147A/2 | Completed
2025-06-08 | 2025-06-23 | Eagle Enterprises Paramand | 36.1598 | 2.26 | TA505 | 129A/1 | Completed
2025-06-08 | 2025-06-15 | Gokul Rajwanshi | 43.8044 | 5.4756 | TA505 | 156/1 | Completed
2025-06-08 | 2025-07-31 | Paramanand 1 | 36.1598 | 0.66963 | TA505 | 160/3 | Completed
2025-06-11 | 2025-06-16 | Jwala Singh | 43.8044 | 7.3007 | TA505 | 150/3 | Completed
2025-06-11 | 2025-06-15 | Jwala Singh 2 | 43.8044 | 8.7609 | TA505 | 147A/3 | Completed
2025-06-26 | 2025-07-12 | Eagle Enterprises Paramand | 45.697 | 2.6881 | TA505 | 147/1 | Completed
2025-06-16 | 2025-06-22 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 156/4 | Completed
2025-06-17 | 2025-06-25 | Jwala Singh | 43.8044 | 4.8672 | TA505 | 152A/9 | Completed
2025-06-24 | 2025-06-30 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/2 | Completed
2025-06-27 | 2025-06-30 | Jwala Singh | 43.8044 | 10.9511 | TA505 | 150/4 | Completed
2025-07-01 | 2025-07-07 | Gokul Rajwanshi | 35.602 | 5.086 | TA505 | 154/1 | Completed
2025-07-01 | 2025-07-06 | Jwala Singh | 37.9311 | 6.3218 | TA505 | 150/2 | Completed
2025-07-07 | 2025-07-17 | Jwala Singh | 43.8044 | 3.9822 | TA505 | 150/1 | Completed
2025-07-08 | 2025-07-14 | Gokul Rajwanshi | 34.79 | 4.97 | TA505 | 154/3 | Completed
2025-07-15 | 2025-07-24 | Gokul Rajwanshi | 43.8044 | 4.3804 | TA505 | 103/7 | Completed
2025-07-18 | 2025-07-28 | Jwala Singh | 62.444 | 5.6767 | TA505 | 150/0 | Completed
2025-07-25 | 2025-07-31 | Gokul Rajwanshi | 37.9311 | 5.4187 | TA505 | 103/8 | Completed
2025-08-01 | 2025-08-16 | Shila Devi | 73.245 | 4.5778 | TA505 | 127/0 | Completed
2025-08-04 | 2025-08-12 | Jwala Singh | 83.134 | 9.2371 | TA505 | 106/0 | Completed
2025-08-04 | 2025-08-08 | Gokul Rajwanshi | 34.79 | 6.958 | TA505 | 103/5A1 | Completed
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed
2025-08-09 | 2025-08-21 | Gokul Rajwanshi | 73.245 | 5.6342 | TA505 | 103/6A | Completed
2025-08-25 | 2025-09-12 | Paramanand 1 | 35.602 | 1.8738 | TA505 | 158/3 | Completed
2025-08-12 | 2025-08-22 | Jwala Singh | 73.245 | 6.6586 | TA505 | 108/0 | Completed
2025-08-17 | 2025-08-26 | Shila Devi | 59.501 | 5.9501 | TA505 | 126/0 | Completed
2025-08-18 | 2025-09-09 | Jyoti Const | 65.028 | 2.8273 | TA505 | 111/0 | Completed
2025-08-21 | 2025-09-09 | Gokul Rajwanshi | 83.134 | 4.1567 | TA505 | 103/5A | Completed
2025-08-25 | 2025-09-07 | Deglal Mahato | 67.262 | 4.8044 | TA505 | 119/0 | Completed
2025-08-25 | 2025-09-07 | Jhemon Mahato 1 | 73.245 | 5.2318 | TA505 | 135/0 | Completed
2025-08-25 | 2025-09-11 | Jhemon Mahato 2 | 37.9311 | 2.1073 | TA505 | 136/1 | Completed
2025-08-23 | 2025-09-05 | Jwala Singh | 77.077 | 5.5055 | TA505 | 104/0 | Completed
2025-08-27 | 2025-09-09 | Shila Devi | 59.501 | 4.2501 | TA505 | 130/0 | Completed
2025-09-01 | 2025-09-19 | Toshan Mahato | 45.697 | 2.4051 | TA505 | 147A/5 | Completed
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed
2025-09-10 | 2025-09-20 | Jwala Singh | 72.474 | 6.5885 | TA505 | 103/0 | Completed
2025-09-08 | 2025-09-18 | Jhemon Mahato 1 | 45.697 | 4.1543 | TA505 | 135/2 | Completed
2025-09-08 | 2025-09-18 | Deglal Mahato | 77.077 | 7.007 | TA505 | 120/0 | Completed
2025-09-10 | 2025-09-19 | Jyoti Const | 35.602 | 3.5602 | TA505 | 110A/2 | Completed
2025-09-10 | 2025-09-16 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/3 | Completed
2025-09-12 | 2025-09-22 | Jhemon Mahato 2 | 36.1598 | 3.2873 | TA505 | 144A/1 | Completed
2025-09-11 | 2025-09-21 | Deglal Mahato Mp | 36.16 | 3.2873 | TA505 | 169/6 | Completed
2025-09-19 | 2025-09-23 | Deglal Mahato | 43.8044 | 8.7609 | TA505 | 114/8 | Completed
2025-09-18 | 2025-09-24 | Gokul Rajwanshi | 36.16 | 5.1657 | TA505 | 103/1 | Completed
2025-09-10 | 2025-09-25 | Shila Devi | 88.468 | 5.5293 | TA505 | 131/0 | Completed
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed
2025-09-13 | 2025-09-25 | Paramanand 1 | 36.1598 | 2.7815 | TA505 | 159/2 | Completed
2025-09-14 | 2025-09-25 | Pankaj Singh Mp | 34.79 | 2.8992 | TA505 | 167/5 | Completed
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed
2025-09-19 | 2025-09-28 | Jhemon Mahato 1 | 70.74 | 7.074 | TA505 | 136/0 | Completed
2025-09-21 | 2025-09-28 | Jwala Singh | 62.444 | 7.8055 | TA505 | 105/0 | Completed
2025-09-20 | 2025-09-30 | Jyoti Const | 59.501 | 5.4092 | TA505 | 110A/0 | Completed
2025-09-20 | 2025-09-29 | Toshan Mahato | 35.602 | 3.5602 | TA505 | 147A/1 | Completed
2025-09-22 | 2025-09-29 | Deglal Mahato Mp | 36.16 | 4.52 | TA505 | 169/3 | Completed
2025-09-23 |  | Jhemon Mahato 2 | 85.264 |  | TA505 | 144A/0 | In-Progress
2025-09-24 | 2025-10-04 | Deglal Mahato | 87.021 | 7.911 | TA505 | 115/0 | Completed
2025-09-25 | 2025-09-30 | Gokul Rajwanshi | 36.16 | 6.0267 | TA505 | 103/2 | Completed
2025-09-26 | 2025-10-07 | Paramanand 1 | 35.602 | 2.9668 | TA505 | 160/2 | Completed
2025-09-26 | 2025-09-30 | Shila Devi | 36.16 | 7.232 | TA505 | 130/1 | Completed
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress
2025-09-30 | 2025-10-08 | Deglal Mahato Mp | 36.16 | 4.0178 | TA505 | 169/4 | Completed
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress
2025-09-26 | 2025-10-01 | Pankaj Singh Mp | 36.1598 | 6.0266 | TA505 | 167/4 | Completed
2025-10-02 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/2 | In-Progress
2025-10-08 |  | Paramanand 1 | 35.602 |  | TA505 | 160/1 | In-Progress
2025-10-09 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 169/5 | In-Progress
| 2025-09-19 | Dhaneshwar | 171.017 |  | TA325 | 101/0 | Completed
| 2025-08-13 | Dhaneshwar | 172.151 |  | TA325 | 104/0 | Completed
2025-05-24 | 2025-09-23 | Rupesh | 172.151 | 1.3996 | TA325 | 105/0 | Completed
2024-10-03 | 2024-12-08 | Dk Verma | 98.836 | 1.4752 | TA325 | 106/0 | Completed
2024-12-29 | 2025-01-03 | Dk Verma | 64.254 | 10.709 | TA325 | 106A/0 | Completed
2024-12-22 | 2024-12-28 | Dk Verma | 44.728 | 6.3897 | TA325 | 106A/1 | Completed
2024-12-19 | 2024-12-28 | Barkat Ali | 36.045 | 3.6045 | TA325 | 106A/2 | Completed
2024-06-25 | 2024-07-02 | Gourishankar | 39.459 | 4.9324 | TA325 | 106A/3 | Completed
2024-06-14 | 2024-06-24 | Gourishankar | 46.623 | 4.2385 | TA325 | 106A/4 | Completed
2024-08-08 | 2024-08-24 | Rahul Kumar | 65.757 | 3.8681 | TA325 | 106B/0 | Completed
2024-07-28 | 2024-08-08 | Ajay Kumar | 46.263 | 3.8552 | TA325 | 106B/1 | Completed
2024-07-02 | 2024-07-12 | Gourishankar | 44.728 | 4.0662 | TA325 | 106B/2 | Completed
2024-07-13 | 2024-07-29 | Gourishankar | 72.238 | 4.2493 | TA325 | 107/0 | Completed
2024-09-16 | 2024-09-26 | Barkat Ali | 36.045 | 3.2768 | TA325 | 107/1 | Completed
2024-09-28 | 2024-10-13 | Dk Verma | 72.238 | 4.5149 | TA325 | 108/0 | Completed
2024-08-11 | 2024-08-23 | Gourishankar | 54.418 | 4.186 | TA325 | 109/0 | Completed
2024-08-18 | 2024-08-31 | Rahul Kumar | 54.418 | 3.887 | TA325 | 110/0 | Completed
2024-09-09 | 2024-09-21 | Rahul Kumar | 64.254 | 4.9426 | TA325 | 111/0 | Completed
2024-06-05 | 2024-06-13 | Gourishankar | 72.238 | 8.0264 | TA325 | 112/0 | Completed
2024-07-08 | 2024-07-25 | Ajay Kumar | 80.408 | 4.4671 | TA325 | 113/0 | Completed
2024-09-02 | 2024-09-13 | Gourishankar | 72.238 | 6.0198 | TA325 | 114/0 | Completed
2024-12-04 | 2024-12-20 | Gourishankar | 109.608 | 6.4475 | TA325 | 115/0 | Completed
2024-09-10 | 2024-09-27 | Dhaneswar Mahto | 112.424 | 6.2458 | TA325 | 116/0 | Completed
2024-07-30 | 2024-08-11 | Gourishankar | 64.254 | 4.9426 | TA325 | 116A/0 | Completed
2024-12-09 | 2024-12-21 | Dk Verma | 37.73 | 2.9023 | TA325 | 116A/1 | Completed
2024-10-13 | 2024-10-31 | Ajay Kumar | 85.234 | 4.486 | TA325 | 116B/0 | Completed
2024-11-20 | 2024-12-03 | Gourishankar | 84.299 | 6.0214 | TA325 | 117/0 | Completed
2024-08-01 | 2024-08-20 | Rahul Kumar | 72.238 | 3.6119 | TA325 | 118/0 | Completed
2024-09-12 | 2024-09-24 | Ajay Kumar | 72.238 | 5.5568 | TA325 | 119/0 | Completed
2024-09-14 | 2024-09-23 | Gourishankar | 36.045 | 3.6045 | TA325 | 119/1 | Completed
2024-07-08 | 2024-07-12 | Rahul Kumar | 37.73 | 7.546 | TA325 | 119/2 | Completed
2024-07-13 | 2024-07-18 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 119/3 | Completed
2024-10-01 | 2024-10-24 | Gourishankar | 98.836 | 4.1182 | TA325 | 120/0 | Completed
2024-09-23 | 2024-10-10 | Rahul Kumar | 129.341 | 7.1856 | TA325 | 121/0 | Completed
2024-10-04 | 2024-10-15 | Gourishankar | 74.632 | 6.2193 | TA325 | 122/0 | Completed
2024-09-26 | 2024-10-10 | Ajay Kumar | 94.408 | 6.2939 | TA325 | 123/0 | Completed
2024-10-17 | 2024-10-31 | Gourishankar | 39.459 | 2.6306 | TA325 | 123/1 | Completed
2024-10-28 | 2024-11-11 | Ajay Kumar | 66.268 | 4.4179 | TA325 | 124/0 | Completed
2024-12-21 | 2025-01-05 | Gourishankar | 80.408 | 5.0255 | TA325 | 124A/0 | Completed
2024-09-16 | 2024-09-30 | Senahul | 39.459 | 2.6306 | TA325 | 124A/1 | Completed
2024-12-22 | 2025-01-05 | Mjr | 80.408 | 5.3605 | TA325 | 125/0 | Completed
2024-11-02 | 2024-11-13 | Gourishankar | 56.863 | 4.7386 | TA325 | 125A/0 | Completed
2024-07-20 | 2024-07-31 | Rahul Kumar | 64.254 | 5.3545 | TA325 | 126/0 | Completed
2024-12-21 | 2024-12-27 | Gourishankar | 44.728 | 6.3897 | TA325 | 126/1 | Completed
2024-05-31 | 2024-06-10 | Lalan Mahto | 72.238 | 6.5671 | TA325 | 127/0 | Completed
2023-09-30 | 2023-10-15 | Ghanshyam Mahto | 37.73 | 2.3581 | TA325 | 127/1 | Completed
2023-10-16 | 2023-10-29 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 127/2 | Completed
2024-05-25 | 2024-05-31 | Lalan Mahto | 37.73 | 5.39 | TA325 | 127/3 | Completed
2024-05-19 | 2024-05-24 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 127/4 | Completed
2024-11-27 | 2024-12-07 | Ajay Kumar | 39.459 | 3.5872 | TA325 | 127/5 | Completed
2024-11-13 | 2024-11-26 | Ajay Kumar | 94.408 | 6.7434 | TA325 | 128/0 | Completed
2024-12-30 | 2025-01-18 | Barkat Ali | 94.408 | 4.7204 | TA325 | 129/0 | Completed
2024-04-25 | 2024-04-30 | Lalan Mahto | 64.254 | 10.709 | TA325 | 129A/0 | Completed
2024-05-02 | 2024-05-07 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 129A/1 | Completed
2024-05-07 | 2024-05-12 | Lalan Mahto | 39.459 | 6.5765 | TA325 | 129A/2 | Completed
2024-05-07 | 2024-05-18 | Lalan Mahto | 54.418 | 4.5348 | TA325 | 130/0 | Completed
2025-01-25 | 2025-02-09 | Sk Samuil | 37.73 | 2.3581 | TA325 | 130/1 | Completed
2025-01-20 | 2025-01-29 | Mjr | 39.459 | 3.9459 | TA325 | 130/2 | Completed
2025-01-09 | 2025-01-18 | Mjr | 37.73 | 3.773 | TA325 | 130/3 | Completed
2024-12-22 | 2025-01-21 | Sk Samuil | 39.459 | 1.2729 | TA325 | 130/4 | Completed
2025-01-21 | 2025-02-05 | Barkat Ali | 75.452 | 4.7157 | TA325 | 131/0 | Completed
2024-12-08 | 2024-12-21 | Sk Samuil | 66.268 | 4.7334 | TA325 | 132/0 | Completed
2024-12-22 | 2024-12-30 | Sk Samuil | 37.73 | 4.1922 | TA325 | 132/1 | Completed
2024-02-04 | 2024-02-13 | Lalan Mahto | 37.73 | 3.773 | TA325 | 132/2 | Completed
2024-06-12 | 2024-06-18 | Lalan Mahto | 37.73 | 5.39 | TA325 | 132/3 | Completed
2024-02-13 | 2024-02-21 | Lalan Mahto | 54.418 | 6.0464 | TA325 | 133/0 | Completed
2023-12-02 | 2023-12-15 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 133/1 | Completed
2024-02-27 | 2024-03-03 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/2 | Completed
2024-02-20 | 2024-02-28 | Lalan Mahto | 37.73 | 4.1922 | TA325 | 133/3 | Completed
2024-04-20 | 2024-04-24 | Lalan Mahto | 37.73 | 7.546 | TA325 | 133/4 | Completed
2024-03-03 | 2024-03-08 | Lalan Mahto | 37.73 | 6.2883 | TA325 | 133/5 | Completed
2024-03-08 | 2024-03-13 | Lalan Mahto | 54.418 | 9.0697 | TA325 | 133A/0 | Completed
2024-03-13 | 2024-03-13 | Lalan Mahto | 37.73 | 37.73 | TA325 | 133A/1 | Completed
2024-04-13 | 2024-04-19 | Lalan Mahto | 44.728 | 6.3897 | TA325 | 133A/2 | Completed
2024-02-15 | 2024-02-20 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 133A/3 | Completed
2024-09-27 | 2024-10-12 | Mithun Kumar | 44.728 | 2.7955 | TA325 | 133A/4 | Completed
2024-12-04 | 2024-12-20 | Dhaneswar Mahto | 109.608 | 6.4475 | TA325 | 134/0 | Completed
2025-01-09 | 2025-01-22 | Dk Verma | 109.628 | 7.8306 | TA325 | 135/0 | Completed
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed
2023-11-11 | 2023-11-17 | Ghanshyam Mahto | 37.73 | 5.39 | TA325 | 135/2 | Completed
2024-02-26 | 2024-03-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135/3 | Completed
2024-05-31 | 2024-06-10 | Intizer Infratech | 37.73 | 3.43 | TA325 | 135/4 | Completed
2024-05-19 | 2024-05-31 | Intizer Infratech | 37.73 | 2.9023 | TA325 | 135/5 | Completed
2024-05-01 | 2024-05-19 | Intizer Infratech | 37.73 | 1.9858 | TA325 | 135/6 | Completed
2025-04-13 | 2025-04-22 | Sk Samuil | 37.73 | 3.773 | TA325 | 135/7 | Completed
2024-12-27 | 2025-01-04 | Dhaneswar Mahto | 64.254 | 7.1393 | TA325 | 135A/0 | Completed
2024-10-08 | 2024-11-03 | Dhaneswar Mahto | 75.452 | 2.7945 | TA325 | 135A/1 | Completed
2024-11-05 | 2024-11-13 | Dhaneswar Mahto | 65.757 | 7.3063 | TA325 | 135A/2 | Completed
2024-01-23 | 2024-01-28 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135A/3 | Completed
2023-11-01 | 2023-11-09 | Ghanshyam Mahto | 37.73 | 4.1922 | TA325 | 135A/4 | Completed
2025-01-13 | 2025-01-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/5 | Completed
2024-12-21 | 2024-12-26 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 135A/6 | Completed
2023-11-19 | 2023-12-01 | Ghanshyam Mahto | 37.73 | 2.9023 | TA325 | 135A/7 | Completed
2024-02-02 | 2024-02-09 | Poonam Kumari | 54.418 | 6.8022 | TA325 | 135B/0 | Completed
2024-02-20 | 2024-02-26 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/1 | Completed
2024-01-18 | 2024-01-23 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/2 | Completed
2024-01-12 | 2024-01-18 | Poonam Kumari | 37.73 | 5.39 | TA325 | 135B/3 | Completed
2024-01-04 | 2024-01-12 | Poonam Kumari | 44.728 | 4.9698 | TA325 | 135B/4 | Completed
2024-01-28 | 2024-02-02 | Poonam Kumari | 37.73 | 6.2883 | TA325 | 135B/5 | Completed
2024-02-04 | 2024-02-15 | Poonam Kumari | 37.73 | 3.1442 | TA325 | 135B/6 | Completed
2024-03-02 | 2024-04-11 | Poonam Kumari | 39.459 | 0.96241 | TA325 | 135B/7 | Completed
2025-01-09 | 2025-01-25 | Gourishankar | 112.424 | 6.6132 | TA325 | 136/0 | Completed
2025-02-01 | 2025-02-15 | Mjr | 77.718 | 5.1812 | TA325 | 137/0 | Completed
2024-05-25 | 2024-05-31 | Rahul Kumar | 39.459 | 5.637 | TA325 | 137/1 | Completed
2025-02-18 | 2025-02-27 | Mjr | 37.73 | 3.773 | TA325 | 137/2 | Completed
2024-05-19 | 2024-05-24 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 137/3 | Completed
2024-05-07 | 2024-05-18 | Rahul Kumar | 37.73 | 3.1442 | TA325 | 137/4 | Completed
2025-02-03 | 2025-02-07 | Dhaneswar Mahto | 39.459 | 7.8918 | TA325 | 137/5 | Completed
2025-01-27 | 2025-02-07 | Sk Samuil | 37.73 | 3.1442 | TA325 | 137/6 | Completed
2025-01-23 | 2025-01-29 | Dk Verma | 54.418 | 7.774 | TA325 | 137A/0 | Completed
2025-01-27 | 2025-01-29 | Dhaneswar Mahto | 44.728 | 14.9093 | TA325 | 137A/1 | Completed
2025-01-30 | 2025-02-02 | Dhaneswar Mahto | 37.73 | 9.4325 | TA325 | 137A/2 | Completed
2024-11-20 | 2024-11-28 | Dhaneswar Mahto | 44.728 | 4.9698 | TA325 | 137A/3 | Completed
2024-11-29 | 2024-12-03 | Dhaneswar Mahto | 36.045 | 7.209 | TA325 | 137A/4 | Completed
2024-11-14 | 2024-11-20 | Dhaneswar Mahto | 36.045 | 5.1493 | TA325 | 137A/5 | Completed
2025-01-20 | 2025-01-24 | Dhaneswar Mahto | 46.623 | 9.3246 | TA325 | 137A/6 | Completed
2025-01-27 | 2025-02-01 | Gourishankar | 54.418 | 9.0697 | TA325 | 138/0 | Completed
2025-02-03 | 2025-02-09 | Gourishankar | 44.728 | 6.3897 | TA325 | 138/1 | Completed
2025-02-05 | 2025-02-11 | Dk Verma | 37.73 | 5.39 | TA325 | 138/2 | Completed
2025-01-30 | 2025-02-04 | Dk Verma | 54.418 | 9.0697 | TA325 | 139/0 | Completed
2025-02-12 | 2025-02-17 | Dk Verma | 39.459 | 6.5765 | TA325 | 139/1 | Completed
2025-02-10 | 2025-02-14 | Gourishankar | 37.73 | 7.546 | TA325 | 139/2 | Completed
2025-02-09 | 2025-02-14 | Dhaneswar Mahto | 65.757 | 10.9595 | TA325 | 139A/0 | Completed
2025-02-16 | 2025-02-22 | Dhaneswar Mahto | 80.408 | 11.4869 | TA325 | 140/0 | Completed
2025-02-16 | 2025-02-23 | Gourishankar | 84.299 | 10.5374 | TA325 | 141/0 | Completed
2025-02-11 | 2025-02-17 | Sk Samuil | 37.73 | 5.39 | TA325 | 141/1 | Completed
2025-02-13 | 2025-02-19 | Sk Samuil | 36.045 | 5.1493 | TA325 | 141/2 | Completed
2025-02-19 | 2025-02-25 | Sk Samuil | 39.459 | 5.637 | TA325 | 141/3 | Completed
2025-02-18 | 2025-03-03 | Dk Verma | 80.408 | 5.7434 | TA325 | 142/0 | Completed
2025-02-25 | 2025-03-04 | Gourishankar | 84.299 | 10.5374 | TA325 | 143/0 | Completed
2025-02-24 | 2025-03-02 | Dhaneswar Mahto | 72.238 | 10.3197 | TA325 | 143A/0 | Completed
2025-03-01 | 2025-03-09 | Sk Samuil | 44.728 | 4.9698 | TA325 | 143A/1 | Completed
2025-03-04 | 2025-03-17 | Dhaneswar Mahto | 72.238 | 5.1599 | TA325 | 143A/2 | Completed
2025-03-05 | 2025-03-11 | Gourishankar | 75.452 | 10.7789 | TA325 | 143A/3 | Completed
2025-03-02 | 2025-03-10 | Mjr | 37.73 | 4.1922 | TA325 | 143A/4 | Completed
2025-03-05 | 2025-03-10 | Dk Verma | 39.459 | 6.5765 | TA325 | 143A/5 | Completed
2024-10-15 | 2024-11-16 | Mukesh | 56.863 | 1.7231 | TA325 | 144/0 | Completed
2024-06-30 | 2024-07-05 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/1 | Completed
2024-06-11 | 2024-06-15 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/2 | Completed
2024-06-13 | 2024-06-15 | Rahul Kumar | 37.73 | 12.5767 | TA325 | 144/3 | Completed
2024-06-16 | 2024-06-20 | Rahul Kumar | 37.73 | 7.546 | TA325 | 144/4 | Completed
2024-06-21 | 2024-06-26 | Rahul Kumar | 37.73 | 6.2883 | TA325 | 144/5 | Completed
2024-11-18 | 2024-11-24 | Mukesh | 65.757 | 9.3939 | TA325 | 144A/0 | Completed
2024-11-18 | 2024-12-08 | Mukesh | 82.239 | 3.9161 | TA325 | 145/0 | Completed
2025-03-15 | 2025-03-28 | Mjr | 63.509 | 4.5364 | TA325 | 145A/0 | Completed
2025-02-22 | 2025-03-07 | Sulen Sarkar | 39.459 | 2.8185 | TA325 | 145A/1 | Completed
2025-03-19 | 2025-03-27 | Sulen Sarkar | 39.459 | 4.3843 | TA325 | 145A/2 | Completed
2025-03-08 | 2025-03-16 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 145A/3 | Completed
2025-03-12 | 2025-03-22 | Dk Verma | 77.718 | 7.0653 | TA325 | 146/0 | Completed
2025-03-24 | 2025-04-01 | Dk Verma | 77.718 | 8.6353 | TA325 | 147/0 | Completed
2024-12-09 | 2024-12-16 | Mukesh | 64.254 | 8.0318 | TA325 | 147/1 | Completed
2024-12-17 | 2024-12-23 | Mukesh | 64.254 | 9.1791 | TA325 | 147/2 | Completed
2024-11-13 | 2024-12-02 | Modina India | 36.045 | 1.8022 | TA325 | 147/3 | Completed
2024-12-10 | 2024-12-25 | Modina India | 39.459 | 2.4662 | TA325 | 147/4 | Completed
2024-12-03 | 2024-12-22 | Modina India | 44.728 | 2.2364 | TA325 | 147/5 | Completed
2025-01-27 | 2025-02-18 | Ajay Kumar | 36.045 | 1.5672 | TA325 | 147/6 | Completed
2024-12-24 | 2025-01-03 | Mukesh | 82.239 | 7.4763 | TA325 | 147A/0 | Completed
2025-02-26 | 2025-03-22 | Modina India | 82.239 | 3.2896 | TA325 | 147B/0 | Completed
2025-02-13 | 2025-02-21 | Modina India | 37.73 | 4.1922 | TA325 | 147B/1 | Completed
2025-01-04 | 2025-01-10 | Mukesh | 64.254 | 9.1791 | TA325 | 148/0 | Completed
2025-02-01 | 2025-02-09 | Modina India | 39.459 | 4.3843 | TA325 | 148/1 | Completed
2025-01-21 | 2025-01-30 | Modina India | 37.73 | 3.773 | TA325 | 148/2 | Completed
2025-01-10 | 2025-01-19 | Modina India | 37.73 | 3.773 | TA325 | 148/3 | Completed
2024-12-23 | 2025-01-06 | Modina India | 37.73 | 2.5153 | TA325 | 148/4 | Completed
2025-02-25 | 2025-02-28 | Sk Samuil | 37.73 | 9.4325 | TA325 | 148/5 | Completed
2025-03-03 | 2025-03-09 | Sk Samuil | 37.73 | 5.39 | TA325 | 148/6 | Completed
2025-03-08 | 2025-03-20 | Rahim Khan | 37.73 | 2.9023 | TA325 | 148/7 | Completed
2025-03-10 | 2025-04-06 | Sk Samuil | 54.418 | 1.9435 | TA325 | 149/0 | Completed
2025-03-17 | 2025-03-27 | Sk Samuil | 37.73 | 3.43 | TA325 | 149/1 | Completed
2025-03-22 | 2025-03-31 | Dhaneswar Mahto | 98.836 | 9.8836 | TA325 | 150/0 | Completed
2025-03-20 | 2025-04-06 | Mjr | 46.623 | 2.5902 | TA325 | 150/1 | Completed
2025-03-18 | 2025-03-22 | Sk Samuil | 39.459 | 7.8918 | TA325 | 150/2 | Completed
2025-03-19 | 2025-04-01 | Rupesh | 44.728 | 3.1949 | TA325 | 150/3 | Completed
2025-03-25 | 2025-04-11 | Rahim Khan | 64.254 | 3.5697 | TA325 | 150A/0 | Completed
2024-11-10 | 2024-11-22 | Sk Samuil | 39.459 | 3.0353 | TA325 | 150A/1 | Completed
2024-11-23 | 2024-12-02 | Sk Samuil | 37.73 | 3.773 | TA325 | 150A/2 | Completed
2025-03-21 | 2025-03-27 | Gourishankar | 56.863 | 8.1233 | TA325 | 151/0 | Completed
2024-10-15 | 2024-10-24 | Mukesh | 64.254 | 6.4254 | TA325 | 152/0 | Completed
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed
2024-09-24 | 2024-11-07 | Sk Samuil | 36.045 | 0.801 | TA325 | 152/2 | Completed
2024-10-25 | 2024-10-31 | Mukesh | 36.045 | 5.1493 | TA325 | 152/3 | Completed
2024-11-02 | 2024-11-07 | Mukesh | 37.73 | 6.2883 | TA325 | 152/4 | Completed
2025-03-16 | 2025-03-20 | Gourishankar | 54.418 | 10.8836 | TA325 | 152A/0 | Completed
| 2025-08-08 | Nan | 141.874 |  | TA325 | 153/0 | Completed
2025-04-02 | 2025-04-11 | Rahul Kumar | 80.408 | 8.0408 | TA325 | 155/0 | Completed
2025-03-26 | 2025-04-03 | Barkat Ali | 37.73 | 4.1922 | TA325 | 155/1 | Completed
2024-11-16 | 2024-11-30 | Rahul Kumar | 39.459 | 2.6306 | TA325 | 155/2 | Completed
2024-11-16 | 2024-11-22 | Rahul Kumar | 39.459 | 5.637 | TA325 | 155/3 | Completed
2025-04-28 | 2025-05-11 | Sk Samuil | 37.73 | 2.695 | TA325 | 155/4 | Completed
2025-04-29 | 2025-05-11 | Barkat Ali | 37.73 | 2.9023 | TA325 | 155/5 | Completed
2025-03-15 | 2025-03-23 | Barkat Ali | 36.045 | 4.005 | TA325 | 155/6 | Completed
2025-03-22 | 2025-03-28 | Rahul Kumar | 84.299 | 12.0427 | TA325 | 156/0 | Completed
2025-03-12 | 2025-03-27 | Rahim Khan | 94.408 | 5.9005 | TA325 | 157/0 | Completed
2025-02-09 | 2025-02-18 | Sukhriddin | 37.73 | 3.773 | TA325 | 157/1 | Completed
2025-02-23 | 2025-03-11 | Barkat Ali | 37.73 | 2.2194 | TA325 | 157/2 | Completed
2025-04-02 | 2025-04-10 | Rahim Khan | 54.418 | 6.0464 | TA325 | 158/0 | Completed
2025-04-07 | 2025-04-25 | Barkat Ali | 36.045 | 1.8971 | TA325 | 158/1 | Completed
2025-03-13 | 2025-03-18 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 158/2 | Completed
2024-10-23 | 2024-11-12 | Rahul Kumar | 85.234 | 4.0588 | TA325 | 158A/0 | Completed
2024-11-13 | 2024-12-30 | Rahul Kumar | 112.424 | 2.3422 | TA325 | 158B/0 | Completed
2024-11-16 | 2024-12-12 | Rahul Kumar | 39.459 | 1.4614 | TA325 | 158B/1 | Completed
2024-12-31 | 2025-01-10 | Rahul Kumar | 39.459 | 3.5872 | TA325 | 158B/2 | Completed
2024-08-14 | 2024-09-08 | Sukhriddin | 54.418 | 2.093 | TA325 | 159/0 | Completed
2025-01-21 | 2025-02-12 | Rahim Khan | 37.73 | 1.6404 | TA325 | 159/1 | Completed
2024-07-08 | 2024-07-23 | Sukhriddin | 37.73 | 2.3581 | TA325 | 159/3 | Completed
2025-01-21 | 2025-02-03 | Modina India | 37.73 | 2.695 | TA325 | 159/4 | Completed
2025-01-28 | 2025-02-16 | Rahul Kumar | 141.874 | 7.0937 | TA325 | 161/0 | Completed
2025-02-20 | 2025-03-09 | Rahul Kumar | 141.874 | 7.8819 | TA325 | 162/0 | Completed
2025-01-16 | 2025-01-23 | Rahul Kumar | 64.254 | 8.0318 | TA325 | 163/0 | Completed
2024-12-30 | 2025-01-08 | Rahim Khan | 37.73 | 3.773 | TA325 | 163/1 | Completed
2024-11-28 | 2024-12-29 | Rahim Khan | 37.73 | 1.1791 | TA325 | 163/2 | Completed
2024-11-28 | 2024-12-18 | Rahim Khan | 37.73 | 1.7967 | TA325 | 163/3 | Completed
2025-01-16 | 2025-01-29 | Sukhriddin | 37.73 | 2.695 | TA325 | 163/4 | Completed
2025-01-12 | 2025-02-20 | Barkat Ali | 37.73 | 0.94325 | TA325 | 163/5 | Completed
2025-01-10 | 2025-01-25 | Barkat Ali | 37.73 | 2.3581 | TA325 | 163/6 | Completed
2024-12-28 | 2025-01-12 | Sukhriddin | 54.418 | 3.4011 | TA325 | 164/0 | Completed
2024-12-28 | 2025-01-16 | Modina India | 37.73 | 1.8865 | TA325 | 164/1 | Completed
2024-07-27 | 2024-08-13 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/2 | Completed
2025-01-11 | 2025-01-20 | Rahim Khan | 37.73 | 3.773 | TA325 | 164/3 | Completed
2024-11-16 | 2024-11-27 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/4 | Completed
2024-11-28 | 2024-12-14 | Sukhriddin | 37.73 | 2.2194 | TA325 | 164/5 | Completed
2024-12-14 | 2024-12-25 | Sukhriddin | 37.73 | 3.1442 | TA325 | 164/6 | Completed
2024-09-22 | 2024-10-09 | Sukhriddin | 37.73 | 2.0961 | TA325 | 164/7 | Completed
2024-10-09 | 2024-10-28 | Sukhriddin | 54.418 | 2.7209 | TA325 | 165/0 | Completed
2025-05-16 | 2025-05-25 | Barkat Ali | 37.73 | 3.773 | TA325 | 165/1 | Completed
2024-09-09 | 2024-09-20 | Sukhriddin | 37.73 | 3.1442 | TA325 | 165/2 | Completed
2024-10-30 | 2024-11-15 | Sukhriddin | 44.728 | 2.6311 | TA325 | 165/3 | Completed
2025-04-18 | 2025-05-05 | Rupesh | 80.408 | 4.4671 | TA325 | 167/0 | Completed
2025-05-04 | 2025-05-19 | Barkat Ali | 46.623 | 2.9139 | TA325 | 167/1 | Completed
2025-04-08 | 2025-04-18 | Barkat Ali | 44.728 | 4.0662 | TA325 | 167/2 | Completed
2025-03-28 | 2025-04-06 | Barkat Ali | 44.728 | 4.4728 | TA325 | 167/3 | Completed
2025-04-20 | 2025-04-29 | Barkat Ali | 37.73 | 3.773 | TA325 | 167/4 | Completed
2025-04-06 | 2025-04-16 | Rupesh | 64.254 | 5.8413 | TA325 | 168/0 | Completed
2025-05-13 | 2025-05-20 | Rahim Khan | 36.045 | 4.5056 | TA325 | 168/1 | Completed
2025-05-02 | 2025-05-11 | Sukhriddin | 37.73 | 3.773 | TA325 | 168/2 | Completed
2025-05-24 | 2025-06-08 | Dk Verma | 112.424 | 7.0265 | TA325 | 169/0 | Completed
2025-02-26 | 2025-03-29 | Sukhriddin | 141.874 | 4.4336 | TA325 | 171/0 | Completed
2025-04-02 | 2025-04-28 | Sukhriddin | 141.874 | 5.2546 | TA325 | 172/0 | Completed
2025-05-29 | 2025-06-06 | Thanu Mahto | 44.728 | 4.9698 | TA325 | 172/2 | Completed
2025-06-06 | 2025-06-13 | Gourishankar | 54.418 | 6.8022 | TA325 | 174/1 | Completed
2025-05-28 | 2025-06-05 | Gourishankar | 72.238 | 8.0264 | TA325 | 175/0 | Completed
| 2025-07-20 | Nan | 37.73 |  | TA325 | 175/2 | Completed
2025-06-11 | 2025-07-04 | Dk Verma | 80.408 | 3.3503 | TA325 | 176/0 | Completed
2025-05-06 | 2025-05-18 | Gourishankar | 80.408 | 6.1852 | TA325 | 177/0 | Completed
2025-04-06 | 2025-04-13 | Gourishankar | 94.408 | 11.801 | TA325 | 178/0 | Completed
2025-04-16 | 2025-04-22 | Gourishankar | 80.408 | 11.4869 | TA325 | 179/0 | Completed
2025-04-24 | 2025-05-03 | Gourishankar | 89.146 | 8.9146 | TA325 | 180/0 | Completed
2025-04-06 | 2025-04-27 | Dk Verma | 112.424 | 5.1102 | TA325 | 181/0 | Completed
2025-04-24 | 2025-04-30 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/1 | Completed
2025-04-16 | 2025-04-22 | Rahim Khan | 37.73 | 5.39 | TA325 | 181/2 | Completed
2025-05-19 | 2025-05-24 | Gourishankar | 37.73 | 6.2883 | TA325 | 181/3 | Completed
2025-05-03 | 2025-05-11 | Rahim Khan | 37.73 | 4.1922 | TA325 | 181/4 | Completed
2025-04-28 | 2025-05-06 | Dk Verma | 80.408 | 8.9342 | TA325 | 182/0 | Completed
2025-04-03 | 2025-04-12 | Thanu Mahto | 39.459 | 3.9459 | TA325 | 187/1 | Completed
2024-12-26 | 2025-01-04 | Mithun Kumar | 36.045 | 3.6045 | TA325 | 187/2 | Completed
2024-11-22 | 2024-11-26 | Jwala | 37.73 | 7.546 | TA325 | 187/3 | Completed
2024-11-27 | 2024-12-10 | Jwala | 63.509 | 4.5364 | TA325 | 188/0 | Completed
2024-11-22 | 2024-12-14 | Barkat Ali | 63.509 | 2.7613 | TA325 | 189/0 | Completed
2025-04-05 | 2025-04-11 | Dhaneswar Mahto | 37.73 | 5.39 | TA325 | 189/1 | Completed
2025-04-18 | 2025-05-06 | Dhaneswar Mahto | 122.808 | 6.4636 | TA325 | 190/0 | Completed
| 2025-08-26 | Modina India | 122.808 |  | TA325 | 191/0 | Completed
2024-12-09 | 2024-12-23 | Mithun Kumar | 37.73 | 2.5153 | TA325 | 191/1 | Completed
2025-04-23 | 2025-04-27 | Rahul Kumar | 36.045 | 7.209 | TA325 | 191/2 | Completed
2025-04-29 | 2025-05-04 | Rahul Kumar | 36.045 | 6.0075 | TA325 | 191/3 | Completed
2025-04-15 | 2025-04-22 | Rahul Kumar | 54.418 | 6.8022 | TA325 | 191A/0 | Completed
2024-11-22 | 2024-11-30 | Mithun Kumar | 36.045 | 4.005 | TA325 | 191A/1 | Completed
2025-04-13 | 2025-04-28 | Mjr | 64.254 | 4.0159 | TA325 | 192/0 | Completed
2024-12-11 | 2024-12-21 | Jwala | 94.408 | 8.5825 | TA325 | 193/0 | Completed
2025-04-22 | 2025-05-15 | Mjr | 94.408 | 3.9337 | TA325 | 194/0 | Completed
2025-04-28 | 2025-05-11 | Mithun Kumar | 64.254 | 4.5896 | TA325 | 195/0 | Completed
2025-04-16 | 2025-04-25 | Mithun Kumar | 44.728 | 4.4728 | TA325 | 195/1 | Completed
2025-04-01 | 2025-04-08 | Sk Samuil | 37.73 | 4.7162 | TA325 | 195/2 | Completed
2025-04-18 | 2025-04-28 | Sk Samuil | 44.728 | 4.0662 | TA325 | 195/3 | Completed
2025-04-09 | 2025-04-15 | Sk Samuil | 37.73 | 5.39 | TA325 | 195/4 | Completed
2025-05-02 | 2025-05-11 | Sk Samuil | 44.728 | 4.4728 | TA325 | 195/5 | Completed
2025-04-22 | 2025-05-18 | Daulat Mahto | 54.418 | 2.0155 | TA325 | 195A/0 | Completed
2025-04-24 | 2025-05-09 | Modina India | 44.728 | 2.7955 | TA325 | 195A/1 | Completed
2025-04-11 | 2025-04-22 | Modina India | 44.728 | 3.7273 | TA325 | 195A/2 | Completed
2025-03-30 | 2025-04-08 | Modina India | 37.73 | 3.773 | TA325 | 195A/3 | Completed
2024-12-31 | 2025-01-10 | Jwala | 98.839 | 8.9854 | TA325 | 196/0 | Completed
2025-01-12 | 2025-01-22 | Jwala | 98.836 | 8.9851 | TA325 | 197/0 | Completed
2025-04-01 | 2025-04-12 | Mithun Kumar | 37.73 | 3.1442 | TA325 | 197/1 | Completed
2025-01-29 | 2025-02-07 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/2 | Completed
2025-01-07 | 2025-01-16 | Mithun Kumar | 37.73 | 3.773 | TA325 | 197/3 | Completed
2024-12-23 | 2024-12-29 | Jwala | 37.73 | 5.39 | TA325 | 197/4 | Completed
2025-04-01 | 2025-04-15 | Mithun Kumar | 64.254 | 4.2836 | TA325 | 198/0 | Completed
2025-01-17 | 2025-01-27 | Mithun Kumar | 37.73 | 3.43 | TA325 | 198/1 | Completed
2025-04-04 | 2025-04-12 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 198/2 | Completed
2025-04-18 | 2025-05-22 | Mithun Kumar | 112.424 | 3.2121 | TA325 | 199/0 | Completed
2025-05-02 | 2025-05-11 | Jwala | 98.836 | 9.8836 | TA325 | 204/0 | Completed
2025-04-18 | 2025-04-29 | Jwala | 84.299 | 7.0249 | TA325 | 205/0 | Completed
2025-04-11 | 2025-04-16 | Jwala | 36.045 | 6.0075 | TA325 | 205/1 | Completed
2025-05-15 | 2025-05-21 | Jwala | 39.459 | 5.637 | TA325 | 205/2 | Completed
2025-05-08 | 2025-05-16 | Rahul Kumar | 64.254 | 7.1393 | TA325 | 209/0 | Completed
2025-05-13 | 2025-05-18 | Dhaneswar Mahto | 37.73 | 6.2883 | TA325 | 211/1 | Completed
2025-05-04 | 2025-05-18 | Rahim Khan | 39.459 | 2.6306 | TA325 | 217A/1 | Completed
2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed
2025-09-19 | 2025-10-05 | Rahul Kumar | 80.408 | 4.7299 | TA325 | 246/0 | Completed
2025-05-11 | 2025-05-19 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 247/1 | Completed
2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed
2025-04-14 | 2025-04-30 | Anarul Haque | 77.718 | 4.5716 | TA325 | 248/0 | Completed
2025-05-06 | 2025-05-18 | Dk Verma | 46.623 | 3.5864 | TA325 | 248/1 | Completed
2025-04-17 | 2025-04-30 | Sulen Sarkar | 46.623 | 3.3302 | TA325 | 248/2 | Completed
2025-05-09 | 2025-05-20 | Mjr | 44.728 | 3.7273 | TA325 | 248/3 | Completed
2025-04-17 | 2025-05-05 | Mjr | 39.459 | 2.0768 | TA325 | 248/4 | Completed
2025-04-01 | 2025-04-12 | Sulen Sarkar | 37.73 | 3.1442 | TA325 | 248/5 | Completed
2025-04-29 | 2025-05-09 | Senahul | 37.73 | 3.43 | TA325 | 248/6 | Completed
2025-02-14 | 2025-02-26 | Maa Construction | 54.418 | 4.186 | TA325 | 249/0 | Completed
2025-04-13 | 2025-04-21 | Sulen Sarkar | 37.73 | 4.1922 | TA325 | 249/1 | Completed
2025-03-01 | 2025-03-09 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/2 | Completed
2025-03-10 | 2025-03-18 | Maa Construction | 37.73 | 4.1922 | TA325 | 249/3 | Completed
2025-03-21 | 2025-04-12 | Maa Construction | 80.408 | 3.496 | TA325 | 250/0 | Completed
2025-02-14 | 2025-02-24 | Ghanshyam Mahto | 36.045 | 3.2768 | TA325 | 250/1 | Completed
2024-12-03 | 2024-12-28 | Senahul | 65.757 | 2.5291 | TA325 | 251/0 | Completed
2025-03-18 | 2025-04-11 | Anarul Haque | 97.934 | 3.9174 | TA325 | 252/0 | Completed
2025-02-01 | 2025-02-17 | Senahul | 64.254 | 3.7796 | TA325 | 253/0 | Completed
2024-11-04 | 2024-11-21 | Senahul | 54.418 | 3.0232 | TA325 | 254/0 | Completed
2024-11-27 | 2024-12-21 | Senahul | 84.299 | 3.372 | TA325 | 255/0 | Completed
2025-01-19 | 2025-01-27 | Daulat Mahto | 44.728 | 4.9698 | TA325 | 255/1 | Completed
2025-01-03 | 2025-01-10 | Maa Construction | 37.73 | 4.7162 | TA325 | 255/2 | Completed
2024-12-26 | 2025-01-02 | Maa Construction | 39.459 | 4.9324 | TA325 | 255/3 | Completed
2024-07-10 | 2024-08-22 | Ghanshyam Mahto | 37.73 | 0.8575 | TA325 | 255/4 | Completed
2024-08-30 | 2024-09-23 | Ghanshyam Mahto | 64.254 | 2.5702 | TA325 | 257/0 | Completed
2025-01-09 | 2025-01-17 | Daulat Mahto | 37.73 | 4.1922 | TA325 | 257/1 | Completed
2024-09-23 | 2024-10-24 | Ghanshyam Mahto | 36.044 | 1.1264 | TA325 | 257/2 | Completed
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed
2024-10-29 | 2024-11-16 | Thanu Mahto | 37.73 | 1.9858 | TA325 | 257/4 | Completed
2024-11-10 | 2024-12-23 | Maa Construction | 129.341 | 2.9396 | TA325 | 259/0 | Completed
2024-09-11 | 2024-10-31 | Ramjivan | 129.341 | 2.5361 | TA325 | 260/0 | Completed
2024-11-23 | 2024-12-28 | Ghanshyam Mahto | 97.934 | 2.7204 | TA325 | 261/0 | Completed
2025-01-18 | 2025-02-11 | Ghanshyam Mahto | 89.146 | 3.5658 | TA325 | 262/0 | Completed
2024-10-25 | 2024-11-07 | Ghanshyam Mahto | 37.73 | 2.695 | TA325 | 262/1 | Completed
2024-12-31 | 2025-01-13 | Ghanshyam Mahto | 64.254 | 4.5896 | TA325 | 263/0 | Completed
2024-11-17 | 2024-12-10 | Thanu Mahto | 74.632 | 3.1097 | TA325 | 264/0 | Completed
2024-09-30 | 2024-10-31 | Thanu Mahto | 56.863 | 1.777 | TA325 | 265/0 | Completed
2024-12-28 | 2025-01-12 | Senahul | 54.418 | 3.4011 | TA325 | 266/0 | Completed
2025-01-13 | 2025-01-29 | Senahul | 63.509 | 3.7358 | TA325 | 266/1 | Completed
2025-02-04 | 2025-02-12 | Maa Construction | 37.73 | 4.1922 | TA325 | 266/2 | Completed
2025-01-21 | 2025-01-31 | Maa Construction | 77.718 | 7.0653 | TA325 | 267/0 | Completed
2025-02-21 | 2025-03-18 | Senahul | 77.718 | 2.9892 | TA325 | 267A/0 | Completed
2025-02-27 | 2025-03-05 | Daulat Mahto | 37.73 | 5.39 | TA325 | 267A/1 | Completed
2025-03-07 | 2025-03-15 | Daulat Mahto | 36.045 | 4.005 | TA325 | 267A/2 | Completed
2024-08-21 | 2024-09-13 | Ramjivan | 37.73 | 1.5721 | TA325 | 267A/3 | Completed
2024-11-10 | 2024-12-07 | Daulat Mahto | 94.408 | 3.3717 | TA325 | 268/0 | Completed
2025-03-26 | 2025-04-01 | Jwala | 80.408 | 11.4869 | TA325 | 269/0 | Completed
2024-12-28 | 2025-01-07 | Daulat Mahto | 37.73 | 3.43 | TA325 | 269/1 | Completed
2025-01-11 | 2025-01-19 | Maa Construction | 44.728 | 4.9698 | TA325 | 269/2 | Completed
2025-02-22 | 2025-03-16 | Anarul Haque | 72.238 | 3.1408 | TA325 | 270/0 | Completed
2024-12-11 | 2024-12-24 | Daulat Mahto | 37.73 | 2.695 | TA325 | 270/1 | Completed
2024-09-14 | 2024-10-28 | Senahul | 39.459 | 0.87687 | TA325 | 270/2 | Completed
2025-03-19 | 2025-03-28 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 270/3 | Completed
2025-03-09 | 2025-03-28 | Mithun Kumar | 37.73 | 1.8865 | TA325 | 270/4 | Completed
2025-02-20 | 2025-02-28 | Mithun Kumar | 37.73 | 4.1922 | TA325 | 270/5 | Completed
2025-02-11 | 2025-02-17 | Mithun Kumar | 36.045 | 5.1493 | TA325 | 270/6 | Completed
2025-02-17 | 2025-02-23 | Daulat Mahto | 36.045 | 5.1493 | TA325 | 270/7 | Completed
2025-02-05 | 2025-02-15 | Daulat Mahto | 64.254 | 5.8413 | TA325 | 270A/0 | Completed
2025-02-04 | 2025-02-13 | Thanu Mahto | 64.254 | 6.4254 | TA325 | 271/0 | Completed
2025-03-21 | 2025-03-25 | Jwala | 36.045 | 7.209 | TA325 | 271/1 | Completed
2025-02-14 | 2025-02-21 | Thanu Mahto | 37.73 | 4.7162 | TA325 | 271/2 | Completed
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | 271/3 | Completed
2025-02-22 | 2025-03-03 | Thanu Mahto | 36.045 | 3.6045 | TA325 | 271/4 | Completed
2025-01-01 | 2025-01-11 | Thanu Mahto | 36.045 | 3.2768 | TA325 | 271/5 | Completed
2024-12-11 | 2024-12-31 | Thanu Mahto | 74.632 | 3.5539 | TA325 | 272/0 | Completed
2024-12-02 | 2024-12-16 | Mjr | 46.623 | 3.1082 | TA325 | 272/1 | Completed
2025-01-30 | 2025-02-04 | Daulat Mahto | 36.045 | 6.0075 | TA325 | 272/2 | Completed
2025-01-17 | 2025-02-06 | Tajirul | 39.459 | 1.879 | TA325 | 272/3 | Completed
2025-01-25 | 2025-02-02 | Thanu Mahto | 39.459 | 4.3843 | TA325 | 272/4 | Completed
2025-01-13 | 2025-01-23 | Thanu Mahto | 54.418 | 4.9471 | TA325 | 272/5 | Completed
2025-03-19 | 2025-03-30 | Daulat Mahto | 39.459 | 3.2883 | TA325 | 272/6 | Completed
2025-02-10 | 2025-03-07 | Tajirul | 46.623 | 1.7932 | TA325 | 272/7 | Completed
2025-04-03 | 2025-04-26 | Senahul | 82.239 | 3.4266 | TA325 | 272A/0 | Completed
2025-01-24 | 2025-01-29 | Jwala | 44.728 | 7.4547 | TA325 | 272A/1 | Completed
2025-01-30 | 2025-02-04 | Jwala | 37.73 | 6.2883 | TA325 | 272A/2 | Completed
2025-02-05 | 2025-02-09 | Jwala | 37.73 | 7.546 | TA325 | 272A/3 | Completed
2025-03-17 | 2025-03-20 | Jwala | 37.73 | 9.4325 | TA325 | 272A/4 | Completed
2025-03-11 | 2025-03-16 | Jwala | 39.459 | 6.5765 | TA325 | 272A/5 | Completed
2025-03-02 | 2025-03-05 | Jwala | 36.045 | 9.0113 | TA325 | 272A/6 | Completed
2025-03-06 | 2025-03-10 | Jwala | 36.045 | 7.209 | TA325 | 272A/7 | Completed
2025-04-04 | 2025-04-09 | Jwala | 44.728 | 7.4547 | TA325 | 273/1 | Completed
2025-02-24 | 2025-02-28 | Jwala | 44.728 | 8.9456 | TA325 | 273/2 | Completed
2025-02-17 | 2025-02-23 | Jwala | 64.254 | 9.1791 | TA325 | 274/0 | Completed
2025-08-06 | 2025-09-14 | Modina India | 72.238 | 1.8059 | TA325 | 275/0 | Completed
2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed
2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed
2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed
2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed
2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed
2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed
|  | Dhaneshwar Mahto | 156.901 |  | TA325 | 102/0
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325 | 229/3
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325 | 237/1
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | 237/0
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325 | 237/6
|  | Nan | 21414.926 |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325
|  | Nan |  |  | TA325 |  | Completed Erection
|  | Nan | 40 |  | TA325 |  | 35
|  | Nan | 146 |  | TA325 |  | 130
|  | Nan | 40 |  | TA325 |  | 33
|  | Nan | 30 |  | TA325 |  | 28
|  | Nan | 11 |  | TA325 |  | 9
|  | Nan | 267 |  | TA325 |  | 235
|  | Nan | 25 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 9 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 55 |  | TA325
|  | Nan | 26 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 47 |  | TA325
|  | Nan | 16 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 3 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 6 |  | TA325
|  | Nan | 5 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 40 |  | TA325
|  | Nan | 19 |  | TA325
|  | Nan | 8 |  | TA325
|  | Nan | 11 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 7 |  | TA325
|  | Nan | 15 |  | TA325
|  | Nan | 4 |  | TA325
|  | Nan | 2 |  | TA325
|  | Nan | 73 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 1 |  | TA325
|  | Nan | 483 |  | TA325

## Data Issues
Start Date | Complete Date | Gang name | Tower Weight | Productivity | Project Name | Location No. | Status | Issues
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA416 |  |  | Missing start/end date (not expanded)
2025-09-29 |  | M S Mdpl | 60 |  | TA416 | 54/0 | Material shifting work under progress. | Missing start/end date (not expanded)
2024-11-14 | 2026-11-25 | Pinky Dewi | 46.0492 | 0.062061 | TA416 | 6/2 | COMPLETED | Completion on/after 2025-10-09 (not expanded)
2024-11-10 | 2026-11-25 | Horil Mahto | 46.0492 | 0.061728 | TA416 | 38/3 | COMPLETED | Completion on/after 2025-10-09 (not expanded)
2025-06-02 | 2025-06-14 | Devine | 42.3742 | 3.2596 | TA416 | 53A/5 | COMPLETED | Single-occurrence gang (not expanded)
2025-08-14 | 2025-08-26 | Gagan Enterprise 2 Kajol | 46.0492 | 3.5422 | TA416 | 46/2 | COMPLETED | Single-occurrence gang (not expanded)
2025-08-18 | 2025-09-24 | Spotyfy 3 | 42.3742 | 1.1151 | TA416 | 56/8 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-15 | 2025-09-23 | Ananya Trader | 42.3742 | 4.7082 | TA416 | 48/1 | COMPLETED | Single-occurrence gang (not expanded)
2025-09-11 | 2025-09-28 | Maa Construction | 75.8584 | 4.2144 | TA416 | 17/0 | COMPLETED | Single-occurrence gang (not expanded)
2025-07-06 | 2025-08-07 | Bambole Traders | 45.697 | 1.3848 | TA413 | 40/1 | COMPLETED | Single-occurrence gang (not expanded)
| 2025-07-12 | Subash | 33.38 |  | TA421 | 9/10 | Completed | Missing start/end date (not expanded)
| 2025-07-13 | Naziruddin | 71.706 |  | TA421 | 14/0 | Completed | Missing start/end date (not expanded)
2025-09-13 |  | Praveen | 43.079 |  | TA421 | 39/7 | Top Section under Progress | Missing start/end date (not expanded)
2025-09-27 |  | Hassan | 36.37 |  | TA421 | 39/2 | Top Section under Progress | Missing start/end date (not expanded)
2025-10-01 |  | Subash | 72.63 |  | TA421 | 1/0 | Cage Section Completed | Missing start/end date (not expanded)
2025-10-07 |  | Rajiv Yadhav | 37.931 |  | TA421 | 43/5 | Material Shifting Done | Missing start/end date (not expanded)
2025-10-07 |  | D K Verma | 36.37 |  | TA421 | 43/3 | 1st Section under Progress | Missing start/end date (not expanded)
2025-10-07 |  | Khatun | 39.17 |  | TA421 | 9/3 | 1st Section under Progress | Missing start/end date (not expanded)
|  | Rajiv Yadhav | 44.851 |  | TA421 | 39/9 | Material Shifting Done | Missing start/end date (not expanded)
2024-08-23 | 2024-09-08 | S K Janarul | 36.37 | 2.1394 | TA421 | 22/5 | Completed | Single-occurrence gang (not expanded)
2024-09-12 | 2024-09-29 | Ashok Kumar | 36.37 | 2.0206 | TA421 | 21/7 | Completed | Single-occurrence gang (not expanded)
2024-09-21 | 2024-10-04 | Manirul Islam Khatun | 36.37 | 2.5979 | TA421 | 29/4 | Completed | Single-occurrence gang (not expanded)
2024-10-29 | 2024-11-05 | Ashokkumar | 36.37 | 4.5462 | TA421 | 22/2 | Completed | Single-occurrence gang (not expanded)
2025-09-21 | 2025-10-06 | Yadhav D K Verma | 37.931 | 2.3707 | TA421 | 43/4 | Completed | Single-occurrence gang (not expanded)
|  | Nan | 6223.9515 |  | TA505 |  | 132 | Missing start/end date (not expanded)
2025-09-23 |  | Jhemon Mahato 2 | 85.264 |  | TA505 | 144A/0 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Pankaj Singh Mp | 36.16 |  | TA505 | 167/4 | In-Progress | Missing start/end date (not expanded)
2025-09-26 |  | Jagannaath Saw Mp | 55.451 |  | TA505 | 160/0 | In-Progress | Missing start/end date (not expanded)
2025-09-30 |  | Toshan Mahato | 36.1598 |  | TA505 | 148/1 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Jyoti Const | 124.95 |  | TA505 | 112/0 | In-Progress | Missing start/end date (not expanded)
2025-10-01 |  | Shila Devi | 81.828 |  | TA505 | 128/0 | In-Progress | Missing start/end date (not expanded)
2025-10-02 |  | Pankaj Singh Mp | 36.1598 |  | TA505 | 167/2 | In-Progress | Missing start/end date (not expanded)
2025-10-08 |  | Paramanand 1 | 35.602 |  | TA505 | 160/1 | In-Progress | Missing start/end date (not expanded)
2025-10-09 |  | Deglal Mahato Mp | 36.1598 |  | TA505 | 169/5 | In-Progress | Missing start/end date (not expanded)
|  | Nan | 6223.9515 |  | TA505 |  | 132 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-04-22 | 2025-05-08 | Paramanand | 36.1598 | 2.127 | TA505 | 159/1 | Completed | Single-occurrence gang (not expanded)
2025-08-12 | 2025-08-30 | Anil Kumar Rudra Const | 37.9311 | 1.9964 | TA505 | 110/4 | Completed | Single-occurrence gang (not expanded)
2025-09-12 | 2025-10-04 | Anil Kumar | 62.444 | 2.715 | TA505 | 156/0 | Completed | Single-occurrence gang (not expanded)
2025-09-10 | 2025-09-25 | Jagannaath Saw Mp | 37.931 | 2.3707 | TA505 | 161/2 | Completed | Single-occurrence gang (not expanded)
2025-09-14 | 2025-09-28 | Gokul Sarkar Mp | 34.79 | 2.3193 | TA505 | 166/1 | Completed | Single-occurrence gang (not expanded)
| 2025-09-19 | Dhaneshwar | 171.017 |  | TA325 | 101/0 | Completed | Missing start/end date (not expanded)
| 2025-08-13 | Dhaneshwar | 172.151 |  | TA325 | 104/0 | Completed | Missing start/end date (not expanded)
| 2025-08-08 | Nan | 141.874 |  | TA325 | 153/0 | Completed | Missing start/end date (not expanded)
| 2025-07-20 | Nan | 37.73 |  | TA325 | 175/2 | Completed | Missing start/end date (not expanded)
| 2025-08-26 | Modina India | 122.808 |  | TA325 | 191/0 | Completed | Missing start/end date (not expanded)
|  | Dhaneshwar Mahto | 156.901 |  | TA325 | 102/0 |  | Missing start/end date (not expanded)
| 2025-10-05 | Modina India 3 Pgcil | 37.73 |  | TA325 | 229/3 |  | Missing start/end date (not expanded)
| 2025-10-05 | Muni Bibi 2 | 37.73 |  | TA325 | 237/1 |  | Missing start/end date (not expanded)
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | 237/0 |  | Missing start/end date (not expanded)
| 2025-10-08 | Dildar Electrical 2 Pgcil | 39.459 |  | TA325 | 237/6 |  | Missing start/end date (not expanded)
|  | Nan | 21414.926 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan |  |  | TA325 |  | Completed Erection | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  | 35 | Missing start/end date (not expanded)
|  | Nan | 146 |  | TA325 |  | 130 | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  | 33 | Missing start/end date (not expanded)
|  | Nan | 30 |  | TA325 |  | 28 | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 |  | 9 | Missing start/end date (not expanded)
|  | Nan | 267 |  | TA325 |  | 235 | Missing start/end date (not expanded)
|  | Nan | 25 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 9 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 55 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 26 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 47 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 16 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 5 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 40 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 19 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 11 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 15 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 73 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Missing start/end date (not expanded)
|  | Nan | 483 |  | TA325 |  |  | Missing start/end date (not expanded)
2035-03-04 | 2025-03-11 | Thanu Mahto | 36.045 |  | TA325 | 271/3 | Completed | Non-positive duration (Start > End or 0) (not expanded)
| 2025-10-15 | Rupesh | 89.146 |  | TA325 | 237/0 |  | Completion on/after 2025-10-09 (not expanded)
|  | Nan | 21414.926 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 267 |  | TA325 |  | 235 | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 9 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 3 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 6 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 5 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 8 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 7 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 4 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 2 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 1 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
|  | Nan | 483 |  | TA325 |  |  | Tower Weight out of range (<10.0 or >200.0) (not expanded)
2025-01-06 | 2025-01-11 | Surender Mahto | 44.728 | 7.4547 | TA325 | 135/1 | Completed | Single-occurrence gang (not expanded)
2024-09-16 | 2024-10-12 | Rejaul | 37.73 | 1.3974 | TA325 | 152/1 | Completed | Single-occurrence gang (not expanded)
2025-09-24 | 2025-10-05 | Sakia Khatun | 54.418 | 4.5348 | TA325 | 242/0 | Completed | Single-occurrence gang (not expanded)
2025-05-13 | 2025-06-26 | Senahul Modina India 3 | 37.73 | 0.83844 | TA325 | 247/4 | Completed | Single-occurrence gang (not expanded)
2024-08-29 | 2024-10-06 | Chahanur Bibi | 37.73 | 0.96744 | TA325 | 257/3 | Completed | Single-occurrence gang (not expanded)
2025-08-26 | 2025-10-04 | Kamruddin | 80.408 | 2.0102 | TA325 | 276/0 | Completed | Single-occurrence gang (not expanded)
2025-09-24 | 2025-10-03 | Sukhrridin | 36.045 | 3.6045 | TA325 | 237/3 | Completed | Single-occurrence gang (not expanded)
2025-03-14 | 2025-10-06 | Didar Electricals Pgcil | 36.405 | 0.17587 | TA325 | 247/3 | Completed | Single-occurrence gang (not expanded)
2025-09-13 | 2025-10-06 | Prayag Mahto | 63.509 | 2.6462 | TA325 | 215/0 | Completed | Single-occurrence gang (not expanded)
2025-09-24 | 2025-10-06 | Muni Bibi | 36.045 | 2.7727 | TA325 | 237/5 | Completed | Single-occurrence gang (not expanded)
2025-09-18 | 2025-10-08 | Md Akhtar | 72.238 | 3.4399 | TA325 | 234/0 | Completed | Single-occurrence gang (not expanded)

## Diagnostics
file | project | sheet | detected_header_row | columns_detected
DPR TA-416 __ Dt.-07-10-25 (PGCIL).xlsx | TA416 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, nan, nan, 1.0, 2.0, 3.0, 4.0
DPR - TA - 413.xlsx | TA413 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, completion date, gang name, gang strength
DPR TA 421 .xlsx | TA421 | Erection Compiled | 0 | sl no, location no, tower type, classification, starting date, tower weight, status, nan, nan, nan, completion date, gang name, gang strength, remark, tackwelding, tower tightening
DPR TA-505 08-10-2025.xlsx | TA505 | Erection Compiled | 3 | nan, sr. no, location no, tower type, tower weight, rev(inr), month of execution, gang name, status, starting date, completion date, no of compl. days, region, remarks if any
TA-325-DPR-ANTL-08-10-2025.xlsx | TA325 | Erection Compiled | 0 | sl. no, location no, type, type of tower, starting date, revenue, tower weight, status, completion date, gang name, final checking, tack welding

## ProjectDetails
project_code | project_name | client_name | noa_start | loa_end | project_mgr | regional_mgr | planning_eng | pch | section_inch | supervisor | _source_file | Project Name
TA 418 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 2024-02-07 | 2025-11-06 | Mr Sanjay Gupta | Mr Rajiv Sharma | Sanjib Samantaray | Mr Arun Felbin | Prabin Patra, D N Prasad | Rupesh, Bijendra, Rahman, Sitaram, Churamani, Saidur, Madhusudan, Ritlal, Somenath, Aflaudin, Akhtarul | DPR TA-416 __ Dt.-07-10-25 (PGCIL).xlsx | TA416
TA 413 | 765kv D/C Bikaner II to Neemrana II TL-02 | PGCIL | 2024-03-12 | 2025-12-11 | Mr. Anil Kumar Sharma | Mr. Tushar Grover | Mr. Santosh Mishra | Mr. Sanjay Gupta | Surendra Kumar Patel, Kartik Jhorar, Shuvam Gupta, Govind Bhardwaj | Suraj Chaudhary, Rudra Prasad, Aman Kumar Singh, Manoj Gupta, Raju Mahto, Khublal Mahto, Sushil Kumar, Haridashn, Manoj Kumar chaudhary, Nabirul Islam, Sanjay Kumar, Rahul Ravidas, Narayan Mahto, Akbar Ali, Kamal Ravidas, Manirul Islam, Tarique Anwar, Raju Prasad, Abhay Ojha | DPR - TA - 413.xlsx | TA413
TA 421 | 765KV D/C HEXA BIDAR PS - MAHESHWARAM (PG) TL | Power Grid Bidar Transmission Limited | 2024-02-15 | 2025-11-14 | Mr. Appala Naidu | Mr. Ajith Kumar | Mr. Bharath A D | Mr.Arun Felbin | Mr.Manikandan, Mr. Satyam Tiwari | Mr. Ramasish, Mr. Godvin John, Mr. Karunakar Nayak, Mr. Sudalaimuthu, Mr. Susanthpal, Mr. Srinivasan, Mr. Bhim Mahto, Mr. Ganesan, Mr. Ballu Thakur, Mr. Chandrasekar, Mr.Chandrasekharan, Mr. Anand | DPR TA 421 .xlsx | TA421
TA 505 | 765 Kv D/C Beawar-Mandsaur T/L | PBMTL | 2024-07-22 | 2026-06-21 | Mr. Sushil Kr Tiwari | Mr. Vijay Kute | Mr. Partha Pratim Pal | Mr. Arun Felbin | Mr.Deepak Anand, Mr.Bapan Mandal, Mr.Panneri Satish, Mr.Vinod Hankare | Nunuchand Mahto, Birkha Subba, Dilip Kumar, Teklal Mahato, Munid Meena, Mortuj Ali, Devdas Malik, Jayprakash Nishad, Kumar Singh, K. Sanjeevan, Mridul Baruah, Binda Shah, Prasanta Sahana, Lalit Sahoo, Sujit Roy, Ramprasad, Gourshankar, Vipin Mall, Aadesh | DPR TA-505 08-10-2025.xlsx | TA505

## README_Assumptions
Notes
Assumptions & Cleaning Rules:
- Start date cutoff: rows with Start Date before 2021-01-01 are not expanded and logged in 'Data Issues'.
- Completion date must be before 2025-10-09 (future completions go to 'Data Issues').
- Tower Weight range: only [10, 200] MT is considered valid for expansion; out-of-range rows go to 'Data Issues'.
- Missing or non-positive durations (Start/End missing or Start > End or 0) are logged to 'Data Issues' and not expanded.
- Gangs that performed erection only once (per Project+Gang) are not expanded and are logged in 'Data Issues'.
- Gang name normalization: remove special characters (digits kept), Title Case words, and insert a space before trailing digits (e.g., 'xyz4' â†’ 'Xyz 4').
- Sheets:
â€¢ ProdDailyExpanded : per-day expanded rows used by the dashboard
â€¢ ProdDailyExpandedSingles : per-day expanded rows including single-occurrence gangs
â€¢ RawData : per-erection rows (unexpanded), for traceability
â€¢ Data Issues : row-level data problems (reason in 'Issues' column)
â€¢ Issues : file-level problems (missing sheet/headers, read/open errors, etc.)
â€¢ Diagnostics : which sheet used, detected header row, and normalized header text
- Dashboard note: a 15-day productivity loss cap is used in downstream analytics.

## MicroPlanResponsibilities
project_key | project_name | entity_type | entity_name | location_no | revenue_planned | revenue_realised | tower_weight | tower_type | manpower | power_tools_issued | material_feeding | starting_date | completion_date | tack_welding | final_checking
ta413 | TA413 | Gang | Govind Mahto-01 | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Gang | Govind Mahto-01 | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Govind Mahto-01 | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Govind Mahto-01 | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Jawla Singh-1 | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Gang | Jawla Singh-1 | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Jawla Singh-1 | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Gang | Jawla Singh-1 | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Gang | Jwala Singh -2 | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Jwala Singh -2 | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Jwala Singh -2 | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Gang | Govind Mahto-02 | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Govind Mahto-02 | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Govind Mahto-02 | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Bhairaw Mahto | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Gang | Bhairaw Mahto | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Bhairaw Mahto | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Pritam Enterprises-1 | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Pritam Enterprises-2 | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Gang | Pritam Enterprises-2 | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Pritam Enterprises-2 | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Pritam Enterprises-3 | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Gang | Pritam Enterprises-3 | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Gang | Pritam Enterprises-3 | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Gang | Pritam Enterprises-3 | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Pritam Enterprises-4 | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Gang | Pritam Enterprises-4 | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Gang | SK.Samiul -1 | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Gang | SK.Samiul -1 | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Gang | SK.Samiul -1 | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Punam kumari-1 | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Gang | Punam kumari-1 | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Punam kumari-1 | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Gang | Punam kumari-1 | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Gang | Punam kumari-2 | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Gang | Punam kumari-2 | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Gang | Punam kumari-2 | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Gang | Punam kumari-2 | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Punam Kumari 4 | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Fouzi Ratto | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Fouzi Ratto | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Gang | Fouzi Ratto | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Gang | Sherra Const. | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Gang | Sherra Const. | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Gang | Sherra Const. | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Gang | Amar Singh | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Gang | Amar Singh | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Gang | Amar Singh | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Gang | Kartik Mahto | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Gang | Kartik Mahto | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Gang | Kartik Mahto | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Section Incharge | Shuvam Gupta | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Section Incharge | Shuvam Gupta | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Shuvam Gupta | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Section Incharge | Shuvam Gupta | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Shuvam Gupta | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Section Incharge | Shuvam Gupta | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Section Incharge | Kartik Jhorar | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Section Incharge | Kartik Jhorar | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Section Incharge | Shuvam Gupta | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Section Incharge | Shuvam Gupta | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Shuvam Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Kartik Jhorar | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Kartik Jhorar | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Section Incharge | Kartik Jhorar | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Section Incharge | Kartik Jhorar | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Section Incharge | Kartik Jhorar | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Section Incharge | Kartik Jhorar | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Section Incharge | Kartik Jhorar | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Section Incharge | Kartik Jhorar | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Section Incharge | Shuvam Gupta | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Section Incharge | Kartik Jhorar | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Section Incharge | Kartik Jhorar | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Section Incharge | Shuvam Gupta | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta413 | TA413 | Supervisor | Aman Kr Singh | 3B/2 | 9316.84 | 0 | 1 | DA+9 | 36 |  | 2025-09-25 | 2025-09-26 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta413 | TA413 | Supervisor | Aman Kr Singh | 2A/0 | 18633.68 | 0 | 2 | DD45+0 | 36 |  | 2025-10-06 | 2025-10-07 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Aman Kr Singh | 9/8 | 27950.52 | 0 | 3 | DA+0 | 36 |  | 2025-10-17 | 2025-10-18 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Aman Kr Singh | 9/9 | 37267.36 | 0 | 4 | DA+0 | 36 |  | 2025-10-23 | 2025-10-24 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Kamal Ravidas | 4/0 | 46584.2 | 0 | 5 | DB2+9 | 28 |  | 2025-09-24 | 2025-09-25 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Supervisor | Kamal Ravidas | 3A/0 | 55901.04 | 0 | 6 | DD45+3 | 28 |  | 2025-10-07 | 2025-10-08 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Kamal Ravidas | 9/10 | 65217.88 | 0 | 7 | DA+3 | 28 |  | 2025-10-18 | 2025-10-19 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta413 | TA413 | Supervisor | Kamal Ravidas | 9/11 | 74534.72 | 0 | 8 | DA+3 | 28 |  | 2025-10-25 | 2025-10-26 | 2025-11-02 | 2025-11-03 | 2025-11-04
ta413 | TA413 | Supervisor | Rudra Kumar | 3B/3 | 83851.56 | 0 | 9 | DA+6 | 26 |  | 2025-09-24 | 2025-09-25 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Rudra Kumar | 15/7 | 93168.4 | 0 | 10 | DA+0 | 26 |  | 2025-10-09 | 2025-10-10 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Rudra Kumar | 15/9 | 102485.24 | 0 | 11 | DA+0 | 26 |  | 2025-10-19 | 2025-10-20 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Supervisor | Sanjay Kumar | 15/0 | 111802.08 | 0 | 12 | DD60+25 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Sanjay Kumar | 15/1 | 121118.92 | 0 | 13 | DA+6 | 29 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Sanjay Kumar | 14/0 | 130435.76 | 0 | 14 | DD60+18 | 29 |  | 2025-10-18 | 2025-10-19 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 15/8 | 139752.6 | 0 | 15 | DA+1.5 | 47 |  | 2025-09-26 | 2025-09-27 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 17/0 | 149069.44 | 0 | 16 | DC1+3 | 47 |  | 2025-10-05 | 2025-10-06 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Bhupendra Choudhary | 13/0 | 158386.28 | 0 | 17 | DD60+9 | 47 |  | 2025-10-16 | 2025-10-17 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/0 | 167703.12 | 0 | 18 | DB1+6 | 30 |  | 2025-09-30 | 2025-10-01 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/1 | 177019.96 | 0 | 19 | DA+3 | 30 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Sanjay Kumar | 10/2 | 186336.8 | 0 | 20 | DA+3 | 30 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Akbar Ali | 3B/0 | 195653.64 | 0 | 21 | DB1+9 | 27 |  | 2025-09-30 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Supervisor | Akbar Ali | 15/11 | 204970.48 | 0 | 22 | DA+0 | 27 |  | 2025-10-09 | 2025-10-10 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Akbar Ali | 15/12 | 214287.32 | 0 | 23 | DA+6 | 27 |  | 2025-10-16 | 2025-10-17 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Rudra Prasad | 3B/1 | 223604.16 | 0 | 24 | DA+3 | 38 |  | 2025-08-28 | 2025-08-29 | 2025-09-08 | 2025-09-09 | 2025-09-10
ta413 | TA413 | Supervisor | Rudra Prasad | 11/0 | 232921 | 0 | 25 | DD45+0 | 38 |  | 2025-09-07 | 2025-09-08 | 2025-09-20 | 2025-09-21 | 2025-09-22
ta413 | TA413 | Supervisor | Rudra Prasad | 21/0 | 242237.84 | 0 | 26 | DB1+0 | 38 |  | 2025-09-19 | 2025-09-20 | 2025-10-02 | 2025-10-03 | 2025-10-04
ta413 | TA413 | Supervisor | Rudra Prasad | 21/1 | 251554.68 | 0 | 27 | DA+0 | 38 |  | 2025-10-01 | 2025-10-02 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Abhiya Ojha | 3A/4 | 260871.52 | 0 | 28 | DA+0 | 29 |  | 2025-09-30 | 2025-10-01 | 2025-10-11 | 2025-10-12 | 2025-10-13
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/3 | 270188.36 | 0 | 29 | DA+6 | 29 |  | 2025-10-10 | 2025-10-11 | 2025-10-17 | 2025-10-18 | 2025-10-19
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/4 | 279505.2 | 0 | 30 | DA+0 | 29 |  | 2025-10-16 | 2025-10-17 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta413 | TA413 | Supervisor | Abhiya Ojha | 21/5 | 288822.04 | 0 | 31 | DA+0 | 29 |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta413 | TA413 | Supervisor | Haridasn | 30/2 | 298138.88 | 0 | 32 | DA+9 | 22 |  | 2025-09-18 | 2025-09-19 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Supervisor | Haridasn | 29A/0 | 307455.72 | 0 | 33 | DB1+0 | 22 |  | 2025-10-03 | 2025-10-04 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta413 | TA413 | Supervisor | Haridasn | 30/5 | 316772.56 | 0 | 34 | DA+0 | 22 |  | 2025-10-09 | 2025-10-10 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/0 | 326089.4 | 0 | 35 | DD60+3 | 33 |  | 2025-09-30 | 2025-10-01 | 2025-10-08 | 2025-10-09 | 2025-10-10
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/3 | 335406.24 | 0 | 36 | DA+1.5 | 33 |  | 2025-10-07 | 2025-10-08 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/4 | 344723.08 | 0 | 37 | DA+3 | 33 |  | 2025-10-15 | 2025-10-16 | 2025-10-24 | 2025-10-25 | 2025-10-26
ta413 | TA413 | Supervisor | Rahul Ravidas | 20/5 | 354039.92 | 0 | 38 | DA+0 | 33 |  | 2025-10-23 | 2025-10-24 | 2025-11-01 | 2025-11-02 | 2025-11-03
ta413 | TA413 | Supervisor | Nabirul Islam | 18/4 | 363356.76 | 0 | 39 | DA-3 | 32 |  | 2025-09-30 | 2025-10-01 | 2025-10-06 | 2025-10-07 | 2025-10-08
ta413 | TA413 | Supervisor | Nabirul Islam | 18/5 | 372673.6 | 0 | 40 | DA+0 | 32 |  | 2025-10-05 | 2025-10-06 | 2025-10-13 | 2025-10-14 | 2025-10-15
ta413 | TA413 | Supervisor | Nabirul Islam | 18/6 | 381990.44 | 0 | 41 | DA+9 | 32 |  | 2025-10-12 | 2025-10-13 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta413 | TA413 | Supervisor | Nabirul Islam | 18/7 | 391307.28 | 0 | 42 | DA+1.5 | 32 |  | 2025-10-19 | 2025-10-20 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/5 | 400624.12 | 0 | 43 | DA+6 | 39 |  | 2025-09-24 | 2025-09-25 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/4 | 409940.96 | 0 | 44 | DA+3 | 39 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Manoj Gupta | 29A/3 | 419257.8 | 0 | 45 | DA+6 | 39 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Khooblal | 46/0 | 428574.64 | 0 | 46 | DB1+12 | 42 |  | 2025-09-29 | 2025-09-30 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Khooblal | 43/0 | 437891.48 | 0 | 47 | DB1+0 | 42 |  | 2025-10-08 | 2025-10-09 | 2025-10-18 | 2025-10-19 | 2025-10-20
ta413 | TA413 | Supervisor | Khooblal | 37/3 | 447208.32 | 0 | 48 | DA-1.5 | 42 |  | 2025-10-17 | 2025-10-18 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 45/0 | 456525.16 | 0 | 49 | DB1+9 | 38 |  | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-06 | 2025-10-07
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 43/1 | 465842 | 0 | 50 | DA-1.5 | 38 |  | 2025-10-04 | 2025-10-05 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta413 | TA413 | Supervisor | Manoj Kumar Choudhary | 37/2 | 475158.84 | 0 | 51 | DA+3 | 38 |  | 2025-10-11 | 2025-10-12 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta413 | TA413 | Supervisor | Raju Mahto | 41/1 | 484475.68 | 0 | 52 | DA+9 | 25 |  | 2025-09-20 | 2025-09-21 | 2025-10-04 | 2025-10-05 | 2025-10-06
ta413 | TA413 | Supervisor | Raju Mahto | 41/0 | 493792.52 | 0 | 53 | DB1+9 | 25 |  | 2025-10-03 | 2025-10-04 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta413 | TA413 | Supervisor | Raju Mahto | 24/0 | 503109.36 | 0 | 54 | DD60+18 | 25 |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta413 | TA413 | Supervisor | Shuseel | 40/10 | 512426.2 | 0 | 55 | DA+3 | 38 |  | 2025-09-28 | 2025-09-29 | 2025-10-09 | 2025-10-10 | 2025-10-11
ta413 | TA413 | Supervisor | Shuseel | 40/8 | 521743.04 | 0 | 56 | DA-1.5 | 38 |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta413 | TA413 | Supervisor | Shuseel | 25/0 | 531059.88 | 0 | 57 | DD60+18 | 38 |  | 2025-10-14 | 2025-10-15 | 2025-11-04 | 2025-11-05 | 2025-11-06
ta416 | TA416 | Gang | Maa Construction | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Maa Construction | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Gang | Gourishankar | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Gang | Gourishankar | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Gang | Reeta Bharti | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Unity India | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Gang | Unity India | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Ananya Trader-1 | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Amit choudhury | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Gang | Amit choudhury | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Punam Kumari-1 | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Gang | Punam Kumari-1 | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Sainik Trader | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Sainik Trader | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Sainik Trader | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Spotify-1 | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Spotify-1 | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Spotify-1 | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Punam Kumari-2 | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Punam Kumari-2 | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Punam Kumari-2 | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Spotify-1 | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Gang | Spotify-1 | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Gang | Spotify-1 | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Gang | Pankaj | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Gang | Pankaj | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Gang | Mahon Mahto | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Mahon Mahto | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Gang | Mahon Mahto | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Gang | Kongres | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Gang | Kongres | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Gang | Kongres | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | Prabin Patra | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | Prabin Patra | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Section Incharge | Prabin Patra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Section Incharge | Prabin Patra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Section Incharge | Prabin Patra | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Section Incharge | D N Prasad | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Section Incharge | D N Prasad | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Section Incharge | D N Prasad | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Section Incharge | D N Prasad | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Section Incharge | D N Prasad | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Section Incharge | D N Prasad | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Section Incharge | D N Prasad | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Section Incharge | D N Prasad | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Section Incharge | D N Prasad | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Section Incharge | D N Prasad | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Section Incharge | D N Prasad | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Section Incharge | D N Prasad | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Churamani | 0/0 | 666437.14 | 0 | 98.118 | DCT+0 | 20 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Churamani | 2/2 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta416 | TA416 | Supervisor | Bijendra | 22A/0 | 974538 | 0 | 110.575 | DB+25 | 23 | YES | 2025-09-27 | 2025-09-29 | 2025-10-14 | 2025-10-15 | 2025-10-16
ta416 | TA416 | Supervisor | Bijendra | 23/0 | 1004656 | 0 | 110.696 | DC+18 |  |  | 2025-09-14 | 2025-10-15 | 2025-10-27 | 2025-10-28 | 2025-10-29
ta416 | TA416 | Supervisor | Rupesh | 27/0 | 875860 | 0 | 101.692 | DD60+3 | 21 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Maqbul | 37/0 | 1004656 | 0 | 110.696 | DC+18 | 22 | NO | 2025-09-24 | 2025-09-25 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Supervisor | Maqbul | 57/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Saidur | 42/0 | 1492772 | 0 | 143.462 | DD60+18 | 36 | NO | 2025-09-30 | 2025-10-01 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Ali raza | 46/0 | 568303.9 | 0 | 64.482 | DB+0 | 34 | NO | 2025-09-28 | 2025-10-01 | 2025-10-10 | 2025-10-11 | 2025-10-12
ta416 | TA416 | Supervisor | Ali raza | 45/0 | 837742.5 | 0 | 97.229 | DD60+0 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Somenath | 50/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | YES | 2025-09-28 | 2025-10-01 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Supervisor | Somenath | 49/0 | 828626.51 | 0 | 90.125 | DC+9 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Afeludin | 53/0 | 666437.35 | 0 | 73.426 | DC+0 | 25 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Afeludin | 52/1 | 669569.35 | 0 | 75.897 | DB+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Afeludin | 53A/0 | 568303.9 | 0 | 64.482 | DB+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Akhtarul | 53A/1 | 450627.94 | 0 | 53.324 | DA+6 | 26 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Akhtarul | 52/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Akhtarul | 53A/7 | 371402 | 0 | 43.776 | DA+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | madhusudan | 54/0 | 601785.72 | 601785.72 | 67.112 | DB+3 | 24 | NO | 2025-09-25 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | madhusudan | 54/2 | 359483 | 0 | 42.374 | DA-3 |  | NO | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | madhusudan | 55/0 | 666437.35 | 0 | 73.426 | DC+0 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | Akhtarul | 56/6 | 371402 | 0 | 43.776 | DA+0 | 22 | NO | 2025-09-28 | 2025-10-01 | 2025-10-12 | 2025-10-13 | 2025-10-14
ta416 | TA416 | Supervisor | Akhtarul | 56/7 | 450627.94 | 0 | 53.324 | DA+6 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta416 | TA416 | Supervisor | Akhtarul | 55/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-30 | 2025-10-24 | 2025-10-25
ta416 | TA416 | Supervisor | Maqbul | 38/0 | 1004656 | 0 | 110.696 | DC+18 | 31 | NO | 2025-10-04 | 2025-10-05 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta416 | TA416 | Supervisor | Maqbul | 57/1 | 359483 | 0 | 42.374 | DA-3 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta416 | TA416 | Supervisor | Ritlal | 63/0 | 708133.71 | 0 | 78.073 | DC+3 | 40 | NO | 2025-09-28 | 2025-10-01 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | Ritlal | 61/0 | 1853580.61 | 0 | 188.378 | DD60+30 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta416 | TA416 | Supervisor | Ritlal | 62/0 | 1125399 | 0 | 124.037 | DC+25 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta416 | TA416 | Supervisor | Ritlal | 64/3 | 359483 | 359483 | 42.374 | DA-3 | 36 | NO | 2025-09-24 | 2025-09-28 | 2025-10-07 | 2025-10-08 | 2025-10-09
ta416 | TA416 | Supervisor | Ritlal | 69A/0 | 837742.5 | 0 | 97.229 | DD60+0 |  | NO | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-17
ta416 | TA416 | Supervisor | Ritlal | 58/0 | 1492772 | 0 | 143.462 | DD60+18 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta421 | TA421 | Gang | Subash | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Gang | Subash | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Gang | Subash | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Gang | Subash | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Gang | Subash | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Gang | Subash | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Gang | Subash | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Gang | Shakila Khatun | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Gang | Shakila Khatun | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Gang | Shakila Khatun | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Gang | Shakila Khatun | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Gang | Shakila Khatun | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Gang | Shakila Khatun | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Gang | Nasiruddin (Bulbul ) | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Gang | Sabhnam Praveen | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Gang | Sabhnam Praveen | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Gang | Sabhnam Praveen | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Gang | Rajiv Yadhav | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Gang | Rajiv Yadhav | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Gang | D K Verma | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Gang | D K Verma | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Gang | D K Verma | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Gang | D K Verma | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Gang | D K Verma | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Manikandan | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Section Incharge | Mr. Manikandan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Section Incharge | Mr. Manikandan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Section Incharge | Mr. Manikandan | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Section Incharge | Mr. Manikandan | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Section Incharge | Mr. Satyam Tiwari | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 1/0 | 661012 | 0 | 72.63 | 2D60+0 | 33 | No |  | WIP | 2025-10-08 | 2025-10-18 | 2025-10-13
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/3 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-08 | 2025-10-09 | 2025-10-12 | 2025-10-22 | 2025-10-17
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/1 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-10 | 2025-10-13 | 2025-10-16 | 2025-10-26 | 2025-10-21
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/4 | 292211 | 0 | 31.99 | 2DA+0 | 33 | No | 2025-10-15 | 2025-10-17 | 2025-10-20 | 2025-10-30 | 2025-10-25
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/5 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-17 | 2025-10-21 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/8 | 307108 | 0 | 33.38 | 2DA+3 | 33 | No | 2025-10-21 | 2025-10-25 | 2025-10-27 | 2025-11-06 | 2025-11-01
ta421 | TA421 | Supervisor | Mr. Chandrasekar | 4/11 | 347642 | 0 | 37.7169 | 2DA+6 | 33 | No | 2025-10-25 | 2025-10-28 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/18 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No |  | Completed | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Supervisor | Mr. Srinivasan | 9/3 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-05 | 2025-10-06 | 2025-10-09 | 2025-10-19 | 2025-10-14
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/19 | 347642 | 0 | 37.7169 | 2DA+6 | 32 | No | 2025-10-07 | 2025-10-10 | 2025-10-14 | 2025-10-24 | 2025-10-19
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/20 | 362229 | 0 | 39.1682 | 2DA+9 | 32 | No | 2025-10-11 | 2025-10-15 | 2025-10-19 | 2025-10-29 | 2025-10-24
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/13 | 292211 | 0 | 31.99 | 2DA+0 | 32 | No | 2025-10-16 | 2025-10-20 | 2025-10-25 | 2025-11-04 | 2025-10-30
ta421 | TA421 | Supervisor | Mr. Srinivasan | 4/14 | 307108 | 0 | 33.38 | 2DA+3 | 32 | No | 2025-10-23 | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 39/2 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No |  | WIP | 2025-10-05 | 2025-10-15 | 2025-10-10
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 39/9 | 406294 | 0 | 44.85 | 3DA+9 | 24 | No | 2025-09-29 | 2025-10-06 | 2025-10-10 | 2025-10-20 | 2025-10-15
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 36/7 | 342752 | 0 | 37.931 | 3DA+3 | 24 | No | 2025-10-09 | 2025-10-11 | 2025-10-15 | 2025-10-25 | 2025-10-20
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 36/8 | 327992 | 0 | 36.372 | 3DA+0 | 24 | No | 2025-10-14 | 2025-10-16 | 2025-10-22 | 2025-11-01 | 2025-10-27
ta421 | TA421 | Supervisor | Mr. Bhimmahto | 37/0 | 478941 | 0 | 54.66 | 3DB2+0 | 24 | No | 2025-10-20 | 2025-10-23 | 2025-10-30 | 2025-11-09 | 2025-11-04
ta421 | TA421 | Supervisor | Mr. Anand | 39/7 | 391124 | 0 | 43.08 | 3DA+6 | 20 | No |  | WIP | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Supervisor | Mr. Anand | 16/11 | 342752 | 0 | 37.931 | 3DA+3 | 20 | No | 2025-10-07 | 2025-10-08 | 2025-10-17 | 2025-10-27 | 2025-10-22
ta421 | TA421 | Supervisor | Mr. Anand | 11/4 | 327992 | 0 | 36.372 | 3DA+0 | 20 | No | 2025-10-15 | 2025-10-18 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta421 | TA421 | Supervisor | Mr. Ram Asish | 11/7 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-09 | 2025-10-11 | 2025-10-20 | 2025-10-25 | 2025-10-24
ta421 | TA421 | Supervisor | Mr. Ram Asish | 11/8 | 327992 | 0 | 36.372 | 3DA+0 | 22 | No | 2025-10-18 | 2025-10-21 | 2025-10-27 | 2025-10-30 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/4 | 342752 | 0 | 37.931 | 3DA+3 | 25 | yes |  | Completed | 2025-10-07 | 2025-10-17 | 2025-10-12
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/5 | 406294 | 0 | 44.85 | 3DA+9 | 25 | yes | 2025-09-25 | 2025-10-08 | 2025-10-13 | 2025-10-23 | 2025-10-18
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 43/3 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-03 | 2025-10-14 | 2025-10-18 | 2025-10-28 | 2025-10-23
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 41/1 | 342752 | 0 | 36.372 | 3DA+3 | 25 | yes | 2025-10-12 | 2025-10-19 | 2025-10-24 | 2025-11-03 | 2025-10-29
ta421 | TA421 | Supervisor | Mr. Sudalaimuthu | 42/2 | 327992 | 0 | 36.372 | 3DA+0 | 25 | yes | 2025-10-20 | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05
tb408 | TB408 | Gang | Sheetal Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Gang | Priyanka Devi (Santosh) | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Gang | Jirwa Devi | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Gang | Jirwa Devi | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Gang | Jirwa Devi | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Gang | Nimal Mahto | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Gang | Nimal Mahto | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Gang | Nimal Mahto | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Gang | Nimal Mahto | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Gang | Shobha Devi | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Gang | Shobha Devi | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Gang | Shobha Devi | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Gang | Shobha Devi | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Gang | Shobha Devi | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Gang | Vivek Ganju | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Gang | Vivek Ganju | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Gang | Vivek Ganju | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Gang | Vivek Ganju | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Gang | Vivek Ganju | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Gang | Vivek Ganju | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Gang | Chinta Devi | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Gang | Chinta Devi | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Gang | Chinta Devi | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Gang | Chinta Devi | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Gang | Sunny Construction | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Gang | Sunny Construction | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Section Incharge | Sumit Singh | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Section Incharge | Vijay Yadav | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Section Incharge | Vijay Yadav | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Section Incharge | Vijay Yadav | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Section Incharge | Ram Tirath Singh | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Supervisor | Vaibhav Sharma | 6/1 | 331201.1091 | 0 | 37.5044 | DA+0 | 30 | Yes | Yes | 2025-09-25 | 2025-10-03 | 2025-10-05 | 2025-10-04
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/10 | 401042.4503 | 0 | 45.413 | DA+6 | 32 | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/9 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Supervisor | Gangadin Sahu | 21/7 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Supervisor | Gangadin Sahu | 22/0 | 530714.6377 | 0 | 60.0968 | DB2+3 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Supervisor | Gangadin Sahu | 30/2 | 331162.5 | 0 | 37.5 | DA+0 | 34 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Supervisor | Ganesh Singh | 35/0 | 599392.212 | 0 | 67.8737 | DB2+6 |  | No | No | 2025-10-07 | 2025-10-12 | 2025-10-14 | 2025-10-13
tb408 | TB408 | Supervisor | Ganesh Singh | 35/1 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-13 | 2025-10-18 | 2025-10-20 | 2025-10-19
tb408 | TB408 | Supervisor | Ganesh Singh | 35/2 | 508641.2353 | 0 | 57.5972 | DB1+0 | 29 | No | No | 2025-10-19 | 2025-10-24 | 2025-10-26 | 2025-10-25
tb408 | TB408 | Supervisor | Ganesh Singh | 35/3 | 599392.212 | 0 | 67.8737 | DB1+6 |  | No | No | 2025-10-25 | 2025-10-30 | 2025-11-01 | 2025-10-31
tb408 | TB408 | Supervisor | Ganesh Singh | 35/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-10-07 | 2025-10-17 | 2025-10-19 | 2025-10-18
tb408 | TB408 | Supervisor | Ganesh Singh | 35/5 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-27 | 2025-10-06 | 2025-10-08 | 2025-10-07
tb408 | TB408 | Supervisor | Umesh Prasad | 40/0 | 586211.5559 | 0 | 66.3811 | DC2+0 | 32 | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Supervisor | Umesh Prasad | 40/1 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-10 | 2025-10-14 | 2025-10-16 | 2025-10-15
tb408 | TB408 | Supervisor | Umesh Prasad | 41/0 | 689984.1071 | 0 | 78.132 | DC1+6 |  | No | No | 2025-10-15 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Supervisor | Umesh Prasad | 41/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Supervisor | Umesh Prasad | 42/0 | 586211.5559 | 0 | 66.3811 | DC1+0 |  | No | No | 2025-10-26 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/1 | 401042.4503 | 0 | 45.413 | DA+6 | 35 | No | No | 2025-10-07 | 2025-10-11 | 2025-10-13 | 2025-10-12
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/2 | 401042.4503 | 0 | 45.413 | DA+6 |  | No | No | 2025-10-12 | 2025-10-16 | 2025-10-18 | 2025-10-17
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/3 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-17 | 2025-10-21 | 2025-10-23 | 2025-10-22
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/4 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-22 | 2025-10-26 | 2025-10-28 | 2025-10-27
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/5 | 416684.9949 | 0 | 47.1844 | DA+9 |  | No | No | 2025-10-27 | 2025-10-31 | 2025-11-02 | 2025-11-01
tb408 | TB408 | Supervisor | Pramod Kumar Sahoo | 42/6 | 331201.1091 | 0 | 37.5044 | DA+0 |  | Yes | Yes | 2025-09-22 | 2025-10-07 | 2025-10-09 | 2025-10-08
tb408 | TB408 | Supervisor | Shakib Hussain | 43/2 | 331201.1091 | 0 | 37.5044 | DA+0 | 31 | No | No | 2025-10-08 | 2025-10-13 | 2025-10-15 | 2025-10-14
tb408 | TB408 | Supervisor | Shakib Hussain | 43/4 | 343063.2086 | 0 | 38.8476 | DA+3 |  | No | No | 2025-10-14 | 2025-10-19 | 2025-10-21 | 2025-10-20
tb408 | TB408 | Supervisor | Shakib Hussain | 44/8 | 786842.1 | 0 | 89.1 | DCT+0 |  | No | No | 2025-10-20 | 2025-10-25 | 2025-10-27 | 2025-10-26
tb408 | TB408 | Supervisor | Shakib Hussain | 46/0 | 1409883.1891 | 0 | 143.6019 | DD60+25 |  | Yes | Yes | 2025-09-29 | 2025-10-09 | 2025-10-11 | 2025-10-10
tb408 | TB408 | Supervisor | Shakib Hussain | 55/0 | 599392.212 | 0 | 67.8737 | DB1+6 | 37 | Yes | Yes | 2025-09-30 | 2025-10-10 | 2025-10-12 | 2025-10-11
tb408 | TB408 | Supervisor | Shakib Hussain | 55/2 | 331201.1091 | 0 | 37.5044 | DA+0 |  | No | No | 2025-10-11 | 2025-10-21 | 2025-10-23 | 2025-10-22
ta505 | TA505 | Gang | Jwala Singh | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Jwala Singh | 105/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Jwala Singh | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Gang | Jwala Singh | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | New Gang-1 | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Gang | New Gang-1 | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Gang | New Gang-1 | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Gang | New Gang-2 | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Gang | New Gang-2 | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Gang | New Gang-2 | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Gang | Shila Devi | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Gang | Shila Devi | 130/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Gang | Shila Devi | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Shila Devi | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Jyoti Enterprises | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Jyoti Enterprises | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Gang | Jyoti Enterprises | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Deglal Mahto | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Deglal Mahto | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Gang | Deglal Mahto | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Gang | Deglal Mahto | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Anil Kumar | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Gang | Anil Kumar | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Gang | Anil Kumar | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Toshan Mahto | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Gang | Toshan Mahto | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Gang | Toshan Mahto | 147A/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Gang | Toshan Mahto | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Gang | Toshan Mahto | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Gang | Parmanand (MP) | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Parmanand (MP) | 159/0 | 650940.94 | 0 | 59.501 | DB2+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Parmanand (MP) | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Parmanand (MP) | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Gang | Jagannath Mahto | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Gang | Jagannath Mahto | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Gang | Jagannath Mahto | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Gang | Jagannath Mahto | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Gang | Jagannath Mahto | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Gang | Pankaj Singh | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Pankaj Singh | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Gang | Pankaj Singh | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Gang | Pankaj Singh | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Gang | Pankaj Singh | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Gang | Deglal Mahto (MP) | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Gang | Deglal Mahto (MP) | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Gang | Deglal Mahto (MP) | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Section Incharge | Deepak Anand | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Deepak Anand | 105/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Deepak Anand | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Section Incharge | Deepak Anand | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Section Incharge | Deepak Anand | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Section Incharge | Deepak Anand | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Section Incharge | Deepak Anand | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Section Incharge | Deepak Anand | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Section Incharge | Deepak Anand | 130/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Section Incharge | Deepak Anand | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Deepak Anand | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Deepak Anand | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Section Incharge | Deepak Anand | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Deepak Anand | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Section Incharge | Deepak Anand | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Section Incharge | Deepak Anand | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Deepak Anand | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Section Incharge | Bapan Mandal | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Section Incharge | Bapan Mandal | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Bapan Mandal | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Section Incharge | Bapan Mandal | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Section Incharge | Bapan Mandal | 147A/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Section Incharge | Bapan Mandal | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Section Incharge | Bapan Mandal | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Section Incharge | Vinod Hankare | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 159/0 | 650940.94 | 0 | 59.501 | DB2+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Vinod Hankare | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Section Incharge | Vinod Hankare | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Section Incharge | Vinod Hankare | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Section Incharge | Vinod Hankare | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Section Incharge | Vinod Hankare | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Section Incharge | Vinod Hankare | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Supervisor | None | 110/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 105/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 109/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-22 | 2025-10-23 | 2025-10-24
ta505 | TA505 | Supervisor | None | 101/0 | 720650.62 | 0 | 65.873 | DC1+3 |  |  | 2025-10-22 | 2025-10-23 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 116/0 | 843222.38 | 0 | 77.077 | DD45+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Supervisor | None | 102/0 | 773950.3 | 0 | 70.745 | DC2+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Supervisor | None | 118/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Supervisor | None | 103/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-10 | 2025-10-11 | 2025-10-13
ta505 | TA505 | Supervisor | None | 114/4 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-10 | 2025-10-11 | 2025-10-19 | 2025-10-20 | 2025-10-22
ta505 | TA505 | Supervisor | None | 121/0 | 711406.32 | 0 | 65.028 | DB1+6 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-28 | 2025-10-29 | 2025-10-30
ta505 | TA505 | Supervisor | None | 126/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Supervisor | None | 130/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Supervisor | None | 130/2 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 128/0 | 895209.26 | 0 | 81.829 | DC2+9 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 129A/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 132/0 | 1063017.92 | 0 | 97.168 | DD60+6 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-16 | 2025-10-17 | 2025-10-19
ta505 | TA505 | Supervisor | None | 112/0 | 1366953 | 0 | 124.95 | DD60+18 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 114/0 | 735846.28 | 0 | 67.262 | DC2+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 115/0 | 952009.74 | 0 | 87.021 | DD60+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-17 | 2025-10-18 | 2025-10-20
ta505 | TA505 | Supervisor | None | 136/2 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-17 | 2025-10-18 | 2025-10-23 | 2025-10-24 | 2025-10-25
ta505 | TA505 | Supervisor | None | 136/5 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 156/0 | 683137.36 | 0 | 62.444 | DC1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-12 | 2025-10-13 | 2025-10-15
ta505 | TA505 | Supervisor | None | 140/0 | 823552.26 | 0 | 75.279 | DC1+9 |  |  | 2025-10-12 | 2025-10-13 | 2025-10-23 | 2025-10-24 | 2025-10-26
ta505 | TA505 | Supervisor | None | 140/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-23 | 2025-10-24 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 135/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-07 | 2025-10-08 | 2025-10-10
ta505 | TA505 | Supervisor | None | 135/3 | 499925.18 | 0 | 45.697 | DA+9 |  |  | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-14 | 2025-10-16
ta505 | TA505 | Supervisor | None | 147A/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-13 | 2025-10-14 | 2025-10-19 | 2025-10-20 | 2025-10-21
ta505 | TA505 | Supervisor | None | 148/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-19 | 2025-10-20 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Supervisor | None | 148A/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-31 | 2025-11-01 | 2025-11-02
ta505 | TA505 | Supervisor | None | 158/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 159/0 | 650940.94 | 0 | 59.501 | DB2+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 159/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 160/1 | 389485.88 | 0 | 35.602 | DA-1.5 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-29 | 2025-10-30 | 2025-10-31
ta505 | TA505 | Supervisor | None | 160/0 | 606633.94 | 0 | 55.451 | DB1+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-08 | 2025-10-09 | 2025-10-11
ta505 | TA505 | Supervisor | None | 161/0 | 679549.04 | 0 | 62.116 | DB2+3 |  |  | 2025-10-08 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 2025-10-18
ta505 | TA505 | Supervisor | None | 161/1 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-15 | 2025-10-16 | 2025-10-20 | 2025-10-21 | 2025-10-22
ta505 | TA505 | Supervisor | None | 164/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-20 | 2025-10-21 | 2025-10-25 | 2025-10-26 | 2025-10-27
ta505 | TA505 | Supervisor | None | 164/3 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-25 | 2025-10-26 | 2025-10-30 | 2025-10-31 | 2025-11-01
ta505 | TA505 | Supervisor | None | 164/5 | 479215.76 | 0 | 43.804 | DA+6 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 164/6 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Supervisor | None | 164/7 | 414965.14 | 0 | 37.931 | DA+3 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Supervisor | None | 167/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Supervisor | None | 167/3 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28
ta505 | TA505 | Supervisor | None | 167/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-01 | 2025-10-02 | 2025-10-06 | 2025-10-07 | 2025-10-09
ta505 | TA505 | Supervisor | None | 167/1 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-06 | 2025-10-07 | 2025-10-11 | 2025-10-12 | 2025-10-14
ta505 | TA505 | Supervisor | None | 169/2 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-11 | 2025-10-12 | 2025-10-16 | 2025-10-17 | 2025-10-18
ta505 | TA505 | Supervisor | None | 169/4 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-16 | 2025-10-17 | 2025-10-21 | 2025-10-22 | 2025-10-23
ta505 | TA505 | Supervisor | None | 169/5 | 395590.4 | 0 | 36.16 | DA+0 |  |  | 2025-10-21 | 2025-10-22 | 2025-10-26 | 2025-10-27 | 2025-10-28

## MicroPlanIndex
file_path | project_name | project_key | rows_cleaned | status | error
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-413 Oct'25.xlsx | TA413 | ta413 | 57 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-416 Oct'25.xlsx | TA416 | ta416 | 34 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TA-421 Oct'25.xlsx | TA421 | ta421 | 28 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan - TB-408 Oct'25.xlsx | TB408 | tb408 | 29 | ok
C:\Users\kaushikb\Documents\Work\Git\Office-work-\Raw Data\Micro Plans\Micro Plan TA-505 Oct '25.xlsx | TA505 | ta505 | 49 | ok