## Methodology
Item | Definition
Scope | Competitor rows from Competitor Analysis.xlsx; May 2026 and June 2026 only; activities FDN, ERE, STR.
Internal source - Foundation | Parquets/Foundation/FoundationCompletions.parquet. Detail rows are counted by completion month; snapshot cumulative deltas are used only when no detail rows exist for that code/month.
Internal source - Erection | Parquets/Erection/RawData.parquet for completed tower count/MT/average tower weight by completion month; ProdDailyExpandedSingles.parquet for work-date idle baseline.
Internal source - Stringing | Parquets/Stringing/StringingDaily.parquet; daily_km is summed by date month.
Tower weight | Competitor erection tower count is converted to MT using the weighted same-month average tower weight from the listed internal project code(s). If no same-month internal tower weight exists, equivalent MT is blank.
Idle baseline | Idle uses exact internal work dates. Gaps between work dates are capped at 15 days and gaps over 45 days are treated as off-system/excluded, matching the dashboard idle utilities.
Slash-separated internal codes | Codes such as TA505/TA509 are treated as the pooled comparator named by the sheet. Code-level details are retained in Internal_Code_Detail.
Scenario cases | Five cases vary the internal idle baseline applied to competitor productivity: -20%, -10%, base, +10%, +20% idle days.
Productivity | Calendar productivity = output / calendar days in the month. Idle-adjusted productivity = output / (calendar days - assumed capped idle days).
No invented values | Missing internal project codes, missing same-month tower weights, and missing idle baselines are left blank and flagged in notes.

## Competitor_Input_Long
Sl.No. | Competitor Project | Agency | Internal Project Code Raw | Internal Codes Parsed | Month | Activity Code | Activity | Competitor Quantity
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0

## Base_Case_Comparison
Sl.No. | Competitor Project | Agency | Internal Project Code Raw | Internal Codes Parsed | Month | Activity Code | Activity | Competitor Quantity | Month Days | Internal Codes Count | Internal Codes Found | Internal Quantity | Internal Unit | Internal Work Date Count | Internal Avg Idle Days Capped | Internal Productive Days Proxy | Internal Calendar Productivity | Internal Idle Adjusted Productivity | Same-Month Avg Tower Weight MT | Competitor Equivalent Output | Output Unit | Baseline Notes | Scenario | Idle Multiplier | Competitor Assumed Idle Days | Competitor Productive Days Proxy | Competitor Calendar Productivity | Competitor Idle Adjusted Productivity | Competitor vs Internal Difference | Competitor vs Internal Difference %
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle Base | 1 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle Base | 1 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle Base | 1 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle Base | 1 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.12567
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle Base | 1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle Base | 1 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle Base | 1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle Base | 1 | 3 | 27 | 0 | 0 | -0.11157 | -100%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle Base | 1 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle Base | 1 | 12 | 18 | 30.9888 | 51.648 | 35.508 | 220%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle Base | 1 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle Base | 1 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.0884
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle Base | 1 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle Base | 1 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0.2801 | 0.36949 | 0.21114 | 133.3%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 1.691 | 1.7196 | -29.2339 | -94.44%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle Base | 1 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle Base | 1 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle Base | 1 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle Base | 1 | 6.5 | 23.5 | 7.7828 | 9.9355 | -17.3871 | -63.64%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle Base | 1 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle Base | 1 | 7.5 | 23.5 | 0.5461 | 0.72038 | 0.56203 | 354.9%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle Base | 1 | 1 | 29 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle Base | 1 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle Base | 1 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 9.0587 | 9.2122 | -31.3216 | -77.27%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle Base | 1 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle Base | 1 | 2.1095 | 28.8905 | 57.1129 | 61.2831 | 34.7271 | 130.8%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle Base | 1 | 1 | 29 | 0.23333 | 0.24138 | -0.27586 | -53.33%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 28.3499 | 28.8304 | 10.8114 | 60%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle Base | 1 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle Base | 1 | 1 | 29 | 37.1091 | 38.3887 | 26.266 | 216.7%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%

## Scenario_Detail
Sl.No. | Competitor Project | Agency | Internal Project Code Raw | Internal Codes Parsed | Month | Activity Code | Activity | Competitor Quantity | Month Days | Internal Codes Count | Internal Codes Found | Internal Quantity | Internal Unit | Internal Work Date Count | Internal Avg Idle Days Capped | Internal Productive Days Proxy | Internal Calendar Productivity | Internal Idle Adjusted Productivity | Same-Month Avg Tower Weight MT | Competitor Equivalent Output | Output Unit | Baseline Notes | Scenario | Idle Multiplier | Competitor Assumed Idle Days | Competitor Productive Days Proxy | Competitor Calendar Productivity | Competitor Idle Adjusted Productivity | Competitor vs Internal Difference | Competitor vs Internal Difference %
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0.19355 | 0.19355 | -0.29032 | -60%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle -20% | 0.8 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle -10% | 0.9 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle Base | 1 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle +10% | 1.1 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT |  | Idle +20% | 1.2 | 0 | 31 | 34.1834 | 34.1834 | -18.9908 | -35.71%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle -20% | 0.8 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle -10% | 0.9 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle Base | 1 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle +10% | 1.1 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM |  | Idle +20% | 1.2 | 0 | 31 | 0.17258 | 0.17258 | -0.19995 | -53.67%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle -20% | 0.8 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle -10% | 0.9 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle +10% | 1.1 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations |  | Idle +20% | 1.2 | 0 | 30 | 0.4 | 0.4 | -0.13333 | -25%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle -20% | 0.8 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle -10% | 0.9 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle Base | 1 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle +10% | 1.1 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT |  | Idle +20% | 1.2 | 0 | 30 | 34.1705 | 34.1705 | -32.0348 | -48.39%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle -20% | 0.8 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle -10% | 0.9 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle Base | 1 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle +10% | 1.1 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM |  | Idle +20% | 1.2 | 0 | 30 | 0.16 | 0.16 | -0.047833 | -23.02%
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.032258
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.12567
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.12567
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.12567
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.12567
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.12567
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.32258
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle Base | 1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle -20% | 0.8 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle -10% | 0.9 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle Base | 1 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle +10% | 1.1 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM |  | Idle +20% | 1.2 | 0 | 31 | 0.05 | 0.05 | -0.13452 | -72.9%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.7
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle Base | 1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle -20% | 0.8 | 2.4 | 27.6 | 0 | 0 | -0.11157 | -100%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle -10% | 0.9 | 2.7 | 27.3 | 0 | 0 | -0.11157 | -100%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle Base | 1 | 3 | 27 | 0 | 0 | -0.11157 | -100%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle +10% | 1.1 | 3.3 | 26.7 | 0 | 0 | -0.11157 | -100%
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM |  | Idle +20% | 1.2 | 3.6 | 26.4 | 0 | 0 | -0.11157 | -100%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0.93548 | 0.93548 | 0.51613 | 123.1%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle -20% | 0.8 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle -10% | 0.9 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle Base | 1 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle +10% | 1.1 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT |  | Idle +20% | 1.2 | 0 | 31 | 14.7417 | 14.7417 | 0 | 0%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle -20% | 0.8 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle -10% | 0.9 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle +10% | 1.1 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations |  | Idle +20% | 1.2 | 0 | 30 | 0.56667 | 0.56667 | 0.23333 | 70%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle -20% | 0.8 | 9.6 | 20.4 | 30.9888 | 45.5718 | 29.4318 | 182.4%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle -10% | 0.9 | 10.8 | 19.2 | 30.9888 | 48.42 | 32.28 | 200%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle Base | 1 | 12 | 18 | 30.9888 | 51.648 | 35.508 | 220%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle +10% | 1.1 | 13.2 | 16.8 | 30.9888 | 55.3371 | 39.1971 | 242.9%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT |  | Idle +20% | 1.2 | 14.4 | 15.6 | 30.9888 | 59.5938 | 43.4538 | 269.2%
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.35484
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0.6129 | 0.6129 | 0.45161 | 280%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle -20% | 0.8 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle -10% | 0.9 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle Base | 1 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle +10% | 1.1 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT |  | Idle +20% | 1.2 | 0 | 31 | 37.9504 | 37.9504 | 27.4813 | 262.5%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle -20% | 0.8 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle -10% | 0.9 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle +10% | 1.1 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations |  | Idle +20% | 1.2 | 0 | 30 | 0.66667 | 0.66667 | 0.46667 | 233.3%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle -20% | 0.8 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle -10% | 0.9 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle Base | 1 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle +10% | 1.1 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT |  | Idle +20% | 1.2 | 0 | 30 | 54.5205 | 54.5205 | 26.3809 | 93.75%
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.0884
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.0884
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.0884
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.0884
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.0884
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.25806
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle -20% | 0.8 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle -10% | 0.9 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle Base | 1 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle +10% | 1.1 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT |  | Idle +20% | 1.2 | 0 | 31 | 0 | 0 | -22.9567 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle -20% | 0.8 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle -10% | 0.9 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle +10% | 1.1 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT |  | Idle +20% | 1.2 | 0 | 30 | 0 | 0 | -22.613 | -100%
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.64516
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.66667
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.32258
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.53333
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.80645
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0.93333
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -20% | 0.8 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle -10% | 0.9 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle Base | 1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +10% | 1.1 |  |  | 0
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found. | Idle +20% | 1.2 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.032258
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle -20% | 0.8 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle -10% | 0.9 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle Base | 1 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle +10% | 1.1 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT |  | Idle +20% | 1.2 | 0 | 31 | 5.013 | 5.013 | -58.4853 | -92.11%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle -20% | 0.8 | 6 | 25 | 0.2801 | 0.34732 | 0.18897 | 119.3%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle -10% | 0.9 | 6.75 | 24.25 | 0.2801 | 0.35806 | 0.19971 | 126.1%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0.2801 | 0.36949 | 0.21114 | 133.3%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle +10% | 1.1 | 8.25 | 22.75 | 0.2801 | 0.38167 | 0.22332 | 141%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM |  | Idle +20% | 1.2 | 9 | 22 | 0.2801 | 0.39468 | 0.23633 | 149.2%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle -20% | 0.8 | 0.4 | 29.6 | 1.691 | 1.7138 | -29.2397 | -94.46%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle -10% | 0.9 | 0.45 | 29.55 | 1.691 | 1.7167 | -29.2368 | -94.45%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 1.691 | 1.7196 | -29.2339 | -94.44%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle +10% | 1.1 | 0.55 | 29.45 | 1.691 | 1.7226 | -29.2309 | -94.44%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT |  | Idle +20% | 1.2 | 0.6 | 29.4 | 1.691 | 1.7255 | -29.228 | -94.43%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle -20% | 0.8 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle -10% | 0.9 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle Base | 1 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle +10% | 1.1 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM |  | Idle +20% | 1.2 | 0 | 30 | 0.4014 | 0.4014 | -0.010336 | -2.51%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle Base | 1 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0 | 0 | -0.54839 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle -20% | 0.8 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle -10% | 0.9 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle Base | 1 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle +10% | 1.1 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT |  | Idle +20% | 1.2 | 0 | 31 | 3.3463 | 3.3463 | -31.7896 | -90.48%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -20% | 0.8 | 6 | 25 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -10% | 0.9 | 6.75 | 24.25 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +10% | 1.1 | 8.25 | 22.75 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +20% | 1.2 | 9 | 22 | 0 | 0 | -0.15835 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle -20% | 0.8 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle -10% | 0.9 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle +10% | 1.1 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations |  | Idle +20% | 1.2 | 0 | 30 | 0 | 0 | -0.46667 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle -20% | 0.8 | 5.2 | 24.8 | 7.7828 | 9.4147 | -17.9079 | -65.54%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle -10% | 0.9 | 5.85 | 24.15 | 7.7828 | 9.6681 | -17.6545 | -64.62%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle Base | 1 | 6.5 | 23.5 | 7.7828 | 9.9355 | -17.3871 | -63.64%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle +10% | 1.1 | 7.15 | 22.85 | 7.7828 | 10.2181 | -17.1045 | -62.6%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT |  | Idle +20% | 1.2 | 7.8 | 22.2 | 7.7828 | 10.5173 | -16.8053 | -61.51%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle -20% | 0.8 | 0 | 30 | 0 | 0 | -0.41174 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle -10% | 0.9 | 0 | 30 | 0 | 0 | -0.41174 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle +10% | 1.1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle +20% | 1.2 | 0 | 30 | 0 | 0 | -0.41174 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle -20% | 0.8 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle -10% | 0.9 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle Base | 1 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle +10% | 1.1 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511 | Idle +20% | 1.2 | 0 | 31 | 0 | 0 | -20.3941 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle -20% | 0.8 | 6 | 25 | 0.5461 | 0.67716 | 0.51881 | 327.6%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle -10% | 0.9 | 6.75 | 24.25 | 0.5461 | 0.6981 | 0.53975 | 340.9%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle Base | 1 | 7.5 | 23.5 | 0.5461 | 0.72038 | 0.56203 | 354.9%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle +10% | 1.1 | 8.25 | 22.75 | 0.5461 | 0.74413 | 0.58578 | 369.9%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511 | Idle +20% | 1.2 | 9 | 22 | 0.5461 | 0.7695 | 0.61115 | 385.9%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle -20% | 0.8 | 0.8 | 29.2 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle -10% | 0.9 | 0.9 | 29.1 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle Base | 1 | 1 | 29 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle +10% | 1.1 | 1.1 | 28.9 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511 | Idle +20% | 1.2 | 1.2 | 28.8 | 0 | 0 | -12.1228 | -100%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle -20% | 0.8 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle -10% | 0.9 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle Base | 1 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle +10% | 1.1 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511 | Idle +20% | 1.2 | 0 | 30 | 0.3378 | 0.3378 | -0.073936 | -17.96%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0.58065 | 0.58065 | 0.29032 | 100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle -20% | 0.8 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle -10% | 0.9 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle Base | 1 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle +10% | 1.1 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT |  | Idle +20% | 1.2 | 0 | 31 | 29.1485 | 29.1485 | -1.7146 | -5.556%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -20% | 0.8 | 6 | 25 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -10% | 0.9 | 6.75 | 24.25 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +10% | 1.1 | 8.25 | 22.75 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +20% | 1.2 | 9 | 22 | 0 | 0 | -0.15835 | -100%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle -20% | 0.8 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle -10% | 0.9 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle Base | 1 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle +10% | 1.1 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations |  | Idle +20% | 1.2 | 0 | 30 | 0.33333 | 0.33333 | 0 | 0%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle -20% | 0.8 | 0.4 | 29.6 | 9.0587 | 9.1811 | -31.3527 | -77.35%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle -10% | 0.9 | 0.45 | 29.55 | 9.0587 | 9.1966 | -31.3372 | -77.31%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 9.0587 | 9.2122 | -31.3216 | -77.27%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle +10% | 1.1 | 0.55 | 29.45 | 9.0587 | 9.2279 | -31.3059 | -77.23%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT |  | Idle +20% | 1.2 | 0.6 | 29.4 | 9.0587 | 9.2436 | -31.2903 | -77.2%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle -20% | 0.8 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle -10% | 0.9 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle Base | 1 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle +10% | 1.1 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM |  | Idle +20% | 1.2 | 0 | 30 | 0.16667 | 0.16667 | -0.24507 | -59.52%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle -20% | 0.8 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle -10% | 0.9 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle Base | 1 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle +10% | 1.1 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations |  | Idle +20% | 1.2 | 0 | 31 | 0.35484 | 0.35484 | -0.29032 | -45%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle -20% | 0.8 | 1.6876 | 29.3124 | 57.1129 | 60.401 | 33.845 | 127.4%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle -10% | 0.9 | 1.8985 | 29.1014 | 57.1129 | 60.8389 | 34.2829 | 129.1%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle Base | 1 | 2.1095 | 28.8905 | 57.1129 | 61.2831 | 34.7271 | 130.8%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle +10% | 1.1 | 2.3205 | 28.6795 | 57.1129 | 61.7339 | 35.1779 | 132.5%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT |  | Idle +20% | 1.2 | 2.5314 | 28.4686 | 57.1129 | 62.1913 | 35.6353 | 134.2%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -20% | 0.8 | 6 | 25 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle -10% | 0.9 | 6.75 | 24.25 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +10% | 1.1 | 8.25 | 22.75 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM |  | Idle +20% | 1.2 | 9 | 22 | 0 | 0 | -0.15835 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle -20% | 0.8 | 0.8 | 29.2 | 0.23333 | 0.23973 | -0.27752 | -53.65%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle -10% | 0.9 | 0.9 | 29.1 | 0.23333 | 0.24055 | -0.27669 | -53.49%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle Base | 1 | 1 | 29 | 0.23333 | 0.24138 | -0.27586 | -53.33%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle +10% | 1.1 | 1.1 | 28.9 | 0.23333 | 0.24221 | -0.27503 | -53.17%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations |  | Idle +20% | 1.2 | 1.2 | 28.8 | 0.23333 | 0.24306 | -0.27419 | -53.01%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle -20% | 0.8 | 0.4 | 29.6 | 28.3499 | 28.733 | 10.714 | 59.46%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle -10% | 0.9 | 0.45 | 29.55 | 28.3499 | 28.7816 | 10.7626 | 59.73%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle Base | 1 | 0.5 | 29.5 | 28.3499 | 28.8304 | 10.8114 | 60%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle +10% | 1.1 | 0.55 | 29.45 | 28.3499 | 28.8793 | 10.8603 | 60.27%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT |  | Idle +20% | 1.2 | 0.6 | 29.4 | 28.3499 | 28.9284 | 10.9095 | 60.54%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle -20% | 0.8 | 0 | 30 | 0 | 0 | -0.41174 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle -10% | 0.9 | 0 | 30 | 0 | 0 | -0.41174 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle +10% | 1.1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM |  | Idle +20% | 1.2 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 1
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle -20% | 0.8 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle -10% | 0.9 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle Base | 1 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle +10% | 1.1 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514 | Idle +20% | 1.2 | 0 | 31 | 69.3399 | 69.3399 | 48.9458 | 240%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle -20% | 0.8 | 6 | 25 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle -10% | 0.9 | 6.75 | 24.25 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle Base | 1 | 7.5 | 23.5 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle +10% | 1.1 | 8.25 | 22.75 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514 | Idle +20% | 1.2 | 9 | 22 | 0 | 0 | -0.15835 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle -20% | 0.8 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle -10% | 0.9 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle Base | 1 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle +10% | 1.1 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available. | Idle +20% | 1.2 |  |  | 0.46667
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle -20% | 0.8 | 0.8 | 29.2 | 37.1091 | 38.1258 | 26.003 | 214.5%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle -10% | 0.9 | 0.9 | 29.1 | 37.1091 | 38.2568 | 26.1341 | 215.6%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle Base | 1 | 1 | 29 | 37.1091 | 38.3887 | 26.266 | 216.7%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle +10% | 1.1 | 1.1 | 28.9 | 37.1091 | 38.5216 | 26.3988 | 217.8%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514 | Idle +20% | 1.2 | 1.2 | 28.8 | 37.1091 | 38.6553 | 26.5326 | 218.9%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle -20% | 0.8 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle -10% | 0.9 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle Base | 1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle +10% | 1.1 | 0 | 30 | 0 | 0 | -0.41174 | -100%
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514 | Idle +20% | 1.2 | 0 | 30 | 0 | 0 | -0.41174 | -100%

## Internal_Baseline
Sl.No. | Competitor Project | Agency | Internal Project Code Raw | Internal Codes Parsed | Month | Activity Code | Activity | Competitor Quantity | Month Days | Internal Codes Count | Internal Codes Found | Internal Quantity | Internal Unit | Internal Work Date Count | Internal Avg Idle Days Capped | Internal Productive Days Proxy | Internal Calendar Productivity | Internal Idle Adjusted Productivity | Same-Month Avg Tower Weight MT | Competitor Equivalent Output | Output Unit | Baseline Notes
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | Foundation | 6 | 31 | 1 | 1 | 15 | Foundations | 31 | 0 | 31 | 0.48387 | 0.48387 |  | 6 | Foundations
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | Erection | 18 | 31 | 1 | 1 | 1648.3982 | MT | 31 | 0 | 31 | 53.1741 | 53.1741 | 58.8714 | 1059.6846 | MT
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | Stringing | 5.35 | 31 | 1 | 1 | 11.5485 | KM | 31 | 0 | 31 | 0.37253 | 0.37253 |  | 5.35 | KM
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | Foundation | 12 | 30 | 1 | 1 | 16 | Foundations | 26 | 0 | 30 | 0.53333 | 0.53333 |  | 12 | Foundations
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 1986.1585 | MT | 30 | 0 | 30 | 66.2053 | 66.2053 | 64.0696 | 1025.114 | MT
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | Stringing | 4.8 | 30 | 1 | 1 | 6.235 | KM | 30 | 0 | 30 | 0.20783 | 0.20783 |  | 4.8 | KM
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | Foundation | 1 | 31 | 1 | 0 |  | Foundations | [6 empty] | 1 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | Erection | 27 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 0 |  | Foundations | [6 empty] | 0 | Foundations | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | Erection | 7 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA415 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | Stringing | 3.77 | 30 | 1 | 0 |  | KM | [6 empty] | 3.77 | KM | Missing internal code(s): TA415 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 1 | 3 | Foundations | 0 |  |  | 0.096774 |  |  | 10 | Foundations | No same-month internal work-date idle baseline available.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | Erection | 9 | 31 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | Stringing | 1.55 | 31 | 1 | 1 | 5.7202 | KM | 31 | 0 | 31 | 0.18452 | 0.18452 |  | 1.55 | KM
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | Foundation | 21 | 30 | 1 | 1 | 1 | Foundations | 0 |  |  | 0.033333 |  |  | 21 | Foundations | No same-month internal work-date idle baseline available.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | Erection | 20 | 30 | 1 | 1 | 0 | MT | 0 |  |  | 0 |  |  |  | MT | No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 3.0125 | KM | 27 | 3 | 27 | 0.10042 | 0.11157 |  | 0 | KM
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | Foundation | 29 | 31 | 1 | 1 | 13 | Foundations | 31 | 0 | 31 | 0.41935 | 0.41935 |  | 29 | Foundations
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 1 | 456.994 | MT | 31 | 0 | 31 | 14.7417 | 14.7417 | 41.5449 | 456.994 | MT
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available.
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | Foundation | 17 | 30 | 1 | 1 | 10 | Foundations | 25 | 0 | 30 | 0.33333 | 0.33333 |  | 17 | Foundations
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | Erection | 16 | 30 | 1 | 1 | 290.52 | MT | 18 | 12 | 18 | 9.684 | 16.14 | 58.104 | 929.664 | MT
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | Foundation | 11 | 31 | 1 | 0 |  | Foundations | [6 empty] | 11 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | Foundation | 3 | 30 | 1 | 0 |  | Foundations | [6 empty] | 3 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | Foundation | 19 | 31 | 1 | 1 | 5 | Foundations | 31 | 0 | 31 | 0.16129 | 0.16129 |  | 19 | Foundations
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | Erection | 29 | 31 | 1 | 1 | 324.541 | MT | 31 | 0 | 31 | 10.4691 | 10.4691 | 40.5676 | 1176.4611 | MT
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available.
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 1 | 6 | Foundations | 30 | 0 | 30 | 0.2 | 0.2 |  | 20 | Foundations
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | Erection | 31 | 30 | 1 | 1 | 844.1877 | MT | 30 | 0 | 30 | 28.1396 | 28.1396 | 52.7617 | 1635.6137 | MT
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | Stringing | 2.652 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 2.652 | KM | No same-month internal work-date idle baseline available.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | Foundation | 8 | 31 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 8 | Foundations | No same-month internal work-date idle baseline available.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 1 | 711.6587 | MT | 31 | 0 | 31 | 22.9567 | 22.9567 | 24.54 | 0 | MT
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | Foundation | 0 | 30 | 1 | 1 | 0 | Foundations | 0 |  |  | 0 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 1 | 678.3911 | MT | 30 | 0 | 30 | 22.613 | 22.613 | 26.092 | 0 | MT
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 1 | 0 | KM | 0 |  |  | 0 |  |  | 0 | KM | No same-month internal work-date idle baseline available.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | Foundation | 20 | 31 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | Erection | 11 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | Foundation | 20 | 30 | 1 | 0 |  | Foundations | [6 empty] | 20 | Foundations | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | Erection | 18 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA603 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA603 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | Foundation | 10 | 31 | 1 | 0 |  | Foundations | [6 empty] | 10 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | Foundation | 16 | 30 | 1 | 0 |  | Foundations | [6 empty] | 16 | Foundations | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | Erection | 2 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA604 ¦ No same-month internal tower weight available; competitor equivalent MT not calculated. ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA604 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | Foundation | 25 | 31 | 1 | 0 |  | Foundations | [6 empty] | 25 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | Erection | 0 | 31 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | Stringing | 0 | 31 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | Foundation | 28 | 30 | 1 | 0 |  | Foundations | [6 empty] | 28 | Foundations | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | Erection | 0 | 30 | 1 | 0 |  | MT | [7 empty] | MT | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | Stringing | 0 | 30 | 1 | 0 |  | KM | [6 empty] | 0 | KM | Missing internal code(s): TA605 ¦ No same-month internal work-date idle baseline available. ¦ No internal comparator data found.
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | Foundation | 1 | 31 | 2 | 2 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 1 | Foundations | No same-month internal work-date idle baseline available.
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | Erection | 3 | 31 | 2 | 2 | 1968.4489 | MT | 62 | 0 | 31 | 63.4984 | 63.4984 | 51.8013 | 155.4039 | MT
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | Stringing | 8.683 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 8.683 | KM
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 10 | Foundations | 0 |  |  | 0.33333 |  |  | 0 | Foundations | No same-month internal work-date idle baseline available.
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | Erection | 1 | 30 | 2 | 2 | 913.1282 | MT | 59 | 0.5 | 29.5 | 30.4376 | 30.9535 | 50.7293 | 50.7293 | MT
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | Stringing | 12.042 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 12.042 | KM
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 2 | 17 | Foundations | 31 | 0 | 31 | 0.54839 | 0.54839 |  | 0 | Foundations
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | Erection | 2 | 31 | 2 | 2 | 1089.2105 | MT | 62 | 0 | 31 | 35.1358 | 35.1358 | 51.8672 | 103.7343 | MT
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 2 | 14 | Foundations | 25 | 0 | 30 | 0.46667 | 0.46667 |  | 0 | Foundations
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | Erection | 4 | 30 | 2 | 2 | 642.08 | MT | 47 | 6.5 | 23.5 | 21.4027 | 27.3226 | 58.3709 | 233.4836 | MT
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | Foundation | 0 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | Erection | 0 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 0 | MT | Missing internal code(s): TA511
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | Stringing | 16.929 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 16.929 | KM | Missing internal code(s): TA511
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | Foundation | 0 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 0 | Foundations | Missing internal code(s): TA511 ¦ No same-month internal work-date idle baseline available.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | Erection | 0 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 0 | MT | Missing internal code(s): TA511
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | Stringing | 10.134 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 10.134 | KM | Missing internal code(s): TA511
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | Foundation | 18 | 31 | 2 | 2 | 9 | Foundations | 31 | 0 | 31 | 0.29032 | 0.29032 |  | 18 | Foundations
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | Erection | 17 | 31 | 2 | 2 | 956.7575 | MT | 62 | 0 | 31 | 30.8631 | 30.8631 | 53.1532 | 903.6043 | MT
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | Foundation | 10 | 30 | 2 | 2 | 10 | Foundations | 30 | 0 | 30 | 0.33333 | 0.33333 |  | 10 | Foundations
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | Erection | 5 | 30 | 2 | 2 | 1195.7477 | MT | 59 | 0.5 | 29.5 | 39.8583 | 40.5338 | 54.3522 | 271.7609 | MT
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | Stringing | 5 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 5 | KM
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | Foundation | 11 | 31 | 2 | 2 | 20 | Foundations | 31 | 0 | 31 | 0.64516 | 0.64516 |  | 11 | Foundations
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | Erection | 30 | 31 | 2 | 2 | 767.2165 | MT | 53 | 2.1095 | 28.8905 | 24.7489 | 26.556 | 59.0167 | 1770.4996 | MT
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 2 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | Foundation | 7 | 30 | 2 | 2 | 15 | Foundations | 29 | 1 | 29 | 0.5 | 0.51724 |  | 7 | Foundations
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | Erection | 16 | 30 | 2 | 2 | 531.56 | MT | 51 | 0.5 | 29.5 | 17.7187 | 18.019 | 53.156 | 850.496 | MT
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 2 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | Foundation | 31 | 31 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.12903 |  |  | 31 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | Erection | 34 | 31 | 2 | 1 | 632.2165 | MT | 31 | 0 | 31 | 20.3941 | 20.3941 | 63.2217 | 2149.5361 | MT | Missing internal code(s): TA514
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | Stringing | 0 | 31 | 2 | 1 | 3.7213 | KM | 18 | 7.5 | 23.5 | 0.12004 | 0.15835 |  | 0 | KM | Missing internal code(s): TA514
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | Foundation | 14 | 30 | 2 | 1 | 4 | Foundations | 0 |  |  | 0.13333 |  |  | 14 | Foundations | Missing internal code(s): TA514 ¦ No same-month internal work-date idle baseline available.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | Erection | 19 | 30 | 2 | 1 | 351.56 | MT | 29 | 1 | 29 | 11.7187 | 12.1228 | 58.5933 | 1113.2733 | MT | Missing internal code(s): TA514
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | Stringing | 0 | 30 | 2 | 1 | 12.3521 | KM | 30 | 0 | 30 | 0.41174 | 0.41174 |  | 0 | KM | Missing internal code(s): TA514

## Internal_Code_Detail
Sl.No. | Competitor Project | Agency | Internal Project Code Raw | Internal Codes Parsed | Month | Activity Code | Activity | Competitor Quantity | Internal Code | Internal Project Exists | Internal Quantity | Internal Unit | Internal Tower Count | Avg Tower Weight MT | Idle Days Capped | Idle Window Count | Work Date Count | Data Quality Note | Foundation Source Used | Foundation Detail Count | Foundation Snapshot Delta | Foundation Valid Duration Count
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | FDN | FDN | 6 | TA414 | TRUE | 15 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 15 |  | 15
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | ERE | ERE | 18 | TA414 | TRUE | 1648.3982 | MT | 28 | 58.8714 | 0 | 0 | 31
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-05 | STR | STR | 5.35 | TA414 | TRUE | 11.5485 | KM |  |  | 0 | 0 | 31
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | FDN | FDN | 12 | TA414 | TRUE | 16 | Foundations |  |  | 0 | 0 | 26 |  | detail rows | 16 |  | 16
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | ERE | ERE | 16 | TA414 | TRUE | 1986.1585 | MT | 31 | 64.0696 | 0 | 0 | 30
1 | 765 kV D/C Vataman-Navsari TL (TL03) | KPIL | TA414 | TA414 | 2026-06 | STR | STR | 4.8 | TA414 | TRUE | 6.235 | KM |  |  | 0 | 0 | 30
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | FDN | FDN | 1 | TA415 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | ERE | ERE | 27 | TA415 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-05 | STR | STR | 0 | TA415 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | FDN | FDN | 0 | TA415 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | ERE | ERE | 7 | TA415 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
2 | 765 kV D/C Halvad-Vataman TL (TL02) | KPIL | TA415 | TA415 | 2026-06 | STR | STR | 3.77 | TA415 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | FDN | FDN | 10 | TA416 | TRUE | 3 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 3 |  | 0
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | ERE | ERE | 9 | TA416 | TRUE | 0 | MT | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-05 | STR | STR | 1.55 | TA416 | TRUE | 5.7202 | KM |  |  | 0 | 0 | 31
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | FDN | FDN | 21 | TA416 | TRUE | 1 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 1 |  | 0
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | ERE | ERE | 20 | TA416 | TRUE | 0 | MT | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
3 | 765 kV D/C Halvad-Vataman TL (TL01) | BAJEL | TA416 | TA416 | 2026-06 | STR | STR | 0 | TA416 | TRUE | 3.0125 | KM |  |  | 3 | 1 | 27
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | FDN | FDN | 29 | TA510 | TRUE | 13 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 13 |  | 13
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | ERE | ERE | 11 | TA510 | TRUE | 456.994 | MT | 11 | 41.5449 | 0 | 0 | 31
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-05 | STR | STR | 0 | TA510 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | FDN | FDN | 17 | TA510 | TRUE | 10 | Foundations |  |  | 0 | 0 | 25 |  | detail rows | 10 |  | 10
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | ERE | ERE | 16 | TA510 | TRUE | 290.52 | MT | 5 | 58.104 | 12 | 1 | 18
4 | 765 kV D/C Vadodara-South Olpad TL (TL01) | TLL | TA510 | TA510 | 2026-06 | STR | STR | 0 | TA510 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | FDN | FDN | 11 | TA511 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | ERE | ERE | 0 | TA511 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-05 | STR | STR | 0 | TA511 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | FDN | FDN | 3 | TA511 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | ERE | ERE | 0 | TA511 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
5 | 765 kV D/C Vadodara-South Olpad TL (TL02) | TLL | TA511 | TA511 | 2026-06 | STR | STR | 0 | TA511 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | FDN | FDN | 19 | TA512 | TRUE | 5 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 5 |  | 5
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | ERE | ERE | 29 | TA512 | TRUE | 324.541 | MT | 8 | 40.5676 | 0 | 0 | 31
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-05 | STR | STR | 0 | TA512 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | FDN | FDN | 20 | TA512 | TRUE | 6 | Foundations |  |  | 0 | 0 | 30 |  | detail rows | 6 |  | 6
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | ERE | ERE | 31 | TA512 | TRUE | 844.1877 | MT | 16 | 52.7617 | 0 | 0 | 30
6 | 765 kV D/C Ahmedabad-South Olpad TL (TL03) | KPIL | TA512 | TA512 | 2026-06 | STR | STR | 2.652 | TA512 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | FDN | FDN | 8 | TA602 | TRUE | 0 | Foundations | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | ERE | ERE | 0 | TA602 | TRUE | 711.6587 | MT | 29 | 24.54 | 0 | 0 | 31
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-05 | STR | STR | 0 | TA602 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | FDN | FDN | 0 | TA602 | TRUE | 0 | Foundations | [6 empty] | detail rows | 0 |  | 0
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | ERE | ERE | 0 | TA602 | TRUE | 678.3911 | MT | 26 | 26.092 | 0 | 0 | 30
7 | 800 kV HVDC KPS2-Nagpur TL - TL01 | JSL | TA602 | TA602 | 2026-06 | STR | STR | 0 | TA602 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | FDN | FDN | 20 | TA603 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | ERE | ERE | 11 | TA603 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-05 | STR | STR | 0 | TA603 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | FDN | FDN | 20 | TA603 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | ERE | ERE | 18 | TA603 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
8 | 801 kV HVDC KPS2-Nagpur TL - TL04 | L&T | TA603 | TA603 | 2026-06 | STR | STR | 0 | TA603 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | FDN | FDN | 10 | TA604 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | ERE | ERE | 0 | TA604 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-05 | STR | STR | 0 | TA604 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | FDN | FDN | 16 | TA604 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | ERE | ERE | 2 | TA604 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
9 | 802 kV HVDC KPS2-Nagpur TL - TL05 | KPIL | TA604 | TA604 | 2026-06 | STR | STR | 0 | TA604 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | FDN | FDN | 25 | TA605 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | ERE | ERE | 0 | TA605 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-05 | STR | STR | 0 | TA605 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | FDN | FDN | 28 | TA605 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | ERE | ERE | 0 | TA605 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
10 | 803 kV HVDC KPS2-Nagpur TL - TL07 | KPIL | TA605 | TA605 | 2026-06 | STR | STR | 0 | TA605 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | FDN | 1 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | FDN | FDN | 1 | TA509 | TRUE | 0 | Foundations | [6 empty] | detail rows | 0 |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | ERE | 3 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | ERE | ERE | 3 | TA509 | TRUE | 1336.2324 | MT | 28 | 47.7226 | 0 | 0 | 31
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | STR | 8.683 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-05 | STR | STR | 8.683 | TA509 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | FDN | 0 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | FDN | FDN | 0 | TA509 | TRUE | 6 | Foundations | [5 empty] | Foundation progress came from snapshot cumulative delta; exact start/completion idle unavailable. | snapshot cumulative delta | 0 | 6 | 0
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | ERE | 1 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | ERE | ERE | 1 | TA509 | TRUE | 561.5682 | MT | 12 | 46.7973 | 0 | 0 | 30
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | STR | 12.042 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
11 | 765 kV D/C Mandsaur-Kurawar TL (TL-02) | KPIL | TA505/TA509 | TA505/TA509 | 2026-06 | STR | STR | 12.042 | TA509 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | FDN | 0 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | FDN | FDN | 0 | TA510 | TRUE | 13 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 13 |  | 13
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | ERE | 2 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | ERE | ERE | 2 | TA510 | TRUE | 456.994 | MT | 11 | 41.5449 | 0 | 0 | 31
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | STR | 0 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-05 | STR | STR | 0 | TA510 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | FDN | 0 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | FDN | FDN | 0 | TA510 | TRUE | 10 | Foundations |  |  | 0 | 0 | 25 |  | detail rows | 10 |  | 10
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | ERE | 4 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | ERE | ERE | 4 | TA510 | TRUE | 290.52 | MT | 5 | 58.104 | 12 | 1 | 18
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | STR | 0 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
12 | LILO of 765 kV S/C Indore-Bhopal TL | KPIL | TA505/TA510 | TA505/TA510 | 2026-06 | STR | STR | 0 | TA510 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | FDN | 0 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | FDN | FDN | 0 | TA511 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | ERE | 0 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | ERE | ERE | 0 | TA511 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | STR | 16.929 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-05 | STR | STR | 16.929 | TA511 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | FDN | 0 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | FDN | FDN | 0 | TA511 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | ERE | 0 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | ERE | ERE | 0 | TA511 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | STR | 10.134 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
13 | 765 kV D/C Mandsaur PS-Indore TL (TL-01) | L&T | TA505/TA511 | TA505/TA511 | 2026-06 | STR | STR | 10.134 | TA511 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | FDN | 18 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | FDN | FDN | 18 | TA512 | TRUE | 5 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 5 |  | 5
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | ERE | 17 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | ERE | ERE | 17 | TA512 | TRUE | 324.541 | MT | 8 | 40.5676 | 0 | 0 | 31
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | STR | 0 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-05 | STR | STR | 0 | TA512 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | FDN | 10 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | FDN | FDN | 10 | TA512 | TRUE | 6 | Foundations |  |  | 0 | 0 | 30 |  | detail rows | 6 |  | 6
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | ERE | 5 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | ERE | ERE | 5 | TA512 | TRUE | 844.1877 | MT | 16 | 52.7617 | 0 | 0 | 30
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | STR | 5 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
14 | 765 kV D/C Mandsaur PS-Indore TL (TL-02) | TLL | TA505/TA512 | TA505/TA512 | 2026-06 | STR | STR | 5 | TA512 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | FDN | 11 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | FDN | FDN | 11 | TA513 | TRUE | 16 | Foundations |  |  | 0 | 0 | 31 |  | detail rows | 16 |  | 16
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | ERE | 30 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | ERE | ERE | 30 | TA513 | TRUE | 135 | MT | 3 | 45 | 4.219 | 1 | 22
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | STR | 0 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-05 | STR | STR | 0 | TA513 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | FDN | 7 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | FDN | FDN | 7 | TA513 | TRUE | 11 | Foundations |  |  | 1 | 1 | 29 |  | detail rows | 11 |  | 11
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | ERE | 16 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | ERE | ERE | 16 | TA513 | TRUE | 180 | MT | 4 | 45 | 0 | 0 | 22
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | STR | 0 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
15 | 765 kV D/C Mandsaur-Khandwa TL (TL-04) | SKIPPER | TA505/TA513 | TA505/TA513 | 2026-06 | STR | STR | 0 | TA513 | TRUE | 0 | KM | [5 empty] | Project exists internally, but this activity has no completed/progress rows in this month.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | FDN | 31 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | FDN | FDN | 31 | TA514 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | ERE | 34 | TA505 | TRUE | 632.2165 | MT | 10 | 63.2217 | 0 | 0 | 31
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | ERE | ERE | 34 | TA514 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | STR | 0 | TA505 | TRUE | 3.7213 | KM |  |  | 7.5 | 1 | 18
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-05 | STR | STR | 0 | TA514 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | FDN | 14 | TA505 | TRUE | 4 | Foundations | [5 empty] | Some foundation rows have missing start dates; idle only uses valid start/completion rows. | detail rows | 4 |  | 0
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | FDN | FDN | 14 | TA514 | FALSE |  | Foundations | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | ERE | 19 | TA505 | TRUE | 351.56 | MT | 6 | 58.5933 | 1 | 1 | 29
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | ERE | ERE | 19 | TA514 | FALSE |  | MT | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | STR | 0 | TA505 | TRUE | 12.3521 | KM |  |  | 0 | 0 | 30
16 | 765 kV D/C Mandsaur-Khandwa TL (TL-05) | SKIPPER | TA505/TA514 | TA505/TA514 | 2026-06 | STR | STR | 0 | TA514 | FALSE |  | KM | [5 empty] | Internal project code was not found in extracted foundation/erection/stringing/project-details data.

## Agency_Summary
Agency | Activity | Comparable Rows | Avg Competitor vs Internal % | Median Competitor vs Internal % | Rows Competitor Above Internal | Rows Competitor Below Internal
JSL | Erection | 2 | -100% | -100% | 0 | 2
KPIL | Erection | 8 | -8.564% | -56.01% | 2 | 6
L&T | Erection | 2 | -100% | -100% | 0 | 2
SKIPPER | Erection | 4 | 161.9% | 173.7% | 4 | 0
TLL | Erection | 4 | 34.29% | -2.778% | 1 | 2
KPIL | Foundation | 6 | 38.06% | -42.5% | 2 | 4
SKIPPER | Foundation | 2 | -49.17% | -49.17% | 0 | 2
TLL | Foundation | 4 | 73.27% | 85% | 3 | 0
BAJEL | Stringing | 2 | -86.45% | -86.45% | 0 | 2
KPIL | Stringing | 6 | -24.31% | -38.34% | 1 | 5
L&T | Stringing | 2 | 168.5% | 168.5% | 1 | 1
SKIPPER | Stringing | 4 | -100% | -100% | 0 | 4
TLL | Stringing | 2 | -79.76% | -79.76% | 0 | 2