## Summary
stage | avg_productivity_km_month | total_km | active_days | spans | gangs | projects | start_date | end_date
Overall | 2.2162 | 579.4662 | 747 | 394 | 105 | 8 | 2024-01-08 | 2026-01-23
P/O | 4.7991 | 604.6911 | 749 | 403 | 109 | 9 | 2024-01-08 | 2026-01-25
F/S | 6.3393 | 576.6692 | 747 | 393 | 104 | 8 | 2024-01-08 | 2026-01-23

## Gang_Productivity
stage | gang_name | avg_productivity_km_month | total_km | active_days | spans | projects
Overall | AE Solution | 1.102 | 0.4775 | 13 | 2 | 1
Overall | AE Solution(Company) | 0.9447 | 0.4408 | 14 | 1 | 1
Overall | ANARUL ISLAM | 4.3342 | 27.5944 | 166 | 16 | 1
Overall | Abdul Adut | 2.7562 | 0.735 | 8 | 1 | 1
Overall | Alam Construction | 2.6131 | 17.9435 | 138 | 23 | 1
Overall | Alam Construction / Enamul / Giyash / Alongir | 3.405 | 0.227 | 2 | 1 | 1
Overall | Alamgir | 0.5743 | 0.268 | 14 | 1 | 1
Overall | Alongir | 3.1758 | 2.3289 | 22 | 2 | 1
Overall | Amir Sheikh | 6.1432 | 6.348 | 31 | 2 | 1
Overall | Babloo Haque/Anarul-2 | 0.2761 | 0.2393 | 26 | 1 | 1
Overall | Bhola | 1.2 | 0.16 | 4 | 1 | 1
Overall | Bhola Prasad | 0.5222 | 1.323 | 51 | 3 | 1
Overall | Bhola Prasad & Kamruddin | 7.212 | 1.202 | 5 | 1 | 1
Overall | Deepak Sarkar | 2.4228 | 9.3682 | 98 | 10 | 1
Overall | Deepak Sarkar + Manik Sarkar | 5.2476 | 2.9737 | 17 | 2 | 1
Overall | Devi Power | 3.123 | 16.3439 | 99 | 7 | 2
Overall | Dharmendra 1 | 1.0714 | 1.4286 | 40 | 5 | 1
Overall | Dharmendra 2 | 1.5014 | 1.9518 | 39 | 7 | 1
Overall | Dharmendra Electrical | 1.29 | 2.064 | 48 | 8 | 1
Overall | Dhervendra Electricals | 0.3137 | 4.6736 | 429 | 14 | 1
Overall | Enamul + Alam Constrution | 6.7014 | 0.2234 | 1 | 1 | 1
Overall | Enamul Haque | 2.7762 | 18.3228 | 158 | 22 | 1
Overall | GPJ Const. | 3.8006 | 29.391 | 174 | 11 | 1
Overall | Giyash | 0.7582 | 0.278 | 11 | 1 | 1
Overall | Giyash / Alongir | 4.19 | 0.419 | 3 | 1 | 1
Overall | Gokul Sarkar | 1.1406 | 4.4864 | 80 | 7 | 1
Overall | Gopal Associate | 3.322 | 15.835 | 114 | 5 | 1
Overall | Gopal Associate, Hotline | 0.9684 | 0.6456 | 20 | 3 | 1
Overall | Gopal Ji | 0.5377 | 0.233 | 13 | 1 | 1
Overall | Indrajeet | 1.3283 | 17.179 | 171 | 12 | 1
Overall | Indrajeet/Mohan/Amir Sheikh | 0.32 | 0.544 | 51 | 1 | 1
Overall | Indrajeet/Rahim | 1.3922 | 2.97 | 46 | 2 | 1
Overall | J PG CON | 8.9081 | 11.8774 | 40 | 4 | 1
Overall | JPJ Construction/MC Power | 1.1206 | 5.416 | 145 | 2 | 1
Overall | Jahangir Alam | 0.8153 | 1.848 | 35 | 2 | 1
Overall | Jahangir(Company) | 2.3864 | 2.2273 | 28 | 1 | 1
Overall | Kamaruddin | 5.8429 | 6.622 | 29 | 3 | 1
Overall | Kamruddin | 2.0807 | 4.647 | 67 | 3 | 1
Overall | Kamruddin & Deepak | 12.3225 | 4.929 | 12 | 2 | 1
Overall | Kamruddin & Deepak Sarkar | 0.6416 | 2.053 | 96 | 1 | 1
Overall | Kamruddin & Maidul rahman | 1.9532 | 1.237 | 19 | 1 | 1
Overall | Kamruddin Deepak Sarkar | 1.533 | 0.511 | 10 | 1 | 1
Overall | Kamruddinn | 4.8925 | 1.957 | 12 | 1 | 1
Overall | Kamruddinn / Bhola prasad | 1.707 | 0.569 | 10 | 1 | 1
Overall | Kddus Ali | 5.2444 | 2.797 | 16 | 1 | 1
Overall | Krishna Const. | 1.2327 | 17.299 | 349 | 7 | 1
Overall | Krishna Const. -2 | 5.6012 | 7.655 | 41 | 2 | 1
Overall | Krishna-1 | 3.5571 | 0.83 | 7 | 1 | 1
Overall | Kuddus ali | 5.4182 | 22.937 | 88 | 5 | 1
Overall | Kudus Ali | 0.1465 | 1.8948 | 371 | 3 | 1
Overall | Kudus Ali 2 | 3.8468 | 0.2564 | 2 | 1 | 1
Overall | Kunal Kumar | 1.0157 | 0.237 | 7 | 1 | 1
Overall | M R Constructions | 3.1276 | 42.8486 | 268 | 19 | 1
Overall | MC Const. | 6.0487 | 9.073 | 36 | 3 | 1
Overall | MC Power | 7.2525 | 10.8788 | 43 | 6 | 1
Overall | MR Power | 1.912 | 16.3792 | 174 | 6 | 2
Overall | Manik Sarkar | 2.2478 | 5.6195 | 56 | 4 | 1
Overall | Md Anwar | 1.31 | 1.441 | 33 | 2 | 1
Overall | Modia India | 1.3974 | 0.885 | 19 | 2 | 1
Overall | Modina India 2 | 2.4518 | 0.899 | 11 | 2 | 1
Overall | Monera | 1.2842 | 4.409 | 63 | 6 | 1
Overall | Muni bibi / Enamul / Alam / Rafikul | 4.05 | 0.27 | 2 | 1 | 1
Overall | Munni Bibi 1 | 1.2012 | 0.961 | 12 | 2 | 1
Overall | Munni Bibi 2 | 1.09 | 0.654 | 18 | 2 | 1
Overall | Muslehuddin | 3.1541 | 18.2935 | 154 | 18 | 1
Overall | Muslehuddin + Enamul | 1.7995 | 2.3994 | 40 | 1 | 1
Overall | Muslehuddin and Giyash | 3.3488 | 1.786 | 16 | 2 | 1
Overall | Muslehuddinn + GPJ | 2.0689 | 0.8276 | 12 | 1 | 1
Overall | Nasir | 10.9879 | 6.959 | 19 | 2 | 1
Overall | Nasiruddin | 12.3045 | 27.48 | 67 | 7 | 1
Overall | Nasruddin | 0.7946 | 12.581 | 380 | 5 | 1
Overall | Rafikul Alam | 2.9325 | 1.955 | 20 | 2 | 1
Overall | Rafikul Alam + Alam Const. + Enamul | 20.2089 | 2.0209 | 3 | 1 | 1
Overall | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 3.735 | 0.249 | 2 | 1 | 1
Overall | Rafikul Alam Construction | 1.3841 | 1.338 | 29 | 1 | 1
Overall | Rafikul Alam constr. | 2.4092 | 1.044 | 13 | 1 | 1
Overall | Rafikul Alam construction | 3.029 | 2.8271 | 28 | 1 | 1
Overall | Rafikul Alam construction + Enamul | 4.8941 | 5.2204 | 21 | 2 | 1
Overall | RafikulAlam Construction | 2.1412 | 2.9976 | 42 | 1 | 1
Overall | Rahim Khan | 3.2902 | 24.3474 | 142 | 10 | 2
Overall | Ramavat Electricals | 1.1809 | 0.433 | 11 | 1 | 1
Overall | Ramavat Electricals -2 | 0.6575 | 0.263 | 12 | 1 | 1
Overall | Ramavat Electricals 1 | 1.38 | 0.69 | 15 | 2 | 1
Overall | Ramavat Electricals 1& 2 | 0.822 | 0.274 | 10 | 1 | 1
Overall | Ramavat Electricals 1&2 | 0.0179 | 0.221 | 371 | 1 | 1
Overall | Ramavat Electricals 2 | 0.7592 | 0.658 | 26 | 2 | 1
Overall | Ramawat-Hot line | 0.3312 | 0.265 | 24 | 1 | 1
Overall | Ramsingh Yadav | 1.2945 | 1.726 | 40 | 7 | 1
Overall | Ramsingh Yadav 1&2 | 3.47 | 0.347 | 3 | 1 | 1
Overall | Ramsingh Yadav 2 | 1.7318 | 0.635 | 11 | 3 | 1
Overall | Rejaul | 6.088 | 3.4498 | 17 | 2 | 1
Overall | Rejaul + Rafikul | 6.7917 | 2.0375 | 9 | 1 | 1
Overall | Rejaul + enamul | 2.9541 | 1.2801 | 13 | 1 | 1
Overall | Ruhul Amin / Alam Constr. | 1.1045 | 0.405 | 11 | 1 | 1
Overall | S K INFRA | 3.2874 | 34.0798 | 192 | 10 | 1
Overall | SK Infratech | 7.2188 | 16.3627 | 49 | 4 | 1
Overall | SK Zenarul | 1.072 | 2.4298 | 43 | 4 | 1
Overall | SUFIYAN | 2.1106 | 12.945 | 100 | 6 | 1
Overall | Sanjay Singh | 1.158 | 1.351 | 35 | 6 | 1
Overall | Singhvahini | 2.517 | 1.678 | 20 | 4 | 1
Overall | Teklal Saw | 4.1208 | 3.434 | 25 | 3 | 1
Overall | Teklal Saw / Muslehuddin | 3.3771 | 0.788 | 7 | 1 | 1
Overall | Telegance Power | 0.642 | 0.214 | 10 | 1 | 1
Overall | Yakub Ali + Enamul | 0.345 | 0.437 | 38 | 1 | 1
P/O | AE Solution | 1.4326 | 0.4775 | 10 | 2 | 1
P/O | AE Solution(Company) | 1.8893 | 0.4408 | 7 | 1 | 1
P/O | ANARUL ISLAM | 11.4432 | 31.2781 | 82 | 17 | 1
P/O | Abdul Adut | 7.35 | 0.735 | 3 | 1 | 1
P/O | Alam Construction | 5.2263 | 17.9435 | 76 | 23 | 1
P/O | Alam Construction / Enamul / Giyash / Alongir | 3.405 | 0.227 | 2 | 1 | 1
P/O | Alamgir | 2.01 | 0.268 | 4 | 1 | 1
P/O | Alimuddin | 0 | 0 | 6 | 1 | 1
P/O | Alongir | 4.3668 | 2.3289 | 16 | 2 | 1
P/O | Amir Sheikh | 11.9025 | 6.348 | 16 | 2 | 1
P/O | Babloo Haque/Anarul-2 | 0.2991 | 0.2393 | 24 | 1 | 1
P/O | Bhola | 1.2 | 0.16 | 4 | 1 | 1
P/O | Bhola Prasad | 3.0531 | 1.323 | 13 | 3 | 1
P/O | Bhola Prasad & Kamruddin | 9.015 | 1.202 | 4 | 1 | 1
P/O | Deepak | 16.5 | 4.95 | 9 | 1 | 1
P/O | Deepak Sarkar | 4.3913 | 9.3682 | 54 | 10 | 1
P/O | Deepak Sarkar + Manik Sarkar | 11.1512 | 2.9737 | 8 | 2 | 1
P/O | Devi Power | 10.9493 | 17.5189 | 40 | 8 | 2
P/O | Dharmendra 1 | 1.1905 | 1.4286 | 36 | 5 | 1
P/O | Dharmendra 2 | 1.7744 | 1.9518 | 33 | 7 | 1
P/O | Dharmendra Electrical | 2.9486 | 2.064 | 21 | 8 | 1
P/O | Dhervendra Electricals | 0.3201 | 4.6736 | 427 | 14 | 1
P/O | Enamul + Alam Constrution | 6.7014 | 0.2234 | 1 | 1 | 1
P/O | Enamul Haque | 6.5439 | 18.3228 | 81 | 22 | 1
P/O | GPJ Const. | 12.4187 | 29.391 | 71 | 11 | 1
P/O | Giyash | 1.1914 | 0.278 | 7 | 1 | 1
P/O | Giyash / Alongir | 4.19 | 0.419 | 3 | 1 | 1
P/O | Gokul Sarkar | 6.7296 | 4.4864 | 20 | 7 | 1
P/O | Gopal Associate | 10.3272 | 15.835 | 46 | 5 | 1
P/O | Gopal Associate, Hotline | 0.9684 | 0.6456 | 20 | 3 | 1
P/O | Gopal Ji | 0.5377 | 0.233 | 13 | 1 | 1
P/O | Indrajeet | 9.203 | 17.179 | 45 | 12 | 1
P/O | Indrajeet/Mohan/Amir Sheikh | 2.04 | 0.544 | 8 | 1 | 1
P/O | Indrajeet/Rahim | 6.3643 | 2.97 | 14 | 2 | 1
P/O | J PG CON | 14.2529 | 11.8774 | 25 | 4 | 1
P/O | JPJ Construction/MC Power | 6.0178 | 5.416 | 27 | 2 | 1
P/O | Jahangir Alam | 2.31 | 1.848 | 12 | 2 | 1
P/O | Jahangir(Company) | 3.1818 | 2.2273 | 21 | 1 | 1
P/O | Kamaruddin | 13.244 | 6.622 | 15 | 3 | 1
P/O | Kamruddin | 6.3368 | 4.647 | 22 | 3 | 1
P/O | Kamruddin & Deepak | 24.645 | 4.929 | 6 | 2 | 1
P/O | Kamruddin & Deepak Sarkar | 15.3975 | 2.053 | 4 | 1 | 1
P/O | Kamruddin & Maidul rahman | 9.2775 | 1.237 | 4 | 1 | 1
P/O | Kamruddin Deepak Sarkar | 5.11 | 0.511 | 3 | 1 | 1
P/O | Kamruddinn | 11.742 | 1.957 | 5 | 1 | 1
P/O | Kamruddinn / Bhola prasad | 8.535 | 0.569 | 2 | 1 | 1
P/O | Kddus Ali | 20.9775 | 2.797 | 4 | 1 | 1
P/O | Krishna Const. | 1.7727 | 21.213 | 335 | 8 | 1
P/O | Krishna Const. -2 | 12.0619 | 12.464 | 31 | 3 | 1
P/O | Krishna-1 | 6.225 | 0.83 | 4 | 1 | 1
P/O | Kuddus ali | 15.6389 | 22.937 | 44 | 5 | 1
P/O | Kudus Ali | 0.1496 | 1.8948 | 369 | 3 | 1
P/O | Kudus Ali 2 | 3.8468 | 0.2564 | 2 | 1 | 1
P/O | Kunal Kumar | 1.0157 | 0.237 | 7 | 1 | 1
P/O | M R Constructions | 6.2936 | 38.6006 | 141 | 17 | 1
P/O | MC Const. | 14.3258 | 9.073 | 19 | 3 | 1
P/O | MC Power | 12.0876 | 10.8788 | 27 | 6 | 1
P/O | MR Power | 6.0664 | 16.3792 | 81 | 6 | 2
P/O | Manik Sarkar | 8.0278 | 5.6195 | 21 | 4 | 1
P/O | Md Anwar | 2.882 | 1.441 | 15 | 2 | 1
P/O | Modia India | 2.95 | 0.885 | 9 | 2 | 1
P/O | Modina India 2 | 2.4518 | 0.899 | 11 | 2 | 1
P/O | Monera | 7.3483 | 4.409 | 18 | 6 | 1
P/O | Muni bibi / Enamul / Alam / Rafikul | 4.05 | 0.27 | 2 | 1 | 1
P/O | Munni Bibi 1 | 2.6209 | 0.961 | 9 | 2 | 1
P/O | Munni Bibi 2 | 1.4014 | 0.654 | 14 | 2 | 1
P/O | Muslehuddin | 7.8401 | 18.2935 | 67 | 18 | 1
P/O | Muslehuddin + Enamul | 23.9938 | 2.3994 | 3 | 1 | 1
P/O | Muslehuddin and Giyash | 4.465 | 1.786 | 12 | 2 | 1
P/O | Muslehuddinn + GPJ | 12.4134 | 0.8276 | 2 | 1 | 1
P/O | Nasir | 17.3975 | 6.959 | 12 | 2 | 1
P/O | Nasiruddin | 20.1074 | 27.48 | 41 | 7 | 1
P/O | Nasruddin | 13.0148 | 12.581 | 28 | 5 | 1
P/O | National Construction | 26.544 | 4.424 | 5 | 1 | 1
P/O | Rafikul Alam | 7.3312 | 1.955 | 8 | 2 | 1
P/O | Rafikul Alam + Alam Const. + Enamul | 20.2089 | 2.0209 | 3 | 1 | 1
P/O | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 7.47 | 0.249 | 1 | 1 | 1
P/O | Rafikul Alam Construction | 8.028 | 1.338 | 5 | 1 | 1
P/O | Rafikul Alam constr. | 7.83 | 1.044 | 4 | 1 | 1
P/O | Rafikul Alam construction | 16.9626 | 2.8271 | 5 | 1 | 1
P/O | Rafikul Alam construction + Enamul | 19.5764 | 5.2204 | 8 | 2 | 1
P/O | RafikulAlam Construction | 22.4823 | 2.9976 | 4 | 1 | 1
P/O | Rahim Khan | 11.4593 | 25.9745 | 67 | 11 | 2
P/O | Ramavat Electricals | 1.1809 | 0.433 | 11 | 1 | 1
P/O | Ramavat Electricals -2 | 0.6575 | 0.263 | 12 | 1 | 1
P/O | Ramavat Electricals 1 | 1.38 | 0.69 | 15 | 2 | 1
P/O | Ramavat Electricals 1& 2 | 0.822 | 0.274 | 10 | 1 | 1
P/O | Ramavat Electricals 1&2 | 0.018 | 0.221 | 369 | 1 | 1
P/O | Ramavat Electricals 2 | 0.7592 | 0.658 | 26 | 2 | 1
P/O | Ramawat-Hot line | 0.7227 | 0.265 | 11 | 1 | 1
P/O | Ramsingh Yadav | 1.2945 | 1.726 | 40 | 7 | 1
P/O | Ramsingh Yadav 1&2 | 3.47 | 0.347 | 3 | 1 | 1
P/O | Ramsingh Yadav 2 | 1.7318 | 0.635 | 11 | 3 | 1
P/O | Rejaul | 12.9369 | 3.4498 | 8 | 2 | 1
P/O | Rejaul + Rafikul | 10.1875 | 2.0375 | 6 | 1 | 1
P/O | Rejaul + enamul | 12.8012 | 1.2801 | 3 | 1 | 1
P/O | Ruhul Amin / Alam Constr. | 1.215 | 0.405 | 10 | 1 | 1
P/O | S K INFRA | 14.8173 | 34.0798 | 69 | 10 | 1
P/O | SK Infratech | 18.7525 | 21.2529 | 34 | 6 | 1
P/O | SK Zenarul | 4.288 | 2.4298 | 14 | 4 | 1
P/O | SUFIYAN | 11.4221 | 12.945 | 34 | 6 | 1
P/O | Sanjay Singh | 1.158 | 1.351 | 35 | 6 | 1
P/O | Singhvahini | 4.5764 | 1.678 | 11 | 4 | 1
P/O | Teklal Saw | 6.06 | 3.434 | 17 | 3 | 1
P/O | Teklal Saw / Muslehuddin | 3.3771 | 0.788 | 7 | 1 | 1
P/O | Telegance Power | 0.642 | 0.214 | 10 | 1 | 1
P/O | Yakub Ali + Enamul | 0.4097 | 0.437 | 32 | 1 | 1
P/O | nan | 0 | 0 | 4 | 1 | 1
F/S | AE Solution | 3.5815 | 0.4775 | 4 | 2 | 1
F/S | AE Solution(Company) | 1.8893 | 0.4408 | 7 | 1 | 1
F/S | ANARUL ISLAM | 20.6958 | 27.5944 | 39 | 16 | 1
F/S | Abdul Adut | 7.35 | 0.735 | 3 | 1 | 1
F/S | Alam Construction | 5.3831 | 17.9435 | 71 | 23 | 1
F/S | Alam Construction / Enamul / Giyash / Alongir | 3.405 | 0.227 | 2 | 1 | 1
F/S | Alamgir | 1.608 | 0.268 | 5 | 1 | 1
F/S | Alongir | 5.8224 | 2.3289 | 12 | 2 | 1
F/S | Amir Sheikh | 19.044 | 6.348 | 10 | 2 | 1
F/S | Babloo Haque/Anarul-2 | 2.393 | 0.2393 | 3 | 1 | 1
F/S | Bhola | 1.2 | 0.16 | 4 | 1 | 1
F/S | Bhola Prasad | 3.3075 | 1.323 | 12 | 3 | 1
F/S | Bhola Prasad & Kamruddin | 9.015 | 1.202 | 4 | 1 | 1
F/S | Deepak Sarkar | 4.2583 | 9.3682 | 52 | 10 | 1
F/S | Deepak Sarkar + Manik Sarkar | 9.9122 | 2.9737 | 9 | 2 | 1
F/S | Devi Power | 10.6591 | 16.3439 | 39 | 7 | 2
F/S | Dharmendra 1 | 1.0714 | 1.4286 | 40 | 5 | 1
F/S | Dharmendra 2 | 1.5409 | 1.9518 | 38 | 7 | 1
F/S | Dharmendra Electrical | 2.58 | 2.064 | 24 | 8 | 1
F/S | Dhervendra Electricals | 0.3216 | 4.6736 | 423 | 14 | 1
F/S | Enamul + Alam Constrution | 6.7014 | 0.2234 | 1 | 1 | 1
F/S | Enamul Haque | 7.8526 | 18.3228 | 58 | 22 | 1
F/S | GPJ Const. | 16.0315 | 29.391 | 51 | 11 | 1
F/S | Giyash | 2.085 | 0.278 | 4 | 1 | 1
F/S | Giyash / Alongir | 4.19 | 0.419 | 3 | 1 | 1
F/S | Gokul Sarkar | 7.0838 | 4.4864 | 18 | 7 | 1
F/S | Gopal Associate | 16.381 | 15.835 | 29 | 5 | 1
F/S | Gopal Associate, Hotline | 1.0193 | 0.6456 | 19 | 3 | 1
F/S | Gopal Ji | 0.5377 | 0.233 | 13 | 1 | 1
F/S | Indrajeet | 9.911 | 17.179 | 50 | 12 | 1
F/S | Indrajeet/Mohan/Amir Sheikh | 3.264 | 0.544 | 5 | 1 | 1
F/S | Indrajeet/Rahim | 7.425 | 2.97 | 12 | 2 | 1
F/S | J PG CON | 23.7549 | 11.8774 | 15 | 4 | 1
F/S | JPJ Construction/MC Power | 16.248 | 5.416 | 10 | 2 | 1
F/S | Jahangir Alam | 4.62 | 1.848 | 8 | 2 | 1
F/S | Jahangir(Company) | 9.5454 | 2.2273 | 7 | 1 | 1
F/S | Kamaruddin | 11.6859 | 6.622 | 12 | 3 | 1
F/S | Kamruddin | 13.941 | 4.647 | 10 | 3 | 1
F/S | Kamruddin & Deepak | 21.1243 | 4.929 | 7 | 2 | 1
F/S | Kamruddin & Deepak Sarkar | 20.53 | 2.053 | 3 | 1 | 1
F/S | Kamruddin & Maidul rahman | 6.185 | 1.237 | 6 | 1 | 1
F/S | Kamruddin Deepak Sarkar | 3.8325 | 0.511 | 4 | 1 | 1
F/S | Kamruddinn | 19.57 | 1.957 | 3 | 1 | 1
F/S | Kamruddinn / Bhola prasad | 5.69 | 0.569 | 3 | 1 | 1
F/S | Krishna Const. | 13.3069 | 17.299 | 27 | 7 | 1
F/S | Krishna Const. -2 | 17.6654 | 7.655 | 13 | 2 | 1
F/S | Krishna-1 | 6.225 | 0.83 | 4 | 1 | 1
F/S | Kuddus ali | 20.8518 | 22.937 | 33 | 5 | 1
F/S | Kudus Ali | 5.6843 | 1.8948 | 10 | 3 | 1
F/S | Kudus Ali 2 | 3.8468 | 0.2564 | 2 | 1 | 1
F/S | Kunal Kumar | 1.0157 | 0.237 | 7 | 1 | 1
F/S | M R Constructions | 7.9842 | 42.8486 | 112 | 19 | 1
F/S | MC Const. | 19.4421 | 9.073 | 14 | 3 | 1
F/S | MC Power | 17.1771 | 10.8788 | 19 | 6 | 1
F/S | MR Power | 15.3555 | 16.3792 | 32 | 6 | 2
F/S | Manik Sarkar | 14.0486 | 5.6195 | 10 | 4 | 1
F/S | Md Anwar | 3.6025 | 1.441 | 12 | 2 | 1
F/S | Modia India | 2.95 | 0.885 | 9 | 2 | 1
F/S | Modina India 2 | 2.4518 | 0.899 | 11 | 2 | 1
F/S | Monera | 6.2986 | 4.409 | 21 | 6 | 1
F/S | Muni bibi / Enamul / Alam / Rafikul | 8.1 | 0.27 | 1 | 1 | 1
F/S | Munni Bibi 1 | 3.6038 | 0.961 | 4 | 2 | 1
F/S | Munni Bibi 2 | 1.5092 | 0.654 | 13 | 2 | 1
F/S | Muslehuddin | 7.7297 | 18.2935 | 64 | 18 | 1
F/S | Muslehuddin + Enamul | 23.9938 | 2.3994 | 3 | 1 | 1
F/S | Muslehuddin and Giyash | 4.8709 | 1.786 | 11 | 2 | 1
F/S | Muslehuddinn + GPJ | 8.2756 | 0.8276 | 3 | 1 | 1
F/S | Nasir | 41.754 | 6.959 | 5 | 2 | 1
F/S | Nasiruddin | 41.2201 | 27.48 | 20 | 7 | 1
F/S | Nasruddin | 0.9932 | 12.581 | 368 | 5 | 1
F/S | Rafikul Alam | 6.5167 | 1.955 | 9 | 2 | 1
F/S | Rafikul Alam + Alam Const. + Enamul | 20.2089 | 2.0209 | 3 | 1 | 1
F/S | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 7.47 | 0.249 | 1 | 1 | 1
F/S | Rafikul Alam Construction | 10.035 | 1.338 | 4 | 1 | 1
F/S | Rafikul Alam constr. | 10.44 | 1.044 | 3 | 1 | 1
F/S | Rafikul Alam construction | 12.1161 | 2.8271 | 7 | 1 | 1
F/S | Rafikul Alam construction + Enamul | 26.1019 | 5.2204 | 3 | 2 | 1
F/S | RafikulAlam Construction | 22.4823 | 2.9976 | 4 | 1 | 1
F/S | Rahim Khan | 5.9384 | 24.3474 | 98 | 10 | 2
F/S | Ramavat Electricals | 1.1809 | 0.433 | 11 | 1 | 1
F/S | Ramavat Electricals -2 | 0.6575 | 0.263 | 12 | 1 | 1
F/S | Ramavat Electricals 1 | 1.38 | 0.69 | 15 | 2 | 1
F/S | Ramavat Electricals 1& 2 | 0.822 | 0.274 | 10 | 1 | 1
F/S | Ramavat Electricals 1&2 | 1.6575 | 0.221 | 4 | 1 | 1
F/S | Ramavat Electricals 2 | 0.7592 | 0.658 | 26 | 2 | 1
F/S | Ramawat-Hot line | 0.6115 | 0.265 | 13 | 1 | 1
F/S | Ramsingh Yadav | 1.2945 | 1.726 | 40 | 7 | 1
F/S | Ramsingh Yadav 1&2 | 3.47 | 0.347 | 3 | 1 | 1
F/S | Ramsingh Yadav 2 | 1.7318 | 0.635 | 11 | 3 | 1
F/S | Rejaul | 14.785 | 3.4498 | 7 | 2 | 1
F/S | Rejaul + Rafikul | 20.375 | 2.0375 | 3 | 1 | 1
F/S | Rejaul + enamul | 9.6009 | 1.2801 | 4 | 1 | 1
F/S | Ruhul Amin / Alam Constr. | 3.0375 | 0.405 | 4 | 1 | 1
F/S | S K INFRA | 16.4902 | 34.0798 | 45 | 10 | 1
F/S | SK Infratech | 10.9084 | 16.3627 | 34 | 4 | 1
F/S | SK Zenarul | 2.5136 | 2.4298 | 18 | 4 | 1
F/S | SUFIYAN | 12.945 | 12.945 | 25 | 6 | 1
F/S | Sanjay Singh | 1.158 | 1.351 | 35 | 6 | 1
F/S | Singhvahini | 3.1462 | 1.678 | 16 | 4 | 1
F/S | Teklal Saw | 7.9246 | 3.434 | 13 | 3 | 1
F/S | Teklal Saw / Muslehuddin | 3.94 | 0.788 | 6 | 1 | 1
F/S | Telegance Power | 0.642 | 0.214 | 10 | 1 | 1
F/S | Yakub Ali + Enamul | 6.555 | 0.437 | 2 | 1 | 1

## PO_FS_Gap
project_name | from_ap | to_ap | gang_name | po_completion_date | fs_starting_date | gap_days | negative_gap_flag | source_file
TA 325 | 112/0 | 113/0 | Muslehuddin | 2024-08-15 | 2024-08-17 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 111/0 | 112/0 | Gokul Sarkar | 2024-09-24 | 2024-10-02 | 8 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 110/0 | 111/0 | Gokul Sarkar | 2024-09-12 | 2024-10-04 | 22 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 113/0 | 114/0 | Muslehuddin | 2024-09-29 | 2024-10-01 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 109/0 | 110/0 | Gokul Sarkar | 2024-09-09 | 2024-10-10 | 31 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 116/0 | 116A/0 | Gokul Sarkar | 2024-10-18 | 2024-10-26 | 8 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 108/0 | 109/0 | Muslehuddin | 2024-10-20 | 2024-10-25 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 107/0 | 108/0 | Muslehuddin | 2024-11-02 | 2024-11-04 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 133/0 | 133A/0 | Rejaul | 2024-11-02 | 2024-11-03 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 121/0 | 122/0 | Gokul Sarkar | 2024-11-03 | 2024-11-18 | 15 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 129A/0 | 130/0 | Rejaul | 2024-11-18 | 2024-11-21 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 106B/0 | 107/0 | Muslehuddin | 2024-11-16 | 2024-11-20 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 122/0 | 123/0 | Dhervendra Electricals | 2024-11-26 | 2024-11-28 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 118/0 | 119/0 | Enamul Haque | 2024-11-25 | 2024-12-02 | 7 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 117/0 | 118/0 | Enamul Haque | 2024-12-13 | 2024-12-18 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 119/0 | 120/0 | Muslehuddin | 2024-12-20 | 2024-12-21 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 116B/0 | 117/0 | Yakub Ali + Enamul | 2024-12-18 | 2024-12-23 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 144/0 | 144A/0 | Gokul Sarkar | 2024-12-19 | 2024-12-22 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 120/0 | 121/0 | Dhervendra Electricals | 2025-01-01 | 2024-12-28 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 114/0 | 115/0 | Muslehuddin | 2024-12-28 | 2024-12-30 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 115/0 | 116/0 | Muslehuddin | 2024-12-28 | 2024-12-31 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 133A/0 | 134/0 | Rejaul + Rafikul | 2025-01-01 | 2025-01-02 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 123/0 | 124/0 | Enamul Haque | 2024-12-30 | 2025-01-05 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 116A/0 | 116B/0 | Muslehuddin | 2025-01-11 | 2025-01-12 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 144A/0 | 145/0 | Dhervendra Electricals | 2025-01-13 | 2024-01-08 | -371 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 147/1 | 147/2 | Gokul Sarkar | 2025-01-16 | 2025-01-15 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 127/0 | 128/0 | Muslehuddin + Enamul | 2024-12-13 | 2025-01-17 | 35 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 126/0 | 127/0 | Enamul Haque | 2025-01-11 | 2025-01-23 | 12 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 132/0 | 133/0 | Rejaul + enamul | 2025-01-14 | 2025-01-21 | 7 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 259/0 | 260/0 | Dharmendra Electrical | 2025-01-24 | 2025-01-26 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 260/0 | 261/0 | Monera | 2025-01-25 | 2025-01-26 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 125A/0 | 126/0 | Enamul Haque | 2025-01-18 | 2025-02-04 | 17 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 106A/0 | 106B/0 | Muslehuddin | 2025-02-01 | 2025-02-04 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 125/0 | 125A/0 | Enamul Haque | 2025-02-02 | 2025-02-06 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 128/0 | 129/0 | Alam Construction | 2025-02-10 | 2025-02-12 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 129/0 | 129A/0 | Alam Construction | 2025-02-10 | 2025-02-12 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 135A/0 | 135A/1 | SK Zenarul | 2025-01-21 | 2025-02-06 | 16 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 135A/2 | 135B/0 | Rafikul Alam construction + Enamul | 2025-02-06 | 2025-02-12 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 135B/0 | 136/0 | Rafikul Alam construction + Enamul | 2025-01-29 | 2025-02-12 | 14 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 106/0 | 106A/0 | Muslehuddin | 2025-02-05 | 2025-02-14 | 9 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 164/0 | 165/0 | Manik Sarkar | 2025-02-10 | 2025-02-12 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 135A/1 | 135A/2 | SK Zenarul | 2025-02-02 | 2025-02-07 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 124/0 | 124A/0 | Enamul Haque | 2025-02-13 | 2025-02-16 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 124A/0 | 124A/1 | Enamul Haque | 2025-02-19 | 2025-02-15 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 124A/1 | 125/0 | Dhervendra Electricals | 2025-02-19 | 2025-02-15 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 257/0 | 259/0 | Monera | 2025-02-13 | 2025-02-21 | 8 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 137A/0 | 138/0 | Alam Construction | 2025-02-25 | 2025-02-28 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 138/0 | 139/0 | Enamul Haque | 2025-03-01 | 2025-03-02 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 261/0 | 262/0 | Dharmendra Electrical | 2025-03-04 | 2025-03-06 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 139/0 | 139A/0 | SK Zenarul | 2025-03-04 | 2025-03-07 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 130/0 | 131/0 | Muslehuddin | 2025-03-05 | 2025-03-07 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 131/0 | 132/0 | Dhervendra Electricals | 2025-03-10 | 2025-03-06 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 139A/0 | 140/0 | SK Zenarul | 2025-03-05 | 2025-03-07 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 262/0 | 263/0 | Monera | 2025-02-19 | 2025-03-12 | 21 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 263/0 | 264/0 | Dharmendra Electrical | 2025-03-12 | 2025-03-13 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 142/0 | 143/0 | Enamul + Alam Constrution | 2025-03-18 | 2025-03-18 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 143/0 | 143A/0 | Alam Construction | 2025-03-09 | 2025-03-20 | 11 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 255/0 | 257/0 | Kamruddin | 2025-02-25 | 2025-03-20 | 23 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 265/0 | 266/0 | Dharmendra Electrical | 2025-03-18 | 2025-03-19 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 134/0 | 135/0 | Dhervendra Electricals | 2025-03-22 | 2025-03-18 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 163/0 | 163/5 | Manik Sarkar | 2025-02-28 | 2025-03-21 | 21 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 163/5 | 163/6 | Dhervendra Electricals | 2025-03-22 | 2025-03-21 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 163/6 | 164/0 | Manik Sarkar | 2025-03-08 | 2025-03-21 | 13 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 264/0 | 265/0 | Monera | 2025-03-18 | 2025-03-19 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 143A/0 | 143A/2 | Alam Construction | 2025-03-21 | 2025-03-23 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 143A/2 | 143A/3 | Enamul Haque | 2025-03-24 | 2025-03-23 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 143A/3 | 144/0 | Enamul Haque | 2025-03-20 | 2025-03-23 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 266/0 | 266/1 | Dharmendra Electrical | 2025-03-24 | 2025-03-25 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 266/1 | 267/0 | Monera | 2025-03-24 | 2025-03-25 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 136/0 | 137/0 | Dhervendra Electricals | 2025-04-01 | 2025-03-26 | -6 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 137/0 | 137A/0 | Rafikul Alam construction | 2025-03-09 | 2025-03-26 | 17 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 145A/0 | 146/0 | Enamul Haque | 2025-04-04 | 2025-04-07 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 253/0 | 254/0 | Dharmendra Electrical | 2025-04-06 | 2025-04-07 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 254/0 | 255/0 | Monera | 2025-02-28 | 2025-04-07 | 38 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 267/0 | 267A/0 | Kamruddin Deepak Sarkar | 2025-04-03 | 2025-04-07 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 267A/0 | 268/0 | Kamruddin | 2025-03-29 | 2025-04-07 | 9 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 141/0 | 141/1 | Alam Construction | 2025-04-09 | 2025-04-11 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 141/1 | 141/2 | Dhervendra Electricals | 2025-04-09 | 2025-04-11 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 141/2 | 142/0 | Alam Construction | 2025-04-09 | 2025-04-11 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 146/0 | 147/0 | Enamul Haque | 2025-04-15 | 2025-04-12 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 147/0 | 147/1 | Dhervendra Electricals | 2025-04-15 | 2025-04-11 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 147B/0 | 148/0 | Muslehuddinn + GPJ | 2025-04-05 | 2025-04-13 | 8 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 152/0 | 152A/0 | Alongir | 2025-04-09 | 2025-04-13 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 270/0 | 270A/0 | Kamruddin & Deepak | 2025-04-14 | 2025-04-14 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 145/0 | 145A/0 | Dhervendra Electricals | 2025-04-23 | 2025-04-18 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 268/0 | 269/0 | Dharmendra Electrical | 2025-04-19 | 2025-04-21 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 269/0 | 270/0 | Kamruddin & Maidul rahman | 2025-04-08 | 2025-04-18 | 10 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 270A/0 | 271/0 | Alamgir | 2025-04-15 | 2025-04-21 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 271/0 | 272/0 | Kamruddin & Deepak | 2025-04-20 | 2025-04-21 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 148/0 | 149/0 | Muslehuddin | 2025-04-21 | 2025-04-24 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 149/0 | 150/0 | Enamul Haque | 2025-04-23 | 2025-04-24 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 162/0 | 163/0 | Manik Sarkar | 2025-04-13 | 2025-04-23 | 10 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 147A/0 | 147B/0 | Enamul Haque | 2025-04-30 | 2025-04-30 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 135/0 | 135A/0 | RafikulAlam Construction | 2025-03-24 | 2025-04-28 | 35 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 251/0 | 252/0 | Dharmendra Electrical | 2025-05-01 | 2025-05-02 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 161/0 | 162/0 | Dhervendra Electricals | 2025-05-06 | 2025-04-28 | -8 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 252/0 | 253/0 | Deepak Sarkar | 2025-04-19 | 2025-05-04 | 15 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 250/0 | 251/0 | Deepak Sarkar | 2025-05-05 | 2025-05-08 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 249/0 | 250/0 | Kamruddin | 2025-05-03 | 2025-05-09 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 150A/0 | 151/0 | Alam Construction | 2025-04-29 | 2025-05-12 | 13 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 151/0 | 152/0 | Dhervendra Electricals | 2025-05-15 | 2025-05-11 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 147/2 | 147A/0 | Rafikul Alam + Alam Const. + Enamul | 2025-05-18 | 2025-05-16 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 140/0 | 141/0 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 2025-05-22 | 2025-05-23 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 150/0 | 150/1 | Dhervendra Electricals | 2025-05-25 | 2025-05-23 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 150/1 | 150A/0 | Alam Construction | 2025-05-11 | 2025-05-23 | 12 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 156/0 | 157/0 | Deepak Sarkar + Manik Sarkar | 2025-06-04 | 2025-06-03 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 272/0 | 272/5 | Kamruddin & Deepak Sarkar | 2025-03-15 | 2025-06-13 | 90 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 155/0 | 156/0 | Deepak Sarkar + Manik Sarkar | 2025-06-11 | 2025-06-14 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 152A/0 | 153/0 | Alam Construction | 2025-09-10 | 2025-09-06 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 158B/0 | 159/0 | Deepak Sarkar | 2025-09-27 | 2025-10-02 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 158A/0 | 158B/0 | Dharmendra 1 | 2025-10-21 | 2025-10-07 | -14 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 276/0 | Gty | Bhola | 2025-10-21 | 2025-10-18 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 158/0 | 158A/0 | Deepak Sarkar | 2025-10-13 | 2025-10-17 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 192/0 | 193/0 | Teklal Saw | 2025-10-23 | 2025-10-19 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 193/0 | 194/0 | Ramsingh Yadav | 2025-10-25 | 2025-10-21 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 194/0 | 195/0 | Enamul Haque | 2025-10-29 | 2025-10-24 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 191/0 | 191/2 | Alam Construction | 2025-10-25 | 2025-10-25 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 191/2 | 191/3 | Alam Construction | 2025-10-25 | 2025-10-25 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 191/3 | 191A/0 | Alam Construction | 2025-10-25 | 2025-10-25 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 191A/0 | 192/0 | Md Anwar | 2025-10-19 | 2025-10-24 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 204/0 | 205/0 | Dharmendra 2 | 2025-11-03 | 2025-10-26 | -8 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 195/0 | 195A/0 | Enamul Haque | 2025-10-26 | 2025-10-31 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 196/0 | 197/0 | Ramsingh Yadav | 2025-11-04 | 2025-10-26 | -9 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 275/0 | 276/0 | Dharmendra 1 | 2025-11-04 | 2025-10-26 | -9 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 195A/0 | 196/0 | Muslehuddin | 2025-10-18 | 2025-10-29 | 11 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 157/0 | 158/0 | Deepak Sarkar | 2025-11-11 | 2025-11-07 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 190/0 | 191/0 | Ramsingh Yadav | 2025-11-12 | 2025-11-08 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 176/0 | 177/0 | Sanjay Singh | 2025-11-12 | 2025-11-06 | -6 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 177/0 | 178/0 | Ruhul Amin / Alam Constr. | 2025-11-12 | 2025-11-10 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 178/0 | 179/0 | Giyash | 2025-11-09 | 2025-11-10 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 189/0 | 190/0 | Md Anwar | 2025-11-07 | 2025-11-10 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 248/0 | 249/0 | Kamaruddin | 2025-11-10 | 2025-11-07 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 197/0 | 198/0 | Muslehuddin | 2025-11-12 | 2025-11-12 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 224/0 | 225/0 | Dharmendra 2 | 2025-11-12 | 2025-11-12 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 241/0 | 242/0 | Singhvahini | 2025-11-12 | 2025-11-12 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 243/0 | 244/0 | Dharmendra 1 | 2025-11-12 | 2025-11-12 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 168/0 | 169/0 | Rafikul Alam constr. | 2025-11-08 | 2025-11-15 | 7 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 169/0 | 171/0 | Ramavat Electricals | 2025-11-18 | 2025-11-08 | -10 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 181/0 | 182/0 | Alam Construction | 2025-11-17 | 2025-11-14 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 242/0 | 243/0 | Enamul Haque | 2025-11-18 | 2025-11-19 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 179/0 | 180/0 | Sanjay Singh | 2025-11-21 | 2025-11-16 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 188/0 | 189/0 | Ramsingh Yadav | 2025-11-21 | 2025-11-16 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 198/0 | 199/0 | Muslehuddin | 2025-11-19 | 2025-11-18 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 244/0 | 244/1 | Bhola Prasad | 2025-11-13 | 2025-11-19 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 246/0 | 247/0 | Dharmendra 1 | 2025-11-23 | 2025-11-20 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 205/0 | 206/0 | Deepak Sarkar | 2025-11-24 | 2025-11-21 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 230/0 | 231/0 | Alam Construction / Enamul / Giyash / Alongir | 2025-11-25 | 2025-11-24 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 247/0 | 248/0 | Kamruddinn | 2025-11-18 | 2025-11-23 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 244/1 | 245/0 | Bhola Prasad | 2025-11-18 | 2025-11-23 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 231/0 | 232/0 | Giyash / Alongir | 2025-11-28 | 2025-11-26 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 233/0 | 234/0 | Singhvahini | 2025-11-29 | 2025-11-26 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 245/0 | 246/0 | Kamruddinn / Bhola prasad | 2025-11-21 | 2025-11-27 | 6 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 232/0 | 233/0 | Sanjay Singh | 2025-11-30 | 2025-11-26 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 234/0 | 235/0 | Dharmendra 2 | 2025-11-30 | 2025-11-26 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 180/0 | 181/0 | Ramavat Electricals -2 | 2025-12-01 | 2025-11-20 | -11 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 210/0 | 211/0 | Ramsingh Yadav | 2025-12-03 | 2025-11-28 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 222/1 | 223/0 | Ramsingh Yadav 2 | 2025-12-04 | 2025-12-02 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 209/0 | 210/0 | Deepak Sarkar | 2025-12-04 | 2025-12-02 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 235/0 | 236/0 | Singhvahini | 2025-12-05 | 2025-12-03 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 171/0 | 172/0 | Ramavat Electricals 1& 2 | 2025-12-06 | 2025-11-27 | -9 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 226/0 | 227/0 | Muslehuddin | 2025-12-07 | 2025-12-04 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 229/1 | 230/0 | Teklal Saw | 2025-12-03 | 2025-12-04 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 184/0 | 184/1 | Alam Construction | 2025-12-08 | 2025-12-04 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 184/1 | 185/0 | Alam Construction | 2025-12-08 | 2025-12-04 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 225/0 | 226/0 | Muslehuddin | 2025-11-29 | 2025-12-04 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 236/0 | 237/0 | Dharmendra 1 | 2025-12-08 | 2025-12-03 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 237/0 | 239/0 | Enamul Haque | 2025-12-03 | 2025-12-07 | 4 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 240/0 | 241/0 | Enamul Haque | 2025-12-10 | 2025-12-07 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 239/0 | 240/0 | Ramsingh Yadav | 2025-12-11 | 2025-12-07 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 165/0 | 165/4 | Rafikul Alam | 2025-12-01 | 2025-12-08 | 7 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 187/0 | 188/0 | Alam Construction | 2025-12-05 | 2025-12-10 | 5 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 274/0 | 275/0 | Bhola Prasad | 2025-10-27 | 2025-12-09 | 43 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 182/0 | 182A/0 | Ramavat Electricals 2 | 2025-12-13 | 2025-12-11 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 219/0 | 220/0 | Sanjay Singh | 2025-12-13 | 2025-12-08 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 211/0 | 211A/0 | Deepak Sarkar | 2025-12-13 | 2025-12-11 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 212/0 | 213/0 | Ramsingh Yadav 2 | 2025-12-14 | 2025-12-10 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 229/0 | 229/1 | Alongir | 2025-12-15 | 2025-12-07 | -8 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 160/0 | 161/0 | Dharmendra 2 | 2025-12-16 | 2025-12-13 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 167/1 | 168/0 | Rafikul Alam Construction | 2025-11-23 | 2025-12-14 | 21 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 223/0 | 224/0 | Muslehuddin and Giyash | 2025-12-13 | 2025-12-14 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 218/0 | 219/0 | Singhvahini | 2025-12-14 | 2025-12-16 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 182A/0 | 183/0 | Alam Construction | 2025-12-20 | 2025-12-15 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 183/0 | 184/0 | Ramavat Electricals 1 | 2025-12-20 | 2025-12-15 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 213/0 | 214/0 | Kudus Ali | 2025-12-17 | 2025-12-18 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 203/1 | 204/0 | Modia India | 2025-12-18 | 2025-12-19 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 220/0 | 221/0 | Abdul Adut | 2025-12-16 | 2025-12-19 | 3 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 272/5 | 272A/0 | Bhola Prasad & Kamruddin | 2025-12-20 | 2025-12-18 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 199/0 | 200/0 | Ramsingh Yadav | 2025-12-22 | 2025-12-20 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 200/0 | 201/0 | Ramsingh Yadav 2 | 2025-12-22 | 2025-12-20 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 227/0 | 228/0 | Munni Bibi 2 | 2025-12-18 | 2025-12-17 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 228/0 | 229/0 | Sanjay Singh | 2025-12-22 | 2025-12-17 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 217A/0 | 218/0 | Teklal Saw | 2025-12-19 | 2025-12-20 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 105/0 | 106/0 | Kudus Ali 2 | 2025-12-25 | 2025-12-24 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 165/4 | 165/5 | Munni Bibi 1 | 2025-12-22 | 2025-12-22 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 165/5 | 166/0 | Munni Bibi 1 | 2025-12-15 | 2025-12-22 | 7 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 201/0 | 201/1 | Modina India 2 | 2025-12-26 | 2025-12-23 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 272A/0 | 273/0 | Kamaruddin | 2025-12-25 | 2025-12-22 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 273/0 | 274/0 | Kamaruddin | 2025-12-11 | 2025-12-22 | 11 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 211A/0 | 212/0 | Deepak Sarkar | 2025-12-25 | 2025-12-10 | -15 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 175/0 | 175/1 | Dharmendra 2 | 2025-12-27 | 2025-12-23 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 175/1 | 176/0 | Alam Construction | 2025-12-27 | 2025-12-24 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 167/0 | 167/1 | Rafikul Alam | 2025-12-29 | 2025-12-27 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 208/0 | 209/0 | Deepak Sarkar | 2025-12-23 | 2025-12-18 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 214/0 | 215/0 | Kudus Ali | 2025-12-28 | 2025-12-29 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 217/0 | 217A/0 | Ramsingh Yadav 1&2 | 2025-12-31 | 2025-12-29 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 221/0 | 222/0 | Sanjay Singh | 2025-12-31 | 2025-12-27 | -4 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 222/0 | 222/1 | Muslehuddin and Giyash | 2025-12-31 | 2025-12-25 | -6 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 172/0 | 173/0 | Alam Construction | 2025-12-30 | 2025-12-31 | 1 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 201/1 | 202/0 | Modina India 2 | 2026-01-04 | 2025-12-29 | -6 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 202/0 | 203/0 | Teklal Saw / Muslehuddin | 2026-01-04 | 2025-12-30 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 203/0 | 203/1 | Modia India | 2025-12-28 | 2025-12-30 | 2 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 154/1 | 155/0 | Munni Bibi 2 | 2026-01-05 | 2025-12-30 | -6 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 159/0 | 159/2 | Enamul Haque | 2026-01-05 | 2026-01-03 | -2 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 173/0 | 174/0 | Dharmendra 2 | 2026-01-05 | 2025-12-31 | -5 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 174/0 | 174/1 | Alam Construction | 2026-01-06 | 2026-01-03 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 174/1 | 175/0 | Alam Construction | 2026-01-06 | 2026-01-03 | -3 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 159/2 | 160/0 | Enamul Haque | 2025-12-26 | 2026-01-07 | 12 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 206/0 | 208/0 | Ramavat Electricals 2 | 2026-01-09 | 2025-12-18 | -22 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 216/0 | 217/0 | Ramavat Electricals 1 | 2026-01-09 | 2026-01-01 | -8 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 185/0 | 186/0 | Alam Construction | 2026-01-09 | 2026-01-09 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 186/0 | 187/0 | Dharmendra 2 | 2026-01-11 | 2026-01-10 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 215/0 | 215/1 | Ramavat Electricals 1&2 | 2026-01-14 | 2026-01-13 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 215/1 | 216/0 | Kudus Ali | 2026-01-14 | 2026-01-13 | -1 | TRUE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 166/0 | 167/0 | Muni bibi / Enamul / Alam / Rafikul | 2026-01-17 | 2026-01-17 | 0 | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 101/0 | 102/0 | Kudus Ali 2 |  | 2026-01-16 |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 102/0 | 103/0 | Modina India 1 |  | 2026-01-16 |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 103/0 | 104/0 | Muslehuddin |  | 2026-01-16 |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 104/0 | 105/0 | Dharmendra 2 |  | 2026-01-17 |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 153/0 | 154/0 | Modina india 2 |  |  |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | 154/0 | 154/1 | Deepak Sarkar |  |  |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | nan | nan | nan |  |  |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 325 | nan | Total | nan |  |  |  | FALSE | TA 325 - DPR - 2026-01-19.xlsx
TA 413 | 34/0 | 35/0 | SK Infratech | 2025-02-26 | 2025-02-27 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 37A/0 | 38/0 | SK Infratech | 2025-03-20 | 2025-03-21 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 38/0 | 39/0 | SK Infratech | 2025-04-05 | 2025-04-06 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 39/0 | 40/0 | SK Infratech | 2025-04-29 | 2025-04-30 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 7/0 | 7A/0 | Rahim Khan | 2025-09-04 | 2025-09-05 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 7A/0 | 8/0 | Rahim Khan | 2025-09-16 | 2025-09-17 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 8/0 | 8A/0 | Rahim Khan | 2025-10-15 | 2025-10-16 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 8A/0 | 9/0 | Rahim Khan | 2025-10-05 | 2025-10-06 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 6/0 | 7/0 | Rahim Khan | 2025-11-23 | 2025-11-24 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 5A/0 | 6/0 | Rahim Khan | 2025-11-09 | 2025-11-10 | 1 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 5/0 | 5A/0 | Rahim Khan | 2025-12-12 | 2025-12-17 | 5 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 4A/0 | 5/0 | Rahim Khan | 2025-12-22 | 2025-12-25 | 3 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 4/0 | 4A/0 | Rahim Khan | 2025-12-31 | 2026-01-14 | 14 | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 3B/0 | 4/0 | Rahim Khan | 2026-01-17 |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 33/0 | 34/0 | SK Infratech | 2026-01-13 |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 32A/0 | 33/0 | SK Infratech | 2026-01-19 |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 3A/0 | 3B/0 | Rahim Khan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 32/0 | 32A/0 | SK Infratech |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 40/0 | 40A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | GY | 1/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 1/0 | 2A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 2A/0 | 3A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 9/0 | 10/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 10/0 | 11/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 11/0 | 12/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 12/0 | 13/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 13/0 | 13A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 13A/0 | 14/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 14/0 | 15/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 15/0 | 16/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 16/0 | 17/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 17/0 | 18/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 18/0 | 19/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 19/0 | 20/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 20/0 | 21/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 21/0 | 22/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 22/0 | 23/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 23/0 | 23A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 23A/0 | 24/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 24/0 | 25/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 25/0 | 26/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 26/0 | 27/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 27/0 | 28/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 28/0 | 29/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 29/0 | 29A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 29A/0 | 30/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 30/0 | 31/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 31/0 | 32/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 35/0 | 36/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 36/0 | 36A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 36A/0 | 37/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 37/0 | 37A/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 40A/0 | 41/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 41/0 | 42/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 42/0 | 42/3 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 42/3 | 43/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 43/0 | 43/5 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 43/5 | 44/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 44/0 | 45/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | 45/0 | 46/0 | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 413 | nan | nan | nan |  |  |  | FALSE | TA 413 - DPR - 2026-01-19.xlsx
TA 414 | nan | nan | nan |  |  |  | FALSE | TA 414 - DPR - 2026-01-28.xlsx
TA 414 | nan | nan | nan |  |  |  | FALSE | TA 414 - DPR - 2026-01-28.xlsx
TA 414 | nan | Total | nan |  |  |  | FALSE | TA 414 - DPR - 2026-01-28.xlsx
TA 416 | AP7/0 | AP8/0 | ANARUL ISLAM | 2025-05-12 | 2025-05-15 | 3 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP6/0 | AP7/0 | ANARUL ISLAM | 2025-05-17 | 2025-05-19 | 2 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP35/0 | AP36/0 | S K INFRA | 2025-05-25 | 2025-06-27 | 33 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP8/0 | AP8A/0 | ANARUL ISLAM | 2025-05-29 | 2025-05-30 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP31/0 | AP32/0 | S K INFRA | 2025-06-09 | 2025-06-22 | 13 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP8A/0 | AP8B/0 | ANARUL ISLAM | 2025-06-19 | 2025-07-22 | 33 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP32/0 | AP33/0 | S K INFRA | 2025-06-19 | 2025-07-25 | 36 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP8B/0 | AP9/0 | ANARUL ISLAM | 2025-07-21 | 2025-07-26 | 5 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP33/0 | AP34/0 | S K INFRA | 2025-07-21 | 2025-07-25 | 4 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP5/0 | AP6/0 | ANARUL ISLAM | 2025-08-08 | 2025-08-26 | 18 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP9/0 | AP10/0 | ANARUL ISLAM | 2025-08-11 | 2025-08-11 | 0 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP34/0 | AP35/0 | S K INFRA | 2025-08-20 | 2025-08-21 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP4/0 | AP5/0 | ANARUL ISLAM | 2025-08-25 | 2025-08-27 | 2 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP14/0 | AP15/0 | ANARUL ISLAM | 2025-09-10 | 2025-09-28 | 18 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP36/0 | AP37/0 | S K INFRA | 2025-09-11 | 2025-12-06 | 86 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP3/0 | AP4/0 | ANARUL ISLAM | 2025-09-15 | 2025-09-16 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP30/0 | AP31/0 | S K INFRA | 2025-09-28 | 2025-09-30 | 2 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP20/0 | AP21/0 | J PG CON | 2025-09-30 | 2025-10-01 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP12/0 | AP13/0 | ANARUL ISLAM | 2025-10-16 | 2025-10-24 | 8 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP39/0 | AP40/0 | S K INFRA | 2025-10-19 | 2025-10-23 | 4 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP21/0 | AP22/0 | J PG CON | 2025-10-26 | 2025-10-27 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP13/0 | AP14/0 | ANARUL ISLAM | 2025-11-03 | 2025-11-03 | 0 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP38/0 | AP39/0 | S K INFRA | 2025-11-10 | 2025-11-25 | 15 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP19/0 | AP20/0 | J PG CON | 2025-11-13 | 2025-11-15 | 2 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP17/0 | AP18/0 | ANARUL ISLAM |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP18/0 | AP19/0 | J PG CON | 2025-11-24 | 2025-11-24 | 0 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP15/0 | AP16/0 | ANARUL ISLAM | 2025-11-25 | 2025-11-26 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP10/0 | AP11/0 | ANARUL ISLAM | 2025-12-04 | 2025-12-05 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP37/0 | AP38/0 | S K INFRA | 2025-12-10 | 2025-12-06 | -4 | TRUE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP11/0 | AP12/0 | ANARUL ISLAM | 2025-12-10 | 2025-12-11 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP1/0 | AP2/0 | AE Solution | 2025-12-19 | 2025-12-21 | 2 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP0/0 | AP1/0 | ANARUL ISLAM | 2025-12-30 | 2025-12-31 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP24/0 | AP25/0 | AE Solution | 2025-12-30 | 2025-12-29 | -1 | TRUE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP23/0 | AP24/0 | Jahangir(Company) | 2026-01-15 | 2026-01-16 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP40/0 | AP41/0 | Babloo Haque/Anarul-2 | 2026-01-16 | 2026-01-16 | 0 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP41/0 | AP42/0 | ANARUL ISLAM (Company) |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP16/0 | AP17/0 | Ramawat-Hot line | 2026-01-10 | 2026-01-11 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP2/0 | AP3/0 | ANARUL ISLAM | 2026-01-22 | 2026-01-23 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP26/0 | AP27/0 | AE Solution(Company) | 2026-01-15 | 2026-01-16 | 1 | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP25/0 | AP26/0 | Bhola prasad(Company) |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP42/0 | AP43/0 | Babloo Haque/Anarul-2 |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | AP27/0 | AP28/0 | AE Solution(Company) |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | nan | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 416 | nan | Total | nan |  |  |  | FALSE | TA 416 - DPR - 2026-01-22.xlsx
TA 418 | 42/0 | 43/0 | SUFIYAN | 2025-09-28 | 2025-10-13 | 15 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 41/0 | 42/0 | SUFIYAN | 2025-10-06 | 2025-12-22 | 77 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 40/0 | 41/0 | SUFIYAN | 2025-12-26 | 2025-12-30 | 4 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 35/0 | 36/0 | SUFIYAN | 2025-11-17 | 2025-12-05 | 18 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 34/0 | 35/0 | SUFIYAN | 2025-11-30 | 2025-12-05 | 5 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 36/0 | 36/1 | SUFIYAN | 2025-11-03 | 2025-11-10 | 7 | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 33/6 | 34/0 | SUFIYAN |  |  |  | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 33/0 | 33/5 | Haque |  |  |  | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 418 | 33/5 | 33/6 | Ramawat (HL) |  |  |  | FALSE | TA 418 - DPR - 2026-01-27.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 419 | nan | nan | nan |  |  |  | FALSE | TA 419 - DPR - 2026-01-26.xlsx
TA 421 | 23/0 | 24/0 | M R Constructions | 2025-02-16 | 2025-02-27 | 11 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 24/0 | 25/0 | M R Constructions | 2025-03-04 | 2025-03-09 | 5 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 25/0 | 26/0 | M R Constructions | 2025-03-13 | 2025-03-24 | 11 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 26/0 | 27/0 | M R Constructions | 2025-03-28 | 2025-04-18 | 21 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 22/0 | 23/0 | M R Constructions |  | 2025-04-22 |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 29/0 | 29/9 | M R Constructions | 2025-05-16 | 2025-07-06 | 51 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 32/0 | 33/0 | M R Constructions | 2025-05-25 | 2025-05-28 | 3 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 31/0 | 32/0 | M R Constructions | 2025-06-17 | 2025-06-13 | -4 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 30/0 | 31/0 | M R Constructions | 2025-07-02 | 2025-06-23 | -9 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 29/9 | 30/0 | M R Constructions | 2025-07-11 | 2025-07-07 | -4 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 21/0 | 22/0 | M R Constructions | 2025-07-24 | 2025-08-06 | 13 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 20A/0 | 21/0 | M R Constructions | 2025-08-31 | 2025-08-24 | -7 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 20/0 | 20A/0 | M R Constructions | 2025-09-01 | 2025-08-24 | -8 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 12/0 | 13/0 | Nasiruddin | 2025-09-07 | 2025-09-15 | 8 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 10/0 | 11/0 | Nasiruddin | 2025-10-05 | 2025-10-08 | 3 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 19/0 | 20/0 | M R Constructions | 2025-10-19 | 2025-09-17 | -32 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 18/0 | 19/0 | M R Constructions | 2025-10-20 | 2025-09-22 | -28 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 9/0 | 10/0 | M R Constructions | 2025-10-23 | 2025-10-24 | 1 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 13/0 | 14/0 | Nasiruddin | 2025-11-19 | 2025-11-20 | 1 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 11/0 | 12/0 | Nasiruddin | 2025-12-07 | 2025-12-07 | 0 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 17/0 | 18/0 | M R Constructions | 2025-11-15 | 2025-12-08 | 23 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 14/0 | 15/0 | Nasiruddin | 2025-12-17 | 2025-12-15 | -2 | TRUE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 16/0 | 17/0 | M R Constructions | 2025-12-08 | 2025-12-24 | 16 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 15/0 | 16/0 | M R Constructions | 2025-10-23 | 2025-12-24 | 62 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 8/4 | 9/0 | Nasiruddin | 2026-01-06 | 2026-01-06 | 0 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 6/0 | 7/0 | Nasiruddin | 2026-01-15 | 2026-01-18 | 3 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 27/0 | 27/3 | M R Constructions | 2026-01-12 | 2026-01-22 | 10 | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 27/3 | 28/0 | M R Constructions |  | 2026-01-22 |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 8/3 | 8/4 | Ramavath Electricals |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 4/12 | 5/0 | Nasiruddin |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | 7/0 | 8/0 | Nasiruddin |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | Gantry | 1/0 | Kamruddin |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | nan | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 421 | nan | Total | nan |  |  |  | FALSE | TA 421 - DPR - 2026-01-22.xlsx
TA 504 | 16/3 | 17/0 | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | 17/0 | 18/0 | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | 18/0 | 19/0 | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | nan | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 504 | nan | Total | nan |  |  |  | FALSE | TA 504 - DPR - 2026-01-27.xlsx
TA 505 | 100/0 | 101/0 | Alimuddin | 2026-01-25 |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | 101/0 | 102/0 | Alimuddin |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | nan | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 505 | nan | Total | nan |  |  |  | FALSE | TA 505 - DPR - 2026-01-27.xlsx
TA 506 | 1/0 | 2/0 | National Construction | 2026-01-22 |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | 5/0 | 6/0 | National Construction |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | 48/0 | 50/0 | Jahangir Alam | 2025-12-30 | 2026-01-15 | 16 | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | 50/0 | 51/0 | Jahangir Alam | 2025-12-30 | 2026-01-17 | 18 | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | 2/0 | 2A/0 | National Construction |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | 51/0 | 51A/0 | nan | 2026-01-20 |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | nan | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 506 | nan | Total | nan |  |  |  | FALSE | TA 506 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TA 512 | nan | nan | nan |  |  |  | FALSE | TA 512 - DPR - 2026-01-27.xlsx
TB 401 | 57/6 | 58/0 | GPJ Const. | 2024-05-10 | 2024-05-19 | 9 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 57/0 | 57/6 | GPJ Const. | 2024-05-24 | 2024-06-07 | 14 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 56/0 | 57/0 | GPJ Const. | 2024-06-12 | 2024-06-28 | 16 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 55/0 | 56/0 | GPJ Const. | 2024-07-04 | 2024-07-17 | 13 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 53/0 | 55/0 | GPJ Const. | 2024-07-22 | 2024-08-09 | 18 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 52/0 | 53/0 | GPJ Const. | 2024-08-22 | 2024-09-04 | 13 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 51/0 | 52/0 | GPJ Const. | 2024-09-08 | 2024-09-28 | 20 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 50/0 | 51/0 | GPJ Const. | 2024-10-02 | 2024-10-08 | 6 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 72/7 | 73/0 | MR Power | 2024-11-15 | 2024-11-27 | 12 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 58/0 | 58/7 | Kddus Ali | 2024-11-23 |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 72/0 | 72/7 | MR Power | 2024-11-23 | 2024-12-06 | 13 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 67/1 | 68/0 | Nasruddin | 2024-12-23 | 2024-12-23 | 0 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 68/0 | 69/0 | Nasruddin | 2024-12-20 | 2025-01-01 | 12 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 58/7 | 59/0 | MR Power | 2025-01-04 | 2025-01-07 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 71/0 | 72/0 | MR Power | 2024-12-10 | 2025-01-16 | 37 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 67/0 | 67/1 | Nasruddin | 2024-12-22 | 2025-01-20 | 29 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 69/0 | 70/0 | Nasruddin | 2025-01-05 | 2025-01-27 | 22 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 41/0 | 42/0 | Nasruddin | 2025-02-20 | 2025-02-28 | 8 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 59/0 | 60/0 | MR Power | 2025-01-25 | 2025-05-02 | 97 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 42/0 | 43/0 | Indrajeet | 2025-05-11 | 2025-05-07 | -4 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 49/0 | 50/0 | Indrajeet | 2025-05-17 | 2025-05-15 | -2 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 48/0 | 49/0 | Indrajeet | 2025-05-17 | 2025-05-19 | 2 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 47/0 | 48/0 | Indrajeet | 2025-05-21 | 2025-05-25 | 4 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 37/2 | 38/0 | Indrajeet | 2025-05-30 | 2025-06-11 | 12 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 43/0 | 44/0 | Indrajeet | 2025-05-10 | 2025-06-20 | 41 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 61/0 | 62/0 | GPJ Const. | 2025-06-29 | 2025-07-07 | 8 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 62/0 | 63/0 | GPJ Const. | 2025-07-10 | 2025-07-07 | -3 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 38/0 | 38/9 | Indrajeet | 2025-06-10 | 2025-07-07 | 27 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 40/10 | 41/0 | Indrajeet/Rahim | 2025-07-05 | 2025-07-24 | 19 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 63/0 | 64/0 | GPJ Const. | 2025-07-28 | 2025-07-31 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 39/0 | 40/0 | Amir Sheikh | 2025-08-06 | 2025-08-09 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 40/5 | 40/10 | Indrajeet/Rahim | 2025-07-20 | 2025-08-10 | 21 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 38/9 | 39/0 | Indrajeet/Mohan/Amir Sheikh | 2025-07-11 | 2025-08-19 | 39 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 40/0 | 40/2 | Rahim Khan | 2025-08-01 | 2025-08-23 | 22 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 40/2 | 40/5 | Rahim Khan | 2025-08-14 | 2025-08-23 | 9 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 66/0 | 67/0 | MC Const. | 2025-09-10 | 2025-09-13 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 35/0 | 36/0 | Amir Sheikh | 2025-09-14 | 2025-09-18 | 4 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 46/0 | 47/0 | Indrajeet | 2025-06-27 | 2025-10-04 | 99 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 31/0 | 32/0 | Krishna Const. | 2025-09-24 | 2025-10-07 | 13 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 44/0 | 45/0 | Indrajeet | 2025-06-18 | 2025-10-12 | 116 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | Gantry | 1/0 | Devi Power | 2025-10-17 | 2025-10-09 | -8 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 65/0 | 66/0 | MC Const. | 2025-10-06 | 2025-10-13 | 7 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 1/0 | 1A/0 | Devi Power | 2025-10-06 | 2025-10-12 | 6 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 1A/0 | 2/0 | Devi Power | 2025-10-17 | 2025-10-23 | 6 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 64/0 | 65/0 | MC Const. | 2025-10-18 | 2025-10-23 | 5 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 32/0 | 33/0 | Krishna Const. | 2025-10-13 | 2025-10-23 | 10 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 33/0 | 34/0 | Krishna Const. | 2025-10-27 | 2025-10-23 | -4 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 36/0 | 37/0 | Telegance Power | 2025-11-08 | 2025-10-30 | -9 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 60/0 | 61/0 | Indrajeet | 2025-11-11 | 2025-11-10 | -1 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 34/0 | 34/5 | Krishna Const. | 2025-11-06 | 2025-11-14 | 8 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 34/5 | 35/0 | Krishna Const. | 2025-11-13 | 2025-11-14 | 1 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 45/0 | 46/0 | Gopal Ji | 2025-11-26 | 2025-11-14 | -12 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 37/0 | 37/1 | Indrajeet | 2025-11-30 | 2025-11-29 | -1 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 37/1 | 37/2 | Indrajeet | 2025-11-30 | 2025-11-29 | -1 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 25/0 | 26/0 | Krishna Const. -2 | 2025-11-24 | 2025-11-29 | 5 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 2/0 | 3/0 | Devi Power | 2025-11-05 | 2025-11-30 | 25 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 30/0 | 31/0 | Krishna Const. | 2025-11-24 | 2025-11-30 | 6 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 5/0 | 6/0 | Kunal Kumar | 2025-12-11 | 2025-12-05 | -6 | TRUE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 4/0 | 5/0 | Devi Power | 2025-12-08 | 2025-12-09 | 1 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 15/0 | 16/0 | Nasir | 2025-12-10 | 2025-12-11 | 1 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 29/0 | 30/0 | Krishna Const. | 2025-12-08 | 2025-12-11 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 16/0 | 17/0 | Nasir | 2025-12-17 | 2025-12-20 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 24/0 | 25/0 | Krishna Const. -2 | 2025-12-08 | 2025-12-13 | 5 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 6/0 | 7/0 | Devi Power | 2025-12-18 |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 28/0 | 29/0 | Krishna Const. | 2025-12-21 | 2025-12-23 | 2 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 23/0 | 24/0 | Krishna Const. -2 | 2025-12-22 | 2025-12-25 | 3 | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 27/1 | 28/0 | Krishna Const. |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 9/0 | 10/0 | Gopal Ji |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 17/0 | 18/0 | Nasir |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 10/12 | 10/20 | Deepak |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 70/0 | 71/0 | GPJ Const. |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 14/0 | 15/0 | Nasir |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 3/0 | 4/0 | Gopal Ji |  | 2025-12-23 |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 401 | 22/0 | 23/0 | Krishna Const. -2 |  |  |  | FALSE | TB 401 - DPR - 2025-12-26.xlsx
TB 408 | 60/0 | 61/0 | Kuddus ali | 2024-08-28 | 2024-09-09 | 12 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 61/0 | 62/0 | Kuddus ali | 2024-09-16 | 2024-09-26 | 10 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 62/0 | 63/0 | Kuddus ali | 2024-10-02 | 2024-10-17 | 15 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 63/0 | 64/0 | Kuddus ali | 2024-10-21 | 2024-10-31 | 10 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 64/0 | 65/0 | Kuddus ali | 2024-11-05 | 2024-11-13 | 8 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 59/8 | 60/0 | Gopal Associate | 2024-12-27 | 2025-01-04 | 8 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 59/0 | 59/8 | Gopal Associate | 2025-01-08 | 2025-01-12 | 4 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 65/0 | 66/0 | MR Power | 2025-03-22 | 2025-03-10 | -12 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 50/0 | 51/0 | Gopal Associate | 2025-03-23 | 2025-03-17 | -6 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 49/0 | 50/0 | Gopal Associate | 2025-02-19 | 2025-05-01 | 71 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 51/0 | 52/0 | Gopal Associate | 2025-04-08 | 2025-04-04 | -4 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 73/0 | 74/0 | JPJ Construction/MC Power | 2025-06-21 | 2025-09-26 | 97 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 72/0 | 73/0 | JPJ Construction/MC Power | 2025-11-08 | 2025-11-21 | 13 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 2/0 | 3/0 | Devi Power | 2025-11-18 | 2025-12-30 | 42 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 71/0 | 72/0 | MC Power | 2025-11-25 | 2025-11-28 | 3 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 1A/0 | 2/0 | Devi Power | 2025-11-28 | 2025-11-28 | 0 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 70/0 | 71/0 | MC Power | 2025-12-16 | 2025-12-12 | -4 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 56/0 | 57/0 | Gopal Associate, Hotline | 2025-11-26 | 2025-11-20 | -6 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 46/0 | 47/0 | Gopal Associate, Hotline | 2025-12-11 | 2025-12-06 | -5 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 69/0 | 70/0 | MC Power | 2025-12-24 | 2025-12-21 | -3 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 67/0 | 68/0 | MC Power | 2025-12-28 | 2026-01-06 | 9 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 68/0 | 69/0 | MC Power | 2025-12-29 | 2025-12-29 | 0 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 66/0 | 67/0 | MC Power | 2026-01-03 | 2026-01-03 | 0 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 3/0 | 4/0 | Gopal Associate, Hotline | 2026-01-16 | 2026-01-11 | -5 | TRUE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 57/0 | 58/0 | MC Power |  |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 10/12 | 11/0 | Deepak | 2026-01-22 |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 47/0 | 48/0 | Krishna-1 |  |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 55/0 | 56/0 | MC Power |  |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | 48/0 | 49/0 | Krishna-1 | 2026-01-20 | 2026-01-20 | 0 | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | nan | nan | nan |  |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 408 | nan | nan | nan |  |  |  | FALSE | TB 408 - DPR - 2026-01-23.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 501 | nan | nan | nan |  |  |  | FALSE | TB 501 - DPR - 2026-01-08.xlsx
TB 507 | 149A/0 | 149/0 | nan |  |  |  | FALSE | TB 507 - DPR - 2026-01-27.xlsx
TB 507 | 149/0 | 148/0 | Mahadev Enterprises |  |  |  | FALSE | TB 507 - DPR - 2026-01-27.xlsx
TB 507 | 148/0 | 147/0 | nan |  |  |  | FALSE | TB 507 - DPR - 2026-01-27.xlsx
TB 507 | nan | Total | nan |  |  |  | FALSE | TB 507 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx
TB 605 | nan | nan | nan |  |  |  | FALSE | TB 605 - DPR - 2026-01-27.xlsx

## PO_FS_Gap_Summary
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
397 | 7.09 | 2 | 0 | 116

## Erection_PO_Gap
project_name | from_ap | to_ap | gang_name | po_start_date | source_file | last_erection_completion_date | gap_days | erection_locations
TA 325 | 112/0 | 113/0 | Muslehuddin | 2024-08-12 | TA 325 - DPR - 2026-01-19.xlsx | 2024-07-25 | 18 | 2
TA 325 | 111/0 | 112/0 | Gokul Sarkar | 2024-09-23 | TA 325 - DPR - 2026-01-19.xlsx | 2024-09-21 | 2 | 2
TA 325 | 110/0 | 111/0 | Gokul Sarkar | 2024-09-11 | TA 325 - DPR - 2026-01-19.xlsx | 2024-09-21 | 0 | 2
TA 325 | 113/0 | 114/0 | Muslehuddin | 2024-09-26 | TA 325 - DPR - 2026-01-19.xlsx | 2024-09-13 | 13 | 2
TA 325 | 109/0 | 110/0 | Gokul Sarkar | 2024-09-06 | TA 325 - DPR - 2026-01-19.xlsx | 2024-08-31 | 6 | 2
TA 325 | 116/0 | 116A/0 | Gokul Sarkar | 2024-10-15 | TA 325 - DPR - 2026-01-19.xlsx | 2024-09-27 | 18 | 2
TA 325 | 108/0 | 109/0 | Muslehuddin | 2024-10-17 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-13 | 4 | 2
TA 325 | 107/0 | 108/0 | Muslehuddin | 2024-10-30 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-13 | 17 | 3
TA 325 | 133/0 | 133A/0 | Rejaul | 2024-10-29 | TA 325 - DPR - 2026-01-19.xlsx | 2024-04-24 | 188 | 7
TA 325 | 121/0 | 122/0 | Gokul Sarkar | 2024-11-02 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-15 | 18 | 2
TA 325 | 129A/0 | 130/0 | Rejaul | 2024-11-16 | TA 325 - DPR - 2026-01-19.xlsx | 2024-05-18 | 182 | 4
TA 325 | 106B/0 | 107/0 | Muslehuddin | 2024-11-15 | TA 325 - DPR - 2026-01-19.xlsx | 2024-08-24 | 83 | 4
TA 325 | 122/0 | 123/0 | Dhervendra Electricals | 2024-11-23 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-15 | 39 | 2
TA 325 | 118/0 | 119/0 | Enamul Haque | 2024-11-23 | TA 325 - DPR - 2026-01-19.xlsx | 2024-09-24 | 60 | 2
TA 325 | 117/0 | 118/0 | Enamul Haque | 2024-12-08 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-03 | 5 | 2
TA 325 | 119/0 | 120/0 | Muslehuddin | 2024-12-19 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-24 | 56 | 5
TA 325 | 116B/0 | 117/0 | Yakub Ali + Enamul | 2024-11-17 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-03 | 0 | 2
TA 325 | 144/0 | 144A/0 | Gokul Sarkar | 2024-12-16 | TA 325 - DPR - 2026-01-19.xlsx | 2024-11-24 | 22 | 7
TA 325 | 120/0 | 121/0 | Dhervendra Electricals | 2024-12-28 | TA 325 - DPR - 2026-01-19.xlsx | 2024-10-24 | 65 | 2
TA 325 | 114/0 | 115/0 | Muslehuddin | 2024-12-26 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-20 | 6 | 2
TA 325 | 115/0 | 116/0 | Muslehuddin | 2024-12-26 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-20 | 6 | 2
TA 325 | 133A/0 | 134/0 | Rejaul + Rafikul | 2024-12-27 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-20 | 7 | 6
TA 325 | 123/0 | 124/0 | Enamul Haque | 2024-12-29 | TA 325 - DPR - 2026-01-19.xlsx | 2024-11-11 | 48 | 3
TA 325 | 116A/0 | 116B/0 | Muslehuddin | 2025-01-09 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-21 | 19 | 3
TA 325 | 144A/0 | 145/0 | Dhervendra Electricals | 2024-01-08 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-08 | 0 | 2
TA 325 | 147/1 | 147/2 | Gokul Sarkar | 2025-01-15 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-23 | 23 | 2
TA 325 | 127/0 | 128/0 | Muslehuddin + Enamul | 2024-12-11 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-07 | 4 | 7
TA 325 | 126/0 | 127/0 | Enamul Haque | 2025-01-09 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-27 | 13 | 3
TA 325 | 132/0 | 133/0 | Rejaul + enamul | 2025-01-12 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-30 | 13 | 5
TA 325 | 259/0 | 260/0 | Dharmendra Electrical | 2025-01-23 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-23 | 31 | 2
TA 325 | 260/0 | 261/0 | Monera | 2025-01-23 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-28 | 26 | 2
TA 325 | 125A/0 | 126/0 | Enamul Haque | 2025-01-16 | TA 325 - DPR - 2026-01-19.xlsx | 2024-11-13 | 64 | 2
TA 325 | 106A/0 | 106B/0 | Muslehuddin | 2025-01-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-03 | 25 | 6
TA 325 | 125/0 | 125A/0 | Enamul Haque | 2025-01-31 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-05 | 26 | 2
TA 325 | 128/0 | 129/0 | Alam Construction | 2025-02-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-18 | 23 | 2
TA 325 | 129/0 | 129A/0 | Alam Construction | 2025-02-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-18 | 23 | 2
TA 325 | 135A/0 | 135A/1 | SK Zenarul | 2025-01-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-04 | 16 | 2
TA 325 | 135A/2 | 135B/0 | Rafikul Alam construction + Enamul | 2025-02-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-18 | 17 | 7
TA 325 | 135B/0 | 136/0 | Rafikul Alam construction + Enamul | 2025-01-25 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-25 | 0 | 9
TA 325 | 106/0 | 106A/0 | Muslehuddin | 2025-02-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-03 | 30 | 2
TA 325 | 164/0 | 165/0 | Manik Sarkar | 2025-02-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-20 | 18 | 9
TA 325 | 135A/1 | 135A/2 | SK Zenarul | 2025-01-29 | TA 325 - DPR - 2026-01-19.xlsx | 2024-11-13 | 77 | 2
TA 325 | 124/0 | 124A/0 | Enamul Haque | 2025-02-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-05 | 36 | 2
TA 325 | 124A/0 | 124A/1 | Enamul Haque | 2025-02-15 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-05 | 41 | 2
TA 325 | 124A/1 | 125/0 | Dhervendra Electricals | 2025-02-15 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-05 | 41 | 2
TA 325 | 257/0 | 259/0 | Monera | 2025-02-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-17 | 25 | 6
TA 325 | 137A/0 | 138/0 | Alam Construction | 2025-02-21 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-02 | 19 | 8
TA 325 | 138/0 | 139/0 | Enamul Haque | 2025-02-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-11 | 16 | 4
TA 325 | 261/0 | 262/0 | Dharmendra Electrical | 2025-03-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-11 | 19 | 2
TA 325 | 139/0 | 139A/0 | SK Zenarul | 2025-03-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-17 | 13 | 4
TA 325 | 130/0 | 131/0 | Muslehuddin | 2025-03-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-09 | 22 | 6
TA 325 | 131/0 | 132/0 | Dhervendra Electricals | 2025-03-06 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-05 | 29 | 2
TA 325 | 139A/0 | 140/0 | SK Zenarul | 2025-02-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-22 | 5 | 2
TA 325 | 262/0 | 263/0 | Monera | 2025-02-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-11 | 6 | 3
TA 325 | 263/0 | 264/0 | Dharmendra Electrical | 2025-03-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-13 | 57 | 2
TA 325 | 142/0 | 143/0 | Enamul + Alam Constrution | 2025-03-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-04 | 14 | 2
TA 325 | 143/0 | 143A/0 | Alam Construction | 2025-03-08 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-04 | 4 | 2
TA 325 | 255/0 | 257/0 | Kamruddin | 2025-02-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-27 | 16 | 6
TA 325 | 265/0 | 266/0 | Dharmendra Electrical | 2025-03-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-12 | 63 | 2
TA 325 | 134/0 | 135/0 | Dhervendra Electricals | 2025-03-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-22 | 55 | 2
TA 325 | 163/0 | 163/5 | Manik Sarkar | 2025-02-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-20 | 4 | 6
TA 325 | 163/5 | 163/6 | Dhervendra Electricals | 2025-03-21 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-20 | 29 | 2
TA 325 | 163/6 | 164/0 | Manik Sarkar | 2025-03-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-25 | 38 | 2
TA 325 | 264/0 | 265/0 | Monera | 2025-03-16 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-10 | 96 | 2
TA 325 | 143A/0 | 143A/2 | Alam Construction | 2025-03-19 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-17 | 2 | 3
TA 325 | 143A/2 | 143A/3 | Enamul Haque | 2025-03-23 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-17 | 6 | 2
TA 325 | 143A/3 | 144/0 | Enamul Haque | 2025-03-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-11 | 7 | 4
TA 325 | 266/0 | 266/1 | Dharmendra Electrical | 2025-03-23 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-29 | 53 | 2
TA 325 | 266/1 | 267/0 | Monera | 2025-03-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-12 | 38 | 3
TA 325 | 136/0 | 137/0 | Dhervendra Electricals | 2025-03-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-15 | 39 | 2
TA 325 | 137/0 | 137A/0 | Rafikul Alam construction | 2025-03-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-27 | 6 | 8
TA 325 | 145A/0 | 146/0 | Enamul Haque | 2025-04-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-28 | 5 | 5
TA 325 | 253/0 | 254/0 | Dharmendra Electrical | 2025-04-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-17 | 46 | 2
TA 325 | 254/0 | 255/0 | Monera | 2025-02-26 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-21 | 67 | 2
TA 325 | 267/0 | 267A/0 | Kamruddin Deepak Sarkar | 2025-04-01 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-18 | 14 | 2
TA 325 | 267A/0 | 268/0 | Kamruddin | 2025-03-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-18 | 9 | 5
TA 325 | 141/0 | 141/1 | Alam Construction | 2025-04-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-23 | 41 | 2
TA 325 | 141/1 | 141/2 | Dhervendra Electricals | 2025-04-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-19 | 45 | 2
TA 325 | 141/2 | 142/0 | Alam Construction | 2025-04-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-03 | 33 | 3
TA 325 | 146/0 | 147/0 | Enamul Haque | 2025-04-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-01 | 11 | 2
TA 325 | 147/0 | 147/1 | Dhervendra Electricals | 2025-04-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-01 | 10 | 2
TA 325 | 147B/0 | 148/0 | Muslehuddinn + GPJ | 2025-04-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-22 | 13 | 3
TA 325 | 152/0 | 152A/0 | Alongir | 2025-04-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-20 | 14 | 6
TA 325 | 270/0 | 270A/0 | Kamruddin & Deepak | 2025-04-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-28 | 15 | 9
TA 325 | 145/0 | 145A/0 | Dhervendra Electricals | 2025-04-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-28 | 21 | 2
TA 325 | 268/0 | 269/0 | Dharmendra Electrical | 2025-04-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-01 | 16 | 2
TA 325 | 269/0 | 270/0 | Kamruddin & Maidul rahman | 2025-04-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-01 | 4 | 4
TA 325 | 270A/0 | 271/0 | Alamgir | 2025-04-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-15 | 56 | 2
TA 325 | 271/0 | 272/0 | Kamruddin & Deepak | 2025-04-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-25 | 24 | 7
TA 325 | 148/0 | 149/0 | Muslehuddin | 2025-04-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-06 | 12 | 9
TA 325 | 149/0 | 150/0 | Enamul Haque | 2025-04-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-06 | 16 | 3
TA 325 | 162/0 | 163/0 | Manik Sarkar | 2025-04-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-09 | 29 | 2
TA 325 | 147A/0 | 147B/0 | Enamul Haque | 2025-04-30 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-22 | 39 | 2
TA 325 | 135/0 | 135A/0 | RafikulAlam Construction | 2025-03-21 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-22 | 0 | 9
TA 325 | 251/0 | 252/0 | Dharmendra Electrical | 2025-04-29 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-11 | 18 | 2
TA 325 | 161/0 | 162/0 | Dhervendra Electricals | 2025-04-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-09 | 50 | 2
TA 325 | 252/0 | 253/0 | Deepak Sarkar | 2025-04-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-11 | 6 | 2
TA 325 | 250/0 | 251/0 | Deepak Sarkar | 2025-05-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-12 | 22 | 3
TA 325 | 249/0 | 250/0 | Kamruddin | 2025-04-29 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-21 | 8 | 5
TA 325 | 150A/0 | 151/0 | Alam Construction | 2025-04-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-11 | 15 | 4
TA 325 | 151/0 | 152/0 | Dhervendra Electricals | 2025-05-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-27 | 45 | 2
TA 325 | 147/2 | 147A/0 | Rafikul Alam + Alam Const. + Enamul | 2025-05-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-18 | 87 | 6
TA 325 | 140/0 | 141/0 | Rafikul Alam + Alam Const. + Enamul + Manik sarkar | 2025-05-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-23 | 88 | 2
TA 325 | 150/0 | 150/1 | Dhervendra Electricals | 2025-05-23 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-06 | 47 | 2
TA 325 | 150/1 | 150A/0 | Alam Construction | 2025-05-06 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-11 | 25 | 4
TA 325 | 156/0 | 157/0 | Deepak Sarkar + Manik Sarkar | 2025-06-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-03-28 | 67 | 2
TA 325 | 272/0 | 272/5 | Kamruddin & Deepak Sarkar | 2025-03-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-02-06 | 34 | 6
TA 325 | 155/0 | 156/0 | Deepak Sarkar + Manik Sarkar | 2025-06-06 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-11 | 26 | 8
TA 325 | 152A/0 | 153/0 | Alam Construction | 2025-09-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-08-08 | 25 | 2
TA 325 | 158B/0 | 159/0 | Deepak Sarkar | 2025-09-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-10 | 249 | 4
TA 325 | 158A/0 | 158B/0 | Dharmendra 1 | 2025-10-07 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-30 | 281 | 2
TA 325 | 276/0 | Gty | Bhola | 2025-10-18 | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 325 | 158/0 | 158A/0 | Deepak Sarkar | 2025-10-09 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-25 | 167 | 4
TA 325 | 192/0 | 193/0 | Teklal Saw | 2025-10-15 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-28 | 170 | 2
TA 325 | 193/0 | 194/0 | Ramsingh Yadav | 2025-10-21 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-15 | 159 | 2
TA 325 | 194/0 | 195/0 | Enamul Haque | 2025-10-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-15 | 162 | 2
TA 325 | 191/0 | 191/2 | Alam Construction | 2025-10-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-08-26 | 57 | 3
TA 325 | 191/2 | 191/3 | Alam Construction | 2025-10-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-04 | 171 | 2
TA 325 | 191/3 | 191A/0 | Alam Construction | 2025-10-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-04 | 171 | 2
TA 325 | 191A/0 | 192/0 | Md Anwar | 2025-10-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-28 | 167 | 3
TA 325 | 204/0 | 205/0 | Dharmendra 2 | 2025-10-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-11 | 168 | 2
TA 325 | 195/0 | 195A/0 | Enamul Haque | 2025-10-19 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-18 | 154 | 7
TA 325 | 196/0 | 197/0 | Ramsingh Yadav | 2025-10-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-01-22 | 277 | 2
TA 325 | 275/0 | 276/0 | Dharmendra 1 | 2025-10-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-04 | 22 | 2
TA 325 | 195A/0 | 196/0 | Muslehuddin | 2025-10-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-18 | 147 | 5
TA 325 | 157/0 | 158/0 | Deepak Sarkar | 2025-11-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-21 | 14 | 5
TA 325 | 190/0 | 191/0 | Ramsingh Yadav | 2025-11-08 | TA 325 - DPR - 2026-01-19.xlsx | 2025-08-26 | 74 | 2
TA 325 | 176/0 | 177/0 | Sanjay Singh | 2025-11-06 | TA 325 - DPR - 2026-01-19.xlsx | 2025-07-04 | 125 | 2
TA 325 | 177/0 | 178/0 | Ruhul Amin / Alam Constr. | 2025-11-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-18 | 169 | 2
TA 325 | 178/0 | 179/0 | Giyash | 2025-11-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-22 | 195 | 2
TA 325 | 189/0 | 190/0 | Md Anwar | 2025-11-01 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-06 | 179 | 3
TA 325 | 248/0 | 249/0 | Kamaruddin | 2025-11-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-20 | 168 | 8
TA 325 | 197/0 | 198/0 | Muslehuddin | 2025-11-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-15 | 206 | 6
TA 325 | 224/0 | 225/0 | Dharmendra 2 | 2025-11-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-23 | 20 | 2
TA 325 | 241/0 | 242/0 | Singhvahini | 2025-11-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-18 | 25 | 2
TA 325 | 243/0 | 244/0 | Dharmendra 1 | 2025-11-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-19 | 24 | 2
TA 325 | 168/0 | 169/0 | Rafikul Alam constr. | 2025-11-05 | TA 325 - DPR - 2026-01-19.xlsx | 2025-06-08 | 150 | 4
TA 325 | 169/0 | 171/0 | Ramavat Electricals | 2025-11-08 | TA 325 - DPR - 2026-01-19.xlsx | 2025-06-08 | 153 | 2
TA 325 | 181/0 | 182/0 | Alam Construction | 2025-11-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-24 | 174 | 6
TA 325 | 242/0 | 243/0 | Enamul Haque | 2025-11-15 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-26 | 20 | 5
TA 325 | 179/0 | 180/0 | Sanjay Singh | 2025-11-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-03 | 197 | 2
TA 325 | 188/0 | 189/0 | Ramsingh Yadav | 2025-11-16 | TA 325 - DPR - 2026-01-19.xlsx | 2024-12-14 | 337 | 2
TA 325 | 198/0 | 199/0 | Muslehuddin | 2025-11-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-22 | 176 | 4
TA 325 | 244/0 | 244/1 | Bhola Prasad | 2025-11-09 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-16 | 24 | 2
TA 325 | 246/0 | 247/0 | Dharmendra 1 | 2025-11-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-16 | 35 | 2
TA 325 | 205/0 | 206/0 | Deepak Sarkar | 2025-11-21 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-19 | 33 | 4
TA 325 | 230/0 | 231/0 | Alam Construction / Enamul / Giyash / Alongir | 2025-11-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-09 | 15 | 2
TA 325 | 247/0 | 248/0 | Kamruddinn | 2025-11-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-24 | 21 | 6
TA 325 | 244/1 | 245/0 | Bhola Prasad | 2025-11-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-10 | 6 | 2
TA 325 | 231/0 | 232/0 | Giyash / Alongir | 2025-11-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-01 | 25 | 2
TA 325 | 233/0 | 234/0 | Singhvahini | 2025-11-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-17 | 40 | 2
TA 325 | 245/0 | 246/0 | Kamruddinn / Bhola prasad | 2025-11-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-10 | 10 | 3
TA 325 | 232/0 | 233/0 | Sanjay Singh | 2025-11-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-01 | 25 | 2
TA 325 | 234/0 | 235/0 | Dharmendra 2 | 2025-11-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-19 | 38 | 2
TA 325 | 180/0 | 181/0 | Ramavat Electricals -2 | 2025-11-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-05-03 | 201 | 2
TA 325 | 210/0 | 211/0 | Ramsingh Yadav | 2025-11-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-06 | 22 | 2
TA 325 | 222/1 | 223/0 | Ramsingh Yadav 2 | 2025-12-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-13 | 19 | 2
TA 325 | 209/0 | 210/0 | Deepak Sarkar | 2025-12-01 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-09 | 22 | 3
TA 325 | 235/0 | 236/0 | Singhvahini | 2025-12-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-19 | 45 | 2
TA 325 | 171/0 | 172/0 | Ramavat Electricals 1& 2 | 2025-11-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-28 | 213 | 2
TA 325 | 226/0 | 227/0 | Muslehuddin | 2025-12-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-09 | 25 | 2
TA 325 | 229/1 | 230/0 | Teklal Saw | 2025-11-29 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-14 | 15 | 6
TA 325 | 184/0 | 184/1 | Alam Construction | 2025-12-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-18 | 16 | 2
TA 325 | 184/1 | 185/0 | Alam Construction | 2025-12-04 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-18 | 16 | 2
TA 325 | 225/0 | 226/0 | Muslehuddin | 2025-11-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-09 | 19 | 3
TA 325 | 236/0 | 237/0 | Dharmendra 1 | 2025-12-03 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-03 | 30 | 2
TA 325 | 237/0 | 239/0 | Enamul Haque | 2025-11-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-30 | 0 | 8
TA 325 | 240/0 | 241/0 | Enamul Haque | 2025-12-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-13 | 24 | 2
TA 325 | 239/0 | 240/0 | Ramsingh Yadav | 2025-12-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-30 | 7 | 2
TA 325 | 165/0 | 165/4 | Rafikul Alam | 2025-11-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-01 | 0 | 5
TA 325 | 187/0 | 188/0 | Alam Construction | 2025-12-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-24 | 8 | 5
TA 325 | 274/0 | 275/0 | Bhola Prasad | 2025-10-23 | TA 325 - DPR - 2026-01-19.xlsx | 2025-09-14 | 39 | 2
TA 325 | 182/0 | 182A/0 | Ramavat Electricals 2 | 2025-12-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-02 | 9 | 2
TA 325 | 219/0 | 220/0 | Sanjay Singh | 2025-12-08 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-30 | 8 | 2
TA 325 | 211/0 | 211A/0 | Deepak Sarkar | 2025-12-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-28 | 12 | 4
TA 325 | 212/0 | 213/0 | Ramsingh Yadav 2 | 2025-12-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-01 | 9 | 2
TA 325 | 229/0 | 229/1 | Alongir | 2025-12-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-11 | 26 | 2
TA 325 | 160/0 | 161/0 | Dharmendra 2 | 2025-12-13 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-07 | 6 | 2
TA 325 | 167/1 | 168/0 | Rafikul Alam Construction | 2025-11-19 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-05 | 0 | 5
TA 325 | 223/0 | 224/0 | Muslehuddin and Giyash | 2025-12-09 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-03 | 6 | 5
TA 325 | 218/0 | 219/0 | Singhvahini | 2025-12-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-30 | 12 | 3
TA 325 | 182A/0 | 183/0 | Alam Construction | 2025-12-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-04 | 10 | 2
TA 325 | 183/0 | 184/0 | Ramavat Electricals 1 | 2025-12-15 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-04 | 11 | 2
TA 325 | 213/0 | 214/0 | Kudus Ali | 2025-12-12 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-28 | 14 | 3
TA 325 | 203/1 | 204/0 | Modia India | 2025-12-13 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-18 | 25 | 2
TA 325 | 220/0 | 221/0 | Abdul Adut | 2025-12-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-30 | 14 | 3
TA 325 | 272/5 | 272A/0 | Bhola Prasad & Kamruddin | 2025-12-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-04-26 | 235 | 4
TA 325 | 199/0 | 200/0 | Ramsingh Yadav | 2025-12-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-06 | 14 | 2
TA 325 | 200/0 | 201/0 | Ramsingh Yadav 2 | 2025-12-20 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-06 | 14 | 2
TA 325 | 227/0 | 228/0 | Munni Bibi 2 | 2025-12-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-05 | 9 | 2
TA 325 | 228/0 | 229/0 | Sanjay Singh | 2025-12-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-05 | 12 | 2
TA 325 | 217A/0 | 218/0 | Teklal Saw | 2025-12-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-25 | 22 | 4
TA 325 | 105/0 | 106/0 | Kudus Ali 2 | 2025-12-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-09-23 | 92 | 2
TA 325 | 165/4 | 165/5 | Munni Bibi 1 | 2025-12-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-07 | 7 | 2
TA 325 | 165/5 | 166/0 | Munni Bibi 1 | 2025-12-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-07 | 7 | 2
TA 325 | 201/0 | 201/1 | Modina India 2 | 2025-12-23 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-02 | 21 | 2
TA 325 | 272A/0 | 273/0 | Kamaruddin | 2025-12-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-23 | 60 | 9
TA 325 | 273/0 | 274/0 | Kamaruddin | 2025-12-08 | TA 325 - DPR - 2026-01-19.xlsx | 2025-10-23 | 46 | 4
TA 325 | 211A/0 | 212/0 | Deepak Sarkar | 2025-12-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-01 | 9 | 4
TA 325 | 175/0 | 175/1 | Dharmendra 2 | 2025-12-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-29 | 23 | 2
TA 325 | 175/1 | 176/0 | Alam Construction | 2025-12-22 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-29 | 23 | 3
TA 325 | 167/0 | 167/1 | Rafikul Alam | 2025-12-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-13 | 13 | 2
TA 325 | 208/0 | 209/0 | Deepak Sarkar | 2025-12-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-05 | 13 | 2
TA 325 | 214/0 | 215/0 | Kudus Ali | 2025-12-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-28 | 26 | 3
TA 325 | 217/0 | 217A/0 | Ramsingh Yadav 1&2 | 2025-12-29 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-25 | 4 | 2
TA 325 | 221/0 | 222/0 | Sanjay Singh | 2025-12-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-12 | 15 | 2
TA 325 | 222/0 | 222/1 | Muslehuddin and Giyash | 2025-12-25 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-12 | 13 | 2
TA 325 | 172/0 | 173/0 | Alam Construction | 2025-12-27 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-19 | 8 | 4
TA 325 | 201/1 | 202/0 | Modina India 2 | 2025-12-29 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-02 | 27 | 1
TA 325 | 202/0 | 203/0 | Teklal Saw / Muslehuddin | 2025-12-29 | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 325 | 203/0 | 203/1 | Modia India | 2025-12-26 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-18 | 38 | 1
TA 325 | 154/1 | 155/0 | Munni Bibi 2 | 2025-12-28 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-07 | 21 | 2
TA 325 | 159/0 | 159/2 | Enamul Haque | 2025-12-31 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-21 | 10 | 3
TA 325 | 173/0 | 174/0 | Dharmendra 2 | 2025-12-31 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-24 | 7 | 2
TA 325 | 174/0 | 174/1 | Alam Construction | 2025-12-31 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-24 | 7 | 2
TA 325 | 174/1 | 175/0 | Alam Construction | 2026-01-02 | TA 325 - DPR - 2026-01-19.xlsx | 2025-06-13 | 203 | 2
TA 325 | 159/2 | 160/0 | Enamul Haque | 2025-12-24 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-21 | 3 | 4
TA 325 | 206/0 | 208/0 | Ramavat Electricals 2 | 2025-12-18 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-05 | 13 | 2
TA 325 | 216/0 | 217/0 | Ramavat Electricals 1 | 2026-01-01 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-25 | 7 | 2
TA 325 | 185/0 | 186/0 | Alam Construction | 2026-01-07 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-30 | 8 | 3
TA 325 | 186/0 | 187/0 | Dharmendra 2 | 2026-01-10 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-30 | 11 | 2
TA 325 | 215/0 | 215/1 | Ramavat Electricals 1&2 | 2025-01-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-11-24 | 0 | 2
TA 325 | 215/1 | 216/0 | Kudus Ali | 2025-01-11 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-25 | 0 | 2
TA 325 | 166/0 | 167/0 | Muni bibi / Enamul / Alam / Rafikul | 2026-01-16 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-13 | 34 | 2
TA 325 | 101/0 | 102/0 | Kudus Ali 2 | 2026-01-14 | TA 325 - DPR - 2026-01-19.xlsx | 2025-12-27 | 18 | 2
TA 325 | 102/0 | 103/0 | Modina India 1 | 2026-01-15 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-10 | 5 | 2
TA 325 | 103/0 | 104/0 | Muslehuddin | 2026-01-15 | TA 325 - DPR - 2026-01-19.xlsx | 2026-01-10 | 5 | 2
TA 325 | 104/0 | 105/0 | Dharmendra 2 | 2026-01-17 | TA 325 - DPR - 2026-01-19.xlsx | 2025-09-23 | 116 | 2
TA 325 | 153/0 | 154/0 | Modina india 2 |  | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 325 | 154/0 | 154/1 | Deepak Sarkar |  | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 325 | nan | nan | nan |  | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 325 | nan | Total | nan |  | TA 325 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 34/0 | 35/0 | SK Infratech | 2025-02-21 | TA 413 - DPR - 2026-01-19.xlsx | 2025-02-23 | 0 | 14
TA 413 | 37A/0 | 38/0 | SK Infratech | 2025-03-17 | TA 413 - DPR - 2026-01-19.xlsx | 2025-04-11 | 0 | 8
TA 413 | 38/0 | 39/0 | SK Infratech | 2025-03-29 | TA 413 - DPR - 2026-01-19.xlsx | 2025-04-11 | 0 | 12
TA 413 | 39/0 | 40/0 | SK Infratech | 2025-04-25 | TA 413 - DPR - 2026-01-19.xlsx | 2025-04-30 | 0 | 13
TA 413 | 7/0 | 7A/0 | Rahim Khan | 2025-08-27 | TA 413 - DPR - 2026-01-19.xlsx | 2025-07-31 | 27 | 8
TA 413 | 7A/0 | 8/0 | Rahim Khan | 2025-09-12 | TA 413 - DPR - 2026-01-19.xlsx | 2025-02-14 | 210 | 7
TA 413 | 8/0 | 8A/0 | Rahim Khan | 2025-10-05 | TA 413 - DPR - 2026-01-19.xlsx | 2025-08-14 | 52 | 13
TA 413 | 8A/0 | 9/0 | Rahim Khan | 2025-10-03 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-06 | 27 | 2
TA 413 | 6/0 | 7/0 | Rahim Khan | 2025-11-19 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-06 | 74 | 14
TA 413 | 5A/0 | 6/0 | Rahim Khan | 2025-11-05 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-01 | 65 | 2
TA 413 | 5/0 | 5A/0 | Rahim Khan | 2025-12-07 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-30 | 68 | 12
TA 413 | 4A/0 | 5/0 | Rahim Khan | 2025-12-15 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-30 | 76 | 8
TA 413 | 4/0 | 4A/0 | Rahim Khan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 3B/0 | 4/0 | Rahim Khan | 2026-01-14 | TA 413 - DPR - 2026-01-19.xlsx | 2025-11-07 | 68 | 5
TA 413 | 33/0 | 34/0 | SK Infratech | 2026-01-07 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-20 | 109 | 11
TA 413 | 32A/0 | 33/0 | SK Infratech | 2026-01-16 | TA 413 - DPR - 2026-01-19.xlsx | 2025-09-20 | 118 | 3
TA 413 | 3A/0 | 3B/0 | Rahim Khan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 32/0 | 32A/0 | SK Infratech |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 40/0 | 40A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | GY | 1/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 1/0 | 2A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 2A/0 | 3A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 9/0 | 10/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 10/0 | 11/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 11/0 | 12/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 12/0 | 13/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 13/0 | 13A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 13A/0 | 14/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 14/0 | 15/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 15/0 | 16/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 16/0 | 17/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 17/0 | 18/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 18/0 | 19/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 19/0 | 20/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 20/0 | 21/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 21/0 | 22/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 22/0 | 23/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 23/0 | 23A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 23A/0 | 24/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 24/0 | 25/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 25/0 | 26/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 26/0 | 27/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 27/0 | 28/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 28/0 | 29/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 29/0 | 29A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 29A/0 | 30/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 30/0 | 31/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 31/0 | 32/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 35/0 | 36/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 36/0 | 36A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 36A/0 | 37/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 37/0 | 37A/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 40A/0 | 41/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 41/0 | 42/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 42/0 | 42/3 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 42/3 | 43/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 43/0 | 43/5 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 43/5 | 44/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 44/0 | 45/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | 45/0 | 46/0 | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 413 | nan | nan | nan |  | TA 413 - DPR - 2026-01-19.xlsx |  |  | 0
TA 414 | nan | nan | nan |  | TA 414 - DPR - 2026-01-28.xlsx |  |  | 0
TA 414 | nan | nan | nan |  | TA 414 - DPR - 2026-01-28.xlsx |  |  | 0
TA 414 | nan | Total | nan |  | TA 414 - DPR - 2026-01-28.xlsx |  |  | 0
TA 416 | AP7/0 | AP8/0 | ANARUL ISLAM | 2025-05-03 | TA 416 - DPR - 2026-01-22.xlsx | 2025-03-27 | 37 | 13
TA 416 | AP6/0 | AP7/0 | ANARUL ISLAM | 2025-05-14 | TA 416 - DPR - 2026-01-22.xlsx | 2025-03-29 | 46 | 4
TA 416 | AP35/0 | AP36/0 | S K INFRA | 2025-05-18 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-14 | 34 | 11
TA 416 | AP8/0 | AP8A/0 | ANARUL ISLAM | 2025-05-24 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-30 | 24 | 6
TA 416 | AP31/0 | AP32/0 | S K INFRA | 2025-06-02 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-21 | 42 | 12
TA 416 | AP8A/0 | AP8B/0 | ANARUL ISLAM | 2025-06-17 | TA 416 - DPR - 2026-01-22.xlsx | 2025-05-14 | 34 | 2
TA 416 | AP32/0 | AP33/0 | S K INFRA | 2025-06-18 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-22 | 57 | 2
TA 416 | AP8B/0 | AP9/0 | ANARUL ISLAM | 2025-07-15 | TA 416 - DPR - 2026-01-22.xlsx | 2025-05-14 | 62 | 7
TA 416 | AP33/0 | AP34/0 | S K INFRA | 2025-07-17 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-10 | 37 | 13
TA 416 | AP5/0 | AP6/0 | ANARUL ISLAM | 2025-08-05 | TA 416 - DPR - 2026-01-22.xlsx | 2025-03-29 | 129 | 3
TA 416 | AP9/0 | AP10/0 | ANARUL ISLAM | 2025-08-11 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-28 | 105 | 2
TA 416 | AP34/0 | AP35/0 | S K INFRA | 2025-08-11 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-18 | 54 | 9
TA 416 | AP4/0 | AP5/0 | ANARUL ISLAM | 2025-08-22 | TA 416 - DPR - 2026-01-22.xlsx | 2025-05-11 | 103 | 12
TA 416 | AP14/0 | AP15/0 | ANARUL ISLAM | 2025-09-05 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-30 | 67 | 10
TA 416 | AP36/0 | AP37/0 | S K INFRA | 2025-09-05 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-31 | 0 | 14
TA 416 | AP3/0 | AP4/0 | ANARUL ISLAM | 2025-09-15 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-23 | 84 | 2
TA 416 | AP30/0 | AP31/0 | S K INFRA | 2025-09-21 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-21 | 92 | 8
TA 416 | AP20/0 | AP21/0 | J PG CON | 2025-09-21 | TA 416 - DPR - 2026-01-22.xlsx | 2025-04-22 | 152 | 14
TA 416 | AP12/0 | AP13/0 | ANARUL ISLAM | 2025-10-12 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-02 | 40 | 11
TA 416 | AP39/0 | AP40/0 | S K INFRA | 2025-10-14 | TA 416 - DPR - 2026-01-22.xlsx | 2025-06-30 | 106 | 12
TA 416 | AP21/0 | AP22/0 | J PG CON | 2025-10-24 | TA 416 - DPR - 2026-01-22.xlsx | 2025-07-07 | 109 | 5
TA 416 | AP13/0 | AP14/0 | ANARUL ISLAM | 2025-11-03 | TA 416 - DPR - 2026-01-22.xlsx | 2025-08-11 | 84 | 2
TA 416 | AP38/0 | AP39/0 | S K INFRA | 2025-11-02 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-26 | 7 | 13
TA 416 | AP19/0 | AP20/0 | J PG CON | 2025-11-06 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-24 | 43 | 14
TA 416 | AP17/0 | AP18/0 | ANARUL ISLAM | 2025-11-17 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-28 | 50 | 10
TA 416 | AP18/0 | AP19/0 | J PG CON | 2025-11-21 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-24 | 58 | 2
TA 416 | AP15/0 | AP16/0 | ANARUL ISLAM | 2025-11-22 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-14 | 69 | 2
TA 416 | AP10/0 | AP11/0 | ANARUL ISLAM | 2025-12-02 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-14 | 79 | 3
TA 416 | AP37/0 | AP38/0 | S K INFRA | 2025-12-05 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-31 | 35 | 2
TA 416 | AP11/0 | AP12/0 | ANARUL ISLAM | 2025-12-08 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-14 | 85 | 2
TA 416 | AP1/0 | AP2/0 | AE Solution | 2025-12-17 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-21 | 87 | 2
TA 416 | AP0/0 | AP1/0 | ANARUL ISLAM | 2025-12-21 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-28 | 54 | 6
TA 416 | AP24/0 | AP25/0 | AE Solution | 2025-12-24 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-29 | 86 | 2
TA 416 | AP23/0 | AP24/0 | Jahangir(Company) | 2025-12-26 | TA 416 - DPR - 2026-01-22.xlsx | 2025-12-14 | 12 | 7
TA 416 | AP40/0 | AP41/0 | Babloo Haque/Anarul-2 | 2025-12-24 | TA 416 - DPR - 2026-01-22.xlsx | 2025-08-08 | 138 | 2
TA 416 | AP41/0 | AP42/0 | ANARUL ISLAM (Company) | 2025-12-28 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-14 | 75 | 4
TA 416 | AP16/0 | AP17/0 | Ramawat-Hot line | 2025-12-31 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-28 | 94 | 2
TA 416 | AP2/0 | AP3/0 | ANARUL ISLAM | 2026-01-13 | TA 416 - DPR - 2026-01-22.xlsx | 2025-11-13 | 61 | 10
TA 416 | AP26/0 | AP27/0 | AE Solution(Company) | 2026-01-09 | TA 416 - DPR - 2026-01-22.xlsx | 2025-10-12 | 89 | 2
TA 416 | AP25/0 | AP26/0 | Bhola prasad(Company) | 2026-01-23 | TA 416 - DPR - 2026-01-22.xlsx | 2025-09-29 | 116 | 5
TA 416 | AP42/0 | AP43/0 | Babloo Haque/Anarul-2 |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | AP27/0 | AP28/0 | AE Solution(Company) |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | nan | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 416 | nan | Total | nan |  | TA 416 - DPR - 2026-01-22.xlsx |  |  | 0
TA 418 | 42/0 | 43/0 | SUFIYAN | 2025-09-25 | TA 418 - DPR - 2026-01-27.xlsx | 2025-04-10 | 168 | 4
TA 418 | 41/0 | 42/0 | SUFIYAN | 2025-10-03 | TA 418 - DPR - 2026-01-27.xlsx | 2025-08-06 | 58 | 7
TA 418 | 40/0 | 41/0 | SUFIYAN | 2025-12-20 | TA 418 - DPR - 2026-01-27.xlsx | 2025-07-21 | 152 | 7
TA 418 | 35/0 | 36/0 | SUFIYAN | 2025-11-07 | TA 418 - DPR - 2026-01-27.xlsx | 2025-08-17 | 82 | 13
TA 418 | 34/0 | 35/0 | SUFIYAN | 2025-11-26 | TA 418 - DPR - 2026-01-27.xlsx | 2025-05-28 | 182 | 6
TA 418 | 36/0 | 36/1 | SUFIYAN | 2025-11-01 | TA 418 - DPR - 2026-01-27.xlsx | 2025-08-19 | 74 | 2
TA 418 | 33/6 | 34/0 | SUFIYAN | 2026-01-18 | TA 418 - DPR - 2026-01-27.xlsx | 2025-06-24 | 208 | 8
TA 418 | 33/0 | 33/5 | Haque |  | TA 418 - DPR - 2026-01-27.xlsx |  |  | 0
TA 418 | 33/5 | 33/6 | Ramawat (HL) | 2026-01-19 | TA 418 - DPR - 2026-01-27.xlsx | 2025-06-24 | 209 | 2
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 419 | nan | nan | nan |  | TA 419 - DPR - 2026-01-26.xlsx |  |  | 0
TA 421 | 23/0 | 24/0 | M R Constructions | 2025-02-12 | TA 421 - DPR - 2026-01-22.xlsx | 2024-11-26 | 78 | 6
TA 421 | 24/0 | 25/0 | M R Constructions | 2025-02-24 | TA 421 - DPR - 2026-01-22.xlsx | 2024-12-11 | 75 | 10
TA 421 | 25/0 | 26/0 | M R Constructions | 2025-03-08 | TA 421 - DPR - 2026-01-22.xlsx | 2025-02-25 | 11 | 7
TA 421 | 26/0 | 27/0 | M R Constructions | 2025-03-23 | TA 421 - DPR - 2026-01-22.xlsx | 2024-11-30 | 113 | 6
TA 421 | 22/0 | 23/0 | M R Constructions | 2025-04-07 | TA 421 - DPR - 2026-01-22.xlsx | 2025-03-12 | 26 | 7
TA 421 | 29/0 | 29/9 | M R Constructions | 2025-05-05 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-18 | 0 | 10
TA 421 | 32/0 | 33/0 | M R Constructions | 2025-05-22 | TA 421 - DPR - 2026-01-22.xlsx | 2025-04-09 | 43 | 5
TA 421 | 31/0 | 32/0 | M R Constructions | 2025-06-12 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-06 | 6 | 8
TA 421 | 30/0 | 31/0 | M R Constructions | 2025-06-22 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-11 | 11 | 7
TA 421 | 29/9 | 30/0 | M R Constructions | 2025-07-06 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-18 | 18 | 2
TA 421 | 21/0 | 22/0 | M R Constructions | 2025-07-17 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-19 | 28 | 11
TA 421 | 20A/0 | 21/0 | M R Constructions | 2025-08-23 | TA 421 - DPR - 2026-01-22.xlsx | 2025-07-07 | 47 | 2
TA 421 | 20/0 | 20A/0 | M R Constructions | 2025-08-22 | TA 421 - DPR - 2026-01-22.xlsx | 2025-07-07 | 46 | 2
TA 421 | 12/0 | 13/0 | Nasiruddin | 2025-09-01 | TA 421 - DPR - 2026-01-22.xlsx | 2025-08-29 | 3 | 13
TA 421 | 10/0 | 11/0 | Nasiruddin | 2025-09-28 | TA 421 - DPR - 2026-01-22.xlsx | 2025-08-12 | 47 | 11
TA 421 | 19/0 | 20/0 | M R Constructions | 2025-09-15 | TA 421 - DPR - 2026-01-22.xlsx | 2025-05-22 | 116 | 5
TA 421 | 18/0 | 19/0 | M R Constructions | 2025-09-21 | TA 421 - DPR - 2026-01-22.xlsx | 2025-05-22 | 122 | 5
TA 421 | 9/0 | 10/0 | M R Constructions | 2025-10-16 | TA 421 - DPR - 2026-01-22.xlsx | 2025-10-12 | 4 | 12
TA 421 | 13/0 | 14/0 | Nasiruddin | 2025-11-13 | TA 421 - DPR - 2026-01-22.xlsx | 2025-07-13 | 123 | 13
TA 421 | 11/0 | 12/0 | Nasiruddin | 2025-12-03 | TA 421 - DPR - 2026-01-22.xlsx | 2025-11-19 | 14 | 13
TA 421 | 17/0 | 18/0 | M R Constructions | 2025-11-10 | TA 421 - DPR - 2026-01-22.xlsx | 2025-06-04 | 159 | 5
TA 421 | 14/0 | 15/0 | Nasiruddin | 2025-12-15 | TA 421 - DPR - 2026-01-22.xlsx | 2025-07-13 | 155 | 2
TA 421 | 16/0 | 17/0 | M R Constructions | 2025-11-27 | TA 421 - DPR - 2026-01-22.xlsx | 2025-11-23 | 4 | 13
TA 421 | 15/0 | 16/0 | M R Constructions | 2025-12-19 | TA 421 - DPR - 2026-01-22.xlsx | 2025-07-04 | 168 | 6
TA 421 | 8/4 | 9/0 | Nasiruddin | 2025-12-31 | TA 421 - DPR - 2026-01-22.xlsx | 2025-12-08 | 23 | 12
TA 421 | 6/0 | 7/0 | Nasiruddin | 2026-01-12 | TA 421 - DPR - 2026-01-22.xlsx | 2025-12-16 | 27 | 9
TA 421 | 27/0 | 27/3 | M R Constructions | 2026-12-09 | TA 421 - DPR - 2026-01-22.xlsx | 2025-12-10 | 364 | 4
TA 421 | 27/3 | 28/0 | M R Constructions | 2026-01-12 | TA 421 - DPR - 2026-01-22.xlsx | 2025-12-10 | 33 | 8
TA 421 | 8/3 | 8/4 | Ramavath Electricals | 2026-01-20 | TA 421 - DPR - 2026-01-22.xlsx | 2025-11-14 | 67 | 2
TA 421 | 4/12 | 5/0 | Nasiruddin |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | 7/0 | 8/0 | Nasiruddin |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | Gantry | 1/0 | Kamruddin |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | nan | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 421 | nan | Total | nan |  | TA 421 - DPR - 2026-01-22.xlsx |  |  | 0
TA 504 | 16/3 | 17/0 | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | 17/0 | 18/0 | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | 18/0 | 19/0 | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | nan | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 504 | nan | Total | nan |  | TA 504 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | 100/0 | 101/0 | Alimuddin | 2026-01-20 | TA 505 - DPR - 2026-01-27.xlsx | 2025-11-29 | 52 | 2
TA 505 | 101/0 | 102/0 | Alimuddin | 2026-01-27 | TA 505 - DPR - 2026-01-27.xlsx | 2025-10-26 | 93 | 10
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | nan | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 505 | nan | Total | nan |  | TA 505 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | 1/0 | 2/0 | National Construction | 2026-01-18 | TA 506 - DPR - 2026-01-27.xlsx | 2025-12-22 | 27 | 12
TA 506 | 5/0 | 6/0 | National Construction | 2026-01-25 | TA 506 - DPR - 2026-01-27.xlsx | 2025-10-07 | 110 | 5
TA 506 | 48/0 | 50/0 | Jahangir Alam | 2025-12-19 | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | 50/0 | 51/0 | Jahangir Alam | 2025-12-19 | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | 2/0 | 2A/0 | National Construction |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | 51/0 | 51A/0 | nan | 2026-01-17 | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | nan | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 506 | nan | Total | nan |  | TA 506 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TA 512 | nan | nan | nan |  | TA 512 - DPR - 2026-01-27.xlsx |  |  | 0
TB 401 | 57/6 | 58/0 | GPJ Const. | 2024-05-06 | TB 401 - DPR - 2025-12-26.xlsx | 2024-04-16 | 20 | 9
TB 401 | 57/0 | 57/6 | GPJ Const. | 2024-05-16 | TB 401 - DPR - 2025-12-26.xlsx | 2023-12-19 | 149 | 7
TB 401 | 56/0 | 57/0 | GPJ Const. | 2024-06-04 | TB 401 - DPR - 2025-12-26.xlsx | 2024-04-16 | 49 | 11
TB 401 | 55/0 | 56/0 | GPJ Const. | 2024-06-25 | TB 401 - DPR - 2025-12-26.xlsx | 2024-04-04 | 82 | 13
TB 401 | 53/0 | 55/0 | GPJ Const. | 2024-07-16 | TB 401 - DPR - 2025-12-26.xlsx | 2024-04-18 | 89 | 6
TB 401 | 52/0 | 53/0 | GPJ Const. | 2024-08-19 | TB 401 - DPR - 2025-12-26.xlsx | 2024-05-05 | 106 | 7
TB 401 | 51/0 | 52/0 | GPJ Const. | 2024-09-01 | TB 401 - DPR - 2025-12-26.xlsx | 2024-02-04 | 210 | 12
TB 401 | 50/0 | 51/0 | GPJ Const. | 2024-09-26 | TB 401 - DPR - 2025-12-26.xlsx | 2024-09-26 | 0 | 6
TB 401 | 72/7 | 73/0 | MR Power | 2024-11-12 | TB 401 - DPR - 2025-12-26.xlsx | 2024-10-17 | 26 | 2
TB 401 | 58/0 | 58/7 | Kddus Ali | 2024-11-20 | TB 401 - DPR - 2025-12-26.xlsx | 2024-05-10 | 194 | 8
TB 401 | 72/0 | 72/7 | MR Power | 2024-11-18 | TB 401 - DPR - 2025-12-26.xlsx | 2024-10-03 | 46 | 8
TB 401 | 67/1 | 68/0 | Nasruddin | 2024-12-22 | TB 401 - DPR - 2025-12-26.xlsx | 2024-11-29 | 23 | 2
TB 401 | 68/0 | 69/0 | Nasruddin | 2024-12-11 | TB 401 - DPR - 2025-12-26.xlsx | 2024-11-30 | 11 | 8
TB 401 | 58/7 | 59/0 | MR Power | 2024-12-27 | TB 401 - DPR - 2025-12-26.xlsx | 2024-12-19 | 8 | 11
TB 401 | 71/0 | 72/0 | MR Power | 2024-12-03 | TB 401 - DPR - 2025-12-26.xlsx | 2024-12-17 | 0 | 7
TB 401 | 67/0 | 67/1 | Nasruddin | 2024-12-21 | TB 401 - DPR - 2025-12-26.xlsx | 2024-12-08 | 13 | 2
TB 401 | 69/0 | 70/0 | Nasruddin | 2024-12-30 | TB 401 - DPR - 2025-12-26.xlsx | 2024-12-31 | 0 | 11
TB 401 | 41/0 | 42/0 | Nasruddin | 2025-02-13 | TB 401 - DPR - 2025-12-26.xlsx | 2025-01-29 | 15 | 14
TB 401 | 59/0 | 60/0 | MR Power | 2025-01-20 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-19 | 0 | 8
TB 401 | 42/0 | 43/0 | Indrajeet | 2025-05-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-18 | 75 | 2
TB 401 | 49/0 | 50/0 | Indrajeet | 2025-05-15 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-23 | 81 | 2
TB 401 | 48/0 | 49/0 | Indrajeet | 2025-05-14 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-23 | 80 | 4
TB 401 | 47/0 | 48/0 | Indrajeet | 2025-05-19 | TB 401 - DPR - 2025-12-26.xlsx | 2024-09-12 | 249 | 5
TB 401 | 37/2 | 38/0 | Indrajeet | 2025-05-24 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-04 | 109 | 8
TB 401 | 43/0 | 44/0 | Indrajeet | 2025-05-05 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-28 | 66 | 8
TB 401 | 61/0 | 62/0 | GPJ Const. | 2025-06-27 | TB 401 - DPR - 2025-12-26.xlsx | 2025-05-09 | 49 | 4
TB 401 | 62/0 | 63/0 | GPJ Const. | 2025-07-07 | TB 401 - DPR - 2025-12-26.xlsx | 2025-05-19 | 49 | 2
TB 401 | 38/0 | 38/9 | Indrajeet | 2025-06-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-03-29 | 67 | 10
TB 401 | 40/10 | 41/0 | Indrajeet/Rahim | 2025-07-02 | TB 401 - DPR - 2025-12-26.xlsx | 2025-02-08 | 144 | 4
TB 401 | 63/0 | 64/0 | GPJ Const. | 2025-07-24 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-06 | 48 | 8
TB 401 | 39/0 | 40/0 | Amir Sheikh | 2025-07-30 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-03 | 27 | 9
TB 401 | 40/5 | 40/10 | Indrajeet/Rahim | 2025-07-11 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-18 | 23 | 6
TB 401 | 38/9 | 39/0 | Indrajeet/Mohan/Amir Sheikh | 2025-07-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-03-07 | 119 | 2
TB 401 | 40/0 | 40/2 | Rahim Khan | 2025-07-28 | TB 401 - DPR - 2025-12-26.xlsx | 2025-03-12 | 138 | 3
TB 401 | 40/2 | 40/5 | Rahim Khan | 2025-08-08 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-30 | 39 | 4
TB 401 | 66/0 | 67/0 | MC Const. | 2025-09-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-09 | 87 | 6
TB 401 | 35/0 | 36/0 | Amir Sheikh | 2025-09-07 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-06 | 63 | 11
TB 401 | 46/0 | 47/0 | Indrajeet | 2025-06-22 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-30 | 0 | 6
TB 401 | 31/0 | 32/0 | Krishna Const. | 2025-09-18 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-09 | 40 | 6
TB 401 | 44/0 | 45/0 | Indrajeet | 2025-06-13 | TB 401 - DPR - 2025-12-26.xlsx | 2025-05-23 | 21 | 7
TB 401 | Gantry | 1/0 | Devi Power | 2025-10-08 | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 65/0 | 66/0 | MC Const. | 2025-10-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-05 | 91 | 9
TB 401 | 1/0 | 1A/0 | Devi Power | 2025-10-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-31 | 65 | 2
TB 401 | 1A/0 | 2/0 | Devi Power | 2025-10-10 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-27 | 44 | 9
TB 401 | 64/0 | 65/0 | MC Const. | 2025-10-10 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-08 | 94 | 11
TB 401 | 32/0 | 33/0 | Krishna Const. | 2025-10-04 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-27 | 38 | 10
TB 401 | 33/0 | 34/0 | Krishna Const. | 2025-10-21 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-12 | 70 | 10
TB 401 | 36/0 | 37/0 | Telegance Power | 2025-10-30 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-30 | 122 | 2
TB 401 | 60/0 | 61/0 | Indrajeet | 2025-11-10 | TB 401 - DPR - 2025-12-26.xlsx | 2025-03-03 | 252 | 2
TB 401 | 34/0 | 34/5 | Krishna Const. | 2025-01-01 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-31 | 0 | 6
TB 401 | 34/5 | 35/0 | Krishna Const. | 2025-11-10 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-26 | 107 | 3
TB 401 | 45/0 | 46/0 | Gopal Ji | 2025-11-14 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-30 | 137 | 2
TB 401 | 37/0 | 37/1 | Indrajeet | 2025-11-29 | TB 401 - DPR - 2025-12-26.xlsx | 2025-06-30 | 152 | 2
TB 401 | 37/1 | 37/2 | Indrajeet | 2025-11-29 | TB 401 - DPR - 2025-12-26.xlsx | 2025-05-24 | 189 | 2
TB 401 | 25/0 | 26/0 | Krishna Const. -2 | 2025-11-13 | TB 401 - DPR - 2025-12-26.xlsx | 2025-11-05 | 8 | 13
TB 401 | 2/0 | 3/0 | Devi Power | 2025-10-30 | TB 401 - DPR - 2025-12-26.xlsx | 2025-11-22 | 0 | 10
TB 401 | 30/0 | 31/0 | Krishna Const. | 2025-11-19 | TB 401 - DPR - 2025-12-26.xlsx | 2025-11-11 | 8 | 5
TB 401 | 5/0 | 6/0 | Kunal Kumar | 2025-12-05 | TB 401 - DPR - 2025-12-26.xlsx | 2025-10-28 | 38 | 2
TB 401 | 4/0 | 5/0 | Devi Power | 2025-12-05 | TB 401 - DPR - 2025-12-26.xlsx | 2025-10-28 | 38 | 5
TB 401 | 15/0 | 16/0 | Nasir | 2025-12-03 | TB 401 - DPR - 2025-12-26.xlsx | 2025-07-19 | 137 | 11
TB 401 | 29/0 | 30/0 | Krishna Const. | 2025-12-01 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-09 | 114 | 12
TB 401 | 16/0 | 17/0 | Nasir | 2025-12-14 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-18 | 118 | 8
TB 401 | 24/0 | 25/0 | Krishna Const. -2 | 2025-12-01 | TB 401 - DPR - 2025-12-26.xlsx | 2025-11-05 | 26 | 8
TB 401 | 6/0 | 7/0 | Devi Power | 2025-12-17 | TB 401 - DPR - 2025-12-26.xlsx | 2025-10-21 | 57 | 4
TB 401 | 28/0 | 29/0 | Krishna Const. | 2025-12-15 | TB 401 - DPR - 2025-12-26.xlsx | 2025-10-09 | 67 | 11
TB 401 | 23/0 | 24/0 | Krishna Const. -2 | 2025-12-12 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-31 | 103 | 13
TB 401 | 27/1 | 28/0 | Krishna Const. | 2025-12-24 | TB 401 - DPR - 2025-12-26.xlsx | 2025-08-26 | 120 | 6
TB 401 | 9/0 | 10/0 | Gopal Ji |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 17/0 | 18/0 | Nasir |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 10/12 | 10/20 | Deepak |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 70/0 | 71/0 | GPJ Const. |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 14/0 | 15/0 | Nasir |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 401 | 3/0 | 4/0 | Gopal Ji | 2025-12-23 | TB 401 - DPR - 2025-12-26.xlsx | 2025-11-22 | 31 | 2
TB 401 | 22/0 | 23/0 | Krishna Const. -2 |  | TB 401 - DPR - 2025-12-26.xlsx |  |  | 0
TB 408 | 60/0 | 61/0 | Kuddus ali | 2024-08-21 | TB 408 - DPR - 2026-01-23.xlsx | 2024-05-18 | 95 | 13
TB 408 | 61/0 | 62/0 | Kuddus ali | 2024-09-06 | TB 408 - DPR - 2026-01-23.xlsx | 2024-09-08 | 0 | 12
TB 408 | 62/0 | 63/0 | Kuddus ali | 2024-09-23 | TB 408 - DPR - 2026-01-23.xlsx | 2024-09-08 | 15 | 13
TB 408 | 63/0 | 64/0 | Kuddus ali | 2024-10-14 | TB 408 - DPR - 2026-01-23.xlsx | 2024-05-12 | 155 | 10
TB 408 | 64/0 | 65/0 | Kuddus ali | 2024-10-30 | TB 408 - DPR - 2026-01-23.xlsx | 2024-10-24 | 6 | 13
TB 408 | 59/8 | 60/0 | Gopal Associate | 2024-12-22 | TB 408 - DPR - 2026-01-23.xlsx | 2024-10-26 | 57 | 10
TB 408 | 59/0 | 59/8 | Gopal Associate | 2025-01-02 | TB 408 - DPR - 2026-01-23.xlsx | 2024-12-16 | 17 | 9
TB 408 | 65/0 | 66/0 | MR Power | 2025-02-03 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-06 | 0 | 13
TB 408 | 50/0 | 51/0 | Gopal Associate | 2025-03-12 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-20 | 20 | 12
TB 408 | 49/0 | 50/0 | Gopal Associate | 2025-02-06 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-14 | 0 | 9
TB 408 | 51/0 | 52/0 | Gopal Associate | 2025-04-02 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-14 | 47 | 4
TB 408 | 73/0 | 74/0 | JPJ Construction/MC Power | 2025-06-01 | TB 408 - DPR - 2026-01-23.xlsx | 2025-01-19 | 133 | 11
TB 408 | 72/0 | 73/0 | JPJ Construction/MC Power | 2025-11-03 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-06 | 270 | 5
TB 408 | 2/0 | 3/0 | Devi Power | 2025-11-13 | TB 408 - DPR - 2026-01-23.xlsx | 2025-11-10 | 3 | 11
TB 408 | 71/0 | 72/0 | MC Power | 2025-11-20 | TB 408 - DPR - 2026-01-23.xlsx | 2025-03-25 | 240 | 10
TB 408 | 1A/0 | 2/0 | Devi Power | 2025-11-21 | TB 408 - DPR - 2026-01-23.xlsx | 2025-08-13 | 100 | 10
TB 408 | 70/0 | 71/0 | MC Power | 2025-12-08 | TB 408 - DPR - 2026-01-23.xlsx | 2025-07-14 | 147 | 13
TB 408 | 56/0 | 57/0 | Gopal Associate, Hotline | 2025-11-20 | TB 408 - DPR - 2026-01-23.xlsx | 2025-09-29 | 52 | 2
TB 408 | 46/0 | 47/0 | Gopal Associate, Hotline | 2025-12-06 | TB 408 - DPR - 2026-01-23.xlsx | 2025-10-18 | 49 | 2
TB 408 | 69/0 | 70/0 | MC Power | 2025-12-18 | TB 408 - DPR - 2026-01-23.xlsx | 2025-07-21 | 150 | 3
TB 408 | 67/0 | 68/0 | MC Power | 2025-12-26 | TB 408 - DPR - 2026-01-23.xlsx | 2025-05-29 | 211 | 4
TB 408 | 68/0 | 69/0 | MC Power | 2025-12-29 | TB 408 - DPR - 2026-01-23.xlsx | 2025-07-21 | 161 | 2
TB 408 | 66/0 | 67/0 | MC Power | 2026-01-03 | TB 408 - DPR - 2026-01-23.xlsx | 2025-05-29 | 219 | 2
TB 408 | 3/0 | 4/0 | Gopal Associate, Hotline | 2026-01-10 | TB 408 - DPR - 2026-01-23.xlsx | 2025-11-10 | 61 | 2
TB 408 | 57/0 | 58/0 | MC Power | 2026-01-19 | TB 408 - DPR - 2026-01-23.xlsx | 2025-09-29 | 112 | 9
TB 408 | 10/12 | 11/0 | Deepak | 2026-01-14 | TB 408 - DPR - 2026-01-23.xlsx | 2025-12-31 | 14 | 13
TB 408 | 47/0 | 48/0 | Krishna-1 |  | TB 408 - DPR - 2026-01-23.xlsx |  |  | 0
TB 408 | 55/0 | 56/0 | MC Power |  | TB 408 - DPR - 2026-01-23.xlsx |  |  | 0
TB 408 | 48/0 | 49/0 | Krishna-1 | 2026-01-17 | TB 408 - DPR - 2026-01-23.xlsx | 2025-02-14 | 337 | 3
TB 408 | nan | nan | nan |  | TB 408 - DPR - 2026-01-23.xlsx |  |  | 0
TB 408 | nan | nan | nan |  | TB 408 - DPR - 2026-01-23.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 501 | nan | nan | nan |  | TB 501 - DPR - 2026-01-08.xlsx |  |  | 0
TB 507 | 149A/0 | 149/0 | nan |  | TB 507 - DPR - 2026-01-27.xlsx |  |  | 0
TB 507 | 149/0 | 148/0 | Mahadev Enterprises |  | TB 507 - DPR - 2026-01-27.xlsx |  |  | 0
TB 507 | 148/0 | 147/0 | nan |  | TB 507 - DPR - 2026-01-27.xlsx |  |  | 0
TB 507 | nan | Total | nan |  | TB 507 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0
TB 605 | nan | nan | nan |  | TB 605 - DPR - 2026-01-27.xlsx |  |  | 0

## Erection_PO_Gap_Summary
count | avg_gap_days | median_gap_days | min_gap_days | max_gap_days
416 | 60.1 | 34 | 0 | 364

## Method_Summary
Method | Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
Manual | 0.9439 | 52.1021 | 115 | 47 | 4
Other | 1.4383 | 167.1782 | 134 | 36 | 4
TSE | 4.0006 | 360.1859 | 145 | 47 | 6

## Stringing Summary
Scope: to ¦ Projects: 8 ¦ Spans: 394 ¦ Gangs: 104
Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
2.2162 | 579.4662 | 394 | 104 | 8
Scope: to ¦ Projects: 8 ¦ Spans: 394 ¦ Gangs: 104
PCH | Avg Productivity (KM/month) | Total KM | Spans | Gangs | Projects
Mr Arun Felbin | 3.5797 | 77.2015 | 36 | 8 | 1
Mr. Arun Felbin | 1.5352 | 186.6323 | 230 | 69 | 2
Mr. Nabajit Baruah | 0.8153 | 1.848 | 2 | 1 | 1
Mr. Sanjay Gupta | 5.044 | 38.8391 | 12 | 2 | 1
Mr. Sanjay Kumar Gupta | 2.2137 | 204.6166 | 88 | 23 | 2
Mr.Arun Felbin | 4.4139 | 70.3287 | 26 | 2 | 1
Scope: to ¦ Projects: 8 ¦ Spans: 394 ¦ Gangs: 104
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans | Gangs
Mr Arun Felbin | TA 416 | 3.5797 | 77.2015 | 36 | 8
Mr. Arun Felbin | TA 325 | 1.5047 | 173.6873 | 224 | 68
Mr. Arun Felbin | TA 418 | 2.1106 | 12.945 | 6 | 1
Mr. Nabajit Baruah | TA 506 | 0.8153 | 1.848 | 2 | 1
Mr. Sanjay Gupta | TA 413 | 5.044 | 38.8391 | 12 | 2
Mr. Sanjay Kumar Gupta | TB401 | 1.8866 | 136.0892 | 63 | 17
Mr. Sanjay Kumar Gupta | TB408 | 3.3757 | 68.5274 | 25 | 8
Mr.Arun Felbin | TA 421 | 4.4139 | 70.3287 | 26 | 2

## Review_Format
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr Arun Felbin
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr Arun Felbin | TA 416 | 3.5797 | 77.2015 | 36
|  | Total | 77.2015 | 36
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr. Arun Felbin
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr. Arun Felbin | TA 325 | 1.5047 | 173.6873 | 224
Mr. Arun Felbin | TA 418 | 2.1106 | 12.945 | 6
|  | Total | 186.6323 | 230
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr. Nabajit Baruah
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr. Nabajit Baruah | TA 506 | 0.8153 | 1.848 | 2
|  | Total | 1.848 | 2
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr. Sanjay Gupta
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr. Sanjay Gupta | TA 413 | 5.044 | 38.8391 | 12
|  | Total | 38.8391 | 12
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr. Sanjay Kumar Gupta
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr. Sanjay Kumar Gupta | TB401 | 1.8866 | 136.0892 | 63
Mr. Sanjay Kumar Gupta | TB408 | 3.3757 | 68.5274 | 25
|  | Total | 204.6166 | 88
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
PCH: Mr.Arun Felbin
PCH | Project | Avg Productivity (KM/month) | Total KM | Spans
Mr.Arun Felbin | TA 421 | 4.4139 | 70.3287 | 26
|  | Total | 70.3287 | 26
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0.03 | 0.03 | 0.03 | 0.03 | 2.05 | 2.27 | 2.32 | 1.88 | 2.41 | 2.23 | 2.58 | 2.22 | 1.87 | 2.23 | 1.94 | 2.21 | 2.03 | 1.77 | 1.4 | 1.41 | 2.22 | 2.61 | 2.79 | 2.97 | 2.14
No of Gangs engaged (Avg) | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 4 | 5 | 6 | 9 | 11 | 17 | 17 | 21 | 26 | 19 | 12 | 14 | 14 | 17 | 26 | 44 | 51 | 23
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.08 | 2.63 | 2.79 | 5.28 | 4.19 | 5.73 | 4.31 | 2.02 | 1.02
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 6 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 416
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.08 | 2.63 | 2.79 | 5.28 | 4.19 | 5.73 | 4.31 | 2.02 | 1.02
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 6 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.31 | 0.29 | 0.61 | 1.56 | 1.81 | 1.49 | 2.11 | 1.64 | 2.1 | 1.4 | 1.09 | 0.03 | 0.03 | 0.56 | 1.12 | 2.03 | 2.22 | 1.63
No of Gangs engaged (Avg) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 4 | 6 | 7 | 13 | 11 | 15 | 20 | 11 | 4 | 2 | 2 | 5 | 14 | 28 | 33 | 13
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 325
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.31 | 0.29 | 0.61 | 1.56 | 1.81 | 1.49 | 2.11 | 1.64 | 2.1 | 1.4 | 1.09 | 0.03 | 0.03 | 0.49 | 1.12 | 2.01 | 2.15 | 1.56
No of Gangs engaged (Avg) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 4 | 6 | 7 | 13 | 11 | 15 | 20 | 11 | 4 | 2 | 2 | 4 | 13 | 27 | 32 | 12
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 418
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.58 | 1.11 | 2.1 | 2.86 | 5.2
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Nabajit Baruah
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81 | 0.82
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 506
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81 | 0.82
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.25 | 4.83 | 7.54 | 0 | 0 | 0 | 3.52 | 4.26 | 3.43 | 4.1 | 4.82 | 0
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 413
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.25 | 4.83 | 7.54 | 0 | 0 | 0 | 3.52 | 4.26 | 3.43 | 4.1 | 4.82 | 0
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Kumar Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 3.84 | 3.77 | 4.02 | 3.67 | 4.41 | 4.66 | 4.3 | 2.73 | 2.25 | 1.75 | 1.73 | 0.73 | 1.35 | 1.16 | 1.05 | 0.92 | 1.34 | 2.68 | 3.11 | 4.66 | 2.21
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 9 | 9 | 6 | 6 | 10 | 8 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB401
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 3.84 | 3.77 | 4.02 | 2.83 | 3.68 | 3.89 | 2.77 | 2.38 | 1.6 | 1.6 | 0.49 | 0.32 | 1.36 | 1.2 | 1.06 | 0.92 | 1.42 | 2.68 | 2.52 | 5.02 | 0
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 8 | 8 | 5 | 6 | 7 | 6 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB408
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.42 | 5.06 | 4.92 | 7.23 | 5.97 | 6.69 | 2.05 | 3.49 | 1.69 | 1.09 | 0.93 | 0.93 | 0.93 | 0.93 | 0 | 4.37 | 4.1 | 2.21
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 4 | 3 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr.Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.12 | 3.42 | 2.89 | 2.56 | 4.14 | 3.47 | 1.97 | 4.49 | 4.71 | 5.55 | 5.86 | 15.22
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 421
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.12 | 3.42 | 2.89 | 2.56 | 4.14 | 3.47 | 1.97 | 4.49 | 4.71 | 5.55 | 5.86 | 15.22
No of Gangs engaged (Avg) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.39 | 7.24 | 17.62 | 15.14 | 10.17 | 31.2 | 15.42 | 45.23 | 40.8 | 30.18 | 21.52 | 19.62 | 22.59 | 24.04 | 64.97 | 70.25 | 96.55 | 30.74
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 4 | 6 | 6 | 13 | 8 | 15 | 18 | 13 | 5 | 6 | 8 | 8 | 19 | 35 | 45 | 23
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.07 | 8.24 | 7.64 | 8.62 | 3.89 | 17.69 | 10.92 | 8.96 | 3.17
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 416
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.07 | 8.24 | 7.64 | 8.62 | 3.89 | 17.69 | 10.92 | 8.96 | 3.17
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 1.81 | 6.01 | 4.78 | 10.23 | 15.42 | 18.66 | 24.03 | 11.48 | 5.03 | 0 | 0 | 0.37 | 7.02 | 26.21 | 43.85 | 11.34
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 4 | 4 | 9 | 8 | 10 | 15 | 8 | 2 | 0 | 0 | 1 | 9 | 21 | 31 | 13
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 325
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 1.81 | 6.01 | 4.78 | 10.23 | 15.42 | 18.66 | 24.03 | 11.48 | 5.03 | 0 | 0 | 0.37 | 5.91 | 25.73 | 34.92 | 8.92
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 4 | 4 | 9 | 8 | 10 | 15 | 8 | 2 | 0 | 0 | 1 | 8 | 20 | 30 | 12
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 418
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0.48 | 8.93 | 2.43
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Nabajit Baruah
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 506
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 4.9 | 11.46 | 0 | 0 | 0 | 0 | 5.13 | 4.92 | 4.9 | 7.52 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 413
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 4.9 | 11.46 | 0 | 0 | 0 | 0 | 5.13 | 4.92 | 4.9 | 7.52 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Kumar Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.01 | 7.24 | 15.8 | 9.13 | 5.39 | 20.27 | 0 | 14.16 | 1.05 | 8.97 | 5.57 | 5.54 | 9.93 | 9.42 | 23.4 | 23.31 | 22.76 | 6.15
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 0 | 3 | 1 | 3 | 1 | 3 | 5 | 3 | 4 | 9 | 8 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB401
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.01 | 2.36 | 6.37 | 0.5 | 5.39 | 13.15 | 0 | 4.98 | 0 | 5.75 | 5.57 | 5.54 | 9.93 | 5.63 | 23.4 | 14.36 | 16.63 | 0
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 1 | 0 | 2 | 1 | 3 | 5 | 2 | 4 | 6 | 6 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB408
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.88 | 9.43 | 8.63 | 0 | 7.12 | 0 | 9.18 | 1.05 | 3.23 | 0 | 0 | 0 | 3.79 | 0 | 8.95 | 6.13 | 6.15
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 4 | 2 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr.Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.51 | 4.25 | 1.66 | 2.69 | 6.45 | 4.04 | 5.22 | 11.93 | 4.9 | 13.46 | 8.23
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 421
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.51 | 4.25 | 1.66 | 2.69 | 6.45 | 4.04 | 5.22 | 11.93 | 4.9 | 13.46 | 8.23
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1

## Monthly_Breakup
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Overall
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.39 | 7.24 | 17.62 | 15.14 | 10.17 | 31.2 | 15.42 | 45.23 | 40.8 | 30.18 | 21.52 | 19.62 | 22.59 | 24.04 | 64.97 | 70.25 | 96.55 | 30.74
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 4 | 6 | 6 | 13 | 8 | 15 | 18 | 13 | 5 | 6 | 8 | 8 | 19 | 35 | 45 | 23
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.07 | 8.24 | 7.64 | 8.62 | 3.89 | 17.69 | 10.92 | 8.96 | 3.17
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 414
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 416
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.07 | 8.24 | 7.64 | 8.62 | 3.89 | 17.69 | 10.92 | 8.96 | 3.17
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 3 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 1.81 | 6.01 | 4.78 | 10.23 | 15.42 | 18.66 | 24.03 | 11.48 | 5.03 | 0 | 0 | 0.37 | 7.02 | 26.21 | 43.85 | 11.34
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 4 | 4 | 9 | 8 | 10 | 15 | 8 | 2 | 0 | 0 | 1 | 9 | 21 | 31 | 13
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 325
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 1.81 | 6.01 | 4.78 | 10.23 | 15.42 | 18.66 | 24.03 | 11.48 | 5.03 | 0 | 0 | 0.37 | 5.91 | 25.73 | 34.92 | 8.92
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 4 | 4 | 9 | 8 | 10 | 15 | 8 | 2 | 0 | 0 | 1 | 8 | 20 | 30 | 12
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 418
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.11 | 0.48 | 8.93 | 2.43
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB501
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Nabajit Baruah
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 504
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 505
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 506
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.85
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 4.9 | 11.46 | 0 | 0 | 0 | 0 | 5.13 | 4.92 | 4.9 | 7.52 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 413
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 4.9 | 11.46 | 0 | 0 | 0 | 0 | 5.13 | 4.92 | 4.9 | 7.52 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA-419
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr. Sanjay Kumar Gupta
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.01 | 7.24 | 15.8 | 9.13 | 5.39 | 20.27 | 0 | 14.16 | 1.05 | 8.97 | 5.57 | 5.54 | 9.93 | 9.42 | 23.4 | 23.31 | 22.76 | 6.15
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 0 | 3 | 1 | 3 | 1 | 3 | 5 | 3 | 4 | 9 | 8 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB401
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 3.14 | 2.34 | 9.03 | 2.01 | 2.36 | 6.37 | 0.5 | 5.39 | 13.15 | 0 | 4.98 | 0 | 5.75 | 5.57 | 5.54 | 9.93 | 5.63 | 23.4 | 14.36 | 16.63 | 0
No of Gangs | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 1 | 0 | 2 | 1 | 3 | 5 | 2 | 4 | 6 | 6 | 0
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TB408
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.88 | 9.43 | 8.63 | 0 | 7.12 | 0 | 9.18 | 1.05 | 3.23 | 0 | 0 | 0 | 3.79 | 0 | 8.95 | 6.13 | 6.15
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 4 | 2 | 4
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
PCH: Mr.Arun Felbin
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.51 | 4.25 | 1.66 | 2.69 | 6.45 | 4.04 | 5.22 | 11.93 | 4.9 | 13.46 | 8.23
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
Project: TA 421
Stringing productivity | Jan'24 | Feb'24 | Mar'24 | Apr'24 | May'24 | Jun'24 | Jul'24 | Aug'24 | Sep'24 | Oct'24 | Nov'24 | Dec'24 | Jan'25 | Feb'25 | Mar'25 | Apr'25 | May'25 | Jun'25 | Jul'25 | Aug'25 | Sep'25 | Oct'25 | Nov'25 | Dec'25 | Jan'26
KM/month (Total) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.51 | 4.25 | 1.66 | 2.69 | 6.45 | 4.04 | 5.22 | 11.93 | 4.9 | 13.46 | 8.23
No of Gangs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1

## README
Assumption | Details
Productivity units | Avg productivity is reported per month as mean(daily_km) * 30. Total_km is the sum of daily_km.
Overall / P/O / F/S daily rows | Overall uses PO start to FS complete. P/O uses PO start to PO completion with PO length as primary metric (fallback to span length). F/S uses FS start to FS complete with span length.
PO-FS gap | gap_days = fs_starting_date - po_completion_date. Negative gaps are flagged in Data_Issues and retained in PO_FS_Gap; summary stats clamp negatives to 0. Missing dates are excluded from stats.
Erection-PO gap | gap_days = po_start_date - last erection completion date within the span (inclusive). Negative gaps are flagged and clamped to 0. Missing dates or unmatched spans are logged in Data_Issues.
Location parsing | From/To AP values strip a leading 'AP' (case-insensitive) with optional separators. Parsed as main number + optional letters + optional '/sub'. Order key = main*1,000,000 + letter_rank*1,000 + sub.
Length units | Span lengths are auto-detected per source_file (fallback per project): if p90 <= 50 and max <= 100, values are treated as KM; otherwise meters. KM values are converted to meters for length_m and used directly for length_km.
Span matching | Span ranges are inclusive of From and To locations. If From/To order is reversed, the range is normalized.
Project matching | Projects are matched using a compact key (lowercase, alphanumeric only).
Date filters | PO-FS gaps are filtered by PO completion date; Erection-PO gaps are filtered by PO start date; daily outputs are filtered by the daily date column.
Method split | Method is read from the stringing daily data (method/method_norm). Rows without method are logged in Data_Issues. Summary groups into TSE, Manual, and Other.
Monthly breakup | Monthly KM tables use sum(length_km) grouped by F/S completion month and count unique gangs per month.

## Data_Issues
issue_type | project | from_ap | to_ap | po_start_date | po_completion_date | fs_starting_date | fs_complete_date | details | date | row_id
PO_FS_NEGATIVE_GAP | TA 325 | 120/0 | 121/0 | 2024-12-28 | 2025-01-01 | 2024-12-28 | 2025-01-01 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 144A/0 | 145/0 | 2024-01-08 | 2025-01-13 | 2024-01-08 | 2025-01-13 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 147/1 | 147/2 | 2025-01-15 | 2025-01-16 | 2025-01-15 | 2025-01-16 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 124A/0 | 124A/1 | 2025-02-15 | 2025-02-19 | 2025-02-15 | 2025-02-19 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 124A/1 | 125/0 | 2025-02-15 | 2025-02-19 | 2025-02-15 | 2025-02-19 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 131/0 | 132/0 | 2025-03-06 | 2025-03-10 | 2025-03-06 | 2025-03-10 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 134/0 | 135/0 | 2025-03-18 | 2025-03-22 | 2025-03-18 | 2025-03-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 163/5 | 163/6 | 2025-03-21 | 2025-03-22 | 2025-03-21 | 2025-03-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 143A/2 | 143A/3 | 2025-03-23 | 2025-03-24 | 2025-03-23 | 2025-03-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 136/0 | 137/0 | 2025-03-26 | 2025-04-01 | 2025-03-26 | 2025-04-01 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 146/0 | 147/0 | 2025-04-12 | 2025-04-15 | 2025-04-12 | 2025-04-15 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 147/0 | 147/1 | 2025-04-11 | 2025-04-15 | 2025-04-11 | 2025-04-15 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 145/0 | 145A/0 | 2025-04-18 | 2025-04-23 | 2025-04-18 | 2025-04-23 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 161/0 | 162/0 | 2025-04-28 | 2025-05-06 | 2025-04-28 | 2025-05-06 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 151/0 | 152/0 | 2025-05-11 | 2025-05-15 | 2025-05-11 | 2025-05-15 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 147/2 | 147A/0 | 2025-05-16 | 2025-05-18 | 2025-05-16 | 2025-05-18 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 150/0 | 150/1 | 2025-05-23 | 2025-05-25 | 2025-05-23 | 2025-05-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 156/0 | 157/0 | 2025-06-03 | 2025-06-04 | 2025-06-03 | 2025-06-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 152A/0 | 153/0 | 2025-09-02 | 2025-09-10 | 2025-09-06 | 2025-09-10 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 158A/0 | 158B/0 | 2025-10-07 | 2025-10-21 | 2025-10-07 | 2025-10-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 276/0 | Gty | 2025-10-18 | 2025-10-21 | 2025-10-18 | 2025-10-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 192/0 | 193/0 | 2025-10-15 | 2025-10-23 | 2025-10-19 | 2025-10-23 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 193/0 | 194/0 | 2025-10-21 | 2025-10-25 | 2025-10-21 | 2025-10-25 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 194/0 | 195/0 | 2025-10-24 | 2025-10-29 | 2025-10-24 | 2025-10-29 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 204/0 | 205/0 | 2025-10-26 | 2025-11-03 | 2025-10-26 | 2025-11-03 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 196/0 | 197/0 | 2025-10-26 | 2025-11-04 | 2025-10-26 | 2025-11-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 275/0 | 276/0 | 2025-10-26 | 2025-11-04 | 2025-10-26 | 2025-11-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 157/0 | 158/0 | 2025-11-04 | 2025-11-11 | 2025-11-07 | 2025-11-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 190/0 | 191/0 | 2025-11-08 | 2025-11-12 | 2025-11-08 | 2025-11-12 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 176/0 | 177/0 | 2025-11-06 | 2025-11-12 | 2025-11-06 | 2025-11-12 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 177/0 | 178/0 | 2025-11-03 | 2025-11-12 | 2025-11-10 | 2025-11-13 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 248/0 | 249/0 | 2025-11-04 | 2025-11-10 | 2025-11-07 | 2025-11-13 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 169/0 | 171/0 | 2025-11-08 | 2025-11-18 | 2025-11-08 | 2025-11-18 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 181/0 | 182/0 | 2025-11-14 | 2025-11-17 | 2025-11-14 | 2025-11-19 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 179/0 | 180/0 | 2025-11-16 | 2025-11-21 | 2025-11-16 | 2025-11-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 188/0 | 189/0 | 2025-11-16 | 2025-11-21 | 2025-11-16 | 2025-11-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 198/0 | 199/0 | 2025-11-14 | 2025-11-19 | 2025-11-18 | 2025-11-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 246/0 | 247/0 | 2025-11-20 | 2025-11-23 | 2025-11-20 | 2025-11-23 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 205/0 | 206/0 | 2025-11-21 | 2025-11-24 | 2025-11-21 | 2025-11-25 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 230/0 | 231/0 | 2025-11-24 | 2025-11-25 | 2025-11-24 | 2025-11-25 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 231/0 | 232/0 | 2025-11-26 | 2025-11-28 | 2025-11-26 | 2025-11-28 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 233/0 | 234/0 | 2025-11-26 | 2025-11-29 | 2025-11-26 | 2025-11-29 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 232/0 | 233/0 | 2025-11-26 | 2025-11-30 | 2025-11-26 | 2025-11-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 234/0 | 235/0 | 2025-11-26 | 2025-11-30 | 2025-11-26 | 2025-11-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 180/0 | 181/0 | 2025-11-20 | 2025-12-01 | 2025-11-20 | 2025-12-01 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 210/0 | 211/0 | 2025-11-28 | 2025-12-03 | 2025-11-28 | 2025-12-03 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 222/1 | 223/0 | 2025-12-02 | 2025-12-04 | 2025-12-02 | 2025-12-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 209/0 | 210/0 | 2025-12-01 | 2025-12-04 | 2025-12-02 | 2025-12-05 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 235/0 | 236/0 | 2025-12-03 | 2025-12-05 | 2025-12-03 | 2025-12-05 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 171/0 | 172/0 | 2025-11-27 | 2025-12-06 | 2025-11-27 | 2025-12-06 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 226/0 | 227/0 | 2025-12-04 | 2025-12-07 | 2025-12-04 | 2025-12-07 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 184/0 | 184/1 | 2025-12-04 | 2025-12-08 | 2025-12-04 | 2025-12-08 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 184/1 | 185/0 | 2025-12-04 | 2025-12-08 | 2025-12-04 | 2025-12-08 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 236/0 | 237/0 | 2025-12-03 | 2025-12-08 | 2025-12-03 | 2025-12-08 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 240/0 | 241/0 | 2025-12-07 | 2025-12-10 | 2025-12-07 | 2025-12-10 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 239/0 | 240/0 | 2025-12-07 | 2025-12-11 | 2025-12-07 | 2025-12-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 182/0 | 182A/0 | 2025-12-11 | 2025-12-13 | 2025-12-11 | 2025-12-13 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 219/0 | 220/0 | 2025-12-08 | 2025-12-13 | 2025-12-08 | 2025-12-13 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 211/0 | 211A/0 | 2025-12-10 | 2025-12-13 | 2025-12-11 | 2025-12-14 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 212/0 | 213/0 | 2025-12-10 | 2025-12-14 | 2025-12-10 | 2025-12-14 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 229/0 | 229/1 | 2025-12-07 | 2025-12-15 | 2025-12-07 | 2025-12-15 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 160/0 | 161/0 | 2025-12-13 | 2025-12-16 | 2025-12-13 | 2025-12-16 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 182A/0 | 183/0 | 2025-12-14 | 2025-12-20 | 2025-12-15 | 2025-12-20 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 183/0 | 184/0 | 2025-12-15 | 2025-12-20 | 2025-12-15 | 2025-12-20 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 272/5 | 272A/0 | 2025-12-17 | 2025-12-20 | 2025-12-18 | 2025-12-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 199/0 | 200/0 | 2025-12-20 | 2025-12-22 | 2025-12-20 | 2025-12-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 200/0 | 201/0 | 2025-12-20 | 2025-12-22 | 2025-12-20 | 2025-12-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 227/0 | 228/0 | 2025-12-14 | 2025-12-18 | 2025-12-17 | 2025-12-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 228/0 | 229/0 | 2025-12-17 | 2025-12-22 | 2025-12-17 | 2025-12-22 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 105/0 | 106/0 | 2025-12-24 | 2025-12-25 | 2025-12-24 | 2025-12-25 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 201/0 | 201/1 | 2025-12-23 | 2025-12-26 | 2025-12-23 | 2025-12-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 272A/0 | 273/0 | 2025-12-22 | 2025-12-25 | 2025-12-22 | 2025-12-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 211A/0 | 212/0 | 2025-12-10 | 2025-12-25 | 2025-12-10 | 2025-12-27 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 175/0 | 175/1 | 2025-12-22 | 2025-12-27 | 2025-12-23 | 2025-12-29 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 175/1 | 176/0 | 2025-12-22 | 2025-12-27 | 2025-12-24 | 2025-12-29 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 167/0 | 167/1 | 2025-12-26 | 2025-12-29 | 2025-12-27 | 2025-12-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 208/0 | 209/0 | 2025-12-18 | 2025-12-23 | 2025-12-18 | 2025-12-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 217/0 | 217A/0 | 2025-12-29 | 2025-12-31 | 2025-12-29 | 2025-12-31 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 221/0 | 222/0 | 2025-12-27 | 2025-12-31 | 2025-12-27 | 2025-12-31 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 222/0 | 222/1 | 2025-12-25 | 2025-12-31 | 2025-12-25 | 2025-12-31 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 201/1 | 202/0 | 2025-12-29 | 2026-01-04 | 2025-12-29 | 2026-01-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 202/0 | 203/0 | 2025-12-29 | 2026-01-04 | 2025-12-30 | 2026-01-04 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 154/1 | 155/0 | 2025-12-28 | 2026-01-05 | 2025-12-30 | 2026-01-05 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 159/0 | 159/2 | 2025-12-31 | 2026-01-05 | 2026-01-03 | 2026-01-05 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 173/0 | 174/0 | 2025-12-31 | 2026-01-05 | 2025-12-31 | 2026-01-05 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 174/0 | 174/1 | 2025-12-31 | 2026-01-06 | 2026-01-03 | 2026-01-06 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 174/1 | 175/0 | 2026-01-02 | 2026-01-06 | 2026-01-03 | 2026-01-06 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 206/0 | 208/0 | 2025-12-18 | 2026-01-09 | 2025-12-18 | 2026-01-09 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 216/0 | 217/0 | 2026-01-01 | 2026-01-09 | 2026-01-01 | 2026-01-09 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 186/0 | 187/0 | 2026-01-10 | 2026-01-11 | 2026-01-10 | 2026-01-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 215/0 | 215/1 | 2025-01-11 | 2026-01-14 | 2026-01-13 | 2026-01-16 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 325 | 215/1 | 216/0 | 2025-01-11 | 2026-01-14 | 2026-01-13 | 2026-01-16 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 416 | AP37/0 | AP38/0 | 2025-12-05 | 2025-12-10 | 2025-12-06 | 2025-12-18 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 416 | AP24/0 | AP25/0 | 2025-12-24 | 2025-12-30 | 2025-12-29 | 2025-12-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 31/0 | 32/0 | 2025-06-12 | 2025-06-17 | 2025-06-13 | 2025-06-17 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 30/0 | 31/0 | 2025-06-22 | 2025-07-02 | 2025-06-23 | 2025-07-02 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 29/9 | 30/0 | 2025-07-06 | 2025-07-11 | 2025-07-07 | 2025-07-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 20A/0 | 21/0 | 2025-08-23 | 2025-08-31 | 2025-08-24 | 2025-08-31 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 20/0 | 20A/0 | 2025-08-22 | 2025-09-01 | 2025-08-24 | 2025-09-01 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 19/0 | 20/0 | 2025-09-15 | 2025-10-19 | 2025-09-17 | 2025-10-20 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 18/0 | 19/0 | 2025-09-21 | 2025-10-20 | 2025-09-22 | 2025-10-21 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TA 421 | 14/0 | 15/0 | 2025-12-15 | 2025-12-17 | 2025-12-15 | 2025-12-17 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 42/0 | 43/0 | 2025-05-04 | 2025-05-11 | 2025-05-07 | 2025-05-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 49/0 | 50/0 | 2025-05-15 | 2025-05-17 | 2025-05-15 | 2025-05-17 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 62/0 | 63/0 | 2025-07-07 | 2025-07-10 | 2025-07-07 | 2025-07-10 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | Gantry | 1/0 | 2025-10-08 | 2025-10-17 | 2025-10-09 | 2025-10-17 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 33/0 | 34/0 | 2025-10-21 | 2025-10-27 | 2025-10-23 | 2025-10-29 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 36/0 | 37/0 | 2025-10-30 | 2025-11-08 | 2025-10-30 | 2025-11-08 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 60/0 | 61/0 | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 45/0 | 46/0 | 2025-11-14 | 2025-11-26 | 2025-11-14 | 2025-11-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 37/0 | 37/1 | 2025-11-29 | 2025-11-30 | 2025-11-29 | 2025-11-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 37/1 | 37/2 | 2025-11-29 | 2025-11-30 | 2025-11-29 | 2025-11-30 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 401 | 5/0 | 6/0 | 2025-12-05 | 2025-12-11 | 2025-12-05 | 2025-12-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 65/0 | 66/0 | 2025-02-03 | 2025-03-22 | 2025-03-10 | 2025-03-23 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 50/0 | 51/0 | 2025-03-12 | 2025-03-23 | 2025-03-17 | 2025-03-24 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 51/0 | 52/0 | 2025-04-02 | 2025-04-08 | 2025-04-04 | 2025-04-09 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 70/0 | 71/0 | 2025-12-08 | 2025-12-16 | 2025-12-12 | 2025-12-17 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 56/0 | 57/0 | 2025-11-20 | 2025-11-26 | 2025-11-20 | 2025-11-26 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 46/0 | 47/0 | 2025-12-06 | 2025-12-11 | 2025-12-06 | 2025-12-11 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 69/0 | 70/0 | 2025-12-18 | 2025-12-24 | 2025-12-21 | 2025-12-25 | FS start is before PO completion
PO_FS_NEGATIVE_GAP | TB 408 | 3/0 | 4/0 | 2026-01-10 | 2026-01-16 | 2026-01-11 | 2026-01-16 | FS start is before PO completion
ERECTION_PO_NEGATIVE_GAP | TA 325 | 110/0 | 111/0 | 2024-09-11 | 2024-09-12 00:00:00 | 2024-10-04 00:00:00 | 2024-10-06 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 116B/0 | 117/0 | 2024-11-17 | 2024-12-18 00:00:00 | 2024-12-23 00:00:00 | 2024-12-24 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 144A/0 | 145/0 | 2024-01-08 | 2025-01-13 00:00:00 | 2024-01-08 00:00:00 | 2025-01-13 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 135/0 | 135A/0 | 2025-03-21 | 2025-03-24 00:00:00 | 2025-04-28 00:00:00 | 2025-05-01 00:00:00 | PO start is before last erection completion in span
LOCATION_PARSE_FAILED | TA 325 | 276/0 | Gty | 2025-10-18 | 2025-10-21 00:00:00 | 2025-10-18 00:00:00 | 2025-10-21 00:00:00 | Unable to parse span location ordering
ERECTION_PO_NEGATIVE_GAP | TA 325 | 237/0 | 239/0 | 2025-11-28 | 2025-12-03 00:00:00 | 2025-12-07 00:00:00 | 2025-12-10 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 165/0 | 165/4 | 2025-11-28 | 2025-12-01 00:00:00 | 2025-12-08 00:00:00 | 2025-12-12 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 167/1 | 168/0 | 2025-11-19 | 2025-11-23 00:00:00 | 2025-12-14 00:00:00 | 2025-12-17 00:00:00 | PO start is before last erection completion in span
ERECTION_SPAN_EMPTY | TA 325 | 202/0 | 203/0 | 2025-12-29 | 2026-01-04 00:00:00 | 2025-12-30 00:00:00 | 2026-01-04 00:00:00 | No erection locations found in span range
ERECTION_PO_NEGATIVE_GAP | TA 325 | 215/0 | 215/1 | 2025-01-11 | 2026-01-14 00:00:00 | 2026-01-13 00:00:00 | 2026-01-16 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 325 | 215/1 | 216/0 | 2025-01-11 | 2026-01-14 00:00:00 | 2026-01-13 00:00:00 | 2026-01-16 00:00:00 | PO start is before last erection completion in span
PO_START_MISSING | TA 325 | 153/0 | 154/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 325 | 154/0 | 154/1 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 325 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 325 | nan | Total |  | nan | nan | nan | Missing PO start date
ERECTION_PO_NEGATIVE_GAP | TA 413 | 34/0 | 35/0 | 2025-02-21 | 2025-02-26 00:00:00 | 2025-02-27 00:00:00 | 2025-03-04 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 413 | 37A/0 | 38/0 | 2025-03-17 | 2025-03-20 00:00:00 | 2025-03-21 00:00:00 | 2025-04-16 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 413 | 38/0 | 39/0 | 2025-03-29 | 2025-04-05 00:00:00 | 2025-04-06 00:00:00 | 2025-04-16 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TA 413 | 39/0 | 40/0 | 2025-04-25 | 2025-04-29 00:00:00 | 2025-04-30 00:00:00 | 2025-04-30 00:00:00 | PO start is before last erection completion in span
PO_START_MISSING | TA 413 | 4/0 | 4A/0 |  | 2025-12-31 00:00:00 | 2026-01-14 00:00:00 | 2025-01-18 00:00:00 | Missing PO start date
PO_START_MISSING | TA 413 | 3A/0 | 3B/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 32/0 | 32A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 40/0 | 40A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | GY | 1/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 1/0 | 2A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 2A/0 | 3A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 9/0 | 10/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 10/0 | 11/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 11/0 | 12/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 12/0 | 13/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 13/0 | 13A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 13A/0 | 14/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 14/0 | 15/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 15/0 | 16/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 16/0 | 17/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 17/0 | 18/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 18/0 | 19/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 19/0 | 20/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 20/0 | 21/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 21/0 | 22/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 22/0 | 23/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 23/0 | 23A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 23A/0 | 24/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 24/0 | 25/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 25/0 | 26/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 26/0 | 27/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 27/0 | 28/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 28/0 | 29/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 29/0 | 29A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 29A/0 | 30/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 30/0 | 31/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 31/0 | 32/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 35/0 | 36/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 36/0 | 36A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 36A/0 | 37/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 37/0 | 37A/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 40A/0 | 41/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 41/0 | 42/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 42/0 | 42/3 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 42/3 | 43/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 43/0 | 43/5 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 43/5 | 44/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 44/0 | 45/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | 45/0 | 46/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 413 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 414 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 414 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 414 | nan | Total |  | nan | nan | nan | Missing PO start date
ERECTION_PO_NEGATIVE_GAP | TA 416 | AP36/0 | AP37/0 | 2025-09-05 | 2025-09-11 00:00:00 | 2025-12-06 00:00:00 | 2025-12-17 00:00:00 | PO start is before last erection completion in span
PO_START_MISSING | TA 416 | AP42/0 | AP43/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | AP27/0 | AP28/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 416 | nan | Total |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 418 | 33/0 | 33/5 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 419 | nan | nan |  | nan | nan | nan | Missing PO start date
ERECTION_PO_NEGATIVE_GAP | TA 421 | 29/0 | 29/9 | 2025-05-05 | 2025-05-16 00:00:00 | 2025-07-06 00:00:00 | 11-07-2025 | PO start is before last erection completion in span
PO_START_MISSING | TA 421 | 4/12 | 5/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | 7/0 | 8/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | Gantry | 1/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 421 | nan | Total |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | 16/3 | 17/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | 17/0 | 18/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | 18/0 | 19/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 504 | nan | Total |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 505 | nan | Total |  | nan | nan | nan | Missing PO start date
ERECTION_SPAN_EMPTY | TA 506 | 48/0 | 50/0 | 2025-12-19 | 2025-12-30 00:00:00 | 2026-01-15 00:00:00 | 2026-01-20 00:00:00 | No erection locations found in span range
ERECTION_SPAN_EMPTY | TA 506 | 50/0 | 51/0 | 2025-12-19 | 2025-12-30 00:00:00 | 2026-01-17 00:00:00 | 2026-01-22 00:00:00 | No erection locations found in span range
PO_START_MISSING | TA 506 | 2/0 | 2A/0 |  | nan | nan | nan | Missing PO start date
ERECTION_SPAN_EMPTY | TA 506 | 51/0 | 51A/0 | 2026-01-17 | 2026-01-20 00:00:00 | nan | nan | No erection locations found in span range
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 506 | nan | Total |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TA 512 | nan | nan |  | nan | nan | nan | Missing PO start date
ERECTION_PO_NEGATIVE_GAP | TB 401 | 71/0 | 72/0 | 2024-12-03 | 10.12.24 | 16.01.25 | 19.01.25 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 401 | 69/0 | 70/0 | 2024-12-30 | 05.01.25 | 27.01.25 | 28.01.25 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 401 | 59/0 | 60/0 | 2025-01-20 | 25.01.25 | 02.05.25 | 04.05.25 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 401 | 46/0 | 47/0 | 2025-06-22 | 27.06.25 | 04.10.25 | 09.10.25 | PO start is before last erection completion in span
LOCATION_PARSE_FAILED | TB 401 | Gantry | 1/0 | 2025-10-08 | 17.10.25 | 09.10.25 | 17.10.25 | Unable to parse span location ordering
ERECTION_PO_NEGATIVE_GAP | TB 401 | 34/0 | 34/5 | 2025-01-01 | 06.11.25 | 14.11.25 | 18.11.25 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 401 | 2/0 | 3/0 | 2025-10-30 | 05.11.25 | 30.11.25 | 30.11.25 | PO start is before last erection completion in span
PO_START_MISSING | TB 401 | 9/0 | 10/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 401 | 17/0 | 18/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 401 | 10/12 | 10/20 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 401 | 70/0 | 71/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 401 | 14/0 | 15/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 401 | 22/0 | 23/0 |  | nan | nan | nan | Missing PO start date
ERECTION_PO_NEGATIVE_GAP | TB 408 | 61/0 | 62/0 | 2024-09-06 | 2024-09-16 00:00:00 | 2024-09-26 00:00:00 | 2024-10-03 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 408 | 65/0 | 66/0 | 2025-02-03 | 2025-03-22 00:00:00 | 2025-03-10 00:00:00 | 2025-03-23 00:00:00 | PO start is before last erection completion in span
ERECTION_PO_NEGATIVE_GAP | TB 408 | 49/0 | 50/0 | 2025-02-06 | 2025-02-19 00:00:00 | 2025-05-01 00:00:00 | 2025-05-05 00:00:00 | PO start is before last erection completion in span
PO_START_MISSING | TB 408 | 47/0 | 48/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 408 | 55/0 | 56/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 408 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 408 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 501 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 507 | 149A/0 | 149/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 507 | 149/0 | 148/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 507 | 148/0 | 147/0 |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 507 | nan | Total |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
PO_START_MISSING | TB 605 | nan | nan |  | nan | nan | nan | Missing PO start date
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:d0f75ba16250446d
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:20029146e514fbde
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:dfa8e26aca904f32
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:7c425bd1511b4a6e
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:4b3b8f8ee15bd2aa
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:d6e6afba5309728a
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:8a7ebb62632bc57a
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:03e14128089bdbaf
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:71d4f4c40b2bcafe
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:0d4622b7f01a6b58
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:b9ab519eeee674d1
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:c186accd7e6dbb28
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:13c27d416ae0a406
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:cb9ea4cd2aed0dc9
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:991be6bf3b148f1f
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:b55514ea29f6dbba
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:ae68f750d047b610
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:7777eea4b66e17e7
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:c121489aa9989c42
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:34e45f077bf0add0
METHOD_MISSING | TA 418 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:1d7b69f3a2a5721a
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:a34fd2f90dc95d26
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:2b8f463318b3d147
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:e1aeb5aa4827ccb2
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:7799759a5fcf07db
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:8b91197cb09f9397
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:5798e5aac33fed94
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:2ff927aad2067445
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:c846753fc6d1707a
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:40049a8465cadff6
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:c0a145df4fae7692
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:4d043938342d5e25
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:fbaaee395fc03e7c
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:c8fdc47036e26a25
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:a9d3c9d02bdebcf9
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:05ea6f5f601695dd
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:a1dbcfde519d0324
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:21cfd313b05eed21
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:04ada5d4d324ae2e
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:3ca50dd37f0e61d1
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:67fe7696467c4bf7
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:8538c4c685d16ed3
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:f7759b200e2c9b31
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:6a672ad70410d1c1
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:ed7b956c492a8b11
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-27 | stringing:c7806364d7dd037a
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-28 | stringing:5a37e50105ba019b
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-29 | stringing:f2410b272e71f93b
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-30 | stringing:b6f23e551779291d
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-10-31 | stringing:66e71ff7cc28ac98
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:29f91f84da06c3a0
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:5eb6aa05636f98f0
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:7c92c1e5c08f58d4
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:42685e728ac62fe9
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:31190ec127736ca1
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:3583ce7c2ef7afad
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:6575a2012a709cce
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:7f8327330552f611
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:343d940bf2f36d85
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:aa1154769e69df92
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:81add55ba60a433d
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:306b682056349d40
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:00fbd3f786db615c
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:999cafb9b5f46c71
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:954279461436bee3
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:fa3e920de642dd07
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:c8e98300c7e4bc72
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:f0db8c47acfff045
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:69311ca50bfe2984
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:5f5bc5e0c70d2a46
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:4561e736fc122309
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:dea1c347ee3295e7
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:9033c9a77a95fa12
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:cb1e62335d17364d
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:fe91f0f3d1eceb43
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:8b584025a1f39d5d
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:924471ae312f5d1e
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:07a247e148560eeb
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:8e9220c02215ee3b
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:bf9447c8b2f2aab8
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:4ad95d096e73191a
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:f26623c7b23f1aaf
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:5319a52b3f5639a3
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:9f77bd857ea83fa2
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:14df50170599facf
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:dc48dbf7d9d841fb
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:b062276ec74bd177
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:a23c4cdd4610f6f9
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:978ea3db2f449b60
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:0a06e1906a610a82
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:9516d19ed50e53e8
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:e6bf37027124a210
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-13 | stringing:259975f23ddf8b73
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-14 | stringing:247f284025b640f3
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-15 | stringing:865f2e3feb9418cc
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-16 | stringing:20cbadae72cf038c
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-17 | stringing:b99e364e3ee0785f
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-18 | stringing:9ba7125b4b61f5a9
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-19 | stringing:851ec91a5e8e0a2f
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-20 | stringing:efb8b4052b599576
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-21 | stringing:b0a3f2655dc697a8
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-22 | stringing:22132f0587e11115
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-23 | stringing:141d45c49005d69e
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-24 | stringing:f3901bfc69095c79
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-25 | stringing:650c75ac643e1da8
METHOD_MISSING | TA 418 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-12-26 | stringing:88a5bdc6ad89ca88
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-20 | stringing:a3133325ad46fd49
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-21 | stringing:f086c7f7c01f2302
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-22 | stringing:0a22d723feb997ba
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-23 | stringing:9c6a9479b027d360
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-24 | stringing:0c85099cd47f00fa
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-25 | stringing:bdf16050a6b09c35
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-26 | stringing:52d4e8bdbad3ceef
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-27 | stringing:94df90cec6a3cb46
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-28 | stringing:f779b36e8040725a
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-29 | stringing:7d21d9781b8f7f4c
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-30 | stringing:e8b40990fba1f0fc
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2025-12-31 | stringing:2a8b305a2cbbbfcc
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2026-01-01 | stringing:e3e480b53278e676
METHOD_MISSING | TA 418 | 40/0 | 41/0 |  |  |  |  | Method column missing or blank | 2026-01-02 | stringing:d6bddd5061e29def
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:5f6adebef1f25398
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:5dddad6c98a0a288
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:60b108f98cd51022
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:d01b475ee27520c1
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:565ce3b8dc5ee7c9
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:f7ad4d989f60b8c1
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:eadd319c7d8f0d70
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:3dbac13596fe737a
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:e721b36d34bd5a6d
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:a55e61b5ab58b5dc
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:184c885392ee3141
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:c38c9e6350ad99a5
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:0d12e734671eed06
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:90b186d85fe53f66
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:1e0fe0fd6d3d43a8
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:12e26cce72507cff
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:103dc76bc301df66
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:c7cbaf0d4f7acb9a
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:0c6e092cb4543e8b
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:43b6f0c960825fa5
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:2744a6f65d2d9ae3
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:309c1e507c8a72df
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:85a9bfdcb3cba9c8
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:a14b2878ea99ef50
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:c020ccbd2f172e52
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:19723abeb047c80e
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:634923e3772c117f
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:bbf602035fc3ea3c
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:fcc26dbc6b183da2
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:1bc016dbbe124063
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:9f28de2cfbb4ee65
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:7ff2a881b4c1600d
METHOD_MISSING | TA 418 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:ff3a9f460c615c34
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:d3b5359d2dfa5e22
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:b7cc04fac9f62dc9
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:f3db7d09a1869873
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:6f36f63b20ee1aeb
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:497fb32d11e6f7c9
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:4de52cabbeefc132
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:e586fbd10f76d3af
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:c19e630c44c73167
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:cb8fd70fe443a92d
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:a8f25b1e9b054725
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:0b1879023475709c
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:e0cbf1bf066ed90b
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:beafce228e09bdf7
METHOD_MISSING | TA 418 | 34/0 | 35/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:7e4b346721aa655b
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:fbf29e5013c008d7
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:534d4df9a0986d7e
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:94c48534b518d3a4
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:e4f748e764858857
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:de0001f497f6663f
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:4763484b6c3a3578
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:9a4ddddff93a1a4f
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:1d74a5f14763637e
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:9d4e2e93768f1e9a
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:cf905dbd00c47433
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:d9c90087f79c797e
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:28656942efbac390
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:4ce32cd77feea4fe
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:2fc38cb376de2b0c
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:8f37671a3b54155e
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:2a07672a12574db5
METHOD_MISSING | TA 418 | 36/0 | 36/1 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:5248752cc2f1af3a
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-06 | stringing:1b90d8f798831408
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-07 | stringing:0476c9c2fac0c89d
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-08 | stringing:076574140bcd7452
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-09 | stringing:d2114495f21d0fc0
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-10 | stringing:b0e4b3351a52b7df
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-11 | stringing:d7e34869726daf9d
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-12 | stringing:54b406471a8381a6
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-13 | stringing:9b682141a2a773ca
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-14 | stringing:b125b9f30a9abd1c
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-15 | stringing:89b2fd43c398f2eb
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-16 | stringing:c3d1f0e839795102
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-17 | stringing:4878e9cb875ea5d7
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-18 | stringing:1d8a7671f7cf2201
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-19 | stringing:8e1aee7667e8d2ae
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-20 | stringing:f8596bbfcd8b1239
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-21 | stringing:8392994c0bcd57e1
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-22 | stringing:480bb1bcf139c602
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-23 | stringing:18803cd8491d4d16
METHOD_MISSING | TB 401 | 57/6 | 58/0 |  |  |  |  | Method column missing or blank | 2024-05-24 | stringing:fac80591b11389b9
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-16 | stringing:13b675dc17dcdbb4
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-17 | stringing:2272ceffdb564217
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-18 | stringing:9069c8e193dfe6b6
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-19 | stringing:b1b1839c35564441
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-20 | stringing:b4faaa14b7aa4aa4
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-21 | stringing:f2aebe5e6d05d344
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-22 | stringing:175f56d226ebaf7f
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-23 | stringing:c6247883267d5b1a
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-24 | stringing:e23a250d3a639d54
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-25 | stringing:2c3ff19c2a34b325
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-26 | stringing:66d3d98dfe9136fb
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-27 | stringing:9a17ca8179a39ee9
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-28 | stringing:de54587d8c965773
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-29 | stringing:ee75e038a102a681
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-30 | stringing:5776169214a60987
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-05-31 | stringing:6fedbaad49a25c6e
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-01 | stringing:6d66691eb305739c
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-02 | stringing:ca7fba976d0fe67e
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-03 | stringing:c6e380cea149b0cb
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-04 | stringing:e2d36633b9cf4c6b
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-05 | stringing:69d6cfedf671981e
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-06 | stringing:4f4f39653595b96a
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-07 | stringing:a9643b0fbf12087a
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-08 | stringing:9988c256168803b0
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-09 | stringing:b8cf54456f811004
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-10 | stringing:43cb86b3c4e9bdba
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-11 | stringing:fc486426df68a5b4
METHOD_MISSING | TB 401 | 57/0 | 57/6 |  |  |  |  | Method column missing or blank | 2024-06-12 | stringing:079b6f0e37fd8294
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-04 | stringing:bac0228b83ea010d
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-05 | stringing:44570d28c60660a5
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-06 | stringing:dff8164d15c7df8c
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-07 | stringing:e7936aee017ee903
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-08 | stringing:f0224b869bb303d7
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-09 | stringing:735a13d6f4320dd8
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-10 | stringing:5ab2e5ced36ae3d5
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-11 | stringing:283f94c443408b6b
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-12 | stringing:07ce03326700ebce
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-13 | stringing:de861bdef0d6fef3
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-14 | stringing:b27eed9b0495e828
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-15 | stringing:84e9ebd6110f8657
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-16 | stringing:ae924f89e74ca6e1
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-17 | stringing:65421bc7ffeb1cb4
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-18 | stringing:600b315c65127040
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-19 | stringing:4f42d7fd74b5c57b
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-20 | stringing:00cd7abf9a54f309
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-21 | stringing:65f0678cf6e4a323
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-22 | stringing:1762ed67d4c62150
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-23 | stringing:b9d2c5a133c64702
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-24 | stringing:9fb55f85e203804f
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-25 | stringing:5f82b25ee1c08124
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-26 | stringing:7eca98c82c63fac2
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-27 | stringing:7dc0118afa4f693c
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-28 | stringing:c06bde1e345411c6
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-29 | stringing:0abd406f15f1d92e
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-06-30 | stringing:1e22f2cb035b243b
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-07-01 | stringing:2e315b01d48d4eb2
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-07-02 | stringing:1f038286c39bc61e
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-07-03 | stringing:a297c1c867490229
METHOD_MISSING | TB 401 | 56/0 | 57/0 |  |  |  |  | Method column missing or blank | 2024-07-04 | stringing:ddb4d6e0fa905891
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-25 | stringing:8699dbc88ed5838a
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-26 | stringing:148adfcb7e4ad9fa
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-27 | stringing:3b381d2fe87d4c32
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-28 | stringing:e4734a2f69590965
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-29 | stringing:a32a656fe70ddd66
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-06-30 | stringing:3795598560b67cdb
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-01 | stringing:c8f204cf17b70163
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-02 | stringing:17e11567dffe407b
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-03 | stringing:4900e97b878a2d1f
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-04 | stringing:489fd4a1934e6cad
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-05 | stringing:ff8c04d9d28268db
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-06 | stringing:b97dcf011c032c9a
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-07 | stringing:092e13bd5e32e0b5
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-08 | stringing:6013d492fe72fcfe
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-09 | stringing:dc252fed4e6d8464
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-10 | stringing:f55e206f2033c74d
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-11 | stringing:55530dd22419a55b
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-12 | stringing:79e504dbcc6524e3
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-13 | stringing:301786c48af17240
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-14 | stringing:7deebabf0d3e9e3a
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-15 | stringing:9caf616b18d0b02f
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-16 | stringing:295fb62210be671b
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-17 | stringing:a7af85d696d0e384
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-18 | stringing:975df69078c7529a
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-19 | stringing:a414a67a3793f9cb
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-20 | stringing:2d39e67b9746a751
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-21 | stringing:daa2ca49557f139f
METHOD_MISSING | TB 401 | 55/0 | 56/0 |  |  |  |  | Method column missing or blank | 2024-07-22 | stringing:5e54ddf12e4d145a
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-16 | stringing:c9ace63a3a4658ed
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-17 | stringing:4df9648b6ca3fd76
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-18 | stringing:d4a9206663ad7948
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-19 | stringing:13d719ffb38fd363
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-20 | stringing:dd890fb02c7addde
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-21 | stringing:94e154eb51963dd8
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-22 | stringing:f02e8cdda8793556
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-23 | stringing:49a2a69cab173bfb
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-24 | stringing:dbee4033734d05e6
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-25 | stringing:5d797b4e0e4d4692
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-26 | stringing:0374afb79a819a66
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-27 | stringing:677d3b4aaac0e284
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-28 | stringing:a8d2620092deab69
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-29 | stringing:7e3139228e07dcf7
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-30 | stringing:1325a47c9d755cb5
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-07-31 | stringing:126714134dfb1355
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-01 | stringing:e8a20dec035202ad
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-02 | stringing:a41b33d1753a35d1
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-03 | stringing:b82add1706e3e637
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-04 | stringing:ab7278c38eac6ef5
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-05 | stringing:703844062c65230b
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-06 | stringing:4fca23d9e559ef0a
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-07 | stringing:db563c8022c01433
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-08 | stringing:87ea9d175b5d282a
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-09 | stringing:15461fa5d0d717cb
METHOD_MISSING | TB 401 | 53/0 | 55/0 |  |  |  |  | Method column missing or blank | 2024-08-10 | stringing:09fc19ca1c9b6773
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-19 | stringing:54cb8323e2e9420c
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-20 | stringing:aec931afe2f32267
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-21 | stringing:02ad9173566f0f2c
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-22 | stringing:c0fc0d351944c9e9
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-23 | stringing:86b46a7d11c9cfeb
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-24 | stringing:037adc8a81bce8d8
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-25 | stringing:60c3f8cf47af4b35
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-26 | stringing:68fd0daacf1c5430
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-27 | stringing:99894ff8915b2e80
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-28 | stringing:7113843804dbe4d8
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-29 | stringing:c47be02c14a230d1
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-30 | stringing:f8947311c1df0d2e
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-08-31 | stringing:156533c23698afe0
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-01 | stringing:b399e17c00fa4e9d
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-02 | stringing:63a1de8ff3c81256
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-03 | stringing:bd8859bc655d6a23
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-04 | stringing:50c2f0646b1b5fa8
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-05 | stringing:c8cc48217191989e
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-06 | stringing:f51561df5e5d7a05
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-07 | stringing:89afb82c07d363b2
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-08 | stringing:359288725b265930
METHOD_MISSING | TB 401 | 52/0 | 53/0 |  |  |  |  | Method column missing or blank | 2024-09-09 | stringing:77544fbdf3575007
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-01 | stringing:17170f84d83be423
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-02 | stringing:28e4a181ebc09bde
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-03 | stringing:2cc6e9ecac3c01ac
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-04 | stringing:bbec6d904b59caae
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-05 | stringing:d4b83500d24154c7
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-06 | stringing:e8b52a035622d071
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-07 | stringing:f4954ab143913d9d
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-08 | stringing:9866483f7d1bab43
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-09 | stringing:2dcba5bd696fd0e8
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-10 | stringing:6a7cb8c2ac4872ea
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-11 | stringing:d4a4a82665b9dd81
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-12 | stringing:80e6f070652aa432
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-13 | stringing:a36de1a8e4c645c1
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-14 | stringing:9f071bab2081571c
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-15 | stringing:aaf7b69d789c4b6f
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-16 | stringing:a323697417cbac4f
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-17 | stringing:5670558ac1696281
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-18 | stringing:564220c6b991e693
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-19 | stringing:f6dcaf24dc06daf4
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-20 | stringing:14a3a9b0939e3298
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-21 | stringing:b53cdc7464cdeb36
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-22 | stringing:94dafc2211eeec99
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-23 | stringing:d5ab776ef9cb57f8
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-24 | stringing:27770e3174dc08fe
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-25 | stringing:2ce9877faea5011f
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-26 | stringing:f17978a37eec350d
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-27 | stringing:1651dbd7da898e17
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-28 | stringing:b808c79c1524b081
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-29 | stringing:03b1d56463b5e56e
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-09-30 | stringing:bce3a778c828b93e
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-10-01 | stringing:05401ae5c2ead514
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-10-02 | stringing:42a438354b745c4d
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-10-03 | stringing:730b3770ee0ebc3c
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-10-04 | stringing:2cd649f2e5c72f7f
METHOD_MISSING | TB 401 | 51/0 | 52/0 |  |  |  |  | Method column missing or blank | 2024-10-05 | stringing:f9480cc2d44dce6f
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-09-26 | stringing:77e62baf1d053ff7
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-09-27 | stringing:fabef358e3e149f8
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-09-28 | stringing:5eb88e7a26a299fc
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-09-29 | stringing:70e05d2ce3d15286
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-09-30 | stringing:9d9c2525f2d8e473
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-01 | stringing:f1e072756537597c
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-02 | stringing:d2acc559cdc3112e
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-03 | stringing:d08d3fc943831e87
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-04 | stringing:ea5b3d6213c636bf
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-05 | stringing:64929015d37b05fa
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-06 | stringing:9f238e4d2bc35234
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-07 | stringing:1c4c2282b686fca6
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-08 | stringing:9670903ea1dce35b
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-09 | stringing:375f915be9a591b5
METHOD_MISSING | TB 401 | 50/0 | 51/0 |  |  |  |  | Method column missing or blank | 2024-10-10 | stringing:979b7423abc6a3b2
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-12 | stringing:257b4f641b8a5532
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-13 | stringing:f325ea4ac1ed5d6d
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-14 | stringing:dd677204885e092c
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-15 | stringing:af53d3ec7ac5f70b
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-16 | stringing:1c5f98ee99e37ffd
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-17 | stringing:b043ddac7ab9999d
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-18 | stringing:a00b16f2704dd8ee
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-19 | stringing:7368b07a462ffe94
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-20 | stringing:187e3dd2868eb112
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-21 | stringing:c0c73ba17a71ac09
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-22 | stringing:1b3d53e80d7650e3
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-23 | stringing:8433c8ed1f33c8b2
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-24 | stringing:fa0198325b60c901
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-25 | stringing:fb4771c2674dfa64
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-26 | stringing:5ea5001f8f14ec45
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-27 | stringing:63e22f38d3b62e5b
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-28 | stringing:49481a3d514e5d4c
METHOD_MISSING | TB 401 | 72/7 | 73/0 |  |  |  |  | Method column missing or blank | 2024-11-29 | stringing:cbce24689c397268
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-20 | stringing:4e6d71388cd13aa4
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-21 | stringing:3e14b7063917dbbd
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-22 | stringing:933ace0de25b1ebe
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-23 | stringing:1adefbb8c999fc31
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-24 | stringing:c0f763bbc508f416
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-25 | stringing:42c90755ecfc9e53
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-26 | stringing:35ed9d137ba27ec7
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-27 | stringing:eec8eede46de3795
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-28 | stringing:57adae988d6ab32b
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-29 | stringing:ad23ee29caffd745
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-11-30 | stringing:916c2b324998a382
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-12-01 | stringing:7b55094c281f45ae
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-12-02 | stringing:cd80da073ba3dcb8
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-12-03 | stringing:d3761679ad86f507
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-12-04 | stringing:c11396d48193d8a9
METHOD_MISSING | TB 401 | 58/0 | 58/7 |  |  |  |  | Method column missing or blank | 2024-12-05 | stringing:0e0eb04cd69253e4
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-18 | stringing:48619a383dd01fd5
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-19 | stringing:4031b12cb471d5f3
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-20 | stringing:af3d8b2298cf0692
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-21 | stringing:4efe5e84b4953af8
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-22 | stringing:1ff003e8b9b32168
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-23 | stringing:d5db7283a4460ed8
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-24 | stringing:c07af3cf2cf4bc0f
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-25 | stringing:644167b24354a0a4
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-26 | stringing:6e12dfd0e182c6e4
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-27 | stringing:622180658587b306
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-28 | stringing:5bc562f56bca30cc
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-29 | stringing:deb8f986b7eeb7d0
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-11-30 | stringing:84883d31960fcd04
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-01 | stringing:b08d4b35f3c1685d
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-02 | stringing:fe990cd9c47f31fb
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-03 | stringing:0efc5866b775c4f6
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-04 | stringing:0f768b5b479d50e4
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-05 | stringing:e3f8ad84ea41ce9c
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-06 | stringing:a862ab08e0ddbd33
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-07 | stringing:6a8529b898387a93
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-08 | stringing:0bfc34237a986114
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-09 | stringing:66890bf056773aee
METHOD_MISSING | TB 401 | 72/0 | 72/7 |  |  |  |  | Method column missing or blank | 2024-12-10 | stringing:7c26860fb546f1de
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-22 | stringing:de9ded8f91cff4e9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-23 | stringing:2e25507ef19f13d7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-24 | stringing:22efe32eade28b25
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-25 | stringing:d5da9fe6676f5201
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-26 | stringing:5ee5320da1b0c8b1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-27 | stringing:2b67ad81cf0a1cb5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-28 | stringing:1138cb7d1433353b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-29 | stringing:142651e880669330
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:44a93fe9f1f5cf22
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:40ff6efa61fc3e53
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:0fb48b737164fa7e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:d05a7c760f2dafc5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:eb9073de1ff57d3d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:fef93c8dd1b59e10
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:8315d1a7473e69a7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:bb2500640d86aa18
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:d2f7a214389e87b3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:82f428c7919988dc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:86d456ad16f1d669
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-10 | stringing:ae1117e016477897
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-11 | stringing:207c5e35f38a3442
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-12 | stringing:af9a167eac28f33a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-13 | stringing:ce76c72dce53c2e1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-14 | stringing:51996676c0b9491f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-15 | stringing:9968294e7a33b11a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-16 | stringing:978cda53898165ce
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-17 | stringing:ef86b1146acac571
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-18 | stringing:2b4775d7b163015e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-19 | stringing:64fdae13c5396499
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-20 | stringing:8aadcfb6b5f52c20
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-21 | stringing:d1e290b4b9245749
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-22 | stringing:dbab8b25de856327
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-23 | stringing:02bf66f3def36f09
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-24 | stringing:2dfbb859b91b433c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-25 | stringing:9c97f40bd5db2584
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-26 | stringing:1c62a16c82d7626b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-27 | stringing:420261bf07a84e0c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-28 | stringing:7be37b977a0902f7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-29 | stringing:a4b8633efb788182
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-30 | stringing:efa8346427194a6b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-01-31 | stringing:953d1a5d9871ce96
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-01 | stringing:dfd09539cda18d8d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-02 | stringing:b0506b1792dff67b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-03 | stringing:3a259febed41a61a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-04 | stringing:832bbf576bdb11a6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-05 | stringing:732f0bc6eecc5734
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-06 | stringing:1dd6b99bac691380
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-07 | stringing:fa5ab19e77383485
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-08 | stringing:5fba3bffb54d2414
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-09 | stringing:99ca4530bb93c309
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-10 | stringing:8691a6c96ca1798f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-11 | stringing:695d842b5adf71ae
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-12 | stringing:82d6d53bef78d314
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-13 | stringing:32b0794fd12ddfc3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-14 | stringing:375a5a0bcca90322
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-15 | stringing:0b66a97df43830b8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-16 | stringing:89f657721635253f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-17 | stringing:b9b5b2d02c4eea78
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-18 | stringing:b26bf7895c906385
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-19 | stringing:2a74fb1caa61bfcf
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-20 | stringing:177a09f2b58fb461
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-21 | stringing:7e35e0dfc5836f73
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-22 | stringing:7f2781639d790883
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-23 | stringing:ac5d071601d4e74c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-24 | stringing:6204d1af0d3c6805
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-25 | stringing:81db192399c768a8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-26 | stringing:165f19d8df5f632c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-27 | stringing:37ad1ea0724e4b53
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-02-28 | stringing:e31453ea04e6a48e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-01 | stringing:808b6d7d8a3eb989
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-02 | stringing:8c92aba06fc1a461
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-03 | stringing:d46c660101d2c8bc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-04 | stringing:d29a374c304d54e1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-05 | stringing:128658d33d515e17
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-06 | stringing:68bc2b0cd9e385b2
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-07 | stringing:25a74b3e24a5fe3e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-08 | stringing:e63fb00b698b2c01
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-09 | stringing:51cd4b8037ccc0e4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-10 | stringing:762a89ecf357b1f0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-11 | stringing:3a436e7690792e88
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-12 | stringing:56b3706d710dbce1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-13 | stringing:e77b01dd9b556a22
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-14 | stringing:7e2cb5b32c6d2d2e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-15 | stringing:b882d4d58ec553dd
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-16 | stringing:89e98f3b1cfef39e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-17 | stringing:bd73ebe783baf1c4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-18 | stringing:bc46c50772d6c1ad
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-19 | stringing:3d127f537e4b44b9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-20 | stringing:ac95f2cfb6b2a1bd
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-21 | stringing:fd60d2ff16c5f3ef
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-22 | stringing:0e2d8f8ad7600d7a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-23 | stringing:4496ea03468ae5be
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-24 | stringing:39e4b38c873b48a0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-25 | stringing:e436615de49befd2
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-26 | stringing:d3a2d1948f3c019f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-27 | stringing:3b34c40e58d24dc6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-28 | stringing:4cd2773152917bf1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-29 | stringing:12987d94ce746dfe
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-30 | stringing:6b7bbf40a93f03b1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-03-31 | stringing:1482d46b57325953
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-01 | stringing:a69a878a17d0ec4f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-02 | stringing:61185ce2a16b556d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-03 | stringing:4c01afccb6e54f63
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-04 | stringing:984ed5661a0bed60
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-05 | stringing:95379938eef589cc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-06 | stringing:2fc41268f19e9ad9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-07 | stringing:04478b3f99f50560
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-08 | stringing:ac01df3ce5b8ab6c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-09 | stringing:f8c2932d801592a1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-10 | stringing:dd61c03e1b6b66d3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-11 | stringing:4251edc8297d87da
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-12 | stringing:992a8d822c65aae8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-13 | stringing:71e09116b9ce5de6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-14 | stringing:e6e2ff648d18bd6b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-15 | stringing:788bbb730aea5a58
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-16 | stringing:0c4d727e1621e87d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-17 | stringing:5d8e05bc5ffe2890
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-18 | stringing:8e0237b516304aae
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-19 | stringing:3c6ac432b02ff322
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-20 | stringing:cc40e8f25f832432
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-21 | stringing:9cac463c42cafed8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-22 | stringing:c57ac0b3692542d2
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-23 | stringing:ae174915358f47aa
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-24 | stringing:1aca173b3b3f18e6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-25 | stringing:f7776ae6397f23fa
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-26 | stringing:65db59cdc0d9de63
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-27 | stringing:4eaf06fc611d3fd4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-28 | stringing:d313afe2257531cc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-29 | stringing:e326b9c08efe4f2b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-04-30 | stringing:140721125ce1a1dd
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-01 | stringing:2e71b26e4588cfb4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-02 | stringing:4a3e658e532cae59
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-03 | stringing:aa584f25ee4d0e0a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-04 | stringing:6671372289b94328
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-05 | stringing:547f83a270291dc5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-06 | stringing:dbf45a92f1e6853d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-07 | stringing:025a483e16b23a41
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-08 | stringing:1066dab688784b38
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-09 | stringing:7d77e65c1e872570
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-10 | stringing:5b385dc575e2e720
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-11 | stringing:8900abdbb3c4d670
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-12 | stringing:67f3ed8832a6c863
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-13 | stringing:4b5d45e6047c4dc0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-14 | stringing:08de44ad5823921c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-15 | stringing:7fd3112a1d56fdf1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-16 | stringing:04a3c72e62be2363
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-17 | stringing:b244271881c79d71
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-18 | stringing:94835ca6f35b715d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-19 | stringing:dbe7aac3ef6825d3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-20 | stringing:c763f649c4c6e49c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-21 | stringing:023d075f79026005
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-22 | stringing:61b8db00c11ccecb
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-23 | stringing:246e2ea2ba931f6a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-24 | stringing:75c00fb91f27d6a5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-25 | stringing:4c4dde9551988601
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-26 | stringing:80e6c3b9bfee93ac
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-27 | stringing:e78a427cf087bca3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-28 | stringing:6508276884c29f98
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-29 | stringing:0ddb4c74394e1363
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-30 | stringing:d7b4de293b142f3f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-05-31 | stringing:e9da6445a6d88249
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-01 | stringing:3150cf0bc84d8ac3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-02 | stringing:b63695c8e336c807
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-03 | stringing:a9f7142c657d49b3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-04 | stringing:eeb3e85a49698cc5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-05 | stringing:5bcac3e674a11360
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-06 | stringing:0989bd011c1a5ae2
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-07 | stringing:574ba183f7778447
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-08 | stringing:60ac42498dc3fc25
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-09 | stringing:1a7839280ecd7b00
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-10 | stringing:14df4f5248fbad24
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-11 | stringing:3d6b6f46d83242e7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-12 | stringing:4b24a1d25c76419d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:844e248ebe6d85b6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:d4278f7d6968223e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:54f399fa5c1ddc30
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-16 | stringing:dae2fb478e6bf76f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-17 | stringing:a69e4fe8b1c56929
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-18 | stringing:b1b635e3d515a9a8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-19 | stringing:7c14be4b4ed01cc7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-20 | stringing:8e238b8bffeb3082
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-21 | stringing:2be8a76d3a02c131
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:3421f2934089ec75
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:d1cb89e6fe7e0a6c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:0a60df46c997bf84
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:ce117764cfed908e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-26 | stringing:64edc2b7f944d04f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:0dd4ab2d88b99566
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:b3516eea0102bada
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:f206c7df6bec1358
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:1d5c5a7481eb4f11
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:8f03920c0a9eeafc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:1be8cee7de516737
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:cae0a24ed47a71ca
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:67628c7fcfdc062c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:cf86343e7bc3ffec
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:d8bad196d8fcb5fe
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:bd5bb7ebb97746d7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:3ca1ef0427bec67b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:0b64e6954313a04c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:6056a57ad16e948f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:0d221523f1fc23bc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:28dc03a9c03f8823
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:41005f63008b7905
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:d45c0223ef20b071
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:9c72106241b0f0b1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:89fa937b3d621092
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:513b868a3f2d20b4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:7d0c6234f855b9a6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:541d8b4fe87b035e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:9b4c6082b6870730
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:30d302af39db5b63
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:e0bd115318214620
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:693ab5cd07c7e28c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:912a0e4dcda27fd9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:b750e00990afb25f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:756ed3aa30aaef75
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:9774177376203bbc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:a9cbab5454a73dd1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:f4a91e14560fb158
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:3135635dec24918a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:644b4139c2538866
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:908497d4103b8b24
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:aa2546d80a8147ec
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:642e4bca773fd7e3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:925aec2de9508a89
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:b0601cbd3c9993ef
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:e269f7ab774d5de1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:d405a3d58f2eb5f8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:e41c2f6e4b4e39f1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:24c704eaad608dff
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:e765943ae33a7bc7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:d1719af488576c27
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:0db6f2179e460cb1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:d13a3ba71be6faa5
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:638f788295d98a44
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:91442ce028be53ad
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:e1044519bc5ce4d7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:6242159ffa34418b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:84182a718a10d8b0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:8d211d1178ed72e7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:f74bc12b218cb6a9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:273c84ec62f819e7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:5fe09eda652c841f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:07b73df3f5c1e72b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:d22b38fafab3c46c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:69383bde1e2ed9fd
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:05220658f61aa7ad
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:aa4e0ad7f9beefa6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:383d1c1fa5e284b3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:baea77fb919fd116
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:f887fa30d4b4e910
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:3ea7f0475d446ebe
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-01 | stringing:772f42f27ad4d11c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-02 | stringing:763bd9d6a2e62f40
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-03 | stringing:8b2a636c8738e7db
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-04 | stringing:6d34a01e8f3bea9e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-05 | stringing:b1fef4804325d4e3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-06 | stringing:0f320d92ad8bcf20
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:ab358b0b67e5b753
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:73a8fdcf896c61b1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:7ae8811ca4a19af4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:8b189806951db04e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:93e5a0dec87aae86
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:12d7967ca99beb7b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:2cc01d0e359c6584
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:0201a0163d16f4f4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:7694658cfd4a7db8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:8481ffe613c81f91
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-17 | stringing:fe2b808090795e5b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:87a1b911dd9d69d4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:412e9cf3412b78d6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:296a109c7955e823
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:14e044c0d65bb474
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:7104435c8364ddc7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:33cf5eeb421756f1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-24 | stringing:15e51fae14555e3a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:30ae84db5fae34b9
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:5d57d0f2c266ed3f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:6524b4f57861b158
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:f212a4d4ec4619ea
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:b1ff63eef1b6a663
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:5fd6272c4dfb310c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:76c55dd00ae22a48
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:bfdc9dece4b58b50
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:6428723d83e04772
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:282ba17bf51c773d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:8c4926d9bab2b078
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:f523427f9c67b335
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:33ee841132b373d6
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:68751b115f755653
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:dccd32061c7e16f7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:36b05e84b7ff68d3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:d8deee3d3e36c544
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:e1a318a981cb72cc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:9a5ecd51f99f876f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:adb4d13349cc1f2c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:2575915d84ed05bc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:3abe8dcecd9229a0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:a933a8cffb594f14
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:8a3ac25e0be005f1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:2d1d17f906acdccc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:8c71fc9806b9c961
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:078a390da79b6c46
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:f87e05b747bd9d01
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:acf64c226349911d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:f03c8cbd351df956
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:4d9a90b76f1a8c58
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:85569aefa3a28ed4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-27 | stringing:505454911d7524cc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-28 | stringing:9c8831566a6215b3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-29 | stringing:526dc53a049483a4
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-30 | stringing:2e62476b649c5a56
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-10-31 | stringing:89004014a35f5726
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:9c3f10c41455d5ca
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:7d91fae480251644
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:9273c6d3ed682fd8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:c4f7573e16500fa8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:99fbc5121e77f6f2
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:0af9410b01e9b484
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:a4974c9a4fd57099
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:48c9d48bce67f6e1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:1a87b0c546401d27
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:6fa25b0528d8a678
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:e02972cc9a34d066
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:261119c054a92773
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:b8016e9f40cbce98
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:2963a6c1c8963614
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:bf1756acaf41f4c8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:a032cfc6895e977b
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:569a26c1168cd4e0
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:493dfb90254ac6cb
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:24682ef582c8ac06
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:8c74768bf55560c1
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:ff25cd4c040d4d46
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:76a3d74aa85d4bbc
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:0ac274ed0338b77a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:be89d1d962c6980a
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:0451bf2e5a04ae95
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:73696a1152d92235
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:79c7109ef43608ef
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:3881579c49f460af
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:5544e72d5d018973
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:7a27efebe809c2f8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:2377be935e343006
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:48695e1e2f013aab
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:4b9b1f5d5b85e93f
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:60724e947182a836
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:a1796a78e50fe9f8
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:abb5aa41f889e921
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:35f994d5691853ae
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:2b91a47ef6233788
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:c6424d2867da364c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:ac7adaba3687816c
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:e49bbc1225278eef
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:e9cd18691cba3ca3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-13 | stringing:67343c33e84b0e23
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-14 | stringing:19d360baf7510ddd
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-15 | stringing:7bb37a3c8d9e0368
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-16 | stringing:538fba574b35db32
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-17 | stringing:aff971c567983f08
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-18 | stringing:6fdced855f72f1bb
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-19 | stringing:a96486bf8637b6af
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-20 | stringing:75bbb7635047a3a7
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-21 | stringing:b78327707404ed9e
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-22 | stringing:0a6ddb81e9f6b70d
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-23 | stringing:da42f64cc2c3db84
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-24 | stringing:e082f8e29b18f4a3
METHOD_MISSING | TB 401 | 67/1 | 68/0 |  |  |  |  | Method column missing or blank | 2025-12-25 | stringing:73eec56f4708634a
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-11 | stringing:5e9e2a8a89e33752
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-12 | stringing:d4ff37d85ab4b589
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-13 | stringing:d2d26b0ef1ef7602
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-14 | stringing:9bb8bff8266ffef4
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-15 | stringing:a540c47c0c6799b7
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-16 | stringing:580433e00eecbf28
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-17 | stringing:c4d70b2b01a2aa7a
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-18 | stringing:f08f900bfe68d46e
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-19 | stringing:d00a1fd2dc40a7dd
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-20 | stringing:3bb589e64f58cd0d
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-21 | stringing:d6967ead039e8909
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-22 | stringing:bfb130887e564638
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-23 | stringing:fac5dbaa97b9b33a
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-24 | stringing:3d8c2fc8818b6ee5
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-25 | stringing:e8a14a5478baa5fa
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-26 | stringing:acec12f2fc366e18
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-27 | stringing:2861a2ddd263378e
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-28 | stringing:930739a70a92e434
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-29 | stringing:560563b38200138f
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:0ab5a1410e9b0500
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:f8dc7c7178bf22f3
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:afba13eb2e73a2d6
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:561e135b546011b3
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:7b0f0d9a82fdb061
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:afd8dcea1e770402
METHOD_MISSING | TB 401 | 68/0 | 69/0 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:3e65d7dd8f859e60
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2024-12-27 | stringing:28f0a1d45e135612
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2024-12-28 | stringing:c675282af9023c95
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2024-12-29 | stringing:3e5a8706eab52d1f
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:ede08c993aebcc72
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:f49da126965126a8
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:1a263b837fc963f2
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:d101ed96c273de24
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:e014384306fd584c
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:206a4a365bb64050
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:06b2ba16c57dd135
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:c1def5a6f2baf106
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:874d2121e59de0a9
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:282c5cda9186d311
METHOD_MISSING | TB 401 | 58/7 | 59/0 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:c905f85635856f3c
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-03 | stringing:bc19287add573d3b
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-04 | stringing:5a6c7478275ee6d1
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-05 | stringing:9a5607da06802519
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-06 | stringing:3984f0a45fce408c
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-07 | stringing:c58dd6a8a228d0da
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-08 | stringing:a55ab562ada0ef1e
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-09 | stringing:fb35d6f42b0b6441
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-10 | stringing:88cdee045792a204
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-11 | stringing:1486fc5a62f2fd1f
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-12 | stringing:acc690948ac03ba6
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-13 | stringing:b710c7f4c595aa86
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-14 | stringing:8e937dfa119bcf68
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-15 | stringing:282efa6689b6b571
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-16 | stringing:71d1a77b4ea3598a
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-17 | stringing:af59f58538b687c1
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-18 | stringing:230e3493166a3b7c
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-19 | stringing:e5c30a33f3df2c6c
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-20 | stringing:3b03a14bf785c13b
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-21 | stringing:4312b8dac84765a2
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-22 | stringing:319a313b609fc938
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-23 | stringing:81efb44424a49b09
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-24 | stringing:487d5ff6e7f04933
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-25 | stringing:d9429880e5f38df1
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-26 | stringing:cb8ef835f2071663
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-27 | stringing:dabcc297aab122a3
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-28 | stringing:b2d1afae62088e5e
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-29 | stringing:0c659850aecc7657
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:930246f5d7ed2971
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:0b84af3b60116e6d
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:221643b20021d103
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:334e6b6fc9e12601
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:59080d1c989146eb
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:5c7b189ae26aac7a
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:202506870dab953e
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:d357f9cce578d6f7
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:907d4738296ef0e3
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:734b1b9d01571a3d
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:164d798d2d657ad5
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-10 | stringing:bcdc98a009d3295d
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-11 | stringing:edcfe1d7113ef22c
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-12 | stringing:98bcdc82079c1f5d
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-13 | stringing:fe2589674d6d9651
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-14 | stringing:f1f7890163bea384
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-15 | stringing:9fb4098c5aea64ea
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-16 | stringing:00dffdd25b0c25ac
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-17 | stringing:788aefb40c6edd3b
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-18 | stringing:28be878a3f664e25
METHOD_MISSING | TB 401 | 71/0 | 72/0 |  |  |  |  | Method column missing or blank | 2025-01-19 | stringing:206d21f44f983119
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-21 | stringing:7a4c333e2a27582a
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-22 | stringing:818b2a1f9adba2f8
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-23 | stringing:970e4ab824152944
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-24 | stringing:974d8857c3549052
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-25 | stringing:79faad98e6430142
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-26 | stringing:3523b5f104e40a09
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-27 | stringing:b1631bd9a490636c
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-28 | stringing:b09a0e877bd739f4
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-29 | stringing:4839d25e0d1a2e37
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:ce135fdbb484472e
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:35a226e0dc44c3fc
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:94e4e171fe65fa68
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:9034722974048483
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:fad1221857bb6723
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:d1a6b891c34a3a9e
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:ab34c73910b07d8f
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:b7e8824af89de7b5
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:a31d0f4dc5934e34
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:8635dcf668c22b99
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:7d5a6931cff4689b
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-10 | stringing:b554224fa9d8c4b5
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-11 | stringing:e37dd6273520fb27
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-12 | stringing:96f2e0ab13410277
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-13 | stringing:0a170fd010b47cb4
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-14 | stringing:9b4d6f0276876d46
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-15 | stringing:28d2e7e5abc6bdf6
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-16 | stringing:def41d5ac80b8ae3
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-17 | stringing:ad44822bee38dab6
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-18 | stringing:6471588425665e45
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-19 | stringing:99a82f09402c059c
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-20 | stringing:1354442cde6096f1
METHOD_MISSING | TB 401 | 67/0 | 67/1 |  |  |  |  | Method column missing or blank | 2025-01-21 | stringing:99c8af055976248c
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2024-12-30 | stringing:f7560b65ef430dbd
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2024-12-31 | stringing:772d727e41af4409
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:358e97505ac73f6d
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:0accd09deddb3015
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:421da96bf4ebd1e1
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:f80815fc19bab10f
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:e328ff73081f1c01
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:fd536027169f1536
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:157338a308fb0486
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:3ab552bb89aad336
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:12186d575f9cc4d8
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-10 | stringing:16faf25056bc1ea7
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-11 | stringing:0fead5e862328a54
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-12 | stringing:c31127ad09e737e5
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-13 | stringing:863d5aa9b3fb207f
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-14 | stringing:53a1c89ac5e0c6d5
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-15 | stringing:6ae05544d71d59db
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-16 | stringing:0fe3d1ada7aedf42
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-17 | stringing:cd8a41114835fcc7
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-18 | stringing:8e41e68d7dac2e9a
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-19 | stringing:b72503daee72b89e
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-20 | stringing:614026dde3348abb
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-21 | stringing:55b9836fdf6afd5a
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-22 | stringing:6f79aec1e135e65a
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-23 | stringing:6b456125589eb7d4
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-24 | stringing:0bc8ce969ba52511
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-25 | stringing:477b552ccff08ad0
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-26 | stringing:4daccc698f1cbf76
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-27 | stringing:c29f23fb0466f125
METHOD_MISSING | TB 401 | 69/0 | 70/0 |  |  |  |  | Method column missing or blank | 2025-01-28 | stringing:0aee0852d5865815
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-13 | stringing:8bb45687b4b1a3f5
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-14 | stringing:ca5403863c9a1802
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-15 | stringing:5e45df1ca4ffdd25
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-16 | stringing:34f6f87aa8bbfdc4
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-17 | stringing:e191253263a7565a
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-18 | stringing:823006eb07aa4722
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-19 | stringing:6984ce88728183ae
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-20 | stringing:38fd8142e8f26be5
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-21 | stringing:3bedad4110a7e6cb
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-22 | stringing:a726e57fc015aeac
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-23 | stringing:c332f7e7eb1df872
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-24 | stringing:376c68f37c12f755
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-25 | stringing:a9d8f7a4f1eb07e5
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-26 | stringing:453d8503be5800d9
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-27 | stringing:202bb21ebb348a4e
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-02-28 | stringing:2b37dc097308a21d
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-03-01 | stringing:abc54a0e203fb358
METHOD_MISSING | TB 401 | 41/0 | 42/0 |  |  |  |  | Method column missing or blank | 2025-03-02 | stringing:9e458c7ed725034f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-20 | stringing:11d3e762d1760fa1
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-21 | stringing:0e7c11967bda0967
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-22 | stringing:ca1adb847574c289
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-23 | stringing:f1c827b5cea8b27c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-24 | stringing:ac17b21a13eb2a1d
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-25 | stringing:59e8e68e1ce36fbc
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-26 | stringing:8582c68bce7a9b8f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-27 | stringing:84b85489eaaba9e2
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-28 | stringing:ce532a30781b6294
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-29 | stringing:ce0169c7bb9517a1
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-30 | stringing:39915462844a61e9
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-01-31 | stringing:b0c68ee1b448ae7a
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-01 | stringing:098179befdd6bcce
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-02 | stringing:b8f9e2fd15da3e14
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-03 | stringing:f370bf4a2f52580c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-04 | stringing:a4ce640c4b83af4d
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-05 | stringing:9e52eba3e156bdcb
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-06 | stringing:fc04232fd8803147
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-07 | stringing:a69ff885e93fbb52
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-08 | stringing:8f05fcc2ad289564
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-09 | stringing:9bb05f4b58cd9ae0
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-10 | stringing:e0766590d3e6883a
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-11 | stringing:68ce70b1d4bd0ab9
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-12 | stringing:8396aa279e6f98dc
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-13 | stringing:a32f8a0c494a5b67
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-14 | stringing:97547d7721873d49
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-15 | stringing:6ef620d77efc4662
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-16 | stringing:bc17232090702844
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-17 | stringing:eb62d0f7e0dd7e5b
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-18 | stringing:8fd14e95c8f211e0
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-19 | stringing:c22619c390b3c0ba
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-20 | stringing:4039e7663986565c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-21 | stringing:da9d13fb670259a4
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-22 | stringing:92f167459fcad9c8
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-23 | stringing:fc5eacfa9c45884a
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-24 | stringing:9a43f955e594fe31
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-25 | stringing:aa866dbb64b3868f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-26 | stringing:4ac374c4b950866e
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-27 | stringing:df5efce1b9621874
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-02-28 | stringing:75a6382abea710db
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-01 | stringing:2dc667add075d9bf
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-02 | stringing:030717ee1962132b
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-03 | stringing:b1a251adb396e135
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-04 | stringing:0c76c28764a7a32f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-05 | stringing:e6ea8a49a67a49ab
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-06 | stringing:e4a9795a82d2eb26
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-07 | stringing:ac000288b270f789
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-08 | stringing:b0222bfac3fa9b75
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-09 | stringing:ead06aa277c8b63f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-10 | stringing:103fedcda72f76ff
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-11 | stringing:d589e47196b29c58
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-12 | stringing:e6f671bbe1657b34
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-13 | stringing:bcede1154a6df5fb
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-14 | stringing:7b4ea12a41a215bb
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-15 | stringing:40f14023533c6d5b
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-16 | stringing:af6975616fd70b19
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-17 | stringing:859f9cd38750280b
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-18 | stringing:10afda669cfa835c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-19 | stringing:aa095cd5ed86d809
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-20 | stringing:f49f9b5f31c8b8fc
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-21 | stringing:c58061eb4f064689
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-22 | stringing:f9ebf5df38d8a265
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-23 | stringing:d4e49a2df548005f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-24 | stringing:d78f3eec8380fa0c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-25 | stringing:b576d54540c9af2c
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-26 | stringing:ae9635f2e31b8fd4
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-27 | stringing:b3a1324bb132cee3
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-28 | stringing:b4e090293bf1364d
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-29 | stringing:d8a07deb3f7bdb90
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-30 | stringing:cf99e2116feeb9c2
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-03-31 | stringing:ab31243cf1a8ede6
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-01 | stringing:d2a25a3b4a0c7f10
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-02 | stringing:1931470cc0577700
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-03 | stringing:57de7fc86d373d43
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-04 | stringing:8f6e10a2515480d3
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-05 | stringing:48cfba80db5d9c03
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-06 | stringing:eef47844d38dddb7
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-07 | stringing:aa28ba8c0e3c975f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-08 | stringing:cce561d2e5990f74
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-09 | stringing:7db8a6874d754bb4
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-10 | stringing:31d340825cc3e056
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-11 | stringing:98b193b7208425ca
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-12 | stringing:a389f043346ec9d5
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-13 | stringing:c3c42aefa2302372
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-14 | stringing:a1f290e8e37cb842
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-15 | stringing:652a324ce24e0406
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-16 | stringing:49850ab383bc1431
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-17 | stringing:21526ed9d5be43f4
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-18 | stringing:3c50a8b2891cdb35
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-19 | stringing:440de4712af8f9a7
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-20 | stringing:73513da2bf6014e5
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-21 | stringing:03c78c9ef6178bc8
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-22 | stringing:1f8bf99b12551fc5
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-23 | stringing:75eca3254d9a684d
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-24 | stringing:c353468e698ccdd8
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-25 | stringing:8cb73cae3b8adc5d
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-26 | stringing:b4944dcbf11e3b80
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-27 | stringing:182f41a1d93f7a5b
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-28 | stringing:66ddd0d29a8746ab
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-29 | stringing:5116089ea85bc78f
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-04-30 | stringing:787bd379a28138fa
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-05-01 | stringing:736fa6f2040b28df
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-05-02 | stringing:5754ed05623a838a
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-05-03 | stringing:bc9d9513501a9906
METHOD_MISSING | TB 401 | 59/0 | 60/0 |  |  |  |  | Method column missing or blank | 2025-05-04 | stringing:6a9bd3124d62c886
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-04 | stringing:6ebe4a3c8402d03a
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-05 | stringing:2e5d69557e45eed9
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-06 | stringing:d16c1ae3c8628f32
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-07 | stringing:12ac12bd9a77f599
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-08 | stringing:8030514b5fd17519
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-09 | stringing:41d373e266acb757
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-10 | stringing:3b8611703f53df1c
METHOD_MISSING | TB 401 | 42/0 | 43/0 |  |  |  |  | Method column missing or blank | 2025-05-11 | stringing:24a2c795d8aa8c93
METHOD_MISSING | TB 401 | 49/0 | 50/0 |  |  |  |  | Method column missing or blank | 2025-05-15 | stringing:76a2df1ea6a1baea
METHOD_MISSING | TB 401 | 49/0 | 50/0 |  |  |  |  | Method column missing or blank | 2025-05-16 | stringing:e65168a6939f6ea7
METHOD_MISSING | TB 401 | 49/0 | 50/0 |  |  |  |  | Method column missing or blank | 2025-05-17 | stringing:e0b602b550345c8a
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-14 | stringing:909d914919660f4d
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-15 | stringing:bbbb121c2882f0af
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-16 | stringing:895266c4860fb446
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-17 | stringing:a4054b34d0e6d9b5
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-18 | stringing:a30f27b5a731a4ee
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-19 | stringing:9b827ebed8a4e51b
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-20 | stringing:d98b4ffc7dcaeacb
METHOD_MISSING | TB 401 | 48/0 | 49/0 |  |  |  |  | Method column missing or blank | 2025-05-21 | stringing:61c31eb75694d046
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-19 | stringing:1340ebedae425540
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-20 | stringing:9501026c99093a55
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-21 | stringing:790eb4c46b38084c
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-22 | stringing:74ab0b4ed795140f
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-23 | stringing:ea2a9cc0439966dd
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-24 | stringing:e49286630c5302dc
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-25 | stringing:5596d53924bbea52
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-26 | stringing:4b6beb6aa00c3c16
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-27 | stringing:7fc063a924f69959
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-28 | stringing:0cea583302c54d76
METHOD_MISSING | TB 401 | 47/0 | 48/0 |  |  |  |  | Method column missing or blank | 2025-05-29 | stringing:e3f23bf327b116b5
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-24 | stringing:8e72d3e7221e9c10
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-25 | stringing:4137506c27bc4ad4
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-26 | stringing:0d81c06379d3d088
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-27 | stringing:4e530646dd3cd7bd
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-28 | stringing:3b613fcaeb3539b0
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-29 | stringing:53f8a7e743c1a40d
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-30 | stringing:022ae3191cad2891
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-05-31 | stringing:f4bfb66c88105744
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-01 | stringing:af32a158e16eacaf
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-02 | stringing:123cfc3dca181d20
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-03 | stringing:f334c62e682d44da
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-04 | stringing:94eaae9a0462daec
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-05 | stringing:7cf26306c28a4cc8
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-06 | stringing:0b74dc316151a144
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-07 | stringing:9e2ba2e94f7f88f5
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-08 | stringing:16f95d08294f4606
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-09 | stringing:423bf095a3758e31
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-10 | stringing:9eaf15a2802b67b9
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-11 | stringing:6af7324947f1245a
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-12 | stringing:84f7b76a5ee7acec
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:88c6b058335e6bc8
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:9feced4fae573270
METHOD_MISSING | TB 401 | 37/2 | 38/0 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:94b1877edeefa034
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-05 | stringing:717a9978cd46b977
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-06 | stringing:18938d9683bb8173
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-07 | stringing:4882bb9ae6f59a2a
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-08 | stringing:736a929ebf92b919
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-09 | stringing:c69705c7b65d655c
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-10 | stringing:fb1b50fcece034f5
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-11 | stringing:b64f5f003aa6f43b
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-12 | stringing:2bd766cedcda9b43
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-13 | stringing:0200356c0bcb5f29
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-14 | stringing:275536a36626efbe
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-15 | stringing:cc4c5c65094b7923
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-16 | stringing:656ec9698641c0b6
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-17 | stringing:e9dde6dd1862e78f
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-18 | stringing:dfbd8eb6a98720c1
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-19 | stringing:0e0a028d7007c429
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-20 | stringing:93745e4f2b60b7d5
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-21 | stringing:6bf287346ffbda63
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-22 | stringing:3fc53ac81bb6b8f8
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-23 | stringing:85333e99df703f58
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-24 | stringing:85328dca618fbae1
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-25 | stringing:a6293bbed9621486
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-26 | stringing:b90a919188b9de9c
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-27 | stringing:5d143b3b7229ac18
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-28 | stringing:c2c1b56fad006ebe
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-29 | stringing:70350ad37dafce36
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-30 | stringing:b0921bd4e07ee379
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-05-31 | stringing:fb29bfc16fa4c29a
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-01 | stringing:d1a9da179b926453
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-02 | stringing:deee87b6331239aa
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-03 | stringing:909bde7dee54af64
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-04 | stringing:d732e186a2315f5a
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-05 | stringing:1b4b6ce90b9bcb7c
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-06 | stringing:daa50d000e3cb15c
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-07 | stringing:fa8de7fcf96f15f1
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-08 | stringing:853b384bd19a910a
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-09 | stringing:f721862afbf54784
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-10 | stringing:b5516f3f4281cd1e
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-11 | stringing:8b1912efc37db710
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-12 | stringing:e6acdff3c5fa0424
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:b4ef26dfccf15970
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:d376a56b4e9d3581
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:4f33f678b69dbd8f
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-16 | stringing:46419de214bd41b8
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-17 | stringing:532483121748f361
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-18 | stringing:56080f3a7324ea03
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-19 | stringing:de9acf2e0d4cb158
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-20 | stringing:b2722a2d7e842dbf
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-21 | stringing:7196f1812a87244a
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:e9a82673358fb69f
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:742153f163896e47
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:1f1522f9c75f5698
METHOD_MISSING | TB 401 | 43/0 | 44/0 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:9bbacf336c544df4
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:3b5249d045fa6563
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:2a7a69a32202bccf
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:21a8dca77b12d25d
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:e8871d45c4a22f32
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:80f7daf18ca4e440
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:a8459263633051d6
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:6091cd28ee54e2ba
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:1eca226509885a19
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:227a868eff83442f
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:84f1ec9542a003ae
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:e3bd3140e2b8ec82
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:39707bedf5bcc290
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:c68dbd10b1e90f83
METHOD_MISSING | TB 401 | 61/0 | 62/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:9024f534dfd8e8cc
METHOD_MISSING | TB 401 | 62/0 | 63/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:3256f3bf3e64224f
METHOD_MISSING | TB 401 | 62/0 | 63/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:461c365eaf529743
METHOD_MISSING | TB 401 | 62/0 | 63/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:433c02c3791ae95d
METHOD_MISSING | TB 401 | 62/0 | 63/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:2f1091ba0a7c2f04
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-04 | stringing:2342b10a880df3d7
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-05 | stringing:07912ef3635a4d3f
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-06 | stringing:f8a817b40f5f01d6
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-07 | stringing:cb96fc5d315a6b46
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-08 | stringing:e2f79ce5aefa519e
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-09 | stringing:c2f90f62a7a7c271
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-10 | stringing:acd2e579411c1d5c
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-11 | stringing:8458cc0dc9dd3418
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-12 | stringing:d1f5f55bf2757860
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:95a0497ede32ddd8
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:e48d7b581c74aa3c
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:bafdeaff5c50da4c
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-16 | stringing:0b8ec9e55eddc21b
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-17 | stringing:4daaf375925991f3
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-18 | stringing:ac1b88547a005c8b
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-19 | stringing:1683baeb1ce947f6
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-20 | stringing:636f9d51419246dc
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-21 | stringing:e8af1a081be4e877
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:3a9af10cdba35629
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:0822f59bca7de301
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:738ac2008ea24910
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:68a5d47e00ab9213
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-26 | stringing:c6553760d21b4db6
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:f93d03a97fc3caa7
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:563be2305ad66d4a
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:f3c33ac1ceaacaa0
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:d9a3bfb09c9b2aac
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:c7fc988f43898f17
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:2a813c35909ace92
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:c1a6cac3980af98d
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:761ade764daec8e9
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:28997e0afb66a5b4
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:afe728fc03e015e5
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:cf5f1986f58d6fba
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:83f5f471643093ec
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:bb07f0c06cf696f4
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:c7a59575d10d34be
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:7021c532cbaf9485
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:f3c75440759928b6
METHOD_MISSING | TB 401 | 38/0 | 38/9 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:7119443dca47e23c
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:78220c85694c2868
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:5964026a50aa4d10
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:c44fcc2fd6498a74
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:8469f3b9ea313a93
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:25aabaa410d921a1
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:aa402f8513f5fdd1
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:32ba9e8d395f1237
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:839f0b5866c14067
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:37efc6802a0df68b
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:b68ddb59ac35d6a6
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:998c86e3fbaef43a
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:3c9269377cb1594a
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:61125aa9445481d9
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:445e5a1f3c30ed7e
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:40a98a522d4ee1b6
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:d292b2de4e80dcd0
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:d218b9e5c7c7564f
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:c32e006edcd9426d
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:4ee4421418cab84f
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:19447b55b2292ea4
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:74afec6c3428b523
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:159816a72a84b12f
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:7d38cd3a68c27881
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:0222c28d67694de3
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:5c0fa6750780b238
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:73c0064230dd07d7
METHOD_MISSING | TB 401 | 40/10 | 41/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:dd28cea9f87185f2
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:db0a71f99ff31c8a
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:e600925ff90e2f83
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:28a11c281a3433ac
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:d602d95dbf78755b
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:18d8512440153e13
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:8e48178f6428e470
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:a7f33f8808a11bc9
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:b8da49f2a9aee33e
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:df215ce83a967124
METHOD_MISSING | TB 401 | 63/0 | 64/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:8dc298038f2c0496
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:7025332ca55b26f9
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:64b8057a1fb3fe50
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:2654e5644ced96ec
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:f225f2419554be68
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:fc00b402178e0c12
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:3210a8deea071991
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:38960146af1105a4
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:acc3bd6054918dee
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:b847f9ffbc11f08a
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:6cac1291f97f7233
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:1618283fd1705096
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:92a2e3a11bebb133
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:114b318cb4e93e7f
METHOD_MISSING | TB 401 | 39/0 | 40/0 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:6955d7e43e6a19c3
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:704fea239ab1ee86
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:a632dda9989582c5
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:70783c88cb9d6c12
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:c301c7c73f6b4613
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:9abb41c2bece448e
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:94677d71fbb7ecb4
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:a955c4b331902099
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:032f66697e7e868a
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:67c49665b13d81fe
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:eb55b1b89966f534
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:c02afded18c78e39
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:b4163e0f677f3d21
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:00a7649cf91f8551
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:e7100004fe1ce1d4
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:bb6784bfbc59bdf6
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:ced3092c5d101a1b
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:6bf94e90b31cdf04
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:97c5858a554919c2
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:0a2c4a3a7154e58e
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:b484071cc667b571
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:a9cf9cafde5c63c8
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:c2543f064ab01f05
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:294014bb2613daca
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:d8b614bb66f6de37
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:82cfc606ccaede62
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:3805e763c412d99b
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:c5b0e42ed79f6ee7
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:25e07a7ef88d2410
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:fdcd30e2d29f497f
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:0ed6031aeca961e3
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:f009e2935fbf5880
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:06fe358c41d781d1
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:c98efe8546ecc8e2
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:2e79c6c7cf7d2df7
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:52676fb26c2ec1b9
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:49784bbc5d9f54f2
METHOD_MISSING | TB 401 | 40/5 | 40/10 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:12148084f6b7e611
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:d7d774e8436db76b
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:7986bcc9938aaf62
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:2d6ae3af9200b06f
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:c789ef2519577d00
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:d394a08ed5720ab3
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:8b134e396a240d50
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:b3f652d98f0af3bc
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:f12a81a690800886
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:f2ff02b6e9fd415a
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:bc80dea826878b91
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:64f4e33078d39a77
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:e474501026c7bdeb
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:36171a8cd80234d6
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:c22a685ec8fc6aba
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:734712e35b38f8ea
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:f13aaa179d031269
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:d5af8a827d176a93
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:3e627089ad327583
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:65a6651d8d620663
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:77f90a1e2abd7275
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:8d7332b5e7ebf1eb
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:9bdb00139486a9a8
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:6a303210fc26859c
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:b28900b4abf650a0
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:af09023079aa337a
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:9e64b3fa66513fe8
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:f317ec8d19d2c40d
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:0bdd09ba63a4de80
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:149c55654992ce11
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:c98cae97d3f683d6
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:4de104b6e6971db1
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:d2ec0ae55a5f0c7a
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:f031f53376784846
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:ed9352799cd4668b
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:106f4eed490062a3
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:b8687b3338581b2f
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:1bfdfd7ec508523c
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:340360fc207589de
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:c005ca6c7e502d4e
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:c53a0a0376345f72
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:5fca14d2dfddf55d
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:bbcb303036ec4de9
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:6a5f1ef75421bc1b
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:5e6619bbf6544dd0
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:ac611a8181114844
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:47b902a71dd0f328
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:b1ccaf41a243fd28
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:b8570c0e713c7e41
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:583672ec71ba8225
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:60aaeb0810725fc3
METHOD_MISSING | TB 401 | 38/9 | 39/0 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:574f0578968320c2
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:5bbc704351cfdc37
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:b9761c41e91f8af5
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:6d72e1a711911b9c
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:b9f9603895b676ae
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:ed36b8d75063b6d6
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:0db8e86d8315b7be
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:bca081f49be51b5c
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:817413260c4840c0
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:9da9070cf8bb0a15
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:e6d380c5064dcf6c
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:85d0e6356967051d
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:6e2452f9e4a9f270
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:7bb860f96b2519e3
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:f41d473d06bea894
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:715c3fe4b3bafacf
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:c8aeae601d6c3ef9
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:0a93332e2fc021e7
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:9f13e4ea4b204dc3
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:a9b1a7dd14b5f3af
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:4f309c165998ad38
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:92bd7a7b5a97e215
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:4b77cebf3f3edd49
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:eafa7ded2762949f
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:300e5751898f4893
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:201ea03bbeb2bba9
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:a15b08a3a3b273cd
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:ad485158c8609702
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:d27fee8c65d8e503
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:af0e3acc328a5fe5
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:3ba7f8c0f224e007
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:7d5d81dd8c9a1b0f
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:b9535b3aed2d57a4
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:bfe6e54b49b6d415
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:144ec19c53cf7ed2
METHOD_MISSING | TB 401 | 40/0 | 40/2 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:a1beeb2cc4c830d6
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:e5cd104f56e8f529
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:db8ec6426a4f377b
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:d224bc5db9b313ff
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:88497faf9f00962a
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:3dcb0dd5c0b57d47
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:0a60bdc9486cfe5e
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:662ea4556b513aa8
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:ffbbe68360bf696f
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:7407eb040a754a96
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:653f7ab2c2f57487
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:7cecff64d63501d7
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:5353db98d962cc97
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:e64356ae2097d94a
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:9f0d8020a47d1c09
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:c299955a59f21606
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:d2aef13cb604be48
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:397fa2bbf6f868aa
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:3d07453076eee156
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:0b734b1e9406b8e9
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:06c65c465fa03f88
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:08bbf944c3f6b481
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:f891cfd7aefb1e9e
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:dbf02645cd21393a
METHOD_MISSING | TB 401 | 40/2 | 40/5 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:eff93db68d748a21
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-04 | stringing:8bbf4ce832863bac
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-05 | stringing:d4f2b80f0319503c
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-06 | stringing:00cc671ef654f4dc
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:f5a011210ccb4764
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:47af664258fbc630
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:be6d9804ebadcc61
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:1b155c32140b4a10
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:8e8fe2055b296c79
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:59ef6ee0a63dae2b
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:edf36ba9b796d392
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:deef8ed9f4bb6d6d
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:eb2b0d265e7e643a
METHOD_MISSING | TB 401 | 66/0 | 67/0 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:0f88ef1c3202b3d9
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:fd77966bbb403369
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:4a58c7cb1a5fdc70
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:4adabd9264ce9322
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:7ff58afc7f9db18e
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:833b19c0231bb8a8
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:e2ad76a14afd6c6e
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:7a427f565e87d199
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:3e8218da2f94d3db
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:ec52615911e7de09
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:68dd8be72c0e6d98
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-17 | stringing:119208c24051e443
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:f504667627e0b59b
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:ae8067c8a6764cbd
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:fd3c9ed5bcf75502
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:a820d28e2c21489d
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:c87e5e35ef5ca32b
METHOD_MISSING | TB 401 | 35/0 | 36/0 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:2c1128beee2045cd
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:53f0eb339f244264
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:d3caf0758911e0d6
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:1c0c27ccbcc2778e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:49a96ba5f6c6eb6a
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-26 | stringing:0897abf4d9cec018
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:d9d6497403591607
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:4d15735c01174859
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:d6f6b025b77b7f33
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:23fd92d66ea75fcf
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:c2a222083fbaf770
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:1053ac6db1ad78e9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:85bedb2cedbd6003
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:ec2b9d84ba1d4126
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:15c353ef92dc68eb
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:ca5146659cc127fd
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:00882224a56658de
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:deb3567d69f8da8d
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:8d6bdbe986726766
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:a6206291fb0dd809
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:ec6bd8a90d0bbf26
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:99860a185d145831
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:6f1b5cc82747f392
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:54d29ca5ab858bfe
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:6944e9a6e04fc8ab
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:42eadad573af91f3
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:93546627f1ee2029
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:5a39d448444cdae8
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:b51b5d4446e69647
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:62d0c88721a95489
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:86c61279918d09b9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:684408c89bada564
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:6a9ec8810d73b565
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:40039e11fd379f9a
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:e0f19866f06eb961
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:04bbf69051753074
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:1040d63519590926
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:1140715f918c9c5d
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:a9e2c7ab8c135542
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:52a3ac162fd12c32
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:97e058f70b9492a7
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:371a8e9ca74077c3
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:69e6305706824725
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:f629b0ea946887cb
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:43d1c807d767b527
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:90876f4c33778b0c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:97e2bef34c20cf5e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:594f0494478c949e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:a68cd18f7587a35c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:ec61251cca34d161
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:c3fd18e93ae10459
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:ad56a573ded2356d
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:5d62fc30004ede81
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:e27638d49b42fa36
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:660db6ac6819016f
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:18265c88a4a39e4c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:f7965f207c5c0a1c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:1485950d6a2af5e1
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:eaf2dc5a25f35a3a
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:dad6162e53f84248
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:7a22b27f35a7551a
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:883f097b29a1965e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:bd192f648be3c491
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:42cc611387f468e3
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:3e8893251d457911
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:e7ea933f581a092f
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:36b0ff3e14ef9313
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:a7f63ccde2edc440
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:f08cbf53ab4d0875
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:68ccfcb452d69717
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:6c9bc9930ff1e3b7
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:14316b8d29c8f438
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-01 | stringing:321c29d5e7d1e2a9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-02 | stringing:6d01a7cd712a8121
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-03 | stringing:5dd704140fc066b9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-04 | stringing:dd4fca0c6fe30801
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-05 | stringing:5aacc6a41f71aa06
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-06 | stringing:8b211237860bd814
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:ad7135ef9d5495ee
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:0b77cf5e8a520f7e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:54b29c373462d9d2
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:9d94a63a171ccfa2
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:47c1ce469cfb2bc9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:f6812d601712bb73
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:db7e9670aff582c9
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:0da27e30bf82486c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:c971d5cdecd8f387
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:67f3dd2d1a88a48f
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-17 | stringing:889f7f1dd5be66fa
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:f6b956117f645297
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:c57cf3c064cb9349
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:b23beeed4f0e3ae5
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:af2772a842c23562
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:44197d52498c2a54
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:4990d2ad16bfc576
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-24 | stringing:750c00a70a05f59b
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:472caf609a658fa8
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:95bbe442f7d3575f
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:c5e395c9792216cb
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:b0aef22c04d1de12
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:844796fb71e51a93
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:64b0327d280485e6
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:597fd9cabbab9296
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:3da717ac2114bb8c
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:feb1a3c0256fdcda
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:0a677577ced34bef
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:69373e74fa607c65
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:c4cf030605bced00
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:94abfd268d72e19e
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:37186bae2efed086
METHOD_MISSING | TB 401 | 46/0 | 47/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:11e0d14899a2525d
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:42cf833624ce3457
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:9fe7d7f79d9dc293
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:238f96d1499e52d6
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:18a1bffcc7434956
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:073f544f6b8d35a5
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:ffe872a64c30d045
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-24 | stringing:e028a14a2662e545
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:3e306a0f5cdee1ea
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:776309b000936b59
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:d7d9eea109630b9e
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:3d23dd56e2c3153a
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:26cfc3b7e735791b
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:f6817d071c4efa54
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:8f6ae2cd2d586fb5
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:6b67a3a1151f66d6
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:df615d39dc3d71e3
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:7d7638c35fea302c
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:a34a3477b01b8769
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:1d930ef11123dcab
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:3bff69a0f48bf271
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:9677dc66716b293f
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:49ee9f5021b4c2eb
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:dcd0c2f59fd0b012
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:544eae5ab412dec0
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:0cdd7216fbd5d300
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:24ef573cd75d9bff
METHOD_MISSING | TB 401 | 31/0 | 32/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:94d58eef437dde6f
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:0c190e18c31cbedf
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:3939d3c55e3f8ef6
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:0726c888d169e811
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-16 | stringing:b5e9b85517ae15f1
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-17 | stringing:3a4b2ddeeb100f35
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-18 | stringing:ff2521a964f6cdfe
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-19 | stringing:6a07a082a7c7931e
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-20 | stringing:081621fbd9671f2b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-21 | stringing:5aca0e740722afa3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:ec62bb246d54a181
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:a98ba401caa11c6f
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:1dc5a3f837f247ab
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:5f96abc83f514b3a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-26 | stringing:c7b95f632301d75f
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:3b92e1f29c96fd06
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:e1bfbdf2ee99eee2
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:05261aa443716ffc
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:8949894bb1e69437
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:6371bc4ad58690b5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:4f94887168dc59bd
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:0f2a8c6f3cba56c4
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:5d6cc2479eabcdff
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:d93c48d314b093b0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:35ab6dcf434b1ced
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:fa6c0afe09bf676a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:5e226157b0e1bb21
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:dc5ec0ae83039b2e
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:8b29175969686253
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:6ffaa3b6c1816dd0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:1d406adeb1a907b5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:27d90b4ec7702da6
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:b766ff1eb5a1e540
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:72433fa03a870418
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:71750fd514d23925
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:69212fc49b67b2c0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:c074c96570859854
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:67a070cb87541c62
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:ff82d13759dec3d3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:aee4b2d498faf8fe
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:4b9900ea5b3284c3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:123a60ae757cc491
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:3cb64068dd02a69b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:b6c723d03fffafd2
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:7f3697f58ad8cee2
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:3c789645c284de2f
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:3fe9194daf7a09ef
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:29942d76eac0b2f0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:048367273d759138
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:7ff64b819762f254
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:3d5159acaa5bc117
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:275bee301d4f8ce8
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:054a65c60e91a53b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:0eda073be42b4977
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:90af0653c39c8289
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:e122a0e1db94e876
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:070bc61b57cf8718
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:5e7d55569fa10ab3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:6f3574b331693959
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:e29d7f835c9347b5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:405e07be6a58d1ec
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:d1f81a04a67ee66c
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:e232f81aa9c48867
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:9ae7d4e279a591b5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:357920a59bba4f49
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:c56757ece65f306c
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:f1570a6aee0ea8cd
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:f496d31c957e42ac
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:291e298da1c8d820
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:874728c649e69454
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:3ded40d0d3ecc7b5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:5db4054605bdb376
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:44b83aa0d95e4fd5
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:0d4acc39ebb7ba55
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:6936cab3c30abc6b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:b3d2839d5a5f1978
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:e61efcea9a5efdc6
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:a46653f1a7ca006d
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:ff4e259e333d83b7
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:f55bedadaa41ff86
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:6129c62d6434274e
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-01 | stringing:8ff29ed1b68c5f62
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-02 | stringing:09ba6396c7e76612
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-03 | stringing:3a0ba7db8e1d7d13
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-04 | stringing:59c071d83f0226f3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-05 | stringing:392c6c859595e25f
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-06 | stringing:63a002a1dd951f39
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:71443e281026549b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:112932a4c4afc679
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:db2936d28903699c
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:8894086eee57ea04
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:64bd2fdd1544bc96
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:4f6fd71408fec7c6
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:9f343162c7396b69
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:010c3c3254920abe
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:71ba013ecfebf08e
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:06249a5d460d66a0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-17 | stringing:13edfae6e02e0663
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:51c134eda04fe95a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:7d7401d4254bf494
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:c553bb5712fbad2b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:eea4e6b0dd925c6a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:dcd506f71b0659da
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:0102fbb6b4ad7b60
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-24 | stringing:72ed7d037b85e2da
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:9c0db44436bb0b4b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:b02cec85c7d7ff9a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:960654e941e7abfc
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:2cfdcc747551419b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:76ba50a4ec84e71b
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:3e4cc443f38c046a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:c17e098b70c32a86
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:f3e210369cc01bc3
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:feb151bd1d791239
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:7fc6e0b11eed6973
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:1ab6c851e23bd7f0
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:1aba0f1f1dfa25a9
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:21481cbdf98a76ef
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:e598134f2a7b1bea
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:6ca731b220a92c8a
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:e3d407ff5f08a0ae
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:e1a20120226f50b4
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:4921671e78d7eb63
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:9ea253712547aac7
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:f6fa4936dbd55485
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:67f81c9d4970bbd9
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:cd86ccff9a9bc4bb
METHOD_MISSING | TB 401 | 44/0 | 45/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:68bdbb7d5c10f57f
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:dbca2867e8e6bc3d
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:8cc9eec8fe6be241
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:288a5e576dcd2809
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:de5913c3d0228070
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:4fe8685da8a81b6f
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:63bc949a7a584a52
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:aa976d37e006eddf
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:d9a543a0b0a6a32c
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:d170fcd4a627d565
METHOD_MISSING | TB 401 | Gantry | 1/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:e2b3e6ad788b5b93
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:5e1fdc092a036c97
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:360d20ffd11d4f8e
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:62accb64a512b6b7
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:f599015b886d0869
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:93618251c38a3368
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:f8191f698974300c
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:9bd63e49e100c25c
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:0e74169a6b5d5a49
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:d030f3153e89a15b
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:e427befca205a122
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:bda5c6ff11d02d39
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:83ebabfd5c2d49ee
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:f403aa45d7585922
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:8884b903722705c1
METHOD_MISSING | TB 401 | 65/0 | 66/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:b0c047cf9a896c5a
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:1d6f416fc5833130
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:21019dc500c24385
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:f1c12c5bca351158
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:633eb1d9f96bcda0
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:d94692278addd7bd
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:cbf8a784c9f5fff3
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:bfc11e0aec6c1175
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:431196738ca58605
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:357e6ee7c2bc94af
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:318638a7ac26be33
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:2b31298841368546
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:795aab5b570b20f8
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:e0acb8ce565c0ec0
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:76d95e546853b6a3
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:e742d19d4b20b707
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:59cb7e23346eca78
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:8b07438edb140886
METHOD_MISSING | TB 401 | 1/0 | 1A/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:e0be072ae0dcb5d2
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:eb5aab4f3eccf44a
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:61a833a6d3d15003
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:990da136088d42e4
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:71ee501f348aef71
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:a1ce3a3ca6e46dd6
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:3e9cbddc4d437e05
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:73ee8e860cad48eb
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:778937de7cf24141
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:09fcf299484721d1
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:ba0f0430cdd53af0
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:902b681c7926fe3a
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:ef179cb1054aa261
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:a6a6d8355444951f
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:16098b038a40c2b0
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:91b8a4681734ecab
METHOD_MISSING | TB 401 | 1A/0 | 2/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:b82bd716b28a1318
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:ee8e61c3363298d7
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:f73c52b8afe6426c
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:2d5082033d9a66ec
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:fd283b674c98a2c2
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:21b1eb1ddf8b6103
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:2c6c60be799f03cc
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:18c6e3510ac39198
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:3187fa3f82421227
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:ffa1b390c0f2eea9
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:88a703ee302a7709
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:3817c941395c78c2
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:4ae4213833f31225
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:66cc90de0e719cd7
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:298eb7860b33aa2f
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:bb0f838625659107
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:fdb66a4292ae8e10
METHOD_MISSING | TB 401 | 64/0 | 65/0 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:14985dab00efeac2
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:f46a4495e1b8b28c
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:0d082fa6e4487621
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:973990f74fc613c8
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:265565590b1b4be5
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:8802753f384579d8
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:dd600ba60496a010
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:27ca5d2554d717cf
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:255bad8cce732e28
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:eb3fa3e346e28697
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:f38c4980abedb447
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:91d15d394195db8a
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:db5f0cd2699486b8
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:30272b58f3505056
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:3dbac40aa5612a93
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:bd0c8ee77a2ed357
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:e1adc9d123117c6a
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:93bc67fde7a071a2
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:99e8a111494f2c68
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:649cdcaf787f08c9
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:78124a6b0167da9e
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:6e411788e80514c0
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:b8387f77462252d9
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:f0ce338cf4e6ff93
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-27 | stringing:03158f463133b89e
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-28 | stringing:785a230fe99f835b
METHOD_MISSING | TB 401 | 32/0 | 33/0 |  |  |  |  | Method column missing or blank | 2025-10-29 | stringing:caf77ea90babcfb8
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:9794567b203af5d6
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:8ba1c9e135ac4145
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:0254aa18b38b1f40
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:3e968a0a929b099d
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:76983b361cc3dee4
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:4815ac4d61357530
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-27 | stringing:717adb38c8efbf7c
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-28 | stringing:282c18639e1d6215
METHOD_MISSING | TB 401 | 33/0 | 34/0 |  |  |  |  | Method column missing or blank | 2025-10-29 | stringing:4efd4ddbe1961ea1
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-10-30 | stringing:fb450c9ce5c8baa7
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-10-31 | stringing:8fce6bb5d7a3c135
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:434a9c5f122d67b7
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:66d7894382db0ebd
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:813c24fc5aa9ba26
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:97302261ce1e10df
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:9219e0015767421c
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:691d4da81c616879
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:c783bb0761a13546
METHOD_MISSING | TB 401 | 36/0 | 37/0 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:b154118647fd0c87
METHOD_MISSING | TB 401 | 60/0 | 61/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:510613f9e34d1f86
METHOD_MISSING | TB 401 | 60/0 | 61/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:6825ef66cde7f9ab
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-01 | stringing:c22407ecd7d1dc33
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-02 | stringing:4cab8d7107a074bd
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-03 | stringing:b55908bc55fbd2c0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-04 | stringing:3a58f958dd0b3b2b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-05 | stringing:fb8e199d8e92bd5b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-06 | stringing:fe3f0356835ee61b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-07 | stringing:bff8ef973e45ca87
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-08 | stringing:4c1e0c05f4e650c0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-09 | stringing:ebab3e7d7fa3dd8e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-10 | stringing:d8d46e0f1098a6ed
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-11 | stringing:77a953eb33416109
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-12 | stringing:98d01b6489164c41
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-13 | stringing:92abf44c75a90067
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-14 | stringing:781b42d33e35a094
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-15 | stringing:8f40a8ef685d2474
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-16 | stringing:e2271d37fef88d4e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-17 | stringing:a6aa817318a8ebe2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-18 | stringing:4e72c3ec5192be39
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-19 | stringing:3cc72db361976707
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-20 | stringing:e654abfee9a644c1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-21 | stringing:cc04ef46bc7ff3e7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-22 | stringing:9e36e156d9e8976c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-23 | stringing:9272f826c200a98a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-24 | stringing:7799dd275a6bcc9a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-25 | stringing:0eaf01f62fe3f0f0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-26 | stringing:a044b8c775fed1c4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-27 | stringing:aaccb650ec26793a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-28 | stringing:a7e0b9d407a03d60
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-29 | stringing:8dfffd6c8aef26d0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-30 | stringing:540c62c94dbcd851
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-01-31 | stringing:eec2f41b7b3080bc
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-01 | stringing:410a172f869a1b74
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-02 | stringing:29680dd53475297e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-03 | stringing:f43b57eb83bbc4a0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-04 | stringing:ff3cc8c082bfe38c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-05 | stringing:633d0d5e62b57936
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-06 | stringing:4282c5e6dfc55638
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-07 | stringing:fff3705a7521d7bb
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-08 | stringing:21a5aa67613dd918
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-09 | stringing:6cd33ddb473e4531
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-10 | stringing:169fd5ec826330d7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-11 | stringing:beea9b4c3ed55496
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-12 | stringing:3c5a1b823fd26c9d
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-13 | stringing:daab2c7cb89784e1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-14 | stringing:f842121ed3324356
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-15 | stringing:abeab681a8a26b1f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-16 | stringing:fce6dfb823da1639
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-17 | stringing:d46af3958b560946
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-18 | stringing:553f344adc8f252d
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-19 | stringing:97ed2a09f9b69e5e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-20 | stringing:651e42fb8b36e092
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-21 | stringing:70cb9782bc5e03ce
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-22 | stringing:79fb14325790ac72
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-23 | stringing:a6f390e0e56d91b9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-24 | stringing:2ef6a4f199741896
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-25 | stringing:e3e9ac5a4b35bbb1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-26 | stringing:4febb1c9f00b02cc
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-27 | stringing:726cbedcf61a88c1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-02-28 | stringing:5ca63132fe0780e8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-01 | stringing:eb8ae1769df24221
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-02 | stringing:33479ed3a73c070d
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-03 | stringing:14fcef68a40bcf74
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-04 | stringing:8de40f0bb968f4ec
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-05 | stringing:61f598b7b6360bb6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-06 | stringing:e10621d0ff2b6c45
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-07 | stringing:a2c50ed8460741ce
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-08 | stringing:f1d0586ae1df9add
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-09 | stringing:edb56b91b718b8ed
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-10 | stringing:a60cac79807677b4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-11 | stringing:a765f8394be71f10
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-12 | stringing:f99db9d3a3486a6e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-13 | stringing:783c8a3950066f8c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-14 | stringing:10870d2997d86b16
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-15 | stringing:e797e666c5178037
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-16 | stringing:8a544bd579352405
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-17 | stringing:0ce4d38fb9e12347
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-18 | stringing:9183b95cbf6e58ed
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-19 | stringing:e540e73d3bceb114
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-20 | stringing:63a160dd4e49ca2a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-21 | stringing:83f59475f277d03e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-22 | stringing:105c502ab0d30f53
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-23 | stringing:1ed9bf90a6616d3e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-24 | stringing:fb30057b1b37c8bd
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-25 | stringing:1df53d56ff3e1c07
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-26 | stringing:bb3aa07db42ecb42
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-27 | stringing:7e1f914fb5e1ef84
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-28 | stringing:58b1d49afeb00551
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-29 | stringing:31ea13e4cf587d30
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-30 | stringing:cf17534ac3cd097e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-03-31 | stringing:2f6c63d533f23c80
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-01 | stringing:93cf8010fc796dbb
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-02 | stringing:360ead9567902267
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-03 | stringing:d74583d0c1d701a4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-04 | stringing:1f2c7881706c309f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-05 | stringing:066a04823f67222e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-06 | stringing:6d76ec9f9c2d69c8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-07 | stringing:99a3860e7537017e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-08 | stringing:58e7911986f3ac19
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-09 | stringing:5cac1c3c6fe30292
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-10 | stringing:eade37afb233f9f8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-11 | stringing:d1c0a092b6ed8d58
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-12 | stringing:2ecb7e993481679a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-13 | stringing:e49dd744a3a8d4fa
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-14 | stringing:6defd2e7695b38bf
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-15 | stringing:823c75ec9a31a0f6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-16 | stringing:8d30f575af2f5360
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-17 | stringing:58a6ef6f7678148c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-18 | stringing:e072f17ecc477ed9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-19 | stringing:1c67b70bff9ed393
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-20 | stringing:5cfb224b22de97af
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-21 | stringing:c451bb7a594b5b12
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-22 | stringing:34b29603ff5e0d58
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-23 | stringing:169dd13e3e0af181
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-24 | stringing:f585dc8d3944f7c4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-25 | stringing:2b1cf54fb679f4ce
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-26 | stringing:843771b7353b8a85
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-27 | stringing:f77393642f48e034
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-28 | stringing:3f077262b7b3f6f0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-29 | stringing:8e04d28aaa7a1177
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-04-30 | stringing:66a4cf00475d3ac0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-01 | stringing:5f287dc48f44af3c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-02 | stringing:ebb14b036b17586b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-03 | stringing:c1d05eb4f7ee3b5a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-04 | stringing:4cc90b7b499861ab
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-05 | stringing:867a86e3c64d4653
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-06 | stringing:0d045ef8da674760
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-07 | stringing:3b070f248c041ead
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-08 | stringing:81708cb3a7e6ad54
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-09 | stringing:4792b31d89d80722
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-10 | stringing:c23e26cf829f92e8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-11 | stringing:06143479d18d98b7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-12 | stringing:886b5cbabea0f513
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-13 | stringing:5bc13d81f989dd11
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-14 | stringing:1c5c50f2cd6a7c7e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-15 | stringing:69a8a811c7350923
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-16 | stringing:87e49f7fef013747
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-17 | stringing:02c81c6697a93c20
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-18 | stringing:d1efefd176e955c8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-19 | stringing:bf3810018e9d82e3
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-20 | stringing:69fddc1491d261df
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-21 | stringing:1627a2457b4e745a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-22 | stringing:0abc0608eed2671c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-23 | stringing:e46429d5c4cd7ae9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-24 | stringing:7f319c27977f996b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-25 | stringing:2e5797838fd932d5
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-26 | stringing:127d70bf5165add2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-27 | stringing:90cc3181d0d9dc49
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-28 | stringing:8ac6a4c4f8a8aa47
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-29 | stringing:3ed89e67bf828279
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-30 | stringing:30d94b016d615c6a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-05-31 | stringing:4fee2d5029a0e2d6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-01 | stringing:ff2bc0740c5b851f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-02 | stringing:01a5f284f8be47ec
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-03 | stringing:3d1bd61198c99415
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-04 | stringing:f3270365bfbe4f69
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-05 | stringing:80687c6f60a22f4c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-06 | stringing:390d09dbb4be6768
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-07 | stringing:f51222add09439d0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-08 | stringing:ab49a94ce62e384f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-09 | stringing:b30d712af81d9fa3
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-10 | stringing:fd14cf8d08bdd0c4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-11 | stringing:7f568690942eee1f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-12 | stringing:ffc96390e428cd64
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-13 | stringing:9d57c7fba6e2f0c3
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-14 | stringing:c345b22d166b3384
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-15 | stringing:34b0ce63117ddd08
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-16 | stringing:2af7e712653134a9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-17 | stringing:b6e171288f891d00
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-18 | stringing:ecfb4d678a4acc06
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-19 | stringing:da181a9da6ba96f4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-20 | stringing:e0e3a2f6a4dc2b48
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-21 | stringing:ec81aa9972582e1c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-22 | stringing:63c577a8253b57d5
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-23 | stringing:02dfdb1cd26fbdd6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-24 | stringing:1fc7a75ee29ab27c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-25 | stringing:d5ee583cab415d71
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-26 | stringing:1e4df2be6186e4bf
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-27 | stringing:c59dabac490a29f6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-28 | stringing:6aea06b7a079a796
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-29 | stringing:fee7b82050db5cdc
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-06-30 | stringing:d806225768f8a8d2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-01 | stringing:d2c80575b30eed7a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-02 | stringing:b1256b44fe5e3fa1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-03 | stringing:ebafda0c1ea7853b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-04 | stringing:0430500a854186cf
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-05 | stringing:502a91b2ebe72332
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-06 | stringing:c9c1456da7f63330
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-07 | stringing:85923a2c7776e0e1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-08 | stringing:7cbb637340d57766
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-09 | stringing:761d7c639188c42e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-10 | stringing:07a2ac2d3a494388
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-11 | stringing:d00a0419881ffa79
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-12 | stringing:ba2f2f6276d99ee4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-13 | stringing:74adb97f08861438
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-14 | stringing:45c82350648a1d60
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-15 | stringing:01d7fbb424d7e4d1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-16 | stringing:b022fdabe02ee05c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-17 | stringing:6411814b3a9c3b27
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-18 | stringing:350f79191233ea3f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-19 | stringing:50a659beb449ef38
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-20 | stringing:b4bb641e7b9a3ed4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-21 | stringing:fa3bdcc758b2804e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-22 | stringing:f39ddc2b138fadc2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-23 | stringing:b5c51648a5ce0b66
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-24 | stringing:c901d93b94b8fcec
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-25 | stringing:bc4db81cd24617b8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-26 | stringing:583f942416501ca2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-27 | stringing:058672a3b94da1fc
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-28 | stringing:42758f50c4098e9c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-29 | stringing:36f47ce5d4db0931
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-30 | stringing:235bddaedd00e8f7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-07-31 | stringing:fe6e7aca5f039243
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-01 | stringing:b3066e37e9899e5a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-02 | stringing:9f49e1b9db6d49ec
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-03 | stringing:1f17e0eb99f560cb
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-04 | stringing:9288dd702ccdbaa4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-05 | stringing:7190501e5536c363
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-06 | stringing:b98e3bfa7b5d3642
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-07 | stringing:90ab7bed0c9f639e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-08 | stringing:571b0e8d2fb0c55c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-09 | stringing:d0e99f0605d204e7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-10 | stringing:a6c4c392f409db31
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-11 | stringing:b441dcdd77fb2154
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-12 | stringing:48b65b013e69ddb3
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-13 | stringing:8d50d5b1d281f2fd
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-14 | stringing:b35bcb847a8d1a54
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-15 | stringing:72a5130e2b047207
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-16 | stringing:01b74e724b9f0cc6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-17 | stringing:9cace403b6b6a211
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-18 | stringing:659b78ee84fae0bc
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-19 | stringing:672a4d7b7937ab6b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-20 | stringing:c1bb66c8fe524d52
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-21 | stringing:e8220a46c19b024c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-22 | stringing:26a2c5df4f048920
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-23 | stringing:4000cad3cede9fd2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-24 | stringing:47baf5a20fb8d7c4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-25 | stringing:d0f0aabe2c9c9f4b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-26 | stringing:4d861aa77bc44269
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-27 | stringing:52b96f403f19c7d7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-28 | stringing:9dd0363a377a69de
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-29 | stringing:2f03250c1f15bf04
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-30 | stringing:418720e8c4e44d7f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-08-31 | stringing:cb9336822df6d5f9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-01 | stringing:b1d06633094612ca
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-02 | stringing:fe68b43ebb25b1e9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-03 | stringing:ba0217a77868a59c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-04 | stringing:1c4e4ac942192392
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-05 | stringing:6509704180ee8d0f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-06 | stringing:ddb839a39cee24f4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-07 | stringing:cf587733910f4c49
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-08 | stringing:59c7ed42cbe819ec
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-09 | stringing:4fcce6a7413c0d18
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-10 | stringing:28184e2fee05e37d
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-11 | stringing:7625c30a636035a6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-12 | stringing:e4b98eda563e558a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-13 | stringing:6cdc6e3f0050b2e4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-14 | stringing:9ea0cba6cb619fb3
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-15 | stringing:f431a564c39c2150
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-16 | stringing:cc2bc30fa92b1eaa
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-17 | stringing:739fafc2920e1a89
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-18 | stringing:089f8d745b7e8f81
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-19 | stringing:edeef727475e09da
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-20 | stringing:92447009e2c2ae64
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-21 | stringing:6adf338563a4b390
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-22 | stringing:0b4df9dd6020bc3c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-23 | stringing:d249869773328f5a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-24 | stringing:68ab78871bccabab
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-25 | stringing:a2b67c4217fe0fb4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-26 | stringing:3000f02ee674bb1f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-27 | stringing:e575018f6531e966
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-28 | stringing:be87b5e31c73a18c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-29 | stringing:7330a07a25f89c98
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-09-30 | stringing:7adc5dddc5ec8cee
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-01 | stringing:a8585f6438589870
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-02 | stringing:188b3290ac594c9b
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-03 | stringing:bca07e4a858e2235
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-04 | stringing:7941a83e54d0e586
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-05 | stringing:47ebf9d5e1badd90
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-06 | stringing:b26e6bb4f3347ec8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-07 | stringing:41135b965094f353
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-08 | stringing:f1611202b34c857c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-09 | stringing:31651ddb8ed0cca9
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-10 | stringing:262ce0f3ae58e775
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-11 | stringing:3c807a82f88d632a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-12 | stringing:33dc79f703f26637
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-13 | stringing:c22bfb6c0794f5ce
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-14 | stringing:a21d61c1d97e7088
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-15 | stringing:dc697ebd6f7461b1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-16 | stringing:73f25ecb0270c1a8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-17 | stringing:468cec5985e943f2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-18 | stringing:a9894f18c06fb7d4
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-19 | stringing:b0fb5952b3aa72b8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-20 | stringing:fe3389c46f0a8f9e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-21 | stringing:ee9956c100d8b834
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-22 | stringing:6c5229d5c3fd304c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-23 | stringing:db68b64a449356c5
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-24 | stringing:ca4ace54c4747488
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-25 | stringing:fe5db70efe9bd940
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-26 | stringing:f47b3b1fcfb63a3c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-27 | stringing:71fea7246f1b6c44
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-28 | stringing:0203b654234554dd
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-29 | stringing:9d74f841a4654ce2
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-30 | stringing:289ec1a32ee0046f
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-10-31 | stringing:71fd6027ad22d75a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:39b7cede900350a8
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:2bb9e2d0cc736c82
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:fbc1d3c5789c69e6
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:a3f54085c4b2d10c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:0c28cd35ec8b033a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:3e62b342f64b1f06
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:085f7f4a00026c3a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:46476b2dbe121531
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:8b9a7141a45702f0
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:3b31b6ca717bd53e
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:04cc16bc42f07511
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:82131097f25e580a
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:2e28cb1b5c7e14d1
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:4a38c70337a53a3c
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:67fbc380d25911f7
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:ed9f9004a523d443
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:8d149e6d33a10b31
METHOD_MISSING | TB 401 | 34/0 | 34/5 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:65ee73db5b4cb9e2
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:d638309a10d1964a
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:f857bff6cb59cd1a
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:03d80a5313fc5129
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:a2a3d96831a0d798
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:3a0939ec7f8c3070
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:9a525cf1608e8165
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:3afedbbd868c84ce
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:448f20eae4493a7d
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:77bab32342e5a077
METHOD_MISSING | TB 401 | 34/5 | 35/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:7f58d2bd3fda4b0f
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:5d6d637f3b653dca
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:044b7c11e2c7ea65
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:834a6b1ae03517ec
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:92198b74d5eedb17
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:8d791e2b875eb2a2
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:af95431464517479
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:9b32edcd99d1240e
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:da1d3cab752015ec
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:57ff2587350aaaf5
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:894841765c64db72
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:16dce498e056013e
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:d56e0d72cd0890ef
METHOD_MISSING | TB 401 | 45/0 | 46/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:dfc76618c45d55aa
METHOD_MISSING | TB 401 | 37/0 | 37/1 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:683c9d853089baea
METHOD_MISSING | TB 401 | 37/0 | 37/1 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:11707c9065f262f8
METHOD_MISSING | TB 401 | 37/1 | 37/2 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:4ad2a94842aec119
METHOD_MISSING | TB 401 | 37/1 | 37/2 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:73e4405edba531fe
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:db72f3b13a4f474c
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:b0d30804d9f0bd11
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:4e4e3900765ed1a5
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:96e057162a382af9
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:ed6146031e227f08
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:1107119383532e4e
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:b8a17d396a7608f0
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:3642a4b6209bd313
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:26d076902e0ade44
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:205fee1dff3e098d
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:9c9b8314d4c9cecc
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:afdfd4d432716fcc
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:736f906f2405540a
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:0be9dc78161c50ba
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:b9f9e4daa94d0173
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:394fc7cca2b5998d
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:35df8ecca8aaab06
METHOD_MISSING | TB 401 | 25/0 | 26/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:c39480ed12ffc04e
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-10-30 | stringing:ff138943fc7efd8f
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-10-31 | stringing:2541fe5471814d98
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-01 | stringing:715e8eb015780d72
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-02 | stringing:216990a3a03fe6a4
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-03 | stringing:213275107955e3fe
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-04 | stringing:c7d030315d5bd4f7
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-05 | stringing:f3177e7b0638331c
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-06 | stringing:f76ba2bc0e0f12fd
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-07 | stringing:bc9cf52d114ea3e3
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-08 | stringing:ff3f8411a2226c4d
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-09 | stringing:1636071bb5bcbb06
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-10 | stringing:9134749ed0192fb4
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-11 | stringing:3c3658e0f16f081e
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-12 | stringing:5927ed6e31da1677
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-13 | stringing:37109d45c385f8f5
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-14 | stringing:2d55d4630d1fb1f9
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-15 | stringing:7b67178b18b4b56b
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-16 | stringing:3d3d7438f63515fe
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-17 | stringing:80436365aa67c9f0
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-18 | stringing:ef73c7c49643cddb
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:c739aaf83189c7af
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:0d60be2dbee2e4ff
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:fb4b456568cba548
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:0ea4c9b254fcd135
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:2a2d43c2b4eaf9ac
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:a28af8016bbd448a
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:c1081a6870d513a2
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:a1d9de12d6e491e3
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:fe2d9f9fc98e2bf8
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:c8aa9ee9d49470e1
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:6b07d87780b34693
METHOD_MISSING | TB 401 | 2/0 | 3/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:adc321450d346c52
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-19 | stringing:50416d160d375597
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-20 | stringing:03f83dabf00d4ba5
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-21 | stringing:c5fed1f42e3c1679
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-22 | stringing:1a0a5bc890ebb342
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-23 | stringing:58c20ae732418038
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-24 | stringing:68bc70c0d5a74107
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-25 | stringing:3635c50867833362
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-26 | stringing:d0b180bd16f57468
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-27 | stringing:5c9ee2c17b24dc31
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-28 | stringing:0d1eae1aa78e307d
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-29 | stringing:5f1ea63d86ceef0e
METHOD_MISSING | TB 401 | 30/0 | 31/0 |  |  |  |  | Method column missing or blank | 2025-11-30 | stringing:de7ee0a25f7f83cc
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:eeb9eed7785c8636
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:f80929b2ba26dcb2
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:9475f06024088bb4
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:01e4908f3ddd570a
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:e4c02c2953c67bb5
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:367a6832367f9383
METHOD_MISSING | TB 401 | 5/0 | 6/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:47e87d802bb91880
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:a2fac86f065912fb
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:85487bbcdec2f6ed
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:af8a0c1a2df4d8a6
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:0d21b939d04a1ecc
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:e5aa3d209cc008d5
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:9267baeab6a7ec82
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:0f804d338a5911c2
METHOD_MISSING | TB 401 | 4/0 | 5/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:6d466036662091d4
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:c056d95630023fc6
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:da9ff6df16e26e98
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:bfc69749468310d9
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:e7bf221a9f713f8d
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:30a2f013e413655b
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:af594ccceba2b17f
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:057fc6ebf9807228
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:08098ca7e84a6aa4
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:512e409301805f9c
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:9fd3229f0a490775
METHOD_MISSING | TB 401 | 15/0 | 16/0 |  |  |  |  | Method column missing or blank | 2025-12-13 | stringing:308fe513eb4397f0
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:facf87b3616e3a45
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:f4866f8741d4543a
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:36e67a611c004ac2
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:0c8e4db934d0b72c
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:085165502cb7ae99
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:530f9e873dd5ff44
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:21bb45cebe5d8b3a
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:a2f9bf12953b7638
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:741f95e3c118c6d9
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:a148032e4d8c6c19
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:157b1a6e2aa2ea5e
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:f9fbdc6a571f519a
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-13 | stringing:e621348b45b2a937
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-14 | stringing:42ea64c4cd4ff0dc
METHOD_MISSING | TB 401 | 29/0 | 30/0 |  |  |  |  | Method column missing or blank | 2025-12-15 | stringing:28187e7c83158103
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-14 | stringing:55c272cbcf4494f7
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-15 | stringing:27021593d46d0441
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-16 | stringing:ba3964c7f75b1327
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-17 | stringing:a8022ed7476f007c
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-18 | stringing:b7b819d9e2ddf50d
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-19 | stringing:70e9d4ca7b9d8399
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-20 | stringing:76eaa2e2ec654833
METHOD_MISSING | TB 401 | 16/0 | 17/0 |  |  |  |  | Method column missing or blank | 2025-12-21 | stringing:8db91ea19895e8e5
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-01 | stringing:1f1809eff363d364
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-02 | stringing:84c741708307abde
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-03 | stringing:fd7494f8615024f9
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-04 | stringing:2dac1d5bbeab6ba5
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-05 | stringing:bcc59ab73c990222
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-06 | stringing:91253f8965ee00d0
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-07 | stringing:997f77cfb1bd6000
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-08 | stringing:8099dcd7659698e6
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-09 | stringing:938220469f13fd84
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-10 | stringing:78dcf8cdebf4bae3
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-11 | stringing:33fbc8a26ec6ef64
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-12 | stringing:ca2876ff6db2f6c4
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-13 | stringing:431d9c142aa96960
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-14 | stringing:48f4e0f346d7ef98
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-15 | stringing:8fefce642e50568b
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-16 | stringing:f354b8dcc6f864ae
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-17 | stringing:892713cc052776db
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-18 | stringing:4da55af7654b83ef
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-19 | stringing:41bdba0a0af092e4
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-20 | stringing:84af5d54488ed2d8
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-21 | stringing:04f8ca75e58a8f1c
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-22 | stringing:c11ed3b0352fbdc2
METHOD_MISSING | TB 401 | 24/0 | 25/0 |  |  |  |  | Method column missing or blank | 2025-12-23 | stringing:b37a0943d2b0a166