## Project Details
Project Code | Project Name | Client Name | LOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor/Engineer
TA 421 | 765KV D/C HEXA BIDAR PS - MAHESHWARAM (PG) TL | Power Grid Bidar | 2024-02-15 | 2025-11-14 | Mr. Bharath A D | Mr.Arun Felbin | Mr. Ajith Kumar | Mr. Appala Naidu | Mr.Manikandan | Mr. Ramasish
| (PKG 01) | Transmission Limited | [6 empty] | Mr. Satyam Tiwari | Mr. Godvin John
Mr. Karunakar Nayak
Mr. Sudalaimuthu
Mr. Susanthpal
Mr. Srinivasan
Mr. Bhim Mahto
Mr. Ganesan
Mr. Ballu Thakur
Mr. Chandrasekar
Mr.Chandrasekharan
Mr. Anand

## Master Sheet
| Project Code | TA-421 |  |  | Date | 2025-11-06 | SBU Head | Mr. Rajinder Gupta
| Project Name | 765kV D/C Bidar - Maheshwaram TL |  |  | LOA Start Date | 15.02.2024 | PCH | Mr. Sivaraman N
| Client Name | Power Grid Corporation of India Limited |  |  | LOA End Date | 14.11.2025 | Regional Manager | Mr. Ajith Kumar MG
| Revised End Date | 14.11.2025 |  |  | Planning Engineer | Mr. Bharath A D | Project Manger | Mr. Appala Naidu |  | 0
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Completed till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's
Tower | No's
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
Detailed Survey | kms | 121.342 | 121.342 | 121.342 | 121.342 |  |  |  |  | 121.342
Check Survey | kms | 121.342 | 121.342 | 121.342 | 121.342 |  |  |  |  | 121.342
Progress Status
Activity | Final Estimated Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | 309 | 309 | 307 |  | 2 |  |  | 309 | 307 | 2 |  | 1 | AP 7/0 & 8/0 - Court case
Earthing | 309 | 309 | 289 |  | 20 |  |  | 309 | 289 | 20
Tower Erection | 309 | 309 | 256 |  | 30 |  | 4 | 309 | 260 | 49 | 5 | 5 | WIP - 3/1, 8/3, 36/0, 39/8,43B/0
Tackwelding | 309 |  | 124 | [5 empty] | 124 | 185
Tower Tightening | 309 |  | 129 | [5 empty] | 129 | 180 | 3 | 2 | WIP - 16/5, 13/11, 14/0
Stringing -R/S | 121.342 | 121.342 | 43.743 |  | 19.285 |  |  | 121.342 | 43.743 | 77.599 | 6.439 | 2 | 17/0-18/0 ( 1.539 km ) - Pilot Paying out u/p ; AP 13/0 to 14/0(4.900 km) -Insulator Hosting Done
Stringing -F/S | 121.342 | 121.342 | 43.743 |  | 19.285 |  |  | 121.342 | 43.743 | 77.599
OPGW | 121.342 | 121.342 | 34.282 |  |  |  |  | 121.342 | 34.282 | 87.06
NH Crossing | 3 |  | 3 | [5 empty] | 3
Power Line Crossing | 5 |  | 5 | [5 empty] | 5
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | Set | 312 | 312 | 312 |  |  |  |  | 312 | 0
Tower | No's | 312 | 312 | 311 |  |  |  | 1 | 312 | 0

## ProGress Sheet
Survey Status
| Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Balance to Approve | L2 Submission Plan for Current Month | Progress For Month | Approved till Current Month | Remarks
| Detailed Survey | kms | 121.342 | 121.342 | 121.342 | 121.342 |  |  |  |  | 121.342
| Check Survey | kms | 121.342 | 121.342 | 121.342 | 121.342 |  |  |  |  | 121.342
PROGRESS - FDN & EREC
| S.No | Location No. | Tower Type | Classification | Start Date | Conc Volume | Foundation Status |  |  |  | End Date | Gang Name | Erection Status | Gang Strength | Remarks
| 1 | 24/4 | 3DA+0 | DFR | 2024-05-03 | 25.578 | COMPLETED |  |  |  | 2024-05-22 | ATK CONSTRUCTIONS | Completed | 13
| 2 | 24/2 | 3DA+3 | DFR | 2024-05-23 | 25.578 | COMPLETED |  |  |  | 2024-06-02 | ATK CONSTRUCTIONS | Completed | 13
| 3 | 24/3 | 3DA+0 | DFR | 2024-05-06 | 25.578 | COMPLETED |  |  |  | 2024-06-07 | ATK CONSTRUCTIONS | Completed | 13
| 4 | 24/5 | 3DA+0 | DFR | 2024-05-09 | 25.578 | COMPLETED |  |  |  | 2024-06-11 | ATK CONSTRUCTIONS | Completed | 13
| 5 | 24/6 | 3DA+0 | DFR | 2024-05-25 | 25.578 | COMPLETED |  |  |  | 2024-06-15 | ATK CONSTRUCTIONS | Completed | 13
| 6 | 24/7 | 3DA+0 | DFR | 2024-05-25 | 25.578 | COMPLETED |  |  |  | 2024-06-19 | ATK CONSTRUCTIONS | Completed | 13
| 7 | 23/4 | 3DA+0 | DFR | 2024-05-31 | 25.578 | COMPLETED |  |  |  | 2024-06-20 | AMMU ENG. | Completed | 14
| 8 | 25/4 | 3DA+0 | DFR | 2024-06-13 | 25.578 | COMPLETED |  |  |  | 2024-06-22 | ATK CONSTRUCTIONS | Completed | 15
| 9 | 25/5 | 3DA+6 | DFR | 2024-06-17 | 26.872 | COMPLETED |  |  |  | 2024-06-25 | ATK CONSTRUCTIONS | Completed | 14
| 10 | 23/3 | 3DA+0 | DFR | 2024-06-03 | 25.578 | COMPLETED |  |  |  | 2024-06-27 | AMMU ENG. | Completed | 13
| 11 | 29/1 | 3DA+9 | DFR | 2024-06-15 | 26.872 | COMPLETED |  |  |  | 2024-06-29 | TSB | Completed | 21
| 12 | 25/1 | 3DA+0 | DFR | 2024-06-20 | 25.578 | COMPLETED |  |  |  | 2024-06-28 | ATK CONSTRUCTIONS | Completed | 14
| 13 | 24/8 | 3DA+3 | DFR | 2024-06-21 | 26.872 | COMPLETED |  |  |  | 2024-06-29 | ATK CONSTRUCTIONS | Completed | 14
| 14 | 22/4 | 3DA+3 | DFR | 2024-06-23 | 26.872 | COMPLETED |  |  |  | 2024-06-29 | AMMU ENG. | Completed | 13
| 15 | 12/3 | 3DA+3 | DFR | 2024-06-22 | 26.872 | COMPLETED |  |  |  | 2024-06-30 | RR CONST | Completed | 12
| 16 | 26/1 | 3DA+0 | DFR | 2024-06-25 | 25.578 | COMPLETED |  |  |  | 2024-07-04 | ATK CONSTRUCTIONS | Completed | 14
| 17 | 12/4 | 3DA+3 | DFR | 2024-06-19 | 26.872 | COMPLETED |  |  |  | 2024-07-05 | RR CONST | Completed | 12
| 18 | 22/5 | 3DA+0 | DFR | 2024-06-27 | 25.578 | COMPLETED |  |  |  | 2024-07-06 | AMMU ENG. | Completed | 13
| 19 | 26/3 | 3DA+0 | DFR | 2024-07-01 | 25.578 | COMPLETED |  |  |  | 2024-07-07 | ATK CONSTRUCTIONS | Completed | 14
| 20 | 23/2 | 3DA+0 | DFR | 2024-07-03 | 25.578 | COMPLETED |  |  |  | 2024-07-10 | AMMU ENG. | Completed | 13
| 21 | 12/2 | 3DA+3 | DFR | 2024-06-24 | 27.872 | COMPLETED |  |  |  | 2024-07-10 | RR CONST | Completed | 13
| 22 | 26/2 | 3DA+0 | DFR | 2024-06-25 | 25.578 | COMPLETED |  |  |  | 2024-07-10 | ATK CONSTRUCTIONS | Completed | 14
| 23 | 12/11 | 3DA+6 | DFR | 2024-06-28 | 26.872 | COMPLETED |  |  |  | 2024-07-11 | ANJU Const. | Completed | 12
| 24 | 26/4 | 3DA+0 | DFR | 2024-07-07 | 25.578 | COMPLETED |  |  |  | 2024-07-13 | ATK CONSTRUCTIONS | Completed | 19
| 25 | 22/3 | 3DA+6 | DFR | 2024-07-02 | 26.872 | COMPLETED |  |  |  | 2024-07-14 | AMMU ENG. | Completed | 13
| 26 | 24/1 | 3DA+6 | DFR | 2024-07-10 | 26.872 | COMPLETED |  |  |  | 2024-07-16 | ATK CONSTRUCTIONS | Completed | 19
| 27 | 12/7 | 3DA+0 | DFR | 2024-06-28 | 25.578 | COMPLETED |  |  |  | 2024-07-17 | ANJU Const. | Completed | 12
| 28 | 22/2 | 3DA+0 | DFR | 2024-07-08 | 25.578 | COMPLETED |  |  |  | 2024-07-17 | AMMU ENG. | Completed | 13
| 29 | 27/1 | 3DA+0 | DFR | 2024-07-10 | 25.578 | COMPLETED |  |  |  | 2024-07-19 | ATK CONSTRUCTIONS | Completed | 19
| 30 | 21/9 | 3DA+0 | DFR | 2024-07-12 | 25.578 | COMPLETED |  |  |  | 2024-07-22 | AMMU ENG.-2 | Completed | 13
| 31 | 12/6 | 3DA+0 | DFR | 2024-07-09 | 25.578 | COMPLETED |  |  |  | 2024-07-23 | ANJU Const. | Completed | 12
| 32 | 21/8 | 3DA+0 | DFR | 2024-07-24 | 25.578 | COMPLETED |  |  |  | 2024-07-30 | AMMU ENG.-2 | Completed | 13
| 33 | 21/7 | 3DA+0 | DFR | 2024-07-19 | 25.578 | COMPLETED |  |  |  | 2024-07-31 | AMMU ENG.-2 | Completed | 13
| 34 | 27/8 | 3DA+0 | DFR | 2024-06-26 | 25.578 | COMPLETED |  |  |  | 2024-07-31 | TSB | Completed | 22
| 35 | 12/5 | 3DA+0 | DFR | 2024-07-14 | 25.578 | COMPLETED |  |  |  | 2024-07-31 | ANJU Const. | Completed | 12
| 36 | 27/4 | 3DA+0 | DFR | 2024-07-11 | 25.578 | COMPLETED |  |  |  | 2024-08-05 | ATK CONSTRUCTIONS | Completed | 19
| 37 | 27/5 | 3DA+0 | DFR | 2024-08-03 | 25.578 | COMPLETED |  |  |  | 2024-08-08 | ATK CONSTRUCTIONS | Completed | 14
| 38 | 12/8 | 3DA+3 | DFR | 2024-07-05 | 26.872 | COMPLETED |  |  |  | 2024-08-11 | ANJU Const. | Completed | 12
| 39 | 23/0 | 3DB2+0 | DFR | 2024-08-02 | 45.764 | COMPLETED |  |  |  | 2024-08-11 | Ammu Eng | Completed | 13
| 40 | 27/0 | 3DB1+0 | DFR | 2024-07-19 | 43.668 | COMPLETED |  |  |  | 2024-08-11 | ATK CONSTRUCTIONS | Completed | 19
| 41 | 27/7 | 3DA+0 | DFR | 2024-06-25 | 25.578 | COMPLETED |  |  |  | 2024-08-13 | Company Gang | Completed | 22
| 42 | 27/6 | 3DA+0 | DFR | 2024-07-11 | 25.578 | COMPLETED |  |  |  | 2024-08-13 | ATK CONSTRUCTIONS | Completed | 19
| 43 | 26/0 | 3DB2+0 | DFR | 2024-07-22 | 45.764 | COMPLETED |  |  |  | 2024-08-14 | ATK CONSTRUCTIONS | Completed | 13
| 44 | 21/4 | 3DA+3 | WFR | 2024-08-05 | 40.406 | COMPLETED |  |  |  | 2024-08-16 | Ammu Eng | Completed | 13
| 45 | 25/0 | 3DB2+0 | DFR | 2024-07-17 | 45.764 | COMPLETED |  |  |  | 2024-08-16 | ATK CONSTRUCTIONS | Completed | 19
| 46 | 24/0 | 3DB1+0 | DFR | 2024-07-28 | 43.668 | COMPLETED |  |  |  | 2024-08-17 | Ammu Eng | Completed | 13
| 47 | 27/2 | 3DA+0 | DFR | 2024-07-20 | 25.578 | COMPLETED |  |  |  | 2024-08-19 | ATK CONSTRUCTIONS | Completed | 19
| 48 | 12/9 | 3DA+3 | DFR | 2024-07-13 | 26.872 | COMPLETED |  |  |  | 2024-08-22 | ANJU Const. | Completed | 12
| 49 | 27/9 | 3DA+3 | DFR | 2024-08-11 | 26.872 | COMPLETED |  |  |  | 2024-08-23 | Company Gang | Completed | 11
| 50 | 22/1 | 3DA+0 | WFR | 2024-07-06 | 39.527 | COMPLETED |  |  |  | 2024-08-23 | AMMU ENG. | Completed | 13
| 51 | 29/4 | 3DA+0 | DFR | 2024-08-08 | 25.578 | COMPLETED |  |  |  | 2024-08-24 | ATK CONSTRUCTIONS | Completed | 12
| 52 | 22/0 | 3DB1+0 | DFR | 2024-08-13 | 43.668 | COMPLETED |  |  |  | 2024-08-25 | Ammu Eng | Completed | 13
| 53 | 29/5 | 3DA+3 | DFR | 2024-08-20 | 26.872 | COMPLETED |  |  |  | 2024-08-27 | ATK CONSTRUCTIONS | Completed | 19
| 54 | 11/11 | 3DA+3 | DFR | 2024-08-20 | 26.872 | COMPLETED |  |  |  | 2024-08-28 | ANJU Const. | Completed | 12
| 55 | 29/3 | 3DA+0 | DFR | 2024-08-25 | 25.578 | COMPLETED |  |  |  | 2024-08-30 | ATK CONSTRUCTIONS | Completed | 19
| 56 | 21/2 | 3DA+0 | WFR | 2024-08-08 | 39.527 | COMPLETED |  |  |  | 2024-08-31 | Ammu Eng | Completed | 13
| 57 | 12/0 | 3DB2+0 | DFR | 2024-08-16 | 45.764 | COMPLETED |  |  |  | 2024-09-08 | ANJU Const. | Completed | 12
| 58 | 30/4 | 3DA+3 | WFR | 2024-08-24 | 40.406 | COMPLETED |  |  |  | 2024-09-11 | Company Gang | Completed | 11
| 59 | 29/9 | 3DB1+9 | DFR | 2024-09-05 | 47.611 | COMPLETED |  |  |  | 2024-09-11 | ATK CONSTRUCTIONS | Completed | 19
| 60 | 29/8 | 3DA+0 | DFR | 09.09.2024 | 26.872 | COMPLETED |  |  |  | 16.09.2024 | ATK CONSTRUCTIONS | Completed | 19
| 61 | 23/1 | 3DA+6 | WFR | 2024-06-27 | 40.406 | COMPLETED |  |  |  | 20.09.2024 | AMMU ENG. | Completed | 13
| 62 | 30/5 | 3DA+0 | DFR | 2024-09-11 | 25.578 | COMPLETED |  |  |  | 20.09.2024 | Company Gang | Completed | 12
| 63 | 29/6 | 3DA+0 | DFR | 2024-08-28 | 25.578 | COMPLETED |  |  |  | 20.09.2024 | ATK CONSTRUCTIONS | Completed | 19
| 64 | 12/10 | 3DA+0 | DFR | 2024-08-24 | 25.578 | COMPLETED |  |  |  | 22.09.2024 | ANJU Const. | Completed | 11
| 65 | 30/1 | 3DA+3 | DFR | 2024-09-23 | 25.578 | COMPLETED |  |  |  | 2024-09-27 | ATK CONSTRUCTIONS | Completed | 19
| 66 | 13/0 | 3DB1+0 | DFR | 2024-09-23 | 43.668 | COMPLETED |  |  |  | 2024-09-30 | ANJU Const. | Completed | 11
| 67 | 30/3 | 3DA+3 | DFR | 2024-08-31 | 26.872 | COMPLETED |  |  |  | 2024-10-03 | ATK CONSTRUCTIONS | Completed | 19
| 68 | 25/2 | 3DA+0 | WFR | 2024-09-24 | 39.527 | COMPLETED |  |  |  | 2024-10-04 | Ammu Eng | Completed | 13
| 69 | 19/3 | 3DA+3 | DFR | 2024-09-22 | 25.578 | COMPLETED |  |  |  | 2024-10-10 | Ammu Eng | Completed | 13
| 70 | 30/0 | 3DC1+6 | DFR | 2024-10-05 | 67.247 | COMPLETED |  |  |  | 2024-10-12 | ATK CONSTRUCTIONS | Completed | 19
| 71 | 12/1 | 3DA+3 | WFR | 2024-08-31 | 39.527 | COMPLETED |  |  |  | 2024-10-14 | ANJU Const. | Completed | 12
| 72 | 19/2 | 3DA+0 | DFR | 2024-10-10 | 25.578 | COMPLETED |  |  |  | 2024-10-17 | Ammu Eng | Completed | 13
| 73 | 27/3 | 3DC1+0(TP) | DFR | 2024-10-14 | 67.247 | COMPLETED |  |  |  | 2024-10-18 | ATK Constructions |  | 19
| 74 | 31/1 | 3DA+3 | DFR | 2024-09-17 | 26.872 | COMPLETED |  |  |  | 2024-10-21 | Company Gang + ATK | Completed | 14
| 75 | 39/7 | 3DA+6 | WFR | 2024-09-30 | 40.406 | COMPLETED |  |  |  | 2024-10-21 | Ashok | Completed | 14
| 76 | 17/3 | 3DA+6 | DFR | 2024-10-14 | 26.872 | COMPLETED |  |  |  | 2024-10-24 | Ammu Eng | Completed | 13
| 77 | 21/6 | 3DA+0 | DFR | 2024-10-22 | 25.578 | COMPLETED |  |  |  | 2024-10-30 | Ammu Eng | Completed | 13
| 78 | 13/1 | 3DA+3 | WET | 2024-09-29 | 41.944 | COMPLETED |  |  |  | 2024-10-30 | ANJU Const. | Completed | 12
| 79 | 42/0 | 3DB1+9 | DFR | 2024-10-05 | 47.611 | COMPLETED |  |  |  | 2024-10-30 | Ashok | Completed | 14
| 80 | 41/1 | 3DA+0 | WET | 2024-10-23 | 41.042 | COMPLETED |  |  |  | 2024-11-07 | Ashok | Completed | 14
| 81 | 15/2 | 3DA+3 | WET | 2024-10-18 | 41.944 | COMPLETED |  |  |  | 2024-11-08 | Ashok kumar | Completed | 17
| 82 | 11/6 | 3DA+0 | DFR | 2024-11-02 | 25.578 | COMPLETED |  |  |  | 2024-11-13 | Amit Kumar | Completed | 15
| 83 | 18/3 | 3DA+0 | WET | 2024-11-08 | 41.042 | COMPLETED |  |  |  | 2024-11-15 | Ammu Eng | Completed | 17
| 84 | 15/1 | 3DA+0 | WBC | 2024-11-10 | 68.906 | COMPLETED |  |  |  | 2024-11-16 | Ashok Kumar | Completed | 12
| 85 | 39/1 | 3DA+6 | WFR | 2024-11-08 | 40.406 | COMPLETED |  |  |  | 2024-11-18 | Ashok-2 | Completed | 13
| 86 | 11/10 | 3DA+0 | WET | 2024-11-06 | 41.042 | COMPLETED |  |  |  | 2024-11-19 | Amit Kumar | Completed | 15
| 87 | 15/4 | 3DA+3 | WBC | 2024-10-18 | 71.655 | COMPLETED |  |  |  | 2024-11-23 | Ashok kumar | Completed | 13
| 88 | 13/4 | 3DA+3 | WBC | 2024-10-25 | 71.655 | COMPLETED |  |  |  | 2024-11-24 | Balraj | Completed | 12
| 89 | 38/3 | 3DA+3 | WET | 2024-11-14 | 41.944 | COMPLETED |  |  |  | 2024-11-24 | Ashok-2 | Completed | 11
| 90 | 11/9 | 3DA+0 | WET | 2024-11-13 | 41.042 | COMPLETED |  |  |  | 2024-11-24 | Amit Kumar | Completed | 14
| 91 | 17/1 | 3DA+3 | WET | 2024-10-18 | 41.944 | COMPLETED |  |  |  | 2024-11-26 | Ammu Eng | Completed | 15
| 92 | 16/6 | 3DA+0 | WBC | 2024-10-18 | 68.906 | COMPLETED |  |  |  | 2024-11-26 | Visionary Co | Completed | 13
| 93 | 38/1 | 3DA+0 | WFR | 2024-11-18 | 39.527 | COMPLETED |  |  |  | 2024-11-28 | venkateshwarlu | Completed | 14
| 94 | 39/3 | 3DA+3 | DFR | 2024-11-18 | 26.872 | COMPLETED |  |  |  | 2024-11-29 | Ashok-2 | Completed | 11
| 95 | 18/0 | 3DB2+0 | DFR | 2024-11-04 | 45.764 | COMPLETED |  |  |  | 2024-11-29 | Ammu Eng | Completed | 16
| 96 | 13/3 | 3DA+6 | WBC | 2024-11-23 | 71.655 | COMPLETED |  |  |  | 2024-11-29 | Balraj | Completed | 14
| 97 | 38/2 | 3DA+0 | DFR | 2024-11-24 | 25.578 | COMPLETED |  |  |  | 2024-11-30 | venkateshwarlu | Completed | 11
| 98 | 13/9 | 3DA+3 | WBC | 2024-11-16 | 71.655 | COMPLETED |  |  |  | 2024-11-30 | Ashok kumar | Completed | 16
| 99 | 10/8 | 3DA+3 | DFR | 2024-11-23 | 40.406 | COMPLETED |  |  |  | 2024-11-30 | Amit Kumar | Completed | 14
| 100 | 13/5 | 3DA+0 | WET | 2024-11-28 | 41.042 | COMPLETED |  |  |  | 2024-11-30 | Balraj | Completed | 14
| 101 | 16/9 | 3DA+0 | WBC | 2024-11-22 | 68.906 | COMPLETED |  |  |  | 2024-12-05 | Visionary Co | Completed | 16
| 102 | 13/2 | 3DA+0 | WBC | 2024-12-01 | 68.906 | COMPLETED |  |  |  | 2024-12-06 | Balraj | Completed | 14
| 103 | 37/5 | 3DA+0 | DFR | 2024-11-18 | 25.578 | COMPLETED |  |  |  | 2024-12-07 | venkateshwarlu | Completed | 11
| 104 | 18/1 | 3DA+0 | DFR | 2024-12-01 | 25.578 | COMPLETED |  |  |  | 2024-12-07 | Ammu Eng | Completed | 16
| 105 | 35/2 | 3DA+0 | DFR | 2024-11-28 | 25.578 | COMPLETED |  |  |  | 2024-12-08 | Tagore | Completed | 14
| 106 | 18/2 | 3DA+0 | DFR | 2024-12-02 | 25.578 | COMPLETED |  |  |  | 2024-12-09 | Ammu Eng | Completed | 14
| 107 | 39/2 | 3DA+0 | WBC | 2024-11-30 | 68.906 | COMPLETED |  |  |  | 2024-12-10 | Ashok-2 |  | 16
| 108 | 11/0 | 3DC1+0 | DFR | 2024-12-02 | 67.247 | COMPLETED |  |  |  | 2024-12-11 | Amit Kumar | Completed | 14
| 109 | 31/3 | 3DA-3 | WFR | 2024-12-03 | 39.527 | COMPLETED |  |  |  | 2024-12-11 | ATK Constructions | Completed | 14
| 110 | 13/10 | 3DA+0 | WBC | 2024-12-01 | 68.906 | COMPLETED |  |  |  | 2024-12-12 | Ashok kumar | Completed | 17
| 111 | 38/4 | 3DA+0 | DFR | 2024-12-04 | 25.578 | COMPLETED |  |  |  | 2024-12-12 | venkateshwarlu | Completed | 15
| 112 | 13/6 | 3DA+6 | WBC | 2024-12-04 | 71.655 | COMPLETED |  |  |  | 2024-12-13 | Balraj | Completed | 17
| 113 | 21/5 | 3DA-3 | WFR | 2024-12-07 | 39.527 | COMPLETED |  |  |  | 2024-12-13 | Ammu Eng | Completed | 12
| 114 | 21/1 | 3DA+0 | DFR | 2024-12-07 | 25.578 | COMPLETED |  |  |  | 2024-12-14 | Ammu Eng | Completed | 13
| 115 | 31/5 | 3DA+0 | WFR | 2024-12-08 | 39.527 | COMPLETED |  |  |  | 2024-12-15 | ATK Constructions | Completed | 15
| 116 | 39/4 | 3DA+3 | DFR | 2024-12-08 | 26.872 | COMPLETED |  |  |  | 2024-12-15 | Ashok-2 | Completed | 16
| 117 | 35/3 | 3DA+0 | DFR | 2024-12-08 | 25.578 | COMPLETED |  |  |  | 2024-12-16 | Tagore |  | 14
| 118 | 31/2 | 3DA+0 | WFR | 2024-09-24 | 39.527 | COMPLETED |  |  |  | 2024-12-19 | ATK Constructions | Completed | 14
| 119 | 38/5 | 3DA+0 | WET | 2024-12-09 | 41.042 | COMPLETED |  |  |  | 2024-12-20 | Ashok-2 | Completed | 16
| 120 | 30/2 | 3DA+3 | WFR | 2024-12-17 | 40.406 | COMPLETED |  |  |  | 2024-12-21 | ATK Constructions | Completed | 17
| 121 | 38/7 | 3DA+0 | WFR | 2024-12-15 | 39.527 | COMPLETED |  |  |  | 2024-12-22 | Ashok-2 |  | 12
| 122 | 31/4 | 3DA+0 | DFR | 2024-12-19 | 25.578 | COMPLETED |  |  |  | 2024-12-23 | ATK Constructions | Completed | 13
| 123 | 11/3 | 3DA-3 | WBC | 2024-12-14 | 68.906 | COMPLETED |  |  |  | 2024-12-23 | Ashok kumar | Completed | 15
| 124 | 16/11 | 3DA+3 | WBC | 2024-12-09 | 71.655 | COMPLETED |  |  |  | 2024-12-23 | Visionary Co |  | 16
| 125 | 21/3 | 3DA+6 | WBC | 2024-12-11 | 71.655 | COMPLETED |  |  |  | 2024-12-22 | Ammu Eng | Completed | 14
| 126 | 37/4 | 3DA+6 | DFR | 2024-12-14 | 26.872 | COMPLETED |  |  |  | 2024-12-24 | Ashok-2 | Completed | 16
| 127 | 25/3 | 3DA+0 | DFR | 2024-12-15 | 25.578 | COMPLETED |  |  |  | 2024-12-25 | Tagore | Completed | 17
| 128 | 16/10 | 3DA+3 | WBC | 2024-12-23 | 71.655 | COMPLETED |  |  |  | 2024-12-27 | Visionary & Co | Completed | 15
| 129 | 31/0 | 3DB2+0 | WFR | 2024-12-22 | 67.774 | COMPLETED |  |  |  | 2024-12-28 | ATK Constructions | Completed | 15
| 130 | 21/0 | 3DD45+0 | DFR | 2024-12-22 | 79.708 | COMPLETED |  |  |  | 2024-12-30 | Ammu Eng | Completed | 14
| 131 | 11/2 | 3DA+0 | WBC | 2024-12-22 | 68.906 | COMPLETED |  |  |  | 2024-12-30 | Ashok-1 | Completed | 14
| 132 | 16/8 | 3DA+3 | WET | 2024-12-24 | 41.944 | COMPLETED |  |  |  | 2024-12-31 | BalraJ | Completed | 16
| 133 | 38/6 | 3DA+0 | WBC | 2024-12-24 | 68.906 | COMPLETED |  |  |  | 2024-12-31 | Venkateshwarlu | Completed | 14
| 134 | 28/0 | 3DC1+0 | DFR | 2024-12-24 | 67.247 | COMPLETED |  |  |  | 2024-12-31 | ATK Constructions | Completed | 16
| 135 | 29/2 | 3DA+0 | WFR | 2024-12-29 | 39.527 | COMPLETED |  |  |  | 2025-01-03 | ATK Constructions | Completed | 17
| 136 | 36/7 | 3DA+3 | WFR | 2024-12-18 | 40.406 | COMPLETED |  |  |  | 2025-01-04 | TaGore | Completed | 15
| 137 | 19/1 | 3DA+6 | WBC | 2024-12-27 | 71.655 | COMPLETED |  |  |  | 2025-01-05 | Ammu Engineering | Completed | 14
| 138 | 11/4 | 3DA+0 | DFR | 2024-12-31 | 25.578 | COMPLETED |  |  |  | 2025-01-05 | Ashok kumar (Thotta) | Completed | 14
| 139 | 16/7 | 3DA-3 | WET | 2024-12-24 | 41.042 | COMPLETED |  |  |  | 2025-01-05 | Visionary & Co | Completed | 16
| 140 | 36/8 | 3DA+0 | WFR | 2024-12-26 | 39.527 | COMPLETED |  |  |  | 2025-01-05 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 141 | 29/7 | 3DA+3 | WFR | 2025-01-03 | 40.406 | COMPLETED |  |  |  | 2025-01-06 | ATK Constructions | Completed | 14
| 142 | 36/6 | 3DA+3 | DFR | 2024-12-29 | 26.872 | COMPLETED |  |  |  | 2025-01-09 | TaGore | Completed | 15
| 143 | 11/5 | 3DA+0 | DFR | 2025-01-03 | 25.578 | COMPLETED |  |  |  | 2025-01-10 | Ashok kumar (Thotta) | Completed | 16
| 144 | 31/6 | 3DA+3 | DFR | 2025-01-05 | 26.872 | COMPLETED |  |  |  | 2025-01-12 | ATK Constructions | Completed | 17
| 145 | 13/7 | 3DA+6 | WET | 2025-01-05 | 41.944 | COMPLETED |  |  |  | 2025-01-13 | BaLraJ | Completed | 12
| 146 | 38/0 | 3DC1+0 | DFR | 2025-01-03 | 67.247 | COMPLETED |  |  |  | 2025-01-15 | Ashok-2 (Venkateshwarlu) |  | 13
| 147 | 17/0 | 3DC1+0 | WBC | 2025-01-06 | 157.938 | COMPLETED |  |  |  | 2025-01-16 | Ammu Engineering |  | 15
| 148 | 37/6 | 3DA+0 | DFR | 2025-01-03 | 25.578 | COMPLETED |  |  |  | 2025-01-16 | Venkateshwarlu | Completed | 16
| 149 | 33/0 | 3DD45+6 | WFR | 2025-01-09 | 102.566 | COMPLETED |  |  |  | 2025-01-16 | ATK Constructions | Completed | 14
| 150 | 11/1 | 3DA+0 | WBC | 2025-01-12 | 68.906 | COMPLETED |  |  |  | 2025-01-17 | Ashok kumar (Thotta) | Completed | 16
| 151 | 36/5 | 3DA+0 | DFR | 2025-01-07 | 25.578 | COMPLETED |  |  |  | 2025-01-18 | TaGore | Completed | 17
| 152 | 17/2 | 3DA+3 | WET | 2025-01-13 | 41.944 | COMPLETED |  |  |  | 2025-01-18 | Ammu Engineering | Completed | 15
| 153 | 29/0 | 3DC1+0 | DFR | 2025-01-08 | 67.247 | COMPLETED |  |  |  | 2025-01-19 | ATK Constructions | Completed | 15
| 154 | 16/2 | 3DA+0 | WET | 2025-01-06 | 41.042 | COMPLETED |  |  |  | 2025-01-21 | Visionary & Co | Completed | 15
| 155 | 33/2 | 3DA-3 | DFR | 2025-01-17 | 25.578 | COMPLETED |  |  |  | 2025-01-22 | ATK Constructions | Completed | 16
| 156 | 36/4 | 3DA+3 | DFR | 2025-01-12 | 26.872 | COMPLETED |  |  |  | 2025-01-24 | TaGore | Completed | 16
| 157 | 39/5 | 3DA+3 | DFR | 2025-01-17 | 26.872 | COMPLETED |  |  |  | 2025-01-24 | Ashok-2 (Venkateshwarlu) | Completed | 15
| 158 | 33/1 | 3DA+0 | DFR | 2025-01-13 | 25.578 | COMPLETED |  |  |  | 2025-01-25 | ATK Constructions |  | 14
| 159 | 37/1 | 3DA+3 | DFR | 2025-01-07 | 26.872 | COMPLETED |  |  |  | 2025-01-25 | Venkateshwarlu |  | 15
| 160 | 10/0 | 3DB2+0 | DFR | 2025-01-19 | 45.764 | COMPLETED |  |  |  | 2025-01-27 | Ashok kumar (Thotta) | Completed | 13
| 161 | 32/1 | 3DA+0 | WFR | 2025-01-22 | 25.578 | COMPLETED |  |  |  | 2025-01-27 | ATK Constructions | Completed | 16
| 162 | 39/6 | 3DA+0 | WFR | 2025-01-17 | 39.527 | COMPLETED |  |  |  | 2025-01-28 | Ashok-2 (Venkateshwarlu) | Completed | 14
| 163 | 32/2 | 3DA+3 | DFR | 2025-01-22 | 26.872 | COMPLETED |  |  |  | 2025-01-29 | ATK Constructions | Completed | 16
| 164 | 14/0 | 3DC2+6 | WET | 2025-01-18 | 88.492 | COMPLETED |  |  |  | 2025-01-30 | BaLraJ | Completed | 16
| 165 | 10/2 | 3DA+0 | DFR | 2025-01-24 | 25.578 | COMPLETED |  |  |  | 2025-01-30 | Ashok kumar (Thotta) | Completed | 17
| 166 | 37/2 | 3DA+0 | DFR | 2025-01-24 | 25.578 | COMPLETED |  |  |  | 2025-01-30 | Venkateshwarlu |  | 15
| 167 | 36/3 | 3DA+3 | DFR | 2025-01-20 | 26.872 | COMPLETED |  |  |  | 2025-01-30 | TaGore |  | 14
| 168 | 35/1 | 3DA+0 | DFR | 2025-01-27 | 25.578 | COMPLETED |  |  |  | 2025-01-31 | ATK Constructions | Completed | 16
| 169 | 19/0 | 3DD45+0 | WET | 2025-01-19 | 114.453 | COMPLETED |  |  |  | 2025-01-31 | Ammu Engineering | Completed | 18
| 170 | 39/8 | 3DA+3 | DFR | 2025-01-25 | 26.872 | COMPLETED |  |  |  | 2025-01-31 | Ashok-2 (Venkateshwarlu) |  | 20
| 171 | 35/4 | 3DA+6 | DFR | 2025-01-30 | 26.872 | COMPLETED |  |  |  | 2025-02-02 | ATK Constructions | Completed | 15
| 172 | 10/1 | 3DA+3 | DFR | 2025-01-25 | 26.872 | COMPLETED |  |  |  | 2025-02-04 | Ashok kumar (Thotta) | Completed | 13
| 173 | 36/1 | 3DA+0 | DFR | 2025-01-25 | 25.578 | COMPLETED |  |  |  | 2025-02-06 | TaGore | Completed | 16
| 174 | 9/10 | 2DA+3 | DFR | 2025-01-25 | 19.144 | COMPLETED |  |  |  | 2025-02-06 | Ammu Engineering | Completed | 14
| 175 | 9/9 | 2DA+0 | DFR | 2025-01-27 | 18.592 | COMPLETED |  |  |  | 2025-02-09 | Ammu Engineering | Completed | 16
| 176 | 36/0 | 3DD60+3 | DFR | 2025-01-27 | 144.452 | COMPLETED |  |  |  | 2025-02-09 | ATK Constructions |  | 16
| 177 | 37/0 | 3DB2+0 | DFR | 2025-01-28 | 45.764 | COMPLETED |  |  |  | 2025-02-10 | Venkateshwarlu |  | 17
| 178 | 16/0 | 3DD45+0 | WET | 2025-02-01 | 114.453 | COMPLETED |  |  |  | 2025-02-10 | BaLraJ | Completed | 15
| 179 | 10/4 | 3DA+3 | DFR | 2025-02-05 | 26.872 | COMPLETED |  |  |  | 2025-02-12 | Ashok kumar (Thotta) | Completed | 15
| 180 | 32/0 | 3DC1+0 | DFR | 2025-02-01 | 67.247 | COMPLETED |  |  |  | 2025-02-13 | ATK Constructions | Completed | 14
| 181 | 36/2 | 3DA+3 | DFR | 2025-02-05 | 26.872 | COMPLETED |  |  |  | 2025-02-14 | TaGore | Completed | 16
| 182 | 9/7 | 2DA+3 | DFR | 2025-01-29 | 19.144 | COMPLETED |  |  |  | 2025-02-14 | Ammu Engineering | Completed | 16
| 183 | 10/3 | 3DA+3 | DFR | 2025-02-09 | 26.872 | COMPLETED |  |  |  | 2025-02-15 | Ashok kumar (Thotta) | Completed | 16
| 184 | 39/0 | 3DC1+3 | DFR | 2025-02-05 | 67.247 | COMPLETED |  |  |  | 2025-02-16 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 185 | 10/5 | 3DA+3 | DFR | 2025-02-06 | 26.872 | COMPLETED |  |  |  | 2025-02-16 | BaLraJ | Completed | 16
| 186 | 9/5 | 2DA+0 | DFR | 2025-02-01 | 18.592 | COMPLETED |  |  |  | 2025-02-16 | Ammu Engineering | Completed | 16
| 187 | 39/9 | 3DA+9 | DFR | 2025-02-02 | 26.872 | COMPLETED |  |  |  | 2025-02-18 | Ashok-2 (Venkateshwarlu) |  | 17
| 188 | 10/9 | 3DA+6 | DFR | 2025-01-23 | 26.872 | COMPLETED |  |  |  | 2025-02-19 | BaLraJ | Completed | 17
| 189 | 9/8 | 2DA+0 | DFR | 2025-01-24 | 18.592 | COMPLETED |  |  |  | 2025-02-20 | Ammu Engineering | Completed | 15
| 190 | 35/0 | 3DB1+9 | DFR | 2025-02-16 | 47.611 | COMPLETED |  |  |  | 2025-02-20 | ATK Constructions | Completed | 15
| 191 | 42/6 | 3DA+0 | DFR | 2025-02-13 | 25.578 | COMPLETED |  |  |  | 2025-02-21 | TaGore | Completed | 14
| 192 | 42/4 | 3DA+3 | DFR | 2025-02-12 | 26.872 | COMPLETED |  |  |  | 2025-02-21 | Venkateshwarlu | Completed | 16
| 193 | 13/8 | 3DA+0 | WET | 2025-02-17 | 41.042 | COMPLETED |  |  |  | 2025-02-21 | Ashok kumar (Thotta) | Completed | 16
| 194 | 42/5 | 3DA+3 | DFR | 2025-02-13 | 26.872 | COMPLETED |  |  |  | 2025-02-23 | Venkateshwarlu | Completed | 16
| 195 | 10/7 | 3DA+3 | DFR | 2025-01-19 | 26.872 | COMPLETED |  |  |  | 2025-02-23 | BaLraJ | Completed | 17
| 196 | 9/6 | 2DA+3 | DFR | 2025-02-04 | 19.144 | COMPLETED |  |  |  | 2025-02-24 | Ammu Engineering | Completed | 17
| 197 | 10/6 | 3DA+6 | DFR | 2025-02-11 | 26.872 | COMPLETED |  |  |  | 2025-02-25 | BaLraJ | Completed | 15
| 198 | 9/4 | 2DA+0 | DFR | 2025-02-14 | 18.592 | COMPLETED |  |  |  | 2025-02-27 | Ammu Engineering | Completed | 15
| 199 | 9/3 | 2DA+9 | DFR | 2025-02-19 | 19.144 | COMPLETED |  |  |  | 2025-02-28 | Ammu Engineering | Completed | 16
| 200 | 42/7 | 3DA+9 | DFR | 2025-02-16 | 26.872 | COMPLETED |  |  |  | 2025-02-28 | TaGore | Completed | 16
| 201 | 42/3 | 3DA+3 | WFR | 2025-02-18 | 40.406 | COMPLETED |  |  |  | 2025-03-01 | Venkateshwarlu | Completed | 17
| 202 | 15/0 | 3DD45+3 | WET | 2025-02-18 | 112.797 | COMPLETED |  |  |  | 2025-03-04 | Ashok kumar (Thotta) | Completed | 17
| 203 | 9/2 | 2DA+0 | DFR | 2025-02-27 | 18.592 | COMPLETED |  |  |  | 2025-03-04 | Ammu Engineering | Completed | 15
| 204 | 16/4 | 3DA+0 | WET | 2025-02-26 | 41.042 | COMPLETED |  |  |  | 2025-03-04 | BaLraJ | Completed | 15
| 205 | 40/0 | 3DB2+9 | DFR | 2025-02-20 | 49.777 | COMPLETED |  |  |  | 2025-03-06 | Ashok-2 (Venkateshwarlu) | Completed | 16
| 206 | 42/2 | 3DA+0 | DFR | 2025-02-26 | 25.578 | COMPLETED |  |  |  | 2025-03-07 | Venkateshwarlu | Completed | 15
| 207 | 9/1 | 2DA+3 | DFR | 2025-02-27 | 19.144 | COMPLETED |  |  |  | 2025-03-07 | Ammu Engineering | Completed | 16
| 208 | 16/5 | 3DA+0 | WET | 2025-03-04 | 41.042 | COMPLETED |  |  |  | 2025-03-08 | BaLraJ | Completed | 17
| 209 | 32/3 | 3DA+6 | DFR | 2025-02-25 | 26.872 | COMPLETED |  |  |  | 2025-03-08 | TaGore | Completed | 15
| 210 | 40/1 | 3DA+9(2mRC) | DFR | 2025-02-20 | 34.753 | COMPLETED |  |  |  | 2025-03-12 | Ashok-2 (Venkateshwarlu) |  | 16
| 211 | 16/1 | 3DA+0 | WET | 2025-03-04 | 41.042 | COMPLETED |  |  |  | 2025-03-13 | BaLraJ |  | 17
| 212 | 8/15 | 2DA+3 | DFR | 2024-03-05 | 19.144 | COMPLETED |  |  |  | 2025-03-13 | Ammu Engineering | Completed | 17
| 213 | 8/14 | 2DA+3 | DFR | 2025-03-13 | 19.144 | COMPLETED |  |  |  | 2025-03-18 | Ammu Engineering | Completed | 17
| 214 | 16/3 | 3DA+3 | WET | 2025-03-05 | 41.944 | COMPLETED |  |  |  | 2025-03-18 | BaLraJ | Completed | 18
| 215 | 11/7 | 3DA+0 | WET | 2025-03-06 | 41.042 | COMPLETED |  |  |  | 2025-03-19 | Ashok kumar (Thotta) | Completed | 15
| 216 | 9/0 | 2DB1+0 | DFR | 2025-03-08 | 39.01 | COMPLETED |  |  |  | 2025-03-24 | Ammu Engineering | Completed | 16
| 217 | 34/1 | 3DB1+0 | DFR | 2024-03-05 | 43.668 | COMPLETED |  |  |  | 2025-03-26 | TaGore | Completed | 17
| 218 | 8/12 | 2DA+0 | DFR | 2025-03-17 | 18.592 | COMPLETED |  |  |  | 2025-03-28 | Ammu Engineering | Completed | 17
| 219 | 13/11 | 3DA+0 | WET | 2025-03-22 | 41.042 | COMPLETED |  |  |  | 2025-03-30 | Venkateshwarlu |  | 18
| 220 | 15/3 | 3DA+0 | WBC | 2025-03-27 | 68.906 | COMPLETED |  |  |  | 2025-04-08 | Venkateshwarlu | Completed | 18
| 221 | 34/2 | 3DB1+6 | DFR | 2025-03-10 | 47.611 | COMPLETED |  |  |  | 2025-04-11 | TaGore | Completed | 17
| 222 | 11/8 | 3DA+0 | WET | 2025-04-09 | 41.042 | COMPLETED |  |  |  | 2025-04-14 | Venkateshwarlu |  | 15
| 223 | 6/2 | 2DA+0 | DFR | 2025-04-08 | 18.592 | COMPLETED |  |  |  | 2025-04-18 | Venkateshwarlu | Completed | 16
| 224 | 37/3 | 3DA+0 | DFR | 2025-04-07 | 25.578 | COMPLETED |  |  |  | 2025-04-19 | TaGore | Completed | 17
| 225 | 6/1 | 2DA+3 | DFR | 2025-04-14 | 19.144 | COMPLETED |  |  |  | 2025-04-22 | Venkateshwarlu | Completed | 17
| 226 | 20/0 | 3DB1+0 | DFR | 2025-04-01 | 43.668 | COMPLETED |  |  |  | 2025-04-25 | ATK Constructions | Completed | 17
| 227 | 6/6 | 2DA+0 | DFR | 2025-04-23 | 18.592 | COMPLETED |  |  |  | 2025-04-27 | Venkateshwarlu | Completed | 16
| 228 | 42/1 | 3DA+6 | DFR | 2025-04-21 | 41.944 | COMPLETED |  |  |  | 2025-04-28 | Ashok-2 (Venkateshwarlu) |  | 18
| 229 | 6/7 | 2DA+3 | DFR | 2025-04-17 | 19.144 | COMPLETED |  |  |  | 2025-04-29 | Venkateshwarlu |  | 17
| 230 | 20A/0 | 3DB2+0 | DFR | 2025-04-07 | 45.764 | COMPLETED |  |  |  | 2025-04-30 | ATK Constructions | Completed | 17
| 231 | 34/0 | 3DC1+0 | DFR | 2025-03-13 | 67.247 | COMPLETED |  |  |  | 2025-05-03 | TaGore | Completed | 17
| 232 | 8/8 | 2DA+0 | DFR | 2025-03-18 | 18.592 | COMPLETED |  |  |  | 2025-05-03 | Ammu Engineering | Completed | 15
| 233 | 4/7 | 2DA+3 | DFR | 2025-04-19 | 19.144 | COMPLETED |  |  |  | 2025-05-04 | BaLraJ | Completed | 17
| 234 | 8/7 | 2DA+3 | DFR | 2025-04-07 | 19.144 | COMPLETED |  |  |  | 2025-05-04 | ATK Constructions | Completed | 18
| 235 | 4/20 | 2DA+9 | DFR | 2025-04-11 | 19.144 | COMPLETED |  |  |  | 2025-05-06 | ATK Constructions | Completed | 17
| 236 | 4/8 | 2DA+3 | DFR | 2025-05-01 | 19.144 | COMPLETED |  |  |  | 2025-05-07 | BaLraJ |  | 17
| 237 | 8/9 | 2DA+3 | DFR | 2025-04-10 | 19.144 | COMPLETED |  |  |  | 2025-05-08 | Ammu Engineering | Completed | 16
| 238 | 41/0 | 3DC1+0 | WET | 01--05-2025 | 100.373 | COMPLETED |  |  |  | 2025-05-11 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 239 | 4/9 | 2DA+0 | DFR | 2025-04-12 | 18.592 | COMPLETED |  |  |  | 2025-05-11 | BaLraJ | Completed | 16
| 240 | 8/5 | 2DA+0 | DFR | 2025-04-06 | 27.13 | COMPLETED |  |  |  | 2025-05-12 | ATK Constructions |  | 18 | SF
| 241 | 8/10 | 2DA+0 | DFR | 2025-04-15 | 18.592 | COMPLETED |  |  |  | 2025-05-13 | Ammu Engineering |  | 18
| 242 | 4/6 | 2DA+0 | DFR | 2025-04-20 | 18.592 | COMPLETED |  |  |  | 2025-05-13 | BaLraJ | Completed | 18
| 243 | 42/9 | 3DA+3 | DFR | 2025-04-15 | 41.944 | COMPLETED |  |  |  | 2025-05-15 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 244 | 8/6 | 2DA+0 | DFR | 2025-04-06 | 27.13 | COMPLETED |  |  |  | 2025-05-15 | ATK Constructions | Completed | 18 | SF
| 245 | 4/12 | 2DB1+0 | DFR | 2025-05-07 | 39.01 | COMPLETED |  |  |  | 2025-05-16 | ATK Constructions | Completed | 19
| 246 | 4/3 | 2DA+6 | DFR | 2025-04-17 | 27.89 | COMPLETED |  |  |  | 2025-05-17 | BaLraJ | Completed | 17 | SF
| 247 | 4/21 | 2DA+3 | DFR | 2025-04-11 | 27.89 | COMPLETED |  |  |  | 2025-05-18 | ATK Constructions | Completed | 17
| 248 | 6/3 | 2DA+0 | DFR | 2025-04-16 | 18.592 | COMPLETED |  |  |  | 2025-05-19 | Venkateshwarlu | Completed | 17
| 249 | 6/4 | 2DA+0 | DFR | 2025-04-16 | 27.13 | COMPLETED |  |  |  | 2025-05-20 | Venkateshwarlu | Completed | 16 | SF
| 250 | 4/19 | 2DA+6 | DFR | 2025-04-17 | 27.89 | COMPLETED |  |  |  | 2025-05-20 | ATK Constructions | Completed | 16 | SF
| 251 | 4/5 | 2DA+3 | DFR | 2025-04-17 | 19.144 | COMPLETED |  |  |  | 2025-05-20 | BaLraJ |  | 16
| 252 | 4/18 | 2DA+0 | DFR | 2025-04-19 | 27.13 | COMPLETED |  |  |  | 2025-05-21 | ATK Constructions | Completed | 16 | SF
| 253 | 8/11 | 2DA+0 | DFR | 2025-04-15 | 18.592 | COMPLETED |  |  |  | 2025-05-22 | Ammu Engineering |  | 17 | SF
| 254 | 43A/2 | 3DA+0 | DFR | 2025-05-18 | 25.578 | COMPLETED |  |  |  | 2025-05-22 | Ashok-2 (Venkateshwarlu) |  | 17
| 255 | 6/5 | 2DA+0 | DFR | 2025-05-05 | 27.13 | COMPLETED |  |  |  | 2025-05-23 | Venkateshwarlu | Completed | 15 | SF
| 256 | 4/23 | 2DA+0 | DFR | 2025-04-17 | 27.13 | COMPLETED |  |  |  | 2025-05-23 | ATK Constructions | Completed | 16 | SF
| 257 | 43A/3 | 3DA+0 | DFR | 2025-05-18 | 25.578 | COMPLETED |  |  |  | 2025-05-25 | Ashok-2 (Venkateshwarlu) |  | 17
| 258 | 4/4 | 2DA+0 | DFR | 2025-04-17 | 27.13 | COMPLETED |  |  |  | 2025-05-25 | BaLraJ | Completed | 17 | SF
| 259 | 4/17 | 2DA+3 | DFR | 2025-05-15 | 27.89 | COMPLETED |  |  |  | 2025-05-27 | ATK Constructions | Completed | 17 | SF
| 260 | 4/14 | 2DA+3 | DFR | 2025-05-11 | 27.89 | COMPLETED |  |  |  | 2025-05-28 | ATK Constructions |  | 16 | SF
| 261 | 43A/4 | 3DA+0 | DFR | 2025-05-18 | 25.578 | COMPLETED |  |  |  | 2025-05-28 | Ashok-2 (Venkateshwarlu) |  | 17
| 262 | 4/15 | 2DA+0 | DFR | 2025-05-04 | 27.13 | COMPLETED |  |  |  | 2025-05-30 | ATK Constructions |  | 17 | SF
| 263 | 8/13 | 2DA+3 | DFR | 2025-04-08 | 27.89 | COMPLETED |  |  |  | 2025-05-30 | Ammu Engineering | Completed | 17 | SF
| 264 | 4/0 | 2DB2+0 | DFR | 2025-05-19 | 39.75 | COMPLETED |  |  |  | 2025-05-31 | BaLraJ | Completed | 17
| 265 | 4/16 | 2DA+0 | DFR | 2025-04-29 | 27.13 | COMPLETED |  |  |  | 2025-05-31 | ATK Constructions |  | 17 | SF
| 266 | 3/3 | 2DA+0 | DFR | 2025-04-26 | 18.592 | COMPLETED |  |  |  | 2025-05-31 | Venkateshwarlu |  | 17
| 267 | 43A/5 | 3DA+3 | DFR | 2025-05-18 | 26.872 | COMPLETED |  |  |  | 2025-05-31 | Ashok-2 (Venkateshwarlu) |  | 16
| 268 | 4/13 | 2DA+0 | DFR | 2025-05-11 | 27.13 | COMPLETED |  |  |  | 2025-06-01 | ATK Constructions | Completed | 15 | SF
| 269 | 4/2 | 2DA+3 | DFR | 2025-05-03 | 27.89 | COMPLETED |  |  |  | 2025-06-03 | BaLraJ | Completed | 17 | SF
| 270 | 4/11 | 2DA+6 | DFR | 2025-05-17 | 27.89 | COMPLETED |  |  |  | 2025-06-03 | ATK Constructions |  | 19 | SF
| 271 | 43/3 | 3DA+0 | DFR | 2025-05-27 | 25.578 | COMPLETED |  |  |  | 2025-06-04 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 272 | 4/10 | 2DA+3 | DFR | 2025-05-24 | 19.144 | COMPLETED |  |  |  | 2025-06-06 | BaLraJ | Completed | 17 | SF
| 273 | 3/0 | 2DB2+3 | DFR | 2025-05-24 | 25.4 | COMPLETED |  |  |  | 2025-06-06 | Venkateshwarlu |  | 15
| 274 | 28/1 | 3DA+9 | WET(2mRC) | 2025-05-19 | 48.328 | COMPLETED |  |  |  | 2025-06-08 | Tagore |  | 19
| 275 | 1B/3 | 2DA+0 | DFR | 2025-06-01 | 18.592 | COMPLETED |  |  |  | 2025-06-08 | ATK Constructions |  | 15
| 276 | 43/2 | 3DA-3 | DFR | 2025-06-03 | 25.578 | COMPLETED |  |  |  | 2025-06-09 | Ashok-2 (Venkateshwarlu) |  | 17
| 277 | 2/5 | 2DA+0 | DFR | 2025-05-31 | 18.592 | COMPLETED |  |  |  | 2025-06-14 | Ammu Engineering |  | 17
| 278 | 42/8 | 3DA+9(2mRC) | DFR | 2025-06-10 | 32.186 | COMPLETED |  |  |  | 2025-06-14 | Ashok-2 (Venkateshwarlu) |  | 17
| 279 | 1B/2 | 2DA+3 | DFR | 2025-06-01 | 19.144 | COMPLETED |  |  |  | 2025-06-15 | ATK Constructions |  | 16
| 280 | 4/1 | 2DA+3 | DFR | 2025-05-31 | 19.144 | COMPLETED |  |  |  | 2025-06-15 | BaLraJ | Completed | 17
| 281 | 3/1 | 2DA+9 | DFR | 2025-05-31 | 19.144 | COMPLETED |  |  |  | 2025-06-17 | Venkateshwarlu |  | 17
| 282 | 1B/0 | 2DB2+3 | DFR | 2025-06-01 | 42.95 | COMPLETED |  |  |  | 2025-06-19 | ATK Constructions |  | 16
| 283 | 3/2 | 2DA+9 | DFR | 2025-05-24 | 19.144 | COMPLETED |  |  |  | 2025-06-21 | Venkateshwarlu |  | 17
| 284 | 1A/0 | 2DD45+0 | DFR | 2025-06-13 | 57.746 | COMPLETED |  |  |  | 2025-06-21 | BaLraJ |  | 17
| 285 | 43/1 | 3DA+3 | WFR | 2025-06-13 | 40.406 | COMPLETED |  |  |  | 2025-06-21 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 286 | 1B/1 | 2DA+6 | DFR | 2025-06-17 | 19.144 | COMPLETED |  |  |  | 2025-06-21 | ATK Constructions |  | 16
| 287 | 2/3 | 2DA+0 | DFR | 2025-06-02 | 18.592 | COMPLETED |  |  |  | 2025-06-23 | Ammu Engineering | Completed | 17
| 288 | 43/4 | 3DA+3 | DFR | 2025-06-17 | 26.872 | COMPLETED |  |  |  | 2025-06-24 | Ashok-2 (Venkateshwarlu) | Completed | 16
| 289 | 8/2 | 2DB1+6 | DFR | 2025-06-20 | 39.13 | COMPLETED |  |  |  | 2025-06-25 | ATK Constructions |  | 17
| 290 | 1C/0 | 2DB1+9 | DFR | 2025-06-24 | 39.13 | COMPLETED |  |  |  | 2025-06-29 | ATK Constructions |  | 16
| 291 | 2/1 | 2DA+0 | DFR | 2025-06-18 | 18.592 | COMPLETED |  |  |  | 2025-06-29 | Venkateshwarlu |  | 17
| 292 | 43/0 | 3DB2+0 | DFR | 2025-06-25 | 45.764 | COMPLETED |  |  |  | 2025-06-30 | Ashok-2 (Venkateshwarlu) |  | 16
| 293 | 2/2 | 2DA+0 | DFR | 2025-06-18 | 18.592 | COMPLETED |  |  |  | 2025-07-03 | ATK Constructions |  | 17
| 294 | 8/4 | 2DB1+6 | DFR | 2025-07-02 | 39.13 | COMPLETED |  |  |  | 2025-07-08 | ATK Constructions |  | 17
| 295 | 2/0 | 2DB2+6 | DFR | 2025-06-24 | 25.4 | COMPLETED |  |  |  | 2025-07-10 | Venkateshwarlu |  | 17
| 296 | 2/4 | 2DA+0 | DFR | 2025-05-31 | 18.592 | COMPLETED |  |  |  | 2025-07-12 | Ammu Engineering |  | 17
| 297 | 6/0 | 2DD45+6 | DFR | 2025-07-08 | 57.746 | COMPLETED |  |  |  | 2025-07-13 | ATK Constructions |  | 15
| 298 | 43/5 | 3DA+3(2mRC) | DFR | 2025-06-29 | 37.5 | COMPLETED |  |  |  | 2025-07-14 | Ashok-2 (Venkateshwarlu) | Completed | 17
| 299 | 5/0 | 2DD45+6 | DFR | 2025-07-01 | 57.746 | COMPLETED |  |  |  | 2025-07-16 | ATK Constructions | Completed | 17
| 300 | 8/3 | 2DB1+9 | DFR | 2025-07-13 | 39.13 | COMPLETED |  |  |  | 2025-07-18 | ATK Constructions |  | 17
| 301 | 43A/1 | 3DB1+3 | DFR | 2025-07-07 | 47.611 | COMPLETED |  |  |  | 2025-07-20 | Ashok-2 (Venkateshwarlu) |  | 17
| 302 | 8/1 | 2DB1+6 | DFR | 2025-07-19 | 39.13 | COMPLETED |  |  |  | 2025-07-22 | Ashok-2 (Venkateshwarlu) |  | 17
| 303 | 4/22 | 2DA+6(3mRc ) | DFR | 2025-07-09 | 21.518 | COMPLETED |  |  |  | 2025-07-25 | ATK Constructions |  | 17
| 304 | 43B/0 | 3DB1+9 | DFR | 2025-07-16 | 47.611 | COMPLETED |  |  |  | 2025-07-28 | Ashok-2 (Venkateshwarlu) |  | 17
| 305 | 43A/0 | 3DD45+9 | DFR | 2025-07-22 | 102.566 | COMPLETED |  |  |  | 2025-08-03 | Ashok-2 (Venkateshwarlu) |  | 17
| 306 | 1/0 | 2DD60+0 | DFR | 2025-08-11 | 107.12 | COMPLETED |  |  |  | 2025-08-25 | Venkateshwarlu |  | 15
| 307 | 44/0 | 3DD45+3 | DFR | 2025-07-16 | 80.164 | COMPLETED |  |  |  | 2025-10-26 | Ashok-2 (Venkateshwarlu) |  | 17
| 308 | 8/0 | 2DD60+0 | DFR | 2025-07-22 | 107.12 | 1.5 m + 2.3 m +2.9 m +1.5 m Excavation Done (Courtcase)
EARTHING
| SL No. | Location No. | Tower Type | Classification | Start Date | Status |  |  |  | End Date | Gang Name | Remark
| 1 | 24/4 | 3DA+0 | DFR | 2024-05-25 | COMPLETED |  |  |  | 2024-05-25 | ATK CONSTRUCTIONS
| 2 | 24/2 | 3DA+3 | DFR | 2024-06-07 | COMPLETED |  |  |  | 2024-06-07 | ATK CONSTRUCTIONS
| 3 | 24/3 | 3DA+0 | DFR | 2024-06-11 | COMPLETED |  |  |  | 2024-06-11 | ATK CONSTRUCTIONS
| 4 | 24/5 | 3DA+0 | DFR | 2024-06-23 | COMPLETED |  |  |  | 2024-06-23 | ATK CONSTRUCTIONS
| 5 | 24/6 | 3DA+0 | DFR | 2024-06-24 | COMPLETED |  |  |  | 2024-06-24 | ATK CONSTRUCTIONS
| 6 | 29/1 | 3DA+9 | DFR | 2024-07-06 | COMPLETED |  |  |  | 2024-07-06 | TSB
| 7 | 25/4 | 3DA+0 | DFR | 2024-07-06 | COMPLETED |  |  |  | 2024-07-06 | ATK CONSTRUCTIONS
| 8 | 25/5 | 3DA+6 | DFR | 2024-07-06 | COMPLETED |  |  |  | 2024-07-06 | ATK CONSTRUCTIONS
| 9 | 12/2 | 3DA+3 | DFR | 2024-07-12 | COMPLETED |  |  |  | 2024-07-12 | RR Const.
| 10 | 12/3 | 3DA+3 | DFR | 2024-07-12 | COMPLETED |  |  |  | 2024-07-12 | RR Const.
| 11 | 12/4 | 3DA+3 | DFR | 2024-07-12 | COMPLETED |  |  |  | 2024-07-12 | RR Const.
| 12 | 22/3 | 3DA+6 | DFR | 2024-07-12 | COMPLETED |  |  |  | 2024-07-12 | Ammu Eng
| 13 | 23/4 | 3DA+0 | DFR | 2024-07-12 | COMPLETED |  |  |  | 2024-07-12 | Ammu Eng
| 14 | 22/4 | 3DA+3 | DFR | 2024-07-13 | COMPLETED |  |  |  | 2024-07-13 | Ammu Eng
| 15 | 22/5 | 3DA+0 | DFR | 2024-07-13 | COMPLETED |  |  |  | 2024-07-13 | Ammu Eng
| 16 | 26/1 | 3DA+0 | DFR | 2024-07-13 | COMPLETED |  |  |  | 2024-07-13 | ATK CONSTRUCTIONS
| 17 | 26/3 | 3DA+0 | DFR | 2024-07-13 | COMPLETED |  |  |  | 2024-07-13 | ATK CONSTRUCTIONS
| 18 | 21/9 | 3DA+0 | DFR | 2024-07-28 | COMPLETED |  |  |  | 2024-07-28 | Ammu Eng
| 19 | 26/4 | 3DA+0 | DFR | 2024-07-28 | COMPLETED |  |  |  | 2024-07-28 | ATK CONSTRUCTIONS
| 20 | 24/1 | 3DA+6 | DFR | 2024-07-28 | COMPLETED |  |  |  | 2024-07-28 | ATK CONSTRUCTIONS
| 21 | 22/2 | 3DA+0 | DFR | 2024-07-30 | COMPLETED |  |  |  | 2024-07-30 | Ammu Eng
| 22 | 25/1 | 3DA+0 | DFR | 2024-07-30 | COMPLETED |  |  |  | 2024-07-30 | ATK CONSTRUCTIONS
| 23 | 24/7 | 3DA+0 | DFR | 2024-07-31 | COMPLETED |  |  |  | 2024-07-31 | ATK CONSTRUCTIONS
| 24 | 23/2 | 3DA+0 | DFR | 2024-07-31 | COMPLETED |  |  |  | 2024-07-31 | Ammu Eng
| 25 | 23/3 | 3DA+0 | DFR | 2024-07-31 | COMPLETED |  |  |  | 2024-07-31 | Ammu Eng
| 26 | 27/1 | 3DA+0 | DFR | 2024-07-31 | COMPLETED |  |  |  | 2024-07-31 | ATK CONSTRUCTIONS
| 27 | 26/2 | 3DA+0 | DFR | 2024-08-01 | COMPLETED |  |  |  | 2024-08-01 | ATK CONSTRUCTIONS
| 28 | 12/5 | 3DA+0 | DFR | 2024-08-03 | COMPLETED |  |  |  | 2024-08-03 | ANJU CONSTRUCTIONS
| 29 | 27/4 | 3DA+0 | DFR | 2024-08-09 | COMPLETED |  |  |  | 2024-08-09 | ATK CONSTRUCTIONS
| 30 | 27/8 | 3DA+0 | DFR | 2024-08-10 | COMPLETED |  |  |  | 2024-08-10 | Company Gang
| 31 | 12/11 | 3DA+6 | DFR | 2024-08-14 | COMPLETED |  |  |  | 2024-08-14 | ANJU CONSTRUCTIONS
| 32 | 12/6 | 3DA+0 | DFR | 2024-08-14 | COMPLETED |  |  |  | 2024-08-14 | ANJU CONSTRUCTIONS
| 33 | 27/5 | 3DA+0 | DFR | 2024-08-19 | COMPLETED |  |  |  | 2024-08-19 | ATK CONSTRUCTIONS
| 34 | 27/7 | 3DA+0 | DFR | 2024-08-19 | COMPLETED |  |  |  | 2024-08-19 | Company Gang
| 35 | 21/8 | 3DA+0 | DFR | 2024-08-25 | COMPLETED |  |  |  | 2024-08-25 | Ammu Eng
| 36 | 12/8 | 3DA+3 | DFR | 2024-08-27 | COMPLETED |  |  |  | 2024-08-27 | ANJU Const.
| 37 | 12/9 | 3DA+3 | DFR | 2024-08-27 | COMPLETED |  |  |  | 2024-08-27 | ANJU Const.
| 38 | 12/0 | 3DB2+0 | DFR | 2024-09-11 | COMPLETED |  |  |  | 2024-09-11 | ANJU Const.
| 39 | 21/7 | 3DA+0 | DFR | 2024-09-10 | COMPLETED |  |  |  | 2024-09-10 | Ammu Eng
| 40 | 29/4 | 3DA+0 | DFR | 2024-09-13 | COMPLETED |  |  |  | 2024-09-13 | ATK CONSTRUCTIONS
| 41 | 27/2 | 3DA+0 | DFR | 2024-09-14 | COMPLETED |  |  |  | 2024-09-14 | ATK CONSTRUCTIONS
| 42 | 29/9 | 3DB1+9 | DFR | 2024-09-15 | COMPLETED |  |  |  | 2024-09-15 | ATK CONSTRUCTIONS
| 43 | 12/7 | 3DA+0 | DFR | 2024-09-15 | COMPLETED |  |  |  | 2024-09-15 | ANJU Const.
| 44 | 29/5 | 3DA+3 | DFR | 2024-09-20 | COMPLETED |  |  |  | 2024-09-20 | ATK CONSTRUCTIONS
| 45 | 12/10 | 3DA+0 | DFR | 2024-09-24 | COMPLETED |  |  |  | 2024-09-24 | ANJU Const.
| 46 | 27/6 | 3DA+0 | DFR | 2024-09-27 | COMPLETED |  |  |  | 2024-09-27 | ATK CONSTRUCTIONS
| 47 | 29/8 | 3DA+0 | DFR | 2024-09-28 | COMPLETED |  |  |  | 2024-09-28 | ATK CONSTRUCTIONS
| 48 | 23/1 | 3DA+6 | DFR | 2024-10-03 | COMPLETED |  |  |  | 2024-10-03 | Ammu Eng
| 49 | 25/0 | 3DB2+0 | DFR | 2024-10-04 | COMPLETED |  |  |  | 2024-10-04 | ATK CONSTRUCTIONS
| 50 | 26/0 | 3DB2+0 | DFR | 2024-10-05 | COMPLETED |  |  |  | 2024-10-05 | ATK CONSTRUCTIONS
| 51 | 22/1 | 3DA+0 | WFR | 2024-10-09 | COMPLETED |  |  |  | 2024-10-09 | Ammu Eng
| 52 | 22/0 | 3DB1+0 | DFR | 2024-10-09 | COMPLETED |  |  |  | 2024-10-09 | Ammu Engineering
| 53 | 24/8 | 3DA+3 | DFR | 2024-10-12 | COMPLETED |  |  |  | 2024-10-12 | ATK CONSTRUCTIONS
| 54 | 27/0 | 3DB1+0 | DFR | 2024-10-12 | COMPLETED |  |  |  | 2024-10-12 | ATK CONSTRUCTIONS
| 55 | 27/3 | 3DC1+0(TP) | DFR | 2024-10-23 | COMPLETED |  |  |  | 2024-10-23 | ATK CONSTRUCTIONS
| 56 | 21/2 | 3DA+0 | WFR | 2024-10-23 | COMPLETED |  |  |  | 2024-10-23 | Ammu Engineering
| 57 | 31/1 | 3DA+3 | DFR | 2024-10-24 | COMPLETED |  |  |  | 2024-10-24 | ATK CONSTRUCTIONS
| 58 | 21/6 | 3DA+0 | DFR | 2024-11-04 | COMPLETED |  |  |  | 2024-11-04 | Ammu Engineering
| 59 | 19/2 | 3DA+0 | DFR | 2024-11-07 | COMPLETED |  |  |  | 2024-11-07 | Ammu Engineering
| 60 | 25/2 | 3DA+0 | WFR | 2024-11-07 | COMPLETED |  |  |  | 2024-11-07 | Ammu Engineering
| 61 | 17/3 | 3DA+6 | DFR | 16.11.2024 | COMPLETED |  |  |  | 2024-11-16 | Ammu Engineering
| 62 | 23/0 | 3DB2+0 | DFR | 2024-11-19 | COMPLETED |  |  |  | 2024-11-19 | Ammu Engineering
| 63 | 11/6 | 3DA+0 | DFR | 2024-12-02 | COMPLETED |  |  |  | 2024-12-02 | Amit Kumar
| 64 | 11/10 | 3DA+0 | WET | 2024-11-23 | COMPLETED |  |  |  | 2024-11-23 | Amit Kumar
| 65 | 11/9 | 3DA+0 | WET | 2024-11-26 | COMPLETED |  |  |  | 2024-11-26 | Amit Kumar
| 66 | 18/1 | 3DA+0 | DFR | 2024-12-09 | COMPLETED |  |  |  | 2024-12-09 | Ammu Eng
| 67 | 11/11 | 3DA+3 | DFR | 2024-12-11 | COMPLETED |  |  |  | 2024-12-11 | Ashok-1
| 68 | 11/0 | 3DC1+0 | DFR | 2024-12-12 | COMPLETED |  |  |  | 2024-12-12 | Amit Kumar
| 69 | 10/8 | 3DA+3 | DFR | 2024-12-12 | COMPLETED |  |  |  | 2024-12-12 | Amit Kumar
| 70 | 15/1 | 3DA+0 | WBC | 2024-12-13 | COMPLETED |  |  |  | 2024-12-13 | Ashok Kumar
| 71 | 15/2 | 3DA+3 | WET | 2024-12-13 | COMPLETED |  |  |  | 2024-12-13 | Ashok Kumar
| 72 | 13/2 | 3DA+0 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Balraj
| 73 | 13/3 | 3DA+6 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Balraj
| 74 | 13/4 | 3DA+3 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Balraj
| 75 | 13/5 | 3DA+0 | WET | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Balraj
| 76 | 13/9 | 3DA+3 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Ashok kumar
| 77 | 13/10 | 3DA+0 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Ashok-1
| 78 | 15/4 | 3DA+3 | WBC | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Ashok kumar
| 79 | 38/1 | 3DA+0 | WFR | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Venkateshwaralu
| 80 | 38/2 | 3DA+0 | DFR | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Venkateshwaralu
| 81 | 39/1 | 3DA+6 | WFR | 2024-12-14 | COMPLETED |  |  |  | 2024-12-14 | Ashok-2
| 82 | 13/6 | 3DA+6 | WBC | 2024-12-15 | COMPLETED |  |  |  | 2024-12-15 | Balraj
| 83 | 41/1 | 3DA+0 | WET | 2024-12-18 | COMPLETED |  |  |  | 2024-12-18 | Ashok-2
| 84 | 39/2 | 3DA+0 | WBC | 2024-12-18 | COMPLETED |  |  |  | 2024-12-18 | Ashok-2
| 85 | 21/5 | 3DA-3 | WFR | 2024-12-19 | COMPLETED |  |  |  | 2024-12-19 | Ammu Eng
| 86 | 30/2 | 3DA+3 | WFR | 2024-12-23 | COMPLETED |  |  |  | 2024-12-23 | ATK CONSTRUCTIONS
| 87 | 31/2 | 3DA+0 | WFR | 2024-12-24 | COMPLETED |  |  |  | 2024-12-24 | ATK CONSTRUCTIONS
| 88 | 18/0 | 3DB2+0 | DFR | 2024-12-26 | COMPLETED |  |  |  | 2024-12-26 | Ammu Eng
| 89 | 38/7 | 3DA+0 | WFR | 2024-12-26 | COMPLETED |  |  |  | 2024-12-26 | Ashok-2
| 90 | 39/3 | 3DA+3 | DFR | 2025-01-03 | COMPLETED |  |  |  | 2025-01-03 | Ashok-2
| 91 | 38/6 | 3DA+0 | WBC | 2025-01-04 | COMPLETED |  |  |  | 2025-01-04 | Venkateshwaralu
| 92 | 21/0 | 3DA+0 | DFR | 2025-01-05 | COMPLETED |  |  |  | 2025-01-05 | Tagore
| 93 | 25/3 | 3DA+0 | WFR | 2025-01-05 | COMPLETED |  |  |  | 2025-01-05 | ATK CONSTRUCTIONS
| 94 | 29/2 | 3DD45+0 | DFR | 2025-01-04 | COMPLETED |  |  |  | 2025-01-05 | Ammu Eng
| 95 | 29/7 | 3DA+3 | WFR | 2025-01-08 | COMPLETED |  |  |  | 2025-01-08 | ATK CONSTRUCTIONS
| 96 | 11/2 | 3DA+0 | WBC | 2025-01-11 | COMPLETED |  |  |  | 2025-01-11 | Ashok-1
| 97 | 11/3 | 3DA-3 | WBC | 2025-01-11 | COMPLETED |  |  |  | 2025-01-11 | Ashok-1
| 98 | 29/3 | 3DA+0 | DFR | 2025-01-11 | COMPLETED |  |  |  | 2025-01-11 | ATK CONSTRUCTIONS
| 99 | 29/6 | 3DA+0 | DFR | 2025-01-11 | COMPLETED |  |  |  | 2025-01-11 | ATK CONSTRUCTIONS
| 100 | 17/0 | 3DC1+0 | WBC | 2025-01-18 | COMPLETED |  |  |  | 2025-01-18 | Ammu Eng
| 101 | 13/7 | 3DA+6 | WET | 2025-01-18 | COMPLETED |  |  |  | 2025-01-18 | BaLraJ
| 102 | 33/0 | 3DD45+6 | WFR | 2025-01-19 | COMPLETED |  |  |  | 2025-01-19 | ATK CONSTRUCTIONS
| 103 | 16/10 | 3DA+3 | WBC | 2025-01-20 | COMPLETED |  |  |  | 2025-01-20 | Visionary & Co
| 104 | 17/1 | 3DA+3 | WET | 2025-01-20 | COMPLETED |  |  |  | 2025-01-20 | Ammu Eng
| 105 | 29/0 | 3DC1+0 | DFR | 2025-01-21 | COMPLETED |  |  |  | 2025-01-21 | ATK CONSTRUCTIONS
| 106 | 18/3 | 3DA+0 | WET | 2025-01-21 | COMPLETED |  |  |  | 2025-01-21 | Ammu Eng
| 107 | 19/1 | 3DA+6 | WBC | 2025-01-21 | COMPLETED |  |  |  | 2025-01-21 | Ammu Eng
| 108 | 17/2 | 3DA+3 | WET | 2025-01-21 | COMPLETED |  |  |  | 2025-01-21 | Ammu Eng
| 109 | 19/3 | 3DA+3 | DFR | 2025-01-23 | COMPLETED |  |  |  | 2025-01-23 | Ammu Eng
| 110 | 36/8 | 3DA+0 | WFR | 2025-01-25 | COMPLETED |  |  |  | 2025-01-25 | Ashok-2 (Venkateshwarlu)
| 111 | 39/4 | 3DA+3 | DFR | 2025-01-25 | COMPLETED |  |  |  | 2025-01-25 | Tagore
| 112 | 37/1 | 3DA+3 | DFR | 2025-01-26 | COMPLETED |  |  |  | 2025-01-26 | Venkateshwaralu
| 113 | 24/0 | 3DB1+0 | DFR | 2025-01-25 | COMPLETED |  |  |  | 2025-01-25 | Ammu Eng
| 114 | 11/1 | 3DA+0 | WBC | 2025-01-28 | COMPLETED |  |  |  | 2025-01-28 | Ashok kumar (Thotta)
| 115 | 21/1 | 3DA+0 | DFR | 2025-01-29 | COMPLETED |  |  |  | 2025-01-29 | Ammu Eng
| 116 | 21/3 | 3DA+6 | WBC | 2025-01-29 | COMPLETED |  |  |  | 2025-01-29 | Ammu Eng
| 117 | 11/5 | 3DA+0 | DFR | 2025-01-29 | COMPLETED |  |  |  | 2025-01-29 | Ashok kumar (Thotta)
| 118 | 14/0 | 3DC2+6 | WET | 2025-01-31 | COMPLETED |  |  |  | 2025-01-31 | BaLraJ
| 119 | 31/6 | 3DA+3 | DFR | 2025-01-31 | COMPLETED |  |  |  | 2025-01-31 | ATK CONSTRUCTIONS
| 120 | 32/1 | 3DA+0 | WFR | 2025-02-01 | COMPLETED |  |  |  | 2025-02-01 | ATK CONSTRUCTIONS
| 121 | 32/2 | 3DA+3 | DFR | 2025-02-01 | COMPLETED |  |  |  | 2025-02-01 | ATK CONSTRUCTIONS
| 122 | 10/2 | 3DA+0 | DFR | 2025-02-01 | COMPLETED |  |  |  | 2025-02-01 | Ashok kumar (Thotta)
| 123 | 19/0 | 3DD45+0 | WET | 2025-02-01 | COMPLETED |  |  |  | 2025-02-01 | Ammu Eng
| 124 | 36/3 | 3DA+3 | DFR | 2025-02-02 | COMPLETED |  |  |  | 2025-02-02 | TaGore
| 125 | 37/2 | 3DA+0 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | Venkateshwaralu
| 126 | 37/4 | 3DA+6 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | Ashok-2
| 127 | 37/5 | 3DA+0 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | Venkateshwaralu
| 128 | 13/0 | 3DB+0 | DFR | 2024-10-23 | COMPLETED |  |  |  | 2024-10-23 | ANJU Const.
| 129 | 16/8 | 3DA+3 | WET | 2025-01-15 | COMPLETED |  |  |  | 2025-01-15 | BaLraJ
| 130 | 38/4 | 3DA+0 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | Venkateshwaralu
| 131 | 35/1 | 3DA+0 | DFR | 2025-02-02 | COMPLETED |  |  |  | 2025-02-02 | ATK CONSTRUCTIONS
| 132 | 35/2 | 3DA+0 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | TaGore
| 133 | 38/0 | 3DC1+0 | DFR | 2025-02-04 | COMPLETED |  |  |  | 2025-02-04 | Ashok-2 (Venkateshwarlu)
| 134 | 39/5 | 3DA+3 | DFR | 2025-02-04 | COMPLETED |  |  |  | 2025-02-04 | Ashok-2 (Venkateshwarlu)
| 135 | 39/6 | 3DA+0 | WFR | 2025-02-04 | COMPLETED |  |  |  | 2025-02-04 | Ashok-2 (Venkateshwarlu)
| 136 | 39/8 | 3DA+3 | DFR | 2025-02-04 | COMPLETED |  |  |  | 2025-02-04 | Ashok-2 (Venkateshwarlu)
| 137 | 35/4 | 3DA+6 | DFR | 2025-02-05 | COMPLETED |  |  |  | 2025-02-05 | ATK CONSTRUCTIONS
| 138 | 36/4 | 3DA+3 | DFR | 2024-02-06 | COMPLETED |  |  |  | 2024-02-06 | TaGore
| 139 | 10/0 | 3DB2+0 | DFR | 2025-02-07 | COMPLETED |  |  |  | 2025-02-07 | Ashok kumar (Thotta)
| 140 | 31/4 | 3DA+0 | DFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | ATK CONSTRUCTIONS
| 141 | 31/3 | 3DA-3 | WFR | 2025-02-03 | COMPLETED |  |  |  | 2025-02-03 | ATK CONSTRUCTIONS
| 142 | 36/5 | 3DA+0 | DFR | 2025-02-04 | COMPLETED |  |  |  | 2025-02-04 | TaGore
| 143 | 31/0 | 3DB2+0 | WFR | 2025-02-05 | COMPLETED |  |  |  | 2025-02-05 | ATK CONSTRUCTIONS
| 144 | 16/0 | 3DD45+0 | WET | 2025-02-10 | COMPLETED |  |  |  | 2025-02-10 | BaLraJ
| 145 | 37/0 | 3DB2+0 | DFR | 2025-02-12 | COMPLETED |  |  |  | 2025-02-12 | Venkateshwarlu
| 146 | 9/9 | 2DA+0 | DFR | 2025-02-13 | COMPLETED |  |  |  | 2025-02-13 | Ammu Eng
| 147 | 9/10 | 2DA+3 | DFR | 2025-02-13 | COMPLETED |  |  |  | 2025-02-13 | Ammu Eng
| 148 | 33/1 | 3DA+0 | DFR | 2025-02-13 | COMPLETED |  |  |  | 2025-02-13 | ATK CONSTRUCTIONS
| 149 | 33/2 | 3DA-3 | DFR | 2025-02-13 | COMPLETED |  |  |  | 2025-02-13 | ATK CONSTRUCTIONS
| 150 | 10/1 | 3DA+3 | DFR | 2025-02-14 | COMPLETED |  |  |  | 2025-02-14 | Ashok kumar (Thotta)
| 151 | 36/0 | 3DD60+3 | DFR | 2025-02-14 | COMPLETED |  |  |  | 2025-02-14 | ATK CONSTRUCTIONS
| 152 | 36/1 | 3DA+0 | DFR | 2025-02-15 | COMPLETED |  |  |  | 2025-02-15 | TaGore
| 153 | 36/2 | 3DA+3 | DFR | 2025-02-15 | COMPLETED |  |  |  | 2025-02-15 | TaGore
| 154 | 30/0 | 3DC1+6 | DFR | 2025-02-17 | COMPLETED |  |  |  | 2025-02-17 | ATK CONSTRUCTIONS
| 155 | 10/3 | 3DA+3 | DFR | 2025-02-17 | COMPLETED |  |  |  | 2025-02-17 | Ashok kumar (Thotta)
| 156 | 10/4 | 3DA+3 | DFR | 2025-02-17 | COMPLETED |  |  |  | 2025-02-17 | Ashok kumar (Thotta)
| 157 | 30/4 | 3DA+3 | WFR | 2024-10-10 | COMPLETED |  |  |  | 2024-10-10 | Company Gang
| 158 | 11/4 | 3DA+0 | DFR | 2025-01-09 | COMPLETED |  |  |  | 2025-01-09 | Ashok kumar (Thotta)
| 159 | 12/1 | 3DA+3 | WFR | 2024-10-22 | COMPLETED |  |  |  | 2024-10-22 | AnJu Constructions
| 160 | 18/2 | 3DA+0 | DFR | 2024-12-11 | COMPLETED |  |  |  | 2024-12-11 | Ammu Eng
| 161 | 10/9 | 3DA+6 | DFR | 2025-02-24 | COMPLETED |  |  |  | 2025-02-24 | BaLraJ
| 162 | 42/6 | 3DA+0 | DFR | 2025-03-02 | COMPLETED |  |  |  | 2025-03-02 | TaGore
| 163 | 42/7 | 3DA+9 | DFR | 2025-03-02 | COMPLETED |  |  |  | 2025-03-02 | TaGore
| 164 | 39/7 | 3DA+6 | WFR | 2025-03-02 | COMPLETED |  |  |  | 2025-03-02 | Ashok-2 (Venkateshwarlu)
| 165 | 39/9 | 3DA+9 | DFR | 2025-03-02 | COMPLETED |  |  |  | 2025-03-02 | Ashok-2 (Venkateshwarlu)
| 166 | 42/3 | 3DA+3 | WFR | 2025-03-04 | COMPLETED |  |  |  | 2025-03-04 | Venkateshwarlu
| 167 | 42/5 | 3DA+3 | DFR | 2025-03-04 | COMPLETED |  |  |  | 2025-03-04 | Venkateshwarlu
| 168 | 13/8 | 3DA+0 | WET | 2025-03-06 | COMPLETED |  |  |  | 2025-03-06 | Ashok kumar (Thotta)
| 169 | 15/0 | 3DD45+3 | WET | 2025-03-06 | COMPLETED |  |  |  | 2025-03-06 | Ashok kumar (Thotta)
| 170 | 39/0 | 3DC1+3 | DFR | 2025-03-09 | COMPLETED |  |  |  | 2025-03-09 | Ashok-2 (Venkateshwarlu)
| 171 | 32/3 | 3DA+6 | DFR | 2025-03-10 | COMPLETED |  |  |  | 2025-03-10 | TaGore
| 172 | 42/2 | 3DA+0 | DFR | 2025-03-10 | COMPLETED |  |  |  | 2025-03-10 | Venkateshwarlu
| 173 | 10/5 | 3DA+3 | DFR | 2025-03-11 | COMPLETED |  |  |  | 2025-03-11 | BalraJ
| 174 | 10/6 | 3DA+6 | DFR | 2025-03-11 | COMPLETED |  |  |  | 2025-03-11 | BalraJ
| 175 | 10/7 | 3DA+3 | DFR | 2025-03-11 | COMPLETED |  |  |  | 2025-03-11 | BalraJ
| 176 | 42/0 | 3DB1+9 | DFR | 2025-03-12 | COMPLETED |  |  |  | 2025-03-12 | Ashok-2 (Venkateshwarlu)
| 177 | 40/0 | 3DB2+9 | DFR | 2025-03-12 | COMPLETED |  |  |  | 2025-03-12 | Ashok-2 (Venkateshwarlu)
| 178 | 38/3 | 3DA+3 | WET | 2025-03-13 | COMPLETED |  |  |  | 2025-03-13 | Ashok-2 (Venkateshwarlu)
| 179 | 38/5 | 3DA+0 | WET | 2025-03-13 | COMPLETED |  |  |  | 2025-03-13 | Ashok-2 (Venkateshwarlu)
| 180 | 21/4 | 3DA+3 | WFR | 2024-11-11 | COMPLETED |  |  |  | 2024-11-11 | Ammu Eng
| 181 | 30/1 | 3DA+3 | DFR | 2024-01-02 | COMPLETED |  |  |  | 2024-01-02 | ATK CONSTRUCTIONS
| 182 | 30/3 | 3DA+3 | DFR | 2024-12-20 | COMPLETED |  |  |  | 2024-12-20 | ATK CONSTRUCTIONS
| 183 | 30/5 | 3DA+0 | DFR | 2024-12-20 | COMPLETED |  |  |  | 2024-12-20 | ATK CONSTRUCTIONS
| 184 | 32/0 | 3DC1+0 | DFR | 2025-03-15 | COMPLETED |  |  |  | 2025-03-15 | FC Gang - Muthu
| 185 | 9/6 | 2DA+3 | DFR | 2025-03-16 | COMPLETED |  |  |  | 2025-03-16 | Ammu Eng
| 186 | 9/7 | 2DA+3 | DFR | 2025-03-16 | COMPLETED |  |  |  | 2025-03-16 | Ammu Eng
| 187 | 9/8 | 2DA+0 | DFR | 2025-03-16 | COMPLETED |  |  |  | 2025-03-16 | Ammu Eng
| 188 | 16/3 | 3DA+3 | WET | 2025-03-19 | COMPLETED |  |  |  | 2025-03-19 | BalraJ
| 189 | 16/4 | 3DA+0 | WET | 2025-03-19 | COMPLETED |  |  |  | 2025-03-19 | BalraJ
| 190 | 16/5 | 3DA+0 | WET | 2025-03-19 | COMPLETED |  |  |  | 2025-03-19 | BalraJ
| 191 | 11/7 | 3DA+0 | WET | 2025-03-20 | COMPLETED |  |  |  | 2025-03-20 | Ashok kumar (Thotta)
| 192 | 9/1 | 2DA+3 | DFR | 2025-03-23 | COMPLETED |  |  |  | 2025-03-23 | Ammu Eng
| 193 | 9/2 | 2DA+0 | DFR | 2025-03-23 | COMPLETED |  |  |  | 2025-03-23 | Ammu Eng
| 194 | 9/3 | 2DA+9 | DFR | 2025-03-23 | COMPLETED |  |  |  | 2025-03-23 | Ammu Eng
| 195 | 9/4 | 2DA+0 | DFR | 2025-03-23 | COMPLETED |  |  |  | 2025-03-23 | Ammu Eng
| 196 | 9/5 | 2DA+0 | DFR | 2025-03-24 | COMPLETED |  |  |  | 2025-03-24 | Ammu Eng
| 197 | 34/1 | 3DB1+0 | DFR | 2025-03-29 | COMPLETED |  |  |  | 2025-03-29 | Ammu Eng
| 198 | 8/12 | 2DA+0 | DFR | 2025-03-30 | COMPLETED |  |  |  | 2025-03-30 | Ammu Eng
| 199 | 8/14 | 2DA+3 | DFR | 2025-03-30 | COMPLETED |  |  |  | 2025-03-30 | Ammu Eng
| 200 | 8/15 | 2DA+3 | DFR | 2025-03-30 | COMPLETED |  |  |  | 2025-03-30 | Ammu Eng
| 201 | 9/0 | 2DB1+0 | DFR | 2025-03-30 | COMPLETED |  |  |  | 2025-03-30 | Ammu Eng
| 202 | 13/11 | 3DA+0 | WET | 2025-03-30 | COMPLETED |  |  |  | 2025-03-30 | Ammu Eng
| 203 | 42/4 | 3DA+3 | DFR | 2025-04-03 | COMPLETED |  |  |  | 2025-04-03 | Venkateshwarlu
| 204 | 15/3 | 3DA+0 | WBC | 2025-04-07 | COMPLETED |  |  |  | 2025-04-07 | Venkateshwarlu
| 205 | 11/8 | 3DA+0 | WET | 2025-04-15 | COMPLETED |  |  |  | 2025-04-15
| 206 | 34/2 | 3DB1+6 | DFR | 2025-04-17 | COMPLETED |  |  |  | 2025-04-17 | TaGore
| 207 | 28/0 | 3DC1+0 | DFR | 2025-05-05 | COMPLETED |  |  |  | 2025-04-20 | Company Gang
| 208 | 37/3 | 3DA+0 | DFR | 2025-04-22 | COMPLETED |  |  |  | 2025-04-22 | TaGore
| 209 | 36/6 | 3DA+3 | DFR | 2025-04-23 | COMPLETED |  |  |  | 2025-04-23 | TaGore
| 210 | 27/9 | 3DA+3 | DFR | 2025-04-25 | COMPLETED |  |  |  | 2025-05-25 | ATK CONSTRUCTIONS
| 211 | 6/2 | 2DA+0 | DFR | 2025-05-01 | COMPLETED |  |  |  | 2025-05-01 | Venkateshwarlu
| 212 | 6/6 | 2DA+0 | DFR | 2025-05-01 | COMPLETED |  |  |  | 2025-05-01 | Venkateshwarlu
| 213 | 42/1 | 3DA+6 | DFR | 2025-05-01 | COMPLETED |  |  |  | 2025-05-01 | Ashok-2 (Venkateshwarlu)
| 214 | 6/1 | 2DA+3 | DFR | 2025-05-02 | COMPLETED |  |  |  | 2025-05-02 | Venkateshwarlu
| 215 | 20/0 | 3DB1+0 | DFR | 2025-05-02 | COMPLETED |  |  |  | 2025-05-02 | ATK CONSTRUCTIONS
| 216 | 20A/0 | 3DB2+0 | DFR | 2025-05-03 | COMPLETED |  |  |  | 2025-05-03 | ATK CONSTRUCTIONS
| 217 | 8/7 | 2DA+3 | DFR | 2025-05-06 | COMPLETED |  |  |  | 2025-05-06 | ATK CONSTRUCTIONS
| 218 | 6/7 | 2DA+3 | DFR | 2025-05-06 | COMPLETED |  |  |  | 2025-05-06 | Venkateshwarlu
| 219 | 4/20 | 2DA+9 | DFR | 2025-05-09 | COMPLETED |  |  |  | 2025-05-09 | ATK Constructions
| 220 | 8/8 | 2DA+0 | DFR | 2025-05-12 | COMPLETED |  |  |  | 2025-05-12 | Ammu Eng
| 221 | 34/0 | 3DC1+0 | DFR | 2025-05-13 | COMPLETED |  |  |  | 2025-05-13 | TaGore
| 222 | 4/7 | 2DA+3 | DFR | 2025-05-13 | COMPLETED |  |  |  | 2025-05-13 | BalraJ
| 223 | 4/8 | 2DA+3 | DFR | 2025-05-15 | COMPLETED |  |  |  | 2025-05-15 | BalraJ
| 224 | 8/9 | 2DA+3 | DFR | 2025-05-19 | COMPLETED |  |  |  | 2025-05-19 | Ammu Eng
| 225 | 42/9 | 3DA+3 | DFR | 2025-05-19 | COMPLETED |  |  |  | 2025-05-19 | Ashok-2(Venkateshwarlu)
| 226 | 4/3 | 2DA+6 | DFR | 2025-05-25 | COMPLETED |  |  |  | 2025-05-25 | BalraJ
| 227 | 6/3 | 2DA+0 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | Venkateshwarlu
| 228 | 6/4 | 2DA+0 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | Venkateshwarlu
| 229 | 6/5 | 2DA+0 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | Venkateshwarlu
| 230 | 4/19 | 2DA+6 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | ATK Constructions
| 231 | 4/21 | 2DA+3 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | ATK Constructions
| 232 | 4/23 | 2DA+0 | DFR | 2025-05-26 | COMPLETED |  |  |  | 2025-05-26 | ATK Constructions
| 233 | 4/4 | 2DA+0 | DFR | 2025-05-27 | COMPLETED |  |  |  | 2025-05-27 | BalraJ
| 234 | 8/5 | 2DA+0 | DFR | 2025-05-27 | COMPLETED |  |  |  | 2025-05-27 | ATK Constructions
| 235 | 8/6 | 2DA+0 | DFR | 2025-05-28 | COMPLETED |  |  |  | 2025-05-28 | ATK Constructions
| 236 | 4/6 | 2DA+0 | DFR | 2025-05-30 | COMPLETED |  |  |  | 2025-05-30 | BalraJ
| 237 | 4/17 | 2DA+3 | DFR | 2025-05-31 | COMPLETED |  |  |  | 2025-05-31 | ATK Constructions
| 238 | 4/18 | 2DA+0 | DFR | 2025-05-31 | COMPLETED |  |  |  | 2025-05-31 | ATK Constructions
| 239 | 4/5 | 2DA+3 | DFR | 2025-05-31 | COMPLETED |  |  |  | 2025-05-31 | BalraJ
| 240 | 4/9 | 2DA+0 | DFR | 2025-05-31 | COMPLETED |  |  |  | 2025-05-31 | BalraJ
| 241 | 8/10 | 2DA+0 | DFR | 2025-06-01 | COMPLETED |  |  |  | 2025-06-01 | Ammu Eng
| 242 | 4/0 | 2DB2+0 | DFR | 2025-06-04 | COMPLETED |  |  |  | 2025-06-04 | BalraJ
| 243 | 4/13 | 2DA+0 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | ATK Constructions
| 244 | 4/14 | 2DA+3 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | ATK Constructions
| 245 | 4/15 | 2DA+0 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | ATK Constructions
| 246 | 43/3 | 3DA+0 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | Ashok-2 (Venkateshwarlu)
| 247 | 43A/2 | 3DA+0 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | Ashok-2 (Venkateshwarlu)
| 248 | 43A/3 | 3DA+0 | DFR | 2025-06-06 | COMPLETED |  |  |  | 2025-06-06 | Ashok-2 (Venkateshwarlu)
| 249 | 41/0 | 3DC1+0 | WET | 2025-06-08 | COMPLETED |  |  |  | 2025-06-08 | Ashok-2 (Venkateshwarlu)
| 250 | 43/2 | 3DA-3 | DFR | 2025-06-13 | COMPLETED |  |  |  | 2025-06-13 | Ashok-2 (Venkateshwarlu)
| 251 | 36/7 | 3DA+3 | WFR | 2025-06-15 | COMPLETED |  |  |  | 2025-06-15 | Tagore
| 252 | 28/1 | 3DA+9 | WET(2mRC) | 2025-06-17 | COMPLETED |  |  |  | 2025-06-17 | Tagore
| 253 | 3/1 | 2DA+9 | DFR | 2025-06-21 | COMPLETED |  |  |  | 2025-06-21 | Venkateshwarlu
| 254 | 1B/2 | 2DA+3 | DFR | 2025-06-21 | COMPLETED |  |  |  | 2025-06-21 | ATK Constructions
| 255 | 4/1 | 2DA+3 | DFR | 2025-06-21 | COMPLETED |  |  |  | 2025-06-21 | BalraJ
| 256 | 8/11 | 2DA+0 | DFR | 2025-06-21 | COMPLETED |  |  |  | 2025-06-21 | Ammu Eng
| 257 | 3/0 | 2DB2+3 | DFR | 2025-06-22 | COMPLETED |  |  |  | 2025-06-22 | Venkateshwarlu
| 258 | 3/2 | 2DA+9 | DFR | 2025-06-22 | COMPLETED |  |  |  | 2025-06-22 | Venkateshwarlu
| 259 | 3/3 | 2DA+0 | DFR | 2025-06-22 | COMPLETED |  |  |  | 2025-06-22 | Venkateshwarlu
| 260 | 1A/0 | 2DD45+0 | DFR | 2025-06-22 | COMPLETED |  |  |  | 2025-06-22 | BalraJ
| 261 | 1B/1 | 2DA+6 | DFR | 2025-06-24 | COMPLETED |  |  |  | 2025-06-24 | ATK Constructions
| 262 | 43/1 | 3DA+3 | WFR | 2025-06-25 | COMPLETED |  |  |  | 2025-06-25 | Ashok-2 (Venkateshwarlu)
| 263 | 2/3 | 2DA+0 | DFR | 2025-06-27 | COMPLETED |  |  |  | 2025-06-27 | Ammu Eng
| 264 | 1B/0 | 2DB2+3 | DFR | 2025-06-28 | COMPLETED |  |  |  | 2025-06-28 | ATK Constructions
| 265 | 43/4 | 3DA+3 | DFR | 2025-06-28 | COMPLETED |  |  |  | 2025-06-28 | Ashok-2 (Venkateshwarlu)
| 266 | 43/0 | 3DB2+0 | DFR | 2025-06-30 | COMPLETED |  |  |  | 2025-06-30 | Ashok-2 (Venkateshwarlu)
| 267 | 8/2 | 2DB1+6 | DFR | 2025-06-30 | COMPLETED |  |  |  | 2025-06-30 | ATK Constructions
| 268 | 1C/0 | 2DB1+9 | DFR | 2025-07-04 | COMPLETED |  |  |  | 2025-07-04 | ATK Constructions
| 269 | 2/2 | 2DA+0 | DFR | 2025-07-04 | COMPLETED |  |  |  | 2025-07-04 | ATK Constructions
| 270 | 42/8 | 3DA+9(2mRC) | DFR | 2025-07-08 | COMPLETED |  |  |  | 2025-07-08 | Ashok-2 (Venkateshwarlu)
| 271 | 43/0 | 3DB2+0 | DFR | 2025-07-08 | COMPLETED |  |  |  | 2025-07-08 | Ashok-2 (Venkateshwarlu)
| 272 | 8/4 | 2DB1+6 | DFR | 2025-07-09 | COMPLETED |  |  |  | 2025-07-09 | ATK Constructions
| 273 | 2/1 | 2DA+0 | DFR | 2025-07-11 | COMPLETED |  |  |  | 2025-07-11 | Venkateshwarlu
| 274 | 4/16 | 2DA+0 | DFR | 2025-07-11 | COMPLETED |  |  |  | 2025-07-11 | ATK Constructions
| 275 | 16/6 | 3DA+0 | WBC | 2025-07-12 | COMPLETED |  |  |  | 2025-07-12 | Ammu Engineering
| 276 | 16/7 | 3DA-3 | WET | 2025-07-12 | COMPLETED |  |  |  | 2025-07-12 | Ammu Engineeering
| 277 | 2/4 | 2DA+0 | DFR | 2025-07-13 | COMPLETED |  |  |  | 2025-07-13 | Ammu Engineering
| 278 | 2/0 | 2DB2+6 | DFR | 2025-07-14 | COMPLETED |  |  |  | 2025-07-14 | Venkateshwarlu
| 279 | 8/13 | 2DA+3 | DFR | 2025-07-16 | COMPLETED |  |  |  | 2025-07-16 | Ammu Engineering
| 280 | 43/5 | 3DA+3(2mRC) | DFR | 2025-07-17 | COMPLETED |  |  |  | 2025-07-17 | Ashok-2 (Venkateshwarlu)
| 281 | 5/0 | 2DD45+6 | DFR | 2025-07-18 | COMPLETED |  |  |  | 2025-07-18 | ATK Constructions
| 282 | 6/0 | 2DD45+6 | DFR | 2025-07-18 | COMPLETED |  |  |  | 2025-07-18 | ATK Constructions
| 283 | 8/3 | 2DB1+9 | DFR | 2025-07-20 | COMPLETED |  |  |  | 2025-07-20 | ATK Constructions
| 284 | 8/1 | 2DB1+6 | DFR | 2025-07-24 | COMPLETED |  |  |  | 2025-07-24 | ATK Constructions
| 285 | 4/22 | 2DA+6(3mRc ) | DFR | 2025-07-29 | COMPLETED |  |  |  | 2025-07-29 | ATK Constructions
| 286 | 1/0 | 2DD60+0 | DFR | 2025-08-26 | COMPLETED |  |  |  | 2025-08-26 | Venkateshwarlu
| 287 | 4/2 | 2DA+3 | DFR | 2025-10-12 | COMPLETED |  |  |  | 2025-09-20
| 288 | 43B/0 | 3DB1+9 | DFR | 2025-10-13 | COMPLETED |  |  |  | 2025-10-13 | Ashok-2 (Venkateshwarlu)
| 289 | 4/10 | 2DA+3 | DFR | 2025-10-31 | COMPLETED |  |  |  | 2025-10-31
Stringing
| S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | RouGH SaG | F!n@L sAG | E@rthwire | Remarks
| 1 | 23/0-24/0 | 1.826 | Final Sag Completed |  |  |  | M.R. Const | 35 | 12-02-2025 to 16-02-2025 | 27-02-2025 to 04-03-2025 | 17-02-2025 & 04-03-2025
| 2 | 24/0-25/0 | 3.406 | Final Sag Completed |  |  |  | M.R. Const | 35 | 24-02-2025 to 04-03-2025 | 09-03-2025 to 16-03-2025 | 04-03-2025 & 16-03-2025
| 3 | 25/0-26/0 | 2.279 | Final Sag Completed |  |  |  | M.R. Const | 35 | 08-03-2025 to 13-03-2025 | 24-03-2025 to 29-03-2025 | & 29-03-2025
| 4 | 26/0-27/0 | 1.914 | Final Sag Completed |  |  |  | M.R. Const | 35 | 23-03-2025 to 28-03-2025 | 18-04-2025 & 20-04-2025 | 28-03-2025 &
| 5 | 22/0 - 23/0 | 2.338 | Final Sag Completed |  |  |  | M.R. Const | 35 | 07-04-2025 to 11-04-2025 | 22-04-2025 & 24-04-2025 | 11-04-2025 & 25-04-2025
| 6 | 29/0 - 29/9 | 3.555 | Final Sag Completed |  |  |  | M.R. Const | 35 | 05-05-2025 to 16-05-2025 | 06- 07-2025 to 11-07-2025 | 17-05-2025 & 12-07-2025
| 7 | 32/0-33/0 | 1.658 | Final Sag Completed |  |  |  | M.R. Const | 35 | 22-05-2025 to 25-05-2025 | 28-05-2025 -30-05-2025 | 25-05-2025 & 31-05-2025
| 8 | 31/0-32/0 | 2.689 | Final Sag Completed |  |  |  | M.R. Const | 35 | 12-06-2025 to 17-06-2025 | 13-06-2025 to 17-06-2025 | 2025-06-17
| 9 | 30/0-31/0 | 2.383 | Final Sag Completed |  |  |  | M.R. Const | 45 | 22-06-2025 to 02-07-2025 | 23-06-2025 to 02-07-2025 | 02-07-2025 to 03-07-2025
| 10 | 29/9-30/0 | 0.508 | Final Sag Completed |  |  |  | M.R. Const | 45 | 06-07-2025 to 11-07-2025 | 07-07-2025 to 11-07-2025 | 2025-07-12
| 11 | 21/0-22/0 | 3.867 | Final Sag Completed |  |  |  | M.R. Const | 45 | 17-07-2025 to 24-07-2025 | 06-08-2025 to 09-08-2025 | 2025-05-25
| 12 | 20A/0 - 21/0 | 0.172 | Final Sag Completed |  |  |  | M.R. Const | 45 | 23-08-2025 to 31-08-2025 | 24--08-2025 to 31-08-2025 | 2025-09-01
| 13 | 20/0- 20A/0 | 0.241 | Final Sag Completed |  |  |  | M.R. Const | 45 | 22-08-2025 to 01-09-2025 | 24--08-2025 to 01-09-2025 | 2025-09-01
| 14 | 12/0-13/0 | 4.9795 | Final Sag Completed |  |  |  | Nasiruddin | 40 | 01-09-2025 to 07-09-2025 | 15-09-2025 to 18-09-2025 | 08-09-2025 & 19-09-2025
| 15 | 10/0-11/0 | 4.1245 | Final Sag Completed |  |  |  | Nasiruddin | 40 | 28-09-2025 to 05-10-2025 | 08-10-2025 to 10-10-2025 | 05-10-2025 & 10-10-2025
| 16 | 19/0-20/0 | 1.6396 | Final Sag Completed |  |  |  | M.R. Const | 45 | 15-09-2025 to 20-10-2025 | 2025-10-19 | 2025-09-07
| 17 | 18/0-19/0 | 1.564 | Final Sag Completed |  |  |  | M.R. Const | 45 | 21-09-2025 to 20-10-2025 | 2025-10-21 | 2025-10-23
| 18 | 9/10-10/0 | 4.598 | Final Sag Completed |  |  |  | Nasiruddin | 40 | 16-10-2025 to 23-10-2025 | 24-10-2025 to 26-10-2025 | 2025-10-26
| 19 | 17/0 -18/0 | 1.539 | 17/1,2,3 - Insulator Hosting Done - Pilot Payingout u/p |  |  |  | M.R. Const | 45
| 20 | 13/0- 14/0 | 4.9 | 13/1,2,3,4,5,6,7,8,10 - Insulator Hosting Done + pilot Payingout work Stopped due to Row |  |  |  | Nasiruddin | 40
OPGW Stringing
| S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | Remarks
| 1 | 30/0-32/0 | 5.072 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 2025-07-25
| 2 | 29/0 - 30/0 | 4.063 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 29-07-2025 to 30-07-2025
| 3 | 22/0-24/0 | 4.164 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 2025-08-02
| 4 | 24/0-25/0 | 3.406 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 2025-08-04
| 5 | 25/0-27/0 | 4.193 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 2025-08-06
| 6 | 20/0-22/0 | 4.28 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 10-10-2025 to 12-10-2025
| 7 | 12/0-13/0 | 4.98 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 15-10-2025 to 16-10-2025
| 8 | 10/0 - 11/0 | 4.125 | OPGW Final Sag Done |  |  |  | BK Construct | 15 | 17-10-2025 to 19-10-2025
Erection
| SL No. | Location No. | Tower Type | Classification | Start Date | MT | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark | Tackwelding | Tower Tightening
| 1 | 25/4 | 3DA+0 | DFR | 10-07-2024 | 36.37 | Completed |  |  |  | 2024-07-19 | Khatan | 25 | Commenced on 10.07.2024 | Completed | Completed
| 2 | 26/1 | 3DA+0 | DFR | 18-07-2024 | 36.37 | Completed |  |  |  | 2024-07-28 | Khatan | 25 |  | Completed | Completed
| 3 | 26/4 | 3DA+0 | DFR | 27-07-2024 | 36.37 | Completed |  |  |  | 2024-08-03 | Khatan | 25 |  | Completed | Completed
| 4 | 25/1 | 3DA+0 | DFR | 02-08-2024 | 36.37 | Completed |  |  |  | 2024-08-09 | Khatan | 25 |  | Completed | Completed
| 5 | 26/2 | 3DA+0 | DFR | 09-08-2024 | 36.37 | Completed |  |  |  | 2024-08-14 | Khatan | 25 |  | Completed | Completed
| 6 | 26/3 | 3DA+0 | DFR | 2024-08-16 | 36.37 | Completed |  |  |  | 2024-08-18 | Khatan | 25 |  | Completed | Completed
| 7 | 27/1 | 3DA+0 | DFR | 2024-08-19 | 36.37 | Completed |  |  |  | 2024-08-24 | Khatan | 25 |  | Completed | Completed
| 8 | 24/5 | 3DA+0 | DFR | 2024-08-22 | 36.37 | Completed |  |  |  | 2024-08-29 | Khatan | 25 |  | Completed | Completed
| 9 | 24/4 | 3DA+0 | DFR | 2024-08-29 | 36.37 | Completed |  |  |  | 2024-09-06 | Khatan | 25 |  | Completed | Completed
| 10 | 22/5 | 3DA+0 | DFR | 2024-08-23 | 36.37 | Completed |  |  |  | 2024-09-08 | s.K.Janarul | 24 |  | Completed | Completed
| 11 | 24/3 | 3DA+0 | DFR | 2024-08-29 | 36.37 | Completed |  |  |  | 2024-09-12 | Khatan | 24 |  | Completed | Completed
| 12 | 27/2 | 3DA+0 | DFR | 2024-09-14 | 36.37 | Completed |  |  |  | 2024-09-19 | Khatan | 24 |  | Completed | Completed
| 13 | 21/9 | 3DA+0 | DFR | 2024-09-09 | 36.37 | Completed |  |  |  | 2024-09-21 | s.K.Janarul Sheikh | 25 |  | Completed | Completed
| 14 | 27/4 | 3DA+0 | DFR | 2024-09-19 | 36.37 | Completed |  |  |  | 2024-09-23 | Khatan | 24 |  | Completed | Completed
| 15 | 27/5 | 3DA+0 | DFR | 2024-09-24 | 36.37 | Completed |  |  |  | 2024-09-28 | Khatan | 24 |  | Completed | Completed
| 16 | 21/7 | 3DA+0 | DFR | 2024-09-12 | 36.37 | Completed |  |  |  | 2024-09-29 | Ashok kumar | 25 |  | Completed | Completed
| 17 | 12/3 | 3DA+3 | DFR | 2024-09-14 | 37.9313 | Completed |  |  |  | 2024-09-30 | Maa Const. | 24 |  | Completed | Completed
| 18 | 27/6 | 3DA+0 | DFR | 2024-09-29 | 36.37 | Completed |  |  |  | 2024-10-03 | Khatan | 24 |  | Completed | Completed
| 19 | 23/2 | 3DA+0 | DFR | 2024-09-26 | 36.37 | Completed |  |  |  | 2024-10-03 | s.K.Janarul Sheikh | 25 |  | Completed | Completed
| 20 | 29/4 | 3DA+0 | DFR | 2024-09-21 | 36.37 | Completed |  |  |  | 2024-10-04 | Manirul (Islam)-Khatun | 25 |  | Completed | Completed
| 21 | 27/7 | 3DA+0 | DFR | 2024-10-03 | 36.37 | Completed |  |  |  | 2024-10-07 | Khatan | 24 |  | Completed | Completed
| 22 | 29/5 | 3DA+3 | DFR | 2024-10-05 | 37.9313 | Completed |  |  |  | 2024-10-14 | Khatan | 24 |  | Completed | Completed
| 23 | 23/4 | 3DA+0 | DFR | 2024-10-05 | 36.37 | Completed |  |  |  | 2024-10-14 | s.K.Janarul Sheikh | 25 |  | Completed | Completed
| 24 | 21/8 | 3DA+0 | DFR | 2024-10-01 | 36.37 | Completed |  |  |  | 2024-10-17 | Ashok | 25 |  | Completed | Completed
| 25 | 12/4 | 3DA+3 | DFR | 2024-10-01 | 37.9313 | Completed |  |  |  | 2024-10-19 | Maa Const. | 25 |  | Completed | Completed
| 26 | 30/4 | 3DA+3 | WFR | 2024-10-16 | 37.9313 | Completed |  |  |  | 2024-10-21 | Khatun | 25 |  | Completed | Completed
| 27 | 24/8 | 3DA+3 | DFR | 2024-10-21 | 37.9313 | Completed |  |  |  | 2024-10-26 | Khatan |  |  | Completed | Completed
| 28 | 12/9 | 3DA+3 | DFR | 2024-10-01 | 37.9313 | Completed |  |  |  | 2024-10-26 | Praveen | 25 |  | Completed | Completed
| 29 | 22/4 | 3DA+3 | WFR | 2024-10-17 | 37.9313 | Completed |  |  |  | 2024-10-27 | Subash | 26 |  | Completed | Completed
| 30 | 22/1 | 3DA+0 | WFR | 2024-10-18 | 36.37 | Completed |  |  |  | 2024-10-27 | Ashok | 25 |  | Completed | Completed
| 31 | 12/2 | 3DA+3 | DFR | 2024-10-19 | 36.37 | Completed |  |  |  | 2024-10-30 | Maa Const. | 25 |  | Completed | Completed
| 32 | 24/7 | 3DA+0 | DFR | 2024-10-27 | 36.37 | Completed |  |  |  | 2024-11-01 | khatun | 24 |  | Completed | Completed
| 33 | 23/3 | 3DA+0 | DFR | 2024-10-16 | 36.37 | Completed |  |  |  | 2024-11-01 | Subash | 24 |  | Completed | Completed
| 34 | 22/2 | 3DA+0 | DFR | 2024-10-29 | 36.37 | Completed |  |  |  | 2024-11-05 | Ashokkumar | 25 |  | Completed | Completed
| 35 | 12/5 | 3DA+0 | DFR | 2024-11-01 | 36.37 | Completed |  |  |  | 2024-11-07 | Maa Const. | 24 |  | Completed | Completed
| 36 | 24/0 | 3DB1+0 | DFR | 2024-11-02 | 54.655 | Completed |  |  |  | 2024-11-07 | Subash | 24 |  | Completed | Completed
| 37 | 25/0 | 3DB2+0 | DFR | 2024-11-02 | 54.66 | Completed |  |  |  | 2024-11-07 | khatun | 25 |  | Completed | Completed
| 38 | 12/10 | 3DA+0 | DFR | 2024-10-27 | 36.37 | Completed |  |  |  | 2024-11-12 | Praveen | 25 |  | Completed | Completed
| 39 | 25/2 | 3DA+0 | WFR | 2024-11-08 | 36.37 | Completed |  |  |  | 2024-11-13 | Khatun | 24 |  | Completed | Completed
| 40 | 12/6 | 3DA+0 | DFR | 2024-11-07 | 36.37 | Completed |  |  |  | 2024-11-14 | Maa Const. | 24 |  | Completed | Completed
| 41 | 23/1 | 3DA+6 | WFR | 2024-11-09 | 43.08 | Completed |  |  |  | 2024-11-14 | Subash | 25 |  | Completed | Completed
| 42 | 22/0 | 3DB1+0 | DFR | 2024-11-05 | 54.66 | Completed |  |  |  | 2024-11-15 | Ashok | 25 |  | Completed | Completed
| 43 | 24/6 | 3DA+0 | DFR | 2024-11-13 | 36.37 | Completed |  |  |  | 2024-11-18 | Khatun | 22 |  | Completed | Completed
| 44 | 24/1 | 3DA+6 | DFR | 2024-11-15 | 43.08 | Completed |  |  |  | 2024-11-20 | Subash | 25 |  | Completed | Completed
| 45 | 12/7 | 3DA+0 | DFR | 2024-11-14 | 36.37 | Completed |  |  |  | 2024-11-21 | Maa Const. | 23 |  | Completed | Completed
| 46 | 26/0 | 3DB2+0 | DFR | 2024-11-19 | 54.66 | Completed |  |  |  | 2024-11-24 | Khatun | 22 |  | Completed | Completed
| 47 | 21/4 | 3DA+3 | WFR | 2024-11-16 | 37.93 | Completed |  |  |  | 2024-11-25 | Ashok | 25 |  |  | Completed
| 48 | 23/0 | 3DB2+0 | DFR | 2024-11-21 | 54.66 | Completed |  |  |  | 2024-11-26 | Subash | 25 |  | Completed | Completed
| 49 | 12/0 | 3DB2+0 | DFR | 2024-11-22 | 54.66 | Completed |  |  |  | 2024-11-30 | Maa Const. | 23 |  | Completed | Completed
| 50 | 27/0 | 3DB1+0 | DFR | 2024-11-24 | 54.66 | Completed |  |  |  | 2024-11-30 | Khatun | 22 |  | Completed | Completed
| 51 | 21/2 | 3DA+0 | WFR | 2024-11-26 | 36.37 | Completed |  |  |  | 2024-12-02 | Subash | 25 |  | Completed | Completed
| 52 | 12/8 | 3DA+3 | DFR | 2024-11-12 | 37.93 | Completed |  |  |  | 2024-12-05 | Praveen | 23 |  | Completed | Completed
| 53 | 21/6 | 3DA+0 | DFR | 2024-12-03 | 36.37 | Completed |  |  |  | 2024-12-06 | Subash | 25 |  | Completed | Completed
| 54 | 27/8 | 3DA+0 | DFR | 2024-12-03 | 36.37 | Completed |  |  |  | 2024-12-08 | Khatun | 22 |  | Completed | Completed
| 55 | 24/2 | 3DA+3 | DFR | 2024-12-03 | 37.93 | Completed |  |  |  | 2024-12-11 | Subash | 25 |  | Completed | Completed
| 56 | 29/3 | 3DA+0 | DFR | 2024-12-09 | 36.37 | Completed |  |  |  | 2024-12-13 | Khatun | 22 |  | Completed | Completed
| 57 | 19/3 | 3DA+3 | DFR | 2024-12-11 | 37.93 | Completed |  |  |  | 2024-12-15 | Subash | 25 |  | Completed | Completed
| 58 | 19/2 | 3DA+0 | DFR | 2024-12-16 | 36.37 | Completed |  |  |  | 2024-12-18 | Subash | 23 |  | Completed | Completed
| 59 | 29/8 | 3DA+0 | DFR | 2024-12-15 | 36.37 | Completed |  |  |  | 2024-12-19 | Khatun | 25 |  | Completed | Completed
| 60 | 18/3 | 3DA+0 | WET | 2024-12-19 | 36.37 | Completed |  |  |  | 2024-12-22 | Subash | 22 |  | Completed | Completed
| 61 | 18/2 | 3DA+0 | DFR | 2024-12-23 | 36.37 | Completed |  |  |  | 2024-12-25 | Subash | 25 |  | Completed | Completed
| 62 | 29/1 | 3DA+9 | DFR | 2024-12-20 | 44.825 | Completed |  |  |  | 2024-12-25 | Khatun | 22 |  | Completed | Completed
| 63 | 11/11 | 3DA+3 | DFR | 2024-12-12 | 37.93 | Completed |  |  |  | 2024-12-28 | Praveen | 23
| 64 | 18/1 | 3DA+0 | DFR | 2024-12-26 | 36.37 | Completed |  |  |  | 2024-12-28 | Subash | 25 |  | Completed | Completed
| 65 | 30/3 | 3DA+3 | DFR | 2024-12-26 | 37.93 | Completed |  |  |  | 2024-12-31 | Khatun | 22 |  | Completed | Completed
| 66 | 18/0 | 3DB2+0 | DFR | 2024-12-27 | 54.66 | Completed |  |  |  | 2025-01-03 | Subash | 25 |  | Completed | Completed
| 67 | 30/2 | 3DA+3 | WFR | 2024-12-02 | 37.93 | Completed |  |  |  | 2025-01-06 | Khatun | 26 |  | Completed | Completed
| 68 | 17/1 | 3DA+3 | WFR | 2025-01-03 | 37.93 | Completed |  |  |  | 2025-01-08 | Subash | 27 |  |  | Completed
| 69 | 21/1 | 3DA+0 | DFR | 2024-12-28 | 36.37 | Completed |  |  |  | 2025-01-13 | Subash | 25 |  | Completed | Completed
| 70 | 30/1 | 3DA+3 | DFR | 2025-01-04 | 37.93 | Completed |  |  |  | 2025-01-15 | Khatun | 28 |  | Completed | Completed
| 71 | 11/10 | 3DA+0 | WET | 2025-01-02 | 36.37 | Completed |  |  |  | 2025-01-15 | Praveen | 25
| 72 | 16/6 | 3DA+0 | WBC | 2025-01-14 | 36.37 | Completed |  |  |  | 2025-01-18 | Subash | 30 |  |  | Completed
| 73 | 29/6 | 3DA+0 | DFR | 2025-01-16 | 36.37 | Completed |  |  |  | 2025-01-19 | Khatun | 27 |  | Completed | Completed
| 74 | 16/8 | 3DA+3 | WET | 2025-01-18 | 37.93 | Completed |  |  |  | 2025-01-22 | Subash | 30 |  |  | Completed
| 75 | 29/2 | 3DA+0 | WFR | 2025-01-19 | 36.37 | Completed |  |  |  | 2025-01-23 | Khatun | 27 |  | Completed | Completed
| 76 | 16/10 | 3DA+3 | WBC | 2025-01-22 | 37.93 | Completed |  |  |  | 2025-01-27 | Subash | 30
| 77 | 30/5 | 3DA+0 | DFR | 2025-01-23 | 36.37 | Completed |  |  |  | 2025-01-28 | Khatun | 27 |  | Completed | Completed
| 78 | 11/6 | 3DA+0 | DFR | 2025-01-16 | 36.37 | Completed |  |  |  | 2025-01-30 | Praveen | 25
| 79 | 16/9 | 3DA+0 | WBC | 2025-01-22 | 36.37 | Completed |  |  |  | 2025-01-30 | Subash | 30 |  |  | Completed
| 80 | 31/1 | 3DA+3 | DFR | 2025-01-28 | 37.93 | Completed |  |  |  | 2025-02-03 | Khatun | 27 |  | Completed | Completed
| 81 | 16/2 | 3DA+0 | WET | 2025-01-30 | 36.37 | Completed |  |  |  | 2025-02-03 | Subash | 25
| 82 | 13/2 | 3DA+0 | WBC | 2025-02-04 | 36.37 | Completed |  |  |  | 2025-02-08 | Subash | 30
| 83 | 31/4 | 3DA+0 | DFR | 2025-02-04 | 36.37 | Completed |  |  |  | 2025-02-09 | Khatun | 25 |  | Completed | Completed
| 84 | 11/5 | 3DA+0 | DFR | 2025-01-30 | 36.37 | Completed |  |  |  | 2025-02-10 | Praveen | 30
| 85 | 13/1 | 3DA+3 | WET | 2025-02-09 | 37.93 | Completed |  |  |  | 2025-02-12 | Subash | 27
| 86 | 31/5 | 3DA+0 | WFR | 2025-02-10 | 36.37 | Completed |  |  |  | 2025-02-14 | Khatun | 27 |  | Completed | Completed
| 87 | 25/3 | 3DA+0 | DFR | 2025-02-10 | 36.37 | Completed |  |  |  | 2025-02-18 | J.$lnGH | 25 |  | Completed | Completed
| 88 | 13/3 | 3DA+6 | WBC | 2025-02-13 | 43.08 | Completed |  |  |  | 2025-02-19 | Subash | 30
| 89 | 31/6 | 3DA+3 | DFR | 2025-02-15 | 37.93 | Completed |  |  |  | 2025-02-20 | Khatun | 27 |  | Completed | Completed
| 90 | 12/11 | 3DA+6 | DFR | 2025-02-11 | 43.08 | Completed |  |  |  | 2025-02-21 | Praveen | 25 |  | Completed | Completed
| 91 | 13/4 | 3DA+3 | WBC | 2025-02-19 | 37.93 | Completed |  |  |  | 2025-02-23 | Subash | 30
| 92 | 25/5 | 3DA+6 | DFR | 2025-02-19 | 43.08 | Completed |  |  |  | 2025-02-25 | J.$lnGH | 27 |  | Completed | Completed
| 93 | 31/2 | 3DA+0 | WFR | 2025-02-21 | 36.37 | Completed |  |  |  | 2025-02-25 | Khatun | 25 |  | Completed | Completed
| 94 | 13/6 | 3DA+6 | WBC | 2025-02-24 | 43.08 | Completed |  |  |  | 2025-02-27 | Subash | 27
| 95 | 11/9 | 3DA+0 | WET | 2025-02-22 | 36.37 | Completed |  |  |  | 2025-03-01 | Praveen | 25
| 96 | 29/7 | 3DA+3 | WFR | 2025-02-26 | 37.93 | Completed |  |  |  | 2025-03-01 | Khatun | 23 |  | Completed | Completed
| 97 | 13/5 | 3DA+0 | WET | 2025-02-28 | 36.37 | Completed |  |  |  | 2025-03-02 | Subash | 25
| 98 | 38/1 | 3DA+0 | WFR | 2025-02-26 | 36.37 | Completed |  |  |  | 2025-03-02 | J.$lnGH | 27
| 99 | 13/7 | 3DA+6 | WET | 2025-03-03 | 43.08 | Completed |  |  |  | 2025-03-07 | Subash | 25
| 100 | 31/0 | 3DB2+0 | WFR | 2025-03-02 | 54.66 | Completed |  |  |  | 2025-03-07 | Khatun | 27 |  | Completed | Completed
| 101 | 38/3 | 3DA+3 | WET | 2025-03-03 | 37.93 | Completed |  |  |  | 2025-03-09 | J.$lnGH | 30
| 102 | 13/0 | 3DB1+0 | DFR | 2025-03-08 | 54.66 | Completed |  |  |  | 2025-03-11 | Subash | 27 |  | Completed | Completed
| 103 | 22/3 | 3DA+6 | DFR | 2025-03-03 | 43.08 | Completed |  |  |  | 2025-03-12 | Praveen | 25 |  | Completed | Completed
| 104 | 32/1 | 3DA+0 | WFR | 2025-03-08 | 36.37 | Completed |  |  |  | 2025-03-12 | Khatun | 23 |  | Completed | Completed
| 105 | 38/4 | 3DA+0 | DFR | 2025-03-10 | 36.37 | Completed |  |  |  | 2025-03-13 | J.$lnGH | 25
| 106 | 13/8 | 3DA+0 | WET | 2025-03-12 | 36.37 | Completed |  |  |  | 2025-03-16 | Subash | 25
| 107 | 33/1 | 3DA+0 | DFR | 2025-03-13 | 36.37 | Completed |  |  |  | 2025-03-17 | Khatun | 27
| 108 | 13/9 | 3DA+3 | WBC | 2025-03-16 | 37.93 | Completed |  |  |  | 2025-03-19 | Subash | 25
| 109 | 38/5 | 3DA+0 | WET | 2025-03-15 | 36.37 | Completed |  |  |  | 2025-03-19 | J.$lnGH | 25
| 110 | 13/10 | 3DA+0 | WBC | 2025-03-20 | 36.37 | Completed |  |  |  | 2025-03-22 | Subash | 25 |  | Completed | Completed
| 111 | 38/6 | 3DA+0 | WBC | 2025-03-20 | 36.37 | Completed |  |  |  | 2025-03-23 | J.$lnGH | 27
| 112 | 32/0 | 3DC1+0 | DFR | 2025-03-17 | 62.5353 | Completed |  |  |  | 2025-03-23 | Khatun | 27 |  | Completed | Completed
| 113 | 15/1 | 3DA+0 | WBC | 2025-03-23 | 36.37 | Completed |  |  |  | 2025-03-26 | Subash | 27
| 114 | 21/3 | 3DA+6 | WBC | 2025-03-13 | 43.08 | Completed |  |  |  | 2025-03-27 | Praveen | 25 |  | Completed | Completed
| 115 | 32/2 | 3DA+3 | DFR | 2025-03-23 | 37.93 | Completed |  |  |  | 2025-03-27 | Khatun | 25 |  | Completed | Completed
| 116 | 15/2 | 3DA+3 | WET | 2025-03-27 | 37.93 | Completed |  |  |  | 2025-03-29 | Subash | 27
| 117 | 38/7 | 3DA+0 | WFR | 2025-03-24 | 36.37 | Completed |  |  |  | 2025-03-29 | J.$lnGH - o1 | 25
| 118 | 36/3 | 3DA+3 | DFR | 2025-03-01 | 37.93 | Completed |  |  |  | 2025-03-30 | J.$lnGH - o2 | 27
| 119 | 32/3 | 3DA+6 | DFR | 2025-03-28 | 43.08 | Completed |  |  |  | 2025-04-01 | Khatun | 27 |  | Completed | Completed
| 120 | 15/4 | 3DA+3 | WBC | 2025-03-29 | 37.93 | Completed |  |  |  | 2025-04-02 | Subash | 27
| 121 | 37/5 | 3DA+0 | DFR | 2025-03-29 | 36.37 | Completed |  |  |  | 2025-04-04 | J.$lnGH - o1 | 25
| 122 | 36/1 | 3DA+0 | DFR | 2025-03-30 | 36.37 | Completed |  |  |  | 2025-04-05 | J.$lnGH - o2 | 25
| 123 | 33/0 | 3DD45+6 | WFR | 2025-04-02 | 84.248 | Completed |  |  |  | 2025-04-09 | Khatun | 25 |  | Completed | Completed
| 124 | 16/0 | 3DD45+0 | WET | 2025-04-03 | 72.721 | Completed |  |  |  | 2025-04-10 | Subash | 27
| 125 | 19/1 | 3DA+6 | WBC | 2025-03-28 | 43.08 | Completed |  |  |  | 2025-04-11 | Praveen | 27 |  | Completed | Completed
| 126 | 36/2 | 3DA+3 | DFR | 2025-04-06 | 37.93 | Completed |  |  |  | 2025-04-13 | J.$lnGH - o2 | 25
| 127 | 35/4 | 3DA+6 | DFR | 2025-04-10 | 43.08 | Completed |  |  |  | 2025-04-14 | Khatun | 27
| 128 | 16/1 | 3DA+0 | WET | 2025-04-11 | 36.37 | Completed |  |  |  | 2025-04-15 | Subash | 27
| 129 | 38/0 | 3DC1+0 | DFR | 2025-04-05 | 62.54 | Completed |  |  |  | 2025-04-17 | J.$lnGH - o1 | 27
| 130 | 35/3 | 3DA+0 | DFR | 2025-04-15 | 36.37 | Completed |  |  |  | 2025-04-18 | Khatun | 25
| 131 | 16/3 | 3DA+3 | WET | 2025-04-16 | 37.93 | Completed |  |  |  | 2025-04-19 | Subash | 25
| 132 | 16/4 | 3DA+0 | WET | 2025-04-19 | 36.37 | Completed |  |  |  | 2025-04-21 | Subash | 25
| 133 | 36/5 | 3DA+0 | DFR | 2025-04-14 | 36.37 | Completed |  |  |  | 2025-04-21 | J.$lnGH - o2 | 27
| 134 | 29/0 | 3DC1+0 | DFR | 2025-04-19 | 62.54 | Completed |  |  |  | 2025-04-23 | Khatun | 28 |  | Completed | Completed
| 135 | 37/4 | 3DA+6 | DFR | 2025-04-18 | 43.08 | Completed |  |  |  | 2025-04-23 | J.$lnGH - o1 | 29
| 136 | 16/5 | 3DA+0 | WET | 2025-04-22 | 36.37 | Completed |  |  |  | 2025-04-24 | Subash | 26
| 137 | 17/3 | 3DA+6 | DFR | 2025-04-12 | 43.08 | Completed |  |  |  | 2025-04-26 | Praveen | 27 |  | Completed | Completed
| 138 | 36/4 | 3DA+3 | DFR | 2025-04-22 | 37.93 | Completed |  |  |  | 2025-04-27 | J.$lnGH - o2 | 25
| 139 | 15/3 | 3DA+0 | WBC | 2025-04-25 | 36.37 | Completed |  |  |  | 2025-04-27 | Subash | 27
| 140 | 28/0 | 3DC1+0 | DFR | 2025-04-24 | 62.535 | Completed |  |  |  | 2025-04-28 | Khatun | 28
| 141 | 37/2 | 3DA+0 | DFR | 2025-04-24 | 36.37 | Completed |  |  |  | 2025-04-30 | J.$lnGH - o1 | 29
| 142 | 13/11 | 3DA+0 | WET | 2025-04-28 | 36.37 | Completed |  |  |  | 2025-04-30 | Subash | 28
| 143 | 27/9 | 3DA+3 | DFR | 2025-04-29 | 37.93 | Completed |  |  |  | 2025-05-02 | Khatun | 25
| 144 | 10/7 | 3DA+3 | DFR | 2025-05-01 | 37.93 | Completed |  |  |  | 2025-05-04 | Subash | 26 |  | Completed | Completed
| 145 | 38/2 | 3DA+0 | DFR | 2025-05-02 | 36.37 | Completed |  |  |  | 2025-05-05 | J.$lnGH - o1 | 26
| 146 | 11/1 | 3DA+0 | WBC | 2025-05-05 | 36.37 | Completed |  |  |  | 2025-05-06 | Subash | 26
| 147 | 21/0 | 3DD45+0 | DFR | 2025-05-03 | 72.72 | Completed |  |  |  | 2025-05-08 | Khatun | 25 |  | Completed | Completed
| 148 | 17/2 | 3DA+3 | WET | 2025-04-27 | 37.93 | Completed |  |  |  | 2025-05-09 | Praveen | 27 |  |  | Completed
| 149 | 10/9 | 3DA+6 | DFR | 2025-05-07 | 43.08 | Completed |  |  |  | 2025-05-10 | Subash | 28 |  | Completed | Completed
| 150 | 37/3 | 3DA+0 | DFR | 2025-05-06 | 36.37 | Completed |  |  |  | 2025-05-10 | Jwala Singh -01 | 29
| 151 | 10/4 | 3DA+3 | DFR | 2025-05-10 | 37.93 | Completed |  |  |  | 2025-05-13 | Subash | 25 |  | Completed | Completed
| 152 | 20/0 | 3DB1+0 | DFR | 2025-05-10 | 54.66 | Completed |  |  |  | 2025-05-14 | Khatun | 29 |  | Completed | Completed
| 153 | 37/6 | 3DA+0 | DFR | 2025-05-11 | 36.37 | Completed |  |  |  | 2025-05-16 | Jwala Singh -01 | 28
| 154 | 10/2 | 3DA+0 | DFR | 2025-05-14 | 36.37 | Completed |  |  |  | 2025-05-17 | Subash | 30 |  | Completed | Completed
| 155 | 10/1 | 3DA+3 | DFR | 2025-05-18 | 37.93 | Completed |  |  |  | 2025-05-20 | Subash | 28 |  | Completed | Completed
| 156 | 19/0 | 3DD45+0 | WET | 2025-05-15 | 72.72 | Completed |  |  |  | 2025-05-22 | Khatun | 27 |  | WIP | Completed
| 157 | 36/6 | 3DA+3 | DFR | 2025-05-11 | 37.93 | Completed |  |  |  | 2025-05-24 | Hassan | 28
| 158 | 10/3 | 3DA+3 | DFR | 2025-05-21 | 37.93 | Completed |  |  |  | 2025-05-28 | Subash | 28 |  | Completed | Completed
| 159 | 35/1 | 3DA+0 | DFR | 2025-05-08 | 36.37 | Completed |  |  |  | 2025-05-31 | Hassan | 25
| 160 | 10/5 | 3DA+3 | DFR | 2025-05-29 | 37.93 | Completed |  |  |  | 2025-06-02 | Subash | 25 |  | Completed | Completed
| 161 | 17/0 | 3DC1+0 | WBC | 2025-05-10 | 62.535 | Completed |  |  |  | 2025-06-04 | Praveen | 28 |  |  | Completed
| 162 | 31/3 | 3DA-3 | WFR | 2025-06-01 | 34.946 | Completed |  |  |  | 2025-06-06 | Hassan | 28 |  | Completed | Completed
| 163 | 30/0 | 3DC1+6 | DFR | 2025-06-03 | 71.7057 | Completed |  |  |  | 2025-06-11 | Subash | 30 |  | WIP | Completed
| 164 | 33/2 | 3DA-3 | DFR | 2025-06-05 | 34.946 | Completed |  |  |  | 2025-06-16 | Hassan | 27
. | 165 | 29/9 | 3DB1+9 | DFR | 2025-06-06 | 64.891 | Completed |  |  |  | 2025-06-18 | Subash | 28 |  | WIP | Completed
| 166 | 21/5 | 3DA-3 | WFR | 2025-06-05 | 34.946 | Completed |  |  |  | 2025-06-19 | Praveen | 28 |  | Completed | Completed
| 167 | 10/6 | 3DA+6 | DFR | 2025-06-19 | 43.08 | Completed |  |  |  | 2025-06-24 | Subash | 25 |  | Completed | Completed
| 168 | 34/0 | 3DC1+0 | DFR | 2025-06-17 | 62.535 | Completed |  |  |  | 2025-06-25 | Hassan | 29 |  |  | WIP
| 169 | 11/2 | 3DA+0 | WBC | 2025-06-25 | 36.372 | Completed |  |  |  | 2025-06-28 | Subash | 28
| 170 | 11/3 | 3DA-3 | WBC | 2025-06-29 | 34.946 | Completed |  |  |  | 2025-07-02 | Subash | 27
| 171 | 15/0 | 3DD45+3 | WET | 2025-06-24 | 76.193 | Completed |  |  |  | 2025-07-04 | Naziruddin | 30
| 172 | 35/2 | 3DA+0 | DFR | 2025-06-25 | 36.372 | Completed |  |  |  | 2025-07-04 | Hassan | 28
| 173 | 39/4 | 3DA+3 | DFR | 2025-06-24 | 37.931 | Completed |  |  |  | 2025-07-05 | Hassan-2 | 27
| 174 | 20A/0 | 3DB2+0 | DFR | 2025-06-20 | 54.66 | Completed |  |  |  | 2025-07-07 | Praveen | 28 |  | Completed | Completed
| 175 | 10/0 | 3DB2+0 | DFR | 2025-07-03 | 54.66 | Completed |  |  |  | 2025-07-07 | Subash | 28 |  | Completed | Completed
| 176 | 6/5 | 2DA+0 | DFR | 2025-07-04 | 31.99 | Completed |  |  |  | 2025-07-10 | Khatun | 24
| 177 | 9/10 | 2DA+3 | DFR | 08-07-20225 | 33.38 | Completed |  |  |  | 2025-07-12 | Subash | 27 |  | Completed | Completed
| 178 | 39/3 | 3DA+3 | DFR | 2025-07-06 | 37.931 | Completed |  |  |  | 2025-07-12 | Hassan-2 | 24
| 179 | 14/0 | 3DC2+6 | WET | 05-07-205 | 71.706 | Completed |  |  |  | 2025-07-13 | Naziruddin | 26
| 180 | 6/4 | 2DA+0 | DFR | 2025-07-11 | 31.99 | Completed |  |  |  | 2025-07-15 | Khatun | 27
| 181 | 34/2 | 3DB1+6 | DFR | 2025-07-05 | 63.16 | Completed |  |  |  | 2025-07-16 | Hassan | 25
| 182 | 9/8 | 2DA+0 | DFR | 2025-07-13 | 31.99 | Completed |  |  |  | 2025-07-16 | Subash | 26 |  | Completed | Completed
| 183 | 6/3 | 2DA+0 | DFR | 2025-07-15 | 31.99 | Completed |  |  |  | 2025-07-18 | Khatun | 25
| 184 | 9/7 | 2DA+3 | DFR | 2025-07-17 | 33.3756 | Completed |  |  |  | 2025-07-20 | Subash | 23 |  | Completed | Completed
| 185 | 42/4 | 3DA+3 | DFR | 2025-07-12 | 37.931 | Completed |  |  |  | 2025-07-20 | D k Verma | 25
| 186 | 8/6 | 2DA+0 | DFR | 2025-07-14 | 31.99 | Completed |  |  |  | 2025-07-21 | Naziruddin | 24
| 187 | 6/2 | 2DA+0 | DFR | 2025-07-19 | 31.99 | Completed |  |  |  | 2025-07-21 | Khatun | 24
| 188 | 9/6 | 2DA+3 | DFR | 2025-07-21 | 33.38 | Completed |  |  |  | 2025-07-25 | Subash | 25 |  | Completed | Completed
| 189 | 6/1 | 2DA+3 | DFR | 2025-07-22 | 33.38 | Completed |  |  |  | 2025-07-28 | Khatun | 25
| 190 | 8/14 | 2DA+3 | DFR | 2025-07-22 | 33.38 | Completed |  |  |  | 2025-07-29 | Naziruddin | 24
| 191 | 42/3 | 3DA+3 | WFR | 2025-07-21 | 37.931 | Completed |  |  |  | 2025-07-29 | D K Verma | 24
| 192 | 39/0 | 3DC1+3 | DFR | 2025-07-13 | 65.22 | Completed |  |  |  | 2025-07-30 | Hassan -2 | 25
| 193 | 9/5 | 2DA+0 | DFR | 2025-07-26 | 31.99 | Completed |  |  |  | 2025-07-31 | Subash | 24 |  | Completed | Completed
| 194 | 4/21 | 2DA+3 | DFR | 2025-07-29 | 33.38 | Completed |  |  |  | 2025-08-01 | Khatun | 24
| 195 | 16/7 | 3DA-3 | WET | 2025-07-08 | 34.946 | Completed |  |  |  | 2025-08-02 | Praveen | 25 |  |  | Completed
| 196 | 8/8 | 2DA+0 | DFR | 2025-07-30 | 31.99 | Completed |  |  |  | 2025-08-02 | Naziruddin | 25
| 197 | 35/0 | 3DB1+9 | DFR | 2025-07-17 | 64.89 | Completed |  |  |  | 2025-08-03 | Hassan | 24
| 198 | 6/6 | 2DA+0 | DFR | 2025-08-02 | 31.99 | Completed |  |  |  | 2025-08-04 | Khatun | 24
| 199 | 42/5 | 3DA+3 | DFR | 2025-07-30 | 37.931 | Completed |  |  |  | 2025-08-04 | D K Verma | 24
| 200 | 11/0 | 3DC1+0 | DFR | 2025-08-01 | 62.535 | Completed |  |  |  | 2025-08-06 | Subash | 24 |  | Completed | Completed
| 201 | 8/7 | 2DA+3 | DFR | 2025-08-03 | 33.38 | Completed |  |  |  | 2025-08-07 | Naziruddin | 25
| 202 | 8/13 | 2DA+3 | DFR | 2025-08-05 | 33.38 | Completed |  |  |  | 2025-08-08 | Khatun | 24
| 203 | 4/23 | 2DA+0 | DFR | 2025-08-09 | 31.99 | Completed |  |  |  | 2025-08-11 | Khatun | 24
| 204 | 10/8 | 3DA+3 | DFR | 2025-08-07 | 37.931 | Completed |  |  |  | 2025-08-12 | Subash | 25 |  | Completed | Completed
| 205 | 34/1 | 3DB1+0 | DFR | 2025-08-04 | 54.66 | Completed |  |  |  | 2025-08-12 | Hassan | 25
| 206 | 8/12 | 2DA+0 | DFR | 2025-08-08 | 31.99 | Completed |  |  |  | 2025-08-13 | Naziruddin | 25
| 207 | 42/6 | 3DA+0 | DFR | 2025-08-05 | 36.37 | Completed |  |  |  | 2025-08-14 | D k Verma | 24
| 208 | 9/4 | 2DA+0 | DFR | 2025-08-13 | 31.99 | Completed |  |  |  | 2025-08-18 | Subash | 30 |  | Completed | Completed
| 209 | 9/1 | 2DA+3 | DFR | 2025-08-12 | 33.38 | Completed |  |  |  | 2025-08-19 | Khatun | 25 |  | Completed | Completed
| 210 | 42/7 | 3DA+9 | DFR | 2025-08-16 | 44.825 | Completed |  |  |  | 2025-08-24 | D k Verma | 36
| 211 | 12/1 | 3DA+3 | WFR | 2025-08-23 | 37.931 | Completed |  |  |  | 2025-08-29 | Subash | 30 |  | Completed | Completed
| 212 | 40/0 | 3DB2+9 | DFR | 2025-08-13 | 64.891 | Completed |  |  |  | 2025-08-29 | Hassan | 30
| 213 | 1A/0 | 2DD45+0 | DFR | 2025-08-20 | 66.21 | Completed |  |  |  | 2025-08-30 | Khatun | 29
| 214 | 9/0 | 2DB1+0 | DFR | 2025-08-14 | 51.04 | Completed |  |  |  | 2025-08-30 | Naziruddin | 25 |  | Completed | Completed
| 215 | 9/2 | 2DA+0 | DFR | 2025-08-19 | 31.99 | Completed |  |  |  | 2025-08-31 | Subash | 30 |  | Completed | Completed
| 216 | 42/1 | 3DA+6 | DFR | 2025-08-25 | 43.08 | Completed |  |  |  | 2025-08-31 | D k Verma | 36
| 217 | 2/3 | 2DA+0 | DFR | 2025-08-31 | 31.99 | Completed |  |  |  | 2025-09-03 | Shakila Khatun | 32
| 218 | 9/9 | 2DA+0 | DFR | 2025-09-01 | 31.99 | Completed |  |  |  | 2025-09-04 | Subash | 35 |  | Completed | Completed
| 219 | 40/1 | 3DA+9(2mRC) | DFR | 2025-08-30 | 44.825 | Completed |  |  |  | 2025-09-05 | Hassan | 25
| 220 | 42/8 | 3DA+9(2mRC) | DFR | 2025-09-01 | 44.825 | Completed |  |  |  | 2025-09-06 | D k Verma | 34
| 221 | 8/15 | 2DA+3 | DFR | 2025-08-31 | 33.38 | Completed |  |  |  | 2025-09-07 | Naziruddin | 25
| 222 | 4/6 | 2DA+0 | DFR | 2025-09-05 | 31.99 | Completed |  |  |  | 2025-09-07 | Subash | 35
| 223 | 4/0 | 2DB2+0 | DFR | 2025-09-05 | 51.04 | Completed |  |  |  | 2025-09-08 | Shakila Khatun | 34
| 224 | 39/5 | 3DA+3 | DFR | 2025-08-08 | 37.931 | Completed |  |  |  | 2025-09-08 | Praveen | 25
| 225 | 4/7 | 2DA+3 | DFR | 2025-09-08 | 33.38 | Completed |  |  |  | 2025-09-09 | Subash | 35
| 226 | 42/9 | 3DA+3 | DFR | 2025-09-07 | 37.931 | Completed |  |  |  | 2025-09-10 | D k Verma | 31
| 227 | 41/0 | 3DC1+0 | WET | 2025-09-06 | 62.535 | Completed |  |  |  | 2025-09-13 | Hassan | 25
| 228 | 4/9 | 2DA+0 | DFR | 2025-09-10 | 31.99 | Completed |  |  |  | 2025-09-14 | Subash | 35
| 229 | 8/9 | 2DA+3 | DFR | 2025-09-08 | 33.38 | Completed |  |  |  | 2025-09-15 | Naziruddin | 25
| 230 | 4/12 | 2DB1+0 | DFR | 2025-09-09 | 51.04 | Completed |  |  |  | 2025-09-16 | Khatun | 34
| 231 | 4/10 | 2DA+3 | DFR | 2025-09-14 | 33.38 | Completed |  |  |  | 2025-09-20 | Subash | 35
| 232 | 42/0 | 3DB1+9 | DFR | 2025-09-13 | 64.89 | Completed |  |  |  | 2025-09-23 | D k Verma | 34
| 233 | 4/2 | 2DA+3 | DFR | 2025-09-21 | 33.38 | Completed |  |  |  | 2025-09-24 | Subash | 35
| 234 | 39/1 | 3DA+6 | WFR | 2025-09-16 | 43.079 | Completed |  |  |  | 2025-09-25 | Hassan | 34
| 235 | 4/17 | 2DA+3 | DFR | 2025-09-16 | 33.38 | Completed |  |  |  | 2025-09-26 | Naziruddin | 25
| 236 | 5/0 | 2DD45+6 | DFR | 2025-09-21 | 77.32 | Completed |  |  |  | 2025-09-29 | Khatun | 28
| 237 | 43/2 | 3DA-3 | DFR | 2025-09-24 | 34.946 | Completed |  |  |  | 2025-09-30 | D k Verma | 34
| 238 | 2/2 | 2DA+0 | DFR | 2025-09-25 | 31.99 | Completed |  |  |  | 2025-09-30 | Subash | 35
| 239 | 4/18 | 2DA+0 | DFR | 2025-09-28 | 31.99 | Completed |  |  |  | 2025-10-04 | Khatun | 25
| 240 | 43/4 | 3DA+3 | DFR | 2025-09-21 | 37.931 | Completed |  |  |  | 2025-10-06 | Yadhav + D k Verma | 32
| 241 | 1/0 | 2DD60+0 | DFR | 2025-10-01 | 72.63 | Completed |  |  |  | 2025-10-09 | Subash | 35
| 242 | 39/2 | 3DA+0 | WBC | 2025-09-27 | 36.37 | Completed |  |  |  | 2025-10-09 | Hassan | 34
| 243 | 39/7 | 3DA+6 | WFR | 2025-09-13 | 43.079 | Completed |  |  |  | 2025-10-11 | Praveen | 21
| 244 | 43/3 | 3DA+0 | DFR | 2025-10-07 | 36.37 | Completed |  |  |  | 2025-10-11 | D k Verma | 34
| 245 | 9/3 | 2DA+9 | DFR | 2025-10-07 | 39.17 | Completed |  |  |  | 2025-10-12 | Khatun | 25 |  | Completed | Completed
| 246 | 4/3 | 2DA+6 | DFR | 2025-10-10 | 37.72 | Completed |  |  |  | 2025-10-15 | Subash | 35
| 247 | 43/5 | 3DA+9(2mRC) | DFR | 2025-10-12 | 44.851 | Completed |  |  |  | 2025-10-16 | D k Verma | 34
| 248 | 4/20 | 2DA+9 | DFR | 2025-10-13 | 39.17 | Completed |  |  |  | 2025-10-17 | Khatun | 25
0 | 249 | 36/7 | 3DA+3 | WFR | 2025-10-10 | 37.931 | Completed |  |  |  | 2025-10-19 | Hassan | 34
| 250 | 4/4 | 2DA+0 | DFR | 2025-10-17 | 31.99 | Completed |  |  |  | 2025-10-21 | Subash | 35
| 251 | 42/2 | 3DA+0 | DFR | 2025-10-17 | 36.371 | Completed |  |  |  | 2025-10-21 | D k Verma | 34
| 252 | 4/19 | 2DA+6 | DFR | 2025-10-17 | 37.72 | Completed |  |  |  | 2025-10-22 | Khatun | 25
| 253 | 41/1 | 3DA+0 | WET | 2025-10-22 | 36.371 | Completed |  |  |  | 2025-10-25 | D k Verma | 34
| 254 | 11/4 | 3DA+0 | DFR | 2025-10-23 | 36.37 | Completed |  |  |  | 2025-10-27 | Khatun | 25
| 255 | 39/6 | 3DA+0 | WFR | 2025-10-14 | 36.37 | Completed |  |  |  | 2025-10-27 | Praveen | 22
| 256 | 4/1 | 2DA+3 | DFR | 2025-10-22 | 33.38 | Completed |  |  |  | 2025-10-30 | Subash | 35
| 257 | 11/7 | 3DA+0 | WET | 2025-10-28 | 36.37 | Completed |  |  |  | 2025-11-02 | Khatun | 25
| 258 | 43/1 | 3DA+3 | WFR | 2025-10-26 | 37.931 | Completed |  |  |  | 2025-11-02 | D k Verma | 34
| 259 | 36/8 | 3DA+0 | WFR | 2025-10-21 | 36.37 | Completed |  |  |  | 2025-11-02 | Hassan | 24
| 260 | 4/13 | 2DA+0 | DFR | 2025-10-31 | 31.99 | Completed |  |  |  | 2025-11-05 | Subash | 22
| 261 | 39/9 | 3DA+9 | DFR |  | 44.851 | Material Shifting Done |  |  |  |  | Rajiv Yadhav | 24
| 262 | 39/8 | 3DA+3 | DFR | 2025-11-06 | 37.931 | Ground Assembling under Progress |  |  |  |  | Praveen | 22
| 263 | 37/0 | 3DB2+0 | DFR |  | 54.66 | Material Shifting under Progress |  |  |  |  | Rajiv Yadhav | 24
| 264 | 36/0 | 3DD60+3 | DFR |  | 83.81 | Material Shifting under Progress |  |  |  |  | Hassan | 24
| 265 | 3/1 | 2DA+9 | DFR | 2025-11-06 | 39.17 | Material Shifting under Progress |  |  |  |  | Subash | 22
| 266 | 43B/0 | 3DB1+9 | DFR | 2025-11-04 | 64.89 | 1st Section Under Progress |  |  |  |  | D k Verma | 34
| 267 | 8/3 | 2DB1+9 | DFR | 2025-11-04 | 61.15 | 3rd Section Done |  |  |  |  | Khatun | 25
Formulas:
End Date = [Start Date]

## Erection Compiled
Erection
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength
1 | 25/4 | 3DA+0 | DFR | 10-07-2024 | 36.37 | Completed | 2024-07-19 | Khatan | 25
2 | 26/1 | 3DA+0 | DFR | 18-07-2024 | 36.37 | Completed | 2024-07-28 | Khatan | 25
3 | 26/4 | 3DA+0 | DFR | 27-07-2024 | 36.37 | Completed | 2024-08-03 | Khatan | 25
4 | 25/1 | 3DA+0 | DFR | 02-08-2024 | 36.37 | Completed | 2024-08-09 | Khatan | 25
5 | 26/2 | 3DA+0 | DFR | 09-08-2024 | 36.37 | Completed | 2024-08-14 | Khatan | 25
6 | 26/3 | 3DA+0 | DFR | 2024-08-16 | 36.37 | Completed | 2024-08-18 | Khatan | 25
7 | 27/1 | 3DA+0 | DFR | 2024-08-19 | 36.37 | Completed | 2024-08-24 | Khatan | 25
8 | 24/5 | 3DA+0 | DFR | 2024-08-22 | 36.37 | Completed | 2024-08-29 | Khatan | 25
9 | 24/4 | 3DA+0 | DFR | 2024-08-29 | 36.37 | Completed | 2024-09-06 | Khatan | 25
10 | 22/5 | 3DA+0 | DFR | 2024-08-23 | 36.37 | Completed | 2024-09-08 | s.K.Janarul | 24
11 | 24/3 | 3DA+0 | DFR | 2024-08-29 | 36.37 | Completed | 2024-09-12 | Khatan | 24
12 | 27/2 | 3DA+0 | DFR | 2024-09-14 | 36.37 | Completed | 2024-09-19 | Khatan | 24
13 | 21/9 | 3DA+0 | DFR | 2024-09-09 | 36.37 | Completed | 2024-09-21 | s.K.Janarul Sheikh | 25
14 | 27/4 | 3DA+0 | DFR | 2024-09-19 | 36.37 | Completed | 2024-09-23 | Khatan | 24
15 | 27/5 | 3DA+0 | DFR | 2024-09-24 | 36.37 | Completed | 2024-09-28 | Khatan | 24
16 | 21/7 | 3DA+0 | DFR | 2024-09-12 | 36.37 | Completed | 2024-09-29 | Ashok kumar | 25
17 | 12/3 | 3DA+3 | DFR | 2024-09-14 | 37.9313 | Completed | 2024-09-30 | Maa Const. | 24
18 | 27/6 | 3DA+0 | DFR | 2024-09-29 | 36.37 | Completed | 2024-10-03 | Khatan | 24
19 | 23/2 | 3DA+0 | DFR | 2024-09-26 | 36.37 | Completed | 2024-10-03 | s.K.Janarul Sheikh | 25
20 | 29/4 | 3DA+0 | DFR | 2024-09-21 | 36.37 | Completed | 2024-10-04 | Manirul (Islam)-Khatun | 25
21 | 27/7 | 3DA+0 | DFR | 2024-10-03 | 36.37 | Completed | 2024-10-07 | Khatan | 24
22 | 29/5 | 3DA+3 | DFR | 2024-10-05 | 37.9313 | Completed | 2024-10-14 | Khatan | 24
23 | 23/4 | 3DA+0 | DFR | 2024-10-05 | 36.37 | Completed | 2024-10-14 | s.K.Janarul Sheikh | 25
24 | 21/8 | 3DA+0 | DFR | 2024-10-01 | 36.37 | Completed | 2024-10-17 | Ashok | 25
25 | 12/4 | 3DA+3 | DFR | 2024-10-01 | 37.9313 | Completed | 2024-10-19 | Maa Const. | 25
26 | 30/4 | 3DA+3 | WFR | 2024-10-16 | 37.9313 | Completed | 2024-10-21 | Khatun | 25
27 | 24/8 | 3DA+3 | DFR | 2024-10-21 | 37.9313 | Completed | 2024-10-26 | Khatan
28 | 12/9 | 3DA+3 | DFR | 2024-10-01 | 37.9313 | Completed | 2024-10-26 | Praveen | 25
29 | 22/4 | 3DA+3 | WFR | 2024-10-17 | 37.9313 | Completed | 2024-10-27 | Subash | 26
30 | 22/1 | 3DA+0 | WFR | 2024-10-18 | 36.37 | Completed | 2024-10-27 | Ashok | 25
31 | 12/2 | 3DA+3 | DFR | 2024-10-19 | 36.37 | Completed | 2024-10-30 | Maa Const. | 25
32 | 24/7 | 3DA+0 | DFR | 2024-10-27 | 36.37 | Completed | 2024-11-01 | khatun | 24
33 | 23/3 | 3DA+0 | DFR | 2024-10-16 | 36.37 | Completed | 2024-11-01 | Subash | 24
34 | 22/2 | 3DA+0 | DFR | 2024-10-29 | 36.37 | Completed | 2024-11-05 | Ashokkumar | 25
35 | 12/5 | 3DA+0 | DFR | 2024-11-01 | 36.37 | Completed | 2024-11-07 | Maa Const. | 24
36 | 24/0 | 3DB1+0 | DFR | 2024-11-02 | 54.655 | Completed | 2024-11-07 | Subash | 24
37 | 25/0 | 3DB2+0 | DFR | 2024-11-02 | 54.66 | Completed | 2024-11-07 | khatun | 25
38 | 12/10 | 3DA+0 | DFR | 2024-10-27 | 36.37 | Completed | 2024-11-12 | Praveen | 25
39 | 25/2 | 3DA+0 | WFR | 2024-11-08 | 36.37 | Completed | 2024-11-13 | Khatun | 24
40 | 12/6 | 3DA+0 | DFR | 2024-11-07 | 36.37 | Completed | 2024-11-14 | Maa Const. | 24
41 | 23/1 | 3DA+6 | WFR | 2024-11-09 | 43.08 | Completed | 2024-11-14 | Subash | 25
42 | 22/0 | 3DB1+0 | DFR | 2024-11-05 | 54.66 | Completed | 2024-11-15 | Ashok | 25
43 | 24/6 | 3DA+0 | DFR | 2024-11-13 | 36.37 | Completed | 2024-11-18 | Khatun | 22
44 | 24/1 | 3DA+6 | DFR | 2024-11-15 | 43.08 | Completed | 2024-11-20 | Subash | 25
45 | 12/7 | 3DA+0 | DFR | 2024-11-14 | 36.37 | Completed | 2024-11-21 | Maa Const. | 23
46 | 26/0 | 3DB2+0 | DFR | 2024-11-19 | 54.66 | Completed | 2024-11-24 | Khatun | 22
47 | 21/4 | 3DA+3 | WFR | 2024-11-16 | 37.93 | Completed | 2024-11-25 | Ashok | 25
48 | 23/0 | 3DB2+0 | DFR | 2024-11-21 | 54.66 | Completed | 2024-11-26 | Subash | 25
49 | 12/0 | 3DB2+0 | DFR | 2024-11-22 | 54.66 | Completed | 2024-11-30 | Maa Const. | 23
50 | 27/0 | 3DB1+0 | DFR | 2024-11-24 | 54.66 | Completed | 2024-11-30 | Khatun | 22
51 | 21/2 | 3DA+0 | WFR | 2024-11-26 | 36.37 | Completed | 2024-12-02 | Subash | 25
52 | 12/8 | 3DA+3 | DFR | 2024-11-12 | 37.93 | Completed | 2024-12-05 | Praveen | 23
53 | 21/6 | 3DA+0 | DFR | 2024-12-03 | 36.37 | Completed | 2024-12-06 | Subash | 25
54 | 27/8 | 3DA+0 | DFR | 2024-12-03 | 36.37 | Completed | 2024-12-08 | Khatun | 22
55 | 24/2 | 3DA+3 | DFR | 2024-12-03 | 37.93 | Completed | 2024-12-11 | Subash | 25
56 | 29/3 | 3DA+0 | DFR | 2024-12-09 | 36.37 | Completed | 2024-12-13 | Khatun | 22
57 | 19/3 | 3DA+3 | DFR | 2024-12-11 | 37.93 | Completed | 2024-12-15 | Subash | 25
58 | 19/2 | 3DA+0 | DFR | 2024-12-16 | 36.37 | Completed | 2024-12-18 | Subash | 23
59 | 29/8 | 3DA+0 | DFR | 2024-12-15 | 36.37 | Completed | 2024-12-19 | Khatun | 25
60 | 18/3 | 3DA+0 | WET | 2024-12-19 | 36.37 | Completed | 2024-12-22 | Subash | 22
61 | 18/2 | 3DA+0 | DFR | 2024-12-23 | 36.37 | Completed | 2024-12-25 | Subash | 25
62 | 29/1 | 3DA+9 | DFR | 2024-12-20 | 44.825 | Completed | 2024-12-25 | Khatun | 22
63 | 11/11 | 3DA+3 | DFR | 2024-12-12 | 37.93 | Completed | 2024-12-28 | Praveen | 23
64 | 18/1 | 3DA+0 | DFR | 2024-12-26 | 36.37 | Completed | 2024-12-28 | Subash | 25
65 | 30/3 | 3DA+3 | DFR | 2024-12-26 | 37.93 | Completed | 2024-12-31 | Khatun | 22
66 | 18/0 | 3DB2+0 | DFR | 2024-12-27 | 54.66 | Completed | 2025-01-03 | Subash | 25
67 | 30/2 | 3DA+3 | WFR | 2024-12-02 | 37.93 | Completed | 2025-01-06 | Khatun | 26
68 | 17/1 | 3DA+3 | WFR | 2025-01-03 | 37.93 | Completed | 2025-01-08 | Subash | 27
69 | 21/1 | 3DA+0 | DFR | 2024-12-28 | 36.37 | Completed | 2025-01-13 | Subash | 25
70 | 30/1 | 3DA+3 | DFR | 2025-01-04 | 37.93 | Completed | 2025-01-15 | Khatun | 28
71 | 11/10 | 3DA+0 | WET | 2025-01-02 | 36.37 | Completed | 2025-01-15 | Praveen | 25
72 | 16/6 | 3DA+0 | WBC | 2025-01-14 | 36.37 | Completed | 2025-01-18 | Subash | 30
73 | 29/6 | 3DA+0 | DFR | 2025-01-16 | 36.37 | Completed | 2025-01-19 | Khatun | 27
74 | 16/8 | 3DA+3 | WET | 2025-01-18 | 37.93 | Completed | 2025-01-22 | Subash | 30
75 | 29/2 | 3DA+0 | WFR | 2025-01-19 | 36.37 | Completed | 2025-01-23 | Khatun | 27
76 | 16/10 | 3DA+3 | WBC | 2025-01-22 | 37.93 | Completed | 2025-01-27 | Subash | 30
77 | 30/5 | 3DA+0 | DFR | 2025-01-23 | 36.37 | Completed | 2025-01-28 | Khatun | 27
78 | 11/6 | 3DA+0 | DFR | 2025-01-16 | 36.37 | Completed | 2025-01-30 | Praveen | 25
79 | 16/9 | 3DA+0 | WBC | 2025-01-22 | 36.37 | Completed | 2025-01-30 | Subash | 30
80 | 31/1 | 3DA+3 | DFR | 2025-01-28 | 37.93 | Completed | 2025-02-03 | Khatun | 27
81 | 16/2 | 3DA+0 | WET | 2025-01-30 | 36.37 | Completed | 2025-02-03 | Subash | 25
82 | 13/2 | 3DA+0 | WBC | 2025-02-04 | 36.37 | Completed | 2025-02-08 | Subash | 30
83 | 31/4 | 3DA+0 | DFR | 2025-02-04 | 36.37 | Completed | 2025-02-09 | Khatun | 25
84 | 11/5 | 3DA+0 | DFR | 2025-01-30 | 36.37 | Completed | 2025-02-10 | Praveen | 30
85 | 13/1 | 3DA+3 | WET | 2025-02-09 | 37.93 | Completed | 2025-02-12 | Subash | 27
86 | 31/5 | 3DA+0 | WFR | 2025-02-10 | 36.37 | Completed | 2025-02-14 | Khatun | 27
87 | 25/3 | 3DA+0 | DFR | 2025-02-10 | 36.37 | Completed | 2025-02-18 | J.$lnGH | 25
88 | 13/3 | 3DA+6 | WBC | 2025-02-13 | 43.08 | Completed | 2025-02-19 | Subash | 30
89 | 31/6 | 3DA+3 | DFR | 2025-02-15 | 37.93 | Completed | 2025-02-20 | Khatun | 27
90 | 12/11 | 3DA+6 | DFR | 2025-02-11 | 43.08 | Completed | 2025-02-21 | Praveen | 25
91 | 13/4 | 3DA+3 | WBC | 2025-02-19 | 37.93 | Completed | 2025-02-23 | Subash | 30
92 | 25/5 | 3DA+6 | DFR | 2025-02-19 | 43.08 | Completed | 2025-02-25 | J.$lnGH | 27
93 | 31/2 | 3DA+0 | WFR | 2025-02-21 | 36.37 | Completed | 2025-02-25 | Khatun | 25
94 | 13/6 | 3DA+6 | WBC | 2025-02-24 | 43.08 | Completed | 2025-02-27 | Subash | 27
95 | 11/9 | 3DA+0 | WET | 2025-02-22 | 36.37 | Completed | 2025-03-01 | Praveen | 25
96 | 29/7 | 3DA+3 | WFR | 2025-02-26 | 37.93 | Completed | 2025-03-01 | Khatun | 23
97 | 13/5 | 3DA+0 | WET | 2025-02-28 | 36.37 | Completed | 2025-03-02 | Subash | 25
98 | 38/1 | 3DA+0 | WFR | 2025-02-26 | 36.37 | Completed | 2025-03-02 | J.$lnGH | 27
99 | 13/7 | 3DA+6 | WET | 2025-03-03 | 43.08 | Completed | 2025-03-07 | Subash | 25
100 | 31/0 | 3DB2+0 | WFR | 2025-03-02 | 54.66 | Completed | 2025-03-07 | Khatun | 27
101 | 38/3 | 3DA+3 | WET | 2025-03-03 | 37.93 | Completed | 2025-03-09 | J.$lnGH | 30
102 | 13/0 | 3DB1+0 | DFR | 2025-03-08 | 54.66 | Completed | 2025-03-11 | Subash | 27
103 | 22/3 | 3DA+6 | DFR | 2025-03-03 | 43.08 | Completed | 2025-03-12 | Praveen | 25
104 | 32/1 | 3DA+0 | WFR | 2025-03-08 | 36.37 | Completed | 2025-03-12 | Khatun | 23
105 | 38/4 | 3DA+0 | DFR | 2025-03-10 | 36.37 | Completed | 2025-03-13 | J.$lnGH | 25
106 | 13/8 | 3DA+0 | WET | 2025-03-12 | 36.37 | Completed | 2025-03-16 | Subash | 25
107 | 33/1 | 3DA+0 | DFR | 2025-03-13 | 36.37 | Completed | 2025-03-17 | Khatun | 27
108 | 13/9 | 3DA+3 | WBC | 2025-03-16 | 37.93 | Completed | 2025-03-19 | Subash | 25
109 | 38/5 | 3DA+0 | WET | 2025-03-15 | 36.37 | Completed | 2025-03-19 | J.$lnGH | 25
110 | 13/10 | 3DA+0 | WBC | 2025-03-20 | 36.37 | Completed | 2025-03-22 | Subash | 25
111 | 38/6 | 3DA+0 | WBC | 2025-03-20 | 36.37 | Completed | 2025-03-23 | J.$lnGH | 27
112 | 32/0 | 3DC1+0 | DFR | 2025-03-17 | 62.5353 | Completed | 2025-03-23 | Khatun | 27
113 | 15/1 | 3DA+0 | WBC | 2025-03-23 | 36.37 | Completed | 2025-03-26 | Subash | 27
114 | 21/3 | 3DA+6 | WBC | 2025-03-13 | 43.08 | Completed | 2025-03-27 | Praveen | 25
115 | 32/2 | 3DA+3 | DFR | 2025-03-23 | 37.93 | Completed | 2025-03-27 | Khatun | 25
116 | 15/2 | 3DA+3 | WET | 2025-03-27 | 37.93 | Completed | 2025-03-29 | Subash | 27
117 | 38/7 | 3DA+0 | WFR | 2025-03-24 | 36.37 | Completed | 2025-03-29 | J.$lnGH - o1 | 25
118 | 36/3 | 3DA+3 | DFR | 2025-03-01 | 37.93 | Completed | 2025-03-30 | J.$lnGH - o2 | 27
119 | 32/3 | 3DA+6 | DFR | 2025-03-28 | 43.08 | Completed | 2025-04-01 | Khatun | 27
120 | 15/4 | 3DA+3 | WBC | 2025-03-29 | 37.93 | Completed | 2025-04-02 | Subash | 27
121 | 37/5 | 3DA+0 | DFR | 2025-03-29 | 36.37 | Completed | 2025-04-04 | J.$lnGH - o1 | 25
122 | 36/1 | 3DA+0 | DFR | 2025-03-30 | 36.37 | Completed | 2025-04-05 | J.$lnGH - o2 | 25
123 | 33/0 | 3DD45+6 | WFR | 2025-04-02 | 84.248 | Completed | 2025-04-09 | Khatun | 25
124 | 16/0 | 3DD45+0 | WET | 2025-04-03 | 72.721 | Completed | 2025-04-10 | Subash | 27
125 | 19/1 | 3DA+6 | WBC | 2025-03-28 | 43.08 | Completed | 2025-04-11 | Praveen | 27
126 | 36/2 | 3DA+3 | DFR | 2025-04-06 | 37.93 | Completed | 2025-04-13 | J.$lnGH - o2 | 25
127 | 35/4 | 3DA+6 | DFR | 2025-04-10 | 43.08 | Completed | 2025-04-14 | Khatun | 27
128 | 16/1 | 3DA+0 | WET | 2025-04-11 | 36.37 | Completed | 2025-04-15 | Subash | 27
129 | 38/0 | 3DC1+0 | DFR | 2025-04-05 | 62.54 | Completed | 2025-04-17 | J.$lnGH - o1 | 27
130 | 35/3 | 3DA+0 | DFR | 2025-04-15 | 36.37 | Completed | 2025-04-18 | Khatun | 25
131 | 16/3 | 3DA+3 | WET | 2025-04-16 | 37.93 | Completed | 2025-04-19 | Subash | 25
132 | 16/4 | 3DA+0 | WET | 2025-04-19 | 36.37 | Completed | 2025-04-21 | Subash | 25
133 | 36/5 | 3DA+0 | DFR | 2025-04-14 | 36.37 | Completed | 2025-04-21 | J.$lnGH - o2 | 27
134 | 29/0 | 3DC1+0 | DFR | 2025-04-19 | 62.54 | Completed | 2025-04-23 | Khatun | 28
135 | 37/4 | 3DA+6 | DFR | 2025-04-18 | 43.08 | Completed | 2025-04-23 | J.$lnGH - o1 | 29
136 | 16/5 | 3DA+0 | WET | 2025-04-22 | 36.37 | Completed | 2025-04-24 | Subash | 26
137 | 17/3 | 3DA+6 | DFR | 2025-04-12 | 43.08 | Completed | 2025-04-26 | Praveen | 27
138 | 36/4 | 3DA+3 | DFR | 2025-04-22 | 37.93 | Completed | 2025-04-27 | J.$lnGH - o2 | 25
139 | 15/3 | 3DA+0 | WBC | 2025-04-25 | 36.37 | Completed | 2025-04-27 | Subash | 27
140 | 28/0 | 3DC1+0 | DFR | 2025-04-24 | 62.535 | Completed | 2025-04-28 | Khatun | 28
141 | 37/2 | 3DA+0 | DFR | 2025-04-24 | 36.37 | Completed | 2025-04-30 | J.$lnGH - o1 | 29
142 | 13/11 | 3DA+0 | WET | 2025-04-28 | 36.37 | Completed | 2025-04-30 | Subash | 28
143 | 27/9 | 3DA+3 | DFR | 2025-04-29 | 37.93 | Completed | 2025-05-02 | Khatun | 25
144 | 10/7 | 3DA+3 | DFR | 2025-05-01 | 37.93 | Completed | 2025-05-04 | Subash | 26
145 | 38/2 | 3DA+0 | DFR | 2025-05-02 | 36.37 | Completed | 2025-05-05 | J.$lnGH - o1 | 26
146 | 11/1 | 3DA+0 | WBC | 2025-05-05 | 36.37 | Completed | 2025-05-06 | Subash | 26
147 | 21/0 | 3DD45+0 | DFR | 2025-05-03 | 72.72 | Completed | 2025-05-08 | Khatun | 25
148 | 17/2 | 3DA+3 | WET | 2025-04-27 | 37.93 | Completed | 2025-05-09 | Praveen | 27
149 | 10/9 | 3DA+6 | DFR | 2025-05-07 | 43.08 | Completed | 2025-05-10 | Subash | 28
150 | 37/3 | 3DA+0 | DFR | 2025-05-06 | 36.37 | Completed | 2025-05-10 | Jwala Singh -01 | 29
151 | 10/4 | 3DA+3 | DFR | 2025-05-10 | 37.93 | Completed | 2025-05-13 | Subash | 25
152 | 20/0 | 3DB1+0 | DFR | 2025-05-10 | 54.66 | Completed | 2025-05-14 | Khatun | 29
153 | 37/6 | 3DA+0 | DFR | 2025-05-11 | 36.37 | Completed | 2025-05-16 | Jwala Singh -01 | 28
154 | 10/2 | 3DA+0 | DFR | 2025-05-14 | 36.37 | Completed | 2025-05-17 | Subash | 30
155 | 10/1 | 3DA+3 | DFR | 2025-05-18 | 37.93 | Completed | 2025-05-20 | Subash | 28
156 | 19/0 | 3DD45+0 | WET | 2025-05-15 | 72.72 | Completed | 2025-05-22 | Khatun | 27
157 | 36/6 | 3DA+3 | DFR | 2025-05-11 | 37.93 | Completed | 2025-05-24 | Hassan | 28
158 | 10/3 | 3DA+3 | DFR | 2025-05-21 | 37.93 | Completed | 2025-05-28 | Subash | 28
159 | 35/1 | 3DA+0 | DFR | 2025-05-08 | 36.37 | Completed | 2025-05-31 | Hassan | 25
160 | 10/5 | 3DA+3 | DFR | 2025-05-29 | 37.93 | Completed | 2025-06-02 | Subash | 25
161 | 17/0 | 3DC1+0 | WBC | 2025-05-10 | 62.535 | Completed | 2025-06-04 | Praveen | 28
162 | 31/3 | 3DA-3 | WFR | 2025-06-01 | 34.946 | Completed | 2025-06-06 | Hassan | 28
163 | 30/0 | 3DC1+6 | DFR | 2025-06-03 | 71.7057 | Completed | 2025-06-11 | Subash | 30
164 | 33/2 | 3DA-3 | DFR | 2025-06-05 | 34.946 | Completed | 2025-06-16 | Hassan | 27
165 | 29/9 | 3DB1+9 | DFR | 2025-06-06 | 64.891 | Completed | 2025-06-18 | Subash | 28
166 | 21/5 | 3DA-3 | WFR | 2025-06-05 | 34.946 | Completed | 2025-06-19 | Praveen | 28
167 | 10/6 | 3DA+6 | DFR | 2025-06-19 | 43.08 | Completed | 2025-06-24 | Subash | 25
168 | 34/0 | 3DC1+0 | DFR | 2025-06-17 | 62.535 | Completed | 2025-06-25 | Hassan | 29
169 | 11/2 | 3DA+0 | WBC | 2025-06-25 | 36.372 | Completed | 2025-06-28 | Subash | 28
170 | 11/3 | 3DA-3 | WBC | 2025-06-29 | 34.946 | Completed | 2025-07-02 | Subash | 27
171 | 15/0 | 3DD45+3 | WET | 2025-06-24 | 76.193 | Completed | 2025-07-04 | Naziruddin | 30
172 | 35/2 | 3DA+0 | DFR | 2025-06-25 | 36.372 | Completed | 2025-07-04 | Hassan | 28
173 | 39/4 | 3DA+3 | DFR | 2025-06-24 | 37.931 | Completed | 2025-07-05 | Hassan-2 | 27
174 | 20A/0 | 3DB2+0 | DFR | 2025-06-20 | 54.66 | Completed | 2025-07-07 | Praveen | 28
175 | 10/0 | 3DB2+0 | DFR | 2025-07-03 | 54.66 | Completed | 2025-07-07 | Subash | 28
176 | 6/5 | 2DA+0 | DFR | 2025-07-04 | 31.99 | Completed | 2025-07-10 | Khatun | 24
177 | 9/10 | 2DA+3 | DFR | 08-07-2025 | 33.38 | Completed | 2025-07-12 | Subash | 27
178 | 39/3 | 3DA+3 | DFR | 2025-07-06 | 37.931 | Completed | 2025-07-12 | Hassan-2 | 24
179 | 14/0 | 3DC2+6 | WET | 05-07-2025 | 71.706 | Completed | 2025-07-13 | Naziruddin | 26
180 | 6/4 | 2DA+0 | DFR | 2025-07-11 | 31.99 | Completed | 2025-07-15 | Khatun | 27
181 | 34/2 | 3DB1+6 | DFR | 2025-07-05 | 63.16 | Completed | 2025-07-16 | Hassan | 25
182 | 9/8 | 2DA+0 | DFR | 2025-07-13 | 31.99 | Completed | 2025-07-16 | Subash | 26
183 | 6/3 | 2DA+0 | DFR | 2025-07-15 | 31.99 | Completed | 2025-07-18 | Khatun | 25
184 | 9/7 | 2DA+3 | DFR | 2025-07-17 | 33.3756 | Completed | 2025-07-20 | Subash | 23
185 | 42/4 | 3DA+3 | DFR | 2025-07-12 | 37.931 | Completed | 2025-07-20 | D k Verma | 25
186 | 8/6 | 2DA+0 | DFR | 2025-07-14 | 31.99 | Completed | 2025-07-21 | Naziruddin | 24
187 | 6/2 | 2DA+0 | DFR | 2025-07-19 | 31.99 | Completed | 2025-07-21 | Khatun | 24
188 | 9/6 | 2DA+3 | DFR | 2025-07-21 | 33.38 | Completed | 2025-07-25 | Subash | 25
189 | 6/1 | 2DA+3 | DFR | 2025-07-22 | 33.38 | Completed | 2025-07-28 | Khatun | 25
190 | 8/14 | 2DA+3 | DFR | 2025-07-22 | 33.38 | Completed | 2025-07-29 | Naziruddin | 24
191 | 42/3 | 3DA+3 | WFR | 2025-07-21 | 37.931 | Completed | 2025-07-29 | D K Verma | 24
192 | 39/0 | 3DC1+3 | DFR | 2025-07-13 | 65.22 | Completed | 2025-07-30 | Hassan -2 | 25
193 | 9/5 | 2DA+0 | DFR | 2025-07-26 | 31.99 | Completed | 2025-07-31 | Subash | 24
194 | 4/21 | 2DA+3 | DFR | 2025-07-29 | 33.38 | Completed | 2025-08-01 | Khatun | 24
195 | 16/7 | 3DA-3 | WET | 2025-07-08 | 34.946 | Completed | 2025-08-02 | Praveen | 25
196 | 8/8 | 2DA+0 | DFR | 2025-07-30 | 31.99 | Completed | 2025-08-02 | Naziruddin | 25
197 | 35/0 | 3DB1+9 | DFR | 2025-07-17 | 64.89 | Completed | 2025-08-03 | Hassan | 24
198 | 6/6 | 2DA+0 | DFR | 2025-08-02 | 31.99 | Completed | 2025-08-04 | Khatun | 24
199 | 42/5 | 3DA+3 | DFR | 2025-07-30 | 37.931 | Completed | 2025-08-04 | D K Verma | 24
200 | 11/0 | 3DC1+0 | DFR | 2025-08-01 | 62.535 | Completed | 2025-08-06 | Subash | 24
201 | 8/7 | 2DA+3 | DFR | 2025-08-03 | 33.38 | Completed | 2025-08-07 | Naziruddin | 25
202 | 8/13 | 2DA+3 | DFR | 2025-08-05 | 33.38 | Completed | 2025-08-08 | Khatun | 24
203 | 4/23 | 2DA+0 | DFR | 2025-08-09 | 31.99 | Completed | 2025-08-11 | Khatun | 24
204 | 10/8 | 3DA+3 | DFR | 2025-08-07 | 37.931 | Completed | 2025-08-12 | Subash | 25
205 | 34/1 | 3DB1+0 | DFR | 2025-08-04 | 54.66 | Completed | 2025-08-12 | Hassan | 25
206 | 8/12 | 2DA+0 | DFR | 2025-08-08 | 31.99 | Completed | 2025-08-13 | Naziruddin | 25
207 | 42/6 | 3DA+0 | DFR | 2025-08-05 | 36.37 | Completed | 2025-08-14 | D k Verma | 24
208 | 9/4 | 2DA+0 | DFR | 2025-08-13 | 31.99 | Completed | 2025-08-18 | Subash | 30
209 | 9/1 | 2DA+3 | DFR | 2025-08-12 | 33.38 | Completed | 2025-08-19 | Khatun | 25
210 | 42/7 | 3DA+9 | DFR | 2025-08-16 | 44.825 | Completed | 2025-08-24 | D k Verma | 36
211 | 12/1 | 3DA+3 | WFR | 2025-08-23 | 37.931 | Completed | 2025-08-29 | Subash | 30
212 | 40/0 | 3DB2+9 | DFR | 2025-08-13 | 64.891 | Completed | 2025-08-29 | Hassan | 30
213 | 1A/0 | 2DD45+0 | DFR | 2025-08-20 | 66.21 | Completed | 2025-08-30 | Khatun | 29
214 | 9/0 | 2DB1+0 | DFR | 2025-08-14 | 51.04 | Completed | 2025-08-30 | Naziruddin | 25
215 | 9/2 | 2DA+0 | DFR | 2025-08-19 | 31.99 | Completed | 2025-08-31 | Subash | 30
216 | 42/1 | 3DA+6 | DFR | 2025-08-25 | 43.08 | Completed | 2025-08-31 | D k Verma | 36
217 | 2/3 | 2DA+0 | DFR | 2025-08-31 | 31.99 | Completed | 2025-09-03 | Shakila Khatun | 32
218 | 9/9 | 2DA+0 | DFR | 2025-09-01 | 31.99 | Completed | 2025-09-04 | Subash | 35
219 | 40/1 | 3DA+9(2mRC) | DFR | 2025-08-30 | 44.825 | Completed | 2025-09-05 | Hassan | 25
220 | 42/8 | 3DA+9(2mRC) | DFR | 2025-09-01 | 44.825 | Completed | 2025-09-06 | D k Verma | 34
221 | 8/15 | 2DA+3 | DFR | 2025-08-31 | 33.38 | Completed | 2025-09-07 | Naziruddin | 25
222 | 4/6 | 2DA+0 | DFR | 2025-09-05 | 31.99 | Completed | 2025-09-07 | Subash | 35
223 | 4/0 | 2DB2+0 | DFR | 2025-09-05 | 51.04 | Completed | 2025-09-08 | Shakila Khatun | 34
224 | 39/5 | 3DA+3 | DFR | 2025-08-08 | 37.931 | Completed | 2025-09-08 | Praveen | 25
225 | 4/7 | 2DA+3 | DFR | 2025-09-08 | 33.38 | Completed | 2025-09-09 | Subash | 35
226 | 42/9 | 3DA+3 | DFR | 2025-09-07 | 37.931 | Completed | 2025-09-10 | D k Verma | 31
227 | 41/0 | 3DC1+0 | WET | 2025-09-06 | 62.535 | Completed | 2025-09-13 | Hassan | 25
228 | 4/9 | 2DA+0 | DFR | 2025-09-10 | 31.99 | Completed | 2025-09-14 | Subash | 35
229 | 8/9 | 2DA+3 | DFR | 2025-09-08 | 33.38 | Completed | 2025-09-15 | Naziruddin | 25
230 | 4/12 | 2DB1+0 | DFR | 2025-09-09 | 51.04 | Completed | 2025-09-16 | Khatun | 34
231 | 4/10 | 2DA+3 | DFR | 2025-09-14 | 33.38 | Completed | 2025-09-20 | Subash | 35
232 | 42/0 | 3DB1+9 | DFR | 2025-09-13 | 64.89 | Completed | 2025-09-23 | D k Verma | 34
233 | 4/2 | 2DA+3 | DFR | 2025-09-21 | 33.38 | Completed | 2025-09-24 | Subash | 35
234 | 39/1 | 3DA+6 | WFR | 2025-09-16 | 43.079 | Completed | 2025-09-25 | Hassan | 34
235 | 4/17 | 2DA+3 | DFR | 2025-09-16 | 33.38 | Completed | 2025-09-26 | Naziruddin | 25
236 | 5/0 | 2DD45+6 | DFR | 2025-09-21 | 77.32 | Completed | 2025-09-29 | Khatun | 28
237 | 43/2 | 3DA-3 | DFR | 2025-09-24 | 34.946 | Completed | 2025-09-30 | D k Verma | 34
238 | 2/2 | 2DA+0 | DFR | 2025-09-25 | 31.99 | Completed | 2025-09-30 | Subash | 35
239 | 4/18 | 2DA+0 | DFR | 2025-09-28 | 31.99 | Completed | 2025-10-04 | Khatun | 25
240 | 43/4 | 3DA+3 | DFR | 2025-09-21 | 37.931 | Completed | 2025-10-06 | Yadhav + D k Verma | 32
241 | 1/0 | 2DD60+0 | DFR | 2025-10-01 | 72.63 | Completed | 2025-10-09 | Subash | 35
242 | 39/2 | 3DA+0 | WBC | 2025-09-27 | 36.37 | Completed | 2025-10-09 | Hassan | 34
243 | 39/7 | 3DA+6 | WFR | 2025-09-13 | 43.079 | Completed | 2025-10-11 | Praveen | 21
244 | 43/3 | 3DA+0 | DFR | 2025-10-07 | 36.37 | Completed | 2025-10-11 | D k Verma | 34
245 | 9/3 | 2DA+9 | DFR | 2025-10-07 | 39.17 | Completed | 2025-10-12 | Khatun | 25
246 | 4/3 | 2DA+6 | DFR | 2025-10-10 | 37.72 | Completed | 2025-10-15 | Subash | 35
247 | 43/5 | 3DA+9(2mRC) | DFR | 2025-10-12 | 44.851 | Completed | 2025-10-16 | D k Verma | 34
248 | 4/20 | 2DA+9 | DFR | 2025-10-13 | 39.17 | Completed | 2025-10-17 | Khatun | 25
249 | 36/7 | 3DA+3 | WFR | 2025-10-10 | 37.931 | Completed | 2025-10-19 | Hassan | 34
250 | 4/4 | 2DA+0 | DFR | 2025-10-17 | 31.99 | Completed | 2025-10-21 | Subash | 35
251 | 42/2 | 3DA+0 | DFR | 2025-10-17 | 36.371 | Completed | 2025-10-21 | D k Verma | 34
252 | 4/19 | 2DA+6 | DFR | 2025-10-17 | 37.72 | Completed | 2025-10-22 | Khatun | 25
253 | 41/1 | 3DA+0 | WET | 2025-10-22 | 36.371 | Completed | 2025-10-25 | D k Verma | 34
254 | 11/4 | 3DA+0 | DFR | 2025-10-23 | 36.37 | Completed | 2025-10-27 | Khatun | 25
255 | 39/6 | 3DA+0 | WFR | 2025-10-14 | 36.37 | Completed | 2025-10-27 | Praveen | 22
256 | 4/1 | 2DA+3 | DFR | 2025-10-22 | 33.38 | Completed | 2025-10-30 | Subash | 35
257 | 11/7 | 3DA+0 | WET | 2025-10-28 | 36.37 | Completed | 2025-11-02 | Khatun | 25
258 | 43/1 | 3DA+3 | WFR | 2025-10-26 | 37.931 | Completed | 2025-11-02 | D k Verma | 34
259 | 36/8 | 3DA+0 | WFR | 2025-10-21 | 36.37 | Completed | 2025-11-02 | Hassan | 24
260 | 4/13 | 2DA+0 | DFR | 2025-10-31 | 31.99 | Completed | 2025-11-05 | Subash | 22

## SuPPLY
Supply Status - Stubs & Towers
Stub Details
SL No | Description | Unit | Line Qty | Received | Balance | Telangana | Karnataka
1 | 3DA Stub | Set | 190 | 190 | 0 | 169 | 21
2 | 3DB Stub | Set | 23 | 23 | 0 | 22 | 1
3 | 3DC Stub | Set | 13 | 13 | 0 | 12 | 1
4 | 3D45 Stub | Set | 7 | 7 | 0 | 6 | 1
5 | 3D6o Stub | Set | 1 | 1 | 0 | 1
6 | 2DA Stub | Set | 61 | 61 | 0 |  | 61
7 | 2DB Stub | Set | 11 | 11 | 0 |  | 11
7 | 2D45 Stub | Set | 4 | 4 | 0 |  | 4
8 | 2DC Stub | Set |  |  | 0
9 | 2D6o Stub | Set | 2 | 2 | 0 |  | 2
| Total | Set | 312 | 312 | 0 | 210 | 102
Tower Details
SL No | Tower Type | Description | Line Qty | Received | Balance | Telangana | Karnataka | Remarks
1 | 3DA Type | Basic body | 190 | 190 | 0 | 172 | 18
|  | +0m BE | 99 | 99 | 0 | 90 | 9
|  | +3m BE | 57 | 57 | 0 | 51 | 6
|  | +6m BE | 21 | 21 | 0 | 19 | 2
|  | +9m BE | 7 | 7 | 0 | 7
|  | -3m BE | 6 | 6 | 0 | 5 | 1 |  | Further Plan in 0ct '25
2 | 3DB Type | Basic body | 23 | 23 | 0 | 23 | 1 |  | Tower : 1 No's
|  | +0m BE | 16 | 16 | 0 | 15 | 1
|  | +3m BE | 1 | 1 | 0 | 1
|  | +6m BE | 1 | 1 | 0 | 1 |  |  |  | 3DC+0 (TP Tower ) - 01 No under Transit
|  | +9m BE | 5 | 5 | 0 | 5
-3m BE
3 | 3DC Type | Basic body | 13 | 12 | 1 | 9 | 1
|  | +0m BE | 8 | 8 | 0 | 7 | 1
|  | +3m BE | 2 | 2 | 0 | 2
|  | +6m BE | 2 | 2 | 0 | 2
|  | +0 TP T0wer | 1 | 1 | 1 | 0
-3m BE
3 | 3D45 Type | Basic body | 7 | 7 | 0 | 4 | 1
|  | +0m BE | 3 | 3 | 0 | 3
|  | +3m BE | 2 | 2 | 0 | 1 | 1
|  | +6m BE | 1 | 1 | 0 | 1
|  | +9m BE | 1 | 1 | 1 | 1
-3m BE
4 | 3DD60+3 | Basic body | 1 | 1 | 0 | 1
|  | +3m BE | 1 | 1 | 0 | 1
5 | 2DA Type | Basic body | 61 | 56 | 5 |  | 45
|  | +0m BE | 31 | 31 | 0 |  | 31
|  | +3m BE | 21 | 21 | 0 |  | 21
|  | +6m BE | 5 | 5 | 0 |  | 5
|  | +9m BE | 4 | 4 | 0 |  | 4
|  | -3m BE |  |  | 0
5 | 2DB Type | Basic body | 11 | 11 | 0 |  | 11
|  | +0m BE | 3 | 3 | 0 |  | 3
|  | +3m BE | 2 | 2 | 0 |  | 2
|  | +6m BE | 4 | 4 | 0 |  | 4
|  | +9m BE | 2 | 2 | 0 |  | 2
-3m BE
6 | 2DD45 Type | Basic body | 4 | 4 |  |  | 4
|  | +0m BE | 2 | 2 |  |  | 2
+3m BE
|  | +6m BE | 2 | 2 |  |  | 2
+9m BE
-3m BE
7 | 2DD60 Type | Basic body | 2 | 2 |  |  | 2
|  | +0m BE | 2 | 2 |  |  | 2
|  | Total |  | 311 | 1
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | Set | 312 | 312 | 312 | 0 |  |  |  | 312 | 0
Tower | No's | 312 | 312 | 311 | 1 |  | 1 | 1 | 312 | 0
Cummulative progress till Previous Month
S No | Item | Unit | Total QTY | Planned L2 till Previous Month (0ctober'25) | Completed till Previous month (0ctober25) | L2 Planned for Current Month (Approved L2) | Balance after 0ctober'25 | November '25 Month Plan | November Month Progress | Cummulative Completed | Balance
1 | Supply of Stubs | Sets | 312 | 312 | 312 |  | 0 |  |  | 312 | 0
2 | Supply of Towers | Nos | 312 | 312 | 311 |  | 1 | 01 no under Transit | 1 | 312 | 0
3 | Supply of Earthwire | Km | 126.189 | 126.189 | 122.01 |  | 4.179 | 4.18 |  | 122.01 | 4.179
5 | Supply of Conductor | Km | 4412 | 4412 | 4330.244 |  | 81.756 | 81.8 |  | 4330.244 | 81.756
6 | Supply of H/W Fittings | % | 100% | 100% | 97.57% |  | 2.43% | 2% |  | 97.57% | 2.43%
7 | Supply of Insultor | Nos | 12246 | 12246 | 11776 |  | 470 | 470 |  | 11776 | 470
8 | Supply of OPGW | km | 127.56 | 127.56 | 84.617 |  | 42.943 | 42.94 | 42.927 | 127.544 | 0.016
9 | Supply of OPGW Accessories | % | 100% | 100% | 60% |  | 40% | 40% |  | 60% | 40%
9 | Supply of Earthing Materials | % | 100% | 100% | 100% |  | 0% |  |  | 100% | 0%
10 | Supply of Earthwire Accessories | % | 100% | 100% | 97.65% |  | 2.35% | 2.4% |  | 97.65% | 2.35%
11 | Supply of Tower Accessories | % | 100% | 100% | 100% |  | 0% |  |  | 100% | 0%
12 | Supply of Conductor Accessories | % | 100% | 100% | 95% |  | 5% | 5% |  | 95% | 5%
14
15
16
17
18

## Visual Chart
VISUAL PROGRESS CHART
765 KV D/C Bidar - Maheshwaram Transmission Line TL-01
| Foundation (Nos.):- |  | 307 | / 309 | Erection (Nos.):- |  | 260 | / 309 | Earthing (Nos.):- |  | 289 | / 309 | Rough Sag (Kms):- |  | 43.742 | /121.342 | Final Sag (Kms):- |  | 43.742 | /121.342 | Date:- | 2025-11-06
| COMPLETION CHART | -3 | +0 | +3 | +6 | +9 | Total | Line Qty
[9 empty] | ERECTION | [5 empty] | Rough Sag |  | SH / NH Road Crossing
| DA | 1 | 2 | 3 | 4 |  |  |  | WIP | [11 empty] | River
| DA | 6 | 130 | 78 | 24 | 11 | 249 | 249 |  | Type |  | Angle Tower |  |  |  |  | Gas Pipeline
| DB1 |  | 8 | 1 | 4 | 5 | 18 | 18 | FOUNDATION
| DB2 |  | 11 | 2 | 1 |  | 14 | 15 | [5 empty] | Final Sag
| DC1 |  | 8 | 1 | 1 |  | 11 | 11
| DC2 |  |  |  | 1 |  | 1 | 1 | [9 empty] | Railway
| DCT |  | 1 |  |  |  | 1 | 1 | [7 empty] | WIP
| DD45 |  | 3 | 1 | 4 | 1 | 9 | 11 | Section Tower | SC | [7 empty] | Crossing |  |  | 110-800 KV
| DD60 |  | 1 | 1 |  |  | 2 | 3 | TP | TT |  | Earthing |  |  | OPGW | [5 empty] | Line
| Total Completed Foundations | [5 empty] | 307 | 309
| Windzone -2[Gantry - 9/10] | [12 empty] | 110kv OHTL
SH -122
99.97 |  | 234.53 |  | 397.2 |  | 436 |  | 405 |  | 399 |  | 446.01 |  | 309.77 |  | 394 |  | 396 |  | 370 |  | 383 |  | 405
GANTRY | 1 |  | 1A/0 |  | 1B/0 |  | 1B/1 |  | 1B/2 |  | 1B/3 |  | 1C/0 |  | 2/0 |  | 2/1 |  | 2/2 |  | 2/3 |  | 2/4
| 2DD60+0 |  | 2DD45+0 |  | DB2+3 |  | DA+6 |  | DA+3 |  | DA+0 |  | DB1+9 |  | DB2+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
|  | 416.52 |  | 426 |  | 419 |  | 429 |  | 406.96 |  | 416 |  | 367 |  | 440 |  | 407 |  | 426 |  | 404 |  | 397
| 2/5 |  | 3/0 |  | 3/1 |  | 3/2 |  | 3/3 |  | 4/0 |  | 4/1 |  | 4/2 |  | 4/3 |  | 4/4 |  | 4/5 |  | 4/6
| DA+0 |  | DB2+3 |  | DA+9 |  | DA+9 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+0
|  | 450 |  | 398 |  | 417 |  | 431 |  | 415 |  | 424 |  | 417 |  | 422 |  | 406 |  | 407 |  | 420 |  | 409
| 4/7 |  | 4/8 |  | 4/9 |  | 4/10 |  | 4/11 |  | 4/12 |  | 4/13 |  | 4/14 |  | 4/15 |  | 4/16 |  | 4/17 |  | 4/18
| DA+3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DB1+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
110 kv S/C D/C
|  | 439 |  | 407 |  | 441 |  | 312 |  | 460 |  | 181.66 |  | 428 |  | 418 |  | 401 |  | 382 |  | 463 |  | 385
| 4/19 |  | 4/20 |  | 4/21 |  | 4/22 |  | 4/23 |  | 5/0 |  | 6/0 |  | 6/1 |  | 6/2 |  | 6/3 |  | 6/4 |  | 6/5
| DA+6 |  | DA+9 |  | DA+3 |  | DA+6 |  | DA+0 |  | DD45+6 |  | DD45+6 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
[10 empty] | 110KV S/C OHTL |  |  |  | 110KV S/C OHTL
NH-161A
|  | 399 |  | 417.59 |  | 225.68 |  | 414 |  | 272 |  | 406 |  | 337 |  | 425 |  | 397 |  | 408 |  | 426 |  | 407
| 6/6 |  | 6/7 |  | 7/0 |  | 8/0 |  | 8/1 |  | 8/2 |  | 8/3 |  | 8/4 |  | 8/5 |  | 8/6 |  | 8/7 |  | 8/8
| DA+0 |  | DA+3 |  | DD45+0 |  | DD60+0 |  | DB1+6 |  | DB1+6 |  | DB1+9 |  | DB1+6 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
|  | 402 |  | 383 |  | 416 |  | 423 |  | 409 |  | 432 |  | 405.18 |  | 438 |  | 408 |  | 413 |  | 415 |  | 428
| 8/9 |  | 8/10 |  | 8/11 |  | 8/12 |  | 8/13 |  | 8/14 |  | 8/15 |  | 9/0 |  | 9/1 |  | 9/2 |  | 9/3 |  | 9/4
| DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+0
WINDZONE -03 STARTS
|  | 418 |  | 406 |  | 413 |  | 423 |  | 425 |  | 411.43 |  | 406 |  | 420 |  | 408 |  | 426 |  | 416 |  | 426
| 9/5 |  | 9/6 |  | 9/7 |  | 9/8 |  | 9/9 |  | 9/10 |  | 10/0 |  | 10/1 |  | 10/2 |  | 10/3 |  | 10/4 |  | 10/5
| DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | 3DB2+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3
|  | 413 |  | 429 |  | 356 |  | 424.52 |  | 389 |  | 406 |  | 402 |  | 405 |  | 400 |  | 379 |  | 386 |  | 366
| 10/6 |  | 10/7 |  | 10/8 |  | 10/9 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 11/4 |  | 11/5 |  | 11/6 |  | 11/7
| DA+6 |  | DA+3 |  | DA+3 |  | DA+6 |  | DC1+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0
|  | 421 |  | 418 |  | 417 |  | 361.99 |  | 416 |  | 416 |  | 425 |  | 403 |  | 400 |  | 441 |  | 392 |  | 403
| 11/8 |  | 11/9 |  | 11/10 |  | 11/11 |  | 12/0 |  | 12/1 |  | 12/2 |  | 12/3 |  | 12/4 |  | 12/5 |  | 12/6 |  | 12/7
| DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0
|  | 413 |  | 428 |  | 413 |  | 429.53 |  | 425 |  | 418 |  | 415 |  | 428 |  | 402 |  | 419 |  | 422 |  | 418
| 12/8 |  | 12/9 |  | 12/10 |  | 12/11 |  | 13/0 |  | 13/1 |  | 13/2 |  | 13/3 |  | 13/4 |  | 13/5 |  | 13/6 |  | 13/7
| DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DB1+0 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+6
Manjira River
Manjira River
|  | 421 |  | 384 |  | 370 |  | 378.13 |  | 497.56 |  | 300 |  | 415 |  | 408 |  | 402 |  | 384.49 |  | 389 |  | 370
| 13/8 |  | 13/9 |  | 13/10 |  | 13/11 |  | 14/0 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3 |  | 15/4 |  | 16/0 |  | 16/1
| DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DC2+6 |  | DD45+3 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DD45+0 |  | DA+0
|  | 402 |  | 410 |  | 394 |  | 410 |  | 362 |  | 372 |  | 412 |  | 410 |  | 431 |  | 400.31 |  | 258 |  | 437
| 16/2 |  | 16/3 |  | 16/4 |  | 16/5 |  | 16/6 |  | 16/7 |  | 16/8 |  | 16/9 |  | 16/10 |  | 16/11 |  | 17/0 |  | 17/1
| DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DC1+0 |  | DA+3
[14 empty] | Manjira River | [7 empty] | NH-161B
|  | 406 |  | 437.7 |  | 367 |  | 400 |  | 409 |  | 388.17 |  | 441 |  | 402 |  | 384 |  | 412.61 |  | 205.21 |  | 208
| 17/2 |  | 17/3 |  | 18/0 |  | 18/1 |  | 18/2 |  | 18/3 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 20/0 |  | 20A/0
| DA+3 |  | DA+6 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DD45+0 |  | DA+6 |  | DA+0 |  | DA+3 |  | DB1+0 |  | DB2+0
|  | 372 |  | 384 |  | 376 |  | 468 |  | 370 |  | 473 |  | 364 |  | 342 |  | 366 |  | 352 |  | 381 |  | 400
| 21/0 |  | 21/1 |  | 21/2 |  | 21/3 |  | 21/4 |  | 21/5 |  | 21/6 |  | 21/7 |  | 21/8 |  | 21/9 |  | 22/0 |  | 22/1
| DD45+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0
|  | 415 |  | 394 |  | 362 |  | 386 |  | 425 |  | 412 |  | 337 |  | 323 |  | 329 |  | 315 |  | 465 |  | 374
| 22/2 |  | 22/3 |  | 22/4 |  | 22/5 |  | 23/0 |  | 23/1 |  | 23/2 |  | 23/3 |  | 23/4 |  | 24/0 |  | 24/1 |  | 24/2
| DA+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+6 |  | DA+3
|  | 344 |  | 371 |  | 386 |  | 366 |  | 412 |  | 373 |  | 300 |  | 361 |  | 427 |  | 389 |  | 405 |  | 397
| 24/3 |  | 24/4 |  | 24/5 |  | 24/6 |  | 24/7 |  | 24/8 |  | 25/0 |  | 25/1 |  | 25/2 |  | 25/3 |  | 25/4 |  | 25/5
| DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6
|  | 344 |  | 421 |  | 369 |  | 404 |  | 376 |  | 397 |  | 400 |  | 382 |  | 346 |  | 366 |  | 366 |  | 408
| 26/0 |  | 26/1 |  | 26/2 |  | 26/3 |  | 26/4 |  | 27/0 |  | 27/1 |  | 27/2 |  | 27/3 |  | 27/4 |  | 27/5 |  | 27/6
| DB2+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DB1+0 |  | DA+0 |  | DA+0 |  | DC1+0(TP) |  | DA+0 |  | DA+0 |  | DA+0
|  | 379 |  | 412 |  | 403 |  | 303 |  | 483 |  | 413 |  | 397 |  | 355 |  | 366 |  | 396 |  | 405 |  | 380
| 27/7 |  | 27/8 |  | 27/9 |  | 28/0 |  | 28/1 |  | 29/0 |  | 29/1 |  | 29/2 |  | 29/3 |  | 29/4 |  | 29/5 |  | 29/6
| DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+9 |  | DC1+0 |  | DA+9 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DA+0
|  | 427 |  | 416 |  | 508 |  | 316 |  | 449 |  | 394 |  | 422 |  | 404 |  | 398 |  | 393 |  | 378 |  | 368
| 29/7 |  | 29/8 |  | 29/9 |  | 30/0 |  | 30/1 |  | 30/2 |  | 30/3 |  | 30/4 |  | 30/5 |  | 31/0 |  | 31/1 |  | 31/2
| DA+3 |  | DA+0 |  | DB1+9 |  | DC1+6 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0
NH-65
.
|  | 361 |  | 368 |  | 453 |  | 368 |  | 369 |  | 424 |  | 383 |  | 459 |  | 324 |  | 347 |  | 295 |  | 248
| 31/3 |  | 31/4 |  | 31/5 |  | 31/6 |  | 32/0 |  | 32/1 |  | 32/2 |  | 32/3 |  | 33/0 |  | 33/1 |  | 33/2 |  | 34/0
| DA-3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC1+0 |  | DA+0 |  | DA+3 |  | DA+6 |  | 3DD45+6 |  | DA+0 |  | DA-3 |  | DC1+0
|  |  |  | 132 KV T/L | [9 empty] | Gas PipeLine
|  | 430 |  | 248 |  | 430 |  | 412 |  | 278 |  | 321 |  | 417 |  | 410 |  | 375 |  | 423 |  | 419 |  | 411
| 34/1 |  | 34/2 |  | 35/0 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 36/0 |  | 36/1 |  | 36/2 |  | 36/3 |  | 36/4
| DB1+0 |  | DB1+6 |  | DB1+9 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6 |  | DD60+3 |  | DA+0 |  | DA+3 |  | DA+3 |  | DA+3
|  | 413 |  | 409 |  | 422 |  | 326 |  | 407 |  | 390 |  | 433 |  | 409 |  | 400 |  | 362 |  | 378 |  | 367
| 36/5 |  | 36/6 |  | 36/7 |  | 36/8 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 37/4 |  | 37/5 |  | 37/6 |  | 38/0
| DA+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DB2+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+6 |  | DA+0 |  | DA+0 |  | DC1+0
|  | 357 |  | 390 |  | 410 |  | 370 |  | 335 |  | 405 |  | 402 |  | 432 |  | 408 |  | 421 |  | 419 |  | 423
| 38/1 |  | 38/2 |  | 38/3 |  | 38/4 |  | 38/5 |  | 38/6 |  | 38/7 |  | 39/0 |  | 39/1 |  | 39/2 |  | 39/3 |  | 39/4
| DA+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC1+3 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+3
|  | 420 |  | 418 |  | 425 |  | 416 |  | 428 |  | 411 |  | 302 |  | 324 |  | 438 |  | 320 |  | 427 |  | 413
| 39/5 |  | 39/6 |  | 39/7 |  | 39/8 |  | 39/9 |  | 40/0 |  | 40/1 |  | 41/0 |  | 41/1 |  | 42/0 |  | 42/1 |  | 42/2
| DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+9 |  | DB2+9 |  | DA+9(2MRC) |  | DC1+0 |  | DA+0 |  | DB1+9 |  | DA+6 |  | DA+0
|  | 398 |  | 438 |  | 387 |  | 408 |  | 433 |  | 376 |  | 349 |  | 413 |  | 398 |  | 362 |  | 341 |  | 410
| 42/3 |  | 42/4 |  | 42/5 |  | 42/6 |  | 42/7 |  | 42/8 |  | 42/9 |  | 43/0 |  | 43/1 |  | 43/2 |  | 43/3 |  | 43/4
| DA+3 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+9 |  | DA+9 |  | DA+3 |  | DB2+0 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA+3
|  | 337.75 |  | 485 |  | 292 |  | 322 |  | 471 |  | 368 |  | 421.04 |  | 459.69
| 43/5 |  | 43A/0 |  | 43A/1 |  | 43A/2 |  | 43A/3 |  | 43A/4 |  | 43A/5 |  | 43B/0 |  | 44/0
| DA+9 |  | DD45+9 |  | DB1+3 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+3 |  | DB1+9 |  | 3DD45+3

## X-ing Details
CROSSINGS PROPOSAL STATUS : 765 KV D/C Bidar PS - Maheshwaram (PG) TL01
Crossing Type | 110kV | 132 KV | 400kV | 765kV | SH-Xing | NH-Xing | Gas Pipeline Xing | Total | Remarks
Total Nos | 4 | 1 | 0 | 0 |  | 3 | 1 | 9
Submitted Till Date | 4 | 1 | 0 | 0 | 0 | 3 | 1 | 9
Approved Till Date | 4 | 1 | 0 | 0 | 0 | 3 | 1 | 9
Balance to Execute | 0 | 0 | 0 | 0 | 0 | 0
Crossings Details
Sl. No. | FROM (AP) | TO (AP) | Name of the Line | NAME OF CROSSING | Date of First Submission | Joint Inspection Status | Provisional approval status
1 | 1C/0 | 2/0 | 110kV S/C (D/C Towers) Dongargoan SS to Kamalnagar SS - T/L | Power line | 2025-03-29 | Completed | Approval obtained
2 | 5/0 | 6/0 | 110kV S/C (D/C Towers) Santhpur - Dongargoan SS | Power line | 2025-03-29 | Completed | Approval obtained
3 | 8/1 | 8/2 | 110kV S/C OHTL Santhpur - Solarplant | Power line | 2024-09-17 | Completed | Approval obtained
4 | 8/3 | 8/4 | 110kV S/C OHTL Santhpur - Solarplant | Power line | 2024-09-17 | Completed | Approval obtained
5 | 34/2 | 35/0 | 132 KV OHTL Zaheerabad - sadashivpet | Power line | 2024-11-04 | Completed | Approval obtained
6 | 7/0 | 8/0 | NH - 161A(Bidar - Nanded) | NH | 2024-10-01 | Completed | Approval obtained on 22.05.25
7 | 20/0 | 20A/0 | NH - 161B(Bidar - Nizampet) | NH | 2024-10-01 | Completed | Approval obtained
8 | 34/0 | 34/1 | NH - 65 (Pune - Vijayawada) | NH | 2024-11-04 | Completed | Approval obtained on 22.05.25
9 | 35/4 | 36/0 | Gas Pipeline(Pipeline Infrastructure Limited) | Pipeline Infrastructure Limited | 2024-10-25 | Completed | Approval obtained

## Tack Welding
SL. NO. | LOCATION NO. | TYPE OF TOWER | DATE OF TACKWELDING | Gang Name | Gang Strength | NUMBER OF BOLT & NUT
1 | 23/0 | 3DB2+0 | 2025-05-01 | Ram Reddy & Sons | 4 | 4920
2 | 23/1 | 3DA+6 | 2025-07-01 | Ram Reddy & Sons | 4 | 5972
3 | 23/2 | 3DA+0 | 2025-09-01 | Ram Reddy & Sons | 4 | 4618
4 | 23/3 | 3DA+0 | 2025-11-01 | Ram Reddy & Sons | 4 | 4618
5 | 23/4 | 3DA+0 | 13/1/2025 | Ram Reddy & Sons | 4 | 4618
6 | 24/0 | 3DB1+0 | 15/1/2025 | Ram Reddy & Sons | 4 | 4920
7 | 24/3 | 3DA+0 | 17/1/2025 | Ram Reddy & Sons | 4 | 4618
8 | 24/5 | 3DA+0 | 19/1/2025 | Ram Reddy & Sons | 4 | 4618
9 | 24/6 | 3DA+0 | 21/01/2025 | Ram Reddy & Sons | 4 | 4618
10 | 24/7 | 3DA+0 | 23/01/2025 | Ram Reddy & Sons | 4 | 4618
11 | 24/8 | 3DA+3 | 25/01/2025 | Ram Reddy & Sons | 4 | 4796
12 | 25/0 | 3DB2+0 | 27/01/2025 | Ram Reddy & Sons | 4 | 4920
13 | 25/1 | 3DA+0 | 29/01/2025 | Ram Reddy & Sons | 4 | 4618
14 | 25/2 | 3DA+0 | 31/01/2025 | Ram Reddy & Sons | 4 | 4618
15 | 25/4 | 3DA+0 | 2025-02-02 | Ram Reddy & Sons | 4 | 4618
16 | 26/0 | 3DB2+0 | 2025-04-02 | Ram Reddy & Sons | 4 | 4920
17 | 26/1 | 3DA+0 | 2025-06-02 | Ram Reddy & Sons | 4 | 4618
18 | 26/2 | 3DA+0 | 2025-08-02 | Ram Reddy & Sons | 4 | 4618
19 | 26/3 | 3DA+0 | 2025-10-02 | Ram Reddy & Sons | 4 | 4618
20 | 26/4 | 3DA+0 | 2025-12-02 | Ram Reddy & Sons | 4 | 4618
21 | 27/0 | 3DB1+0 | 14/02/20225 | Ram Reddy & Sons | 4 | 4920
22 | 27/1 | 3DA+0 | 16/02/2025 | Ram Reddy & Sons | 4 | 4618
23 | 27/2 | 3DA+0 | 18/02/2025 | Ram Reddy & Sons | 4 | 4618
24 | 27/4 | 3DA+0 | 20/02/2025 | Ram Reddy & Sons | 4 | 4618
25 | 27/5 | 3DA+0 | 22/02/2025 | Ram Reddy & Sons | 4 | 4618
26 | 27/6 | 3DA+0 | 24/02/2025 | Ram Reddy & Sons | 4 | 4618
27 | 27/7 | 3DA+0 | 26/02/2025 | Ram Reddy & Sons | 4 | 4618
28 | 22/5 | 3DA+0 | 28/02/2025 | Ram Reddy & Sons | 4 | 4618
29 | 27/8 | 3DA+0 | 2025-02-03 | Ram Reddy & Sons | 4 | 4618
30 | 24/2 | 3DA+3 | 2025-04-03 | Ram Reddy & Sons | 4 | 4796
31 | 24/4 | 3DA+0 | 2025-06-03 | Ram Reddy & Sons | 4 | 4618
32 | 24/1 | 3DA+6 | 2025-08-03 | Ram Reddy & Sons | 4 | 5972
33 | 21/9 | 3DA+0 | 2025-10-03 | Ram Reddy & Sons | 4 | 4618
34 | 22/0 | 3DB1+0 | 2025-04-05 | Ali | 4 | 5556
35 | 22/1 | 3DA+0 | 2025-05-05 | Ali | 4 | 4618
36 | 22/3 | 3DA+6 | 2025-07-05 | Ali | 4 | 5972
37 | 22/4 | 3DA+3 | 2025-06-05 | Ali | 4 | 4796
38 | 22/2 | 3DA+0 | 2025-07-05 | Ali | 4 | 4618
39 | 21/8 | 3DA+0 | 2025-08-05 | Ali | 4 | 4618
40 | 21/7 | 3DA+0 | 2025-09-05 | Ali | 4 | 4618
41 | 25/3 | 3DA+0 | 2025-09-05 | Ali | 4 | 4618
42 | 29/1 | 3DA+9 | 2025-10-05 | Ali | 4 | 6376
43 | 25/5 | 3DA+6 | 2025-11-05 | Ali | 4 | 5972
44 | 29/4 | 3DA+0 | 2025-12-05 | Ali | 4 | 4618
45 | 29/2 | 3DA+0 | 13/5/2025 | Ali | 4 | 4618
46 | 29/3 | 3DA+0 | 13/5/2025 | Ali | 4 | 4618
47 | 29/5 | 3DA+3 | 14/5/2025 | Ali | 4 | 4796
48 | 29/6 | 3DA+0 | 14/5/2025 | Ali | 4 | 4618
49 | 29/7 | 3DA+3 | 15/5/2025 | Ali | 4 | 4796
50 | 29/8 | 3DA+0 | 16/5/2025 | Ali | 4 | 4618
51 | 30/1 | 3DA+3 | 17/5/2025 | Ali | 4 | 4796
52 | 30/3 | 3DA+3 | 17/5/2025 | Ali | 4 | 4796
53 | 30/4 | 3DA+3 | 18/5/2025 | Ali | 4 | 4796
54 | 30/5 | 3DA+0 | 18/5/2025 | Ali | 4 | 4618
55 | 29/0 | 3DC1+0 | 19/5/2025 | Ali | 4 | 5428
56 | 31/1 | 3DA+3 | 20/5/2025 | Ali | 4 | 4796
57 | 31/2 | 3DA+0 | 21/5/2025 | Ali | 4 | 4618
58 | 31/4 | 3DA+0 | 22/5/2025 | Ali | 4 | 4618
59 | 32/1 | 3DA+0 | 23/5/2025 | Ali | 4 | 4618
60 | 32/3 | 3DA+6 | 23/5/2025 | Ali | 4 | 4618
61 | 31/6 | 3DA+3 | 21/5/2025 | Ali | 4 | 4796
62 | 31/5 | 3DA+0 | 22/5/2025 | Ali | 4 | 4618
63 | 32/2 | 3DA+3 | 23/5/2025 | Ali | 4 | 4796
64 | 32/0 | 3DC1+0 | 2025-07-09 | Amarendar Reddy | 3 | 5328
65 | 33/0 | 3DD45+6 | 2025-07-10 | Amarendar Reddy | 3 | 7158
66 | 31/3 | 3DA-3 | 2025-07-11 | Amarendar Reddy | 3 | 4355
67 | 31/0 | 3DB2+0 | 2025-07-12 | Amarendar Reddy | 3 | 5495
68 | 29/9 | 3DB1+9 | 2025-07-17 | Amarendar Reddy | 3 | 7326
69 | 30/0 | 3DC1+6 | 2025-07-17 | Amarendar Reddy | 3 | 7196
70 | 30/2 | 3DA+3 | 2025-07-14 | Amarendar Reddy | 3 | 4796
71 | 21/1 | 3DA+0 | 2025-07-17 | Amarendar Reddy | 3 | 4618
72 | 21/2 | 3DA+0 | 2025-07-19 | Amarendar Reddy | 3 | 4618
73 | 21/3 | 3DA+6 | 2025-07-21 | Amarendar Reddy | 3 | 5972
74 | 21/4 | 3DA+3 | 2025-07-21 | Amarendar Reddy | 3 | 5972
75 | 21/5 | 3DA-3 | 2025-07-22 | Amarendar Reddy | 3 | 4355
76 | 21/6 | 3DA+0 | 2025-07-23 | Amarendar Reddy | 3 | 4618
77 | 19/3 | 3DA+3 | 2025-08-12 | Amarendar Reddy | 3 | 4618
78 | 19/1 | 3DA+6 | 2025-08-15 | Amarendar Reddy | 3 | 5972
79 | 19/2 | 3DA+0 | 2025-08-14 | Amarendar Reddy | 3 | 4618
80 | 20A/0 | 3DB2+0 | 2025-08-05 | Amarendar Reddy | 3 | 5495
81 | 20/0 | 3DB1+0 | 2025-08-06 | Amarendar Reddy | 3 | 5495
82 | 13/10 | 3DA+0 | 2025-08-10 | Amarendar Reddy | 3 | 4618
83 | 21/0 | 3DD45+0 | 2025-08-17 | Amarendar Reddy | 3 | 5496
84 | 12/1 | 3DA+3 | 2025-09-03 | Amarendar Reddy | 3 | 4796
85 | 12/2 | 3DA+3 | 2025-09-04 | Amarendar Reddy | 3 | 4796
86 | 12/3 | 3DA+3 | 2025-09-05 | Amarendar Reddy | 3 | 4796
87 | 12/4 | 3DA+3 | 2025-09-06 | Amarendar Reddy | 3 | 4796
88 | 12/5 | 3DA+0 | 2025-09-07 | Amarendar Reddy | 3 | 4618
89 | 12/6 | 3DA+0 | 2025-09-08 | Amarendar Reddy | 3 | 4618
90 | 12/7 | 3DA+0 | 2025-09-09 | Amarendar Reddy | 3 | 4618
91 | 12/8 | 3DA+3 | 2025-09-10 | Amarendar Reddy | 3 | 4796
92 | 12/9 | 3DA+3 | 2025-09-11 | Amarendar Reddy | 3 | 4796
93 | 12/10 | 3DA+0 | 2025-09-12 | Amarendar Reddy | 3 | 4618
94 | 12/11 | 3DA+6 | 2025-09-13 | Amarendar Reddy | 3 | 5972
95 | 17/3 | 3DA+6 | 2025-09-09 | Ali | 4 | 5972
96 | 18/0 | 3DB2+0 | 2025-09-05 | Ali | 4 | 5495
97 | 18/1 | 3DA+0 | 2025-09-06 | Ali | 4 | 4618
98 | 18/2 | 3DA+0 | 2025-09-08 | Ali | 4 | 4618
99 | 18/3 | 3DA+0 | 2025-09-10 | Ali | 4 | 4618
100 | 12/0 | 3DB2+0 | 2025-09-02 | Amarendar Reddy | 3 | 5495
101 | 13/0 | 3DB1+0 | 2025-09-14 | Amarendar Reddy | 3 | 5495
102 | 10/5 | 3DA+3 | 2025-09-15 | Ali | 4 | 4796
103 | 10/9 | 3DA+6 | 2025-09-19 | Ali | 4 | 4796
104 | 10/7 | 3DA+3 | 2025-09-20 | Ali | 4 | 4796
105 | 10/8 | 3DA+3 | 2025-09-20 | Ali | 4 | 4796
106 | 10/1 | 3DA+3 | Completed | Amarendar Reddy | 3 | 4796
107 | 10/3 | 3DA+3 | Completed | Amarendar Reddy | 3 | 4796
108 | 10/4 | 3DA+3 | Completed | Amarendar Reddy | 3 | 4796
109 | 11/0 | 3DC1+0 | Completed | Amarendar Reddy | 3 | 5328
110 | 19/0 | 3DD45+0 | Completed | Ali | 4 | 5496
111 | 10/2 | 3DA+0 | Completed | Ali | 4
112 | 10/0 | 3DB2+0 | Completed | Ali | 4
113 | 9/1 | 2DA+3 | Completed | Ali | 4
114 | 9/2 | 2DA+0 | Completed | Ali | 4
115 | 9/3 | 2DA+9 | Completed | Ali | 4
116 | 9/4 | 2DA+0 | Completed | Ali | 4
117 | 9/5 | 2DA+0 | Completed | Ali | 4
118 | 9/6 | 2DA+3 | Completed | Ali | 4
119 | 9/7 | 2DA+3 | Completed | Ali | 4
120 | 9/8 | 2DA+0 | Completed | Ali | 4
121 | 9/9 | 2DA+0 | Completed | Ali | 4
122 | 9/10 | 2DA+3 | Completed | Ali | 4
123 | 9/0 | 2DB1+0 | Completed | Ali | 5

## Tower Tightening
TOWER NO. | TYPE OF TOWER | Tower Tightening Status | Gang Name | Manpower
Bidar Gantry | Gantry
1/0 | 2DD60+0
1A/0 | 2DD45+0
1B/0 | 2DB2+3
1B/1 | 2DA+6
1B/2 | 2DA+3
1B/3 | 2DA+0
1C/0 | 2DB1+9
2/0 | 2DB2+6
2/1 | 2DA+0
2/2 | 2DA+0
2/3 | 2DA+0
2/4 | 2DA+0
2/5 | 2DA+0
3/0 | 2DB2+3
3/1 | 2DA+9
3/2 | 2DA+9
3/3 | 2DA+0
4/0 | 2DB2+0
4/1 | 2DA+3
4/2 | 2DA+3
4/3 | 2DA+6
4/4 | 2DA+0
4/5 | 2DA+3
4/6 | 2DA+0
4/7 | 2DA+3
4/8 | 2DA+3
4/9 | 2DA+0
4/10 | 2DA+3
4/11 | 2DA+6
4/12 | 2DB1+0
4/13 | 2DA+0
4/14 | 2DA+3
4/15 | 2DA+0
4/16 | 2DA+0
4/17 | 2DA+3
4/18 | 2DA+0
4/19 | 2DA+6
4/20 | 2DA+9
4/21 | 2DA+3
4/22 | 2DA+6
4/23 | 2DA+0
5/0 | 2DD45+6
6/0 | 2DD45+6
6/1 | 2DA+3
6/2 | 2DA+0
6/3 | 2DA+0
6/4 | 2DA+0
6/5 | 2DA+0
6/6 | 2DA+0
6/7 | 2DA+3
7/0 | 2DD45+0
8/0 | 2DD60+0
8/1 | 2DB1+6
8/2 | 2DB1+6
8/3 | 2DB1+9
8/4 | 2DB1+6
8/5 | 2DA+0
8/6 | 2DA+0
8/7 | 2DA+3
8/8 | 2DA+0
8/9 | 2DA+3
8/10 | 2DA+0
8/11 | 2DA+0
8/12 | 2DA+0
8/13 | 2DA+3
8/14 | 2DA+3
8/15 | 2DA+3
9/0 | 2DB1+0 | Completed | Naresh | 9
9/1 | 2DA+3 | Completed | Naresh | 9
9/2 | 2DA+0 | Completed | Naresh | 9
9/3 | 2DA+9 | Completed | Naresh | 9
9/4 | 2DA+0 | Completed | Naresh | 9
9/5 | 2DA+0 | Completed | Naresh | 9
9/6 | 2DA+3 | Completed | Naresh | 9
9/7 | 2DA+3 | Completed | Naresh | 9
9/8 | 2DA+0 | Completed | Naresh | 9
9/9 | 2DA+0 | Completed | Naresh | 9
9/10 | 2DA+3 | Completed | Naresh | 9
10/0 | 3DB2+0 | Completed | Anil & Naresh
10/1 | 3DA+3 | Completed | Anil & Naresh | 13
10/2 | 3DA+0 | Completed | Anil & Naresh | 13
10/3 | 3DA+3 | Completed | Anil & Naresh | 13
10/4 | 3DA+3 | Completed | Anil & Naresh | 13
10/5 | 3DA+3 | Completed | Anil & Naresh | 13
10/6 | 3DA+6 | Completed | Anil & Naresh | 13
10/7 | 3DA+3 | Completed | Anil & Naresh | 13
10/8 | 3DA+3 | Completed | Anil & Naresh | 13
10/9 | 3DA+6 | Completed | Anil & Naresh | 13
11/0 | 3DC1+0 | Completed | Anil & Naresh | 13
11/1 | 3DA+0
11/2 | 3DA+0
11/3 | 3DA-3
11/4 | 3DA+0
11/5 | 3DA+0
11/6 | 3DA+0
11/7 | 3DA+0
11/8 | 3DA+0
11/9 | 3DA+0
11/10 | 3DA+0
11/11 | 3DA+3
12/0 | 3DB2+0 | Completed | Anil & Naresh | 13
12/1 | 3DA+3 | Completed | Anil & Naresh | 13
12/2 | 3DA+3 | Completed | Anil & Naresh | 13
12/3 | 3DA+3 | Completed | Anil & naresh | 13
12/4 | 3DA+3 | Completed | Anil & naresh | 13
12/5 | 3DA+0 | Completed | Anil & naresh | 13
12/6 | 3DA+0 | Completed | Anil & naresh | 13
12/7 | 3DA+0 | Completed | Anil & naresh | 13
12/8 | 3DA+3 | Completed | Anil & naresh | 13
12/9 | 3DA+3 | Completed | Anil & naresh | 13
12/10 | 3DA+0 | Completed | Anil & naresh | 13
12/11 | 3DA+6 | Completed | Anil & naresh | 13
13/0 | 3DB1+0 | Completed | Anil & naresh | 13
13/1 | 3DA+3 | Completed | Naresh | 9
13/2 | 3DA+0 | Completed | Naresh | 10
13/3 | 3DA+6 | Completed | Naresh | 11
13/4 | 3DA+3 | Completed | Naresh | 12
13/5 | 3DA+0 | Completed | Naresh | 13
13/6 | 3DA+6 | Completed | Naresh | 14
13/7 | 3DA+6 | Completed | Naresh | 15
13/8 | 3DA+0 | Completed | Naresh | 16
13/9 | 3DA+3 | Completed | Naresh | 17
13/10 | 3DA+0 | Completed | Anil & naresh | 13
13/11 | 3DA+0 | WIP
14/0 | 3DC2+6 | WIP
15/0 | 3DD45+3
15/1 | 3DA+0
15/2 | 3DA+3
15/3 | 3DA+0
15/4 | 3DA+3
16/0 | 3DD45+0
16/1 | 3DA+0
16/2 | 3DA+0
16/3 | 3DA+3
16/4 | 3DA+0
16/5 | 3DA+0 | WIP
16/6 | 3DA+0 | Completed | Dasharath | 17
16/7 | 3DA-3 | Completed | Dasharath | 17
16/8 | 3DA+3 | Completed | Dasharath | 18
16/9 | 3DA+0 | Completed | Dasharath | 19
16/10 | 3DA+3 | Completed | Dasharath | 20
16/11 | 3DA+3
17/0 | 3DC1+0 | Completed | Dasharath | 17
17/1 | 3DA+3 | Completed | Dasharath | 17
17/2 | 3DA+3 | Completed | Dasharath | 17
17/3 | 3DA+6 | Completed | Dasharath | 17
18/0 | 3DB2+0 | Completed | Dasharath | 17
18/1 | 3DA+0 | Completed | Dasharath | 17
18/2 | 3DA+0 | Completed | Dasharath | 18
18/3 | 3DA+0 | Completed | Dasharath | 19
19/0 | 3DD45+0 | Completed | Dasharath | 20
19/1 | 3DA+6 | Completed | Dasharath | 17
19/2 | 3DA+0 | Completed | Dasharath | 17
19/3 | 3DA+3 | Completed | Dasharath | 17
20/0 | 3DB1+0 | Completed | Dasharath | 18
20A/0 | 3DB2+0 | Completed | Dasharath | 19
21/0 | 3DD45+0 | Completed | Dasharath | 17
21/1 | 3DA+0 | Completed | Dasharath | 17
21/2 | 3DA+0 | Completed | Dasharath | 17
21/3 | 3DA+6 | Completed | Dasharath | 17
21/4 | 3DA+3 | Completed | Dasharath | 17
21/5 | 3DA-3 | Completed | Dasharath | 17
21/6 | 3DA+0 | Completed | Dasharath | 17
21/7 | 3DA+0 | Completed | Dasharath | 17
21/8 | 3DA+0 | Completed | Dasharath | 17
21/9 | 3DA+0 | Completed | Dasharath | 17
22/0 | 3DB1+0 | Completed | Dasharath | 17
22/1 | 3DA+0 | Completed | Dasharath | 17
22/2 | 3DA+0 | Completed | Dasharath | 17
22/3 | 3DA+6 | Completed | Dasharath | 17
22/4 | 3DA+3 | Completed | Dasharath | 17
22/5 | 3DA+0 | Completed | Dasharath | 17
23/0 | 3DB2+0 | Completed | Dasharath | 17
23/1 | 3DA+6 | Completed | Dasharath | 17
23/2 | 3DA+0 | Completed | Dasharath | 17
23/3 | 3DA+0 | Completed | Dasharath | 17
23/4 | 3DA+0 | Completed | Dasharath | 17
24/0 | 3DB1+0 | Completed | Dasharath | 17
24/1 | 3DA+6 | Completed | Dasharath | 17
24/2 | 3DA+3 | Completed | Dasharath | 17
24/3 | 3DA+0 | Completed | Dasharath | 17
24/4 | 3DA+0 | Completed | Dasharath | 17
24/5 | 3DA+0 | Completed | Dasharath | 17
24/6 | 3DA+0 | Completed | Dasharath | 17
24/7 | 3DA+0 | Completed | Dasharath | 17
24/8 | 3DA+3 | Completed | Dasharath | 17
25/0 | 3DB2+0 | Completed | Dasharath | 17
25/1 | 3DA+0 | Completed | Dasharath | 17
25/2 | 3DA+0 | Completed | Dasharath | 17
25/3 | 3DA+0 | Completed | Dasharath | 17
25/4 | 3DA+0 | Completed | Dasharath | 17
25/5 | 3DA+6 | Completed | Dasharath | 17
26/0 | 3DB2+0 | Completed | Dasharath | 17
26/1 | 3DA+0 | Completed | Dasharath | 17
26/2 | 3DA+0 | Completed | Dasharath | 17
26/3 | 3DA+0 | Completed | Dasharath | 17
26/4 | 3DA+0 | Completed | Dasharath | 17
27/0 | 3DB1+0 | Completed | Dasharath | 17
27/1 | 3DA+0 | Completed | Dasharath | 18
27/2 | 3DA+0 | Completed | Dasharath | 19
27/3 | 3DC1+0 (TR) |  | Dasharath | 20
27/4 | 3DA+0 | Completed | Dasharath | 21
27/5 | 3DA+0 | Completed | Dasharath | 22
27/6 | 3DA+0 | Completed | Dasharath | 23
27/7 | 3DA+0 | Completed | Dasharath | 24
27/8 | 3DA+0 | Completed | Dasharath | 25
27/9 | 3DA+3
28/0 | 3DC1+0
28/1 | 3DA+9
29/0 | 3DC1+0 | Completed | Dasharath | 17
29/1 | 3DA+9 | Completed | Dasharath | 17
29/2 | 3DA+0 | Completed | Dasharath | 17
29/3 | 3DA+0 | Completed | Dasharath | 17
29/4 | 3DA+0 | Completed | Dasharath | 17
29/5 | 3DA+3 | Completed | Dasharath | 17
29/6 | 3DA+0 | Completed | Dasharath | 17
29/7 | 3DA+3 | Completed | Dasharath | 17
29/8 | 3DA+0 | Completed | Dasharath | 17
29/9 | 3DB1+9 | Completed | Dasharath | 17
30/0 | 3DC1+6 | Completed | Dasharath | 17
30/1 | 3DA+3 | Completed | Dasharath | 17
30/2 | 3DA+3 | Completed | Dasharath | 17
30/3 | 3DA+3 | Completed | Dasharath | 17
30/4 | 3DA+3 | Completed | Dasharath | 17
30/5 | 3DA+0 | Completed | Dasharath | 17
31/0 | 3DB2+0 | Completed | Dasharath | 17
31/1 | 3DA+3 | Completed | Dasharath | 17
31/2 | 3DA+0 | Completed | Dasharath | 17
31/3 | 3DA-3 | Completed | Dasharath | 17
31/4 | 3DA+0 | Completed | Dasharath | 17
31/5 | 3DA+0 | Completed | Dasharath | 17
31/6 | 3DA+3 | Completed | Dasharath | 17
32/0 | 3DC1+0 | Completed | Dasharath | 17
32/1 | 3DA+0 | Completed | Dasharath | 17
32/2 | 3DA+3 | Completed | Dasharath | 17
32/3 | 3DA+6 | Completed | Dasharath | 17
33/0 | 3DD45+6 | Completed | Dasharath | 17
33/1 | 3DA+0
33/2 | 3DA-3
34/0 | 3DC1+0
34/1 | 3DB1+0
34/2 | 3DB1+6
35/0 | 3DB1+9
35/1 | 3DA+0
35/2 | 3DA+0
35/3 | 3DA+0
35/4 | 3DA+6
36/0 | 3DD60+3
36/1 | 3DA+0
36/2 | 3DA+3
36/3 | 3DA+3
36/4 | 3DA+3
36/5 | 3DA+0
36/6 | 3DA+3
36/7 | 3DA+3
36/8 | 3DA+0
37/0 | 3DB2+0
37/1 | 3DA+3
37/2 | 3DA+0
37/3 | 3DA+0
37/4 | 3DA+6
37/5 | 3DA+0
37/6 | 3DA+0
38/0 | 3DC1+0
38/1 | 3DA+0
38/2 | 3DA+0
38/3 | 3DA+3
38/4 | 3DA+0
38/5 | 3DA+0
38/6 | 3DA+0
38/7 | 3DA+0
39/0 | 3DC1+3
39/1 | 3DA+6
39/2 | 3DA+0
39/3 | 3DA+3
39/4 | 3DA+3
39/5 | 3DA+3
39/6 | 3DA+0
39/7 | 3DA+6
39/8 | 3DA+3
39/9 | 3DA+9
40/0 | 3DB2+9
40/1 | 3DA+9
41/0 | 3DC1+0
41/1 | 3DA+0
42/0 | 3DB1+9
42/1 | 3DA+6
42/2 | 3DA+0
42/3 | 3DA+3
42/4 | 3DA+3
42/5 | 3DA+3
42/6 | 3DA+0
42/7 | 3DA+9
42/8 | 3DA+9
42/9 | 3DA+3
43/0 | 3DB2+0
43/1 | 3DA+3
43/2 | 3DA-3
43/3 | 3DA+0
43/4 | 3DA+3
43/5 | 3DA+9
43A/0 | 3DD45+9
43A/1 | 3DB1+3
43A/2 | 3DA+0
43A/3 | 3DA+0
43A/4 | 3DA+0
43A/5 | 3DA+3
43B/0 | 3DB1+9
44/0 | 3DD45+3

## Stubs and Towers
Supply Status - Stubs & Towers
Stub Details
SL No | Description | Unit | Line Qty | Received | Balance
1 | 3DA Stub | Set | 190 | 190 | 0
2 | 3DB Stub | Set | 23 | 23 | 0
3 | 3DC Stub | Set | 13 | 13 | 0
4 | 3D45 Stub | Set | 7 | 7 | 0
5 | 3D6o Stub | Set | 1 | 1 | 0
6 | 2DA Stub | Set | 61 | 61 | 0
7 | 2DB Stub | Set | 11 | 11 | 0
7 | 2D45 Stub | Set | 4 | 4 | 0
8 | 2DC Stub | Set |  |  | 0
9 | 2D6o Stub | Set | 2 | 2 | 0
| Total | Set | 312 | 312 | 0
Tower Details
SL No | Tower Type | Description | Line Qty | Received | Balance | Remarks
1 | 3DA Type | Basic body | 190 | 190 | 0
|  | +0m BE | 99 | 99 | 0
|  | +3m BE | 57 | 57 | 0
|  | +6m BE | 21 | 21 | 0
|  | +9m BE | 7 | 7 | 0
|  | -3m BE | 6 | 6 | 0
2 | 3DB Type | Basic body | 23 | 23 | 0
|  | +0m BE | 16 | 16 | 0
|  | +3m BE | 1 | 1 | 0
|  | +6m BE | 1 | 1 | 0
|  | +9m BE | 5 | 5 | 0
-3m BE
3 | 3DC Type | Basic body | 13 | 12 | 1
|  | +0m BE | 8 | 8 | 0
|  | +3m BE | 2 | 2 | 0
|  | +6m BE | 2 | 2 | 0
|  | +0 TP T0wer | 1 | 1 | 0
-3m BE
4 | 3D45 Type | Basic body | 7 | 7 | 0
|  | +0m BE | 3 | 3 | 0
|  | +3m BE | 2 | 2 | 0
|  | +6m BE | 1 | 1 | 0
|  | +9m BE | 1 | 1 | 0
-3m BE
5 | 3DD60 Type | Basic body | 1 | 1 | 0
|  | +3m BE | 1 | 1 | 0
6 | 2DA Type | Basic body | 61 | 45 | 16
|  | +0m BE | 31 | 31 | 0
|  | +3m BE | 21 | 21 | 0
|  | +6m BE | 5 | 5 | 0
|  | +9m BE | 4 | 4 | 0
|  | -3m BE |  |  | 0
7 | 2DB Type | Basic body | 11 | 11 | 0
|  | +0m BE | 3 | 3 | 0
|  | +3m BE | 2 | 2 | 0
|  | +6m BE | 4 | 4 | 0
|  | +9m BE | 2 | 2 | 0
-3m BE
8 | 2DD45 Type | Basic body | 4 | 4 | 0
|  | +0m BE | 2 | 2 | 0
|  | +3m BE |  |  | 0
|  | +6m BE | 2 | 2 | 0
|  | +9m BE |  |  | 0
-3m BE
8 | 2DD60 Type | Basic body | 2 | 2 | 0
|  | +0m BE | 2 | 2 | 0
|  | Total | 312 | 312 | 0

## Hardwares & Tower Accessories
LOI Item No. | Activity Description | Description of Work | UOM | Line Quantity | SUPPLY RECEIVED | Balance
47 | CONDUCTOR | ACSR/AL59/AAAC ZEBRA CONDUCTOR | KM | 4412 | 4330.244 | 81.756
62 | HARDWARE FITTINGS | Double ISuspension String | SET | 1506 | 1506 | 0
63 | HARDWARE FITTINGS | Single ISuspension String (Pilot) | SET | 95 | 90 | 5
64 | HARDWARE FITTINGS | Quadruple Tension String | SET | 738 | 690 | 48
65 | HARDWARE FITTINGS | SingleTension String | SET | 4 | 0 | 4
70 | CONDUCTOR ACCESSORIES | HEXAGONAL RIGID SPACER | EA | 1945 | 1814 | 131
71 | CONDUCTOR ACCESSORIES | MID SPAN COMPRESSION JOINT | EA | 2102 | 2076 | 26
72 | CONDUCTOR ACCESSORIES | REPAIR SLEEVE | EA | 692 | 692 | 0
73 | CONDUCTOR ACCESSORIES | ROD TYPE SPACER DAMPER | EA | 13194 | 12450 | 744
74 | CONDUCTOR ACCESSORIES | T-CONNECTOR | EA | 48 | 48 | 0
80 | Earthwire Accessories | Mid Span Compression Joint | EA | 62 | 61 | 1
81 | Earthwire Accessories | FLEXIBLE AL BOND | EA | 378 | 371 | 7
82 | Earthwire Accessories | Vibration damper | EA | 756 | 740 | 16
83 | Earthwire Accessories | Suspension clamp assembly | EA | 251 | 251 | 0
84 | Earthwire Accessories | Tension clamp assembly | EA | 127 | 119 | 8
90 | INSULATOR (CLR) | 160 KN | EA | 6284 | 6229 | 55
91 | INSULATOR (CLR) | 210 KN | EA | 5962 | 5547 | 415
94 | Sleeves H/F | INSULATION SLEEVE FOR CONDUCTOR | EA | 400 | 0 | 400
95 | Earthwire | 7/3.66 G.S. EARTHWIRE | KM | 126.19 | 122.01 | 4.18
97 | OPGW Supply | 24 FIBRE (DWSM) OPGW | KM | 127.56 | 127.54 | 0.02
98 | OPGW Supply | Suspension clamp assembly | EA | 251 | 171 | 80
99 | OPGW Supply | TENSION ASSEMBLY - DEAD END | SET | 2 | 0 | 2
100 | OPGW Supply | TENSION FITTINGS ASSEMBLY -JOINT BOX (SPLICING) | SET | 29 | 17 | 12
101 | OPGW Supply | TENSION ASSEMBLY - DOUBLE TENSION PASS THROUGH | SET | 33 | 18 | 15
103 | OPGW Supply | Vibration Damper | EA | 1228 | 694 | 534
104 | OPGW Supply | Down Lead clamp Assembly | EA | 1116 | 690 | 426
105 | OPGW Supply | Joint Box | EA | 31 | 22 | 9
56 | TOWER ACCESSORIES | Phase Plate (Set of three) | EA | 618 | 618 | 0
57 | TOWER ACCESSORIES | Circuit Plate (Set of two) | EA | 309 | 309 | 0
58 | TOWER ACCESSORIES | Supply of Anti-Climbing Devices of Barbed Wire Type | EA | 309 | 309 | 0
59 | TOWER ACCESSORIES | Bird Guard (Set of Three) | SET | 498 | 498 | 0
60 | TOWER ACCESSORIES | Danger Plate for 765kV | EA | 309 | 309 | 0
61 | TOWER ACCESSORIES | Number Plate for 765kV | EA | 309 | 309 | 0