## DPR-KEC
DAILY PROGRESS REPORT TL (602)
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Agency: - M/s KEC International Limited
NOA No.: CC/T/W-TW/DOM/A06/24/04774/NOA-2/25-105721/02 Dt:13-05-2025
Revenue:613.3 CR | [13 empty] | Date: | 2026-05-30 20:29
Activity |  |  | LOA Quantity | Final Estimated Quantity | Cum. L2 till Last Month | Cum Progress till Last Month | L2 for present Month (May'26) | Plan for the Month | Plan for this Month (May'26) | Progress for Today | Progress for the Month (May'26) | Cum. L2 till date | Cum. Progress till date | Balance Work | Under Progress | Gangs at Present
Route Alignment (Km) |  |  | 186.3 | 185.149 | 184.963 | 185.149 | 0 | 0 | 0 |  |  | 184.963 | 185.149 | 0
Soil Investigation (Loc) |  |  | 36 | 31 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 31
Detailed Survey (Km)
Submitted |  |  | 186.3 | 185.149 | 184.963 | 185.149 | 0 |  | -0.186 |  |  | 184.963 | 185.149 | 3.7Kms | Hold Brick Kilm AP13 to Ap14 Brick Kiln
Approved |  |  | 186.3 | 185.149 | 184.986 | 136.139 | 0 |  | 48.847 |  | 30.393 | 184.986 | 166.532 | 18.617 | 11.995
Check Survey (Km)
Submitted |  |  | 186.3 | 185.149 | 170 | 136.139 | 16.3 |  | 48.847 |  | 19.783 | 186.3 | 155.922 | 29.227
Approved |  |  | 186.3 | 185.149 | 170 | 136.139 | 16.3 |  | 48.847 |  |  | 186.3 | 136.139 | 49.01
Foundation (Loc) |  |  | 494 | 478 | 142 | 136 | 25 | 30 | 35 | 1 | 17 | 167 | 153 | 325 | 8 | 6
Earthing |  |  | 494 | 478 | 142 | 89 | 25 | 30 | 35 |  | 4 | 167 | 93 | 385
Soil Investigation (Loc) |  |  | 31
Pipe Type Chemical |  |  | 10
Rod Type |  |  | 298
Counter Poise |  |  | 181
Counter poise Chemical |  |  | 5
Erection (Loc) | [5 empty] | 0 | [6 empty] | 0
Stringing (Km) |  | Rough Sag | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0
|  | Final Sag | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0
OPGW (Km) |  |  | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | 0
Erection |  |  | 494 | 478 | 77 | 23 | 25 | 7 | 40 |  | 28 | 102 | 51 | 427 | 4 | 4
Status of WIP Location
Foundation
S. No | Loc No | Tower Type | Soil Classification | Conc. Vol (Cum) | Start Date | Completion Date | Work Status as on date |  |  |  | Name of Gang |  | Remarks
| 102/7 | A+0 |  |  | 2025-11-07
| 103/2 | A+0 | WET PADDY |  | 2025-11-07
| 103/3 | A+3 |  |  | 2025-11-07
| 111/2 | A+3 | DFR
| 111/3 | A+0 | WFR
| 121/1 | A+0 | DFR |  | 2025-11-05
| 121/4 | A+0 | DFR
| 121/6 | A+0 | DFR
| 123/2 | A+0 | WFR
| 124/4 | A+3 |  |  | 2025-11-08
| 125/1 | A+3 | WFR
| 126/6 | A+3
| 126/8 | A+0
| 126/9 | A+3 | DFR
| 126/10 | A+0
| 130/2 | A+6 | WFR |  | 2025-11-02
| 130/3 | A+3 |  |  | 2025-11-09
| 132/2 | A+0 |  |  | 2025-11-09

## Survey details
Survey Status | [10 empty] | Date: 04-05-2026 | 2026-03-11
Project Name & Code |  |  | TA-602
Sl No | Section | Kms | Detailed Survey |  |  |  |  | Check Survey
|  |  | Completed | Submitted | Approved | Remarks | Surveyor | Completed | Submitted | Approved | Remarks | Surveyor
1 | AP0 to AP16 |  |  |  |  | Submitted to PGCIL (25-04-2026) 11.823Kms | Mr. Tapas Das
2 | AP0 to AP11 | 8.123 | 8.123 | 8.123 |  | Due to Brick -kiln Hold B/W Section AP13 to AP14 Submitted 26-05-2026
3 | AP16 to AP29 | 7.454 | 7.454 | 7.454 | 7.454 | Approved | Mr. Hemanta/Mr. Tapas Das
4 | AP29 to AP35 | 4.653 | 4.653 | 4.653 | 4.653 | Approved | Mr. Hemanta/Mr. Tapas Das
5 | AP35 to AP 40 | 6.557 | 6.557 | 6.557 | 6.557 | Approved | Mr. Hemanta/Mr. Tapas Das | 19.783 | 19.783
6 | AP 40 to AP 51 | 11.729 | 11.729 | 11.729 | 11.729 | Approved | Mr. Hemanta/Mr. Tapas Das | [5 empty] | #REF!
10
11 | AP0 to AP23 |  |  |  |  | Route Diversion due to Newly under constrction house (Alternate Route Submitted) | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
12 | AP33 to AP38A | [5 empty] | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
13 | AP38 to AP51 | [5 empty] | Hemanta Malik/Tapas Das/Rakesh Debnath | 0 |  | 0
7 | AP51 to AP62 | 8.344 | 8.344 | 8.344 | 8.344 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 8.344 | 8.344 | 8.344 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
8 | AP62 to AP 64 | 3.615 | 3.615 | 3.615 | 3.615 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 3.615 | 3.615 | 3.615 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
9 | AP64 to AP71 | 9.709 | 9.709 | 9.709 | 9.709 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 9.709 | 9.709 | 9.709 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
13 | AP71 to AP75 | 3.714 | 3.714 | 3.714 | 3.714 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 3.714 | 3.714 | 3.714 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
14 | AP75 to AP76 | 1.238 | 1.238 | 1.238 | 1.238 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 1.238 | 1.238 | 1.238 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
15 | AP76 to AP83 | 7.242 | 7.242 | 7.242 | 7.242 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 7.242 | 7.242 | 7.242 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
16 | AP83 to AP92 | 22.602 | 22.602 | 22.602 | 22.602 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 22.602 | 22.602 | 22.602 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
17 | AP92 to AP94 | 4.351 | 4.351 | 4.351 | 4.351 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.351 | 4.351 | 4.351 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
18 | AP94 to AP99 | 6.622 | 6.622 | 6.622 |  | Narmada River Crossing | Hemanta Malik/Tapas Das | 0 | 0 | 0
19 | AP 99 to AP 106 | 11.413 | 11.413 | 11.413 | 11.413 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 11.413 | 11.413 | 11.413 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
20 | AP106 to AP110 | 10.77 | 10.77 | 10.77 | 10.77 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 10.77 | 10.77 | 10.77 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
21 | AP110 to AP118 | 10.198 | 10.198 | 10.198 | 10.198 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 10.198 | 10.198 | 10.198 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
22 | AP118 to AP 123 | 6.502 | 6.502 | 6.502 | 6.502 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 6.502 | 6.502 | 6.502 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
23 | AP123 to AP126 | 6.516 | 6.516 | 6.516 | 6.516 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 6.516 | 6.516 | 6.516 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
24 | AP126 to Ap127 | 4.34 | 4.34 | 4.34 | 4.34 | Approved | Hemanta Malik/Rakesh Debnath | 4.34 | 4.34 | 4.34 | Approved | Hemanta Malik/Rakesh Debnath
25 | AP127 to AP129A | 4.836 | 4.836 | 4.836 | 4.836 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.836 | 4.836 | 4.836 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
26 | AP129A to AP130 | 4.41 | 4.41 | 4.41 | 4.41 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.41 | 4.41 | 4.41 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
27 | AP130 to AP134 | 4.122 | 4.122 | 4.122 | 4.122 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 4.122 | 4.122 | 4.122 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
28 | AP134 to AP141 | 12.203 | 12.203 | 12.203 | 12.203 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath | 12.203 | 12.203 | 12.203 | Approved | Hemanta Malik/Tapas Das/Rakesh Debnath
|  | 181.263 | 181.263 | 181.263 | 166.518 |  |  | 136.125 | 155.908 | 136.125
0

## FDN
KEC International Limited
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Details of Foundation | [11 empty] | 2026-05-30 20:29
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Complete | Days | Name of the Gang | Name of Section In-charge | Name of Engineer/Supervisor | No. | Remarks
1 | 1 | 125/2 | A+3 | DFR | 2025-09-02 | 2025-09-15 | 13 | Balaji Enterprises | Mr. Arindam Das | Mr. Arindam Das | 1 | SEP'25 |  | 1
2 | 1 | 125/3 | A+6 | DFR | 2025-09-09 | 2025-10-03 | 24 | Balaji Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas | 9 | Oct'25 |  | 2
3 | 2 | 123/1 | A+0 | WFR | 2025-10-01 | 2025-10-07 | 6 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 3
4 | 3 | 124/1 | A+6 | WET Paddy | 2025-09-21 | 2025-10-08 | 17 | Balaji Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 4
5 | 4 | 124/2 | A+6 | WFR | 2025-09-07 | 2025-10-15 | 38 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 5
6 | 5 | 121/7 | A+0 | WFR | 2025-09-24 | 2025-10-16 | 22 | Pawan enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 6
7 | 6 | 121/2 | A+6 | DFR | 2025-10-08 | 2025-10-19 | 11 | Balaji Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 7
8 | 7 | 123/3 | A+9 | DFR | 2025-10-08 | 2025-10-19 | 11 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 8 | New Const. House
9 | 8 | 122/2 | A+0 | WFR | 2025-10-10 | 2025-10-25 | 15 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 9
10 | 9 | 126/5 | A+3 | DFR | 2025-10-11 | 2025-10-28 | 17 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 10
11 | 1 | 116/1 | A+3 | DFR | 2025-10-12 | 2025-11-01 | 20 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas | 30 | Nov'25 |  | 11
12 | 2 | 126/4 | A+0 | DFR | 2025-10-12 | 2025-11-01 | 20 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 12
13 | 3 | 116/2 | A+3 | DFR | 2025-10-12 | 2025-11-03 | 22 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 13
14 | 4 | 124/3 | A+9 | WFR | 2025-09-10 | 2025-11-04 | 55 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 14
15 | 5 | 123/4 | A+0 | WET | 2025-09-30 | 2025-11-06 | 37 | Shri Balaji Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 15 | New Const. house
16 | 6 | 126/3 | A+3 | DFR | 2025-10-30 | 2025-11-06 | 7 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 16
17 | 7 | 130/1 | A+0 | DFR | 2025-10-27 | 2025-11-08 | 12 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 17
18 | 8 | 111/1 | A+0 | DFR | 2025-10-31 | 2025-11-09 | 9 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 18
19 | 9 | 126/9 | A+3 | DFR | 2025-10-11 | 2025-11-11 | 31 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 19
20 | 10 | 123/2 | A+0 | WFR | 2025-10-28 | 2025-11-13 | 16 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 20
21 | 11 | 111/2 | A+3 | DFR | 2025-11-08 | 2025-11-14 | 6 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 21
22 | 12 | 126/10 | A+0 | DFR | 2025-10-10 | 2025-11-14 | 35 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 22
23 | 13 | 121/6 | A+0 | DFR | 2025-11-07 | 2025-11-15 | 8 | Pawan enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 23
24 | 14 | 121/1 | A+0 | DFR | 2025-11-07 | 2025-11-16 | 9 | Shri Balaji Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 24
25 | 15 | 111/3 | A+0 | WFR | 2025-11-07 | 2025-11-19 | 12 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 25
26 | 16 | 130/3 | A+3 | WFR | 2025-11-09 | 2025-11-19 | 10 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 26
27 | 17 | 103/2 | A+0 | WET PADDY | 2025-11-09 | 2025-11-20 | 11 | MUKESH MEHTA | Mr. Arindam Das | Mr. Vishnu |  |  |  | 27
28 | 18 | 124/4 | A+3 | WFR | 2025-11-08 | 2025-11-21 | 13 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 28
29 | 19 | 126/2 | A+9 | WFR | 2025-11-13 | 2025-11-21 | 8 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 29
30 | 20 | 121/4 | A+0 | DFR | 2025-11-16 | 2025-11-22 | 6 | Pawan enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 30
31 | 21 | 111/4 | A+0 | DFR | 2025-11-14 | 2025-11-23 | 9 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 31
32 | 22 | 103/3 | A+3 | WET PADDY | 2025-11-07 | 2025-11-24 | 17 | MUKESH MEHTA | Mr. Arindam Das | Mr. Vishnu |  |  |  | 32
33 | 23 | 134/2 | A+3 | WFR | 2025-11-15 | 2025-11-24 | 9 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 33
34 | 24 | 103/1 | A+6 | WET PADDY | 2025-11-23 | 2025-11-28 | 5 | MUKESH MEHTA | Mr. Arindam Das | Mr. Vishnu |  |  |  | 34
35 | 25 | 111/5 | A+6 | DFR | 2025-11-20 | 2025-11-28 | 8 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 35
36 | 26 | 134/3 | A+6 | WFR | 2025-11-24 | 2025-11-28 | 4 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 36
37 | 27 | 102/7 | A+0 | WET PADDY | 2025-11-07 | 2025-11-30 | 23 | Rajiya Infra. | Mr. Arindam Das | Mr. Vishu Nair |  |  |  | 37
38 | 28 | 110/2 | A+0 | DFR | 2025-11-23 | 2025-11-30 | 7 | Shri Balaji Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 38
39 | 29 | 121/5 | A+0 | DFR | 2025-11-23 | 2025-11-30 | 7 | Pawan enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 39
40 | 30 | 134/5 | A+0 | DFR | 2025-11-23 | 2025-11-30 | 7 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 40
41 | 1 | 110/1 | A+7.5 | DFR | 2025-11-28 | 2025-12-03 | 5 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas | 37 | Dec'25 |  | 41
42 | 2 | 134/4 | A+3 | DFR | 2025-11-20 | 2025-12-03 | 13 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 42
43 | 3 | 99/1 | A+3 | WET PADDY | 2025-11-24 | 2025-12-06 | 12 | Dhanraj construction | Mr. Arindam Das | Mr. Vishu Nair |  |  |  | 43
44 | 4 | 109/1 | A+3 | WET PADDY | 2025-11-30 | 2025-12-06 | 6 | MUKESH MEHTA | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 44
45 | 5 | 134/6 | A+3 | DFR | 2025-11-25 | 2025-12-06 | 11 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 45
46 | 6 | 102/9 | A+3 | WET PADDY | 2025-11-21 | 2025-12-07 | 16 | Rajiya Infra. | Mr. Arindam Das | Mr. Vishu Nair |  |  |  | 46
47 | 7 | 109/10 | A-3 | DFR | 2025-12-03 | 2025-12-07 | 4 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 47
48 | 8 | 134/9 | A+0 | WET PADDY | 2025-12-01 | 2025-12-07 | 6 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 48
49 | 9 | 134/7 | A+3 | DFR | 2025-12-01 | 2025-12-08 | 7 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 49
50 | 10 | 136/2 | A+3 | WET Paddy | 2025-12-01 | 2025-12-10 | 9 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 50
51 | 11 | 110/3 | A+0 | DFR | 2025-11-29 | 2025-12-11 | 12 | Shri Balaji Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 51
52 | 12 | 109/2 | A+0 | WET PADDY | 2025-12-07 | 2025-12-12 | 5 | MUKESH MEHTA | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 52
53 | 13 | 109/11 | A+3 | DFR | 2025-12-04 | 2025-12-12 | 8 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 53
54 | 14 | 136/7 | A+0 | WET PADDY | 2025-12-06 | 2025-12-12 | 6 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 54
55 | 15 | 99/2 | A+3 | WET PADDY | 2025-12-07 | 2025-12-13 | 6 | Dhanraj construction | Mr. Arindam Das | Mr. Vishu Nair |  |  |  | 55
56 | 16 | 102/8 | A+0 | WET PADDY | 2025-12-07 | 2025-12-15 | 8 | Rajiya Infra. | Mr. Arindam Das | Mr. Vishu Nair |  |  |  | 56
57 | 17 | 108/7 | A-3 | WET PADDY | 2025-12-10 | 2025-12-16 | 6 | MUKESH MEHTA | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 57
58 | 18 | 136/8 | A+0 | WET PADDY | 2025-12-07 | 2025-12-16 | 9 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 58
59 | 19 | 134/8 | A+3 | WFR | 2025-11-26 | 2025-12-17 | 21 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 59
60 | 20 | 136/5 | A+0 | WET PADDY | 2025-12-13 | 2025-12-17 | 4 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 60
61 | 21 | 110/4 | A+0 | DFR | 2025-12-10 | 2025-12-19 | 9 | Shri Balaji Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 61
62 | 22 | 136/9 | A+0 | WET PADDY | 2025-12-14 | 2025-12-19 | 5 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 62
63 | 23 | 109/7 | A+3 | DFR | 2025-12-11 | 2025-12-20 | 9 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 63
64 | 24 | 108/5 | A-3 | WET PADDY | 2025-12-12 | 2025-12-22 | 10 | MUKESH MEHTA | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 64
65 | 25 | 136/6 | A+0 | WET Paddy | 2025-12-07 | 2025-12-22 | 15 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 65
66 | 26 | 89/9 | A+0 | WFR | 2025-12-22 | 2025-12-24 | 2 | Shree Khatushyam | Mr. Ajay | Mr. Vishu Nair |  |  |  | 66
67 | 27 | 109/9 | A+3 | DFR | 2025-12-22 | 2025-12-24 | 2 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 67
68 | 28 | 139/3 | A+3 | DFR | 2025-12-22 | 2025-12-24 | 2 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 68
69 | 29 | 107/2 | A-3 | WFR | 2025-12-22 | 2025-12-26 | 4 | Rajiya Infra. | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 69
70 | 30 | 108/6 | A-3 | WET PADDY | 2025-12-22 | 2025-12-26 | 4 | MUKESH MEHTA | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 70
71 | 31 | 109/6 | A+3 | DFR | 2025-12-22 | 2025-12-27 | 5 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 71
72 | 32 | 130/2 | A+6 | DFR | 2025-11-06 | 2025-12-27 | 51 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 72
73 | 33 | 89/8 | A+0 | DFR | 2025-12-22 | 2025-12-28 | 6 | Afflux Construction | Mr. Ajay | Mr. Vishu Nair |  |  |  | 73
74 | 34 | 136/1 | A+0 | WET PADDY | 2025-12-25 | 2025-12-29 | 4 | R.K . Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 74
75 | 35 | 89/7 | A+0 | DFR | 2025-12-24 | 2025-12-30 | 6 | Shree Khatushyam | Mr. Ajay | Mr. Vishu Nair |  |  |  | 75
76 | 36 | 109/5 | A+3 | DFR | 2025-12-22 | 2025-12-30 | 8 | B.L Construction | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 76
77 | 37 | 139/2 | A+0 | DFR | 2025-12-25 | 2025-12-30 | 5 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Wahajuddin Biswas |  |  |  | 77
78 | 1 | 107/1 | A+0 | WFR | 2025-12-23 | 2026-01-03 | 11 | Rajiya Infra. | Mr. Arindam Das | Mr. Tanmay | 20 | Jan'26 |  | 78
79 | 2 | 89/6 | A+0 | DFR | 2025-12-28 | 2026-01-04 | 7 | Afflux Construction | Mr. Ajay | Mr. Vishu Nair |  |  |  | 79
80 | 3 | 129A/1 | A-3 | DFR | 2026-01-04 | 2026-01-07 | 3 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay |  |  |  | 80
81 | 4 | 139/5 | A+0 | DFR | 2025-12-31 | 2026-01-09 | 9 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Arindam Das |  |  |  | 81
82 | 5 | 89/5 | A+3 | DFR | 2026-01-02 | 2026-01-10 | 8 | Shree Khatushyam | Mr. Ajay | Mr. Vishu Nair |  |  |  | 82
83 | 6 | 108/4 | A+3 | WFR | 2025-12-18 | 2026-01-11 | 24 | B.L Construction | Mr. Arindam Das | Mr. Tanmay |  |  |  | 83
84 | 7 | 129A/5 | A+9 | DFR | 2026-01-04 | 2026-01-11 | 7 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay |  |  |  | 84
85 | 8 | 108/1 | A+9 | DFR | 2026-01-11 | 2026-01-17 | 6 | B.L Construction | Mr. Arindam Das | Mr. Tanmay |  |  |  | 85
86 | 9 | 76/2 | A+6 | DFR | 2026-01-14 | 2026-01-20 | 6 | Afflux Construction | Mr. Ajay | Mr. Vishu Nair |  |  |  | 86
87 | 10 | 136/4 | A+0 | WET PADDY | 2026-01-16 | 2026-01-20 | 4 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay |  |  |  | 87
88 | 11 | 77/1 | A-3 | DFR | 2026-01-18 | 2026-01-24 | 6 | Shree Khatushyam | Mr. Ajay | Mr. Vishu Nair |  |  |  | 88
89 | 12 | 107/4 | A+3 | DFR | 2026-01-16 | 2026-01-25 | 9 | B.L Construction | Mr. Arindam Das | Mr. Tanmay |  |  |  | 89
90 | 13 | 76/1 | A+6 | DFR | 2026-01-14 | 2026-01-27 | 13 | Afflux Construction | Mr. Ajay | Mr. Vishu Nair |  |  |  | 90
91 | 14 | 129A/7 | A+1.5 | DFR | 2026-01-14 | 2026-01-27 | 13 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay |  |  |  | 91
92 | 15 | 139/6 | A+0 | DFR | 2026-01-11 | 2026-01-28 | 17 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Arindam Das |  |  |  | 92
93 | 16 | 127/7 | A-3 | DFR | 2026-01-19 | 2026-01-30 | 11 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  |  | 93
94 | 17 | 129A/2 | A+7.5 | DFR | 2026-01-23 | 2026-01-30 | 7 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak |  |  |  | 94
95 | 18 | 76/6 | A+1.5 | DFR | 2026-01-20 | 2026-01-31 | 11 | Shree Khatushyam | Mr. Ajaya | Mr. Vishnu Nair |  |  |  | 95
96 | 19 | 129A/4 | A+6 | DFR | 2026-01-23 | 2026-01-31 | 8 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 2026-02-02 | 96
97 | 20 | 136/3 | A+3 | DFR | 2026-01-27 | 2026-01-31 | 4 | Jai Shri Ram Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 2026-02-02 | 97
98 | 1 | 82/2 | A+7.5 | WFR | 2026-01-27 | 2026-02-02 | 6 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair | 12 | Feb'26 | 756242.89 | 98
99 | 2 | 127/4 | A+3 | WFR | 2026-01-20 | 2026-02-03 | 14 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 756242.89 | 99
100 | 3 | 129A/10 | A+1.5 | DFR | 2026-01-30 | 2026-02-05 | 6 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 523354.53 | 100
101 | 4 | 82/3 | A+9 | WET | 2026-01-31 | 2026-02-08 | 8 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair |  |  | 766420.42 | 101
102 | 5 | 127/1 | A+3 | DFR | 2026-01-30 | 2026-02-09 | 10 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 523354.53 | 102
103 | 6 | 129A/3 | A+3 | DFR | 2026-02-07 | 2026-02-11 | 4 | R.K . Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 523354.53 | 103
104 | 7 | 127/2 | A+0 | DFR | 2026-02-06 | 2026-02-13 | 7 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 487344.29 | 104
105 | 8 | 70/3 | A-3 | DFR | 2026-02-06 | 2026-02-13 | 7 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair |  |  | 487344.29 | 105
106 | 9 | 129A/6 | A+9 | WFR | 2026-01-11 | 2026-02-16 | 36 | R.K . Enterprises | Mr. Ajaya | Mr. Vishnu Nair |  |  | 756242.89 | 106
107 | 10 | 121/10 | A+9 | DFR | 2026-02-11 | 2026-02-17 | 6 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 523354.53 | 107
108 | 11 | 70/1 | A+4.5 | DFR | 2026-02-06 | 2026-02-23 | 17 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair |  |  | 523354.53 | 108
109 | 12 | 125/1 | A+3 | WFR | 2026-02-17 | 2026-02-28 | 11 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  |  | 109
110 | 1 | 126/7 | A+0 | DFR | 2026-02-17 | 2026-03-03 | 14 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak | 5 | Mar'26 | 482703.73 | 110
111 | 2 | 70/2 | A+9 | WFR | 2026-02-13 | 2026-03-07 | 22 | Afflux Constrcutoin | Mr. Ajaya | Mr. Vishnu Nair |  |  | 518713.97 | 111
112 | 3 | 124/5 | A+6 | DFR | 2026-02-08 | 2026-03-14 | 34 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak |  |  | 518713.97 | 112
113 | 4 | 76/5 | A+9 | DFR | 2026-03-12 | 2026-03-21 | 9 | Afflux Constrcutoin | Mr. Ajaya | Mr. Vishnu Nair |  |  |  | 113
114 | 5 | 88/2 | A+0 | DFR | 2026-02-23 | 2026-03-30 | 35 | Afflux Constrcutoin | Mr. Ajaya | Mr. Vishnu Nair
115 | 1 | 88/1 | A+3 | DFR | 2026-03-22 | 2026-04-02 | 11 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair | 22 | April'26
116 | 2 | 127/3 | A+0 | DFR | 2026-03-06 | 2026-04-03 | 28 | Jai Shree Ram | Mr. Arindam Das | Mr. Tanmay Nayak
117 | 3 | 124/0 | B2+0 | Wet Paddy | 2026-03-16 | 2026-04-08 | 23 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak
118 | 4 | 87/4 | A+0 | DFR | 2026-03-29 | 2026-04-08 | 10 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair
119 | 5 | 139/4 | A+0 | DFR | 2026-03-18 | 2026-04-11 | 24 | Jai Shree Ram | Mr. Arindam Das | Mr. Tanmay Nayak
120 | 6 | 102/11 | A+9 | Wet Paddy | 2026-03-24 | 2026-04-11 | 18 | Dhanraj | Mr. Arindam Das | Mr. Tanmay Nayak
121 | 7 | 69/2 | A+0 | DFR | 2026-03-17 | 2026-04-13 | 27 | Kalyan Singh | Mr. Ajaya | Mr. Vishnu Nair
122 | 8 | 87/5 | A+3 | DFR | 2026-04-06 | 2026-04-14 | 8 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair
123 | 9 | 121/9 | A+0 | DFR | 2026-04-03 | 2026-04-15 | 12 | B.L Construction | Mr. Arindam Das | Mr. Tanmay Nayak
124 | 10 | 71/1 | A+3 | WFR | 2026-03-14 | 2026-04-18 | 35 | Sohan Enterprises | Mr. Arindam Das | Mr. Tanmay Nayak
125 | 11 | 87/2 | A+0 | DFR | 2026-04-06 | 2026-04-18 | 12 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair
126 | 12 | 69/1 | A+0 | DFR | 2026-03-25 | 2026-04-21 | 27 | Kalyan Singh | Mr. Arindam Das | Mr. Tanmay Nayak
127 | 13 | 109/8 | A+3 | DFR | 2026-04-07 | 2026-04-22 | 15 | B.L Construction | Mr. Tanmay Nayak | Mr. Saddam
128 | 14 | 125/0 | B2+3 | DFR | 2026-03-18 | 2026-04-23 | 36 | BL. Construction | Mr. Tanmay Nayak | Mr. Saddam
129 | 15 | 71/2 | A-3 | DFR | 2026-03-18 | 2026-04-24 | 37 | Soham Entp | Mr. Arindam Das | Mr. Tanmay Nayak
130 | 16 | 136/0 | C2+9 | Wet Paddy | 2026-03-28 | 2026-04-24 | 27 | Jai Shree Ram | Mr. Tanmay Nayak | Mr. Saddam
131 | 17 | 87/3 | A+3 | DFR | 2026-04-18 | 2026-04-25 | 7 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair
132 | 18 | 69/3 | A+0 | DFR | 2026-04-07 | 2026-04-28 | 21 | Kalyan Singh | Mr. Ajaya | Mr. Vishnu Nair
133 | 19 | 88/3 | A-3 | DFR | 2026-04-18 | 2026-04-30 | 12 | Afflux Construction | Mr. Ajaya | Mr. Vishnu Nair
134 | 20 | 71/3 | A+0 | DFR | 2026-04-21 | 2026-04-30 | 9 | Soham Entp | Mr. Ajaya | Mr. Vishnu Nair
135 | 21 | 139/0 | B2+0 | Wet Paddy | 2026-03-30 | 2026-04-30 | 31 | Jai Shree Ram | Mr. Tanmay Nayak | Mr. Saddam
136 | 22 | 127/0 | B1+0 | DFR | 2026-03-20 | 2026-04-30 | 41 | B.L Construction | Mr. Tanmay Nayak | Mr. Saddam
137 | 1 | 71/4 | A-3 | DFR | 2026-04-23 | 2026-05-04 | 11 | Soham Entp | Mr. Ajaya | Mr. Vishnu Nair | 16 | May'26
138 | 2 | 139/1 | A+3 | DFR | 2026-04-23 | 2026-05-04 | 11 | Jai Shree Ram | Mr. Tanmay Nayak | Mr. Saddam
139 | 3 | 108/0 | C1+9 | DFR | 2026-04-24 | 2026-05-04 | 10 | BL. Construction | Mr. Tanmay Nayak | Mr. Saddam
140 | 4 | 107/0 | C2+3 | DFR | 2026-03-27 | 2026-05-06 | 40 | Dhanraj Construction | Mr. Tanmay Nayak | Mr. Biswas
141 | 5 | 69/4 | A+0 | DFR | 2026-05-01 | 2026-05-08 | 7 | Soham Entp | Mr. Ajaya | Mr. Vishnu Nair
142 | 6 | 126/0 | C2+0 | DFR | 2026-04-29 | 2026-05-12 | 13 | BL. Construction | Mr. Tanmay Nayak | Mr. Biswas
143 | 7 | 88/0 | C2+3 | DFR | 2026-04-25 | 2026-05-15 | 20 | Afflux | Mr. Ajaya | Mr. Vishnu Nair
144 | 8 | 135/0 | B2+9 | Wet Paddy | 2026-04-16 | 2026-05-19 | 33 | Jai Shree Ram | Mr. Tanmay Nayak | Mr. Biswas
145 | 9 | 71/5 | A+3 | WFR | 2026-05-04 | 2026-05-21 | 17 | Soham Entp | Mr. Ajaya | Mr. Vishnu Nair
146 | 10 | 123/0 | B2+0 | DFR | 2026-05-05 | 2026-05-23 | 18 | BL. Construction | Mr. Tanmay Nayak | Mr. Biswas
147 | 11 | 102/10 | A+0 | Wet Paddy | 2026-04-21 | 2026-05-23 | 32 | Sawariya | Mr. Tanmay Nayak | Mr. Biswas
148 | 12 | 109/0 | B2+0 | Wet | 2026-04-19 | 2026-05-23 | 34 | BL. Construction | Mr. Tanmay Nayak | Mr. Biswas
149 | 13 | 88/5 | B1+0 | DFR | 2026-04-30 | 2026-05-24 | 24 | Afflux | Mr. Ajaya | Mr. Vishnu Nair
150 | 14 | 102/5 | A+0 | Wet Paddy | 2026-04-16 | 2026-05-26 | 40 | M./S Sanjay kumar | Mr. Tanmay | Mr. Wahijuddin Biswas
151 | 15 | 72/1 | A+9 | DFR | 2026-05-19 | 2026-05-27 | 8 | Soham Entp | Mr. Ajaya | Mr. Vishnu Nair
152 | 16 | 88/4 | B1+3 | Wet Paddy | 2026-05-02 | 2026-05-29 | 27 | Afflux | Mr. Ajaya | Mr. Vishnu Nair
153 | 17 | 132/2 | A+0 | DFR | 2026-05-05 | 2026-05-30 | 25 | Jai Shree Ram | Mr. Tanmay | Mr. Wahijuddin Biswas
Formulas:
Start = VLOOKUP([Loc. No.],'[2]FDN Details (2)'!C63:Z541,17,0)
Start = VLOOKUP([Loc. No.],'[2]FDN Details'!$C5:BO483,56,0)
Complete = VLOOKUP([Loc. No.],'[2]FDN Details (2)'!C63:Z541,18,0)
Complete = VLOOKUP([Loc. No.],'[2]FDN Details'!$C5:BP483,57,0)

## Erection
M/s. KEC INTERNATIONAL LIMITED
Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Details of Erection | [7 empty] | 2026-05-30 20:29
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Start | Complete | Name of the Gang | Name of Supervisor/Engineer | STATUS | Tack welding Status | Zinc Paint status | Tower Weight(MT) | Completion Month | Revenue
1 | 1 | 125/2 | A+3 | 2026-02-18 | 2026-02-22 | M/S Ratani Devi | Mr. Mijanur | Completed |  |  |  | Feb'26 |  | 24.042
2 | 2 | 130/1 | A+0 | 2026-02-22 | 2026-02-28 | M/S Jwala | Mr.Saddam' | Completed |  |  |  | Feb'26 |  | 22.925
3 | 3 | 122/2 | A+0 | 2026-02-25 | 2026-02-28 | M/S Ratani Devi | Mr. Mijanur | Completed |  |  |  | Feb'26 |  | 22.925
4 | 1 | 126/10 | A+0 |  | 2026-03-07 | M/s Ratani Devi | Mr. Saddam | Completed |  |  |  | Mar'26 |  | 22.925
5 | 2 | 129A/3 | A+3 | 2026-03-01 | 2026-03-10 | M/s Jwala | Mr. Saddam | Completed |  |  |  | Mar'26 |  | 24.042
6 | 3 | 126/9 | A+3 | 2026-03-01 | 2026-03-11 | M/s Ratani Devi | Mr. Sanjit | Completed |  |  |  | Mar'26 |  | 24.042
7 | 4 | 129A/4 | A+6 | 2026-03-11 | 2026-03-14 | M/s Jwala | Mr. Sanjit | Completed |  |  |  | Mar'26 |  | 26.765
8 | 5 | 126/5 | A+3 | 2025-03-01 | 2026-03-15 | M/s Ratani Devi | Mr. Mijanur | Completed |  |  |  | Mar'26 |  | 24.042
9 | 6 | 130/2 | A+6 | 2026-03-15 | 2026-03-19 | M/s Jwala | Mr. Saddam | Completed |  |  |  | Mar'26 |  | 26.765
10 | 7 | 126/4 | A+0 | 2026-03-15 | 2026-03-19 | M/s Ratani Devi | Mr. Mizanur | Completed |  |  |  | Mar'26 |  | 22.925
11 | 8 | 130/3 | A+3 | 2026-03-19 | 2026-03-22 | M/s Jwala | Mr. Sanjit | Completed |  |  |  | Mar'26 |  | 24.042
12 | 9 | 126/3 | A+3 | 2026-03-19 | 2026-03-23 | M/s Ratani Devi | Mr. Mizanur | Completed |  |  |  | Mar'26 |  | 24.042
13 | 10 | 134/2 | A+3 | 2026-03-23 | 2026-03-27 | M/s Jwala | Mr. Saddam | Completed |  |  |  | Mar'26 |  | 24.042
14 | 11 | 125/3 | A+6 | 2026-03-23 | 2026-03-28 | M/s Ratani Devi | Mr. Mizanur/Mr. Sanjit | Completed |  |  |  | Mar'26 |  | 26.765
15 | 12 | 134/3 | A+6 | 2026-03-27 | 2026-03-30 | M/s Jwala | Mr. Saddam | Completed |  |  |  | Mar'26 |  | 26.765
16 | 1 | 124/4 | A+3 | 2026-03-28 | 2026-04-02 | M/S Ratani Devi | Mr. Mizanur | Completed |  |  |  | April'26 |  | 24.042
17 | 2 | 134/4 | A+3 | 2026-03-31 | 2026-04-03 | M/s Jwala | Mr.Saddam | Completed |  |  |  | April'26 |  | 24.042
18 | 3 | 134/8 | A+3 | 2026-04-04 | 2026-04-07 | M/s Jwala | Mr. Mizanur | Completed |  |  |  | April'26 |  | 24.042
19 | 4 | 134/9 | A+0 | 2026-04-07 | 2026-04-11 | M/s Jwala | Mr. Mizanur | Completed |  |  |  | April'26 |  | 22.925
20 | 5 | 134/7 | A+3 | 2026-04-12 | 2026-04-15 | M/s Jwala | Sanjit | Completed |  |  |  | April'26 |  | 24.042
21 | 6 | 134/5 | A+0 | 2026-04-15 | 2026-04-19 | M/s Jwala | Sanjit | Completed |  |  |  | April'26 |  | 22.925
22 | 7 | 136/2 | A+0 | 2026-04-19 | 2026-04-23 | M/s Jwala | Sanjit | Completed |  |  |  | April'26 |  | 22.925
23 | 8 | 136/1 | A+0 | 2026-04-24 | 2026-04-28 | M/s Jwala Singh | Sanjit | Completed |  |  |  | April'26 |  | 22.925
24 | 1 | 136/3 | A+3 | 2026-04-28 | 2026-05-02 | M/s Jwala Singh | Sanjit | Completed |  |  |  | May'26 |  | 24.042
25 | 2 | 136/4 | A+0 | 2026-05-02 | 2026-05-04 | M/s Jwala Singh | Mr. Hulas & Mr. Jogindra | Completed |  |  |  | May'26
26 | 3 | 121/2 | A+6 | 2026-04-28 | 2026-05-04 | M/S Gagan Entp. | Mr. Jayanta ,& Mr. Istiyak | Completed |  |  |  | May'26
27 | 4 | 102/7 | A+0 | 2026-04-28 | 2026-05-04 | M/s Aravali Infrastructure | Mr. Sanjit & Mr. Zeshan | Completed |  |  |  | May'26
28 | 5 | 116/2 | A+3 | 2026-04-28 | 2026-05-04 | M/s Amrendra Prasad | Mr. Mizanur & Mr. Ambrish | Completed |  |  |  | May'26
29 | 6 | 136/5 | A+0 | 2026-05-04 | 2026-05-08 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
30 | 7 | 121/1 | A+0 | 2026-05-04 | 2026-05-08 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
31 | 8 | 116/1 | A+3 | 2026-05-04 | 2026-05-09 | M/s Amrendra Prasad | Mr. Mizanur | Completed |  |  |  | May'26
32 | 9 | 109/1 | A+3 | 2026-05-03 | 2026-05-10 | M/s Mukesh Kumar Verma | Mr. Mizanur & Mr. Ambrish | Completed |  |  |  | May'26
33 | 10 | 139/2 | A+0 | 2026-05-08 | 2026-05-12 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
34 | 11 | 121/4 | A+0 | 2026-05-08 | 2026-05-12 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
35 | 12 | 111/1 | A+0 | 2026-05-09 | 2026-05-14 | M/s Amrendra Prasad | Mr. Mizanur | Completed |  |  |  | May'26
36 | 13 | 139/5 | A+0 | 2026-05-09 | 2026-05-15 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
37 | 14 | 109/2 | A+0 | 2026-05-10 | 2026-05-16 | M/s Mukesh Kumar Verma | Mr. Ambrish | Completed |  |  |  | May'26
38 | 15 | 121/7 | A+0 | 2026-05-12 | 2026-05-16 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
39 | 16 | 136/8 | A+0 | 2026-05-16 | 2026-05-18 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
40 | 17 | 121/6 | A+0 | 2026-01-16 | 2026-05-18 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
41 | 18 | 111/2 | A+3 | 2026-05-15 | 2026-05-18 | M/s Amrendra Prasad | Mr. Mizanur | Completed |  |  |  | May'26
42 | 19 | 121/5 | A+0 | 2026-05-18 | 2026-05-20 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
43 | 20 | 139/1 | A+3 | 2026-05-18 | 2026-05-21 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
44 | 21 | 109/5 | A+3 | 2026-05-17 | 2026-05-21 | M/s Mukesh Kumar Verma | Mr. Ambrish | Completed |  |  |  | May'26
45 | 22 | 111/3 | A+0 | 2026-05-18 | 2026-05-22 | M/s Amrendra Prasad | Mr. Mizanur | Completed |  |  |  | May'26
46 | 23 | 124/5 | A+6 | 2026-05-21 | 2026-05-23 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
47 | 24 | 125/1 | A+3 | 2026-05-23 | 2026-05-25 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
48 | 25 | 111/4 | A+0 | 2026-05-23 | 2026-05-26 | M/s Amrendra Prasad | Mr. Mizanur | Completed |  |  |  | May'26
49 | 26 | 109/6 | A+3 | 2026-05-21 | 2026-05-28 | M/s Mukesh Kumar Verma | Mr. Ambrish | Completed |  |  |  | May'26
50 | 27 | 136/0 | C2+9 | 2206-05-22 | 2026-05-29 | M/s Jwala Singh | Mr. Hulash | Completed |  |  |  | May'26
51 | 28 | 125/0 | B2+3 | 2026-05-26 | 2026-05-29 | M/S Gagan Entp. | Mr. Jayanta | Completed |  |  |  | May'26
1
Formulas:
Complete = [Start]+5

## WIP
xz
DAILY PROGRESS REPORT (Activity Wise WIP ) | [9 empty] | 2026-05-30 20:29
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
FOUNDATION
S.NO. | LOC. NO. | Tower Type | Type of FDN | GANG NAME | Man power | Start Date | Completion Date | Section Incharge | Engineer/Supervisor | REMARKS
1 | 70/0 | C2-3 | DFR | Soham Entp |  | 2026-05-03 |  | Mr. Ajay | Mr. vishnu Nair | Excavation WIP
2 | 76/4 | A+0 | DFR | Soham Entp |  | 2026-05-21 |  | Mr. Ajay | Mr. vishnu Nair | B Frustum & A, D Pyramid Completed
3 | 90/0 | C1+0 | DFR | Afflux |  | 2026-05-17 |  | Mr. Ajay | Mr. vishnu Nair | A,B,C & D Stub Setting Done
4 | 64/4 | A+0 | DFR | Afflux |  | 2026-05-25 |  | Mr. Ajay | Mr. vishnu Nair | Excavation Completed
5 | 64/5 | A+3 | Wet Paddy | Afflux |  | 2026-05-25 |  | Mr. Ajay | Mr. vishnu Nair | A,B,C & D Steel binding Done
6 | 104/0 | B2+3 | Wet Paddy | Sawariya |  | 2026-04-18 |  | Mr. Tanmay | Mr. Wahijuddin Biswas | Pit C RCC & Pit D Frustum & Pyramid Completed. | Labour Unvailble
8 | 107/3 | A+3 |  | Dhanraj |  | 2026-03-21 |  | Mr. Tanmay | Mr. Wahijuddin Biswas
7 | 104/1 | A+9 |  | Sawariya |  | 2026-05-29 |  | Mr. Ajay | Mr. vishnu Nair | Excavation WIP
8 | 116/0 | C2+3 | DFR | B.L Construction |  | 2026-05-24 |  | Mr. Ajay | Mr. vishnu Nair | Pit D Frustum Completed
9 | 132/2 | A+0 | DFR | Jai Shree Ram |  | 2026-05-05 | 2026-05-30 | Mr. Tanmay | Mr. Wahijuddin Biswas | Pit A, B C & D Chimney Completed
10 | 102/6 | A+0 |  | Shiv Shakti |  | 2026-04-16 |  | Mr. Tanmay | Mr. Wahijuddin Biswas | Pit Marking Done
ERECTION
S.NO. | LOC. NO. | Tower Type | GANG NAME | Start Date | Completion Date | Status | Engineer/ Supervisor | REMARKS
1 | 127/3 | A+0 | M/s Jwala Singh | 2026-05-30 |  | Gang Shifting | Mr. Hulash
2 | 124/5 | A+6 | M/S Gagan Entp. | 2026-05-30 |  | Bottom Section WIP | Mr. Jayanta
3 | 111/5 | A+6 | M/s Amrendra Prasad | 2026-05-27 |  | Height Section WIP | Mr. Mizanur
4 | 109/7 | A+3 | M/s Mukesh Kumar Verma | 2026-05-21 |  | Bottom WIP | Mr. Sanjit
STRINGING
S.NO. | From |  | Length in Km's | Insulator Hoisting | Drone OPS | Paying Out Start | Paying Out Completed | Final sag | Name of the Contractor | Status | Remarks
OPGW
S.NO. | From |  | Length in Km's | Paying Out Start | Paying Out Completed | Final sag | Name of the Contractor | Remarks

## Visual Chart
KEC INTERNATIONAL LIMITED
l
Name of Line: ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
CLIENT : M/S Powergrid West Central Transmission Ltd.
Date of Commencemen : 13-05-2025
| VISUAL CHART | [44 empty] | Progress as on date : |  |  | 2026-05-30 20:29
[45 empty] | CUM. | Total Loc. | BALANCE
[47 empty] | FDN. | Erec. | Earth | Tack Weld | String ing
[9 empty] | Route Diversion Proposed | [7 empty] | No Diversion DS Submitted | [21 empty] | Route Diversion Proposed
[9 empty] | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  |  | 12 | 0 | 0 | 0 | 0
[9 empty] | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D1 | A1
[9 empty] | 0 | - | 337 | 0 | - | 404 | 0 | - | 309 | 0 | - | 317 | 0 | - | 395 | 0 | - | 361 | 0 | - | 434 | 0 | - | 347 | 0 | - | 344 | 0 | - | 379 | 0 | - | 336 | 0 | - | 439.86 | [7 empty] | 4402.86
[9 empty] | 0/0 |  |  | 0/1 |  |  | 0/2 |  |  | 1/0 |  |  | 2/0 |  |  | 2/1 |  |  | 3/0 |  |  | 3/1 |  |  | 3/2 |  |  | 3/3 |  |  | 4/0 |  |  | 5/0
[9 empty] | D60+9 |  |  | A+9 |  |  | A+9 |  |  | D60(-)3 |  |  | D45+3 |  |  | A+0 |  |  | C2+0 |  |  | A+1.5 |  |  | A(-)3 |  |  | A(-)3 |  |  | D60+0 |  |  | B2+9
[9 empty] | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 |  |  | 11 |  |  | 12
|  | Route Diversion Proposed | [14 empty] | DS Submitted | Route Diverison Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 437 | 0 | - | 335.734 | 0 | - |  | 0 | - | 341.753 | 0 | - | 407.786 | 0 | - | 412 | 0 | - | 426.82 | 0 | - | 337 | 0 | - | 454 | 0 | - | 344.906 | 0 | - | 399 | 0 | - | 379.984 | 0 | - | 464 | 0 | - | 364 | [7 empty] | 5103.983
|  |  | 6/0 |  |  | 6/1 |  |  | 7/0 |  |  | 8/0 |  |  | 9/0 |  |  | 10/0 |  |  | 10/1 |  |  | 11/0 |  |  | 11/1 |  |  | 11/2 |  |  | 12/0 |  |  | 12/1 |  |  | 13/0 |  |  | 13/1
|  |  | D45+3 |  |  | A+6 |  |  | B2(-)3 |  |  | C1+9 |  |  | D45+9 |  |  | C1+3 |  |  | A+6 |  |  | C1+3 |  |  | A+6 |  |  | A+6 |  |  | C1+9 |  |  | A+6 |  |  | D45+0 |  |  | A+9
|  |  | 13 |  |  | 14 |  |  | 15 |  |  | 16 |  |  | 17 |  |  | 18 |  |  | 19 |  |  | 20 |  |  | 21 |  |  | 22 |  |  | 23 |  |  | 24 |  |  | 25 |  |  | 26
|  | Route Diversion Proposed | [17 empty] | No Diversion DS Submitted
|  |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C1 | B1 |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D1 | A1 |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D1 | A1 |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 454 | 0 | - | 379.923 | 0 | - | 422.762 | 0 | - | 446 | 0 | - | 389.71 | 0 | - | 480.749 | 0 | - | 176 | 0 | - | 212 | 0 | - | 220 | 0 | - | 434 | 0 | - | 431 | 0 | - | 440 | 0 | - | 0 | 0 | - | 362 | [7 empty] | 4848.144
|  |  | 13/2 |  |  | 13/3 |  |  | 14/0 |  |  | 15/0 |  |  | 15/1 |  |  | 16/0 |  |  | 17/0 |  |  | 18/0 |  | NH-56 | 19/0 |  |  | 20/0 |  |  | 21/0 |  |  | 22/0 |  |  | 23/0 |  |  | 23/1
|  |  | A+6 |  |  | A+6 |  |  | D45+3 |  |  | B2+0 |  |  | A+3 |  |  | B2+6 |  |  | D45+3 |  |  | D45+0 |  |  | D60(-)3 |  |  | D45+6 |  |  | C2+9 |  |  | D60+0 |  |  | D60+3 |  |  | A+0
|  |  | 27 |  |  | 28 |  |  | 29 |  |  | 30 |  |  | 31 |  |  | 32 |  |  | 33 |  |  | 34 |  |  | 35 |  |  | 36 |  |  | 37 |  |  | 38 |  |  | 39 |  |  | 40
Route Diveriosn Proposed
|  |  | C2 | B2 |  | C2 | B2 |  | C2 | B2 |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D2 | A2 |  | D2 | A2 |  | D2 | A2 |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 365 | 0 | - | 365 | 0 | - | 390 | 0 | - | 390 | 0 | - | 381 | 0 | - | 390 | 0 | - | 369 | 0 | - | 432 | 0 | - | 446 | 0 | - | 395 | 0 | - | 400 | 0 | - | 440 | 0 | - | 439 | 0 | - | 372 | [7 empty] | 5574
|  |  | 23/2 |  |  | 23/3 |  |  | AP24 |  |  | 24/1 |  |  | 24/2 |  |  | 24/3 |  |  | AP25 |  |  | AP26 |  |  | AP27 |  |  | AP28 |  |  | 28/1 |  |  | AP29 |  |  | 29/1 |  |  | AP30
|  |  | A+0 |  |  | A+0 |  |  | D45+0 |  |  | A+6 |  |  | A+3 |  |  | A+6 |  |  | C2+0 |  |  | D45+0 |  |  | D45+0 |  |  | C1+0 |  |  | A+3 |  |  | C1+6 |  |  | B1+9 |  |  | C2+6
|  |  | 41 |  |  | 42 |  |  | 43 |  |  | 44 |  |  | 45 |  |  | 46 |  |  | 47 |  |  | 48 |  |  | 49 |  |  | 50 |  |  | 51 |  |  | 52 |  |  | 53 |  |  | 54
|  |  | Route Diversion Proposed | [26 empty] | DS Submiited
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 372 | 0 | - | 370 | 0 | - | 400 | 0 | - | 360 | 0 | - | 365 | 0 | - | 428 | 0 | - | 360.723 | 0 | - | 260.002 | 0 | - | 456.806 | 0 | - | 444.778 | 0 | - | 407 | 0 | - | 400.912 | 0 | - | 407 | 0 | - | 378 | [7 empty] | 5410.221
|  |  | 30/1 |  |  | 30/2 |  |  | AP31 |  |  | AP32 |  |  | 32/1 |  |  | AP33 |  |  | 33/1 |  |  | AP34 |  |  | 34/1 |  |  | AP35 |  |  | AP36 |  |  | 36/1 |  |  | AP37 |  |  | 37/1
|  |  | A+0 |  |  | A+0 |  |  | C1+3 |  |  | D45+3 |  |  | A+0 |  |  | C1-3 |  |  | A+0 |  |  | C2+0 |  |  | A+6 |  |  | B2+3 |  |  | C1+3 |  |  | A+0 |  |  | C1+3 |  |  | A+6
|  |  | 55 |  |  | 56 |  |  | 57 |  |  | 58 |  |  | 59 |  |  | 60 |  |  | 61 |  |  | 62 |  |  | 63 |  |  | 64 |  |  | 65 |  |  | 66 |  |  | 67 |  |  | 68
|  | DS Submitted | [33 empty] | Route Diversion Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 468 | 0 | - | 379 | 0 | - | 354 | 0 | - | 388 | 0 | - | 442.971 | 0 | - | 508 | 0 | - | 313.962 | 0 | - | 386 | 0 | - | 439 | 0 | - | 362 | 0 | - | 477.962 | 0 | - | 350 | 0 | - | 350 | 0 | - | 325 | [7 empty] | 5543.895
|  |  | 37/2 |  |  | 37/3 |  |  | 37/4 |  |  | 37/5 |  |  | 37/6 |  |  | 38/0 |  |  | 38/1 |  |  | 39/0 |  |  | 39/1 |  |  | 39/2 |  |  | 39/3 |  |  | 40/0 |  |  | 40/1 |  |  | 40/2
|  |  | A+4.5 |  |  | A+4.5 |  |  | A+7.5 |  |  | A+4.5 |  |  | A+9 |  |  | B2+6 |  |  | A+6 |  |  | C2+3 |  |  | A+9 |  |  | A+0 |  |  | A+9 |  |  | C1+9 |  |  | A+1.5 |  |  | A+0
|  |  | 69 |  |  | 70 |  |  | 71 |  |  | 72 |  |  | 73 |  |  | 74 |  |  | 75 |  |  | 76 |  |  | 77 |  |  | 78 |  |  | 79 |  |  | 80 |  |  | 81 |  |  | 82
Route Diversion Proposed
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C2 | B2 |  | C | B |  | C | B |  | C | B |  | C | B |  | C3 | B3 |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D2 | A2 |  | D | A |  | D | A |  | D | A |  | D | A |  | D3 | A3 |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 386 | 0 | - | 458.967 | 0 | - | 329.873 | 0 | - | 369 | 0 | - | 466.935 | 0 | - | 304.854 | 0 | - | 214.003 | 0 | - | 433.999 | 0 | - | 414 | 0 | - | 416 | 0 | - | 334.881 | 0 | - | 356 | 0 | - | 385 | 0 | - | 379.877 | [7 empty] | 5249.389
|  |  | 42/1 |  |  | 42/2 |  |  | 43/0 |  |  | 44/0 |  |  | 44/1 |  |  | 45/0 |  | SH-26 | 46/0 |  | 400 kV SC PL | 47/0 |  |  | 47/1 |  |  | 47/2 |  |  | 47/3 |  |  | 48/0 |  |  | 48/1 |  |  | 48/2
|  |  | A+7.5 |  |  | A+9 |  |  | D45(-)3 |  |  | C2(-)3 |  |  | A+6 |  |  | C1+6 |  |  | D60+18 |  |  | D60+25 |  |  | A+3 |  |  | A+9 |  |  | A+3 |  |  | C1+0 |  |  | A+0 |  |  | A+3
|  |  | 93 |  |  | 94 |  |  | 95 |  |  | 96 |  |  | 97 |  |  | 98 |  |  | 99 |  |  | 100 |  |  | 101 |  |  | 102 |  |  | 103 |  |  | 104 |  |  | 105 |  |  | 106
|  | Route Diversion Proposed | [16 empty] | CS Appproved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 15 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 357.966 | 0 | - | 323.998 | 0 | - | 412 | 0 | - | 430.869 | 0 | - | 230 | 0 | - | 523 | 0 | - | 464 | 0 | - | 397 | 0 | - | 372.208 | 0 | - | 456.278 | 0 | - | 424.237 | 0 | - | 363 | 0 | - | 384.003 | 0 | - | 450.001 | [7 empty] | 5588.56
|  |  | 49/0 |  |  | 49A/0 |  |  | 49B/0 |  |  | 49B/1 |  |  | 50/0 |  | Rly | 51/0 |  |  | 51/1 |  |  | 52/0 |  |  | 52/1 |  |  | 53/0 |  |  | 54/0 |  |  | 55/0 |  |  | 55/1 |  |  | 55/2
|  |  | D45+6 |  |  | D45(-)3 |  |  | D45+3 |  |  | A+0 |  |  | D60+6 |  |  | D60+9 |  |  | B1+9 |  |  | C2+9 |  |  | A+0 |  |  | D45(-)3 |  |  | D60+18 |  |  | C1+9 |  |  | A(-)3 |  |  | A+9
|  |  | 107 |  |  | 108 |  |  | 109 |  |  | 110 |  |  | 111 |  |  | 112 |  |  | 113 |  |  | 114 |  |  | 115 |  |  | 116 |  |  | 117 |  |  | 118 |  |  | 119 |  |  | 120
CS Approved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 362.999 | 0 | - | 373 | 0 | - | 333 | 0 | - | 497.019 | 0 | - | 355 | 0 | - | 439 | 0 | - | 408 | 0 | - | 438 | 0 | - | 258 | 0 | - | 323 | 0 | - | 331.079 | 0 | - | 392.003 | 0 | - | 400 | 0 | - | 400 | [7 empty] | 5310.1
|  |  | 56/0 |  |  | 56/1 |  |  | 57/0 |  |  | 57/1 |  |  | 58/0 |  |  | 58/1 |  |  | 58/2 |  |  | 58/3 |  |  | 59/0 |  | 132 kV SC PL | 60/0 |  |  | 60/1 |  |  | 61/0 |  |  | 62/0 |  |  | 62/1
|  |  | B2+9 |  |  | A+9 |  |  | C1+3 |  |  | A+9 |  |  | C2+9 |  |  | A+9 |  |  | A+9 |  |  | A+6 |  |  | D45+9 |  |  | D45+6 |  |  | A+0 |  |  | D45+0 |  |  | C2+0 |  |  | A+6
|  |  | 121 |  |  | 122 |  |  | 123 |  |  | 124 |  |  | 125 |  |  | 126 |  |  | 127 |  |  | 128 |  |  | 129 |  |  | 130 |  |  | 131 |  |  | 132 |  |  | 133 |  |  | 134
CS Appprved
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 400 | 0 | - | 402 | 0 | - | 400 | 0 | - | 400 | 0 | - | 410 | 0 | - | 410 | 0 | - | 395 | 0 | - | 388 | 0 | - | 382 | 0 | - | 406 | 0 | - | 380 | 0 | - | 436 | 0 | - | 409.052 | 0 | - | 423 | [7 empty] | 5641.052
|  |  | 62/2 |  |  | 62/3 |  |  | AP63 |  |  | 63/1 |  |  | 63/2 |  |  | 63/3 |  |  | 63/4 |  |  | AP-64 |  |  | 64/1 |  |  | 64/2 |  |  | 64/3 |  |  | 64/4 |  |  | 64/5 |  |  | 65/0
|  |  | A+6 |  |  | A+6 |  |  | C1+3 |  |  | A+9 |  |  | A+6 |  |  | A+6 |  |  | A+3 |  |  | B2+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | B2+0
146
|  |  | 135 |  |  | 136 |  |  | 137 |  |  | 138 |  |  | 139 |  |  | 140 |  |  | 141 |  |  | 142 |  |  | 143 |  |  | 144 |  |  | 145 |  |  | 146 |  |  | 147 |  |  | 148
CS Approved
[33 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 12 | 0 | 0 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 4 | 0 | 3 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 372.008 | 0 | - | 369.995 | 0 | - | 352 | 0 | - | 432 | 0 | - | 417 | 0 | - | 428.062 | 0 | - | 379 | 0 | DFR | 396 | 0 | - | 396.008 | 0 | - | 400 | E | - | 397 | E | - | 378.998 | E | - | 379 | 0 | - | 352.701 | [7 empty] | 5449.772
|  |  | 65/1 |  |  | 66/0 |  |  | 67/0 |  |  | 67/1 |  |  | 67/2 |  |  | 67/3 |  |  | 68/0 |  |  | 68/1 |  |  | 68/2 |  |  | 69/0 |  |  | 69/1 |  |  | 69/2 |  |  | 69/3 |  |  | 69/4
|  |  | A+0 |  |  | D45+0 |  |  | D60+0 |  |  | A+0 |  |  | A+6 |  |  | A+6 |  |  | D45+0 |  |  | A+0 |  |  | A+3 |  |  | D45+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0
|  |  | 149 |  |  | 150 |  |  | 151 |  |  | 152 |  |  | 153 |  |  | 154 |  |  | 155 |  |  | 156 |  |  | 157 |  |  | 158 |  |  | 159 |  |  | 160 |  |  | 161 |  |  | 162
CS Approved
[46 empty] | 24 | #REF! | #REF! | 0 | #REF!
[6 empty] | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 7 | 0 | 6 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 280 | E | DFR | 372 | E | WFR | 474 | E | DFR | 308.817 | 0 | - | 434.999 | E |  | 411.001 | E | - | 322 | E | - | 374 | 0 | - | 377 | 0 | - | 417.747 | 0 | - | 450 | 0 | - | 386.804 | 0 | - | 295.747 | 0 | - | 244.846 | [7 empty] | 5148.961
|  |  | 70/0 |  |  | 70/1 |  |  | 70/2 |  |  | 70/3 |  |  | 71/0 |  |  | 71/1 |  |  | 71/2 |  |  | 71/3 |  |  | 71/4 |  |  | 71/5 |  |  | 72/0 |  |  | 72/1 |  |  | 73/0 |  |  | 74/0
|  |  | C2-3 |  |  | A+4.5 |  |  | A+9 |  |  | A-3 |  |  | D45+3 |  |  | A+3 |  |  | A-3 |  |  | A+0 |  |  | A-3 |  |  | A+0 |  |  | D45+3 |  |  | A+9 |  |  | D45+3 |  |  | C2+18
|  |  | 163 |  |  | 164 |  |  | 165 |  |  | 166 |  |  | 167 |  |  | 168 |  |  | 169 |  |  | 170 |  |  | 171 |  |  | 172 |  |  | 173 |  |  | 174 |  |  | 175 |  |  | 176
|  | DS Submitted | [12 empty] | CS Approved
[18 empty] | FC |  |  | FC | [8 empty] | FC |  |  | FC | [5 empty] | FC | [6 empty] | 55 | #REF! | 0 | 0 | #REF!
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 5 | 0 | 4 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 338 | 0 | - | 324 | 0 | - | 261 | 0 | - | 315 | 0 | - | 426 | E | DFR | 418.999 | E | DFR | 367 | 0 | - | 431 | 0 | - | 403 | E | - | 438 | 0 | DFR | 356.71 | 0 | - | 305 | E | DFR | 337.839 | 0 | - | 317 | [7 empty] | 5038.548
|  | 132 kV SC PL | 75/0 |  |  | 75/1 |  |  | 75/2 |  |  | 75/3 |  |  | 76/0 |  |  | 76/1 |  |  | 76/2 |  |  | 76/3 |  |  | 76/4 |  |  | 76/5 |  |  | 76/6 |  |  | 77/0 |  |  | 77/1 |  |  | 78/0
|  |  | B2+9 |  |  | A+9 |  |  | A+0 |  |  | A+0 |  |  | C2+0 |  |  | A+6 |  |  | A+6 |  |  | A-3 |  |  | A+0 |  |  | A+9 |  |  | A+1.5 |  |  | B2+0 |  |  | A-3 |  |  | C2-3
|  |  | 177 |  |  | 178 |  |  | 179 |  |  | 180 |  |  | 181 |  |  | 182 |  |  | 183 |  |  | 184 |  |  | 185 |  |  | 186 |  |  | 187 |  |  | 188 |  |  | 189 |  |  | 190
CS Approved
[24 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 2 | 0 | 2 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 317.777 | 0 | - | 457 | 0 | - | 389.816 | 0 | - | 298.846 | 0 | - | 330.931 | 0 | - | 338.998 | 0 | - | 427 | E | WFR | 401 | E | WET | 479.823 | 0 | - | 435 | 0 | - | 410 | 0 | - | 365 | 0 | - | 466.431 | 0 | - | 421.53 | [7 empty] | 5539.152
|  |  | 78/1 |  |  | 79/0 |  |  | 79/1 |  |  | 80/0 |  | 132 kV SC PL | 81/0 |  | SH-39 | 82/0 |  |  | 82/1 |  |  | 82/2 |  |  | 82/3 |  | River-Wagh | 83/0 |  |  | 83/1 |  |  | 83/2 |  |  | 83/3 |  |  | 85/0
|  |  | B1-3 |  |  | D45+3 |  |  | A+9 |  |  | B1-3 |  |  | B1+6 |  |  | C1+0 |  |  | A+0 |  |  | A+7.5 |  |  | A+9 |  |  | C2+0 |  |  | A+3 |  |  | A+9 |  |  | A+9 |  |  | B1+3
|  |  | 191 |  |  | 192 |  |  | 193 |  |  | 194 |  |  | 195 |  |  | 196 |  |  | 197 |  |  | 198 |  |  | 199 |  |  | 200 |  |  | 201 |  |  | 202 |  |  | 203 |  |  | 204
CS Approved
[12 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 8 | 0 | 6 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 208 | 0 | - | 449 | 0 | - | 398 | E | - | 404 | E | - | 427 | E | - | 400 | E | - | 386 |  | - | 400 | E | - | 442 | E | - | 384 |  | - | 390 |  | - | 539 |  | - | 412 |  | - | 375 | [7 empty] | 5614
|  | SH-26 | 86/0 |  | 132 kV SC PL | 87/0 |  |  | 87/1 |  |  | 87/2 |  |  | 87/3 |  |  | 87/4 |  |  | 87/5 |  |  | 88/0 |  |  | 88/1 |  |  | 88/2 |  |  | 88/3 |  |  | 88/4 |  |  | 88/5 |  |  | 88/6
|  |  | C1+6 |  |  | C1+9 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | C2+3 |  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | B1+3 |  |  | B1+0 |  |  | A+0
|  |  | 205 |  |  | 206 |  |  | 207 |  |  | 208 |  |  | 209 |  |  | 210 |  |  | 211 |  |  | 212 |  |  | 213 |  |  | 214 |  |  | 215 |  |  | 216 |  |  | 217 |  |  | 218
CS Approved
[33 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 14 | 4 | 0 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 423 | 0 | - | 340 | 0 | - | 395 | 0 | - | 370 | 0 | - | 330 | 0 | - | 393 | 0 | - | 387 | 0 | - | 381 | 0 | - | 405 | 0 | - | 425 | E | DFR | 399 | E | DFR | 390 | E | DFR | 373 | E | DFR | 401 | [7 empty] | 5412
|  |  | 88/7 |  |  | 88/8 |  |  | 88/9 |  |  | 88/10 |  |  | 88/11 |  |  | 89/0 |  | River-Wagh uri | 89/1 |  |  | 89/2 |  |  | 89/3 |  |  | 89/4 |  |  | 89/5 |  |  | 89/6 |  |  | 89/7 |  |  | 89/8
|  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | A+0 |  |  | A-3 |  |  | C2+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0
|  |  | 219 |  |  | 220 |  |  | 221 |  |  | 222 |  |  | 223 |  |  | 224 |  |  | 225 |  |  | 226 |  |  | 227 |  |  | 228 |  |  | 229 |  |  | 230 |  |  | 231 |  |  | 232
CS Approved
FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 1 | 0 | 1 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WFR | 369.825 | 0 | - | 390 | 0 | - | 387 | 0 | - | 392 | 0 | - | 394 | 0 | - | 401 | 0 | - | 426 | 0 | - | 378 | 0 | - | 422 | 0 | - | 425 | 0 | - | 407 | 0 | - | 378 | 0 | - | 376.944 | 0 | - | 405 | [7 empty] | 5551.769
|  |  | 89/9 |  |  | 90/0 |  |  | 90/1 |  |  | 90/2 |  |  | 90/3 |  |  | 90/4 |  |  | 90/5 |  |  | 90/6 |  |  | 90/7 |  |  | 90/8 |  |  | 90/9 |  |  | 90/10 |  |  | 90/11 |  |  | AP91
|  |  | A+0 |  |  | C1+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A-3 |  |  | A+6 |  |  | A+6 |  |  | A-3 |  |  | A+0 |  |  | B2+0
|  |  | 233 |  |  | 234 |  |  | 235 |  |  | 236 |  |  | 237 |  |  | 238 |  |  | 239 |  |  | 240 |  |  | 241 |  |  | 242 |  |  | 243 |  |  | 244 |  |  | 245 |  |  | 246
CS Appproved
[46 empty] | 14 | 0 | 0 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 402 | 0 | - | 424 | 0 | - | 404 | 0 | - | 398 | 0 | - | 376 | 0 | - | 337 | 0 | - | 368 | 0 | - | 402 | 0 | - | 416 | 0 | - | 399 | 0 | - | 408 | 0 | - | 378 | 0 | - | 369 | 0 | - | 410 | [7 empty] | 5491
|  |  | 91/1 |  |  | 91/2 |  |  | 91/3 |  |  | 91/4 |  |  | 91/5 |  |  | 91/6 |  |  | 91/7 |  |  | 91/8 |  |  | 91/9 |  |  | 91/10 |  |  | AP92 |  |  | 92/1 |  |  | 92/2 |  |  | 92/3
|  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A-3 |  |  | A-3 |  |  | A+0 |  |  | A+1.5 |  |  | A+3 |  |  | C2+0 |  |  | A+3 |  |  | A-3 |  |  | A+0
|  |  | 247 |  |  | 248 |  |  | 249 |  |  | 250 |  |  | 251 |  |  | 252 |  |  | 253 |  |  | 254 |  |  | 255 |  |  | 256 |  |  | 257 |  |  | 258 |  |  | 259 |  |  | 260
|  | CS Approved | [23 empty] | DS Submitted
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 0 | 0 | 0 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 416 | 0 | - | 392 | 0 | - | 381 | 0 | - | 380 | 0 | - | 397 | 0 | - | 407 | 0 | - | 412.8 | 0 | - | 0 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | [7 empty] | 5179.8
|  |  | 92/4 |  |  | AP93 |  |  | 93/1 |  |  | 93/2 |  |  | 93/3 |  |  | 93/4 |  |  | 93/5 |  |  | 94/0 |  |  | 94/1 |  |  | 94/2 |  |  | 94/3 |  |  | 94/4 |  |  | 94/5 |  |  | 94/6
|  |  | A+3 |  |  | C2+0 |  |  | A+1.5 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | B2+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3
|  |  | 261 |  |  | 262 |  |  | 263 |  |  | 264 |  |  | 265 |  |  | 266 |  |  | 267 |  |  | 268 |  |  | 269 |  |  | 270 |  |  | 271 |  |  | 272 |  |  | 273 |  |  | 274
|  | DS Submitted | [27 empty] | CS Approved
[46 empty] | 14 | 2 | 0 | 2 | 0
[33 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 399 | 0 | - | 399 | 0 | - | 399 | 0 | - | 300 | 0 | - | 855 | 0 | - | 300 | 0 | - | 399 | 0 | - | 390 | 0 | - | 390 | 0 | - | 409 | E | WET PADDY | 420 | E | WET PADDY | 423 | 0 | - | 400 | 0 | - | 372 | [7 empty] | 5855
|  |  | 94/7 |  |  | 94/8 |  |  | 94/9 |  |  | AP95 |  |  | AP96 |  | Narmda River | AP97 |  |  | AP98 |  |  | 98/1 |  |  | 98/2 |  |  | 99/0 |  |  | 99/1 |  |  | 99/2 |  |  | 99/3 |  |  | 99/4
|  |  | A+0 |  |  | A+6 |  |  | A+6 |  |  | D60+15 |  |  | D60+55 |  |  | D60+55 |  |  | D60+15 |  |  | A+6 |  |  | A+3 |  |  | C1+0 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+0
|  |  | 275 |  |  | 276 |  |  | 277 |  |  | 278 |  |  | 279 |  |  | 280 |  |  | 281 |  |  | 282 |  |  | 283 |  |  | 284 |  |  | 285 |  |  | 286 |  |  | 287 |  |  | 288
CS Approved
EC
[18 empty] | FC | [17 empty] | FC |  |  | FC |  |  | FC |  |  |  | 14 | 4 | 1 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 474 | 0 | - | 224 | 0 | - | 409 | 0 | - | 374 | 0 | - | 413 | E | WET PADDY | 393 | 0 | - | 435 | 0 | - | 390 | 0 | - | 416 | 0 | - | 403 | 0 | - | 384 | E | WET PADDY | 382 | E | WET PADDY | 407 | E | WET PADDY | 398 | [7 empty] | 5502
|  |  | 99/5 |  |  | 100/0 |  | 132 kV SC PL | 101/0 |  |  | 101/1 |  |  | 102/0 |  |  | 102/1 |  |  | 102/2 |  |  | 102/3 |  |  | 102/4 |  |  | 102/5 |  |  | 102/6 |  |  | 102/7 |  |  | 102/8 |  |  | 102/9
|  |  | A+6 |  |  | C1+9 |  |  | D60+9 |  |  | A+0 |  |  | C1+0 |  |  | A+9 |  |  | A+9 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+3
|  |  | 289 |  |  | 290 |  |  | 291 |  |  | 292 |  |  | 293 |  |  | 294 |  |  | 295 |  |  | 296 |  |  | 297 |  |  | 298 |  |  | 299 |  |  | 300 |  |  | 301 |  |  | 302
CS Approved
[6 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC | [20 empty] | FC |  |  | FC |  |  |  | 14 | 6 | 0 | 4 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 395 | E | - | 450 | 0 | - | 464 | E | WET PADDY | 385 | E | WET PADDY | 334 | E | WET PADDY | 426 | 0 | - | 411 | 0 | - | 325 | 0 | - | 452 | 0 | - | 245 | 0 | - | 424 | 0 | - | 424.702 | 0 | - | 390 |  | WFR | 350 | [7 empty] | 5475.702
|  |  | 102/10 |  |  | 102/11 |  |  | 103/0 |  |  | 103/1 |  |  | 103/2 |  |  | 103/3 |  |  | 104/0 |  |  | 104/1 |  |  | 104/2 |  |  | 105/0 |  | NH-347 | 106/0 |  |  | 106/1 |  |  | 107/0 |  |  | 107/1
|  |  | A+0 |  |  | A+9 |  |  | C1+3 |  |  | A+6 |  |  | A+0 |  |  | A+3 |  |  | B2+3 |  |  | A+9 |  |  | A+7.5 |  |  | C2+6 |  |  | B2+0 |  |  | A+6 |  |  | C2+3 |  |  | A+0
|  |  | 303 |  |  | 304 |  |  | 305 |  |  | 306 |  |  | 307 |  |  | 308 |  |  | 309 |  |  | 310 |  |  | 311 |  |  | 312 |  |  | 313 |  |  | 314 |  |  | 315 |  |  | 316
CS APProved
EC
|  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  | FC | [8 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 9 | 1 | 5 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | WFR | 378 | 0 | - | 434 | 0 | DFR | 415 | 0 | - | 327.835 | 0 | - | 370 | E | DFR | 463 | 0 | - | 289 | 0 | - | 384 | 0 | WFR | 381 | E | WET PADDY | 300 | E | WET PADDY | 337 | E | WET PADDY | 351.969 | 0 | - | 377 | E | WET PADDY | 290 | [7 empty] | 5097.804
|  |  | 107/2 |  |  | 107/3 |  |  | 107/4 |  |  | 107/5 |  |  | 108/0 |  |  | 108/1 |  |  | 108/2 |  |  | 108/3 |  |  | 108/4 |  |  | 108/5 |  |  | 108/6 |  |  | 108/7 |  |  | 109/0 |  |  | 109/1
|  |  | A-3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | C1+9 |  |  | A+9 |  |  | A+0 |  |  | A+9 |  |  | A+3 |  |  | A-3 |  |  | A-3 |  |  | A-3 |  |  | B2+0 |  |  | A+3
ROW
|  |  | 317 |  |  | 318 |  |  | 319 |  |  | 320 |  |  | 321 |  |  | 322 |  |  | 323 |  |  | 324 |  |  | 325 |  |  | 326 |  |  | 327 |  |  | 328 |  |  | 329 |  |  | 330
CS Approved
|  |  | EC | [42 empty] | 14 | 11 | 0 | 0 | 0
|  |  | FC | [8 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WET PADDY | 426 | 0 | WET PADDY | 408 | 0 | - | 413 | E | DFR | 386 | E | DFR | 360 | E | DFR | 435 | 0 | - | 414 | 0 | DFR | 413 | E | DFR | 405 | 0 | DFR | 423.811 | 0 | - | 449 | E | DFR | 395 | E | DFR | 357 | E | DFR | 423 | [7 empty] | 5707.811
|  |  | 109/2 |  |  | 109/3 |  |  | 109/4 |  |  | 109/5 |  |  | 109/6 |  |  | 109/7 |  |  | 109/8 |  |  | 109/9 |  |  | 109/10 |  |  | 109/11 |  |  | 110/0 |  |  | 110/1 |  |  | 110/2 |  |  | 110/3
|  |  | A+0 |  |  | A+9 |  |  | A-3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A+3 |  |  | A-3 |  |  | A+3 |  |  | D45+3 |  |  | A+7.5 |  |  | A+0 |  |  | A+0
|  |  | 331 |  |  | 332 |  |  | 333 |  |  | 334 |  |  | 335 |  |  | 336 |  |  | 337 |  |  | 338 |  |  | 339 |  |  | 340 |  |  | 341 |  |  | 342 |  |  | 343 |  |  | 344
CS Appproved
[10 empty] | EC |  | EC
|  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [24 empty] | 14 | 6 | 2 | 5 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | DFR | 329 | 0 | - | 373 | E | DFR | 419 | E | DFR | 397 | E | WFR | 374 | E | DFR | 390 | E | DFR | 385 | 0 | - | 432 | 0 | - | 391 | 0 | - | 230 | 0 | - | 286 | 0 | - | 475 | 0 | - | 229 | 0 | - | 218 | [7 empty] | 4928
|  |  | 110/4 |  |  | 111/0 |  |  | 111/1 |  |  | 111/2 |  |  | 111/3 |  |  | 111/4 |  |  | 111/5 |  |  | 111/6 |  |  | 111/7 |  |  | 111A/0 |  | Rly | 111B/0 |  |  | 111B/1 |  |  | 112/0 |  | 132 kV SC PL | 113/0
|  |  | A+0 |  |  | D45+6 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+6 |  |  | A+0 |  |  | A+0 |  |  | D60+9 |  |  | D60+6 |  |  | A+0 |  |  | D45+18 |  |  | B1+9 (RC = 3M)
|  |  | 345 |  |  | 346 |  |  | 347 |  |  | 348 |  |  | 349 |  |  | 350 |  |  | 351 |  |  | 352 |  |  | 353 |  |  | 354 |  |  | 355 |  |  | 356 |  |  | 357 |  |  | 358
CS Appproved
[19 empty] | EC |  | EC
[18 empty] | FC |  |  | FC | [24 empty] | 14 | 2 | 2 | 2 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 187 | 0 | - | 595 | 0 | - | 310 | 0 | - | 325 | 0 | - | 410 | E | DFR | 424 | E | DFR | 379 | 0 | - | 378 | 0 | - | 384 | 0 | - | 254 | 0 | - |  | 0 | - | 244 | 0 | - | 246 | 0 | - | 518 | [7 empty] | 4654
|  |  | 114/0 |  | 132 kV SC PL | 115/0 |  |  | 115/1 |  |  | 115/2 |  |  | 116/0 |  |  | 116/1 |  |  | 116/2 |  |  | 116/3 |  |  | 117/0 |  |  | 117/1 |  | Rly | 118/0 |  | NH-52 | 119/0 |  | 220 kV SC PL | 120/0 |  |  | 121/0
|  |  | B1+18 |  |  | D45+18 |  |  | B1+3(RC 1M) |  |  | A+0 |  |  | C1+3 |  |  | A+3 |  |  | A+3 |  |  | A+9 |  |  | B2+3 |  |  | A+0 |  |  | B1+0 |  |  | C1+18(RC2M) |  |  | D45+18 |  |  | B2+0
|  |  | 359 |  |  | 360 |  |  | 361 |  |  | 362 |  |  | 363 |  |  | 364 |  |  | 365 |  |  | 366 |  |  | 367 |  |  | 368 |  |  | 369 |  |  | 370 |  |  | 371 |  |  | 372
CS Approved
|  |  |  | FC |  | EC | [6 empty] | EC |  |  | EC |  |  | EC |  |  | EC | [16 empty] | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC | [8 empty] | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 9 | 6 | 7 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 430 | E | DFR | 415 | 0 | - | 415 | E | DFR | 425 | E | DFR | 415 |  | DFR | 400 | E | WFR | 337 | 0 | - | 331 | 0 | - | 442 | E | DFR | 435 | 0 | - | 297.195 | 0 | - | 322 | E | WFR | 451 | 0 | - | 379.154 | [7 empty] | 5494.349
|  |  | 121/1 |  |  | 121/2 |  |  | 121/3 |  |  | 121/4 |  |  | 121/5 |  |  | 121/6 |  |  | 121/7 |  |  | 121/8 |  |  | 121/9 |  |  | 121/10 |  |  | 122/0 |  |  | 122/1 |  |  | 122/2 |  |  | 123/0
|  |  | A+0 |  |  | A+6 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B1+3 |  |  | A+9 |  |  | B1+3 |  |  | B1+9 |  |  | A+0 |  |  | B2+0
|  |  | 373 |  |  | 374 |  |  | 375 |  |  | 376 |  |  | 377 |  |  | 378 |  |  | 379 |  |  | 380 |  |  | 381 |  |  | 382 |  |  | 383 |  |  | 384 |  |  | 385 |  |  | 386
CS Appproved
[28 empty] | EC | [14 empty] | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  |  | 14 | 12 | 2 | 9 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | WFR | 365 | E | WFR | 371 | E | DFR | 395 | E | WET | 449 | E | - | 394.576 | E | WET PADDY | 455 | E | WFR | 393 | E | WFR | 452 | E | WFR | 396 | 0 | - | 442 | 0 | - | 407 | 0 | - | 424 | 0 | WFR | 319 |  | DFR | 409 | [7 empty] | 5671.576
|  |  | 123/1 |  |  | 123/2 |  |  | 123/3 |  |  | 123/4 |  |  | 124/0 |  |  | 124/1 |  |  | 124/2 |  |  | 124/3 |  |  | 124/4 |  |  | 124/5 |  |  | 124/6 |  |  | 125/0 |  |  | 125/1 |  |  | 125/2
|  |  | A+0 |  |  | A+0 |  |  | A+9 |  |  | A+0 |  |  | B2+0 |  |  | A+6 |  |  | A+6 |  |  | A+9 |  |  | A+3 |  |  | A+6 |  |  | A+6 |  |  | B2+3 |  |  | A+3 |  |  | A+3
|  |  | 387 |  |  | 388 |  |  | 389 |  |  | 390 |  |  | 391 |  |  | 392 |  |  | 393 |  |  | 394 |  |  | 395 |  |  | 396 |  |  | 397 |  |  | 398 |  |  | 399 |  |  | 400
CS Approved
|  |  |  | EC | [11 empty] | EC |  |  | EC |  | EC | [11 empty] | EC |  |  |  | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC | [5 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 11 | 6 | 8 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  |  | DFR | 422 | 0 | - | 422.541 | 0 | - | 449 | E | WFR | 305 | E | DFR | 439 | E | DFR | 409 | E | DFR | 422 | 0 | - | 390 | E | - | 404 | 0 | - | 331 | E | DFR | 368 | E | DFR | 389 | 0 | - | 390.104 | E | DFR | 406 | [7 empty] | 5546.645
|  |  | 125/3 |  |  | 126/0 |  |  | 126/1 |  |  | 126/2 |  |  | 126/3 |  |  | 126/4 |  |  | 126/5 |  |  | 126/6 |  |  | 126/7 |  |  | 126/8 |  |  | 126/9 |  |  | 126/10 |  |  | 127/0 |  |  | 127/1
|  |  | A+6 |  |  | C2+0 |  |  | A+9 |  |  | A+9 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | B1+0 |  |  | A+3
|  |  | 401 |  |  | 402 |  |  | 403 |  |  | 404 |  |  | 405 |  |  | 406 |  |  | 407 |  |  | 408 |  |  | 409 |  |  | 410 |  |  | 411 |  |  | 412 |  |  | 413 |  |  | 414
CS Appproved
[46 empty] | 14 | 6 | 0 | 4 | 0
|  |  | FC |  |  | FC |  |  | FC | [8 empty] | FC | [20 empty] | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 399 | 0 | - | 400 | E | WFR | 375 | 0 | - | 403 | 0 | - | 347 | E | DFR | 358 | 0 | - | 389 | 0 | - | 335 | 0 | - | 367 | 0 | - | 411.68 | 0 | - | 250 | 0 | - | 395.203 | 0 | DFR | 414 | E | DFR | 396 | [7 empty] | 5239.883
|  |  | 127/2 |  |  | 127/3 |  |  | 127/4 |  |  | 127/5 |  |  | 127/6 |  |  | 127/7 |  |  | 127/8 |  |  | 127/9 |  |  | 127/10 |  |  | 128/0 |  | 765 kV SC PL | 129/0 |  |  | 129A/0 |  |  | 129A/1 |  |  | 129A/2
|  |  | A+0 |  |  | A+0 |  |  | A+3 |  |  | A+4.5 |  |  | A-3 |  |  | A-3 |  |  | A-3 |  |  | A+0 |  |  | B1+3 |  |  | DN+36 |  |  | DN+48 |  |  | C1+9 |  |  | A-3 |  |  | A+7.5
ROW
|  |  | 415 |  |  | 416 |  |  | 417 |  |  | 418 |  |  | 419 |  |  | 420 |  |  | 421 |  |  | 422 |  |  | 423 |  |  | 424 |  |  | 425 |  |  | 426 |  |  | 427 |  |  | 428
CS Approved
|  |  | EC |  |  |  | EC | [22 empty] | EC |  |  |  | EC |  |  | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [8 empty] | FC | [5 empty] | FC |  |  | FC |  |  | FC | [9 empty] | 14 | 9 | 5 | 6 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | E | DFR | 382 | E | DFR | 408 | 0 | DFR | 421 | E | WFR | 401 | 0 | DFR | 448 | 0 | - | 384 | 0 | - | 400 | 0 | DFR | 443 | 0 | - | 313.311 | E | DFR | 292.997 | E | WET PADDY | 448 | E | WFR | 383 | 0 | - | 446 | 0 | - | 403 | [7 empty] | 5573.308
|  |  | 129A/3 |  |  | 129A/4 |  |  | 129A/5 |  |  | 129A/6 |  |  | 129A/7 |  |  | 129A/8 |  |  | 129A/9 |  |  | 129A/10 |  |  | 130/0 |  |  | 130/1 |  |  | 130/2 |  |  | 130/3 |  |  | 130/4 |  |  | 130/5
|  |  | A+3 |  |  | A+6 |  |  | A+9 |  |  | A+9 |  |  | A+1.5 |  |  | A+0 |  |  | A+4.5 |  |  | A+1.5 |  |  | B2+0 |  |  | A+0 |  |  | A+6 |  |  | A+3 |  |  | A+6 |  |  | B1+9
|  |  | 429 |  |  | 430 |  |  | 431 |  |  | 432 |  |  | 433 |  |  | 434 |  |  | 435 |  |  | 436 |  |  | 437 |  |  | 438 |  |  | 439 |  |  | 440 |  |  | 441 |  |  | 442
CS Approved
[28 empty] | EC |  | EC |  |  | EC |  |  |  | EC | [5 empty] | EC
[27 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  |  | 14 | 6 | 5 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 464.078 | 0 | - | 180 | 0 | - | 360 | 0 | - | 310 | 0 | - | 362 | 0 | - | 251 | 0 | - | 222 | 0 | - | 451 | 0 | WFR | 394 | 0 | WFR | 452 | 0 | DFR | 396 | 0 | DFR | 435 | 0 | DFR | 407 | 0 | DFR | 439 | [7 empty] | 5123.078
|  |  | 131/0 |  | 220KV D/C | 132/0 |  |  | 132/1 |  |  | 132/2 |  |  | 132/3 |  |  | 133/0 |  | NH | 134/0 |  |  | 134/1 |  |  | 134/2 |  |  | 134/3 |  |  | 134/4 |  |  | 134/5 |  |  | 134/6 |  |  | 134/7
|  |  | D45+9 |  |  | D45+9 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B1+0 |  |  | B2+6 |  |  | A+9 |  |  | A+3 |  |  | A+6 |  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+3
|  |  | 443 |  |  | 444 |  |  | 445 |  |  | 446 |  |  | 447 |  |  | 448 |  |  | 449 |  |  | 450 |  |  | 451 |  |  | 452 |  |  | 453 |  |  | 454 |  |  | 455 |  |  | 456
CS Approved
|  |  |  | EC |  |  | EC | [8 empty] | EC |  |  | EC |  |  | EC |  |  | EC |  |  | EC | [8 empty] | EC
|  |  | FC |  |  | FC | [5 empty] | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  |  | 14 | 13 | 8 | 10 | 0
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  |  | WFR | 410 | E | WET PADDY | 384 | 0 | - | 372.658 | 0 | - | 526.704 | E | WET PADDY | 455 | E | WET PADDY | 394 | 0 | DFR | 444 | E | WET PADDY | 405 | E | WET PADDY | 404 | E | WET PADDY | 400 | E | WET PADDY | 401 | E | WET PADDY | 384 | E | WET PADDY | 383 | E | - | 397 | [7 empty] | 5760.362
|  |  | 134/8 |  |  | 134/9 |  |  | 135/0 |  |  | 136/0 |  |  | 136/1 |  |  | 136/2 |  |  | 136/3 |  |  | 136/4 |  |  | 136/5 |  |  | 136/6 |  |  | 136/7 |  |  | 136/8 |  |  | 136/9 |  |  | 139/0
|  |  | A+3 |  |  | A+0 |  |  | B2+9 |  |  | C2+9 |  |  | A+0 |  |  | A+3 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | B2+0
|  |  | 457 |  |  | 458 |  |  | 459 |  |  | 460 |  |  | 461 |  |  | 462 |  |  | 463 |  |  | 464 |  |  | 465 |  |  | 466 |  |  | 467 |  |  | 468 |  |  | 469 |  |  | 470
CS Approved
|  |  |  | EC |  |  | EC | [7 empty] | EC
|  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC |  |  | FC | [27 empty] | 14 | 6 | 3 | 0 | 0
|  |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B |  | C | B
|  |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A |  | D | A
|  |  | 0 | - | 425 |  | DFR | 419 | 0 | DFR | 420 | 0 | - | 403 | 0 | DFR | 398 | 0 | DFR | 385 | 0 | - | 390 | 0 | - | 435.775 | 0 | - | 192.579 | [22 empty] | 3468.354
|  |  | 139/1 |  |  | 139/2 |  |  | 139/3 |  |  | 139/4 |  |  | 139/5 |  |  | 139/6 |  |  | 139/7 |  | 132 KV D/C | 140/0 |  |  | 141/0
|  |  | A+3 |  |  | A+0 |  |  | A+3 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | A+0 |  |  | C2+9 |  |  | D45+9
|  |  | 471 |  |  | 472 |  |  | 473 |  |  | 474 |  |  | 475 |  |  | 476 |  |  | 477 |  |  | 478 |  |  | 479 |  |  | 480 |  |  | 481 |  |  | 482 |  |  | 483 |  |  | 484
[46 empty] | 480 | 152 | 52 | 95 | 0 | 0 | 185.065
Cummulative Progress
[11 empty] | INDEX | [19 empty] | Foundation Cumulative |  |  |  |  | Nos. |  | 152
[31 empty] | Earthing Cumulative |  |  |  |  | Nos. |  | 95
|  |  | Suspension Tower |  |  |  | Angel Tower | [23 empty] | Erection Cumulative |  |  |  |  | Nos. |  | 52
[5 empty] | Tower Erection | [25 empty] | Tack Welding |  |  |  |  | Nos.
[31 empty] | Stringing Paying out Cumulative |  |  |  |  | Km.
[31 empty] | Stringing Final sag Cumulative |  |  |  |  | Km.
Tack Welding
|  |  |  | C | B |  | C | B | Foundation
|  |  |  | D | A |  | D | A
|  |  |  | Classification | [9 empty] | Gas Pipe Line |  | NH/SH crossings |  | Railway |  | Power Line |  | River
Earthing
[15 empty] | Stringing Paying Out |  |  |  | Stringing Final Sag
OPGW Final Sag
Earthing completed
Note on I118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CR- Indore to Manmad

## Detail Survey (hidden)
KEC International Limited
Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Detail Survey | [9 empty] | 2026-05-30 20:29
Sl.No | Section | As Per Letter | Section Length KMS | Revenue | Submission Date | Submission Reference No. | Revision | As Per Approved Letter | Approved | Approval date | Approval reference No. | Remark's | Balance to be Approved
1 | AP0 to AP23 |  |  | 14.432 | 2025-12-13 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/69 | 0
2 | AP33 to AP38A |  |  | 5.575 | 2026-01-12 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/94 | 0
3 | AP38 to AP51 |  |  | 14.458 | 2025-12-16 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/73 | 0
4 | AP51 to AP62 | 8.345 | 8.344 | Feb'26 | 2026-01-19 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/100 | 0 |  | 8.344 | 2026-02-16 | WR-II/Khargone/HVDC/TLC/TL-06/58
5 | AP62 to AP 64 | 3.615 | 3.615 | Feb'26 | 2026-02-06 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/115 | 0 |  | 3.615 | 2026-02-16 | WR-II/Khargone/HVDC/TLC/TL-06/57 |  | Not Approved yet
5 | AP64 to AP71 |  | 9.709 | Feb'26 | 2026-01-14 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/98 | 2 |  | 9.709 | 2026-01-15 | WR-II/Khargone/HVDC/TLC/TL-06/51
6 | AP71 to AP75 |  | 3.714 |  | 2025-12-31 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/89 | 2 |  | 4.952 | 2026-02-16 | WR-II/Khargone/HVDC/TLC/TL-06/59 |  | Not Approved yet
7 | AP75 to AP76 |  | 1.238 |  | 2025-10-10 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/27 | 0
8 | AP76 to AP83 |  | 7.242 |  | 2026-12-31 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/86 | 4 |  | 7.242 | 2026-01-02 | WR-II/Khargone/HVDC/TLC/TL-06/46
9 | AP83 to AP92 |  | 22.602 | RA-2 | 2025-11-15 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/48 | 1 |  | 22.602 | 2025-11-24 | WR-II/Khargone/HVDC/TLC/TL-06/35
10 | AP92 to AP94 |  | 4.351 |  | 2025-12-11 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/66 | 0 |  | 4.351 | 2025-12-13 | WR-II/Khargone/HVDC/TLC/TL-06/40
| AP94 to AP99 |  | 6.222 |  | 2026-01-31 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/112 | 0
11 | AP95 to AP98 |  |  | 1.455 | 2026-01-24 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/103 | 0
12 | AP 99 to AP 106 |  | 11.413 | RA-01 | 2025-10-03 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/26 | 0 |  | 11.413 | 2025-10-09 | WR-II/Khargone/HVDC/TLC/TL-06/
13 | AP104 to AP105 |  |  | 1.188 | 2025-12-13 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/70 | 1
14 | AP106 to AP110 |  | 10.77 | RA-2 | 2025-11-22 | KEC/PGCIL-800kV HVDC/KPS2&NGP/TL-06/52 | 1 |  | 10.77 | 2025-11-26 | WR-II/Khargone/HVDC/TLC/TL-06/40
15 | AP110 to AP118 |  | 10.198 | RA-01 | 2025-10-03 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/26 | 1 |  | 10.198 | 2025-10-09 | WR-II/Khargone/HVDC/TLC/TL-06/
16 | AP118 to AP 123 |  | 6.502 | RA-01 | 2025-09-10 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/18 | 0 |  | 6.502 | 2025-09-13 | WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey
17 | AP123 to AP126 |  | 6.516 | RA-01 | 2025-08-25 | KEC/PGCIL800kV HVDC /KPS2 & NGP/TL06/011 | 0 |  | 6.516 | 2025-08-28 | WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey
18 | AP126 to Ap127 |  | 4.34 | RA-01 | 2025-09-22 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/20 | 1 |  | 4.34 | 2025-09-26 | WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey
19 | AP127 to AP129A |  | 4.836 |  | 2026-01-06 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/82 | 1 |  | 4.836 | 2026-01-09 | WR-II/Khargone/HVDC/TLC/TL-06/49
20 | AP129A to AP130 |  | 4.41 |  | 2025-12-31 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/89 | 2 |  | 4.41 | 2026-01-02 | WR-II/Khargone/HVDC/TLC/TL-06/45
21 | AP130 to AP134 |  | 4.122 | RA-01 | 2025-09-22 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/20 | 1 |  | 4.122 | 2025-09-26 | WR-II/Khargone/HVDC/TLC/TL-06/Detail Survey |  | R-1 CS
22 | AP134 to AP141 |  | 12.203 | RA-01 | 2025-11-12 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/46 | 1 |  | 12.203 | 2025-11-14 | WR-II/Khargone/HVDC/TLC/TL-06/33
|  |  | 142.347 | 38 |  |  |  |  | 136.125

## Check Survey (hidden)
KEC International Limited
Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Check Survey | [7 empty] | 2026-05-30 20:29
Sl.No | Section | Section Length | Submission Date | Submission Reference No. | Revision | As Per Approved Letter | Approved | Approval date | Letter Refference no. | Remark's
1 | AP51 to AP64 | 11.959 | 2026-02-17 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/99 |  |  | 11.959 | 2026-02-17 | WR-II/Khargone/HVDC/TLC/TL-06/61
2 | AP64 to AP71 | 9.709 | 2026-01-16 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/99 |  | 9.71 | 9.71 | 2026-02-06 | WR-II/Khargone/HVDC/TLC/TL-06/56
3 | AP71 to AP 76 | 4.965 | 2026-02-17 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/121 |  |  | 4.965 | 2026-02-17 | WR-II/Khargone/HVDC/TLC/TL-06/61
4 | AP76 to AP83 | 7.242 | 2026-01-03 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/90 |  | 7.242 | 7.242 | 2026-01-03 | WR-II/Khargone/HVDC/TLC/TL-06/48
5 | AP83 to AP92 | 18.271 | 2025-11-25 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/56 |  | 18.271 | 18.271 | 2025-11-26 | WR-II/Khargone/HVDC/TLC/TL-06/37 |  | RA-2
6 | AP91 to AP92 | 4.331 | 2025-12-13 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/68 | 2 | 4.331 | 4.331 | 2025-12-27 | WR-II/Khargone/HVDC/TLC/TL-06/44
7 | AP92 To AP94 | 4.351 | 2025-12-15 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/72 |  | 4.351 | 4.351 | 2025-12-16 | WR-II/Khargone/HVDC/TLC/TL-06/41
8 | AP99 to AP106 | 11.413 | 2025-11-03 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/ |  | 11.413 | 11.413 | 2025-11-04 | WR-II/Khargone/HVDC/TLC/TL-06/ |  | RA-01
9 | AP106 to AP110 | 10.77 | 2025-11-28 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/60 |  | 10.77 | 10.77 | 2025-12-03 | WR-II/Khargone/HVDC/TLC/TL-06/39 |  | RA-2
10 | AP110 to AP118 | 10.199 | 2025-11-03 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/ |  | 10.199 | 10.199 | 2025-11-04 | WR-II/Khargone/HVDC/TLC/TL-06/ |  | RA-01
11 | AP118 to AP123 | 2.16 | 2025-09-18 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/19 |  | 6.502 | 2.16 | 2025-09-22 | WR-II/Khargone/HVDC/TLC/TL-06/ |  | RA-01
12 | AP121-AP122 | 4.342 | 2026-04-01 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/155 |  | 2 | 4.342 | 2026-04-02 | WR-II/Khargone/HVDC/TLC/TL-06/ | Revised with Changing in Tower Type
13 | AP123 to AP126 | 6.516 | 2025-08-30 | KEC/PGCIL +_KV HVDC/KPS2&NGP/TL-06/14 |  | 6.516 | 6.516 | 2025-09-01 | WR-II/Khargone/HVDC/TLC/TL-06/Checksurvey |  | RA-01
14 | AP126 to AP127 | 4.34 | 2025-09-26 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 22 | 1 | 4.241 | 4.34 | 2025-09-26 | WR-II/Khargone/HVDC/TLC/TL-06/DetailSurvey | Approval needed
15 | AP127 to AP129A | 4.836 | 2026-01-10 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 92 |  | 4.836 | 4.836 | 2026-01-10 | WR-II/Khargone/HVDC/TLC/TL-06/50
16 | AP129A to AP130 | 4.41 | 2026-01-03 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 91 |  | 4.41 | 4.41 | 2026-01-03 | WR-II/Khargone/HVDC/TLC/TL-06/47
17 | AP130 to Ap131 | 2.437 | 2025-01-07 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 92 |  | 4.042 | 2.437 | 2025-09-26 |  | Approval needed
18 | AP130 to AP134 | 1.685 | 2025-09-26 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 22 |  |  | 1.685 | 2025-09-26 | WR-II/Khargone/HVDC/TLC/TL-06/DetailSurvey
19 | AP134 to AP141 | 12.203 | 2025-11-15 | KEC/PGCILt 800KV HVDC /KPS2&NGP/TL-06/ 47 |  | 12.203 | 12.203 | 2025-11-17 | WR-II/Khargone/HVDC/TLC/TL-06/
|  | 136.139 |  |  |  | 121.037 | 136.14
Formulas:
Approval date = [Submission Date]

## Composite-Survey(05-04-2026) (hidden)
CLIENT :- M/s POWERGRID WEST CENTRAL TRANSMISSION LIMITED
NAME OF PROJECT :- Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
M/s. KEC INTERNATIONAL LIMITED
Composite TS Detail and Check Survey
KEC/TA602/800 KV/TS/ REV.0
Sl.No | AP NO. | TOWER NO. | TYPE OF TOWER | DEVIATION ANGLE (Deg) | SPAN (Mtr) | Section Length (m) | HT of Tower (Mtr) | CUMULATIVE SPAN | R.L (Mtr) | Sum of Adjacent Spans | WIND SPAN (Mtr) | WEIGHT SPAN IN Mtr (Cold) |  |  | WEIGHT SPAN IN Mtr (Hot) |  |  | LONGITUDE (E) | LATITUDE (N) | UTM Coordinates |  | CROSSING DETAILS/ REMARKS | Detail Survey |  | Check Survey |  | Remark'S
[12 empty] | Left | Right | Total | Left | Right | Total |  |  | Easting | Northing |  | Submitted | Approved | Submitted | Approved
1 | AP 0 | 0/0 | D60+9 | 0° 0' 0" |  |  | 57.32 | 0 | 399.684 | 337 | 168.5 | 0 | 209 | 209 | 0 | 197 | 197 | 74°13'43.053" | 22°35'55.261" | 420714.94 | 2499300.38 | Common Point | No | No | No | No
[5 empty] | 337 | [16 empty] | Nala
2 |  | 0/1 | A+9 |  |  |  | 62.83 | 337 | 392.311 | 741 | 370.5 | 128 | 229 | 357 | 141 | 221 | 362 | 74°13'53.56" | 22°35'50.269" | 421014.149 | 2499145.322 |  | No | No | No | No
[5 empty] | 404 | [16 empty] | Low land, Cart track
3 |  | 0/2 | A+9 |  |  |  | 62.83 | 741 | 386.609 | 713 | 370.5 | 176 | 248 | 424 | 184 | 220 | 405 | 74°14'6.156" | 22°35'44.284" | 421372.843 | 2498959.437 |  | No | No | No | No
[5 empty] | 309 | [16 empty] | Nala
4 | AP 1 | 1/0 | D60(-)3 | 50° 18' 45"RT |  | 1049.9 | 45.32 | 1050 | 383.208 | 626 | 370.5 | 62 | 99 | 160 | 90 | 120 | 210 | 74°14'15.786" | 22°35'39.708" | 421647.1 | 2498817.31 |  | No | No | No | No
[5 empty] | 317 | [16 empty] | LT line, 11kV line,Cart track, Well, Nala
5 | AP 2 | 2/0 | D45+3 | 32° 8' 22"LT |  | 316.85 | 51.32 | 1367 | 387.049 | 712 | 370.5 | 219 | 192 | 410 | 198 | 194 | 392 | 74°14'18.204" | 22°35'29.652" | 421714.56 | 2498507.73 |  | Yes | No | No | No
[5 empty] | 395 | [16 empty] | Metal road, LT line
6 |  | 2/1 | A+0 |  |  |  | 53.83 | 1762 | 391.321 | 756 | 370.5 | 204 | 211 | 415 | 203 | 203 | 406 | 74°14'27.938" | 22°35'20.525" | 421991.087 | 2498225.67 |  | Yes | No | No | No
[5 empty] | 361 | [16 empty] | LT line, Pump house, Concrete road, Metal road
7 | AP 3 | 3/0 | C2+0 | 27° 58' 5"LT |  | 755.96 | 48.32 | 2123 | 385.413 | 795 | 370.5 | 150 | 240 | 390 | 159 | 234 | 393 | 74°14'36.834" | 22°35'12.185" | 422243.78 | 2497967.92 |  | Yes | No | No | No
[5 empty] | 434 | [16 empty] | 11kV line, Well, Nala
8 |  | 3/1 | A+1.5 |  |  |  | 55.33 | 2557 | 378.525 | 781 | 370.5 | 195 | 179 | 374 | 201 | 178 | 379 | 74°14'51.344" | 22°35'7.986" | 422657.466 | 2497836.695 |  | Yes | No | No | No
[5 empty] | 347 | [16 empty] | Metal road, 11kV line
9 |  | 3/2 | A(-)3 |  |  |  | 50.83 | 2904 | 382.071 | 691 | 370.5 | 169 | 157 | 325 | 170 | 161 | 332 | 74°15'2.945" | 22°35'4.628" | 422988.224 | 2497731.776 |  | Yes | No | No | No
[5 empty] | 344 | [16 empty] | 11kV line, 33kV line
10 |  | 3/3 | A(-)3 |  |  |  | 50.83 | 3248 | 384.994 | 723 | 370.5 | 188 | 172 | 360 | 184 | 177 | 361 | 74°15'14.446" | 22°35'1.299" | 423316.123 | 2497627.764 |  | Yes | No | No | No
[5 empty] | 379 | [16 empty] | LT line
11 | AP 4 | 4/0 | D60+0 | 57° 23' 7"RT |  | 1503.73 | 48.32 | 3627 | 385.769 | 715 | 370.5 | 208 | 102 | 310 | 203 | 124 | 327 | 74°15'27.108" | 22°34'57.634" | 423677.13 | 2497513.25 |  | Yes | No | No | No
[5 empty] | 336 | [16 empty] | LT line, Well
12 | AP 5 | 5/0 | B2+9 | 12° 2' 19"LT |  | 335.89 | 57.32 | 3963 | 388.43 | 775.86 | 370.5 | 234 | 196 | 430 | 213 | 202 | 415 | 74°15'30.212" | 22°34'47.098" | 423764.15 | 2497188.83 |  | No | No | No | No
[5 empty] | 439.86 | [16 empty] | Nala, Well, Boring, Burning ghat, Pond, LT line, Cart track, Concrete road,Boundary wall
13 | AP 6 | 6/0 | D45+3 | 42° 17' 41"LT |  | 439.86 | 51.32 | 4402.86 | 400.598 | 876.86 | 370.5 | 245 | 221 | 466 | 240 | 221 | 461 | 74°15'37.286" | 22°34'34.392" | 423964.21 | 2496797.1 |  | No | No | No | No
[5 empty] | 437 | [16 empty] | LT line, Pond, Well, Low land
14 |  | 6/1 | A+6 |  |  |  | 59.83 | 4839.86 | 397.069 | 772.734 | 370.5 | 217 | 196 | 413 | 218 | 189 | 407 | 74°15'51.631" | 22°34'29.445" | 424373.13 | 2496642.978 |  | No | No | No | No
[5 empty] | 335.734 | [16 empty] | 11kV line
15 | AP 7 | 7/0 | B2(-)3 | 14° 58' 30"RT |  | 772.73 | 45.32 | 5175.594 | 400.915 | 774.447 | 370.5 | 140 | 142 | 282 | 148 | 159 | 307 | 74°16'2.653" | 22°34'25.645" | 424687.29 | 2496524.57 |  | No | No | No | No
[5 empty] | 438.713 | [16 empty] | Cart track, LT line, Nala, Well, Low land, Toilet
16 | AP 8 | 8/0 | C1+9 | 17° 22' 49"RT |  | 438.71 | 57.32 | 5614.307 | 408.749 | 780.466 | 370.5 | 299 | 107 | 406 | 283 | 127 | 410 | 74°16'15.183" | 22°34'17.391" | 425043.89 | 2496269.02 |  | No | No | No | No
[5 empty] | 341.753 | [16 empty] | 11kV line, Metal road, Nala
17 | AP 9 | 9/0 | D45+9 | 39° 58' 00"LT |  | 341.75 | 57.32 | 5956.06 | 420.469 | 749.539 | 370.5 | 236 | 238 | 474 | 216 | 230 | 446 | 74°16'22.43" | 22°34'8.548" | 425249.53 | 2495996.06 |  | No | No | No | No
[5 empty] | 407.786 | [16 empty] | Metal road, LT line
18 | AP 10 | 10/0 | C1+3 | 19° 40' 35"LT |  | 407.79 | 51.32 | 6363.846 | 418.767 | 819.786 | 370.5 | 170 | 190 | 361 | 179 | 194 | 373 | 74°16'36.356" | 22°34'5.618" | 425646.8 | 2495904.05 |  | No | No | No | No
[5 empty] | 412 | [16 empty] | LT line, Well
19 |  | 10/1 | A+6 |  |  |  | 59.83 | 6775.846 | 419.462 | 838.82 | 370.5 | 222 | 199 | 422 | 219 | 203 | 422 | 74°16'50.678" | 22°34'7.231" | 426056.039 | 2495951.664 |  | No | No | No | No
[5 empty] | 426.82 | [16 empty] | Cart track, Nala, Metal road
20 | AP 11 | 11/0 | C1+3 | 20° 11' 49"RT |  | 838.82 | 51.32 | 7202.666 | 426.135 | 763.82 | 370.5 | 229 | 167 | 396 | 226 | 168 | 394 | 74°17'5.515" | 22°34'8.901" | 426480 | 2496000.99 |  | No | No | No | No
[5 empty] | 337 | [16 empty] | Nala, Metal road, Water tank
21 |  | 11/1 | A+6 |  |  |  | 59.83 | 7539.666 | 423.381 | 791 | 370.5 | 171 | 254 | 424 | 170 | 247 | 418 | 74°17'16.999" | 22°34'6.383" | 426807.605 | 2495921.972 |  | No | No | No | No
[5 empty] | 454 | [16 empty] | Nala, Metal road
22 |  | 11/2 | A+6 |  |  |  | 59.83 | 7993.666 | 416.89 | 798.906 | 370.5 | 202 | 242 | 443 | 209 | 224 | 433 | 74°17'32.471" | 22°34'2.989" | 427248.949 | 2495815.521 |  | No | No | No | No
[5 empty] | 344.906 | [16 empty] | Cart track, Well
23 | AP 12 | 12/0 | C1+9 | 20° 11' 37"LT |  | 1135.91 | 57.32 | 8338.572 | 400.861 | 743.906 | 370.5 | 104 | 258 | 362 | 122 | 243 | 365 | 74°17'44.224" | 22°34'0.411" | 427584.24 | 2495734.65 |  | No | No | No | No
[5 empty] | 399 | [16 empty] | Well, Pond
24 |  | 12/1 | A+6 |  |  |  | 59.83 | 8737.572 | 391.017 | 778.984 | 370.5 | 142 | 210 | 352 | 157 | 205 | 362 | 74°17'58.094" | 22°34'1.97" | 427980.569 | 2495780.738 |  | No | No | No | No
[5 empty] | 379.984 | [16 empty] | Metal road, Well, Boring
25 | AP 13 | 13/0 | D45+0 | 42° 9' 13"RT |  | 778.98 | 48.32 | 9117.556 | 392.948 | 843.984 | 370.5 | 171 | 155 | 326 | 176 | 173 | 349 | 74°18'11.303" | 22°34'3.455" | 428358.01 | 2495824.63 |  | No | No | No | No
[5 empty] | 464 | [16 empty] | Metal road, LT line, Well, Boring, Low land
26 |  | 13/1 | A+9 |  |  |  | 62.83 | 9581.556 | 404.306 | 828 | 370.5 | 311 | 265 | 575 | 293 | 246 | 539 | 74°18'24.57" | 22°33'54.745" | 428735.663 | 2495555.048 |  | No | No | No | No
[5 empty] | 364 | [16 empty] | LT line, Metal road
27 |  | 13/2 | A+6 |  |  |  | 59.83 | 9945.556 | 390.365 | 818 | 370.5 | 101 | 223 | 323 | 120 | 224 | 344 | 74°18'34.978" | 22°33'47.913" | 429031.925 | 2495343.566 |  | No | No | No | No
[5 empty] | 454 | [16 empty] | Low land
28 |  | 13/3 | A+6 |  |  |  | 59.83 | 10399.556 | 391.616 | 833.923 | 370.5 | 233 | 257 | 489 | 232 | 242 | 474 | 74°18'47.959" | 22°33'39.39" | 429401.438 | 2495079.793 |  | No | No | No | No
[5 empty] | 379.923 | [16 empty] | Metal road, LT line
29 | AP 14 | 14/0 | D45+3 | 44° 17' 22"LT |  | 1661.92 | 51.32 | 10779.479 | 380.367 | 802.685 | 370.5 | 124 | 210 | 334 | 140 | 211 | 350 | 74°18'58.821" | 22°33'32.258" | 429710.66 | 2494859.06 |  | No | No | No | No
422.762
30 | AP 15 | 15/0 | B2+0 | 13° 33' 53"LT |  | 422.76 | 48.32 | 11202.241 | 383.817 | 868.762 | 370.5 | 214 | 259 | 473 | 214 | 252 | 465 | 74°19'13.44" | 22°33'34.416" | 430128.48 | 2494923.51 |  | No | No | No | No
[5 empty] | 446 | [16 empty] | Metal road, Nala
31 |  | 15/1 | A+3 |  |  |  | 56.83 | 11648.241 | 371.728 | 835.71 | 370.5 | 188 | 218 | 406 | 196 | 213 | 409 | 74°19'27.858" | 22°33'39.988" | 430541.024 | 2495092.99 |  | No | No | No | No
[5 empty] | 389.71 | [16 empty] | Nala
32 | AP 16 | 16/0 | B2+6 | 13° 4' 34"RT |  | 835.71 | 54.32 | 12037.951 | 363.834 | 870.459 | 370.5 | 173 | 270 | 443 | 178 | 265 | 444 | 74°19'40.456" | 22°33'44.857" | 430901.5 | 2495241.08 |  | Yes | No | No | No
[5 empty] | 480.749 | [16 empty] | Nala, Fencing
33 | AP 17 | 17/0 | D45+3 | 42° 54' 8"RT |  | 480.75 | 51.32 | 12518.7 | 358.603 | 656.749 | 370.5 | 213 | 232 | 445 | 218 | 143 | 362 | 74°19'57.058" | 22°33'47.441" | 431375.987 | 2495318.421 |  | Yes | No | No | No
[5 empty] | 176 | [16 empty] | Ltline, Nala
34 | AP 18 | 18/0 | D45+0 | 40° 55' 18"LT |  | 176.13 | 48.32 | 12694.7 | 351.492 | 388 | 370.5 | -56 | 129 | 73 | 33 | 117 | 150 | 74°20'2.207" | 22°33'44.289" | 431522.61 | 2495220.841 |  | Yes | No | No | No
[5 empty] | 212 | [16 empty] | NH-56, Nala
35 | AP 19 | 19/0 | D60(-)3 | 55° 55' 49"RT |  | 211.81 | 45.32 | 12906.7 | 352.368 | 432 | 370.5 | 83 | -12 | 71 | 95 | 52 | 147 | 74°20'9.559" | 22°33'45.192" | 431732.71 | 2495247.67 |  | Yes | No | No | No
[5 empty] | 220 | [16 empty] | Nala, 11kV line, House
36 | AP 20 | 20/0 | D45+6 | 32° 33' 37"RT |  | 220.14 | 54.32 | 13126.7 | 355.3 | 654 | 370.5 | 233 | 228 | 461 | 169 | 226 | 395 | 74°20'14.677" | 22°33'39.839" | 431878.139 | 2495082.404 |  | Yes | No | No | No
[5 empty] | 434 | [16 empty] | Cart track, 33kV line, 11kV line
37 | AP 21 | 21/0 | C2+9 | 23° 9' 14"LT |  | 434.24 | 57.32 | 13560.7 | 349.766 | 865 | 370.5 | 207 | 246 | 454 | 210 | 240 | 450 | 74°20'17.066" | 22°33'25.893" | 431944.47 | 2494653.26 |  | Yes | No | No | No
[5 empty] | 431 | [16 empty] | Nala
38 | AP 22 | 22/0 | D60+0 | 58° 15' 18"LT |  | 430.8 | 48.32 | 13991.7 | 351.227 | 871 | 370.5 | 185 | 220 | 405 | 192 | 221 | 413 | 74°20'25.102" | 22°33'14.037" | 432172.38 | 2494287.68 |  | Yes | No | No | No
[5 empty] | 440 | [16 empty] | LT line, Nala
39 | AP 23 | 23/0 | D60+3 | 56° 32' 1"RT |  | 440 | 51.32 | 14431.7 | 348.28 | 440 | 370.5 | 221 | 195 | 416 | 221 | 183 | 404 | 74°20'40.502" | 22°33'14.149" | 432612.23 | 2494289.18 |  | Yes | No | No | No
40 |  | 23/1 | A+0 |  |  |  |  | 14431.7 |  | 362 | 370.5 | [11 empty] | No | No | No | No
362
41 |  | 23/2 | A+0 |  |  |  |  | 14793.7 |  | 727 | 370.5 | [11 empty] | No | No | No | No
365
42 |  | 23/3 | A+0 |  |  |  |  | 15158.7 |  | 730 | 370.5 | [11 empty] | No | No | No | No
365
43 | AP24 | AP24 | D45+0 | 40° 57' 16" LT |  | 1454 |  | 15523.7 |  | 755 | 370.5 | [6 empty] | 22° 32' 34.87" | 74° 21' 8.93" | 433418.88 | 2493077.9 |  | No | No | No | No
390
44 |  | 24/1 | A+6 |  |  |  |  | 15913.7 |  | 780 | 370.5 | [11 empty] | No | No | No | No
390
45 |  | 24/2 | A+3 |  |  |  |  | 16303.7 |  | 771 | 370.5 | [11 empty] | No | No | No | No
381
46 |  | 24/3 | A+6 |  |  |  |  | 16684.7 |  | 771 | 370.5 | [11 empty] | No | No | No | No
390
47 | AP25 | AP25 | C2+0 | 28° 58' 0" RT |  | 1551 |  | 17074.7 |  | 759 | 370.5 | [6 empty] | 22° 32' 21.61" | 74° 22' 1.32" | 434913.73 | 2492663.83 |  | No | No | No | No
369
48 | AP26 | AP26 | D45+0 | 49° 6' 19" RT |  | 369 |  | 17443.7 |  | 801 | 370.5 | [6 empty] | 22° 32' 13.24" | 74° 22' 10.59" | 435177.37 | 2492405.21 |  | No | No | No | No
432
49 | AP27 | AP27 | D45+0 | 48° 13' 53" LT |  | 432 |  | 17875.7 |  | 878 | 370.5 | [6 empty] | 22° 31' 59.24" | 74° 22' 9.72" | 435150.64 | 2491974.92 |  | No | No | No | No
446
50 | AP28 | AP28 | C1+0 | 16° 15' 58" LT |  | 446 |  | 18321.7 |  | 841 | 370.5 | [6 empty] | 22° 31' 49" | 74° 22' 20.71" | 435463.38 | 2491658.63 |  | No | No | No | No
395
51 |  | 28/1 | A+3 |  |  |  |  | 18716.7 |  | 795 | 370.5 | [11 empty] | No | No | No | No
400
52 | AP29 | AP29 | C1+6 | 16° 13' 3" LT |  | 795 |  | 19116.7 |  | 840 | 370.5 | [6 empty] | 22° 31' 36.02" | 74° 22' 44.77" | 436148.93 | 2491256.57 |  | No | No | No | No
440
53 |  | 29/1 | B1+9 |  |  |  |  | 19556.7 |  | 879 | 370.5 | [11 empty] | No | No | No | No
439
54 | AP30 | AP30 | C2+6 | 25° 2' 30" RT |  | 879 |  | 19995.7 |  | 811 | 370.5 | [6 empty] | 22° 31' 29.14" | 74° 23' 14.6" | 437000.16 | 2491041.6 |  | No | No | No | No
372
55 |  | 30/1 | A+0 |  |  |  |  | 20367.7 |  | 744 | 370.5 | [11 empty] | No | No | No | No
372
56 |  | 30/2 | A+0 |  |  |  |  | 20739.7 |  | 742 | 370.5 | [11 empty] | No | No | No | No
370
57 | AP31 | AP31 | C1+3 | 16° 21' 35" RT |  | 1114 |  | 21109.7 |  | 770 | 370.5 | [6 empty] | 22° 31' 6.35" | 74° 23' 44.92" | 437863.4 | 2490337.19 |  | No | No | No | No
400
58 | AP32 | AP32 | D45+3 | 31° 30' 19" RT |  | 400 |  | 21509.7 |  | 760 | 370.5 | [6 empty] | 22° 30' 55.66" | 74° 23' 52.87" | 438089.36 | 2490007.5 |  | No | No | No | No
360
59 |  | 32/1 | A+0 |  |  |  |  | 21869.7 |  | 725 | 370.5 | [11 empty] | No | No | No | No
365
60 | AP 33 | AP33 | C1-3 | 20° 21' 28"RT |  |  | 45.32 | 22234.7 | 330.676 | 793 | 370.5 | 187 | 199 | 386 | 185 | 204 | 388 | 74°23'56.736" | 22°30'30.619" | 438196.66 | 2489237.19 |  | No | No | No | No
[5 empty] | 428 | [16 empty] | 11kV line, Boring, Nala
61 |  | 33/1 | A+0 |  |  |  | 53.83 | 22662.7 | 331.278 | 788.723 | 370.5 | 230 | 194 | 425 | 227 | 191 | 418 | 74°24'8.403" | 22°30'21.888" | 438528.913 | 2488967.39 |  | No | No | No | No
[5 empty] | 360.723 | [16 empty] | Cart track, Nala
62 | AP 34 | AP34 | C2+0 | 22° 44' 55"RT |  |  | 48.32 | 23023.423 | 328.637 | 620.725 | 370.5 | 167 | 135 | 303 | 171 | 134 | 305 | 74°24'18.235" | 22°30'14.53" | 438808.94 | 2488740 |  | No | No | No | No
[5 empty] | 260.002 | [16 empty] | Nala
63 |  | 34/1 | A+6 |  |  |  | 59.83 | 23283.425 | 321.809 | 716.808 | 370.5 | 125 | 105 | 231 | 127 | 136 | 263 | 74°24'22.564" | 22°30'7.092" | 438931.7 | 2488510.803 |  | No | No | No | No
[5 empty] | 456.806 | [16 empty] | Nala
64 | AP 35 | AP35 | B2+3 | 9° 17' 25"RT |  |  | 51.32 | 0 | 357.53 | 902 | 451 | 359 | 330 | 689 | 327 | 308 | 635 | 74°24'30.168" | 22°29'54.024" | 439147.38 | 2488108.12 | Strength check required due to weight span limit exceeded | Yes | No | No | No
[5 empty] | 445 | [16 empty] | Cart track, Nala
65 | AP 36 | AP36 | C1+3 | 20° 51' 6"LT |  |  | 51.32 | 445 | 330.144 | 852 | 426 | 117 | 222 | 339 | 139 | 218 | 357 | 74°24'35.264" | 22°29'40.357" | 439291.33 | 2487687.28 |  | Yes | No | No | No
[5 empty] | 407 | [16 empty] | Boring pump, Well, LT line, Nala, Cart track, Toilet
66 |  | 36/1 | A+0 |  |  |  | 53.83 | 852 | 328.929 | 808 | 404 | 185 | 175 | 360 | 190 | 182 | 372 | 74°24'44.413" | 22°29'30.211" | 439551.501 | 2487374.294 |  | Yes | No | No | No
[5 empty] | 401 | [16 empty] | Nala, Boring pump, Cart track
67 | AP 37 | AP37 | C1+3 | 16° 40' 23"LT |  | 1253 | 51.32 | 1253 | 331.749 | 808 | 404 | 227 | 173 | 400 | 220 | 181 | 402 | 74°24'53.424" | 22°29'20.218" | 439807.78 | 2487065.99 |  | Yes | No | No | No
407
68 |  | 37/1 | A+6 |  |  |  | 59.83 | 1660 | 335.578 | 783 | 391.5 | 234 | 276 | 510 | 227 | 255 | 482 | 74°25'5.319" | 22°29'12.937" | 440146.812 | 2486840.808 |  | Yes | No | No | No
[5 empty] | 376 | [16 empty] | Metal road, 11kV line, Nala
69 |  | 37/2 | A+4.5 |  |  | 783 | 58.33 | 2036 | 318.674 | 846 | 423 | 101 | 231 | 332 | 123 | 233 | 355 | 74°25'16.308" | 22°29'6.212" | 440460.02 | 2486632.778 | 11KV Line Diverted | Yes | No | No | No
[5 empty] | 470 | [16 empty] | Nala
70 |  | 37/3 | A+4.5 |  |  | 470 | 58.33 | 2506 | 319.927 | 849 | 424.5 | 240 | 208 | 449 | 240 | 204 | 444 | 74°25'30.044" | 22°28'57.804" | 440851.53 | 2486372.741 |  | Yes | No | No | No
[5 empty] | 379 | [16 empty] | Cart track, Nala, LT lines
71 |  | 37/4 | A+7.5 |  |  | 379 | 61.33 | 2885 | 313.071 | 733 | 366.5 | 172 | 161 | 333 | 176 | 165 | 342 | 74°25'41.12" | 22°28'51.024" | 441167.238 | 2486163.051 |  | Yes | No | No | No
[5 empty] | 354 | [16 empty] | Nala
72 |  | 37/5 | A+4.5 |  |  |  | 58.33 | 3239 | 319.274 | 742 | 371 | 193 | 151 | 345 | 190 | 162 | 352 | 74°25'51.465" | 22°28'44.691" | 441462.12 | 2485967.193 |  | Yes | No | No | No
[5 empty] | 388 | [16 empty] | Nala, Cart track
73 |  | 37/6 | A+7.5 |  |  |  | 61.33 | 3627 | 325.625 | 831 | 415.5 | 238 | 202 | 440 | 227 | 207 | 435 | 74°26'2.804" | 22°28'37.75" | 441785.324 | 2485752.523 |  | Yes | No | No | No
[5 empty] | 443 | [16 empty] | 11kV line, Nala
74 | AP 38 | 38/0 | B2+3 | 5° 42' 9"RT |  | 1185 | 51.32 | 4070 | 335.114 | 951 | 475.5 | 242 | 245 | 487 | 238 | 248 | 485 | 74°26'15.748" | 22°28'29.824" | 442154.32 | 2485507.44 |  | Yes | No | No | No
[5 empty] | 508 | [16 empty] | Nala
75 |  | 38/1 | A+9 |  |  |  | 62.83 | 4578 | 331.876 | 822 | 411 | 265 | 238 | 502 | 263 | 221 | 484 | 74°26'29.547" | 22°28'19.41" | 442547.464 | 2485185.723 |  | Yes | No | No | No
[5 empty] | 314 | [16 empty] | Cart track, Toilet, Temple, Nala
76 | AP 39 | 39/0 | C2+1.5 | 26° 34' 4"LT |  | 822 | 49.82 | 4892 | 324.77 | 700 | 350 | 76 | 124 | 200 | 93 | 140 | 233 | 74°26'38.075" | 22°28'12.973" | 442790.44 | 2484986.89 |  | Yes | No | No | No
[5 empty] | 386 | [16 empty] | Nala, 11kV line, Boring
77 |  | 39/1 | A+9 |  |  |  | 62.83 | 5278 | 332.466 | 816 | 408 | 263 | 243 | 506 | 247 | 237 | 485 | 74°26'51.261" | 22°28'10.253" | 443166.958 | 2484901.857 |  | Yes | No | No | No
430
78 |  | 39/2 | A(-)3 |  |  | 816 | 50.83 | 5708 | 337.736 | 801 | 400.5 | 188 | 176 | 364 | 195 | 178 | 373 | 74°27'5.95" | 22°28'7.222" | 443586.394 | 2484807.131 |  | Yes | No | No | No
[5 empty] | 371 | [16 empty] | Pond
79 |  | 39/3 | A+9 |  |  |  | 62.83 | 6079 | 327.876 | 849 | 424.5 | 196 | 230 | 426 | 194 | 233 | 427 | 74°27'18.623" | 22°28'4.607" | 443948.28 | 2484725.402 |  | Yes | No | No | No
[5 empty] | 478 | [16 empty] | Pond, Metal road, LT line
80 | AP 40 | 40/0 | C1+7.5 | 20° 53' 17"RT |  |  | 55.82 | 6557 | 332.157 | 828 | 414 | 250 | 245 | 495 | 248 | 226 | 475 | 74°27'34.95" | 22°28'1.238" | 444414.5 | 2484620.11 |  | Yes | No | No | No
[5 empty] | 350 | [16 empty] | LT line, 11kV line, Nala, Well
81 |  | 40/1 | A+1.5 |  |  |  | 55.33 | 6907 | 326.252 | 700 | 370.5 | 106 | 190 | 296 | 125 | 186 | 311 | 74°27'45.173" | 22°27'54.971" | 444705.974 | 2484426.35 |  | No | No | No | No
[5 empty] | 350 | [16 empty] | Nla, Well, LT line, 11kV line
82 |  | 40/2 | A+0 |  |  |  | 53.83 | 7257 | 324.984 | 675 | 370.5 | 161 | 106 | 267 | 165 | 122 | 287 | 74°27'55.396" | 22°27'48.703" | 444997.448 | 2484232.59 |  | No | No | No | No
[5 empty] | 325 | [16 empty] | 11kV line, Concrete road, Temple, Cart track
83 |  | 40/3 | A(-)3 |  |  |  | 50.83 | 7582 | 338.023 | 722 | 370.5 | 219 | 234 | 453 | 204 | 225 | 429 | 74°28'4.889" | 22°27'42.883" | 445268.103 | 2484052.67 |  | No | No | No | No
[5 empty] | 397 | [16 empty] | Nala
84 |  | 40/4 | A+0 |  |  |  | 53.83 | 7979 | 327.419 | 811 | 370.5 | 164 | 241 | 405 | 174 | 233 | 406 | 74°28'16.484" | 22°27'35.774" | 445598.717 | 2483832.891 |  | No | No | No | No
[5 empty] | 414 | [16 empty] | Nala
85 |  | 40/5 | A(-)3 |  |  |  | 50.83 | 8393 | 322.748 | 828.923 | 370.5 | 174 | 187 | 361 | 183 | 193 | 376 | 74°28'28.575" | 22°27'28.36" | 445943.489 | 2483603.701 |  | No | No | No | No
[5 empty] | 414.923 | [16 empty] | Cart track, Nala, LT line
86 | AP 41 | 41/0 | C2+0 | 22° 44' 33"LT |  | 2250.92 | 48.32 | 8807.923 | 324.438 | 819.779 | 370.5 | 228 | 136 | 364 | 223 | 153 | 376 | 74°28'40.693" | 22°27'20.929" | 446289.03 | 2483374 |  | No | No | No | No
[5 empty] | 404.856 | [16 empty] | Nala, LT line
87 | AP 41 | 41A/0 | C2+6 | 22° 29' 48"RT |  | 404.86 | 54.32 | 9212.779 | 333.607 | 780.856 | 370.5 | 270 | 190 | 460 | 254 | 190 | 444 | 74°28'54.614" | 22°27'18.49" | 446686.62 | 2483297.64 |  | No | No | No | No
[5 empty] | 376 | [16 empty] | Fencing, Cart track, Nala, 11kV line
88 |  | 41A/1 | A+9 |  |  |  | 62.83 | 9588.779 | 330.278 | 763.884 | 370.5 | 187 | 216 | 403 | 188 | 211 | 398 | 74°29'5.625" | 22°27'11.8" | 447000.637 | 2483090.833 |  | No | No | No | No
[5 empty] | 387.884 | [16 empty] | Nala, Well
89 | AP 41 | 41B/0 | B2+0 | 13° 18' 30"LT |  | 763.88 | 48.32 | 9976.663 | 334.706 | 775.884 | 370.5 | 172 | 160 | 333 | 179 | 169 | 348 | 74°29'16.985" | 22°27'4.898" | 447324.58 | 2482877.49 |  | No | No | No | No
[5 empty] | 388 | [16 empty] | Cart track
90 |  | 41B/1 | A+9 |  |  |  | 62.83 | 10364.663 | 332.912 | 818 | 370.5 | 228 | 210 | 439 | 220 | 212 | 432 | 74°29'29.752" | 22°27'0.61" | 447689.042 | 2482744.405 |  | No | No | No | No
[5 empty] | 430 | [16 empty] | LT line, Cart track, Metal road
91 |  | 41B/2 | A+6 |  |  |  | 59.83 | 10794.663 | 337.142 | 775.984 | 370.5 | 221 | 235 | 456 | 220 | 219 | 439 | 74°29'43.901" | 22°26'55.858" | 448092.955 | 2482596.914 |  | No | No | No | No
345.984
92 | AP 42 | 42/0 | D60+0 | 49° 6' 24"RT |  | 1163.98 | 48.32 | 11140.647 | 331.416 | 728.984 | 370.5 | 112 | 168 | 279 | 128 | 174 | 302 | 74°29'55.285" | 22°26'52.034" | 448417.95 | 2482478.24 |  | No | No | No | No
[5 empty] | 383 | [16 empty] | Nala
93 |  | 42/1 | A+7.5 |  |  |  | 61.33 | 11523.647 | 329.031 | 769 | 370.5 | 216 | 280 | 496 | 210 | 260 | 470 | 74°30'0.093" | 22°26'40.407" | 448554.165 | 2482120.281 |  | No | No | No | No
[5 empty] | 386 | [16 empty] | Boring, Well
94 |  | 42/2 | A+9 |  |  |  | 62.83 | 11909.647 | 308.769 | 844.967 | 370.5 | 107 | 284 | 391 | 128 | 272 | 400 | 74°30'4.937" | 22°26'28.689" | 448691.447 | 2481759.519 |  | No | No | No | No
[5 empty] | 458.967 | [16 empty] | 11kV line, LT line, Nala
95 | AP 43 | 43/0 | D45(-)3 | 38° 42' 5"LT |  | 1227.97 | 45.32 | 12368.614 | 307.028 | 788.84 | 370.5 | 177 | 83 | 260 | 190 | 111 | 301 | 74°30'10.698" | 22°26'14.757" | 448854.68 | 2481330.56 |  | Yes | No | No | No
[5 empty] | 329.873 | [16 empty] | Nala, Concrete road
96 | AP 44 | 44/0 | C2(-)3 | 24° 25' 53"RT |  | 329.87 | 45.32 | 12698.487 | 321.296 | 698.873 | 370.5 | 248 | 114 | 361 | 221 | 130 | 351 | 74°30'20.664" | 22°26'9.348" | 449139.01 | 2481163.31 |  | Yes | No | No | No
[5 empty] | 369 | [16 empty] | Nala
97 |  | 44/1 | A+6 |  |  |  | 59.83 | 13067.487 | 327.36 | 835.935 | 370.5 | 257 | 277 | 534 | 241 | 268 | 509 | 74°30'28.122" | 22°25'59.553" | 449351.206 | 2480861.426 |  | Yes | No | No | No
[5 empty] | 466.935 | [16 empty] | Cart track, 11kV lines
98 | AP 45 | 45/0 | C1+6 | 17° 44' 41"LT |  | 835.94 | 54.32 | 13534.422 | 315.927 | 771.789 | 370.5 | 191 | 93 | 284 | 201 | 115 | 316 | 74°30'37.559" | 22°25'47.158" | 449619.72 | 2480479.42 |  | Yes | No | No | No
[5 empty] | 304.854 | [16 empty] | Metal road, Nala, 11kV line
99 | AP 46 | 46/0 | D60+18 | 31° 18' 18"LT |  | 304.85 | 66.32 | 13839.276 | 313.095 | 518.857 | 370.5 | 212 | 39 | 250 | 190 | 75 | 265 | 74°30'46.08" | 22°25'41.196" | 449862.7 | 2480295.31 |  | Yes | No | No | No
[5 empty] | 214.003 | [16 empty] | 400KV D/C OHTL(MPEB) , 11kV line,
100 | AP 47 | 47/0 | D60+25 | 15° 51' 9"RT |  | 214 | 73.32 | 14053.279 | 312.508 | 648.002 | 370.5 | 176 | 328 | 503 | 139 | 302 | 441 | 74°30'53.529" | 22°25'40.51" | 450075.59 | 2480273.51 |  | Yes | No | No | No
[5 empty] | 433.999 | [16 empty] | 11kV Lines, Nala
101 |  | 47/1 | A+3 |  |  |  | 56.83 | 14487.278 | 307.441 | 847.999 | 370.5 | 108 | 145 | 254 | 135 | 161 | 296 | 74°31'7.653" | 22°25'35.333" | 450478.835 | 2480113.046 |  | Yes | No | No | No
[5 empty] | 414 | [16 empty] | Nala, 11kV line, 33kV line
102 |  | 47/2 | A+9 |  |  |  | 62.83 | 14901.278 | 316.076 | 830 | 370.5 | 270 | 173 | 442 | 255 | 182 | 437 | 74°31'21.126" | 22°25'30.395" | 450863.498 | 2479959.976 |  | Yes | No | No | No
[5 empty] | 416 | [16 empty] | 11kV line, Cart track
103 |  | 47/3 | A+3 |  |  |  | 56.83 | 15317.278 | 330.577 | 750.881 | 370.5 | 245 | 227 | 472 | 236 | 213 | 449 | 74°31'34.664" | 22°25'25.433" | 451250.019 | 2479806.167 |  | Yes | No | No | No
[5 empty] | 334.881 | [16 empty] | Nala, 11kV lines
104 | AP 48 | 48/0 | C1+0 | 21° 49' 11"RT |  | 1598.88 | 48.32 | 15652.159 | 322.33 | 690.881 | 370.5 | 109 | 174 | 283 | 123 | 176 | 299 | 74°31'45.562" | 22°25'21.438" | 451561.17 | 2479682.35 |  | Yes | No | No | No
[5 empty] | 356 | [16 empty] | Nala, Cart track, LT line
105 |  | 48/1 | A+0 |  |  |  | 53.83 | 16008.159 | 323.077 | 741 | 370.5 | 183 | 211 | 394 | 182 | 206 | 388 | 74°31'54.619" | 22°25'13.492" | 451819.322 | 2479437.21 |  | Yes | No | No | No
[5 empty] | 385 | [16 empty] | Nala, Well, LT line, Cart track
106 |  | 48/2 | A+3 |  |  |  | 56.83 | 16393.159 | 316.307 | 764.877 | 370.5 | 175 | 182 | 357 | 180 | 185 | 365 | 74°32'4.413" | 22°25'4.898" | 452098.504 | 2479172.101 |  | Yes | No | No | No
[5 empty] | 379.877 | [16 empty] | Nala, 11kV line, Concrete road, Cart track
107 | AP 49 | 49/0 | D45+6 | 39° 6' 45"RT |  | 1120.88 | 54.32 | 16773.036 | 315.045 | 737.843 | 370.5 | 198 | 270 | 469 | 196 | 244 | 440 | 74°32'14.077" | 22°24'56.419" | 452373.97 | 2478910.52 |  | Yes | No | No | No
[5 empty] | 357.966 | [16 empty] | LT line, Nala, Cart trak, Well
108 | AP 49 | 49A/0 | D45(-)3 | 33° 32' 56"LT |  | 357.97 | 45.32 | 17131.002 | 306.531 | 681.964 | 370.5 | 89 | 141 | 230 | 116 | 149 | 264 | 74°32'15.721" | 22°24'44.878" | 452419.88 | 2478555.51 |  | Yes | No | No | No
[5 empty] | 323.998 | [16 empty] | Metal road, 11kV lines, Nala
109 | AP 49 | 49B/0 | D45+3 | 41° 47' 52"RT |  | 324 | 51.32 | 17455 | 304.088 | 735.998 | 370.5 | 183 | 258 | 441 | 176 | 246 | 423 | 74°32'23.17" | 22°24'36.937" | 452632.09 | 2478310.68 |  | Yes | No | No | No
[5 empty] | 412 | [16 empty] | Nala, LT line, Pump house
110 |  | 49B/1 | A+0 |  |  |  | 53.83 | 17867 | 295.068 | 842.869 | 370.5 | 155 | 197 | 352 | 167 | 202 | 369 | 74°32'22.992" | 22°24'23.539" | 452625.76 | 2477898.729 |  | Yes | No | No | No
[5 empty] | 430.869 | [16 empty] | Nala
111 | AP 50 | 50/0 | D60+6 | 32° 44' 1"LT |  | 842.87 | 54.32 | 18297.869 | 293.76 | 660.869 | 370.5 | 235 | 145 | 380 | 231 | 130 | 361 | 74°32'22.807" | 22°24'9.527" | 452619.14 | 2477467.91 |  | Yes | No | No | No
[5 empty] | 230 | [16 empty] | Railway line, Telecom cable, Nala
112 | AP 51 | 51/0 | D60+9 | 19° 6' 35"LT |  |  | 57.32 | 0 | 287.656 | 650 | 325 | 85 | 263 | 348 | 100 | 248 | 348 | 74°32'27.073" | 22°24'3.186" | 452740.52 | 2477272.55 | VILLAGE :- KANDA | Yes | No | No | No
[5 empty] | 420 | [16 empty] | LT line, Nala
113 |  | 51/1 | A(-)3 |  |  |  | 50.83 | 420 | 287.673 | 758 | 379 | 158 | 171 | 329 | 174 | 171 | 345 | 74°32'38.511" | 22°23'54.615" | 453066.75 | 2477008.025 | VILLAGE :- KANDA | Yes | No | No | No
338
114 |  | 51/2 | A(-)1.5 |  |  |  | 52.33 | 758 | 285.815 | 567 | 283.5 | 167 | 109 | 276 | 168 | 111 | 279 | 74°32'47.715" | 22°23'47.718" | 453329.288 | 2476795.144 | VILLAGE :- KANDA | Yes | No | No | No
[5 empty] | 229 | [16 empty] | Pump house, Temple
115 | AP 52 | 52/0 | C2(-)3 | 26° 53' 12"RT |  | 987 | 45.32 | 987 | 288.11 | 626 | 313 | 121 | 256 | 377 | 119 | 241 | 360 | 74°32'53.952" | 22°23'43.044" | 453507.18 | 2476650.9 | VILLAGE :- KANDA | Yes | No | No | No
[5 empty] | 397 | [16 empty] | River, LT line, 11kV line
116 |  | 52/1 | A(-)3 |  |  |  | 50.83 | 1384 | 275.656 | 769.5 | 384.75 | 143 | 104 | 247 | 158 | 126 | 284 | 74°32'59.654" | 22°23'31.272" | 453669.137 | 2476288.438 | VILLAGE :- KANDA | Yes | No | No | No
[5 empty] | 372.5 | [16 empty] | Nala, Foot track, Temple
117 | AP 53 | 53/0 | D45(-)3 | 33° 50' 48"RT |  | 769.5 | 45.32 | 1756.5 | 292.717 | 829 | 414.5 | 270 | 172 | 442 | 248 | 183 | 431 | 74°33'5" | 22°23'20.235" | 453820.98 | 2475948.61 | VILLAGE :- KANDA | Yes | No | No | No
[5 empty] | 456.5 | [16 empty] | Nala, Cart track, LT line
118 | AP 54 | 54/0 | D45+9 (RC = 2M) | 42° 0' 45"LT |  | 456.5 | 57.32 | 2213 | 293.986 | 881 | 440.5 | 286 | 218 | 504 | 275 | 217 | 492 | 74°33'2.339" | 22°23'5.603" | 453743.55 | 2475498.95 | VILLAGE :- CHAMAR BEGDA EQUAL RC = 2M | Yes | No | No | No
[5 empty] | 424.5 | [16 empty] | LT line, Nala, Mud road, Metal road, 11kV line
119 | AP 55 | 55/0 | C1+9 (RC = 3M) | 20° 33' 21"LT |  | 424.5 | 57.32 | 2637.5 | 291.553 | 787.496 | 393.748 | 206 | 222 | 428 | 208 | 212 | 420 | 74°33'10.291" | 22°22'53.956" | 453969.88 | 2475140.13 | VILLAGE :- CHAMAR BEGDA EQUAL RC = 3M | Yes | No | No | No
[5 empty] | 362.996 | [16 empty] | Nala, Well, Fencing, Boring pump
120 |  | 55/1 | A(-)3 |  |  |  | 50.83 | 3000.496 | 298.275 | 760.999 | 380.4995 | 141 | 159 | 300 | 151 | 169 | 320 | 74°33'20.425" | 22°22'46.846" | 454259.009 | 2474920.652 | VILLAGE :- CHAMAR BEGDA LT line to be shifted | Yes | No | No | No
[5 empty] | 398.003 | [16 empty] | LT line, Nala, Well
121 |  | 55/2 | A+6 |  |  |  | 59.83 | 3398.499 | 298.232 | 834.004 | 417.002 | 240 | 223 | 463 | 230 | 223 | 453 | 74°33'31.535" | 22°22'39.05" | 454576.022 | 2474680.009 | VILLAGE :- CHAMAR BEGDA | Yes | No | No | No
[5 empty] | 436.001 | [16 empty] | Metal road, LT line
122 | AP 56 | 56/0 | B2+9 | 11° 21' 34"LT |  | 1197 | 57.32 | 3834.5 | 294.115 | 799 | 399.5 | 214 | 239 | 453 | 215 | 223 | 438 | 74°33'43.706" | 22°22'30.51" | 454923.3 | 2474416.39 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
[5 empty] | 362.999 | [16 empty] | Cart track, LT line, Pond
123 |  | 56/1 | A+9 |  |  |  | 62.83 | 4197.499 | 282.798 | 735.999 | 367.9995 | 125 | 222 | 347 | 141 | 212 | 353 | 74°33'55.146" | 22°22'25.394" | 455249.997 | 2474258.159 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
[5 empty] | 373 | [16 empty] | 11kV line, Nala, LT line, Well
124 | AP 57 | 57/0 | C1+3 | 18° 38' 25"LT |  | 735.999 | 51.32 | 4570.499 | 281.784 | 706 | 353 | 152 | 77 | 229 | 162 | 97 | 259 | 74°34'6.899" | 22°22'20.139" | 455585.63 | 2474095.6 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
[5 empty] | 333 | [16 empty] | Concrete road, Fencing
125 |  | 57/1 | A+9 |  |  |  | 62.83 | 4903.499 | 292.862 | 830 | 415 | 256 | 215 | 471 | 237 | 223 | 460 | 74°34'18.455" | 22°22'18.812" | 455916.003 | 2474053.852 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
[5 empty] | 497 | [16 empty] | Cart track, LT line, 11kV line, Nala, Pump house
126 | AP 58 | 58/0 | C2+9 | 28° 56' 11"RT |  | 830 | 57.32 | 5400.499 | 302.748 | 853 | 426.5 | 284 | 212 | 496 | 277 | 204 | 481 | 74°34'35.704" | 22°22'16.831" | 456409.1 | 2473991.54 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
356
127 |  | 58/1 | A+7.5 |  |  |  | 61.33 | 5756.499 | 297.575 | 791 | 395.5 | 146 | 208 | 354 | 154 | 211 | 365 | 74°34'45.778" | 22°22'10.029" | 456696.603 | 2473781.592 | VILLAGE :- BANJHABAIDA | Yes | No | No | No
[5 empty] | 435 | [16 empty] | Metal road, Nala
128 |  | 58/2 | A+9 |  |  |  | 62.83 | 6191.499 | 298.551 | 849 | 424.5 | 228 | 268 | 496 | 226 | 254 | 480 | 74°34'58.086" | 22°22'1.718" | 457047.906 | 2473525.055 | VILLAGE :- WAGDI | Yes | No | No | No
[5 empty] | 414 | [16 empty] | Cart track
129 |  | 58/3 | A+3 |  |  |  | 56.83 | 6605.499 | 290.445 | 849 | 424.5 | 147 | 229 | 376 | 162 | 227 | 389 | 74°35'9.801" | 22°21'53.807" | 457382.249 | 2473280.902 | VILLAGE :- JAMNI | Yes | No | No | No
435
130 | AP 59 | 59/0 | D45+9 | 34° 45' 1"LT |  | 1640 | 57.32 | 7040.499 | 281.857 | 693 | 346.5 | 207 | 190 | 397 | 210 | 163 | 373 | 74°35'22.107" | 22°21'45.497" | 457733.49 | 2473024.41 | VILLAGE :- JAMNI | Yes | No | No | No
[5 empty] | 258 | [16 empty] | 132 KV S/C KUKSHI TO JOBAT T/L, Concrete road, Well, Nala
131 | AP 60 | 60/0 | D45+6 | 36° 41' 50"RT |  | 258 | 54.32 | 7298.499 | 277.346 | 641 | 320.5 | 68 | 239 | 307 | 96 | 224 | 320 | 74°35'31.124" | 22°21'45.317" | 457991.36 | 2473018.16 | VILLAGE :- JAMNI | Yes | No | No | No
[5 empty] | 383 | [16 empty] | Cart track, Concrete road, Nala, 11kV line, LT line
132 |  | 60/1 | A(-)1.5 |  |  |  | 52.33 | 7681.499 | 275.261 | 654 | 327 | 145 | 101 | 246 | 160 | 112 | 272 | 74°35'41.687" | 22°21'37.66" | 458292.816 | 2472781.912 | VILLAGE :- JAMNI | Yes | No | No | No
[5 empty] | 271 | [16 empty] | Cart track, 11kV line
133 | AP 61 | 61/0 | D45(-)3 | 41° 0' 23"RT |  | 654 | 45.32 | 7952.499 | 281.841 | 663.003 | 331.5015 | 170 | 175 | 345 | 160 | 181 | 341 | 74°35'49.162" | 22°21'32.24" | 458506.18 | 2472614.7 | VILLAGE :- JAMNI | Yes | No | No | No
[5 empty] | 392.003 | [16 empty] | Cart track, Nala, House
134 | AP 62 | 62/0 | C2(-)3 | 24° 6' 55"LT |  | 392.003 | 45.32 | 8344.502 | 286.39 | 830 | 415 | 217 | 197 | 414 | 212 | 203 | 415 | 74°35'51.792" | 22°21'19.728" | 458580.36 | 2472229.78 | VILLAGE :- JAMNI | No | No | No | No
[5 empty] | 438 | [16 empty] | Nala, Metal road, LT line
135 |  | 62/1 | A+0 |  |  |  | 53.83 | 8782.502 | 288.736 | 848 | 424 | 242 | 205 | 446 | 237 | 205 | 442 | 74°36'0.614" | 22°21'8.085" | 458831.732 | 2471871.094 | VILLAGE :- JAMNI | No | No | No | No
[5 empty] | 410 | [16 empty] | Well, Nala, 11kV line
136 |  | 62/2 | A+3 |  |  |  | 56.83 | 9192.502 | 285.879 | 777 | 388.5 | 206 | 133 | 339 | 206 | 146 | 352 | 74°36'8.872" | 22°20'57.185" | 459067.035 | 2471535.337 | VILLAGE :- JAMNI | No | No | No | No
[5 empty] | 367 | [16 empty] | 33kV line, 11kV line, Nala
137 |  | 62/3 | A+3 |  |  |  | 56.83 | 9559.502 | 296.349 | 761.5 | 380.75 | 235 | 168 | 403 | 223 | 175 | 398 | 74°36'16.263" | 22°20'47.429" | 459277.66 | 2471234.794 | 11kV line to be diverted | No | No | No | No
[5 empty] | 394.5 | [16 empty] | Nala, 11kV line, 33kV line
138 | AP 63 | AP63 | C1+9 | 20° 45' 34"LT |  | 1609.5 | 57.32 | 9954.002 | 296.916 | 767.5 | 383.75 | 227 | 53 | 280 | 220 | 91 | 311 | 74°36'24.205" | 22°20'36.946" | 459503.963 | 2470911.879 | VILLAGE :- JAMNI 33kV line to be diverted | No | No | No | No
[5 empty] | 373 | [16 empty] | 11kV line, Nala, Concrete road, 33kV line
139 |  | 63/1 | B1+9 |  |  |  | 57.32 | 10327.002 | 324.195 | 712 | 356 | 322 | 321 | 643 | 284 | 273 | 557 | 74°36'35.007" | 22°20'30.151" | 459812.403 | 2470702.127 | Cross arm Strengthnening required due to weight span limit exceeded | No | No | No | No
339
140 |  | 63/2 | B1+9 |  |  |  | 57.32 | 10666.002 | 297.155 | 819 | 409.5 | 20 | 226 | 246 | 68 | 230 | 298 | 74°36'44.824" | 22°20'23.975" | 460092.728 | 2470511.494 | VILLAGE :- KHARI | No | No | No | No
[5 empty] | 480 | [16 empty] | Nala, LT line
141 |  | 63/3 | A(-)3 |  |  |  | 50.83 | 11146.002 | 313.104 | 794 | 397 | 255 | 131 | 386 | 253 | 136 | 389 | 74°36'58.725" | 22°20'15.229" | 460489.648 | 2470241.572 | VILLAGE :- KHARI | No | No | No | No
314
142 |  | 63/4 | A+0 |  |  |  | 53.83 | 11460.002 | 314.967 | 813 | 406.5 | 184 | 269 | 452 | 179 | 265 | 444 | 74°37'7.818" | 22°20'9.508" | 460749.301 | 2470064.997 | VILLAGE :- KHARI | Yes | Yes | Yes | No
[5 empty] | 499 | [16 empty] | Cart track, Nala
143 | AP 64 | AP64 | B2+0 | 11° 3' 47"RT |  | 2005 | 48.32 | 11959.002 | 309.74 | 866 | 433 | 223 | 174 | 397 | 227 | 179 | 406 | 74°37'22.264" | 22°20'0.418" | 461161.83 | 2469784.46 | VILLAGE :-TAKARI | Yes | Yes | Yes | No
[5 empty] | 388 | [16 empty] | Cart track
144 |  | 64/1 | A+0 |  |  |  | 53.83 | 12347.002 | 314.133 | 770 | 385 | 215 | 243 | 458 | 210 | 230 | 441 | 74°37'31.832" | 22°19'51.474" | 461434.841 | 2469508.763 | VILLAGE :-TAKARI | Yes | Yes | Yes | No
[5 empty] | 382 | [16 empty] | Nala, Well, LT line
145 |  | 64/2 | A+0 |  |  |  | 53.83 | 12729.002 | 303.199 | 819 | 409.5 | 140 | 158 | 298 | 153 | 169 | 322 | 74°37'41.251" | 22°19'42.668" | 461703.631 | 2469237.329 | VILLAGE :-TAKARI | Yes | Yes | Yes | No
[5 empty] | 437 | [16 empty] | Cart track
146 |  | 64/3 | A+3 |  |  |  | 59.83 | 13166.002 | 307.749 | 822 | 411 | 250 | 213 | 463 | 239 | 212 | 452 | 74°37'52.027" | 22°19'32.594" | 462011.12 | 2468926.815 | VILLAGE :-TAKARI RC EXPECTED | Yes | Yes | Yes | No
[5 empty] | 385 | [16 empty] | Well
147 |  | 64/4 | A+0 |  |  |  | 56.83 | 13551.002 | 309.623 | 821 | 410.5 | 203 | 203 | 406 | 205 | 206 | 411 | 74°38'1.52" | 22°19'23.718" | 462282.021 | 2468653.25 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 436 | [16 empty] | Cart track
148 |  | 64/5 | A+3 |  |  |  | 58.33 | 13987.002 | 311.254 | 849 | 424.5 | 229 | 192 | 421 | 226 | 197 | 423 | 74°38'12.27" | 22°19'13.666" | 462588.807 | 2468343.446 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 413 | [16 empty] | 11kV line, Well
149 | AP 65 | 65/0 | B2+0 | 10° 39' 10"RT |  | 2441 | 48.32 | 14400.002 | 316.718 | 818 | 409 | 227 | 313 | 540 | 223 | 288 | 511 | 74°38'22.454" | 22°19'4.143" | 462879.457 | 2468049.936 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 405 | [16 empty] | 11kV line, Cart track, Pump house, LT line
150 |  | 65/1 | A+0 |  |  |  | 53.83 | 14805.002 | 299.079 | 756 | 378 | 118 | 198 | 315 | 144 | 189 | 332 | 74°38'30.412" | 22°18'53.25" | 463106.322 | 2467714.44 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 351 | [16 empty] | Well, Low land
151 | AP 66 | 66/0 | D45+0 | 35° 58' 19"RT |  | 756 | 48.32 | 15156.002 | 290.794 | 720.995 | 360.4975 | 130 | 215 | 345 | 139 | 207 | 346 | 74°38'37.301" | 22°18'43.818" | 463302.74 | 2467423.97 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 369.995 | [16 empty] | Tar road, Nala, 11kV line, Cart track, Fencing, Well
152 | AP 67 | 67/0 | D60+0 | 52° 20' 9"LT |  | 369.995 | 48.32 | 15525.997 | 284.789 | 721.995 | 360.9975 | 155 | 194 | 349 | 164 | 190 | 354 | 74°38'36.902" | 22°18'31.791" | 463290.44 | 2467054.18 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 352 | [16 empty] | Cart track, Nala, LT line
153 |  | 67/1 | A+0 |  |  |  | 53.83 | 15877.997 | 281.249 | 784 | 392 | 159 | 205 | 364 | 163 | 208 | 372 | 74°38'46.404" | 22°18'24.519" | 463561.781 | 2466829.952 | VILLAGE :-TALAWADI | Yes | Yes | Yes | No
[5 empty] | 432 | [16 empty] | Pump house, Nala, LT line
154 |  | 67/2 | A+6 |  |  |  | 59.83 | 16309.997 | 277.97 | 849 | 424.5 | 228 | 222 | 450 | 225 | 219 | 445 | 74°38'58.066" | 22°18'15.594" | 463894.79 | 2466554.763 | VILLAGE :-TALAWADI ,LT line to be diverted | Yes | Yes | Yes | No
[5 empty] | 417 | [16 empty] | Cart track, Well
155 |  | 67/3 | A+6 |  |  |  | 59.83 | 16726.997 | 274.867 | 845 | 422.5 | 196 | 256 | 452 | 199 | 246 | 446 | 74°39'9.322" | 22°18'6.979" | 464216.237 | 2466289.13 | VILLAGE :-SALKHEDA | Yes | Yes | Yes | No
[5 empty] | 428 | [16 empty] | Nala, Well, Concrete road, LT line, 11kV line
156 | AP 68 | 68/0 | D45+0 | 37° 21' 21"RT |  | 1629 | 48.32 | 17154.997 | 270.996 | 806.999 | 403.4995 | 173 | 206 | 379 | 184 | 202 | 386 | 74°39'20.876" | 22°17'58.136" | 464546.21 | 2466016.45 | VILLAGE :-SALKHEDA | Yes | Yes | Yes | No
[5 empty] | 378.999 | [16 empty] | Metal road
157 |  | 68/1 | A+0 |  |  |  | 53.83 | 17533.996 | 267.533 | 774.999 | 387.4995 | 174 | 210 | 383 | 178 | 207 | 385 | 74°39'23.902" | 22°17'46.136" | 464631.949 | 2465647.276 | VILLAGE :-SALKHEDA | Yes | Yes | Yes | No
[5 empty] | 396 | [16 empty] | Water pipeline
158 |  | 68/2 | A+3 |  |  |  | 56.83 | 17929.996 | 262.033 | 792 | 396 | 187 | 231 | 418 | 190 | 223 | 413 | 74°39'27.064" | 22°17'33.597" | 464721.533 | 2465261.543 | VILLAGE :-SALKHEDA | Yes | Yes | Yes | No
[5 empty] | 396 | [16 empty] | 11kV line, LT line, Low land
159 | AP 69 | 69/0 | D45+0 | 30° 47' 8"LT |  | 1170.999 | 48.32 | 18325.996 | 258.081 | 795.999 | 397.9995 | 166 | 226 | 393 | 175 | 220 | 395 | 74°39'30.225" | 22°17'21.058" | 464811.12 | 2464875.8 | VILLAGE :-SALKHEDA | Yes | Yes | Yes | No
[5 empty] | 399.999 | [16 empty] | Nala, Cart track
160 |  | 69/1 | A+0 |  |  |  | 53.83 | 18725.995 | 252.335 | 796.999 | 398.4995 | 175 | 204 | 378 | 182 | 203 | 385 | 74°39'39.934" | 22°17'11.699" | 465088.28 | 2464587.388 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
[5 empty] | 397 | [16 empty] | Temple, Cart track, Nala
161 |  | 69/2 | A+0 |  |  |  | 53.83 | 19122.995 | 251.236 | 775.998 | 387.999 | 194 | 209 | 403 | 196 | 204 | 400 | 74°39'49.569" | 22°17'2.409" | 465363.363 | 2464301.139 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
[5 empty] | 378.998 | [16 empty] | Cart track
162 |  | 69/3 | A+0 |  |  |  | 53.83 | 19501.993 | 247.21 | 757.998 | 378.999 | 170 | 194 | 365 | 176 | 193 | 369 | 74°39'58.767" | 22°16'53.541" | 465625.972 | 2464027.87 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
[5 empty] | 379 | [16 empty] | Cart track, 11kV line
163 |  | 69/4 | A+0 |  |  |  | 53.83 | 19880.993 | 246.276 | 732 | 366 | 185 | 208 | 393 | 187 | 200 | 386 | 74°40'7.965" | 22°16'44.672" | 465888.582 | 2463754.599 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
[5 empty] | 353 | [16 empty] | 11kV lines
164 | AP 70 | 70/0 | C2(-)3 | 23° 53' 41"RT |  | 1907.997 | 45.32 | 20233.993 | 243.396 | 633 | 316.5 | 146 | 92 | 239 | 155 | 106 | 260 | 74°40'16.525" | 22°16'36.418" | 466132.97 | 2463500.29 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
[5 empty] | 280 | [16 empty] | Pond
165 |  | 70/1 | A+4.5 |  |  |  | 58.33 | 20513.993 | 243.215 | 652 | 326 | 188 | 237 | 426 | 176 | 224 | 399 | 74°40'19.886" | 22°16'27.866" | 466228.578 | 2463237.119 | VILLAGE :-BHEMPURA | Yes | Yes | Yes | No
372
166 |  | 70/2 | A+9 |  |  |  | 62.83 | 20885.993 | 228.364 | 846 | 423 | 136 | 276 | 411 | 150 | 266 | 416 | 74°40'24.351" | 22°16'16.504" | 466355.601 | 2462887.477 | VILLAGE :-MOGRA , 11kV line to be diverted | Yes | Yes | Yes | No
[5 empty] | 474 | [16 empty] | Nala, LT line, Well, Metal road, 11kV line
167 |  | 70/3 | A(-)3 |  |  |  | 50.83 | 21359.993 | 230.535 | 783 | 391.5 | 200 | 218 | 418 | 211 | 201 | 411 | 74°40'30.04" | 22°16'2.026" | 466517.452 | 2462441.966 | VILLAGE :-MOGRA | Yes | Yes | Yes | No
[5 empty] | 309 | [16 empty] | Well, LT line, Boring pump
168 | AP 71 | 71/0 | D45+3 | 38° 12' 10"LT |  | 1435 | 51.32 | 21668.993 | 213.907 | 744 | 372 | 92 | 239 | 331 | 109 | 234 | 343 | 74°40'33.746" | 22°15'52.593" | 466622.9 | 2462151.71 | VILLAGE :-MOGRA | Yes | No | No | No
[5 empty] | 435 | [16 empty] | Well, Nala
169 |  | 71/1 | A+3 |  |  |  | 56.83 | 22103.993 | 208.741 | 846 | 423 | 197 | 235 | 432 | 203 | 228 | 431 | 74d40'46.677"E | 22d15'45.157"N | 466992.478 | 2461922.281 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 411 | [16 empty] | Nala, 11kV line, LT line
170 |  | 71/2 | A(-)3 |  |  |  | 50.83 | 22514.993 | 208.121 | 733 | 366.5 | 177 | 164 | 341 | 185 | 163 | 348 | 74d40'58.893"E | 22d15'38.131"N | 467341.665 | 2461705.511 | LT line to be diverted | Yes | No | No | No
[5 empty] | 322 | [16 empty] | LT line, Well, Cart track,
171 |  | 71/3 | A+0 |  |  |  | 53.83 | 22836.993 | 204.617 | 696 | 348 | 158 | 222 | 380 | 159 | 213 | 373 | 74d41'8.464"E | 22d15'32.626"N | 467615.237 | 2461535.681 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 374 | [16 empty] | Nala, Cart track |  |  |  |  | RC Excepted
172 |  | 71/4 | A(-)3 |  |  |  | 50.83 | 23210.993 | 200.506 | 763 | 381.5 | 153 | 189 | 342 | 162 | 191 | 353 | 74d41'19.581"E | 22d15'26.232"N | 467932.989 | 2461338.425 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 389 | [16 empty] | LT line, Well |  |  |  |  | RC Excepted
173 |  | 71/5 | A+3 |  |  |  | 56.83 | 23599.993 | 195.732 | 809.5 | 404.75 | 201 | 233 | 434 | 199 | 228 | 427 | 74d41'31.143"E | 22d15'19.582"N | 468263.484 | 2461133.258 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 420.5 | [16 empty] | 11kV line, Nala, LT line, Well
174 | AP 72 | 72/0 | D45+0 | 40° 35' 57"RT |  | 2351.5 | 48.32 | 24020.493 | 193.59 | 906.5 | 453.25 | 188 | 180 | 368 | 194 | 189 | 384 | 74d41'43.635"E | 22d15'12.395"N | 468620.572 | 2460911.583 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 436 | [16 empty] | 11kV line, Temple, Nala, Metal road
175 |  | 72/1 | A+9 |  |  |  | 62.83 | 24456.493 | 194.012 | 823.5 | 411.75 | 257 | 233 | 490 | 249 | 224 | 473 | 74d41'48.262"E | 22d14'58.886"N | 468752.184 | 2460495.922 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 387.5 | [16 empty] | Nala
176 | AP 73 | 73/0 | D45+3 | 35° 1' 14"LT |  | 823.5 | 51.32 | 24843.993 | 191.64 | 763.5 | 381.75 | 155 | 126 | 282 | 165 | 144 | 309 | 74d41'52.373"E | 22d14'46.883"N | 468869.11 | 2460126.64 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 376 | [16 empty] | Nala, 11kV line, Cart track
177 | AP 74 | 74/0 | D45+9(RC=2.0M) | 38° 7' 30"LT |  | 376 | 57.32 | 25219.993 | 196.42 | 612 | 306 | 251 | 150 | 401 | 234 | 135 | 369 | 74d42'2.83"E | 22d14'39.468"N | 469167.979 | 2459898.055 | RC=2m | Yes | No | No | No
[5 empty] | 236 | [16 empty] | 132KV S/C Bhatyari -Susari TL, 11kV line, Nala, Cart track
178 | AP 75 | 75/0 | B1+9 | 1° 26' 40"RT |  | 236 | 57.32 | 25455.993 | 194.94 | 730 | 365 | 86 | 310 | 396 | 102 | 296 | 398 | 74d42'11.076"E | 22d14'39.579"N | 469404 | 2459901 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 494 | [16 empty] | Isai river, LT line, 33kV line, Nala
179 |  | 75/1 | A+0 |  |  |  | 53.83 | 25949.993 | 186.569 | 841 | 420.5 | 186 | 157 | 342 | 201 | 161 | 362 | 74d42'28.334"E | 22d14'39.406"N | 469897.96 | 2459894.711 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 347 | [16 empty] | Nala
180 |  | 75/2 | A(-)3 |  |  |  | 50.83 | 26296.993 | 192.915 | 684 | 342 | 191 | 183 | 374 | 187 | 180 | 367 | 74d42'40.456"E | 22d14'39.284"N | 470244.932 | 2459890.293 | VILLAGE :-GIVANYA | Yes | No | No | No
[5 empty] | 337 | [16 empty] | Nala |  |  |  |  | RC Excepted
181 | AP 76 | 76/0 | C2(-)3 | 22° 40' 44"RT |  | 1178 | 45.32 | 26633.993 | 190.38 | 763 | 381.5 | 155 | 138 | 294 | 159 | 157 | 316 | 74d42'52.234"E | 22d14'39.165"N | 470582.06 | 2459886 | VILLAGE :-GIVANYA | Yes | Yes | Yes | Yes
[5 empty] | 426 | [16 empty] | 11kV line, Well, LT line, Nala, Metal road
182 |  | 76/1 | A+6 |  |  |  | 59.83 | 27059.993 | 199.32 | 844.999 | 422.4995 | 277 | 242 | 519 | 262 | 235 | 497 | 74°43'5.903" | 22°14'33.684" | 470972.999 | 2459716.758 | VILLAGE :-GIVANYA | Yes | Yes | Yes | Yes
[5 empty] | 418.999 | [16 empty] | 11kV line, Cart track, Nala |  |  |  |  | RC Excepted
183 |  | 76/2 | A+6 |  |  |  | 59.83 | 27478.992 | 191.799 | 785.999 | 392.9995 | 178 | 223 | 401 | 186 | 214 | 400 | 74°43'19.347" | 22°14'28.294" | 471357.513 | 2459550.298 | VILLAGE :-GIVANYA | Yes | Yes | Yes | Yes
367
184 |  | 76/3 | A(-)3 |  |  |  | 50.83 | 27845.992 | 192.678 | 798 | 399 | 144 | 264 | 408 | 154 | 253 | 407 | 74°43'31.123" | 22°14'23.572" | 471694.308 | 2459404.496 | RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 431 | [16 empty] | Well, Nala |  |  |  |  | RC Excepted
185 |  | 76/4 | A+0 |  |  |  | 53.83 | 28276.992 | 178.113 | 834 | 417 | 168 | 126 | 294 | 180 | 145 | 325 | 74°43'44.951" | 22°14'18.026" | 472089.835 | 2459233.267 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 403 | [16 empty] | ISAI river, Nala |  |  |  |  | RC Excepted
186 |  | 76/5 | A+9 |  |  |  | 62.83 | 28679.992 | 186.294 | 841 | 420.5 | 278 | 112 | 391 | 260 | 139 | 399 | 74°43'57.881" | 22°14'12.84" | 472459.667 | 2459073.163 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 438 | [16 empty] | Cart track
187 |  | 76/6 | A+1.5 |  |  |  | 55.33 | 29117.992 | 220.103 | 794.71 | 397.355 | 327 | 272 | 599 | 302 | 250 | 551 | 74°44'11.934" | 22°14'7.204" | 472861.619 | 2458899.154 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 356.71 | [21 empty] | RC Excepted
188 | AP 77 | 77/0 | B2+0 | 7° 20' 6"LT |  | 2840.709 | 48.32 | 29474.702 | 203.09 | 661.71 | 330.855 | 86 | 189 | 275 | 109 | 177 | 285 | 74°44'23.378" | 22°14'2.613" | 473188.97 | 2458757.44 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 305 | [21 empty] | RC Excepted
189 |  | 77/1 | A(-)3 |  |  |  | 50.83 | 29779.702 | 200.232 | 642.839 | 321.4195 | 116 | 140 | 257 | 129 | 151 | 280 | 74°44'33.621" | 22°13'59.883" | 473482.047 | 2458672.996 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 337.839 | [16 empty] | 11kV line, Cart track
190 | AP 78 | 78/0 | C2(-)3 | 22° 32' 0"RT |  | 642.839 | 45.32 | 30117.541 | 205.39 | 654.839 | 327.4195 | 198 | 301 | 500 | 189 | 252 | 441 | 74°44'44.967" | 22°13'56.859" | 473806.68 | 2458579.46 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 317 | [16 empty] | 11kV line, Metal road
191 |  | 78/1 | B1(-)3 |  |  |  | 45.32 | 30434.541 | 182.061 | 634.777 | 317.3885 | 17 | 179 | 196 | 67 | 172 | 239 | 74°44'53.633" | 22°13'50.439" | 474054.399 | 2458381.662 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 317.777 | [16 empty] | 11kV lines, LT line, Metal road
192 | AP 79 | 79/0 | D45+3 | 35° 5' 26"LT |  | 634.777 | 51.32 | 30752.318 | 172.82 | 774.777 | 387.3885 | 139 | 246 | 386 | 147 | 243 | 390 | 74°45'2.319" | 22°13'44.004" | 474302.726 | 2458183.379 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 457 | [16 empty] | ISAI river, Nala
193 |  | 79/1 | A+9 |  |  |  | 62.83 | 31209.318 | 162.009 | 846.816 | 423.408 | 212 | 230 | 442 | 216 | 223 | 439 | 74°45'18.255" | 22°13'43.117" | 474758.866 | 2458155.351 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 389.816 | [16 empty] | Nala
194 | AP 80 | 80/0 | B1(-)3 | 4° 34' 25"RT |  | 846.816 | 45.32 | 31599.134 | 165.85 | 688.662 | 344.331 | 161 | 105 | 265 | 168 | 122 | 290 | 74°45'31.848" | 22°13'42.359" | 475147.948 | 2458131.445 | VILLAGE :-KURDU DIGPURA | Yes | Yes | Yes | Yes
[5 empty] | 298.846 | [16 empty] | 132 KV S/C RAJGARH TO KUKSHI DP LINE.
195 | AP 81 | 81/0 | B1+6 | 3° 55' 6"RT |  | 298.846 | 54.32 | 31897.98 | 163.68 | 629.777 | 314.8885 | 195 | 207 | 402 | 178 | 194 | 372 | 74°45'42.185" | 22°13'41.007" | 475443.82 | 2458089.39 | VILLAGE :-KAVDIYA KHEDA | Yes | Yes | Yes | Yes
[5 empty] | 330.931 | [16 empty] | SH-39, 11kV lines, Nala
196 | AP 82 | 82/0 | C1+0 | 15° 40' 14"RT |  | 330.931 | 48.32 | 32228.911 | 162.49 | 669.929 | 334.9645 | 125 | 194 | 319 | 138 | 188 | 327 | 74°45'53.497" | 22°13'38.784" | 475767.51 | 2458020.54 | VILLAGE :-KAVDIYA KHEDA | Yes | Yes | Yes | Yes
[5 empty] | 338.998 | [16 empty] | Cart track, LT line, 11kV line
197 |  | 82/1 | A+0 |  |  |  | 50.83 | 32567.909 | 160.87 | 765.998 | 382.999 | 146 | 180 | 325 | 152 | 189 | 341 | 74°46'3.992" | 22°13'33.678" | 476067.715 | 2457863.071 | VILLAGE :-KAVDIYA KHEDA | Yes | Yes | Yes | Yes
[5 empty] | 427 | [16 empty] | 33kV line, 11kV line, Nala, Cart track |  |  |  |  | 1 Mtr. Equal RC
198 |  | 82/2 | A+7.5 |  |  |  | 61.33 | 32994.909 | 158.435 | 828 | 414 | 248 | 196 | 444 | 240 | 198 | 438 | 74°46'17.211" | 22°13'27.246" | 476445.853 | 2457664.724 | VILLAGE :-KAVDIYA KHEDA | Yes | Yes | Yes | Yes
[5 empty] | 401 | [16 empty] | Nala, 11kV line, LT line
199 |  | 82/3 | A+9 |  |  |  | 57.32 | 33395.909 | 158.043 | 880.823 | 440.4115 | 206 | 269 | 475 | 205 | 264 | 469 | 74°46'29.626" | 22°13'21.205" | 476800.965 | 2457478.454 | VILLAGE :-KAVDIYA KHEDA | Yes | Yes | Yes | Yes
[5 empty] | 479.823 | [16 empty] | Wagh river, Nala, Metal road
200 | AP 83 | 83/0 | C2+0 | 25° 22' 54"RT |  | 1646.821 | 48.32 | 33875.732 | 159.06 | 914.823 | 457.4115 | 207 | 184 | 392 | 213 | 192 | 405 | 74°46'44.48" | 22°13'13.976" | 477225.88 | 2457255.57 | VILLAGE :-KAPSI | Yes | Yes | Yes | Yes
[5 empty] | 435 | [16 empty] | 11kV line, Cart track
201 |  | 83/1 | A+3 |  |  |  | 56.83 | 34310.732 | 164.456 | 845 | 422.5 | 252 | 180 | 433 | 245 | 186 | 431 | 74°46'53.629" | 22°13'2.681" | 477487.303 | 2456907.888 | VILLAGE :-KAPSI | Yes | Yes | Yes | Yes
410
202 |  | 83/2 | A+9 |  |  |  | 62.83 | 34720.732 | 164.386 | 775 | 387.5 | 231 | 167 | 398 | 225 | 171 | 397 | 74°47'2.252" | 22°12'52.034" | 477733.702 | 2456580.187 | VILLAGE :-DHARNA | Yes | Yes | Yes | Yes
[5 empty] | 365 | [16 empty] | Cart track, 11kV line, LT line
203 |  | 83/3 | A+9 |  |  |  | 62.83 | 35085.732 | 167.61 | 831.431 | 415.7155 | 198 | 264 | 462 | 195 | 257 | 452 | 74°47'9.928" | 22°12'42.556" | 477953.057 | 2456288.454 | VILLAGE :-DHARNA | Yes | Yes | Yes | Yes
[5 empty] | 466.431 | [16 empty] | 11kV line,SH-26, Nala, Boundary wall
204 | AP 85 | 85/0 | B1+3 | 1° 5' 18"LT |  | 1676.431 | 51.32 | 35552.163 | 165.753 | 887.961 | 443.9805 | 204 | 205 | 409 | 211 | 207 | 418 | 74°47'19.737" | 22°12'30.444" | 478233.37 | 2455915.65 | VILLAGE :-DHARNA | Yes | Yes | Yes | Yes
[5 empty] | 421.53 | [16 empty] | Boundary wall, Cart track, 11kV line, LT line
205 | AP 86 | 86/0 | C1+6 | 16° 52' 42"RT |  | 421.53 | 54.32 | 35973.693 | 164.26 | 629.53 | 314.765 | 218 | 84 | 302 | 217 | 95 | 312 | 74°47'28.823" | 22°12'19.657" | 478493.05 | 2455583.61 | VILLAGE :-DHARNA | Yes | Yes | Yes | Yes
[5 empty] | 208 | [16 empty] | 220kV D/C Suasari to Manawar line, LT line
206 | AP 87 | 87/0 | C1+9 | 16° 27' 36"LT |  | 208 | 57.32 | 36181.693 | 163.01 | 657 | 328.5 | 124 | 265 | 389 | 113 | 256 | 369 | 74°47'31.452" | 22°12'13.356" | 478568.04 | 2455389.77 | VILLAGE :-DHARNA | Yes | Yes | Yes | Yes
[5 empty] | 449 | [16 empty] | 33kV line
207 |  | 87/1 | A+0 |  |  |  | 53.83 | 36630.693 | 161.76 | 847 | 423.5 | 185 | 218 | 403 | 195 | 214 | 409 | 74°47'41.039" | 22°12'1.8" | 478842.055 | 2455034.078 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 398 | [16 empty] | Cart track
208 |  | 87/2 | A+0 |  |  |  | 53.83 | 37028.693 | 157.593 | 802 | 401 | 181 | 199 | 380 | 186 | 200 | 386 | 74°47'49.537" | 22°11'51.556" | 479084.945 | 2454718.787 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 404 | [16 empty] | Cart track, LT line, Well, Pump house
209 |  | 87/3 | A+3 |  |  |  | 56.83 | 37432.693 | 155.409 | 831 | 415.5 | 206 | 221 | 427 | 205 | 220 | 425 | 74°47'58.163" | 22°11'41.158" | 479331.498 | 2454398.744 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 427 | [16 empty] | Cart track, 11kV line, LT line, Well,
210 |  | 87/4 | A+0 |  |  |  | 53.83 | 37859.693 | 156.674 | 827 | 413.5 | 207 | 204 | 411 | 209 | 203 | 412 | 74°48'7.279" | 22°11'30.167" | 479592.086 | 2454060.479 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | LT line, Cart track, Nala
211 |  | 87/5 | A+3 |  |  |  | 56.83 | 38259.693 | 152.915 | 786 | 393 | 197 | 205 | 402 | 198 | 202 | 400 | 74°48'15.818" | 22°11'19.872" | 479836.197 | 2453743.604 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 386 | [16 empty] | LT Line Nala, Well, Metal road, 11kV line LT line to be diverted
212 | AP 88 | 88/0 | C2+3 | 22° 16' 33"LT |  | 2464 | 51.32 | 38645.693 | 150.45 | 786 | 393 | 181 | 208 | 389 | 184 | 206 | 391 | 74°48'24.056" | 22°11'9.94" | 480071.68 | 2453437.93 | VILLAGE :-LONI | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | 11kV line, Nala
213 |  | 88/1 | A+3 |  |  |  | 56.83 | 39045.693 | 148.73 | 842 | 421 | 193 | 245 | 437 | 195 | 239 | 434 | 74°48'36.148" | 22°11'3.427" | 480417.689 | 2453237.237 | VILLAGE :-BARUD | Yes | Yes | Yes | Yes
[5 empty] | 442 | [16 empty] | Nala, Cart track, LT line, Metal road
214 |  | 88/2 | A+0 |  |  |  | 53.83 | 39487.693 | 146.044 | 826 | 413 | 198 | 208 | 407 | 205 | 205 | 409 | 74°48'49.509" | 22°10'56.23" | 480800.029 | 2453015.471 | VILLAGE :-BARUD | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | LT line, Nala, Custard apple Garden
215 |  | 88/3 | A(-)3 |  |  |  | 50.83 | 39871.693 | 145.598 | 774 | 387 | 176 | 180 | 357 | 181 | 184 | 365 | 74°49'1.117" | 22°10'49.977" | 481132.198 | 2452822.806 | VILLAGE :-BARUD | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | Cart track, Nala, Bore, 11kV line, Garden
216 |  | 88/4 | B1+3 |  |  |  | 51.32 | 40261.693 | 142.963 | 929 | 464.5 | 211 | 249 | 460 | 207 | 253 | 460 | 74°49'12.906" | 22°10'43.626" | 481469.557 | 2452627.13 | VILLAGE :-BARUD | Yes | Yes | Yes | Yes
[5 empty] | 539 | [16 empty] | 11kV line, Nala, Uri-Wagah river, Well
217 |  | 88/5 | B1+0 |  |  |  | 48.32 | 40800.693 | 153.04 | 951 | 475.5 | 292 | 204 | 497 | 290 | 205 | 495 | 74°49'29.199" | 22°10'34.848" | 481935.804 | 2452356.697 | VILLAGE :-KOLGAON | Yes | Yes | Yes | Yes
[5 empty] | 412 | [16 empty] | Cart track, Nala, Bore
218 |  | 88/6 | A+0 |  |  |  | 53.83 | 41212.693 | 153.435 | 787 | 393.5 | 209 | 161 | 369 | 208 | 168 | 377 | 74°49'41.652" | 22°10'28.138" | 482292.194 | 2452149.983 | VILLAGE :-KOLGAON | Yes | Yes | Yes | Yes
[5 empty] | 375 | [16 empty] | Bore, Cart track
219 |  | 88/7 | A+3 |  |  |  | 56.83 | 41587.693 | 156.044 | 798 | 399 | 215 | 219 | 435 | 208 | 218 | 426 | 74°49'52.987" | 22°10'22.031" | 482616.577 | 2451961.833 | VILLAGE :-KOLGAON | Yes | Yes | Yes | Yes
[5 empty] | 423 | [16 empty] | Nala, Well, Cart track, 11kV line
220 |  | 88/8 | A+0 |  |  |  | 53.83 | 42010.693 | 157.337 | 763 | 381.5 | 205 | 201 | 406 | 207 | 193 | 400 | 74°50'5.772" | 22°10'15.141" | 482982.482 | 2451749.601 | VILLAGE :-NANODA | Yes | Yes | Yes | Yes
[5 empty] | 340 | [16 empty] | Bore
221 |  | 88/9 | A(-)3 |  |  |  | 50.83 | 42350.693 | 154.569 | 735 | 367.5 | 139 | 209 | 349 | 148 | 207 | 354 | 74°50'16.048" | 22°10'9.603" | 483276.59 | 2451579.012 | VILLAGE :-NANODA | Yes | Yes | Yes | Yes
[5 empty] | 395 | [16 empty] | LT line, Metal, road, Well, Nala
222 |  | 88/10 | A+0 |  |  |  | 53.83 | 42745.693 | 149.116 | 765 | 382.5 | 187 | 206 | 392 | 190 | 201 | 390 | 74°50'27.986" | 22°10'3.169" | 483618.274 | 2451380.827 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 370 | [16 empty] | Nala, Well
223 |  | 88/11 | A(-)3 |  |  |  | 50.83 | 43115.693 | 147.98 | 700 | 350 | 165 | 134 | 299 | 171 | 142 | 313 | 74°50'39.168" | 22°9'57.142" | 483938.332 | 2451195.186 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 330 | [16 empty] | Metal road, 11kV line, Nala, Well
224 | AP 89 | 89/0 | C2+0 | 27° 35' 4"LT |  | 4800 | 48.32 | 43445.693 | 150.66 | 723 | 361.5 | 196 | 191 | 387 | 188 | 192 | 380 | 74°50'49.137" | 22°9'51.769" | 484223.66 | 2451029.69 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 393 | [16 empty] | 11kV line
225 |  | 89/1 | A+0 |  |  |  | 53.83 | 43838.693 | 151.912 | 780 | 390 | 203 | 178 | 380 | 201 | 182 | 384 | 74°51'2.847" | 22°9'51.218" | 484616.277 | 2451012.341 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 387 | [16 empty] | Cart track, LT line, Well, 11kV line
226 |  | 89/2 | A+0 |  |  |  | 53.83 | 44225.693 | 155.35 | 768 | 384 | 210 | 169 | 379 | 206 | 175 | 381 | 74°51'16.347" | 22°9'50.674" | 485002.902 | 2450995.345 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 381 | [16 empty] | 11kV lines, LT line 11kV line to be diverted
227 |  | 89/3 | A+0 |  |  |  | 53.83 | 44606.693 | 159.945 | 786 | 393 | 213 | 189 | 401 | 207 | 193 | 400 | 74°51'29.638" | 22°9'50.139" | 485383.528 | 2450978.437 | VILLAGE :-DESHWALYA | Yes | Yes | Yes | Yes
[5 empty] | 405 | [16 empty] | LT line, Cart track, Nala, Well, LT line to be diverted
228 |  | 89/4 | A+0 |  |  |  | 53.83 | 45011.693 | 163.14 | 830 | 415 | 217 | 187 | 404 | 214 | 194 | 408 | 74°51'43.766" | 22°9'49.57" | 485788.133 | 2450960.558 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
[5 empty] | 425 | [16 empty] | 11kV line, Cart track
229 |  | 89/5 | A+3 |  |  |  | 56.83 | 45436.693 | 166.243 | 824 | 412 | 239 | 214 | 453 | 233 | 211 | 444 | 74°51'58.592" | 22°9'48.972" | 486212.719 | 2450941.796 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
[5 empty] | 399 | [16 empty] | LT line, Cart track, Well
230 |  | 89/6 | A+0 |  |  |  | 53.83 | 45835.693 | 166.075 | 789 | 394.5 | 186 | 214 | 399 | 190 | 209 | 399 | 74°52'12.51" | 22°9'48.41" | 486611.33 | 2450924.182 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
390
231 |  | 89/7 | A+0 |  |  |  | 53.83 | 46225.693 | 162.148 | 763 | 381.5 | 177 | 189 | 366 | 182 | 189 | 371 | 74°52'26.115" | 22°9'47.861" | 487000.95 | 2450906.965 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
[5 empty] | 373 | [16 empty] | Nala, Cart track, Well
232 |  | 89/8 | A+0 |  |  |  | 53.83 | 46598.693 | 161.656 | 774 | 387 | 184 | 198 | 382 | 185 | 199 | 384 | 74°52'39.127" | 22°9'47.335" | 487373.586 | 2450890.499 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
[5 empty] | 401 | [16 empty] | LT lines, Well, Nala
233 |  | 89/9 | A+0 |  |  |  | 53.83 | 46999.693 | 162.358 | 770.825 | 385.4125 | 204 | 197 | 401 | 204 | 194 | 398 | 74°52'53.115" | 22°9'46.77" | 487774.195 | 2450872.796 | VILLAGE :-KHANDWA | Yes | Yes | Yes | Yes
[5 empty] | 369.825 | [16 empty] | Metal road, Canal, LT line
234 | AP 90 | 90/0 | C1+0 | 21° 57' 36"RT |  | 3923.825 | 48.32 | 47369.518 | 160.05 | 759.825 | 379.9125 | 174 | 210 | 384 | 177 | 207 | 384 | 74°53'6.016" | 22°9'46.248" | 488143.66 | 2450856.47 | VILLAGE :-NIMBOL | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | Water tank, Bore, Cart track, Pump house
235 |  | 90/1 | A+0 |  |  |  | 53.83 | 47759.518 | 156.892 | 777 | 388.5 | 181 | 200 | 381 | 185 | 199 | 384 | 74°53'18.413" | 22°9'40.999" | 488498.572 | 2450694.8 | VILLAGE :-NIMBOL | Yes | Yes | Yes | Yes
[5 empty] | 387 | [16 empty] | Nala, LT line, Cart track
236 |  | 90/2 | A+0 |  |  |  | 53.83 | 48146.518 | 155.554 | 779 | 389.5 | 188 | 194 | 381 | 190 | 195 | 384 | 74°53'30.714" | 22°9'35.789" | 488850.754 | 2450534.373 | VILLAGE :-NIMBOL | Yes | Yes | Yes | Yes
[5 empty] | 392 | [16 empty] | LT line, Nala, Well, Cart track, Water tank
237 |  | 90/3 | A+0 |  |  |  | 53.83 | 48538.518 | 156.151 | 786 | 393 | 199 | 205 | 405 | 199 | 204 | 403 | 74°53'43.173" | 22°9'30.512" | 489207.487 | 2450371.874 | VILLAGE :-NIMBOL | Yes | Yes | Yes | Yes
[5 empty] | 394 | [16 empty] | Cart track, Nala, Well
238 |  | 90/4 | A+0 |  |  |  | 53.83 | 48932.518 | 154.385 | 795 | 397.5 | 189 | 197 | 386 | 192 | 198 | 390 | 74°53'55.696" | 22°9'25.208" | 489566.039 | 2450208.545 | VILLAGE :-NIMBOL | Yes | Yes | Yes | Yes
[5 empty] | 401 | [16 empty] | Cart track, Nala, LT line
239 |  | 90/5 | A+3 |  |  |  | 56.83 | 49333.518 | 152.29 | 827 | 413.5 | 205 | 208 | 413 | 204 | 210 | 414 | 74°54'8.441" | 22°9'19.809" | 489930.962 | 2450042.315 | VILLAGE :-MASANYA | Yes | Yes | Yes | Yes
[5 empty] | 426 | [16 empty] | 11kV line, Nala, LT line
240 |  | 90/6 | A+3 |  |  |  | 56.83 | 49759.518 | 153.641 | 804 | 402 | 219 | 218 | 437 | 218 | 211 | 429 | 74°54'21.98" | 22°9'14.074" | 490318.635 | 2449865.722 | VILLAGE :-MASANYA | Yes | Yes | Yes | Yes
[5 empty] | 378 | [16 empty] | Cart track, Nala, Pump house
241 |  | 90/7 | A(-)3 |  |  |  | 50.83 | 50137.518 | 153.635 | 800 | 400 | 161 | 175 | 336 | 168 | 185 | 353 | 74°54'33.994" | 22°9'8.984" | 490662.627 | 2449709.026 | VILLAGE :-BEDWALYA | Yes | Yes | Yes | Yes
[5 empty] | 422 | [16 empty] | Cart track, Nala, LT line, Well
242 |  | 90/8 | A+6 |  |  |  | 59.83 | 50559.518 | 153.144 | 847 | 423.5 | 248 | 199 | 447 | 239 | 203 | 442 | 74°54'47.406" | 22°9'3.302" | 491046.661 | 2449534.09 | VILLAGE :-BEDWALYA | Yes | Yes | Yes | Yes
[5 empty] | 425 | [16 empty] | Pond, Cart track, Metal road, Well, 11kV line, Nala
243 |  | 90/9 | A+6 |  |  |  | 59.83 | 50984.518 | 156.473 | 832 | 416 | 227 | 237 | 464 | 224 | 229 | 453 | 74°55'0.912" | 22°8'57.579" | 491433.424 | 2449357.911 | VILLAGE :-BEDWALYA | Yes | Yes | Yes | Yes
[5 empty] | 407 | [16 empty] | Pump house, Nala
244 |  | 90/10 | A(-)3 |  |  |  | 50.83 | 51391.518 | 158.11 | 785 | 392.5 | 171 | 167 | 339 | 180 | 173 | 353 | 74°55'13.847" | 22°8'52.098" | 491803.807 | 2449189.194 | VILLAGE :-BEDWALYA | Yes | Yes | Yes | Yes
[5 empty] | 378 | [16 empty] | 11kV line
245 |  | 90/11 | A+0 |  |  |  | 53.83 | 51769.518 | 159.726 | 754.944 | 377.472 | 211 | 201 | 413 | 206 | 198 | 404 | 74°55'25.859" | 22°8'47.008" | 492147.799 | 2449032.498 | VILLAGE :-BEDWALYA | Yes | Yes | Yes | Yes
[5 empty] | 376.944 | [16 empty] | Well, LT line, Canal, Nala, Pump house, Cart track
246 | AP 91 | AP91 | B2+0 | 11° 45' 16"RT |  | 4776.944 | 48.32 | 52146.462 | 157.24 | 781.944 | 390.972 | 177 | 193 | 369 | 180 | 196 | 376 | 74°55'37.838" | 22°8'41.931" | 492490.83 | 2448876.24 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 405 | [16 empty] | Water tank, Nala
247 |  | 91/1 | A+3 |  |  |  | 56.83 | 52551.462 | 156.498 | 807 | 403.5 | 213 | 221 | 434 | 211 | 216 | 427 | 74°55'49.245" | 22°8'34.148" | 492817.462 | 2448636.79 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 402 | [16 empty] | Cart track, 11kV line, Nala, Canal, Pond, LT line, Water tank
248 |  | 91/2 | A+3 |  |  |  | 56.83 | 52953.462 | 152.234 | 826 | 413 | 182 | 225 | 407 | 187 | 222 | 410 | 74°56'0.568" | 22°8'26.423" | 493141.675 | 2448399.113 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 424 | [16 empty] | Cart track, Nala
249 |  | 91/3 | A+3 |  |  |  | 56.83 | 53377.462 | 149.331 | 828 | 414 | 200 | 212 | 412 | 204 | 210 | 414 | 74°56'12.509" | 22°8'18.274" | 493483.63 | 2448148.429 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 404 | [16 empty] | Nala, LT line, Well, Metal road, Cart track, 11kV line,
250 |  | 91/4 | A+3 |  |  |  | 56.83 | 53781.462 | 147.207 | 802 | 401 | 193 | 221 | 414 | 196 | 216 | 411 | 74°56'23.887" | 22°8'10.51" | 493809.456 | 2447909.57 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 398 | [16 empty] | LT line, Pump
251 |  | 91/5 | A+0 |  |  |  | 53.83 | 54179.462 | 145.478 | 774 | 387 | 178 | 210 | 388 | 184 | 205 | 389 | 74°56'35.096" | 22°8'2.861" | 494130.443 | 2447674.259 | VILLAGE :-MANDVI | Yes | Yes | Yes | Yes
[5 empty] | 376 | [16 empty] | Well, LT line
252 |  | 91/6 | A(-)3 |  |  |  | 50.83 | 54555.462 | 143.923 | 713 | 356.5 | 166 | 176 | 343 | 172 | 174 | 347 | 74°56'45.685" | 22°7'55.634" | 494433.686 | 2447451.954 | VILLAGE :-SIRSI | Yes | Yes | Yes | Yes
[5 empty] | 337 | [16 empty] | LT line, Cart track
253 |  | 91/7 | A(-)3 |  |  |  | 50.83 | 54892.462 | 142.539 | 705 | 352.5 | 161 | 174 | 335 | 163 | 177 | 340 | 74°56'55.175" | 22°7'49.157" | 494705.477 | 2447252.708 | VILLAGE :-SIRSI | Yes | Yes | Yes | Yes
[5 empty] | 368 | [16 empty] | Nala, 11kV line
254 |  | 91/8 | A+0 |  |  |  | 53.83 | 55260.462 | 141.614 | 770 | 385 | 195 | 191 | 386 | 192 | 194 | 386 | 74°57'5.538" | 22°7'42.083" | 495002.268 | 2447035.133 | VILLAGE :-SIRSI | Yes | Yes | Yes | Yes
[5 empty] | 402 | [16 empty] | Cart track, Nala, 11kV line
255 |  | 91/9 | A+1.5 |  |  |  | 55.33 | 55662.462 | 142.431 | 818 | 409 | 212 | 206 | 418 | 210 | 207 | 416 | 74°57'16.858" | 22°7'34.357" | 495326.481 | 2446797.457 | VILLAGE :-SIRSI | Yes | Yes | Yes | Yes
[5 empty] | 416 | [16 empty] | 11kV line, LT line, Metal road, Nala, Well
256 |  | 91/10 | A+3 |  |  |  | 56.83 | 56078.462 | 141.55 | 815 | 407.5 | 211 | 211 | 422 | 211 | 208 | 419 | 74°57'28.572" | 22°7'26.36" | 495661.984 | 2446551.503 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 399 | [16 empty] | Nala, LT line, Cart track
257 | AP 92 | AP92 | C2+0 | 27° 41' 30"LT |  | 4331 | 48.32 | 56477.462 | 142.17 | 807 | 403.5 | 189 | 191 | 379 | 192 | 195 | 386 | 74°57'39.806" | 22°7'18.691" | 495983.75 | 2446315.62 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 408 | [16 empty] | Canal, LT line, 11kV line
258 |  | 92/1 | A+3 |  |  |  | 56.83 | 56885.462 | 142.102 | 786 | 393 | 217 | 220 | 438 | 214 | 213 | 427 | 74°57'53.89" | 22°7'16.721" | 496387.212 | 2446254.94 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 378 | [16 empty] | 11kV line, Metal road, Drain, Nala
259 |  | 92/2 | A(-)3 |  |  |  | 50.83 | 57263.462 | 141.615 | 747 | 373.5 | 158 | 165 | 323 | 167 | 170 | 337 | 74°58'6.939" | 22°7'14.895" | 496761.008 | 2446198.721 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 369 | [16 empty] | 11kV line
260 |  | 92/3 | A+0 |  |  |  | 53.83 | 57632.462 | 142.664 | 779 | 389.5 | 205 | 184 | 388 | 200 | 190 | 389 | 74°58'19.676" | 22°7'13.112" | 497125.905 | 2446143.841 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 410 | [16 empty] | 11kV line, LT line, Pump house, Well, Cart track
261 |  | 92/4 | A+3 |  |  |  | 56.83 | 58042.462 | 144.621 | 826 | 413 | 227 | 205 | 432 | 222 | 206 | 428 | 74°58'33.829" | 22°7'11.131" | 497531.345 | 2446082.863 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 416 | [16 empty] | 11kV line, LT line
262 | AP 93 | AP93 | C2+0 | 22° 51' 17"RT |  | 1981 | 48.32 | 58458.462 | 148.606 | 808 | 404 | 213 | 201 | 413 | 212 | 200 | 412 | 74°58'48.18" | 22°7'9.122" | 497942.472 | 2446021.03 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 392 | [16 empty] | Cart track, Nala
263 |  | 93/1 | A+1.5 |  |  |  | 55.33 | 58850.462 | 146.122 | 773 | 386.5 | 192 | 216 | 409 | 194 | 210 | 404 | 74°58'59.859" | 22°7'2.48" | 498277.036 | 2445816.749 | VILLAGE :-DEVGARGH | Yes | Yes | Yes | Yes
[5 empty] | 381 | [16 empty] | Metal road, 11kV line, LT line, Well
264 |  | 93/2 | A+0 |  |  |  | 53.83 | 59231.462 | 142.281 | 761 | 380.5 | 166 | 198 | 363 | 172 | 196 | 368 | 74°59'11.21" | 22°6'56.023" | 498602.212 | 2445618.2 | VILLAGE :-GANGLI | Yes | Yes | Yes | Yes
[5 empty] | 380 | [16 empty] | Nala, 11kV line
265 |  | 93/3 | A+0 |  |  |  | 53.83 | 59611.462 | 140.724 | 777 | 388.5 | 183 | 205 | 388 | 185 | 204 | 389 | 74°59'22.531" | 22°6'49.583" | 498926.534 | 2445420.172 | VILLAGE :-GANGLI | Yes | Yes | Yes | Yes
[5 empty] | 397 | [16 empty] | Cart track, LT line
266 |  | 93/4 | A+0 |  |  |  | 53.83 | 60008.462 | 139.322 | 804 | 402 | 193 | 190 | 383 | 194 | 194 | 389 | 74°59'34.358" | 22°6'42.855" | 499265.366 | 2445213.285 | VILLAGE :-KAWDI | Yes | Yes | Yes | Yes
[5 empty] | 407 | [16 empty] | Cart track, LT line, Well
267 |  | 93/5 | A+3 |  |  |  | 56.83 | 60415.462 | 139.389 | 819.8 | 409.9 | 218 | 217 | 435 | 214 | 215 | 430 | 74°59'46.483" | 22°6'35.957" | 499612.732 | 2445001.187 | VILLAGE :-KAWDI | Yes | Yes | Yes | Yes
[5 empty] | 412.8 | [16 empty] | Concrete road
268 | AP 94 | AP94 | B2+0 | 13° 8' 54"LT |  |  | 48.32 | 0 | 140.018 | 834 | 417 | 196 | 190 | 386 | 199 | 196 | 395 | 74° 59'58.78" | 22° 6'28.961" | 499965.048 | 2444786.066 |  | Yes | Yes | Yes | Yes
[5 empty] | 421 | [16 empty] | Nala, Boring pump, Cart track
269 |  | 94/1 | A+4.5 |  |  |  | 58.33 | 421 | 140.304 | 845 | 422.5 | 232 | 231 | 463 | 227 | 227 | 454 | 75° 0'12.734" | 22° 6'24.67" | 500364.849 | 2444654.157 |  | Yes | NO | No | No
[5 empty] | 424 | [16 empty] | LT line, Boring pump, Cart track
270 |  | 94/2 | A+0 |  |  |  | 53.83 | 845 | 140.398 | 842 | 421 | 194 | 197 | 391 | 199 | 201 | 400 | 75° 0'26.788" | 22° 6'20.349" | 500767.499 | 2444521.308 |  | Yes | NO | No | No
[5 empty] | 418 | [16 empty] | Metal road, 11kV line, LT line, Cart track, Well
271 |  | 94/3 | A+3 |  |  |  | 56.83 | 1263 | 140.228 | 842 | 421 | 222 | 219 | 441 | 219 | 218 | 437 | 75° 0'40.642" | 22° 6'16.089" | 501164.452 | 2444390.339 |  | Yes | NO | No | No
[5 empty] | 424 | [16 empty] | Boring, Nala
272 |  | 94/4 | A+1.5 |  |  |  | 55.33 | 1687 | 140.167 | 833 | 416.5 | 206 | 210 | 416 | 208 | 209 | 417 | 75° 0'54.695" | 22° 6'11.767" | 501567.102 | 2444257.49 |  | Yes | NO | No | No
[5 empty] | 409 | [16 empty] | Metal road, 11kV line, Nala, Cart track
273 |  | 94/5 | A+0 |  |  |  | 53.83 | 2096 | 140.505 | 820 | 410 | 200 | 197 | 397 | 201 | 199 | 401 | 75° 1'8.251" | 22° 6'7.597" | 501955.507 | 2444129.341 |  | Yes | NO | No | No
[5 empty] | 411 | [16 empty] | Cart track
274 |  | 94/6 | A+1.5 |  |  |  | 55.33 | 2507 | 141.117 | 823 | 411.5 | 215 | 207 | 422 | 213 | 207 | 420 | 75° 1'21.872" | 22° 6'3.407" | 502345.812 | 2444000.566 |  | Yes | NO | No | No
[5 empty] | 412 | [16 empty] | Cart track
275 |  | 94/7 | A+0 |  |  |  | 53.83 | 2919 | 142.524 | 793 | 396.5 | 206 | 208 | 414 | 207 | 204 | 410 | 75° 1'35.527" | 22° 5'59.207" | 502737.067 | 2443871.477 |  | Yes | NO | No | No
[5 empty] | 381 | [16 empty] | Boring, Cart track
276 |  | 94/8 | A(-)3 |  |  |  | 50.83 | 3300 | 141.993 | 730 | 365 | 174 | 177 | 351 | 179 | 177 | 355 | 75° 1'48.154" | 22° 5'55.322" | 503098.882 | 2443752.101 |  | Yes | NO | No | No
[5 empty] | 349 | [16 empty] | Cart track
277 |  | 94/9 | A(-)3 |  |  |  | 50.83 | 3649 | 141.532 | 690 | 345 | 172 | 107 | 279 | 173 | 123 | 296 | 75° 1'59.72" | 22° 5'51.763" | 503430.309 | 2443642.751 |  | Yes | NO | No | No
[5 empty] | 341 | [16 empty] | Boring pump, 11kV line
278 | AP 95 | AP95 | D60+9 | 49° 32' 16"RT |  | 3990 | 57.32 | 3990 | 141.705 | 671 | 335.5 | 235 | -36 | 199 | 219 | 24 | 243 | 75° 2'11.018" | 22° 5'48.287" | 503754.044 | 2443535.939 |  | Yes | NO | No | No
[5 empty] | 330 | [16 empty] | 11kV line, Cart track
279 | AP 96 | AP96 | D60+55 | 0° 0' 00" |  | 330 | 108.32 | 4320 | 130.355 | 1155 | 577.5 | 369 | 419 | 788 | 309 | 420 | 730 | 75°2'14.97" | 22°5'39.257" | 503878.736 | 2443230.561 | RC=4.98 | Yes | NO | No | No
[5 empty] | 825 | [16 empty] | Narmada river
280 | AP 97 | AP97 | D60+55 | 0° 00' 00" |  | 825 | 96.32 | 5145 | 129.71 | 1125 | 562.5 | 419 | 430 | 849 | 420 | 332 | 752 | 75°2'26.24" | 22°5'13.508" | 504190.608 | 2442466.769 | RC=5.63 | Yes | NO | No | No
300
281 | AP 98 | AP98 | D60+9 | 9° 24' 22"LT |  | 300 | 57.32 | 5445 | 129.49 | 767 | 383.5 | -126 | 215 | 90 | -28 | 221 | 193 | 75° 2'30.201" | 22° 5'4.47" | 504304.08 | 2442188.87 | RC=5.85 | Yes | NO | No | No
[5 empty] | 470 | [16 empty] | LT line, 11kV line, Cart track, Bore
282 |  | 98/1 | A+7.5 |  |  |  | 55.33 | 5915 | 142.081 | 825 | 412.5 | 256 | 235 | 492 | 252 | 221 | 473 | 75° 2'38.691" | 22° 4'51.62" | 504550.62 | 2441788.722 |  | Yes | NO | No | No
[5 empty] | 355 | [16 empty] | LT line
283 |  | 98/2 | A(-)3 |  |  |  | 50.83 | 6270 | 141.202 | 707 | 353.5 | 120 | 168 | 288 | 135 | 170 | 305 | 75° 2'45.15" | 22° 4'41.843" | 504736.836 | 2441486.483 |  | Yes | NO | No | No
[5 empty] | 352 | [16 empty] | Cart track, Nala
284 | AP 99 | 99/0 | C1+0 | 19° 4' 17"LT |  | 1177 | 48.32 | 6622 | 139.84 | 761 | 380.5 | 184 | 190 | 374 | 182 | 194 | 376 | 75° 2'51.733" | 22° 4'31.877" | 504921.41 | 2441186.91 |  | Yes | Yes | Yes | Yes
[5 empty] | 409 | [16 empty] | 11kV line, Nala, Metal road, Cart track
285 |  | 99/1 | A+3 |  |  |  | 56.83 | 7031 | 140.232 | 829 | 414.5 | 220 | 207 | 426 | 217 | 208 | 424 | 75° 3'2.776" | 22° 4'23.449" | 505237.955 | 2440927.911 | VILLAGE :-BADHDA | Yes | Yes | Yes | Yes
[5 empty] | 420 | [16 empty] | Nala, Cart track
286 |  | 99/2 | A+3 |  |  |  | 56.83 | 7451 | 141.152 | 843 | 421.5 | 214 | 205 | 419 | 214 | 207 | 421 | 75° 3'14.116" | 22° 4'14.796" | 505563.013 | 2440661.946 | VILLAGE :-BADHDA | Yes | Yes | Yes | Yes
[5 empty] | 423 | [16 empty] | LT lines, 11kV lines, Cart track, Pond, 1No of LT line to be diverted
287 |  | 99/3 | A+3 |  |  |  | 56.83 | 7874 | 142.839 | 823 | 411.5 | 219 | 215 | 434 | 218 | 212 | 430 | 75° 3'25.536" | 22° 4'6.08" | 505890.392 | 2440394.082 | VILLAGE :-BADHDA | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | Nala, Cart track
288 |  | 99/4 | A+0 |  |  |  | 53.83 | 8274 | 142.543 | 772 | 386 | 186 | 155 | 341 | 190 | 163 | 352 | 75° 3'36.335" | 22° 3'57.837" | 506199.972 | 2440140.782 | VILLAGE :-BADHDA | Yes | Yes | Yes | Yes
[5 empty] | 372 | [16 empty] | Cart track, nala, Samadhi, LT line,Well
289 |  | 99/5 | A+6 |  |  |  | 59.83 | 8646 | 143.154 | 846 | 423 | 218 | 225 | 443 | 211 | 228 | 439 | 75° 3'46.377" | 22° 3'50.172" | 506487.88 | 2439905.213 | VILLAGE :-BADHDA | Yes | Yes | Yes | Yes
[5 empty] | 474 | [16 empty] | Well, Cart track, LT line, 11kV line, Pump house
290 | AP 100 | 100/0 | C1+9 | 18° 4' 51"RT |  | 2498 | 57.32 | 9120 | 143.659 | 698 | 349 | 251 | 108 | 358 | 248 | 110 | 358 | 75° 3'59.168" | 22° 3'40.408" | 506854.6 | 2439605.16 | VILLAGE :-ANJAD | Yes | Yes | Yes | Yes
[5 empty] | 224 | [16 empty] | 132KV DCSS BARWANI-NIMRANI TL, Metal road, 11kV line, LT line
291 | AP 101 | 101/0 | D60+9 | 45° 0' 59"LT |  | 224 | 57.32 | 9344 | 144.09 | 633 | 316.5 | 116 | 244 | 360 | 114 | 234 | 348 | 75° 4'3.378" | 22° 3'34.273" | 506975.33 | 2439416.59 | VILLAGE :-ANJAD | Yes | Yes | Yes | Yes
[5 empty] | 409 | [16 empty] | Nala
292 |  | 101/1 | A+0 |  |  |  | 53.83 | 9753 | 144.295 | 783 | 391.5 | 166 | 184 | 350 | 177 | 185 | 361 | 75° 4'17.317" | 22° 3'31.421" | 507374.858 | 2439329.079 | VILLAGE :-ANJAD | Yes | Yes | Yes | Yes
[5 empty] | 374 | [16 empty] | LT line, Cart track
293 | AP 102 | 102/0 | C1+0 | 17° 50' 46"LT |  | 783 | 48.32 | 10127 | 145.099 | 787 | 393.5 | 191 | 167 | 358 | 190 | 177 | 367 | 75° 4'30.06" | 22° 3'28.813" | 507740.14 | 2439249.07 | VILLAGE :-CHAKAIRI | Yes | Yes | Yes | Yes
[5 empty] | 413 | [16 empty] | Metal road, 33kV line, Cart track
294 |  | 102/1 | A+9 |  |  |  | 62.83 | 10540 | 145.168 | 848 | 424 | 246 | 254 | 500 | 237 | 245 | 482 | 75° 4'44.405" | 22° 3'30.092" | 508151.245 | 2439288.592 | VILLAGE :-CHAKAIRI | Yes | Yes | Yes | Yes
[5 empty] | 435 | [16 empty] | Bore, LT line, Cart track
295 |  | 102/2 | A+0 |  |  |  | 53.83 | 10975 | 145.555 | 825 | 412.5 | 183 | 195 | 378 | 192 | 196 | 387 | 75° 4'59.513" | 22° 3'31.438" | 508584.248 | 2439330.22 | VILLAGE :-CHAKAIRI | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | Nala
296 |  | 102/3 | A+0 |  |  |  | 53.83 | 11365 | 145.587 | 806 | 403 | 196 | 194 | 389 | 196 | 198 | 393 | 75° 5'13.059" | 22° 3'32.645" | 508972.458 | 2439367.541 | VILLAGE :-CHAKAIRI | Yes | Yes | Yes | Yes
[5 empty] | 416 | [16 empty] | LT lines, Cart track, Canal
297 |  | 102/4 | A+3 |  |  |  | 56.83 | 11781 | 146.051 | 819 | 409.5 | 223 | 213 | 437 | 220 | 211 | 431 | 75° 5'27.508" | 22° 3'33.932" | 509386.549 | 2439407.35 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 403 | [16 empty] | LT line, Bore
298 |  | 102/5 | A+0 |  |  |  | 53.83 | 12184 | 146.497 | 787 | 393.5 | 191 | 189 | 379 | 194 | 190 | 383 | 75° 5'41.506" | 22° 3'35.178" | 509787.7 | 2439445.916 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | LT line, Nala
299 |  | 102/6 | A+0 |  |  |  | 53.83 | 12568 | 147.315 | 766 | 383 | 196 | 192 | 389 | 196 | 192 | 388 | 75° 5'54.843" | 22° 3'36.365" | 510169.937 | 2439482.663 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 382 | [16 empty] | 11kV line, Cart track, Canal
300 |  | 102/7 | A+0 |  |  |  | 53.83 | 12950 | 147.084 | 775 | 387.5 | 190 | 197 | 387 | 191 | 197 | 388 | 75° 6'8.111" | 22° 3'37.546" | 510550.184 | 2439519.219 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 393 | [16 empty] | Metal road, 33kV line, 11kV line
301 |  | 102/8 | A+0 |  |  |  | 53.83 | 13343 | 147.035 | 800 | 400 | 197 | 189 | 386 | 197 | 193 | 390 | 75° 6'21.762" | 22° 3'38.761" | 510941.381 | 2439556.827 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 407 | [16 empty] | Cart track, 11kV line, Canal, LT lines, Bore
302 |  | 102/9 | A+3 |  |  |  | 56.83 | 13750 | 147.325 | 805 | 402.5 | 218 | 222 | 441 | 215 | 217 | 432 | 75° 6'35.898" | 22° 3'40.018" | 511346.513 | 2439595.775 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 398 | [16 empty] | Cart track, LT line, Bore, Banana garden, LT line to be diverted
303 |  | 102/10 | A+0 |  |  |  | 53.83 | 14148 | 145.218 | 793 | 396.5 | 176 | 156 | 332 | 182 | 166 | 349 | 75° 6'49.722" | 22° 3'41.247" | 511742.686 | 2439633.862 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 395 | [16 empty] | Banana garden, LT line, Nala
304 |  | 102/11 | A+9 |  |  |  | 62.83 | 14543 | 145.566 | 845 | 422.5 | 240 | 245 | 485 | 230 | 241 | 471 | 75° 7'3.442" | 22° 3'42.467" | 512135.873 | 2439671.662 | VILLAGE :-MOHIPURA | Yes | Yes | Yes | Yes
[5 empty] | 450 | [16 empty] | Cart track, LT line, Well, Nala, 11kV line, Bore
305 | AP 103 | 103/0 | C1+3 | 13° 57' 15"RT |  | 4866 | 51.32 | 14993 | 146.771 | 914 | 457 | 206 | 222 | 428 | 212 | 225 | 437 | 75° 7'19.071" | 22° 3'43.856" | 512583.76 | 2439714.72 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 464 | [16 empty] | 11kV lines, Nala, cart track
306 |  | 103/1 | A+6 |  |  |  | 59.83 | 15457 | 146.547 | 849 | 424.5 | 244 | 225 | 469 | 242 | 218 | 459 | 75° 7'35.083" | 22° 3'41.623" | 513042.708 | 2439646.433 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 385 | [16 empty] | Nala
307 |  | 103/2 | A+0 |  |  |  | 53.83 | 15842 | 145.58 | 719 | 359.5 | 161 | 144 | 304 | 169 | 150 | 318 | 75° 7'48.368" | 22° 3'39.77" | 513423.515 | 2439589.773 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 334 | [16 empty] | Canal
308 |  | 103/3 | A+3 |  |  |  | 56.83 | 16176 | 147.002 | 760 | 380 | 191 | 211 | 402 | 185 | 212 | 398 | 75° 7'59.893" | 22° 3'38.162" | 513753.879 | 2439540.619 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 426 | [16 empty] | 11kV lines, LT line, Metal road
309 | AP 104 | 104/0 | B2+3 | 11° 17' 16"RT |  | 1609 | 51.32 | 16602 | 147.554 | 837 | 418.5 | 216 | 213 | 429 | 215 | 212 | 427 | 75°8'14.587" | 22°3'36.111" | 514175.07 | 2439477.95 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 411 | [16 empty] | LT line, Cart track
310 |  | 104/1 | A+9 |  |  |  | 62.83 | 17013 | 139.808 | 736 | 368 | 199 | 142 | 341 | 201 | 147 | 348 | 75°8'28.08" | 22°3'31.583" | 514561.892 | 2439339.061 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 325 | [16 empty] | LT line, Nahali river, LT line to be diverted
311 |  | 104/2 | A+7.5 |  |  |  | 61.33 | 17338 | 145.03 | 777 | 388.5 | 183 | 220 | 403 | 178 | 222 | 400 | 75°8'38.748" | 22°3'28.001" | 514867.773 | 2439229.235 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 452 | [16 empty] | Cart track, Nala, LT lines
312 | AP 105 | 105/0 | C2+6 | 28° 16' 27"RT |  | 1188 | 54.32 | 17790 | 148.37 | 697 | 348.5 | 234 | 159 | 393 | 233 | 142 | 375 | 75°8'53.584" | 22°3'23.021" | 515293.13 | 2439076.51 | VILLAGE :-TAKYAPUR | Yes | Yes | Yes | Yes
[5 empty] | 245 | [16 empty] | NH- 347B, 11kV lines
313 | AP 106 | 106/0 | B2+0 | 10° 36' 47"LT |  | 245 | 48.32 | 18035 | 150.197 | 669 | 334.5 | 86 | 171 | 257 | 104 | 181 | 284 | 75°8'59.293" | 22°3'17.094" | 515456.915 | 2438894.45 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 424 | [16 empty] | 11KV LINE, 33KV LINE, PUMP HOUSE, NALA, LT LINE, WELL
314 |  | 106/1 | A+6 |  |  |  | 59.83 | 18459 | 154.145 | 848.702 | 424.351 | 254 | 212 | 466 | 245 | 213 | 458 | 75°9'11.034" | 22°3'8.705" | 515793.694 | 2438636.853 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 424.702 | [16 empty] | 11KV LINE, LT LINE, CART TRACK, BORE
315 | AP 107 | 107/0 | C2+3 | 28° 18' 53"LT |  | 848.702 | 51.32 | 18883.702 | 157.395 | 814.702 | 407.351 | 214 | 198 | 412 | 214 | 198 | 412 | 75°9'22.794" | 22°3'0.302" | 516131.03 | 2438378.83 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | NALA
316 |  | 107/1 | A+0 |  |  |  | 53.83 | 19273.702 | 159.736 | 740 | 370 | 193 | 171 | 364 | 194 | 172 | 366 | 75°9'36.227" | 22°2'58.284" | 516516.125 | 2438317.168 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 350 | [16 empty] | PUMP HOUSE, CART TRACK, NALA
317 |  | 107/2 | A(-)3 |  |  |  | 50.83 | 19623.702 | 163.598 | 728 | 364 | 180 | 140 | 320 | 179 | 153 | 332 | 75°9'48.283" | 22°2'56.472" | 516861.722 | 2438261.831 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 378 | [16 empty] | LT LINE, PUMP HOUSE, 11KV LINE
318 |  | 107/3 | A+3 |  |  |  | 56.83 | 20001.702 | 168.121 | 812 | 406 | 238 | 186 | 424 | 226 | 194 | 421 | 75°10'1.302" | 22°2'54.515" | 517234.968 | 2438202.066 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 434 | [16 empty] | CANAL, NALA, CART TRACK,
319 |  | 107/4 | A+3 |  |  |  | 56.83 | 20435.702 | 175.922 | 849 | 424.5 | 249 | 131 | 380 | 242 | 151 | 392 | 75°10'16.251" | 22°2'52.268" | 517663.509 | 2438133.448 | VILLAGE :-MANDWADA | Yes | Yes | Yes | Yes
[5 empty] | 415 | [16 empty] | WELL, NALA, CART TRACK
320 |  | 107/5 | A+3 |  |  |  | 56.83 | 20850.702 | 194.16 | 742.835 | 371.4175 | 286 | 207 | 493 | 266 | 196 | 463 | 75°10'30.545" | 22°2'50.119" | 518073.289 | 2438067.833 | VILLAGE :-MANDWADA RC EXPECTED | Yes | Yes | Yes | Yes
327.835
321 | AP 108 | 108/0 | C1+9 | 16° 1' 18"LT |  | 2294.835 | 57.32 | 21178.537 | 180.186 | 697.835 | 348.9175 | 121 | 199 | 320 | 132 | 195 | 327 | 75°10'41.836" | 22°2'48.421" | 518397 | 2438016 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 370 | [16 empty] | WELL
322 |  | 108/1 | A+9 |  |  |  | 62.83 | 21548.537 | 177.327 | 833 | 416.5 | 171 | 254 | 426 | 176 | 249 | 424 | 75°10'54.652" | 22°2'49.858" | 518764.301 | 2438060.609 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 463 | [16 empty] | NALA, LT LINE, CART TRACK
323 |  | 108/2 | A+0 |  |  |  | 53.83 | 22011.537 | 180.747 | 752 | 376 | 210 | 174 | 384 | 217 | 166 | 383 | 75°11'10.69" | 22°2'51.655" | 519223.924 | 2438116.429 | RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 289 | [16 empty] | CART TRACK, NALA 11KV LINE, 11KV LINE TO BE DIVERTED
324 |  | 108/3 | A+9 |  |  |  | 62.83 | 22300.537 | 167.137 | 673 | 336.5 | 115 | 257 | 372 | 124 | 239 | 363 | 75°11'20.701" | 22°2'52.777" | 519510.816 | 2438151.272 | RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | NALA, CART TRACK, CANAL, LT LINE,
325 |  | 108/4 | A+3 |  |  |  | 56.83 | 22684.537 | 159.651 | 765 | 382.5 | 128 | 232 | 360 | 146 | 221 | 367 | 75°11'34.002" | 22°2'54.267" | 519892.015 | 2438197.569 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 381 | [16 empty] | NALA, LT LINE, WELL, CART TRACK
326 |  | 108/5 | A(-)3 |  |  |  | 50.83 | 23065.537 | 157.102 | 681 | 340.5 | 150 | 152 | 301 | 162 | 151 | 313 | 75°11'47.2" | 22°2'55.745" | 520270.235 | 2438243.503 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 300 | [16 empty] | 11KV LINE, BANANA GARDEN
327 |  | 108/6 | A(-)3 |  |  |  | 50.83 | 23365.537 | 156.838 | 637 | 318.5 | 149 | 164 | 313 | 149 | 166 | 315 | 75°11'57.592" | 22°2'56.909" | 520568.047 | 2438279.672 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 337 | [16 empty] | NALA, 11KV LINE, CART TRACK
328 |  | 108/7 | A(-)3 |  |  |  | 50.83 | 23702.537 | 157.67 | 688.969 | 344.4845 | 173 | 162 | 335 | 172 | 166 | 338 | 75°12'9.265" | 22°2'58.216" | 520902.589 | 2438320.302 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 351.969 | [16 empty] | CART TRACK
329 | AP 109 | 109/0 | B2+0 | 10° 4' 8"RT |  | 2875.969 | 48.32 | 24054.506 | 157.529 | 728.969 | 364.4845 | 191 | 205 | 396 | 187 | 201 | 388 | 75°12'21.457" | 22°2'59.581" | 521251.991 | 2438362.737 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 377 | [16 empty] | METAL ROAD, NALA, 11KV LINE, POND
330 |  | 109/1 | A+3 |  |  |  | 56.83 | 24431.506 | 151.089 | 667 | 333.5 | 173 | 161 | 334 | 177 | 157 | 334 | 75°12'34.589" | 22°2'58.892" | 521628.423 | 2438342.058 | VILLAGE :-UCHAWAD | Yes | Yes | Yes | Yes
[5 empty] | 290 | [16 empty] | DEV RIVER
331 |  | 109/2 | A+0 |  |  |  | 53.83 | 24721.506 | 151.502 | 716 | 358 | 129 | 172 | 301 | 133 | 183 | 316 | 75°12'44.691" | 22°2'58.362" | 521917.987 | 2438326.151 | VILLAGE :-SEMALDA DEB | Yes | Yes | Yes | Yes
[5 empty] | 426 | [16 empty] | NALA, POND, LT LINE, 11KV LINE
332 |  | 109/3 | A+9 |  |  |  | 62.83 | 25147.506 | 152.275 | 834 | 417 | 255 | 230 | 484 | 245 | 224 | 469 | 75°12'59.53" | 22°2'57.582" | 522343.346 | 2438302.785 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 408 | [16 empty] | CART TRACK, CANAL, NALA
333 |  | 109/4 | A(-)3 |  |  |  | 50.83 | 25555.506 | 158.592 | 821 | 410.5 | 179 | 131 | 310 | 186 | 150 | 336 | 75°13'13.742" | 22°2'56.835" | 522750.731 | 2438280.406 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 413 | [16 empty] | CART TRACK, NALA, POND
334 |  | 109/5 | A+3 |  |  |  | 56.83 | 25968.506 | 170.061 | 799 | 399.5 | 283 | 196 | 480 | 265 | 196 | 460 | 75°13'28.128" | 22°2'56.079" | 523163.11 | 2438257.752 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
386
335 |  | 109/6 | A+3 |  |  |  | 56.83 | 26354.506 | 169.423 | 746 | 373 | 190 | 171 | 361 | 191 | 173 | 365 | 75°13'41.574" | 22°2'55.372" | 523548.528 | 2438236.58 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 360 | [16 empty] | CART TRACK, NALA, 11KV LINE, BORE
336 |  | 109/7 | A+3 |  |  |  | 56.83 | 26714.506 | 171.317 | 795 | 397.5 | 190 | 244 | 434 | 188 | 238 | 426 | 75°13'54.114" | 22°2'54.712" | 523907.986 | 2438216.833 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 435 | [16 empty] | BANANA GARDEN, LT LINE, BORE, NALA, LT LINE TO BE DIVERTED
337 |  | 109/8 | A+3 |  |  |  | 56.83 | 27149.506 | 165.057 | 849 | 424.5 | 192 | 225 | 417 | 199 | 221 | 420 | 75°14'9.266" | 22°2'53.914" | 524342.332 | 2438192.973 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 414 | [16 empty] | NALA, LT LINE, METAL ROAD, 11KV LINE, WELL, BORE
338 |  | 109/9 | A+3 |  |  |  | 56.83 | 27563.506 | 160.957 | 827 | 413.5 | 190 | 227 | 416 | 194 | 222 | 416 | 75°14'23.687" | 22°2'53.155" | 524755.708 | 2438170.265 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 413 | [16 empty] | NALA, LT LINE
339 |  | 109/10 | A(-)3 |  |  |  | 50.83 | 27976.506 | 162.463 | 818 | 409 | 187 | 175 | 362 | 193 | 182 | 375 | 75°14'38.072" | 22°2'52.397" | 525168.087 | 2438147.611 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 405 | [16 empty] | NALA, LT LINE, WELL, PUMP HOUSE |  |  |  |  | Hold Due to pendencies A+(9 to A+7.5
340 |  | 109/11 | A+3 |  |  |  | 56.83 | 28381.506 | 162.814 | 828.811 | 414.4055 | 231 | 206 | 437 | 224 | 208 | 433 | 75°14'52.18" | 22°2'51.653" | 525572.477 | 2438125.396 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 423.811 | [16 empty] | NALA, LT LINE, 11KV LINE, BORE |  |  |  |  | Hold Due to LT Line Diversion
341 | AP 110 | 110/0 | D45+3 | 36° 39' 1"RT |  | 4750.811 | 51.32 | 28805.317 | 164.366 | 872.811 | 436.4055 | 203 | 194 | 397 | 198 | 202 | 400 | 75°15'6.942" | 22°2'50.874" | 525995.65 | 2438102.15 | VILLAGE :-HATAULA | Yes | Yes | Yes | Yes
[5 empty] | 449 | [16 empty] | 11kV lines, Cart track, Nala, Well
342 |  | 110/1 | A+7.5 |  |  |  | 62.83 | 29254.317 | 166.019 | 844 | 422 | 256 | 214 | 471 | 249 | 211 | 459 | 75°15'18.961" | 22°2'41.509" | 526340.639 | 2437814.776 | VILLAGE :-BHAT GAWLA | Yes | Yes | Yes | Yes
[5 empty] | 395 | [16 empty] | 11kV lines, Bore, Cart track |  |  |  |  | Hold Due to LT Line Diversion
343 |  | 110/2 | A+0 |  |  |  | 53.83 | 29649.317 | 171.403 | 752 | 376 | 181 | 160 | 342 | 186 | 165 | 351 | 75°15'29.534" | 22°2'33.27" | 526644.136 | 2437561.964 | VILLAGE :-BHAT GAWLA | Yes | Yes | Yes | Yes
[5 empty] | 357 | [16 empty] | 11kV line, LT line, Nala, Well, 11kV line to be diverted
344 |  | 110/3 | A+0 |  |  |  | 53.83 | 30006.317 | 175.07 | 780 | 390 | 197 | 166 | 364 | 193 | 178 | 371 | 75°15'39.09" | 22°2'25.824" | 526918.437 | 2437333.472 | VILLAGE :-BHAT GAWLA | Yes | Yes | Yes | Yes
[5 empty] | 423 | [16 empty] | 11kV line, Nala, Cart track
345 |  | 110/4 | A+0 |  |  |  | 53.83 | 30429.317 | 185.789 | 752 | 376 | 258 | 158 | 416 | 247 | 160 | 407 | 75°15'50.412" | 22°2'17" | 527243.449 | 2437062.739 | VILLAGE :-BHAT GAWLA | Yes | Yes | Yes | Yes
[5 empty] | 329 | [16 empty] | 11kV lines, Nala, 11kV line to be diverted
346 | AP 111 | 111/0 | D45+6 | 34° 20' 35"LT |  | 1953 | 54.32 | 30758.317 | 181 | 702 | 351 | 171 | 190 | 361 | 170 | 189 | 359 | 75°15'59.217" | 22°2'10.138" | 527496.21 | 2436852.19 | VILLAGE :-BHAT GAWLA | Yes | Yes | Yes | Yes
[5 empty] | 373 | [16 empty] | Nala
347 |  | 111/1 | A+0 |  |  |  | 53.83 | 31131.317 | 186.378 | 792 | 396 | 184 | 216 | 400 | 185 | 215 | 400 | 75° 16'12.168" | 22° 2'8.964" | 527867.523 | 2436816.757 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 419 | [16 empty] | Nala, LT line, Well
348 |  | 111/2 | A+3 |  |  |  | 56.83 | 31550.317 | 181.96 | 816 | 408 | 204 | 218 | 422 | 206 | 213 | 419 | 75° 16'26.717" | 22° 2'7.646" | 528284.629 | 2436776.954 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 397 | [16 empty] | LT line, Nala
349 |  | 111/3 | A+0 |  |  |  | 53.83 | 31947.317 | 180.761 | 771 | 385.5 | 180 | 175 | 355 | 185 | 179 | 364 | 75° 16'40.501" | 22° 2'6.396" | 528679.833 | 2436739.241 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 374 | [16 empty] | 11kV lines, LT line, Nala, Banana garden, Metal road, Cart track
350 |  | 111/4 | A+0 |  |  |  | 53.83 | 32321.317 | 183.293 | 764 | 382 | 200 | 193 | 393 | 197 | 194 | 391 | 75° 16'53.487" | 22° 2'5.218" | 529052.142 | 2436703.713 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | Nala, Cart track |  |  |  |  | RLY MMR-INDB
351 |  | 111/5 | A+6 |  |  |  | 59.83 | 32711.317 | 177.708 | 775 | 387.5 | 197 | 187 | 384 | 197 | 189 | 386 | 75° 17'7.028" | 22° 2'3.99" | 529440.378 | 2436666.665 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 385 | [16 empty] | Nala, Cart track, Drain |  |  |  |  | RLY MMR-INDB
352 |  | 111/6 | A+0 |  |  |  | 53.83 | 33096.317 | 184.978 | 817 | 408.5 | 199 | 163 | 362 | 198 | 177 | 375 | 75° 17'20.395" | 22° 2'2.777" | 529823.637 | 2436630.091 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 432 | [16 empty] | Cart track, LT line, Well |  |  |  |  | RLY MMR-INDB
353 |  | 111/7 | A+0 |  |  |  | 56.83 | 33528.317 | 194.779 | 823 | 411.5 | 270 | 258 | 528 | 257 | 242 | 499 | 75° 17'35.394" | 22° 2'1.415" | 530253.684 | 2436589.054 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 391 | [21 empty] | RLY MMR-INDB
354 | AP 111A | 111A/0 | D60+9 | 48° 44' 47"RT |  | 3161 | 57.32 | 33919.317 | 175.52 | 621 | 310.5 | 134 | 91 | 226 | 150 | 103 | 254 | 75° 17'48.97" | 22° 2'0.183" | 530642.92 | 2436551.91 | VILLAGE :-GHATI | Yes | Yes | Yes | Yes
[5 empty] | 230 | [16 empty] | Nala, Cart track, LT line, Well PROPOSED RAILWAY MMR-INDB NEW BG LINE |  |  |  |  | Julwania -Ajandi(MPPTCL 11 KV
355 | AP 111B | 111B/0 | D60+6 | 56° 49' 39"LT |  | 230 | 54.32 | 34149.317 | 180.988 | 516 | 258 | 139 | 168 | 307 | 127 | 162 | 289 | 75° 17'53.651" | 22° 1'54.107" | 530777.47 | 2436365.37 | VILLAGE :-ANJADI | Yes | Yes | Yes | Yes
[5 empty] | 286 | [21 empty] | RC Excepted & 11 KV Line
356 |  | 111B/1 | A+0 |  |  |  | 53.83 | 34435.317 | 182.847 | 761 | 380.5 | 118 | 197 | 315 | 124 | 207 | 331 | 75° 18'3.618" | 22° 1'54.516" | 531063.169 | 2436378.494 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 475 | [16 empty] | Nala, cart track, LT line, 33kV line |  |  |  |  | Julwania -Ajandi(MPPTCL 11 KV
357 | AP 112 | 112/0 | D45+18 | 32° 9' 36"RT |  | 761 | 66.32 | 34910.317 | 176.118 | 704 | 352 | 280 | 151 | 431 | 271 | 133 | 404 | 75°18'20.171" | 22°1'55.194" | 531537.63 | 2436400.29 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 229 | [16 empty] | 132KV S/C Julwaniya- Ajandi Pump House TL, LT line, 11kV line, Well 11KV line to be shifted |  |  |  |  | RC Excepted
358 | AP 113 | 113/0 | B1+9 (RC = 3M) | 6° 6' 55"LT |  | 229 | 57.32 | 35139.317 | 178.33 | 447 | 223.5 | 78 | 28 | 106 | 97 | 71 | 168 | 75°18'27.116" | 22°1'51.509" | 531736.939 | 2436287.389 | EQUAL RC= 3 Mtr. | Yes | Yes | Yes | Yes
[5 empty] | 218 | [16 empty] | LT lines, 11kV line |  |  |  |  | RC Excepted
359 | AP 114 | 114/0 | B1+18 | 3° 5' 16"LT |  | 218 | 66.32 | 35357.317 | 180.066 | 405 | 202.5 | 190 | -10 | 180 | 147 | 52 | 199 | 75°18'34.082" | 22°1'48.681" | 531936.821 | 2436200.831 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 187 | [16 empty] | 132 KV DC NIMRANI-JULWANIYA TL , 11kV line |  |  |  |  | RC Excepted
360 | AP 115 | 115/0 | D45+18 | 20° 36' 31"RT |  | 187 | 66.32 | 35544.317 | 187.97 | 782 | 391 | 197 | 275 | 472 | 136 | 279 | 414 | 75°18'40.195" | 22°1'46.557" | 532112.18 | 2436135.87 | RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 595 | [16 empty] | Metal road, Canal, cart track, Nala, Well, 66kV line
361 |  | 115/1 | B1+3 |  |  |  | 51.32 | 36139.317 | 211.874 | 905 | 452.5 | 323 | 88 | 411 | 321 | 111 | 432 | 75° 18'55.846" | 22° 1'33.847" | 532561.67 | 2435746.019 | RC EXPECTED | Yes | Yes | Yes | Yes
310
362 |  | 115/2 | A+0 |  |  |  | 53.83 | 36449.317 | 225.66 | 635 | 317.5 | 223 | 103 | 326 | 199 | 124 | 323 | 75° 19'4.001" | 22° 1'27.225" | 532795.858 | 2435542.904 | RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 325 | [16 empty] | Cart track
363 | AP 116 | 116/0 | C1+3 | 18° 47' 34"LT |  | 1230 | 51.32 | 36774.317 | 232.777 | 735 | 367.5 | 222 | 213 | 435 | 202 | 211 | 413 | 75° 19'12.545" | 22° 1'20.287" | 533041.24 | 2435330.08 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 410 | [16 empty] | 11kV lines
364 |  | 116/1 | A+3 |  |  |  | 56.83 | 37184.317 | 230.99 | 834 | 417 | 198 | 211 | 409 | 200 | 212 | 412 | 75° 19'25.78" | 22° 1'15.235" | 533421.001 | 2435175.543 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 424 | [16 empty] | Metal road |  |  |  |  | RC Excepted
365 |  | 116/2 | A+3 |  |  |  | 56.83 | 37608.317 | 231.33 | 788 | 394 | 214 | 232 | 446 | 214 | 222 | 436 | 75° 19'39.467" | 22° 1'10.01" | 533813.729 | 2435015.729 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 364 | [16 empty] | Well Nala |  |  |  |  | RC Excepted
366 |  | 116/3 | A+9 |  |  |  | 62.83 | 37972.317 | 216.405 | 739 | 369.5 | 147 | 258 | 405 | 158 | 241 | 399 | 75°19'51.19" | 22° 1'5.51" | 534150.882 | 2434878.5305 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 375 | [16 empty] | Nala |  |  |  |  | RC Excepted/ RC
367 | AP 117 | 117/0 | B2+3 | 13° 34' 06"RT |  | 1573 | 51.32 | 38347.317 | 208.204 | 774 | 387 | 122 | 170 | 292 | 139 | 178 | 317 | 75°20'3.31" | 22° 1'0.90" | 534498.1776 | 2434737.2046 | VILLAGE :-KALAPANI | Yes | Yes | Yes | Yes
[5 empty] | 399 | [16 empty] | 11kV lines, Bore, cart track, LT line, 11kV line |  |  |  |  | NH 52 /2 Mtr RC
368 |  | 117/1 | A(-)3 |  |  |  | 53.83 | 38746.317 | 215.684 | 656 | 328 | 215 | 226 | 441 | 208 | 194 | 402 | 75°20'14.56" | 22° 0'53.29" | 534821.8043 | 2434504.5585 | VILLAGE :-KURAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 257 | [16 empty] | MUMBAI-MANMAD BIJWASAN PIPELINE, Pond |  |  |  |  | NH 52 Adj Tower
369 | AP 118 | 118/0 | B1+0 | 1° 38' 14"LT |  | 656 | 48.32 | 39003.317 | 202.5 | 501 | 250.5 | 28 | 50 | 78 | 60 | 85 | 144 | 75° 20'21.87" | 22° 0'48.40" | 535030.56 | 2434354.49 | VILLAGE :-KURAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 244 | [16 empty] | 33kV line, 11kV line (2Nos), NH-52, Nala, 1Nos of 11kV line to be shifted. |  |  |  |  | 220 KV crossing Adj / 2 Leg RC /ULE
370 | AP 119 | 119/0 | C1+18(RC2M) | 16° 54' 12"RT |  | 244 | 66.32 | 39247.317 | 190.788 | 490 | 245 | 236 | 135 | 371 | 182 | 129 | 312 | 75° 20' 28.9" | 22° 0' 43.96" | 535232.593 | 2434217.785 | RC = 2Mtr (4 leg ) To Maintain Power line clearence. | Yes | Yes | Yes | Yes
[5 empty] | 246 | [16 empty] | 220KV D/C Julwaniya-Omkareshwar TL , Nala, LT lines
371 | AP 120 | 120/0 | D45+18 | 35° 12' 20"LT |  | 246 | 66.32 | 39493.317 | 191.436 | 764 | 382 | 111 | 210 | 321 | 117 | 218 | 335 | 75° 20' 35.08" | 22° 0' 38.43" | 535410.318 | 2434048.343 | VILLAGE :-KURAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 518 | [16 empty] | 11kV line, Nala, Metal road, Canal
372 | AP 121 | 121/0 | B2+0 | 9° 20' 1"RT |  |  | 48.32 | 0 | 225.437 | 831 | 415.5 | 308 | 249 | 557 | 301 | 241 | 542 | 75°20'52.962" | 22°0'35.924" | 535923.157 | 2433972.361 |  | Yes | Yes | Yes | Yes
[5 empty] | 429.996 | [16 empty] | 11kV line |  |  |  |  | 2 Leg RC / ULE / LT Line Shifted
373 |  | 121/1 | A+0 |  |  |  | 53.83 | 429.996 | 217.52 | 844.996 | 422.498 | 183 | 188 | 371 | 191 | 193 | 385 | 75°21'7.235" | 22°0'31.627" | 536332.658 | 2433841.19 |  | Yes | Yes | Yes | Yes
[5 empty] | 415 | [16 empty] | Piple tree
374 |  | 121/2 | A+6 |  |  |  | 59.83 | 844.996 | 216.139 | 830 | 415 | 228 | 224 | 452 | 223 | 221 | 444 | 75°21'21.009" | 22°0'27.48" | 536727.877 | 2433714.594 |  | Yes | Yes | Yes | Yes
[5 empty] | 415 | [16 empty] | 11kV lines, Cart track
375 |  | 121/3 | A+3 |  |  |  | 56.83 | 1259.996 | 215.361 | 840 | 420 | 192 | 205 | 397 | 196 | 207 | 404 | 75°21'34.783" | 22°0'23.332" | 537123.097 | 2433587.998 | LT line to shifted | Yes | Yes | Yes | Yes
[5 empty] | 425 | [16 empty] | 11kV lines, LT line, Cart track, Nala
376 |  | 121/4 | A+0 |  |  |  | 53.83 | 1684.996 | 220.222 | 840 | 420 | 221 | 130 | 351 | 219 | 150 | 369 | 75°21'48.889" | 22°0'19.085" | 537527.839 | 2433458.352 |  | Yes | Yes | Yes | Yes
[5 empty] | 415 | [16 empty] | Well
377 |  | 121/5 | A+0 |  |  |  | 53.83 | 2099.996 | 238.281 | 815 | 407.5 | 287 | 200 | 487 | 267 | 201 | 468 | 75°22'2.662" | 22°0'14.937" | 537923.059 | 2433331.756 |  | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | 11kV line |  |  |  |  | 3 Leg RC / ULE Excepted
378 |  | 121/6 | A+0 |  |  |  | 53.83 | 2499.996 | 238.328 | 787 | 393.5 | 201 | 205 | 405 | 201 | 196 | 397 | 75°22'15.938" | 22°0'10.938" | 538303.993 | 2433209.735 |  | Yes | Yes | Yes | Yes
[5 empty] | 337 | [16 empty] | Cart track, LT line, Hand Pump
379 |  | 121/7 | A+0 |  |  |  | 53.83 | 2836.996 | 231.597 | 731.004 | 365.502 | 133 | 123 | 256 | 142 | 142 | 284 | 75°22'27.122" | 22°0'7.569" | 538624.931 | 2433106.933 |  | Yes | Yes | Yes | Yes
[5 empty] | 394.004 | [16 empty] | Bore, Well, Water pipeline
380 |  | 121/8 | A+9 |  |  |  | 62.83 | 3231 | 238.888 | 814.004 | 407.002 | 272 | 321 | 593 | 254 | 293 | 547 | 75°22'40.198" | 22°0'3.63" | 539000.155 | 2432986.742 |  | Yes | Yes | Yes | Yes
[5 empty] | 420 | [16 empty] | 11kV line |  |  |  |  | 3 Leg RC / ULE Excepted
381 |  | 121/9 | A+0 |  |  |  | 53.83 | 3651 | 222.333 | 813.996 | 406.998 | 101 | 152 | 253 | 129 | 164 | 293 | 75°22'54.137" | 21°59'59.431" | 539400.136 | 2432858.621 |  | Yes | Yes | Yes | Yes
[5 empty] | 393.996 | [16 empty] | Nala |  |  |  |  | 2 Leg RC / ULE Excepted
382 |  | 121/10 | A+9 |  |  |  | 62.83 | 4044.996 | 223.174 | 691.195 | 345.5975 | 243 | 102 | 344 | 231 | 114 | 345 | 75°23'7.212" | 21°59'55.491" | 539775.353 | 2432738.432 |  | Yes | Yes | Yes | Yes
297.199
383 | AP 122 | 122/0 | B1+3 | 1° 36' 48"RT |  | 4342.195 | 51.32 | 4342.195 | 237.016 | 619.196 | 309.598 | 196 | 272 | 468 | 184 | 234 | 418 | 75°23'17.075" | 21°59'52.519" | 540058.386 | 2432647.771 |  | Yes | Yes | Yes | Yes
322
384 |  | 122/1 | B1+9 |  |  |  | 57.32 | 4664.195 | 212.499 | 773 | 386.5 | 51 | 286 | 336 | 89 | 272 | 361 | 75° 23' 27.66" | 21° 59' 49.02" | 540362.151 | 2432540.95 | Near Village :-Madranya, RC/ULE Expected/ B Type Tower Proposed due to Wind span & one side Minimum Weight span Limit Violation. | Yes | Yes | Yes | Yes
[5 empty] | 451 | [16 empty] | Metal road, 11kvV line, Bore, Well
385 |  | 122/2 | A+0 |  |  |  | 53.83 | 5115.195 | 206.323 | 830.154 | 415.077 | 167 | 193 | 360 | 181 | 192 | 373 | 75° 23' 42.48" | 21° 59' 44.12" | 540787.611 | 2432391.334 | Near Village :-Madranya | Yes | Yes | Yes | Yes
379.154
386 | AP 123 | 123/0 | B2+0 | 10° 17' 22"RT |  | 1152.154 | 48.32 | 5494.349 | 205.799 | 744.154 | 372.077 | 187 | 209 | 397 | 188 | 203 | 391 | 75° 23' 54.95" | 21° 59' 40" | 541145.294 | 2432265.553 | Near Village :-Madranya | Yes | Yes | Yes | Yes
[5 empty] | 365 | [16 empty] | Cart track, Metal road
387 |  | 123/1 | A+0 |  |  |  | 53.83 | 5859.349 | 200.378 | 736 | 368 | 156 | 203 | 359 | 163 | 199 | 362 | 75° 24' 5.99" | 21° 59' 34.1" | 541462.458 | 2432084.91 | Near Village :-Maltar | Yes | Yes | Yes | Yes
[5 empty] | 371 | [16 empty] | LT line, Nala, Well
388 |  | 123/2 | A+0 |  |  |  | 53.83 | 6230.349 | 196.895 | 766 | 383 | 169 | 160 | 329 | 173 | 170 | 343 | 75° 24' 17.22" | 21° 59' 28.1" | 541784.836 | 2431901.297 | Near Village :-Maltar | Yes | Yes | Yes | Yes
[5 empty] | 395 | [16 empty] | 11kV line, Nala
389 |  | 123/3 | A+9 |  |  |  | 62.83 | 6625.349 | 196.201 | 844 | 422 | 236 | 270 | 506 | 227 | 259 | 486 | 75° 24' 29.17" | 21° 59' 21.71" | 542128.068 | 2431705.806 | Near Village :-Maltar | Yes | Yes | Yes | Yes
[5 empty] | 449 | [16 empty] | Nala, Cart track, Water pipeline, 11kV line, LT line to be shifted
390 |  | 123/4 | A+0 |  |  |  | 53.83 | 7074.349 | 194.04 | 843.576 | 421.788 | 180 | 184 | 364 | 192 | 188 | 380 | 75° 24' 42.75" | 21° 59' 14.45" | 542518.223 | 2431483.59 | Near Village :-Maltar | Yes | Yes | Yes | Yes
[5 empty] | 394.576 | [16 empty] | Near Village :-Maltar
391 | AP 124 | 124/0 | B2+0 | 13° 20' 31"LT |  | 1974.576 | 48.32 | 7468.925 | 197.061 | 849.576 | 424.788 | 211 | 210 | 422 | 208 | 215 | 423 | 75° 24' 54.69" | 21° 59' 8.07" | 542861.087 | 2431288.309 | Near Village :-Maltar | Yes | Yes | Yes | Yes
[5 empty] | 455 | [16 empty] | River, Piple tree, 11kV line, Cart track
392 |  | 124/1 | A+6 |  |  |  | 59.83 | 7923.925 | 195.495 | 848 | 424 | 246 | 186 | 432 | 242 | 189 | 431 | 75° 25' 9.91" | 21° 59' 3.87" | 543297.749 | 2431160.437 | Near Village :-Jotpura | Yes | Yes | Yes | Yes
[5 empty] | 393 | [16 empty] | Well, Nala
393 |  | 124/2 | A+6 |  |  |  | 59.83 | 8316.925 | 197.929 | 845 | 422.5 | 208 | 197 | 405 | 206 | 204 | 410 | 75° 25' 23.05" | 21° 59' 0.24" | 543674.91 | 2431049.99 | Near Village :-Jotpura | Yes | Yes | Yes | Yes
[5 empty] | 452 | [16 empty] | 11kV line, Cart track
394 |  | 124/3 | A+9 |  |  |  | 62.83 | 8768.925 | 202.507 | 848 | 424 | 256 | 211 | 468 | 250 | 209 | 459 | 75° 25' 38.16" | 21° 58' 56.07" | 544108.693 | 2430922.961 | Near Village :-Jotpura | Yes | Yes | Yes | Yes
[5 empty] | 396 | [16 empty] | Metal road, LT line, Nala, 11kV line, Well |  |  |  |  | A+6 & Rdue to excepted RC
395 |  | 124/4 | A+3 |  |  |  | 56.83 | 9164.925 | 205.67 | 838 | 419 | 186 | 205 | 391 | 189 | 209 | 398 | 75° 25' 51.4" | 21° 58' 52.42" | 544488.733 | 2430811.67 | Near Village :-Jotpura | Yes | Yes | Yes | Yes
[5 empty] | 442 | [16 empty] | Well
396 |  | 124/5 | A+6 |  |  |  | 59.83 | 9606.925 | 206.828 | 849 | 424.5 | 238 | 190 | 428 | 235 | 193 | 428 | 75° 26' 6.18" | 21° 58' 48.34" | 544912.919 | 2430687.452 | Near Village;- Near Village :- Beganda | Yes | Yes | Yes | Yes
[5 empty] | 407 | [16 empty] | Well, Cart track, 11kV line(2Nos), Metal road , 1nos 11kV line to be shifted
397 |  | 124/6 | A+6 |  |  |  | 59.83 | 10013.925 | 210.054 | 831 | 415.5 | 218 | 219 | 437 | 215 | 218 | 433 | 75° 26' 19.79" | 21° 58' 44.58" | 545303.516 | 2430573.07 | RC/ULE Expected/Near Village :- Beganda | Yes | Yes | Yes | Yes
[5 empty] | 424 | [16 empty] | LT lines, Nala
398 | AP 125 | 125/0 | B2+3 | 10° 11' 34"LT |  | 2969 | 51.32 | 10437.925 | 211.538 | 743 | 371.5 | 206 | 184 | 390 | 208 | 178 | 386 | 75° 26' 33.97" | 21° 58' 40.67" | 545710.399 | 2430453.918 | Near Village :- Beganda | Yes | Yes | Yes | Yes
[5 empty] | 319 | [16 empty] | Well, LT lines, Cart track
399 |  | 125/1 | A+3 |  |  |  | 56.83 | 10756.925 | 207.172 | 728 | 364 | 136 | 166 | 302 | 142 | 176 | 318 | 75° 26' 45.03" | 21° 58' 39.53" | 546027.575 | 2430419.858 | Near Village :- Beganda | Yes | Yes | Yes | Yes
[5 empty] | 409 | [16 empty] | Cart track, Nala, Well |  |  |  |  | 1 Nos LT Line Shifting
400 |  | 125/2 | A+3 |  |  |  | 56.83 | 11165.925 | 216.024 | 831 | 415.5 | 244 | 148 | 391 | 234 | 164 | 399 | 75° 26' 59.2" | 21° 58' 38.07" | 546434.237 | 2430376.188 | Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 422 | [16 empty] | Metal road |  |  |  |  | RC/ ULE Shifting Excepted
401 |  | 125/3 | A+6 |  |  |  | 59.83 | 11587.925 | 228.056 | 844.541 | 422.2705 | 276 | 276 | 552 | 260 | 260 | 520 | 75° 27' 13.83" | 21° 58' 36.57" | 546853.825 | 2430331.13 | Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 422.541 | [16 empty] | Water pipeline, 11kV line, Cart track, Well
402 | AP 126 | 126/0 | C2+0 | 27° 57' 14"RT |  | 1572.541 | 48.32 | 12010.466 | 219.068 | 871.541 | 435.7705 | 148 | 172 | 320 | 164 | 186 | 350 | 75° 27'28.473" | 21° 58'35.058" | 547273.951 | 2430286.014 | Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 449 | [16 empty] | LT line, Cart track, Well, 11kV line, Nala
403 |  | 126/1 | A+9 |  |  |  | 62.83 | 12459.466 | 223.325 | 754 | 377 | 279 | 125 | 404 | 266 | 132 | 398 | 75° 27'41.414" | 21° 58'26.838" | 547645.824 | 2430034.397 | RC/ULE Expected/Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 305 | [16 empty] | Cart track, Pond, Nala
404 |  | 126/2 | A+9 |  |  |  | 62.83 | 12764.466 | 228.043 | 744 | 372 | 180 | 199 | 379 | 174 | 205 | 378 | 75° 27'50.204" | 21° 58'21.254" | 547898.433 | 2429863.477 | Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 439 | [16 empty] | 11kV line, LT line, Bore
405 |  | 126/3 | A+3 |  |  |  | 56.83 | 13203.466 | 239.253 | 848 | 424 | 241 | 189 | 430 | 237 | 193 | 430 | 75° 28'2.856" | 21° 58'13.217" | 548262.024 | 2429617.463 | Near Village :- Baigandi | Yes | Yes | Yes | Yes
[5 empty] | 409 | [16 empty] | 11kV line
406 |  | 126/4 | A+0 |  |  |  | 53.83 | 13612.466 | 245.921 | 831 | 415.5 | 221 | 194 | 415 | 217 | 199 | 416 | 75° 28'14.643" | 21° 58'5.729" | 548600.769 | 2429388.262 | Near Village :- MIRJAPUR | Yes | Yes | Yes | Yes
[5 empty] | 422 | [16 empty] | Cart track, Metal road, Water pipeline
407 |  | 126/5 | A+3 |  |  |  | 56.83 | 14034.466 | 247.057 | 812 | 406 | 229 | 171 | 400 | 225 | 177 | 402 | 75° 28'26.804" | 21° 57'58.003" | 548950.28 | 2429151.776 | Near Village :- MIRJAPUR | Yes | Yes | Yes | Yes
390
408 |  | 126/6 | A+3 |  |  |  | 56.83 | 14424.466 | 252.368 | 794 | 397 | 220 | 236 | 455 | 214 | 228 | 442 | 75° 28'38.042" | 21° 57'50.862" | 549273.288 | 2428933.222 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 404 | [16 empty] | Pipal tree, LT line
409 |  | 126/7 | A+0 |  |  |  | 53.83 | 14828.466 | 247.923 | 779 | 389.5 | 169 | 192 | 361 | 178 | 191 | 369 | 75° 28'49.684" | 21° 57'43.464" | 549607.892 | 2428706.823 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 375 | [16 empty] | Bore, Well, LT line, Cart track,
410 |  | 126/8 | A+0 |  |  |  | 53.83 | 15203.466 | 247.125 | 743 | 371.5 | 184 | 155 | 339 | 185 | 163 | 348 | 75° 29'0.49" | 21° 57'36.598" | 549918.476 | 2428496.675 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 368 | [16 empty] | Well, Cart track, Bore, 11kV line
411 |  | 126/9 | A+3 |  |  |  | 56.83 | 15571.466 | 250.07 | 757 | 378.5 | 213 | 128 | 342 | 206 | 145 | 352 | 75° 29'11.094" | 21° 57'29.859" | 550223.263 | 2428290.45 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 389 | [16 empty] | Pipal tree, Bore, LT line, 11kV line, Cart track
412 |  | 126/10 | A+0 |  |  |  | 53.83 | 15960.466 | 267.482 | 779.104 | 389.552 | 262 | 209 | 471 | 245 | 206 | 451 | 75° 29'22.302" | 21° 57'22.736" | 550545.443 | 2428072.456 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 390.104 | [16 empty] | Metal road
413 | AP 127 | 127/0 | B1+0 | 2° 19' 21"LT |  | 4340.104 | 48.32 | 16350.57 | 264.577 | 796.104 | 398.052 | 182 | 183 | 365 | 185 | 189 | 374 | 75° 29'33.542" | 21° 57'15.592" | 550868.538 | 2427853.844 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 406 | [16 empty] | Pond, Nala, LT Line, Well,
414 |  | 127/1 | A+3 |  |  |  | 56.83 | 16756.57 | 266.179 | 805 | 402.5 | 224 | 210 | 434 | 219 | 208 | 427 | 75° 29'45.554" | 21° 57'8.606" | 551213.742 | 2427640.138 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 399 | [16 empty] | LT Line
415 |  | 127/2 | A+0 |  |  |  | 53.83 | 17155.57 | 266.91 | 799 | 399.5 | 190 | 194 | 384 | 193 | 196 | 389 | 75° 29'57.357" | 21° 57'1.739" | 551552.994 | 2427430.117 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
400
416 |  | 127/3 | A+0 |  |  |  | 53.83 | 17555.57 | 268.321 | 775 | 387.5 | 207 | 244 | 451 | 205 | 230 | 435 | 75° 30'9.19" | 21° 56'54.856" | 551893.097 | 2427219.569 | Near Village :- SINGUN | Yes | Yes | Yes | Yes
[5 empty] | 375 | [16 empty] | Nala,Pond
417 |  | 127/4 | A+3 |  |  |  | 56.83 | 17930.57 | 253.429 | 778 | 389 | 132 | 172 | 303 | 147 | 180 | 327 | 75° 30'20.283" | 21° 56'48.402" | 552211.943 | 2427022.181 | Near Village :- RAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 403 | [16 empty] | Well, LT Line end
418 |  | 127/5 | A+4.5 |  |  |  | 58.33 | 18333.57 | 258.864 | 750 | 375 | 232 | 200 | 433 | 225 | 194 | 418 | 75° 30'32.205" | 21° 56'41.466" | 552554.596 | 2426810.054 | Near Village :- RAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 347 | [16 empty] | Cart Track
419 |  | 127/6 | A(-)3 |  |  |  | 50.83 | 18680.57 | 261.156 | 705 | 352.5 | 147 | 123 | 270 | 154 | 138 | 293 | 75° 30'42.469" | 21° 56'35.493" | 552849.635 | 2426627.404 | Near Village :- PIPALJHOPA | Yes | Yes | Yes | Yes
[5 empty] | 358 | [16 empty] | Cart Track
420 |  | 127/7 | A(-)3 |  |  |  | 50.83 | 19038.57 | 272.542 | 747 | 373.5 | 236 | 211 | 447 | 221 | 207 | 428 | 75° 30'53.058" | 21° 56'29.332" | 553154.027 | 2426438.964 | Near Village :- PIPALJHOPA | Yes | Yes | Yes | Yes
[5 empty] | 389 | [16 empty] | Cart Track
421 |  | 127/8 | A(-)3 |  |  |  | 50.83 | 19427.57 | 268.939 | 724 | 362 | 179 | 168 | 347 | 183 | 168 | 352 | 75° 31'4.565" | 21° 56'22.636" | 553484.776 | 2426234.207 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 335 | [16 empty] | Well, Metal Road, LT Line, Cart Track, Nala, Water Pipe Line
422 |  | 127/9 | A+0 |  |  |  | 53.83 | 19762.57 | 265.828 | 702 | 351 | 167 | 100 | 267 | 168 | 123 | 290 | 75° 31'14.473" | 21° 56'16.87" | 553769.612 | 2426057.873 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
367
423 |  | 127/10 | B1+0 |  |  |  | 51.32 | 20129.57 | 280.284 | 778.68 | 389.34 | 268 | 66 | 334 | 246 | 98 | 344 | 75° 31'25.328" | 21° 56'10.552" | 554081.656 | 2425864.696 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 411.68 | [16 empty] | Cart Track, Water Tank
424 | AP 128 | 128/0 | D60+43 | 25° 26' 14"RT |  | 4190.68 | 84.32 | 20541.25 | 281.805 | 661.68 | 330.84 | 348 | 155 | 503 | 317 | 143 | 460 | 75° 31'37.504" | 21° 56'3.466" | 554431.69 | 2425648 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 250 | [16 empty] | 765 DC KHARGONE-DHULE TL, Cart track, 11kV line, 765kV earthwire to be removed in between ext. T# 157 and T# 158
425 | AP 129 | 129/0 | D60+55 | 29° 53' 39"LT |  | 250 | 96.32 | 20791.25 | 265.53 | 645.203 | 322.6015 | 95 | 345 | 441 | 107 | 316 | 424 | 75° 31'42.2" | 21° 55'56.616" | 554567.126 | 2425437.864 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 395.203 | [16 empty] | Cart track, Nala,11kV line, LT line, LT line to be diverted
426 | AP 129A | 129A/0 | C1+9 | 18° 3' 17"LT |  | 395.203 | 57.32 | 21186.453 | 265.529 | 809.203 | 404.6015 | 53 | 270 | 322 | 82 | 255 | 337 | 75° 31'54.42" | 21° 55'50.681" | 554918.299 | 2425256.583 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 414 | [16 empty] | 11kV line, LT line, Well, Pond
427 |  | 129A/1 | A(-)3 |  |  |  | 50.83 | 21600.453 | 263.072 | 810 | 405 | 145 | 127 | 272 | 161 | 145 | 306 | 75° 32'8.655" | 21° 55'48.47" | 555326.917 | 2425190.044 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 396 | [16 empty] | 11kV line, Nala, Cart track
428 |  | 129A/2 | A+7.5 |  |  |  | 61.33 | 21996.453 | 268.346 | 778 | 389 | 270 | 121 | 391 | 253 | 139 | 392 | 75° 32'22.272" | 21° 55'46.356" | 555717.769 | 2425126.398 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 382 | [16 empty] | LT line, Cart track
429 |  | 129A/3 | A+3 |  |  |  | 56.83 | 22378.453 | 287.806 | 790 | 395 | 262 | 185 | 447 | 245 | 190 | 435 | 75° 32'35.407" | 21° 55'44.316" | 556094.803 | 2425065.003 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
408
430 |  | 129A/4 | A+6 |  |  |  | 59.83 | 22786.453 | 289.177 | 829 | 414.5 | 224 | 272 | 495 | 219 | 257 | 477 | 75° 32'49.436" | 21° 55'42.137" | 556497.499 | 2424999.428 | Near Village :- PANDHANYA | Yes | Yes | Yes | Yes
[5 empty] | 421 | [16 empty] | Pond, Nala
431 |  | 129A/5 | A+9 |  |  |  | 62.83 | 23207.453 | 271.935 | 822 | 411 | 150 | 220 | 371 | 166 | 216 | 382 | 75° 33'3.912" | 21° 55'39.888" | 556913.026 | 2424931.764 | Near Village :- CHHALPA | Yes | Yes | Yes | Yes
[5 empty] | 401 | [16 empty] | Nala, Metal road, 11kV line, LT line, Cart track, Well
432 |  | 129A/6 | A+9 |  |  |  | 62.83 | 23608.453 | 267.604 | 849 | 424.5 | 182 | 237 | 418 | 187 | 234 | 421 | 75° 33'17.7" | 21° 55'37.745" | 557308.812 | 2424867.315 | Near Village :- CHHALPA | Yes | Yes | Yes | Yes
[5 empty] | 448 | [16 empty] | Nala
433 |  | 129A/7 | A+1.5 |  |  |  | 55.33 | 24056.453 | 272.035 | 832 | 416 | 212 | 107 | 319 | 216 | 128 | 344 | 75° 33'33.103" | 21° 55'35.351" | 557750.988 | 2424795.312 | Near Village :- CHHALPA | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | Cart track, Well, Pond, Nala
434 |  | 129A/8 | A+0 |  |  |  | 53.83 | 24440.453 | 291.885 | 784 | 392 | 278 | 169 | 447 | 257 | 177 | 435 | 75° 33'46.307" | 21° 55'33.299" | 558129.996 | 2424733.595 | Near Village :- CHHALPA | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | Mango garden
435 |  | 129A/9 | A+4.5 |  |  |  | 58.33 | 24840.453 | 294.334 | 843 | 421.5 | 232 | 229 | 461 | 224 | 228 | 452 | 75° 34'0.06" | 21° 55'31.161" | 558524.796 | 2424669.306 | Near Village :- IDARATPUR | Yes | Yes | Yes | Yes
[5 empty] | 443 | [16 empty] | Mango garden
436 |  | 129A/10 | A+1.5 |  |  |  | 55.33 | 25283.453 | 295.575 | 756.311 | 378.1555 | 215 | 210 | 425 | 217 | 197 | 414 | 75° 34'15.291" | 21° 55'28.792" | 558962.037 | 2424598.106 | Near Village :- IDARATPUR | Yes | Yes | Yes | Yes
[5 empty] | 313.311 | [16 empty] | Pond
437 | AP 130 | 130/0 | B2+0 | 6° 43' 29"RT |  | 4410.311 | 48.32 | 25596.764 | 287.905 | 606.308 | 303.154 | 104 | 177 | 282 | 117 | 170 | 287 | 75°34'26.064" | 21°55'27.117" | 559271.275 | 2424547.75 | Near Village :- IDARATPUR ,RC EXPECTED | Yes | Yes | Yes | Yes
[5 empty] | 292.997 | [16 empty] | Cart track, Pond
438 |  | 130/1 | A+0 |  |  |  | 53.83 | 25889.761 | 282.772 | 740.997 | 370.4985 | 116 | 280 | 396 | 124 | 267 | 391 | 75°34'35.787" | 21°55'24.202" | 559550.556 | 2424459.154 | Near Village :-Pokharkhurd | Yes | Yes | Yes | Yes
[5 empty] | 448 | [16 empty] | Pond, Damage bore, 11kV line, Metal road
439 |  | 130/2 | A+6 |  |  |  | 59.83 | 26337.761 | 262.764 | 831 | 415.5 | 169 | 229 | 397 | 183 | 220 | 403 | 75°34'50.654" | 21°55'19.744" | 559977.584 | 2424323.687 | Near Village :-Pokharkhurd | Yes | Yes | Yes | Yes
[5 empty] | 383 | [16 empty] | 11kV line, Nala, Well, LT line, Cart track
440 |  | 130/3 | A+3 |  |  |  | 56.83 | 26720.761 | 257.896 | 829 | 414.5 | 155 | 205 | 360 | 165 | 210 | 374 | 75°35'3.363" | 21°55'15.932" | 560342.655 | 2424207.876 | Near Village :-Pokharkhurd | Yes | Yes | Yes | Yes
[5 empty] | 446 | [16 empty] | LT line, Nala, Well
441 |  | 130/4 | A+6 |  |  |  | 59.83 | 27166.761 | 259.666 | 849 | 424.5 | 243 | 200 | 442 | 238 | 200 | 439 | 75°35'18.163" | 21°55'11.493" | 560767.776 | 2424073.014 | Near Village :-Pokharkhurd | Yes | Yes | Yes | Yes
[5 empty] | 403 | [16 empty] | Nala, Cart track, Pond, Metal road
442 |  | 130/5 | B1+9 |  |  |  | 57.32 | 27569.761 | 257.266 | 867.078 | 433.539 | 204 | 248 | 452 | 204 | 245 | 449 | 75°35'31.536" | 21°55'7.482" | 561151.911 | 2423951.155 | Near Village :-Pokharkhurd | Yes | Yes | Yes | Yes
[5 empty] | 464.078 | [16 empty] | 11kV line, Metal road, 2 Nos 33kV line, Cart track, Water pipeline
443 | AP 131 | 131/0 | D45+9 | 43° 57' 2"LT |  | 2437.075 | 57.32 | 28033.839 | 253.173 | 644.078 | 322.039 | 218 | 119 | 337 | 221 | 102 | 323 | 75° 35'46.935" | 21° 55'2.862" | 561594.264 | 2423810.827 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 180 | [16 empty] | 220KV DC KHALGAT-DESHGAON MPPTCL, Water pipeline, Cart track
444 | AP 132 | 132/0 | D45+9 | 42° 54' 3"RT |  | 180 | 57.32 | 28213.839 | 251.052 | 540 | 270 | 61 | 252 | 313 | 79 | 229 | 307 | 75° 35'52.568" | 21° 55'5.44" | 561755.561 | 2423890.72 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 360 | [16 empty] | 11kV line, Nala, Cart track, Well, Temple, LT line
445 |  | 132/1 | A+0 |  |  |  | 53.83 | 28573.839 | 246.428 | 670 | 335 | 109 | 171 | 279 | 133 | 166 | 298 | 75° 36'4.582" | 21° 55'2.061" | 562100.645 | 2423788.169 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 310 | [16 empty] | LT line, Well
446 |  | 132/2 | A+0 |  |  |  | 53.83 | 28883.839 | 243.908 | 672 | 336 | 140 | 197 | 337 | 145 | 192 | 337 | 75° 36'14.927" | 21° 54'59.151" | 562397.801 | 2423699.861 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 362 | [16 empty] | Nala, Well, LT line, Bore |  |  |  |  | 11 KV Line Shifitng
447 |  | 132/3 | A+0 |  |  |  | 53.83 | 29245.839 | 240.912 | 613 | 306.5 | 166 | 131 | 297 | 171 | 129 | 300 | 75° 36'27.007" | 21° 54'55.753" | 562744.803 | 2423596.74 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 251 | [16 empty] | Nala, 33kV line, LT line, 11kV line, Bore, Fence
448 | AP 133 | 133/0 | B1+0 | 5° 10' 4"RT |  | 1283 | 48.32 | 29496.839 | 240.235 | 473 | 236.5 | 120 | 113 | 233 | 122 | 112 | 234 | 75° 36'35.373" | 21° 54'53.399" | 562985.13 | 2423525.32 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 222 | [16 empty] | Fence, 11kV line, LT line, Well, Bore, NH 347C(KHAREGONE-KASRAWAD) 11kV line to be shifted
449 | AP 134 | 134/0 | B2+6 | 5° 27' 42"LT |  | 222 | 48.32 | 29718.839 | 240.044 | 673 | 336.5 | 109 | 191 | 300 | 110 | 194 | 304 | 75° 36'42.55" | 21° 54'50.7" | 563191.37 | 2423443.17 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 451 | [16 empty] | 33kV line, LT line, Cart track, Nala
450 |  | 134/1 | A+9 |  |  |  | 62.83 | 30169.839 | 234.325 | 845 | 422.5 | 218 | 236 | 454 | 220 | 227 | 448 | 75° 36'55.346" | 21° 54'42.22" | 563559.537 | 2423183.897 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 394 | [16 empty] | Nala, LT line
451 |  | 134/2 | A+3 |  |  |  | 56.83 | 30563.839 | 231.721 | 846 | 423 | 159 | 223 | 382 | 168 | 224 | 392 | 75° 37'6.514" | 21° 54'34.764" | 563880.893 | 2422955.936 | Near Village :-NIMGUL | Yes | Yes | Yes | Yes
[5 empty] | 452 | [16 empty] | Nala, Cart track, LT line, Well
452 |  | 134/3 | A+6 |  |  |  | 59.83 | 31015.839 | 229.644 | 848 | 424 | 230 | 210 | 441 | 230 | 208 | 438 | 75° 37'19.326" | 21° 54'26.21" | 564249.555 | 2422694.417 | Near Village :-RAHIMABAD | Yes | Yes | Yes | Yes
[5 empty] | 396 | [16 empty] | Nala, LT line
453 |  | 134/4 | A+3 |  |  |  | 56.83 | 31411.839 | 229.953 | 831 | 415.5 | 186 | 226 | 412 | 189 | 225 | 414 | 75° 37'30.55" | 21° 54'18.716" | 564572.542 | 2422465.298 | Near Village :-RAHIMABAD | Yes | Yes | Yes | Yes
[5 empty] | 435 | [16 empty] | Nala, LT line, Cart track
454 |  | 134/5 | A+0 |  |  |  | 53.83 | 31846.839 | 231.003 | 842 | 421 | 210 | 206 | 416 | 212 | 206 | 418 | 75° 37'42.88" | 21° 54'10.484" | 564927.339 | 2422213.616 | Near Village :-BORGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 407 | [16 empty] | 11kV line, Cart track
455 |  | 134/6 | A+3 |  |  |  | 56.83 | 32253.839 | 227.485 | 846 | 423 | 202 | 225 | 427 | 203 | 224 | 427 | 75° 37'54.415" | 21° 54'2.781" | 565259.298 | 2421978.133 | Near Village :-NAWALPURA | Yes | Yes | Yes | Yes
[5 empty] | 439 | [16 empty] | LT line, Cart track, Temple, (LT line to be diverted)
456 |  | 134/7 | A+3 |  |  |  | 56.83 | 32692.839 | 226.226 | 849 | 424.5 | 215 | 224 | 439 | 217 | 220 | 436 | 75° 38'6.857" | 21° 53'54.472" | 565617.357 | 2421724.136 | Near Village :-NAWALPURA | Yes | Yes | Yes | Yes
[5 empty] | 410 | [16 empty] | Cart track, Nala
457 |  | 134/8 | A+3 |  |  |  | 56.83 | 33102.839 | 222.026 | 794 | 397 | 187 | 237 | 424 | 192 | 227 | 418 | 75° 38'18.477" | 21° 53'46.712" | 565951.763 | 2421486.917 | Near Village :-BILGAON | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | Cart track, Nala, Well
458 |  | 134/9 | A+0 |  |  |  | 53.83 | 33486.839 | 215.458 | 756.658 | 378.329 | 148 | 136 | 284 | 159 | 148 | 307 | 75° 38'29.359" | 21° 53'39.444" | 566264.963 | 2421264.742 | Near Village :-NAWALPURA | Yes | Yes | Yes | Yes
[5 empty] | 372.658 | [16 empty] | Nala
459 | AP 135 | 135/0 | B2+9 | 5° 27' 46"LT |  | 4140.658 | 57.32 | 33859.497 | 217.248 | 899.362 | 449.681 | 238 | 255 | 493 | 226 | 257 | 483 | 75° 38'39.92" | 21° 53'32.39" | 566568.912 | 2421049.129 | Near Village :-NAWALPURA | Yes | Yes | Yes | Yes
[5 empty] | 526.704 | [16 empty] | Cart track, River, LT line
460 | AP 136 | 136/0 | C2+9 | 24° 12' 30"LT |  | 526.704 | 57.32 | 34386.201 | 220.201 | 981.704 | 490.852 | 273 | 253 | 527 | 273 | 248 | 520 | 75° 38'55.795" | 21° 53'23.792" | 567025.565 | 2420786.67 | Near Village :-KHEDIKHURD | Yes | Yes | Yes | Yes
[5 empty] | 455 | [16 empty] | Metal road, Cart track, Well, 11kV line
461 |  | 136/1 | A+0 |  |  |  | 53.83 | 34841.201 | 222.647 | 849 | 424.5 | 202 | 189 | 391 | 209 | 191 | 400 | 75° 39'11.566" | 21° 53'22.265" | 567478.331 | 2420741.641 | Near Village :-KHEDIKHURD | Yes | Yes | Yes | Yes
[5 empty] | 394 | [16 empty] | Cart track, 11kV line, LT line, Well
462 |  | 136/2 | A+3 |  |  |  | 56.83 | 35235.201 | 221.563 | 838 | 419 | 206 | 224 | 430 | 204 | 224 | 428 | 75° 39'25.222" | 21° 53'20.942" | 567870.397 | 2420702.65 | Near Village :-DONGARGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 444 | [16 empty] | Metal road, Bore, Well, LT line,Nala, LT line to be diverted
463 |  | 136/3 | A+3 |  |  |  | 56.83 | 35679.201 | 221.241 | 849 | 424.5 | 221 | 224 | 445 | 222 | 219 | 441 | 75° 39'40.612" | 21° 53'19.452" | 568312.218 | 2420658.71 | Near Village :-DONGARGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 405 | [16 empty] | Nala
464 |  | 136/4 | A+0 |  |  |  | 53.83 | 36084.201 | 219.5 | 809 | 404.5 | 182 | 207 | 389 | 187 | 206 | 393 | 75° 39'54.65" | 21° 53'18.092" | 568715.23 | 2420618.629 | Near Village :-DONGARGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 404 | [16 empty] | Cart track, LT line
465 |  | 136/5 | A+0 |  |  |  | 53.83 | 36488.201 | 218.572 | 804 | 402 | 198 | 200 | 399 | 200 | 201 | 400 | 75° 40'8.653" | 21° 53'16.735" | 569117.246 | 2420578.648 | Near Village :-DONGARGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 400 | [16 empty] | Cart track
466 |  | 136/6 | A+0 |  |  |  | 53.83 | 36888.201 | 218.589 | 801 | 400.5 | 200 | 195 | 395 | 201 | 197 | 397 | 75° 40'22.517" | 21° 53'15.391" | 569515.283 | 2420539.063 | Near Village :-DONGARGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 401 | [16 empty] | LT line, Well, Pump house,
467 |  | 136/7 | A+0 |  |  |  | 53.83 | 37289.201 | 219.96 | 785 | 392.5 | 207 | 203 | 410 | 206 | 200 | 406 | 75° 40'36.416" | 21° 53'14.043" | 569914.314 | 2420499.378 | Near Village :-THIBGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 384 | [16 empty] | LT lines, Well, Pump house, Water tank, LT line to be diverted
468 |  | 136/8 | A+0 |  |  |  | 53.83 | 37673.201 | 217.775 | 767 | 383.5 | 182 | 215 | 397 | 185 | 209 | 394 | 75° 40'49.726" | 21° 53'12.752" | 570296.429 | 2420461.376 | Near Village :-THIBGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 383 | [16 empty] | Metal road, Cart track, Well, LT line, 11kV line
469 |  | 136/9 | A+0 |  |  | 3670 | 53.83 | 38056.201 | 212.87 | 780 | 390 | 169 | 185 | 354 | 175 | 189 | 364 | 75° 41'3.001" | 21° 53'11.464" | 570677.549 | 2420423.473 | Near Village :-THIBGAON KHURD | Yes | Yes | Yes | Yes
[5 empty] | 397 | [16 empty] | 11kV lines, LT line, Bhanya river, Well, Cart track, LT line & 11kV line to be diverted
470 | AP 139 | 139/0 | B2+0 | 14° 32' 12" RT |  |  | 48.32 | 38453.201 | 215.921 | 822 | 411 | 212 | 191 | 404 | 209 | 197 | 406 | 75° 41'16.753" | 21° 53'10.13" | 571072.371 | 2420384.207 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 425 | [16 empty] | 33kV lines, 11kV line, LT line, Metal road, Cart track
471 |  | 139/1 | A+3 |  |  |  | 56.83 | 38878.201 | 218.005 | 844 | 422 | 235 | 218 | 452 | 230 | 216 | 446 | 75° 41'30.627" | 21° 53'5.295" | 571471.189 | 2420237.343 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 419 | [16 empty] | 11kV line, Nala, LT line
472 |  | 139/2 | A+0 |  |  |  | 53.83 | 39297.201 | 219.204 | 839 | 419.5 | 202 | 191 | 393 | 205 | 196 | 400 | 75° 41'44.305" | 21° 53'0.529" | 571864.377 | 2420092.553 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 420 | [16 empty] | Nala, 11kV line, Metal road
473 |  | 139/3 | A+3 |  |  |  | 56.83 | 39717.201 | 220.833 | 823 | 411.5 | 230 | 208 | 439 | 226 | 207 | 433 | 75° 41'58.016" | 21° 52'55.75" | 572258.503 | 2419947.417 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 403 | [16 empty] | Well
474 |  | 139/4 | A+0 |  |  |  | 53.83 | 40120.201 | 222.381 | 801 | 400.5 | 196 | 205 | 401 | 197 | 204 | 402 | 75° 42'11.171" | 21° 52'51.165" | 572636.677 | 2419808.155 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 398 | [16 empty] | 11kV line, LT line, Well
475 |  | 139/5 | A+0 |  |  |  | 53.83 | 40518.201 | 221.088 | 783 | 391.5 | 194 | 197 | 391 | 195 | 196 | 392 | 75° 42'24.163" | 21° 52'46.637" | 573010.159 | 2419670.622 | Near Village :-THIBGAON BUJURG | Yes | Yes | Yes | Yes
[5 empty] | 385 | [16 empty] | Nala, Cart track, LT line, 11kV line
476 |  | 139/6 | A+0 |  |  |  | 53.83 | 40903.201 | 220.193 | 775 | 387.5 | 189 | 199 | 388 | 190 | 198 | 388 | 75° 42'36.73" | 21° 52'42.256" | 573371.441 | 2419537.58 | Near Village :-MAUSAMPURA | Yes | Yes | Yes | Yes
[5 empty] | 390 | [16 empty] | LT line, Nala, Well
477 |  | 139/7 | A+0 |  |  |  | 53.83 | 41293.201 | 219.388 | 825.775 | 412.8875 | 192 | 176 | 368 | 193 | 187 | 380 | 75° 42'49.461" | 21° 52'37.818" | 573737.415 | 2419402.811 | Near Village :-JAMNYA | Yes | Yes | Yes | Yes
[5 empty] | 435.775 | [16 empty] | Nala,Well, Cart track
478 | AP 140 | 140/0 | C2+9 | 27° 55' 34"RT |  | 3672.775 | 57.32 | 41728.976 | 220.875 | 628.354 | 314.177 | 261 | 77 | 339 | 252 | 89 | 340 | 75° 43'3.685" | 21° 52'32.858" | 574146.345 | 2419252.224 | Near Village :-JAMNYA | Yes | Yes | Yes | Yes
[5 empty] | 192.579 | [16 empty] | 132 KV DC OHTL KHANDWA-KHARGONE , Well, Pump house, LT line
479 | AP 141 | 141/0 | D45+9 |  |  | 192.579 | 57.32 | 41921.555 | 222.415 | 192.579 | 96.2895 | 116 | 0 | 116 | 105 | 0 | 105 | 75° 43'8.139" | 21° 52'28.174" | 574274.85 | 2419108.79 | Near Village :-JAMNYA | Yes | Yes | Yes | Yes
[5 empty] | 185029.234 |  |  |  |  | 0
SUMMARY OF TOWERS QUANTITIES of Above Composite Tower Chanage
[5 empty] | TYPE OF TOWER | EXTENSION | [16 empty] | TOTAL TOWER
[6 empty] | (-)3 | (-)1.5 | +0 | +1.5 | +3 | +4.5 | +6 | +7.5 | +9 | +12 | +15 | +18 | +25 | +36 | +48 | +55 |  | 16
[5 empty] | A | 37 | 2 | 117 | 9 | 72 | 7 | 34 | 9 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 323
[5 empty] | B1 | 2 | 0 | 5 | 0 | 4 | 0 | 1 | 0 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19
[5 empty] | B2 | 1 | 0 | 14 | 0 | 5 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
[5 empty] | C1 | 0 | 0 | 6 | 0 | 8 | 0 | 3 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
[5 empty] | C2 | 6 | 0 | 9 | 1 | 2 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
[5 empty] | D45 | 4 | 0 | 9 | 0 | 10 | 0 | 4 | 0 | 5 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 35
[5 empty] | D60 | 2 | 0 | 4 | 0 | 1 | 0 | 2 | 0 | 6 | 0 | 0 | 1 | 1 | 0 | 0 | 3 | 0 | 20
[5 empty] | Total | 52 | 2 | 164 | 10 | 102 | 7 | 49 | 10 | 67 | 0 | 0 | 5 | 1 | 0 | 0 | 3 | 474
[5 empty] | TOTAL Including RC Location | B1+9 (79/1) 1 mtr. Rc | B1+9 (113/0) 3 mtr. Rc | C1+18 (119/0) 2 mtr. Rc
Hold Location
|  | 72/0 | D45+6 | RC Excepted
|  | 72/1 | A+9 | RC Excepted
|  | 76/1 | A+9 | RC Excepted
|  | 76/3 | A+0 | RC Excepted
|  | 76/5 | A+9 | RC Excepted
|  | 76/6 | A+0 | RC Excepted
|  | 77/1 | A+0 | RC Excepted
|  | 78/0 | C2+0 | RC Excepted
|  | 82/3 | B1+9 | 1 Mtr. Equal RC
|  | 99/2 | A+3 | Hold Due to LT Line Diversion
|  | 99/5 | A+6 | Adjacent Tower MPPTCL
|  | 101/1 | A+0 | Adjacent Tower MPPTCL
|  | 102/9 | A+3 | Hold Due to LT Line Diversion
|  | 104/2 | B1+9 | Hold Due to NH 347-B(Adjacent)
|  | 105/0 | C2+6 | Hold Due to NH 347-B
|  | 106/0 | B2+0 | Hold Due to NH 347-B
|  | 110/1 | A+7.5 | Hold Due to pendencies A+(9 to A+7.5
|  | 110/2 | A+0 | Hold Due to LT Line Diversion
|  | 110/4 | A+0 | Hold Due to LT Line Diversion
|  | 111/7 | A+0 | RLY MMR-INDB
|  | 111A/0 | D60+9 | RLY MMR-INDB
|  | 111B/0 | D60+6 | RLY MMR-INDB
|  | 111B/1 | A+0 | RLY MMR-INDB
|  | 112/0 | D45+18 | Julwania -Ajandi(MPPTCL 11 KV
|  | 113/0 | B1+9 (RC = 3M) | RC Excepted & 11 KV Line
|  | 114/0 | B1+18 | Julwania -Ajandi(MPPTCL 11 KV
|  | 115/0 | C2+18 | RC Excepted
|  | 115/1 | B1+3 | RC Excepted
|  | 115/2 | A+0 | RC Excepted
|  | 117/0 | B2+3 | RC Excepted
|  | 117/1 | A+0 | RC Excepted
|  | 118/0 | B1+0 | RC Excepted/ RC
|  | 119/0 | C1+18(RC2M) | NH 52 /2 Mtr RC
|  | 120/0 | D45+18 | NH 52 Adj Tower
|  | 121/0 | B2+0 | 220 KV crossing Adj / 2 Leg RC /ULE
|  | 121/3 | A+3 | 2 Leg RC / ULE / LT Line Shifted
|  | 121/8 | A+0 | 3 Leg RC / ULE Excepted
|  | 122/0 | B1+3 | 3 Leg RC / ULE Excepted
|  | 122/1 | B1+9 | 2 Leg RC / ULE Excepted
|  | 124/6 | A+6 | A+6 & Rdue to excepted RC
|  | 126/0 | C2+0 | 1 Nos LT Line Shifting
|  | 126/1 | A+9 | RC/ ULE Shifting Excepted
|  | 133/0 | B1+0 | 11 KV Line Shifitng

## Earthing
KEC International Limited
Name of Line: Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Details of Earthing | [9 empty] | 2026-05-30 20:29
CUMM. SR.NO | MONTH SR.NO. | Loc. No. | Type of Tower | Type of Classification | Start | Completion Date | Type | Name of the Gang | Name of Supervisor | No. | Remarks | Revenue
1 | 1 | 123/1 | A+0 | WFR |  | 2025-10-10 | CP | R.K . Enterprises | SUOMEN KHAN & AASISH SHARMA | 4 | Oct'25 | RA-1 |  | CP
2 | 2 | 121/2 | A+6 | DFR |  | 2025-10-20 | CP | Balaji Enterprises | MADHUSUDHAN PRASAD |  |  | RA-1 | RA-3 | CP
3 | 3 | 124/2 | A+6 | WFR |  | 2025-10-20 | CP | Jai Shri Ram Enterprises | UTTAM KUMAR DAS |  |  | RA-1 | RA-3 | CP
4 | 4 | 123/3 | A+9 | DFR |  | 2025-10-22 | CP | R.K . Enterprises | JAYANTA GHOSH |  |  | RA-1 |  | CP
5 | 1 | 122/2 | A+0 | WFR |  | 2025-11-02 | CP | Jai Shri Ram Enterprises | UTTAM KUMAR DAS | 23 | Nov'25 | RA-1 | RA-3 | CP
6 | 2 | 126/5 | A+3 | DFR |  | 2025-11-03 | CP | Rajiya Infra. | BAPI SARKAR |  |  | RA-2
7 | 3 | 116/1 | A+3 | DFR |  | 2025-11-04 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2 | RA-3 | CP
8 | 4 | 121/7 | A+0 | WFR |  | 2025-11-07 | CP | Pawan enterprises | MIJANUR RAHMAN |  |  | RA-1 |  | CP
9 | 5 | 126/4 | A+0 | DFR |  | 2025-11-07 | CP | Rajiya Infra. | DEEP KUMAR DAS |  |  | RA-2 | RA-3
10 | 6 | 116/2 | A+3 | DFR |  | 2025-11-08 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2 |  | CP
11 | 7 | 123/4 | A+0 | WET |  | 2025-11-08 | ROD TYPE & PIPE TYPE | Shri Balaji Construction | MADHUSUDHAN PRASAD |  |  | RA-2
12 | 8 | 126/3 | A+3 | DFR |  | 2025-11-13 | CP | Rajiya Infra. | DEEP KUMAR DAS |  |  | RA-2 | RA-3 | CP
13 | 9 | 121/1 | A+0 | DFR |  | 2025-11-19 | CP | Shri Balaji Construction | MADHUSUDHAN PRASAD |  |  | RA-2 | RA-3 | CP
14 | 10 | 123/2 | A+0 | WFR |  | 2025-11-20 | CP | Jai Shri Ram Enterprises | UTTAM KUMAR DAS |  |  | RA-2 | RA-3 | CP
15 | 11 | 124/1 | A+6 | WET Paddy |  | 2025-11-21 | ROD TYPE & PIPE TYPE | Balaji Enterprises | JAYANTA GHOSH |  |  | RA-1 |  | ROD TYPE & PIPE TYPE
16 | 12 | 103/2 | A+0 | WET PADDY |  | 2025-11-23 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
17 | 13 | 124/4 | A+3 | WFR |  | 2025-11-23 | CP | Jai Shri Ram Enterprises | UTTAM KUMAR DAS |  |  | RA-2 | RA-3 | CP
18 | 14 | 126/2 | A+9 | WFR |  | 2025-11-23 | CP | Rajiya Infra. | MADHUSUDHAN PRASAD |  |  | RA-3 |  | CP
19 | 15 | 111/2 | A+3 | DFR |  | 2025-11-24 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2
20 | 16 | 126/9 | A+3 | DFR |  | 2025-11-24 | CP | Rajiya Infra. | DEEP KUMAR DAS |  |  | RA-2 | RA-3 | CP
21 | 17 | 111/4 | A+0 | DFR |  | 2025-11-25 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2 | RA-3 | CP
22 | 18 | 121/4 | A+0 | DFR |  | 2025-11-25 | CP | Pawan enterprises | MIJANUR RAHMAN |  |  | RA-2
23 | 19 | 126/10 | A+0 | DFR |  | 2025-11-25 | CP | Rajiya Infra. | DEEP KUMAR DAS |  |  | RA-2
24 | 20 | 103/3 | A+3 | WET PADDY |  | 2025-11-26 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-2 |  | ROD TYPE & PIPE TYPE
25 | 21 | 111/3 | A+0 | WFR |  | 2025-11-26 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2 | RA-3 | CP
26 | 22 | 130/3 | A+3 | WFR |  | 2025-11-26 | CP | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-2 | RA-3 | CP
27 | 23 | 111/5 | A+6 | DFR |  | 2025-11-30 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-2 | RA-3 | CP
28 | 1 | 103/1 | A+6 | WET PADDY |  | 2025-12-02 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN | 26 | Dec'25 | RA-2 |  | ROD TYPE & PIPE TYPE
29 | 2 | 130/1 | A+0 | DFR |  | 2025-12-04 | CP | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-2 | RA-3 | CP
30 | 3 | 110/1 | A+7.5 | DFR |  | 2025-12-05 | CP | B.L Construction | JAYANTA GHOSH |  |  | RA-3 |  | CP
31 | 4 | 110/2 | A+0 | DFR |  | 2025-12-05 | CP | Shri Balaji Construction | MADHUSUDHAN PRASAD |  |  | RA-2 | RA-3 | CP
32 | 5 | 109/1 | A+3 | WET PADDY |  | 2025-12-07 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
33 | 6 | 134/9 | A+0 | WET PADDY |  | 2025-12-08 | CP | Jai Shri Ram Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-3 |  | CP
34 | 7 | 99/1 | A+3 | WET PADDY |  | 2025-12-09 | ROD TYPE & PIPE TYPE | Dhanraj construction | MIJANUR RAHMAN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
35 | 8 | 102/7 | A+0 | WET PADDY |  | 2025-12-09 | ROD TYPE & PIPE TYPE | Rajiya Infra. | MIJANUR RAHMAN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
36 | 9 | 102/9 | A+3 | WET PADDY |  | 2025-12-09 | ROD TYPE & PIPE TYPE | Rajiya Infra. | MIJANUR RAHMAN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
37 | 10 | 110/3 | A+0 | DFR |  | 2025-12-13 | CP | Shri Balaji Construction | MADHUSUDHAN PRASAD |  |  | RA-3 |  | CP
38 | 11 | 99/2 | A+3 | WET PADDY |  | 2025-12-20 | ROD TYPE & PIPE TYPE | Dhanraj construction | MIJANUR RAHMAN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
39 | 12 | 136/5 | A+0 | WET PADDY |  | 2025-12-20 | CP | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-3 |  | CP
40 | 13 | 136/7 | A+0 | WET PADDY |  | 2025-12-20 | CP | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-3 |  | CP
41 | 14 | 102/8 | A+0 | WET PADDY |  | 2025-12-21 | ROD TYPE & PIPE TYPE | Rajiya Infra. | MIJANUR RAHMAN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
42 | 15 | 136/2 | A+3 | WET Paddy |  | 2025-12-21 | CP | R.K . Enterprises | TANMAY NAYAK
43 | 16 | 136/8 | A+0 | WET PADDY |  | 2025-12-21 | CP | R.K . Enterprises | UTTAM KUMAR DAS |  |  | RA-3 |  | CP
44 | 17 | 136/9 | A+0 | WET PADDY |  | 2025-12-21 | CP | R.K . Enterprises | TANMAY NAYAK |  |  | RA-3 |  | CP
45 | 18 | 136/6 | A+0 | WET Paddy |  | 2025-12-23 | CP | R.K . Enterprises | HRIDAY CHAKRABARTY & UTTAM KUMAR DAS |  |  | RA-3 |  | CP
46 | 19 | 108/5 | A-3 | WET PADDY |  | 2025-12-24 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
47 | 20 | 89/9 | A+0 | WFR |  | 2025-12-27 | CP | Shree Khatushyam | DEEP KUMAR DAS
48 | 21 | 108/6 | A-3 | WET PADDY |  | 2025-12-27 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
49 | 22 | 108/7 | A-3 | WET PADDY |  | 2025-12-27 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
50 | 23 | 109/2 | A+0 | WET PADDY |  | 2025-12-28 | ROD TYPE & PIPE TYPE | MUKESH MEHTA | SADDAM HOSSAIN |  |  | RA-3 |  | ROD TYPE & PIPE TYPE
51 | 24 | 130/2 | A+6 | DFR |  | 2025-12-29 | CP | R.K . Enterprises | TANMAY NAYAK
52 | 25 | 89/8 | A+0 | DFR |  | 2025-12-30 | CP | Afflux Construction | DEEP KUMAR DAS
53 | 26 | 136/1 | A+0 | WET PADDY |  | 2025-12-30 | CP | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH |  |  | RA-3 |  | CP
54 | 1 | 89/7 | A+0 | DFR |  | 2026-01-03 | CP | Shree Khatushyam | DEEP KUMAR DAS | 6 | Jan'26
55 | 2 | 89/6 | A+0 | DFR |  | 2026-01-08 | CP | Afflux Construction | DEEP KUMAR DAS
56 | 3 | 89/5 | A+3 | DFR |  | 2026-01-12 | CP | Shree Khatushyam | DEEP KUMAR DAS
57 | 4 | 108/1 | A+9 | DFR |  | 2026-01-19 | CP | B.L Construction | SADDAM HOSSAIN
58 | 5 | 136/4 | A+0 | WET PADDY |  | 2026-01-21 | ROD TYPE & PIPE TYPE | R.K . Enterprises | MD WAHIDDUJAMAN BISWASH
59 | 6 | 76/2 | A+6 | DFR |  | 2026-01-24 | CP | Afflux Construction | DEEP KUMAR DAS
60 | 7 | 77/1 | A-3 | DFR |  | 2026-02-02 | CP | Shree Khatushyam |  | 15 | Feb'26
61 | 8 | 127/7 | A-3 | DFR |  | 2026-02-02 | CP | R.K . Enterprises
62 | 9 | 129A/2 | A+7.5 | DFR |  | 2026-02-02 | CP | R.K . Enterprises
63 | 10 | 129A/4 | A+6 | DFR |  | 2026-02-03 | CP | R.K . Enterprises
64 | 11 | 76/1 | A+6 | DFR |  | 2026-02-04 | CP | Afflux Construction
65 | 12 | 82/2 | A+7.5 | WFR |  | 2026-02-04 | CP | Afflux Construction
66 | 13 | 82/3 | A+9 | WET |  | 2026-02-09 | ROD TYPE & PIPE TYPE | Afflux Construction
67 | 14 | 127/1 | A+3 | DFR |  | 2026-02-10 | CP | B.L Construction
68 | 15 | 129A/3 | A+3 | DFR |  | 2026-02-13 | CP | R.K . Enterprises
69 | 16 | 127/2 | A+0 | DFR |  | 2026-02-14 | CP | B.L Construction
70 | 17 | 129A/6 | A+9 | WFR |  | 2026-02-17 | CP | R.K . Enterprises
71 | 18 | 70/3 | A-3 | DFR |  | 2026-02-19 | CP | Afflux Construction
72 | 19 | 70/1 | A+4.5 | DFR |  | 2026-02-24 | CP | Afflux Construction
73 | 20 | 121/10 | A+9 | DFR |  | 2026-02-27 | CP | B.L Construction
74 | 1 | 70/2 | A+9 | WFR |  | 2026-03-08 | CP | Afflux Construction |  | 3 | March'26
75 | 2 | 126/7 | A+0 | DFR |  | 2026-03-10 | CP
76 | 3 | 76/5 | A+9 | DFR |  | 2026-03-23 | CP
77 | 1 | 88/2 | A+0 | DFR |  | 2026-04-04 | CP |  |  | 19 | April'26
78 | 2 | 124/0 | B2+0 | Wet Paddy |  | 2026-04-09 | Rod Type & Pipe Type
79 | 3 | 88/1 | A+3 | DFR |  | 2026-04-12 | CP
80 | 4 | 102/11 | A+9 | Wet Paddy |  | 2026-04-13 | Rod Type & Pipe Type
81 | 5 | 69/2 | A+0 | DFR |  | 2026-04-17 | CP
82 | 6 | 127/4 | A+3 | WFR |  | 2026-04-17 | CP
83 | 7 | 87/5 | A+3 | DFR |  | 2026-04-19 | CP
84 | 8 | 71/1 | A+3 | WFR |  | 2026-04-21 | CP
85 | 9 | 87/4 | A+0 | DFR |  | 2026-04-22 | CP
86 | 10 | 69/1 | A+0 | DFR |  | 2026-04-23 | CP
87 | 11 | 71/2 | A-3 | DFR |  | 2026-04-27 | CP
88 | 12 | 87/2 | A+0 | DFR |  | 2026-04-27 | CP
89 | 13 | 69/3 | A+0 | DFR |  | 2026-04-28 | CP
90 | 1 | 71/3 | A+0 | DFR |  | 2026-05-02 | CP |  |  | 6 | May'26
91 | 2 | 139/0 | B2+0 | Wet Paddy |  | 2026-05-02 | Rod Type & Pipe Type
92 | 3 | 87/3 | A+3 | DFR |  | 2026-05-03 | CP
93 | 4 | 71/4 | A+0 | DFR |  | 2026-05-04 | CP
94 | 5 | 88/3 | A-3 | DFR |  | 2026-05-20 | CP
95 | 6 | 69/4 | A+0 | DFR |  | 2026-05-23 | CP
RA-1
RA-3
Formulas:
Completion Date = VLOOKUP([Loc. No.],'[2]FDN Details'!$C5:BP483,59,0)

## statuary clearance
Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
Details of Crossing
S.No. | Type of Proposal | Tower No. | Name of Existing Line | Voltage Level | Proposal Subitted by KEC to PGCIL. | Joint Inspection Done on | Plan To Submit
1 | PLC | AP46 TO AP47 | 400KV D/C XING | 400KV | Submitted(07/05/2026)
2 | PLC | AP59 TO AP60 | 132KV D/C | 132KV | Submitted(03/04/2026) | Done
3 | PLC | AP74 TO AP75 | 132KV S/C | 132KV | Submitted(03/04/2026) | Done
4 | PLC | AP80 TO AP81 | 132KV S/C ON H POLE | 132KV | Subbmitted (20/01/2026) | Done
5 | PLC | AP86 TO AP87 | 132KV S/C | 132KV | Subbmitted (20/01/2026) | Done
6 | PLC | AP100 TO AP101 | 132KV S/C | 132KV | Subbmitted (20/01/2026) | Done
7 | PLC | AP112 TO AP113 | 132KV S/C ON DC TOWER | 132KV | Submitted(10/11/2025) | Done
8 | PLC | AP114 TO AP115 | 132KV D/C LINE | 132KV | Submitted(10/11/2025) | Done
9 | PLC | AP119 TO AP120 | 220KV D/C LINE | 220KV | Submitted(10/11/2025) | Done
10 | PLC | AP128 TO AP129 | 765KV D/C LINE | 765KV | Submitted(03/04/2026) | Done
11 | PLC | AP131 TO AP132 | 220KV D/C LINE | 220KV | Submitted(10/11/2025) | Done
12 | PLC | AP139 TO AP140 | 132KV D/C LINE | 132KV | Submitted(09-04-2026) | Done
13 | NH | AP18 TO AP19 | N.H-56 |  | Subbmitted (20/01/2026)
14 | NH | AP105 TO AP106 | N.H-347B |  | Subbmitted (20/01/2026) | Done
15 | NH | AP118 TO AP119 | N.H-52 |  | Subbmitted (20/01/2026)
16 | NH | AP133 TO AP134 | N.H347C |  | Subbmitted (20/01/2026)
17 | Rlwy. | AP50 TO AP51 | Railway |  | 2026-05-12 |  | 2026-05-12
18 | Rlwy. | 111A TO 111B | Railway |  | Proposed Railway |  | OHE NO-168/16 & OHE NO- 168/17
19 | Gas Pipe Line | AP117 TO AP118 | Pipe Line |  | 2026-05-16 |  | 2026-05-16
20 | River | AP96 TO AP97 | NARMADA RIVER |  | Submitted(04-04-2026) |  | 15/02/26

## Supply Status (hidden)
KEC International Limited
Package TL-06 for ±800kV HVDC Bipole Line (Hexa Lapwing) between KPS2 (HVDC) & Nagpur (HVDC) (with dedicated metallic Return) -Part- 6 Transmission Line
SUPPLY STATUS
2026-05-30 20:29
SL NO | DESCRIPTION | UNIT | Total LOA Qty. | Cumulative Qty. as per Check Survey | Cumulative Released for Supply (PR) | Unit | RECEIVED Qty. |  | TOTAL RECEIVED | Total Received | Issued From Store | Consumed | Balance at Store | Balance Req. from Plant | Remarks
[7 empty] | HT | MS
STUBS
A | A-TYPE
1 | A TYPE NORMAL STUB | Sets | 313 | 313 | 250 | Set | 2272.944 |  | 180 |  | 115 | 112 | 65 | 70
B | B-TYPE
1 | B TYPE NORMAL STUB(Up to +9 M Extension) | Sets | 64 | 38 | 26 | Set |  |  | 26 |  | 1 | 0 | 25 | 0
C | C-TYPE
1 | C TYPE NORMAL STUB | Sets | 60 | 31 | 19 | Set |  |  | 19 |  | 0 | 0 | 19 | 0
D | D-TYPE
1 | DD45 (Up to +9 M Extension) | Sets | 26 |  | 13 | Set |  |  | 0 |  | 0 | 0 | 0 | 13
2 | DD 45 (+18 to 25 Extension) | Sets | 3
3 | DD60 (Up to +9 M Extension) | Sets | 19 |  | 4 | Set
4 | DD60 (+18 to 25 Extension) | Sets | 3
5 | DD60 (Up to +30 M Extension) | Sets | 3
6 | DD60 (+55 Extension) | Sets | 3
| Total |  | 494
TOWER PARTS
A | A TYPE
1 | BASIC BODY | Nos. | 203 |  |  | Set |  |  | 152 |  | 20
2 | -3M EXTENSION ONLY | Nos.
3 | 0M EXTENSION ONLY | Nos. | 103 |  |  | Set |  |  | 80 |  | 9
4 | +3M EXTENSION ONLY | Nos. | 65 |  |  | Set |  |  | 40 |  | 10
5 | +6M EXTENSION ONLY | Nos. | 23 |  |  | Set |  |  | 20 |  | 4
6 | +9M EXTENSION ONLY | Nos. | 12 |  |  | Set |  |  | 12 |  | 0
7 | Plan at 0M Level | Nos.
8 | ADD. 0 M Extention | Nos.
B | B - TYPE
1 | BASIC BODY | Nos. | 64 |  | 29 | Set
2 | -3M EXTENSION ONLY | Nos.
2 | +0M EXTENSION ONLY | Nos. | 21 |  | 15 | Set
3 | +3M EXTENSION ONLY | Nos. | 11 |  | 8 | Set
4 | +6M EXTENSION ONLY | Nos. | 5 |  | 1 | Set
6 | PLAN+6M EXTENSION ONLY | Nos.
5 | +9M EXTENSION ONLY | Nos. | 27 |  | 5 | Set
8 | Plan at 0M Level | Nos.
9 | +18 EXTENSION ONLY | Nos.
10 | +25 EXTENSION ONLY | Nos.
11 | +12 M BODY ONLY | Nos.
12 | +12 M PLAN EXTENTION ONLY | Nos.
C | C - TYPE
1 | BASIC BODY | Nos. | 60 |  | 22
2 | -3M EXTENSION ONLY | Nos.
3 | +0M EXTENSION ONLY | Nos. | 33 |  | 10 | Set
4 | +3M EXTENSION ONLY | Nos. | 10 |  | 5 | Set
5 | +6M EXTENSION ONLY | Nos. | 4 |  | 2 | Set
6 | +9M EXTENSION ONLY | Nos. | 13 |  | 5 | Set
7 | Plan at 0M Level | Nos.
8 | +12M EXTENSION ONLY | Nos.
D1 | D1 - TYPE
1 | BASIC BODY | Nos. | 29
2 | 0M Extension Only | Nos. | 18 |  | 4 | Set
3 | +3M Extension Only | Nos. | 4
4 | +6M Extension Only | Nos. | 0
5 | +9M Extension Only | Nos. | 4
7 | +18M Extension Only | Nos. | 3
8 | +18M Extension Only | Nos.
9 | +25M Extension Only | Nos.
10 | +35M Extension Only | Nos.
D2 | D2 - TYPE
1 | BASIC BODY | Nos. | 28
2 | 0M Extension Only | Nos. | 8 |  | 1 | Set
3 | +3M Extension Only | Nos. | 4
4 | +6M Extension Only | Nos. | 2
5 | +9M Extension Only | Nos. | 5
6 | +18M Extension Only | Nos. | 3
7 | +30M Extension Only | Nos. | 3
8 | +55M Extension Only | Nos. | 3
9 | +35M Extension Only | Nos.
| Total |  | 565 |  | 56 | Set
Earthing
E) | EARTHING
1 | Pipe Type Earthing | No. |  | 478 |  | Set |  |  | 100
2 | ROD Type Earthing | No. |  | 478 |  | Set |  |  | 100
3 | Counter Poise | No. |  | 478 |  | Set |  |  | 165
LINE MATERIALS
F) | LINE MATERIAL
1 | Earthwire | Km |  |  | 1212 |  |  |  | 51.715 | 135.556
2 | 120 KN Disc Insulator (23 No.= 1set) | Set | [7 empty] | 2657
3 | 160 KN Disc Insulator (23 No.= 1set) | Set | [7 empty] | 4144
2 | ACSR MOOSE CONDUCTOR | Km | [6 empty] | 1068.317 | 1740.733
G) | HTLS Conductor Accessories
1 | Single Suspension I String- TWIN ACSS | Set | [7 empty] | 1916
2 | Double Tension String- TWIN ACSS | Set | [7 empty] | 1664
3 | Suspension Clamp for - SSI | Set | [7 empty] | 3272
4 | Dead end. Clamp | No. | [7 empty] | 3144
5 | MSCJ- ACSS Conductor | No. | [7 empty] | 1060
6 | Repair Sleeve for ACSS conductor | No. | [7 empty] | 356
7 | Rigid Spacer | No. | [7 empty] | 2508
8 | Twin Spacer Damper | No. | [7 empty] | 3500
9 | Suspension Clamp for - SSIP | No. | [7 empty] | 192
H) | E/W Accessories
1 | Susp. Clamp for E/W | No. | [7 empty] | 142
2 | Tension. Clamp for E/W | No. | [7 empty] | 140
3 | Vibration Damper for E/W | No. | [7 empty] | 580
4 | MSCJ for E/W | No. | [7 empty] | 46
5 | Flexible Alu Bond for E/W | No. | [7 empty] | 282
I) | OPGW & ACCESSORIES
1 | OPGW cable | Km | [7 empty] | 127.831
2 | Suspension Clamp Assembly | Set | [7 empty] | 219
3 | Temsion fitting assembly for joint box | Set | [7 empty] | 8
4 | Temsion fitting assembly for Pass Through | Set | [7 empty] | 77
5 | Temsion fitting assembly on suspension tower | Set | [7 empty] | 20
6 | Vibration Damper | No. | [7 empty] | 1414
7 | Downlead Clamp | No. | [7 empty] | 1450