## DPR_TA-506
LINE NAME- : 400 KV D/C Sirohi - Chittorgarh TL
CLIENT-POWERGRID SIROHI TRANSMISSION LIMITED (POWER GRID CORPORATION OF INDIA)
DAILY PROGRESS REPORT (TA-506)
NOA Date :- 23-July-2024 |  |  |  | Completion Date :- 22-June-2026 |  |  |  |  | Date :- 20 Apr 2026.
SUPPLY VALUE = 477.03 Cr. |  |  |  | SERVICE VALUE = 105.43 Cr. |  |  |  |  | F&I VALUE = 11.45 Cr.
PARTICULARS | UOM | Total | Comp | Balance | 2026-04-01 |  | WIP | Cumulative | 2026-05-01 | 2026-06-01 | Remarks
|  | Qty | Till | as on | Plan | Actual |  |  | Plan | Plan
|  |  | 2026-03-01 | 1 Apr'26
Detail Survey | KM | 223 | 223 | 0 |  |  |  | 223
Check Survey | KM | 223 | 223 | 0 |  |  |  | 223
Stub Supply | SET | 602 | 515 | 87 |  |  |  | 515
FOUNDATION | NOS | 602 | 465 | 137 | 27 | 10 | 13 | 475
No of Gangs | [6 empty] | 11
Tower Supply | SETS | 602 | 485 | 117 |  |  |  | 485
TOWER ERECTION | NOS | 602 | 396 | 206 | 34 | 4 |  | 400
No of Gangs | [6 empty] | 2
AL-59 Zebra Conductor | KM | 5402 | 5092 | 310 |  |  |  | 5092
G S Earthwire 7/3.66mm size | KM | 225 | 158 | 67 |  |  |  | 158
Insulator Supply | EA | 18168 | 15288 | 2880 |  |  |  | 15288
Hardware Fittings Supply | % | 100% | 85% | 15% |  |  |  | 85%
Stringing | KM | 223 | 29.359 | 193.641 | 27 | 14.21 | 6 | 43.569
TSE - Section | No | 71 | 12 | 59 |  | 6 |  | 18
Manual - Section | No | 231 | 3 | 228 |  | 3 |  | 6
No of Gangs | [6 empty] | 4 | 4
OPGW Stringing | KM | 231
No of Gangs

## Erection compiled
KEC International Limited
TA506 : 400 KV D/C Sirohi - Chittorgarh TL
Details of Erection | [6 empty] | 6686.8523 | 898.2449 |  | 2026-04-20 | Tack Welding
CUMM. SR.NO | MONTH SR.NO. | Location No | Type of Tower | Starting Date | Completion date | Gang name | Tower Weight | Revenue | Name of Supervisor | Status
105 |  | 137/2 | DA+0 | 2025-08-27 | 2025-09-01 | TEJAL | 16.9667 | 2.2791 | Sahadeb Gope | Completed
106 |  | 13/2 | DA+9 | 2025-09-01 | 2025-09-05 | Shri Karni Construction | 16.9667 | 2.2791 | Anil Kumar | Completed
107 |  | 33/0 | DC1+6 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 37.2057 | 4.9978 | Anil Kumar | Completed
108 |  | 183/4 | DA+9 | 2025-08-31 | 2025-09-04 | PANKAJ -1 | 16.9667 | 2.2791 | Bhola Karmakar | Completed
109 |  | 25/0 | DB2+6 | 2025-08-27 | 2025-09-05 | Shri Karni Construction | 34.1664 | 4.5896 | Anil Kumar | Completed
110 |  | 223/0 | DC2+6 | 2025-09-02 | 2025-09-12 | Govind Mahto | 37.2057 | 4.9978 | Bhola Karmakar | Completed
111 |  | 163/2 | DA+3 | 2025-09-07 | 2025-09-11 | VINOD | 18.1188 | 2.4339 | Bhola Karmakar | Completed
112 |  | 68/0 | DC2+6 | 2025-09-01 | 2025-09-10 | MOHAN MAHTO | 37.2057 | 4.9978 | Bipattaran Dolui | Completed
113 |  | 76A/1 | DB1+6 | 2025-09-09 | 2025-09-17 | JAY PRAKASH | 34.1664 | 4.5896 | Bipattaran Dolui | Completed
114 |  | 141/0 | DC2+3 | 2025-09-03 | 2025-09-12 | TEJAL | 31.8647 | 4.2804 | Sahadeb Gope | Completed
115 |  | 18/7 | DA+6 | 2025-09-04 | 2025-09-08 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
116 |  | 22/0 | DC1+9 | 2025-09-02 | 2025-09-12 | Shri Karni Construction | 42.6134 | 5.7243 | Anil Kumar | Completed
117 |  | 13/3 | DA+3 | 2025-09-07 | 2025-09-11 | shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
118 |  | 2/4 | DA+3 | 2025-09-06 | 2025-09-11 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
119 |  | 5/3 | DA+3 | 2025-09-10 | 2025-09-15 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
120 |  | 218/0 | DD45+3 | 2025-09-06 | 2025-09-15 | PANKAJ-2 | 38.1379 | 5.1231 | Bhola Karmakar | Completed
121 |  | 6/0 | DB1+0 | 2025-09-06 | 2025-09-11 | FATIMA -1 | 27.0921 | 3.6393 | Bipattaran Dolui | Completed
122 |  | 2A/0 | DB2+0 | 2025-09-02 | 2025-09-08 | Radhika Enterprises | 27.0921 | 3.6393 | Bipattaran Dolui | Completed
123 |  | 12/0 | DC1+6 | 2025-08-31 | 2025-09-09 | Shri Karni Construction | 37.2057 | 4.9978 | Anil Kumar | Completed
124 |  | 184/0 | DC1+9 | 2025-09-04 | 2025-09-11 | Pankaj-1 | 42.6134 | 5.7243 | Sahadeb Gope | Completed
125 |  | 18/8 | DA+3 | 2025-09-09 | 2025-09-13 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
126 |  | 12/3 | DA+0 | 2025-09-16 | 2025-09-20 | Shri Karni Construction | 16.9667 | 2.2791 | Anil Kumar | Completed
127 |  | 10/1 | DA+6 | 2025-09-16 | 2025-09-20 | FATIMA | 21.0969 | 2.8339 | Bipattaran Dolui | Completed
128 |  | 11/1 | DA+0 | 2025-09-11 | 2025-09-15 | Shri Karni Construction | 16.9667 | 2.2791 | Anil Kumar | Completed
129 |  | 27/0 | DD45+9 | 2025-09-08 | 2025-09-20 | MOHAN MAHTO | 48.342 | 6.4938 | Bipattaran Dolui | Completed
130 |  | 2/3 | DA+6 | 2025-09-14 | 2025-09-18 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
131 |  | 26/1 | DA+0 | 2025-09-15 | 2025-09-18 | Shri Karni Construction | 16.9667 | 2.2791 | Anil Kumar | Completed
132 |  | 72/2 | DA+9 | 2025-09-13 | 2025-09-17 | MOHAN MAHTO | 22.4884 | 3.0209 | Bipattaran Dolui | Completed
133 |  | 100/2 | DA+0 | 2025-09-18 | 2025-09-22 | A B const.(Birendra Panday) | 16.9667 | 2.2791 | Sahadeb Gope | Completed
134 |  | 141/1 | DA+0 | 2025-09-12 | 2025-09-18 | TEJAL | 16.9667 | 2.2791 | Bhola Karmakar | Completed
135 |  | 166/0 | DC1+9 | 2025-09-14 | 2025-09-25 | VINOD | 42.6134 | 5.7243 | Bhola Karmakar | Completed
136 |  | 186/0 | DD60+0 | 2025-09-10 | 2025-09-24 | Pankaj-1 | 39.5967 | 5.319 | Bhola Karmakar | Completed
137 |  | 191/0 | DB1+0 | 2025-09-10 | 2025-09-14 | Horil | 27.0921 | 3.6393 | Anil Kumar | Completed
138 |  | 220/1 | DA+3 | 2025-09-16 | 2025-09-18 | KHEMLAL | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
139 |  | 220/4 | DA+9 | 2025-09-16 | 2025-09-21 | Govind Mahto | 22.4884 | 3.0209 | Anil Kumar | Completed
140 |  | 194/0 | DC1+3 | 2025-09-14 | 2025-09-19 | Horil | 31.8647 | 4.2804 | Bipattaran Dolui | Completed
141 |  | 214/0 | DC2+0 | 2025-09-14 | 2025-09-27 | PANKAJ-2 | 29.7779 | 4.0001 | Anil Kumar | Completed
142 |  | 2/2 | DA+6 | 2025-09-19 | 2025-09-24 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
143 |  | 6/1 | DA+6 | 2025-09-15 | 2025-09-20 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
144 |  | 10/2 | DA+6 | 2025-09-26 | 2025-09-30 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
145 |  | 19/0 | DB2+0 | 2025-09-15 | 2025-09-21 | Shri Karni Construction | 27.0921 | 3.6393 | Anil Kumar | Completed
146 |  | 60/2 | DA+3 | 2025-09-18 | 2025-09-22 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
147 |  | 11/2 | DA+3 | 2025-09-22 | 2025-09-25 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
148 |  | 79/0 | DD45+0 | 2025-09-20 | 2025-09-25 | JAY PRAKASH | 35.8452 | 4.8151 | Bipattaran Dolui | Completed
149 |  | 212/5 | DA+6 | 2025-09-17 | 2025-09-22 | KHEMLAL | 21.0969 | 2.8339 | Bhola Karmakar | Completed
150 |  | 35A/1 | DA+6 | 2025-09-23 | 2025-09-26 | Shri Karni Construction | 21.0969 | 2.8339 | Bipattaran Dolui | Completed
151 |  | 142/1 | DA+0 | 2025-09-27 | 2025-09-29 | TEJAL | 16.9667 | 2.2791 | Sahadeb Gope | Completed
152 |  | 187A/1 | DA+6 | 2025-09-20 | 2025-09-23 | Horil | 21.0969 | 2.8339 | Bhola Karmakar | Completed
153 |  | 66/1 | DA+3 | 2025-09-18 | 2025-09-21 | MOHAN MAHTO | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
154 |  | 6/2 | DA+9 | 2025-09-22 | 2025-09-26 | Shri Karni Construction | 22.4884 | 3.0209 | Bipattaran Dolui | Completed
155 |  | 2/1 | DA+6 | 2025-09-26 | 2025-09-29 | Shri Karni Construction | 21.0969 | 2.8339 | Bipattaran Dolui | Completed
156 |  | 2/5 | DA-3 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 2.1302 | Anil Kumar | Completed
157 |  | 5/10 | DA+3 | 2025-09-24 | 2025-09-27 | Shri Karni Construction | 18.1188 | 2.4339 | Anil Kumar | Completed
158 |  | 5/9 | DA+9 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 22.4884 | 3.0209 | Anil Kumar | Completed
159 |  | 11/3 | DB1+9 | 2025-09-24 | 2025-09-30 | Shri Karni Construction | 36.5854 | 4.9145 | Anil Kumar | Completed
160 |  | 19/1 | DA+9 | 2025-09-15 | 2025-09-18 | shri Karni Construction | 22.4884 | 3.0209 | Anil Kumar | Completed
161 |  | 18/5 | DA-3 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 15.8578 | 2.1302 | Anil Kumar | Completed
162 |  | 18/6 | DA+6 | 2025-09-25 | 2025-09-28 | Shri Karni Construction | 21.0969 | 2.8339 | Anil Kumar | Completed
163 |  | 60/3 | DA-1.5 | 2025-09-24 | 2025-09-26 | Shri Karni Construction | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
164 |  | 61/1 | DA+3 | 2025-09-27 | 2025-09-30 | Shri Karni Construction | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
165 |  | 66/0 | DC1+0 | 2025-09-25 | 2025-09-30 | JAY PRAKASH | 29.7779 | 4.0001 | Bipattaran Dolui | Completed
166 |  | 187/2 | DA+6 | 2025-09-24 | 2025-09-27 | Horil | 21.0969 | 2.8339 | Bhola Karmakar | Completed
167 |  | 194/2 | DA+6 | 2025-09-27 | 2025-09-30 | Horil | 21.0969 | 2.8339 | Bhola Karmakar | Completed
168 |  | 210/10 | DA+3 | 2025-09-27 | 2025-09-30 | Pankaj-1 | 18.1188 | 2.4339 | Bhola Karmakar | Completed
169 |  | 212/4 | DA+9 | 2025-09-23 | 2025-09-27 | KHEMLAL | 22.4884 | 3.0209 | Bhola Karmakar | Completed
170 |  | 212/3 | DA+6 | 2025-09-27 | 2025-09-30 | KHEMLAL | 21.0969 | 2.8339 | Bhola Karmakar | Completed
171 |  | 220/2 | DA-1.5 | 2025-09-24 | 2025-09-27 | Govind Mahto | 16.4524 | 2.2101 | Bhola Karmakar | Completed
172 |  | 19/2 | DA-3 | 2025-09-28 | 2025-09-30 | Shri Karni Construction | 15.8578 | 2.1302 | Anil Kumar | Completed
173 |  | 10/2 | DA+6 | 2025-09-23 | 2025-10-01 | Karni Const. 5 | 21.0969 | 2.8339 | Anil Kumar | Completed
174 |  | 61/1 | DA+3 | 2025-09-27 | 2025-10-01 | Karni Const. 6 | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
175 |  | 11/3 | DB1+9 | 2025-09-25 | 2025-10-02 | Karni Const. 3 | 36.5854 | 4.9145 | Anil Kumar | Completed
176 |  | 66/0 | DC1+0 | 2025-09-22 | 2025-10-02 | Jai Prakash Mahto | 29.7779 | 4.0001 | Bipattaran Dolui | Completed
177 |  | 2/5 | DA-3 | 2025-10-01 | 2025-10-03 | Karni Const. 1 | 15.8578 | 2.1302 | Anil Kumar | Completed
178 |  | 5/9 | DA+3 | 2025-10-01 | 2025-10-03 | Karni Const. 2 | 18.1188 | 2.4339 | Anil Kumar | Completed
179 |  | 19/2 | DA-3 | 2025-09-30 | 2025-10-03 | Karni Const. 4 | 15.8578 | 2.1302 | Anil Kumar | Completed
180 |  | 101/0 | DD45+9 | 2025-09-26 | 2025-10-03 | AB Const. | 48.342 | 6.4938 | Sahadeb Gope | Completed
181 |  | 140/2 | DA+3 | 2025-09-29 | 2025-10-03 | Tejal Const. | 18.1188 | 2.4339 | Sahadeb Gope | Completed
182 |  | 194/2 | DA+6 | 2025-09-29 | 2025-10-03 | Horil Mahto | 21.0969 | 2.8339 | Bhola Karmakar | Completed
183 |  | 206/1 | DA+0 | 2025-09-27 | 2025-10-03 | Pankaj Const. | 16.9667 | 2.2791 | Bhola Karmakar | Completed
184 |  | 220/1 | DA+3 | 2025-09-28 | 2025-10-03 | Govind Mahto | 18.1188 | 2.4339 | Bhola Karmakar | Completed
185 |  | 51A/2 | DA-1.5 | 2025-10-01 | 2025-10-06 | Karni Const. 6 | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
186 |  | 2/6 | DA+0 | 2025-10-04 | 2025-10-07 | Karni Const. 1 | 16.9667 | 2.2791 | Anil Kumar | Completed
187 |  | 5/11 | DA+3 | 2025-10-04 | 2025-10-07 | Karni Const. 2 | 18.1188 | 2.4339 | Anil Kumar | Completed
188 |  | 19/3 | DA+6 | 2025-10-02 | 2025-10-08 | Karni Const. 4 | 21.0969 | 2.8339 | Anil Kumar | Completed
189 |  | 67/0 | DC1+6 | 2025-10-02 | 2025-10-09 | Jai Prakash Mahto | 37.2057 | 4.9978 | Bipattaran Dolui | Completed
190 |  | 164/0 | DD45+0 | 2025-09-28 | 2025-10-09 | Binod Mahto | 35.8452 | 4.8151 | Sahadeb Gope | Completed
191 |  | 13/1 | DA+9 | 2025-10-05 | 2025-10-10 | Karni Const. 3 | 22.4884 | 3.0209 | Anil Kumar | Completed
192 |  | 51A/1 | DA-1.5 | 2025-10-07 | 2025-10-10 | Karni Const. 6 | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
193 |  | 213/5 | DA+3 | 2025-10-05 | 2025-10-10 | Khemlal Mahto | 18.1188 | 2.4339 | Bhola Karmakar | Completed
194 |  | 224/0 | DD45+3 | 2025-10-04 | 2025-10-10 | Govind Mahto | 38.1379 | 5.1231 | Bhola Karmakar | Completed
195 |  | 19/4 | DA-3 | 2025-10-07 | 2025-10-12 | Karni Const. 4 | 15.8578 | 2.1302 | Anil Kumar | Completed
196 |  | 187/0 | DC2+6 | 2025-10-02 | 2025-10-11 | Horil Mahto | 37.2057 | 4.9978 | Bhola Karmakar | Completed
197 |  | 206/0 | DC2+0 | 2025-10-03 | 2025-10-11 | Pankaj Const. | 29.7779 | 4.0001 | Bhola Karmakar | Completed
198 |  | 2/8 | DA-3 | 2025-10-10 | 2025-10-14 | Karni Const. 1 | 15.8578 | 2.1302 | Anil Kumar | Completed
199 |  | 12/5 | DA-3 | 2025-10-10 | 2025-10-14 | Karni Const. 3 | 15.8578 | 2.1302 | Anil Kumar | Completed
200 |  | 51C/2 | DA-1.5 | 2025-10-11 | 2025-10-14 | Karni Const. 6 | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
201 |  | 142/0 | DC2+0 | 2025-10-08 | 2025-10-14 | Tejal Const. | 29.7779 | 4.0001 | Sahadeb Gope | Completed
202 |  | 193/2 | DA+9 | 2025-10-09 | 2025-10-14 | Horil Mahto | 22.4884 | 3.0209 | Bhola Karmakar | Completed
203 |  | 19/5 | DA+6 | 2025-10-08 | 2025-10-15 | Karni Const. 4 | 21.0969 | 2.8339 | Anil Kumar | Completed
204 |  | 13/0 | DB2+0 | 2025-10-10 | 2025-10-15 | Karni Const. 5 | 27.0921 | 3.6393 | Anil Kumar | Completed
205 |  | 205/1 | DA+6 | 2025-10-11 | 2025-10-15 | Pankaj Const. | 21.0969 | 2.8339 | Bhola Karmakar | Completed
206 |  | 2/7 | DA-3 | 2025-10-12 | 2025-10-16 | Karni Const. 1 | 15.8578 | 2.1302 | Anil Kumar | Completed
207 |  | 65A/0 | DB2+6 | 2025-10-10 | 2025-10-16 | Jai Prakash Mahto | 34.17 | 4.5901 | Bipattaran Dolui | Completed
208 |  | 213/0 | DD45+0 | 2025-10-11 | 2025-10-16 | Pankaj Const. | 36.85 | 4.9501 | Bhola Karmakar | Completed
209 |  | 9/0 | DD45+9 | 2025-10-12 | 2025-10-17 | Karni Const. 2 | 48.342 | 6.4938 | Anil Kumar | Completed
210 |  | 12/6 | DA+0 | 2025-10-14 | 2025-10-17 | Karni Const. 3 | 16.9667 | 2.2791 | Anil Kumar | Completed
211 |  | 220/7 | DA+9 | 2025-10-13 | 2025-10-17 | Govind Mahto | 22.4884 | 3.0209 | Bhola Karmakar | Completed
212 |  | 1/1 | DA+3 | 2025-10-16 | 2025-10-18 | Gulab Mahto | 18.1188 | 2.4339 | Anil Kumar | Completed
213 |  | 1/2 | DA+3 | 2025-10-19 | 2025-10-21 | Gulab Mahto | 18.1188 | 2.4339 | Anil Kumar | Completed
214 |  | 12/7 | DA+0 | 2025-10-18 | 2025-10-21 | Karni Const. 3 | 16.9667 | 2.2791 | Bipattaran Dolui | Completed
215 |  | 51C/0 | DB2+0 | 2025-10-16 | 2025-10-21 | Karni Const. 5 | 27.0921 | 3.6393 | Bipattaran Dolui | Completed
216 |  | 211/7 | DA+9 | 2025-10-17 | 2025-10-22 | Khemlal Mahto | 22.4884 | 3.0209 | Bhola Karmakar | Completed
217 |  | 220/6 | DA+6 | 2025-10-19 | 2025-10-22 | Govind Mahto | 21.0969 | 2.8339 | Bhola Karmakar | Completed
218 |  | 193/1 | DA+3 | 2025-10-18 | 2025-10-24 | Horil Mahto | 18.1188 | 2.4339 | Bhola Karmakar | Completed
219 |  | 205/2 | DA+3 | 2025-10-21 | 2025-10-24 | Horil Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
220 |  | 42/0 | DD45+6 | 2025-10-18 | 2025-10-24 | Karni Const. 4 | 46.4686 | 6.2421 | Anil Kumar | Completed
221 |  | 205/0 | DC1+3 | 2025-10-13 | 2025-10-20 | Horil Mahto | 31.8647 | 4.2804 | Mrityunjay Thakur | Completed
222 |  | 202/2 | DA+3 | 2025-10-08 | 2025-10-12 | Horil Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
223 |  | 1/3 | DA+0 | 2025-10-22 | 2025-10-25 | Gulab Mahto | 16.9667 | 2.2791 | Anil Kumar | Completed
224 |  | 101/1 | DA+6 | 2025-10-19 | 2025-10-26 | AB Const. | 21.0969 | 2.8339 | Sahadeb Gope | Completed
225 |  | 10/0 | DD45+9 | 2025-10-20 | 2025-10-28 | Karni Const. 2 | 48.342 | 6.4938 | Anil Kumar | Completed
226 |  | 53/0 | DB2+9 | 2025-10-19 | 2025-10-28 | Karni Const. 5 | 36.5854 | 4.9145 | Bipattaran Dolui | Completed
227 |  | 65/0 | DD60+9 | 2025-10-20 | 2025-10-27 | Jai Prakash Mahto | 53.1226 | 7.136 | Bipattaran Dolui | Completed
228 |  | 1/7 | DA+3 | 2025-10-26 | 2025-10-29 | Gulab Mahto | 18.1188 | 2.4339 | Anil Kumar | Completed
229 |  | 60/0 | DD60+0 | 2025-10-24 | 2025-10-29 | Prem Kumar | 39.5967 | 5.319 | Bipattaran Dolui | Completed
230 |  | 1/6 | DA+3 | 2025-10-28 | 2025-10-31 | Gulab Mahto | 18.1188 | 2.4339 | Anil Kumar | Completed
231 |  | 14/0 | DC1+9 | 2025-10-26 | 2025-10-31 | Karni Const. 3 | 39.6224 | 5.3225 | Bipattaran Dolui | Completed
232 |  | 97/1 | DA+1.5 | 2025-10-27 | 2025-10-31 | AB Const. | 17.6337 | 2.3687 | Sahadeb Gope | Completed
233 |  | 167/1 | DA+9 | 2025-10-27 | 2025-10-31 | Binod Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
234 |  | 64A/3 | DA+9 | 2025-10-26 | 2025-10-30 | Jai Prakash Mahto | 22.4884 | 3.0209 | Bipattaran Dolui | Completed
235 |  | 12/2 | DA+1.5 | 2025-10-28 | 2025-11-01 | Karni Const. 2 | 17.6337 | 2.3687 | Anil Kumar | Completed
236 |  | 42/2 | DA+0 | 2025-10-30 | 2025-11-01 | Karni Const. 4 | 16.9667 | 2.2791 | Anil Kumar | Completed
237 |  | 52/1 | DA-1.5 | 2025-10-29 | 2025-11-01 | Karni Const. 5 | 16.4524 | 2.2101 | Anil Kumar | Completed
238 |  | 65A/3 | DC1+0 | 2025-10-29 | 2025-11-01 | Jai Prakash Mahto | 29.7779 | 4.0001 | Bipattaran Dolui | Completed
239 |  | 220/5 | DA-1.5 | 2025-10-29 | 2025-11-01 | Govind Mahto | 16.4524 | 2.2101 | Sunil Kumar | Completed
240 |  | 1/8 | DA+1.5 | 2025-10-30 | 2025-11-02 | Gulab Mahto | 17.6337 | 2.3687 | Anil Kumar | Completed
241 |  | 197/2 | DA+3 | 2025-10-29 | 2025-11-02 | Horil Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
242 |  | 167A/0 | DD45+3 | 2025-10-29 | 2025-11-03 | Binod Mahto | 38.1379 | 5.1231 | Sahadeb Gope | Completed
243 |  | 220/8 | DA+3 | 2025-10-31 | 2025-11-03 | Govind Mahto | 18.1188 | 2.4339 | Sunil Kumar | Completed
244 |  | 12/8 | DA-3 | 2025-11-01 | 2025-11-04 | Karni Const. 1 | 15.8578 | 2.1302 | Anil Kumar | Completed
245 |  | 1/9 | DA+1.5 | 2025-11-01 | 2025-11-05 | Gulab Mahto | 17.6337 | 2.3687 | Anil Kumar | Completed
246 |  | 64A/2 | DA+0 | 2025-11-02 | 2025-11-05 | Jai Prakash Mahto | 16.9667 | 2.2791 | Bipattaran Dolui | Completed
247 |  | 95/0 | DC2+3 | 2025-11-02 | 2025-11-06 | Horil Mahto | 31.8647 | 4.2804 | Sahadeb Gope | Completed
248 |  | 110/0 | DC2+9 | 2025-11-02 | 2025-11-06 | Tejal Mahto | 39.6224 | 5.3225 | Sahadeb Gope | Completed
249 |  | 1/10 | DA+0 | 2025-11-05 | 2025-11-07 | Gulab Mahto | 16.9667 | 2.2791 | Anil Kumar | Completed
250 |  | 15/0 | DD45+3 | 2025-11-04 | 2025-11-08 | Karni Const. 3 | 38.1379 | 5.1231 | Anil Kumar | Completed
251 |  | 64A/1 | DA+6 | 2025-11-04 | 2025-11-09 | Jai Prakash Mahto | 21.0969 | 2.8339 | Bipattaran Dolui | Completed
252 |  | 76F/0 | DB1+9 | 2025-11-02 | 2025-11-09 | Khemlal Mahto | 36.5854 | 4.9145 | Bipattaran Dolui | Completed
253 |  | 94/1 | DA+9 | 2025-11-05 | 2025-11-08 | AB Const. | 22.4884 | 3.0209 | Sahadeb Gope | Completed
254 |  | 28/0 | DD45+9 | 2025-11-03 | 2025-11-10 | Karni Const. 2 | 48.342 | 6.4938 | Anil Kumar | Completed
255 |  | 2/0 | DB2+0 | 2025-11-07 | 2025-11-11 | Gulab Mahto | 27.0921 | 3.6393 | Anil Kumar | Completed
256 |  | 34/2 | DA+1.5 | 2025-11-08 | 2025-11-11 | Karni Const. 1 | 17.6337 | 2.3687 | Bipattaran Dolui | Completed
257 |  | 221/0 | DB2+9 | 2025-11-06 | 2025-11-11 | Govind Mahto | 36.5854 | 4.9145 | Sunil Kumar | Completed
258 |  | 37/0 | DD45+9 | 2025-11-05 | 2025-11-12 | Karni Const. 4 | 48.342 | 6.4938 | Bipattaran Dolui | Completed
259 |  | 95A/0 | DB1+9 | 2025-11-07 | 2025-11-12 | Horil Mahto | 36.5854 | 4.9145 | Sahadeb Gope | Completed
260 |  | 13/5 | DA+3 | 2025-11-10 | 2025-11-13 | Karni Const. 3 | 18.1188 | 2.4339 | Anil Kumar | Completed
261 |  | 16/0 | DB2+6 | 2025-11-09 | 2025-11-13 | Zainab Fatima | 34.17 | 4.5901 | Anil Kumar | Completed
262 |  | 55/0 | DC1+9 | 2025-11-07 | 2025-11-13 | Karni Const. 5 | 39.6224 | 5.3225 | Bipattaran Dolui | Completed
263 |  | 95/1 | DA+3 | 2025-11-09 | 2025-11-13 | AB Const. | 18.1188 | 2.4339 | Sahadeb Gope | Completed
264 |  | 76G/0 | DC1+3 | 2025-11-10 | 2025-11-15 | Khemlal Mahto | 31.8647 | 4.2804 | Bipattaran Dolui | Completed
265 |  | 94/2 | DA+9 | 2025-11-12 | 2025-11-15 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
266 |  | 62/0 | DD60+9 | 2025-11-10 | 2025-11-16 | Prem Kumar | 53.1226 | 7.136 | Bipattaran Dolui | Completed
267 |  | 111/0 | DC1+0 | 2025-11-12 | 2025-11-17 | Tejal Mahto | 29.7779 | 4.0001 | Sahadeb Gope | Completed
268 |  | 139/0 | DD60+9 | 2025-11-10 | 2025-11-17 | Binod Mahto | 53.1226 | 7.136 | Sahadeb Gope | Completed
269 |  | 44A/2 | DA+0 | 2025-11-15 | 2025-11-18 | Karni Const. 4 | 16.9667 | 2.2791 | Bipattaran Dolui | Completed
270 |  | 64/0 | DD60+0 | 2025-11-13 | 2025-11-18 | Jai Prakash Mahto | 39.5967 | 5.319 | Bipattaran Dolui | Completed
271 |  | 36/2 | DA+6 | 2025-11-16 | 2025-11-19 | Karni Const. 2 | 21.0969 | 2.8339 | Anil Kumar | Completed
272 |  | 78/0 | DC1+9 | 2025-11-14 | 2025-11-19 | Karni Const. 1 | 39.6224 | 5.3225 | Bipattaran Dolui | Completed
273 |  | 94/3 | DA+9 | 2025-11-15 | 2025-11-19 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
274 |  | 107/1 | DA+3 | 2025-11-16 | 2025-11-19 | AB Const. | 18.1188 | 2.4339 | Sahadeb Gope | Completed
275 |  | 76G/1 | DA+3 | 2025-11-18 | 2025-11-20 | Khemlal Mahto | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
276 |  | 56/0 | DB1+9 | 2025-11-17 | 2025-11-22 | Karni Const. 6 | 36.5854 | 4.9145 | Bipattaran Dolui | Completed
277 |  | 64/1 | DA-3 | 2025-11-19 | 2025-11-22 | Jai Prakash Mahto | 15.8578 | 2.1302 | Bipattaran Dolui | Completed
278 |  | 211/4 | DA+6 | 2025-11-19 | 2025-11-22 | Pankaj | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
279 |  | 17/1 | DA+0 | 2025-11-20 | 2025-11-23 | Karni Const. 1 | 16.9667 | 2.2791 | Anil Kumar | Completed
280 |  | 26/0 | DD45+0 | 2025-11-18 | 2025-11-23 | Karni Const. 3 | 35.8452 | 4.8151 | Anil Kumar | Completed
281 |  | 210/9 | DA+6 | 2025-11-19 | 2025-11-23 | Govind Mahto | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
282 |  | 77/0 | DB1+0 | 2025-11-20 | 2025-11-25 | Khemlal Mahto | 27.0921 | 3.6393 | Bipattaran Dolui | Completed
283 |  | 94/0 | DD45+6 | 2025-11-20 | 2025-11-25 | Horil Mahto | 46.4686 | 6.2421 | Sahadeb Gope | Completed
284 |  | 65A/2 | DA+0 | 2025-11-24 | 2025-11-27 | Jai Prakash Mahto | 16.9667 | 2.2791 | Bipattaran Dolui | Completed
285 |  | 135/2 | DB1+0 | 2025-11-22 | 2025-11-27 | Binod Mahto | 27.0921 | 3.6393 | Sahadeb Gope | Completed
286 |  | 211/5 | DA+6 | 2025-11-23 | 2025-11-27 | Pankaj | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
287 |  | 36/1 | DA+9 | 2025-11-25 | 2025-11-28 | Karni Const. 2 | 22.4884 | 3.0209 | Anil Kumar | Completed
288 |  | 44A/0 | DC2+3 | 2025-11-21 | 2025-11-28 | Karni Const. 4 | 31.8647 | 4.2804 | Bipattaran Dolui | Completed
289 |  | 60/1 | DA+3 | 2025-11-25 | 2025-11-28 | Karni Const. 6 | 18.1188 | 2.4339 | Bipattaran Dolui | Completed
290 |  | 25/2 | DA+1.5 | 2025-11-26 | 2025-11-29 | Karni Const. 3 | 17.6337 | 2.3687 | Anil Kumar | Completed
291 |  | 44A/1 | DA-1.5 | 2025-11-26 | 2025-11-30 | Karni Const. 5 | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
292 |  | 114/1 | DB1+6 | 2025-11-25 | 2025-11-30 | AB Const. | 34.17 | 4.5901 | Sahadeb Gope | Completed
293 |  | 2A/1 | DA-3 | 2025-11-27 | 2025-12-01 | Karni Const. 2 | 15.8578 | 2.1302 | Anil Kumar | Completed
294 |  | 45/0 | DD45+0 | 2025-11-22 | 2025-12-01 | Karni Const. 5 | 35.8452 | 4.8151 | Bipattaran Dolui | Completed
295 |  | 63/0 | DD60+9 | 2025-11-24 | 2025-12-01 | Prem Kumar | 53.1226 | 7.136 | Bipattaran Dolui | Completed
296 |  | 211/6 | DA+6 | 2025-11-26 | 2025-12-01 | Govind Mahto | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
297 |  | 11/0 | DD45+0 | 2025-11-28 | 2025-12-02 | Karni Const. 1 | 35.8452 | 4.8151 | Anil Kumar | Completed
298 |  | 65A/1 | DA-1.5 | 2025-11-30 | 2025-12-02 | Jai Prakash Mahto | 16.4524 | 2.2101 | Bipattaran Dolui | Completed
299 |  | 76A/0 | DC1+3 | 2025-11-29 | 2025-12-03 | Khemlal Mahto | 31.8647 | 4.2804 | Bipattaran Dolui | Completed
300 |  | 212/0 | DB2+3 | 2025-11-29 | 2025-12-03 | Pankaj | 28.3681 | 3.8107 | Mrityunjay Thakur | Completed
301 |  | 128/0 | DB1+6 | 2025-11-30 | 2025-12-04 | Tejal Mahto | 34.17 | 4.5901 | Sahadeb Gope | Completed
302 |  | 113/0 | DB2+9 | 2025-11-30 | 2025-12-05 | Horil Mahto | 36.5854 | 4.9145 | Sahadeb Gope | Completed
303 |  | 211/1 | DA+0 | 2025-12-02 | 2025-12-05 | Khemlal Mahto | 16.9667 | 2.2791 | Mrityunjay Thakur | Completed
304 |  | 47/1 | DB1+9 | 2025-11-28 | 2025-12-06 | Karni Const. 4 | 36.5854 | 4.9145 | Bipattaran Dolui | Completed
305 |  | 135/1 | DA+9 | 2025-12-04 | 2025-12-07 | Binod Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
306 |  | 210/5 | DA+6 | 2025-12-04 | 2025-12-07 | Pankaj | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
307 |  | 4/1 | DA+3 | 2025-12-05 | 2025-12-09 | Karni Const. 2 | 18.1188 | 2.4339 | Anil Kumar | Completed
308 |  | 172/1 | DA-1.5 | 2025-12-05 | 2025-12-09 | Alo Reeva | 16.4524 | 2.2101 | Sahadeb Gope | Completed
309 |  | 30/0 | DD60+3 | 2025-12-01 | 2025-12-10 | Karni Const. 3 | 41.8329 | 5.6194 | Anil Kumar | Completed
310 |  | 210/3 | DA+3 | 2025-12-06 | 2025-12-10 | Tejal Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
311 |  | 1/0 | DD60+0 | 2025-12-02 | 2025-12-11 | Karni Const. 1 | 39.5967 | 5.319 | Anil Kumar | Completed
312 |  | 119/0 | DB2+9 | 2025-12-06 | 2025-12-11 | AB Const. | 36.5854 | 4.9145 | Sahadeb Gope | Completed
313 |  | 210/0 | DB1+0 | 2025-12-03 | 2025-12-12 | Pankaj | 27 | 3.6269 | Mrityunjay Thakur | Completed
314 |  | 46/0 | DD60+09 | 2025-12-08 | 2025-12-12 | Karni Const. 4 | 53 | 7.1195 | Bipattaran Dolui | Completed
315 |  | 68/1 | DB1+0 | 2025-12-08 | 2025-12-13 | Khemlal Mahto | 27.0921 | 3.6393 | Anil Kumar | Completed
316 |  | 227/2 | DD60+00 | 2025-12-03 | 2025-12-14 | Govind Mahto | 39.5967 | 5.319 | Mrityunjay Thakur | Completed
317 |  | 63/1 | DA+6 | 2025-12-10 | 2025-12-16 | Karni Const. 3 | 21.0969 | 2.8339 | Anil Kumar | Completed
318 |  | 18/0 | DD45+00 | 2025-12-03 | 2025-12-16 | Prem Kumar | 35.8452 | 4.8151 | Anil Kumar | Completed
319 |  | 212/1 | DA+6 | 2025-12-15 | 2025-12-17 | Pankaj | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
320 |  | 1/4 | DA-3 | 2025-12-11 | 2025-12-18 | Karni Const. 1 | 15.8578 | 2.1302 | Anil Kumar | Completed
321 |  | 166/2 | DA+6 | 2025-12-11 | 2025-12-20 | Pappu Kumar | 21.0969 | 2.8339 | Sahadeb Gope | Completed
322 |  | 218/1 | DA+3 | 2025-12-16 | 2025-12-21 | Govind Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
323 |  | 31/0 | DD45+6 | 2025-12-11 | 2025-12-22 | Karni Const. 2 | 46.4686 | 6.2421 | Anil Kumar | Completed
324 |  | 1/5 | DA+3 | 2025-12-12 | 2025-12-22 | Karni Const. 1 | 18.1188 | 2.4339 | Anil Kumar | Completed
325 |  | 215/0 | DB1+6 | 2025-12-18 | 2025-12-23 | Pankaj | 34.17 | 4.5901 | Mrityunjay Thakur | Completed
326 |  | 224/1 | DA+0 | 2025-12-23 | 2025-12-28 | Pankaj | 16.9667 | 2.2791 | Mrityunjay Thakur | Completed
327 |  | 64A/0 | DC1-3 | 2025-12-19 | 2025-12-29 | Prem Kumar | 27 | 3.6269 | Anil Kumar | Completed
328 |  | 167/2 | DA+9 | 2025-12-24 | 2025-12-30 | Binod Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
329 |  | 120/0 | DB1-3 | 2025-12-26 | 2025-12-30 | Khemlal Mahto | 24.7001 | 3.318 | Sahadeb Gope | Completed
330 |  | 74/0 | DB2+3 | 2025-12-26 | 2025-12-31 | Karni Const. 2 | 28.3681 | 3.8107 | Anil Kumar | Completed
331 |  | 139A/0 | DC2+9 | 2025-12-22 | 2025-12-31 | Jai Prakash Mahto | 39.6224 | 5.3225 | Sahadeb Gope | Completed
332 |  | 195/0 | DB1+0 | 2025-12-27 | 2026-01-01 | AB Const. | 27.0921 | 3.6393 | Mrityunjay Thakur | Completed
333 |  | 195/3 | DA+3 | 2025-12-28 | 2026-01-01 | AB Const 2 | 18.1188 | 2.4339 | Bhola Karmakar | Completed
334 |  | 182/0 | DD60+0 | 2025-12-26 | 2026-01-01 | Khemlal Mahto | 39.5967 | 5.319 | Mrityunjay Thakur | Completed
335 |  | 113A/0 | DB1+3 | 2025-12-28 | 2026-01-05 | Pankaj | 28.3681 | 3.8107 | Sahadeb Gope | Completed
336 |  | 172/2 | DA+0 | 2025-12-23 | 2026-01-05 | Khemlal Mahto | 16.9667 | 2.2791 | Sahadeb Gope | Completed
337 |  | 175/1 | DA+6 | 2026-01-06 | 2026-01-09 | Khemlal Mahto | 21.0969 | 2.8339 | Sahadeb Gope | Completed
338 |  | 140/1 | DA+6 | 2026-01-04 | 2026-01-09 | Jai Prakash Mahto | 21.0969 | 2.8339 | Sahadeb Gope | Completed
339 |  | 35A/0 | DB2-3 | 2026-01-03 | 2026-01-10 | Prem Kumar | 24.7001 | 3.318 | Anil Kumar | Completed
340 |  | 51B/0 | DB2-1.5 | 2026-01-05 | 2026-01-11 | Karni Const. 2 | 20.1799 | 2.7108 | Anil Kumar | Completed
341 |  | 114/0 | DC1+0 | 2026-01-07 | 2026-01-12 | Pankaj | 29.7779 | 4.0001 | Sahadeb Gope | Completed
342 |  | 156/1 | DB1+6 | 2025-12-28 | 2026-01-12 | AB Const. | 34.17 | 4.5901 | Sahadeb Gope | Completed
343 |  | 172/4 | DA-3 | 2026-01-11 | 2026-01-13 | Vishal Const. | 15.8578 | 2.1302 | Sahadeb Gope | Completed
344 |  | 147/2 | DA+9 | 2026-01-11 | 2026-01-15 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
345 |  | 166/1 | DB1+6 | 2026-01-09 | 2026-01-16 | Binod Mahto | 34.1665 | 4.5896 | Sahadeb Gope | Completed
346 |  | 140/0 | DC2-3 | 2026-01-13 | 2026-01-18 | Jai Prakash Mahto | 27.2521 | 3.6608 | Sahadeb Gope | Completed
347 |  | 147/1 | DA+9 | 2026-01-15 | 2026-01-18 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
348 |  | 156/2 | DB1-3 | 2026-01-14 | 2026-01-18 | AB Construction | 24.7001 | 3.318 | Sahadeb Gope | Completed
349 |  | 172/3 | DA+0 | 2026-01-15 | 2026-01-18 | Khemlal Mahto | 16.9667 | 2.2791 | Sahadeb Gope | Completed
350 |  | 193/0 | DB2+6 | 2026-01-12 | 2026-01-20 | Govind Mahto | 34.1665 | 4.5896 | Mrityunjay Thakur | Completed
351 |  | 137/1 | DA-3 | 2026-01-18 | 2026-01-21 | Mukkhilal 2 | 15.8578 | 2.1302 | Sahadeb Gope | Completed
352 |  | 52/0 | DC1-1.5 | 2026-01-18 | 2026-01-22 | Prem Kumar | 28.432 | 3.8193 | Anil Kumar | Completed
353 |  | 147/3 | DB1+9 | 2026-01-19 | 2026-01-23 | Shradha | 36.5854 | 4.9145 | Sahadeb Gope | Completed
354 |  | 138/1 | DA+9 | 2026-01-20 | 2026-01-24 | Akash & Prabha | 22.4884 | 3.0209 | Sahadeb Gope | Completed
355 |  | 178/0 | DC2+0 | 2026-01-20 | 2026-01-24 | Khemlal Mahto | 29.7779 | 4.0001 | Sahadeb Gope | Completed
356 |  | 156/0 | DC1+0 | 2026-01-20 | 2026-01-25 | AB Construction | 29.7779 | 4.0001 | Sahadeb Gope | Completed
357 |  | 166/3 | DA+0 | 2026-01-21 | 2026-01-27 | Binod Mahto | 16.9667 | 2.2791 | Sahadeb Gope | Completed
358 |  | 227/0 | DD45-3 | 2026-01-22 | 2026-01-27 | Sainik Traders | 34.4306 | 4.6251 | Mrityunjay Thakur | Completed
359 |  | 199/1 | DA+6 | 2026-01-23 | 2026-01-28 | Govind Mahto | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
360 |  | 122/0 | DB1+0 | 2026-01-25 | 2026-01-28 | Horil Mahto | 27.0921 | 3.6393 | Mrityunjay Thakur | Completed
361 |  | 210/4 | DA+6 | 2026-01-27 | 2026-01-30 | Khemlal Mahto | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
362 |  | 75/0 | DC2+3 | 2026-01-25 | 2026-01-31 | Prem Kumar | 31.8647 | 4.2804 | Anil Kumar | Completed
363 |  | 109B/0 | DC1+0 | 2026-01-25 | 2026-01-31 | Horil Mahto | 29.7779 | 4.0001 | Sahadeb Gope | Completed
364 |  | 131/1 | DB1+9 | 2026-01-27 | 2026-01-31 | Jai Prakash Mahto | 36.5854 | 4.9145 | Sahadeb Gope | Completed
365 |  | 135/0 | DB2+0 | 2026-01-23 | 2026-01-31 | Mukkhilal | 27.0921 | 3.6393 | Sahadeb Gope | Completed
366 |  | 158/1 | DA+3 | 2026-01-25 | 2026-01-31 | AB Construction | 18.1188 | 2.4339 | Sahadeb Gope | Completed
367 |  | 182/6 | DA+3 | 2026-01-28 | 2026-01-31 | Govind Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
368 |  | 210/6 | DA+0 | 2026-01-30 | 2026-02-02 | Khemlal Mahto | 16.9667 | 2.2791 | Mrityunjay Thakur | Completed
369 |  | 95A/1 | DA+9 | 2026-01-30 | 2026-02-04 | Sainik Traders | 22.4884 | 3.0209 | Sahadeb Gope | Completed
370 |  | 109B/1 | DB1+3 | 2026-02-03 | 2026-02-06 | Horil Mahto | 28.3681 | 3.8107 | Sahadeb Gope | Completed
371 |  | 159/1 | DA-3 | 2026-02-01 | 2026-02-06 | AB Construction | 15.8578 | 2.1302 | Sahadeb Gope | Completed
372 |  | 167A/1 | DC1+0(DCT) | 2026-01-30 | 2026-02-08 | Binod Mahto | 42.0469 | 5.6482 | Sahadeb Gope | Completed
373 |  | 211/0 | DC2+3 | 2026-02-08 | 2026-02-11 | Khemlal Mahto | 31.8647 | 4.2804 | Mrityunjay Thakur | Completed
374 |  | 117/1 | DB1+9 | 2026-02-06 | 2026-02-11 | Horil Mahto | 36.5854 | 4.9145 | Sahadeb Gope | Completed
375 |  | 61/0 | DC1-3 | 2026-02-05 | 2026-02-12 | Prem Kumar | 27 | 3.6269 | Anil Kumar | Completed
376 |  | 92/0 | DC2+9 | 2026-02-08 | 2026-02-14 | Govind Mahto | 39.6224 | 5.3225 | Sahadeb Gope | Completed
377 |  | 131/0 | DD45-3 | 2026-02-08 | 2026-02-14 | Jai Prakash Mahto | 34.4306 | 4.6251 | Sahadeb Gope | Completed
378 |  | 125/0 | DC1+0 | 2026-02-13 | 2026-02-16 | AB Construction | 29.7779 | 4.0001 | Sahadeb Gope | Completed
379 |  | 158/0 | DC2+0 | 2026-02-10 | 2026-02-16 | Horil Mahto | 29.7779 | 4.0001 | Sahadeb Gope | Completed
380 |  | 120/1 | DA+9 | 2026-02-16 | 2026-02-18 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
381 |  | 4/3 | DA+0 | 2026-02-16 | 2026-02-21 | Prem Kumar | 16.9667 | 2.2791 | Anil Kumar | Completed
382 |  | 92A/0 | DB1+6 | 2026-02-16 | 2026-02-21 | Govind Mahto | 34.17 | 4.5901 | Sahadeb Gope | Completed
383 |  | 134/1 | DA+0 | 2026-02-19 | 2026-02-21 | Horil Mahto | 16.9667 | 2.2791 | Sahadeb Gope | Completed
384 |  | 134/0 | DB2+3 | 2026-02-22 | 2026-02-25 | Horil Mahto | 28.3681 | 3.8107 | Sahadeb Gope | Completed
385 |  | 96/0 | DB1+0 | 2026-02-22 | 2026-02-26 | Govind Mahto | 27.0921 | 3.6393 | Sahadeb Gope | Completed
386 |  | 133/1 | DA+0 | 2026-02-26 | 2026-02-27 | Horil Mahto | 16.9667 | 2.2791 | Sahadeb Gope | Completed
387 |  | 108/0 | DD45+6 | 2026-03-05 | 2026-03-09 | Horil Mahto | 46.4686 | 6.2421 | Sahadeb Gope | Completed
388 |  | 100/1 | DA+6 | 2026-03-10 | 2026-03-12 | Govind Mahto | 21.0969 | 2.8339 | Sahadeb Gope | Completed
389 |  | 125G/1 | DA-3 | 2026-03-11 | 2026-03-14 | Horil Mahto | 15.8578 | 2.1302 | Sahadeb Gope | Completed
390 |  | 204/0 | DB2+9 | 2026-03-09 | 2026-03-15 | Govind Mahto | 36.5854 | 4.9145 | Mrityunjay Thakur | Completed
391 |  | 145/1 | DA+9 | 2026-03-14 | 2026-03-17 | Horil Mahto | 22.4884 | 3.0209 | Sahadeb Gope | Completed
392 |  | 199/3 | DA+3 | 2026-03-15 | 2026-03-20 | Govind Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
393 |  | 181/3 | DA+6 | 2026-03-20 | 2026-03-22 | Govind Mahto | 21.0969 | 2.8339 | Mrityunjay Thakur | Completed
394 |  | 125P/0 | DB2+6 | 2026-03-21 | 2026-03-25 | Horil Mahto | 34.1665 | 4.5896 | Sahadeb Gope | Completed
395 |  | 210/11 | DA+3 | 2026-03-23 | 2026-03-27 | Govind Mahto | 18.1188 | 2.4339 | Mrityunjay Thakur | Completed
396 |  | 4/0 | DD60+18 | 2026-03-23 | 2026-03-30 | Horil Mahto | 72.5324 | 9.7433 | Anil Kumar | Completed
397 |  | 17/4 | DA+6 | 2026-04-01 | 2026-04-03 | Horil Mahto | 21.0969 | 2.8339 | Anil Kumar | Completed
398 |  | 17/0 | DC1+18 | 2026-04-04 | 2026-04-10 | Horil Mahto | 53.2386 | 7.1515 | Anil Kumar | Completed
399 |  | 203/0 | DD45+9 | 2026-04-07 | 2026-04-13 | Govind Mahto | 48.342 | 6.4938 | Mrityunjay Thakur | Completed
400 |  | 13/4 | DA+9 | 2026-04-11 | 2026-04-14 | Horil Mahto | 22.4884 | 3.0209 | Mrityunjay Thakur | Completed

## Stringing
|  |  | Number of TSE | 2
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | Insulator Hoisting | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Jumpering | Spacering | Clipping | Length | Status | Gang Name | Gang Strength | No. of Fitters | Hindrance | Remarks
1 | Sirohi | 1/0 | 2/0 | 4424.083 | TSE | Ready |  | 2026-01-18 | 2026-01-22 | 4424.083 | 2026-01-26 | 2026-01-31 |  |  | Completed | 4424.083 | Completed | National Construction | 40 | 12
2 | Sirohi | 5/0 | 6/0 | 4949.33 | TSE | Ready |  | 2026-01-22 | 2026-01-27 | 4949.33 | 2026-01-27 | 2026-02-05 |  |  | Completed | 4949.33 | Completed | National Construction | 40 | 12
3 | Sirohi | 48/0 | 50/0 | 688.47 | TSE | Ready |  | 2025-12-19 | 2025-12-30 | 688.47 | 2026-01-15 | 2026-01-20 |  |  | Completed | 688.47 | Completed | Jahangir Alam | 39 | 16
4 | Sirohi | 50/0 | 51/0 | 1160.08 | TSE | Ready |  | 2025-12-19 | 2025-12-30 | 1160.08 | 2026-01-17 | 2026-01-22 |  |  | Completed | 1160.08 | Completed | Jahangir Alam | 39 | 16
5 | Sirohi | 2/0 | 2A/0 | 3318.603 | TSE | Ready |  | 2026-02-15 | 2026-02-19 | 3318.603 | 2026-02-22 | 2026-02-23 |  |  | Completed | 3318.603 | Completed | National Construction | 40 | 12
6 | Sirohi | 51/0 | 51A/0 | 1244.855 | TSE | Ready |  | 2026-01-17 | 2026-01-20 | 1244.855 | 2026-01-27 | 2026-01-31 |  |  | Completed | 1244.855 | Completed | Jahangir Alam | 39 | 16
7 | Sirohi | 51A/0 | 51C/0 | 1234.81 | TSE | Ready |  | 2026-01-21 | 2026-01-26 | 1234.81 | 2026-01-27 | 2026-01-31 |  |  | Completed | 1234.81 | Completed | Jahangir Alam | 39 | 16
8 | Sirohi | 51C/0 | 52/0 | 1968.185 | TSE | Ready |  | 2026-02-13 | 2026-02-16 | 1968.185 | 2026-02-26 | 2026-02-27 |  |  | Completed | 1968.185 | Completed | Jahangir Alam | 39 | 16
9 | Sirohi | 52/0 | 53/0 | 992.08 | TSE | Ready |  | 2026-02-23 | 2026-02-25 | 992.08 | 2026-02-24 | 2026-02-27 |  |  | Completed | 992.08 | Completed | Jahangir Alam | 39 | 16
10 | Sirohi | 4/0 | 5/0 | 2809.04 | TSE | Ready |  | 2026-02-23 | 2026-02-25 | 2809.04 | 2026-02-24 | 2026-02-28 |  |  | Completed | 2809.04 | Completed | National Construction | 40 | 12
11 | Sirohi | 18/0 | 19/0 | 3934.01 | TSE | Ready |  | 2026-02-17 | 2026-02-23 | 3934.01 | 2026-02-24 | 2026-02-28 |  |  | Completed | 3934.01 | Completed | Jahangir Alam | 39 | 16
12 | Sirohi | 68/0 | 68/1 | 504 | Manual | Ready |  | 2026-03-02 | 2026-03-05 | 504 | 2026-03-08 | 2026-03-10 |  |  | Completed | 504 | Completed | Taimoor Ali | 22 | 10
13 | Sirohi | 67/0 | 68/0 | 176.73 | Manual | Ready |  | 2026-03-05 | 2026-03-05 | 176.73 | 2026-03-20 | 2026-03-23 |  |  | Completed | 176.73 | Completed | Taimoor Ali | 22 | 10
14 | Sirohi | 6/0 | 9/0 | 1210.68 | TSE | Ready |  | 2026-03-15 | 17-03-2026 | 1210.68 | 2026-03-17 | 2026-03-18 |  |  | Completed | 1210.68 | Completed | National Construction | 40 | 12
15 | Sirohi | 66/0 | 67/0 | 743.77 | Manual | Ready |  | 2026-03-18 | 2026-03-22 | 743.77 | 2026-03-28 | 2026-03-29 |  |  | Completed | 743.77 | Completed | Taimoor Ali | 22 | 10
16 | Sirohi | 10/0 | 11/0 | 1256.34 | TSE | Ready |  | 2026-03-23 | 2026-03-24 | 1256.34 | 2026-04-01 | 2026-04-02 |  |  | Completed | 1256.34 | Completed | National Construction | 40 | 12
17 | Sirohi | 11/0 | 11/3 | 1114 | TSE | Ready |  | 2026-04-03 | 2026-04-04 | 1114 | 2026-04-15 | 2026-04-16 |  |  | Completed | 1114 | Completed | National Construction | 40 | 12
18 | Sirohi | 11/3 | 12/0 | 530.153 | Manual | Ready |  | 2026-03-28 | 2026-03-28 | 530.153 | 2026-04-15 | 2026-04-16 |  |  | Completed | 530.153 | Completed | National Construction | 40 | 12
19 | Sirohi | 65A/3 | 66/0 | 244.262 | Manual | Ready |  | 2026-03-25 | 2026-03-25 | 244.262 | 2026-04-06 | 2026-04-07 |  |  | Completed | 244.262 | Completed | Taimoor Ali | 22 | 10
20 | Udaipur | 213/0 | 214/0 | 2351.3 | TSE | Ready |  | 2026-04-01 | 2026-04-04 | 2351.3 | 2026-04-06 | 2026-04-07 |  |  | Completed | 2351.3 | Completed | Bilkish Rehena | 33 | 10
21 | Sirohi | 17/0 | 18/0 | 2732.97 | TSE | Ready |  | 2026-04-06 | 2026-04-09 | 2732.97 | 2026-04-13 | 2026-04-14 |  |  | Completed | 2732.97 | Completed | Jahangir Alam | 39 | 16
22 | Sirohi | 9/0 | 10/0 | 272.18 | Manual | Ready |  | 2026-04-09 | 2026-04-09 | 272.18 | 2026-04-09 | 2026-04-09 |  |  | Completed | 272.18 | Completed | National Construction | 40 | 12
23 | Gogunda | 139/0 | 139A/0 | 655.83 | Manual | Ready |  | 2026-04-10 | [9 empty] | Innquete Pvt Ltd | 30 | 10
24 | Gogunda | 139A/0 | 140/0 | 242.66 | Manual | Ready |  | 2026-04-13 | [9 empty] | Innquete Pvt Ltd | 30 | 10
25 | Udaipur | 212/0 | 213/0 | 2393.12 | TSE | Ready |  | 2026-04-13 | 2026-04-15 | 2393.12 | 2026-04-16 | 2026-04-17 |  |  |  | 2393.12 | Completed | Bilkish Rehena | 33 | 10
26 | Sirohi | 12/0 | 13/0 | 3315.27 | TSE | Ready |  | 2026-04-11 | 2026-04-14 | 3315.27 | 2026-04-18 | 2026-04-19 |  |  |  | 3315.27 | Completed | National Construction | 40 | 12
27 | Sirohi | 65/0 | 65A/0 | 195.07 | Manual | Ready |  | 2026-04-12 | 2026-04-12 | 195.07 | [7 empty] | Taimoor Ali | 22 | 10
28 | Sirohi | 65A/0 | 65A/3 | 919 | TSE | Ready |  | 2026-04-15 | 2026-04-17 | 919 | [7 empty] | Taimoor Ali | 22 | 10
29 | Sirohi | 15/0 | 16/0 | 1674.936 | TSE | Ready |  | 2026-04-16 | 2026-04-18 | 1674.936 | [7 empty] | Jahangir Alam | 39 | 16
U/C 220 KV
|  |  | Total | 47.2558

## Visual Chart
V I S U A L C H A R T
| DATE : |  | 2026-04-20
| Name of Line : |  |  | 400 kV D/C Sirohi Chittorgarh TL
| Project Code: |  |  |  | TA 506
| Name of Contractor: |  |  |  | M/s. KEC INTERNATIONAL LTD.
[30 empty] | FDN | EAR | ERE | STR
|  | SIROHI GANTRY |  | 1/0 |  | 1/1 |  | 1/2 |  | 1/3 |  | 1/4 |  | 1/5 |  | 1/6 |  | 1/7 |  | 1/8 |  | 1/9 |  | 1/10 |  | 2/0 |  | 2/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
0 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
|  | SS Land | 175 | Completed | 396 | Completed | 427 | Completed | 408 | Completed | 356 | Completed | 380 | Completed | 433 | Completed | 409 | Completed | 429 | Completed | 403 | Completed | 403 | Completed | 380.083 | Completed | 378 | Completed |  | 13 | 13 | 0
|  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | SIROHI GANTRY |  | DD60+0 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA-3 |  | DA+3 |  | DA+3 |  | DA+3 |  | DA+1.5 |  | DA+1.5 |  | DA+0 |  | DB2+0 |  | DA+0
|  | 2/2 |  | 2/3 |  | 2/4 |  | 2/5 |  | 2/6 |  | 2/7 |  | 2/8 |  | 2A/0 |  | 2A/1 |  | 2A/2 |  | 3/0 |  | 4/0 |  | 4/1 |  | 4/2
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed
14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28
| 420 | Completed | 402 | Completed | 371 | Completed | 341 | Completed | 354 | Completed | 358 | Completed | 342 | Completed | 352.603 | Completed | 351 | Completed | 390 | ROW | 388.14 | ROW | 160.683 |  | 426 | Completed | 414 | Completed |  | 11 | 12 | 1
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed
|  | DA+6 |  | DA+6 |  | DA+3 |  | DA-3 |  | DA+0 |  | DA-3 |  | DA-3 |  | DB2+0 |  | DA-3 |  | DA+6 |  | DD60+18 |  | DD60+6 |  | DA+3 |  | DA+0
|  | 4/3 |  | 4/4 |  | 4/5 |  | 4/6 |  | 5/0 |  | 5/1 |  | 5/2 |  | 5/3 |  | 5/4 |  | 5/5 |  | 5/6 |  | 5/7 |  | 5/8 |  | 5/9
|  | #REF! |  | Completed |  | ROW |  | WIP |  | ROW |  | #REF! |  | ROW |  | ROW |  | ROW |  | Completed |  | WIP |  | Completed |  | Completed |  | ROW
28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42
| 385 |  | 368 | Completed | 425 | Completed | 388 | Completed | 403.041 | Completed | 387 | Completed | 433 | Completed | 379 | Completed | 429 | Completed | 389 | Completed | 409 | Completed | 434 | Completed | 408 | Completed | 429 | Completed |  | 13 | 14 | 4
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+3 |  | DA+0 |  | DA+3 |  | DB2+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+3 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DA+9
|  | 5/10 |  | 5/11 |  | 6/0 |  | 6/1 |  | 6/2 |  | 9/0 |  | 10/0 |  | 10/1 |  | 10/2 |  | 11/0 |  | 11/1 |  | 11/2 |  | 11/3 |  | 12/0
|  | ROW |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 54 |  | 55 |  | 56
| 415 | Completed | 429 | Completed | 408.334 | Completed | 370 | Completed | 432 | Completed | 408.684 | Completed | 272.182 | Completed | 417 | Completed | 420 | Completed | 419.336 | Completed | 354 | Completed | 380 | Completed | 380 | Completed | 530.153 | Completed |  | 14 | 14 | 0
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+3 |  | DA+3 |  | DB1+0 |  | DA+6 |  | DA+9 |  | DD45+9 |  | DD45+9 |  | DA+6 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DB1+9 |  | DC1+6
|  | 12/1 |  | 12/2 |  | 12/3 |  | 12/4 |  | 12/5 |  | 12/6 |  | 12/7 |  | 12/8 |  | 13/0 |  | 13/1 |  | 13/2 |  | 13/3 |  | 13/4 |  | 13/5
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
56 |  | 57 |  | 58 |  | 59 |  | 60 |  | 61 |  | 62 |  | 63 |  | 64 |  | 65 |  | 66 |  | 67 |  | 68 |  | 69 |  | 70
| 362 | Completed | 448 | Completed | 355 | Completed | 355 | Completed | 360 | Completed | 360 | Completed | 361 | Completed | 359 | Completed | 355.274 | Completed | 429 | Completed | 414 | Completed | 398 | Completed | 443 | Completed | 389 | Completed |  | 14 | 14 | 0
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+9 |  | DA+1.5 |  | DA+0 |  | DA+0 |  | DA-3 |  | DA+0 |  | DA+0 |  | DA-3 |  | DB2+0 |  | DA+9 |  | DA+9 |  | DA+3 |  | DA+9 |  | DA+3
|  | 14/0 |  | 15/0 |  | 15/1 |  | 15/2 |  | 15/3 |  | 16/0 |  | 17/0 |  | 17/1 |  | 17/2 |  | 17/3 |  | 17/4 |  | 17/5 |  | 17/6 |  | 18/0
|  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | ROW |  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF!
70 |  | 71 |  | 72 |  | 73 |  | 74 |  | 75 |  | 76 |  | 77 |  | 78 |  | 79 |  | 80 |  | 81 |  | 82 |  | 83 |  | 84
| 381.452 | Completed | 280 | Completed | 458 | Completed | 384 | Completed | 400 | Completed | 432.936 | Completed | 204.967 | Completed | 371.001 | Completed | 406 | Completed | 408 | Completed | 429 |  | 291 | Completed | 434 | Completed | 393.965 | Completed |  | 13 | 3 | 7
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF!
|  | DC1+9 |  | DD45+3 |  | DA+6 |  | DA+6 |  | DA+3 |  | DB2+6 |  | DC1+18 |  | DA+0 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DA+0 |  | DD45+0
|  | 18/1 |  | 18/2 |  | 18/3 |  | 18/4 |  | 18/5 |  | 18/6 |  | 18/7 |  | 18/8 |  | 18/9 |  | 19/0 |  | 19/1 |  | 19/2 |  | 19/3 |  | 19/4
|  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | ROW |  | ROW |  | #REF! |  | Completed |  | #REF! |  | ROW |  | #REF! |  | ROW |  | #REF!
84 |  | 85 |  | 86 |  | 87 |  | 88 |  | 89 |  | 90 |  | 91 |  | 92 |  | 93 |  | 94 |  | 95 |  | 96 |  | 97 |  | 98
| 386 | Completed | 276 | Completed | 415 | Completed | 396 | Completed | 433 | Completed | 377 | Completed | 405 | Completed | 406 | Completed | 425 | Completed | 415.006 | Completed | 438 | Completed | 400 | Completed | 410 | Completed | 423 | Completed |  | 14 | 6 | 5
|  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA+9 |  | DA+6 |  | DA+0 |  | DA+6 |  | DA-3 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DB2+0 |  | DA+9 |  | DA-3 |  | DA+6 |  | DA-3
|  | 19/5 |  | 20/0 |  | 21/0 |  | 22/0 |  | 22A/0 |  | 22B/0 |  | 23/0 |  | 24/0 |  | 25/0 |  | 25/1 |  | 25/2 |  | 26/0 |  | 26/1 |  | 27/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | ROW
98 |  | 99 |  | 100 |  | 101 |  | 102 |  | 103 |  | 104 |  | 105 |  | 106 |  | 107 |  | 108 |  | 109 |  | 110 |  | 111 |  | 112
| 411 | Completed | 416.593 | Forest | 275.029 | Forest | 499.091 | Completed | 467.444 | NH | 239.999 | NH | 394.467 |  | 236.752 | Completed | 264.528 | Completed | 429.999 | Completed | 349 | Completed | 389.068 | Completed | 318 | Completed | 446.386 | Completed |  | 9 | 6 | 0
|  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed
|  | DA+6 |  | DC1+3 |  | DB1+3 |  | DC1+9 |  | DB2+9 |  | DC2-1.5 |  | DD60+18 |  | DD60+18 |  | DB2+6 |  | DA+9 |  | DA+1.5 |  | DD45+0 |  | DA+0 |  | DD45+9
|  | 28/0 |  | 28/1 |  | 28/2 |  | 28/3 |  | 29/0 |  | 30/0 |  | 31/0 |  | 31/1 |  | 32/0 |  | 32/1 |  | 33/0 |  | 33/1 |  | 33/2 |  | 34/0
|  | ROW |  | #REF! |  | WIP |  | #REF! |  | #REF! |  | #REF! |  | ROW |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF!
112 |  | 113 |  | 114 |  | 115 |  | 116 |  | 117 |  | 118 |  | 119 |  | 120 |  | 121 |  | 122 |  | 123 |  | 124 |  | 125 |  | 126
| 394.884 | Completed | 453 |  | 420 | Completed | 273 | Forest | 256.003 | Forest | 263.182 | Completed | 373.852 | Completed | 384 | Completed | 449.427 | Completed | 407 | Completed | 387 | Completed | 378.806 | Forest | 460 | Forest | 380 | Forest |  | 8 | 1 | 3
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DD45+9 |  | DB1+9 |  | DA+9 |  | DA+9 |  | DB1-3 |  | DD60+3 |  | DD45+6 |  | DA+9 |  | DC2+0 |  | DA+9 |  | DC1+6 |  | DA+1.5 |  | DA+9 |  | DC1+9
|  | 34/1 |  | 34/2 |  | 34/3 |  | 35/0 |  | 35A/0 |  | 35A/1 |  | 36/0 |  | 36/1 |  | 36/2 |  | 37/0 |  | 37/1 |  | 37/2 |  | 37/3 |  | 37/4
|  | #REF! |  | #REF! |  | completed |  | completed |  | #REF! |  | ROW |  | #REF! |  | #REF! |  | #REF! |  | ROW |  | #REF! |  | #REF! |  | Completed |  | Completed
126 |  | 127 |  | 128 |  | 129 |  | 130 |  | 131 |  | 132 |  | 133 |  | 134 |  | 135 |  | 136 |  | 137 |  | 138 |  | 139 |  | 140
| 459.885 | Forest | 364 | Completed | 429 | Completed | 394 | Completed | 371.816 | Completed | 427.997 | Completed | 415.652 | Completed | 378 | Completed | 409 | Completed | 343.461 | Completed | 425 | Completed | 395 | Completed | 380 | Completed | 422 | Completed |  | 13 | 4 | 5
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF!
|  | DA+3 |  | DA+1.5 |  | DA+9 |  | DD45+0 |  | DB2-3 |  | DA+6 |  | DC1-3 |  | DA+9 |  | DA+6 |  | DD45+9 |  | DA+0 |  | DA+0 |  | DA+0 |  | DA+6
|  | 38/0 |  | 38/1 |  | 39/0 |  | 40/0 |  | 41/0 |  | 42/0 |  | 42/1 |  | 42/2 |  | 42/3 |  | 42/4 |  | 43/0 |  | 44/0 |  | 44/1 |  | 44A/0
|  | Completed |  | Completed |  | Completed |  | ROW |  | Completed |  | #REF! |  | #REF! |  | ROW |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
140 |  | 141 |  | 142 |  | 143 |  | 144 |  | 145 |  | 146 |  | 147 |  | 148 |  | 149 |  | 150 |  | 151 |  | 152 |  | 153 |  | 154
| 418.002 | Completed | 415 | Completed | 347.52 | Completed | 392.674 | Completed | 373.355 | Completed | 457.079 | Completed | 360 | Completed | 365 | Completed | 385 | Water Logg | 370 | Completed | 409.224 | ROW | 327.162 | Completed | 371 | Completed | 323.578 | Completed |  | 12 | 8 | 4
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | #REF! |  | #REF!
|  | DC2+6 |  | DA+6 |  | DB2+6 |  | DD45+0 |  | DB2+6 |  | DD45+6 |  | DA+0 |  | DA-3 |  | DA+1.5 |  | DA+0 |  | DB2+6 |  | DC2+3 |  | DA+0 |  | DC2+3
|  | 44A/1 |  | 44A/2 |  | 45/0 |  | 46/0 |  | 47/0 |  | 47/1 |  | 47/2 |  | 48/0 |  | 48/1 |  | 50/0 |  | 50/1 |  | 50/2 |  | 51/0 |  | 51/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | ROW |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
154 |  | 155 |  | 156 |  | 157 |  | 158 |  | 159 |  | 160 |  | 161 |  | 162 |  | 163 |  | 164 |  | 165 |  | 166 |  | 167 |  | 168
| 355 | Completed | 276 | Completed | 273.688 | Completed | 354.412 | Completed | 291.447 | Forest | 275 | Completed | 265 | Completed | 308.872 | Completed | 365 | Completed | 323.467 | Completed | 394 | Completed | 356 | Completed | 410.081 | Completed | 410 | Completed |  | 13 | 0 | 7
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA-1.5 |  | DA+0 |  | DD45+0 |  | DD60+9 |  | DB1-3 |  | DB1+9 |  | DA+9 |  | DD45+0 |  | DA+0 |  | DD45+0 |  | DA+6 |  | DA+0 |  | DC2+3 |  | DA+0
|  | 51/2 |  | 51A/0 |  | 51A/1 |  | 51A/2 |  | 51B/0 |  | 51C/0 |  | 51C/1 |  | 51C/2 |  | 51C/3 |  | 51C/4 |  | 52/0 |  | 52/1 |  | 52/2 |  | 53/0
|  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | #REF!
168 |  | 169 |  | 170 |  | 171 |  | 172 |  | 173 |  | 174 |  | 175 |  | 176 |  | 177 |  | 178 |  | 179 |  | 180 |  | 181 |  | 182
| 420 | Completed | 414.855 | Completed | 262 | Completed | 323 | Completed | 359.444 | Completed | 290.367 | Completed | 375 | Completed | 440 | Completed | 404 | Completed | 403 | Completed | 346.185 | Completed | 300 | Completed | 280 | Completed | 412.08 | Completed |  | 14 | 2 | 6
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF!
|  | DA+3 |  | DB1+0 |  | DA-1.5 |  | DA-1.5 |  | DB2-1.5 |  | DB2+0 |  | DA+9 |  | DA-1.5 |  | DA+3 |  | DA+0 |  | DC1-1.5 |  | DA-1.5 |  | DA+0 |  | DB2+9
|  | 54/0 |  | 54/1 |  | 54/2 |  | 54/3 |  | 55/0 |  | 56/0 |  | 57/0 |  | 58/0 |  | 59/0 |  | 60/0 |  | 60/1 |  | 60/2 |  | 60/3 |  | 61/0
|  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
182 |  | 183 |  | 184 |  | 185 |  | 186 |  | 187 |  | 188 |  | 189 |  | 190 |  | 191 |  | 192 |  | 193 |  | 194 |  | 195 |  | 196
| 245.539 | Completed | 395 | ROW | 385 | Completed | 312 | Completed | 393.948 | Completed | 219.41 | Completed | 396.194 | ROW | 160.209 | ROW | 261.315 | ROW | 361.808 | Completed | 405 | Completed | 350 | Completed | 274 | Completed | 250.503 | Completed |  | 10 | 3 | 2
|  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | #REF!
|  | DC2+18 |  | DA+0 |  | DA+0 |  | DA+0 |  | DC1+9 |  | DB1+9 |  | DC1+6 |  | DD60+9 |  | DD60+9 |  | DD60+0 |  | DA+3 |  | DA+3 |  | DA-1.5 |  | DC1-3
|  | 61/1 |  | 62/0 |  | 63/0 |  | 63/1 |  | 64/0 |  | 64/1 |  | 64A/0 |  | 64A/1 |  | 64A/2 |  | 64A/3 |  | 65/0 |  | 65A/0 |  | 65A/1 |  | 65A/2
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
196 |  | 197 |  | 198 |  | 199 |  | 200 |  | 201 |  | 202 |  | 203 |  | 204 |  | 205 |  | 206 |  | 207 |  | 208 |  | 209 |  | 210
| 373 | Completed | 422.223 | Completed | 217.681 | Completed | 345 | Completed | 433.97 | Completed | 218 | Completed | 253.961 | Completed | 375 | Completed | 469 | Completed | 375 | Completed | 440.139 | Completed | 195.073 | Completed | 283 | Completed | 317 | Completed |  | 14 | 1 | 0
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA+3 |  | DD60+9 |  | DD60+9 |  | DA+6 |  | DD60+0 |  | DA-3 |  | DC1-3 |  | DA+6 |  | DA+6 |  | DA+9 |  | DD60+9 |  | DB2+6 |  | DA-1.5 |  | DA+0
|  | 65A/3 |  | 66/0 |  | 66/1 |  | 67/0 |  | 68/0 |  | 68/1 |  | 70/0 |  | 71/0 |  | 72/0 |  | 72/1 |  | 72/2 |  | 74/0 |  | 75/0 |  | 76/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
210 |  | 211 |  | 212 |  | 213 |  | 214 |  | 215 |  | 216 |  | 217 |  | 218 |  | 219 |  | 220 |  | 221 |  | 222 |  | 223 |  | 224
| 319 | Completed | 244.262 | Completed | 341 | Completed | 402.766 | Completed | 176.728 | Completed | 504 | Completed | 438.808 | Forest | 355.892 | Forest | 416.355 | Completed | 468 | Forest | 376 | Completed | 428.958 |  | 396.087 | Completed | 470.636 | Forest |  | 9 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DC1+0 |  | DC1+0 |  | DA+3 |  | DC1+6 |  | DC2+6 |  | DB1+0 |  | DC2-3 |  | DD60-3 |  | DD60+0 |  | DA+9 |  | DA+9 |  | DB2+3 |  | DC2+3 |  | DC2+6
|  | 76A/0 |  | 76A/1 |  | 76B/0 |  | 76C/0 |  | 76D/0 |  | 76E/0 |  | 76F/0 |  | 76G/0 |  | 76G/1 |  | 77/0 |  | 78/0 |  | 79/0 |  | 79/1 |  | 80/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
224 |  | 225 |  | 226 |  | 227 |  | 228 |  | 229 |  | 230 |  | 231 |  | 232 |  | 233 |  | 234 |  | 235 |  | 236 |  | 237 |  | 238
| 387.706 | Completed | 374 | Completed | 407.289 | Completed | 408.317 | 0 | 491.227 | Completed | 174.302 | Completed | 448.997 | Completed | 384.049 | Completed | 446.999 | Completed | 335.02 | Completed | 332.146 | Completed | 436.17 | Completed | 292 |  | 276.315 | Completed |  | 12 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DC1+3 |  | DB1+6 |  | DD60-3 |  | DB2+9 |  | DC1+6 |  | DC2-3 |  | DB1+9 |  | DC1+3 |  | DA+3 |  | DB1+0 |  | DC1+9 |  | DD45+0 |  | DA+0 |  | DD45+0
|  | 81/0 |  | 81/1 |  | 82/0 |  | 83/0 |  | 83/1 |  | 84/0 |  | 84/1 |  | 85/0 |  | 85/1 |  | 86/0 |  | 87/0 |  | 88/0 |  | 89/0 |  | 90/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
238 |  | 239 |  | 240 |  | 241 |  | 242 |  | 243 |  | 244 |  | 245 |  | 246 |  | 247 |  | 248 |  | 249 |  | 250 |  | 251 |  | 252
| 367.701 |  | 504 | ULE/RC | 250.65 | ULE/RC | 437.556 | ULE/RC | 296.128 | ULE/RC | 468.882 | Water Logg | 350.512 | Forest | 432.698 | Forest | 243 | Forest | 256.912 | Forest | 315.777 | Forest | 432.481 | Forest | 194.143 | ULE/RC | 130.625 | ULE/RC |  | 0 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DD60+18 |  | DA+9 |  | DC1-3 |  | DB1-3 |  | DB1+6 |  | DB2+9 |  | DB1+0 |  | DB2-3 |  | DA-3 |  | DD45-3 |  | DB2-3 |  | DC2-3 |  | DD60+9 |  | DD45+6
|  | 90/1 |  | 90/2 |  | 91/0 |  | 91/1 |  | 92/0 |  | 92A/0 |  | 92/2 |  | 93/0 |  | 94/0 |  | 94/1 |  | 94/2 |  | 94/3 |  | 95/0 |  | 95/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
252 |  | 253 |  | 254 |  | 255 |  | 256 |  | 257 |  | 258 |  | 259 |  | 260 |  | 261 |  | 262 |  | 263 |  | 264 |  | 265 |  | 266
| 283.958 | ULE/RC | 339.66 | ULE/RC | 330.737 | ULE/RC | 300.585 | ULE/RC | 383.896 | ULE/RC | 422.069 | Completed | 384 | WIP | 406.834 | Completed | 441.715 | Completed | 407 | Completed | 399 | Completed | 385 | Completed | 434.052 | Completed | 449.999 | Completed |  | 8 | 7 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DB2+6 |  | DB1+18 |  | DC2-3 |  | DB1+6 |  | DC2+9 |  | DB1+6 |  | DA-1.5 |  | DD45+6 |  | DD45+6 |  | DA+9 |  | DA+9 |  | DA+9 |  | DC2+9 |  | DA+3
|  | 95A/0 |  | 95A/1 |  | 96/0 |  | 97/0 |  | 97/1 |  | 98/0 |  | 99/0 |  | 99/1 |  | 100/0 |  | 100/1 |  | 100/2 |  | 101/0 |  | 101/1 |  | 102/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
266 |  | 267 |  | 268 |  | 269 |  | 270 |  | 271 |  | 272 |  | 273 |  | 274 |  | 275 |  | 276 |  | 277 |  | 278 |  | 279 |  | 280
| 353.293 | Completed | 406.998 | Completed | 441.72 |  | 309.586 | Completed | 435.999 | Completed | 309.153 |  | 438.057 | ULE/RC | 443.996 | ULE/RC | 392.527 |  | 447.004 | 0 | 331.003 | Completed | 354.721 | Completed | 409.003 | Completed | 352.453 | Completed |  | 8 | 7 | 0
|  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | Completed |  | Completed |  | Completed
|  | DB1+9 |  | DB1+9 |  | DB1+0 |  | DB2+1.5 |  | DA+1.5 |  | DC1+9 |  | DB2+18 |  | DA+0 |  | DC2+3 |  | DA+6 |  | DA+0 |  | DD45+9 |  | DA+6 |  | DC1-1.5
|  | 103/0 |  | 103/1 |  | 104/0 |  | 104/1 |  | 105/0 |  | 105A/0 |  | 106/0 |  | 107/0 |  | 107/1 |  | 108/0 |  | 109/0 |  | 109A/0 |  | 109B/0 |  | 109B/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
280 |  | 281 |  | 282 |  | 283 |  | 284 |  | 285 |  | 286 |  | 287 |  | 288 |  | 289 | 298.173 | 290 |  | 291 |  | 292 |  | 293 |  | 294
| 354.851 | Completed | 487.211 | Forest | 266.598 | Forest | 391.411 | Forest | 447.254 | Forest | 490.899 | WIP | 623.277 | Forest | 384.275 |  | 282 | Completed |  |  | 215.91 | Completed | 547.861 | ULE/RC | 569.68 | ULE/RC | 276.549 | Completed |  | 4 | 7 | 0
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed
|  | DC1+18 |  | DB2+6 |  | DB1-3 |  | DB1-3 |  | DD45+0 |  | DD60+6 |  | DC2-3 |  | DD45+6 |  | DA+3 |  | DD45+6 |  | DD45+0 |  | DC2+25 |  | DC1+0 |  | DA+0
|  | 110/0 |  | 111/0 |  | 112/0 |  | 113/0 |  | 113A/0 |  | 113A/1 |  | 114/0 |  | 114/1 |  | 115/0 |  | 115A/0 |  | 116/0 |  | 117/0 |  | 117/1 |  | 118/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
294 |  | 295 |  | 296 |  | 297 |  | 298 |  | 299 |  | 300 |  | 301 |  | 302 |  | 303 |  | 304 |  | 305 |  | 306 |  | 307 |  | 308
| 493.797 | Completed | 315.251 | Completed | 371.063 | ROW | 257.103 | Completed | 467.783 | Completed | 163 | Completed | 242.712 | Completed | 371.966 | Completed | 308.497 | ROW | 314.841 |  | 237.578 |  | 484.676 |  | 460 |  | 406.011 |  |  | 7 | 7 | 0
|  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF!
|  | DC2+3 |  | DC1+0 |  | DD45+9 |  | DB2+9 |  | DB1+3 |  | DB1+0 |  | DC1+0 |  | DB1+6 |  | DC2+9 |  | DB2-3 |  | DD45+9 |  | DC2+9 |  | DB1+9 |  | DC1+6
|  | 118/1 |  | 119/0 |  | 120/0 |  | 120/1 |  | 121/0 |  | 122/0 |  | 123/0 |  | 124/0 |  | 125/0 |  | 125A/0 |  | 125B/0 |  | 125C/0 |  | 125D/0 |  | 125E/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
308 |  | 309 |  | 310 |  | 311 |  | 312 |  | 313 |  | 314 |  | 315 |  | 316 |  | 317 |  | 318 |  | 319 |  | 320 |  | 321 |  | 322
| 449 | 0 | 396.259 | Completed | 329.144 | Completed | 321 |  | 386.9 |  | 374.965 | Completed | 241.812 |  | 97.959 |  | 325.893 |  | 231.825 | Forest | 134.1 | Forest | 398.146 | Forest | 534.656 | Forest | 388.578 | Forest |  | 3 | 4 | 0
|  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DB1+3 |  | DB2+9 |  | DB1-3 |  | DA+9 |  | DD60-3 |  | DB1+0 |  | DB2-3 |  | DC2+9 |  | DC1+9 |  | DC2-1.5 |  | DC1-3 |  | DC2+9 |  | DD60+0 |  | DB2+3
|  | 125F/0 |  | 125G/0 |  | 125G/1 |  | 125H/0 |  | 125I/0 |  |  |  | 125K/0 |  | 125L/0 |  |  |  | 125N/0 |  | 125O/0 |  | 125P/0 |  | 125Q/0 |  | 126/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
322 |  | 323 |  | 324 |  | 325 |  | 326 |  | 327 |  | 328 |  | 329 |  | 330 |  | 331 |  | 332 |  | 333 |  | 334 |  | 335 |  | 336
| 469.257 | Forest | 359.474 |  | 205 |  | 310.661 |  | 378.844 |  | 592.25 |  |  | WIP | 304.02 |  | 509.7 |  |  |  | 374.435 |  | 417.854 |  | 469.136 | ROW | 320.942 | ROW |  | 0 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DC2+3 |  | DC2+3 |  | DA-3 |  | DC2-3 |  | DB2-3 |  |  |  | DB2-3 |  | DB1+9 |  |  |  | DB2-3 |  | DB2+0 |  | DB2+6 |  | DC1-3 |  | DC1-3
|  | 126A/0 |  | 127/0 |  | 128/0 |  | 128/1 |  | 129/0 |  | 130/0 |  | 131/0 |  | 131/1 |  | 132/0 |  | 132/1 |  | 133/0 |  | 133/1 |  | 133/2 |  | 133/3
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
336 |  | 337 |  | 338 |  | 339 |  | 340 |  | 341 |  | 342 |  | 343 |  | 344 |  | 345 |  | 346 |  | 347 |  | 348 |  | 349 |  | 350
| 395.015 | ROW | 233.713 | ROW | 383.415 | Completed | 400 | Forest | 342.492 | Forest | 428.428 | ULE/RC | 537.591 | Completed | 369 | Completed | 572.273 |  | 406 | ROW | 430.79 | ROW | 294 |  | 489.014 | ROW | 390.821 | ROW | 418.07 | 3 | 3 | 0
|  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DB1-3 |  | DB2+9 |  | DB1+6 |  | DB1+3 |  | DC2+3 |  | DC2+9 |  | DD45-3 |  | DB1+9 |  | DD45+9 |  | DA+3 |  | DC1+3 |  | DA+0 |  | DB1+9 |  | DA+6
|  | 134/0 |  | 134/1 |  | 135/0 |  | 135/1 |  | 135/2 |  | 136/0 |  | 137/0 |  | 137/1 |  | 137/2 |  | 138/0 |  | 138/1 |  | 139/0 |  | 139A |  | 140/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
350 |  | 351 |  | 352 |  | 353 |  | 354 |  | 355 |  | 356 |  | 357 |  | 358 |  | 359 |  | 360 |  | 361 |  | 362 |  | 363 |  | 364
| 418.07 |  | 422.998 |  | 418.88 | Completed | 428.999 | Completed | 402 | Completed | 457.141 | PLC | 227.27 | ULE/RC | 396 | Completed | 344 | Completed | 316.753 | Water Logg | 386.999 | Completed | 390.079 | Completed | 655.833 | Completed | 242.661 | Completed | 473.001 | 9 | 8 | 0
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | Completed
|  | DB2+3 |  | DA+0 |  | DB2+3 |  | DA+9 |  | DB1+0 |  | DD60+9 |  | DD60+18 |  | DA-3 |  | DA+0 |  | DC1+0 |  | DA+9 |  | DD60+9 |  | DC2+9 |  | DC2-3
|  | 140/1 |  | 140/2 |  | 141/0 |  | 141/1 |  | 142/0 |  | 142/1 |  | 143/0 |  | 144/0 |  | 145/0 |  | 145/1 |  | 147/0 |  | 147/1 |  | 147/2 |  | 147/3
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
364 |  | 365 |  | 366 |  | 367 |  | 368 |  | 369 |  | 370 |  | 371 |  | 372 |  | 373 |  | 374 |  | 375 |  | 376 |  | 377 |  | 378
| 473.001 | Completed | 322 | Completed | 357.709 | Completed | 373.999 | Completed | 346.381 | Completed | 320 | Completed | 409.088 |  | 420.71 |  | 409.461 | Water Logg | 460 |  | 349.388 |  | 451 | Completed | 319 | Completed | 341 | ULE/RC | 512.478 | 8 | 4 | 0
|  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA+6 |  | DA+3 |  | DC2+3 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DC1+9 |  | DC2+9 |  | DB2+6 |  | DA+9 |  | DC1+0 |  | DA+9 |  | DA+9 |  | DB1+9
|  | 148/0 |  | 149/0 |  | 150/0 |  | 151/0 |  | 152/0 |  | 153/0 |  | 154/0 |  | 154/1 |  | 156/0 |  | 156/1 |  | 156/2 |  | 157/0 |  | 158/0 |  | 158/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
378 |  | 379 |  | 380 |  | 381 |  | 382 |  | 383 |  | 384 |  | 385 |  | 386 |  | 387 |  | 388 |  | 389 |  | 390 |  | 391 |  | 392
| 512.478 | Completed | 403.799 |  | 379.248 |  | 415.201 | ULE/RC | 379.609 | ULE/RC | 398.966 | ULE/RC | 369.804 | ROW | 238.002 | ROW | 384.484 | Completed | 377.996 | Completed | 494.003 | Completed | 363.172 | Completed | 402.31 | ULE/RC | 382.005 |  | 376.93 | 5 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | [7 empty] | #REF! |  | #REF! |  | #REF!
|  | DC2+6 |  | DD45-3 |  | DB2+6 |  | DB1+3 |  | DB2+4.5 |  | DC1+0 |  | DC2+0 |  | DB1+9 |  | DC1+0 |  | DB1+6 |  | DB1-3 |  | DB1-3 |  | DC2+6 |  | DA+0
|  | 159/0 |  | 159/1 |  | 159/2 |  | 159/3 |  | 160/0 |  | 161/0 |  | 161/1 |  | 162/0 |  | 162/1 |  | 162/2 |  | 163/0 |  | 163/1 |  | 163/2 |  | 163/3
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
392 |  | 393 |  | 394 |  | 395 |  | 396 |  | 397 |  | 398 |  | 399 |  | 400 |  | 401 |  | 402 |  | 403 |  | 404 |  | 405 |  | 406
| 376.93 | Completed | 194 |  | 341.416 | ULE/RC | 413 | NH | 192.382 | NH | 180.054 | NH | 354 | ULE/RC | 317.73 | NH | 333 | ROW | 455 | ULE/RC | 297.839 | ULE/RC | 220 | 0 | 498 | Completed | 285 | 0 | 406.309 | 2 | 0 | 0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DB1-3 |  | DA-3 |  | DB2+0 |  | DA+3 |  | DD45-3 |  | DD60-1.5 |  | DA+3 |  | DC1+6 |  | DA+9 |  | DB1+6 |  | DC1+25 |  | DB1+6 |  | DA+3 |  | DA-3
|  | 164/0 |  | 164/1 |  | 164/2 |  | 164/3 |  | 165/0 |  | 165A/0 |  | 165A/1 |  | 165A/2 |  | 166/0 |  | 166/1 |  | 166/2 |  | 166/3 |  | 166/4 |  | 166/5
|  | #REF! |  | WIP |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | completed
406 |  | 407 |  | 408 |  | 409 |  | 410 |  | 411 |  | 412 |  | 413 |  | 414 |  | 415 |  | 416 |  | 417 |  | 418 |  | 419 |  | 420
| 406.309 | Completed | 291 | 0 | 298 | Completed | 355 | NH | 383.268 | NH | 198.082 | NH | 301.999 | ULE/RC | 427 | 0 | 564.027 | Completed | 382 | Completed | 394 | Completed | 391 | Completed | 253 | WIP | 408 | 0 | 377.686 | 6 | 0 | 1
|  |  |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | [9 empty] | #REF! |  | #REF!
|  | DD45+0 |  | DB1+9 |  | DA+3 |  | DA+9 |  | DD45+6 |  | DC1+1.5 |  | DB1+9 |  | DB1+9 |  | DC1+9 |  | DB1+6 |  | DA+6 |  | DA+0 |  | DA+3 |  | DA+6
|  | 167/0 |  | 167/1 |  | 167/2 |  | 167A/0 |  | 167A/1 |  | 167A/2 |  | 168/0 |  | 169/0 |  | 169/1 |  | 171/0 |  | 171/1 |  | 172/0 |  | 172/1 |  | 172/2
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
420 |  | 421 |  | 422 |  | 423 |  | 424 |  | 425 |  | 426 |  | 427 |  | 428 |  | 429 |  | 430 |  | 431 |  | 432 |  | 433 |  | 434
| 377.686 | Completed | 393 | Completed | 316 | Completed | 347.524 | Completed | 365 | Completed | 300 | Completed | 303.665 | Completed | 316.197 | Completed | 402.89 |  | 490.419 | ULE/RC | 377 | ROW | 390.752 | Completed | 340 | Completed | 387 | Completed | 451 | 11 | 0 | 1
[10 empty] | #REF! |  | #REF! | [5 empty] | #REF! |  | #REF! |  | #REF!
|  | DC2+0 |  | DA+9 |  | DA+9 |  | DD45+3 |  | DC1+0 (DCT) |  | DA+0 |  | DB2+9 |  | DC1+18 |  | DB1+0 |  | DB2+9 |  | DA+9 |  | DC2-1.5 |  | DA-1.5 |  | DA+0
|  | 172/3 |  | 172/4 |  | 172/5 |  | 174/0 |  | 175/0 |  | 175/1 |  | 175/2 |  | 176/0 |  | 176/1 |  | 176A/0 |  | 177/0 |  | 178/0 |  | 179/0 |  | 180/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
434 |  | 435 |  | 436 |  | 437 |  | 438 |  | 439 |  | 440 |  | 441 |  | 442 |  | 443 |  | 444 |  | 445 |  | 446 |  | 447 |  | 448
| 451 |  | 366 | Completed | 263 |  | 338.559 |  | 367.779 |  | 445 | Completed | 335 | ROW | 367.63 | ULE/RC | 210 | ULE/RC | 482.888 |  | 345.839 | WIP | 361.454 | Completed | 221.507 | Forest | 235.127 |  | 415.141 | 3 | 0 | 0
|  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA+0 |  | DA-3 |  | DA+3 |  | DD45-3 |  | DC1-3 |  | DA+6 |  | DA+6 |  | DB2+0 |  | DB1-3 |  | DC1-3 |  | DD60+9 |  | DC2+0 |  | DD45+3 |  | DB2+9
|  | 181/0 |  | 181/1 |  | 181/2 |  | 181/3 |  | 182/0 |  | 182/1 |  | 182/2 |  | 182/3 |  | 182/4 |  | 182/5 |  | 182/6 |  | 183/0 |  | 183/1 |  | 183/2
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed
448 |  | 449 |  | 450 |  | 451 |  | 452 |  | 453 |  | 454 |  | 455 |  | 456 |  | 457 |  | 458 |  | 459 |  | 460 |  | 461 |  | 462
| 415.141 |  | 322.002 | ROW | 385 | Completed | 277 | Completed | 228.726 | Completed | 358 | Completed | 416 | Completed | 385 | Completed | 340 | Completed | 412 | Completed | 424 | Completed | 397.241 | ROW | 385.999 | Completed | 416 | Completed | 369 | 11 | 9 | 7
|  | #REF! |  | 0 |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed | [5 empty] | Completed
|  | DB1+6 |  | DA+6 |  | DA+9 |  | DA+6 |  | DD60+0 |  | DA+9 |  | DA+0 |  | DA+9 |  | DA+6 |  | DA+3 |  | DA+3 |  | DC1+3 |  | DA+3 |  | DA+6
|  | 183/3 |  | 183/4 |  | 183/5 |  | 184/0 |  | 184/1 |  | 184/2 |  | 184/3 |  | 185/0 |  | 185/1 |  | 185/2 |  | 186/0 |  | 186/1 |  | 186/2 |  | 187/0
|  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed |  | #REF! |  | Completed
462 |  | 463 |  | 464 |  | 465 |  | 466 |  | 467 |  | 468 |  | 469 |  | 470 |  | 471 |  | 472 |  | 473 |  | 474 |  | 475 |  | 476
| 369 | Completed | 392 | Completed | 423.001 | Completed | 407.543 | Completed | 393 | Completed | 432 | Completed | 393 | Completed | 338.549 | Completed | 325 | Completed | 434 | Completed | 369.197 | Completed | 365 | Completed | 390 | Completed | 440.652 | Completed | 400 | 14 | 14 | 9
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+9 |  | DA+9 |  | DC1+9 |  | DA+3 |  | DA+6 |  | DA+0 |  | DC1+0 |  | DA+0 |  | DA+6 |  | DD60+0 |  | DA+3 |  | DA+9 |  | DC2+6
|  | 187/1 |  | 187/2 |  | 187A/0 |  | 187A/1 |  | 188/0 |  | 189/0 |  | 189/1 |  | 190/0 |  | 190/1 |  | 190/2 |  | 190/3 |  | 190/4 |  | 191/0 |  | 192/0
|  | #REF! |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF!
476 |  | 477 |  | 478 |  | 479 |  | 480 |  | 481 |  | 482 |  | 483 |  | 484 |  | 485 |  | 486 |  | 487 |  | 488 |  | 489 |  | 490
| 400 | Completed | 416 | Completed | 388.128 | Completed | 380 | Completed | 460 |  | 320 | Completed | 417 | ROW | 414.221 | Completed | 328 | ROW | 374 | Completed | 402 | Completed | 327 | Completed | 369.277 | Completed | 243.472 | Completed | 240 | 11 | 7 | 5
|  | Completed |  | Completed | [5 empty] | #REF! | [5 empty] | Completed |  |  |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+6 |  | DA+6 |  | DC2+3 |  | DA+6 |  | DC2+18 |  | DD45+18 |  | DA+0 |  | DC2+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DA+0 |  | DB1+0 |  | DB2+18
|  | 193/0 |  | 193/1 |  | 193/2 |  | 194/0 |  | 194/1 |  | 194/2 |  | 195/0 |  | 195/1 |  | 195/2 |  | 195/3 |  | 196/0 |  | 197/0 |  | 197/1 |  | 197/2
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed
490 |  | 491 |  | 492 |  | 493 |  | 494 |  | 495 |  | 496 |  | 497 |  | 498 |  | 499 |  | 500 |  | 501 |  | 502 |  | 503 |  | 504
| 240 | Completed | 427 | Completed | 322 | Completed | 386.251 | Completed | 428 | Completed | 379 | Completed | 361.747 | Completed | 408 | Completed | 384 | Completed | 422 | Completed | 417.615 | RLY | 206.464 | RLY | 420 |  | 393 | Completed | 424 | 11 | 6 | 4
|  | Completed | [13 empty] | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  |  |  | Completed
|  | DB2+6 |  | DA+3 |  | DA+9 |  | DC1+3 |  | DA+6 |  | DA+6 |  | DB1+0 |  | DA+0 |  | DA+6 |  | DA+3 |  | DD60+6 |  | DD60+6 |  | DA+3 |  | DA+3
|  | 197/3 |  | 199/0 |  | 199/1 |  | 199/2 |  | 199/3 |  | 199/4 |  | 199/5 |  | 199/6 |  | 200/0 |  | 200/1 |  | 200/2 |  | 200/3 |  | 201/0 |  | 202/0
|  | Completed |  | #REF! |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | WIP |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | WIP
504 |  | 505 |  | 506 |  | 507 |  | 508 |  | 509 |  | 510 |  | 511 |  | 512 |  | 513 |  | 514 |  | 515 |  | 516 |  | 517 |  | 518
| 424 | Completed | 334.314 | Completed | 300 | Completed | 365 |  | 393 | Completed | 393 | Completed | 425 | Completed | 265 | Completed | 365.34 | Completed | 456 | Completed | 371 | Completed | 318 | Completed | 442.001 | Completed | 462.456 | Completed | 420 | 13 | 9 | 9
|  | Completed |  | Completed |  | Completed | [5 empty] | Completed |  | Completed |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF!
|  | DA+3 |  | DC1+0 |  | DA+6 |  | DA+9 |  | DA+3 |  | DA+0 |  | DA+3 |  | DA+6 |  | DB2+6 |  | DA+9 |  | DA+0 |  | DA+0 |  | DD45+9 |  | DD45+9
|  | 202/1 |  | 202/2 |  | 203/0 |  | 204/0 |  | 204/1 |  | 205/0 |  | 205/1 |  | 205/2 |  | 206/0 |  | 206/1 |  | 206/2 |  | 207/0 |  | 207/1 |  | 207/2
|  | WIP |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
518 |  | 519 |  | 520 |  | 521 |  | 522 |  | 523 |  | 524 |  | 525 |  | 526 |  | 527 |  | 528 |  | 529 |  | 530 |  | 531 |  | 532 |  | 11 | 0 | 0
| 420 | Completed | 424 | Completed | 411.763 |  | 190.339 |  | 381 | Completed | 399.794 | Completed | 388 | Completed | 377 | Completed | 344.719 | Completed | 330 | Completed | 325 | Completed | 419.572 | Completed | 435 | Completed | 400 | NH | 395
|  | Completed |  | Completed |  | #REF! |  |  |  | Completed |  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
|  | DA+6 |  | DA+3 |  | DD45+9 |  | DB2+9 |  | DA+3 |  | DC1+3 |  | DA+6 |  | DA+3 |  | DC2+0 |  | DA+0 |  | DA+9 |  | DD45+6 |  | DA+3 |  | DA+3
|  | 207/3 |  | 207/4 |  | 208/0 |  | 209/0 |  | 209/1 |  | 209/2 |  | 209A/0 |  | 209A/1 |  | 209A/2 |  | 210/0 |  | 210/3 |  | 210/4 |  | 210/5 |  | 210/6
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed
532 |  | 533 |  | 534 |  | 535 |  | 536 |  | 537 |  | 538 |  | 539 |  | 540 |  | 541 |  | 542 |  | 543 |  | 544 |  | 545 |  | 546 |  | 6 | 0 | 0
| 395 | Completed | 381 |  | 297.373 | RLY | 219.801 | RLY | 411 | ROW | 390 | ROW | 454.046 | ROW | 400.998 | ROW | 360 | ROW | 335.073 | Completed | 399.998 | Completed | 421 | Completed | 411 | Completed | 371 | Completed | 396
|  | Completed |  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+3 |  | DD60+9 |  | DD60+6 |  | DA+3 |  | DA+9 |  | DC1+9 |  | DA+0 |  | DA-3 |  | DB1+0 |  | DA+3 |  | DA+6 |  | DA+6 |  | DA+0
|  | 210/7 |  | 210/8 |  | 210/9 |  | 210/10 |  | 210/11 |  | 211/0 |  | 211/1 |  | 211/2 |  | 211/3 |  | 211/4 |  | 211/5 |  | 211/6 |  | 211/7 |  | 212/0
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | WIP |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
546 |  | 547 |  | 548 |  | 549 |  | 550 |  | 551 |  | 552 |  | 553 |  | 554 |  | 555 |  | 556 |  | 557 |  | 558 |  | 559 |  | 560 |  | 13 | 0 | 0
| 396 | Completed | 413 | Completed | 402 | Completed | 402 | Completed | 418 |  | 418.319 | Completed | 396 | Completed | 373 | Completed | 420 | Completed | 409 | Completed | 408 | Completed | 430 | Completed | 414 | Completed | 404.508 | Completed | 378
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+0 |  | DA+6 |  | DA+6 |  | DA+3 |  | DA+3 |  | DC2+3 |  | DA+0 |  | DA+6 |  | DA+9 |  | DA+6 |  | DA+6 |  | DA+6 |  | DA+9 |  | DB2+3
|  | 212/1 |  | 212/2 |  | 212/3 |  | 212/4 |  | 212/5 |  | 213/0 |  | 213/1 |  | 213/2 |  | 213/3 |  | 213/4 |  | 213/5 |  | 214/0 |  | 214/1 |  | 214/2
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | #REF! |  | Completed |  | Completed |  | Completed
560 |  | 561 |  | 562 |  | 563 |  | 564 |  | 565 |  | 566 |  | 567 |  | 568 |  | 569 |  | 570 |  | 571 |  | 572 |  | 573 |  | 574 |  | 14 | 0 | 0
| 378 | Completed | 405 | Completed | 412 | Completed | 403 | Completed | 429 | Completed | 366.121 | Completed | 383 | Completed | 416 | Completed | 340 | Completed | 388 | Completed | 415 | Completed | 409.295 | Completed | 369 | Completed | 341 | Completed | 411
|  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF! |  | Completed |  | Completed |  | Completed |  | Completed
|  | DA+6 |  | DA+3 |  | DA+6 |  | DA+9 |  | DA+6 |  | DD45+0 |  | DA+0 |  | DA+3 |  | DA+0 |  | DA+0 |  | DA+3 |  | DC2+0 |  | DA+0 |  | DA+0
|  | 214/3 |  | 215/0 |  | 216/0 |  | 217/0 |  | 218/0 |  | 218/1 |  | 219/0 |  | 220/0 |  | 220/1 |  | 220/2 |  | 220/3 |  | 220/4 |  | 220/5 |  | 220/6
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | WIP |  | #REF! |  | #REF! |  | #REF! |  | #REF!
574 |  | 575 |  | 576 |  | 577 |  | 578 |  | 579 |  | 580 |  | 581 |  | 582 |  | 583 |  | 584 |  | 585 |  | 586 |  | 587 |  | 588 |  | 11 | 0 | 0
| 411 | Completed | 426.044 | Completed | 252.678 | Completed | 147.659 | ROW | 175.996 | Completed | 411 | Completed | 398.903 | ROW | 233.522 | ROW | 310 | Completed | 362 | Completed | 390 | Completed | 450 | Completed | 390 | Completed | 336 | Completed | 430
|  | Completed |  | #REF! |  | #REF! |  | #REF! |  | Completed |  | #REF! |  | #REF! |  |  |  | Completed |  | Completed |  | Completed |  | Completed |  | Completed |  | #REF!
|  | DA+9 |  | DB1+6 |  | DB1+18 |  | DB1+9 |  | DD45+3 |  | DA+3 |  | DC2+0 |  | DD60+0 |  | DA+3 |  | DA-1.5 |  | DA+9 |  | DA+9 |  | DA-1.5 |  | DA+6
|  | 220/7 |  | 220/8 |  | 221/0 |  | 222/0 |  | 223/0 |  | 223/1 |  | 224/0 |  | 224/1 |  | 225/0 |  | 225/1 |  | 225/2 |  | 226/0 |  | 227/0 |  | 227/1
|  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
588 |  | 589 |  | 590 |  | 591 |  | 592 |  | 593 |  | 594 |  | 595 |  | 596 |  | 597 |  | 598 |  | 599 |  | 600 |  | 601 |  | 602 |  | 9 | 0 | 0
| 430 | Completed | 410 | Completed | 430.07 | Completed | 264.827 | Completed | 476.566 | Completed | 387 | Completed | 343.94 | Completed | 291 |  | 330.201 |  | 75 | PLC | 99.983 | PLC | 75 | ROW | 372.207 | Completed | 285 | Completed | 322
|  | #REF! |  | #REF! |  | Completed |  |  |  | Completed |  | Completed |  | Completed | [5 empty] | #REF! |  | #REF! |  | #REF!
|  | DA+9 |  | DA+3 |  | DB2+9 |  | DD45+18 |  | DC2+6 |  | DA+6 |  | DD45+3 |  | DA+0 |  | DD60+0 |  | DDH |  | DDH |  | DD60+6 |  | DD45+0 |  | DA+3
|  | 227/2 |  | 228/0 |  | 229/0
|  | #REF! |  | #REF! |  | #REF!
602 |  | 603 |  | 604 |  | 605 | [23 empty] | 1 | 0 | 0
| 322 | DD60+0(AUX. X.ARM) | 95.244 | Completed | 194.837 | 0 | 63.502
#REF!
|  | DD60+0 |  | DD60+0(AUX. X.ARM) |  | DD60+0(AUX. X.ARM)
| LEGEND: | [16 empty] | PROGRESS AT A GLANCE : | [9 empty] | TOTAL |  | 408 | 193 | 80 | 0
[6 empty] | Stringing WIP |  | Stringing Completed |  |  |  | Front Clear For Stringing |  | Check Survey Completed |  |  |  | SR. NO. |  | ACTIVITY |  |  | UNIT | TOTAL |  | COMPLETED |  | BALANCE
[5 empty] | EREC. COMP. | [7 empty] | EREC. U/P
[5 empty] | FDN. COMP. |  |  | SPAN |  | SPAN |  |  | FDN. U/P |  |  |  |  | 1 |  | Foundation |  |  | Nos. | 602 |  | 475 |  | 127
[5 empty] | EAR.COMP. | [12 empty] | 2 |  | Erection |  |  | Nos. | 602 |  | 400 |  | 202
[18 empty] | 3 |  | Stringing (Final Sag) |  |  | Km. | 222.8 |  | 43.57 |  | 179.23
[18 empty] | 4 |  | Earthing |  |  | Nos. | 602 |  | 280 |  | 322
| NH/SH Xing |  | RAILWAY Xing |  |  | 11/33 KV X-ING |  |  | 66/132/ 220/400KV CROSSING |  |  | RIVER X-ING |  |  | GAS PIPELINE

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 506 | 400 KV D/C Sirohi - Chittorgarh Line | PGCIL | 2024-07-23 | 2026-06-22 | Mr. Abir Kumar Das | Mr. Nabajit Baruah |  | Mr. Rajiv Sharma | Dharmendra Pandey | Anil Kumar
[9 empty] | Rajkumar Tomar | Bipattaran Dolui
[9 empty] | Rajib Biswas | Sahadeo Gope
[9 empty] | Abhishek Kumar | Sunil Kumar
[9 empty] | Krishna Prasad | Mrityunjay Thakur
Bhola Karmakat
Ram Sekhar
Dwarika Mahto

## Location Summary (hidden)
Over all Tower Location details
S. No. | No of | Location | Type of |  | RC |  | Span | Cumm. | DS Status as on | 306 | 292 | 257 | 102 | 26 | Remarks
| AP | Tower No. | Tower |  |  |  | Length (m) | Span (km) | 2025-11-01 | Foundation | Earthing | Tower Erection | Tack welding | SPT
0 |  | Gantry | Gantry |  |  |  |  | 0
[6 empty] | Gantry | 150.014
3 | AP-1 | 1/0 | DD60+0 | T |  |  |  | 0.15 | Approved | Completed | Completed | Completed
[6 empty] | 1/0 | 290.21
2 | AP-2A | 2A/0 | DD45+0 | T |  |  |  | 0.4402 | Approved | Completed | Completed
[6 empty] | 2A/0 | 378
3 | AP-3 | 2A/1 | DA+0 |  |  |  |  | 0.8182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/1 | 381
4 |  | 2A/2 | DA+3 |  |  |  |  | 1.1992 | Approved | Completed | Completed | Completed
[6 empty] | 2A/2 | 419
5 |  | 2A/3 | DA+3 |  |  |  |  | 1.6182 | Approved | Completed | Completed | Completed
[6 empty] | 2A/3 | 422
6 |  | 2A/4 | DA+3 |  |  |  |  | 2.0402 | Approved | Completed | Completed | Completed
[6 empty] | 2A/4 | 399
7 |  | 2A/5 | DA+3 |  |  |  |  | 2.4392 | Approved | Completed | Completed | Completed
[6 empty] | 2A/5 | 423
8 |  | 2A/6 | DA+6 |  |  |  |  | 2.8622 | Approved | Completed | Completed | Completed
[6 empty] | 2A/6 | 414.992
9 |  | 3A/0 | DD45+3 | T |  |  |  | 3.2772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/0 | 409
10 |  | 3A/1 | DA+3 |  |  |  |  | 3.6862 | Approved | Completed | Completed | Completed
[6 empty] | 3A/1 | 402
11 |  | 3A/2 | DA+3 |  |  |  |  | 4.0882 | Approved | Completed | Completed | Completed
[6 empty] | 3A/2 | 409
12 |  | 3A/3 | DA+0 |  |  |  |  | 4.4972 | Approved | Completed | Completed | Completed |  | Completed |  | 274
[6 empty] | 3A/3 | 337
13 |  | 3A/4 | DA+0 |  |  |  |  | 4.8342 | Approved | Completed | Completed | Completed
[6 empty] | 3A/4 | 365
14 |  | 3A/5 | DA+3 |  |  |  |  | 5.1992 | Approved | Completed | Completed | Completed
[6 empty] | 3A/5 | 378
15 | AP-4 | 3A/6 | DA+0 |  |  |  |  | 5.5772 | Approved | Completed | Completed | Completed
[6 empty] | 3A/6 | 391.467
16 |  | 3B/0 | DB1+9 |  |  |  |  | 5.9687 | Approved | Completed | Completed | Completed
[6 empty] | 3B/0 | 356
17 |  | 3B/1 | DA+3 |  |  |  |  | 6.3247 | Approved | Completed | Completed | Completed
[6 empty] | 3B/1 | 439
18 |  | 3B/2 | DA+9 |  |  |  |  | 6.7637 | Approved | Completed | Completed | Completed
[6 empty] | 3B/2 | 377
19 |  | 3B/3 | DA+6 |  |  |  |  | 7.1407 | Approved | Completed | Completed
[6 empty] | 3B/3 | 455.07 | [8 empty] | 39
20 |  | 4/0 | DB2+9 |  |  |  |  | 7.5958 | Approved | Completed | Completed | Completed
[6 empty] | 4/0 | 344.163
21 |  | 4/5 | DA+6 |  |  |  |  | 7.94 | Approved | Completed | Completed | Completed |  |  | NO CHANGE S
[6 empty] | 4/5 | 365
22 | AP- 4A/0 | 4A/0 | DB1+3 |  |  |  |  | 8.305 | Approved | Completed | Completed | Completed
[6 empty] | 4A/0 | 340
23 |  | 4A/1 | DA+6 |  |  |  |  | 8.645 | Approved | Completed | Completed | Completed
[6 empty] | 4A/1 | 419.999
24 |  | 4A/2 | DA+6 |  |  |  |  | 9.065 | Approved | Completed | Completed | Completed
[6 empty] | 4A/2 | 415
25 |  | 4A/3 | DA+9 |  |  |  |  | 9.48 | Approved | Completed | Completed | Completed
[6 empty] | 4A/3 | 365
26 |  | 4A/4 | DA+6 |  |  |  |  | 9.845 | Approved | Completed | Completed | Completed
[6 empty] | 4A/4 | 330
27 |  | 4A/5 | DA+9 |  |  |  |  | 10.175 | Approved | Completed | Completed | Completed
[6 empty] | 4A/5 | 457
28 |  | 4A/6 | DA+9 |  |  |  |  | 10.632 | Approved | Completed | Completed | Completed
[6 empty] | 4A/6 | 354.612
29 | AP5 | 5/0 | DB1+6 |  |  |  |  | 10.9866 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 5/0 | 428.389
30 |  | 5/1 | DA+6 |  |  |  |  | 11.415 | Approved | Completed | Completed | Completed
[6 empty] | 5/1 | 340
31 |  | 5/2 | DA+9 |  |  |  |  | 11.755 | Approved | Completed | Completed | Completed
[6 empty] | 5/2 | 375
32 |  | 5/3 | DA+9 |  |  |  |  | 12.13 | Approved | Completed | Completed | Completed
[6 empty] | 5/3 | 365
33 |  | 5/4 | DA-1.5 |  |  |  |  | 12.495 | Approved | Completed | Completed | Completed
[6 empty] | 5/4 | 460
34 |  | 5/5 | DA+6 |  |  |  |  | 12.955 | Approved | Completed | Completed | Completed
[6 empty] | 5/5 | 380
35 |  | 5/6 | DA+3 |  |  |  |  | 13.335 | Approved | Completed | Completed | Completed
[6 empty] | 5/6 | 410
36 |  | 5/7 | DA+9 |  |  |  |  | 13.745 | Approved | Completed | Completed | Completed
[6 empty] | 5/7 | 400
37 |  | 5/8 | DA+6 |  |  |  |  | 14.145 | Approved | Completed | Completed | Completed
[6 empty] | 5/8 | 420
38 |  | 5/9 | DA+6 |  |  |  |  | 14.565 | Approved | Completed | Completed | Completed
[6 empty] | 5/9 | 345
39 |  | 5/10 | DA+9 |  |  |  |  | 14.91 | Approved | Completed | Completed | Completed
[6 empty] | 5/10 | 495
40 | AP-5A | 5A/0 | DB1+12 |  |  |  |  | 15.405 | Approved | Completed | Completed | Completed
[6 empty] | 5A/0 | 419.48
41 | AP-6 | 6/0 | DB1+9 |  |  |  |  | 15.8245 | Approved | Completed | Completed | Completed
[6 empty] | 6/0 | 350.52
42 |  | 6/1 | DA+9 |  |  |  |  | 16.175 | Approved | Completed | Completed | Completed
[6 empty] | 6/1 | 445
43 |  | 6/2 | DA+6 |  |  |  |  | 16.62 | Approved | Completed | Completed | Completed
[6 empty] | 6/2 | 390
44 |  | 6/3 | DA+3 |  |  |  |  | 17.01 | Approved | Completed | Completed | Completed
[6 empty] | 6/3 | 350
45 |  | 6/4 | DA+9 |  |  |  |  | 17.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/4 | 490
46 |  | 6/5 | DA+9 |  |  |  |  | 17.85 | Approved | Completed | Completed | Completed
[6 empty] | 6/5 | 350
47 |  | 6/6 | DA-3 |  |  |  |  | 18.2 | Approved | Completed | Completed | Completed
[6 empty] | 6/6 | 347
48 |  | 6/7 | DA+1.5 |  |  |  |  | 18.547 | Approved | Completed | Completed | Completed
[6 empty] | 6/7 | 373
49 |  | 6/8 | DA+3 |  |  |  |  | 18.92 | Approved | Completed | Completed | Completed
[6 empty] | 6/8 | 380
50 |  | 6/9 | DA+6 |  |  |  |  | 19.3 | Approved | Completed | Completed | Completed
[6 empty] | 6/9 | 335
51 |  | 6/10 | DA+1.5 |  |  |  |  | 19.635 | Approved | Completed | Completed | Completed
[6 empty] | 6/10 | 315
52 |  | 6/11 | DA-1.5 |  |  |  |  | 19.95 | Approved | Completed | Completed | Completed
[6 empty] | 6/11 | 410
53 |  | 6/12 | DA+1.5 |  |  |  |  | 20.36 | Approved | Completed | Completed | Completed
[6 empty] | 6/12 | 365.716
54 | AP-7 | 7/0 | DB2+0 |  |  |  |  | 20.7257 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7/0 | 319.284
55 |  | 7/1 | DA-3 |  |  |  |  | 21.045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/1 | 465
56 |  | 7/2 | DA+6 |  |  |  |  | 21.51 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/2 | 375
57 |  | 7/3 | DA+9 |  |  |  |  | 21.885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/3 | 355
58 |  | 7/4 | DA+6 |  |  |  |  | 22.24 | Approved | Completed | Completed | Completed
[6 empty] | 7/4 | 420
59 |  | 7/5 | DA+6 |  |  |  |  | 22.66 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/5 | 315
60 |  | 7/6 | DA-1.5 |  |  |  |  | 22.975 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7/6 | 450
61 | AP-7A | 7A/0 | DB1+6 |  |  |  |  | 23.425 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/0 | 435
62 |  | 7A/1 | DA+1.5 |  |  |  |  | 23.86 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/1 | 385
63 |  | 7A/2 | DA+3 |  |  |  |  | 24.245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/2 | 390
64 |  | 7A/3 | DA+3 |  |  |  |  | 24.635 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/3 | 405
65 |  | 7A/4 | DA+3 |  |  |  |  | 25.04 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 7A/4 | 390
66 |  | 7A/5 | DA+3 |  |  |  |  | 25.43 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 7A/5 | 429.77
67 | AP-8 | 8/0 | DB1+0 |  |  |  |  | 25.8598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/0 | 350
68 |  | 8/1 | DA-3 |  |  |  |  | 26.2098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/1 | 330
69 |  | 8/2 | DA+6 |  |  |  |  | 26.5398 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/2 | 390
70 |  | 8/3 | DA+9 |  |  |  |  | 26.9298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/3 | 400
71 |  | 8/4 | DA+6 |  |  |  |  | 27.3298 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/4 | 345
72 |  | 8/5 | DA+9 |  |  |  |  | 27.6748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/5 | 350
73 |  | 8/6 | DA+3 |  |  |  |  | 28.0248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/6 | 335
74 |  | 8/7 | DA+3 |  |  |  |  | 28.3598 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/7 | 415
75 |  | 8/8 | DA+9 |  |  |  |  | 28.7748 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/8 | 375
76 |  | 8/9 | DA+3 |  |  |  |  | 29.1498 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/9 | 375
77 |  | 8/10 | DA+0 |  |  |  |  | 29.5248 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/10 | 375
78 |  | 8/11 | DA+9 |  |  |  |  | 29.8998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8/11 | 415
79 | AP-8A | 8A/0 | DB1+12 |  |  |  |  | 30.3148 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 8A/0 | 466.629
80 | AP-9 | 9/0 | DB1+12 |  |  |  |  | 30.7814 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 9/0 | 418.372
81 |  | 9/1 | DA+3 |  |  |  |  | 31.1998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/1 | 410
82 |  | 9/2 | DA+3 |  |  |  |  | 31.6098 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/2 | 395
83 |  | 9/3 | DA+0 |  |  |  |  | 32.0048 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/3 | 395
84 |  | 9/4 | DA+6 |  |  |  |  | 32.3998 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 9/4 | 425
85 |  | 9/5 | DA+3 |  |  |  |  | 32.8248 | Approved | Completed | Completed | Completed
[6 empty] | 9/5 | 415
86 |  | 9/6 | DA+3 |  |  |  |  | 33.2398 | Approved | Completed | Completed | Completed
[6 empty] | 9/6 | 405
87 |  | 9/7 | DA+9 |  |  |  |  | 33.6448 | Approved | Completed | Completed | Completed
[6 empty] | 9/7 | 435
90 |  | 9/8 | DA+0 |  |  |  |  | 34.0798 | Approved | Completed | Completed
[6 empty] | 9/8 | 405
89 |  | 9/9 | DA+0 |  |  |  |  | 34.4848 | Approved | Completed | Completed
[6 empty] | 9/9 | 435
90 |  | 9/10 | DA+3 |  |  |  |  | 34.9198 | Approved | Completed | Completed
[6 empty] | 9/10 | 395
91 |  | 9/11 | DA+3 |  |  |  |  | 35.3148 | Approved | Completed | Completed | Completed
[6 empty] | 9/11 | 431.548
92 | AP-10 | 10/0 | DB1+6 |  |  |  |  | 35.7463 | Approved | Completed | Completed | Completed
[6 empty] | 10/0 | 363.452
93 |  | 10/1 | DA+3 |  |  |  |  | 36.1098 | Approved | Completed | Completed | Completed
[6 empty] | 10/1 | 295
94 |  | 10/2 | DA+3 |  |  |  |  | 36.4048 | Approved | Completed | Completed
[6 empty] | 10/2 | 345.731
95 | AP-11 | 11/0 | DD45+0 |  |  |  |  | 36.7505 | Approved | Completed | Completed
[6 empty] | 11/0 | 242.893 | [7 empty] | NH
96 | AP-12 | 12/0 | DB1+9 |  |  |  |  | 36.9934 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 12/0 | 329.728 | [7 empty] | 132 KV PL
97 | AP-13 | 13/0 | DD60+9 |  |  |  |  | 37.3231 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 13/0 | 416.878
98 | AP-13A | 13A/0 | DB1+9 |  |  |  |  | 37.74 | Approved | Completed | Completed
[6 empty] | 13A/0 | 480.269
99 | AP-14 | 14/0 | DD60+18 |  | 2 |  |  | 38.2203 | Approved | Completed | Completed
[6 empty] | 14/0 | 223.816 | [7 empty] | 400 KV PL
100 | AP-15 | 15/0 | DD60+25 |  |  |  |  | 38.4441 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 15/0 | 405.915
101 |  | 15/1 | DA+6 |  |  |  |  | 38.85 | Approved | Completed | Completed
[6 empty] | 15/1 | 405
102 |  | 15/2 | DA+3 |  |  |  |  | 39.255 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/2 | 420
103 |  | 15/3 | DA+3 |  |  |  |  | 39.675 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/3 | 415
104 |  | 15/4 | DA+6 |  |  |  |  | 40.09 | Approved | Completed | Completed | Completed
[6 empty] | 15/4 | 410
105 |  | 15/5 | DA+3 |  |  |  |  | 40.5 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/5 | 285
106 |  | 15/6 | DA+9 |  |  |  |  | 40.785 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 15/6 | 355
107 |  | 15/7 | DA+0 |  |  |  |  | 41.14 | Approved | Completed | Completed
[6 empty] | 15/7 | 355
108 |  | 15/8 | DA+1.5 |  |  |  |  | 41.495 | Approved | Completed | Completed | Completed
[6 empty] | 15/8 | 410
109 |  | 15/9 | DA+0 |  |  |  |  | 41.905 | Approved | Completed | Completed
[6 empty] | 15/9 | 430
110 |  | 15/10 | DA-1.5 |  |  |  |  | 42.335 | Approved | Completed | Completed
[6 empty] | 15/10 | 385
111 |  | 15/11 | DA+0 |  |  |  |  | 42.72 | Approved | Completed | Completed
[6 empty] | 15/11 | 455
112 |  | 15/12 | DA+6 |  |  |  |  | 43.175 | Approved | Completed
[6 empty] | 15/12 | 288.425
113 | AP-16 | 16/0 | DC2+0 |  |  |  |  | 43.4634 | Approved | Completed
[6 empty] | 16/0 | 392.694 | [7 empty] | 11KV LINE
114 | AP-17 | 17/0 | DC1+3 |  |  |  |  | 43.8561 | Approved | Completed | Completed
[6 empty] | 17/0 | 398.404 | [7 empty] | 11KV LINE
115 | AP-18 | 18/0 | DB2+6 |  |  |  |  | 44.2545 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 18/0 | 307.595
116 |  | 18/1 | DA+3 |  |  |  |  | 44.5621 | Approved | Completed | Completed | Completed
[6 empty] | 18/1 | 390
117 |  | 18/2 | DA+1.5 |  |  |  |  | 44.9521 | Approved | Completed | Completed | Completed
[6 empty] | 18/2 | 380
118 |  | 18/3 | DA+6 |  |  |  |  | 45.3321 | Approved | Completed | Completed | Completed
[6 empty] | 18/3 | 405
119 |  | 18/4 | DA-3 |  |  |  |  | 45.7371 | Approved | Completed | Completed | Completed
[6 empty] | 18/4 | 335
120 |  | 18/5 | DA+0 |  |  |  |  | 46.0721 | Approved | Completed | Completed | Completed
[6 empty] | 18/5 | 425
121 |  | 18/6 | DA+9 |  |  |  |  | 46.4971 | Approved | Completed | Completed | Completed
[6 empty] | 18/6 | 402
122 |  | 18/7 | DA+1.5 |  |  |  |  | 46.8991 | Approved | Completed | Completed | Completed
[6 empty] | 18/7 | 385.434
123 | AP-19 | 19/0 | DD60+3 |  |  |  |  | 47.2845 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 19/0 | 279.36 | [7 empty] | Rly
124 | AP-20 | 20/0 | DD60+3 |  |  |  |  | 47.5639 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 20/0 | 388.515
125 |  | 20/1 | DA-3 |  |  |  |  | 47.9524 | Approved | Completed | Completed | Completed
[6 empty] | 20/1 | 330
126 |  | 20/2 | DA-3 |  |  |  |  | 48.2824 | Approved | Completed | Completed | Completed
[6 empty] | 20/2 | 340
127 |  | 20/3 | DA+1.5 |  |  |  |  | 48.6224 | Approved | Completed | Completed
[6 empty] | 20/3 | 420
128 |  | 20/4 | DA+3 |  |  |  |  | 49.0424 | Approved | Completed | Completed
[6 empty] | 20/4 | 375
129 |  | 20/5 | DA+0 |  |  |  |  | 49.4174 | Approved | Completed | Completed | Completed
[6 empty] | 20/5 | 355
130 |  | 20/6 | DA-3 |  |  |  |  | 49.7724 | Approved | Completed | Completed | Completed
[6 empty] | 20/6 | 341.652
131 | AP-21 | 21/0 | DB1+0 |  |  |  |  | 50.1141 | Approved | Completed | Completed | Completed
[6 empty] | 21/0 | 326.348
132 |  | 21/1 | DA+0 |  |  |  |  | 50.4404 | Approved | Completed | Completed | Completed
[6 empty] | 21/1 | 427
133 |  | 21/2 | DA+6 |  |  |  |  | 50.8674 | Approved | Completed | Completed
[6 empty] | 21/2 | 410
134 |  | 21/3 | DA+6 |  |  |  |  | 51.2774 | Approved | Completed | Completed
[6 empty] | 21/3 | 405
135 |  | 21/4 | DA+0 |  |  |  |  | 51.6824 | Approved | Completed | Completed
[6 empty] | 21/4 | 300
136 |  | 21/5 | DA+0 |  |  |  |  | 51.9824 | Approved | Completed | Completed
[6 empty] | 21/5 | 415.187
137 | AP-22 | 22/0 | DC2+15 |  |  |  |  | 52.3976 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 22/0 | 259.048 | [7 empty] | 220 kv PL
138 | AP-23 | 23/0 | DB2+9 |  |  |  |  | 52.6566 | Approved | Completed | Completed
[6 empty] | 23/0 | 440.455
139 | AP-23A | 23A/0 | DB1+9 |  |  |  |  | 53.0971 | Approved | Completed | Completed
[6 empty] | 23A/0 | 496.685
140 | AP-24 | 24/0 | DD60+18 |  |  |  |  | 53.5938 | Approved | Completed | Completed
[6 empty] | 24/0 | 244.029 | [7 empty] | 400 kv PL
141 | AP-25 | 25/0 | DD60+18 |  |  |  |  | 53.8378 | Approved | Completed | Completed
[6 empty] | 25/0 | 237.428
142 | AP-26 | 26/0 | DD60+35 |  |  |  |  | 54.0752 | Approved | Completed | Completed
[6 empty] | 26/0 | 203.479 | [7 empty] | 765 kv PL
143 | AP-27 | 27/0 | DD60+35 |  |  |  |  | 54.2787 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 27/0 | 453.688
144 |  | 27/1 | DA+9 |  |  |  |  | 54.7324 | Approved | Completed | Completed
[6 empty] | 27/1 | 345
145 |  | 27/2 | DA-1.5 |  |  |  |  | 55.0774 | Approved | Completed | Completed
[6 empty] | 27/2 | 360
146 |  | 27/3 | DA+1.5 |  |  |  |  | 55.4374 | Approved | Completed | Completed
[6 empty] | 27/3 | 410
147 |  | 27/4 | DA+1.5 |  |  |  |  | 55.8474 | Approved | Completed | Completed
[6 empty] | 27/4 | 350
148 |  | 27/5 | DA-1.5 |  |  |  |  | 56.1974 | Approved | Completed | Completed | Completed
[6 empty] | 27/5 | 355
149 |  | 27/6 | DA-3 |  |  |  |  | 56.5524 | Approved | Completed | Completed
[6 empty] | 27/6 | 274.587
150 | AP-28 | 28/0 | DC2-3 |  |  |  |  | 56.827 | Approved | Completed | Completed
[6 empty] | 28/0 | 211.209 | [7 empty] | NH
151 | AP-29 | 29/0 | DC1+0 |  |  |  |  | 57.0382 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 29/0 | 384.204
152 |  | 29/1 | DA+6 |  |  |  |  | 57.4224 | Approved | Completed | Completed | Completed
[6 empty] | 29/1 | 430
153 |  | 29/2 | DA+0 |  |  |  |  | 57.8524 | Approved | Completed | Completed
[6 empty] | 29/2 | 370
154 |  | 29/3 | DA+0 |  |  |  |  | 58.2224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/3 | 390
155 |  | 29/4 | DA+3 |  |  |  |  | 58.6124 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/4 | 435
156 |  | 29/5 | DA+0 |  |  |  |  | 59.0474 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29/5 | 370
157 | AP-29A/0 | 29A/0 | DB1+0 |  |  |  |  | 59.4174 | Approved | Completed | Completed | Completed
[6 empty] | 29A/0 | 455
158 |  | 29A/1 | DA+6 |  |  |  |  | 59.8724 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/1 | 325
159 |  | 29A/2 | DA+6 |  |  |  |  | 60.1974 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/2 | 395
160 |  | 29A/3 | DA+6 |  |  |  |  | 60.5924 | Approved | Completed | Completed
[6 empty] | 29A/3 | 345
161 |  | 29A/4 | DA+3 |  |  |  |  | 60.9374 | Approved | Completed | Completed | Completed
[6 empty] | 29A/4 | 365
162 |  | 29A/5 | DA+6 |  |  |  |  | 61.3024 | Approved | Completed | Completed | Completed
[6 empty] | 29A/5 | 420
163 |  | 29A/6 | DA+9 |  |  |  |  | 61.7224 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 29A/6 | 364.007
164 | AP-30 | 30/0 | DB1+0 |  |  |  |  | 62.0864 | Approved | Completed | Completed | Completed
[6 empty] | 30/0 | 295.993
165 |  | 30/1 | DA+0 |  |  |  |  | 62.3824 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 30/1 | 425
166 |  | 30/2 | DA+9 |  |  |  |  | 62.8074 | Approved | Completed | Completed | Completed
[6 empty] | 30/2 | 315
167 |  | 30/3 | DA+3 |  |  |  |  | 63.1224 | Approved | Completed | Completed | Completed
[6 empty] | 30/3 | 380
168 |  | 30/4 | DA+9 |  |  |  |  | 63.5024 | Approved | Completed | Completed | Completed
[6 empty] | 30/4 | 430
169 |  | 30/5 | DA+0 |  |  |  |  | 63.9324 | Approved | Completed | Completed
[6 empty] | 30/5 | 380
170 |  | 30/6 | DA+6 |  |  |  |  | 64.3124 | Approved | Completed | Completed | Completed
[6 empty] | 30/6 | 335
171 |  | 30/7 | DA-3 |  |  |  |  | 64.6474 | Approved | Completed | Completed | Completed
[6 empty] | 30/7 | 395
172 |  | 30/8 | DA+3 |  |  |  |  | 65.0424 | Approved | Completed | Completed | Completed
[6 empty] | 30/8 | 390
173 |  | 30/9 | DA-3 |  |  |  |  | 65.4324 | Approved | Completed | Completed | Completed
[6 empty] | 30/9 | 350
174 |  | 30/10 | DA+3 |  |  |  |  | 65.7824 | Approved | Completed | Completed | Completed
[6 empty] | 30/10 | 428.239
175 | AP-31 | 31/0 | DB1+0 |  |  |  |  | 66.2106 | Approved | Completed | Completed | Completed
[6 empty] | 31/0 | 376.761
176 |  | 31/1 | DA+3 |  |  |  |  | 66.5874 | Approved | Completed | Completed | Completed
[6 empty] | 31/1 | 410
177 |  | 31/2 | DA+1.5 |  |  |  |  | 66.9974 | Approved | Completed | Completed | Completed
[6 empty] | 31/2 | 430
178 |  | 31/3 | DA+3 |  |  |  |  | 67.4274 | Approved | Completed | Completed | Completed
[6 empty] | 31/3 | 380
179 |  | 31/4 | DA-1.5 |  |  |  |  | 67.8074 | Approved | Completed | Completed | Completed
[6 empty] | 31/4 | 445
180 |  | 31/5 | DA+6 |  |  |  |  | 68.2524 | Approved | Completed | Completed | Completed
[6 empty] | 31/5 | 385
181 |  | 31/6 | DA+9 |  |  |  |  | 68.6374 | Approved | Completed | Completed | Completed
[6 empty] | 31/6 | 420
182 |  | 31/7 | DA+0 |  |  |  |  | 69.0574 | Approved | Completed | Completed | Completed
[6 empty] | 31/7 | 415
183 |  | 31/8 | DA+0 |  |  |  |  | 69.4724 | Approved | Completed | Completed | Completed
[6 empty] | 31/8 | 310
184 |  | 31/9 | DA+1.5 |  |  |  |  | 69.7824 | Approved | Completed | Completed | Completed
[6 empty] | 31/9 | 445
185 |  | 31/10 | DA+4.5 |  |  |  |  | 70.2274 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 31/10 | 316.608
186 | AP-32 | 32/0 | DB2+0 |  |  |  |  | 70.544 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/0 | 385.51
187 |  | 32/1 | DA+6 |  |  |  |  | 70.9295 | Approved | Completed | Completed | Completed
[6 empty] | 32/1 | 390
188 |  | 32/2 | DA+9 |  |  |  |  | 71.3195 | Approved | Completed | Completed | Completed
[6 empty] | 32/2 | 410
189 |  | 32/3 | DA+6 |  |  |  |  | 71.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/3 | 430
190 |  | 32/4 | DA+9 |  |  |  |  | 72.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/4 | 390
191 |  | 32/5 | DA+9 |  | 2 |  |  | 72.5495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/5 | 439
192 |  | 32/6 | DA+9 |  | 2 |  |  | 72.9885 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/6 | 360
193 |  | 32/7 | DA+3 |  |  |  |  | 73.3485 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32/7 | 479
194 | AP-32A/0 | 32A/0 | DB1+9 |  |  |  |  | 73.8275 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 32A/0 | 402
195 |  | 32A/1 | DA+6 |  |  |  |  | 74.2295 | Approved | Completed | Completed | Completed
[6 empty] | 32A/1 | 438.439
196 | AP-33 | 33/0 | DB1+9 |  | 2 |  |  | 74.6679 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 33/0 | 441.561
197 |  | 33/1 | DA+9 |  | 2 |  |  | 75.1095 | Approved | Completed | Completed | Completed
[6 empty] | 33/1 | 395
198 |  | 33/2 | DA+9 |  |  |  |  | 75.5045 | Approved | Completed | Completed | Completed
[6 empty] | 33/2 | 435
199 |  | 33/3 | DA+3 |  |  |  |  | 75.9395 | Approved | Completed | Completed | Completed
[6 empty] | 33/3 | 405
200 |  | 33/4 | DA+3 |  |  |  |  | 76.3445 | Approved | Completed | Completed | Completed
[6 empty] | 33/4 | 420
201 |  | 33/5 | DA+0 |  |  |  |  | 76.7645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/5 | 405
202 |  | 33/6 | DA+6 |  |  |  |  | 77.1695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/6 | 415
203 |  | 33/7 | DA+6 |  |  |  |  | 77.5845 | Approved | Completed | Completed | Completed
[6 empty] | 33/7 | 355
204 |  | 33/8 | DA+3 |  |  |  |  | 77.9395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 33/8 | 380
205 |  | 33/9 | DA+1.5 |  |  |  |  | 78.3195 | Approved | Completed | Completed | Completed
[6 empty] | 33/9 | 398.203
206 | AP-34 | 34/0 | DB1+6 |  |  |  |  | 78.7177 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 34/0 | 441.798
207 |  | 34/1 | DA+9 |  |  |  |  | 79.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/1 | 395
208 |  | 34/2 | DA+9 |  |  |  |  | 79.5545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/2 | 375
209 |  | 34/3 | DA+1.5 |  |  |  |  | 79.9295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/3 | 445
210 |  | 34/4 | DA+6 |  |  |  |  | 80.3745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/4 | 395
211 |  | 34/5 | DA+9 |  |  |  |  | 80.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/5 | 435
212 |  | 34/6 | DA+3 |  |  |  |  | 81.2045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/6 | 330
213 |  | 34/7 | DA+0 |  |  |  |  | 81.5345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/7 | 330
214 |  | 34/8 | DA+0 |  |  |  |  | 81.8645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/8 | 400
215 |  | 34/9 | DA+1.5 |  |  |  |  | 82.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/9 | 310
216 |  | 34/10 | DA-3 |  |  |  |  | 82.5745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/10 | 315
217 |  | 34/11 | DA+1.5 |  |  |  |  | 82.8895 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/11 | 375
218 |  | 34/12 | DA+3 |  |  |  |  | 83.2645 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 34/12 | 351.79
219 | AP-35 | 35/0 | DB2+0 |  |  |  |  | 83.6163 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 35/0 | 393.209
220 |  | 35/1 | DA+6 |  |  |  |  | 84.0095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/1 | 435
221 |  | 35/2 | DA+6 |  |  |  |  | 84.4445 | Approved | Completed |  | Completed
[6 empty] | 35/2 | 390
222 |  | 35/3 | DA-3 |  |  |  |  | 84.8345 | Approved | Completed
[6 empty] | 35/3 | 405
223 |  | 35/4 | DA+9 |  |  |  |  | 85.2395 | Approved | Completed | Completed | Completed
[6 empty] | 35/4 | 435
224 |  | 35/5 | DA+9 |  |  |  |  | 85.6745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/5 | 360
225 |  | 35/6 | DA+6 |  |  |  |  | 86.0345 | Approved | Completed | Completed | Completed
[6 empty] | 35/6 | 395
226 |  | 35/7 | DA+3 |  |  |  |  | 86.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/7 | 440
227 |  | 35/8 | DA+6 |  |  |  |  | 86.8695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 35/8 | 400
228 |  | 35/9 | DA+1.5 |  |  |  |  | 87.2695 | Approved | Completed | Completed | Completed
[6 empty] | 35/9 | 440
229 |  | 35/10 | DA+3 |  |  |  |  | 87.7095 | Approved | Completed
[6 empty] | 35/10 | 330
230 |  | 35/11 | DA+3 |  |  |  |  | 88.0395 | Approved | Completed | Completed | Completed
[6 empty] | 35/11 | 493.084
231 | AP-36 | 36/0 | DB2+3 |  |  |  |  | 88.5326 | Approved | Completed | Completed |  |  | Completed
[6 empty] | 36/0 | 453.999
232 |  | 36A/0 | DB1+9 |  |  |  |  | 88.9866 | Approved | Completed |  | Completed
[6 empty] | 36A/0 | 451
233 |  | 36A/1 | DA+3 |  |  |  |  | 89.4376 | Approved | Completed | Completed | Completed
[6 empty] | 36A/1 | 389
234 |  | 36A/2 | DA+9 |  |  |  |  | 89.8266 | Approved | Completed | Completed | Completed
[6 empty] | 36A/2 | 451.523
235 | AP-37 | 37/0 | DB2+3 |  |  |  |  | 90.2781 | Approved | Completed | Completed
[6 empty] | 37/0 | 401.394
236 |  | 37/1 | DA+3 |  |  |  |  | 90.6795 | Approved | Completed | Completed
[6 empty] | 37/1 | 430
237 |  | 37/2 | DA+3 |  |  |  |  | 91.1095 | Approved | Completed | Completed
[6 empty] | 37/2 | 405
238 |  | 37/3 | DA-1.5 |  |  |  |  | 91.5145 | Approved | Completed | Completed
[6 empty] | 37/3 | 430
239 |  | 37/4 | DA+9 |  |  |  |  | 91.9445 | Approved | Completed | Completed | Completed
[6 empty] | 37/4 | 410
240 |  | 37/5 | DA+3 |  |  |  |  | 92.3545 | Approved | Completed | Completed | Completed
[6 empty] | 37/5 | 420
241 | AP-37A | 37A/0 | DB1+0 |  |  |  |  | 92.7745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/0 | 280
242 |  | 37A/1 | DA+3 |  |  |  |  | 93.0545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/1 | 345
243 |  | 37A/2 | DA+1.5 |  |  |  |  | 93.3995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/2 | 330
244 |  | 37A/3 | DA+3 |  |  |  |  | 93.7295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/3 | 455
245 |  | 37A/4 | DA+9 |  |  |  |  | 94.1845 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 37A/4 | 340
246 |  | 37A/5 | DA+3 |  |  |  |  | 94.5245 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/5 | 435
247 |  | 37A/6 | DA+3 |  |  |  |  | 94.9595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 37A/6 | 398.589
248 | AP-38 | 38/0 | DB1+3 |  |  |  |  | 95.3581 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/0 | 426.411
249 |  | 38/1 | DA+0 |  |  |  |  | 95.7845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/1 | 390
250 |  | 38/2 | DA+0 |  |  |  |  | 96.1745 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/2 | 335
251 |  | 38/3 | DA+3 |  |  |  |  | 96.5095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/3 | 440
252 |  | 38/4 | DA+1.5 |  |  |  |  | 96.9495 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/4 | 280
253 |  | 38/5 | DA+3 |  |  |  |  | 97.2295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/5 | 450
254 |  | 38/6 | DA+6 |  |  |  |  | 97.6795 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/6 | 285
255 |  | 38/7 | DA+9 |  |  |  |  | 97.9645 | Approved | Completed | Completed | Completed
[6 empty] | 38/7 | 445
256 |  | 38/8 | DA+1.5 |  |  |  |  | 98.4095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/8 | 360
257 |  | 38/9 | DA+0 |  |  |  |  | 98.7695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/9 | 430
258 |  | 38/10 | DA+3 |  |  |  |  | 99.1995 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 38/10 | 322.266
259 | AP-39 | 39/0 | DB2+0 |  |  |  |  | 99.5218 | Approved | Completed | Completed | Completed | Completed | Completed
[6 empty] | 39/0 | 392.73
260 |  | 39/1 | DA-1.5 |  |  |  |  | 99.9145 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/1 | 395
261 |  | 39/2 | DA+3 |  |  |  |  | 100.3095 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/2 | 385
262 |  | 39/3 | DA+1.5 |  |  |  |  | 100.6945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/3 | 340
263 |  | 39/4 | DA+3 |  |  |  |  | 101.0345 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/4 | 395
264 |  | 39/5 | DA+1.5 |  |  |  |  | 101.4295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/5 | 410
265 |  | 39/6 | DA+1.5 |  |  |  |  | 101.8395 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/6 | 415
266 |  | 39/7 | DA+3 |  |  |  |  | 102.2545 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/7 | 415
267 |  | 39/8 | DA+1.5 |  |  |  |  | 102.6695 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/8 | 350
268 |  | 39/9 | DA+6 |  |  |  |  | 103.0195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/9 | 425
269 |  | 39/10 | DA+3 |  |  |  |  | 103.4445 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/10 | 350
270 |  | 39/11 | DA+6 |  |  |  |  | 103.7945 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 39/11 | 444.081
271 | AP-40 | 40/0 | DB1+6 |  |  |  |  | 104.2386 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 40/0 | 260.918
272 |  | 40/1 | DA+9 |  | 2 |  |  | 104.4995 | Approved | Completed |  | Completed
[6 empty] | 40/1 | 385
273 |  | 40/2 | DA+6 |  |  |  |  | 104.8845 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/2 | 435
274 |  | 40/3 | DA+3 |  |  |  |  | 105.3195 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/3 | 385
275 |  | 40/4 | DA+6 |  |  |  |  | 105.7045 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/4 | 455
276 |  | 40/5 | DA+9 |  |  |  |  | 106.1595 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/5 | 370
277 |  | 40/6 | DA+9 |  |  |  |  | 106.5295 | Approved | Completed | Completed | Completed | Completed
[6 empty] | 40/6 | 400
278 |  | 40/7 | DA+3 |  |  |  |  | 106.9295 | Approved | Completed | Completed | Completed
[6 empty] | 40/7 | 350
279 |  | 40/8 | DA-1.5 |  |  |  |  | 107.2795 | Approved | Completed | Completed | Completed
[6 empty] | 40/8 | 470
280 |  | 40/9 | DA+9 |  |  |  |  | 107.7495 | Approved | Completed | Completed | Completed
[6 empty] | 40/9 | 355
281 |  | 40/10 | DA+3 |  |  |  |  | 108.1045 | Approved | Completed | Completed | Completed
[6 empty] | 40/10 | 485
282 |  | 40/11 | DA+9 |  |  |  |  | 108.5895 | Approved | Completed | Completed | Completed
[6 empty] | 40/11 | 315
283 | AP-40A | 40A/0 | DB1+9 |  |  |  |  | 108.9045 | Approved | Completed | Completed | Completed
[6 empty] | 40A/0 | 410.607
284 | AP-41 | 41/0 | DB1+9 |  |  |  |  | 109.3151 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 41/0 | 358
285 |  | 41/1 | DA+9 |  |  |  |  | 109.6731 | Approved | Completed |  | Completed
[6 empty] | 41/1 | 465.782
286 | AP-42 | 42/0 | DB2+0 |  |  |  |  | 110.1389 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 42/0 | 419.998
287 |  | 42/1 | DA+3 |  |  |  |  | 110.5589 | Approved | Completed | Completed | Completed
[6 empty] | 42/1 | 375
288 |  | 42/2 | DA+9 |  |  |  |  | 110.9339 | Approved | Completed | Completed | Completed
[6 empty] | 42/2 | 464
289 |  | 42/3 | DB1+9 |  |  |  |  | 111.3979 | Approved | Completed | Completed | Completed
[6 empty] | 42/3 | 424.891
290 | AP-43 | 43/0 | DB1+0 |  |  |  |  | 111.8228 | Approved | Completed
[6 empty] | 43/0 | 341.866
291 |  | 43/1 | DA-1.5 |  |  |  |  | 112.1647 | Approved | Completed
[6 empty] | 43/1 | 375
292 |  | 43/2 | DA+6 |  |  |  |  | 112.5397 | Approved | Completed | Completed | Completed |  | Completed
[6 empty] | 43/2 | 375
293 |  | 43/3 | DA-1.5 |  |  |  |  | 112.9147 | Approved | Completed | Completed | Completed
[6 empty] | 43/3 | 355
294 |  | 43/4 | DA+0 |  |  |  |  | 113.2697 | Approved | Completed | Completed | Completed
[6 empty] | 43/4 | 405
295 |  | 43/5 | DC2+0 |  |  |  |  | 113.6747 | Approved | Completed |  |  |  |  | TP tower modified cross arms
[6 empty] | 43/5 | 375
296 |  | 43/6 | DA+3 |  |  |  |  | 114.0497 | Approved | Completed | Completed | Completed
[6 empty] | 43/6 | 385
297 |  | 43/7 | DA+0 |  |  |  |  | 114.4347 | Approved | Completed | Completed | Completed
[6 empty] | 43/7 | 415
298 |  | 43/8 | DA+9 |  |  |  |  | 114.8497 | Approved | Completed | Completed | Completed
[6 empty] | 43/8 | 409.546
299 | AP-44 | 44/0 | DB1+6 |  |  |  |  | 115.2592 | Approved | Completed |  | Completed
[6 empty] | 44/0 | 400
300 |  | 44/1 | DA+3 |  |  |  |  | 115.6592 | Approved | Completed | Completed | Completed
[6 empty] | 44/1 | 427
301 |  | 44/2 | DA+3 |  |  |  |  | 116.0862 | Approved | Completed | Completed | Completed
[6 empty] | 44/2 | 366
302 |  | 44/3 | DA+3 |  |  |  |  | 116.4522 | Approved | Completed | Completed | Completed
[6 empty] | 44/3 | 350
303 |  | 44/4 | DA+0 |  |  |  |  | 116.8022 | Approved | Completed | Completed | Completed
[6 empty] | 44/4 | 383
304 |  | 44/5 | DA+0 |  |  |  |  | 117.1852 | Approved | Completed | Completed | Completed
[6 empty] | 44/5 | 457.155
305 | AP45 | 45/0 | DB1+9 |  |  |  |  | 117.6424 | Approved | Completed |  | Completed |  |  | PLC
[6 empty] | 45/0 | 208.53
306 | AP46 | 46/0 | DB1+12 | [5 empty] | Approved | Completed |  | Completed |  |  | PLC
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+0 to gantry
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DC2+0 to DD60+0
Note on D202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DD60+25 to DD60+18