## RawData
project_code | project_display | project_scope_key | line_name | line_name_source | section_label | report_date | source_file | source_sheet | configured_sheet | template_sheet | stringing_resolution_policy | header_row_number | source_row_number | activity_raw | activity_norm | quantity_loa | quantity_estimated_or_total | quantity_primary | cumulative_last_month | plan_for_month | progress_for_month | today_progress | cumulative_progress | balance_progress | gangs_working | remarks
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 11 | Route Alignment | route_alignment |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 12 | Detailed Survey | detailed_survey |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 13 | Check Survey | check_survey |  | 8.572 | 8.572 | 0 | 0 | 0 | 0 | 0 | 8.572 | 0.0 | 0
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 14 | Foundation | foundation |  | 37 | 37 | 0 | 0 |  | 5 | 3 | 25 | 3.0 | 12
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 15 | Earthing-Pipe | earthing |  | 7 | 7 | 0 | 0 | 0 |  |  | 2 |  | 5
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 16 | Earthing-CP/SE/CE | earthing |  | 30 | 30 | 0 | 0 | 0 | 5 |  | 8 |  | 22
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 17 | Tower Erection | tower_erection |  | 37 | 37 | 0 | 0 |  | 6 |  | 0 |  | 37
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 18 | Tack welding | tack_welding |  | 134 | 134 | 134 | 0 | 0 | 0 | 1 | 52 | 1.0 | 82
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 19 | Stringing | stringing |  | 8.572 | 8.572 | 0 | 0 |  | 0 |  | 0 |  | 8.572
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 20 | Paying Out | paying_out |  | 52.39 | 52.39 | 52.39 |  |  |  |  | 15.1581 |  | 50.853
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 21 | Final Sag | final_sag |  | 52.39 | 52.39 | 52.39 |  |  |  |  | 15.1581 |  | 50.853
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 22 | OPGW | opgw_stringing |  | 8.572 | 8.572 | 0 |  |  |  |  | 0 |  | 8.572
TA 310 | TA 310 | ta310 |  | filename | Progress Status of TW02: 400kV D/c Navasari-Kala Transmission Line. | 2026-01-12 | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | TA 310 Status |  | 9 | 23 | Foundation | foundation
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 14 | Soil Investigation | soil_investigation |  | 29 | 29 | 29 | 0 |  |  | 29 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 15 | Foundation | foundation |  | 484 | 484 | 484 | 0 |  |  | 484 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 16 | Earthing | earthing |  | 484 | 484 | 484 | 0 |  |  | 484 | 0 |  | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 17 | Tower Erection | tower_erection |  | 484 | 484 | 482 | 2 | 2 |  | 484 | 0 | 3.0 | Completed.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 18 | Tack welding | tack_welding |  | 484 | 484 | 441 | 43 | 26 | 1 | 467 | 17 | 4.0 | 4 No Location WIP.
TA 325 | TA 325 | ta325 |  | filename | Progress Status | 2026-01-19 | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | TA 325 Status |  | 13 | 19 | Stringing(Km) | stringing |  | 177.35 | 177.35 | 164.769 | 12.581 | 8.924 | 0 | 173.693 | 3.657 | 17.0 | 2.42 Km P/O and 2.42 Km F/S WIP
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 7 | Detail Survey (Km) | detail_survey_km | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 8 | Soil Investigation (Nos.) | soil_investigation | 29 | 29 | 29 | 26 |  | 0 | 0 | 26 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 9 | Check Survey approved(Km) | check_survey | 112.611 | 117.8509 | 117.8509 | 117.8509 |  | 0 | 0 | 117.8509 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 10 | Excavation | excavation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 11 | Foundation (Nos.) | foundation | 287 | 316 | 316 | 316 | 0 | 0 | 0 | 316 | 0 |  | Completed
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 12 | Earthing (Nos.) | earthing | 287 | 309 | 309 | 307 | 2 | 1 | 0 | 308 | 1 |  | G_1 Sanjay Construction 36A/0 ROW
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 13 | Tower Erection (Nos) | tower_erection | 287 | 306 | 306 | 302 | 4 | 1 | 0 | 303 | 3
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 14 | Tack Welding | tack_welding | 287 | 306 | 306 | 255 | 47 | 15 | 0 | 270 | 36 | 1.0 | G_1:- M.S Enterprises G_2:- M.B Sharma
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 16 | Stringing (Km) | stringing | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 | 3.0 | G_1:- Rahim Khan (AP 18/0 to AP 19/0) & (AP13/0 to AP14/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 17 | Paying Out | paying_out | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 |  | G_2:- SK infra (AP 35/0 to AP 36/0 ) & (AP40 to 40A/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 18 | Final Sag | final_sag | 112.611 | 117.8509 | 117.8509 | 77.189 | 21.51 | 10.051 | 0 | 87.24 | 30.6109 | 1.0 | G_3:- Gopal Associate (AP 24/0 to AP 25/0) G_4 Amir Sekh (AP23A/0 to AP24/0)
TA 413 | TA 413 | ta413 |  | filename | Office: Hansera, Bikaner, Rajasthan. | 2026-06-28 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | TA 413 Status |  | 6 | 19 | OPGW (Km) | opgw_stringing | 112.611 | 117.8509 | 117.8509 | 59.762 | 20 | 9.298 | 4.8 | 69.06 | 48.7909 | 1.0 | G_1 B.K Construction.
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 6 | Route Alignment (Km) | route_alignment |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 9 | Check Survey (Km) | check_survey |  | 127.799 | 127.799 | 127.799 |  |  |  | 127.799 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 28 | 28 | 28 |  |  |  | 28 | 0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 11 | Excavation | excavation |  | 352 | 352 | 319 | 31 | 17 |  | 336 | 16
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 12 | Foundation (Nos.) | foundation |  | 352 | 352 | 319 | 31 | 17 |  | 336 | 16 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 13 | Earthing (Nos.) | earthing |  | 352 | 352 | 296 | 31 | 36 | 1 | 332 | 20
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 352 | 352 | 235 | 44 | 30 | 2 | 265 | 87 | 16.0 | 1 gang arrived on 25.06.26
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 15 | Tack Welding | tack_welding |  | 352 | 352 | 120 | 55 | 61 |  | 181 | 171 | 3.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 16 | Stringing (Km) | stringing |  | 127.799 | 127.799 | 15.944 | 20 | 9.1022 |  | 25.0462 | 102.7528 | 4.0
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 17 | Paying Out | paying_out |  | 127.799 | 127.799 | 21.618 | 20 | 5.952 |  | 27.57 | 100.229
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 18 | Final Sag | final_sag |  | 127.799 | 127.799 | 15.944 | 20 | 9.1022 |  | 25.0462 | 102.7528
TA 414 | TA 414 | ta414 |  | filename | NOA Ref. No.: CC/T/W/-TW/DOM/A06/23/05757/NOA-2/24-103439/02, Dt.12.03.24 | 2026-06-29 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | TA 414 Status |  | 5 | 19 | OPGW (Km) | opgw_stringing |  | 127.799 | 127.799 | 0 | 20 |  |  | 0 | 127.799
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 21 | Foundation | foundation |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 22 | Earthing | earthing |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 23 | Erection | tower_erection |  | 302 | 302 | 302 | 0 | 0 | 0 | 302 | 0 | 0
TA 416 | TA 416 | ta416 |  | filename | Progress Status | 2026-06-25 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | TA 416 Status |  | 20 | 24 | Stringing | stringing |  | 115.134 | 115.134 | 111.1 | 4 | 3.319 | 0.372 | 114.458 | 0.676 | 4
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 20 | Foundation | foundation |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 21 | Earthing | earthing |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 22 | Tower Erection | tower_erection |  | 127 | 127 | 127 | 0 | 0 | 0 | 127 | 0 | 0
TA 418 | TA 418 | ta418 |  | filename | Progress Status | 2026-06-17 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | TA 418 Status |  | 19 | 23 | Stringing - RS | stringing |  | 47.84 | 47.84 | 29.582 | 18.258 | 1.6442 | 3.6311 | 31.2262 | 16.6138 | 5
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 120.21 | 122.071 | 122.071 | 121.41 | 0 | 0 |  | 121.41 | 0.661
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 120.21 | 122.071 | 122.071 | 122.07 | 0 | 0 |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 13 | Check Survey (Km) | check_survey | 120.21 | 122.071 | 122.071 | 122.07 |  |  |  | 122.07 | 0.001
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 14 | Soil Investigation (Nos) | soil_investigation | 31 | 31 | 31 | 31 | 0 |  |  | 31
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 15 | Excavation (Nos) | excavation | 322 | 331 | 331 | 167 |  |  |  | 167 | 164
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 16 | Foundation (Nos) | foundation | 322 | 331 | 331 | 255 | 49 | 15 |  | 270 | 61 | 14 | 38/4, 39/0, 47/0, 48/1, 50/0, 50/1 , 61/1, 63B/4 66/0, 79/0, 82/0, 86/0, 86/1, 87/1, 96/0, 96/2, 98/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 17 | Earthing (Nos) | earthing | 322 | 330 | 330 | 217 | 50 | 0 |  | 217 | 113
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 18 | Tower Erection (Nos) | tower_erection | 322 | 331 | 331 | 207 | 50 | 11 |  | 218 | 113 | 13 | 36/4, 37/0, 41/0, 44/0,52/1, 52/0, 54/0, 65/0, 65/2, 64/4, 71/0, 73/0, 75/0, 76/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 19 | Tack Welding (Nos) | tack_welding | 322 | 331 | 331 | 35 | 50 | 25 |  | 60 | 271 | 2
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 20 | Stringing (Km) | stringing | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 21 | Paying Out (Km) | paying_out | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | 3 | 0C/0-0D/0, 0D/0-0D/5, 0D/5-0E/0, 4/0-5/0, 5/0-6/0
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 22 | Final Sag (Km) | final_sag | 120.21 | 122.071 | 122.071 | 0.447 |  | 2.099 |  | 2.546 | 119.525 | `
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 23 | OPGW Stringing (Km) | opgw_stringing | 120.21 | 122.071 | 122.071 | 0 |  |  |  | 0 | 122.071
TA 419 | TA 419 | ta419 |  | filename | Completed Days | 2026-06-26 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | TA 419 Status |  | 8 | 26 | Power Line Crossings | power_line_crossings
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 19 | Foundation | foundation |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | Foundation Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 20 | Earthing | earthing |  | 309 | 309 | 303 | 6 | 0 |  | 303 | 6
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 21 | Tower Erection | tower_erection |  | 309 | 309 | 309 |  | 0 |  | 309 | 0 |  | TE Activity Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 22 | Tackwelding | tack_welding |  | 309 | 309 | 283 | 26 | 26 |  | 309 | 0 |  | Tackwelding Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 23 | Tower Tightening | tower_tightening |  | 309 | 309 | 309 |  |  |  | 309 | 0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 24 | Stringing -R/S | stringing |  | 121.342 | 121.342 | 116.433 | 4.912 | 4.9087 | 1.475 | 121.3417 |  |  | RS Completed
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 25 | Stringing -F/S | stringing |  | 121.342 | 121.342 | 115.467 | 5.878 | 4.4027 |  | 119.8697 | 1.4723 | 2.0 | 40/0-41/0-42/0 - 1.475 Km -WIP
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 26 | OPGW | opgw_stringing |  | 121.342 | 121.342 | 97.672 | 23.67 | 5.466 |  | 103.138 | 18.204 | 1.0 | WIP - 39/0 - 41/0
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 27 | NH Crossing | nh_crossing |  | 3 | 3 | 3 |  |  |  | 3
TA 421 | TA 421 | ta421 |  | filename | Progress Status | 2026-06-29 | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 421 Status | prefer_final_else_stringing | 18 | 28 | Power Line Crossing | power_line_crossing |  | 5 | 5 | 5 |  |  |  | 5
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 69 | 69 | 69 |  |  |  | 69 | 0
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 11 | Check Survey | check_survey |  | 69 | 69 | 67 | 2 |  |  | 67 | 2
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 13 | FOUNDATION | foundation |  | 186 | 186 | 144 | 6 | 2 |  | 146 | 42
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 186 | 186 | 121 | 6 | 3 |  | 124 | 65
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 22 | Stringing | stringing |  | 69 | 69 | 13.422 | 8 | 7.14 |  | 20.562 | 55.578
TA 504 | TA 504 | ta504 |  | filename | SUPPLY VALUE = 212.95 Cr. | 2026-06-27 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | TA 504 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 69 | 69 |  |  |  |  | 0 | 69
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 10 | Detail Survey | detail_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 11 | Check Survey | check_survey |  | 139.6 | 139.6 | 139.6 |  |  |  |  | 0
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 13 | FOUNDATION | foundation |  | 379 | 379 | 375 | 4 | 3 |  | 378 | 4 |  | Earthing-266/376.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 16 | TOWER ERECTION | tower_erection |  | 379 | 379 | 357 | 7 | 6 |  | 363 | 22 |  | Tack Welding Completed- 174/362, Gangs Engaged-3.
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 22 | Stringing (Final Sag) | final_sag |  | 139.6 | 139.6 | 15.462 | 23.008 | 9.751 |  | 25.213 | 124.138
TA 505 | TA 505 | ta505 |  | filename | SUPPLY VALUE = 458.32 Cr. | 2026-06-28 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | TA 505 Status | prefer_final_else_stringing | 7 | 23 | Stringing (Rough Sag) | stringing |  | 139.6 | 139.6 | 16.429 | 23 | 13.264 |  | 28.726 | 123.171 |  | 119/0-120/0= Hot line work U/P
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 10 | Detail Survey | detail_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 11 | Check Survey | check_survey |  | 223 | 223 | 223 |  |  |  | 223 | 0
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 13 | FOUNDATION | foundation |  | 602 | 602 | 492 | 40 | 7 |  | 499 | 110
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 16 | TOWER ERECTION | tower_erection |  | 602 | 602 | 405 | 25 | 15 |  | 420 | 197
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 22 | Stringing | stringing |  | 223 | 223 | 55.632 | 30 | 7.478 |  | 63.11 | 167.368
TA 506 | TA 506 | ta506 |  | filename | SUPPLY VALUE = 477.03 Cr. | 2026-06-27 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | TA 506 Status |  | 7 | 26 | OPGW Stringing | opgw_stringing |  | 231 | 231
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 7 | Foundation (Loc) | foundation | 309 | 309 | 309 | 268 | 13 | 6 |  | 274 | 35 | 2.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 8 | Earthing (Loc) | earthing | 309 | 309 | 309 | 247 | 20 | 2 |  | 249 | 60
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 9 | Erection (Loc) | tower_erection | 309 | 309 | 309 | 208 | 30 | 11 |  | 219 | 90 | 3.0
TA 509 | TA 509 | ta509 |  | filename | NOA No.: CC/T/W-TW/DOM/A00/23/13147/NOA-1/24-114171/01 Dated 26/11/2024 | 2026-06-28 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | TA 509 Status |  | 5 | 10 | Stringing (Km) | stringing | 118.397 | 119.178 | 119.178 | 0 | 12 | 3.461 |  | 3.461 | 115.717 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 6 | Route Alignment (Km) | route_alignment |  | 114.516 | 114.516 | 114.516 | 0 |  |  | 114.516 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 7 | Detailed Survey (Km) | detailed_survey |  | 114.516 | 114.516 | 107.971 | 0 |  |  | 107.971 | 6.545
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 9 | Check Survey (Km) | check_survey |  | 114.516 | 114.516 | 94.519 | 0 |  |  | 94.519 | 19.997
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 10 | Soil Investigation (Nos.) | soil_investigation |  | 30 | 30 | 30 | 0 |  |  | 30 | 0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 11 | Excavation | excavation |  | 293 | 293 | 88 | 16 |  |  | 92 | 201
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 12 | Foundation (Nos.) | foundation |  | 293 | 293 | 85 | 16 | 10 |  | 95 | 198 | 4.0 | ROW & Fronts are not cleared for further work 3Teams are idle due to ROWand unvailability of clear front
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 13 | Earthing (Nos.) | earthing |  | 293 | 293 | 78 | 16 | 7 |  | 85 | 208
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 14 | Tower Erection (Nos) | tower_erection |  | 293 | 293 | 40 | 30 | 5 |  | 45 | 248 | 1.0
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 15 | Tack Welding | tack_welding |  | 293 | 293 | 13 | 30 |  |  | 13 | 280
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 16 | Stringing (Km) | stringing |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 17 | Paying Out | paying_out |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 18 | Final Sag | final_sag |  | 114.516 | 114.516 | 0 | 11 |  |  | 0 | 114.516
TA 510 | TA 510 | ta510 |  | filename | NOA Ref. No.: | 2026-06-29 | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | TA 510 Status | prefer_final_else_stringing | 5 | 19 | OPGW (Km) | opgw_stringing |  | 114.516 | 114.516 | 0 | 20 |  |  | 0 | 114.516
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 8 | Route Alignment (Km) | route_alignment | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 9 | Detailed Survey (Km) | detailed_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 11 | Check Survey (Km) | check_survey | 120.944 | 124.568 | 124.568 | 124.568 | 0 | 0 | 0 | 124.568 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 13 | Soil Investigation (Nos.) | soil_investigation | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 28 | 0
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 14 | Excavation | excavation | 315 | 319 | 319 | 308 | 18 | 8 | 1 | 316 | 3
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 15 | Foundation (Nos.) | foundation | 315 | 319 | 319 | 306 | 18 | 6 | 0 | 312 | 7 | 02/19
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 16 | Earthing (Nos.) | earthing | 315 | 319 | 319 | 269 |  | 30 | 0 | 299 | 20
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 17 | Tower Erection (Nos) | tower_erection | 315 | 319 | 319 | 221 | 30 | 14 | 2 | 235 | 84 | 08/244
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 18 | Tack Welding | tack_welding | 315 | 319 | 319 | 79 |  | 30 | 1 | 109 | 210
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 19 | Stringing (Km) | stringing | 120.944 | 124.568 | 124.568 | 0 | 12 |  | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 20 | Paying Out | paying_out | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 21 | Final Sag | final_sag | 120.944 | 124.568 | 124.568 | 0 |  | 0 | 0 | 0 | 124.568
TA 512 | TA 512 | ta512 |  | filename | Office : Hansera, Lunkaransar | 2026-06-28 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | TA 512 Status | prefer_final_else_stringing | 7 | 22 | OPGW (Km) | opgw_stringing | 120.944 | 124.568 | 124.568 | 0 | 20 | 0 | 0 | 0 | 124.568
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 16 | Foundation | foundation |  | 292 | 292 | 124 | 35 | 21 | 0 | 145 | 147 | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 17 | Earthing | earthing |  | 292 | 292 | 102 | 35 | 6 | 0 | 108 | 184
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 18 | Tower Erection | tower_erection |  | 292 | 292 | 71 | 25 | 16 | 0 | 87 | 205 | 7
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 19 | Stringing -R/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 20 | Stringing -F/S | stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 21 | OPGW | opgw_stringing |  | 113.286 | 113.286 | 0 | 0 | 0 | 0 | 0 | 113.286
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 22 | NH Crossing | nh_crossing |  | 3 | 3 | [5 empty] | 3
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 23 | SH Crossing | sh_crossing |  | 1 | 1 | [5 empty] | 1
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 24 | Railway crossing | railway_crossing |  | 2 | 2 | [5 empty] | 2
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 25 | Power Line Crossing | power_line_crossing |  | 6 | 6 | [5 empty] | 6
TA 601 | TA 601 | ta601 |  | filename | Foundation Status | 2026-06-29 | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | TA 601 Status |  | 15 | 27 | WIP - Foundations | foundation | [9 empty] | Gang
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 14 | Soil Investigation | soil_investigation |  | 31 | 31 | 16 | 0 |  |  | 17 | 14
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 15 | Foundation | foundation |  | 480 | 480 | 154 | 30 | 11 | 0 | 165 | 315 | 3.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 16 | Earthing | earthing |  | 480 | 480 | 96 | 30 | 10 | 0 | 106 | 374
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 17 | Tower Erection | tower_erection |  | 480 | 480 | 52 | 35 | 25 | 2 | 77 | 403 | 4.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 18 | Tack welding | tack_welding |  | 480 | 480 | 0 | 35 | 0 | 0 | 0 | 480 | 2.0
TA 602 | TA 602 | ta602 |  | filename | Progress Status | 2026-06-26 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | TA 602 Status | prefer_final_else_stringing | 13 | 19 | Stringing(Km) | stringing |  | 184.986 | 184.986 | 0 | 0 | 0 |  | 0 | 184.986 | 0.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 5 | FOUNDATION | foundation |  | 521 | 521 | 519 | 2 | 1 |  | 520 | 1 | 0.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 6 | EARTHING | earthing |  | 521 | 521 | 494 | 27 | 1 |  | 495 | 26
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 7 | ERECTION | tower_erection |  | 521 | 521 | 502 | 19 | 12 |  | 514 | 7 | 2.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 8 | TACK WELDING | tack_welding |  | 521 | 521 | 356 | 35 | 31 |  | 387 | 134 | 3.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 10 | Strg (Final Sag) | final_sag |  | 202 | 202 | 119.886 | 51 | 16.203 |  | 136.089 | 65.911 | 4.0
TB 401 | TB 401 | tb401 |  | filename | Client Name | 2025-12-25 | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | TB 401 Status |  | 4 | 11 | Stringing OPGW | opgw_stringing |  | 202 | 202 | 51.706 | 30 | 19.57 |  | 71.276 | 130.724 | 1.0
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 6 | Foundation (Nos.) | foundation |  | 485 | 485 | 485 | 0 |  |  | 485 | 0 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 7 | Earthing (Nos.) | earthing |  | 485 | 485 | 485 | 0 |  |  | 485 | 0 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 8 | Tower Erection (Nos) | tower_erection |  | 485 | 485 | 484 | 1 |  |  | 484 | 1 | -
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 9 | Tack Welding (Nos) | tack_welding |  | 485 | 485 | 433 | 52 |  |  | 433 | 52 | 1
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 10 | Paying Out (Kms) | paying_out |  | 191.392 | 191.392 | 125.953 | 25 |  |  | 125.953 | 31.673 | 2 | AP12-13:- WIP.
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 11 | Final Sag (Kms) | final_sag |  | 191.392 | 191.392 | 125.9367 | 25 |  |  | 125.9367 | 31.6893 |  | AP11A-12:- Completed AP12-13:- WIP.
TB 408 | TB 408 | tb408 |  | filename | Project Name- | 2026-06-01 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | TB 408 Status |  | 4 | 12 | OPGW (Kms) | opgw_stringing |  | 191.392 | 191.392 | 88.466 | 30 |  |  | 88.466 | 69.16
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 11 | Route Alignment (Km) | route_alignment | 165 | 150.833 | 150.833 | 150.833 | 0 | 0 |  | 150.833 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 12 | Detailed Survey (Km) | detailed_survey | 165 | 150.833 | 150.833 | 149.21 | 1.623 | 0 |  | 149.21 | 1.623 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 13 | Detailed Survey Profiling (Km) | detailed_survey | 165 | 150.833 | 150.833 | 147.635 | 3.198 | 0 |  | 147.635 | 3.198 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 15 | Check Survey (Km) | check_survey | 165 | 150.833 | 150.833 | 119.962 | 25.288 | 0 |  | 119.962 | 30.871 | 0.0 | U/P
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 16 | Approved check survey ( Km) | check_survey | 165 | 150.833 | 150.833 | 102.416 | 36.061 | 0 |  | 102.416 | 48.417 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 17 | Soil Investigation (Nos) | soil_investigation | 165 | 147 | 147 | 147 | 0 | 0 |  | 147 | 0 | 0.0 | Completed
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 18 | Excavation (Nos) | excavation | 564 | 505 | 505 | 274 | 80 | 30 |  | 304 | 201 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 19 | Foundation (Nos) | foundation | 564 | 505 | 505 | 264 | 80 | 32 |  | 296 | 196 | 13.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 20 | Earthing (Nos) | earthing | 564 | 505 | 505 | 185 | 80 | 29 |  | 214 | 291 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 21 | Tower Erection (Nos) | tower_erection | 564 | 505 | 505 | 87 | 70 | 38 |  | 125 | 372 | 8.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 22 | Tack Welding (Nos) | tack_welding | 564 | 505 | 505 | 21 | 55 | 0 |  | 21 | 484 | 0.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 23 | Stringing (Km) | stringing | 165 | 150.833 | 150.833 | 0 | 12 | 3.199 |  | 3.199 | 147.285 | 2.0
TB 412 | TB 412 | tb412 |  | filename | NOA Service: | 2026-06-24 | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | TB 412 Status |  | 8 | 24 | OPGW Stringing (Km) | opgw_stringing | 165 | 150.833 | 150.833 | 0 | 0 | 0 |  | 0 | 150.833 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 8 | Detailed Survey | detailed_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 9 | Check Survey | check_survey |  | 64 | 64 | 64.178 | 0 | 0 | 0 | 64.178 | -0.178
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 10 | Foundation | foundation |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0 |  | 6/0 Revetment Wip
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 11 | Earthing | earthing |  | 199 | 199 | 199 | 0 | 0 | 0 | 199 | 0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 12 | Tower Erection | tower_erection |  | 199 | 199 | 199 | 0 | 0 |  | 199 | 0 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 13 | Tack Welding | tack_welding |  | 199 | 199 | 194 | 5 | 0 | 0 | 198 | 1 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 14 | Stringing | stringing | [5 empty] | 0 |  |  |  |  | 14/0 to 14/2 Stringing final checking done
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 15 | Paying Out | paying_out |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 16 | Final Sag | final_sag |  | 64.03 | 64.03 | 61.2 | 2.8 | 2.8251 | 0 | 64.0251 | 0.004899
TB 501 | TB 501 | tb501 |  | filename | 220kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 6 | 17 | OPGW | opgw_stringing |  | 64.03 | 64.03 | 53.7218 | 10.2782 | 9.5173 | 0 | 63.2391 | 0.7909 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 22 | Detailed Survey | detailed_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 23 | Check Survey | check_survey |  | 9 | 9 | 9 |  | 0 | 0 | 9 | 0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 24 | Foundation | foundation |  | 39 | 39 | 36 | 3 | 2 | 1 | 38 | 1 | 1.0 | SC-5 All pits Foundation excavation done
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 25 | Earthing | earthing |  | 39 | 39 | 34 | 5 | 4 | 0 | 38 | 1 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 26 | Tower Erection | tower_erection |  | 39 | 39 | 31 | 5 | 3 | 0 | 34 | 5 | 1.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 27 | Tack Welding | tack_welding |  | 39 | 39 | 29 | 0 | 0 | 0 | 29 | 10 | 0.0
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 28 | Stringing | stringing
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 29 | Paying Out | paying_out |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251 | 1.0 | 1/0-2/0 Stringing Wip,
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 30 | Final Sag | final_sag |  | 9.24 | 9.24 | 6.231 | 3.009 | 0.48393 | 0 | 6.7149 | 2.5251
TB 501 | TB 501 | tb501 |  | filename | 132kV Line | 2026-06-29 | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | TB 501 Status | prefer_final_else_stringing | 20 | 31 | OPGW | opgw_stringing |  | 9.24 | 9.24 | 0 | 9 | 6.2313 | 0 | 6.2313 | 3.0087 | 0.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 184 | 188.678 | 188.678 | 188.678 | 0 | 0 | 0 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 73 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 508 | 513 | 513 | 308 | 34 | 14 | 1 | 322 | 191 | 6.0 | 57.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 508 | 513 | 513 | 266 |  |  |  | 266 | 247
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 508 | 513 | 513 | 218 | 39 | 13 |  | 231 | 282 | 3.0 | 60.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 508 | 513 | 513 | 104 | 153 | 24 |  | 128 | 385 | 2.0 | 5.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 19 | Stringing (Kms) | stringing
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 | 21.797 | 21.084 | 3.345 |  | 25.142 | 163.536 | 3.0 | 62.0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 | 21.36 | 21.084 |  |  | 21.36 | 167.318
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 184 | 188.678 | 188.678 | 0
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 23 | Paying Out (Kms) | paying_out | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - MAIN | tb507main | MAIN | config | Progress Summary | 2026-06-28 | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | TB 507 400kV Status |  | 10 | 24 | Final Sag (Kms) | final_sag | 184 | 188.678 | 188.678 |  |  |  |  | 0 | 188.678
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 11 | Route Alignment (Kms) | route_alignment | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 12 | Detailed Survey (Kms) | detailed_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 13 | Check Survey (Kms) | check_survey | 15.478 | 15.478 | 15.478 | 15.478 | 0 | 0 | 0 | 15.478 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 14 | Soil Investigation (Nos) | soil_investigation | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 26 | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 15 | Foundation (Nos) | foundation | 43 | 43 | 43 | 34 | 8 | 4 |  | 38 | 5 | 2.0 | 24.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 16 | Earthing (Nos) | earthing | 43 | 43 | 43 | 3 |  |  | 0 | 3 | 40
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 17 | Tower Erection (Nos) | tower_erection | 43 | 43 | 43 | 3 | 12 | 2 |  | 5 | 38 | 3.0 | 93.0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 18 | Tack Welding (Nos) | tack_welding | 43 | 43 | 43 |  |  |  |  | 0 | 43
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 19 | Stringing (Kms) | stringing | [8 empty] | 0
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 20 | Paying Out (Kms) | paying_out | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 21 | Final Sag (Kms) | final_sag | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 507 | TB 507 - 765kV | tb507765kv | 765kV | config | Progress Summary | 2026-06-28 | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | TB 507 765kV Status |  | 10 | 22 | OPGW Stringing (Kms) | opgw_stringing | 15.478 | 15.478 | 15.478 | 0 |  |  |  | 0 | 15.478
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 7 | Check Survey | check_survey |  | 175.719 | 175.719 | 175.719 | 0 | 0 | 0 | 175.719 |  | 3.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 8 | Foundation | foundation |  | 523 | 523 | 370 | 65 | 43 | 0 | 413 | 110 | 24.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 9 | Earthing | earthing |  | 523 | 523 | 308 | 65 | 39 | 0 | 347 | 176 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 10 | Tower Erection | tower_erection |  | 523 | 523 | 203 | 60 | 42 | 1 | 245 | 278 | 9.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 11 | Tack welding | tack_welding |  | 523 | 523 | 0 | 60 | 0 | 0 | 0 | 523 | 0.0
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 12 | Stringing-P/O-R/S | stringing |  | 175.719 | 175.719 | 0 | 11.63 | 1.47 | 0 | 1.47 | 174.249 | 3.0 | 1 additional team reached at site 65 Manpower ( Saludin)
TB 605 | TB 605 | tb605 |  | filename | Progress Summary - Ratle Kiru Power Transmission Ltd | 2026-06-28 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | TB 605 Status |  | 6 | 13 | Stringing-F/S | stringing |  | 175.719 | 175.719 |  | 11.63 | 1.47 | 0 | 1.47 | 174.249
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 8 | Route Alignment | route_alignment
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 9 | Route Alignment - Main Line | route_alignment | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 10 | Route Alignment - Loop In | route_alignment | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 11 | Route Alignment - Loop Out | route_alignment | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 12 | Detail Survey | detail_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 13 | Detailed Survey - Main Line | detailed_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 14 | Detailed Survey - Loop In | detailed_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 15 | Detailed Survey - Loop Out | detailed_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 16 | Check Survey | check_survey
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 17 | Check Survey - Main Line | check_survey | 87.47 | 87.9079 | 87.9079 | 87.9079 | 0 | 0 | 0 | 87.9079 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 18 | Check Survey - Loop In | check_survey | 13.6 | 8.0518 | 8.0518 | 8.0518 | 0 | 0 | 0 | 8.0518 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 19 | Check Survey - Loop Out | check_survey | 13.52 | 8.0134 | 8.0134 | 8.0134 | 0 | 0 | 0 | 8.0134 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 20 | Normal Open Cast Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 21 | Normal Foundation - Main Line | foundation | 256 | 266 | 266 | 131 | 8 | 4 | 0 | 135 | 131 | 6.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 22 | Normal Foundation - Loop In (Incld. Stone Column) | foundation | 10 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 20
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 23 | Normal Foundation - Loop Out (Incld. Stone Column) | foundation | 9 | 15 | 15 | 1 | 0 | 0 | 0 | 1 | 14
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 24 | Pile Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 25 | Pile Foundation_River_Main Line | foundation | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 1
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 26 | Pile Foundation_Non River_Loop In | foundation | 33 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 27 | Pile Foundation_Non River_Loop Out | foundation | 32 | 8 | 8 | 6 | 0 | 0 | 0 | 6 | 2
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 28 | Pile Cap Foundation | foundation
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 32 | Earthing | earthing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 36 | Erection | tower_erection
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 37 | Tower Erection - Main Line | tower_erection | 261 | 268 | 268 | 31 | 20 | 9 | 1 | 40 | 228 | 7.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 38 | Tower Erection - loop In | tower_erection | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 39 | Tower Erection - Loop Out | tower_erection | 41 | 23 | 23 | 0 | 0 | 1 | 0 | 1 | 22 | 1.0
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 40 | Tack welding | tack_welding
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 41 | Tack welding - Main Line | tack_welding | 261 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 268
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 42 | Tack welding - Loop In | tack_welding | 43 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 27
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 43 | Tack welding - Loop Out | tack_welding | 41 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 23
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 44 | Conductor Stringing/Earthwire | stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 46 | Final Sag - Main Line | final_sag | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 48 | Final Sag - Loop In | final_sag | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 50 | Final Sag - Loop Out | final_sag | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 51 | OPGW Stringing | opgw_stringing
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 52 | OPGW Stringing - Main Line | opgw_stringing | 87.47 | 87.9079 | 87.9079 | 0 | 0 | 0 | 0 | 0 | 87.9079
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 53 | OPGW Stringing - Loop In | opgw_stringing | 13.6 | 8.0518 | 8.0518 | 0 | 0 | 0 | 0 | 0 | 8.0518
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 54 | OPGW Stringing - Loop Out | opgw_stringing | 13.52 | 8.0134 | 8.0134 | 0 | 0 | 0 | 0 | 0 | 8.0134
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 57 | Foundation | foundation | 318 | 142 | 142
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 58 | Erection | tower_erection | 318 | 31 | 31
TB 608 | TB 608 | tb608 |  | filename | LOA | 2026-06-28 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | TB 608 Status | prefer_final_else_stringing | 5 | 59 | Stringing | stringing | 103.9731 | 0 | 0

## Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | FilenameDate | InternalDate | DateQuality | Status | Reason
TA 310 - DPR - 2026-01-12.xlsx | TA 310 | NKTL DPR | NKTL DPR |  | filename | TA 310 Status | TRUE | C1:Activity->activity_raw; C3:Unit->quantity_loa; C4:LOA Qty.->quantity_estimated_or_total; C6:Cumulative L2 till Dec-2025->cumulative_last_month; C9:L2 for Jan'26->plan_for_month; C10:Plan for Jan'2026->today_progress; C11:Today's Progress->progress_for_month; C13:WIP->gangs_working; C14:Gangs at Present->cumulative_progress; C15:Cumulative Progress till date->balance_progress; C16:Balance Work->remarks |  | 1 | 1 | 13 | 2026-01-12 | 2026-01-12 | MATCH | OK
TA 325 - DPR - 2026-01-19.xlsx | TA 325 | 765KV TA 325 ANTL | 765KV TA 325 ANTL |  | filename | TA 325 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(Dec'25)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working |  | 1 | 1 | 6 | 2026-01-19 | 2026-01-19 | MATCH | OK
TA 413 - DPR - 2026-06-28.xlsx | TA 413 | TA413_PBNTL | TA413_PBNTL |  | filename | TA 413 Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:As per latest Estimate->quantity_estimated_or_total; C5:Cumm. Progress up to last Month->cumulative_last_month; C7:Plan for this Month->plan_for_month; C8:Current Month Achieved (As on dated )->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working | XML scrub fallback used for sheet 'TA413_PBNTL' | 1 | 1 | 12 | 2026-06-28 | 2024-03-12 | MISMATCH | OK
TA 414 - DPR - 2026-06-29.xlsx | TA 414 | VNTL - KEC | VNTL - KEC |  | filename | TA 414 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month (May'26)->cumulative_last_month; C6:L3 Plan for the month (June'26 )->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks | XML scrub fallback used for sheet 'VNTL - KEC' | 1 | 1 | 13 | 2026-06-29 |  | MISSING_INTERNAL | OK
TA 416 - DPR - 2026-06-25.xlsx | TA 416 | MASTER SHEET | MASTER SHEET |  | filename | TA 416 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-25 | 2026-06-25 | MATCH | OK
TA 418 - DPR - 2026-06-17.xlsx | TA 418 | MASTER SHEET | MASTER SHEET |  | filename | TA 418 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-17 | 2026-06-17 | MATCH | OK
TA 419 - DPR - 2026-06-26.xlsx | TA 419 | DPR_TA419 | DPR_TA419 |  | filename | TA 419 Status | TRUE | C3:Activity->activity_raw; C4:Quantity->quantity_loa; C5:unnamed_col_5->quantity_estimated_or_total; C7:unnamed_col_7->cumulative_last_month; C9:unnamed_col_9->plan_for_month; C10:Progress for the Month->progress_for_month; C11:unnamed_col_11->today_progress; C12:Cumulative Progress->cumulative_progress; C13:Balance Progress->balance_progress; C14:Gangs working Jun-26->gangs_working; C15:2026-06-26 00:00:00 Remarks->remarks | XML scrub fallback used for sheet 'DPR_TA419' | 1 | 1 | 14 | 2026-06-26 |  | MISSING_INTERNAL | OK
TA 421 - DPR - 2026-06-29.xlsx | TA 421 | Master Sheet | Master Sheet |  | filename | TA 421 Status | TRUE | C3:Activity->activity_raw; C4:Final Estimated Quantity->quantity_estimated_or_total; C6:Cumulative Progress till Last Month->cumulative_last_month; C8:Plan for the Month->plan_for_month; C9:Today's Progress->today_progress; C10:Progress till Date for the Month->progress_for_month; C12:Completed till Date->cumulative_progress; C13:Balance Work->balance_progress; C15:Gangs at Present->gangs_working |  | 1 | 1 | 10 | 2026-06-29 | 2026-06-29 | MATCH | OK
TA 504 - DPR - 2026-06-27.xlsx | TA 504 | DPR_TA-504 | DPR_TA-504 |  | filename | TA 504 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-01 00:00:00->cumulative_last_month; C6:Balance as on 1 June'26->balance_progress; C7:2026-06-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-504' | 1 | 1 | 6 | 2026-06-27 |  | MISSING_INTERNAL | OK
TA 505 - DPR - 2026-06-28.xlsx | TA 505 | DPR-Summary | DPR-Summary |  | filename | TA 505 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-31 00:00:00->cumulative_last_month; C6:Balance as on 1st June-26->balance_progress; C7:June'26 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress |  | 1 | 1 | 6 | 2026-06-28 |  | MISSING_INTERNAL | OK
TA 506 - DPR - 2026-06-27.xlsx | TA 506 | DPR_TA-506 | DPR_TA-506 |  | filename | TA 506 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-01 00:00:00->cumulative_last_month; C6:Balance as on 1 June'26->balance_progress; C7:2026-06-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-506' | 1 | 1 | 6 | 2026-06-27 |  | MISSING_INTERNAL | OK
TA 509 - DPR - 2026-06-28.xlsx | TA 509 | SUMMARY | SUMMARY |  | filename | TA 509 Status | TRUE | C1:Activity->activity_raw; C4:LOA Quantity->quantity_loa; C5:Final Estimated Quantity->quantity_estimated_or_total; C7:Cum Progress till Last Month->cumulative_last_month; C9:Plan for the Month->plan_for_month; C10:Progress for Today->today_progress; C11:Progress for the Month->progress_for_month; C13:Cum. Progress till date->cumulative_progress; C14:Balance Work->balance_progress; C16:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-28 | 2026-06-28 | MATCH | OK
TA 510 - DPR - 2026-06-29.xlsx | TA 510 | AOTL - KEC | AOTL - KEC |  | filename | TA 510 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month May'26)->cumulative_last_month; C5:Target as per L2 Schedule Cummulative (upto May'26)->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-06-29 |  | MISSING_INTERNAL | OK
TA 512 - DPR - 2026-06-28.xlsx | TA 512 | Summary E | Summary E |  | filename | TA 512 Status | TRUE | C2:Activity->activity_raw; C3:LOA Qty->quantity_loa; C4:Estimated Quantity->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (May'26)->cumulative_last_month; C7:Month's Plan as per L2 Schedule->plan_for_month; C8:Progress of Month->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress Till Date->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs/MP->gangs_working |  | 1 | 1 | 13 | 2026-06-28 |  | MISSING_INTERNAL | OK
TA 513 - DPR - 2026-06-28.xlsx | TA 513 | Summary | Summary |  | filename | TA 513 Status | TRUE |  |  | 0 | 0 | 0 | 2026-06-28 |  | MISSING_INTERNAL | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 601 - DPR - 2026-06-29.xlsx | TA 601 | Master Sheet | Master Sheet |  | filename | TA 601 Status | TRUE | C2:Activity->activity_raw; C3:Scope Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress for Current Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 11 | 2026-06-29 | 2026-06-29 | MATCH | OK
TA 602 - DPR - 2026-06-26.xlsx | TA 602 | 800kV HVDC TA-602 | 800kV HVDC TA-602 |  | filename | TA 602 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(May'26)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working | XML scrub fallback used for sheet '800kV HVDC TA-602' | 1 | 1 | 6 | 2026-06-26 | 2026-06-27 | MISMATCH | OK
TB 401 - DPR - 2025-12-25.xlsx | TB 401 | Progress | Progress |  | filename | TB 401 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress Till last Month->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed Till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at present->gangs_working |  | 1 | 1 | 6 | 2025-12-25 | 2025-12-26 | MISMATCH | OK
TB 408 - DPR - 2026-06-01.xlsx | TB 408 | Progress Summary | Progress Summary |  | filename | TB 408 Status | TRUE | C2:Activity->activity_raw; C3:As per latest Estimate->quantity_estimated_or_total; C4:Cumm. Progress up to last Month->cumulative_last_month; C6:Plan for this Month->plan_for_month; C7:Today Progress->today_progress; C8:MTD->progress_for_month; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:Gangs at present->gangs_working |  | 1 | 1 | 7 | 2026-06-01 | 2026-06-01 | MATCH | OK
TB 412 - DPR - 2026-06-24.xlsx | TB 412 | TB-412 SUMMARY | TB-412 SUMMARY |  | filename | TB 412 Status | TRUE | C2:Activity->activity_raw; C3:Total Quantity->quantity_loa; C4:unnamed_col_4->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (May'26)->cumulative_last_month; C7:Target of Month for (June'2026)->plan_for_month; C8:Comp This Month (June'2026)->progress_for_month; C9:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-06-24 | 2026-06-24 | MATCH | OK
TB 501 - DPR - 2026-06-29.xlsx | TB 501 | Summary | Summary |  | filename | TB 501 Status | TRUE | C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (June'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks; C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (June'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks |  | 2 | 2 | 20 | 2026-06-29 | 2026-06-29 | MATCH | OK
TB 507 [MAIN] - DPR - 2026-06-28.xlsx | TB 507 | 400kV Summery | 400kV Summery | MAIN | config | TB 507 400kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For JUNE'26->plan_for_month; C7:Progress in JUNE'26->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jun-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 14 | 2026-06-28 |  | MISSING_INTERNAL | OK
TB 507 - DPR - 2026-06-28.xlsx | TB 507 | 765kV Summery | 765kV Summery | 765kV | config | TB 507 765kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For June'25->plan_for_month; C7:Progress in June'25->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jun-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 12 | 2026-06-28 |  | MISSING_INTERNAL | OK
TB 605 - DPR - 2026-06-28.xlsx | TB 605 | TB-605 | TB-605 |  | filename | TB 605 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Qty->quantity_estimated_or_total; C4:Cumulative Progress till Last Month->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working |  | 1 | 1 | 7 | 2026-06-28 | 2026-06-28 | MATCH | OK
TB 608 - DPR - 2026-06-28.xlsm | TB 608 | DPR Sum. | DPR Sum. |  | filename | TB 608 Status | TRUE | C2:Description->activity_raw; C4:LOA Qty->quantity_loa; C5:Revised Qty->quantity_estimated_or_total; C9:As Per Actual->cumulative_last_month; C10:unnamed_col_10->progress_for_month; C11:unnamed_col_11->cumulative_progress; C12:Balance->balance_progress; C13:Target for the month->plan_for_month; C22:Today's progress->today_progress; C23:Gang->gangs_working |  | 1 | 1 | 41 | 2026-06-28 |  | MISSING_INTERNAL | OK

## Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason
TA 513 - DPR - 2026-06-28.xlsx | TA 513 | Summary | Summary |  | filename | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 515 - DPR - 2026-06-18.xlsx | TA 515 | DPR | DPR |  | filename | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found.

## Coverage
project_code | project_display | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | filename_date | internal_date | date_quality | available_sheets
TA 310 | TA 310 | OK | OK |  | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | 13 | 2026-01-12 | 2026-01-12 | MATCH | NKTL DPR PGCIL; Visual Chart NKTL; NKTL DPR; Sheet2; Sheet1; Visual Chart-Old; Location wise status; Survey Status; Soil investigation; Crossing Details; Line Scenario; Sheet3; Supply Status
TA 325 | TA 325 | OK | OK |  | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | 6 | 2026-01-19 | 2026-01-19 | MATCH | 101-276 FINAL 11-07-2025; 765KV TA 325 ANTL; Project Details; Visual chart Compiled; Soil Invst.; Foundation-Compliled; FDN-VDRA; FDN-NVSR; Erection-Compiled; EREC-VDRA; EREC-NAV; Stringing Compiled; Striging-VDRA; String-Nav; Visual chart NAVSARI Revised; Crossing Vadodara; Crossing Navsari ; Gangs; OPGW; Splicing; Add. Earthing
TA 413 | TA 413 | OK | OK |  | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | 12 | 2026-06-28 | 2024-03-12 | MISMATCH | TA413_PBNTL; WIP; Visual Chart; Stringing; Stretch readiness ; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Aviation Paint; Accessories; OPGW; Foundation; JUMPER Details; Crossing status; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area
TA 414 | TA 414 | OK | OK |  | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | 13 | 2026-06-29 |  | MISSING_INTERNAL | Project Details; 765KV TA 414 VNTL; VNTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Sheet6; Sheet4; Sheet7; Stringing Compiled; Visual chart; Pile Fdn; Crossing; Sheet2; Survey; Soil Inv.; Survey Anx
TA 416 | TA 416 | OK | OK |  | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-06-25 | 2026-06-25 | MATCH | Project Details; MASTER SHEET; Erection Compiled ; Stringing compiled; Progress.; Visual chart.; PENDING FDN DETAILS; PENDING ERE DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; TS; TS (2)
TA 418 | TA 418 | OK | OK |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-06-17 | 2026-06-17 | MATCH | MASTER SHEET; Progress; Erection Completed; Stringing Completed; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2)
TA 419 | TA 419 | OK | OK |  | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | 14 | 2026-06-26 |  | MISSING_INTERNAL | Const Revenue; DPR_TA419; Soil Inv; TOWER SUPPLY; RATE; Tack Welding; Ins Hosting; Stringing; L2; Supply Status; ROW; Tower Schedule; FDN; Latest Tower Schedule; Sheet8; Sheet7; Erection productivity; Foundation Daily Progress; Sheet9; Summary; Sheet10; Visual Chart; Tower schedule_07.03.25; ERT; ERECTION COMPILED; Stringing Compiled; Stringing Stretch Readiness; Project details; Detailed Survey; Supply; Stock Details; PGCIL; dont change; TOWER ABSTRACT; Pkg 2_Foundation; Foundation Daily Progresss; Erection Daily Progress; Statutory; Pkg 2_Erection; Pkg2_Stringing
TA 421 | TA 421 | OK | OK |  | TA 421 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | 10 | 2026-06-29 | 2026-06-29 | MATCH | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; AL Bond ; Birdguard ; Tower Tightening ; Hardwares & Tower Accessories
TA 504 | TA 504 | OK | OK |  | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | 6 | 2026-06-27 |  | MISSING_INTERNAL | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_MAIN; VC_Lilo; Project Details; Location Summary
TA 505 | TA 505 | OK | OK |  | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | 6 | 2026-06-28 |  | MISSING_INTERNAL | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2
TA 506 | TA 506 | OK | OK |  | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | 6 | 2026-06-27 |  | MISSING_INTERNAL | DPR_TA-506; VC; Erection compiled; Tightening; Stringing; Project Details; Location Summary
TA 509 | TA 509 | OK | OK |  | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | 4 | 2026-06-28 | 2026-06-28 | MATCH | Visual Chart; VC-765kV MKTL; DPR; FDN pivot; Erc pivot; SUMMARY; FOUNDATION; ERECTION; Sheet2; XING; EARTHING; SUPPLY; CST Gantry To AP 68 Common Poin; Final Tower Schedule; Sheet1; SURVEY SUMMARY; SURVEY STATUS ; Erection productivity
TA 510 | TA 510 | OK | OK |  | TA 510 - DPR - 2026-06-29.xlsx | AOTL - KEC | AOTL - KEC | 13 | 2026-06-29 |  | MISSING_INTERNAL | 765KV TA 414 VNTL; 765KV ASOTL; Project Details; AOTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; Soil Inv.; Survey Anx; Survey; FDN; Erection ; Visual chart 1 ; Pile Foundation; Sheet6; Sheet4; Sheet7; Stringing Compiled; String; Crossing; Tree Enumeration; Sheet2
TA 512 | TA 512 | OK | OK |  | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | 13 | 2026-06-28 |  | MISSING_INTERNAL | Summary S; Supply Status; Summary E; DPR Sheet ; DS; CS; Hindrance Record; Earthing; Foundation; Erection Compiled; Tack Welding; Visual Chart; WIP; Statuary clearance; Stringing; OPGW; Accessories; Shield Wire Earthing; TS Gantry - AP47; Project Details; L3 Plan; Supply DPR ; Power line Crossings ; Hardware
TA 513 | TA 513 | HEADER_NOT_FOUND | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters. | TA 513 - DPR - 2026-06-28.xlsx | Summary | Summary | 0 | 2026-06-28 |  | MISSING_INTERNAL | Summary; LS Physical; T.Marking; ERT; VC SF ; VC SP; LS; Survey ; FDN S-P; FDN S-F; Total Supply; Ere S-F ; Ere S-P ; T.Abstract; Earthing S-P; Crossing status ; Earthing S-F; Proposal .; ROW S-F; ROW S-P; TS SP ; TS SF; Sheet1; Forest
TA 515 | TA 515 | TEMPLATE_CONFIG_ERROR | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found. | TA 515 - DPR - 2026-06-18.xlsx | DPR | DPR | 0 | 2026-06-18 |  | UNREADABLE | DPR; Foundation Compiled; Earthing; Erection Compiled; Store Stock; Visual chart
TA 601 | TA 601 | OK | OK |  | TA 601 - DPR - 2026-06-29.xlsx | Master Sheet | Master Sheet | 11 | 2026-06-29 | 2026-06-29 | MATCH | Visual Chart ; Master Sheet; Progress Sheet ; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled
TA 602 | TA 602 | OK | OK |  | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6 | 2026-06-26 | 2026-06-27 | MISMATCH | Completion Plan; Project Details; PGCIL - KEC; PPT-Erection Part; CMD-1; CMD-2; PPT _Statutory; PPT Supply; Supply Status; 800kV HVDC TA-602; DPR Sheet; Survey details 11-06-2026; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; TA-602Visual Chart ; Visual chart; Pile Fdn; Crossing; Survey; Soil Inv.; Survey Anx
TB 401 | TB 401 | OK | OK |  | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | 6 | 2025-12-25 | 2025-12-26 | MISMATCH | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); TB401 DPR; Foundation (Pkg-F) ; Earthing (PKG-F); Project Details; Progress; Hindrance; Foundation (Pkg-G); Earthing (PKG-G); Benching Status-F; Revetment Pkg-G; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-F; Tack Welding - PKG-G; Painting - PKG-F; Painting - PKG-G; Idling details from Aug; Erection Compiled; Crane Erection PKG-G; Erection Productivity; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing Productivity; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Visual Chart (Pkg -F.); Clear locs shared by client; Visual Chart PKG-G; Sheet3; Sheet2
TB 408 | TB 408 | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | 7 | 2026-06-01 | 2026-06-01 | MATCH | Progress Summary; Project Details; X-ing Status; L2 Schedule vs Actual; Hindrance Register (Row); Page Chart; Survey; Foundation; Earthing; Erection Productivity; Crane Erection Productivity; Erection Compiled; Tackwelding; Stringing; Stringing associated works; Stringing Productivity; OPGW; Accessories details; Visual chart; Visual chart Edit; Benching F
TB 412 | TB 412 | OK | OK |  | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | 13 | 2026-06-24 | 2026-06-24 | MATCH | TB-412 SUMMARY; Summary-; Survey Status; Sheet3; DPR Sheet ; WIP; GANG Mapping MAY-26 ; Soil Investigation; Sheet1; Progress 400kV QM; VC 400 KV QM; Progress 220KV TM; VC 220 TM; VC 220 SZ; ROW; 220 SZ Status; CS-220kV TM ; DS-220 KV TM; DS 400kV LI; DS 400 kV LO; Survey Report; FDN; Earthing Pending; Erection; Earthing; Earthing Balance; Statutary ; Power line Crossings
TB 501 | TB 501 | OK | OK |  | TB 501 - DPR - 2026-06-29.xlsx | Summary | Summary | 20 | 2026-06-29 | 2026-06-29 | MATCH | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body
TB 507 | TB 507 - MAIN | OK | OK |  | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | 14 | 2026-06-28 |  | MISSING_INTERNAL | 400kV Summery; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Project Details; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Foundation; Royalty; Sheet14; Sheet7; Erection ; Completion date; Sheet12; Erection Compiled ; Earthing; Final Check In And Tack Welding; Sheet10; Sheet11; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart 1; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 507 | TB 507 - 765kV | OK | OK |  | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | 12 | 2026-06-28 |  | MISSING_INTERNAL | 765kV Summery; Check Survey Status; Check Survey; Sheet8; Sheet2; Sheet1; VC 51-96; VC; ROW; June; Check survey Loop out; Check survey Loop In; Foundation; Royalty; Sheet14; Sheet7; Project Details; Erection ; Completion date; Erection Compiled ; Earthing; Final Checking and Tack Welding; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 605 | TB 605 | OK | OK |  | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | 7 | 2026-06-28 | 2026-06-28 | MATCH | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); Sheet2; Sheet3; Sheet4; Sheet5; ROW; Sheet13 (2); TB-605; Sheet19; Sheet16; Sheet14; Sheet12; Sheet13; Sheet15; TB401 DPR; Survey-Summary; Sheet6; Approved Survey; Approved CS J-S Line; Approved CS K-S Line; Foundation JS-Line -Jammu; Sheet10; Erection -Jammu; Vertical Chart -JS Line Jammu ; Sheet17; Stringing JS-Jammu; Erection -SK; Sheet7; Sheet8; LILO; Erection-Punjab; Vertical Chart -JS Line Punjab; Foundation -JS Line- Punjab; Sheet9; ROW Front vs Progress; Pile FDN; Hindrance; Foundation -KS Line; Manpower; Final Checking; Stubs JS; Stubs SK; Towers JS; Towers SK; Sum; Sheet18; JS-Supply Stubs; JS Supply Towers; SK Supply Stubs; SK Supply Towers; Sheet11; Planned Vs Actual -FDN; Supply Status; Material Status-Jammu-Punjab; Material Status-Punjab; Earthing (PKG-F); Earthing (PKG-G); Revetment Pkg-G; Benching Status-F; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-G; Tack Welding - PKG-F; Painting - PKG-G; Painting - PKG-F; Eretion - PKG-G; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Clear locs shared by client
TB 608 | TB 608 | OK | OK |  | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | 41 | 2026-06-28 |  | MISSING_INTERNAL | Master Sheet; DPR Sum.; Master Sheet ; Gang Movement; Support Required; WIP-FDN; WIP-ERC; Line Details; Visual_Chart; Foundation Activity; Supply; Sheet2