## Project Summary
project_code | dashboard_rows | rows_with_issues | latest_raw_dpr_date | issue_flags | dashboard_june_total | actual_june_total | dashboard_balance_may_total | actual_balance_may_total | diff_june_total_dashboard_minus_actual | diff_balance_may_total_dashboard_minus_actual | needs_dashboard_update
TA 413 | 7 | 6 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 29.55 | 36.349 | 111.44 | 155.7507 | -6.799 | -44.3107 | TRUE
TA 414 | 7 | 7 | 2026-06-29 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 87.99 | 153.1022 | 543.46 | 677.654 | -65.1122 | -134.194 | TRUE
TA 416 | 7 | 4 | 2026-06-25 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 4 | 3.319 | 19.52 | 4.034 | 0.681 | 15.486 | TRUE
TA 418 | 7 | 4 | 2026-06-17 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 3.21 | 1.6442 | 47.53 | 18.258 | 1.5658 | 29.272 | TRUE
TA 419 | 7 | 7 | 2026-06-26 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 112 | 53.099 | 772.28 | 852.696 | 58.901 | -80.416 | TRUE
TA 421 | 7 | 7 | 2026-06-25 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 10.49 | 6.261 | 34.92 | 35.545 | 4.229 | -0.625 | TRUE
TA 504 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 15.14 | 12.14 | 438.74 | 233.578 | 3 | 205.162 | TRUE
TA 505 | 7 | 6 | 2026-06-28 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 0 | 18.751 | 629.92 | 150.138 | -18.751 | 479.782 | TRUE
TA 506 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 63.59 | 29.478 | 1190.89 | 705.368 | 34.112 | 485.522 | TRUE
TA 509 | 7 | 7 | 2026-06-28 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS; REVISED_MISMATCH | 0 | 22.461 | 1087.82 | 323.178 | -22.461 | 764.642 | TRUE
TA 510 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 20 | 22 | 838.09 | 1205.029 | -2 | -366.939 | TRUE
TA 512 | 7 | 5 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 26 | 80 | 478.64 | 650.136 | -54 | -171.496 | TRUE
TA 513 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 0 | 0 | 2908 | 0 | 0 | 2908 | TRUE
TA 514 | 8 | 8 |  | NO_RAW_DPR_STATUS_DATA | 4 | 0 | 1752.08 | 0 | 4 | 1752.08 | TRUE
TA 515 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 10 | 0 | 1010.66 | 0 | 10 | 1010.66 | TRUE
TA 601 | 7 | 5 | 2026-06-27 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; JUNE_ACTUAL_MISMATCH | 11 | 39 | 1132.35 | 805.572 | -28 | 326.778 | TRUE
TA 602 | 7 | 7 | 2026-06-26 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 1.29 | 46 | 1179.47 | 1802.986 | -44.71 | -623.516 | TRUE
TA 609 | 8 | 8 |  | NO_RAW_DPR_STATUS_DATA | 0 | 0 | 891.84 | 0 | 0 | 891.84 | TRUE
TB 408 | 7 | 4 | 2026-06-01 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | 0 | 0 | 380.59 | 221.3813 | 0 | 159.2087 | TRUE
TB 501 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 253.34 | 26.214 | 257.06 | 56.1492 | 227.126 | 200.9108 | TRUE
TB 507 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 0 | 57 | 1983.59 | 1674.952 | -57 | 308.638 | TRUE
TB 605 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 0 | 125.47 | 1837.47 | 1386.719 | -125.47 | 450.751 | TRUE
TB 608 | 8 | 8 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR; JUNE_ACTUAL_MISMATCH | 33 | 14 | 940.08 | 1157.9462 | 19 | -217.8662 | TRUE
TB 611 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 66.66 | 0 | 1154.49 | 0 | 66.66 | 1154.49 | TRUE

## Projects Needing Update
project_code | dashboard_rows | rows_with_issues | latest_raw_dpr_date | issue_flags | dashboard_june_total | actual_june_total | dashboard_balance_may_total | actual_balance_may_total | diff_june_total_dashboard_minus_actual | diff_balance_may_total_dashboard_minus_actual | needs_dashboard_update
TA 413 | 7 | 6 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 29.55 | 36.349 | 111.44 | 155.7507 | -6.799 | -44.3107 | TRUE
TA 414 | 7 | 7 | 2026-06-29 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 87.99 | 153.1022 | 543.46 | 677.654 | -65.1122 | -134.194 | TRUE
TA 416 | 7 | 4 | 2026-06-25 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 4 | 3.319 | 19.52 | 4.034 | 0.681 | 15.486 | TRUE
TA 418 | 7 | 4 | 2026-06-17 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 3.21 | 1.6442 | 47.53 | 18.258 | 1.5658 | 29.272 | TRUE
TA 419 | 7 | 7 | 2026-06-26 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 112 | 53.099 | 772.28 | 852.696 | 58.901 | -80.416 | TRUE
TA 421 | 7 | 7 | 2026-06-25 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 10.49 | 6.261 | 34.92 | 35.545 | 4.229 | -0.625 | TRUE
TA 504 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 15.14 | 12.14 | 438.74 | 233.578 | 3 | 205.162 | TRUE
TA 505 | 7 | 6 | 2026-06-28 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 0 | 18.751 | 629.92 | 150.138 | -18.751 | 479.782 | TRUE
TA 506 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 63.59 | 29.478 | 1190.89 | 705.368 | 34.112 | 485.522 | TRUE
TA 509 | 7 | 7 | 2026-06-28 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS; REVISED_MISMATCH | 0 | 22.461 | 1087.82 | 323.178 | -22.461 | 764.642 | TRUE
TA 510 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 20 | 22 | 838.09 | 1205.029 | -2 | -366.939 | TRUE
TA 512 | 7 | 5 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 26 | 80 | 478.64 | 650.136 | -54 | -171.496 | TRUE
TA 513 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 0 | 0 | 2908 | 0 | 0 | 2908 | TRUE
TA 514 | 8 | 8 |  | NO_RAW_DPR_STATUS_DATA | 4 | 0 | 1752.08 | 0 | 4 | 1752.08 | TRUE
TA 515 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 10 | 0 | 1010.66 | 0 | 10 | 1010.66 | TRUE
TA 601 | 7 | 5 | 2026-06-27 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; JUNE_ACTUAL_MISMATCH | 11 | 39 | 1132.35 | 805.572 | -28 | 326.778 | TRUE
TA 602 | 7 | 7 | 2026-06-26 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 1.29 | 46 | 1179.47 | 1802.986 | -44.71 | -623.516 | TRUE
TA 609 | 8 | 8 |  | NO_RAW_DPR_STATUS_DATA | 0 | 0 | 891.84 | 0 | 0 | 891.84 | TRUE
TB 408 | 7 | 4 | 2026-06-01 | NO_MATCHING_ACTIVITY_IN_RAW_DPR; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | 0 | 0 | 380.59 | 221.3813 | 0 | 159.2087 | TRUE
TB 501 | 7 | 7 | 2026-06-27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | 253.34 | 26.214 | 257.06 | 56.1492 | 227.126 | 200.9108 | TRUE
TB 507 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | 0 | 57 | 1983.59 | 1674.952 | -57 | 308.638 | TRUE
TB 605 | 7 | 7 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS; NO_MATCHING_ACTIVITY_IN_RAW_DPR | 0 | 125.47 | 1837.47 | 1386.719 | -125.47 | 450.751 | TRUE
TB 608 | 8 | 8 | 2026-06-28 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; NO_MATCHING_ACTIVITY_IN_RAW_DPR; JUNE_ACTUAL_MISMATCH | 33 | 14 | 940.08 | 1157.9462 | 19 | -217.8662 | TRUE
TB 611 | 7 | 7 |  | NO_RAW_DPR_STATUS_DATA | 66.66 | 0 | 1154.49 | 0 | 66.66 | 1154.49 | TRUE

## Row Comparison
Region | Project | PCH | Activity | UoM | LoA Qty | Revised | L2 Target | Completed (Till May 2026) | Balance (Till May 2026) | Total Completion % | Gangs | Monthly Plan (June 2026) | Monthly Actual (June 2026) | Plan (July 2026) | Plan (August 2026) | project_code | actual_revised | actual_completed_may | actual_balance_may | actual_june | actual_current_balance | actual_rows | source_files | source_sheets | actual_raw_activities | match_rule | latest_raw_dpr_date | diff_revised_dashboard_minus_actual | diff_completed_may_dashboard_minus_actual | diff_balance_may_dashboard_minus_actual | diff_june_dashboard_minus_actual | issue_flags | has_issue
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Check Survey | Km | 222.5 | 230.55 | 0 | 147.65 | 82.9 | 64% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Earthing | No | 597 | 621 | 28 | 41 | 580 | 7% | 0 | 0 | 0 | 0 | 20 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Piling Foundation - Concreting | No | 597 | 621 | 28 | 58 | 563 | 9% | 0 | 20 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Tower Erection | No | 597 | 621 | 35 | 11 | 610 | 2% | 0 | 10 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Tightening | No | 597 | 621 | 35 | 10 | 611 | 2% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Conductor Stringing - S&C | Km | 222.5 | 230.55 | 13 | 0 | 230.55 | 0% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | OPGW Stringing - S&C | Km | 222.5 | 230.55 | 35 | 0 | 230.55 | 0% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Check Survey | Km | 0 | 122.14 | 0 | 122.14 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 122.07 | 0.001 | 0 | 0.001 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Check Survey (Km) | check_survey | 2026-06-26 | 0.069 | 0.07 | -0.001 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Open Foundation - RCC | No | 0 | 333 | 0 | 223 | 110 | 67% | 0 | 0 | 19 | 0 | 0 | TA 419 | 331 | 255 | 76 | 15 | 61 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Foundation (Nos) | foundation_open_or_all_fallback | 2026-06-26 | 2 | -32 | 34 | 4 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Earthing | No | 0 | 333 | 0 | 223 | 110 | 67% | 0 | 0 | 25 | 0 | 0 | TA 419 | 330 | 217 | 113 | 0 | 113 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Earthing (Nos) | earthing | 2026-06-26 | 3 | 6 | -3 | 25 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Tower Erection | No | 0 | 333 | 0 | 179 | 154 | 54% | 0 | 0 | 34 | 0 | 0 | TA 419 | 331 | 207 | 124 | 11 | 113 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Tower Erection (Nos) | tower_erection | 2026-06-26 | 2 | -28 | 30 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Tightening | No | 0 | 333 | 0 | 179 | 154 | 54% | 0 | 0 | 34 | 0 | 0 | TA 419 | 331 | 35 | 296 | 25 | 271 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Tack Welding (Nos) | tack_welding_fallback | 2026-06-26 | 2 | 144 | -142 | 9 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Conductor Stringing - S&C | Km | 0 | 122.14 | 0 | 0 | 122.14 | 0% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 0.447 | 121.624 | 2.099 | 119.525 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Final Sag (Km) | final_sag | 2026-06-26 | 0.069 | -0.447 | 0.516 | -2.099 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | OPGW Stringing - S&C | Km | 0 | 122.14 | 0 | 0 | 122.14 | 0% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 0 | 122.071 | 0 | 122.071 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | OPGW Stringing (Km) | opgw_stringing | 2026-06-26 | 0.069 | 0 | 0.069 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Check Survey | Km | 178.19 | 138.63 | 0 | 102.42 | 36.21 | 74% | 0 | 0 | 0 | 0 | 0 | TB 605 | 175.719 | 175.719 | 0 | 0 | 0 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Check Survey | check_survey | 2026-06-28 | -37.089 | -73.299 | 36.21 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Open Foundation - RCC | No | 577 | 399 | 60 | 62 | 337 | 16% | 0 | 0 | 0 | 40 | 30 | TB 605 | 523 | 370 | 153 | 43 | 110 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Foundation | foundation_open_or_all_fallback | 2026-06-28 | -124 | -308 | 184 | -43 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Earthing | No | 577 | 399 | 60 | 5 | 394 | 1% | 0 | 0 | 0 | 40 | 30 | TB 605 | 523 | 308 | 215 | 39 | 176 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Earthing | earthing | 2026-06-28 | -124 | -303 | 179 | -39 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Tower Erection | No | 577 | 399 | 63 | 5 | 394 | 1% | 0 | 0 | 0 | 35 | 35 | TB 605 | 523 | 203 | 320 | 42 | 278 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Tower Erection | tower_erection | 2026-06-28 | -124 | -198 | 74 | -42 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Tightening | No | 577 | 399 | 63 | 0 | 399 | 0% | 0 | 0 | 0 | 35 | 35 | TB 605 | 523 | 0 | 523 | 0 | 523 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Tack welding | tack_welding_fallback | 2026-06-28 | -124 | 0 | -124 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Conductor Stringing - S&C | Km | 179.04 | 138.63 | 15.5 | 0 | 138.63 | 0% | 0 | 0 | 0 | 15 | 15 | TB 605 | 175.719 | 0 | 175.719 | 1.47 | 174.249 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Stringing-F/S | stringing_fs | 2026-06-28 | -37.089 | 0 | -37.089 | -1.47 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | OPGW Stringing - S&C | Km | 179.04 | 138.63 | 0 | 0 | 138.63 | 0% | 0 | 0 | 0 | 0 | 0 | TB 605 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Check Survey | Km | 118.6 | 113.29 | 0 | 78.52 | 34.77 | 69% | 0 | 0.3988 | 0 | 0 | 0 | TA 601 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Open Foundation - RCC | No | 316 | 292 | 10 | 124 | 168 | 42% | 0 | 35 | 7 | 0 | 0 | TA 601 | 292 | 124 | 168 | 21 | 147 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Foundation | foundation_open_or_all_fallback | 2026-06-27 | 0 | 0 | 0 | -14 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Earthing | No | 316 | 292 | 10 | 102 | 190 | 35% | 0 | 35 | 2 | 0 | 0 | TA 601 | 292 | 102 | 190 | 5 | 185 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Earthing | earthing | 2026-06-27 | 0 | 0 | 0 | -3 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Tower Erection | No | 316 | 292 | 15 | 71 | 221 | 24% | 0 | 25 | 2 | 0 | 0 | TA 601 | 292 | 71 | 221 | 13 | 208 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Tower Erection | tower_erection | 2026-06-27 | 0 | 0 | 0 | -11 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Tightening | No | 316 | 292 | 15 | 0 | 292 | 0% | 0 | 25 | 0 | 0 | 0 | TA 601 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Conductor Stringing - S&C | Km | 118.6 | 113.29 | 5 | 0 | 113.29 | 0% | 0 | 0 | 0 | 0 | 0 | TA 601 | 113.286 | 0 | 113.286 | 0 | 113.286 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Stringing -F/S | stringing_fs | 2026-06-27 | 0.004 | 0 | 0.004 | 0 | OK | FALSE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | OPGW Stringing - S&C | Km | 118.6 | 113.29 | 5 | 0 | 113.29 | 0% | 0 | 0 | 0 | 0 | 0 | TA 601 | 113.286 | 0 | 113.286 | 0 | 113.286 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | OPGW | opgw_stringing | 2026-06-27 | 0.004 | 0 | 0.004 | 0 | OK | FALSE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Check Survey | Km | 47 | 47.84 | 0 | 47.84 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Open Foundation - RCC | No | 121 | 127 | 0 | 127 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | 127 | 127 | 0 | 0 | 0 | 1 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | Foundation | foundation_open_or_all_fallback | 2026-06-17 | 0 | 0 | 0 | 0 | OK | FALSE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Earthing | No | 121 | 127 | 0 | 127 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | 127 | 127 | 0 | 0 | 0 | 1 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | Earthing | earthing | 2026-06-17 | 0 | 0 | 0 | 0 | OK | FALSE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Tower Erection | No | 121 | 127 | 0 | 127 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | 127 | 127 | 0 | 0 | 0 | 1 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | Tower Erection | tower_erection | 2026-06-17 | 0 | 0 | 0 | 0 | OK | FALSE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Tightening | No | 121 | 127 | 0 | 127 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Conductor Stringing - S&C | Km | 47 | 47.84 | 0 | 27.34 | 20.5 | 57% | 0 | 0 | 3.21 | 10.971 | 0 | TA 418 | 47.84 | 29.582 | 18.258 | 1.6442 | 16.6138 | 1 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | Stringing - RS | stringing | 2026-06-17 | 0 | -2.242 | 2.242 | 1.5658 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | OPGW Stringing - S&C | Km | 47 | 47.84 | 0 | 20.81 | 27.03 | 43% | 0 | 0 | 0 | 27.802 | 0 | TA 418 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Check Survey | Km | 0 | 121.34 | 0 | 121.34 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Open Foundation - RCC | No | 0 | 310 | 0 | 310 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Foundation | foundation_open_or_all_fallback | 2026-06-25 | 1 | 1 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Earthing | No | 0 | 310 | 0 | 305 | 5 | 98% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 303 | 6 | 0 | 6 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Earthing | earthing | 2026-06-25 | 1 | 2 | -1 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Tower Erection | No | 0 | 310 | 0 | 310 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Tower Erection | tower_erection | 2026-06-25 | 1 | 1 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Tightening | No | 0 | 310 | 0 | 309 | 1 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Tower Tightening | tower_tightening | 2026-06-25 | 1 | 0 | 1 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Conductor Stringing - S&C | Km | 0 | 121.34 | 0 | 115.26 | 6.08 | 95% | 0 | 5.9 | 5.02 | 0 | 0 | TA 421 | 121.342 | 115.467 | 5.875 | 4.403 | 1.472 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Stringing -F/S | stringing_fs | 2026-06-25 | -0.002 | -0.207 | 0.205 | 0.617 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | OPGW Stringing - S&C | Km | 0 | 121.34 | 0 | 98.5 | 22.84 | 81% | 0 | 23.6 | 5.47 | 0 | 0 | TA 421 | 121.342 | 97.672 | 23.67 | 1.858 | 21.812 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | OPGW | opgw_stringing | 2026-06-25 | -0.002 | 0.828 | -0.83 | 3.612 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Check Survey | Km | 119.43 | 118.41 | 0 | 118.41 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 509 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Open Foundation - RCC | No | 306 | 309 | 0 | 185 | 124 | 60% | 0 | 13 | 0 | 13 | 11 | TA 509 | 309 | 268 | 41 | 6 | 35 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Foundation (Loc) | foundation_open_or_all_fallback | 2026-06-28 | 0 | -83 | 83 | -6 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Earthing | No | 306 | 309 | 0 | 184 | 125 | 60% | 0 | 13 | 0 | 13 | 11 | TA 509 | 309 | 247 | 62 | 2 | 60 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Earthing (Loc) | earthing | 2026-06-28 | 0 | -63 | 63 | -2 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Tower Erection | No | 306 | 309 | 16 | 8 | 301 | 3% | 0 | 20 | 0 | 30 | 30 | TA 509 | 309 | 208 | 101 | 11 | 90 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Erection (Loc) | tower_erection | 2026-06-28 | 0 | -200 | 200 | -11 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Tightening | No | 306 | 309 | 16 | 8 | 301 | 3% | 0 | 20 | 0 | 30 | 30 | TA 509 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 119.43 | 118.41 | 12 | 0 | 118.41 | 0% | 0 | 10.774 | 0 | 19.171 | 17.013 | TA 509 | 119.178 | 0 | 119.178 | 3.461 | 115.717 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Stringing (Km) | stringing | 2026-06-28 | -0.768 | 0 | -0.768 | -3.461 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 119.43 | 118.41 | 20 | 0 | 118.41 | 0% | 0 | 0 | 0 | 19.171 | 17.013 | TA 509 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Check Survey | Km | 66 | 79.08 | 0 | 79.08 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 504 | 69 | 67 | 2 | 0 | 2 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | Check Survey | check_survey | 2026-06-27 | 10.08 | 12.08 | -2 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Open Foundation - RCC | No | 166 | 207 | 0 | 152 | 55 | 73% | 0 | 6 | 1 | 15 | 15 | TA 504 | 186 | 144 | 42 | 2 | 42 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | FOUNDATION | foundation_open_or_all_fallback | 2026-06-27 | 21 | 8 | 13 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Earthing | No | 166 | 207 | 0 | 140 | 67 | 68% | 0 | 6 | 1 | 15 | 15 | TA 504 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Tower Erection | No | 166 | 207 | 0 | 121 | 86 | 58% | 0 | 6 | 3 | 27 | 26 | TA 504 | 186 | 121 | 65 | 3 | 65 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | TOWER ERECTION | tower_erection | 2026-06-27 | 21 | 0 | 21 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Tightening | No | 166 | 207 | 0 | 121 | 86 | 58% | 0 | 6 | 3 | 27 | 26 | TA 504 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 66 | 79.08 | 0 | 13.42 | 65.66 | 17% | 0 | 8 | 7.14 | 20 | 20 | TA 504 | 69 | 13.422 | 55.578 | 7.14 | 55.578 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | Stringing | stringing | 2026-06-27 | 10.08 | -0.002 | 10.082 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 74 | 79.08 | 0 | 0 | 79.08 | 0% | 0 | 0 | 0 | 0 | 36 | TA 504 | 69 | 0 | 69 | 0 | 69 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | OPGW Stringing | opgw_stringing | 2026-06-27 | 10.08 | 0 | 10.08 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Check Survey | Km | 126 | 139.63 | 0 | 139.63 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 505 | 139.6 | 139.6 | 0 | 0 | 0 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | Check Survey | check_survey | 2026-06-28 | 0.03 | 0.03 | 0 | 0 | OK | FALSE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Earthing | No | 358 | 380 | 0 | 373 | 7 | 98% | 0 | 0 | 0 | 0 | 0 | TA 505 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Piling Foundation - Concreting | No | 358 | 380 | 0 | 373 | 7 | 98% | 0 | 0 | 0 | 0 | 0 | TA 505 | 379 | 375 | 4 | 3 | 4 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | FOUNDATION | foundation_pile_or_all_fallback | 2026-06-28 | 1 | -2 | 3 | -3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Tower Erection | No | 358 | 380 | 0 | 353 | 27 | 93% | 0 | 0 | 0 | 5 | 10 | TA 505 | 379 | 357 | 22 | 6 | 22 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | TOWER ERECTION | tower_erection | 2026-06-28 | 1 | -4 | 5 | -6 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Tightening | No | 358 | 380 | 0 | 43 | 337 | 11% | 0 | 0 | 0 | 5 | 10 | TA 505 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 126 | 139.63 | 0 | 15.01 | 124.62 | 11% | 0 | 0 | 0 | 40 | 40 | TA 505 | 139.6 | 15.462 | 124.138 | 9.751 | 124.138 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | Stringing (Final Sag) | final_sag | 2026-06-28 | 0.03 | -0.452 | 0.482 | -9.751 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 126 | 139.63 | 0 | 12.33 | 127.3 | 9% | 0 | 0 | 0 | 0 | 70 | TA 505 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Check Survey | Km | 211 | 222.83 | 0 | 222.83 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 506 | 223 | 223 | 0 | 0 | 0 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | Check Survey | check_survey | 2026-06-27 | -0.17 | -0.17 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Open Foundation - RCC | No | 583 | 605 | 0 | 487 | 118 | 80% | 0 | 25 | 10 | 40 | 40 | TA 506 | 602 | 492 | 110 | 7 | 110 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | FOUNDATION | foundation_open_or_all_fallback | 2026-06-27 | 3 | -5 | 8 | 3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Earthing | No | 583 | 605 | 0 | 337 | 268 | 56% | 0 | 25 | 9 | 40 | 40 | TA 506 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Tower Erection | No | 583 | 605 | 0 | 397 | 208 | 66% | 0 | 25 | 18 | 55 | 55 | TA 506 | 602 | 405 | 197 | 15 | 197 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | TOWER ERECTION | tower_erection | 2026-06-27 | 3 | -8 | 11 | 3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Tightening | No | 583 | 605 | 0 | 400 | 205 | 66% | 0 | 25 | 18 | 55 | 55 | TA 506 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 211 | 222.83 | 0 | 53.77 | 169.06 | 24% | 0 | 30 | 8.59 | 42 | 40 | TA 506 | 223 | 55.632 | 167.368 | 7.478 | 167.368 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | Stringing | stringing | 2026-06-27 | -0.17 | -1.862 | 1.692 | 1.112 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 211 | 222.83 | 0 | 0 | 222.83 | 0% | 0 | 30 | 0 | 40 | 40 | TA 506 | 231 | 0 | 231 | 0 | 231 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | OPGW Stringing | opgw_stringing | 2026-06-27 | -8.17 | 0 | -8.17 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Check Survey | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 10.66 | 8 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Open Foundation - RCC | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 28 | 16 | 11 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Earthing | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 28 | 16 | 11 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Tower Erection | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Tightening | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Conductor Stringing - S&C | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | OPGW Stringing - S&C | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Check Survey | Km | 0 | 63.89 | 0 | 63.89 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 501 | 73 | 73.178 | -0.178 | 0 | -0.178 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Check Survey; Check Survey | check_survey | 2026-06-27 | -9.11 | -9.288 | 0.178 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Open Foundation - RCC | No | 0 | 199 | 0 | 174 | 25 | 87% | 0 | 0 | 25 | 0 | 0 | TB 501 | 238 | 235 | 3 | 2 | 1 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Foundation; Foundation | foundation_open_or_all_fallback | 2026-06-27 | -39 | -61 | 22 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Earthing | No | 0 | 199 | 0 | 173 | 26 | 87% | 0 | 0 | 26 | 0 | 0 | TB 501 | 238 | 233 | 5 | 3 | 2 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Earthing; Earthing | earthing | 2026-06-27 | -39 | -60 | 21 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Tower Erection | No | 0 | 199 | 0 | 169 | 30 | 85% | 0 | 0 | 30 | 0 | 0 | TB 501 | 238 | 230 | 8 | 3 | 5 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Tower Erection; Tower Erection | tower_erection | 2026-06-27 | -39 | -61 | 22 | 27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Tightening | No | 0 | 199 | 0 | 108 | 91 | 54% | 0 | 0 | 91 | 0 | 0 | TB 501 | 238 | 223 | 15 | 0 | 11 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Tack Welding; Tack Welding | tack_welding_fallback | 2026-06-27 | -39 | -115 | 76 | 91 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 0 | 63.89 | 0 | 21.36 | 42.53 | 33% | 0 | 0 | 39.58 | 0 | 0 | TB 501 | 73.24 | 67.431 | 5.809 | 2.4654 | 3.3436 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Final Sag; Final Sag | final_sag | 2026-06-27 | -9.35 | -46.071 | 36.721 | 37.1146 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 0 | 63.89 | 0 | 21.36 | 42.53 | 33% | 0 | 0 | 41.76 | 0 | 0 | TB 501 | 73.24 | 53.7218 | 19.5182 | 15.7486 | 3.7696 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | OPGW; OPGW | opgw_stringing | 2026-06-27 | -9.35 | -32.3618 | 23.0118 | 26.0114 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Check Survey | Km | 114.59 | 86.11 | 0 | 62.25 | 23.86 | 72% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 103.9731 | 0 | 0 | 0 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Check Survey - Main Line; Check Survey - Loop In; Check Survey - Loop Out | check_survey | 2026-06-28 | -17.8631 | -41.7231 | 23.86 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Open Foundation - RCC | No | 345 | 262 | 0 | 130 | 132 | 50% | 0 | 0 | 4 | 6 | 3 | TB 608 | 443 | 132 | 311 | 4 | 307 | 4 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Normal Foundation - Main Line; Normal Foundation - Loop In (Incld. Stone Column); Normal Foundation - Loop Out (Incld. Stone Column); Foundation | foundation_open_or_all_fallback | 2026-06-28 | -181 | -2 | -179 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Earthing | No | 347 | 264 | 0 | 127 | 137 | 48% | 0 | 0 | 5 | 6 | 3 | TB 608 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Piling Foundation - Concreting | No | 2 | 2 | 0 | 1 | 1 | 50% | 0 | 0 | 0 | 0 | 0 | TB 608 | 17 | 14 | 3 | 0 | 3 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Pile Foundation_River_Main Line; Pile Foundation_Non River_Loop In; Pile Foundation_Non River_Loop Out | foundation_pile_or_all_fallback | 2026-06-28 | -15 | -13 | -2 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Tower Erection | No | 345 | 264 | 0 | 27 | 237 | 10% | 0 | 0 | 12 | 12 | 12 | TB 608 | 349 | 31 | 318 | 10 | 308 | 4 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Tower Erection - Main Line; Tower Erection - loop In; Tower Erection - Loop Out; Erection | tower_erection | 2026-06-28 | -85 | -4 | -81 | 2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Tightening | No | 345 | 264 | 0 | 27 | 237 | 10% | 0 | 0 | 12 | 12 | 12 | TB 608 | 318 | 0 | 318 | 0 | 318 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Tack welding - Main Line; Tack welding - Loop In; Tack welding - Loop Out | tack_welding_fallback | 2026-06-28 | -54 | 27 | -81 | 12 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Conductor Stringing - S&C | Km | 114.59 | 86.11 | 0 | 0 | 86.11 | 0% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 0 | 103.9731 | 0 | 103.9731 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Final Sag - Main Line; Final Sag - Loop In; Final Sag - Loop Out | final_sag | 2026-06-28 | -17.8631 | 0 | -17.8631 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | OPGW Stringing - S&C | Km | 114.59 | 86.11 | 0 | 0 | 86.11 | 0% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 0 | 103.9731 | 0 | 103.9731 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | OPGW Stringing - Main Line; OPGW Stringing - Loop In; OPGW Stringing - Loop Out | opgw_stringing | 2026-06-28 | -17.8631 | 0 | -17.8631 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Check Survey | Km | 120.94 | 124.32 | 0 | 124.32 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 512 | 124.568 | 124.568 | 0 | 0 | 0 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Check Survey (Km) | check_survey | 2026-06-28 | -0.248 | -0.248 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Open Foundation - RCC | No | 315 | 319 | 0 | 306 | 13 | 96% | 0 | 0 | 6 | 7 | 0 | TA 512 | 319 | 306 | 13 | 6 | 7 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-28 | 0 | 0 | 0 | 0 | OK | FALSE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Earthing | No | 315 | 319 | 0 | 306 | 13 | 96% | 0 | 0 | 6 | 0 | 0 | TA 512 | 319 | 269 | 50 | 30 | 20 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Earthing (Nos.) | earthing | 2026-06-28 | 0 | 37 | -37 | -24 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Tower Erection | No | 315 | 319 | 30 | 221 | 98 | 69% | 0 | 0 | 14 | 33 | 31 | TA 512 | 319 | 221 | 98 | 14 | 84 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Tower Erection (Nos) | tower_erection | 2026-06-28 | 0 | 0 | 0 | 0 | OK | FALSE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Tightening | No | 315 | 319 | 30 | 213 | 106 | 67% | 0 | 0 | 0 | 0 | 0 | TA 512 | 319 | 79 | 240 | 30 | 210 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Tack Welding | tack_welding_fallback | 2026-06-28 | 0 | 134 | -134 | -30 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Conductor Stringing - S&C | Km | 120.94 | 124.32 | 12 | 0 | 124.32 | 0% | 0 | 0 | 0 | 24.718 | 23.1381 | TA 512 | 124.568 | 0 | 124.568 | 0 | 124.568 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Final Sag | final_sag | 2026-06-28 | -0.248 | 0 | -0.248 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | OPGW Stringing - S&C | Km | 120.94 | 124.32 | 20 | 0 | 124.32 | 0% | 0 | 0 | 0 | 0 | 0 | TA 512 | 124.568 | 0 | 124.568 | 0 | 124.568 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | OPGW (Km) | opgw_stringing | 2026-06-28 | -0.248 | 0 | -0.248 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Check Survey | Km | 0 | 117.85 | 0 | 117.85 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 413 | 117.8509 | 117.8509 | 0 | 0 | 0 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Check Survey approved(Km) | check_survey | 2026-06-28 | -0.000851 | -0.000851 | 0 | 0 | OK | FALSE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Open Foundation - RCC | No | 0 | 306 | 0 | 306 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 413 | 316 | 316 | 0 | 0 | 0 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-28 | -10 | -10 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Earthing | No | 0 | 306 | 0 | 306 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 413 | 309 | 307 | 2 | 1 | 1 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Earthing (Nos.) | earthing | 2026-06-28 | -3 | -1 | -2 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Tower Erection | No | 0 | 306 | 0 | 303 | 3 | 99% | 0 | 0 | 0 | 3 | 0 | TA 413 | 306 | 302 | 4 | 1 | 3 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Tower Erection (Nos) | tower_erection | 2026-06-28 | 0 | 1 | -1 | -1 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Tightening | No | 0 | 306 | 0 | 303 | 3 | 99% | 0 | 0 | 0 | 3 | 0 | TA 413 | 306 | 255 | 51 | 15 | 36 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Tack Welding | tack_welding_fallback | 2026-06-28 | 0 | 48 | -48 | -15 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Conductor Stringing - S&C | Km | 0 | 117.85 | 0 | 78.3 | 39.55 | 66% | 0 | 0 | 11.27 | 20.065 | 10.574 | TA 413 | 117.8509 | 77.189 | 40.6619 | 10.051 | 30.6109 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Final Sag | final_sag | 2026-06-28 | -0.000851 | 1.111 | -1.1119 | 1.219 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | OPGW Stringing - S&C | Km | 0 | 117.85 | 0 | 51.96 | 65.89 | 44% | 0 | 0 | 18.28 | 38.08 | 10.752 | TA 413 | 117.8509 | 59.762 | 58.0889 | 9.298 | 48.7909 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | OPGW (Km) | opgw_stringing | 2026-06-28 | -0.000851 | -7.802 | 7.8011 | 8.982 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Check Survey | Km | 0 | 73.8 | 0 | 27.81 | 45.99 | 38% | 0 | 0 | 0 | 0 | 0 | TB 507 | 204.156 | 204.156 | 0 | 0 | 0 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Check Survey (Kms); Check Survey (Kms) | check_survey | 2026-06-28 | -130.356 | -176.346 | 45.99 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Open Foundation - RCC | No | 0 | 500 | 0 | 138 | 362 | 28% | 0 | 34 | 0 | 38 | 40 | TB 507 | 556 | 342 | 214 | 18 | 196 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Foundation (Nos); Foundation (Nos) | foundation_open_or_all_fallback | 2026-06-28 | -56 | -204 | 148 | -18 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Earthing | No | 0 | 500 | 0 | 59 | 441 | 12% | 0 | 34 | 0 | 38 | 40 | TB 507 | 556 | 269 | 287 | 0 | 287 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Earthing (Nos); Earthing (Nos) | earthing | 2026-06-28 | -56 | -210 | 154 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Tower Erection | No | 0 | 500 | 0 | 12 | 488 | 2% | 0 | 40 | 0 | 39 | 45 | TB 507 | 556 | 221 | 335 | 15 | 320 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Tower Erection (Nos); Tower Erection (Nos) | tower_erection | 2026-06-28 | -56 | -209 | 153 | -15 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Tightening | No | 0 | 500 | 0 | 1 | 499 | 0% | 0 | 40 | 0 | 39 | 45 | TB 507 | 556 | 104 | 452 | 24 | 428 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Tack Welding (Nos); Tack Welding (Nos) | tack_welding_fallback | 2026-06-28 | -56 | -103 | 47 | -24 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Conductor Stringing - S&C | Km | 0 | 73.8 | 0 | 0 | 73.8 | 0% | 0 | 0 | 0 | 19.128 | 20 | TB 507 | 204.156 | 21.36 | 182.796 | 0 | 182.796 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Final Sag (Kms); Final Sag (Kms) | final_sag | 2026-06-28 | -130.356 | -21.36 | -108.996 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | OPGW Stringing - S&C | Km | 0 | 73.8 | 0 | 0 | 73.8 | 0% | 0 | 0 | 0 | 0 | 0 | TB 507 | 204.156 | 0 | 204.156 | 0 | 204.156 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | OPGW Stringing (Kms); OPGW Stringing (Kms) | opgw_stringing | 2026-06-28 | -130.356 | 0 | -130.356 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Check Survey | Km | 0 | 191.39 | 0 | 191.39 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 408 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Open Foundation - RCC | No | 0 | 485 | 0 | 485 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 408 | 485 | 485 | 0 | 0 | 0 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-01 | 0 | 0 | 0 | 0 | OK | FALSE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Earthing | No | 0 | 485 | 0 | 485 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 408 | 485 | 485 | 0 | 0 | 0 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Earthing (Nos.) | earthing | 2026-06-01 | 0 | 0 | 0 | 0 | OK | FALSE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Tower Erection | No | 0 | 485 | 0 | 484 | 1 | 100% | 0 | 0 | 0 | 0 | 0 | TB 408 | 485 | 484 | 1 | 0 | 1 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Tower Erection (Nos) | tower_erection | 2026-06-01 | 0 | 0 | 0 | 0 | OK | FALSE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Tightening | No | 0 | 485 | 0 | 324 | 161 | 67% | 0 | 0 | 0 | 0 | 0 | TB 408 | 485 | 433 | 52 | 0 | 52 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Tack Welding (Nos) | tack_welding_fallback | 2026-06-01 | 0 | -109 | 109 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Conductor Stringing - S&C | Km | 0 | 191.39 | 0 | 125.82 | 65.57 | 66% | 0 | 0 | 0 | 0 | 0 | TB 408 | 191.392 | 125.9367 | 65.4553 | 0 | 31.6893 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Final Sag (Kms) | final_sag | 2026-06-01 | -0.002 | -0.1167 | 0.1147 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | OPGW Stringing - S&C | Km | 0 | 191.39 | 0 | 38.37 | 153.02 | 20% | 0 | 0 | 0 | 0 | 0 | TB 408 | 191.392 | 88.466 | 102.926 | 0 | 69.16 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | OPGW (Kms) | opgw_stringing | 2026-06-01 | -0.002 | -50.096 | 50.094 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Check Survey | Km | 0 | 115.13 | 0 | 115.13 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Open Foundation - RCC | No | 0 | 302 | 0 | 302 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 416 | 302 | 302 | 0 | 0 | 0 | 1 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | Foundation | foundation_open_or_all_fallback | 2026-06-25 | 0 | 0 | 0 | 0 | OK | FALSE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Earthing | No | 0 | 302 | 0 | 302 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 416 | 302 | 302 | 0 | 0 | 0 | 1 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | Earthing | earthing | 2026-06-25 | 0 | 0 | 0 | 0 | OK | FALSE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Tower Erection | No | 0 | 302 | 0 | 302 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 416 | 302 | 302 | 0 | 0 | 0 | 1 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | Erection | tower_erection | 2026-06-25 | 0 | 0 | 0 | 0 | OK | FALSE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Tightening | No | 0 | 302 | 0 | 302 | 0 | 100% | 4 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Conductor Stringing - S&C | Km | 0 | 115.13 | 0 | 110.46 | 4.67 | 96% | 0 | 0 | 4 | 0 | 0 | TA 416 | 115.134 | 111.1 | 4.034 | 3.319 | 0.676 | 1 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | Stringing | stringing | 2026-06-25 | -0.004 | -0.64 | 0.636 | 0.681 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | OPGW Stringing - S&C | Km | 0 | 115.13 | 0 | 100.28 | 14.85 | 87% | 0 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Check Survey | Km | 80 | 73.92 | 0 | 73.92 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Open Foundation - RCC | No | 159 | 147 | 4 | 22 | 125 | 15% | 0 | 0 | 0 | 2 | 2 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Earthing | No | 228 | 197 | 14 | 20 | 177 | 10% | 0 | 0 | 0 | 2 | 2 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Piling Foundation - Concreting | No | 69 | 50 | 10 | 0 | 50 | 0% | 0 | 0 | 0 | 4 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Tower Erection | No | 228 | 197 | 30 | 1 | 196 | 1% | 0 | 0 | 0 | 3 | 3 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Tightening | No | 228 | 197 | 30 | 1 | 196 | 1% | 0 | 0 | 0 | 3 | 3 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Conductor Stringing - S&C | Km | 80 | 73.92 | 20 | 0 | 73.92 | 0% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | OPGW Stringing - S&C | Km | 80 | 73.92 | 20 | 0 | 73.92 | 0% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Check Survey | Km | 111.27 | 84.48 | 0 | 80.35 | 4.13 | 95% | 0 | 16.867 | 0 | 16.484 | 0 | TA 510 | 114.516 | 94.519 | 19.997 | 0 | 19.997 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Check Survey (Km) | check_survey | 2026-06-28 | -30.036 | -14.169 | -15.867 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Earthing | No | 293 | 224 | 0 | 83 | 141 | 37% | 0 | 47 | 9 | 20 | 20 | TA 510 | 293 | 78 | 215 | 7 | 208 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Earthing (Nos.) | earthing | 2026-06-28 | -69 | 5 | -74 | 2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Piling Foundation - Concreting | No | 293 | 224 | 0 | 82 | 142 | 37% | 0 | 47 | 9 | 20 | 20 | TA 510 | 293 | 85 | 208 | 10 | 198 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Foundation (Nos.) | foundation_pile_or_all_fallback | 2026-06-28 | -69 | -3 | -66 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Tower Erection | No | 293 | 224 | 8 | 33 | 191 | 15% | 0 | 30 | 1 | 10 | 10 | TA 510 | 293 | 40 | 253 | 5 | 248 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Tower Erection (Nos) | tower_erection | 2026-06-28 | -69 | -7 | -62 | -4 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Tightening | No | 293 | 224 | 8 | 33 | 191 | 15% | 0 | 30 | 1 | 10 | 10 | TA 510 | 293 | 13 | 280 | 0 | 280 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Tack Welding | tack_welding_fallback | 2026-06-28 | -69 | 20 | -89 | 1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Conductor Stringing - S&C | Km | 111.27 | 84.48 | 11 | 0 | 84.48 | 0% | 0 | 0 | 0 | 0 | 0 | TA 510 | 114.516 | 0 | 114.516 | 0 | 114.516 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Final Sag | final_sag | 2026-06-28 | -30.036 | 0 | -30.036 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | OPGW Stringing - S&C | Km | 111.27 | 84.48 | 20 | 0 | 84.48 | 0% | 0 | 0 | 0 | 0 | 0 | TA 510 | 114.516 | 0 | 114.516 | 0 | 114.516 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | OPGW (Km) | opgw_stringing | 2026-06-28 | -30.036 | 0 | -30.036 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Check Survey | Km | 83.14 | 83.33 | 0 | 83.33 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Open Foundation - RCC | No | 215 | 218 | 10 | 14 | 204 | 6% | 0 | 0 | 5 | 2 | 2 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Earthing | No | 215 | 218 | 10 | 14 | 204 | 6% | 0 | 0 | 5 | 2 | 2 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Tower Erection | No | 215 | 218 | 12 | 0 | 218 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Tightening | No | 215 | 218 | 12 | 0 | 218 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Conductor Stringing - S&C | Km | 83.14 | 83.33 | 2 | 0 | 83.33 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | OPGW Stringing - S&C | Km | 83.14 | 83.33 | 2 | 0 | 83.33 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Check Survey | Km | 130 | 127.85 | 0 | 127.85 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 414 | 127.799 | 127.799 | 0 | 0 | 0 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Check Survey (Km) | check_survey | 2026-06-29 | 0.051 | 0.051 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Open Foundation - RCC | No | 340 | 351 | 0 | 316 | 35 | 90% | 0 | 0 | 15 | 15 | 0 | TA 414 | 352 | 319 | 33 | 17 | 16 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-29 | -1 | -3 | 2 | -2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Earthing | No | 340 | 351 | 0 | 314 | 37 | 89% | 0 | 0 | 16 | 15 | 0 | TA 414 | 352 | 296 | 56 | 36 | 20 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Earthing (Nos.) | earthing | 2026-06-29 | -1 | 18 | -19 | -20 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Tower Erection | No | 340 | 351 | 0 | 235 | 116 | 67% | 0 | 0 | 25 | 40 | 45 | TA 414 | 352 | 235 | 117 | 30 | 87 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Tower Erection (Nos) | tower_erection | 2026-06-29 | -1 | 0 | -1 | -5 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Tightening | No | 340 | 351 | 0 | 235 | 116 | 67% | 0 | 0 | 25 | 40 | 45 | TA 414 | 352 | 120 | 232 | 61 | 171 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Tack Welding | tack_welding_fallback | 2026-06-29 | -1 | 115 | -116 | -36 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Conductor Stringing - S&C | Km | 130 | 127.85 | 0 | 16.24 | 111.61 | 13% | 0 | 0 | 6.99 | 17.592 | 17.562 | TA 414 | 127.799 | 15.944 | 111.855 | 9.1022 | 102.7528 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Final Sag | final_sag | 2026-06-29 | 0.051 | 0.296 | -0.245 | -2.1122 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | OPGW Stringing - S&C | Km | 130 | 127.85 | 0 | 0 | 127.85 | 0% | 0 | 0 | 0 | 0 | 0 | TA 414 | 127.799 | 0 | 127.799 | 0 | 127.799 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | OPGW (Km) | opgw_stringing | 2026-06-29 | 0.051 | 0 | 0.051 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Check Survey | Km | 139.48 | 142.07 | 0 | 134.13 | 7.94 | 94% | 0 | 0 | 0 | 1.67 | 6.25 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Open Foundation - RCC | No | 361 | 356 | 15 | 24 | 332 | 7% | 0 | 0 | 2 | 5 | 5 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Earthing | No | 722 | 377 | 30 | 24 | 353 | 6% | 0 | 0 | 2 | 0 | 5 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Piling Foundation - Concreting | No | 361 | 21 | 15 | 0 | 21 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Tower Erection | No | 361 | 377 | 15 | 0 | 377 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Tightening | No | 361 | 377 | 15 | 0 | 377 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Conductor Stringing - S&C | Km | 139.48 | 142.07 | 5 | 0 | 142.07 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | OPGW Stringing - S&C | Km | 139.48 | 142.07 | 5 | 0 | 142.07 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Check Survey | Km | 186.3 | 88.49 | 0 | 0 | 88.49 | 0% | 0 | 0 | 0.29 | 6.622 | 0 | TA 602 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Open Foundation - RCC | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 1 | 30 | 30 | TA 602 | 480 | 154 | 326 | 11 | 315 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Foundation | foundation_open_or_all_fallback | 2026-06-26 | -249 | -154 | -95 | -10 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Earthing | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 0 | 30 | 30 | TA 602 | 480 | 96 | 384 | 10 | 374 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Earthing | earthing | 2026-06-26 | -249 | -96 | -153 | -10 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Tower Erection | No | 494 | 231 | 10 | 10 | 221 | 4% | 0 | 0 | 0 | 30 | 35 | TA 602 | 480 | 52 | 428 | 25 | 403 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Tower Erection | tower_erection | 2026-06-26 | -249 | -42 | -207 | -25 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Tightening | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 0 | 30 | 35 | TA 602 | 480 | 0 | 480 | 0 | 480 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Tack welding | tack_welding_fallback | 2026-06-26 | -249 | 0 | -249 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Conductor Stringing - S&C | Km | 186.3 | 88.49 | 5 | 0 | 88.49 | 0% | 0 | 0 | 0 | 0 | 0 | TA 602 | 184.986 | 0 | 184.986 | 0 | 184.986 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Stringing(Km) | stringing | 2026-06-26 | -96.496 | 0 | -96.496 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | OPGW Stringing - S&C | Km | 186.3 | 88.49 | 5 | 0 | 88.49 | 0% | 0 | 0 | 0 | 0 | 0 | TA 602 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE

## Issue Rows Only
Region | Project | PCH | Activity | UoM | LoA Qty | Revised | L2 Target | Completed (Till May 2026) | Balance (Till May 2026) | Total Completion % | Gangs | Monthly Plan (June 2026) | Monthly Actual (June 2026) | Plan (July 2026) | Plan (August 2026) | project_code | actual_revised | actual_completed_may | actual_balance_may | actual_june | actual_current_balance | actual_rows | source_files | source_sheets | actual_raw_activities | match_rule | latest_raw_dpr_date | diff_revised_dashboard_minus_actual | diff_completed_may_dashboard_minus_actual | diff_balance_may_dashboard_minus_actual | diff_june_dashboard_minus_actual | issue_flags | has_issue
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Check Survey | Km | 222.5 | 230.55 | 0 | 147.65 | 82.9 | 64% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Earthing | No | 597 | 621 | 28 | 41 | 580 | 7% | 0 | 0 | 0 | 0 | 20 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Piling Foundation - Concreting | No | 597 | 621 | 28 | 58 | 563 | 9% | 0 | 20 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Tower Erection | No | 597 | 621 | 35 | 11 | 610 | 2% | 0 | 10 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Tightening | No | 597 | 621 | 35 | 10 | 611 | 2% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | Conductor Stringing - S&C | Km | 222.5 | 230.55 | 13 | 0 | 230.55 | 0% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA - 513 - TA - 513, 400 Kv (Quad) SIWANI - FATEHABAD & SIWANI - PATRAN TL PROJECT | N K Gupta | OPGW Stringing - S&C | Km | 222.5 | 230.55 | 35 | 0 | 230.55 | 0% | 0 | 0 | 0 | 0 | 0 | TA 513 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Check Survey | Km | 0 | 122.14 | 0 | 122.14 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 122.07 | 0.001 | 0 | 0.001 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Check Survey (Km) | check_survey | 2026-06-26 | 0.069 | 0.07 | -0.001 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Open Foundation - RCC | No | 0 | 333 | 0 | 223 | 110 | 67% | 0 | 0 | 19 | 0 | 0 | TA 419 | 331 | 255 | 76 | 15 | 61 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Foundation (Nos) | foundation_open_or_all_fallback | 2026-06-26 | 2 | -32 | 34 | 4 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Earthing | No | 0 | 333 | 0 | 223 | 110 | 67% | 0 | 0 | 25 | 0 | 0 | TA 419 | 330 | 217 | 113 | 0 | 113 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Earthing (Nos) | earthing | 2026-06-26 | 3 | 6 | -3 | 25 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Tower Erection | No | 0 | 333 | 0 | 179 | 154 | 54% | 0 | 0 | 34 | 0 | 0 | TA 419 | 331 | 207 | 124 | 11 | 113 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Tower Erection (Nos) | tower_erection | 2026-06-26 | 2 | -28 | 30 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Tightening | No | 0 | 333 | 0 | 179 | 154 | 54% | 0 | 0 | 34 | 0 | 0 | TA 419 | 331 | 35 | 296 | 25 | 271 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Tack Welding (Nos) | tack_welding_fallback | 2026-06-26 | 2 | 144 | -142 | 9 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | Conductor Stringing - S&C | Km | 0 | 122.14 | 0 | 0 | 122.14 | 0% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 0.447 | 121.624 | 2.099 | 119.525 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | Final Sag (Km) | final_sag | 2026-06-26 | 0.069 | -0.447 | 0.516 | -2.099 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Haryana | TA419 - 765 KV D/C Sikar II- Narela T/L | N K Gupta | OPGW Stringing - S&C | Km | 0 | 122.14 | 0 | 0 | 122.14 | 0% | 0 | 0 | 0 | 0 | 0 | TA 419 | 122.071 | 0 | 122.071 | 0 | 122.071 | 1 | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | OPGW Stringing (Km) | opgw_stringing | 2026-06-26 | 0.069 | 0 | 0.069 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Check Survey | Km | 178.19 | 138.63 | 0 | 102.42 | 36.21 | 74% | 0 | 0 | 0 | 0 | 0 | TB 605 | 175.719 | 175.719 | 0 | 0 | 0 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Check Survey | check_survey | 2026-06-28 | -37.089 | -73.299 | 36.21 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Open Foundation - RCC | No | 577 | 399 | 60 | 62 | 337 | 16% | 0 | 0 | 0 | 40 | 30 | TB 605 | 523 | 370 | 153 | 43 | 110 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Foundation | foundation_open_or_all_fallback | 2026-06-28 | -124 | -308 | 184 | -43 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Earthing | No | 577 | 399 | 60 | 5 | 394 | 1% | 0 | 0 | 0 | 40 | 30 | TB 605 | 523 | 308 | 215 | 39 | 176 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Earthing | earthing | 2026-06-28 | -124 | -303 | 179 | -39 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Tower Erection | No | 577 | 399 | 63 | 5 | 394 | 1% | 0 | 0 | 0 | 35 | 35 | TB 605 | 523 | 203 | 320 | 42 | 278 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Tower Erection | tower_erection | 2026-06-28 | -124 | -198 | 74 | -42 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Tightening | No | 577 | 399 | 63 | 0 | 399 | 0% | 0 | 0 | 0 | 35 | 35 | TB 605 | 523 | 0 | 523 | 0 | 523 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Tack welding | tack_welding_fallback | 2026-06-28 | -124 | 0 | -124 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | Conductor Stringing - S&C | Km | 179.04 | 138.63 | 15.5 | 0 | 138.63 | 0% | 0 | 0 | 0 | 15 | 15 | TB 605 | 175.719 | 0 | 175.719 | 1.47 | 174.249 | 1 | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | Stringing-F/S | stringing_fs | 2026-06-28 | -37.089 | 0 | -37.089 | -1.47 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
J&K | TB 605 - TB-605-400kV D/C Ratle Kiru Transmission Line TL | N K Gupta | OPGW Stringing - S&C | Km | 179.04 | 138.63 | 0 | 0 | 138.63 | 0% | 0 | 0 | 0 | 0 | 0 | TB 605 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Check Survey | Km | 118.6 | 113.29 | 0 | 78.52 | 34.77 | 69% | 0 | 0.3988 | 0 | 0 | 0 | TA 601 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Open Foundation - RCC | No | 316 | 292 | 10 | 124 | 168 | 42% | 0 | 35 | 7 | 0 | 0 | TA 601 | 292 | 124 | 168 | 21 | 147 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Foundation | foundation_open_or_all_fallback | 2026-06-27 | 0 | 0 | 0 | -14 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Earthing | No | 316 | 292 | 10 | 102 | 190 | 35% | 0 | 35 | 2 | 0 | 0 | TA 601 | 292 | 102 | 190 | 5 | 185 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Earthing | earthing | 2026-06-27 | 0 | 0 | 0 | -3 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Tower Erection | No | 316 | 292 | 15 | 71 | 221 | 24% | 0 | 25 | 2 | 0 | 0 | TA 601 | 292 | 71 | 221 | 13 | 208 | 1 | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Tower Erection | tower_erection | 2026-06-27 | 0 | 0 | 0 | -11 | JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA 601 - TA 601- 765Kv DC Kurnool IV to Bidar Transmission Line, Kurnool (TL-02) | Arun Felbin R | Tightening | No | 316 | 292 | 15 | 0 | 292 | 0% | 0 | 25 | 0 | 0 | 0 | TA 601 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Check Survey | Km | 47 | 47.84 | 0 | 47.84 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Tightening | No | 121 | 127 | 0 | 127 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 418 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | Conductor Stringing - S&C | Km | 47 | 47.84 | 0 | 27.34 | 20.5 | 57% | 0 | 0 | 3.21 | 10.971 | 0 | TA 418 | 47.84 | 29.582 | 18.258 | 1.6442 | 16.6138 | 1 | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | Stringing - RS | stringing | 2026-06-17 | 0 | -2.242 | 2.242 | 1.5658 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA418 - TA-418 Koppal ll to Raichur TL 765 kv DC | Arun Felbin R | OPGW Stringing - S&C | Km | 47 | 47.84 | 0 | 20.81 | 27.03 | 43% | 0 | 0 | 0 | 27.802 | 0 | TA 418 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Check Survey | Km | 0 | 121.34 | 0 | 121.34 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Open Foundation - RCC | No | 0 | 310 | 0 | 310 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Foundation | foundation_open_or_all_fallback | 2026-06-25 | 1 | 1 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Earthing | No | 0 | 310 | 0 | 305 | 5 | 98% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 303 | 6 | 0 | 6 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Earthing | earthing | 2026-06-25 | 1 | 2 | -1 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Tower Erection | No | 0 | 310 | 0 | 310 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Tower Erection | tower_erection | 2026-06-25 | 1 | 1 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Tightening | No | 0 | 310 | 0 | 309 | 1 | 100% | 0 | 0 | 0 | 0 | 0 | TA 421 | 309 | 309 | 0 | 0 | 0 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Tower Tightening | tower_tightening | 2026-06-25 | 1 | 0 | 1 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | Conductor Stringing - S&C | Km | 0 | 121.34 | 0 | 115.26 | 6.08 | 95% | 0 | 5.9 | 5.02 | 0 | 0 | TA 421 | 121.342 | 115.467 | 5.875 | 4.403 | 1.472 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Stringing -F/S | stringing_fs | 2026-06-25 | -0.002 | -0.207 | 0.205 | 0.617 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Karnataka | TA421 - TA421 PGCIL WZ 2 & 3 Transmission Line Package TL01 for Bidar PS Maheshwaram PG 765 kV DC Line Part-I | Arun Felbin R | OPGW Stringing - S&C | Km | 0 | 121.34 | 0 | 98.5 | 22.84 | 81% | 0 | 23.6 | 5.47 | 0 | 0 | TA 421 | 121.342 | 97.672 | 23.67 | 1.858 | 21.812 | 1 | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | OPGW | opgw_stringing | 2026-06-25 | -0.002 | 0.828 | -0.83 | 3.612 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Check Survey | Km | 119.43 | 118.41 | 0 | 118.41 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 509 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Open Foundation - RCC | No | 306 | 309 | 0 | 185 | 124 | 60% | 0 | 13 | 0 | 13 | 11 | TA 509 | 309 | 268 | 41 | 6 | 35 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Foundation (Loc) | foundation_open_or_all_fallback | 2026-06-28 | 0 | -83 | 83 | -6 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Earthing | No | 306 | 309 | 0 | 184 | 125 | 60% | 0 | 13 | 0 | 13 | 11 | TA 509 | 309 | 247 | 62 | 2 | 60 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Earthing (Loc) | earthing | 2026-06-28 | 0 | -63 | 63 | -2 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Tower Erection | No | 306 | 309 | 16 | 8 | 301 | 3% | 0 | 20 | 0 | 30 | 30 | TA 509 | 309 | 208 | 101 | 11 | 90 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Erection (Loc) | tower_erection | 2026-06-28 | 0 | -200 | 200 | -11 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Tightening | No | 306 | 309 | 16 | 8 | 301 | 3% | 0 | 20 | 0 | 30 | 30 | TA 509 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 119.43 | 118.41 | 12 | 0 | 118.41 | 0% | 0 | 10.774 | 0 | 19.171 | 17.013 | TA 509 | 119.178 | 0 | 119.178 | 3.461 | 115.717 | 1 | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | Stringing (Km) | stringing | 2026-06-28 | -0.768 | 0 | -0.768 | -3.461 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA-509 - TA-509 765 KV Mandsaur Korawar TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 119.43 | 118.41 | 20 | 0 | 118.41 | 0% | 0 | 0 | 0 | 19.171 | 17.013 | TA 509 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Check Survey | Km | 66 | 79.08 | 0 | 79.08 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 504 | 69 | 67 | 2 | 0 | 2 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | Check Survey | check_survey | 2026-06-27 | 10.08 | 12.08 | -2 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Open Foundation - RCC | No | 166 | 207 | 0 | 152 | 55 | 73% | 0 | 6 | 1 | 15 | 15 | TA 504 | 186 | 144 | 42 | 2 | 42 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | FOUNDATION | foundation_open_or_all_fallback | 2026-06-27 | 21 | 8 | 13 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Earthing | No | 166 | 207 | 0 | 140 | 67 | 68% | 0 | 6 | 1 | 15 | 15 | TA 504 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Tower Erection | No | 166 | 207 | 0 | 121 | 86 | 58% | 0 | 6 | 3 | 27 | 26 | TA 504 | 186 | 121 | 65 | 3 | 65 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | TOWER ERECTION | tower_erection | 2026-06-27 | 21 | 0 | 21 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Tightening | No | 166 | 207 | 0 | 121 | 86 | 58% | 0 | 6 | 3 | 27 | 26 | TA 504 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 66 | 79.08 | 0 | 13.42 | 65.66 | 17% | 0 | 8 | 7.14 | 20 | 20 | TA 504 | 69 | 13.422 | 55.578 | 7.14 | 55.578 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | Stringing | stringing | 2026-06-27 | 10.08 | -0.002 | 10.082 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA504 - TA-504- 765 KV D/C Rishabhdeo - Mandsaur TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 74 | 79.08 | 0 | 0 | 79.08 | 0% | 0 | 0 | 0 | 0 | 36 | TA 504 | 69 | 0 | 69 | 0 | 69 | 1 | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | OPGW Stringing | opgw_stringing | 2026-06-27 | 10.08 | 0 | 10.08 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Earthing | No | 358 | 380 | 0 | 373 | 7 | 98% | 0 | 0 | 0 | 0 | 0 | TA 505 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Piling Foundation - Concreting | No | 358 | 380 | 0 | 373 | 7 | 98% | 0 | 0 | 0 | 0 | 0 | TA 505 | 379 | 375 | 4 | 3 | 4 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | FOUNDATION | foundation_pile_or_all_fallback | 2026-06-28 | 1 | -2 | 3 | -3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Tower Erection | No | 358 | 380 | 0 | 353 | 27 | 93% | 0 | 0 | 0 | 5 | 10 | TA 505 | 379 | 357 | 22 | 6 | 22 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | TOWER ERECTION | tower_erection | 2026-06-28 | 1 | -4 | 5 | -6 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Tightening | No | 358 | 380 | 0 | 43 | 337 | 11% | 0 | 0 | 0 | 5 | 10 | TA 505 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 126 | 139.63 | 0 | 15.01 | 124.62 | 11% | 0 | 0 | 0 | 40 | 40 | TA 505 | 139.6 | 15.462 | 124.138 | 9.751 | 124.138 | 1 | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | Stringing (Final Sag) | final_sag | 2026-06-28 | 0.03 | -0.452 | 0.482 | -9.751 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
MP | TA505 - TA-505- 765 KV D/C Beawar - Mandsaur TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 126 | 139.63 | 0 | 12.33 | 127.3 | 9% | 0 | 0 | 0 | 0 | 70 | TA 505 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Check Survey | Km | 211 | 222.83 | 0 | 222.83 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 506 | 223 | 223 | 0 | 0 | 0 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | Check Survey | check_survey | 2026-06-27 | -0.17 | -0.17 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Open Foundation - RCC | No | 583 | 605 | 0 | 487 | 118 | 80% | 0 | 25 | 10 | 40 | 40 | TA 506 | 602 | 492 | 110 | 7 | 110 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | FOUNDATION | foundation_open_or_all_fallback | 2026-06-27 | 3 | -5 | 8 | 3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Earthing | No | 583 | 605 | 0 | 337 | 268 | 56% | 0 | 25 | 9 | 40 | 40 | TA 506 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Tower Erection | No | 583 | 605 | 0 | 397 | 208 | 66% | 0 | 25 | 18 | 55 | 55 | TA 506 | 602 | 405 | 197 | 15 | 197 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | TOWER ERECTION | tower_erection | 2026-06-27 | 3 | -8 | 11 | 3 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Tightening | No | 583 | 605 | 0 | 400 | 205 | 66% | 0 | 25 | 18 | 55 | 55 | TA 506 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 211 | 222.83 | 0 | 53.77 | 169.06 | 24% | 0 | 30 | 8.59 | 42 | 40 | TA 506 | 223 | 55.632 | 167.368 | 7.478 | 167.368 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | Stringing | stringing | 2026-06-27 | -0.17 | -1.862 | 1.692 | 1.112 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TA506 - TA-506- 400 KV D/C Chittorgarh - Sirohi TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 211 | 222.83 | 0 | 0 | 222.83 | 0% | 0 | 30 | 0 | 40 | 40 | TA 506 | 231 | 0 | 231 | 0 | 231 | 1 | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | OPGW Stringing | opgw_stringing | 2026-06-27 | -8.17 | 0 | -8.17 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Check Survey | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 10.66 | 8 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Open Foundation - RCC | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 28 | 16 | 11 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Earthing | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 28 | 16 | 11 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Tower Erection | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Tightening | No | 0 | 225 | 0 | 0 | 225 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | Conductor Stringing - S&C | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB 611 - 765KV D/C WZ4 MORENA |  | OPGW Stringing - S&C | Km | 0 | 84.83 | 0 | 0 | 84.83 | 0% | 0 | 0 | 0 | 0 | 0 | TB 611 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Check Survey | Km | 0 | 63.89 | 0 | 63.89 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 501 | 73 | 73.178 | -0.178 | 0 | -0.178 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Check Survey; Check Survey | check_survey | 2026-06-27 | -9.11 | -9.288 | 0.178 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Open Foundation - RCC | No | 0 | 199 | 0 | 174 | 25 | 87% | 0 | 0 | 25 | 0 | 0 | TB 501 | 238 | 235 | 3 | 2 | 1 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Foundation; Foundation | foundation_open_or_all_fallback | 2026-06-27 | -39 | -61 | 22 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Earthing | No | 0 | 199 | 0 | 173 | 26 | 87% | 0 | 0 | 26 | 0 | 0 | TB 501 | 238 | 233 | 5 | 3 | 2 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Earthing; Earthing | earthing | 2026-06-27 | -39 | -60 | 21 | 23 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Tower Erection | No | 0 | 199 | 0 | 169 | 30 | 85% | 0 | 0 | 30 | 0 | 0 | TB 501 | 238 | 230 | 8 | 3 | 5 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Tower Erection; Tower Erection | tower_erection | 2026-06-27 | -39 | -61 | 22 | 27 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Tightening | No | 0 | 199 | 0 | 108 | 91 | 54% | 0 | 0 | 91 | 0 | 0 | TB 501 | 238 | 223 | 15 | 0 | 11 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Tack Welding; Tack Welding | tack_welding_fallback | 2026-06-27 | -39 | -115 | 76 | 91 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | Conductor Stringing - S&C | Km | 0 | 63.89 | 0 | 21.36 | 42.53 | 33% | 0 | 0 | 39.58 | 0 | 0 | TB 501 | 73.24 | 67.431 | 5.809 | 2.4654 | 3.3436 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | Final Sag; Final Sag | final_sag | 2026-06-27 | -9.35 | -46.071 | 36.721 | 37.1146 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
MP | TB501 - TB-501 NEEMUCH SS & TL | Nabajit Baruah | OPGW Stringing - S&C | Km | 0 | 63.89 | 0 | 21.36 | 42.53 | 33% | 0 | 0 | 41.76 | 0 | 0 | TB 501 | 73.24 | 53.7218 | 19.5182 | 15.7486 | 3.7696 | 2 | TB 501 - DPR - 2026-06-27.xlsx | Summary | OPGW; OPGW | opgw_stringing | 2026-06-27 | -9.35 | -32.3618 | 23.0118 | 26.0114 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Check Survey | Km | 114.59 | 86.11 | 0 | 62.25 | 23.86 | 72% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 103.9731 | 0 | 0 | 0 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Check Survey - Main Line; Check Survey - Loop In; Check Survey - Loop Out | check_survey | 2026-06-28 | -17.8631 | -41.7231 | 23.86 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Open Foundation - RCC | No | 345 | 262 | 0 | 130 | 132 | 50% | 0 | 0 | 4 | 6 | 3 | TB 608 | 443 | 132 | 311 | 4 | 307 | 4 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Normal Foundation - Main Line; Normal Foundation - Loop In (Incld. Stone Column); Normal Foundation - Loop Out (Incld. Stone Column); Foundation | foundation_open_or_all_fallback | 2026-06-28 | -181 | -2 | -179 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Earthing | No | 347 | 264 | 0 | 127 | 137 | 48% | 0 | 0 | 5 | 6 | 3 | TB 608 | [5 empty] | 0 |  |  |  | earthing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Piling Foundation - Concreting | No | 2 | 2 | 0 | 1 | 1 | 50% | 0 | 0 | 0 | 0 | 0 | TB 608 | 17 | 14 | 3 | 0 | 3 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Pile Foundation_River_Main Line; Pile Foundation_Non River_Loop In; Pile Foundation_Non River_Loop Out | foundation_pile_or_all_fallback | 2026-06-28 | -15 | -13 | -2 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Tower Erection | No | 345 | 264 | 0 | 27 | 237 | 10% | 0 | 0 | 12 | 12 | 12 | TB 608 | 349 | 31 | 318 | 10 | 308 | 4 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Tower Erection - Main Line; Tower Erection - loop In; Tower Erection - Loop Out; Erection | tower_erection | 2026-06-28 | -85 | -4 | -81 | 2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Tightening | No | 345 | 264 | 0 | 27 | 237 | 10% | 0 | 0 | 12 | 12 | 12 | TB 608 | 318 | 0 | 318 | 0 | 318 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Tack welding - Main Line; Tack welding - Loop In; Tack welding - Loop Out | tack_welding_fallback | 2026-06-28 | -54 | 27 | -81 | 12 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | Conductor Stringing - S&C | Km | 114.59 | 86.11 | 0 | 0 | 86.11 | 0% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 0 | 103.9731 | 0 | 103.9731 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | Final Sag - Main Line; Final Sag - Loop In; Final Sag - Loop Out | final_sag | 2026-06-28 | -17.8631 | 0 | -17.8631 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
North East Region (NER) | TB-608 - TB-608- Bornagar TL | N K Gupta | OPGW Stringing - S&C | Km | 114.59 | 86.11 | 0 | 0 | 86.11 | 0% | 0 | 0 | 0 | 0 | 0 | TB 608 | 103.9731 | 0 | 103.9731 | 0 | 103.9731 | 3 | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | OPGW Stringing - Main Line; OPGW Stringing - Loop In; OPGW Stringing - Loop Out | opgw_stringing | 2026-06-28 | -17.8631 | 0 | -17.8631 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Check Survey | Km | 120.94 | 124.32 | 0 | 124.32 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 512 | 124.568 | 124.568 | 0 | 0 | 0 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Check Survey (Km) | check_survey | 2026-06-28 | -0.248 | -0.248 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Earthing | No | 315 | 319 | 0 | 306 | 13 | 96% | 0 | 0 | 6 | 0 | 0 | TA 512 | 319 | 269 | 50 | 30 | 20 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Earthing (Nos.) | earthing | 2026-06-28 | 0 | 37 | -37 | -24 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Tightening | No | 315 | 319 | 30 | 213 | 106 | 67% | 0 | 0 | 0 | 0 | 0 | TA 512 | 319 | 79 | 240 | 30 | 210 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Tack Welding | tack_welding_fallback | 2026-06-28 | 0 | 134 | -134 | -30 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | Conductor Stringing - S&C | Km | 120.94 | 124.32 | 12 | 0 | 124.32 | 0% | 0 | 0 | 0 | 24.718 | 23.1381 | TA 512 | 124.568 | 0 | 124.568 | 0 | 124.568 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Final Sag | final_sag | 2026-06-28 | -0.248 | 0 | -0.248 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA-512 - TA-512 765 KV D/C Bikaner IV PS to Siwani 2nd Part-I (TL01) Transmission Line. | N K Gupta | OPGW Stringing - S&C | Km | 120.94 | 124.32 | 20 | 0 | 124.32 | 0% | 0 | 0 | 0 | 0 | 0 | TA 512 | 124.568 | 0 | 124.568 | 0 | 124.568 | 1 | TA 512 - DPR - 2026-06-28.xlsx | Summary E | OPGW (Km) | opgw_stringing | 2026-06-28 | -0.248 | 0 | -0.248 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Open Foundation - RCC | No | 0 | 306 | 0 | 306 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 413 | 316 | 316 | 0 | 0 | 0 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-28 | -10 | -10 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Earthing | No | 0 | 306 | 0 | 306 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 413 | 309 | 307 | 2 | 1 | 1 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Earthing (Nos.) | earthing | 2026-06-28 | -3 | -1 | -2 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Tower Erection | No | 0 | 306 | 0 | 303 | 3 | 99% | 0 | 0 | 0 | 3 | 0 | TA 413 | 306 | 302 | 4 | 1 | 3 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Tower Erection (Nos) | tower_erection | 2026-06-28 | 0 | 1 | -1 | -1 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Tightening | No | 0 | 306 | 0 | 303 | 3 | 99% | 0 | 0 | 0 | 3 | 0 | TA 413 | 306 | 255 | 51 | 15 | 36 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Tack Welding | tack_welding_fallback | 2026-06-28 | 0 | 48 | -48 | -15 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | Conductor Stringing - S&C | Km | 0 | 117.85 | 0 | 78.3 | 39.55 | 66% | 0 | 0 | 11.27 | 20.065 | 10.574 | TA 413 | 117.8509 | 77.189 | 40.6619 | 10.051 | 30.6109 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | Final Sag | final_sag | 2026-06-28 | -0.000851 | 1.111 | -1.1119 | 1.219 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TA413 - TA-413 Bikaner III to Nimrana II | N K Gupta | OPGW Stringing - S&C | Km | 0 | 117.85 | 0 | 51.96 | 65.89 | 44% | 0 | 0 | 18.28 | 38.08 | 10.752 | TA 413 | 117.8509 | 59.762 | 58.0889 | 9.298 | 48.7909 | 1 | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | OPGW (Km) | opgw_stringing | 2026-06-28 | -0.000851 | -7.802 | 7.8011 | 8.982 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Check Survey | Km | 0 | 73.8 | 0 | 27.81 | 45.99 | 38% | 0 | 0 | 0 | 0 | 0 | TB 507 | 204.156 | 204.156 | 0 | 0 | 0 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Check Survey (Kms); Check Survey (Kms) | check_survey | 2026-06-28 | -130.356 | -176.346 | 45.99 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Open Foundation - RCC | No | 0 | 500 | 0 | 138 | 362 | 28% | 0 | 34 | 0 | 38 | 40 | TB 507 | 556 | 342 | 214 | 18 | 196 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Foundation (Nos); Foundation (Nos) | foundation_open_or_all_fallback | 2026-06-28 | -56 | -204 | 148 | -18 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Earthing | No | 0 | 500 | 0 | 59 | 441 | 12% | 0 | 34 | 0 | 38 | 40 | TB 507 | 556 | 269 | 287 | 0 | 287 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Earthing (Nos); Earthing (Nos) | earthing | 2026-06-28 | -56 | -210 | 154 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Tower Erection | No | 0 | 500 | 0 | 12 | 488 | 2% | 0 | 40 | 0 | 39 | 45 | TB 507 | 556 | 221 | 335 | 15 | 320 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Tower Erection (Nos); Tower Erection (Nos) | tower_erection | 2026-06-28 | -56 | -209 | 153 | -15 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Tightening | No | 0 | 500 | 0 | 1 | 499 | 0% | 0 | 40 | 0 | 39 | 45 | TB 507 | 556 | 104 | 452 | 24 | 428 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Tack Welding (Nos); Tack Welding (Nos) | tack_welding_fallback | 2026-06-28 | -56 | -103 | 47 | -24 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | Conductor Stringing - S&C | Km | 0 | 73.8 | 0 | 0 | 73.8 | 0% | 0 | 0 | 0 | 19.128 | 20 | TB 507 | 204.156 | 21.36 | 182.796 | 0 | 182.796 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | Final Sag (Kms); Final Sag (Kms) | final_sag | 2026-06-28 | -130.356 | -21.36 | -108.996 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB 507 - TB-507 Fatehgarh Bhinmal TL | N K Gupta | OPGW Stringing - S&C | Km | 0 | 73.8 | 0 | 0 | 73.8 | 0% | 0 | 0 | 0 | 0 | 0 | TB 507 | 204.156 | 0 | 204.156 | 0 | 204.156 | 2 | TB 507 - DPR - 2026-06-28.xlsx; TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery; 765kV Summery | OPGW Stringing (Kms); OPGW Stringing (Kms) | opgw_stringing | 2026-06-28 | -130.356 | 0 | -130.356 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Check Survey | Km | 0 | 191.39 | 0 | 191.39 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TB 408 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Tightening | No | 0 | 485 | 0 | 324 | 161 | 67% | 0 | 0 | 0 | 0 | 0 | TB 408 | 485 | 433 | 52 | 0 | 52 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Tack Welding (Nos) | tack_welding_fallback | 2026-06-01 | 0 | -109 | 109 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | Conductor Stringing - S&C | Km | 0 | 191.39 | 0 | 125.82 | 65.57 | 66% | 0 | 0 | 0 | 0 | 0 | TB 408 | 191.392 | 125.9367 | 65.4553 | 0 | 31.6893 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Final Sag (Kms) | final_sag | 2026-06-01 | -0.002 | -0.1167 | 0.1147 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Rajasthan | TB408 - TB-408 765 KV D/C Fathegarh-3 Bewar T/Line (Part-F) | N K Gupta | OPGW Stringing - S&C | Km | 0 | 191.39 | 0 | 38.37 | 153.02 | 20% | 0 | 0 | 0 | 0 | 0 | TB 408 | 191.392 | 88.466 | 102.926 | 0 | 69.16 | 1 | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | OPGW (Kms) | opgw_stringing | 2026-06-01 | -0.002 | -50.096 | 50.094 | 0 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Check Survey | Km | 0 | 115.13 | 0 | 115.13 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Tightening | No | 0 | 302 | 0 | 302 | 0 | 100% | 4 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | tack_welding_fallback | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | Conductor Stringing - S&C | Km | 0 | 115.13 | 0 | 110.46 | 4.67 | 96% | 0 | 0 | 4 | 0 | 0 | TA 416 | 115.134 | 111.1 | 4.034 | 3.319 | 0.676 | 1 | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | Stringing | stringing | 2026-06-25 | -0.004 | -0.64 | 0.636 | 0.681 | COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
UP | TA416 - TA416-765KV Neemrana to Bareilly | Arun Felbin R | OPGW Stringing - S&C | Km | 0 | 115.13 | 0 | 100.28 | 14.85 | 87% | 0 | 0 | 0 | 0 | 0 | TA 416 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Check Survey | Km | 80 | 73.92 | 0 | 73.92 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Open Foundation - RCC | No | 159 | 147 | 4 | 22 | 125 | 15% | 0 | 0 | 0 | 2 | 2 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Earthing | No | 228 | 197 | 14 | 20 | 177 | 10% | 0 | 0 | 0 | 2 | 2 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Piling Foundation - Concreting | No | 69 | 50 | 10 | 0 | 50 | 0% | 0 | 0 | 0 | 4 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Tower Erection | No | 228 | 197 | 30 | 1 | 196 | 1% | 0 | 0 | 0 | 3 | 3 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Tightening | No | 228 | 197 | 30 | 1 | 196 | 1% | 0 | 0 | 0 | 3 | 3 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | Conductor Stringing - S&C | Km | 80 | 73.92 | 20 | 0 | 73.92 | 0% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA 609 - TB 609 | Arun Felbin R | OPGW Stringing - S&C | Km | 80 | 73.92 | 20 | 0 | 73.92 | 0% | 0 | 0 | 0 | 0 | 0 | TA 609 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Check Survey | Km | 111.27 | 84.48 | 0 | 80.35 | 4.13 | 95% | 0 | 16.867 | 0 | 16.484 | 0 | TA 510 | 114.516 | 94.519 | 19.997 | 0 | 19.997 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Check Survey (Km) | check_survey | 2026-06-28 | -30.036 | -14.169 | -15.867 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Earthing | No | 293 | 224 | 0 | 83 | 141 | 37% | 0 | 47 | 9 | 20 | 20 | TA 510 | 293 | 78 | 215 | 7 | 208 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Earthing (Nos.) | earthing | 2026-06-28 | -69 | 5 | -74 | 2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Piling Foundation - Concreting | No | 293 | 224 | 0 | 82 | 142 | 37% | 0 | 47 | 9 | 20 | 20 | TA 510 | 293 | 85 | 208 | 10 | 198 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Foundation (Nos.) | foundation_pile_or_all_fallback | 2026-06-28 | -69 | -3 | -66 | -1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Tower Erection | No | 293 | 224 | 8 | 33 | 191 | 15% | 0 | 30 | 1 | 10 | 10 | TA 510 | 293 | 40 | 253 | 5 | 248 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Tower Erection (Nos) | tower_erection | 2026-06-28 | -69 | -7 | -62 | -4 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Tightening | No | 293 | 224 | 8 | 33 | 191 | 15% | 0 | 30 | 1 | 10 | 10 | TA 510 | 293 | 13 | 280 | 0 | 280 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Tack Welding | tack_welding_fallback | 2026-06-28 | -69 | 20 | -89 | 1 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | Conductor Stringing - S&C | Km | 111.27 | 84.48 | 11 | 0 | 84.48 | 0% | 0 | 0 | 0 | 0 | 0 | TA 510 | 114.516 | 0 | 114.516 | 0 | 114.516 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | Final Sag | final_sag | 2026-06-28 | -30.036 | 0 | -30.036 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-510 - TA-510-765kV Ahmedabad – Oplad TL | Arun Felbin R | OPGW Stringing - S&C | Km | 111.27 | 84.48 | 20 | 0 | 84.48 | 0% | 0 | 0 | 0 | 0 | 0 | TA 510 | 114.516 | 0 | 114.516 | 0 | 114.516 | 1 | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | OPGW (Km) | opgw_stringing | 2026-06-28 | -30.036 | 0 | -30.036 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Check Survey | Km | 83.14 | 83.33 | 0 | 83.33 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Open Foundation - RCC | No | 215 | 218 | 10 | 14 | 204 | 6% | 0 | 0 | 5 | 2 | 2 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Earthing | No | 215 | 218 | 10 | 14 | 204 | 6% | 0 | 0 | 5 | 2 | 2 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Tower Erection | No | 215 | 218 | 12 | 0 | 218 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Tightening | No | 215 | 218 | 12 | 0 | 218 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | Conductor Stringing - S&C | Km | 83.14 | 83.33 | 2 | 0 | 83.33 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA-515 - TA-515 - 800 kV HVDC KHAVDA-NAGPUR TL-03 | Arun Felbin R | OPGW Stringing - S&C | Km | 83.14 | 83.33 | 2 | 0 | 83.33 | 0% | 0 | 0 | 0 | 0 | 0 | TA 515 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Check Survey | Km | 130 | 127.85 | 0 | 127.85 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | TA 414 | 127.799 | 127.799 | 0 | 0 | 0 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Check Survey (Km) | check_survey | 2026-06-29 | 0.051 | 0.051 | 0 | 0 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Open Foundation - RCC | No | 340 | 351 | 0 | 316 | 35 | 90% | 0 | 0 | 15 | 15 | 0 | TA 414 | 352 | 319 | 33 | 17 | 16 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Foundation (Nos.) | foundation_open_or_all_fallback | 2026-06-29 | -1 | -3 | 2 | -2 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Earthing | No | 340 | 351 | 0 | 314 | 37 | 89% | 0 | 0 | 16 | 15 | 0 | TA 414 | 352 | 296 | 56 | 36 | 20 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Earthing (Nos.) | earthing | 2026-06-29 | -1 | 18 | -19 | -20 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Tower Erection | No | 340 | 351 | 0 | 235 | 116 | 67% | 0 | 0 | 25 | 40 | 45 | TA 414 | 352 | 235 | 117 | 30 | 87 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Tower Erection (Nos) | tower_erection | 2026-06-29 | -1 | 0 | -1 | -5 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Tightening | No | 340 | 351 | 0 | 235 | 116 | 67% | 0 | 0 | 25 | 40 | 45 | TA 414 | 352 | 120 | 232 | 61 | 171 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Tack Welding | tack_welding_fallback | 2026-06-29 | -1 | 115 | -116 | -36 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | Conductor Stringing - S&C | Km | 130 | 127.85 | 0 | 16.24 | 111.61 | 13% | 0 | 0 | 6.99 | 17.592 | 17.562 | TA 414 | 127.799 | 15.944 | 111.855 | 9.1022 | 102.7528 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | Final Sag | final_sag | 2026-06-29 | 0.051 | 0.296 | -0.245 | -2.1122 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA414 - 765 kV D/C VATAMAN-NAVSARI TL | Arun Felbin R | OPGW Stringing - S&C | Km | 130 | 127.85 | 0 | 0 | 127.85 | 0% | 0 | 0 | 0 | 0 | 0 | TA 414 | 127.799 | 0 | 127.799 | 0 | 127.799 | 1 | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | OPGW (Km) | opgw_stringing | 2026-06-29 | 0.051 | 0 | 0.051 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Check Survey | Km | 139.48 | 142.07 | 0 | 134.13 | 7.94 | 94% | 0 | 0 | 0 | 1.67 | 6.25 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Open Foundation - RCC | No | 361 | 356 | 15 | 24 | 332 | 7% | 0 | 0 | 2 | 5 | 5 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Earthing | No | 722 | 377 | 30 | 24 | 353 | 6% | 0 | 0 | 2 | 0 | 5 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Piling Foundation - Concreting | No | 361 | 21 | 15 | 0 | 21 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Tower Erection | No | 361 | 377 | 15 | 0 | 377 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Tightening | No | 361 | 377 | 15 | 0 | 377 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | Conductor Stringing - S&C | Km | 139.48 | 142.07 | 5 | 0 | 142.07 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA514 - TA 514- 800KV HVDC Khavda to Nagpur TL-02. | Arun Felbin R | OPGW Stringing - S&C | Km | 139.48 | 142.07 | 5 | 0 | 142.07 | 0% | 0 | 0 | 0 | 0 | 0 | TA 514 | [5 empty] | 0 |  |  |  | NO_PROJECT_IN_RAW_DPR_RECALC | [5 empty] | NO_RAW_DPR_STATUS_DATA | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Check Survey | Km | 186.3 | 88.49 | 0 | 0 | 88.49 | 0% | 0 | 0 | 0.29 | 6.622 | 0 | TA 602 | [5 empty] | 0 |  |  |  | check_survey | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Open Foundation - RCC | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 1 | 30 | 30 | TA 602 | 480 | 154 | 326 | 11 | 315 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Foundation | foundation_open_or_all_fallback | 2026-06-26 | -249 | -154 | -95 | -10 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Earthing | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 0 | 30 | 30 | TA 602 | 480 | 96 | 384 | 10 | 374 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Earthing | earthing | 2026-06-26 | -249 | -96 | -153 | -10 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Tower Erection | No | 494 | 231 | 10 | 10 | 221 | 4% | 0 | 0 | 0 | 30 | 35 | TA 602 | 480 | 52 | 428 | 25 | 403 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Tower Erection | tower_erection | 2026-06-26 | -249 | -42 | -207 | -25 | REVISED_MISMATCH; COMPLETED_MAY_MISMATCH; BALANCE_MAY_MISMATCH; JUNE_ACTUAL_MISMATCH; DASHBOARD_JUNE_ZERO_BUT_DPR_HAS_PROGRESS | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Tightening | No | 494 | 231 | 10 | 0 | 231 | 0% | 0 | 0 | 0 | 30 | 35 | TA 602 | 480 | 0 | 480 | 0 | 480 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Tack welding | tack_welding_fallback | 2026-06-26 | -249 | 0 | -249 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | Conductor Stringing - S&C | Km | 186.3 | 88.49 | 5 | 0 | 88.49 | 0% | 0 | 0 | 0 | 0 | 0 | TA 602 | 184.986 | 0 | 184.986 | 0 | 184.986 | 1 | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | Stringing(Km) | stringing | 2026-06-26 | -96.496 | 0 | -96.496 | 0 | REVISED_MISMATCH; BALANCE_MAY_MISMATCH | TRUE
Western Region | TA602 - TA602-800KV HVDC KPS2 - Nagpur Transmission Line Package TL06 | Arun Felbin R | OPGW Stringing - S&C | Km | 186.3 | 88.49 | 5 | 0 | 88.49 | 0% | 0 | 0 | 0 | 0 | 0 | TA 602 | [5 empty] | 0 |  |  |  | opgw_stringing | [5 empty] | NO_MATCHING_ACTIVITY_IN_RAW_DPR | TRUE

## DPR Recalc Diagnostics
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | TemplateSheet | TemplateApplied | TemplateChanges | FallbackNote | SectionsDetected | HeadersDetected | Rows | FilenameDate | InternalDate | DateQuality | Status | Reason
TA 310 - DPR - 2026-01-12.xlsx | TA 310 | NKTL DPR | NKTL DPR |  | filename | TA 310 Status | TRUE | C1:Activity->activity_raw; C3:Unit->quantity_loa; C4:LOA Qty.->quantity_estimated_or_total; C6:Cumulative L2 till Dec-2025->cumulative_last_month; C9:L2 for Jan'26->plan_for_month; C10:Plan for Jan'2026->today_progress; C11:Today's Progress->progress_for_month; C13:WIP->gangs_working; C14:Gangs at Present->cumulative_progress; C15:Cumulative Progress till date->balance_progress; C16:Balance Work->remarks |  | 1 | 1 | 13 | 2026-01-12 | 2026-01-12 | MATCH | OK
TA 325 - DPR - 2026-01-19.xlsx | TA 325 | 765KV TA 325 ANTL | 765KV TA 325 ANTL |  | filename | TA 325 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(Dec'25)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working |  | 1 | 1 | 6 | 2026-01-19 | 2026-01-19 | MATCH | OK
TA 413 - DPR - 2026-06-28.xlsx | TA 413 | TA413_PBNTL | TA413_PBNTL |  | filename | TA 413 Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:As per latest Estimate->quantity_estimated_or_total; C5:Cumm. Progress up to last Month->cumulative_last_month; C7:Plan for this Month->plan_for_month; C8:Current Month Achieved (As on dated )->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working | XML scrub fallback used for sheet 'TA413_PBNTL' | 1 | 1 | 12 | 2026-06-28 | 2024-03-12 | MISMATCH | OK
TA 414 - DPR - 2026-06-29.xlsx | TA 414 | VNTL - KEC | VNTL - KEC |  | filename | TA 414 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month (May'26)->cumulative_last_month; C6:L3 Plan for the month (June'26 )->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks | XML scrub fallback used for sheet 'VNTL - KEC' | 1 | 1 | 13 | 2026-06-29 |  | MISSING_INTERNAL | OK
TA 416 - DPR - 2026-06-25.xlsx | TA 416 | MASTER SHEET | MASTER SHEET |  | filename | TA 416 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-25 | 2026-06-25 | MATCH | OK
TA 418 - DPR - 2026-06-17.xlsx | TA 418 | MASTER SHEET | MASTER SHEET |  | filename | TA 418 Status | TRUE | C1:Activity->activity_raw; C3:Final Estimated Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress till Date for the Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-17 | 2026-06-17 | MATCH | OK
TA 419 - DPR - 2026-06-26.xlsx | TA 419 | DPR_TA419 | DPR_TA419 |  | filename | TA 419 Status | TRUE | C3:Activity->activity_raw; C4:Quantity->quantity_loa; C5:unnamed_col_5->quantity_estimated_or_total; C7:unnamed_col_7->cumulative_last_month; C9:unnamed_col_9->plan_for_month; C10:Progress for the Month->progress_for_month; C11:unnamed_col_11->today_progress; C12:Cumulative Progress->cumulative_progress; C13:Balance Progress->balance_progress; C14:Gangs working Jun-26->gangs_working; C15:2026-06-26 00:00:00 Remarks->remarks | XML scrub fallback used for sheet 'DPR_TA419' | 1 | 1 | 14 | 2026-06-26 |  | MISSING_INTERNAL | OK
TA 421 - DPR - 2026-06-25.xlsx | TA 421 | Master Sheet | Master Sheet |  | filename | TA 421 Status | TRUE | C3:Activity->activity_raw; C4:Final Estimated Quantity->quantity_estimated_or_total; C6:Cumulative Progress till Last Month->cumulative_last_month; C8:Plan for the Month->plan_for_month; C9:Today's Progress->today_progress; C10:Progress till Date for the Month->progress_for_month; C12:Completed till Date->cumulative_progress; C13:Balance Work->balance_progress; C15:Gangs at Present->gangs_working |  | 1 | 1 | 10 | 2026-06-25 | 2026-06-25 | MATCH | OK
TA 504 - DPR - 2026-06-27.xlsx | TA 504 | DPR_TA-504 | DPR_TA-504 |  | filename | TA 504 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-01 00:00:00->cumulative_last_month; C6:Balance as on 1 June'26->balance_progress; C7:2026-06-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-504' | 1 | 1 | 6 | 2026-06-27 |  | MISSING_INTERNAL | OK
TA 505 - DPR - 2026-06-28.xlsx | TA 505 | DPR-Summary | DPR-Summary |  | filename | TA 505 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-31 00:00:00->cumulative_last_month; C6:Balance as on 1st June-26->balance_progress; C7:June'26 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress |  | 1 | 1 | 6 | 2026-06-28 |  | MISSING_INTERNAL | OK
TA 506 - DPR - 2026-06-27.xlsx | TA 506 | DPR_TA-506 | DPR_TA-506 |  | filename | TA 506 Status | TRUE | C2:PARTICULARS->activity_raw; C4:Total Qty->quantity_estimated_or_total; C5:Comp Till 2026-05-01 00:00:00->cumulative_last_month; C6:Balance as on 1 June'26->balance_progress; C7:2026-06-01 00:00:00 Plan->plan_for_month; C8:Actual->progress_for_month; C10:Cumulative->cumulative_progress | XML scrub fallback used for sheet 'DPR_TA-506' | 1 | 1 | 6 | 2026-06-27 |  | MISSING_INTERNAL | OK
TA 509 - DPR - 2026-06-28.xlsx | TA 509 | SUMMARY | SUMMARY |  | filename | TA 509 Status | TRUE | C1:Activity->activity_raw; C4:LOA Quantity->quantity_loa; C5:Final Estimated Quantity->quantity_estimated_or_total; C7:Cum Progress till Last Month->cumulative_last_month; C9:Plan for the Month->plan_for_month; C10:Progress for Today->today_progress; C11:Progress for the Month->progress_for_month; C13:Cum. Progress till date->cumulative_progress; C14:Balance Work->balance_progress; C16:Gangs at Present->gangs_working |  | 1 | 1 | 4 | 2026-06-28 | 2026-06-28 | MATCH | OK
TA 510 - DPR - 2026-06-28.xlsx | TA 510 | AOTL - KEC | AOTL - KEC |  | filename | TA 510 Status | TRUE | C2:Activity->activity_raw; C3:Estimated Quantity->quantity_estimated_or_total; C4:Cumm. Progress up to till last Month May'26)->cumulative_last_month; C5:Target as per L2 Schedule Cummulative (upto May'26)->plan_for_month; C7:Today's Progress->today_progress; C8:Progress in this month->progress_for_month; C9:Cumm. Progress till date->cumulative_progress; C10:Cumm. Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-06-28 |  | MISSING_INTERNAL | OK
TA 512 - DPR - 2026-06-28.xlsx | TA 512 | Summary E | Summary E |  | filename | TA 512 Status | TRUE | C2:Activity->activity_raw; C3:LOA Qty->quantity_loa; C4:Estimated Quantity->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (May'26)->cumulative_last_month; C7:Month's Plan as per L2 Schedule->plan_for_month; C8:Progress of Month->progress_for_month; C9:Today->today_progress; C10:Cumulative Progress Till Date->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs/MP->gangs_working |  | 1 | 1 | 13 | 2026-06-28 |  | MISSING_INTERNAL | OK
TA 513 - DPR - 2026-06-28.xlsx | TA 513 | Summary | Summary |  | filename | TA 513 Status | TRUE |  |  | 0 | 0 | 0 | 2026-06-28 |  | MISSING_INTERNAL | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 601 - DPR - 2026-06-27.xlsx | TA 601 | Master Sheet | Master Sheet |  | filename | TA 601 Status | TRUE | C2:Activity->activity_raw; C3:Scope Quantity->quantity_estimated_or_total; C5:Cumulative Progress till Last Month->cumulative_last_month; C7:Plan for the Month->plan_for_month; C8:Today's Progress->today_progress; C9:Progress for Current Month->progress_for_month; C11:Completed till Date->cumulative_progress; C12:Balance Work->balance_progress; C14:Gangs at Present->gangs_working |  | 1 | 1 | 11 | 2026-06-27 | 2026-06-27 | MATCH | OK
TA 602 - DPR - 2026-06-26.xlsx | TA 602 | 800kV HVDC TA-602 | 800kV HVDC TA-602 |  | filename | TA 602 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress till Last Month(May'26)->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working | XML scrub fallback used for sheet '800kV HVDC TA-602' | 1 | 1 | 6 | 2026-06-26 | 2026-06-27 | MISMATCH | OK
TB 401 - DPR - 2025-12-25.xlsx | TB 401 | Progress | Progress |  | filename | TB 401 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Quantity->quantity_estimated_or_total; C4:Cumulative Progress Till last Month->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed Till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at present->gangs_working |  | 1 | 1 | 6 | 2025-12-25 | 2025-12-26 | MISMATCH | OK
TB 408 - DPR - 2026-06-01.xlsx | TB 408 | Progress Summary | Progress Summary |  | filename | TB 408 Status | TRUE | C2:Activity->activity_raw; C3:As per latest Estimate->quantity_estimated_or_total; C4:Cumm. Progress up to last Month->cumulative_last_month; C6:Plan for this Month->plan_for_month; C7:Today Progress->today_progress; C8:MTD->progress_for_month; C10:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:Gangs at present->gangs_working |  | 1 | 1 | 7 | 2026-06-01 | 2026-06-01 | MATCH | OK
TB 412 - DPR - 2026-06-24.xlsx | TB 412 | TB-412 SUMMARY | TB-412 SUMMARY |  | filename | TB 412 Status | TRUE | C2:Activity->activity_raw; C3:Total Quantity->quantity_loa; C4:unnamed_col_4->quantity_estimated_or_total; C5:Cumm. Progress up to Last Month (May'26)->cumulative_last_month; C7:Target of Month for (June'2026)->plan_for_month; C8:Comp This Month (June'2026)->progress_for_month; C9:Cumulative Progress->cumulative_progress; C11:Balance->balance_progress; C12:No of Gangs->gangs_working; C13:Remark->remarks |  | 1 | 1 | 13 | 2026-06-24 | 2026-06-24 | MATCH | OK
TB 501 - DPR - 2026-06-27.xlsx | TB 501 | Summary | Summary |  | filename | TB 501 Status | TRUE | C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (June'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks; C2:Activity->activity_raw; C4:Total Quantity->quantity_estimated_or_total; C8:Actual->cumulative_last_month; C9:Progress of Current Month (June'26) Plan->plan_for_month; C10:Today->today_progress; C11:Progress in Month->progress_for_month; C13:Completed->cumulative_progress; C14:Balance->balance_progress; C16:Available Gang->gangs_working; C18:Critical Issues, if any & Remark->remarks |  | 2 | 2 | 20 | 2026-06-27 | 2026-06-27 | MATCH | OK
TB 507 [MAIN] - DPR - 2026-06-28.xlsx | TB 507 | 400kV Summery | 400kV Summery | MAIN | config | TB 507 400kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For JUNE'26->plan_for_month; C7:Progress in JUNE'26->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jun-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 14 | 2026-06-28 |  | MISSING_INTERNAL | OK
TB 507 - DPR - 2026-06-28.xlsx | TB 507 | 765kV Summery | 765kV Summery | 765kV | config | TB 507 765kV Status | TRUE | C2:Activity->activity_raw; C3:LOA Quantity->quantity_loa; C4:Estimated Line Quantity->quantity_estimated_or_total; C5:Cumm. Progress till Last Month->cumulative_last_month; C6:Plan For June'25->plan_for_month; C7:Progress in June'25->progress_for_month; C9:Today's Progress->today_progress; C10:Cumulative progress till date->cumulative_progress; C11:Balance->balance_progress; C12:Gangs working Jun-26->gangs_working; C13:Manpower->remarks |  | 1 | 1 | 12 | 2026-06-28 |  | MISSING_INTERNAL | OK
TB 605 - DPR - 2026-06-28.xlsx | TB 605 | TB-605 | TB-605 |  | filename | TB 605 Status | TRUE | C1:Activity->activity_raw; C2:Final Estimated Qty->quantity_estimated_or_total; C4:Cumulative Progress till Last Month->cumulative_last_month; C6:Plan for the Month->plan_for_month; C7:Today's Progress->today_progress; C8:Progress till Date for the Month->progress_for_month; C10:Completed till Date->cumulative_progress; C11:Balance Work->balance_progress; C13:Gangs at Present->gangs_working |  | 1 | 1 | 7 | 2026-06-28 | 2026-06-28 | MATCH | OK
TB 608 - DPR - 2026-06-28.xlsm | TB 608 | DPR Sum. | DPR Sum. |  | filename | TB 608 Status | TRUE | C2:Description->activity_raw; C4:LOA Qty->quantity_loa; C5:Revised Qty->quantity_estimated_or_total; C9:As Per Actual->cumulative_last_month; C10:unnamed_col_10->progress_for_month; C11:unnamed_col_11->cumulative_progress; C12:Balance->balance_progress; C13:Target for the month->plan_for_month; C22:Today's progress->today_progress; C23:Gang->gangs_working |  | 1 | 1 | 41 | 2026-06-28 |  | MISSING_INTERNAL | OK

## DPR Recalc Issues
Workbook | Project | Sheet | ConfiguredSheet | LineName | LineNameSource | Issue | Reason
TA 513 - DPR - 2026-06-28.xlsx | TA 513 | Summary | Summary |  | filename | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters.
TA 515 - DPR - 2026-06-18.xlsx | TA 515 | DPR | DPR |  | filename | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found.

## DPR Recalc Coverage
project_code | project_display | status | reason_code | reason | workbook | configured_sheet | resolved_sheet | rows | filename_date | internal_date | date_quality | available_sheets
TA 310 | TA 310 | OK | OK |  | TA 310 - DPR - 2026-01-12.xlsx | NKTL DPR | NKTL DPR | 13 | 2026-01-12 | 2026-01-12 | MATCH | NKTL DPR PGCIL; Visual Chart NKTL; NKTL DPR; Sheet2; Sheet1; Visual Chart-Old; Location wise status; Survey Status; Soil investigation; Crossing Details; Line Scenario; Sheet3; Supply Status
TA 325 | TA 325 | OK | OK |  | TA 325 - DPR - 2026-01-19.xlsx | 765KV TA 325 ANTL | 765KV TA 325 ANTL | 6 | 2026-01-19 | 2026-01-19 | MATCH | 101-276 FINAL 11-07-2025; 765KV TA 325 ANTL; Project Details; Visual chart Compiled; Soil Invst.; Foundation-Compliled; FDN-VDRA; FDN-NVSR; Erection-Compiled; EREC-VDRA; EREC-NAV; Stringing Compiled; Striging-VDRA; String-Nav; Visual chart NAVSARI Revised; Crossing Vadodara; Crossing Navsari ; Gangs; OPGW; Splicing; Add. Earthing
TA 413 | TA 413 | OK | OK |  | TA 413 - DPR - 2026-06-28.xlsx | TA413_PBNTL | TA413_PBNTL | 12 | 2026-06-28 | 2024-03-12 | MISMATCH | TA413_PBNTL; WIP; Visual Chart; Stringing; Stretch readiness ; Erection; L2 Plan vs Actual; Survey summary; Detailed Survey ; Check Survey ; Earthing; Tack Welding; Final checking; Bird Guard ; Aviation Paint; Accessories; OPGW; Foundation; JUMPER Details; Crossing status; ROW Tracker; S-Curve FDN; S-Curve Erection; S-Curve Stringing; Supply Status; Hardware Supply; Tower Abstract sheet; Statutory Proposals; Tower Abstarct ; Location Summary; Foundation Daily Progress; Tower PRS abstract ; Stretch readiness (2); Area
TA 414 | TA 414 | OK | OK |  | TA 414 - DPR - 2026-06-29.xlsx | VNTL - KEC | VNTL - KEC | 13 | 2026-06-29 |  | MISSING_INTERNAL | Project Details; 765KV TA 414 VNTL; VNTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Sheet6; Sheet4; Sheet7; Stringing Compiled; Visual chart; Pile Fdn; Crossing; Sheet2; Survey; Soil Inv.; Survey Anx
TA 416 | TA 416 | OK | OK |  | TA 416 - DPR - 2026-06-25.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-06-25 | 2026-06-25 | MATCH | Project Details; MASTER SHEET; Erection Compiled ; Stringing compiled; Progress.; Visual chart.; PENDING FDN DETAILS; PENDING ERE DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; TS; TS (2)
TA 418 | TA 418 | OK | OK |  | TA 418 - DPR - 2026-06-17.xlsx | MASTER SHEET | MASTER SHEET | 4 | 2026-06-17 | 2026-06-17 | MATCH | MASTER SHEET; Progress; Erection Completed; Stringing Completed; Visual Chart; ROW TRACKER; PENDING FDN DETAILS; TSE-MANUAL-LT-11KV-33KV Details; Crossing Details; Project Details; TS; TS (2)
TA 419 | TA 419 | OK | OK |  | TA 419 - DPR - 2026-06-26.xlsx | DPR_TA419 | DPR_TA419 | 14 | 2026-06-26 |  | MISSING_INTERNAL | Const Revenue; DPR_TA419; Soil Inv; TOWER SUPPLY; RATE; Tack Welding; Ins Hosting; Stringing; L2; Supply Status; ROW; Tower Schedule; FDN; Latest Tower Schedule; Sheet8; Sheet7; Erection productivity; Foundation Daily Progress; Sheet9; Summary; Sheet10; Visual Chart; Tower schedule_07.03.25; ERT; ERECTION COMPILED; Stringing Compiled; Stringing Stretch Readiness; Project details; Detailed Survey; Supply; Stock Details; PGCIL; dont change; TOWER ABSTRACT; Pkg 2_Foundation; Foundation Daily Progresss; Erection Daily Progress; Statutory; Pkg 2_Erection; Pkg2_Stringing
TA 421 | TA 421 | OK | OK |  | TA 421 - DPR - 2026-06-25.xlsx | Master Sheet | Master Sheet | 10 | 2026-06-25 | 2026-06-25 | MATCH | Project Details; Master Sheet; ProGress Sheet ; Erection Compiled ; Stringing Compiled ; Erection Productivity ; Visual Chart ; Stubs and Towers ; SuPPLY ; X-ing Details ; Tack Welding ; Tower Accessories ; AL Bond ; Birdguard ; Tower Tightening ; Hardwares & Tower Accessories
TA 504 | TA 504 | OK | OK |  | TA 504 - DPR - 2026-06-27.xlsx | DPR_TA-504 | DPR_TA-504 | 6 | 2026-06-27 |  | MISSING_INTERNAL | DPR_TA-504; Erection compiled; Tightening; Stringing Compiled; VC_MAIN; VC_Lilo; Project Details; Location Summary
TA 505 | TA 505 | OK | OK |  | TA 505 - DPR - 2026-06-28.xlsx | DPR-Summary | DPR-Summary | 6 | 2026-06-28 |  | MISSING_INTERNAL | DPR-Summary; Sheet1; Project Details; Sheet5; Foundation; Balance Erc-RAJ; ERC ROW-MP; Erection Compiled; Stringing Compiled; Visual Chart; Erection Productivity; Earthing Status; Sheet4; Sheet3; Sheet2
TA 506 | TA 506 | OK | OK |  | TA 506 - DPR - 2026-06-27.xlsx | DPR_TA-506 | DPR_TA-506 | 6 | 2026-06-27 |  | MISSING_INTERNAL | DPR_TA-506; VC; Erection compiled; Tightening; Stringing; Project Details; Location Summary
TA 509 | TA 509 | OK | OK |  | TA 509 - DPR - 2026-06-28.xlsx | SUMMARY | SUMMARY | 4 | 2026-06-28 | 2026-06-28 | MATCH | Visual Chart; VC-765kV MKTL; DPR; FDN pivot; Erc pivot; SUMMARY; FOUNDATION; ERECTION; Sheet2; XING; EARTHING; SUPPLY; CST Gantry To AP 68 Common Poin; Final Tower Schedule; Sheet1; SURVEY SUMMARY; SURVEY STATUS ; Erection productivity
TA 510 | TA 510 | OK | OK |  | TA 510 - DPR - 2026-06-28.xlsx | AOTL - KEC | AOTL - KEC | 13 | 2026-06-28 |  | MISSING_INTERNAL | 765KV TA 414 VNTL; 765KV ASOTL; Project Details; AOTL - KEC; DPR Sheet; Sheet5; Sheet3; Sheet1; Soil Inv.; Survey Anx; Survey; FDN; Erection ; Visual chart 1 ; Pile Foundation; Sheet6; Sheet4; Sheet7; Stringing Compiled; String; Crossing; Tree Enumeration; Sheet2
TA 512 | TA 512 | OK | OK |  | TA 512 - DPR - 2026-06-28.xlsx | Summary E | Summary E | 13 | 2026-06-28 |  | MISSING_INTERNAL | Summary S; Supply Status; Summary E; DPR Sheet ; DS; CS; Hindrance Record; Earthing; Foundation; Erection Compiled; Tack Welding; Visual Chart; WIP; Statuary clearance; Stringing; OPGW; Accessories; Shield Wire Earthing; TS Gantry - AP47; Project Details; L3 Plan; Supply DPR ; Power line Crossings ; Hardware
TA 513 | TA 513 | HEADER_NOT_FOUND | HEADER_NOT_FOUND | No matching rows after guardrails/activity filters. | TA 513 - DPR - 2026-06-28.xlsx | Summary | Summary | 0 | 2026-06-28 |  | MISSING_INTERNAL | Summary; LS Physical; T.Marking; ERT; VC SF ; VC SP; LS; Survey ; FDN S-P; FDN S-F; Total Supply; Ere S-F ; Ere S-P ; T.Abstract; Earthing S-P; Crossing status ; Earthing S-F; Proposal .; ROW S-F; ROW S-P; TS SP ; TS SF; Sheet1; Forest
TA 515 | TA 515 | TEMPLATE_CONFIG_ERROR | TEMPLATE_CONFIG_ERROR | Status Template Check is Yes but no mapping tab matching project 'TA 515' was found. | TA 515 - DPR - 2026-06-18.xlsx | DPR | DPR | 0 | 2026-06-18 |  | UNREADABLE | DPR; Foundation Compiled; Earthing; Erection Compiled; Store Stock; Visual chart
TA 601 | TA 601 | OK | OK |  | TA 601 - DPR - 2026-06-27.xlsx | Master Sheet | Master Sheet | 11 | 2026-06-27 | 2026-06-27 | MATCH | Visual Chart ; Master Sheet; Progress Sheet ; SUPPLY; Erection Compiled; X-ing Details ; Visual Chart; Foundation & Erection; STRG Stretch ; Stringing Compiled
TA 602 | TA 602 | OK | OK |  | TA 602 - DPR - 2026-06-26.xlsx | 800kV HVDC TA-602 | 800kV HVDC TA-602 | 6 | 2026-06-26 | 2026-06-27 | MISMATCH | Completion Plan; Project Details; PGCIL - KEC; PPT-Erection Part; CMD-1; CMD-2; PPT _Statutory; PPT Supply; Supply Status; 800kV HVDC TA-602; DPR Sheet; Survey details 11-06-2026; FDN; FDN Completed; Erection ; Erection Completed ; Erection Compiled; Stringing; Stringing Completed; Stringing Compiled; TA-602Visual Chart ; Visual chart; Pile Fdn; Crossing; Survey; Soil Inv.; Survey Anx
TB 401 | TB 401 | OK | OK |  | TB 401 - DPR - 2025-12-25.xlsx | Progress | Progress | 6 | 2025-12-25 | 2025-12-26 | MISMATCH | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); TB401 DPR; Foundation (Pkg-F) ; Earthing (PKG-F); Project Details; Progress; Hindrance; Foundation (Pkg-G); Earthing (PKG-G); Benching Status-F; Revetment Pkg-G; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-F; Tack Welding - PKG-G; Painting - PKG-F; Painting - PKG-G; Idling details from Aug; Erection Compiled; Crane Erection PKG-G; Erection Productivity; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing Productivity; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Visual Chart (Pkg -F.); Clear locs shared by client; Visual Chart PKG-G; Sheet3; Sheet2
TB 408 | TB 408 | OK | OK |  | TB 408 - DPR - 2026-06-01.xlsx | Progress Summary | Progress Summary | 7 | 2026-06-01 | 2026-06-01 | MATCH | Progress Summary; Project Details; X-ing Status; L2 Schedule vs Actual; Hindrance Register (Row); Page Chart; Survey; Foundation; Earthing; Erection Productivity; Crane Erection Productivity; Erection Compiled; Tackwelding; Stringing; Stringing associated works; Stringing Productivity; OPGW; Accessories details; Visual chart; Visual chart Edit; Benching F
TB 412 | TB 412 | OK | OK |  | TB 412 - DPR - 2026-06-24.xlsx | TB-412 SUMMARY | TB-412 SUMMARY | 13 | 2026-06-24 | 2026-06-24 | MATCH | TB-412 SUMMARY; Summary-; Survey Status; Sheet3; DPR Sheet ; WIP; GANG Mapping MAY-26 ; Soil Investigation; Sheet1; Progress 400kV QM; VC 400 KV QM; Progress 220KV TM; VC 220 TM; VC 220 SZ; ROW; 220 SZ Status; CS-220kV TM ; DS-220 KV TM; DS 400kV LI; DS 400 kV LO; Survey Report; FDN; Earthing Pending; Erection; Earthing; Earthing Balance; Statutary ; Power line Crossings
TB 501 | TB 501 | OK | OK |  | TB 501 - DPR - 2026-06-27.xlsx | Summary | Summary | 20 | 2026-06-27 | 2026-06-27 | MATCH | Detail Survey-220kV; Check Survey-220kV; Detail Survey-132kV; Check Survey-132kV; Summary; Statutory; Progress-132kV; Progress-220kV; Stringing-220kV; Stringing-132KV; VC-220kV; VC-132kV; Supply; Mail Body
TB 507 | TB 507 - MAIN | OK | OK |  | TB 507 [MAIN] - DPR - 2026-06-28.xlsx | 400kV Summery | 400kV Summery | 14 | 2026-06-28 |  | MISSING_INTERNAL | 400kV Summery; Check Survey ; Check Survey Status; Check Survey; Sheet8; Sheet2; Project Details; Statutory Clearence; Crossing Proposal; Sheet1; VC 51-96; VC; ROW; June; Foundation; Royalty; Sheet14; Sheet7; Erection ; Completion date; Sheet12; Erection Compiled ; Earthing; Final Check In And Tack Welding; Sheet10; Sheet11; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart 1; Visual Chart; L2 Vs Actual Progress Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 507 | TB 507 - 765kV | OK | OK |  | TB 507 - DPR - 2026-06-28.xlsx | 765kV Summery | 765kV Summery | 12 | 2026-06-28 |  | MISSING_INTERNAL | 765kV Summery; Check Survey Status; Check Survey; Sheet8; Sheet2; Sheet1; VC 51-96; VC; ROW; June; Check survey Loop out; Check survey Loop In; Foundation; Royalty; Sheet14; Sheet7; Project Details; Erection ; Completion date; Erection Compiled ; Earthing; Final Checking and Tack Welding; Stringing Compiled ; Soil Investigation; Sheet9; VC ; Sheet6; VC 51-121; Sheet5; Sheet3; Tower Schedule; Visual Chart; L2 Vs Actual Progress Chart (2); Sheet4
TB 605 | TB 605 | OK | OK |  | TB 605 - DPR - 2026-06-28.xlsx | TB-605 | TB-605 | 7 | 2026-06-28 | 2026-06-28 | MATCH | TB401 DPR.....; Eng.; Fdn (Pkg -G Section -I); Sheet2; Sheet3; Sheet4; Sheet5; ROW; Sheet13 (2); TB-605; Sheet19; Sheet16; Sheet14; Sheet12; Sheet13; Sheet15; TB401 DPR; Survey-Summary; Sheet6; Approved Survey; Approved CS J-S Line; Approved CS K-S Line; Foundation JS-Line -Jammu; Sheet10; Erection -Jammu; Vertical Chart -JS Line Jammu ; Sheet17; Stringing JS-Jammu; Erection -SK; Sheet7; Sheet8; LILO; Erection-Punjab; Vertical Chart -JS Line Punjab; Foundation -JS Line- Punjab; Sheet9; ROW Front vs Progress; Pile FDN; Hindrance; Foundation -KS Line; Manpower; Final Checking; Stubs JS; Stubs SK; Towers JS; Towers SK; Sum; Sheet18; JS-Supply Stubs; JS Supply Towers; SK Supply Stubs; SK Supply Towers; Sheet11; Planned Vs Actual -FDN; Supply Status; Material Status-Jammu-Punjab; Material Status-Punjab; Earthing (PKG-F); Earthing (PKG-G); Revetment Pkg-G; Benching Status-F; Benching Status-G; Earthing Pkg -G Ist section; Earthing balance; Tack Welding - PKG-G; Tack Welding - PKG-F; Painting - PKG-G; Painting - PKG-F; Eretion - PKG-G; Eretion - PKG-F; Sheet1; JMC 27.9.23; Jumpering-G; Insulator Hoisting - F; Insulator Hoisting - G; Jumpering-F; Stringing - PKG-F; Stringing - PKG-G; OPGW PKG-G; OPGW PKG-F; Crossing; Clear locs shared by client
TB 608 | TB 608 | OK | OK |  | TB 608 - DPR - 2026-06-28.xlsm | DPR Sum. | DPR Sum. | 41 | 2026-06-28 |  | MISSING_INTERNAL | Master Sheet; DPR Sum.; Master Sheet ; Gang Movement; Support Required; WIP-FDN; WIP-ERC; Line Details; Visual_Chart; Foundation Activity; Supply; Sheet2