## Simple Project Summary
project_code | Foundation status | Foundation note | Erection status | Erection note | Stringing status | Stringing note | overall
TA 413 | OK | OK | Mismatch | balance dash 3 vs DPR 4; June actual dash 0 vs DPR 1 | Mismatch | balance dash 39.55 vs DPR 40.66; June actual dash 11.27 vs DPR 10.05 | Review: Erection, Stringing
TA 414 | Mismatch | balance dash 35 vs DPR 33; June actual dash 15 vs DPR 17 | Mismatch | balance dash 116 vs DPR 117; June actual dash 25 vs DPR 30 | Mismatch | balance dash 111.61 vs DPR 111.86; June actual dash 6.99 vs DPR 9.10 | Review: Foundation, Erection, Stringing
TA 416 | OK | OK | OK | OK | Mismatch | balance dash 4.67 vs DPR 4; June actual dash 4 vs DPR 3.32 | Review: Stringing
TA 418 | OK | OK | OK | OK | Mismatch | balance dash 20.50 vs DPR 18.26; June actual dash 3.21 vs DPR 1.64 | Review: Stringing
TA 419 | Mismatch | balance dash 110 vs DPR 76; June actual dash 19 vs DPR 15 | Mismatch | balance dash 154 vs DPR 124; June actual dash 34 vs DPR 11 | Mismatch | balance dash 122.14 vs DPR 121.62; June actual dash 0 vs DPR 2.10 | Review: Foundation, Erection, Stringing
TA 421 | OK | OK | OK | OK | Mismatch | balance dash 6.08 vs DPR 5.87; June actual dash 5.02 vs DPR 4.40 | Review: Stringing
TA 504 | Mismatch | balance dash 55 vs DPR 42; June actual dash 1 vs DPR 2 | Mismatch | balance dash 86 vs DPR 65 | Mismatch | balance dash 65.66 vs DPR 55.58 | Review: Foundation, Erection, Stringing
TA 505 | Mismatch | balance dash 7 vs DPR 4; June actual dash 0 vs DPR 3 | Mismatch | balance dash 27 vs DPR 22; June actual dash 0 vs DPR 6 | Mismatch | balance dash 124.62 vs DPR 124.14; June actual dash 0 vs DPR 9.75 | Review: Foundation, Erection, Stringing
TA 506 | Mismatch | balance dash 118 vs DPR 110; June actual dash 10 vs DPR 7 | Mismatch | balance dash 208 vs DPR 197; June actual dash 18 vs DPR 15 | Mismatch | balance dash 169.06 vs DPR 167.37; June actual dash 8.59 vs DPR 7.48 | Review: Foundation, Erection, Stringing
TA 509 | Mismatch | balance dash 124 vs DPR 41; June actual dash 0 vs DPR 6 | Mismatch | balance dash 301 vs DPR 101; June actual dash 0 vs DPR 11 | Mismatch | balance dash 118.41 vs DPR 119.18; June actual dash 0 vs DPR 3.46 | Review: Foundation, Erection, Stringing
TA 510 | Mismatch | balance dash 142 vs DPR 208; June actual dash 9 vs DPR 10 | Mismatch | balance dash 191 vs DPR 253; June actual dash 1 vs DPR 5 | No DPR summary | balance dash 84.48 vs DPR 114.52 | Review: Foundation, Erection, Stringing
TA 512 | OK | OK | OK | OK | Mismatch | balance dash 124.32 vs DPR 124.57 | Review: Stringing
TA 513 | Mismatch | balance dash 563 vs DPR 530; June actual dash 0 vs DPR 9 | Mismatch | balance dash 610 vs DPR 588; June actual dash 0 vs DPR 4 | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 514 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 515 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 601 | Mismatch | June actual dash 7 vs DPR 21 | Mismatch | June actual dash 2 vs DPR 16 | Mismatch | balance dash 113.29 vs DPR 226.57 | Review: Foundation, Erection, Stringing
TA 602 | Mismatch | balance dash 231 vs DPR 326; June actual dash 1 vs DPR 11 | Mismatch | balance dash 221 vs DPR 428; June actual dash 0 vs DPR 25 | Mismatch | balance dash 88.49 vs DPR 184.99 | Review: Foundation, Erection, Stringing
TA 609 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TB 408 | No DPR summary | OK | No DPR summary | OK | No DPR summary | balance dash 65.57 vs DPR 65.46 | Review: Foundation, Erection, Stringing
TB 501 | Mismatch | balance dash 25 vs DPR 3; June actual dash 25 vs DPR 2 | Mismatch | balance dash 30 vs DPR 8; June actual dash 30 vs DPR 3 | Mismatch | balance dash 42.53 vs DPR 5.84; June actual dash 39.58 vs DPR 3.31 | Review: Foundation, Erection, Stringing
TB 507 | Mismatch | balance dash 362 vs DPR 214; June actual dash 0 vs DPR 18 | Mismatch | balance dash 488 vs DPR 335; June actual dash 0 vs DPR 15 | No DPR summary | balance dash 73.80 vs DPR 371.47 | Review: Foundation, Erection, Stringing
TB 605 | Mismatch | balance dash 337 vs DPR 153; June actual dash 0 vs DPR 43 | Mismatch | balance dash 394 vs DPR 320; June actual dash 0 vs DPR 42 | Mismatch | balance dash 138.63 vs DPR 351.44; June actual dash 0 vs DPR 2.94 | Review: Foundation, Erection, Stringing
TB 608 | Mismatch | balance dash 133 vs DPR 314 | Mismatch | balance dash 237 vs DPR 318; June actual dash 12 vs DPR 10 | Mismatch | balance dash 86.11 vs DPR 103.97 | Review: Foundation, Erection, Stringing
TB 611 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing

## Projects Needing Review
project_code | Foundation status | Foundation note | Erection status | Erection note | Stringing status | Stringing note | overall
TA 413 | OK | OK | Mismatch | balance dash 3 vs DPR 4; June actual dash 0 vs DPR 1 | Mismatch | balance dash 39.55 vs DPR 40.66; June actual dash 11.27 vs DPR 10.05 | Review: Erection, Stringing
TA 414 | Mismatch | balance dash 35 vs DPR 33; June actual dash 15 vs DPR 17 | Mismatch | balance dash 116 vs DPR 117; June actual dash 25 vs DPR 30 | Mismatch | balance dash 111.61 vs DPR 111.86; June actual dash 6.99 vs DPR 9.10 | Review: Foundation, Erection, Stringing
TA 416 | OK | OK | OK | OK | Mismatch | balance dash 4.67 vs DPR 4; June actual dash 4 vs DPR 3.32 | Review: Stringing
TA 418 | OK | OK | OK | OK | Mismatch | balance dash 20.50 vs DPR 18.26; June actual dash 3.21 vs DPR 1.64 | Review: Stringing
TA 419 | Mismatch | balance dash 110 vs DPR 76; June actual dash 19 vs DPR 15 | Mismatch | balance dash 154 vs DPR 124; June actual dash 34 vs DPR 11 | Mismatch | balance dash 122.14 vs DPR 121.62; June actual dash 0 vs DPR 2.10 | Review: Foundation, Erection, Stringing
TA 421 | OK | OK | OK | OK | Mismatch | balance dash 6.08 vs DPR 5.87; June actual dash 5.02 vs DPR 4.40 | Review: Stringing
TA 504 | Mismatch | balance dash 55 vs DPR 42; June actual dash 1 vs DPR 2 | Mismatch | balance dash 86 vs DPR 65 | Mismatch | balance dash 65.66 vs DPR 55.58 | Review: Foundation, Erection, Stringing
TA 505 | Mismatch | balance dash 7 vs DPR 4; June actual dash 0 vs DPR 3 | Mismatch | balance dash 27 vs DPR 22; June actual dash 0 vs DPR 6 | Mismatch | balance dash 124.62 vs DPR 124.14; June actual dash 0 vs DPR 9.75 | Review: Foundation, Erection, Stringing
TA 506 | Mismatch | balance dash 118 vs DPR 110; June actual dash 10 vs DPR 7 | Mismatch | balance dash 208 vs DPR 197; June actual dash 18 vs DPR 15 | Mismatch | balance dash 169.06 vs DPR 167.37; June actual dash 8.59 vs DPR 7.48 | Review: Foundation, Erection, Stringing
TA 509 | Mismatch | balance dash 124 vs DPR 41; June actual dash 0 vs DPR 6 | Mismatch | balance dash 301 vs DPR 101; June actual dash 0 vs DPR 11 | Mismatch | balance dash 118.41 vs DPR 119.18; June actual dash 0 vs DPR 3.46 | Review: Foundation, Erection, Stringing
TA 510 | Mismatch | balance dash 142 vs DPR 208; June actual dash 9 vs DPR 10 | Mismatch | balance dash 191 vs DPR 253; June actual dash 1 vs DPR 5 | No DPR summary | balance dash 84.48 vs DPR 114.52 | Review: Foundation, Erection, Stringing
TA 512 | OK | OK | OK | OK | Mismatch | balance dash 124.32 vs DPR 124.57 | Review: Stringing
TA 513 | Mismatch | balance dash 563 vs DPR 530; June actual dash 0 vs DPR 9 | Mismatch | balance dash 610 vs DPR 588; June actual dash 0 vs DPR 4 | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 514 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 515 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TA 601 | Mismatch | June actual dash 7 vs DPR 21 | Mismatch | June actual dash 2 vs DPR 16 | Mismatch | balance dash 113.29 vs DPR 226.57 | Review: Foundation, Erection, Stringing
TA 602 | Mismatch | balance dash 231 vs DPR 326; June actual dash 1 vs DPR 11 | Mismatch | balance dash 221 vs DPR 428; June actual dash 0 vs DPR 25 | Mismatch | balance dash 88.49 vs DPR 184.99 | Review: Foundation, Erection, Stringing
TA 609 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing
TB 408 | No DPR summary | OK | No DPR summary | OK | No DPR summary | balance dash 65.57 vs DPR 65.46 | Review: Foundation, Erection, Stringing
TB 501 | Mismatch | balance dash 25 vs DPR 3; June actual dash 25 vs DPR 2 | Mismatch | balance dash 30 vs DPR 8; June actual dash 30 vs DPR 3 | Mismatch | balance dash 42.53 vs DPR 5.84; June actual dash 39.58 vs DPR 3.31 | Review: Foundation, Erection, Stringing
TB 507 | Mismatch | balance dash 362 vs DPR 214; June actual dash 0 vs DPR 18 | Mismatch | balance dash 488 vs DPR 335; June actual dash 0 vs DPR 15 | No DPR summary | balance dash 73.80 vs DPR 371.47 | Review: Foundation, Erection, Stringing
TB 605 | Mismatch | balance dash 337 vs DPR 153; June actual dash 0 vs DPR 43 | Mismatch | balance dash 394 vs DPR 320; June actual dash 0 vs DPR 42 | Mismatch | balance dash 138.63 vs DPR 351.44; June actual dash 0 vs DPR 2.94 | Review: Foundation, Erection, Stringing
TB 608 | Mismatch | balance dash 133 vs DPR 314 | Mismatch | balance dash 237 vs DPR 318; June actual dash 12 vs DPR 10 | Mismatch | balance dash 86.11 vs DPR 103.97 | Review: Foundation, Erection, Stringing
TB 611 | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | No DPR summary | No DPR project-level summary found | Review: Foundation, Erection, Stringing

## Activity Comparison
project_key | project_code | fes_activity | dashboard_scope | dashboard_completed_may | dashboard_balance_may | dashboard_june_plan | dashboard_june_actual | dashboard_rows | dashboard_activities | dpr_project | dpr_scope | dpr_completed_may | dpr_balance_may | dpr_june_plan | dpr_june_actual | dpr_completed_current | dpr_report_date | diff_scope | diff_completed_may | diff_balance_may | diff_june_plan | diff_june_actual | balance_status | june_actual_status | simple_status | notes
TA413 | TA 413 | Erection | 306 | 303 | 3 | 0 | 0 | 1 | Tower Erection | TA 413 | 306 | 302 | 4 | 4 | 1 | 303 | 2026-06-28 | 0 | 1 | -1 | -4 | -1 | Mismatch | Mismatch | Mismatch | balance dash 3 vs DPR 4; June actual dash 0 vs DPR 1
TA413 | TA 413 | Foundation | 306 | 306 | 0 | 0 | 0 | 1 | Open Foundation - RCC | TA 413 | 316 | 316 | 0 | 0 | 0 | 316 | 2026-06-28 | -10 | -10 | 0 | 0 | 0 | OK | OK | OK | OK
TA413 | TA 413 | Stringing | 117.85 | 78.3 | 39.55 | 0 | 11.27 | 1 | Conductor Stringing - S&C | TA 413 | 117.8509 | 77.189 | 40.6619 | 21.51 | 10.051 | 87.24 | 2026-06-28 | -0.000851 | 1.111 | -1.1119 | -21.51 | 1.219 | Mismatch | Mismatch | Mismatch | balance dash 39.55 vs DPR 40.66; June actual dash 11.27 vs DPR 10.05
TA414 | TA 414 | Erection | 351 | 235 | 116 | 0 | 25 | 1 | Tower Erection | TA 414 | 352 | 235 | 117 | 44 | 30 | 265 | 2026-06-29 | -1 | 0 | -1 | -44 | -5 | Mismatch | Mismatch | Mismatch | balance dash 116 vs DPR 117; June actual dash 25 vs DPR 30
TA414 | TA 414 | Foundation | 351 | 316 | 35 | 0 | 15 | 1 | Open Foundation - RCC | TA 414 | 352 | 319 | 33 | 31 | 17 | 336 | 2026-06-29 | -1 | -3 | 2 | -31 | -2 | Mismatch | Mismatch | Mismatch | balance dash 35 vs DPR 33; June actual dash 15 vs DPR 17
TA414 | TA 414 | Stringing | 127.85 | 16.24 | 111.61 | 0 | 6.99 | 1 | Conductor Stringing - S&C | TA 414 | 127.799 | 15.944 | 111.855 | 20 | 9.1022 | 25.0462 | 2026-06-29 | 0.051 | 0.296 | -0.245 | -20 | -2.1122 | Mismatch | Mismatch | Mismatch | balance dash 111.61 vs DPR 111.86; June actual dash 6.99 vs DPR 9.10
TA416 | TA 416 | Erection | 302 | 302 | 0 | 0 | 0 | 1 | Tower Erection | TA 416 | 302 | 302 | 0 | 0 | 0 | 302 | 2026-06-25 | 0 | 0 | 0 | 0 | 0 | OK | OK | OK | OK
TA416 | TA 416 | Foundation | 302 | 302 | 0 | 0 | 0 | 1 | Open Foundation - RCC | TA 416 | 302 | 302 | 0 | 0 | 0 | 302 | 2026-06-25 | 0 | 0 | 0 | 0 | 0 | OK | OK | OK | OK
TA416 | TA 416 | Stringing | 115.13 | 110.46 | 4.67 | 0 | 4 | 1 | Conductor Stringing - S&C | TA 416 | 115.134 | 111.139 | 3.995 | 4 | 3.319 | 114.458 | 2026-06-25 | -0.004 | -0.679 | 0.675 | -4 | 0.681 | Mismatch | Mismatch | Mismatch | balance dash 4.67 vs DPR 4; June actual dash 4 vs DPR 3.32
TA418 | TA 418 | Erection | 127 | 127 | 0 | 0 | 0 | 1 | Tower Erection | TA 418 | 127 | 127 | 0 | 0 | 0 | 127 | 2026-06-17 | 0 | 0 | 0 | 0 | 0 | OK | OK | OK | OK
TA418 | TA 418 | Foundation | 127 | 127 | 0 | 0 | 0 | 1 | Open Foundation - RCC | TA 418 | 127 | 127 | 0 | 0 | 0 | 127 | 2026-06-17 | 0 | 0 | 0 | 0 | 0 | OK | OK | OK | OK
TA418 | TA 418 | Stringing | 47.84 | 27.34 | 20.5 | 0 | 3.21 | 1 | Conductor Stringing - S&C | TA 418 | 47.84 | 29.582 | 18.258 | 18.258 | 1.6442 | 31.2262 | 2026-06-17 | 0 | -2.242 | 2.242 | -18.258 | 1.5658 | Mismatch | Mismatch | Mismatch | balance dash 20.50 vs DPR 18.26; June actual dash 3.21 vs DPR 1.64
TA419 | TA 419 | Erection | 333 | 179 | 154 | 0 | 34 | 1 | Tower Erection | TA 419 | 331 | 207 | 124 | 50 | 11 | 218 | 2026-06-26 | 2 | -28 | 30 | -50 | 23 | Mismatch | Mismatch | Mismatch | balance dash 154 vs DPR 124; June actual dash 34 vs DPR 11
TA419 | TA 419 | Foundation | 333 | 223 | 110 | 0 | 19 | 1 | Open Foundation - RCC | TA 419 | 331 | 255 | 76 | 49 | 15 | 270 | 2026-06-26 | 2 | -32 | 34 | -49 | 4 | Mismatch | Mismatch | Mismatch | balance dash 110 vs DPR 76; June actual dash 19 vs DPR 15
TA419 | TA 419 | Stringing | 122.14 | 0 | 122.14 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 419 | 122.071 | 0.447 | 121.624 |  | 2.099 | 2.546 | 2026-06-26 | 0.069 | -0.447 | 0.516 |  | -2.099 | Mismatch | Mismatch | Mismatch | balance dash 122.14 vs DPR 121.62; June actual dash 0 vs DPR 2.10
TA421 | TA 421 | Erection | 310 | 310 | 0 | 0 | 0 | 1 | Tower Erection | TA 421 | 309 | 309 | 0 |  | 0 | 309 | 2026-06-29 | 1 | 1 | 0 |  | 0 | OK | OK | OK | OK
TA421 | TA 421 | Foundation | 310 | 310 | 0 | 0 | 0 | 1 | Open Foundation - RCC | TA 421 | 309 | 309 | 0 |  | 0 | 309 | 2026-06-29 | 1 | 1 | 0 |  | 0 | OK | OK | OK | OK
TA421 | TA 421 | Stringing | 121.34 | 115.26 | 6.08 | 5.9 | 5.02 | 1 | Conductor Stringing - S&C | TA 421 | 121.342 | 115.467 | 5.875 | 5.878 | 4.4027 | 119.8697 | 2026-06-29 | -0.002 | -0.207 | 0.205 | 0.022 | 0.61731 | Mismatch | Mismatch | Mismatch | balance dash 6.08 vs DPR 5.87; June actual dash 5.02 vs DPR 4.40
TA504 | TA 504 | Erection | 207 | 121 | 86 | 6 | 3 | 1 | Tower Erection | TA 504 | 186 | 121 | 65 | 6 | 3 | 124 | 2026-06-27 | 21 | 0 | 21 | 0 | 0 | Mismatch | OK | Mismatch | balance dash 86 vs DPR 65
TA504 | TA 504 | Foundation | 207 | 152 | 55 | 6 | 1 | 1 | Open Foundation - RCC | TA 504 | 186 | 144 | 42 | 6 | 2 | 146 | 2026-06-27 | 21 | 8 | 13 | 0 | -1 | Mismatch | Mismatch | Mismatch | balance dash 55 vs DPR 42; June actual dash 1 vs DPR 2
TA504 | TA 504 | Stringing | 79.08 | 13.42 | 65.66 | 8 | 7.14 | 1 | Conductor Stringing - S&C | TA 504 | 69 | 13.422 | 55.578 | 8 | 7.14 | 20.562 | 2026-06-27 | 10.08 | -0.002 | 10.082 | 0 | 0 | Mismatch | OK | Mismatch | balance dash 65.66 vs DPR 55.58
TA505 | TA 505 | Erection | 380 | 353 | 27 | 0 | 0 | 1 | Tower Erection | TA 505 | 379 | 357 | 22 | 7 | 6 | 363 | 2026-06-28 | 1 | -4 | 5 | -7 | -6 | Mismatch | Mismatch | Mismatch | balance dash 27 vs DPR 22; June actual dash 0 vs DPR 6
TA505 | TA 505 | Foundation | 380 | 373 | 7 | 0 | 0 | 1 | Piling Foundation - Concreting | TA 505 | 379 | 375 | 4 | 4 | 3 | 378 | 2026-06-28 | 1 | -2 | 3 | -4 | -3 | Mismatch | Mismatch | Mismatch | balance dash 7 vs DPR 4; June actual dash 0 vs DPR 3
TA505 | TA 505 | Stringing | 139.63 | 15.01 | 124.62 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 505 | 139.6 | 15.462 | 124.138 | 23.008 | 9.751 | 25.213 | 2026-06-28 | 0.03 | -0.452 | 0.482 | -23.008 | -9.751 | Mismatch | Mismatch | Mismatch | balance dash 124.62 vs DPR 124.14; June actual dash 0 vs DPR 9.75
TA506 | TA 506 | Erection | 605 | 397 | 208 | 25 | 18 | 1 | Tower Erection | TA 506 | 602 | 405 | 197 | 25 | 15 | 420 | 2026-06-27 | 3 | -8 | 11 | 0 | 3 | Mismatch | Mismatch | Mismatch | balance dash 208 vs DPR 197; June actual dash 18 vs DPR 15
TA506 | TA 506 | Foundation | 605 | 487 | 118 | 25 | 10 | 1 | Open Foundation - RCC | TA 506 | 602 | 492 | 110 | 40 | 7 | 499 | 2026-06-27 | 3 | -5 | 8 | -15 | 3 | Mismatch | Mismatch | Mismatch | balance dash 118 vs DPR 110; June actual dash 10 vs DPR 7
TA506 | TA 506 | Stringing | 222.83 | 53.77 | 169.06 | 30 | 8.59 | 1 | Conductor Stringing - S&C | TA 506 | 223 | 55.632 | 167.368 | 30 | 7.478 | 63.11 | 2026-06-27 | -0.17 | -1.862 | 1.692 | 0 | 1.112 | Mismatch | Mismatch | Mismatch | balance dash 169.06 vs DPR 167.37; June actual dash 8.59 vs DPR 7.48
TA509 | TA 509 | Erection | 309 | 8 | 301 | 20 | 0 | 1 | Tower Erection | TA 509 | 309 | 208 | 101 | 30 | 11 | 219 | 2026-06-28 | 0 | -200 | 200 | -10 | -11 | Mismatch | Mismatch | Mismatch | balance dash 301 vs DPR 101; June actual dash 0 vs DPR 11
TA509 | TA 509 | Foundation | 309 | 185 | 124 | 13 | 0 | 1 | Open Foundation - RCC | TA 509 | 309 | 268 | 41 | 13 | 6 | 274 | 2026-06-28 | 0 | -83 | 83 | 0 | -6 | Mismatch | Mismatch | Mismatch | balance dash 124 vs DPR 41; June actual dash 0 vs DPR 6
TA509 | TA 509 | Stringing | 118.41 | 0 | 118.41 | 10.774 | 0 | 1 | Conductor Stringing - S&C | TA 509 | 119.178 | 0 | 119.178 | 12 | 3.461 | 3.461 | 2026-06-28 | -0.768 | 0 | -0.768 | -1.226 | -3.461 | Mismatch | Mismatch | Mismatch | balance dash 118.41 vs DPR 119.18; June actual dash 0 vs DPR 3.46
TA510 | TA 510 | Erection | 224 | 33 | 191 | 30 | 1 | 1 | Tower Erection | TA 510 | 293 | 40 | 253 | 30 | 5 | 45 | 2026-06-29 | -69 | -7 | -62 | 0 | -4 | Mismatch | Mismatch | Mismatch | balance dash 191 vs DPR 253; June actual dash 1 vs DPR 5
TA510 | TA 510 | Foundation | 224 | 82 | 142 | 47 | 9 | 1 | Piling Foundation - Concreting | TA 510 | 293 | 85 | 208 | 16 | 10 | 95 | 2026-06-29 | -69 | -3 | -66 | 31 | -1 | Mismatch | Mismatch | Mismatch | balance dash 142 vs DPR 208; June actual dash 9 vs DPR 10
TA510 | TA 510 | Stringing | 84.48 | 0 | 84.48 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 510 | 114.516 | 0 | 114.516 | 11 |  | 0 | 2026-06-29 | -30.036 | 0 | -30.036 | -11 |  | Mismatch | No DPR summary | No DPR summary | balance dash 84.48 vs DPR 114.52
TA512 | TA 512 | Erection | 319 | 221 | 98 | 0 | 14 | 1 | Tower Erection | TA 512 | 319 | 221 | 98 | 30 | 14 | 235 | 2026-06-28 | 0 | 0 | 0 | -30 | 0 | OK | OK | OK | OK
TA512 | TA 512 | Foundation | 319 | 306 | 13 | 0 | 6 | 1 | Open Foundation - RCC | TA 512 | 319 | 306 | 13 | 18 | 6 | 312 | 2026-06-28 | 0 | 0 | 0 | -18 | 0 | OK | OK | OK | OK
TA512 | TA 512 | Stringing | 124.32 | 0 | 124.32 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 512 | 124.568 | 0 | 124.568 |  | 0 | 0 | 2026-06-28 | -0.248 | 0 | -0.248 |  | 0 | Mismatch | OK | Mismatch | balance dash 124.32 vs DPR 124.57
TA513 | TA 513 | Erection | 621 | 11 | 610 | 10 | 0 | 1 | Tower Erection | TA 513 | 619 | 31 | 588 | 16 | 4 | 35 | 2026-06-22 | 2 | -20 | 22 | -6 | -4 | Mismatch | Mismatch | Mismatch | balance dash 610 vs DPR 588; June actual dash 0 vs DPR 4
TA513 | TA 513 | Foundation | 621 | 58 | 563 | 20 | 0 | 1 | Piling Foundation - Concreting | TA 513 | 619 | 89 | 530 | 35 | 9 | 98 | 2026-06-22 | 2 | -31 | 33 | -15 | -9 | Mismatch | Mismatch | Mismatch | balance dash 563 vs DPR 530; June actual dash 0 vs DPR 9
TA513 | TA 513 | Stringing | 230.55 | 0 | 230.55 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 513 | 230.387 | [5 empty] | 2026-06-22 | 0.163 |  |  |  |  | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA514 | TA 514 | Erection | 377 | 0 | 377 | 0 | 0 | 1 | Tower Erection | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA514 | TA 514 | Foundation | 377 | 24 | 353 | 0 | 2 | 2 | Open Foundation - RCC; Piling Foundation - Concreting | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA514 | TA 514 | Stringing | 142.07 | 0 | 142.07 | 0 | 0 | 1 | Conductor Stringing - S&C | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA515 | TA 515 | Erection | 218 | 0 | 218 | 0 | 0 | 1 | Tower Erection | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA515 | TA 515 | Foundation | 218 | 14 | 204 | 0 | 5 | 1 | Open Foundation - RCC | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA515 | TA 515 | Stringing | 83.33 | 0 | 83.33 | 0 | 0 | 1 | Conductor Stringing - S&C | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA601 | TA 601 | Erection | 292 | 71 | 221 | 25 | 2 | 1 | Tower Erection | TA 601 | 292 | 71 | 221 | 25 | 16 | 87 | 2026-06-29 | 0 | 0 | 0 | 0 | -14 | OK | Mismatch | Mismatch | June actual dash 2 vs DPR 16
TA601 | TA 601 | Foundation | 292 | 124 | 168 | 35 | 7 | 1 | Open Foundation - RCC | TA 601 | 292 | 124 | 168 | 35 | 21 | 145 | 2026-06-29 | 0 | 0 | 0 | 0 | -14 | OK | Mismatch | Mismatch | June actual dash 7 vs DPR 21
TA601 | TA 601 | Stringing | 113.29 | 0 | 113.29 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 601 | 226.572 | 0 | 226.572 | 0 | 0 | 0 | 2026-06-29 | -113.282 | 0 | -113.282 | 0 | 0 | Mismatch | OK | Mismatch | balance dash 113.29 vs DPR 226.57
TA602 | TA 602 | Erection | 231 | 10 | 221 | 0 | 0 | 1 | Tower Erection | TA 602 | 480 | 52 | 428 | 35 | 25 | 77 | 2026-06-26 | -249 | -42 | -207 | -35 | -25 | Mismatch | Mismatch | Mismatch | balance dash 221 vs DPR 428; June actual dash 0 vs DPR 25
TA602 | TA 602 | Foundation | 231 | 0 | 231 | 0 | 1 | 1 | Open Foundation - RCC | TA 602 | 480 | 154 | 326 | 30 | 11 | 165 | 2026-06-26 | -249 | -154 | -95 | -30 | -10 | Mismatch | Mismatch | Mismatch | balance dash 231 vs DPR 326; June actual dash 1 vs DPR 11
TA602 | TA 602 | Stringing | 88.49 | 0 | 88.49 | 0 | 0 | 1 | Conductor Stringing - S&C | TA 602 | 184.986 | 0 | 184.986 | 0 | 0 | 0 | 2026-06-26 | -96.496 | 0 | -96.496 | 0 | 0 | Mismatch | OK | Mismatch | balance dash 88.49 vs DPR 184.99
TA609 | TA 609 | Erection | 197 | 1 | 196 | 0 | 0 | 1 | Tower Erection | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA609 | TA 609 | Foundation | 197 | 22 | 175 | 0 | 0 | 2 | Open Foundation - RCC; Piling Foundation - Concreting | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TA609 | TA 609 | Stringing | 73.92 | 0 | 73.92 | 0 | 0 | 1 | Conductor Stringing - S&C | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TB408 | TB 408 | Erection | 485 | 484 | 1 | 0 | 0 | 1 | Tower Erection | TB 408 | 485 | 484 | 1 | 1 |  | 484 | 2026-06-01 | 0 | 0 | 0 | -1 |  | OK | No DPR summary | No DPR summary | OK
TB408 | TB 408 | Foundation | 485 | 485 | 0 | 0 | 0 | 1 | Open Foundation - RCC | TB 408 | 485 | 485 | 0 | 0 |  | 485 | 2026-06-01 | 0 | 0 | 0 | 0 |  | OK | No DPR summary | No DPR summary | OK
TB408 | TB 408 | Stringing | 191.39 | 125.82 | 65.57 | 0 | 0 | 1 | Conductor Stringing - S&C | TB 408 | 191.392 | 125.9367 | 65.4553 | 25 |  | 125.9367 | 2026-06-01 | -0.002 | -0.1167 | 0.1147 | -25 |  | Mismatch | No DPR summary | No DPR summary | balance dash 65.57 vs DPR 65.46
TB501 | TB 501 | Erection | 199 | 169 | 30 | 0 | 30 | 1 | Tower Erection | TB 501 | 238 | 230 | 8 | 5 | 3 | 233 | 2026-06-29 | -39 | -61 | 22 | -5 | 27 | Mismatch | Mismatch | Mismatch | balance dash 30 vs DPR 8; June actual dash 30 vs DPR 3
TB501 | TB 501 | Foundation | 199 | 174 | 25 | 0 | 25 | 1 | Open Foundation - RCC | TB 501 | 238 | 235 | 3 | 3 | 2 | 237 | 2026-06-29 | -39 | -61 | 22 | -3 | 23 | Mismatch | Mismatch | Mismatch | balance dash 25 vs DPR 3; June actual dash 25 vs DPR 2
TB501 | TB 501 | Stringing | 63.89 | 21.36 | 42.53 | 0 | 39.58 | 1 | Conductor Stringing - S&C | TB 501 | 73.27 | 67.431 | 5.839 | 5.809 | 3.309 | 70.74 | 2026-06-29 | -9.38 | -46.071 | 36.691 | -5.809 | 36.271 | Mismatch | Mismatch | Mismatch | balance dash 42.53 vs DPR 5.84; June actual dash 39.58 vs DPR 3.31
TB507 | TB 507 | Erection | 500 | 12 | 488 | 40 | 0 | 1 | Tower Erection | TB 507 | 556 | 221 | 335 | 51 | 15 | 236 | 2026-06-28 | -56 | -209 | 153 | -11 | -15 | Mismatch | Mismatch | Mismatch | balance dash 488 vs DPR 335; June actual dash 0 vs DPR 15
TB507 | TB 507 | Foundation | 500 | 138 | 362 | 34 | 0 | 1 | Open Foundation - RCC | TB 507 | 556 | 342 | 214 | 42 | 18 | 360 | 2026-06-28 | -56 | -204 | 148 | -8 | -18 | Mismatch | Mismatch | Mismatch | balance dash 362 vs DPR 214; June actual dash 0 vs DPR 18
TB507 | TB 507 | Stringing | 73.8 | 0 | 73.8 | 0 | 0 | 1 | Conductor Stringing - S&C | TB 507 | 392.834 | 21.36 | 371.474 | 21.084 |  | 21.36 | 2026-06-28 | -319.034 | -21.36 | -297.674 | -21.084 |  | Mismatch | No DPR summary | No DPR summary | balance dash 73.80 vs DPR 371.47
TB605 | TB 605 | Erection | 399 | 5 | 394 | 0 | 0 | 1 | Tower Erection | TB 605 | 523 | 203 | 320 | 60 | 42 | 245 | 2026-06-28 | -124 | -198 | 74 | -60 | -42 | Mismatch | Mismatch | Mismatch | balance dash 394 vs DPR 320; June actual dash 0 vs DPR 42
TB605 | TB 605 | Foundation | 399 | 62 | 337 | 0 | 0 | 1 | Open Foundation - RCC | TB 605 | 523 | 370 | 153 | 65 | 43 | 413 | 2026-06-28 | -124 | -308 | 184 | -65 | -43 | Mismatch | Mismatch | Mismatch | balance dash 337 vs DPR 153; June actual dash 0 vs DPR 43
TB605 | TB 605 | Stringing | 138.63 | 0 | 138.63 | 0 | 0 | 1 | Conductor Stringing - S&C | TB 605 | 351.438 | 0 | 351.438 | 23.26 | 2.94 | 2.94 | 2026-06-28 | -212.808 | 0 | -212.808 | -23.26 | -2.94 | Mismatch | Mismatch | Mismatch | balance dash 138.63 vs DPR 351.44; June actual dash 0 vs DPR 2.94
TB608 | TB 608 | Erection | 264 | 27 | 237 | 0 | 12 | 1 | Tower Erection | TB 608 | 349 | 31 | 318 | 20 | 10 | 41 | 2026-06-28 | -85 | -4 | -81 | -20 | 2 | Mismatch | Mismatch | Mismatch | balance dash 237 vs DPR 318; June actual dash 12 vs DPR 10
TB608 | TB 608 | Foundation | 264 | 131 | 133 | 0 | 4 | 2 | Open Foundation - RCC; Piling Foundation - Concreting | TB 608 | 460 | 146 | 314 | 8 | 4 | 150 | 2026-06-28 | -196 | -15 | -181 | -8 | 0 | Mismatch | OK | Mismatch | balance dash 133 vs DPR 314
TB608 | TB 608 | Stringing | 86.11 | 0 | 86.11 | 0 | 0 | 1 | Conductor Stringing - S&C | TB 608 | 103.9731 | 0 | 103.9731 | 0 | 0 | 0 | 2026-06-28 | -17.8631 | 0 | -17.8631 | 0 | 0 | Mismatch | OK | Mismatch | balance dash 86.11 vs DPR 103.97
TB611 | TB 611 | Erection | 225 | 0 | 225 | 0 | 0 | 1 | Tower Erection | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TB611 | TB 611 | Foundation | 225 | 0 | 225 | 0 | 28 | 1 | Open Foundation - RCC | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found
TB611 | TB 611 | Stringing | 84.83 | 0 | 84.83 | 0 | 0 | 1 | Conductor Stringing - S&C | [13 empty] | No DPR summary | No DPR summary | No DPR summary | No DPR project-level summary found

## DPR Foundation Source
project_key | fes_activity | dpr_project | dpr_scope | dpr_completed_may | dpr_balance_may | dpr_june_plan | dpr_june_actual | dpr_completed_current | dpr_report_date
TA413 | Foundation | TA 413 | 316 | 316 | 0 | 0 | 0 | 316 | 2026-06-28
TA414 | Foundation | TA 414 | 352 | 319 | 33 | 31 | 17 | 336 | 2026-06-29
TA416 | Foundation | TA 416 | 302 | 302 | 0 | 0 | 0 | 302 | 2026-06-25
TA418 | Foundation | TA 418 | 127 | 127 | 0 | 0 | 0 | 127 | 2026-06-17
TA419 | Foundation | TA 419 | 331 | 255 | 76 | 49 | 15 | 270 | 2026-06-26
TA421 | Foundation | TA 421 | 309 | 309 | 0 |  | 0 | 309 | 2026-06-29
TA504 | Foundation | TA 504 | 186 | 144 | 42 | 6 | 2 | 146 | 2026-06-27
TA505 | Foundation | TA 505 | 379 | 375 | 4 | 4 | 3 | 378 | 2026-06-28
TA506 | Foundation | TA 506 | 602 | 492 | 110 | 40 | 7 | 499 | 2026-06-27
TA509 | Foundation | TA 509 | 309 | 268 | 41 | 13 | 6 | 274 | 2026-06-28
TA510 | Foundation | TA 510 | 293 | 85 | 208 | 16 | 10 | 95 | 2026-06-29
TA512 | Foundation | TA 512 | 319 | 306 | 13 | 18 | 6 | 312 | 2026-06-28
TA513 | Foundation | TA 513 | 619 | 89 | 530 | 35 | 9 | 98 | 2026-06-22
TA601 | Foundation | TA 601 | 292 | 124 | 168 | 35 | 21 | 145 | 2026-06-29
TA602 | Foundation | TA 602 | 480 | 154 | 326 | 30 | 11 | 165 | 2026-06-26
TB408 | Foundation | TB 408 | 485 | 485 | 0 | 0 |  | 485 | 2026-06-01
TB412 | Foundation | TB 412 | 505 | 264 | 241 | 80 | 32 | 296 | 2026-06-24
TB501 | Foundation | TB 501 | 238 | 235 | 3 | 3 | 2 | 237 | 2026-06-29
TB507 | Foundation | TB 507 | 556 | 342 | 214 | 42 | 18 | 360 | 2026-06-28
TB605 | Foundation | TB 605 | 523 | 370 | 153 | 65 | 43 | 413 | 2026-06-28
TB608 | Foundation | TB 608 | 460 | 146 | 314 | 8 | 4 | 150 | 2026-06-28

## Mail Erection Source
PCH | Project | Plan (Nos.) | Actual Towers (Nos.) | Total MT | Avg Tower Wt (MT) | Productivity
Mr. Arun Felbin | TA 414 | 44 | 30 | 1913.92 | 63.8 | 4.59
Mr. Arun Felbin | TA 510 | 30 | 5 | 290.52 | 58.1 | 7.43
Mr. Arun Felbin | TA 601 | 25 | 16 | 633.9 | 39.62 | 4.91
Mr. Arun Felbin | TA 602 | 35 | 26 | 678.39 | 26.09 | 5.02
Mr. NK Gupta | TA 413 | 4 | 1 | 67.26 | 67.26 | 3.74
Mr. NK Gupta | TA 419 | 50 | 11 | 730.89 | 66.44 | 3.18
Mr. NK Gupta | TA 512 | 30 | 14 | 745.55 | 53.25 | 5.84
Mr. NK Gupta | TA 513 | 16 | 4 | 180 | 45 | 6.84
Mr. NK Gupta | TB 408 | 1 | 0
Mr. NK Gupta | TB 412 | 70 | 38 | 511.24 | 13.45 | 2.28
Mr. NK Gupta | TB 507 | 51 | 15 | 308.07 | 20.54 | 1.89
Mr. NK Gupta | TB 605 | 60 | 42 | 1205.67 | 28.71 | 3.54
Mr. NK Gupta | TB 608 | 20 | 10 | 307.27 | 30.73 | 2.22
Mr. Nabajit Baruah | TA 504 | 6 | 5 | 223.45 | 44.69 | 4.18
Mr. Nabajit Baruah | TA 505 | 7 | 6 | 351.56 | 58.59 | 6.87
Mr. Nabajit Baruah | TA 506 | 25 | 21 | 845.2 | 40.25 | 6.09
Mr. Nabajit Baruah | TA 509 | 30 | 11 | 502.03 | 45.64 | 5.67
Mr. Nabajit Baruah | TB 501 | 5 | 3 | 28.64 | 9.55 | 2.4

## Mail Stringing Source
PCH | Project | Plan (KM) | Actual Achieved (KM) | Productivity | Scope (KM) | Stringing Completed (KM) | Stretch Ready (KM)
Mr. Arun Felbin | TA 414 | 20 | 9.1 | 2.39 | 127.8 | 25.05
Mr. Arun Felbin | TA 416 | 4 | 3.32 | 3.49 | 115.13 | 114.46
Mr. Arun Felbin | TA 418 | 18.26 | 1.64 | 2.27 | 47.84 | 31.23
Mr. Arun Felbin | TA 421 | 5.88 | 4.4 | 3.67 | 121.34 | 119.87 | 0
Mr. Arun Felbin | TA 510 | 11 | 0 |  | 114.52 | 0
Mr. NK Gupta | TA 413 | 21.51 | 10.05 | 12.56 | 117.85 | 87.24 | 0
Mr. NK Gupta | TA 419 |  | 2.1 |  | 122.07 | 2.55 | 0
Mr. NK Gupta | TB 408 | 25 | 0 |  | 191.39 | 125.94 | 0
Mr. NK Gupta | TB 412 | 12 | 3.2 |  | 150.83 | 3.2
Mr. NK Gupta | TB 507 | 21.08 | 0 |  | 392.83 | 21.36 | 0
Mr. NK Gupta | TB 605 | 23.26 | 2.94 |  | 351.44 | 2.94
Mr. Nabajit Baruah | TA 504 | 8 | 7.14 | 5.19 | 69 | 20.56 | 0
Mr. Nabajit Baruah | TA 505 | 23.01 | 9.75 | 11.27 | 139.6 | 25.21 | 0
Mr. Nabajit Baruah | TA 506 | 30 | 7.48 | 7.31 | 223 | 63.11 | 68.26
Mr. Nabajit Baruah | TA 509 | 12 | 3.46 |  | 119.18 | 3.46
Mr. Nabajit Baruah | TB 501 | 5.81 | 3.31 |  | 73.27 | 70.74
Mr. Nabajit Baruah | TB 501220KV |  | 2.46 | 4.6