## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TA 509 | 765KV D/C MANDSAUR-KURAWAR(PART-1) TRANSMISSION LINE(WZ-4) | PGCIL | 2025-11-26 | 2026-10-26 | Pawan Sharma | Mr Arun Felbin | Mr Vijay Kute | Mr Prithviraj | Prasanta Das | Faljeet kumar
[9 empty] | Himanshu Yadav | Abhishek Yadav
Manjur Alam
Abhishek Mishra
Teklal Mahato
Manoj Kumar Mahato
Bendict Lakra
Shashi Paswan
Sunil Chauhan
Dhamender Singh

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | 16/4 | DA+0 |  | 2025-08-22 | 36.15 | COMPLETED | 2025-09-03 | DEVI CONST.-I
2 | 13/2 | DA+0 |  | 2025-08-22 | 36.15 | COMPLETED | 2025-09-15 | DEONATH MAHATO
3 | 8/5 | DA+0 |  | 2025-08-25 | 36.15 | COMPLETED | 2025-09-08 | JAWALA SINGH
4 | 12/6 | DA+0 |  | 2025-08-25 | 36.15 | COMPLETED | 2025-09-18 | MODINA INDIA
5 | 12/1 | DA+3 |  | 2025-09-02 | 37.93 | COMPLETED | 2025-09-23 | OM CONSTRUCTION
6 | 15/2 | DA+3 |  | 2025-09-02 | 37.93 | COMPLETED | 2025-09-12 | HEMLAL MAHATO-I (Anita Devi)
7 | 20/1 | DA-3 |  | 2025-09-07 | 34.79 | COMPLETED | 2025-09-14 | DEVI CONST.-I
8 | 16/1 | DA+0 |  | 2025-09-07 | 36.15 | COMPLETED | 2025-09-12 | DEVI CONST.-II
9 | 8/6 | DA+0 |  | 414788 | 36.15 | COMPLETED | 2025-09-14 | JAWALA SINGH
10 | 13/4 | DA-3 |  | 2025-09-13 | 34.79 | COMPLETED | 2025-09-27 | DEONATH MAHATO
11 | 15/5 | DA-3 |  | 2025-09-01 | 34.79 | COMPLETED | 2025-09-19 | HEMLAL MAHATO-I (Anita Devi)
12 | 16/8 | DA-3 |  | 2025-09-13 | 34.79 | COMPLETED | 2025-09-19 | DEVI CONST.-I
13 | 8/7 | DA+0 |  | 2025-09-14 | 36.15 | COMPLETED | 2025-09-20 | JAWALA SINGH
14 | 22/1 | DA+6 |  | 2025-09-15 | 43.8 | COMPLETED | 2025-09-23 | DEVI CONST.-II
15 | 14/1 | DA+0 |  | 2025-09-16 | 36.15 | COMPLETED | 2025-09-24 | OM CONSTRUCTION
16 | 16/9 | DA+0 |  | 2025-09-19 | 36.15 | COMPLETED | 2025-09-25 | HEMLAL MAHATO-II (Anita Devi)
17 | 9/1 | DA+3 |  | 2025-09-20 | 37.93 | COMPLETED | 2025-09-26 | DEVI CONST.-I
18 | 20/2 | DA-3 |  | 2025-09-23 | 34.79 | COMPLETED | 2025-09-29 | JAWALA SINGH
19 | 14/2 | DA+0 |  | 2025-09-24 | 36.15 | COMPLETED | 2025-09-30 | DEVI CONST.-II
20 | 16/7 | DA+0 |  | 2025-10-01 | 36.15 | COMPLETED | 2025-10-06 | HEMLAL MAHATO-I (Anita Devi)
21 | 12/2 | DA-3 |  | 2025-09-16 | 34.79 | COMPLETED | 2025-10-04 | DEVI CONST.-I
22 | 10/1 | DA+0 |  | 2025-09-27 | 36.15 | COMPLETED | 2025-10-02 | JAWALA SINGH
23 | 13/1 | DA-1.5 |  | 2025-10-01 | 35.602 | COMPLETED | 2025-10-13 | DEONATH MAHATO
24 | 16/11 | DA+6 |  | 2025-09-25 | 43.8 | COMPLETED | 2025-10-01 | DEVI CONST.-I
25 | 24/6 | DA+3 |  | 2025-10-01 | 37.93 | COMPLETED | 2025-10-06 | DEVI CONST.-II
26 | 14/3 | DA-3 |  | 2025-10-05 | 34.79 | COMPLETED | 2025-10-16 | OM CONSTRUCTION
27 | 24/7 | DA+0 |  | 2025-10-07 | 36.15 | COMPLETED | 2025-10-11 | DEVI CONST.
28 | 8/10 | DA+0 |  | 2025-10-12 | 36.15 | COMPLETED | 2025-10-16 | DEVI CONST.
29 | 8/9 | DA-3 |  | 2025-10-16 | 34.79 | COMPLETED | 2025-10-22 | DEVI CONST.
30 | 8/8 | DA+3 |  | 2025-10-22 | 37.93 | COMPLETED | 2025-10-25 | DEVI CONST.
31 | 9/2 | DA+0 |  | 2025-10-26 | 36.15 | COMPLETED | 2025-02-11 | DEVI CONST.
32 | 8/4 | DA+3 |  | 2025-11-03 | 37.93 | COMPLETED | 2025-11-07 | DEVI CONST.
33 | 10/2 | DA-3 |  | 2025-11-07 | 34.79 | COMPLETED | 2025-11-11 | DEVI CONST.
34 | 12/3 | DA-3 |  | 2025-11-11 | 34.79 | COMPLETED | 2025-11-16 | DEVI CONST.
35 | 15/4 |  |  | 13/11/2025 | 43.8044 | COMPLETED | 25/11/2025 | Arawali infra-1
36 | 16/2 |  |  | 13.11.2025 | 36.1598 | COMPLETED | 24.11.2025
37 | 21/4 |  |  |  |  | 1st Section U/P
38 | 12/3 | DA-3 |  | 11.11.2025 | 34.79 | COMPLETED | 16.11.2025 | DEVI CONST.
39 | 13/0 | DB2+0 |  | 16.11.2025 | 59.5006 | COMPLETED | 27.11.2025 | DEVI CONST.
40 | 5/1 | DA-3 |  | 20.11.2025 | 34.79 | COMPLETED | 25.11.2025 | JAWALA SINGH

## Stringing Compiled
|  |  | Number of TSE | 4
S.no | Sec | From AP | To AP | Span (M) | Method | Section Readiness | P/O Starting Date | P/O Completion Date | P/O | F/S Starting Date | F/S/ Completion Date | Length | Status | Gang Name | Hindrance | Remarks