## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer/Manager | PCH | Regional Manager | Project Manger | Section Incharge | Supervisor
TA 418 | 765KV D/C HEXA NEEMRANA II BAREILLY TL -03 | PGCIL | 2024-02-07 | 2025-11-06 | Sanjib Samantaray | Mr Arun Felbin | Mr Rajiv Sharma | Mr Sanjay Gupta | Prabin Patra | Rupesh
[9 empty] | Shikhar Pratap | Bijendra
Rahman
Sitaram
Churamani
Saidur
Madhusudan
Ritlal
Somenath
Aflaudin
Akhtarul

## MASTER SHEET
| Project Code | TA-416 | Date | 2025-10-10 |  |  | SBU Head | Mr. Rajinder Gupta
| Project Name | 765KV D/C NEEMRANA II - BAREILLY TL (Part-3) |  |  | NOA Start Date | 07.02.2025 | PCH | Mr. Arun Felbin
| Client Name | Power Grid Corporation of India Limited |  |  | NOA End Date | 06.11.2025 | Regional Manager | Mr. Rajiv Sharma
| End Date | 06.11.2025 |  |  | Planning | Sanjib Samantaray | Project Manger | Mr Sanjay Gupta
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Tower | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Check Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Progress Status
Activity | Unit | Final Estimated Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | Nos | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 302 | 0 | 0 | 0 | Team demobilised due to non availability of further work front.
Earthing | Nos | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 302 | 0 | 0 | 0
Tower Erection | Nos | 302 | 302 | 260 | 0 | 32 | 1 | 10 | 302 | 270 | 32 | 10 | 10
Stringing | Km | 115.134 | 107 | 49 | 8 | 30 | 0 | 8.379 | 115 | 57.379 | 57.755 | 9.985 | 3
Sl.No | Nature of Work | GANG NAME | WIP LOCATION |  | AS ON DATE - WORK FRONT |  | REMARKS
| TOWER ERECTION | Maa Construction | 0/0 |  | 2/2
| TOWER ERECTION | Gourishankar | 22A/0 |  | 23/0
| TOWER ERECTION | Reeta Bharti | 23/0 |  | 57/0
| TOWER ERECTION | Unity India | 37/0
| TOWER ERECTION | Pankaj Kumar | 38/0 |  | 58/0
| TOWER ERECTION | Amit Choudhury | 45/0
| TOWER ERECTION | Punam Kumari-1 | 49/0
| TOWER ERECTION | Sainik trader | 53A/0 |  | 53A/07
| TOWER ERECTION | Spotify-1 | 52/7
| TOWER ERECTION | Punam Kumari-2 | 55/0 |  | 55/1
| TOWER ERECTION | Spotify-2 | 56/6 |  | 56/7
| TOWER ERECTION | Mahon Mahto | 61/0 |  | 62/0
TOWER ERECTION
TOWER ERECTION
TOWER ERECTION
*SUPPORT REQUIRED :
* | Required further work front for foundation works In order to sustain the manpower and Machinary.
* | Required further work front for Erection works without frequest shifting of gang In order to sustain the manpower.
* | Tree Cutting arrangements for Planned stringing stretches.
SUPPLY STATUS:
Sl. No. | Description |  | UOM | LOA Qty | As per L2 till Sep'25 | Supplied AS on Date | Supply Shortfall against L2 | Balance Qty. | Remarks
1 | STUB |  | Sets | 302 | 302 | 302 | 0 | 0
2 | TOWER PARTS |  | Sets | 302 | 302 | 302 | 0 | 0
3 | Earthing Materials |  | EA | 302 | 302 | 302 | 0 | 0
4 | 7/3.66 G.S Earthwire |  | KM | 116 | 116 | 116 | 0 | 0
5 | Conductor - ACSR AL-59 Zebra |  | KM | 4186 | 4186 | 4186 | 0 | 0
6 | 160KN CLR Insulator Supply |  | Nos | 5784 | 5784 | 5784 | 0 | 0
7 | 210KN CLR Insulator Supply |  | Nos | 7440 | 7440 | 7440 | 0 | 0
8 | OPGW supply |  | KM | 121 | 121 | 121 | 0 | 0
9 | Quadruple Tension String |  | Set | 936 | 936 | 936 | 0 | 0
10 | Double ISuspension String |  | Set | 1350 | 1350 | 1350 | 0 | 0
11 | HEXAGONAL RIGID SPACER |  | Set | 2870 | 2870 | 2760 | 110 | 110
12 | Single ISuspension String (Pilot) |  | Set | 196 | 196 | 196 | 0 | 0
13 | Mid Span Comp. Joint For Cond. |  | Set | 2100 | 2100 | 2100 | 0 | 0
14 | Spacer Damper |  | Set | 12726 | 12726 | 12726 | 0 | 0 | Balance Quantity will be supplied in OCT'25
15 | REPAIR SLEEVE FOR CONDUCTOR |  | Set | 700 | 700 | 700 | 0 | 0
16 | FLEXIBLE AL BOND |  | Set | 381 | 381 | 379 | 2 | 2
17 | Suspension Clamp E/W |  | Set | 225 | 225 | 225 | 0 | 0
18 | Vibration Damper for E/W |  | Set | 760 | 760 | 756 | 4 | 4
19 | Tension Clamp for E/W |  | Set | 156 | 156 | 154 | 2 | 2
20 | Mid Span Comp. Joint for E/W |  | Set | 64 | 64 | 64 | 0 | 0

## Erection Compiled
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | 2/8 | DA+0 |  | 2024-09-01 | 43.7758 | COMPLETED | 2024-09-16 | Dewi Construction(Girendra)
2 | 2/4 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED | 2024-09-29 | Dewi Construction(Girendra)
3 | 39/10 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED | 2024-10-01 | Horil Mahto
4 | 20/8 | DA+0 |  | 2024-10-01 | 43.7758 | COMPLETED | 2024-10-07 | Dewi Construction(Girendra)
5 | 39/8 | DA+0 |  | 2024-10-03 | 43.7758 | COMPLETED | 2024-10-15 | Horil Mahto
6 | 20/6 | DA+0 |  | 2024-10-08 | 43.7758 | COMPLETED | 2024-10-13 | Dewi Construction(Girendra)
7 | 20/9 | DA+3 |  | 2024-10-14 | 46.0492 | COMPLETED | 2024-10-19 | Dewi Construction(Girendra)
8 | 39/7 | DA+3 |  | 2024-10-15 | 46.0492 | COMPLETED | 2024-10-24 | Horil Mahto
9 | 20/5 | DA+3 |  | 2024-10-20 | 46.0492 | COMPLETED | 2024-10-24 | Dewi Construction(Girendra)
10 | 20/7 | DA-3 |  | 2024-10-24 | 42.3742 | COMPLETED | 2024-10-29 | Dewi Construction(Girendra)
11 | 39/9 | DA+3 |  | 2024-10-24 | 46.0492 | COMPLETED | 2024-10-31 | Horil Mahto
12 | 20/12 | DA-3 |  | 2024-11-01 | 42.3742 | COMPLETED | 2024-11-04 | Dewi Construction(Girendra)
13 | 14/6 | DA+3 |  | 2024-11-05 | 46.0492 | COMPLETED | 2024-11-10 | Dewi Construction(Girendra)
14 | 39/6 | DA+3 |  | 2024-11-01 | 46.0492 | COMPLETED | 14.11.2024 | Horil Mahto
15 | 14/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-17 | Dewi Construction(Girendra)
16 | 14/4 | DA+3 |  | 2024-11-17 | 46.0492 | COMPLETED | 2024-11-22 | Dewi Construction(Girendra)
17 | 2/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-24 | Pankaj
18 | 19/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2024-11-26 | Reeta Bharti
19 | 6/2 | DA+3 |  | 2024-11-14 | 46.0492 | COMPLETED | 2026-11-25 | Pinky Dewi
20 | 38/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED | 2026-11-25 | Horil Mahto
21 | 14/8 | DA+3 |  | 2024-11-22 | 46.0492 | COMPLETED | 2024-11-28 | Dewi Construction(Girendra)
22 | 41/1 | DA+0 |  | 2024-11-10 | 43.7758 | COMPLETED | 2024-11-29 | Amar Singh
23 | 2/7 | DA+3 |  | 2024-11-26 | 46.0492 | COMPLETED | 2024-12-03 | Pankaj
24 | 19/2 | DA+0 |  | 2024-11-28 | 43.7758 | COMPLETED | 2024-12-05 | Reeta Bharti
25 | 14/7 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED | 2024-12-05 | Dewi Construction(Girendra)
26 | 4/3 | DA+3 |  | 2024-11-28 | 46.0492 | COMPLETED | 2024-12-05 | Pinky Dewi
27 | 36/12 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED | 2024-12-06 | Horil Mahto
28 | 2/6 | DA+0 |  | 2024-12-01 | 43.7758 | COMPLETED | 2024-12-09 | Pankaj
29 | 41/2 | DA+3 |  | 2024-11-30 | 46.0492 | COMPLETED | 2024-12-10 | Amar Singh
30 | 14/3 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-12 | Dewi Construction(Girendra)
31 | 4/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-12 | Pinky Dewi
32 | 19/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED | 2024-12-13 | Reeta Bharti
33 | 2/3 | DA+3 |  | 2024-12-10 | 46.0492 | COMPLETED | 2024-12-16 | Pankaj
34 | 4/2 | DA-3 |  | 2024-12-12 | 42.3742 | COMPLETED | 2024-12-16 | Pinky Dewi
35 | 14/2 | DA+0 |  | 2024-12-12 | 43.7758 | COMPLETED | 2024-12-17 | Dewi Construction(Girendra)
36 | 38/2 | DA+3 |  | 2024-12-06 | 46.0492 | COMPLETED | 2024-12-19 | Horil Mahto
37 | 45/3 | DA-3 |  | 2024-12-10 | 42.3742 | COMPLETED | 2024-12-20 | Amar Singh
38 | 19/1 | DA+0 |  | 2024-12-13 | 43.7758 | COMPLETED | 2024-12-21 | Reeta Bharti
39 | 4/8 | DA+0 |  | 2024-12-17 | 43.7758 | COMPLETED | 2024-12-22 | Pinky Dewi
40 | 14/1 | DA+0 |  | 2024-12-18 | 43.7758 | COMPLETED | 2024-12-23 | Dewi Construction(Girendra)
41 | 7/10 | DA+3 |  | 2024-12-18 | 46.0492 | COMPLETED | 2024-12-23 | Pankaj
42 | 45/2 | DA+3 |  | 2024-12-21 | 46.0492 | COMPLETED | 2024-12-27 | Amar Singh
43 | 19/5 | DA-3 |  | 2024-12-22 | 42.3742 | COMPLETED | 2024-12-27 | Reeta Bharti
44 | 4/7 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED | 2024-12-27 | Pinky Dewi
45 | 7/9 | DA+0 |  | 2024-12-24 | 43.7758 | COMPLETED | 2024-12-30 | Pankaj
46 | 38/4 | DA+3 |  | 2024-12-20 | 46.0492 | COMPLETED | 2024-12-31 | Horil Mahto
47 | 17/1 | DA-3 |  | 2024-12-24 | 42.3742 | COMPLETED | 2024-12-31 | Dewi Construction(Girendra)
48 | 31/3 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED | 2025-01-03 | ASC heights
49 | 4/5 | DA+3 |  | 2024-12-28 | 46.0492 | COMPLETED | 2025-01-03 | Pinky Dewi
50 | 46/1 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED | 2025-01-04 | Amar Singh
51 | 7/2 | DA+3 |  | 2024-12-31 | 46.0492 | COMPLETED | 2025-01-07 | Pankaj
52 | 19/6 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED | 2025-01-08 | Reeta Bharti
53 | 17/4 | DA+3 |  | 2025-01-01 | 46.0492 | COMPLETED | 2025-01-10 | Dewi Construction(Girendra)
54 | 31/4 | DA-3 |  | 2025-01-04 | 42.3742 | COMPLETED | 2025-01-11 | ASC heights
55 | 12/2 | DA+3 |  | 2025-01-03 | 46.0492 | COMPLETED | 2025-01-11 | Pinky Dewi
56 | 7/8 | DA+3 |  | 2025-01-08 | 46.0492 | COMPLETED | 2025-01-14 | Pankaj
57 | 36/3 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED | 2025-01-15 | Amar Singh
58 | 38/1 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED | 2025-01-17 | Horil Mahto
59 | 19/7 | DA+3 |  | 2025-01-09 | 46.0492 | COMPLETED | 2025-01-17 | Reeta Bharti
60 | 17/3 | DA+0 |  | 2025-01-10 | 43.7758 | COMPLETED | 2025-01-17 | Dewi Construction(Girendra)
61 | 31/2 | DA+0 |  | 2025-01-11 | 43.7758 | COMPLETED | 2025-01-19 | ASC heights
62 | 12/3 | DA+3 |  | 2025-01-12 | 46.0492 | COMPLETED | 2025-01-21 | Pinky Dewi
63 | 7/7 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED | 2025-01-22 | Pankaj
64 | 17/2 | DA+0 |  | 2025-01-17 | 43.7758 | COMPLETED | 2025-01-23 | Dewi Construction(Girendra)
65 | 36/5 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED | 2025-01-24 | Amar Singh
66 | 31/6 | DA+3 |  | 2025-01-20 | 46.0492 | COMPLETED | 2025-01-25 | ASC heights
67 | 12/4 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED | 2025-01-25 | Pinky Dewi
68 | 19/9 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED | 2025-01-27 | Reeta Bharti
69 | 35/1 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED | 2025-01-28 | Horil Mahto
70 | 17/5 | DA+3 |  | 2025-01-24 | 46.0492 | COMPLETED | 2025-01-29 | Dewi Construction(Girendra) |  |  | 1: 3; 16: 3; 17: 2; 18: 2; 19: 1; 20: 1; 21: 4; 22: 1; 23: 1; 24: 2; 25: 2; 26: 1; 27: 3; 28: 1; 29: 2; 30: 1; 31: 3
71 | 7/6 | DA+0 |  | 2025-01-21 | 43.7758 | COMPLETED | 2025-01-30 | Pankaj
72 | 36/1 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED | 2025-01-30 | Amar Singh
73 | 33/10 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED | 2025-01-31 | Rudra Construction
74 | 12/5 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED | 2025-02-01 | Pinky Dewi
75 | 31/1 | DA+0 |  | 2025-01-25 | 43.7758 | COMPLETED | 2025-02-02 | ASC heights |  |  | 1: 3; 2: 1; 3: 7; 4: 2; 5: 6; 6: 1; 7: 6; 8: 5; 9: 2; 10: 1; 31: 1
76 | 17/7 | DA+3 |  | 2025-01-30 | 46.0492 | COMPLETED | 2025-02-05 | Dewi Construction(Girendra) |  |  | 1: 1; 2: 2; 3: 2; 4: 3; 5: 17; 6: 6; 7: 3; 8: 15; 9: 2; 10: 1; 11: 9; 12: 2
77 | 20/0 | DB+0 |  | 2025-01-28 | 64.4817 | COMPLETED | 2025-02-06 | Reeta Bharti |  |  | 3: 5.91; 4: 8.93; 5: 9.52; 6: 1.67; 7: 1.87
78 | 36/2 | DA+0 |  | 2025-02-02 | 43.7758 | COMPLETED | 2025-02-07 | Amar Singh | 27
79 | 12/9 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED | 2025-02-08 | Pinky Dewi
80 | 7/5 | DA+3 |  | 2025-01-29 | 46.0492 | COMPLETED | 2025-02-09 | Pankaj |  |  | 9: 1; 10: 2; 11: 10; 12: 13; 13: 3
81 | 31/7 | DA+0 |  | 2025-02-03 | 43.7758 | COMPLETED | 2025-02-10 | ASC heights | 23
82 | 35/0 | DC+0 |  | 2025-01-29 | 73.4258 | COMPLETED | 2025-02-11 | Horil Mahto |  |  | 12: 3.88; 13: 3.74; 14: 2.37; 15: 2.87; 16: 4.33; 17: 1.63; 18: 3.32; 19: 4.2; 20: 1.91; 21: 0.98; 22: 4.07
83 | 33/11 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED | 2025-02-12 | Rudra Construction |  |  | 14: 5.56; 15: 6.8; 16: 8.93; 17: 2.19; 18: 2.48; 19: 2.29; 20: 5.28; 21: 6.24; 22: 3.45; 23: 3.31; 24: 3.19; 25: 1.98
84 | 21/0 | DB+0 |  | 2025-02-06 | 64.4817 | COMPLETED | 2025-02-13 | Dewi Construction(Girendra) |  |  | 16: 17; 17: 15; 18: 4; 19: 3; 20: 2; 21: 14; 22: 1; 23: 4
85 | 20/2 | DA+0 |  | 2025-02-07 | 43.7758 | COMPLETED | 2025-02-13 | Reeta Bharti | 29
86 | 35/9 | DA+3 |  | 2025-02-08 | 46.0492 | COMPLETED | 2025-02-15 | Amar Singh | 26
87 | 8/1 | DA+3 |  | 2025-02-09 | 46.0492 | COMPLETED | 2025-02-15 | Pinky Dewi | 34
88 | 7/4 | DA+0 |  | 2025-02-10 | 43.7758 | COMPLETED | 2025-02-18 | Pankaj
89 | 20/3 | DA+0 |  | 2025-02-12 | 43.7758 | COMPLETED | 2025-02-19 | Reeta Bharti
90 | 31/9 | DA+3 |  | 2025-02-11 | 46.0492 | COMPLETED | 2025-02-20 | ASC heights
91 | 34/7 | DA+3 |  | 2025-02-12 | 46.0492 | COMPLETED | 2025-02-20 | Horil Mahto
92 | 33/6 | DA+3 |  | 2025-02-14 | 46.0492 | COMPLETED | 2025-02-20 | Dewi Construction(Girendra)
93 | 8/2 | DA+0 |  | 2025-02-16 | 43.7758 | COMPLETED | 2025-02-21 | Pinky Dewi
94 | 35/7 | DA+3 |  | 2025-02-16 | 46.0492 | COMPLETED | 2025-02-21 | Amar Singh
95 | 33/9 | DA+0 |  | 2025-02-14 | 43.7758 | COMPLETED | 2025-02-22 | Rudra Construction
96 | 20/4 | DA-3 |  | 2025-02-20 | 42.3742 | COMPLETED | 2025-02-25 | Reeta Bharti
97 | 33/7 | DA+3 |  | 2025-02-21 | 46.0492 | COMPLETED | 2025-02-25 | Dewi Construction(Girendra)
98 | 7/1 | DA+0 |  | 2025-02-19 | 43.7758 | COMPLETED | 2025-02-25 | Pankaj
99 | 34/6 | DA+0 |  | 2025-02-21 | 43.7758 | COMPLETED | 2025-02-27 | Horil Mahto
100 | 35/4 | DA+0 |  | 2025-02-20 | 43.7758 | COMPLETED | 2025-02-27 | Amar Singh
101 | 31/0 | DB+0 |  | 2025-02-19 | 64.4817 | COMPLETED | 2025-02-28 | ASC heights
102 | 8/0 | DB+0 |  | 2025-02-22 | 64.4817 | COMPLETED | 2025-02-28 | Pinky Dewi
103 | 33/3 | DA+3 |  | 2025-02-26 | 46.0492 | COMPLETED | 2025-03-02 | Dewi Construction(Girendra)
104 | 35/5 | DA+3 |  | 2025-02-27 | 46.0492 | COMPLETED | 2025-03-03 | Amar Singh
105 | 4/10 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-05 | Reeta Bharti
106 | 33/8 | DA+3 |  | 2025-03-03 | 46.0492 | COMPLETED | 2025-03-07 | Dewi Construction(Girendra)
107 | 7/0 | DB+0 |  | 2025-02-27 | 64.4817 | COMPLETED | 2025-03-08 | Pankaj
108 | 7/11 | DA+0 |  | 2025-03-01 | 43.7758 | COMPLETED | 2025-03-08 | Pinky Dewi
109 | 35/3 | DA+0 |  | 2025-02-28 | 43.7758 | COMPLETED | 2025-03-08 | Horil Mahto
110 | 30/4 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-09 | ASC heights
111 | 34/1 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED | 2025-03-11 | Rudra Construction
112 | 33/4 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED | 2025-03-11 | Dewi Construction(Girendra)
113 | 8/3 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED | 2025-03-12 | Pinky Dewi
114 | 5/0 | DB+0 |  | 2025-03-01 | 64.4817 | COMPLETED | 2025-03-13 | Reeta Bharti
115 | 30/5 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED | 2025-03-16 | ASC heights
116 | 35/6 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED | 2025-03-18 | Horil Mahto
117 | 33/1 | DA-3 |  | 2025-03-12 | 42.3742 | COMPLETED | 2025-03-18 | Dewi Construction(Girendra)
118 | 6/1 | DA+3 |  | 2025-03-09 | 46.0492 | COMPLETED | 2025-03-19 | Pankaj
119 | 8/4 | DA+9 |  | 2025-03-13 | 55.3387 | COMPLETED | 2025-03-21 | Pinky Dewi
120 | 5/1 | DA+3 |  | 2025-03-16 | 46.0492 | COMPLETED | 2025-03-21 | Reeta Bharti
121 | 31/8 | DA-3 |  | 2025-03-16 | 42.3742 | COMPLETED | 2025-03-23 | ASC heights
122 | 33/2 | DA-3 |  | 2025-03-19 | 42.3742 | COMPLETED | 2025-03-23 | Dewi Construction(Girendra)
123 | 8B/1 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED | 2025-03-26 | Pinky Dewi
124 | 7/3 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED | 2025-03-27 | Pankaj
125 | 6/0 | DB+0 |  | 2025-03-22 | 64.4817 | COMPLETED | 2025-03-29 | Reeta Bharti
126 | 35/2 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED | 2025-03-30 | Horil Mahto
127 | 31/10 | DA-3 |  | 2025-03-24 | 42.3742 | COMPLETED | 2025-03-30 | ASC heights
128 | 34/0 | DB+0 |  | 2025-03-24 | 64.4817 | COMPLETED | 2025-03-31 | Dewi Construction(Girendra)
129 | 38/8 | DA+3 |  | 2025-03-21 | 46.0492 | COMPLETED | 2025-03-31 | M K infra
130 | 35/8 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED | 2025-03-31 | Amar Singh
131 | 39/3 | DA+3 |  | 2025-03-24 | 46.0492 | COMPLETED | 2025-03-31 | Ananya Traders-1
132 | 8B/5 | DA+6 |  | 2025-03-24 | 53.3239 | COMPLETED | 2025-03-31 | Pinky Dewi
133 | 4/6 | DA+0 |  | 2025-03-28 | 43.7758 | COMPLETED | 2025-04-05 | Reeta Bharti
134 | 8B/3 | DA+3 |  | 2025-03-28 | 46.0492 | COMPLETED | 2025-04-07 | Pinky Dewi
135 | 20/11 | DA-3 |  | 2025-03-31 | 42.3742 | COMPLETED | 2025-04-08 | Gagan enterprise.1
136 | 34/4 | DA-3 |  | 2025-04-03 | 42.3742 | COMPLETED | 2025-04-10 | Dewi Construction(Girendra)
137 | 4/1 | DA+3 |  | 2025-03-31 | 46.0492 | COMPLETED | 2025-04-11 | Anand Construction
138 | 38/6 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-11 | M K infra
139 | 9/0 | DB+6 |  | 2025-04-01 | 75.8584 | COMPLETED | 2025-04-11 | Gagan enterprise.2
140 | 32/0 | DC+6 |  | 2025-04-01 | 87.0116 | COMPLETED | 2025-04-11 | ASC heights
141 | 39/1 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-12 | Ananya Traders-1
142 | 53A/4 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED | 2025-04-12 | Horil Mahto
143 | 8B/2 | DA-3 |  | 2025-04-08 | 42.3742 | COMPLETED | 2025-04-13 | Pinky Dewi
144 | 36/0 | DB+0 |  | 2025-04-02 | 64.4817 | COMPLETED | 2025-04-14 | Amar Singh
145 | 20/10 | DA+3 |  | 2025-04-09 | 46.0492 | COMPLETED | 2025-04-15 | Gagan enterprise.1
146 | 52/6 | DA+3 |  | 2025-04-05 | 46.0492 | COMPLETED | 2025-04-16 | Ananya Traders-2
147 | 10/1 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-16 | Gagan enterprise.2
148 | 4/0 | DD45+0 |  | 2025-04-06 | 86.2562 | COMPLETED | 2025-04-17 | Reeta Bharti
149 | 39/0 | DB+0 |  | 2025-04-12 | 64.4817 | COMPLETED | 2025-04-19 | Ananya Traders-1
150 | 8B/4 | DA+6 |  | 2025-04-14 | 53.3239 | COMPLETED | 2025-04-21 | Pinky Dewi
151 | 31/5 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-21 | ASC heights
152 | 33/0 | DC+6 |  | 2025-04-12 | 87.0116 | COMPLETED | 2025-04-22 | Dewi Construction(Girendra)
153 | 38/7 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED | 2025-04-22 | M K infra
154 | 36/6 | DA+3 |  | 2025-04-12 | 46.0492 | COMPLETED | 2025-04-22 | Amar Singh
155 | 20/1 | DA+6 |  | 2025-04-16 | 53.3239 | COMPLETED | 2025-04-22 | Gagan enterprise.1
156 | 25/2 | DA+0 |  | 2025-04-15 | 43.7758 | COMPLETED | 2025-04-23 | Rudra Construction
157 | 52/5 | DA-3 |  | 2025-04-17 | 42.3742 | COMPLETED | 2025-04-25 | Ananya Traders-2
158 | 0/4 | DA+9 |  | 2025-04-12 | 55.3387 | COMPLETED | 2025-04-26 | Anand Construction
159 | 19/12 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED | 2025-04-26 | Gagan enterprise.1
160 | 39/2 | DA-3 |  | 2025-04-20 | 42.3742 | COMPLETED | 2025-04-26 | Ananya Traders-1
161 | 36/7 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED | 2025-04-28 | Amar Singh
162 | 34/2 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED | 2025-04-28 | Dewi Construction(Girendra)
163 | 10/0 | DB+9 |  | 2025-04-17 | 78.6775 | COMPLETED | 2025-04-28 | Gagan enterprise.2
164 | 30/6 | DA-3 |  | 2025-04-22 | 42.3742 | COMPLETED | 2025-04-28 | ASC heights
165 | 52/4 | DA-3 |  | 2025-04-26 | 42.3742 | COMPLETED | 2025-04-29 | Ananya Traders-2
166 | 38/9 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED | 2025-06-01 | M K infra
167 | 8A/0 | DD60+0 |  | 2025-04-22 | 97.2286 | COMPLETED | 2025-04-30 | Pinky Dewi
168 | 19/11 | DA-3 |  | 2025-04-27 | 42.3742 | COMPLETED | 2025-04-30 | Gagan enterprise.1
169 | 34/3 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED | 2025-05-03 | Dewi Construction(Girendra)
170 | 39/4 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED | 2025-05-04 | Ananya Traders-1
171 | 36/8 | DA-3 |  | 2025-04-29 | 42.3742 | COMPLETED | 2025-05-05 | Amar Singh
172 | 19/10 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED | 2025-05-06 | Gagan enterprise.1
173 | 30/3 | DA+0 |  | 2025-04-30 | 43.7758 | COMPLETED | 2025-05-06 | ASC heights
174 | 52/3 | DA-3 |  | 2025-04-30 | 42.3742 | COMPLETED | 2025-05-06 | Ananya Traders-2
175 | 25/3 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED | 2025-05-07 | Rudra Construction
176 | 19/8 | DA-3 |  | 2025-05-06 | 42.3742 | COMPLETED | 2025-05-09 | Gagan enterprise.1
177 | 12/1 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED | 2025-05-10 | Gagan enterprise.2
178 | 4/9 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED | 2025-05-11 | Reeta Bharti
179 | 39/5 | DA-3 |  | 2025-05-05 | 42.3742 | COMPLETED | 2025-05-11 | Ananya Traders-1
180 | 52/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED | 2025-05-12 | Ananya Traders-2
181 | 30/1 | DA-3 |  | 2025-05-07 | 42.3742 | COMPLETED | 2025-05-13 | ASC heights
182 | 36/4 | DA+0 |  | 2025-05-07 | 43.7758 | COMPLETED | 2025-05-13 | Amar Singh
183 | 56/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED | 2025-05-14 | Dewi Construction(Girendra)
184 | 8B/0 | DD60+0 |  | 2025-05-05 | 97.2286 | COMPLETED | 2025-05-14 | Pinky Dewi
185 | 17/8 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED | 2025-05-15 | Gagan enterprise.1
186 | 52/9 | DA-3 |  | 2025-05-13 | 42.3742 | COMPLETED | 2025-05-17 | Ananya Traders-2
187 | 56/1 | DA+0 |  | 2025-05-14 | 43.7758 | COMPLETED | 2025-05-19 | Dewi Construction(Girendra)
188 | 36/11 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED | 2025-05-19 | Amar Singh
189 | 38/11 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED | 2025-05-19 | Ananya Traders-1
190 | 30/2 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED | 2025-05-20 | ASC heights
191 | 2/1 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED | 2025-05-21 | Reeta Bharti
192 | 52/10 | DA+3 |  | 2025-05-16 | 46.0492 | COMPLETED | 2025-05-21 | Ananya Traders-2
193 | 23/3 | DA-3 |  | 2025-05-15 | 42.3742 | COMPLETED | 2025-05-22 | Pinky Dewi
194 | 12/6 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED | 2025-05-22 | Gagan enterprise.2
195 | 53/1 | DA+6 |  | 2025-05-12 | 53.3239 | COMPLETED | 2025-05-22 | Amit Const
196 | 36/9 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Amar Singh
197 | 38/10 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Ananya Traders-1
198 | 56/3 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED | 2025-05-24 | Dewi Construction(Girendra)
199 | 15/0 | DC+3 |  | 2025-05-16 | 78.0732 | COMPLETED | 2025-05-25 | Gagan enterprise.1
200 | 23/5 | DA-3 |  | 2025-05-10 | 42.3742 | COMPLETED | 2025-05-27 | Rudra Construction
201 | 52/8 | DA-3 |  | 2025-05-22 | 42.3742 | COMPLETED | 2025-05-27 | Ananya Traders-2
202 | 23/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-28 | Pinky Dewi
203 | 0/2 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-30 | Reeta Bharti
204 | 56/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED | 2025-05-30 | Dewi Construction(Girendra)
205 | 12/8 | DA-3 |  | 2025-05-26 | 42.3742 | COMPLETED | 2025-05-31 | Gagan enterprise.1
206 | 36/10 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED | 2025-05-31 | Amar Singh
207 | 38/5 | DA+3 |  | 2025-05-28 | 46.0492 | COMPLETED | 2025-06-02 | Ananya Traders-1
208 | 23/1 | DA+9 |  | 2025-05-28 | 55.3387 | COMPLETED | 2025-06-03 | Pinky Dewi
209 | 0/3 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED | 2025-06-04 | Reeta Bharti
210 | 56/5 | DA-3 |  | 2025-05-30 | 42.3742 | COMPLETED | 2025-06-04 | Dewi Construction(Girendra)
211 | 51/0 | DD60+0 |  | 2025-05-27 | 97.2286 | COMPLETED | 2025-06-07 | Ananya Traders-2
212 | 23/2 | DA+0 |  | 2025-06-04 | 43.7758 | COMPLETED | 2025-06-09 | Pinky Dewi
213 | 33/5 | DA+3 |  | 2025-06-02 | 46.0492 | COMPLETED | 2025-06-10 | Amar Singh
214 | 0/1 | DA-3 |  | 2025-06-04 | 42.3742 | COMPLETED | 2025-06-11 | Reeta Bharti
215 | 50/1 | DA+0 |  | 2025-06-08 | 43.7758 | COMPLETED | 2025-06-13 | Ananya Traders-2
216 | 53A/5 | DA-3 |  | 2025-06-02 | 42.3742 | COMPLETED | 2025-06-14 | Devine
217 | 34/5 | DA+0 |  | 2025-06-12 | 43.7758 | COMPLETED | 2025-06-18 | Amar Singh
218 | 53A/2 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED | 2025-06-18 | Amit Const
219 | 22/0 | DB+3 |  | 2025-06-12 | 67.112 | COMPLETED | 2025-06-20 | Pinky Dewi
220 | 30/0 | DD60+18 |  | 2025-05-25 | 143.4621 | COMPLETED | 2025-06-21 | ASC heights
221 | 3/0 | DC+0 |  | 2025-06-12 | 73.4258 | COMPLETED | 2025-06-23 | Reeta Bharti
222 | 21/2 | DA+3 |  | 2025-06-21 | 46.0492 | COMPLETED | 2025-06-26 | Pinky Dewi
223 | 45/1 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED | 2025-06-27 | M K infra
224 | 53A/3 | DA+3 |  | 2025-06-20 | 46.0492 | COMPLETED | 2025-06-29 | Amit Const
225 | 48/0 | DD45+9 |  | 2025-06-15 | 104.8666 | COMPLETED | 2025-06-29 | Ananya Traders-2
226 | 12/7 | DA-3 |  | 2025-06-24 | 42.3742 | COMPLETED | 2025-06-30 | Reeta Bharti
227 | 21/1 | DA-3 |  | 2025-06-27 | 42.3742 | COMPLETED | 2025-06-30 | Pinky Dewi
228 | 40/0 | DD60+25 |  | 2025-06-04 | 161.3552 | COMPLETED | 2025-06-30 | Ananya Traders-1
229 | 14/0 | DD60+30 |  | 2025-06-01 | 188.3779 | COMPLETED | 2025-06-30 | Gagan enterprise.1
230 | 28/1 | DA+3 |  | 2025-06-24 | 46.0492 | COMPLETED | 2025-07-05 | ASC heights
231 | 21/3 | DA+3 |  | 2025-07-01 | 46.0492 | COMPLETED | 2025-07-07 | Pinky Dewi
232 | 25/1 | DA+9 |  | 2025-07-01 | 55.3387 | COMPLETED | 2025-07-12 | Reeta Bharti
233 | 44/0 | DD60+3 |  | 2025-07-05 | 101.692 | COMPLETED | 2025-07-18 | Ananya Traders-1
234 | 56/0 | DD45+0 |  | 2025-06-28 | 86.2562 | COMPLETED | 2025-07-22 | Amar singh
235 | 28/0 | DD60+0 |  | 2025-07-08 | 97.2286 | COMPLETED | 2025-07-31 | Reeta Bharti
236 | 41/0 | DD60+18 |  | 2025-07-20 | 143.4621 | COMPLETED | 2025-08-08 | Ananya Traders-1
237 | 13/0 | DD60+30 |  | 2025-07-09 | 188.3779 | COMPLETED | 2025-08-11 | Gagan enterprise.1
238 | 53A/6 | DA+3 |  | 2025-07-27 | 46.0492 | COMPLETED | 2025-08-17 | Punam Kumari
239 | 46/2 | DA+3 |  | 2025-08-14 | 46.0492 | COMPLETED | 2025-08-26 | Gagan enterprise.2 (Kajol)
240 | 24/0 | DD60+25 |  | 2025-07-26 | 161.3552 | COMPLETED | 2025-08-27 | Kongres Kumar-1
241 | 65/0 | DD60+0 |  | 2025-08-02 | 97.2286 | COMPLETED | 2025-08-30 | Kongres Kumar-2
242 | 18/0 | DB+6 |  | 2025-08-04 | 75.8584 | COMPLETED | 2025-08-30 | Sainik Trader
243 | 1/0 | DC+3 |  | 2025-08-09 | 78.0732 | COMPLETED | 2025-08-30 | Radha Construction
244 | 12/0 | DB+18 |  | 2025-08-12 | 97.6534 | COMPLETED | 2025-09-02 | Gagan enterprise.1
245 | 54/1 | DA+9 |  | 2025-08-18 | 55.3387 | COMPLETED | 2025-09-04 | Punam Kumari
246 | 43/0 | DD60+9 |  | 2025-08-10 | 118.4303 | COMPLETED | 2025-09-06 | Ananya Traders-1
247 | 16/0 | DB+25 |  | 2025-08-16 | 110.6255 | COMPLETED | 2025-09-14 | Amit Choudhury
248 | 11/0 | DB+18 |  | 2025-08-24 | 97.6534 | COMPLETED | 2025-09-14 | Gouri Shankar
249 | 2/0 | DD45+3 |  | 2025-09-03 | 89.7178 | COMPLETED | 2025-09-21 | Radha Construction
250 | 64/0 | DC+0 |  | 2025-08-31 | 73.4258 | COMPLETED | 2025-09-22 | Kongres Kumar-2
251 | 52/0 | DC+9 |  | 2025-09-05 | 90.1252 | COMPLETED | 2025-09-22 | Punam Kumari
252 | 47/0 | DC+9 |  | 2025-09-07 | 90.1252 | COMPLETED | 2025-09-22 | Ananya Traders-1
253 | 29/0 | DD60+25 |  | 2025-08-06 | 161.3552 | COMPLETED | 2025-09-22 | Reeta Bharti
254 | 56/8 | DA-3 |  | 2025-08-18 | 42.3742 | COMPLETED | 2025-09-24 | Spotyfy-3
255 | 48/1 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED | 2025-09-23 | Ananya trader
256 | 17/6 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED | 2025-09-24 | Amit Choudhury
257 | 19/0 | DC+6 |  | 2025-08-31 | 87.0116 | COMPLETED | 2025-09-24 | Sainik Trader
258 | 26/0 | DB+9 |  | 2025-09-15 | 78.6775 | COMPLETED | 2025-09-25 | Gouri Shankar
259 | 17/0 | DB+6 |  | 2025-09-11 | 75.8584 | COMPLETED | 2025-09-28 | Maa Construction
260 | 25/0 | DD60+25 |  | 2025-08-28 | 161.3552 | COMPLETED | 2025-09-29 | Kongres Kumar-1
261 | 64/3 | DA-3 |  | 2025-09-24 | 42.3742 | COMPLETED | 2025-10-07 | Kongres Kumar-1
262 | 54/0 | DB+3 |  | 2025-09-25 | 67.112 | COMPLETED | 2025-10-07 | Punam Kumari
263 | 46/0 | DB+0 |  | 2025-09-25 | 64.4817 | COMPLETED | 2025-10-08 | Amit Choudhury
264 | 63/0 | DC+3 |  | 2025-10-01 | 78.0732 | COMPLETED | 2025-10-12 | Mahon Mahto
265 | 27/0 | DD60+3 |  | 2025-09-22 | 101.692 | COMPLETED | 2025-10-12 | Reeta Bharti
266 | 53A/1 | DA+6 |  | 2025-09-18 | 53.3239 | COMPLETED | 2025-10-13 | Spotyfy
267 | 50/0 | DC+18 |  | 2025-09-25 | 110.6958 | COMPLETED | 2025-10-14 | Punam kumari-1
268 | 53/0 | DC+0 |  | 2025-09-26 | 73.4258 | COMPLETED | 2025-10-14 | Sainik Trader
269 | 42/0 | DD60+18 |  | 2025-09-23 | 143.4621 | COMPLETED | 2025-10-14 | Ananya trader
270 | 54/2 | DA-3 |  | 2025-10-08 | 42.3742 | COMPLETED | 2025-10-22 | Punam kumari-2
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302

## Progress.
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Tower | No's | 302 | 302 | 302 | 0 | 0 | 0 | 0 | 302 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
Check Survey | kms | 115.134 | 115.134 | 115.134 | 115.134 | 0 | 0 | 0 | 0 | 0 | 115.134
S.No | Location No. | Tower Type | Classification | Start Date | Conc Volume | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 2/8 | DA+0 | Wet Paddy | 2024-04-24 | 37.64 | Completed |  |  |  | 2024-05-06 | Sumit Constrcution
2 | 2/7 | DA+3 | Wet Paddy | 2024-05-01 | 41.37 | Completed |  |  |  | 2024-05-10 | Sumit Constrcution
3 | 2/6 | DA+0 | Wet Paddy | 2024-05-09 | 37.64 | Completed |  |  |  | 2024-05-14 | Sumit Constrcution
4 | 2/5 | DA+3 | Wet Paddy | 2024-05-13 | 41.37 | Completed |  |  |  | 2024-05-18 | Sumit Constrcution
5 | 2/4 | DA+0 | Wet Paddy | 2024-05-16 | 37.64 | Completed |  |  |  | 2024-05-21 | Sumit Constrcution
6 | 2/3 | DA+3 | Wet Paddy | 2024-05-22 | 41.37 | Completed |  |  |  | 2024-05-28 | Sumit Constrcution
7 | 39/10 | DA+0 | Wet Paddy | 2024-05-28 | 37.64 | Completed |  |  |  | 2024-06-04 | Dharamdas Contractor
8 | 17/4 | DA+3 | Wet Paddy | 2024-05-31 | 41.37 | Completed |  |  |  | 2024-06-03 | Sumit Constrcution
9 | 17/5 | DA+3 | Wet Paddy | 2024-05-31 | 41.37 | Completed |  |  |  | 2024-06-06 | Sumit Constrcution
10 | 17/3 | DA+0 | Wet Paddy | 2024-06-04 | 37.64 | Completed |  |  |  | 2024-06-09 | Sumit Constrcution
11 | 39/8 | DA+0 | Wet Paddy | 2024-06-04 | 37.64 | Completed |  |  |  | 2024-06-08 | Dharamdas Contractor
12 | 6/2 | DA+3 | Sandy | 2024-06-06 | 49.03 | Completed |  |  |  | 2024-06-12 | Khalil Const.
13 | 17/6 | DA-3 | Wet Paddy | 2024-06-07 | 37.64 | Completed |  |  |  | 2024-06-11 | Sumit Constrcution
14 | 39/9 | DA+3 | Wet Paddy | 2024-06-08 | 41.37 | Completed |  |  |  | 2024-06-13 | Dharamdas Contractor
15 | 17/7 | DA+3 | Wet Paddy | 2024-06-10 | 41.37 | Completed |  |  |  | 2024-06-14 | Sumit Constrcution
16 | 39/7 | DA+3 | Wet Paddy | 2024-06-12 | 41.37 | Completed |  |  |  | 2024-06-19 | Dharamdas Contractor
17 | 39/1 | DA+3 | Wet Paddy | 2024-06-13 | 41.37 | Completed |  |  |  | 2024-06-23 | Anshika con.
18 | 20/6 | DA+0 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-22 | Khalil Const.
19 | 17/8 | DA-3 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-17 | Sumit Constrcution
20 | 17/1 | DA-3 | Wet Paddy | 2024-06-13 | 37.64 | Completed |  |  |  | 2024-06-20 | Sumit Constrcution
21 | 39/6 | DA+3 | Wet Paddy | 2024-06-20 | 41.37 | Completed |  |  |  | 2024-06-25 | Dharamdas Contractor
22 | 20/7 | DA-3 | Wet Paddy | 2024-06-21 | 37.64 | Completed |  |  |  | 2024-06-27 | Khalil Const.
23 | 38/11 | DA+3 | Sandy | 2024-06-22 | 49.03 | Completed |  |  |  | 2024-06-30 | Anshika con.
24 | 38/1 | DA+3 | Sandy | 2024-07-01 | 49.03 | Completed |  |  |  | 2024-07-11 | Anshika con.
25 | 20/12 | DA-3 | Wet Paddy | 2024-07-08 | 37.64 | Completed |  |  |  | 2024-07-15 | Jay Sri Ram
26 | 38/2 | DA+3 | Sandy | 2024-07-11 | 49.03 | Completed |  |  |  | 2024-07-18 | Anshika con.
27 | 19/11 | DA-3 | Wet Paddy | 2024-07-12 | 37.64 | Completed |  |  |  | 2024-07-23 | K R Associates
28 | 14/5 | DA+3 | Wet Paddy | 2024-07-13 | 41.37 | Completed |  |  |  | 2024-07-20 | SSR engineering
29 | 38/3 | DA+3 | Sandy | 2024-07-15 | 49.03 | Completed |  |  |  | 2024-07-25 | Anshika con.
30 | 38/4 | DA+3 | WET | 2024-07-20 | 61.06 | Completed |  |  |  | 2024-07-31 | Anshika con.
31 | 19/8 | DA-3 | Wet Paddy | 2024-07-20 | 37.64 | Completed |  |  |  | 2024-07-30 | Jay Sri Ram
32 | 20/8 | DA+0 | Wet Paddy | 2024-07-20 | 37.64 | Completed |  |  |  | 2024-07-29 | VH Rajpoot cont.
33 | 14/6 | DA+3 | Wet Paddy | 2024-07-22 | 41.37 | Completed |  |  |  | 2024-07-28 | SSR engineering
34 | 19/9 | DA+3 | Wet Paddy | 2024-07-28 | 41.37 | Completed |  |  |  | 2024-08-04 | K R Associates
35 | 14/4 | DA+3 | Wet Paddy | 2024-07-28 | 41.37 | Completed |  |  |  | 2024-08-09 | SSR engineering
36 | 20/9 | DA+3 | Wet Paddy | 2024-07-30 | 41.37 | Completed |  |  |  | 2024-08-03 | VH Rajpoot cont.
37 | 36/12 | DA+0 | Sandy | 2025-08-01 | 46.16 | Completed |  |  |  | 2024-08-08 | Anshika con.
38 | 20/5 | DA+3 | Wet Paddy | 2024-08-05 | 41.37 | Completed |  |  |  | 2024-08-10 | VH Rajpoot cont.
39 | 36/11 | DA-3 | Wet Paddy | 2024-08-08 | 37.64 | Completed |  |  |  | 2024-08-14 | Anshika con.
40 | 14/3 | DA+0 | Wet Paddy | 2024-08-10 | 37.64 | Completed |  |  |  | 2024-08-21 | SSR engineering
41 | 23/3 | DA-3 | Wet Paddy | 2024-08-12 | 37.64 | Completed |  |  |  | 2024-08-18 | VH Rajpoot cont.
42 | 19/12 | DA-3 | Wet Paddy | 2024-08-12 | 37.64 | Completed |  |  |  | 2024-08-24 | K R Associates
43 | 12/9 | DA+3 | Wet Paddy | 2024-08-16 | 41.37 | Completed |  |  |  | 2024-08-31 | VED ENTTERPRISE
44 | 23/4 | DA-3 | Wet Paddy | 2024-08-23 | 37.64 | Completed |  |  |  | 2024-08-31 | VH Rajpoot cont.
45 | 36/3 | DA+3 | Wet Paddy | 2024-08-23 | 41.37 | Completed |  |  |  | 2024-08-31 | J M Enterprise
46 | 14/7 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-08-30 | SSR engineering
47 | 36/7 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-09 | SAIFI CON.
48 | 38/8 | DA+3 | WET | 2024-08-24 | 61.06 | Completed |  |  |  | 2024-09-08 | A V I ENTERPRISE
49 | 19/1 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-30 | MALLIK CON
50 | 19/3 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-05 | Garg Construction
51 | 19/2 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-22 | Shree Krishna
52 | 36/6 | DA+3 | Wet Paddy | 2024-08-24 | 41.37 | Completed |  |  |  | 2024-09-20 | SAIFI CON.
53 | 45/3 | DA-3 | WET | 2024-08-24 | 58.51 | Completed |  |  |  | 2024-09-08 | Vinayak Enterprise
54 | 50/1 | DA+0 | Wet Paddy | 2024-08-24 | 37.64 | Completed |  |  |  | 2024-09-11 | Vishal construction
55 | 39/4 | DA+3 | WET | 2024-08-29 | 61.06 | Completed |  |  |  | 2024-09-08 | Dharamdas Contractor
56 | 20/1 | DA+6 | Wet Paddy | 2024-08-30 | 41.37 | Completed |  |  |  | 2024-09-22 | K R Associates
57 | 12/8 | DA-3 | Wet Paddy | 2024-09-01 | 37.64 | Completed |  |  |  | 2024-09-09 | VED ENTTERPRISE
58 | 12/4 | DA+3 | Wet Paddy | 2024-09-01 | 41.37 | Completed |  |  |  | 2024-09-08 | SSR engineering
59 | 12/2 | DA+3 | Wet Paddy | 2024-09-08 | 41.37 | Completed |  |  |  | 2024-09-24 | SSR engineering
60 | 23/5 | DA-3 | Wet Paddy | 2024-09-08 | 37.64 | Completed |  |  |  | 2024-09-11 | VH Rajpoot cont.
61 | 30/3 | DA+0 | Wet Paddy | 2024-09-08 | 37.64 | Completed |  |  |  | 2024-09-22 | Garg Construction
62 | 41/1 | DA+0 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-09-20 | Dharamdas Contractor
63 | 36/10 | DA-3 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-09-30 | J M Enterprise
64 | 45/2 | DA+3 | Wet Paddy | 2024-09-09 | 41.37 | Completed |  |  |  | 2024-09-29 | Vinayak Enterprise
65 | 23/2 | DA+0 | Wet Paddy | 2024-09-11 | 37.64 | Completed |  |  |  | 2024-09-20 | VH Rajpoot cont.
66 | 30/6 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-24 | Laxmi Const.
67 | 35/2 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-26 | A V I ENTERPRISE
68 | 41/2 | DA+3 | Wet Paddy | 2024-09-19 | 41.37 | Completed |  |  |  | 2024-09-26 | Dharamdas Contractor
69 | 36/9 | DA-3 | Wet Paddy | 2024-09-19 | 37.64 | Completed |  |  |  | 2024-09-24 | SAIFI CON.
70 | 36/5 | DA+0 | Wet Paddy | 2024-09-20 | 37.64 | Completed |  |  |  | 2024-09-26 | J M Enterprise
71 | 25/1 | DA+9 | Wet Paddy | 2024-09-22 | 41.37 | Completed |  |  |  | 2024-09-26 | VH Rajpoot cont.
72 | 30/4 | DA+3 | Wet Paddy | 2024-09-22 | 41.37 | Completed |  |  |  | 2024-09-30 | Garg Construction
73 | 12/6 | DA-3 | Wet Paddy | 2024-09-23 | 37.64 | Completed |  |  |  | 2024-09-30 | VED ENTTERPRISE
74 | 12/1 | DA-3 | Wet Paddy | 2024-09-25 | 37.64 | Completed |  |  |  | 2024-09-30 | SSR engineering
75 | 23/1 | DA+9 | Wet Paddy | 2024-09-26 | 41.37 | Completed |  |  |  | 2024-09-30 | VH Rajpoot cont.
76 | 12/7 | DA-3 | Wet Paddy | 2024-09-27 | 37.64 | Completed |  |  |  | 2024-10-06 | VED ENTTERPRISE
77 | 46/1 | DA+0 | Wet Paddy | 2024-09-09 | 37.64 | Completed |  |  |  | 2024-10-10 | Vinayak Enterprise
78 | 35/1 | DA+3 | Wet Paddy | 2024-09-20 | 41.37 | Completed |  |  |  | 2024-10-01 | Maa Durga
79 | 46/2 | DA+3 | Wet Paddy | 2024-09-25 | 41.37 | Completed |  |  |  | 2024-10-03 | Vishal construction
80 | 36/8 | DA-3 | Wet Paddy | 2024-09-26 | 37.64 | Completed |  |  |  | 2024-10-06 | SAIFI CON.
81 | 34/7 | DA+3 | Wet Paddy | 2024-09-26 | 41.37 | Completed |  |  |  | 2024-10-03 | Aneshwar Traders
82 | 35/3 | DA+0 | Wet Paddy | 2024-09-27 | 37.64 | Completed |  |  |  | 2024-10-01 | A V I ENTERPRISE
83 | 25/2 | DA+0 | Wet Paddy | 2024-10-01 | 37.64 | Completed |  |  |  | 2024-10-04 | VH Rajpoot cont.
84 | 12/3 | DA+3 | Wet Paddy | 2024-10-01 | 41.37 | Completed |  |  |  | 2024-10-07 | SSR engineering
85 | 30/2 | DA-3 | Wet Paddy | 2024-10-01 | 37.64 | Completed |  |  |  | 2024-10-07 | Garg Construction
86 | 31/2 | DA+0 | Wet Paddy | 2024-10-03 | 37.64 | Completed |  |  |  | 2024-10-07 | Laxmi Const.
87 | 25/3 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-08 | VH Rajpoot cont.
88 | 35/9 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-10 | A V I ENTERPRISE
89 | 39/5 | DA-3 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-08 | Dharamdas Contractor
90 | 34/6 | DA+0 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-08 | Aneshwar Traders
91 | 34/3 | DA+3 | Wet Paddy | 2024-10-04 | 41.37 | Completed |  |  |  | 2024-10-10 | Maa Durga
92 | 34/4 | DA-3 | Wet Paddy | 2024-10-04 | 37.64 | Completed |  |  |  | 2024-10-10 | M A Construction
93 | 31/1 | DA+0 | Wet Paddy | 2024-10-08 | 37.64 | Completed |  |  |  | 2024-10-10 | Laxmi Const.
94 | 34/2 | DA+3 | Wet Paddy | 2024-10-08 | 41.37 | Completed |  |  |  | 2024-10-13 | Aneshwar Traders
95 | 12/5 | DA+3 | Wet Paddy | 2024-10-10 | 41.37 | Completed |  |  |  | 2024-10-13 | SSR engineering
96 | 4/2 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | VED ENTTERPRISE
97 | 31/8 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | VH Rajpoot cont.
98 | 30/1 | DA-3 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-14 | Garg Construction
99 | 30/5 | DA+0 | Wet Paddy | 2024-10-10 | 37.64 | Completed |  |  |  | 2024-10-16 | Laxmi Const.
100 | 20/2 | DA+0 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-21 | K R Associates
101 | 36/2 | DA+0 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-16 | SAIFI CON.
102 | 35/8 | DA-3 | Wet Paddy | 2024-10-12 | 37.64 | Completed |  |  |  | 2024-10-21 | A V I ENTERPRISE
103 | 52/9 | DA-3 | WET | 2024-10-13 | 58.51 | Completed |  |  |  | 2024-10-22 | Dharamdas Contractor
104 | 14/2 | DA+0 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-20 | SSR engineering
105 | 33/11 | DA+3 | Wet Paddy | 2024-10-13 | 41.37 | Completed |  |  |  | 2024-10-18 | Aneshwar Traders
106 | 33/1 | DA-3 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-16 | M A Construction
107 | 34/1 | DA+3 | Wet Paddy | 2024-10-13 | 41.37 | Completed |  |  |  | 2024-10-21 | Maa Durga
108 | 31/10 | DA-3 | Wet Paddy | 2024-10-13 | 37.64 | Completed |  |  |  | 2024-10-18 | VH Rajpoot cont.
109 | 31/3 | DA+3 | Wet Paddy | 2024-10-16 | 41.37 | Completed |  |  |  | 2024-10-20 | Laxmi Const.
110 | 33/2 | DA-3 | Wet Paddy | 2024-10-16 | 37.64 | Completed |  |  |  | 2024-10-20 | M A Construction
111 | 4/3 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-23 | VED ENTTERPRISE
112 | 8B/3 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-26 | Garg Construction
113 | 28/1 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | J M Enterprise
114 | 31/9 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | VH Rajpoot cont.
115 | 33/5 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | Vinayak Enterprise
116 | 33/10 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-23 | Aneshwar Traders
117 | 36/1 | DA+3 | Wet Paddy | 2024-10-17 | 41.37 | Completed |  |  |  | 2024-10-24 | SAIFI CON.
118 | 7/10 | DA+3 | Wet Paddy | 2024-10-19 | 41.37 | Completed |  |  |  | 2024-10-25 | Vivan Enterprise
119 | 14/1 | DA+0 | Wet Paddy | 2024-10-21 | 37.64 | Completed |  |  |  | 2024-10-24 | SSR engineering
120 | 31/5 | DA-3 | Wet Paddy | 2024-10-22 | 37.64 | Completed |  |  |  | 2024-10-25 | Laxmi Const.
121 | 33/3 | DA+3 | Wet Paddy | 2024-10-22 | 41.37 | Completed |  |  |  | 2024-10-26 | M A Construction
122 | 33/9 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-26 | Aneshwar Traders
123 | 35/7 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-10-26 | A V I ENTERPRISE
124 | 4/4 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-27 | VED ENTTERPRISE
125 | 7/11 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-10-27 | Vivan Enterprise
126 | 14/8 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-11-01 | SSR engineering
127 | 31/6 | DA+3 | Wet Paddy | 2024-10-24 | 41.37 | Completed |  |  |  | 2024-11-01 | Laxmi Const.
128 | 31/7 | DA+0 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-11-01 | VH Rajpoot cont.
129 | 52/10 | DA+3 | WET | 2024-10-24 | 61.06 | Completed |  |  |  | 2024-11-01 | Dharamdas Contractor
130 | 20/4 | DA-3 | Wet Paddy | 2024-10-24 | 37.64 | Completed |  |  |  | 2024-11-01 | K R Associates
131 | 35/4 | DA+0 | Wet Paddy | 2024-10-25 | 37.64 | Completed |  |  |  | 2024-11-10 | Maa Durga
132 | 33/4 | DA-3 | Wet Paddy | 2024-10-25 | 37.64 | Completed |  |  |  | 2024-11-02 | M A Construction
133 | 35/5 | DA+3 | Wet Paddy | 2024-10-25 | 41.37 | Completed |  |  |  | 2024-11-02 | A V I ENTERPRISE
134 | 8B/1 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-05 | Garg Construction
135 | 20/0 | DB1+0 | Wet Paddy | 2024-11-03 | 58.25 | Completed |  |  |  | 2024-11-13 | J M Enterprise
136 | 7/9 | DA+0 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-11 | Vivan Enterprise
137 | 20/3 | DA+0 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-13 | K R Associates
138 | 31/4 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-09 | Laxmi Const.
139 | 8B/2 | DA-3 | Wet Paddy | 2024-11-03 | 37.64 | Completed |  |  |  | 2024-11-13 | Garg Construction
140 | 33/8 | DA+3 | Wet Paddy | 2024-11-03 | 41.37 | Completed |  |  |  | 2024-11-11 | Aneshwar Traders
141 | 33/6 | DA+3 | Wet Paddy | 2024-11-03 | 41.37 | Completed |  |  |  | 2024-11-08 | Vinayak Enterprise
142 | 34/0 | DB1+0 | Wet Paddy | 2024-11-03 | 58.25 | Completed |  |  |  | 2024-11-09 | M A Construction
143 | 19/7 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-13 | VH Rajpoot cont.
144 | 17/2 | DA+0 | Wet Paddy | 2024-11-06 | 37.64 | Completed |  |  |  | 2024-11-10 | SSR engineering
145 | 19/4 | DA+0 | Wet Paddy | 2024-11-06 | 37.64 | Completed |  |  |  | 2024-11-11 | VH Rajpoot cont.
146 | 7/8 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-15 | Vivan Enterprise
147 | 33/7 | DA+3 | Wet Paddy | 2024-11-06 | 41.37 | Completed |  |  |  | 2024-11-15 | Aneshwar Traders
148 | 32/0 | DC1+6 | Wet Paddy | 2024-11-08 | 71.04 | Completed |  |  |  | 2024-11-16 | Laxmi Const.
149 | 10/1 | DA-3 | Wet Paddy | 2024-11-09 | 37.64 | Completed |  |  |  | 2024-11-18 | SSR engineering
150 | 19/5 | DA-3 | Wet Paddy | 2024-11-10 | 37.64 | Completed |  |  |  | 2024-11-18 | VH Rajpoot cont.
151 | 39/3 | DA+3 | PS | 2024-11-12 | 71.43 | Completed |  |  |  | 2024-11-20 | M A Construction
152 | 8B/4 | DA+6 | Wet Paddy | 2024-11-14 | 41.37 | Completed |  |  |  | 2024-11-21 | Garg Construction
153 | 4/8 | DA+0 | Wet Paddy | 2024-11-14 | 37.64 | Completed |  |  |  | 2024-11-21 | R K Constrcution
154 | 33/0 | DC2+6 | Wet Paddy | 2024-11-14 | 77.81 | Completed |  |  |  | 2024-11-21 | Aneshwar Traders
155 | 19/6 | DA+0 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-21 | VH Rajpoot cont.
156 | 36/4 | DA+0 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-21 | Maa Durga
157 | 54/1 | DA+9 | PS | 2024-11-16 | 71.43 | Completed |  |  |  | 2024-11-23 | Dharamdas Contractor
158 | 21/0 | DB1+0 | Wet Paddy | 2024-11-18 | 58.25 | Completed |  |  |  | 2024-11-22 | J M Enterprise
159 | 8/3 | DA-3 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-22 | A V I ENTERPRISE
160 | 20/11 | DA-3 | Wet Paddy | 2024-11-18 | 37.64 | Completed |  |  |  | 2024-11-24 | K R Associates
161 | 38/6 | DA+3 | PS | 2024-11-20 | 71.43 | Completed |  |  |  | 2024-11-29 | Vinayak Enterprise
162 | 39/2 | DA-3 | Wet Paddy | 2024-11-22 | 37.64 | Completed |  |  |  | 2024-11-26 | M A Construction
163 | 35/0 | DC1+0 | Wet Paddy | 2024-11-22 | 70.25 | Completed |  |  |  | 2024-11-29 | Aneshwar Traders
164 | 36/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-11-27 | SAIFI CON.
165 | 8/4 | DA+9 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-27 | A V I ENTERPRISE
166 | 4/7 | DA+3 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | R K Constrcution
167 | 8B/5 | DA+6 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | Garg Construction
168 | 7/3 | DA-3 | Wet Paddy | 2024-11-22 | 37.64 | Completed |  |  |  | 2024-11-26 | Laxmi Const.
169 | 7/2 | DA+3 | Wet Paddy | 2024-11-22 | 41.37 | Completed |  |  |  | 2024-11-29 | Laxmi Const.
170 | 10/0 | DB1+9 | Wet Paddy | 2024-11-22 | 58.25 | Completed |  |  |  | 2024-11-30 | SSR engineering
171 | 31/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-11-29 | VH Rajpoot cont.
172 | 54/2 | DA-3 | PS | 2024-11-20 | 68.85 | Completed |  |  |  | 2024-12-01 | Dharamdas Contractor
173 | 39/0 | DB2+0 | Wet Paddy | 2024-11-22 | 65.714 | Completed |  |  |  | 2024-12-02 | M A Construction
174 | 8/2 | DA+0 | Wet Paddy | 2024-11-25 | 37.64 | Completed |  |  |  | 2024-12-03 | A V I ENTERPRISE
175 | 26/0 | DB2+9 | Wet Paddy | 2024-11-29 | 65.912 | Completed |  |  |  | 2024-12-04 | VH Rajpoot cont.
176 | 7/1 | DA+0 | Wet Paddy | 2024-11-30 | 37.64 | Completed |  |  |  | 2024-12-04 | Laxmi Const.
177 | 4/5 | DA+3 | Wet Paddy | 2024-11-30 | 41.37 | Completed |  |  |  | 2024-12-06 | R K Constrcution
178 | 5/1 | DA+3 | Wet Paddy | 2024-12-03 | 41.37 | Completed |  |  |  | 2024-12-09 | J M Enterprise
179 | 7/4 | DA+0 | Wet Paddy | 2024-12-03 | 37.64 | Completed |  |  |  | 2024-12-09 | Laxmi Const.
180 | 7/7 | DA+0 | Wet Paddy | 2024-12-03 | 37.64 | Completed |  |  |  | 2024-12-09 | Garg Construction
181 | 8/1 | DA+3 | Wet Paddy | 2024-12-03 | 41.37 | Completed |  |  |  | 2024-12-09 | A V I ENTERPRISE
182 | 17/0 | DB2+6 | Wet Paddy | 2024-12-03 | 65.912 | Completed |  |  |  | 2024-12-09 | SSR engineering
183 | 3/0 | DC2+0 | Wet Paddy | 2024-12-04 | 77.07 | Completed |  |  |  | 2024-12-10 | VH Rajpoot cont.
184 | 56/5 | DA-3 | WET | 2024-12-04 | 58.51 | Completed |  |  |  | 2024-12-10 | Aneshwar Traders
185 | 38/10 | DA-3 | WET | 2024-12-01 | 58.51 | Completed |  |  |  | 2024-12-11 | Maa Durga
186 | 55/1 | DA-3 | WET | 2024-12-02 | 58.51 | Completed |  |  |  | 2024-12-11 | Dharamdas Contractor
187 | 7/5 | DA+3 | Wet Paddy | 2024-12-09 | 41.37 | Completed |  |  |  | 2024-12-13 | Laxmi Const.
188 | 49/0 | DC2+9 | WET | 2024-12-09 | 113.26 | Completed |  |  |  | 2024-12-15 | M A Construction
189 | 4/9 | DA-3 | Wet Paddy | 2024-12-09 | 37.64 | Completed |  |  |  | 2024-12-16 | R K Constrcution
190 | 7/6 | DA+0 | Wet Paddy | 2024-12-09 | 37.64 | Completed |  |  |  | 2024-12-16 | Garg Construction
191 | 6/1 | DA+3 | Wet Paddy | 2024-12-09 | 41.37 | Completed |  |  |  | 2024-12-16 | J M Enterprise
192 | 4/0 | DD45+0 | Wet Paddy | 2024-12-09 | 94.55 | Completed |  |  |  | 2024-12-17 | VH Rajpoot cont.
193 | 56/8 | DA-3 | PS | 2024-12-09 | 68.85 | Completed |  |  |  | 2024-12-17 | Aneshwar Traders
194 | 38/7 | DA-3 | PS | 2024-12-09 | 68.85 | Completed |  |  |  | 2024-12-17 | Vinayak Enterprise
195 | 52/7 | DA+6 | PS | 2024-12-09 | 71.43 | Completed |  |  |  | 2024-12-18 | SAIFI CON.
196 | 7/0 | DB2+0 | Wet Paddy | 2024-12-10 | 65.714 | Completed |  |  |  | 2024-12-20 | Laxmi Const.
197 | 8/0 | DB2+0 | Wet Paddy | 2024-12-10 | 65.714 | Completed |  |  |  | 2024-12-20 | A V I ENTERPRISE
198 | 48/1 | DA-3 | Wet Paddy | 2024-12-15 | 37.64 | Completed |  |  |  | 2024-12-20 | M A Construction
199 | 47/0 | DC2+9 | Wet Paddy | 2024-12-10 | 77.81 | Completed |  |  |  | 2024-12-21 | Maa Durga
200 | 56/1 | DA+0 | WET | 2024-12-10 | 58.51 | Completed |  |  |  | 2024-12-22 | Dharamdas Contractor
201 | 9/0 | DB2+6 | Wet Paddy | 2024-12-10 | 65.912 | Completed |  |  |  | 2024-12-24 | VH Rajpoot cont.
202 | 4/10 | DA+3 | Wet Paddy | 2024-12-17 | 41.37 | Completed |  |  |  | 2024-12-24 | R K Constrcution
203 | 52/8 | DA-3 | Wet Paddy | 2024-12-19 | 37.64 | Completed |  |  |  | 2024-12-27 | SAIFI CON.
204 | 6/0 | DB1+0 | Wet Paddy | 2024-12-20 | 58.25 | Completed |  |  |  | 2024-12-27 | J M Enterprise
205 | 56/7 | DA+6 | PS | 2024-11-20 | 71.43 | Completed |  |  |  | 2024-12-27 | Aneshwar Traders
206 | 46/0 | DB2+0 | Wet Paddy | 2024-12-18 | 65.714 | Completed |  |  |  | 2024-12-28 | Vinayak Enterprise
207 | 4/6 | DA+0 | Wet Paddy | 2024-12-23 | 37.64 | Completed |  |  |  | 2024-12-31 | R K Constrcution
208 | 54/0 | DB1+3 | WET | 2024-12-23 | 82.51 | Completed |  |  |  | 2024-12-31 | Dharamdas Contractor
209 | 53A/5 | DA-3 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-02 | A K Rajpoot
210 | 64/1 | DA+0 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-02 | M A Construction
211 | 15/0 | DC2+3 | Wet Paddy | 2024-12-17 | 77.81 | Completed |  |  |  | 2025-01-03 | SSR engineering
212 | 38/9 | DA-3 | WET | 2024-11-24 | 58.51 | Completed |  |  |  | 2025-01-03 | Maa Durga
213 | 8A/0 | DD60+0 | Wet Paddy | 2024-11-20 | 169.71 | Completed |  |  |  | 2025-01-09 | Garg Construction
214 | 5/0 | DB1+0 | Wet Paddy | 2024-12-29 | 58.25 | Completed |  |  |  | 2025-01-09 | J M Enterprise
215 | 53A/0 | DB2+0 | WET | 2025-01-03 | 95.47 | Completed |  |  |  | 2025-01-10 | Laxmi Const.
216 | 53A/4 | DA+3 | WET | 2025-01-03 | 61.06 | Completed |  |  |  | 2025-01-11 | A K Rajpoot
217 | 56/0 | DD45+0 | WET | 2025-01-03 | 139.03 | Completed |  |  |  | 2025-01-11 | Aneshwar Traders
218 | 64/2 | DA+3 | PS | 2025-01-03 | 71.43 | Completed |  |  |  | 2025-01-11 | M A Construction
219 | 52/0 | DC2+9 | Wet Paddy | 2025-01-03 | 77.81 | Completed |  |  |  | 2025-01-11 | Vinayak Enterprise
220 | 48/0 | DD45+9 | Wet Paddy | 2025-01-04 | 94.55 | Completed |  |  |  | 2025-01-12 | Maa Durga
221 | 28/0 | DD60+0 | FS | 2024-12-28 | 326.62 | Completed |  |  |  | 2025-01-12 | VH Rajpoot cont.
222 | 8B/0 | DD60+0 | Wet Paddy | 2024-12-26 | 169.71 | Completed |  |  |  | 2025-01-14 | A V I ENTERPRISE
223 | 19/10 | DA+3 | Wet Paddy | 2025-01-10 | 41.37 | Completed |  |  |  | 2025-01-14 | SSR engineering
224 | 53/0 | DC1+0 | WET | 2025-01-03 | 98.56 | Completed |  |  |  | 2025-01-15 | SAIFI CON.
225 | 53A/2 | DA+3 | WET | 2025-01-10 | 61.06 | Completed |  |  |  | 2025-01-18 | Laxmi Const.
226 | 52/3 | DA-3 | Wet Paddy | 2025-01-12 | 37.64 | Completed |  |  |  | 2025-01-20 | Vinayak Enterprise
227 | 20/10 | DA+3 | Wet Paddy | 2025-01-10 | 41.37 | Completed |  |  |  | 2025-01-20 | Garg Construction
228 | 55/0 | DC1+0 | PS | 2025-01-04 | 111.17 | Completed |  |  |  | 2025-01-22 | Dharamdas Contractor
229 | 53A/6 | DA+3 | WET | 2025-01-12 | 61.06 | Completed |  |  |  | 2025-01-23 | A K Rajpoot
230 | 51/0 | DD60+0 | Wet paddy | 2025-01-12 | 169.71 | Completed |  |  |  | 2025-01-24 | M A Construction
231 | 53A/3 | DA-3 | WET | 2025-01-18 | 58.51 | Completed |  |  |  | 2025-01-25 | Laxmi Const.
232 | 27/0 | DD60+3 | FS | 2025-01-14 | 331.82 | Completed |  |  |  | 2025-01-29 | VH Rajpoot cont.
233 | 45/1 | DA+3 | Wet Paddy | 2025-01-21 | 41.37 | Completed |  |  |  | 2025-01-30 | Maa Durga
234 | 21/3 | DA+3 | Wet Paddy | 2025-01-25 | 41.37 | Completed |  |  |  | 2025-01-31 | A K Rajpoot
235 | 52/6 | DA+3 | WET | 2025-01-21 | 61.06 | Completed |  |  |  | 2025-01-31 | SAIFI CON.
236 | 57/0 | DB2+0 | PS | 2025-01-15 | 119.635 | Completed |  |  |  | 2025-01-31 | Aneshwar Traders
237 | 0/2 | DA-3 | Wet Paddy | 2025-01-23 | 37.64 | Completed |  |  |  | 2025-01-31 | SSR engineering
238 | 0/3 | DA-3 | Wet Paddy | 2025-01-24 | 37.64 | Completed |  |  |  | 2025-01-31 | Garg Construction
239 | 53/1 | DA+6 | WET | 2025-01-26 | 61.06 | Completed |  |  |  | 2025-02-03 | Laxmi Const.
240 | 24/0 | DD60+25 | Wet Paddy | 2025-01-18 | 165.36 | Completed |  |  |  | 2025-02-04 | A V I ENTERPRISE
241 | 42/0 | DD60+18 | Wet Paddy | 2025-01-23 | 165.36 | Completed |  |  |  | 2025-02-05 | Dharamdas Contractor
242 | 35/6 | DA+0 | Wet Paddy | 2025-02-01 | 37.64 | Completed |  |  |  | 2025-02-06 | Maa Durga
243 | 22/0 | DB2+3 | Wet Paddy | 2025-02-01 | 65.912 | Completed |  |  |  | 2025-02-07 | A K Rajpoot
244 | 56/2 | DA+3 | WET | 2025-02-01 | 61.06 | Completed |  |  |  | 2025-02-07 | R K Constrcution
245 | 0/4 | DA+9 | Wet Paddy | 2025-02-01 | 41.37 | Completed |  |  |  | 2025-02-09 | Garg Construction
246 | 29/0 | DD60+25 | Wet Paddy | 2025-01-30 | 165.36 | Completed |  |  |  | 2025-02-09 | VH Rajpoot cont.
247 | 52/4 | DA-3 | WET | 2025-02-01 | 58.51 | Completed |  |  |  | 2025-02-10 | Vinayak Enterprise
248 | 52/5 | DA-3 | WET | 2025-02-02 | 58.51 | Completed |  |  |  | 2025-02-15 | SAIFI CON.
249 | 40/0 | DD60+25 2mtr RC | Wet Paddy | 2025-02-02 | 173.792 | Completed |  |  |  | 2025-02-15 | Aneshwar Traders
250 | 59/0 | DD60+6 | WET | 2025-02-02 | 253.37 | Completed |  |  |  | 2025-02-15 | M A Construction
251 | 0/1 | DA-3 | WET | 2025-02-02 | 58.51 | Completed |  |  |  | 2025-02-15 | SSR engineering
252 | 22A/0 | DB1+25 | WET | 2025-02-09 | 85.98 | Completed |  |  |  | 2025-02-17 | A K Rajpoot
253 | 25/0 | DD60+25 | Wet Paddy | 2025-02-06 | 165.36 | Completed |  |  |  | 2025-02-18 | A V I ENTERPRISE
254 | 64/0 | DC1+0 | WET | 2025-02-06 | 98.56 | Completed |  |  |  | 2025-02-18 | Laxmi Const.
255 | 53A/7 | DA+0 | Wet Paddy | 2025-02-10 | 37.64 | Completed |  |  |  | 2025-02-20 | Maa Durga
256 | 30/0 | DD60+18 | Wet Paddy | 2025-02-10 | 165.36 | Completed |  |  |  | 2025-02-21 | VH Rajpoot cont.
257 | 52/2 | DA+3 | WET | 2025-02-11 | 61.06 | Completed |  |  |  | 2025-02-21 | Vinayak Enterprise
258 | 43/0 | DD60+9,2mtr RC | Wet Paddy | 2025-02-06 | 177.252 | Completed |  |  |  | 2025-02-21 | Dharamdas Contractor
259 | 4/1 | DA+3 Normal leg A,B | Wet Paddy | 2025-02-10 | 20.685 | Completed |  |  |  | 2025-02-22 | Garg Construction
| 4/1 | DA+3, 2mtr RC(C,D) | Wet Paddy | 2025-02-10 | 27.165 | Completed |  |  |  | 2025-02-22 | Garg Construction
260 | 56/3 | DA-3 | WET | 2025-02-10 | 58.51 | Completed |  |  |  | 2025-02-23 | R K Constrcution
261 | 41/0 | DD60+18,2mtr RC | Wet Paddy | 2025-02-16 | 173.792 | Completed |  |  |  | 2025-02-25 | Aneshwar Traders
262 | 63/0 | DC1+3 | WET | 2025-02-19 | 100.37 | Completed |  |  |  | 2025-02-27 | Laxmi Const.
263 | 11/0 | DB1+18 | Wet Paddy | 2025-02-19 | 59.55 | Completed |  |  |  | 2025-02-28 | SSR engineering
264 | 58/0 | DD60+18 | WET | 2025-02-19 | 243.46 | Completed |  |  |  | 2025-02-28 | M A Construction
265 | 53A/1 | DA+6 | WET | 2025-02-20 | 61.06 | Completed |  |  |  | 2025-02-28 | SAIFI CON.
266 | 21/2 | DA+3 | Wet Paddy | 2025-02-26 | 41.37 | Completed |  |  |  | 2025-02-28 | VH Rajpoot cont.
267 | 13/0 | DD60+30 | Wet Paddy | 2025-02-26 | 165.36 | Completed |  |  |  | 2025-03-03 | A K Rajpoot
268 | 50/0 | DC1+18 | Wet Paddy | 2025-02-26 | 90.44 | Completed |  |  |  | 2025-03-04 | Maa Durga
269 | 23/0 | DC2+18 | Wet Paddy | 2025-03-01 | 100.19 | Completed |  |  |  | 2025-03-08 | VH Rajpoot cont.
270 | 60/0 | DD45+6 | WET | 2025-02-27 | 141.75 | Completed |  |  |  | 2025-03-08 | Laxmi Const.
271 | 14/0 | DD60+30 | Wet Paddy | 2025-03-04 | 165.36 | Completed |  |  |  | 2025-03-09 | A K Rajpoot
272 | 34/5 | DA+0 | Wet Paddy | 2025-03-04 | 37.64 | Completed |  |  |  | 2025-03-09 | Maa Durga
273 | 12/0 | DB2+18 | Wet Paddy | 2025-03-01 | 68.11 | Completed |  |  |  | 2025-03-10 | Garg Construction
274 | 56/4 | DA-3 | WET | 2025-03-01 | 58.51 | Completed |  |  |  | 2025-03-11 | R K Constrcution
275 | 61/0 | DD60+30 | WET | 2025-03-01 | 243.46 | Completed |  |  |  | 2025-03-20 | M A Construction
276 | 67/0 | DD60+30 | WET | 2025-03-01 | 243.46 | Completed |  |  |  | 2025-03-20 | Aneshwar Traders
277 | 52/1 | DB1+6 | WET | 2025-03-01 | 82.51 | Completed |  |  |  | 2025-03-22 | Vinayak Enterprise
278 | 18/0 | DB1+6 | Wet Paddy | 2025-03-20 | 58.25 | Completed |  |  |  | 2025-03-25 | A K Rajpoot
279 | 64/3 | DA-3 | WET | 2025-03-20 | 58.51 | Completed |  |  |  | 2025-03-26 | Laxmi Const.
280 | 66/1 | DA+0 | WET | 2025-03-20 | 58.51 | Completed |  |  |  | 2025-03-26 | SAIFI CON.
281 | 62/0 | DC1+25 | WET | 2025-03-20 | 132.23 | Completed |  |  |  | 2025-03-27 | M A Construction
282 | 19/0 | DC2+6 | Wet Paddy | 2025-03-25 | 77.81 | Completed |  |  |  | 2025-03-30 | A K Rajpoot
283 | 57/1 | DA-3 | WET | 2025-03-25 | 58.51 | Completed |  |  |  | 2025-04-02 | Maa Durga
284 | 56/6 | DA+0 | WET | 2025-03-25 | 58.51 | Completed |  |  |  | 2025-04-02 | R K Constrcution
285 | 21/1 | DA-3 | Wet Paddy | 2025-03-31 | 37.64 | Completed |  |  |  | 2025-04-03 | A K Rajpoot
286 | 66/0 A,B | DD60+0 | FS | 2025-03-25 | 163.31 | Completed |  |  |  | 2025-04-10 | Dharamdas Contractor
| 66/0 C,D | DD60+0, 1mtr RC | FS | 2025-03-25 | 164.495 | Completed |  |  |  | 2025-04-10 | Dharamdas Contractor
287 | 16/0 | DB2+25 | Wet Paddy | 2025-04-04 | 68.11 | Completed |  |  |  | 2025-04-10 | A K Rajpoot
288 | 68/0 | DD60+30 | WET | 2025-04-04 | 243.46 | Completed |  |  |  | 2025-04-17 | Aneshwar Traders
289 | 2/1 | DA+3 | WET | 2025-04-17 | 61.06 | Completed |  |  |  | 2025-04-21 | VH Rajpoot cont.
290 | 44/0 | DD60+3 | FS | 2025-04-04 | 331.82 | Completed |  |  |  | 2025-04-21 | Laxmi Const.
291 | 1/0 | DC1+3 | Wet Paddy | 2025-04-22 | 71.04 | Completed |  |  |  | 2025-04-27 | VH Rajpoot cont.
292 | 65/0 | DD60+0 | FS | 2025-04-11 | 326.62 | Completed |  |  |  | 2025-04-28 | Dharamdas Contractor
293 | 2/0 | DD45+3 | Wet Paddy | 2025-04-22 | 94.55 | Completed |  |  |  | 2025-04-29 | A V I ENTERPRISE
294 | 70/0 | DD60+0 | WET | 2025-04-17 | 249.38 | Completed |  |  |  | 2025-04-30 | SAIFI CON.
295 | 2/2 | DA+0 | Wet Paddy | 2025-04-27 | 37.64 | Completed |  |  |  | 2025-04-30 | VH Rajpoot cont.
296 | 45/0 | DD60+0 | FS | 2025-04-25 | 326.62 | Completed |  |  |  | 2025-05-11 | Laxmi Const.
297 | 38/5 | DA+3 | WET | 2025-05-05 | 61.06 | Completed |  |  |  | 2025-05-11 | VH Rajpoot cont.
298 | 0/0 | DCT+0 | WET | 2025-05-05 | 118.54 | Completed |  |  |  | 2025-05-17 | A V I ENTERPRISE
299 | 69/0 | DC2+0 | WET | 2025-05-06 | 110.03 | Completed |  |  |  | 2025-05-19 | SAIFI CON.
300 | 37/0 | DC2+18 | FS | 2025-05-11 | 261.196 | Completed |  |  |  | 2025-05-23 | VH Rajpoot cont.
301 | 69A/0 | DD60+0 | WET | 2025-05-14 | 249.38 | Completed |  |  |  | 2025-05-28 | Aneshwar Traders
302 | 38/0 | DC2+18 | FS | 2025-05-20 | 261.196 | Completed |  |  |  | 2025-06-03 | A V I ENTERPRISE
SL No. | Location No. | Tower Type | Classification | Start Date | MT | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 2/8 | DA+0 |  | 2024-09-01 | 43.7758 | COMPLETED |  |  |  | 2024-09-16 | Dewi Construction(Girendra)
2 | 2/4 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED |  |  |  | 2024-09-29 | Dewi Construction(Girendra)
3 | 39/10 | DA+0 |  | 2024-09-16 | 43.7758 | COMPLETED |  |  |  | 2024-10-01 | Horil Mahto
4 | 20/8 | DA+0 |  | 2024-10-01 | 43.7758 | COMPLETED |  |  |  | 2024-10-07 | Dewi Construction(Girendra)
5 | 39/8 | DA+0 |  | 2024-10-03 | 43.7758 | COMPLETED |  |  |  | 2024-10-15 | Horil Mahto
6 | 20/6 | DA+0 |  | 2024-10-08 | 43.7758 | COMPLETED |  |  |  | 2024-10-13 | Dewi Construction(Girendra)
7 | 20/9 | DA+3 |  | 2024-10-14 | 46.0492 | COMPLETED |  |  |  | 2024-10-19 | Dewi Construction(Girendra)
8 | 39/7 | DA+3 |  | 2024-10-15 | 46.0492 | COMPLETED |  |  |  | 2024-10-24 | Horil Mahto
9 | 20/5 | DA+3 |  | 2024-10-20 | 46.0492 | COMPLETED |  |  |  | 2024-10-24 | Dewi Construction(Girendra)
10 | 20/7 | DA-3 |  | 2024-10-24 | 42.3742 | COMPLETED |  |  |  | 2024-10-29 | Dewi Construction(Girendra)
11 | 39/9 | DA+3 |  | 2024-10-24 | 46.0492 | COMPLETED |  |  |  | 2024-10-31 | Horil Mahto
12 | 20/12 | DA-3 |  | 2024-11-01 | 42.3742 | COMPLETED |  |  |  | 2024-11-04 | Dewi Construction(Girendra)
13 | 14/6 | DA+3 |  | 2024-11-05 | 46.0492 | COMPLETED |  |  |  | 2024-11-10 | Dewi Construction(Girendra)
14 | 39/6 | DA+3 |  | 2024-11-01 | 46.0492 | COMPLETED |  |  |  | 14.11.2024 | Horil Mahto
15 | 14/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-17 | Dewi Construction(Girendra)
16 | 14/4 | DA+3 |  | 2024-11-17 | 46.0492 | COMPLETED |  |  |  | 2024-11-22 | Dewi Construction(Girendra)
17 | 2/5 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-24 | Pankaj
18 | 19/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-26 | Reeta Bharti
19 | 6/2 | DA+3 |  | 2024-11-14 | 46.0492 | COMPLETED |  |  |  | 2024-11-25 | Pinky Dewi
20 | 38/3 | DA+3 |  | 2024-11-10 | 46.0492 | COMPLETED |  |  |  | 2024-11-25 | Horil Mahto
21 | 14/8 | DA+3 |  | 2024-11-22 | 46.0492 | COMPLETED |  |  |  | 2024-11-28 | Dewi Construction(Girendra)
22 | 41/1 | DA+0 |  | 2024-11-10 | 43.7758 | COMPLETED |  |  |  | 2024-11-29 | Amar Singh
23 | 2/7 | DA+3 |  | 2024-11-26 | 46.0492 | COMPLETED |  |  |  | 2024-12-03 | Pankaj
24 | 19/2 | DA+0 |  | 2024-11-28 | 43.7758 | COMPLETED |  |  |  | 2024-12-05 | Reeta Bharti
25 | 14/7 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED |  |  |  | 2024-12-05 | Dewi Construction(Girendra)
26 | 4/3 | DA+3 |  | 2024-11-28 | 46.0492 | COMPLETED |  |  |  | 2024-12-05 | Pinky Dewi
27 | 36/12 | DA+0 |  | 2024-11-29 | 43.7758 | COMPLETED |  |  |  | 2024-12-06 | Horil Mahto
28 | 2/6 | DA+0 |  | 2024-12-01 | 43.7758 | COMPLETED |  |  |  | 2024-12-09 | Pankaj
29 | 41/2 | DA+3 |  | 2024-11-30 | 46.0492 | COMPLETED |  |  |  | 2024-12-10 | Amar Singh
30 | 14/3 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-12 | Dewi Construction(Girendra)
31 | 4/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-12 | Pinky Dewi
32 | 19/4 | DA+0 |  | 2024-12-06 | 43.7758 | COMPLETED |  |  |  | 2024-12-13 | Reeta Bharti
33 | 2/3 | DA+3 |  | 2024-12-10 | 46.0492 | COMPLETED |  |  |  | 2024-12-16 | Pankaj
34 | 4/2 | DA-3 |  | 2024-12-12 | 42.3742 | COMPLETED |  |  |  | 2024-12-16 | Pinky Dewi
35 | 14/2 | DA+0 |  | 2024-12-12 | 43.7758 | COMPLETED |  |  |  | 2024-12-17 | Dewi Construction(Girendra)
36 | 38/2 | DA+3 |  | 2024-12-06 | 46.0492 | COMPLETED |  |  |  | 2024-12-19 | Horil Mahto
37 | 45/3 | DA-3 |  | 2024-12-10 | 42.3742 | COMPLETED |  |  |  | 2024-12-20 | Amar Singh
38 | 19/1 | DA+0 |  | 2024-12-13 | 43.7758 | COMPLETED |  |  |  | 2024-12-21 | Reeta Bharti
39 | 4/8 | DA+0 |  | 2024-12-17 | 43.7758 | COMPLETED |  |  |  | 2024-12-22 | Pinky Dewi
40 | 14/1 | DA+0 |  | 2024-12-18 | 43.7758 | COMPLETED |  |  |  | 2024-12-23 | Dewi Construction(Girendra)
41 | 7/10 | DA+3 |  | 2024-12-18 | 46.0492 | COMPLETED |  |  |  | 2024-12-23 | Pankaj
42 | 45/2 | DA+3 |  | 2024-12-21 | 46.0492 | COMPLETED |  |  |  | 2024-12-27 | Amar Singh
43 | 19/5 | DA-3 |  | 2024-12-22 | 42.3742 | COMPLETED |  |  |  | 2024-12-27 | Reeta Bharti
44 | 4/7 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED |  |  |  | 2024-12-27 | Pinky Dewi
45 | 7/9 | DA+0 |  | 2024-12-24 | 43.7758 | COMPLETED |  |  |  | 2024-12-30 | Pankaj
46 | 38/4 | DA+3 |  | 2024-12-20 | 46.0492 | COMPLETED |  |  |  | 2024-12-31 | Horil Mahto
47 | 17/1 | DA-3 |  | 2024-12-24 | 42.3742 | COMPLETED |  |  |  | 2024-12-31 | Dewi Construction(Girendra)
48 | 31/3 | DA+3 |  | 2024-12-24 | 46.0492 | COMPLETED |  |  |  | 2025-01-03 | ASC heights
49 | 4/5 | DA+3 |  | 2024-12-28 | 46.0492 | COMPLETED |  |  |  | 2025-01-03 | Pinky Dewi
50 | 46/1 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED |  |  |  | 2025-01-04 | Amar Singh
51 | 7/2 | DA+3 |  | 2024-12-31 | 46.0492 | COMPLETED |  |  |  | 2025-01-07 | Pankaj
52 | 19/6 | DA+0 |  | 2024-12-28 | 43.7758 | COMPLETED |  |  |  | 2025-01-08 | Reeta Bharti
53 | 17/4 | DA+3 |  | 2025-01-01 | 46.0492 | COMPLETED |  |  |  | 2025-01-10 | Dewi Construction(Girendra)
54 | 31/4 | DA-3 |  | 2025-01-04 | 42.3742 | COMPLETED |  |  |  | 2025-01-11 | ASC heights
55 | 12/2 | DA+3 |  | 2025-01-03 | 46.0492 | COMPLETED |  |  |  | 2025-01-11 | Pinky Dewi
56 | 7/8 | DA+3 |  | 2025-01-08 | 46.0492 | COMPLETED |  |  |  | 2025-01-14 | Pankaj
57 | 36/3 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED |  |  |  | 2025-01-15 | Amar Singh
58 | 38/1 | DA+3 |  | 2025-01-07 | 46.0492 | COMPLETED |  |  |  | 2025-01-17 | Horil Mahto
59 | 19/7 | DA+3 |  | 2025-01-09 | 46.0492 | COMPLETED |  |  |  | 2025-01-17 | Reeta Bharti
60 | 17/3 | DA+0 |  | 2025-01-10 | 43.7758 | COMPLETED |  |  |  | 2025-01-17 | Dewi Construction(Girendra)
61 | 31/2 | DA+0 |  | 2025-01-11 | 43.7758 | COMPLETED |  |  |  | 2025-01-19 | ASC heights
62 | 12/3 | DA+3 |  | 2025-01-12 | 46.0492 | COMPLETED |  |  |  | 2025-01-21 | Pinky Dewi
63 | 7/7 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED |  |  |  | 2025-01-22 | Pankaj
64 | 17/2 | DA+0 |  | 2025-01-17 | 43.7758 | COMPLETED |  |  |  | 2025-01-23 | Dewi Construction(Girendra)
65 | 36/5 | DA+0 |  | 2025-01-15 | 43.7758 | COMPLETED |  |  |  | 2025-01-24 | Amar Singh
66 | 31/6 | DA+3 |  | 2025-01-20 | 46.0492 | COMPLETED |  |  |  | 2025-01-25 | ASC heights
67 | 12/4 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED |  |  |  | 2025-01-25 | Pinky Dewi
68 | 19/9 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED |  |  |  | 2025-01-27 | Reeta Bharti
69 | 35/1 | DA+3 |  | 2025-01-16 | 46.0492 | COMPLETED |  |  |  | 2025-01-28 | Horil Mahto
70 | 17/5 | DA+3 |  | 2025-01-24 | 46.0492 | COMPLETED |  |  |  | 2025-01-29 | Dewi Construction(Girendra)
71 | 7/6 | DA+0 |  | 2025-01-21 | 43.7758 | COMPLETED |  |  |  | 2025-01-30 | Pankaj
72 | 36/1 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED |  |  |  | 2025-01-30 | Amar Singh
73 | 33/10 | DA+3 |  | 2025-01-21 | 46.0492 | COMPLETED |  |  |  | 2025-01-31 | Rudra Construction
74 | 12/5 | DA+3 |  | 2025-01-25 | 46.0492 | COMPLETED |  |  |  | 2025-02-01 | Pinky Dewi
75 | 31/1 | DA+0 |  | 2025-01-25 | 43.7758 | COMPLETED |  |  |  | 2025-02-02 | ASC heights
76 | 17/7 | DA+3 |  | 2025-01-30 | 46.0492 | COMPLETED |  |  |  | 2025-02-05 | Dewi Construction(Girendra)
77 | 20/0 | DB+0 |  | 2025-01-28 | 64.4817 | COMPLETED |  |  |  | 2025-02-06 | Reeta Bharti
78 | 36/2 | DA+0 |  | 2025-02-02 | 43.7758 | COMPLETED |  |  |  | 2025-02-07 | Amar Singh | 27
79 | 12/9 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED |  |  |  | 2025-02-08 | Pinky Dewi
80 | 7/5 | DA+3 |  | 2025-01-29 | 46.0492 | COMPLETED |  |  |  | 2025-02-09 | Pankaj
81 | 31/7 | DA+0 |  | 2025-02-03 | 43.7758 | COMPLETED |  |  |  | 2025-02-10 | ASC heights | 23
82 | 35/0 | DC+0 |  | 2025-01-29 | 73.4258 | COMPLETED |  |  |  | 2025-02-11 | Horil Mahto
83 | 33/11 | DA+3 |  | 2025-02-02 | 46.0492 | COMPLETED |  |  |  | 2025-02-12 | Rudra Construction
84 | 21/0 | DB+0 |  | 2025-02-06 | 64.4817 | COMPLETED |  |  |  | 2025-02-13 | Dewi Construction(Girendra)
85 | 20/2 | DA+0 |  | 2025-02-07 | 43.7758 | COMPLETED |  |  |  | 2025-02-13 | Reeta Bharti
86 | 35/9 | DA+3 |  | 2025-02-08 | 46.0492 | COMPLETED |  |  |  | 2025-02-15 | Amar Singh
87 | 8/1 | DA+3 |  | 2025-02-09 | 46.0492 | COMPLETED |  |  |  | 2025-02-15 | Pinky Dewi
88 | 7/4 | DA+0 |  | 2025-02-10 | 43.7758 | COMPLETED |  |  |  | 2025-02-18 | Pankaj
89 | 20/3 | DA+0 |  | 2025-02-12 | 43.7758 | COMPLETED |  |  |  | 2025-02-19 | Reeta Bharti
90 | 31/9 | DA+3 |  | 2025-02-11 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | ASC heights
91 | 34/7 | DA+3 |  | 2025-02-12 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | Horil Mahto
92 | 33/6 | DA+3 |  | 2025-02-14 | 46.0492 | COMPLETED |  |  |  | 2025-02-20 | Dewi Construction(Girendra)
93 | 8/2 | DA+0 |  | 2025-02-16 | 43.7758 | COMPLETED |  |  |  | 2025-02-21 | Pinky Dewi
94 | 35/7 | DA+3 |  | 2025-02-16 | 46.0492 | COMPLETED |  |  |  | 2025-02-21 | Amar Singh
95 | 33/9 | DA+0 |  | 2025-02-14 | 43.7758 | COMPLETED |  |  |  | 2025-02-22 | Rudra Construction
96 | 20/4 | DA-3 |  | 2025-02-20 | 42.3742 | COMPLETED |  |  |  | 2025-02-25 | Reeta Bharti
97 | 33/7 | DA+3 |  | 2025-02-21 | 46.0492 | COMPLETED |  |  |  | 2025-02-25 | Dewi Construction(Girendra)
98 | 7/1 | DA+0 |  | 2025-02-19 | 43.7758 | COMPLETED |  |  |  | 2025-02-25 | Pankaj
99 | 34/6 | DA+0 |  | 2025-02-21 | 43.7758 | COMPLETED |  |  |  | 2025-02-27 | Horil Mahto
100 | 35/4 | DA+0 |  | 2025-02-20 | 43.7758 | COMPLETED |  |  |  | 2025-02-27 | Amar Singh
101 | 31/0 | DB+0 |  | 2025-02-19 | 64.4817 | COMPLETED |  |  |  | 2025-02-28 | ASC heights
102 | 8/0 | DB+0 |  | 2025-02-22 | 64.4817 | COMPLETED |  |  |  | 2025-02-28 | Pinky Dewi
103 | 33/3 | DA+3 |  | 2025-02-26 | 46.0492 | COMPLETED |  |  |  | 2025-03-02 | Dewi Construction(Girendra)
104 | 35/5 | DA+3 |  | 2025-02-27 | 46.0492 | COMPLETED |  |  |  | 2025-03-03 | Amar Singh
105 | 4/10 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-05 | Reeta Bharti
106 | 33/8 | DA+3 |  | 2025-03-03 | 46.0492 | COMPLETED |  |  |  | 2025-03-07 | Dewi Construction(Girendra)
107 | 7/0 | DB+0 |  | 2025-02-27 | 64.4817 | COMPLETED |  |  |  | 2025-03-08 | Pankaj
108 | 7/11 | DA+0 |  | 2025-03-01 | 43.7758 | COMPLETED |  |  |  | 2025-03-08 | Pinky Dewi
109 | 35/3 | DA+0 |  | 2025-02-28 | 43.7758 | COMPLETED |  |  |  | 2025-03-08 | Horil Mahto
110 | 30/4 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-09 | ASC heights
111 | 34/1 | DA+3 |  | 2025-03-01 | 46.0492 | COMPLETED |  |  |  | 2025-03-11 | Rudra Construction
112 | 33/4 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED |  |  |  | 2025-03-11 | Dewi Construction(Girendra)
113 | 8/3 | DA-3 |  | 2025-03-08 | 42.3742 | COMPLETED |  |  |  | 2025-03-12 | Pinky Dewi
114 | 5/0 | DB+0 |  | 2025-03-01 | 64.4817 | COMPLETED |  |  |  | 2025-03-13 | Reeta Bharti
115 | 30/5 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED |  |  |  | 2025-03-16 | ASC heights
116 | 35/6 | DA+0 |  | 2025-03-10 | 43.7758 | COMPLETED |  |  |  | 2025-03-18 | Horil Mahto
117 | 33/1 | DA-3 |  | 2025-03-12 | 42.3742 | COMPLETED |  |  |  | 2025-03-18 | Dewi Construction(Girendra)
118 | 6/1 | DA+3 |  | 2025-03-09 | 46.0492 | COMPLETED |  |  |  | 2025-03-19 | Pankaj
119 | 8/4 | DA+9 |  | 2025-03-13 | 55.3387 | COMPLETED |  |  |  | 2025-03-21 | Pinky Dewi
120 | 5/1 | DA+3 |  | 2025-03-16 | 46.0492 | COMPLETED |  |  |  | 2025-03-21 | Reeta Bharti
121 | 31/8 | DA-3 |  | 2025-03-16 | 42.3742 | COMPLETED |  |  |  | 2025-03-23 | ASC heights
122 | 33/2 | DA-3 |  | 2025-03-19 | 42.3742 | COMPLETED |  |  |  | 2025-03-23 | Dewi Construction(Girendra)
123 | 8B/1 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED |  |  |  | 2025-03-26 | Pinky Dewi
124 | 7/3 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED |  |  |  | 2025-03-27 | Pankaj
125 | 6/0 | DB+0 |  | 2025-03-22 | 64.4817 | COMPLETED |  |  |  | 2025-03-29 | Reeta Bharti
126 | 35/2 | DA-3 |  | 2025-03-20 | 42.3742 | COMPLETED |  |  |  | 2025-03-30 | Horil Mahto
127 | 31/10 | DA-3 |  | 2025-03-24 | 42.3742 | COMPLETED |  |  |  | 2025-03-30 | ASC heights
128 | 34/0 | DB+0 |  | 2025-03-24 | 64.4817 | COMPLETED |  |  |  | 2025-03-31 | Dewi Construction(Girendra)
129 | 38/8 | DA+3 |  | 2025-03-21 | 46.0492 | COMPLETED |  |  |  | 2025-03-31 | M K infra
130 | 35/8 | DA-3 |  | 2025-03-22 | 42.3742 | COMPLETED |  |  |  | 2025-03-31 | Amar Singh
131 | 39/3 | DA+3 |  | 2025-03-24 | 46.0492 | COMPLETED |  |  |  | 2025-03-31 | Ananya Traders-1
132 | 8B/5 | DA+6 |  | 2025-03-24 | 53.3239 | COMPLETED |  |  |  | 2025-03-31 | Pinky Dewi
133 | 4/6 | DA+0 |  | 2025-03-28 | 43.7758 | COMPLETED |  |  |  | 2025-04-05 | Reeta Bharti
134 | 8B/3 | DA+3 |  | 2025-03-28 | 46.0492 | COMPLETED |  |  |  | 2025-04-07 | Pinky Dewi
135 | 20/11 | DA-3 |  | 2025-03-31 | 42.3742 | COMPLETED |  |  |  | 2025-04-08 | Gagan enterprise.1
136 | 34/4 | DA-3 |  | 2025-04-03 | 42.3742 | COMPLETED |  |  |  | 2025-04-10 | Dewi Construction(Girendra)
137 | 4/1 | DA+3 |  | 2025-03-31 | 46.0492 | COMPLETED |  |  |  | 2025-04-11 | Anand Construction
138 | 38/6 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-11 | M K infra
139 | 9/0 | DB+6 |  | 2025-04-01 | 75.8584 | COMPLETED |  |  |  | 2025-04-11 | Gagan enterprise.2
140 | 32/0 | DC+6 |  | 2025-04-01 | 87.0116 | COMPLETED |  |  |  | 2025-04-11 | ASC heights
141 | 39/1 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-12 | Ananya Traders-1
142 | 53A/4 | DA+3 |  | 2025-04-01 | 46.0492 | COMPLETED |  |  |  | 2025-04-12 | Horil Mahto
143 | 8B/2 | DA-3 |  | 2025-04-08 | 42.3742 | COMPLETED |  |  |  | 2025-04-13 | Pinky Dewi
144 | 36/0 | DB+0 |  | 2025-04-02 | 64.4817 | COMPLETED |  |  |  | 2025-04-14 | Amar Singh
145 | 20/10 | DA+3 |  | 2025-04-09 | 46.0492 | COMPLETED |  |  |  | 2025-04-15 | Gagan enterprise.1
146 | 52/6 | DA+3 |  | 2025-04-05 | 46.0492 | COMPLETED |  |  |  | 2025-04-16 | Ananya Traders-2
147 | 10/1 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-16 | Gagan enterprise.2
148 | 4/0 | DD45+0 |  | 2025-04-06 | 86.2562 | COMPLETED |  |  |  | 2025-04-17 | Reeta Bharti
149 | 39/0 | DB+0 |  | 2025-04-12 | 64.4817 | COMPLETED |  |  |  | 2025-04-19 | Ananya Traders-1
150 | 8B/4 | DA+6 |  | 2025-04-14 | 53.3239 | COMPLETED |  |  |  | 2025-04-21 | Pinky Dewi
151 | 31/5 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-21 | ASC heights
152 | 33/0 | DC+6 |  | 2025-04-12 | 87.0116 | COMPLETED |  |  |  | 2025-04-22 | Dewi Construction(Girendra)
153 | 38/7 | DA-3 |  | 2025-04-12 | 42.3742 | COMPLETED |  |  |  | 2025-04-22 | M K infra
154 | 36/6 | DA+3 |  | 2025-04-12 | 46.0492 | COMPLETED |  |  |  | 2025-04-22 | Amar Singh
155 | 20/1 | DA+6 |  | 2025-04-16 | 53.3239 | COMPLETED |  |  |  | 2025-04-22 | Gagan enterprise.1
156 | 25/2 | DA+0 |  | 2025-04-15 | 43.7758 | COMPLETED |  |  |  | 2025-04-23 | Rudra Construction
157 | 52/5 | DA-3 |  | 2025-04-17 | 42.3742 | COMPLETED |  |  |  | 2025-04-25 | Ananya Traders-2
158 | 0/4 | DA+9 |  | 2025-04-12 | 55.3387 | COMPLETED |  |  |  | 2025-04-26 | Anand Construction
159 | 19/12 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED |  |  |  | 2025-04-26 | Gagan enterprise.1
160 | 39/2 | DA-3 |  | 2025-04-20 | 42.3742 | COMPLETED |  |  |  | 2025-04-26 | Ananya Traders-1
161 | 36/7 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED |  |  |  | 2025-04-28 | Amar Singh
162 | 34/2 | DA+3 |  | 2025-04-23 | 46.0492 | COMPLETED |  |  |  | 2025-04-28 | Dewi Construction(Girendra)
163 | 10/0 | DB+9 |  | 2025-04-17 | 78.6775 | COMPLETED |  |  |  | 2025-04-28 | Gagan enterprise.2
164 | 30/6 | DA-3 |  | 2025-04-22 | 42.3742 | COMPLETED |  |  |  | 2025-04-28 | ASC heights
165 | 52/4 | DA-3 |  | 2025-04-26 | 42.3742 | COMPLETED |  |  |  | 2025-04-29 | Ananya Traders-2
166 | 38/9 | DA-3 |  | 2025-04-23 | 42.3742 | COMPLETED |  |  |  | 2025-06-01 | M K infra
167 | 8A/0 | DD60+0 |  | 2025-04-22 | 97.2286 | COMPLETED |  |  |  | 2025-04-30 | Pinky Dewi
168 | 19/11 | DA-3 |  | 2025-04-27 | 42.3742 | COMPLETED |  |  |  | 2025-04-30 | Gagan enterprise.1
169 | 34/3 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED |  |  |  | 2025-05-03 | Dewi Construction(Girendra)
170 | 39/4 | DA+3 |  | 2025-04-29 | 46.0492 | COMPLETED |  |  |  | 2025-05-04 | Ananya Traders-1
171 | 36/8 | DA-3 |  | 2025-04-29 | 42.3742 | COMPLETED |  |  |  | 2025-05-05 | Amar Singh
172 | 19/10 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED |  |  |  | 2025-05-06 | Gagan enterprise.1
173 | 30/3 | DA+0 |  | 2025-04-30 | 43.7758 | COMPLETED |  |  |  | 2025-05-06 | ASC heights
174 | 52/3 | DA-3 |  | 2025-04-30 | 42.3742 | COMPLETED |  |  |  | 2025-05-06 | Ananya Traders-2
175 | 25/3 | DA+3 |  | 2025-04-30 | 46.0492 | COMPLETED |  |  |  | 2025-05-07 | Rudra Construction
176 | 19/8 | DA-3 |  | 2025-05-06 | 42.3742 | COMPLETED |  |  |  | 2025-05-09 | Gagan enterprise.1
177 | 12/1 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED |  |  |  | 2025-05-10 | Gagan enterprise.2
178 | 4/9 | DA-3 |  | 2025-05-04 | 42.3742 | COMPLETED |  |  |  | 2025-05-11 | Reeta Bharti
179 | 39/5 | DA-3 |  | 2025-05-05 | 42.3742 | COMPLETED |  |  |  | 2025-05-11 | Ananya Traders-1
180 | 52/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED |  |  |  | 2025-05-12 | Ananya Traders-2
181 | 30/1 | DA-3 |  | 2025-05-07 | 42.3742 | COMPLETED |  |  |  | 2025-05-13 | ASC heights
182 | 36/4 | DA+0 |  | 2025-05-07 | 43.7758 | COMPLETED |  |  |  | 2025-05-13 | Amar Singh
183 | 56/2 | DA+3 |  | 2025-05-07 | 46.0492 | COMPLETED |  |  |  | 2025-05-14 | Dewi Construction(Girendra)
184 | 8B/0 | DD60+0 |  | 2025-05-05 | 97.2286 | COMPLETED |  |  |  | 2025-05-14 | Pinky Dewi
185 | 17/8 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED |  |  |  | 2025-05-15 | Gagan enterprise.1
186 | 52/9 | DA-3 |  | 2025-05-13 | 42.3742 | COMPLETED |  |  |  | 2025-05-17 | Ananya Traders-2
187 | 56/1 | DA+0 |  | 2025-05-14 | 43.7758 | COMPLETED |  |  |  | 2025-05-19 | Dewi Construction(Girendra)
188 | 36/11 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED |  |  |  | 2025-05-19 | Amar Singh
189 | 38/11 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED |  |  |  | 2025-05-19 | Ananya Traders-1
190 | 30/2 | DA-3 |  | 2025-05-14 | 42.3742 | COMPLETED |  |  |  | 2025-05-20 | ASC heights
191 | 2/1 | DA+3 |  | 2025-05-12 | 46.0492 | COMPLETED |  |  |  | 2025-05-21 | Reeta Bharti
192 | 52/10 | DA+3 |  | 2025-05-16 | 46.0492 | COMPLETED |  |  |  | 2025-05-21 | Ananya Traders-2
193 | 23/3 | DA-3 |  | 2025-05-15 | 42.3742 | COMPLETED |  |  |  | 2025-05-22 | Pinky Dewi
194 | 12/6 | DA-3 |  | 2025-05-11 | 42.3742 | COMPLETED |  |  |  | 2025-05-22 | Gagan enterprise.2
195 | 53/1 | DA+6 |  | 2025-05-12 | 53.3239 | COMPLETED |  |  |  | 2025-05-22 | Amit Const
196 | 36/9 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Amar Singh
197 | 38/10 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Ananya Traders-1
198 | 56/3 | DA-3 |  | 2025-05-20 | 42.3742 | COMPLETED |  |  |  | 2025-05-24 | Dewi Construction(Girendra)
199 | 15/0 | DC+3 |  | 2025-05-16 | 78.0732 | COMPLETED |  |  |  | 2025-05-25 | Gagan enterprise.1
200 | 23/5 | DA-3 |  | 2025-05-10 | 42.3742 | COMPLETED |  |  |  | 2025-05-27 | Rudra Construction
201 | 52/8 | DA-3 |  | 2025-05-22 | 42.3742 | COMPLETED |  |  |  | 2025-05-27 | Ananya Traders-2
202 | 23/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-28 | Pinky Dewi
203 | 0/2 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-30 | Reeta Bharti
204 | 56/4 | DA-3 |  | 2025-05-23 | 42.3742 | COMPLETED |  |  |  | 2025-05-30 | Dewi Construction(Girendra)
205 | 12/8 | DA-3 |  | 2025-05-26 | 42.3742 | COMPLETED |  |  |  | 2025-05-31 | Gagan enterprise.1
206 | 36/10 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED |  |  |  | 2025-05-31 | Amar Singh
207 | 38/5 | DA+3 |  | 2025-05-28 | 46.0492 | COMPLETED |  |  |  | 2025-06-02 | Ananya Traders-1
208 | 23/1 | DA+9 |  | 2025-05-28 | 55.3387 | COMPLETED |  |  |  | 2025-06-03 | Pinky Dewi
209 | 0/3 | DA-3 |  | 2025-05-25 | 42.3742 | COMPLETED |  |  |  | 2025-06-04 | Reeta Bharti
210 | 56/5 | DA-3 |  | 2025-05-30 | 42.3742 | COMPLETED |  |  |  | 2025-06-04 | Dewi Construction(Girendra)
211 | 51/0 | DD60+0 |  | 2025-05-27 | 97.2286 | COMPLETED |  |  |  | 2025-06-07 | Ananya Traders-2
212 | 23/2 | DA+0 |  | 2025-06-04 | 43.7758 | COMPLETED |  |  |  | 2025-06-09 | Pinky Dewi
213 | 33/5 | DA+3 |  | 2025-06-02 | 46.0492 | COMPLETED |  |  |  | 2025-06-10 | Amar Singh
214 | 0/1 | DA-3 |  | 2025-06-04 | 42.3742 | COMPLETED |  |  |  | 2025-06-11 | Reeta Bharti
215 | 50/1 | DA+0 |  | 2025-06-08 | 43.7758 | COMPLETED |  |  |  | 2025-06-13 | Ananya Traders-2
216 | 53A/5 | DA-3 |  | 2025-06-02 | 42.3742 | COMPLETED |  |  |  | 2025-06-14 | Devine
217 | 34/5 | DA+0 |  | 2025-06-12 | 43.7758 | COMPLETED |  |  |  | 2025-06-18 | Amar Singh
218 | 53A/2 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED |  |  |  | 2025-06-18 | Amit Const
219 | 22/0 | DB+3 |  | 2025-06-12 | 67.112 | COMPLETED |  |  |  | 2025-06-20 | Pinky Dewi
220 | 30/0 | DD60+18 |  | 2025-05-25 | 143.4621 | COMPLETED |  |  |  | 2025-06-21 | ASC heights
221 | 3/0 | DC+0 |  | 2025-06-12 | 73.4258 | COMPLETED |  |  |  | 2025-06-23 | Reeta Bharti
222 | 21/2 | DA+3 |  | 2025-06-21 | 46.0492 | COMPLETED |  |  |  | 2025-06-26 | Pinky Dewi
223 | 45/1 | DA+3 |  | 2025-06-10 | 46.0492 | COMPLETED |  |  |  | 2025-06-27 | M K infra
224 | 53A/3 | DA+3 |  | 2025-06-20 | 46.0492 | COMPLETED |  |  |  | 2025-06-29 | Amit Const
225 | 48/0 | DD45+9 |  | 2025-06-15 | 104.8666 | COMPLETED |  |  |  | 2025-06-29 | Ananya Traders-2
226 | 12/7 | DA-3 |  | 2025-06-24 | 42.3742 | COMPLETED |  |  |  | 2025-06-30 | Reeta Bharti
227 | 21/1 | DA-3 |  | 2025-06-27 | 42.3742 | COMPLETED |  |  |  | 2025-06-30 | Pinky Dewi
228 | 40/0 | DD60+25 |  | 2025-06-04 | 161.3552 | COMPLETED |  |  |  | 2025-06-30 | Ananya Traders-1
229 | 14/0 | DD60+30 |  | 2025-06-01 | 188.3779 | COMPLETED |  |  |  | 2025-06-30 | Gagan enterprise.1
230 | 28/1 | DA+3 |  | 2025-06-24 | 46.0492 | COMPLETED |  |  |  | 2025-07-05 | ASC heights
231 | 21/3 | DA+3 |  | 2025-07-01 | 46.0492 | COMPLETED |  |  |  | 2025-07-07 | Pinky Dewi
232 | 25/1 | DA+9 |  | 2025-07-01 | 55.3387 | COMPLETED |  |  |  | 2025-07-12 | Reeta Bharti
233 | 44/0 | DD60+3 |  | 2025-07-05 | 101.692 | COMPLETED |  |  |  | 2025-07-18 | Ananya Traders-1
234 | 56/0 | DD45+0 |  | 2025-06-28 | 86.2562 | COMPLETED |  |  |  | 2025-07-22 | Amar singh
235 | 28/0 | DD60+0 |  | 2025-07-08 | 97.2286 | COMPLETED |  |  |  | 2025-07-31 | Reeta Bharti
236 | 41/0 | DD60+18 |  | 2025-07-20 | 143.4621 | COMPLETED |  |  |  | 2025-08-08 | Ananya Traders-1
237 | 13/0 | DD60+30 |  | 2025-07-09 | 188.3779 | COMPLETED |  |  |  | 2025-08-11 | Gagan enterprise.1
238 | 53A/6 | DA+3 |  | 2025-07-27 | 46.0492 | COMPLETED |  |  |  | 2025-08-17 | Punam Kumari
239 | 46/2 | DA+3 |  | 2025-08-14 | 46.0492 | COMPLETED |  |  |  | 2025-08-26 | Gagan enterprise.2 (Kajol)
240 | 24/0 | DD60+25 |  | 2025-07-26 | 161.3552 | COMPLETED |  |  |  | 2025-08-27 | Kongres Kumar-1
241 | 65/0 | DD60+0 |  | 2025-08-02 | 97.2286 | COMPLETED |  |  |  | 2025-08-30 | Kongres Kumar-2
242 | 18/0 | DB+6 |  | 2025-08-04 | 75.8584 | COMPLETED |  |  |  | 2025-08-30 | Sainik Trader
243 | 1/0 | DC+3 |  | 2025-08-09 | 78.0732 | COMPLETED |  |  |  | 2025-08-30 | Radha Construction
244 | 12/0 | DB+18 |  | 2025-08-12 | 97.6534 | COMPLETED |  |  |  | 2025-09-02 | Gagan enterprise.1
245 | 54/1 | DA+9 |  | 2025-08-18 | 55.3387 | COMPLETED |  |  |  | 2025-09-04 | Punam Kumari
246 | 43/0 | DD60+9 |  | 2025-08-10 | 118.4303 | COMPLETED |  |  |  | 2025-09-06 | Ananya Traders-1
247 | 16/0 | DB+25 |  | 2025-08-16 | 110.6255 | COMPLETED |  |  |  | 2025-09-14 | Amit Choudhury
248 | 11/0 | DB+18 |  | 2025-08-24 | 97.6534 | COMPLETED |  |  |  | 2025-09-14 | Gouri Shankar
249 | 2/0 | DD45+3 |  | 2025-09-03 | 89.7178 | COMPLETED |  |  |  | 2025-09-21 | Radha Construction
250 | 64/0 | DC+0 |  | 2025-08-31 | 73.4258 | COMPLETED |  |  |  | 2025-09-22 | Kongres Kumar-2
251 | 52/0 | DC+9 |  | 2025-09-05 | 90.1252 | COMPLETED |  |  |  | 2025-09-22 | Punam Kumari
252 | 47/0 | DC+9 |  | 2025-09-07 | 90.1252 | COMPLETED |  |  |  | 2025-09-22 | Ananya Traders-1
253 | 29/0 | DD60+25 |  | 2025-08-06 | 161.3552 | COMPLETED |  |  |  | 2025-09-22 | Reeta Bharti
254 | 56/8 | DA-3 |  | 2025-08-18 | 42.3742 | COMPLETED |  |  |  | 2025-09-24 | Spotyfy-3
255 | 48/1 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED |  |  |  | 2025-09-23 | Ananya trader
256 | 17/6 | DA-3 |  | 2025-09-15 | 42.3742 | COMPLETED |  |  |  | 2025-09-24 | Amit Choudhury
257 | 19/0 | DC+6 |  | 2025-08-31 | 87.0116 | COMPLETED |  |  |  | 2025-09-24 | Sainik Trader
258 | 26/0 | DB+9 |  | 2025-09-15 | 78.6775 | COMPLETED |  |  |  | 2025-09-25 | Gouri Shankar
259 | 17/0 | DB+6 |  | 2025-09-11 | 75.8584 | COMPLETED |  |  |  | 2025-09-28 | Maa Construction
260 | 25/0 | DD60+25 |  | 2025-08-28 | 161.3552 | COMPLETED |  |  |  | 2025-09-29 | Kongres Kumar-
261 | 64/3 | DA-3 |  | 2025-09-24 | 42.374 | COMPLETED |  |  |  | 2025-10-07 | Kongres Kumar-
262 | 54/0 | DB+3 |  | 2025-09-25 | 67.112 | COMPLETED |  |  |  | 2025-10-07 | Punam Kumari
263 | 46/0 | DB+0 |  | 2025-09-25 | 64.4817 | COMPLETED |  |  |  | 2025-10-08 | Amit Choudhry
264 | 63/0 | DC+3 |  | 2025-10-01 | 78.0732 | COMPLETED |  |  |  | 2025-10-12 | Mahon Mahto
265 | 27/0 | DD60+3 |  | 2025-09-22 | 101.692 | COMPLETED |  |  |  | 2025-10-12 | Reeta Bharti
266 | 53A/1 | DA+6 |  | 2025-09-18 | 53.3239 | COMPLETED |  |  |  | 2025-10-13 | Spotyfy-1
267 | 42/0 | DD60+18 |  | 2025-09-23 | 143.4621 | COMPLETED |  |  |  | 2025-10-14 | Ananya trader
268 | 50/0 | DC+18 |  | 2025-09-25 | 110.6958 | COMPLETED |  |  |  | 2025-10-14 | Punam kumari-1
269 | 53/0 | DC+0 |  | 2025-09-26 | 73.4258 | COMPLETED |  |  |  | 2025-10-14 | Sainik Trader
270 | 54/2 | DA-3 |  | 2025-10-08 | 42.3742 | COMPLETED |  |  |  | 2025-10-22 | Punam kumari-2
271 | 37/0 | DC+18 |  | 2025-09-23 | 110.6958 | Under Progress |  |  |  |  | Unity India
272 | 56/6 | DA+0 |  | 2025-09-24 | 43.7758 | Under Progress |  |  |  |  | Spotyfy-2
273 | 61/0 | DD60+30 |  | 2025-09-25 | 188.3779 | Under Progress |  |  |  |  | Mahon mahto
274 | 22A/0 | DB+25 |  | 2025-09-27 | 110.6255 | Under Progress |  |  |  |  | Gouri Shankar
275 | 0/0 | DCT+0 |  | 2025-10-03 | 97.8338 | Under Progress |  |  |  |  | Maa Construction
276 | 38/0 | DC+18 |  | 2025-10-07 | 110.6958 | Under Progress |  |  |  |  | Pankaj Kumar
277 | 69A/0 | DD60+0 |  | 2025-10-08 | 97.2286 | Under Progress |  |  |  |  | Kongres Kumar-1
278 | 45/0 | DD60+0 |  | 2025-10-09 | 97.2286 | Under Progress |  |  |  |  | Amit Choudhry
279 | 49/0 | DC+9 |  | 2025-10-15 | 90.125 | Under Progress |  |  |  |  | Punam kumari-1
280 | 55/0 | DC+0 |  | 2025-10-23 | 73.4258 | Under Progress |  |  |  |  | Punam kumari-2
281
282
283
284
285
286
Stringing
S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | Remarks
1 | AP7/0-AP8/0 | 4.8187 | COMPLETED |  |  |  | Anarul Islam
2 | AP6/0-AP7/0 | 1.2343 | COMPLETED |  |  |  | Anarul Islam
3 | AP35/0-AP36/0 | 3.9571 | COMPLETED |  |  |  | S K Infra
4 | AP8/0-AP8A/0 | 2.0167 | COMPLETED |  |  |  | Anarul Islam
5 | AP31/0-AP32/0 | 4.2837 | COMPLETED |  |  |  | S K Infra
6 | AP8A/0-AP8B/0 | 0.22361 | COMPLETED |  |  |  | Anarul Islam
7 | AP32/0-AP33/0 | 0.40717 | COMPLETED |  |  |  | S K Infra
8 | AP8B/0-AP9/0 | 2.2262 | COMPLETED |  |  |  | Anarul Islam
9 | AP33/0-AP34/0 | 4.7815 | COMPLETED |  |  |  | S K Infra
10 | AP5/0-AP6/0 | 0.72357 | COMPLETED |  |  |  | Anarul Islam
11 | AP9/0-AP10/0 | 0.28343 | COMPLETED |  |  |  | Anarul Islam
12 | AP34/0-AP35/0 | 3.1932 | COMPLETED |  |  |  | S K Infra
13 | AP4/0-AP5/0 | 4.4157 | COMPLETED |  |  |  | Anarul Islam
14 | AP14/0-AP15/0 | 3.611 | COMPLETED |  |  |  | Anarul Islam
15 | AP3/0-AP4/0 | 0.28 | COMPLETED |  |  |  | Anarul Islam
16 | AP30/0-AP31/0 | 2.75 | COMPLETED |  |  |  | S K Infra
17 | AP20/0-AP21/0 | 4.958 | COMPLETED |  |  |  | G P J con.
18 | AP36/0-AP37/0 | 4.947 | Rough sag completed |  |  |  | S K Infra
19 | AP12/0-AP13/0 | 3.919 | Rough sag completed |  |  |  | Anarul Islam
20 | AP21/0-AP22/0 | 1.606 | Insulator Hoisting |  |  |  | G P J con.
21 | AP39/0-AP40/0 | 4.431 | Rough sag completed |  |  |  | S K Infra
22
OPGW Stringing
S.No | Section | Length in MTR | Status |  |  |  | Gang Name | Gang Strength | Remarks
1 | 4/0-5/0 | 4415.75 | COMPLETED |  |  |  | B K CONSTRUCTION | 14 |  | 2025-10-14 | 2025-10-18

## Visual chart.
Visual Chart :- 765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03
[8 empty] | Project Code : TA416 | [25 empty] | Dated: |  | 2025-10-24
[11 empty] | LEGEND: |  |  |  |  | OPGW Stringing | [7 empty] | Description of Item |  |  |  |  | Total Line Qty |  |  | Total Completed |  | WIP locations |  |  | Total Balance
|  |  |  | Stringing Comp | [12 empty] | Location No.
|  | Erection Comp | [16 empty] | Stringing WIP |  |  |  |  | Foundation |  |  |  |  | 302 |  |  | 302 |  | 0 |  |  | 0
[13 empty] | TW |  |  |  | Erection Comp | [6 empty] | Earthing |  |  |  |  | 302 |  |  | 302 |  |  |  |  | 0
|  | Foundation Comp | [7 empty] | C | B | SPAN |  | C | B | [8 empty] | Erection |  |  |  |  | 302 |  |  | 270 |  | 10 |  |  | 32
[10 empty] | D | A |  |  | D | A |  | Foundation Comp | [6 empty] | Tack Welding |  |  |  |  | 302 |  |  | 158 |  |  |  |  | 144
|  | Earthing Comp | [18 empty] | Holdup location |  |  | Stringing (Rough Sag) |  |  |  |  | 114.985 |  |  | 57.4912 |  | 9 |  |  | 57.4938
[24 empty] | Stringing (Final Sag) |  |  |  |  | 114.985 |  |  | 44.1634 |  |  |  |  | 70.8216
[5 empty] | Type of Tower |  |  |  |  | TREE CUTTING CLEARANCE
|  | NH/SH Xing |  |  |  | RAILWAY Xing | [6 empty] | 132/220/400/765 Kv CROSSING |  |  | RIVER X-ING |  |  |  | Gas pipeline
|  | OPGW DRUM-1 | [21 empty] | OPGW DRUM-2
[40 empty] | 115133.98 | 301
| 0/0 |  |  |  | 0/1 |  |  |  | 0/2 |  |  |  | 0/3 |  |  | 0/4 |  |  |  | 1/0 |  |  | 2/0 |  |  | 2/1 |  |  |  | 2/2 |  |  | 2/3 |  |  |  | 2/4
| C | B | 369 |  | C | B | 367 |  | C | B | 354 |  | C | B | 381 | C | B | 450.563 |  | C | B | 245.982 | C | B | 420 | C | B | 412 |  | C | B | 413 | C | B | 415 |  | C | B | 414 | 4241.545 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| TPT+0 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DC1+3 |  |  | DD45+3 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
NH 509, Agra-Moradabad
| OPGW DRUM-2 | [19 empty] | OPGW DRUM-3
| 2/5 |  |  |  | 2/6 |  |  |  | 2/7 |  |  |  | 2/8 |  |  | 3/0 |  |  |  | 4/0 |  |  | 4/1 |  |  | 4/2 |  |  |  | 4/3 |  |  | 4/4 |  |  |  | 4/5
| C | B | 410 |  | C | B | 378 |  | C | B | 420 |  | C | B | 401.695 | C | B | 279.997 |  | C | B | 383.064 | C | B | 400.004 | C | B | 397.002 |  | C | B | 414 | C | B | 415 |  | C | B | 411 | 4309.762 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DC2+0 |  |  |  | DD45+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
[17 empty] | 220 KV SC Moradabad - Narora TL | [5 empty] | 2M RC in C&D Leg
132 KV DC LINE DISMANTLED
OPGW DRUM-3 | [20 empty] | OPGW DRUM-4
| 4/6 |  |  |  | 4/7 |  |  |  | 4/8 |  |  |  | 4/9 |  |  | 4/10 |  |  |  | 5/0 |  |  | 5/1 |  |  | 6/0 |  |  |  | 6/1 |  |  | 6/2 |  |  |  | 7/0
| C | B | 416 |  | C | B | 409.231 |  | C | B | 378.001 |  | C | B | 391 | C | B | 401.443 |  | C | B | 321 | C | B | 402.569 | C | B | 408 |  | C | B | 419 | C | B | 407.275 |  | C | B | 414 | 4367.519 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DB1+0 |  |  | DA+3 |  |  | DB1+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DB2+0
| OPGW DRUM-4 | [19 empty] | OPGW DRUM-5
| 7/1 |  |  |  | 7/2 |  |  |  | 7/3 |  |  |  | 7/4 |  |  | 7/5 |  |  |  | 7/6 |  |  | 7/7 |  |  | 7/8 |  |  |  | 7/9 |  |  | 7/10 |  |  |  | 7/11
| C | B | 419 |  | C | B | 361.097 |  | C | B | 361 |  | C | B | 404 | C | B | 424 |  | C | B | 406 | C | B | 410 | C | B | 423 |  | C | B | 409 | C | B | 425 |  | C | B | 362.65 | 4404.747 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0
| OPGW DRUM-5 | [22 empty] | OPGW DRUM-6
| 8/0 |  |  |  | 8/1 |  |  |  | 8/2 |  |  |  | 8/3 |  |  | 8/4 |  |  |  | 8A/0 |  |  | 8B/0 |  |  | 8B/1 |  |  |  | 8B/2 |  |  | 8B/3 |  |  |  | 8B/4
| C | B | 416 |  | C | B | 400 |  | C | B | 367 |  | C | B | 420 | C | B | 413.716 |  | C | B | 223.61 | C | B | 341 | C | B | 332 |  | C | B | 292.526 | C | B | 426.186 |  | C | B | 373 | 4005.038 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DB2+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DA+9 |  |  |  | DD60+0 |  |  | DD60+0 |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+6
GAIL GAS PIPE LINE
OPGW DRUM-6 | [20 empty] | OPGW DRUM-7
| 8B/5 |  |  |  | 9/0 |  |  |  | 10/0 |  |  |  | 10/1 |  |  | 11/0 |  |  |  | 12/0 |  |  | 12/1 |  |  | 12/2 |  |  |  | 12/3 |  |  | 12/4 |  |  |  | 12/5
| C | B | 461.51 |  | C | B | 283.431 |  | C | B | 426 |  | C | B | 396.092 | C | B | 312.879 |  | C | B | 418.999 | C | B | 370.199 | C | B | 424.996 |  | C | B | 404 | C | B | 428 |  | C | B | 395 | 4321.106 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+6 |  |  |  | DB2+6 |  |  |  | DB1+9 |  |  |  | DA-3 |  |  | DB1+18 |  |  |  | DB2+18 |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[6 empty] | 132 Kv S/C Sambhal-Babrala | [10 empty] | 132 KV D/C CKT-I Sambhal-Babrala
& CKT-II Sambhsal-Bisauli Line
OPGW DRUM-7 | [20 empty] | OPGW DRUM-8
| 12/6 |  |  |  | 12/7 |  |  |  | 12/8 |  |  |  | 12/9 |  |  | 13/0 |  |  |  | 14/0 |  |  | 14/1 |  |  | 14/2 |  |  |  | 14/3 |  |  | 14/4 |  |  |  | 14/5
| C | B | 318 |  | C | B | 357 |  | C | B | 385 |  | C | B | 418.776 | C | B | 319.133 |  | C | B | 436 | C | B | 395 | C | B | 306 |  | C | B | 412 | C | B | 414 |  | C | B | 420 | 4180.909 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  | DD60+30 |  |  |  | DD60+30 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
400 KV D/C Sambhal - Budaun Line
OPGW DRUM-8 | [20 empty] | OPGW DRUM-9
| 14/6 |  |  |  | 14/7 |  |  |  | 14/8 |  |  |  | 15/0 |  |  | 16/0 |  |  |  | 17/0 |  |  | 17/1 |  |  | 17/2 |  |  |  | 17/3 |  |  | 17/4 |  |  |  | 17/5
| C | B | 410 |  | C | B | 410 |  | C | B | 407.995 |  | C | B | 464.742 | C | B | 264.687 |  | C | B | 400 | C | B | 310 | C | B | 361.497 |  | C | B | 366.002 | C | B | 436.999 |  | C | B | 389.999 | 4221.921 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC2+3 |  |  | DB2+25 |  |  |  | DB2+6 |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | SH-51, Islamnagr- Bhajoi Road |  | 132 KV D/C Sahaswan-Chandausi
CGD INFRA GA LINE
OPGW DRUM-9 | [16 empty] | OPGW DRUM-10
| 17/6 |  |  |  | 17/7 |  |  |  | 17/8 |  |  |  | 18/0 |  |  | 19/0 |  |  |  | 19/1 |  |  | 19/2 |  |  | 19/3 |  |  |  | 19/4 |  |  | 19/5 |  |  |  | 19/6
| C | B | 400.999 |  | C | B | 391.999 |  | C | B | 374.07 |  | C | B | 323.03 | C | B | 343.13 |  | C | B | 392 | C | B | 407 | C | B | 412 |  | C | B | 371 | C | B | 376 |  | C | B | 421 | 4212.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  |  | DB1+6 |  |  | DC2+6 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DA-3 |  |  |  | DA+0
Ganga Express-way
OPGW DRUM-10 | [23 empty] | OPGW DRUM-11
| 19/7 |  |  |  | 19/8 |  |  |  | 19/9 |  |  |  | 19/10 |  |  | 19/11 |  |  |  | 19/12 |  |  | 20/0 |  |  | 20/1 |  |  |  | 20/2 |  |  | 20/3 |  |  |  | 20/4
| C | B | 387 |  | C | B | 364 |  | C | B | 423 |  | C | B | 335 | C | B | 343 |  | C | B | 362.453 | C | B | 433 | C | B | 393 |  | C | B | 400 | C | B | 375.659 |  | C | B | 366.466 | 4182.578 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DB1+0 |  |  | DA+6 |  |  |  | DA+0 |  |  | DA+0 |  |  |  | DA-3
OPGW DRUM-11 | [30 empty] | OPGW DRUM-12
| 20/5 |  |  |  | 20/6 |  |  |  | 20/7 |  |  |  | 20/8 |  |  | 20/9 |  |  |  | 20/10 |  |  | 20/11 |  |  | 20/12 |  |  |  | 21/0 |  |  | 21/1 |  |  |  | 21/2
| C | B | 408 |  | C | B | 372 |  | C | B | 370 |  | C | B | 400 | C | B | 426 |  | C | B | 399 | C | B | 358 | C | B | 256.857 |  | C | B | 388 | C | B | 391 |  | C | B | 394 | 4162.857 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA-3 |  |  | DA-3 |  |  |  | DB1+0 |  |  | DA-3 |  |  |  | DA+3
GAIL GAS PIPE LINE
OPGW DRUM-12 | [37 empty] | OPGW DRUM-13
| 21/3 |  |  |  | 22/0 |  |  |  | 22A/0 |  |  |  | 23/0 |  |  | 23/1 |  |  |  | 23/2 |  |  | 23/3 |  |  | 23/4 |  |  |  | 23/5 |  |  | 24/0 |  |  |  | 25/0
| C | B | 432.898 |  | C | B | 190.948 |  | C | B | 267.423 |  | C | B | 371 | C | B | 438.912 |  | C | B | 340.132 | C | B | 283.996 | C | B | 323 |  | C | B | 470.227 | C | B | 231.533 |  | C | B | 386 | 3736.069 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DB2+3 |  |  |  | DB1+25 |  |  |  | DC2+18 |  |  | DA+9 |  |  |  | DA+0 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3 |  |  | DD60+25 |  |  |  | DD60+25
|  | SH-43, |  |  |  |  | 132 Kv S/C Budaun-Chandausi Dead line | [26 empty] | 765 KV S/C Ghatampur-Hapur
Chandausi - Badaun Road | [6 empty] | 132 Kv S/C Bisauli To Chandausi
OPGW DRUM-13 | [30 empty] | OPGW DRUM-14
| 25/1 |  |  |  | 25/2 |  |  |  | 25/3 |  |  |  | 26/0 |  |  | 27/0 |  |  |  | 28/0 |  |  | 28/1 |  |  | 29/0 |  |  |  | 30/0 |  |  | 30/1 |  |  |  | 30/2
| C | B | 446 |  | C | B | 368 |  | C | B | 466.431 |  | C | B | 440.836 | C | B | 299.473 |  | C | B | 233 | C | B | 454.669 | C | B | 270.08 |  | C | B | 435 | C | B | 347 |  | C | B | 396 | 4156.489 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+9 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DB2+9 |  |  | DD60+3 |  |  |  | DD60+0 |  |  | DA+3 |  |  | DD60+25 |  |  |  | DD60+18 |  |  | DA-3 |  |  |  | DA-3
[19 empty] | Rly Crossing Single track, Chandausi-Bareilly | [8 empty] | 765 Kv S/c Ghatampur-Rampur
OPGW DRUM-14 | [16 empty] | OPGW DRUM-15
| 30/3 |  |  |  | 30/4 |  |  |  | 30/5 |  |  |  | 30/6 |  |  | 31/0 |  |  |  | 31/1 |  |  | 31/2 |  |  | 31/3 |  |  |  | 31/4 |  |  | 31/5 |  |  |  | 31/6
| C | B | 410 |  | C | B | 424 |  | C | B | 373 |  | C | B | 365.461 | C | B | 376 |  | C | B | 403 | C | B | 399 | C | B | 404 |  | C | B | 358 | C | B | 363 |  | C | B | 407 | 4282.461 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+3 |  |  |  | DA+0 |  |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA+0 |  |  | DA+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-15 | [20 empty] | OPGW DRUM-16
| 31/7 |  |  |  | 31/8 |  |  |  | 31/9 |  |  |  | 31/10 |  |  | 32/0 |  |  |  | 33/0 |  |  | 33/1 |  |  | 33/2 |  |  |  | 33/3 |  |  | 33/4 |  |  |  | 33/5
| C | B | 384 |  | C | B | 386 |  | C | B | 394 |  | C | B | 409.666 | C | B | 407.17 |  | C | B | 365 | C | B | 365 | C | B | 406 |  | C | B | 389 | C | B | 395 |  | C | B | 430 | 4330.836 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DC1+6 |  |  |  | DC2+6 |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DA-3 |  |  |  | DA+3
OPGW DRUM-16 | [23 empty] | OPGW DRUM-17
| 33/6 |  |  |  | 33/7 |  |  |  | 33/8 |  |  |  | 33/9 |  |  | 33/10 |  |  |  | 33/11 |  |  | 34/0 |  |  | 34/1 |  |  |  | 34/2 |  |  | 34/3 |  |  |  | 34/4
| C | B | 394 |  | C | B | 439.95 |  | C | B | 355.05 |  | C | B | 410 | C | B | 410 |  | C | B | 421.496 | C | B | 418 | C | B | 378 |  | C | B | 417 | C | B | 395 |  | C | B | 364 | 4402.496 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DB1+0 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-17 | [13 empty] | OPGW DRUM-18
| 34/5 |  |  |  | 34/6 |  |  |  | 34/7 |  |  |  | 35/0 |  |  | 35/1 |  |  |  | 35/2 |  |  | 35/3 |  |  | 35/4 |  |  |  | 35/5 |  |  | 35/6 |  |  |  | 35/7
| C | B | 397 |  | C | B | 419 |  | C | B | 405.228 |  | C | B | 383 | C | B | 397 |  | C | B | 345 | C | B | 389 | C | B | 416 |  | C | B | 414 | C | B | 415 |  | C | B | 404 | 4384.228 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+0 |  |  |  | DA+0 |  |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3
SH-125
Shahabad-Aonla Road
OPGW DRUM-18 | [9 empty] | OPGW DRUM-19
| 35/8 |  |  |  | 35/9 |  |  |  | 36/0 |  |  |  | 36/1 |  |  | 36/2 |  |  |  | 36/3 |  |  | 36/4 |  |  | 36/5 |  |  |  | 36/6 |  |  | 36/7 |  |  |  | 36/8
| C | B | 373 |  | C | B | 421.049 |  | C | B | 401 |  | C | B | 412 | C | B | 415 |  | C | B | 411 | C | B | 395 | C | B | 402 |  | C | B | 432 | C | B | 392.011 |  | C | B | 352.989 | 4407.049 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DB2+0 |  |  |  | DA+3 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-19 | [16 empty] | OPGW DRUM-20
| 36/9 |  |  |  | 36/10 |  |  |  | 36/11 |  |  |  | 36/12 |  |  | 37/0 |  |  |  | 38/0 |  |  | 38/1 |  |  | 38/2 |  |  |  | 38/3 |  |  | 38/4 |  |  |  | 38/5
| C | B | 361 |  | C | B | 302 |  | C | B | 310 |  | C | B | 361.31 | C | B | 475.951 |  | C | B | 399 | C | B | 426 | C | B | 408 |  | C | B | 419 | C | B | 415 |  | C | B | 415.118 | 4292.379 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA+0 |  |  | DC2+18 |  |  |  | DC2+18 |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA+3
[16 empty] | 5 Mtr Depth |  |  |  |  | 5 Mtr Depth
Ramganga River Crossing
OPGW DRUM-20 | [20 empty] | OPGW DRUM-21
| 38/6 |  |  |  | 38/7 |  |  |  | 38/8 |  |  |  | 38/9 |  |  | 38/10 |  |  |  | 38/11 |  |  | 39/0 |  |  | 39/1 |  |  |  | 39/2 |  |  | 39/3 |  |  |  | 39/4
| C | B | 400 |  | C | B | 408.002 |  | C | B | 393 |  | C | B | 353 | C | B | 383 |  | C | B | 403.723 | C | B | 398 | C | B | 402 |  | C | B | 393.003 | C | B | 436.597 |  | C | B | 376.011 | 4346.336 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA+3 |  |  | DB2+0 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DA+3
OPGW DRUM-21 | [23 empty] | OPGW DRUM-22
| 39/5 |  |  |  | 39/6 |  |  |  | 39/7 |  |  |  | 39/8 |  |  | 39/9 |  |  |  | 39/10 |  |  | 40/0 |  |  | 41/0 |  |  |  | 41/1 |  |  | 41/2 |  |  |  | 42/0
| C | B | 374.389 |  | C | B | 420.398 |  | C | B | 414.002 |  | C | B | 416.001 | C | B | 408.002 |  | C | B | 422.124 | C | B | 239.302 | C | B | 425 |  | C | B | 370 | C | B | 346.556 |  | C | B | 309.23 | 4145.004 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DA+3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DA+0 |  |  | DD60+25 |  |  | DD60+18 |  |  |  | DA+0 |  |  | DA+3 |  |  |  | DD60+18
[23 empty] | 2 M RC |  |  | 2 M RC | [10 empty] | 220 KV S/C Rampur-CB Ganj
[23 empty] | 400 Kv D/C Bareilly-Meerut | [13 empty] | 400 KV S/C Bareilly-Moradabad
OPGW DRUM-22 | [33 empty] | OPGW DRUM-23
| 43/0 |  |  |  | 44/0 |  |  |  | 45/0 |  |  |  | 45/1 |  |  | 45/2 |  |  |  | 45/3 |  |  | 46/0 |  |  | 46/1 |  |  |  | 46/2 |  |  | 47/0 |  |  |  | 48/0
| C | B | 459.669 |  | C | B | 300.001 |  | C | B | 331 |  | C | B | 422 | C | B | 395 |  | C | B | 309.881 | C | B | 331 | C | B | 421 |  | C | B | 403.606 | C | B | 358.626 |  | C | B | 388 | 4119.783 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD60+9 |  |  |  | DD60+3 |  |  |  | DD60+0 |  |  |  | DA+3 |  |  | DA+3 |  |  |  | DA-3 |  |  | DB2+0 |  |  | DA+0 |  |  |  | DA+3 |  |  | DC2+9 |  |  |  | DD45+9
| 2 M RC |  |  |  |  | NH-530, RAILWAY TRACK, | [27 empty] | 132 KV S/c CB Ganj-Meerganj
OPGW DRUM-23 | [23 empty] | OPGW DRUM-24
| 48/1 |  |  |  | 49/0 |  |  |  | 50/0 |  |  |  | 50/1 |  |  | 51/0 |  |  |  | 52/0 |  |  | 52/1 |  |  | 52/2 |  |  |  | 52/3 |  |  | 52/4 |  |  |  | 52/5
| C | B | 387.943 |  | C | B | 372.026 |  | C | B | 435 |  | C | B | 242.996 | C | B | 238.926 |  | C | B | 461 | C | B | 421 | C | B | 375 |  | C | B | 346 | C | B | 348 |  | C | B | 357 | 3984.891 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA-3 |  |  |  | DC2+9 |  |  |  | DC1+18 |  |  |  | DA+0 |  |  | DD60+0 |  |  |  | DC2+9 |  |  | DB1+6 |  |  | DA+3 |  |  |  | DA-3 |  |  | DA-3 |  |  |  | DA-3
[5 empty] | 132 KV D/C CB Ganj-Meerganj | [10 empty] | 132 KV D/C CB-GANJ - MEERGANJ T/L
OPGW DRUM-24 | [20 empty] | OPGW DRUM-25
| 52/6 |  |  |  | 52/7 |  |  |  | 52/8 |  |  |  | 52/9 |  |  | 52/10 |  |  |  | 53/0 |  |  | 53/1 |  |  | 53A/0 |  |  |  | 53A/1 |  |  | 53A/2 |  |  |  | 53A/3
| C | B | 439 |  | C | B | 378 |  | C | B | 349 |  | C | B | 392 | C | B | 409.43 |  | C | B | 428 | C | B | 403.778 | C | B | 370 |  | C | B | 441 | C | B | 375 |  | C | B | 399 | 4384.208 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA+6 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+3 |  |  |  | DC1+0 |  |  | DA+6 |  |  | DB2+0 |  |  |  | DA+6 |  |  | DA+3 |  |  |  | DA-3
OPGW DRUM-25 | [16 empty] | OPGW DRUM-26
| 53A/4 |  |  |  | 53A/5 |  |  |  | 53A/6 |  |  |  | 53A/7 |  |  | 54/0 |  |  |  | 54/1 |  |  | 54/2 |  |  | 55/0 |  |  |  | 55/1 |  |  | 56/0 |  |  |  | 56/1
| C | B | 391 |  | C | B | 392 |  | C | B | 412 |  | C | B | 385.995 | C | B | 460 |  | C | B | 360 | C | B | 366.157 | C | B | 300 |  | C | B | 307.205 | C | B | 336 |  | C | B | 409 | 4119.357 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA+3 |  |  |  | DA+0 |  |  | DB1+3 |  |  |  | DA+9 |  |  | DA-3 |  |  | DC1+0 |  |  |  | DA-3 |  |  | DD45+0 |  |  |  | DA+0
OPGW DRUM-26 | [16 empty] | OPGW DRUM-27
| 56/2 |  |  |  | 56/3 |  |  |  | 56/4 |  |  |  | 56/5 |  |  | 56/6 |  |  |  | 56/7 |  |  | 56/8 |  |  | 57/0 |  |  |  | 57/1 |  |  | 58/0 |  |  |  | 59/0
| C | B | 374 |  | C | B | 351 |  | C | B | 345 |  | C | B | 380.058 | C | B | 422 |  | C | B | 387.54 | C | B | 369 | C | B | 291 |  | C | B | 386.28 | C | B | 281.561 |  | C | B | 418.001 | 4005.44 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DA+3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  |  | DA-3 |  |  | DA+0 |  |  |  | DA+6 |  |  | DA-3 |  |  | DB2+0 |  |  |  | DA-3 |  |  | DD60+18 |  |  |  | DD60+6
400 KV S/C BAREILLY - RAMPUR T/L
OPGW DRUM-27 | [16 empty] | OPGW DRUM-28
| 60/0 |  |  |  | 61/0 |  |  |  | 62/0 |  |  |  | 63/0 |  |  | 64/0 |  |  |  | 64/1 |  |  | 64/2 |  |  | 64/3 |  |  |  | 65/0 |  |  | 66/0 |  |  |  | 66/1
| C | B | 467.857 |  | C | B | 478.067 |  | C | B | 349.189 |  | C | B | 285.978 | C | B | 395 |  | C | B | 384 | C | B | 409 | C | B | 363.017 |  | C | B | 298.042 | C | B | 387 |  | C | B | 425.359 | 4242.509 | 11
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A |  |  | D | A |  | D | A |  | D | A |  |  | D | A |  | D | A |  |  | D | A
| DD45+6 |  |  |  | DD60+30 |  |  |  | DC1+25 |  |  |  | DC1+3 |  |  | DC1+0 |  |  |  | DA+0 |  |  | DA+3 |  |  | DA-3 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | DA+0
[9 empty] | 220 KV S/C BAIKUNTHAPUR - PANTNAGAR T/L |  | 132 KV S/C DOHNA - RICHHA T/L | [21 empty] | 1M RC in C&D Leg
OPGW DRUM-28 | [30 empty] | SH-37, ELECTRIFIED, SINGLE RAILWAY TRACK
Bareilly
| 67/0 |  |  |  | 68/0 |  |  |  | 69/0 |  |  |  | 69A/0 |  |  | 70/0 |  |  |  | Gantry
| C | B | 318.405 |  | C | B | 303.77 |  | C | B | 232.6 |  | C | B | 202.46 | C | B | 127 | [21 empty] | 1184.235 | 4
| D | A |  |  | D | A |  |  | D | A |  |  | D | A |  | D | A
| DD60+30 |  |  |  | DD60+30 |  |  |  | DC2+0 |  |  |  | DD60+0 |  |  | DD60+0 |  |  |  | Gantry
400 KV D/c Bareilly-Kasipur
TW

## PENDING FDN DETAILS
765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03 ¦ BALANCE WORK DETAILS
Sl. No. | Loc. No. | Type of Tower | Village | Taluk | FDN STATUS | ROW STATUS | REMARKS
1
2
3
4
5
6
7
8
9
10
11
12

## PENDING ERE DETAILS
Sl. No. | Loc. No. | Type of Tower | FDN STATUS | ERE STATUS | ROW STATUS | REMARKS
1 | 0/0 | TPT+0 | Completed | WIP
2 | 2/2 | DA+0 | Completed
3 | 22A/0 | DB1+25 | Completed | WIP
4 | 23/0 | DC2+18 | Completed
5 | 37/0 | DC2+18 | Completed | WIP
6 | 38/0 | DC2+18 | Completed | WIP
7 | 45/0 | DD60+0 | Completed | WIP
8 | 49/0 | DC2+9 | Completed | WIP
9 | 52/1 | DB1+6 | Completed
10 | 52/7 | DA+6 | Completed
11 | 53A/0 | DB2+0 | Completed
12 | 53A/7 | DA+0 | Completed
13 | 55/0 | DC1+0 | Completed | WIP
14 | 55/1 | DA-3 | Completed
15 | 56/6 | DA+0 | Completed | WIP
16 | 56/7 | DA+6 | Completed
17 | 57/0 | DB2+0 | Completed
18 | 57/1 | DA-3 | Completed
19 | 58/0 | DD60+18 | Completed
20 | 59/0 | DD60+6 | Completed
21 | 60/0 | DD45+6 | Completed
22 | 61/0 | DD60+30 | Completed | WIP
23 | 62/0 | DC1+25 | Completed
24 | 64/1 | DA+0 | Completed
25 | 64/2 | DA+3 | Completed
26 | 66/0 | DD60+0 | Completed
27 | 66/1 | DA+0 | Completed
28 | 67/0 | DD60+30 | Completed
29 | 68/0 | DD60+30 | Completed
30 | 69/0 | DC2+0 | Completed
31 | 69A/0 | DD60+0 | Completed | WIP
32 | 70/0 | DD60+0 | Completed

## TSE-MANUAL-LT-11KV-33KV Details
765kV D/C Neemrana II Bareilly Transmission Line, WZ-05, TL-03
Sl. No | SECTION |  | Section Length | No. Of Towers B/W Angle Towers | TSE Section (In KM) | Manual Section (In KM) | LT | 11KV | 33KV
| FROM | TO
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Crossing Details
KEC INTERNATIONAL LIMITED
NOA Supply: CC/T/W-TW/DOM/A10/23/10706/NOA-1/24-101862/01 dated 07.02.24.
NOA Services: CC/T/W-TW/DOM/A10/23/10706/NOA-2/24-101862/02 dated 07.02.24.
Contract: TL03 for Neemrana-II- Bareilly (PG) 765kV D/C line - Part III associated with “Transmission system for evacuation of power from Rajasthan REZ Ph-IV (Part-1) (Bikaner Complex : 7.7GW) PART-D” through tariff based competitive bidding (TBCB) route.
STATUTORY CLEARANCE
POWER LINE CROSSING | [7 empty] | 2025-09-30
Name of the Transmission | Voltage Rating in kV | Name of Owner | Name of Nearest switching/ sub-station | (Crossing in Proposed Line Loc.No) | Proposal submission Date | Status | APPROVED Date | Remark
Moradabad To Narora | 220kv S/C & 132kv Dismental | UPPTCL |  | Loc.:-AP3 - AP4 | 2024-04-29 | Approved | 2024-07-19
Sambhal-Babrala | 132kV.S/C | UPPTCL |  | Loc.:-AP9 - AP10 | 2024-05-07 | Approved | 2024-07-18
CKT-I Sambhal-Babrala & CKT-II Sambhsal-Bisauli Line | 132kV.D/C | UPPTCL |  | Loc.:-AP11 - AP12 | 2024-05-07 | Approved | 2024-07-19
400 KV D/C Sambhal - Budaun Line | 400kV.D/C | PGCIL |  | Loc.:-AP13 - AP14 | 2024-05-07 | Approved | 2024-07-19
Sahaswan-Chandausi | 132kV.D/C | UPPTCL |  | Loc.:-AP16- AP17 | 2024-05-07 | Approved | 2024-09-30
Budaun-Chandausi Dead line & Bisauli To Chandaus | 132kv S/C dead line & 132kv S/C | UPPTCL |  | Loc.:-AP22 - AP22A | 2024-04-29 | Approved | 2025-01-23
Budaun-Sambhal | 220kV.S/C | UPPTCL |  | Loc.:-AP22A - AP23 | 2024-04-29 | Approved | 2024-09-10
Ghatampur-Hapur | 765kv S/C | PGCIL |  | Loc.:-AP24 - AP25 | 2024-04-29 | Approved | 2024-07-18
Ghatampur-Rampur | 765kv S/C | PGCIL |  | Loc.:-AP29 - AP30 | 2024-04-29 | Approved | 2024-07-18
Bareilly-Mandola | 400kV.D/C |  |  | Loc.:-AP40 - AP41 | 2024-08-07 | Approved | 2024-11-13
Lucknow-Moradabad and Rampur-CB Ganj | 400kv S/C & 220kv S/C | PGCIL & UPPTCL |  | Loc.:-AP42 - AP43 | 2024-07-29 | Approved | 2024-09-28
CB Ganj-Meerganj | 132kV.S/C | UPPTCL |  | Loc.:-AP47- AP48 | 2024-08-07 | Approved | 2024-09-28
CB Ganj-Meerganj | 132kV.D/C | UPPTCL |  | Loc.:-AP49 - AP50 | 2024-07-29 | Approved | 2024-09-28
Rampur-CB Ganj | 132kV.D/C | UPPTCL |  | Loc.:-AP51- AP52 | 2024-07-17 | Approved | 2024-09-28
Bareilly-Moradabad | 400kV.S/C | PGCIL |  | Loc.:-AP58 - AP59 | 2024-07-17 | Approved | 2024-09-28
220 KV S/C Line | 220kV.S/C | UPPTCL |  | Loc.:-AP61 - AP62 | 2024-07-17 | Approved | 2024-09-28
220 KV S/C Line | 220kV.S/C | UPPTCL |  | Loc.:-AP52 - AP63 | 2024-07-17 | Approved | 2024-09-28
Bareilly-Kasipur | 400kV.D/C | PGCIL |  | Loc.:-AP67 - AP68 | 2024-07-17 | Approved | 2024-09-28
RAILWAY CROSSING
Name of the Railway Line | Type of Gauge Broad/Metre/Narrow | Single/ Double Line | Electrified / Non-electrified | Crossing loc no of proposed line | Date of Submission | Status
| Broad Gauge | Single | Under construction | AP27-AP28 | 04.08.24 | Online submission done 15/08/24, | Approvaed | 2025-01-06
| Broad Gauge | Double |  | AP44-AP45 | 10.09.24 | Online submission done 12/09/24, | Approvaed | 2025-01-06
| Broad Gauge | Single | Electrified | AP65-AP66 | 11.10.24 | Online submission done 12/09/24, | Approvaed | 2025-02-07
NH/SH/EXPRESS WAY CROSSING
Name of the Highway Line | Type of NH | Nearest town | Nearest Village | Crossing loc no of proposed line | Date of Submission | Status
| NH-509 | Gunnaur | Kuravar | AP1-AP-2 | Submitted on 20.06.24, at Moradabad | Approved | 2025-04-04
| SH51 | Islam Nagar | Talen | AP15-AP16 | Submitted on 10.06.24, at Badaun | Approved | 2024-07-25
| Ganga Express-way |  | Padana | AP18-AP19 | Submitted at Lucknow on 03-07-24 | Approved | 2025-03-07
| SH-43 | Chandausi-Bisauli |  | 21/3-AP22 | Submitted | Approved | 2024-07-25
| SH-125 |  |  | 35/3-35/4 | Submitted on 17-07-24 | Approved | 2024-09-09
| NH-530 |  |  | AP44-AP45 | Submitted on 23-08-24 | Approved | 2025-03-25
| SH-37 |  |  | AP65-AP66 | Submitted on 29-07-24 | Approved | 2024-10-18
FOREST PROPOSAL
SL.NO. | Protected Forest | Crossing span/ area in Hac. | Detail survey submission by KEC | Planning for submission letter to DFO for joint inspection for confirmation of forest area | Date of Joint inspection with local forest department | Planning for submission of Document to powergrid from KEC | Date of proposal online submission to DFO from powergrid | Date of Joint inspection with DFO | DFO to Nodal lucknow for approval | Remark
1 | AP-1/0 to AP-2/0 | 0.1742 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | DFO not given CA land KMZ file
2 | 21/3 to AP-22/0 | 0.2594 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | CA land DGPS map submitted to Concern DFO
3 | AP-44/0 to AP-45/0 | 0.161 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL |  |  |  | Letter given to DFO Badaun for CA land of Bareilly section
4 | AP-52/0 to AP-53/0 | 0.1245 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL
5 | AP-65/0 to AP-66/0 | 0.1038 | completed | Submitted on 13-03-2024 | Completed | Submitted to PGCIL
Total PF |  | 0.8229
Scheduled for statuary clearance: Gas Pipe Line
SL.NO. | Location | Type Tower | Location | Type Tower | Submission Date | Submission from PGCIL GAS PIPE LINE AUTHORITY | Aproved Date | Clearance / NOC | Remark
1 | AP8A/0 | DD60+0 | AP8B/0 | DD60+0 | 2024-08-08 | Online submission done on 15/09/24 | 2025-01-27 | NOC 27-01-25 | GAIL
2 | 20/10 | DA+3 | 20/11 | DA-3 | 2024-07-30 |  | 2025-05-05 | NOC 05-05-25 | GAIL

## TS (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 10 | 7 | 3 | 1 | 26 | 2 | 21 | 2 | 8 | 6 | 0 | 86
|  |  |  | 1DB1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 1 | 5 | 0 | 14 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 7
|  |  |  | 1DC1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 0 | 6 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[5 empty] | 0 | 10 | 7 | 3 | 1 | 42 | 2 | 28 | 2 | 14 | 14 | 1 | 124 | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[18 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[18 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[18 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 2 | 18 | 0 | 0 | 37 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 2 | 4 | 0 | 15 | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 1 | 0 | 0 | 7 | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 2 | 20 | 0 | 0 | 52 | 0 | 26 | 0 | 15 | 11 | 1 | 127 |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[21 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[21 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[21 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DB2+3 | 417
35 | 37/1 | 1DA+3 | 409
36 | 37/2 | 1DA+0 | 432.782
37 | AP38 | 1DD60+6 | 469
38 | 38/1 | 1DA+9 | 387
39 | 38/2 | 1DA+0 | 428.876
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 394
83 | 47/1 | 1DA+3 | 419.445
84 | AP48 | 1DB2+0 | 402
85 | 48/1 | 1DA+6 | 426
86 | 48/2 | 1DA+3 | 429.059
87 | AP48A | 1DC1+0 | 336
88 | 48A/1 | 1DA+9 | 441
89 | 48A/2 | 1DA-1.5 | 324.049
90 | AP49 | 1DC1+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+6 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA+0 | 372.201
125 | AP61 | 1DC2+0 | 358.086
126 | AP62 | 1DD60+0 | 278.704
127 | AP63 | 1DD60+0 | 135.008
47836.988
| Koppal-II Gantry | GANTRY

## TS (2) (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 3 | 18 | 0 | 0 | 34 | 0 | 19 | 0 | 7 | 6 | 0 | 87 | 2
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 | 0 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4 | 0
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 | 0 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6 | 1
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2
[5 empty] | 0 | 3 | 20 | 0 | 0 | 47 | 0 | 25 | 0 | 14 | 11 | 2 | 122 |  | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[19 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[19 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[19 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total |  | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 4 | 18 | 0 | 0 | 35 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 |  | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 |  | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 3 | 0 | 0 | 7
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 4 | 20 | 0 | 0 | 50 | 0 | 25 | 0 | 15 | 11 | 2 | 127 |  |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[22 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[22 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[22 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DC2+3 | 415
35 | 37/1 | 1DA+3 | 425
36 | 37/2 | 1DA+3 | 395
37 | 37/3 | 1DA-3 | 329.074
38 | AP38 | 1DC2+0 | 390
39 | 38/1 | 1DA+3 | 444.771
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 400
83 | 47/1 | 1DA+3 | 435
84 | AP48 | 1DC1+3 | 345
85 | 48/1 | 1DA+0 | 410
86 | 48/2 | 1DA+0 | 410
87 | 48/3 | 1DA-1.5 | 320
88 | 48/4 | 1DA+6 | 400
89 | 48/5 | 1DA+9 | 410.1
90 | AP49 | 1DB2+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+9 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA-1.5 | 402.199
125 | AP61 | 1DC2+6 | 419
126 | AP62 | 1DD60+0 | 231
127 | AP63 | 1DD60+0 | 103
47661.922
GANTRY