## MASTER SHEET
| Project Code | TA-418 | Date | 2025-10-15 |  |  | SBU Head | Mr. Rajinder Gupta
| Project Name | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) |  |  | NOA Start Date | 12.03.2024 | PCH | Mr. Sivaraman N
| Client Name | Power Grid Corporation of India Limited |  |  | NOA End Date | 11.12.2025 | Regional Manager | Mr. Ajith Kumar MG
| End Date | 11.12.2025 |  |  | Planning Engineer | Mr.Ajith Jayasurya | Project Manger | Mr. Tamil Velan
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 127 | 127 | 127 | 0 | 0 | 0 | 0 | 127 | 0
Tower | No's | 127 | 127 | 122 | 0 | 0 | 5 | 3 | 127 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 47.84 | 47.84 | 47.84 | 47.84 | 0 | 0 | 0 | 0 | 0 | 47.84
Check Survey | kms | 47.84 | 47.84 | 47.84 | 47.84 | 0 | 0 | 0 | 0 | 0 | 47.84
Progress Status
Activity | Unit | Final Estimated Quantity | Cumulative L2 till Last Month | Cumulative Progress till Last Month | L2 for present Month | Plan for the Month | Today's Progress | Progress till Date for the Month | L2 till Current Month | Completed till Date | Balance Work | Under Progress | Gangs at Present | Remarks
Foundation | Nos | 127 | 127 | 115 | 0 | 12 | 0 | 0 | 127 | 115 | 12 | 0 | 0 | Team demobilised due to non availability of further work front.
Earthing | Nos | 127 |  | 110 | 0 | 17 | 0 | 1 | 0 | 111 | 16 | 0 | 0
Tower Erection | Nos | 127 | 127 | 83 | 0 | 25 | 0 | 2 | 127 | 85 | 42 | 3 | 3 | Gang-02 & 03 Left from site without prior information due to unavailability of work front.
Stringing | Km | 47.84 | 47.84 | 1.106 | 0 | 11.3 | 0 | 2.473 | 47.84 | 3.579 | 44.261 | 2.426 | 1
Sl.No | Nature of Work | GANG NAME | WIP LOCATION |  | AS ON DATE - WORK FRONT |  | REMARKS
1 | Tower Erection | M/s MDPL | 54/0 |  | 39/0
3 | Tower Erection | M/s BARKAT ALI - 02 | 60/2 |  | NIL
4 | Tower Erection | M/s TOFIT | 32/0 |  | NIL
*SUPPORT REQUIRED :
* | Required further work front for foundation works In order to sustain the manpower and Machinery.
* | Required further work front for Erection works without frequent shifting of gang In order to sustain the manpower.
* | Tree Cutting arrangements for Planned stringing stretches.
SUPPLY STATUS:
Sl. No. | Description |  | UOM | LOA Qty | As per L2 till Current Month | Supplied AS on Date | Shortfall against L2 | Balance Qty. | Remarks
1 | STUB |  | Sets | 127 | 127 | 127 | 0 | 0
2 | TOWER PARTS |  | Sets | 127 | 127 | 127 | 0 | 0
3 | Earthing Materials |  | EA | 127 | 127 | 127 | 0 | 0
4 | 7/3.66 G.S Earthwire |  | KM | 49.5 | 49.5 | 46.88 | 2.62 | 2.62 | Balance Quantity will be supplied in OCT'25
5 | Conductor - ACSR AL-59 Zebra |  | KM | 1740 | 1740 | 1601.411 | 138.589 | 138.589 | Balance Quantity will be supplied in 4th week of OCT'25
6 | 160KN CLR Insulator Supply |  | Nos | 2224 | 2224 | 2224 | 0 | 0
7 | 210KN CLR Insulator Supply |  | Nos | 3781 | 3781 | 3781 | 0 | 0
8 | OPGW supply |  | KM | 50.48 | 50.48 | 50.224 | 0.256 | 0.256
9 | Quadruple Tension String |  | Set | 468 | 468 | 468 | 0 | 0
10 | Double I Suspension String |  | Set | 528 | 528 | 528 | 0 | 0
11 | HEXAGONAL RIGID SPACER |  | Set | 1170 | 1170 | 1170 | 0 | 0
12 | Single I Suspension String (Pilot) |  | Set | 45 | 45 | 45 | 0 | 0
13 | Mid Span Comp. Joint For Cond. |  | Set | 828 | 828 | 828 | 0 | 0
14 | Spacer Damper |  | Set | 5628 | 5628 | 4992 | 636 | 636 | Balance Quantity will be supplied in OCT'25
15 | REPAIR SLEEVE FOR CONDUCTOR |  | Set | 338 | 338 | 338 | 0 | 0
16 | FLEXIBLE AL BOND |  | Set | 169 | 169 | 169 | 0 | 0
17 | Suspension Clamp E/W |  | Set | 88 | 88 | 88 | 0 | 0
18 | Vibration Damper for E/W |  | Set | 340 | 340 | 340 | 0 | 0
19 | Tension Clamp for E/W |  | Set | 81 | 81 | 81 | 0 | 0
20 | Mid Span Comp. Joint for E/W |  | Set | 26 | 26 | 26 | 0 | 0

## Progress
Supply Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Received till Last Month | Balance as per L2 | L2 Plan for Current Month | Plan for Current Month | Progress for the Month | Received till Current Month | Gap between Suppy & Cumm.L2 | Remarks
Stub | No's | 127 | 127 | 127 | 0 | 0 | 0 | 0 | 127 | 0
Tower | No's | 127 | 127 | 122 | 0 | 0 | 5 | 3 | 127 | 0
Survey Status
Activity | Unit | Final Est. Qty | L2 till Last Month | Completed till Last Month | Approved till Last Month | Balance to Submit | Approved in current month | Balance to Approve | L2 Submission Plan for Current Month | Survey Progress For current Month | Survey Completed till Current Month | Remarks
Detailed Survey | kms | 47.84 | 47.84 | 47.84 | 47.84 | 0 | 0 | 0 | 0 | 0 | 47.84
Check Survey | kms | 47.84 | 47.84 | 47.84 | 47.84 | 0 | 0 | 0 | 0 | 0 | 47.84
Foundation
S.No | Location No. | Tower Type | Classification | Start Date | Conc Volume | Status |  |  |  | End Date | Gang Name | Gang Strength | Remark
1 | 42/1 | DA+0 | DFR | 2024-06-09 | 11.42 | COMPLETED |  |  |  | 2024-06-22 | GANG - 1
2 | 42/2 | DA+0 | DFR | 2024-06-10 | 11.42 | COMPLETED |  |  |  | 2024-06-29 | GANG - 1
3 | 54/4 | DA+0 | WFR | 2024-06-29 | 16.7 | COMPLETED |  |  |  | 2024-07-11 | GANG - 1
4 | 55/1 | DA+3 | DFR | 2024-06-29 | 11.73 | COMPLETED |  |  |  | 2024-07-16 | GANG-1
5 | 40/1 | DA+0 | DFR | 2024-07-01 | 11.42 | COMPLETED |  |  |  | 2024-07-16 | GANG-2
6 | 55/2 | DA+0 | DFR | 2024-07-02 | 11.42 | COMPLETED |  |  |  | 2024-07-23 | Team - 1 (Sanjay)
7 | 41/3 | DA+0 | DFR | 2024-07-03 | 11.42 | COMPLETED |  |  |  | 2024-07-12 | GANG-2
8 | 41/2 | DA+3 | DFR | 2024-07-07 | 11.73 | COMPLETED |  |  |  | 2024-07-23 | GANG-2
9 | 40/5 | DA-3 | DFR | 2024-07-10 | 11.42 | COMPLETED |  |  |  | 2024-07-26 | Team - 3 (ATK-01)
10 | 40/2 | DA+0 | DFR | 2024-07-14 | 11.42 | COMPLETED |  |  |  | 2024-07-31 | Team - 2 (SM Constr.)
11 | 35/3 | DA-3 | DFR | 2024-07-18 | 11.42 | COMPLETED |  |  |  | 2024-08-11 | Team - 3 (ATK-01)
12 | 35/4 | DA+0 | DFR | 2024-07-18 | 11.42 | COMPLETED |  |  |  | 2024-08-06 | Team - 3 (ATK-01)
13 | 40/3 | DA+3 | DFR | 2024-07-20 | 11.73 | COMPLETED |  |  |  | 2024-08-03 | Team - 2 (SM Constr.)
14 | 54/3 | DA+3 | DFR | 2024-07-24 | 11.73 | COMPLETED |  |  |  | 2024-08-02 | Team - 1 (Sanjay)
15 | 41/4 | DA+3 | DFR | 2024-07-27 | 11.73 | COMPLETED |  |  |  | 2024-08-10 | Team - 2 (SM Constr.)
16 | 55/3 | DA+3 | DFR | 2024-07-29 | 11.73 | COMPLETED |  |  |  | 2024-08-10 | Team - 1 (Sanjay)
17 | 41/1 | DA+6 | DFR | 2024-08-03 | 11.73 | COMPLETED |  |  |  | 2024-08-26 | Team - 2 (SM Constr.)
18 | 35/6 | DA+0 | DFR | 2024-08-07 | 11.42 | COMPLETED |  |  |  | 2024-08-21 | Team - 3 (ATK-01)
19 | 35/7 | DA+9 | DFR | 2024-08-09 | 11.73 | COMPLETED |  |  |  | 2024-08-27 | Team - 3 (ATK-01)
20 | 52/1 | DA-3 | DFR | 11-08-2024 and 01-07-25 | 11.42 | COMPLETED |  |  |  | 2025-07-05 | Haque Constr.
21 | 40/4 | DA+0 | DFR | 2024-08-14 | 11.42 | COMPLETED |  |  |  | 2024-09-09 | Team - 2 (SM Constr.)
22 | 35/8 | DA+3 | DFR | 2024-08-25 | 11.73 | COMPLETED |  |  |  | 2024-09-03 | Team - 3 (ATK-01)
23 | 35/11 | DA+3 | DFR | 2024-09-02 | 11.73 | COMPLETED |  |  |  | 2024-09-10 | Team - 3 (ATK-01)
24 | 34/3 | DA+0 | DFR | 2024-09-02 | 11.42 | COMPLETED |  |  |  | 2024-09-08 | (ATK-02)
25 | 34/4 | DA+3 | DFR | 2024-09-02 | 11.73 | COMPLETED |  |  |  | 2024-09-12 | (ATK-02)
26 | 34/1 | DA+0 | DFR | 2024-09-05 | 11.42 | COMPLETED |  |  |  | 2024-09-16 | (ATK-02)
27 | 52/2 | DA-3 | DFR | 2024-09-12 | 11.42 | COMPLETED |  |  |  | 2024-09-19 | (ATK-02)
28 | 46/9 | DA+0 | DFR | 2024-09-20 | 11.42 | COMPLETED |  |  |  | 2025-01-23 | ADARSH
29 | 33/12 | DA+0 | DFR | 2024-09-22 | 11.42 | COMPLETED |  |  |  | 2024-09-28 | (ATK-02)
30 | 46/14 | DA+0 | DFR | 2024-09-24 | 11.42 | COMPLETED |  |  |  | 2024-10-11 | (ATK-02)
31 | 33/11 | DA-3 | WET/WFR | 2024-09-24 | 17.65 | COMPLETED |  |  |  | 2024-10-03 | (ATK-02)
32 | 33/10 | DA+0 | DFR | 2024-09-27 | 11.42 | COMPLETED |  |  |  | 2024-11-19 | LALA GANG
33 | 33/9 | DA-3 | DFR | 2024-09-29 | 11.42 | COMPLETED |  |  |  | 2024-11-11 | GANG - 4
34 | 46/8 | DA+3 | DFR | 2024-10-08 | 11.73 | COMPLETED |  |  |  | 2024-10-19 | (ATK-02)
35 | 34/0 | DB1+0 | DFR | 2024-10-19 | 32.22 | COMPLETED |  |  |  | 2024-10-29 | Bindu
36 | 33/7 | DA-3 | DFR | 2024-10-27 | 11.42 | COMPLETED |  |  |  | 2024-11-04 | LALA GANG
37 | 46/7 | DB1+0 | DFR | 2024-10-30 | 32.22 | COMPLETED |  |  |  | 2024-11-22 | Adarsh Gang
38 | 33/8 | DA-3 | DFR | 2024-11-08 | 11.42 | COMPLETED |  |  |  | 2024-11-27 | Bindu
39 | 34/2 | DA+0 | DFR | 2024-11-13 | 11.42 | COMPLETED |  |  |  | 2024-12-26 | Bindu
40 | 46/5 | DA+6 | DFR | 2024-11-15 | 11.73 | COMPLETED |  |  |  | 2025-02-10 | Haque Constr.
41 | 46/4 | DA+0 | DFR | 2024-11-15 | 11.42 | COMPLETED |  |  |  | 2024-12-24 | Adarsh Gang
42 | 41/0 | DB1+0 | DFR | 2024-11-19 | 32.22 | COMPLETED |  |  |  | 2024-12-05 | Adarsh Gang
43 | 43/0 | DB1+0 | DFR | 2024-11-24 | 32.22 | COMPLETED |  |  |  | 2024-12-18 | Bindu
44 | 45/02 | DA+0 | DFR | 2024-12-04 | 11.42 | COMPLETED |  |  |  | 2024-12-20 | Bindu
45 | 45/0 | DC1+3 | DFR | 2024-12-09 | 28.1 | COMPLETED |  |  |  | 2024-12-30 | KAVAL CHAND
46 | 45/1 | DB1+6 | DFR | 2024-12-10 | 32.22 | COMPLETED |  |  |  | 2025-01-21 | ANURADHA
47 | 46/0 | DB1+0 | DFR | 2024-12-11 | 32.22 | COMPLETED |  |  |  | 2025-01-11 | ANURADHA
48 | 35/0 | DB1+0 | DFR | 2024-12-22 | 32.22 | COMPLETED |  |  |  | 2025-01-13 | KEC GANG -02
49 | 46/2 | DA+0 | WFR | 2025-01-01 | 16.7 | COMPLETED |  |  |  | 2025-03-21 | KEVAL CHAND
50 | 46/15 | DA+9 | DFR | 2025-01-03 | 11.73 | COMPLETED |  |  |  | 2025-01-13 | Adarsh Gang
51 | 33/6 | DB1+9 | DFR | 07-01-2025 25-5-25 | 32.22 | COMPLETED |  |  |  | 2025-06-02 | Haque Constr.
52 | 33/5 | DB1+9 | DFR | 2025-01-10 | 32.22 | COMPLETED |  |  |  | 2025-01-24 | KEC GANG -02
53 | 42/0 | DB2+3 | DFR | 2025-01-17 | 27.5 | COMPLETED |  |  |  | 2025-02-03 | ANURADHA
54 | 33/1 | DA-3 | DFR | 2025-01-23 | 11.42 | COMPLETED |  |  |  | 2025-02-01 | KEC GANG -02
55 | 55/0 | DB2+0 | DFR | 2025-01-28 | 27.5 | COMPLETED |  |  |  | 2025-02-19 | Haque Constr.
56 | 40/0 | DB2+9 | DFR | 2025-01-30 | 27.5 | COMPLETED |  |  |  | 2025-02-20 | ANURADHA
57 | 32/0 | DC2+6 | DFR | 2025-01-31 | 28.1 | COMPLETED |  |  |  | 2025-02-16 | KEC GANG -02
58 | 55/4 | DA+3 | DFR | 2025-02-12 | 11.73 | COMPLETED |  |  |  | 2025-02-24 | Haque Constr.
59 | 37/0 | DB2+3 | DFR | 2025-02-15 | 27.5 | COMPLETED |  |  |  | 2025-03-01 | KEC GANG -02
60 | 37/1 | DA+3 | DFR | 2025-02-15 | 11.73 | COMPLETED |  |  |  | 2025-03-02 | ANURADHA
61 | 48A/0 | DC1+0 | DFR | 2025-02-23 | 28.1 | COMPLETED |  |  |  | 2025-03-05 | Haque Constr.
62 | 38/1 | DA+9 | DFR | 2025-02-24 | 11.73 | COMPLETED |  |  |  | 2025-03-24 | ANURADHA
63 | 36/0 | DB1+3 | DFR | 2025-02-27 | 32.22 | COMPLETED |  |  |  | 2025-05-11 | KPK
64 | 60/4 | DA+0 | DFR | 2025-03-01 | 11.42 | COMPLETED |  |  |  | 2025-03-10 | Haque Constr.
65 | 37/2 | DA+0 | DFR | 2025-03-01 | 11.42 | COMPLETED |  |  |  | 2025-03-12 | ANURADHA
66 | 38/2 | DA+0 | DFR | 2025-03-10 | 11.42 | COMPLETED |  |  |  | 2025-04-04 | KEC GANG -04
67 | 47/1 | DA+3 | DFR | 2025-03-13 | 11.73 | COMPLETED |  |  |  | 2025-03-19 | Haque Constr.
68 | 54/2 | DA-3 | DFR | 2025-03-13 | 11.42 | COMPLETED |  |  |  | 2025-03-24 | Haque Constr.
69 | 61/0 | DC2+0 | DFR | 2025-03-20 | 28.1 | COMPLETED |  |  |  | 2025-04-04 | Haque Constr.
70 | 54/1 | DA-3 | DFR/WFR | 2025-03-28 | 11.42 | COMPLETED |  |  |  | 2025-04-11 | Haque Constr.
71 | 46/13 | DA+0 (RC) | DFR | 2025-04-02 | 11.42 | COMPLETED |  |  |  | 2025-05-05 | KEC GANG -04
72 | 56/0 | DB1+0 | DFR | 2025-04-08 | 32.22 | COMPLETED |  |  |  | 2025-05-01 | Haque Constr.
73 | 60/2 | DA+0 | DFR | 2025-04-11 | 11.42 | COMPLETED |  |  |  | 2025-04-18 | Haque Constr.
74 | 45/3 | DA+6 (RC) | DFR | 2025-04-13 | 11.73 | COMPLETED |  |  |  | 2025-05-23 | KEC GANG -04
75 | 46/12 | DA+0 (RC) | DFR | 2025-04-15 | 11.42 | COMPLETED |  |  |  | 2025-05-15 | KEC GANG -04
76 | 43/2 | DA+0 (RC) | DFR | 2025-04-16 | 11.42 | COMPLETED |  |  |  | 2025-05-19 | KEC GANG -04
77 | 60/0 | DC2+0 | DFR | 2025-04-17 | 11.42 | COMPLETED |  |  |  | 2025-04-25 | Haque Constr.
78 | 59/0 | DD60+6 | DFR | 2025-05-02 | 72.2 | COMPLETED |  |  |  | 2025-05-14 | Haque Constr.
79 | 52/0 | DC2+0 | DFR | 2025-05-10 | 28.1 | COMPLETED |  |  |  | 2025-05-26 | KPK
80 | 48/1 | DA+6 | DFR | 2025-05-11 | 11.73 | COMPLETED |  |  |  | 2025-05-23 | Haque Constr.
81 | 35/1 | DA+3 (RC) | DFR | 2025-05-11 | 11.73 | COMPLETED |  |  |  | 2025-06-03 | KPK
82 | 48/2 | DA+3 | DFR | 2025-05-14 | 11.73 | COMPLETED |  |  |  | 2025-05-24 | Haque Constr.
83 | 35/2 | DA+3 (RC) | DFR | 2025-05-26 | 11.73 | COMPLETED |  |  |  | 2025-06-09 | KPK
84 | 41/5 | DA+3 (RC) | DFR | 2025-05-25 | 11.73 | COMPLETED |  |  |  | 2025-06-01 | KEC GANG -04
85 | 35/5 | DA+0 (RC) | DFR | 2025-06-02 | 11.42 | COMPLETED |  |  |  | 2025-06-11 | KEC GANG -04
86 | 33/0 | DD45+18 | DFR | 2025-06-02 | 49.3 | COMPLETED |  |  |  | 2025-06-16 | Haque Constr.
87 | 35/9 | DA+9 | DFR | 2025-06-02 | 11.73 | COMPLETED |  |  |  | 2025-06-20 | KEC GANG -04
88 | 35/10 | DA+9 | DFR | 2025-06-03 | 11.73 | COMPLETED |  |  |  | 2025-06-10 | KEC GANG -05
89 | 33/2 | DA+6 (RC) | DFR | 2025-06-06 | 11.73 | COMPLETED |  |  |  | 2025-06-21 | KEC GANG -06
90 | 36/1 | DB1+9 (RC) | DFR | 2025-06-09 | 34 | COMPLETED |  |  |  | 2025-06-20 | KPK
91 | 33/4 | DA+3 (RC) | DFR | 2025-06-10 | 11.73 | COMPLETED |  |  |  | 2025-07-02 | KEC GANG - 06
92 | 33/3 | DA+6 (RC) | DFR | 2025-06-12 | 11.73 | COMPLETED |  |  |  | 2025-06-30 | Haque Constr.
93 | 43/1 | DA+0 (RC) | DFR | 2025-06-12 | 11.42 | COMPLETED |  |  |  | 2025-06-18 | KEC GANG -05
94 | 62/0 | DD60+6 | DFR | 2025-06-16 | 99.27 | COMPLETED |  |  |  | 2025-06-25 | KEC GANG -05
95 | 39/0 | DD45+18 | DFR | 2025-06-18 | 49.3 | COMPLETED |  |  |  | 2025-07-01 | KPK
96 | 44/1 | DA+0 (RC) | DFR | 2025-06-18 | 11.42 | COMPLETED |  |  |  | 2025-06-24 | KEC GANG -05
97 | 57/2 | DA+0 | DFR | 2025-06-23 | 11.42 | COMPLETED |  |  |  | 2025-06-27 | KEC GANG -06
98 | 46/6 | DA+0 (RC) | DFR | 2025-06-24 | 11.42 | COMPLETED |  |  |  | 2025-07-09 | KEC GANG - 08
99 | 46/3 | DA+0 (RC) | DFR | 2025-06-24 | 11.42 | COMPLETED |  |  |  | 2025-07-03 | KEC GANG -07
100 | 46/1 | DA-3 | DFR | 2025-06-25 | 11.42 | COMPLETED |  |  |  | 2025-06-30 | KEC GANG -06
101 | 44/0 | DC1-3 | DFR | 2025-06-25 | 28.1 | COMPLETED |  |  |  | 2025-07-20 | KEC GANG - 08
102 | 46/10 | DA+0 | DFR | 2025-06-27 | 11.42 | COMPLETED |  |  |  | 2025-07-05 | KEC GANG -07
103 | 46/11 | DA-1.5 | DFR | 2025-06-28 | 11.42 | COMPLETED |  |  |  | 2025-07-23 | KEC GANG - 06
104 | 48/0 | DB2+0 | DFR | 2025-06-30 | 27.5 | COMPLETED |  |  |  | 2025-07-08 | Haque Constr.
105 | 57/1 | DA-1.5 | DFR | 2025-06-29 | 11.42 | COMPLETED |  |  |  | 2025-07-02 | KEC GANG -09
106 | 47/0 | DC1+0 | DFR | 2025-07-03 | 28.1 | COMPLETED |  |  |  | 2025-07-13 | KPK
107 | 58/0 | DD60+6 | DFR | 2025-07-03 | 99.27 | COMPLETED |  |  |  | 2025-07-16 | KEC GANG - 09
108 | 53/0 | DC2+6 | DFR | 2025-07-04 | 28.1 | COMPLETED |  |  |  | 2025-07-14 | Haque Constr.
109 | 60/1 | DA+6 | DFR | 2025-07-04 | 11.73 | COMPLETED |  |  |  | 2025-07-10 | KEC GANG -07
110 | 43/3 | DA-3 | DFR | 2025-07-10 | 11.42 | COMPLETED |  |  |  | 2025-07-16 | KEC GANG - 06
111 | 56/1 | DA+6 | DFR | 13-07-2025 & 26-7-25 | 11.73 | COMPLETED |  |  |  | 2025-07-29 | KEC GANG -06
112 | 57/3 | DA-3 | DFR | 2025-07-15 | 11.42 | COMPLETED |  |  |  | 2025-07-18 | Haque Constr.
113 | 56/2 | DA-3 | DFR | 2025-08-01 | 11.42 | COMPLETED |  |  |  | 2025-08-03 | KEC GANG -06
114 | 56/3 | DB1+6 | DFR | 2025-08-02 | 11.42 | COMPLETED |  |  |  | 2025-08-06 | KEC GANG -07 - HQ
115 | 54/0 | DC1+6 | DFR | 2025-08-23 | 28.1 | COMPLETED |  |  |  | 2025-08-29 | KEC GANG -07 - HQ
Erection
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status |  |  |  | Completion Date | Gang Name | Gang Strength | Remark
1 | 34/1 | DA+0 | DFR | 2024-10-09 | 27.96 | COMPLETED |  |  |  | 2024-10-27 | Gang-01 (Sanjay)
2 | 33/12 | DA+0 | DFR | 2024-10-28 | 27.96 | COMPLETED |  |  |  | 2024-11-05 | Gang-01 (Sanjay)
3 | 35/06 | DA+0 | DFR | 2024-11-05 | 27.96 | COMPLETED |  |  |  | 2024-11-13 | Gang-01 (Sanjay)
4 | 34/3 | DA+0 | DFR | 2024-11-14 | 27.96 | COMPLETED |  |  |  | 2024-11-19 | Gang-01 (Sanjay) |  | 11KV
5 | 35/4 | DA+0 | DFR | 2024-11-19 | 27.96 | COMPLETED |  |  |  | 2024-11-24 | Gang-01 (Sanjay) |  | LT
6 | 40/1 | DA+0 | DFR | 2024-11-26 | 27.96 | COMPLETED |  |  |  | 2024-12-01 | Gang-01 (Sanjay)
7 | 40/2 | DA+0 | DFR | 2024-12-02 | 27.96 | COMPLETED |  |  |  | 2024-12-06 | Gang-01 (Sanjay)
8 | 42/2 | DA+0 | DFR | 2024-12-03 | 27.96 | COMPLETED |  |  |  | 2024-12-11 | Gang-02 (Sanjay) |  | 11KV
9 | 41/3 | DA+0 | DFR | 2024-12-06 | 27.96 | COMPLETED |  |  |  | 2024-12-11 | Gang-01 (Sanjay)
10 | 41/4 | DA+3 | DFR | 2024-12-12 | 29.12 | COMPLETED |  |  |  | 2024-12-18 | Gang-01 (Sanjay)
11 | 42/1 | DA+0 | DFR | 2024-12-12 | 27.96 | COMPLETED |  |  |  | 2024-12-18 | Gang-02 (Sanjay)
12 | 35/11 | DA+3 | DFR | 2024-12-19 | 29.12 | COMPLETED |  |  |  | 2024-12-27 | Gang-01 (Sanjay)
13 | 35/7 | DA+9 | DFR | 2024-12-19 | 34.63 | COMPLETED |  |  |  | 2024-12-29 | Gang-02 (Sanjay)
14 | 33/10 | DA+0 | DFR | 2024-12-29 | 27.96 | COMPLETED |  |  |  | 2024-01-05 | Gang-01 (Sanjay)
15 | 40/4 | DA+0 | DFR | 2024-12-30 | 27.96 | COMPLETED |  |  |  | 2024-01-07 | Gang-02 (Sanjay)
16 | 46/14 | DA+0 | DFR | 2024-01-07 | 27.96 | COMPLETED |  |  |  | 2025-01-11 | Gang-01 (Sanjay)
17 | 54/4 | DA+0 | DFR | 2024-01-09 | 27.96 | COMPLETED |  |  |  | 2025-01-15 | Gang-02 (Sanjay)
18 | 46/8 | DA+3 | DFR | 2025-01-13 | 29 | COMPLETED |  |  |  | 2025-01-18 | Gang-01 (Sanjay)
19 | 55/1 | DA+3 | DFR | 2025-01-16 | 29 | COMPLETED |  |  |  | 2025-01-23 | Gang-02 (Sanjay)
20 | 46/4 | DA+0 | DFR | 2025-01-16 | 28 | COMPLETED |  |  |  | 2025-01-23 | Gang-01 (Sanjay)
21 | 55/3 | DA+3 | DFR | 2025-01-24 | 29 | COMPLETED |  |  |  | 2025-02-11 | Gang-02 (Sanjay)
22 | 34/2 | DA+0 | DFR | 2025-01-24 | 28 | COMPLETED |  |  |  | 2025-01-30 | Gang-01 (Sanjay)
23 | 55/2 | DA+0 | DFR | 2025-01-25 | 28 | COMPLETED |  |  |  | 2025-02-02 | Gang-02 (Sanjay)
24 | 35/8 | DA+3 | DFR | 2025-01-31 | 29 | COMPLETED |  |  |  | 2025-02-05 | Gang-01 (Sanjay)
25 | 41/1 | DA+6 | DFR | 2025-02-06 | 33 | COMPLETED |  |  |  | 2025-02-11 | Gang-01 (Sanjay)
26 | 41/2 | DA+3 | DFR | 2025-02-12 | 29 | COMPLETED |  |  |  | 2025-02-17 | Gang-01 (Sanjay)
27 | 54/3 | DA+3 | DFR | 2025-02-12 | 29 | COMPLETED |  |  |  | 2025-02-20 | Gang-01 (Sanjay)
28 | 41/0 | DB1+0 | DFR | 2025-02-21 | 45 | COMPLETED |  |  |  | 2025-02-26 | Gang-01 (Sanjay)
29 | 43/0 | DB1+0 | DFR | 2025-02-26 | 45 | COMPLETED |  |  |  | 2025-03-03 | Gang-01 (Sanjay)
30 | 46/0 | DB1+0 | DFR | 2025-03-03 | 45 | COMPLETED |  |  |  | 2025-03-08 | Gang-01 (Sanjay)
31 | 46/9 | DA+0 | DFR | 2025-03-06 | 28 | COMPLETED |  |  |  | 2025-03-11 | Gang-02 (Sanjay)
32 | 46/7 | DB1+0 | DFR | 2025-03-12 | 45 | COMPLETED |  |  |  | 2025-03-17 | Gang-02 (Sanjay)
33 | 45/0 | DC1+3 | DFR | 2025-03-18 | 54 | COMPLETED |  |  |  | 2025-03-23 | Gang-02 (Sanjay)
34 | 45/1 | DB1+6 | DFR | 2025-03-18 | 52 | COMPLETED |  |  |  | 2025-03-28 | Gang-02 (Sanjay)
35 | 45/2 | DA+0 | DFR | 2025-03-28 | 28 | COMPLETED |  |  |  | 2025-04-01 | Gang-02 (Sanjay)
36 | 40/3 | DA+3 | DFR | 2025-04-02 | 29 | COMPLETED |  |  |  | 2025-04-05 | Gang-02 (Sanjay)
37 | 42/0 | DB2+3 | DFR | 2025-04-05 | 47 | COMPLETED |  |  |  | 2025-04-10 | Gang-02 (Sanjay)
38 | 33/5 | DB2+9 | DFR | 2025-04-11 | 54 | COMPLETED |  |  |  | 2025-04-21 | Gang-01 (Sanjay)
39 | 55/4 | DA+3 | DFR | 2025-04-12 | 29 | COMPLETED |  |  |  | 2025-04-18 | Gang-02 (Sanjay)
40 | 55/0 | DB2+0 | DFR | 2025-04-18 | 45 | COMPLETED |  |  |  | 2025-04-26 | Gang-02(Sanjay) |  | LT
41 | 34/0 | DB1+0 | DFR | 2025-04-22 | 45 | COMPLETED |  |  |  | 2025-04-29 | Gang-01(Sanjay)
42 | 46/15 | DA+9 | DFR | 2025-04-27 | 34.63 | COMPLETED |  |  |  | 2025-05-03 | Gang-02(Sanjay)
43 | 37/1 | DA+3 | DFR | 2025-04-29 | 29 | COMPLETED |  |  |  | 2025-05-07 | Gang-01(Sanjay)
44 | 46/2 | DA+0 | DFR | 2025-05-05 | 28 | COMPLETED |  |  |  | 2025-05-10 | Gang-02(Sanjay) |  | LT
45 | 35/0 | DB1+0 | DFR | 2025-05-08 | 45 | COMPLETED |  |  |  | 2025-05-17 | Gang-02(Sanjay)
46 | 46/5 | DA+6 | DFR | 2025-05-11 | 33 | COMPLETED |  |  |  | 2025-05-19 | Gang-01(Sanjay)
47 | 33/11 | DA-3 | DFR | 2025-05-11 | 27 | COMPLETED |  |  |  | 2025-05-26 | Gang-02(Sanjay)
48 | 34/4 | DA+3 | DFR | 2025-05-22 | 29 | COMPLETED |  |  |  | 2025-05-28 | Gang-01(Sanjay)
49 | 35/3 | DA-3 | DFR | 2025-05-30 | 27 | COMPLETED |  |  |  | 2025-06-04 | Gang-02(Sanjay)
50 | 40/5 | DA-3 | DFR | 2025-05-29 | 27 | COMPLETED |  |  |  | 2025-06-02 | Gang-01(Sanjay)
51 | 33/7 | DA-3 | DFR | 2025-06-03 | 27 | COMPLETED |  |  |  | 2025-06-08 | Gang-02(Sanjay)
52 | 33/8 | DA-3 | DFR | 2025-06-09 | 27 | COMPLETED |  |  |  | 2025-06-12 | Gang-02(Sanjay)
53 | 33/9 | DA-3 | DFR | 2025-06-12 | 27 | COMPLETED |  |  |  | 2025-06-17 | Gang-01(Sanjay)
54 | 33/6 | DB+9 | DFR | 2025-06-14 | 56 | COMPLETED |  |  |  | 2025-06-24 | Gang-02(Sanjay)
55 | 36/0 | DB1+3 | DFR | 2025-06-19 | 47 | COMPLETED |  |  |  | 2025-07-01 | Gang-01(Sanjay)
56 | 38/2 | DA+0 | DFR | 2025-07-03 | 28 | COMPLETED |  |  |  | 2025-07-12 | KEC - 01 (Barkat Ali)
57 | 40/0 | DB2+9 | DFR | 2025-07-03 | 54 | COMPLETED |  |  |  | 2025-07-21 | Gang-02(Sanjay)
58 | 37/0 | DB2+3 | DFR | 2025-07-03 | 47 | COMPLETED |  |  |  | 2025-07-14 | KEC - 02 (Barkat Ali)
59 | 37/2 | DA+0 | DFR | 2025-07-14 | 28 | COMPLETED |  |  |  | 2025-07-20 | KEC - 01 (Barkat Ali)
60 | 38/1 | DA+9 | DFR | 2025-07-15 | 34.6 | COMPLETED |  |  |  | 2025-07-23 | KEC - 02 (Barkat Ali)
61 | 35/9 | DA+9 | DFR | 2025-07-21 | 34.6 | COMPLETED |  |  |  | 2025-07-31 | KEC - 02 (Barkat Ali)
62 | 35/5 | DA+0 | DFR | 2025-07-22 | 28 | COMPLETED |  |  |  | 2025-07-30 | KEC - 01 (Barkat Ali)
63 | 35/1 | DA+3 | DFR | 2025-07-21 | 29 | COMPLETED |  |  |  | 2025-08-07 | SAVITHA
64 | 41/5 | DA+3 | DFR | 2025-07-24 | 29 | COMPLETED |  |  |  | 2025-08-06 | Gang-02(Sanjay) / KEC - 02 (Barkat Ali)
65 | 35/2 | DA+3 | DFR | 2025-06-29 | 29 | COMPLETED |  |  |  | 2025-08-07 | KEC - 01 (Barkat Ali)
66 | 36/1 | DB1+9 | DFR | 2025-08-06 | 54 | COMPLETED |  |  |  | 2025-08-19 | KEC - 02 (Barkat Ali)
67 | 35/10 | DA+9 | DFR | 2025-08-07 | 34.63 | COMPLETED |  |  |  | 2025-08-17 | KEC - 01 (Barkat Ali)
68 | 48A/0 | DC1+0 | DFR | 2025-08-07 | 51.6 | COMPLETED |  |  |  | 2025-08-16 | SUBHASH
69 | 46/13 | DA+0 | DFR | 2025-08-09 | 28 | COMPLETED |  |  |  | 2025-08-22 | SAVITHA
70 | 48/1 | DA+6 | DFR | 2025-08-16 | 33 | COMPLETED |  |  |  | 2025-09-01 | SUBHASH
71 | 43/1 | DA+0 | DFR | 2025-08-18 | 28 | COMPLETED |  |  |  | 2025-08-26 | KEC - 01 (Barkat Ali)
72 | 52/0 | DC2+0 | DFR | 2025-08-19 | 51.6 | COMPLETED |  |  |  | 2025-08-26 | SUBHASH
73 | 46/3 | DA+0 | DFR | 2025-08-22 | 28 | COMPLETED |  |  |  | 2025-08-26 | KEC - 02 (Barkat Ali)
74 | 60/2 | DA+0 | DFR | 2025-08-26 | 28 | Bottom section work under progress. |  |  |  |  | KEC - 02 (Barkat Ali) | 31
75 | 33/3 | DA+9 | DFR | 2025-08-31 | 35 | COMPLETED |  |  |  | 2025-09-10 | KEC - 01 (Barkat Ali)
76 | 62/0 | DD60+0 | DFR | 2025-09-01 | 63 | COMPLETED |  |  |  | 2025-09-12 | KEC - 02 (Barkat Ali)
77 | 46/12 | DA+0 | DFR | 2025-09-03 | 27.9 | COMPLETED |  |  |  | 2025-09-07 | SUBHASH
78 | 56/0 | DB1+0 | DFR | 2025-09-05 | 45 | COMPLETED |  |  |  | 2025-10-03 | SAVITHA
79 | 46/11 | DA-1.5 | DFR | 2025-09-08 | 33 | (ROW) |  |  |  |  | SUBHASH
80 | 48/2 | DA+3 | DFR | 2025-09-09 | 29 | COMPLETED |  |  |  | 2025-09-13 | SUBHASH
81 | 45/3 | DA+6 | DFR | 2025-09-09 | 33.3 | COMPLETED |  |  |  | 2025-09-30 | M/S MDPL
82 | 33/2 | DA+6 | DFR | 2025-09-12 | 33.3 | COMPLETED |  |  |  | 2025-09-22 | M/s TOFIT
83 | 61/0 | DC2+0 | DFR | 2025-09-14 | 51.7 | COMPLETED |  |  |  | 2025-09-25 | KEC - 02 (Barkat Ali)
84 | 53/0 | DC2+6 | DFR | 2025-09-16 | 60 | COMPLETED |  |  |  | 2025-09-23 | SUBHASH
85 | 33/1 | DA-3 | DFR | 2025-09-22 | 27 | COMPLETED |  |  |  | 2025-09-30 | M/s TOFIT
86 | 44/0 | DC1-3 | DFR | 2025-09-25 | 50 | COMPLETED |  |  |  | 2025-10-01 | SUBHASH
87 | 54/1 | DA-3 | DFR | 2025-09-28 | 27 | COMPLETED |  |  |  | 2025-10-05 | KEC - 02 (Barkat Ali)
88 | 54/0 | DC1+6 | DFR | 2025-09-29 | 60 | Top section work under progress. |  |  |  |  | M/S MDPL | 27
89 | 32/0 | DC2+6 | DFR | 2025-10-04 | 60 | cage 02 section Work under progress. |  |  |  |  | M/s TOFIT | 33
Stringing
S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | Remarks
1 | 42/0 - 43/0 | 1.106 | COMPLETED |  |  |  | SUFIYAN
2 | 41/0 - 42/0 | 2.473 | COMPLETED |  |  |  | SUFIYAN
3 | 40/0 - 41/0 | 2.426 | Conductor pulling arrangements Done. (Progress Affected due to Corridor- ROW) |  |  |  | SUFIYAN | 47
OPGW Stringing
S.No | Section | Length | Status |  |  |  | Gang Name | Gang Strength | Remarks

## Erection Compiled
Erection
SL No. | Location No. | Tower Type | Classification | Starting Date | Tower Weight | Status | Completion Date | Gang Name | Gang Strength | Remark
1 | 34/1 | DA+0 | DFR | 2024-10-09 | 27.96 | COMPLETED | 2024-10-27 | Gang-01 (Sanjay)
2 | 33/12 | DA+0 | DFR | 2024-10-28 | 27.96 | COMPLETED | 2024-11-05 | Gang-01 (Sanjay)
3 | 35/06 | DA+0 | DFR | 2024-11-05 | 27.96 | COMPLETED | 2024-11-13 | Gang-01 (Sanjay)
4 | 34/3 | DA+0 | DFR | 2024-11-14 | 27.96 | COMPLETED | 2024-11-19 | Gang-01 (Sanjay) |  | 11KV
5 | 35/4 | DA+0 | DFR | 2024-11-19 | 27.96 | COMPLETED | 2024-11-24 | Gang-01 (Sanjay) |  | LT
6 | 40/1 | DA+0 | DFR | 2024-11-26 | 27.96 | COMPLETED | 2024-12-01 | Gang-01 (Sanjay)
7 | 40/2 | DA+0 | DFR | 2024-12-02 | 27.96 | COMPLETED | 2024-12-06 | Gang-01 (Sanjay)
8 | 42/2 | DA+0 | DFR | 2024-12-03 | 27.96 | COMPLETED | 2024-12-11 | Gang-02 (Sanjay) |  | 11KV
9 | 41/3 | DA+0 | DFR | 2024-12-06 | 27.96 | COMPLETED | 2024-12-11 | Gang-01 (Sanjay)
10 | 41/4 | DA+3 | DFR | 2024-12-12 | 29.12 | COMPLETED | 2024-12-18 | Gang-01 (Sanjay)
11 | 42/1 | DA+0 | DFR | 2024-12-12 | 27.96 | COMPLETED | 2024-12-18 | Gang-02 (Sanjay)
12 | 35/11 | DA+3 | DFR | 2024-12-19 | 29.12 | COMPLETED | 2024-12-27 | Gang-01 (Sanjay)
13 | 35/7 | DA+9 | DFR | 2024-12-19 | 34.63 | COMPLETED | 2024-12-29 | Gang-02 (Sanjay)
14 | 33/10 | DA+0 | DFR | 2024-12-29 | 27.96 | COMPLETED | 2024-01-05 | Gang-01 (Sanjay)
15 | 40/4 | DA+0 | DFR | 2024-12-30 | 27.96 | COMPLETED | 2024-01-07 | Gang-02 (Sanjay)
16 | 46/14 | DA+0 | DFR | 2024-01-07 | 27.96 | COMPLETED | 2025-01-11 | Gang-01 (Sanjay)
17 | 54/4 | DA+0 | DFR | 2024-01-09 | 27.96 | COMPLETED | 2025-01-15 | Gang-02 (Sanjay)
18 | 46/8 | DA+3 | DFR | 2025-01-13 | 29 | COMPLETED | 2025-01-18 | Gang-01 (Sanjay)
19 | 55/1 | DA+3 | DFR | 2025-01-16 | 29 | COMPLETED | 2025-01-23 | Gang-02 (Sanjay)
20 | 46/4 | DA+0 | DFR | 2025-01-16 | 28 | COMPLETED | 2025-01-23 | Gang-01 (Sanjay)
21 | 55/3 | DA+3 | DFR | 2025-01-24 | 29 | COMPLETED | 2025-02-11 | Gang-02 (Sanjay)
22 | 34/2 | DA+0 | DFR | 2025-01-24 | 28 | COMPLETED | 2025-01-30 | Gang-01 (Sanjay)
23 | 55/2 | DA+0 | DFR | 2025-01-25 | 28 | COMPLETED | 2025-02-02 | Gang-02 (Sanjay)
24 | 35/8 | DA+3 | DFR | 2025-01-31 | 29 | COMPLETED | 2025-02-05 | Gang-01 (Sanjay)
25 | 41/1 | DA+6 | DFR | 2025-02-06 | 33 | COMPLETED | 2025-02-11 | Gang-01 (Sanjay)
26 | 41/2 | DA+3 | DFR | 2025-02-12 | 29 | COMPLETED | 2025-02-17 | Gang-01 (Sanjay)
27 | 54/3 | DA+3 | DFR | 2025-02-12 | 29 | COMPLETED | 2025-02-20 | Gang-01 (Sanjay)
28 | 41/0 | DB1+0 | DFR | 2025-02-21 | 45 | COMPLETED | 2025-02-26 | Gang-01 (Sanjay)
29 | 43/0 | DB1+0 | DFR | 2025-02-26 | 45 | COMPLETED | 2025-03-03 | Gang-01 (Sanjay)
30 | 46/0 | DB1+0 | DFR | 2025-03-03 | 45 | COMPLETED | 2025-03-08 | Gang-01 (Sanjay)
31 | 46/9 | DA+0 | DFR | 2025-03-06 | 28 | COMPLETED | 2025-03-11 | Gang-02 (Sanjay)
32 | 46/7 | DB1+0 | DFR | 2025-03-12 | 45 | COMPLETED | 2025-03-17 | Gang-02 (Sanjay)
33 | 45/0 | DC1+3 | DFR | 2025-03-18 | 54 | COMPLETED | 2025-03-23 | Gang-02 (Sanjay)
34 | 45/1 | DB1+6 | DFR | 2025-03-18 | 52 | COMPLETED | 2025-03-28 | Gang-02 (Sanjay)
35 | 45/2 | DA+0 | DFR | 2025-03-28 | 28 | COMPLETED | 2025-04-01 | Gang-02 (Sanjay)
36 | 40/3 | DA+3 | DFR | 2025-04-02 | 29 | COMPLETED | 2025-04-05 | Gang-02 (Sanjay)
37 | 42/0 | DB2+3 | DFR | 2025-04-05 | 47 | COMPLETED | 2025-04-10 | Gang-02 (Sanjay)
38 | 33/5 | DB2+9 | DFR | 2025-04-11 | 54 | COMPLETED | 2025-04-21 | Gang-01 (Sanjay)
39 | 55/4 | DA+3 | DFR | 2025-04-12 | 29 | COMPLETED | 2025-04-18 | Gang-02 (Sanjay)
40 | 55/0 | DB2+0 | DFR | 2025-04-18 | 45 | COMPLETED | 2025-04-26 | Gang-02(Sanjay) |  | LT
41 | 34/0 | DB1+0 | DFR | 2025-04-22 | 45 | COMPLETED | 2025-04-29 | Gang-01(Sanjay)
42 | 46/15 | DA+9 | DFR | 2025-04-27 | 34.63 | COMPLETED | 2025-05-03 | Gang-02(Sanjay)
43 | 37/1 | DA+3 | DFR | 2025-04-29 | 29 | COMPLETED | 2025-05-07 | Gang-01(Sanjay)
44 | 46/2 | DA+0 | DFR | 2025-05-05 | 28 | COMPLETED | 2025-05-10 | Gang-02(Sanjay) |  | LT
45 | 35/0 | DB1+0 | DFR | 2025-05-08 | 45 | COMPLETED | 2025-05-17 | Gang-02(Sanjay)
46 | 46/5 | DA+6 | DFR | 2025-05-11 | 33 | COMPLETED | 2025-05-19 | Gang-01(Sanjay)
47 | 33/11 | DA-3 | DFR | 2025-05-11 | 27 | COMPLETED | 2025-05-26 | Gang-02(Sanjay)
48 | 34/4 | DA+3 | DFR | 2025-05-22 | 29 | COMPLETED | 2025-05-28 | Gang-01(Sanjay)
49 | 35/3 | DA-3 | DFR | 2025-05-30 | 27 | COMPLETED | 2025-06-04 | Gang-02(Sanjay)
50 | 40/5 | DA-3 | DFR | 2025-05-29 | 27 | COMPLETED | 2025-06-02 | Gang-01(Sanjay)
51 | 33/7 | DA-3 | DFR | 2025-06-03 | 27 | COMPLETED | 2025-06-08 | Gang-02(Sanjay)
52 | 33/8 | DA-3 | DFR | 2025-06-09 | 27 | COMPLETED | 2025-06-12 | Gang-02(Sanjay)
53 | 33/9 | DA-3 | DFR | 2025-06-12 | 27 | COMPLETED | 2025-06-17 | Gang-01(Sanjay)
54 | 33/6 | DB+9 | DFR | 2025-06-14 | 56 | COMPLETED | 2025-06-24 | Gang-02(Sanjay)
55 | 36/0 | DB1+3 | DFR | 2025-06-19 | 47 | COMPLETED | 2025-07-01 | Gang-01(Sanjay)
56 | 38/2 | DA+0 | DFR | 2025-07-03 | 28 | COMPLETED | 2025-07-12 | KEC - 01 (Barkat Ali)
57 | 40/0 | DB2+9 | DFR | 2025-07-03 | 54 | COMPLETED | 2025-07-21 | Gang-02(Sanjay)
58 | 37/0 | DB2+3 | DFR | 2025-07-03 | 47 | COMPLETED | 2025-07-14 | KEC - 02 (Barkat Ali)
59 | 37/2 | DA+0 | DFR | 2025-07-14 | 28 | COMPLETED | 2025-07-20 | KEC - 01 (Barkat Ali)
60 | 38/1 | DA+9 | DFR | 2025-07-15 | 34.6 | COMPLETED | 2025-07-23 | KEC - 02 (Barkat Ali)
61 | 35/9 | DA+9 | DFR | 2025-07-21 | 34.6 | COMPLETED | 2025-07-31 | KEC - 02 (Barkat Ali)
62 | 35/5 | DA+0 | DFR | 2025-07-22 | 28 | COMPLETED | 2025-07-30 | KEC - 01 (Barkat Ali)
63 | 35/1 | DA+3 | DFR | 2025-07-21 | 29 | COMPLETED | 2025-08-07 | SAVITHA
64 | 41/5 | DA+3 | DFR | 2025-07-24 | 29 | COMPLETED | 2025-08-06 | Gang-02(Sanjay) / KEC - 02 (Barkat Ali)
65 | 35/2 | DA+3 | DFR | 2025-06-29 | 29 | COMPLETED | 2025-08-07 | KEC - 01 (Barkat Ali)
66 | 36/1 | DB1+9 | DFR | 2025-08-06 | 54 | COMPLETED | 2025-08-19 | KEC - 02 (Barkat Ali)
67 | 35/10 | DA+9 | DFR | 2025-08-07 | 34.63 | COMPLETED | 2025-08-17 | KEC - 01 (Barkat Ali)
68 | 48A/0 | DC1+0 | DFR | 2025-08-07 | 51.6 | COMPLETED | 2025-08-16 | SUBHASH
69 | 46/13 | DA+0 | DFR | 2025-08-09 | 28 | COMPLETED | 2025-08-22 | SAVITHA
70 | 48/1 | DA+6 | DFR | 2025-08-16 | 33 | COMPLETED | 2025-09-01 | SUBHASH
71 | 43/1 | DA+0 | DFR | 2025-08-18 | 28 | COMPLETED | 2025-08-26 | KEC - 01 (Barkat Ali)
72 | 52/0 | DC2+0 | DFR | 2025-08-19 | 51.6 | COMPLETED | 2025-08-26 | SUBHASH
73 | 46/3 | DA+0 | DFR | 2025-08-22 | 28 | COMPLETED | 2025-08-26 | KEC - 02 (Barkat Ali)
74 | 60/2 | DA+0 | DFR | 2025-08-26 | 28 | Ground Assembling work under progress. (Severe ROW) |  | KEC - 02 (Barkat Ali) | 31
75 | 33/3 | DA+9 | DFR | 2025-08-31 | 35 | COMPLETED | 2025-09-10 | KEC - 01 (Barkat Ali)
76 | 62/0 | DD60+0 | DFR | 2025-09-01 | 63 | COMPLETED | 2025-09-12 | KEC - 02 (Barkat Ali)
77 | 46/12 | DA+0 | DFR | 2025-09-03 | 27.9 | COMPLETED | 2025-09-07 | SUBHASH
78 | 56/0 | DB1+0 | DFR | 2025-09-05 | 45 | COMPLETED | 2025-10-03 | SAVITHA
79 | 46/11 | DA-1.5 | DFR | 2025-09-08 | 33 | (ROW) |  | SUBHASH
80 | 48/2 | DA+3 | DFR | 2025-09-09 | 29 | COMPLETED | 2025-09-13 | SUBHASH
81 | 45/3 | DA+6 | DFR | 2025-09-09 | 33.3 | COMPLETED | 2025-09-30 | M/S MDPL
82 | 33/2 | DA+6 | DFR | 2025-09-12 | 33.3 | COMPLETED | 2025-09-22 | M/s TOFIT
83 | 61/0 | DC2+0 | DFR | 2025-09-14 | 51.7 | COMPLETED | 2025-09-25 | KEC - 02 (Barkat Ali)
84 | 53/0 | DC2+6 | DFR | 2025-09-16 | 60 | COMPLETED | 2025-09-23 | SUBHASH
85 | 33/1 | DA-3 | DFR | 2025-09-22 | 27 | COMPLETED | 2025-09-30 | M/s TOFIT
86 | 44/0 | DC1-3 | DFR | 2025-09-25 | 50 | COMPLETED | 2025-10-01 | SUBHASH
87 | 54/1 | DA-3 | DFR | 2025-09-28 | 27 | COMPLETED | 2025-10-05 | KEC - 02 (Barkat Ali)
88 | 54/0 | DC1+6 | DFR | 2025-09-29 | 60 | Top section work under progress. |  | M/S MDPL | 27
89 | 32/0 | DC2+6 | DFR | 2025-10-04 | 60 | cage 02 section Work under progress. |  | M/s TOFIT | 33

## Visual Chart
VISUAL CHART - 765kV D/C KOPPAL II(PS) - RAICHUR TRANSMISSION LINE
Name of Contractor : M/s KEC International Ltd
Progress at a Glance :
| Sl. No. | Activity |  |  |  | UoM |  | Total Qty |  |  | Completed |  |  | Balance
| 1 | Detailed Survey |  |  |  | Kms |  | 47.84 |  |  | 47.84 |  |  | 0
| 2 | Check Survey |  |  |  | Kms |  | 47.84 |  |  | 47.84 |  |  | 0
| 3 | Foundation |  |  |  | Nos |  | 127 |  |  | 115 |  |  | 12
| 4 | Earthing |  |  |  | Nos |  | 127 |  |  | 110 |  |  | 17
| 5 | Erection |  |  |  | Nos |  | 127 |  |  | 85 |  |  | 42
| 7 | Stringing (Paying out) |  |  |  | Kms |  | 47.84 |  |  | 3.579 |  |  | 44.261 |  |  |  |  | Line Length (KM): | 47.8357
| 8 | Stringing (Final Sag) |  |  |  | Nos |  | 47.84 |  |  | 0 |  |  | 47.84
Trippur
RAICHUR DISTRICT
|  |  | 220kV S/C Sindhanur LILO Line |  |  | TW-3 |  | TW-4 |  | TW-5 |  | TW-6 |  |  | 110kV S/C TL on D/C Tower |  |  | TW-9 |  | TW-10
|  | TW-1 |  | TW-2 | [9 empty] | TW-7 |  | TW-8 | 11KV-2 | [5 empty] | FDN | ERTH | ERE | TW | STRG
|  |  | 249.635 |  | 425 |  | 425 |  | 390 |  | 265 |  | 510 |  | 380 |  | 420 |  | 335 |  | 345 | 3744.635
1 |  | DFR |  | DFR |  | DFR |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR |  | DFR |  | DFR |  | DFR |  |  | 10 | 10 | 7 | 0 | 0 | COM
[23 empty] | 0 | 0 | 1 | 0 | 0 | WIP
|  | AP32 |  | AP33 |  | 33/1 |  | 33/2 |  | 33/3 |  | 33/4 |  | 33/5 |  | 33/6 |  | 33/7 |  | 33/8 |  |  | 0 | 0 | 1 | 0 | 0 | ROW
|  | DC2+06 |  | DD45+18 |  | 1DA-3 |  | 1DA+6 |  | 1DA+9 |  | 1DA+3 |  | 1DB1+9 |  | 1DB1+9 |  | 1DA-3 |  | 1DA-3 |  |  |  | 0 |  | 7 |  | WFT
0.24963
|  |  | CHIKKEBERAGI | [5 empty] | BUKKANAHATTI | [8 empty] | UMALOOTI
|  | TW-11 |  | TW-12 |  | TW-13 |  | TW-14 |  | TW-15
|  |  | 11KV-3 33KV-1 | [19 empty] | FDN | ERTH | ERE | TW | STRG
|  |  | 365 |  | 356 |  | 332 |  | 384.424 |  | 385 | [10 empty] | 1822.424
2 |  | DFR |  | DFR |  | WET/WFR |  | DFR |  | DFR | [12 empty] | 5 | 5 | 5 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | 33/9 |  | 33/10 |  | 33/11 |  | 33/12 |  | AP34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | ROW
|  | 1DA-3 |  | 1DA+0 |  | 1DA-3 |  | 1DA+0 |  | 1DB1+0 | [13 empty] | 0 | 0 | 5 |  | WFT
4.9324
|  | UMALOOTI | [20 empty] | FDN | ERTH | ERE | TW | STRG
[23 empty] | 15 | 15 | 12 | 0 | 0 | com
| KOPPAL DISTRICT | [21 empty] | 0 | 0 | 1 | 0 | 0 | WIP |  | SINDHANURU
|  | TW-16 |  | TW-17 |  | TW-18 |  | TW-19 |  | TW-20 |  | TW-21 |  | TW-22 |  | TW-23 |  | TW-24 |  | TW-25 |  |  | 0 | 0 | 1 | 0 | 0 | ROW
|  |  | LT-2 | [13 empty] | LT-2 | [5 empty] | 0 | 0 | #VALUE! | 12 | 0 | WFT
|  |  | 423 |  | 382 |  | 405 |  | 388.458 |  | 405 |  | 360 |  | 390 |  | 325 |  | 430 |  | 298 | 3806.458
3 |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR - RC |  | DFR - RC |  | DFR |  | DFR |  | DFR - RC |  |  | 10 | 10 | 10 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | 34/1 |  | 34/2 |  | 34/3 |  | 34/4 |  | AP35 |  | 35/1 |  | 35/2 |  | 35/3 |  | 35/4 |  | 35/5 |  |  | 0 | 0 | 0 | 0 | 0 | ROW
|  | 1DA+0 |  | 1DA+0 |  | 1DA+0 |  | 1DA+3 |  | 1DB1+0 |  | 1DA+3 |  | 1DA+3 |  | 1DA-3 |  | 1DA+0 |  | 1DA+0 |  |  |  | 0 | 0 | 10 |  | WFT
1.9835
[6 empty] | PURA | [12 empty] | KANNALA
|  | TW-26 |  | TW-27 |  | TW-28 |  | TW-29 |  | TW-30 |  | TW-31 |  | TW-32 |  | TW-33 |  | TW-34 |  | TW-35
[11 empty] | LT-3 |  | LT-2 |  |  |  | 110kV S/C TL
|  |  | 422 |  | 345 |  | 370 |  | 320 |  | 390 |  | 425.02 |  | 480 |  | 297.315 |  | 417 |  | 409 | 3875.335 | FDN | ERTH | ERE | TW | STRG
4 |  | DFR |  | DFR |  | DFR |  | DFR - RC |  | DFR - RC |  | DFR |  | DFR |  | DFR - RC |  | DFR |  | DFR |  |  | 10 | 10 | 10 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | 35/6 |  | 35/7 |  | 35/8 |  | 35/9 |  | 35/10 |  | 35/11 |  | AP36 |  | 36/1 |  | AP37 |  | 37/1 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA+0 |  | 1DA+9 |  | 1DA+3 |  | 1DA+9 |  | 1DA+9 |  | 1DA+3 |  | 1DB1+3 |  | 1DB1+9 |  | 1DB2+3 |  | 1DA+3 |  |  |  | 0 | 0 | 10 |  | WFT
|  | 4.48 | [11 empty] | 0.77732
METTHINALA
|  | TW-36 |  | TW-37 |  | TW-38 |  | TW-39 |  | TW-40 | 220kV D/C LINE | TW-41 |  | TW-42 |  | TW-43 |  | TW-44 |  | TW-45
[5 empty] | 11KV-4 |  | 11KV-2 |  |  |  | 220kV D/C LINE | [7 empty] | 11KV-2 |  |  |  | FDN | ERTH | ERE | TW | STRG
|  |  | 432.782 |  | 469 |  | 387 |  | 444.76 |  | 230.87 |  | 430 |  | 400 |  | 410 |  | 435 |  | 360 | 3999.412
5 |  | DFR |  |  |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  |  | 9 | 9 | 8 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 2035 | WIP
|  | 37/2 |  | AP38 |  | 38/1 |  | 38/2 |  | AP39 |  | AP40 |  | 40/1 |  | 40/2 |  | 40/3 |  | 40/4 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA+0 |  | 1DD60+6 |  | 1DA+9 |  | 1DA+0 |  | 1DD45+18 |  | 1DB2+9 |  | 1DA+0 |  | 1DA+0 |  | 1DA+3 |  | 1DA+0 |  |  |  | 0 | 1 | 8 |  | WFT
|  | 1.7278 |  |  |  | 0.83176 |  |  |  | 0.23087
|  |  | MANEDHAL | [13 empty] | HADAGALI
|  | TW-46 |  | TW-47 |  | TW-48 |  | TW-49 |  | TW-50 |  | TW-51 |  | TW-52 |  | TW-53 |  | TW-54 |  | TW-55
[23 empty] | FDN | ERTH | ERE | TW | STRG
|  |  | 391.451 |  | 380 |  | 475 |  | 380 |  | 390 |  | 465 |  | 383.208 |  | 380 |  | 348 |  | 377.784 | 3970.443
#REF! |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR - RC |  | DFR |  | DFR |  | DFR |  |  | 10 | 10 | 10 | 0 | 3578.992 | COM
[23 empty] | 0 | 0 | 0 | 0 | 391.451 | WIP
|  | 40/5 |  | AP41 |  | 41/1 |  | 41/2 |  | 41/3 |  | 41/4 |  | 41/5 |  | AP42 |  | 42/1 |  | 42/2 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA-3 |  | 1DB1+0 |  | 1DA+6 |  | 1DA+3 |  | 1DA+0 |  | 1DA+3 |  | 1DA+3 |  | 1DB2+3 |  | 1DA+0 |  | 1DA+0 |  |  |  | 0 | 0 | 10 |  | WFT
|  | 2.4265 |  | 2.4732 | [12 empty] | 1.1058
|  |  |  | VIRAPAPURA | [14 empty] | LINGADHAHALLI
|  | TW-56 |  | TW-57 |  | TW-58 |  | TW-59 |  | TW-60 |  | TW-61 |  | TW-62 |  | TW-63 |  | TW-64 |  | TW-65
[9 empty] | LT-2 | [5 empty] | 110kV S/C TL on D/C Tower |  | LT-3 |  | LT-2 |  |  |  | FDN | ERTH | ERE | TW | STRG |  | FDN | ERTH | ERE | TW | STRG
|  |  | 410 |  | 380 |  | 325 |  | 329.8 |  | 385 |  | 312.558 |  | 242 |  | 464 |  | 391 |  | 417.518 | 3656.876
#REF! |  | DFR |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR |  | DFR |  | DFR |  | DFR - RC |  |  | 10 | 10 | 7 | 0 | 0 | COM | 0 | 0 | 0 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP | 0 | 0 | 0 | 0 | 0 | WIP
|  | AP43 |  | 43/1 |  | 43/2 |  | 43/3 |  | AP44 |  | 44/1 |  | AP45 |  | 45/1 |  | 45/2 |  | 45/3 |  |  | 0 | 0 | 0 | 0 | 0 | ROW | 0 | 0 | 0 | 0 | 0 | ROW
|  | 1DB1+0 |  | 1DA+0 |  | 1DA+0 |  | 1DA-3 |  | 1DC1-3 |  | 1DA+0 |  | 1DC1+3 |  | 1DB1+6 |  | 1DA+0 |  | 1DA+6 |  |  |  | 0 | 3 | 7 |  | WFT |  | 0 | 0 | 0 |  | WFT
|  | 1.4448 | [8 empty] | 0.69756 |  |  |  | 1.5145 | [7 empty] | 49 | 49 | 45 | 0 | 3578.992 | com
|  | LINGADHAHALLI | [6 empty] | HOMMINALA | [9 empty] | GANADHALA |  |  |  | 0 | 0 | 0 | 0 | 2426.451 | WIP |  | KUSHTAGI
|  | TW-66 |  | TW-67 |  | TW-68 |  | TW-69 |  | TW-70 |  | TW-71 |  | TW-72 |  | TW-73 |  | TW-74 |  | TW-75 |  |  | 0 | 0 | 0 | 0 | 0 | ROW
|  |  | 11KV-4 |  | 11KV-2 LT-2 | [17 empty] | 0 | 0 | 4 | 45 | 0 | WFT
|  |  | 315 |  | 375 |  | 416 |  | 422 |  | 388 |  | 409 |  | 420 |  | 399 |  | 381 |  | 382 | 3907
#REF! |  | DFR |  | DFR |  | WFR |  | DFR - RC |  | DFR |  | DFR |  | DFR - RC |  | DFR |  | DFR |  | DFR |  |  | 10 | 10 | 8 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | AP46 |  | 46/1 |  | 46/2 |  | 46/3 |  | 46/4 |  | 46/5 |  | 46/6 |  | 46/7 |  | 46/8 |  | 46/9 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DB1+0 |  | 1DA-3 |  | 1DA+0 |  | 1DA+0 |  | 1DA+0 |  | 1DA+6 |  | 1DA+0 |  | 1DB1+0 |  | 1DA+3 |  | 1DA+0 |  |  |  | 0 | 2 | 8 |  | WFT
|  | GANADHALA | [17 empty] | KATAGIHAL
|  | TW-76 |  | TW-77 |  | TW-78 |  | TW-79 |  | TW-80 |  | TW-81 |  | TW-82 |  | TW-83 |  | TW-84 |  | TW-85
[9 empty] | LT-2 |  |  |  | LT-3 |  | LT-2 |  | LT-2 |  | 11KV-2 LT-2 |  | 11KV-2 |  | FDN | ERTH | ERE | TW | STRG
|  |  | 391 |  | 433 |  | 415 |  | 430 |  | 314 |  | 402.249 |  | 394 |  | 419.445 |  | 402 |  | 426 | 4026.694
10 |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR - RC |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR |  | DFR - RC |  |  | 10 | 10 | 5 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | 46/10 |  | 46/11 |  | 46/12 |  | 46/13 |  | 46/14 |  | 46/15 |  | AP47 |  | 47/1 |  | AP48 |  | 48/1 |  |  | 0 | 0 | 1 | 0 | 0 | ROW
|  | 1DA+0 |  | 1DA-1.5 |  | 1DA+0 |  | 1DA+0 |  | 1DA+0 |  | 1DA+9 |  | 1DC1+0 |  | 1DA+3 |  | 1DB2+0 |  | 1DA+6 |  |  |  | 0 | 4 | 5 |  | WFT
|  | 6.2922 | [11 empty] | 0.81344
[9 empty] | THIPPANAHALA |  |  |  | NH-50 (Hosapete - Kushtagi) | [5 empty] | UCHHALAKUNTI
|  | TW-86 |  | TW-87 |  | TW-88 |  | TW-89 |  | TW-90 |  | TW-91 |  | TW-92 |  | TW-93 |  | TW-94 |  | TW-95 | [11 empty] | 35805
|  |  | LT-2 |  | LT-2 | [5 empty] | LT-2 |  | 11KV-3 | [9 empty] | FDN | ERTH | ERE | TW | STRG
|  |  | 429.059 |  | 336 |  | 441 |  | 324.049 |  | 417.219 |  | 249.602 |  | 333.602 |  | 313 |  | 337 |  | 384.098 | 3564.629
11 |  | DFR - RC |  | DFR |  | RC |  | RC |  |  |  | RC |  | RC |  | DFR |  | DFR |  | DFR |  |  | 5 | 4 | 3 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | 48/2 |  | AP48A |  | 48A/1 |  | 48A/2 |  | AP49 |  | AP50 |  | AP51 |  | AP52 |  | 52/1 |  | 52/2 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA+3 |  | 1DC1+0 |  | 1DA+9 |  | 1DA-1.5 |  | 1DC1+3 |  | 1DC1+0 |  | 1DB1-3 |  | 1DC2+0 |  | 1DA-3 |  | 1DA-3 |  |  |  | 1 | 2 | 3 |  | WFT
|  | 2.3581 | [8 empty] | 0.41722 |  | 0.2496 |  | 0.3336 |  | 1.0341
GUNNALA
|  | TW-96 | 110kV D/C LINE | TW-97 |  | TW-98 |  | TW-99 |  | TW-100 |  | TW-101 |  | TW-102 |  | TW-103 |  | TW-104 |  | TW-105
[5 empty] | 11KV -2 LT-2 | [5 empty] | LT-4 |  | 11KV-8 LT-4 |  |  |  | LT-3 |  | LT-2 |  | 11KV-2 LT-5 |  | FDN | ERTH | ERE | TW | STRG
|  |  | 258.616 |  | 390 |  | 290 |  | 345 |  | 423 |  | 388.693 |  | 405 |  | 385 |  | 366 |  | 444 | 3695.309
12 |  | DFR |  | DFR |  | DFR/WFR |  | DFR |  | DFR |  | WFR |  | DFR |  | DFR |  | DFR |  | DFR |  |  | 10 | 7 | 8 | 0 | 0 | COM
[23 empty] | 0 | 0 | 1 | 0 | 0 | WIP
|  | AP53 |  | AP54 |  | 54/1 |  | 54/2 |  | 54/3 |  | 54/4 |  | AP55 |  | 55/1 |  | 55/2 |  | 55/3 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DC2+6 |  | 1DC1+6 |  | 1DA-3 |  | 1DA-3 |  | 1DA+3 |  | 1DA+0 |  | 1DB2+0 |  | 1DA+3 |  | 1DA+0 |  | 1DA+3 |  |  |  | 3 | 1 | 8 |  | WFT
|  | 0.25862 |  |  | 1.8367
HUNASIHALA
|  | TW-106 |  | TW-107 |  | TW-108 |  | TW-109 |  | TW-110 |  | TW-111 |  | TW-112 | SH-36 110kV D/C LINE | TW-113 |  | TW-114 |  | TW-115
|  |  | LT-2 | [5 empty] | 11KV-2 |  | LT-3 |  |  |  | 11KV-3 |  | LT-5 |  | LT-3 |  |  |  | FDN | ERTH | ERE | TW | STRG
|  |  | 355 |  | 375 |  | 374.49 |  | 434 |  | 406 |  | 390 |  | 276.492 |  | 397 |  | 380 |  | 342 | 3729.982
13 |  | DFR | [5 empty] | DFR |  | DFR |  | DFR |  | DFR |  |  |  | DFR - RC |  | DFR - RC |  |  | 7 | 6 | 2 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 |  | WIP
|  | 55/4 |  | 55/5 |  | 55/6 |  | AP56 |  | 56/1 |  | 56/2 |  | 56/3 |  | AP57 |  | 57/1 |  | 57/2 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA+3 |  | 1DA+0 |  | 1DA-3 |  | 1DB1+0 |  | 1DA+6 |  | 1DA-3 |  | 1DB1+6 |  | 1DC1+6 |  | 1DA-1.5 |  | 1DA+0 |  |  |  | 1 | 5 | 2 |  | WFT
|  | 2.7045 | [6 empty] | 1.5065
BEVURA
|  | TW-116 |  | TW-117 |  | TW-118 |  | TW-119 |  | TW-120 |  | TW-121 |  | TW-122 |  | TW-123 |  | TW-124 |  | TW-125
|  |  | 11KV-2 LT-2 |  | 110kV DC |  | LT-5 |  | LT-2 |  | LT-3 |  | LT-3 | [5 empty] | LT-3 |  |  |  | FDN | ERTH | ERE | TW | STRG
|  |  | 416.81 |  | 203.902 |  | 382 |  | 320.796 |  | 414 |  | 425 |  | 373 |  | 357 |  | 372.201 |  | 358.086 | 3622.795
14 |  | DFR |  | DFR |  | DFR |  |  |  | DFR |  | DFR |  | DFR |  |  |  | DFR |  | DFR |  |  | 8 | 8 | 1 | 0 | 0 | COM
[23 empty] | 0 | 0 | 1 | 0 | 0 | WIP
|  | 57/3 |  | AP58 |  | AP59 |  | 59/1 |  | AP60 |  | 60/1 |  | 60/2 |  | 60/3 |  | 60/4 |  | AP61 |  |  | 0 | 0 | 0 | 0 |  | ROW
|  | 1DA-3 |  | 1DD60+6 |  | 1DD60+6 |  | 1DA-3 |  | 1DC2+0 |  | 1DA+6 |  | 1DA+0 |  | 1DA+0 |  | 1DA+0 |  | 1DC2+0 |  |  |  | 0 | 6 | 1 |  | WFT
|  | 1.5358 |  | 0.2039 |  |  | 0.7028 |  |  |  | 1.9412 | [9 empty] | 0.35809
|  | VANAGERI | [20 empty] | FDN | ERTH | ERE | TW | STRG
|  | TW-126 |  | TW-127
[23 empty] | FDN | ERTH | ERE | TW | STRG
|  |  | 278.704 |  | 135.008 | [16 empty] | 413.712
|  | DFR | [20 empty] | 1 | 1 | 1 | 0 | 0 | COM
[23 empty] | 0 | 0 | 0 | 0 | 0 | WIP
|  | AP62 |  | AP63 |  | GANTRY | [16 empty] | 0 | 0 | 0 | 0 |  | ROW
|  | 1DD60+0 |  | 1DD60+0 | [19 empty] | 0 | 0 | 1 |  | WFT
0.414KM
[23 empty] | FDN | ERTH | ERE | TW | STRG
[23 empty] | 51 | 46 | 28 | 0 | 0 | COM
[23 empty] | 0 | 0 | 2 | 0 | 0 | WIP |  | YELBURGA
[6 empty] | Paying out Done/ Final sag |  |  | Paying out/ Rough sag | [13 empty] | 0 | 0 | 1 | 0 | 0 | ROW
[12 empty] | Tack welding completed | [5 empty] | Erection ROW |  |  |  |  | 0 | 5 | 20 | 28 | 0 | WFT
Erection Completed ------>
|  |  | Foundation completed ----> | [8 empty] | <------Insulator hosting | [10 empty] | 115 | 110 | 85 | 0 | 3578.992 | COM | TOTAL
|  |  | Earthing completed -----> |  |  |  |  | U/P | [9 empty] | Erection Cleared |  |  |  |  | 0 | 0 | 3 | 0 | 2426.451 | WIP
[13 empty] | LT Line Crossing | [9 empty] | 0 | 0 | 2 | 0 | 0 | ROW
[8 empty] | 325 | Span | [13 empty] | 0 | 5 | #VALUE! | 85 | 0 | WFT
[13 empty] | HT-D/C Power Line Crossing |  |  |  |  | Mtr. Gauge Railway Line Crossing
[5 empty] | ROW | ROW |  |  | Minor River Crossing
[5 empty] | A+0 | Tower Type |  |  | LAKE Crossing |  |  |  | HT-M/C Power Line Crossing |  |  |  |  | Broad Gauge Railway
Line Crossing
[5 empty] | 1/0 | Location No. | [6 empty] | HT(11/22/33KV) Line Crossing
[9 empty] | Hill Crossing | [8 empty] | Road Crossing
Canal/POND Crossing
HT-S/C Power Line Crossing
[5 empty] | RC | Raised Chimney |  |  | Major River Crossing | [8 empty] | SH/NH Crossing
EU - Line Daily Progress Report
| District | Taluk | No of TWR | Length in KM | Foundation |  |  |  |  | Earthing |  |  | Erection |  |  |  |  | Stringing
[5 empty] | COMP | WIP | ROW | WFT | BAL | COMP | ROW | BAL | COMP | WIP | ROW | WFT | BAL | COMP | WIP | ROW | WFT | BAL
| Raichur | SINDHANURU | 15 | 5.5671 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 12 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 5.5671
|  | Total | 15 | 5.5671 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 12 | 1 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 5.5671
| Koppal | KUSHTAGI | 50 | 19.3085 | 49 | 0 | 0 | 0 | 1 | 49 | 0 | 1 | 45 | 0 | 0 | 4 | 5 | 3.579 | 2.4265 | 0 | 0 | 15.7295
|  | YELBURGA | 62 | 22.9601 | 51 | 0 | 0 | 0 | 11 | 46 | 0 | 16 | 28 | 2 | 1 | 1 | 34 | 0 | 0 | 0 | 0 | 22.9601
|  | Total | 112 | 42.2686 | 100 | 0 | 0 | 0 | 12 | 95 | 0 | 17 | 73 | 2 | 1 | 5 | 39 | 3.579 | 2.4265 | 0 | 0 | 38.6897
| Total |  | 127 | 47.8357 | 115 | 0 | 0 | 0 | 12 | 110 | 0 | 17 | 85 | 3 | 2 | 6 | 42 | 3.579 | 2.4265 | 0 | 0 | 44.2567
+
+

## PENDING FDN DETAILS
765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) ¦ BALANCE WORK DETAILS
Sl. No. | Loc. No. | Type of Tower | Village | Taluk | FDN STATUS | ROW STATUS | REMARKS
1 | AP38 | 1DD60+6 | Manadhal | Tavaragera | ROW | ROW | Land Owner Not Accepted
2 | 48A/1 | 1DA+9 | Uchhalakunti | Hirevankalakunta | ROW | ROW | Land Owner Not Accepted
3 | 48A/2 | 1DA-1.5 | Uchhalakunti | Hirevankalakunta | ROW | ROW | Land Owner Not Accepted
4 | AP49 | 1DC1+3 | Gunnala | Hirevankalakunta | ROW | ROW | Land Owner Not Accepted
5 | AP50 | 1DC1+0 | Gunnala | Hirevankalakunta | RC | ROW | Land Owner Not Accepted
6 | AP51 | 1DB1-3 | Gunnala | Hirevankalakunta | ROW | ROW | Land Owner Not Accepted
7 | 55/5 | 1DA+0 | Hunasihala | Hirevankalakunta | ROW | SEVERE ROW | Land Owner Not Accepted
8 | 55/6 | 1DA-3 | Hunasihala | Hirevankalakunta | ROW | ROW | Land Owner Not Accepted
9 | AP57 | 1DC1+6 | Bevura | Yalaburga | ROW | ROW | Land Owner Not Accepted
10 | 59/1 | 1DA-3 | Vanageri | Yalaburga | ROW | ROW | Land Owner Not Accepted
11 | 60/3 | 1DA+0 | Gutthura | Yalaburga | ROW | ROW | Land Owner Not Accepted
12 | 63/0 | 1DD60+0 | Lakamagooli | Yalaburga | ROW | ROW | Land Owner Not Accepted
| Koppal-II Gantry | Koppal-II Gantry | Lakamagooli | Yalaburga

## PENDING ERE DETAILS
Sl. No. | Loc. No. | Type of Tower | FDN STATUS | ERE STATUS | ROW STATUS | REMARKS
1 | AP32 | 1DC2+6 | COMPLETED | WIP | WIP | WIP
2 | AP33 | 1DD45+18 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
3 | 33/4 | 1DA+3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
4 | AP38 | 1DD60+6 | PENDING | PENDING | ROW | Land Owner Not Accepted
5 | AP39 | 1DD45+18 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
6 | 43/2 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
7 | 43/3 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
8 | 44/1 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
9 | 46/1 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
10 | 46/6 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
11 | 46/10 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
12 | 46/11 | 1DA-1.5 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
13 | AP47 | 1DC1+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
14 | 47/1 | 1DA+3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
15 | AP48 | 1DB2+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
16 | 48A/1 | 1DA+9 | PENDING | PENDING | ROW | Land Owner Not Accepted
17 | 48A/2 | 1DA-1.5 | PENDING | PENDING | ROW | Land Owner Not Accepted
18 | AP49 | 1DC1+3 | PENDING | PENDING | ROW | Land Owner Not Accepted
19 | AP50 | 1DC1+0 | PENDING | PENDING | ROW | Land Owner Not Accepted
20 | AP51 | 1DB1-3 | PENDING | PENDING | ROW | Land Owner Not Accepted
21 | 52/1 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
22 | 52/2 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
23 | AP54 | 1DC1+6 | COMPLETED | WIP | WIP | WIP
24 | 54/2 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
25 | 55/5 | 1DA+0 | PENDING | PENDING | ROW | Land Owner Not Accepted
26 | 55/6 | 1DA-3 | PENDING | PENDING | ROW | Land Owner Not Accepted
27 | 56/1 | 1DA+6 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
28 | 56/2 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
29 | 56/3 | 1DB1+6 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
30 | AP57 | 1DC1+6 | PENDING | PENDING | ROW | Land Owner Not Accepted
31 | 57/1 | 1DA-1.5 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
32 | 57/2 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
33 | 57/3 | 1DA-3 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
34 | 58/0 | 1DD60+6 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
35 | 59/0 | 1DD60+6 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
36 | 59/1 | 1DA-3 | PENDING | PENDING | ROW | Land Owner Not Accepted
37 | 60/0 | 1DC2+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
38 | 60/1 | 1DA+6 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
39 | 60/2 | 1DA+0 | COMPLETED | WIP | WIP | WIP
40 | 60/3 | 1DA+0 | PENDING | PENDING | ROW | Land Owner Not Accepted
41 | 60/4 | 1DA+0 | COMPLETED | PENDING | ROW | Land Owner Not Accepted
42 | 63/0 | 1DD60+0 | PENDING | PENDING | ROW | Land Owner Not Accepted

## TSE-MANUAL-LT-11KV-33KV Details
765kV D/C KOPPAL II(PS) - RAICHUR TRANSMISSION LINE
Sl. No | SECTION |  | Section Length | No. Of Towers B/W Angle Towers | TSE Section (In KM) | Manual Section (In KM) | LT | 11KV | 33KV
| FROM | TO
1 | AP32 | AP33 | 249.635 | 0 |  | 249.635 | 1 | 1 | 0
2 | AP33 | 33/5 | 2015 | 4 | 2015 |  | 1 | 1 | 1
3 | 33/5 | 33/6 | 380 | 0 |  | 380 | 0 | 0 | 0
4 | 33/6 | 34/0 | 2537.42 | 6 | 2537.42 |  | 2 | 6 | 2
5 | 34/0 | AP35 | 1983.46 | 4 | 1983.46 |  | 5 | 3 | 0
6 | AP35 | AP36 | 4480.02 | 11 | 4480.02 |  | 8 | 3 | 0
7 | AP36 | 36/1 | 480 | 0 |  | 480 | 0 | 0 | 0
8 | 36/1 | 37/0 | 297.32 | 0 |  | 297.32 | 0 | 0 | 0
9 | 37/0 | AP38 | 1258.78 | 2 | 1258.78 |  | 2 | 2 | 0
10 | AP38 | AP39 | 1284.88 | 2 | 1284.88 |  | 4 | 2 | 0
11 | AP39 | AP40 | 248.04 | 0 |  | 248.04 | 1 | 0 | 0
12 | AP40 | AP41 | 2426.45 | 5 | 2426.45 |  | 2 | 2 | 0
13 | AP41 | AP42 | 2473.21 | 5 | 2473.21 |  | 2 | 1 | 0
14 | AP42 | AP43 | 1105.78 | 2 | 1105.78 |  | 2 | 3 | 0
15 | AP43 | AP44 | 1444.8 | 3 | 1444.8 |  | 4 | 1 | 0
16 | AP44 | AP45 | 697.56 | 1 | 697.56 |  | 2 | 2 | 0
17 | AP45 | 45/1 | 242 | 0 |  | 242 | 0 | 0 | 0
18 | 45/1 | AP46 | 1272.52 | 2 | 1272.52 |  | 5 | 2 | 0
19 | AP46 | 46/7 | 2745 | 6 | 2745 |  | 5 | 6 | 1
20 | 46/7 | AP47/0 | 3547.25 | 8 | 3547.25 |  | 8 | 4 | 1
20 | AP47/0 | AP48 | 813.45 | 1 | 813.45 |  | 3 | 1 | 1
21 | AP48 | 48A/0 | 1257.06 | 2 | 1257.06 |  | 5 | 4 | 1
| 48A/0 | 49/0 | 1101.05 | 2 | 1101.05 |  | 3
22 | 49/0 | AP50 | 417.22 | 0 |  | 417.22 | 2 | 0 | 0
23 | AP50 | AP51 | 249.6 | 0 |  | 249.6 | 0 | 3 | 0
24 | AP51 | AP52 | 333.6 | 0 |  | 333.6 | 0 | 0 | 0
25 | AP52 | AP53 | 1034.1 | 2 | 1034.1 |  | 1 | 0 | 0
26 | AP53 | AP54 | 258.62 | 0 |  | 258.62 | 0 | 0 | 0
27 | AP54 | AP55 | 1836.69 | 4 | 1836.69 |  | 11 | 12 | 0
28 | AP55 | AP56 | 2704.49 | 6 | 2704.49 |  | 13 | 5 | 0
29 | AP56 | 56/3 | 1230 | 2 | 1230 |  | 4 | 2
30 | 56/3 | 57/0 | 276.49 | 0 |  | 276.49 | 0 | 3 | 0
31 | 57/0 | 58/0 | 1535.81 | 3 | 1535.81 |  | 10 | 3 | 0
32 | 58/0 | 59/0 | 203.9 | 0 |  | 203.9 | 0 | 0 | 0
33 | 59/0 | 60/0 | 702.8 | 1 | 702.8 |  | 5 | 1 | 0
34 | 60/0 | 61/0 | 1942 | 4 | 1942 |  | 10 | 1 | 0
35 | 61/0 | 62/0 | 358.1 | 0 |  | 358.1 | 1 | 0 | 0
36 | 62/0 | 63/0 | 278.7 | 0 |  | 278.7 | 0 | 1 | 0
37 | 63/0 | GNTY | 135 | 0 |  | 135 | 0 | 1 | 0
TOTAL |  |  | 47837.805 | 88 | 43.4296 | 4.4082 | 122 | 76 | 7

## Crossing Details
CROSSINGS PROPOSAL STATUS
765kV D/c Koppal II (PS)-Raichur (Part-1) transmission line project
Crossing Type | 110kV | 220kV | 400kV | 765kV | SH-Xing | NH-Xing | Railway Xing | Total | Remarks
Total Nos | 6 | 3 | 0 | 0 | 4 | 1 | 0 | 14
Submitted Till Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Completed Till Date | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance to Execute | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 14
Crossings Details
Sl. No. | FROM (AP) | TO (AP) | Name of the Line | NAME OF CROSSING | Date of First Submission | Joint Inspection Status | Provisional approval status | Remarks
1 | 33/5 | 33/6 | 110kV S/C LINE on D/C TOWERS | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
2 | 36/1 | AP37 | 110kV S/C LINE ON D/C TOWERS | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
3 | AP45 | 45/1 | 110kV S/C LINE ON D/C TOWERS | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
4 | AP53 | AP54 | 110kV D/C LINE UNDER CONSTRUCTION | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
5 | AP58 | AP59 | 110kV DC YALBURGA-BEWOOR UNDER CONSTRUCTION T/L | Power line | 2025-01-30 | Completed | Submitted | Formal Approval Awaited
6 | 56/3 | AP57 | 110kV D/C LINE | Power line | 2024-12-19 | Completed | Submitted | Formal Approval Awaited
7 | AP32 | AP33 | 220kV S/C Sindhanur LILO Line on DC Towers | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
8 | AP39 | AP40 | 220kV D/C LINE | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
9 | AP39 | AP40 | 220kV D/C LINE | Power line | 2024-10-11 | Completed | Submitted | Formal Approval Awaited
10 | 33/6 | 33/7 | STATE HIGHWAY-30 (Sindhanur - Tawargere Section | SH crossing
11 | AP38 | 38/1 | STATE HIGHWAY-29 (Hulihaider - Tawargeri Section) | SH crossing
12 | 56/3 | AP57 | STATE HIGHWAY-36 (Koppal - Kushtagi Section | SH crossing
13 | 57/2 | 57/3 | STATE HIGHWAY-130 (Bewoor - Yelburga Section | SH crossing
14 | AP50 | AP51 | NATIONAL HIGHWAY-50 (Hosapete - Kushtagi Section) | NH crossing | 2024-09-14 | Completed | Submitted | Formal Approval Awaited

## Project Details
Project Code | Project Name | Client Name | NOA Start Date | LOA End Date | Planning Engineer | PCH | Regional Manager | Project Manger | Section Incharge | Engineer/Supervisor
TA 418 | 765KV D/C KOPPAL II(PS) - RAICHUR TL (Part-1) | PGCIL | 12.03.2024 | 11.12.2025 | Mr. Ajith Jayasurya | Mr. Sivaraman N | Mr. Ajith Kumar MG | Mr. Tamil Velan | Not Available | Prathab DK
[9 empty] | Mr. Ajith Jayasurya | Subha Parui
Prabhu Prasad
Ashok Prasad
Basudev Mahato
Ajay Kumar
Rahman
Jitender
Durai swamy
Umesh Kumar
Vennilavan

## TS (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 10 | 7 | 3 | 1 | 26 | 2 | 21 | 2 | 8 | 6 | 0 | 86
|  |  |  | 1DB1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 1 | 5 | 0 | 14 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 7
|  |  |  | 1DC1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1 | 1 | 0 | 6 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[5 empty] | 0 | 10 | 7 | 3 | 1 | 42 | 2 | 28 | 2 | 14 | 14 | 1 | 124 | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[18 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[18 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[18 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 2 | 18 | 0 | 0 | 37 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 2 | 4 | 0 | 15 | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 1 | 0 | 0 | 7 | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2 |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 2 | 20 | 0 | 0 | 52 | 0 | 26 | 0 | 15 | 11 | 1 | 127 |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[21 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[21 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[21 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DB2+3 | 417
35 | 37/1 | 1DA+3 | 409
36 | 37/2 | 1DA+0 | 432.782
37 | AP38 | 1DD60+6 | 469
38 | 38/1 | 1DA+9 | 387
39 | 38/2 | 1DA+0 | 428.876
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 394
83 | 47/1 | 1DA+3 | 419.445
84 | AP48 | 1DB2+0 | 402
85 | 48/1 | 1DA+6 | 426
86 | 48/2 | 1DA+3 | 429.059
87 | AP48A | 1DC1+0 | 336
88 | 48A/1 | 1DA+9 | 441
89 | 48A/2 | 1DA-1.5 | 324.049
90 | AP49 | 1DC1+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+6 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA+0 | 372.201
125 | AP61 | 1DC2+0 | 358.086
126 | AP62 | 1DD60+0 | 278.704
127 | AP63 | 1DD60+0 | 135.008
47836.988
| Koppal-II Gantry | GANTRY

## TS (2) (hidden)
Name of the Line :765kV D/C KOPPAL II(PS) - RAICHUR (Part-1) TRANSMISSION LINE
Sl.No | Loc. No. (Provisional) | Type of Tower | Span (Mtr)
1 | AP32 | 1DC2+6 | 249.635 | 32/0-33/0
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total
2 | AP33 | 1DD45+18 | 425 | 1DA | 0 | 3 | 18 | 0 | 0 | 34 | 0 | 19 | 0 | 7 | 6 | 0 | 87 | 2
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 | 0 | 113 | AP57 | 1DC2+6 | 57/0 | 1DC1+3 | 73.125
3 | 33/1 | 1DA-3 | 425 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4 | 0
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 | 0 | 114 | 57/1 | 1DA+0 | 57/1 | 1DA+0 | 71.43
4 | 33/2 | 1DA+6 | 390 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 6 | 1
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 115 | 57/2 | 1DA+6 | 57/2 | 1DA+0 | 71.43
5 | 33/3 | 1DA+9 | 265 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2
[5 empty] | 0 | 3 | 20 | 0 | 0 | 47 | 0 | 25 | 0 | 14 | 11 | 2 | 122 |  | 116 | 57/3 | 1DA+0 | 57/3 | 1DA-3 | 68.43
6 | 33/4 | 1DA+3 | 510
[19 empty] | 117 | 57/4 | 1DA+3 | 58/0 | 1DD60+6 | 76.525
7 | 33/5 | 1DB1+9 | 380
[19 empty] | 118 | AP58 | 1DD45+0 | 59/0 | 1DD60+6 | 76.525
8 | 33/6 | 1DB1+9 | 420
[19 empty] | 119 | 58/1 | 1DA-1.5 | 59/1 | 1DA-3 | 68.43
9 | 33/7 | 1DA-3 | 335
[5 empty] | -0 | -1.5 | -3 | -4.5 | -6 | +0 | +1.5 | +3 | +4.5 | +6 | +9 | +18 | Total |  | 120 | AP59 | 1DB2+3 | 60/0 | 1DC2+0 | 70.125
10 | 33/8 | 1DA-3 | 345 | 1DA | 0 | 4 | 18 | 0 | 0 | 35 | 0 | 19 | 0 | 7 | 6 | 0 | 89
|  |  |  | 1DB1 | 0 | 0 | 1 | 0 | 0 | 7 | 0 | 1 | 0 | 1 | 4 | 0 | 14 |  | 121 | AP60 | 1DD60+0 | 60/1 | 1DA+6 | 77.43
11 | 33/9 | 1DA-3 | 365 | 1DB2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 4
|  |  |  | 1DC1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 7 |  | 122 | GANTRY | GANTRY | 60/2 | 1DA+0 | 71.43
12 | 33/10 | 1DA+0 | 356 | 1DC2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 3 | 0 | 0 | 7
|  |  |  | 1DD45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |  |  |  |  | 60/3 | 1DA+0 | 71.43
13 | 33/11 | 1DA-3 | 332 | 1DD60 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 4
[5 empty] | 0 | 4 | 20 | 0 | 0 | 50 | 0 | 25 | 0 | 15 | 11 | 2 | 127 |  |  |  |  | 60/4 | 1DA-1.5 | 69.93
14 | 33/12 | 1DA+0 | 384.424
[22 empty] | 61/0 | 1DD45+6 | 76.525
15 | AP34 | 1DB1+0 | 385
[22 empty] | AP-62 | DD60
16 | 34/1 | 1DA+0 | 423
[22 empty] | AP-63 | DD60
17 | 34/2 | 1DA+0 | 382
18 | 34/3 | 1DA+0 | 405
19 | 34/4 | 1DA+3 | 388.458
20 | AP35 | 1DB1+0 | 405
21 | 35/1 | 1DA+3 | 360
22 | 35/2 | 1DA+3 | 390
23 | 35/3 | 1DA-3 | 325
24 | 35/4 | 1DA+0 | 430
25 | 35/5 | 1DA+0 | 298
26 | 35/6 | 1DA+0 | 422
27 | 35/7 | 1DA+9 | 345
28 | 35/8 | 1DA+3 | 370
29 | 35/9 | 1DA+9 | 320
30 | 35/10 | 1DA+9 | 390
31 | 35/11 | 1DA+3 | 425.02
32 | AP36 | 1DB1+3 | 480
33 | 36/1 | 1DB1+9 | 297.315
34 | AP37 | 1DC2+3 | 415
35 | 37/1 | 1DA+3 | 425
36 | 37/2 | 1DA+3 | 395
37 | 37/3 | 1DA-3 | 329.074
38 | AP38 | 1DC2+0 | 390
39 | 38/1 | 1DA+3 | 444.771
40 | AP39 | 1DD45+18 | 248.038
41 | AP40 | 1DB2+9 | 430
42 | 40/1 | 1DA+0 | 400
43 | 40/2 | 1DA+0 | 410
44 | 40/3 | 1DA+3 | 435
45 | 40/4 | 1DA+0 | 360
46 | 40/5 | 1DA-3 | 391.451
47 | AP41 | 1DB1+0 | 380
48 | 41/1 | 1DA+6 | 475
49 | 41/2 | 1DA+3 | 380
50 | 41/3 | 1DA+0 | 390
51 | 41/4 | 1DA+3 | 465
52 | 41/5 | 1DA+3 | 383.208
53 | AP42 | 1DB2+3 | 380
54 | 42/1 | 1DA+0 | 348
55 | 42/2 | 1DA+0 | 377.784
56 | AP43 | 1DB1+0 | 410
57 | 43/1 | 1DA+0 | 380
58 | 43/2 | 1DA+0 | 325
59 | 43/3 | 1DA-3 | 329.8
60 | AP44 | 1DC1-3 | 385
61 | 44/1 | 1DA+0 | 312.558
62 | AP45 | 1DC1+3 | 242
63 | 45/1 | 1DB1+6 | 464
64 | 45/2 | 1DA+0 | 391
65 | 45/3 | 1DA+6 | 417.518
66 | AP46 | 1DB1+0 | 315
67 | 46/1 | 1DA-3 | 375
68 | 46/2 | 1DA+0 | 416
69 | 46/3 | 1DA+0 | 422
70 | 46/4 | 1DA+0 | 388
71 | 46/5 | 1DA+6 | 409
72 | 46/6 | 1DA+0 | 420
73 | 46/7 | 1DB1+0 | 399
74 | 46/8 | 1DA+3 | 381
75 | 46/9 | 1DA+0 | 382
76 | 46/10 | 1DA+0 | 391
77 | 46/11 | 1DA-1.5 | 433
78 | 46/12 | 1DA+0 | 415
79 | 46/13 | 1DA+0 | 430
80 | 46/14 | 1DA+0 | 314
81 | 46/15 | 1DA+9 | 402.249
82 | AP47 | 1DC1+0 | 400
83 | 47/1 | 1DA+3 | 435
84 | AP48 | 1DC1+3 | 345
85 | 48/1 | 1DA+0 | 410
86 | 48/2 | 1DA+0 | 410
87 | 48/3 | 1DA-1.5 | 320
88 | 48/4 | 1DA+6 | 400
89 | 48/5 | 1DA+9 | 410.1
90 | AP49 | 1DB2+3 | 417.219
91 | AP50 | 1DC1+0 | 249.602
92 | AP51 | 1DB1-3 | 333.602
93 | AP52 | 1DC2+0 | 313
94 | 52/1 | 1DA-3 | 337
95 | 52/2 | 1DA-3 | 384.098
96 | AP53 | 1DC2+6 | 258.616
97 | AP54 | 1DC1+6 | 390
98 | 54/1 | 1DA-3 | 290
99 | 54/2 | 1DA-3 | 345
100 | 54/3 | 1DA+3 | 423
101 | 54/4 | 1DA+0 | 388.693
102 | AP55 | 1DB2+0 | 405
103 | 55/1 | 1DA+3 | 385
104 | 55/2 | 1DA+0 | 366
105 | 55/3 | 1DA+3 | 444
106 | 55/4 | 1DA+3 | 355
107 | 55/5 | 1DA+0 | 375
108 | 55/6 | 1DA-3 | 374.49
109 | AP56 | 1DB1+0 | 434
110 | 56/1 | 1DA+6 | 406
111 | 56/2 | 1DA-3 | 390
112 | 56/3 | 1DB1+9 | 276.492
113 | AP57 | 1DC1+6 | 397
114 | 57/1 | 1DA-1.5 | 380
115 | 57/2 | 1DA+0 | 342
116 | 57/3 | 1DA-3 | 416.81
117 | AP58 | 1DD60+6 | 203.902
118 | AP59 | 1DD60+6 | 382
119 | 59/1 | 1DA-3 | 320.796
120 | AP60 | 1DC2+0 | 414
121 | 60/1 | 1DA+6 | 425
122 | 60/2 | 1DA+0 | 373
123 | 60/3 | 1DA+0 | 357
124 | 60/4 | 1DA-1.5 | 402.199
125 | AP61 | 1DC2+6 | 419
126 | AP62 | 1DD60+0 | 231
127 | AP63 | 1DD60+0 | 103
47661.922
GANTRY