## Stub dispatch (hidden)
Location | Project | Tower type | Structure | B LOT | Actual PRS Date | STEEL Wt (MT) | BNA Wt | Disp Bal | May'24 Disp Plan | Wk01 | WK02 | WK03 | WK04 | Jun'24 Disp Plan MT | July'24 Disp Plan | Remark
JPR | TA416 | DA | Stub - 28 Nos | TA416-00018 | 2024-04-11 | 26.8617 | 0.46323 | 26.8617 | 0 |  |  |  | 0 | 26.8617 | 0 | As on date 160 stub reieved.
JPR | TA416 | DA | Stub - 132 Nos | TA416-00026 | 2024-04-15 | 126.634 | 2.184 | 126.634 | [5 empty] | 126.634 | 0
Total |  |  | 160 | [10 empty] | 153.4957

## Erection - Oct'25
Sl | Location No. | Tower type | Tower Weight | Gang Name | Manpower | Section Incharge | Supervisor | Power Tools Issued (YES/NO) | Material Feeding | Starting Date | Completion Date | Tack-welding | Final checking | Revenue Planned | Revenue Realised
1 | 0B/0 | DC1+6 | 72.474 | Infinidea 1 | 25 | Mr. Tanay Kumar | Mr. Abhishek | No | 2025-09-23 | WIP | 2025-10-20 | 2025-10-30 | 2025-10-25 | 555078.366
2 | 40/4 | DA+1.5 | 37.138 | Infidia 1 | 25 | Mr. Tanay Kumar | Mr. Abhishek | No |  | 2025-10-21 | 2025-10-25 | 2025-11-04 | 2025-10-30 | 284439.942
3 | 40/5 | DA+1.5 | 37.138 | Infidia 1 | 25 | Mr. Tanay Kumar | Mr. Abhishek | No |  | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 284439.942
4 | 3/3 | DA-1.5 | 35.602 | Madhu Sah | 27 | Mr. Tanay Kumar | Mr. prince | No | 2025-09-27 | 2025-09-28 | 2025-10-05 | 2025-10-15 | 2025-10-10 | 272675.718
5 | 3/4 | DA+6 | 43.804 | Madhu Sah | 27 | Mr. Tanay Kumar | Mr. prince | No | 2025-10-10 | 2025-10-06 | 2025-10-13 | 2025-10-23 | 2025-10-18 | 335494.836
6 | 38/5 | DA+3 | 37.931 | Madhu Sah | 27 | Mr. Tanay Kumar | Mr. prince | No |  | 2025-10-15 | 2025-10-22 | 2025-11-01 | 2025-10-27 | 290513.529
7 | 38/6 | DA+1.5 | 37.138 | Madhu Sah | 27 | Mr. Tanay Kumar | Mr. prince | No |  | 2025-10-23 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 284439.942
8 | 16/0 | DB2+6 | 69.376 | Poonam Kumari 1 | 29 | Mr. Tanay Kumar | Mr. PD Sharma | No | 2025-10-11 | WIP | 2025-10-21 | 2025-10-31 | 2025-10-26 | 531350.784
9 | 15/0 | DC1+0 | 62.444 | Poonam Kumari 1 | 29 | Mr. Tanay Kumar | Mr. PD Sharma | No |  | 2025-10-23 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 478258.596
10 | 31/2 | DA+0 | 36.16 | Poonam Kumari 2 | 30 | Mr. Tanay Kumar | Mr. Satyaprakash | No | 2025-10-14 | WIP | 2025-10-21 | 2025-10-31 | 2025-10-26 | 276949.44
11 | 30/0 | DA+3 | 37.931 | Poonam Kumari 2 | 30 | Mr. Tanay Kumar | Mr. Satyaprakash | No |  | 2025-10-22 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 290513.529
12 | 21/0 | DD60+25 | 137.046 | Radha Enterprises | 24 | Mr. Tanay Kumar | Mr Sunil | No | 2025-09-12 | 2025-09-14 | 2025-10-05 | 2025-10-15 | 2025-10-10 | 1049635.314
13 | 26/0 | DC2+18 | 99.779 | Radha Enterprises | 24 | Mr. Tanay Kumar | Mr Sunil | No | 2025-10-16 | WIP | 2025-10-24 | 2025-11-03 | 2025-10-29 | 764207.361
14 | 38/11 | DA+0 | 36.16 | Radha Enterprises | 24 | Mr. Tanay Kumar | Mr Sunil | No |  | 2025-10-25 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 276949.44
15 | 36/6 | DA+0 | 36.16 | Jwala Singh | 28 | Mr. Tanay Kumar | Mr. Yogendra | No |  | 2025-10-17 | 2025-10-21 | 2025-10-31 | 2025-10-26 | 276949.44
16 | 36/7 | DA+0 | 36.16 | Jwala Singh | 28 | Mr. Tanay Kumar | Mr. Yogendra | No |  | 2025-10-21 | 2025-10-26 | 2025-11-05 | 2025-10-31 | 276949.44
17 | 36/8 | DA+0 | 36.16 | Jwala Singh | 28 | Mr. Tanay Kumar | Mr. Yogendra | No |  | 2025-10-26 | 2025-10-31 | 2025-11-10 | 2025-11-05 | 276949.44
|  |  | 888.601 | [10 empty] | 6805795.059
Formulas:
Tack-welding = [Completion Date]+10
Final checking = [Completion Date]+5